## Sheet1
INDEX (DO NOT MODIFY) | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LEG DISTRICT | NO. OF SITES | SCOPE OF WORK | TOTAL ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
4 | Region IV-B | Occidental Mindoro | 301596 | Sablayan National Comprehensive High School | SABLAYAN | Lone | 1 | PROPOSED TWO (2) - STOREY ALTERNATIVE LEARNING SYSTEM (ALS) BUILDING (22.50m x 9.50m) - with Roof Deck | 16540705.31 | 16458637.91 | completed | 1 | April 10, 2025 | April 15,2025 | DepEd-OccMdo-2024-05 |  | May 31, 2024 | June 10 2024 | June 24, 2024 | June 28, 2024 | June 19, 2024 | hawkstow construction and development | actual target completion was adjusted due to contractor request for extension regarding weather condition

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%