## Sheet1
INDEX (DO NOT MODIFY) | PROGRAM-YEAR | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | BATCH | TOTAL PROJECT ALLOCATION | TOTAL PROJECT COST | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
3202 | NC 2014 | SHS (2014) | Region IV-B | Calapan City | 301798 | Canubing National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1 | 2016-11-30 |  | 4B0314S00110 | 13ED0102 | 2015-07-17 | 2015-07-14 | 2015-07-27 | 2015-08-14 | 2015-09-02 | F.S. SUGAY CONSTRUCTION & SUPPLIES
3203 | NC 2014 | SHS (2014) | Region IV-B | Calapan City | 301797 | Community Vocational High School | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1 | 2016-06-30 |  | 4B0314S00111 | 13ED0102 | 2015-07-10 | 2015-07-14 | 2015-07-27 | 2015-08-19 | 2015-09-02 | KARANGYAN BUILDERS & TRADERS
3204 | NC 2014 | K10 (2014) | Region IV-B | Calapan City | 111540 | M. Kalaw MS | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 4B0314S00056 | 14ED0040 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | B5 BUILDERS & SUPPLIES
3205 | NC 2014 | SHS (2014) | Region IV-B | Calapan City | 301805 | Managpi National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1 | 2016-10-20 | 2016-10-20 | 4B0314S00112 | 13ED0102 | 2015-07-13 | 2015-07-14 | 2015-07-27 | 2015-08-12 | 2015-09-02 | LN. SALVADOR
3206 | NC 2014 | SHS (2014) | Region IV-B | Calapan City | 301802 | Nag-iba National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10917131.51 |  |  | COMPLETED | 1 | 2016-11-30 |  | 4B0314S00105 | 13ED0088 | 2015-07-27 |  |  |  |  | ORIENT STAR CONSTRUCTION, INC.
3207 | NC 2014 | SHS (2014) | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High school | CITY OF CALAPAN (Capital) | 1 | 1 | 16 | 4STY16CL | 2014 SHS BATCH 1 | 27242469.42 |  |  | Reverted | 0 | [9 empty] | Reverted
3208 | NC 2014 | SHS (2014) | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High school | CITY OF CALAPAN (Capital) | 1 |  | 16 | 4STY16CL | 2014 SHS BATCH 1 | 27242469.42 |  |  | Reverted | 0 | [9 empty] | Reverted
3209 | NC 2014 | K10 (2014) | Region IV-B | Calapan City | 111546 | San Antonio ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2016-10-30 |  | 4B0314S00077 | 13ED0102 | 2015-07-20 | 2015-07-23 | 2015-08-05 | 2015-08-21 | 2015-09-02 | KARANGYAN BUILDERS & TRADERS
3210 | NC 2014 | K10 (2014) | Region IV-B | Calapan City | 111580 | T.C. Montellano MS | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 4B0314S00057 | 14ED0041 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | F.S. SUGAY CONSTRUCTION & SUPPLIES
3211 | NC 2014 | K10 (2014) | Region IV-B | Marinduque | 308805 | Bagtingon NHS | BUENAVISTA | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2015-01-02 | 2014-12-29 | 4B0114S00002 | 4B01-14-S-00002 | 2014-09-30 | 2014-10-13 | 2014-10-16 | 2014-10-20 | 2014-10-30 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS)
3212 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301530 | Balanacan NHS | MOGPOG | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-28 |  | 4B0114S00022 | 15EA0063 | 2015-06-14 | 2015-06-17 | 2015-06-30 | 2015-07-04 | 2015-07-21 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS)
3213 | NC 2014 | K10 (2014) | Region IV-B | Marinduque | 109905 | Bancoro ES | BUENAVISTA | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-10 | 2015-12-10 | 4B0114S00032 | 15EA0076 | 2015-07-07 | 2015-07-21 | 2015-07-21 | 2015-07-25 | 2015-08-10 | R.C. TAGALA CONSTRUCTION
3214 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301531 | Bangbang NHS | GASAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-28 |  | 4B0114S00016 | 15EA0063 | 2015-06-14 | 2015-06-17 | 2015-06-30 | 2015-07-04 | 2015-07-21 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS)
3215 | NC 2014 | K10 (2014) | Region IV-B | Marinduque | 301532 | Bognuyan NHS | GASAN | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1977417.57 |  |  | COMPLETED | 1
3216 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301532 | Bognuyan NHS | GASAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
3217 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301533 | Bonliw NHS | TORRIJOS | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-24 | 4B0114S00031 | 15EA0079 | 2015-06-01 | 2015-06-03 | 2015-06-15 | 2015-06-19 | 2015-07-03 | R.C. TAGALA CONSTRUCTION
3218 | NC 2014 | SHS (2014) | Region IV-B | MARINDUQUE | 301534 | Botilao NHS | SANTA CRUZ | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-16 | 2015-10-16 | 4B0114S00013 | 15EA0046-4 | 2015-05-18 | 2015-05-21 | 2015-06-02 | 2015-06-12 | 2015-06-25 | R.C. TAGALA CONSTRUCTION
3219 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301535 | Buenavista NHS | BUENAVISTA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-07 |  | 4B0114S00030 | 15EA0068 | 2015-06-22 | 2015-06-24 | 2015-07-07 | 2015-07-11 | 2015-07-27 | 8 Rs CONSTRUCTION
3220 | NC 2014 | SHS (2014) | Region IV-B | MARINDUQUE | 301536 | Buenavista NHS - Bagacay Annex | BUENAVISTA | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-26 | 2015-10-26 | 4B0114S00012 | 15EA0047-3 | 2015-05-18 | 2015-05-21 | 2015-06-02 | 2015-06-12 | 2015-06-25 | R.C. TAGALA CONSTRUCTION
3221 | NC 2014 | SHS (2014) | Region IV-B | MARINDUQUE | 301542 | Dolores NHS | SANTA CRUZ | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-16 | 2015-10-16 | 4B0114S00011 | 15EA0046-3 | 2015-05-18 | 2015-05-21 | 2015-06-02 | 2015-06-12 | 2015-06-25 | R.C. TAGALA CONSTRUCTION
3222 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301543 | Hupi NHS | SANTA CRUZ | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 | 2015-11-26 | 2015-11-21 | 4B0114S00029 | 15EA0050 | 2015-06-01 | 2015-06-03 | 2015-06-15 | 2015-06-19 | 2015-07-03 | PERFORMANCE BUILDERS & DEVELOPERS CORPORATION
3223 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301544 | Ilaya NHS | BOAC (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-03 |  | 4B0114S00028 | 15EA0070 | 2015-06-22 | 2015-07-24 | 2015-07-25 | 2015-07-30 | 2015-08-24 | R.C. TAGALA CONSTRUCTION
3224 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301547 | Kilo-Kilo NHS | SANTA CRUZ | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-11-26 | 2015-11-19 | 4B0114S00027 | 15EA0055 | 2015-06-01 | 2015-06-03 | 2015-06-15 | 2015-06-19 | 2015-07-03 | PERFORMANCE BUILDERS & DEVELOPERS CORPORATION
3225 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301548 | Landy National High School | SANTA CRUZ | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2015-12-20 | 2015-12-14 | 4B0114S00026 | 15EA0061 | 2015-06-14 | 2015-06-17 | 2015-06-30 | 2015-07-04 | 2015-07-21 | PERFORMANCE BUILDERS & DEVELOPERS CORPORATION
3226 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301549 | Makapuyat NHS | SANTA CRUZ | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-16 |  | 4B0114S00024 | 15EA0067 | 2015-06-22 | 2015-07-24 | 2015-07-25 | 2015-07-30 | 2015-08-24 | R.C. TAGALA CONSTRUCTION
3227 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301550 | Makapuyat NHS - Masaguisi Annex | SANTA CRUZ | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-04 | 2015-11-27 | 4B0114S00006 | 15EA0054 | 2015-06-01 | 2015-06-03 | 2015-06-15 | 2015-06-19 | 2015-07-03 | PERFORMANCE BUILDERS & DEVELOPERS CORPORATION
3228 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301553 | Maranlig NHS | TORRIJOS | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-27 | 4B0114S00019 | 15EA0053 | 2015-06-01 | 2015-06-03 | 2015-06-15 | 2015-06-19 | 2015-07-03 | R.C. TAGALA CONSTRUCTION
3229 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301554 | Marinduque NHS | BOAC (Capital) | 0 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15221327.92 |  |  | COMPLETED | 1 | 2016-04-18 |  | 4B0114S00023 | 15EA0077 | 2015-07-06 | 2015-07-08 | 2015-07-21 | 2015-07-28 | 2015-08-10 | PERFORMANCE BUILDERS & DEVELOPERS CORPORATION
3230 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301555 | Matalaba NHS | SANTA CRUZ | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-01-29 |  | 4B0114S00021 | 15EA0066 | 2015-06-22 | 2015-06-24 | 2015-07-07 | 2015-07-11 | 2015-07-27 | 8 Rs CONSTRUCTION
3231 | NC 2014 | K10 (2014) | Region IV-B | Marinduque | 109932 | Matandang Gasan ES | GASAN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2015-01-02 | 2014-12-29 | 4B0114S00001 | 4B01-14-S-00001 | 2014-09-30 | 2014-10-13 | 2014-10-16 | 2014-10-20 | 2014-10-30 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS)
3232 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301556 | Matuyatuya NHS | TORRIJOS | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 4B0114S00020 | 15EA0062 | 2015-06-14 | 2015-06-30 | 2015-07-28 | 2015-08-04 | 2015-08-17 | R.C. TAGALA CONSTRUCTION
3233 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301557 | Mogpog NCHS | MOGPOG | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-03 |  | 4B0114S00018 | 15EA0065 | 2015-07-21 | 2015-08-04 | 2015-08-04 | 2015-08-08 | 2015-08-24 | R.C. TAGALA CONSTRUCTION
3234 | NC 2014 | SHS (2014) | Region IV-B | MARINDUQUE | 301558 | Mongpong NHS | SANTA CRUZ | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-16 | 2015-10-16 | 4B0114S00010 | 15EA0046-2 | 2015-05-18 | 2015-05-21 | 2015-06-02 | 2015-06-12 | 2015-06-25 | R.C. TAGALA CONSTRUCTION
3235 | NC 2014 | SHS (2014) | Region IV-B | MARINDUQUE | 308804 | Paciano A. Sena Mem. HS (Tabionan NHS) | GASAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-26 | 2015-10-26 | 4B0114S00009 | 15EA0047-2 | 2015-05-18 | 2015-05-21 | 2015-06-02 | 2015-06-12 | 2015-06-25 | R.C. TAGALA CONSTRUCTION
3236 | NC 2014 | SHS (2014) | Region IV-B | MARINDUQUE | 308801 | Poctoy NHS (Bonliw NHS-Poctoy Annex) | TORRIJOS | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-26 | 2015-10-26 | 4B0114S00008 | 15EA0047-1 | 2015-05-18 | 2015-05-21 | 2015-06-02 | 2015-06-12 | 2015-06-25 | R.C. TAGALA CONSTRUCTION
3237 | NC 2014 | SHS (2014) | Region IV-B | MARINDUQUE | 301560 | Punong NHS | SANTA CRUZ | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-16 | 2015-10-16 | 4B0114S00007 | 15EA0046-1 | 2015-05-18 | 2015-05-21 | 2015-06-02 | 2015-06-12 | 2015-06-25 | R.C. TAGALA CONSTRUCTION
3238 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301562 | Sibuyao NHS | TORRIJOS | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 | 2015-12-04 | 2015-12-04 | 4B0114S00017 | 15EA0052 | 2015-06-01 | 2015-06-03 | 2015-06-15 | 2015-06-19 | 2015-07-03 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS)
3239 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301565 | Tapuyan NHS | GASAN | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 4B0114S00005 | 15EA0056 | 2015-06-01 | 2015-06-03 | 2015-06-15 | 2015-06-19 | 2015-07-03 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS)
3240 | NC 2014 | K10 (2014) | Region IV-B | Marinduque | 301566 | Tigwi NHS | TORRIJOS | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1
3241 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301566 | Tigwi NHS | TORRIJOS | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
3242 | NC 2014 | SHS (2014) | Region IV-B | Marinduque | 301568 | Yook NHS | BUENAVISTA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-28 |  | 4B0114S00014 | 15EA0064 | 2015-06-14 | 2015-06-17 | 2015-06-30 | 2015-07-04 | 2015-07-21 | R.C. TAGALA CONSTRUCTION
3243 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301569 | Abra de Ilog NHS | ABRA DE ILOG | 0 | 1 | 12 | 3STY12CL | 2014 SHS BATCH 1 | 18392268.79 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3244 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110194 | Adela ES | RIZAL | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-25 | 4B0214S00045 | 14EB0083 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES
3245 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110209 | Alag ES | SABLAYAN | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0214S00014 | 14EB0078 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | THREE W BUILDERS, INC.
3246 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110296 | Alitaytayan ES | SAN JOSE | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-10-25 | 4B0214S00025 | 14EB0085 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | BLACER CONSTRUCTION
3247 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110196 | Amaling II ES | RIZAL | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-10-25 | 4B0214S00044 | 14EB0084 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | BLACER CONSTRUCTION
3248 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110277 | Ambulong ES Annex - Patag PS | SAN JOSE | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2940828.124 |  |  | COMPLETED | 1 | 2016-01-26 |  | 4B0214S00078 | 15EB0046 | 2015-07-07 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | FIRMABUILT CONSTRUCTION | no remarks
3249 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 169509 | Aroma PS | MAMBURAO (Capital) | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 4B0214S00017 | 14EB0076 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | THREE W BUILDERS, INC.
3250 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110040 | Balao ES | ABRA DE ILOG | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1
3251 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110040 | Balao ES | ABRA DE ILOG | 0 | 1 | 6 | 1STY5CL, 1STY1CL | 2014 K10 BATCH 2 | 4989000 |  |  | COMPLETED | 1
3252 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110279 | Bangkal ES | SAN JOSE | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3075174.43 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-05-25 | 4B0214S00002 | 14EB0086 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | BLACER CONSTRUCTION
3253 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301573 | Barahan NHS | SANTA CRUZ | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-05-12 |  | 4B0214S00110 | 15EB0031 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-12-02 | 2015-12-07 | Hi-Tone Construction | no remarks
3254 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 169522 | Bato Singit Minority School | RIZAL | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-10-25 | 4B0214S00018 | 14EB0084 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | BLACER CONSTRUCTION
3255 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110041 | Biga Minority School | ABRA DE ILOG | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 4B0214S00038 | 14EB0074 | 2014-06-30 | 2014-08-04 | 2014-08-15 | 2014-09-02 | 2014-09-16 | NEW MINDORENOS LUMBER, HARDWARE AND GEN MERCHANDIS
3256 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110281 | Buri ES | SAN JOSE | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-05-25 | 4B0214S00001 | 14EB0086 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | BLACER CONSTRUCTION
3257 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110099 | Burol ES | LOOC | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-08 |  | 4B0214S00041 | 14EB0090 | 2014-06-30 | 2014-12-18 | 2014-12-19 | 2014-12-22 | 2014-12-23 | By Administration | no remarks
3258 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110042 | Cabacao ES | ABRA DE ILOG | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2790828.124 |  |  | COMPLETED | 1 | 2016-01-26 | 2016-01-26 | 4B0214S00079 | 15EB0046 | 2015-07-07 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | FIRMABUILT CONSTRUCTION | no remarks
3259 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110122 | Cabag ES | MAGSAYSAY | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 953000 |  |  | COMPLETED | 1 | 2015-05-09 | 2015-04-25 | 4B0214S00075 | 14EB0095 | 2014-08-27 | 2014-10-31 | 2014-11-03 | 2014-11-07 | 2014-11-10 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES
3260 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301574 | CALINTAAN NATIONAL HIGH SCHOOL | CALINTAAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3261 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 301574 | CALINTAAN NATIONAL HIGH SCHOOL | CALINTAAN | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1
3262 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110282 | Caminawit Central School | SAN JOSE | 0 | 1 | 7 | 1STY5CL, 1STY2CL | 2014 K10 BATCH 2 | 5746000 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 4B0214S00071 | 14EB0093 | 2014-07-07 | 2014-10-31 | 2014-11-03 | 2014-11-07 | 2014-11-10 | M.A. GUINTO CONSTRUCTION (SAN JOSE BRANCH)
3263 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 308909 | Caminawit NHS | SAN JOSE | 0 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3264 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 308909 | Caminawit NHS | SAN JOSE | 0 |  | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3265 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110127 | Cawit ES | MAGSAYSAY | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-25 | 4B0214S00032 | 14EB0088 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | JEENE-SON CONSTRUCTION
3266 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301600 | Central NHS | SAN JOSE | 0 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10477131.51 |  |  | COMPLETED | 1 | 2016-03-19 |  | 4B0214S00108 | 15EB0087 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-10-01 | 2015-10-16 | KINGs BUILDERS & DEVELOPMENT CORPORATION | no remarks
3267 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110211 | Claudio Salgado ES | SABLAYAN | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0214S00012 | 14EB0078 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | THREE W BUILDERS, INC.
3268 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110162 | Cuarenta ES | SANTA CRUZ | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-03-11 | 2015-03-11 | 4B0214S00050 | 14EB0077 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | KATHA BUILDERS
3269 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110181 | Eleuterio Soriano School | SANTA CRUZ | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-03-11 | 2015-03-11 | 4B0214S00047 | 14EB0077 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | KATHA BUILDERS
3270 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110129 | Gapasan ES | MAGSAYSAY | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-25 | 4B0214S00049 | 14EB0088 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | JEENE-SON CONSTRUCTION
3271 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110234 | Gen. E. Aguinaldo ES | SABLAYAN | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0214S00011 | 14EB0080 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | N. SALES CONSTRUCTION
3272 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110131 | Guballa ES | MAGSAYSAY | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 953000 |  |  | COMPLETED | 1 | 2015-05-09 | 2015-04-25 | 4B0214S00077 | 14EB0095 | 2014-07-07 | 2014-10-31 | 2014-11-03 | 2014-11-07 | 2014-11-10 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES
3273 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110260 | Hilltop ES | SAN JOSE | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-10-25 | 4B0214S00004 | 14EB0085 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | BLACER CONSTRUCTION
3274 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110132 | Hinango ES | MAGSAYSAY | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-05-25 | 4B0214S00053 | 14EB0089 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | BLACER CONSTRUCTION
3275 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301578 | Iling NHS | SAN JOSE | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8844965.051 |  |  | COMPLETED | 1 | 2016-03-21 |  | 4B0214S00097 | 15EB0041R1 | 2015-11-12 | 2015-11-19 | 2015-12-01 | 2015-12-11 |  | FIRMABUILT CONSTRUCTION | no remarks
3276 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110261 | Insulman Primary Sch. | SAN JOSE | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 1906000 |  |  | COMPLETED | 1 | 2015-04-09 | 2015-11-25 | 4B0214S00073 | 14EB0111 | 2014-07-07 | 2014-10-31 | 2014-11-03 | 2014-11-07 | 2014-11-10 | F.P.N. CONSTRUCTORS , INC
3277 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110165 | Kabangkalan ES | SANTA CRUZ | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-03-11 | 2015-03-11 | 4B0214S00043 | 14EB0077 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | KATHA BUILDERS
3278 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301583 | Looc National School Of Fisheries | LOOC | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8454965.051 |  |  | COMPLETED | 1 | 2016-04-12 |  | 4B0214S00107 | 15EB0045 | 2015-08-13 | 2015-09-04 | 2015-09-14 | 2015-11-27 | 2015-12-08 | R.C. TAGALA CONSTRUCTION | no remarks
3279 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301585 | Lubang IS | LUBANG | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8454965.051 |  |  | COMPLETED | 1 |  |  | 4B0214S00112 | 15EB0044 | 2015-07-20 | 2015-07-24 |  |  |  | C.L. CARANDANG ENTERPRISES | no remarks
3280 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301586 | LUBANG VOCATIONAL HIGH SCHOOL | LUBANG | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8454965.051 |  |  | COMPLETED | 1 |  |  | 4B0214S00095 | 15EB0044 | 2015-11-12 | 2015-11-19 | 2015-12-01 | 2015-12-11 |  | C.L. CARANDANG ENTERPRISES | no remarks
3281 | NC 2014 | SHS (2014) | Region IV-B | OCCIDENTAL MINDORO | 301587 | Lubang Vocational High School-Cabra | LUBANG | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 4B0214S00105 | 15EB0044 | 2015-07-20 | 2015-07-24 |  |  |  | C.L. CARANDANG ENTERPRISES | no remarks
3282 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110199 | Lumintao ES | RIZAL | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-25 | 4B0214S00034 | 14EB0083 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES
3283 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110135 | Magarang ES | MAGSAYSAY | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-05-25 | 4B0214S00052 | 14EB0089 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | BLACER CONSTRUCTION
3284 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301588 | Magsaysay NHS | MAGSAYSAY | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3285 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 301589 | Magsaysay NHS - Mapaya Annex | SAN JOSE | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3286 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301589 | Magsaysay NHS - Mapaya Annex | SAN JOSE | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3287 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 301589 | Magsaysay NHS-Mapaya Annex | SAN JOSE | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 1906000 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3288 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110200 | Magsikap ES | RIZAL | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-25 | 4B0214S00019 | 14EB0083 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES
3289 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110201 | Malawaan ES | RIZAL | 0 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 4C | 10877342.5917 |  |  | COMPLETED | 1 | 2016-04-06 |  | 4B0214S00121 | 14EB0048R2 | 2015-09-01 | 2015-09-18 | 2015-09-30 | 2015-10-15 | 2015-11-03 | R.C. TAGALA CONSTRUCTION | no remarks
3290 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110238 | Malisbong ES | SABLAYAN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0214S00007 | 14EB0080 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | N. SALES CONSTRUCTION
3291 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110087 | Malpalon ES | CALINTAAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-01 |  | 4B0214S00114 | 15EB0047 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-08-24 | 2015-08-28 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | no remarks
3292 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 301575 | Malpalon National High School | CALINTAAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-01 |  | 4B0214S00116 | 15EB0047 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-08-24 | 2015-08-28 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | no remarks
3293 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110058 | Mamara Min. ES | PALUAN | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 4B0214S00037 | 14EB0075 | 2014-06-30 | 2014-08-04 | 2014-08-15 | 2014-09-02 | 2014-09-16 | THREE W BUILDERS, INC.
3294 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110059 | Mananao ES | ABRA DE ILOG | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 4B0214S00036 | 14EB0074 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | NEW MINDORENOS LUMBER, HARDWARE AND GEN MERCHANDIS
3295 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110290 | Manga ES | SAN JOSE | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1
3296 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110290 | Manga ES | SAN JOSE | 0 | 1 | 3 | 1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 2663000 |  |  | COMPLETED | 1
3297 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110202 | Manoot ES | RIZAL | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-04-06 |  | 4B0214S00120 | 14EB0048R2 | 2015-09-01 | 2015-09-18 | 2015-09-30 | 2015-10-15 | 2015-11-03 | R.C. TAGALA CONSTRUCTION
3298 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110291 | Natandol ES | SAN JOSE | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-05-25 | 4B0214S00024 | 14EB0086 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | BLACER CONSTRUCTION
3299 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110138 | Nicolas ES | MAGSAYSAY | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-05-25 | 4B0214S00051 | 14EB0089 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | BLACER CONSTRUCTION
3300 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301593 | Occidental Mindoro NHS | MAMBURAO (Capital) | 0 | 1 | 15 | 3STY15CL | 2014 SHS BATCH 1 | 21493013.45 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3301 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110065 | Paluan CS - Annex | PALUAN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3302 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301594 | Paluan NHS | PALUAN | 0 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15401327.92 |  |  | COMPLETED | 1 | 2016-05-18 |  | 4B0214S00088 | 15EB0083 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-10-02 | 2015-10-16 | Hi-Tone Construction | no remarks
3303 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301582 | Paulino Legaspi, Sr. Memorial. NHS | SABLAYAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-05-12 |  | 4B0214S00087 | 15EB0035 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-08-24 | 2015-12-08 | R.C. TAGALA CONSTRUCTION | no remarks
3304 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110292 | Pawican ES | SAN JOSE | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3075174.43 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 4B0214S00031 | 14EB0087 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | JEENE-SON CONSTRUCTION
3305 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110294 | Pawican ES Annex - Tabay PS | SAN JOSE | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2110417.57 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 4B0214S00021 | 14EB0087 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | JEENE-SON CONSTRUCTION
3306 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110295 | Pawican ES Annex - Tibago PS | SAN JOSE | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2110417.57 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 4B0214S00020 | 14EB0087 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | JEENE-SON CONSTRUCTION
3307 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110239 | Payompon ES | SABLAYAN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-02-25 | 4B0214S00006 | 14EB0079 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | STEVEN CONSTRUCTION & SUPPLY
3308 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301592 | Pedro T. Mendiola Sr. Memorial National High School | SAN JOSE | 0 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2016-03-19 |  | 4B0214S00086 | 15EB0040 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-10-01 | 2015-10-16 | M.A. GUINTO CONSTRUCTION (SAN JOSE BRANCH)
3309 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 169525 | Pinagbayanan Minority School | PALUAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 2334740.174 |  |  | COMPLETED | 1 | 2016-01-26 | 2015-12-30 | 4B0214S00082 | 15EB0046 | 2015-07-07 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | FIRMABUILT CONSTRUCTION
3310 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110240 | Poblacion ES | SABLAYAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1052049.6543 |  |  | COMPLETED | 1 | 2016-01-26 |  | 4B0214S00080 | 15EB0046 | 2015-07-07 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | FIRMABUILT CONSTRUCTION
3311 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110069 | Rayusan Min. Sch. | ABRA DE ILOG | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 4B0214S00030 | 14EB0075 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | THREE W BUILDERS, INC.
3312 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301595 | RIZAL NATIONAL HIGH SCHOOL | RIZAL | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-18 |  | 4B0214S00085 | 15EB0038 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-08-24 | 2015-10-16 | M.A. GUINTO CONSTRUCTION (SAN JOSE BRANCH)
3313 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 308904 | Rizal NHS - Manoot Extension | RIZAL | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-18 |  | 4B0214S00084 | 15EB0038 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-10-01 | 2015-10-16 | M.A. GUINTO CONSTRUCTION (SAN JOSE BRANCH)
3314 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301596 | Sablayan NCHS | SABLAYAN | 0 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15151327.92 |  |  | COMPLETED | 1 | 2016-07-11 |  | 4B0214S00083 | 15EB0085 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-08-24 | 2015-12-08 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | no remarks
3315 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301597 | Sablayan NCHS - Claudio Salgado Annex | SABLAYAN | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2750828.124 |  |  | COMPLETED | 1 | 2016-04-12 |  | 4B0214S00089 | 15EB0034R1 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-08-24 | 2015-12-08 | Hi-Tone Construction | no remarks
3316 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301598 | Sablayan NCHS - Pag-asa Annex | SABLAYAN | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 | 2016-04-12 |  | 4B0214S00094 | 15EB0034R1 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-08-24 | 2015-12-08 | Hi-Tone Construction | no remarks
3317 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 169503 | Sablayan Prison and Penal Farm ES | SABLAYAN | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0214S00023 | 14EB0081 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | THREE W BUILDERS, INC.
3318 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110269 | San Agustin ES | SAN JOSE | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-10-25 | 4B0214S00003 | 14EB0085 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | BLACER CONSTRUCTION
3319 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 308908 | San Jose NAIHS - Mangarin Annex | SAN JOSE | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1
3320 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 308908 | San Jose NAIHS - Mangarin Annex | SAN JOSE | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1
3321 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 308901 | San Jose National Agricultural and Industrial High School | SAN JOSE | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-03-19 |  | 4B0214S00096 | 15EB0041R1 | 2015-11-12 | 2015-11-19 | 2015-12-01 | 2015-12-11 |  | FIRMABUILT CONSTRUCTION
3322 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301599 | San Jose NHS | SAN JOSE | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-19 |  | 4B0214S00091 | 15EB0042 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-10-01 | 2015-10-16 | Hi-Tone Construction | no remarks
3323 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110178 | San Luis ES | MAMBURAO (Capital) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3324 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110244 | San Nicolas ES | SABLAYAN | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0214S00015 | 14EB0080 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | N. SALES CONSTRUCTION
3325 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110254 | San Roque 2 ES | SAN JOSE | 0 | 1 | 7 | 1STY4CL, 1STY3CL | 2014 K10 BATCH 2 | 5752000 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 4B0214S00070 | 14EB0092 | 2014-07-07 | 2014-10-31 | 2014-11-03 | 2014-11-07 | 2014-11-10 | R.B. ALCAZAR CONSTRUCTION & DEVELOPMENT
3326 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301601 | San Vicente NHS | SABLAYAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-05-12 |  | 4B0214S00098 | 15EB0035 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-08-24 | 2015-12-08 | R.C. TAGALA CONSTRUCTION | no remarks
3327 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301602 | San Vicente NHS - Yapang Annex | SABLAYAN | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2670828.124 |  |  | COMPLETED | 1 | 2016-04-12 |  | 4B0214S00099 | 15EB0034R1 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-08-24 | 2015-12-08 | Hi-Tone Construction
3328 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301603 | Santa Cruz NHS | SANTA CRUZ | 0 | 1 | 15 | 3STY15CL | 2014 SHS BATCH 1 | 21613013.45 |  |  | COMPLETED | 1 | 2016-08-10 |  | 4B0214S00100 | 15EB0084R1 | 2015-09-01 | 2015-09-21 | 2015-09-30 | 2015-11-27 | 2015-12-08 | R.C. TAGALA CONSTRUCTION | no remarks
3329 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 301604 | Santa Cruz NHS - Pinagturilan Annex | SANTA CRUZ | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3330 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301604 | Santa Cruz NHS - Pinagturilan Annex | SANTA CRUZ | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | [10 empty] | no remarks
3331 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110222 | Selina ES | SABLAYAN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0214S00008 | 14EB0078 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | THREE W BUILDERS, INC.
3332 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110223 | Sotero Baluyot ES | SABLAYAN | 0 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3840805.49 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-02-25 | 4B0214S00009 | 14EB0079 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | STEVEN CONSTRUCTION & SUPPLY
3333 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301605 | Sta Teresa NHS | MAGSAYSAY | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 | 2016-03-26 |  | 4B0214S00102 | 13EB0189 | 2015-09-01 | 2015-09-21 | 2015-10-05 | 2015-10-18 | 2015-10-23 | GRANBY TRADING & CONSTRUCTION | no remarks
3334 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110246 | Sta. Lucia II ES | SABLAYAN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-02-25 | 4B0214S00005 | 14EB0079 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | STEVEN CONSTRUCTION & SUPPLY
3335 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110142 | Sto Cristo ES | MAGSAYSAY | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 953000 |  |  | COMPLETED | 1 | 2015-05-09 | 2015-04-25 | 4B0214S00074 | 14EB0095 | 2014-07-07 | 2014-10-31 | 2014-11-03 | 2014-11-07 | 2014-11-10 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES
3336 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110225 | Sto. Nino ES | SABLAYAN | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0214S00010 | 14EB0081 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | THREE W BUILDERS, INC.
3337 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110095 | Tabao ES (Ambil ES-Tabao Site) | LOOC | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-28 |  | 4B0214S00035 | 14EB0090 | 2014-06-30 | 2014-12-18 | 2014-12-19 | 2014-12-22 | 2014-12-23 | By Administration | no remarks
3338 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110092 | Tanyag ES | CALINTAAN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-02-25 | 4B0214S00039 | 14EB0082 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | STEVEN CONSTRUCTION & SUPPLY
3339 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301606 | Tanyag NHS | CALINTAAN | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 | 2016-02-18 |  | 4B0214S00103 | 15EB0037 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-10-01 | 2015-10-16 | M.A. GUINTO CONSTRUCTION (SAN JOSE BRANCH)
3340 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110190 | Tayamaan ES Annex - Dungon | MAMBURAO (Capital) | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-01-25 | 4B0214S00046 | 14EB0076 | 2014-06-30 | 2014-08-01 | 2014-08-04 | 2014-09-02 | 2014-09-16 | THREE W BUILDERS, INC.
3341 | NC 2014 | K10 (2014) | Region IV-B | Occidental Mindoro | 110247 | Tuban ES | SABLAYAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1874740.174 |  |  | COMPLETED | 1 | 2016-01-26 |  | 4B0214S00081 | 15EB0046 | 2015-07-07 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | FIRMABUILT CONSTRUCTION
3342 | NC 2014 | SHS (2014) | Region IV-B | Occidental Mindoro | 301609 | Victoria NHS - Ilvita Annex | SABLAYAN | 0 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1 | 2016-05-10 |  | 4B0214S00104 | 15EB0086 | 2015-07-20 | 2015-07-24 | 2015-07-27 | 2015-08-24 | 2015-12-08 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | no remarks
3343 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 301611 | Apitong NHS | NAUJAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1
3344 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301611 | Apitong NHS | NAUJAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8424965.051 |  |  | COMPLETED | 1
3345 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110317 | Asiko Bo. Sch. | BACO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-11-27 | 2015-11-27 | 4B0314S00147 | 15ED0046 | 2015-06-26 | 2015-06-30 | 2015-07-14 | 2015-07-21 | 2015-07-27 | ETVR TRADING & CONSTRUCTION
3346 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301613 | Aurelio Arago MNHS | VICTORIA | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1
3347 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 309012 | Aurelio Arago MNHS - Alcate Annex | VICTORIA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
3348 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301614 | Aurora NHS | NAUJAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8504965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 4B0314S00087 | 13ED0102 | 2015-07-17 | 2015-07-23 | 2015-08-17 | 2015-08-26 | 2015-09-02 | GREAT LAKES ENTERPRISES
3349 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301616 | Baco NHS | BACO | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10817131.51 |  |  | COMPLETED | 1 |  |  | 4B0314S00120 | 13ED0102 | 2015-07-31 |  |  |  |  | GREAT LAKES ENTERPRISES
3350 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 309008 | Baco NHS - Dulangan II Annex | BACO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8694965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 4B0314S00100 | 13ED0102 | 2015-07-20 | 2015-07-23 | 2015-08-17 | 2015-08-21 | 2015-09-02 | GREAT LAKES ENTERPRISES
3351 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 309036 | Baco NHS - Lumambayan Annex | BACO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 4B0314S00040 | 14ED0032 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | GREAT LAKES ENTERPRISES
3352 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 170014 | Bagong Silang II ES | VICTORIA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-25 | 4B0314S00046 | 14ED0033 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | DK CONSTRUCTION
3353 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110319 | Bayanan ES | BACO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-11-27 | 2015-11-09 | 4B0314S00144 | 15 ED0047 | 2015-07-10 | 2015-06-30 | 2015-07-14 | 2015-07-21 | 2015-07-27 | JARO BUILDERS & CONSTRUCTION SUPPLY
3354 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301619 | Bayuin NHS | SOCORRO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 4B0314S00119 | 13ED0102 | 2015-07-20 | 2015-07-23 | 2015-08-05 | 2015-08-24 | 2015-09-11 | GREAT LAKES ENTERPRISES
3355 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110537 | Buhangin ES | NAUJAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-10-25 | 2014-10-25 | 4B0314S00051 | 14ED0034 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | KINGs BUILDERS & DEVELOPMENT CORPORATION
3356 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110668 | Calucmoy PS | SOCORRO | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 4B0314S00049 | 14ED0038 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | KINGs BUILDERS & DEVELOPMENT CORPORATION
3357 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301628 | Domingo Yu Chu MNHS - Bacawan Annex | POLA | 1 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2970828.124 |  |  | COMPLETED | 1 | 2016-02-24 |  | 4B0314S00121 | 15ED0107 | 2015-09-23 | 2015-09-21 | 2015-10-07 | 2015-10-15 | 2015-10-21 | FRAMECON BUILDERS
3358 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301629 | Domingo Yu Chu MNHS-Matulatula | POLA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8444965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 4B0314S00125 | 13ED0102 | 2015-07-17 | 2015-07-23 | 2015-08-17 | 2015-08-24 | 2015-09-02 | GREAT LAKES ENTERPRISES
3359 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301627 | Domingo Yu Chu NHS | POLA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8584965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 4B0314S00135 | 13ED0102 | 2015-07-20 | 2015-07-23 | 2015-08-17 | 2015-08-25 | 2015-09-02 | GREAT LAKES ENTERPRISES
3360 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 309025 | Domingo Yu Chu NHS - Tagumpay Ext. | POLA | 1 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2850828.124 |  |  | COMPLETED | 1 | 2016-02-24 |  | 4B0314S00124 | 15ED0106 | 2015-10-05 | 2015-09-24 | 2015-10-07 | 2015-10-15 | 2015-10-21 | FRAMECON BUILDERS
3361 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301630 | Doroteo Mendoza NHS | NAUJAN | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1 |  |  | 4B0314S00118 | 13ED0102 | 2015-07-27 |  |  |  |  | GREAT LAKES ENTERPRISES
3362 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 301615 | Evangelista NHS | NAUJAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-17 | 4B0314S00044 | 14ED0037 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | B5 BUILDERS & SUPPLIES
3363 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 301635 | Fortuna NHS | SOCORRO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2080417.57 |  |  | COMPLETED | 1
3364 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301635 | Fortuna NHS | SOCORRO | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6809337.6381 |  |  | COMPLETED | 1
3365 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110672 | Granvida ES | SOCORRO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-27 | 4B0314S00050 | 14ED0045 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | F.S. SUGAY CONSTRUCTION & SUPPLIES
3366 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 309001 | Inarawan NHS | NAUJAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8734965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 4B0314S00127 | 13ED0102 | 2015-07-20 | 2015-07-23 | 2015-08-05 | 2015-08-19 | 2015-09-02 | GREAT LAKES ENTERPRISES
3367 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110613 | Isidoro Suzara Memorial School | PUERTO GALERA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 4B0314S00038 | 14ED0031 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | HIGH AND MILES CONSTRUCTION
3368 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301634 | Leuteboro NHS | SOCORRO | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 4B0314S00128 | 13ED0102 | 2015-07-29 |  |  |  |  | GREAT LAKES ENTERPRISES
3369 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110517 | Mabini ES | NAUJAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-27 | 4B0314S00054 | 14ED0042 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | CMSEL CONSTRUCTION & DEVELOPER
3370 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301612 | Macatoc NHS (Aurelio Arago NHS ( Macatoc)) | VICTORIA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 4B0314S00129 | 13ED0102 | 2015-07-20 | 2015-07-23 | 2015-08-05 | 2015-08-19 | 2015-09-02 | GREAT LAKES ENTERPRISES
3371 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110520 | Malvar ES | NAUJAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 4B0314S00053 | 14ED0030 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-08-04 | 2014-08-06 | KASANGA CONSTRUCTION AND SUPPLIES
3372 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110341 | Mangangan II Elem.. Sch. | BACO | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 4B0314S00055 | 14ED0039 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | ETVR TRADING & CONSTRUCTION
3373 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110679 | Maria Concepcion ES | SOCORRO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-11-27 | 2015-11-27 | 4B0314S00143 | 15ED0045 | 2015-07-10 | 2015-06-30 | 2015-07-14 | 2015-07-17 | 2015-07-27 | L.N. SALVADOR CONSTRUCTION
3374 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301642 | Melgar NHS | NAUJAN | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10667131.51 |  |  | COMPLETED | 1 |  |  | 4B0314S00130 | 13ED0102 | 2015-07-29 |  |  |  |  | GREAT LAKES ENTERPRISES
3375 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 309003 | Melgar NHS-Masaging Annex | NAUJAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 4B0314S00042 | 14ED0035 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | B5 BUILDERS & SUPPLIES
3376 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110499 | Nag-Iba I ES | NAUJAN | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-06 |  | 4B0314S00076 | 13ED0102 | 2015-07-20 | 2015-07-23 | 2015-08-05 | 2015-08-21 | 2015-09-02 | GREAT LAKES ENTERPRISES
3377 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301645 | Naujan Municipal NHS | NAUJAN | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10637131.51 |  |  | COMPLETED | 1 |  |  | 4B0314S00131 | 13ED0102 | 2015-07-29 |  |  |  |  | GREAT LAKES ENTERPRISES
3378 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301648 | Porfirio Comia MNHS | NAUJAN | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10717131.51 |  |  | COMPLETED | 1 |  |  | 4B0314S00132 | 13ED0102 | 2015-07-29 |  |  |  |  | GREAT LAKES ENTERPRISES
3379 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 309004 | Puerto Galera NHS | PUERTO GALERA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8574965.051 |  |  | COMPLETED | 1 |  |  | 4B0314S00133 | 13ED0102 | [5 empty] | GREAT LAKES ENTERPRISES
3380 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 309035 | Puerto Galera NHS - San Isidro Ext. | PUERTO GALERA | 1 | 1 | 4 | 2UNITS 2STY2CL | 2014 K10 BATCH 4A | 3504128.1735 |  |  | COMPLETED | 1
3381 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 309035 | Puerto Galera NHS - San Isidro Ext. | PUERTO GALERA | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10647131.51 |  |  | COMPLETED | 1
3382 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301651 | San Agustin NHS | NAUJAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8694965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 4B0314S00098 | 13ED0102 | 2015-07-29 | 2015-08-03 | 2015-08-17 | 2015-08-25 | 2015-09-02 | GREAT LAKES ENTERPRISES
3383 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110527 | San Carlos ES | NAUJAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-27 | 4B0314S00052 | 14ED0047 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-08-04 | 2014-08-06 | L.N. SALVADOR CONSTRUCTION
3384 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110700 | San Isidro ES | VICTORIA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-06 |  | 4B0314S00142 | 13ED0102 | 2015-07-27 | 2015-07-28 | 2015-08-05 | 2015-08-17 | 2015-09-02 | GREAT LAKES ENTERPRISES
3385 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110661 | San Rafael Elementary School | SAN TEODORO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-27 | 4B0314S00020 | 14ED0044 | 2014-06-26 | 2014-07-03 | 2014-07-24 | 2014-07-31 | 2014-08-06 | KINGs BUILDERS & DEVELOPMENT CORPORATION
3386 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301653 | San Teodoro NHS | SAN TEODORO | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10817131.51 |  |  | COMPLETED | 1 |  |  | 4B0314S00092 | 13ED0102 | 2015-07-27 |  |  |  |  | GREAT LAKES ENTERPRISES
3387 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 170034 | Abintang ES | BULALACAO (SAN PEDRO) | 2 | 1 | 6 | 2UNITS 1STY 3CL | 2014 K10 BATCH 1 | 5850348.86 |  |  | COMPLETED | 1 | 2015-12-28 |  | 4B0314S00035 | 14EIE037 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3388 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110432 | Agsalin ES | GLORIA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 4B0314S00065 | 14EI004 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3389 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 170039 | Akliyang ES | BONGABONG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
3390 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 170039 | Akliyang ES | BONGABONG | 2 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
3391 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301610 | Alcadesma NHS | BANSUD | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8619965.051 |  |  | COMPLETED | 1 | 2016-03-13 |  | 4B0314S00088 | 15EI0076 | 2015-08-12 | 2015-08-13 | 2015-09-01 | 2015-09-11 | 2015-09-21 | F.S. SUGAY CONSTRUCTION & SUPPLIES
3392 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 170005 | Aplaya ES | BONGABONG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2015-04-19 | 2015-04-19 | 4B0314S00036 | 14EIE015 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3393 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110350 | Apnagan ES | BANSUD | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 4B0314S00039 | 14EIE008 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | KINGs BUILDERS & DEVELOPMENT CORPORATION
3394 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110370 | Bagong Bayan CS | BONGABONG | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-06 |  | 4B0314S00136 | 15EI0058 | 2015-08-11 | 2015-08-13 | 2015-08-26 | 2015-09-04 | 2015-09-21 | F.S. SUGAY CONSTRUCTION & SUPPLIES
3395 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301617 | Balugo NHS | MANSALAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 | 2016-03-06 |  | 4B0314S00083 | 15EI0064 | 2015-08-11 | 2015-08-13 | 2015-08-26 | 2015-09-04 | 2015-09-21 | KINGs BUILDERS & DEVELOPMENT CORPORATION
3396 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110412 | Bangkal ES | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-19 | 4B0314S00062 | 14EIE033 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3397 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301618 | Bansud NHS - Regional Science High School | BANSUD | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  | 6485100 | COMPLETED | 1 | 2016-02-21 |  | 4B0314S00082 | 15EI0078 | 2015-08-18 | 2015-08-19 | 2015-09-04 | 2015-09-21 | 2015-09-30 | I.F. BLANCOS CONSTRUCTION | With Approved Buffer Fund (2018 Batch 2)
3398 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110436 | Banutan ES | GLORIA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 4B0314S00068 | 14EIE005 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3399 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 170035 | Bating ES | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-19 | 4B0314S00034 | 14EIE032 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3400 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110352 | Bato ES | BANSUD | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-28 |  | 4B0314S00078 | 15EI0049 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-21 | 2015-09-30 | LUMEL GLENN CONSTRUCTION
3401 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301620 | Bulalacao NHS | BULALACAO (SAN PEDRO) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-03-06 |  | 4B0314S00081 | 15EI0053 | 2015-08-11 | 2015-08-13 | 2015-08-26 | 2015-09-04 | 2015-09-21 | LUMEL GLENN CONSTRUCTION
3402 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 309034 | Bulalacao NHS - Maasin Ext. | BULALACAO (SAN PEDRO) | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3880805.49 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-06 | 4B0314S00021 | 14EIE036 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3403 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301623 | Bulbugan NHS | GLORIA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8309965.051 |  | 8266933.53 | COMPLETED | 1 | 2016-03-06 |  | 4B0314S00080 | 15EI0065 | 2015-08-11 | 2015-08-13 | 2015-08-26 | 2015-09-04 | 2015-09-21 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3404 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110465 | Cabuyao PS | MANSALAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-12-20 |  | 4B0314S00015 | 14EIE022 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3405 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110416 | Cambunang ES | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-19 | 4B0314S00063 | 14EIE034 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3406 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 309006 | Carmundo NHS | BONGABONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-03-06 |  | 4B0314S00084 | 15EI0055 | 2015-08-11 | 2015-08-13 | 2015-08-26 | 2015-09-04 | 2015-09-21 | ORIENT STAR CONSTRUCTION, INC. (FORMERLY: ORIENT S
3407 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110353 | Catmon ES | BANSUD | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 4B0314S00047 | 14EIE009 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | KINGs BUILDERS & DEVELOPMENT CORPORATION
3408 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301624 | Cawayan NHS | BONGABONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1 | 2016-03-13 |  | 4B0314S00089 | 15EI0075 | 2015-08-12 | 2015-08-13 | 2015-09-01 | 2015-09-11 | 2015-09-21 | A.D.L. CONSTRAK
3409 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110440 | Dalagan ES | GLORIA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 4B0314S00069 | 14EIE003 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3410 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110630 | Dangay ES | ROXAS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 4B0314S00005 | 14EI0093 | 2014-11-13 | 2014-11-14 | 2014-11-26 | 2014-12-12 | 2015-01-05 | LUMEL GLENN CONSTRUCTION
3411 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301640 | Dangay National High School | ROXAS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 | 2016-03-13 |  | 4B0314S00115 | 15EI0073 | 2015-08-12 | 2015-08-13 | 2015-09-01 | 2015-09-11 | 2015-09-21 | LUMEL GLENN CONSTRUCTION
3412 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301625 | Dayhagan NHS | BONGABONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1 | 2016-03-06 |  | 4B0314S00090 | 15EI0067 | 2015-08-11 | 2015-08-13 | 2015-08-26 | 2015-09-04 | 2015-09-21 | KINGs BUILDERS & DEVELOPMENT CORPORATION
3413 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110441 | Don Joaquin Roque MS | GLORIA | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  | 8172238.09 | COMPLETED | 1 | 2016-03-06 |  | 4B0314S00137 | 15EI0059 | 2015-08-11 | 2015-08-13 | 2015-08-26 | 2015-09-04 | 2015-09-21 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3414 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301631 | Fe del Mundo NHS | MANSALAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 | 2016-03-06 |  | 4B0314S00097 | 15EI0063 | 2015-08-11 | 2015-08-13 | 2015-08-26 | 2015-09-04 | 2015-09-21 | D.M. MALIWANAG BUILDERS AND ENTERPRISES
3415 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 309027 | Felimon M. Salcedo Sr. MNHS | BANSUD | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1
3416 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 309027 | Felimon M. Salcedo Sr. MNHS | BANSUD | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6479337.6381 |  |  | COMPLETED | 1
3417 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110396 | Kaligtasan ES | BONGABONG | 2 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 4C | 10877342.5917 |  |  | COMPLETED | 1 | 2016-05-02 |  | 4B0314S00140 | 15EI0103 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-27 | 2015-11-03 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3418 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 301633 | Kaligtasan NHS | BONGABONG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1
3419 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301633 | Kaligtasan NHS | BONGABONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8569965.051 |  |  | COMPLETED | 1
3420 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110468 | Kilapnit ES | MANSALAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-12-20 |  | 4B0314S00014 | 14EIE023 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3421 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 309005 | Labasan National High School | BONGABONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8579965.051 |  |  | COMPLETED | 1 | 2016-03-13 |  | 4B0314S00086 | 15EI0077 | 2015-08-12 | 2015-08-13 | 2015-09-01 | 2015-09-11 | 2015-09-21 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3422 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110479 | Lamac PS | MANSALAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 4B0314S00010 | 14EIE027 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3423 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110419 | Libtong ES | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-02 | 4B0314S00064 | 14EI0058 | 2014-10-02 | 2014-10-03 | 2014-10-15 | 2014-10-29 | 2014-11-17 | ADL GENERAL CONSTRUCTION
3424 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110378 | Lisap ES | BONGABONG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-06-25 | 2015-06-25 | 4B0314S00067 | 14EIE012 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3425 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110634 | Little Tanauan ES | ROXAS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0314S00001 | 14EIE017 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3426 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 301636 | Malamig NHS | GLORIA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1
3427 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301636 | Malamig NHS | GLORIA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
3428 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301638 | Manaul NHS | MANSALAY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6529337.6381 |  |  | COMPLETED | 1 | 2016-02-21 |  | 4B0314S00094 | 15EI0079 | 2015-08-18 | 2015-08-20 | 2015-09-01 | 2015-09-21 | 2015-09-30 | A.D.L. CONSTRAK
3429 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301639 | Marcelo I. Cabrera Vocational High School | ROXAS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
3430 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301641 | Masaguisi NHS | BONGABONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8454965.051 |  |  | COMPLETED | 1 | 2016-03-13 |  | 4B0314S00096 | 15EI0069 | 2015-08-12 | 2015-08-13 | 2015-09-01 | 2015-09-11 | 2015-09-21 | KARANGYAN BUILDERS & TRADERS
3431 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301621 | Maujao NHS | BULALACAO (SAN PEDRO) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1 | 2016-03-06 |  | 4B0314S00113 | 15EI0066 | 2015-08-11 | 2015-08-13 | 2015-08-26 | 2015-09-04 | 2015-09-21 | ORIENT STAR CONSTRUCTION, INC. (FORMERLY: ORIENT S
3432 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 309033 | Maujao NHS - Cabugao Ext. | BULALACAO (SAN PEDRO) | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2901174.43 |  |  | COMPLETED | 1 | 2015-04-16 | 2015-04-16 | 4B0314S00022 | 14EI0087 | 2014-10-16 | 2014-10-17 | 2014-10-28 | 2014-11-21 | 2014-12-18 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3433 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110452 | Mirayan ES | GLORIA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0314S00048 | 14EIE006 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3434 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301643 | Morente NHS | BONGABONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 | 2016-03-06 |  | 4B0314S00123 | 15EI0061 | 2015-08-11 | 2015-08-13 | 2015-08-26 | 2015-09-04 | 2015-09-21 | F.S. SUGAY CONSTRUCTION & SUPPLIES
3435 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 309030 | Morente NHS - Batangan Annex | BONGABONG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 4B0314S00024 | 14EIE014 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3436 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301644 | Nabuslot National High School | PINAMALAYAN | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10567131.51 |  | 10513148.48 | COMPLETED | 1 | 2016-05-31 |  | 4B0314S00107 | 15EI0104 | 2015-10-12 | 2015-10-15 | 2015-10-27 | 2015-11-26 | 2015-12-03 | I.F. BLANCOS CONSTRUCTION
3437 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 309018 | Nabuslot NHS - Sabang Ext. | PINAMALAYAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 4B0314S00037 | 14EI0080 | 2014-11-13 | 2014-11-14 | 2014-11-26 | 2014-12-12 | 2015-01-05 | ADL GENERAL CONSTRUCTION
3438 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110403 | Ogbot ES | BONGABONG | 2 | 1 | 5 | 1STY5CL (Toilet Attached) | 2014 K10 BATCH 4C | 4673636.82 |  |  | COMPLETED | 1 | 2015-12-22 | 2015-12-22 | 4B0314S00146 | 15EI0050 | 2015-07-21 | 2015-07-23 | 2015-08-05 | 2015-08-18 | 2015-08-25 | ORIENT STAR CONSTRUCTION, INC. (FORMERLY: ORIENT S
3439 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110637 | P. Olarte ES | ROXAS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0314S00003 | 14EIE018 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3440 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 309019 | Pag-asa NHS | BANSUD | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  | 8321721.81 | COMPLETED | 1 | 2016-03-13 |  | 4B0314S00101 | 15EI0068 | 2015-08-12 | 2015-08-13 | 2015-09-01 | 2015-09-11 | 2015-09-21 | ALBERTO UY CONSTRUCTION & DEVELOPMENT | With Approved Buffer Fund (2018 Batch 2)
3441 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301646 | Pambisan NHS | PINAMALAYAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8394965.051 |  | 8352000 | COMPLETED | 1 | 2016-03-13 |  | 4B0314S00102 | 15EI0071 | 2015-08-12 | 2015-08-13 | 2015-09-01 | 2015-09-11 | 2015-09-21 | I.F. BLANCOS CONSTRUCTION
3442 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110472 | Panaytayan ES | MANSALAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0314S00013 | 14EIE024 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3443 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110383 | Panluan ES | BONGABONG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 4B0314S00060 | 14EI0084 | 2014-11-13 | 2014-11-14 | 2014-11-26 | 2014-12-12 | 2015-01-05 | ADL GENERAL CONSTRUCTION
3444 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301647 | Pili NHS | PINAMALAYAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8644965.051 |  |  | COMPLETED | 1 | 2016-03-13 |  | 4B0314S00103 | 15EI0074 | 2015-08-12 | 2015-08-13 | 2015-09-01 | 2015-09-11 | 2015-09-21 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3445 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 309026 | Pili NHS - Buli Ext. | PINAMALAYAN | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4572048.49 |  |  | COMPLETED | 1 | 2016-02-21 |  | 4B0314S00075 | 15EI0082 | 2015-08-18 | 2015-08-19 | 2015-09-01 | 2015-09-21 | 2015-09-30 | A.D.L. CONSTRAK
3446 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 309002 | President Diosdado Macapagal Memorial NAtional HIgh School | GLORIA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1
3447 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 309002 | President Diosdado Macapagal MNHS | GLORIA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1
3448 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110405 | Pulosahi ES | BONGABONG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 4B0314S00061 | 14EIE013 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3449 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 301649 | Quinabigan NHS | PINAMALAYAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1
3450 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301649 | Quinabigan NHS | PINAMALAYAN | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10577131.51 |  | 10521638.86 | COMPLETED | 1
3451 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110473 | Quinonay PS | MANSALAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-12-20 | 2015-12-15 | 4B0314S00012 | 14EIE025 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3452 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110565 | Ranzo ES | PINAMALAYAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 4B0314S00007 | 14EI0092 | 2014-11-13 | 2014-11-14 | 2014-11-26 | 2014-12-12 | 2015-01-05 | LUMEL GLENN CONSTRUCTION
3453 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110639 | Raymundo Escarez MS | ROXAS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0314S00002 | 14EIE019 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3454 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110566 | Rosario ES | PINAMALAYAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0314S00006 | 14EIE002 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | KINGs BUILDERS & DEVELOPMENT CORPORATION
3455 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110583 | Safa ES (Minority-Sabang) | PINAMALAYAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 4B0314S00004 | 14EIE001 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | KINGs BUILDERS & DEVELOPMENT CORPORATION
3456 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 170001 | Salay ES | MANSALAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 4B0314S00028 | 14EI030 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3457 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110642 | San Jose Elementary School | ROXAS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 4B0314S00011 | 14EIE020 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3458 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 301652 | San Mariano NHS | ROXAS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1
3459 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301652 | San Mariano NHS | ROXAS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
3460 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110428 | San Miguel ES | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-19 | 4B0314S00059 | 14EIE035 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3461 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301622 | San Roque NHS | BULALACAO (SAN PEDRO) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 | 2016-03-06 |  | 4B0314S00122 | 15EI0060 | 2015-08-11 | 2015-08-13 | 2015-08-26 | 2015-09-04 | 2015-09-21 | A.D.L. CONSTRAK
3462 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 309032 | San Roque NHS - Bangkal Ext. | BULALACAO (SAN PEDRO) | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2015-05-12 | 2015-05-12 | 4B0314S00023 | 14EI0086 | 2014-11-13 | 2014-11-14 | 2014-11-26 | 2014-12-12 | 2015-01-05 | LUMEL GLENN CONSTRUCTION
3463 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110476 | Sinariri ES | MANSALAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | REVERTED | 0 | 2015-12-20 |  | 4B0314S00016 | 14EIE026 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION | Contract Terminated. No access road for the 10km. distance to the project site, hence, making it technically impossible to implement the project.
3464 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110455 | Tambong ES | GLORIA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-03-13 | 2015-03-13 | 4B0314S00019 | 14EI0090 | 2014-11-13 | 2014-11-14 | 2014-11-26 | 2014-12-12 | 2015-01-05 | ALBERTO UY CONSTRUCTION & DEVELOPMENT
3465 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110480 | Teresita ES | MANSALAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 4B0314S00009 | 14EIE028 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3466 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 170037 | Umabang Elementary School | BULALACAO (SAN PEDRO) | 2 | 1 | 5 | 1STY5CL (Toilet Attached) | 2014 K10 BATCH 4C | 4673636.82 |  |  | Terminated | 0 | 2016-02-29 |  | 4B0314S00139 | 15EI0097 | 2015-09-10 | 2015-09-17 | 2015-09-30 | 2015-10-14 | 2015-10-26 | LUMEL GLENN CONSTRUCTION | Contract Terminated. No access road for the 10km. distance to the project site, hence, making it technically impossible to implement the project.
3467 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 301654 | Vicente B. Ylagan NHS | BONGABONG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2035417.57 |  |  | COMPLETED | 1
3468 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301654 | Vicente B. Ylagan NHS | BONGABONG | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1
3469 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110400 | Villa Gertrudes I. Enriquez MES | BONGABONG | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-21 |  | 4B0314S00138 | 15EI0081 | 2015-08-18 | 2015-08-20 | 2015-09-01 | 2015-09-21 | 2015-09-30 | A.D.L. CONSTRAK
3470 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 301655 | Villapagasa NHS | BANSUD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1
3471 | NC 2014 | SHS (2014) | Region IV-B | Oriental Mindoro | 301655 | Villapagasa NHS | BANSUD | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1
3472 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 170019 | Wawa ES | PINAMALAYAN | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4572048.49 |  |  | REVERTED | 0 | 2016-02-21 |  | 4B0314S00074 | 15EI0083 | 2015-08-18 | 2015-08-19 | 2015-08-31 | 2015-09-21 | 2015-09-30 | LUMEL GLENN CONSTRUCTION | Contract Terminated. Limited access to transport materials to the project site. Futher per re-assestment the project site, school site is near the marine zone, hence, considered a no build zone.
3473 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110483 | Waygan ES | MANSALAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 4B0314S00008 | 14EIE029 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3474 | NC 2014 | K10 (2014) | Region IV-B | Oriental Mindoro | 110430 | Yunot ES (Hanunuo) | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-19 | 4B0314S00066 | 14EIE031 | 2014-12-04 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-06 | LUMEL GLENN CONSTRUCTION
3475 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111206 | Alacalian ES | TAYTAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1827535 |  |  | COMPLETED | 1 | 2015-04-10 | 2015-04-10 | 4B0414S00188 | 14EE0088 | 2014-11-19 | 2014-11-20 | 2014-12-05 | 2014-12-18 | 2014-12-29 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3476 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111040 | Alcoba ES | MAGSAYSAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-29 | 4B0414S00116 | 14EE0039 | 2014-09-01 | 2014-09-02 | 2014-09-15 | 2014-09-24 | 2014-10-08 | JQM CONSTRUCTION AND TRADING
3477 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 301660 | Alimanguan NHS | SAN VICENTE | 1 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3142746.69 |  |  | COMPLETED | 1
3478 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301662 | Araceli NHS | ARACELI | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2016-03-09 |  | 4B0414S00273 | 15EE0044 | 2015-08-20 | 2015-08-24 | 2015-08-24 | 2015-09-09 | 2015-09-25 | SEVEN DIGIT CONSTRUCTION & SUPPLIES
3479 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111014 | Bagong Bayan ES | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2014-12-17 | 2015-01-08 | 4B0414S00022 | 14EE0044 | 2014-09-04 | 2014-09-05 | 2014-09-17 | 2014-09-30 | 2014-10-13 | A.P. CONSEBIDO CONSTRUCTION AND TRADING
3480 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110972 | Balisungan ES | CORON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-29 | 4B0414S00023 | 14EE0038 | 2014-08-28 | 2014-08-29 | 2014-09-10 | 2014-09-22 | 2014-10-07 | JQM CONSTRUCTION AND TRADING
3481 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111208 | Bantulan ES | TAYTAY | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2652787.3721 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-06 | 4B0414S00121 | 14EE0061 | 2014-10-22 | 2014-11-06 | 2014-11-14 | 2014-11-17 | 2014-11-28 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3482 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110973 | Banuang Daan ES | CORON | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-29 | 4B0414S00035 | 14EE0038 | 2014-08-28 | 2014-08-29 | 2014-09-10 | 2014-09-22 | 2014-10-07 | JQM CONSTRUCTION AND TRADING
3483 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111209 | Baras ES | TAYTAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1645431.19 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4B0414S00187 | 14EE0087 | 2014-11-19 | 2014-11-20 | 2014-12-05 | 2014-12-18 | 2014-12-29 | E.C. TIMBANCAYA ENTERPRISES
3484 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301667 | Barotuan NHS | EL NIDO (BACUIT) | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
3485 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111210 | Batas ES | TAYTAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1827534.9184 |  |  | COMPLETED | 1 | 2015-03-03 | 2015-03-18 | 4B0414S00159 | 14EE0060 | 2014-10-22 | 2014-10-23 | 2014-11-04 | 2014-11-17 | 2014-11-28 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3486 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301669 | Bato NHS | TAYTAY | 1 | 1 | 12 | 3STY12CL | 2014 SHS BATCH 1 | 18222268.79 |  |  | COMPLETED | 1 |  |  | 4B0414S00268 | 15EE0113 | 2015-12-15 | 2015-12-03 | 2015-12-15 | 2015-12-22 |  | E.V. VILLAOS TRADING & CONSTRUCTION
3487 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170526 | Binaluan PS | TAYTAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-04-02 | 2015-04-02 | 4B0414S00126 | 14EE0059 | 2014-10-22 | 2014-10-23 | 2014-11-04 | 2014-11-17 | 2014-11-28 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3488 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111212 | Binuan ES | TAYTAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-01-15 | 4B0414S00034 | 14EE0041 | 2014-10-02 | 2014-10-03 | 2014-10-20 | 2014-10-24 | 2014-11-06 | LEA & SONS TRADING AND CONSTRUCTION
3489 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111213 | Biton ES | TAYTAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1
3490 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110927 | Bogtong ES | BUSUANGA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-29 | 4B0414S00031 | 14EE0037 | 2014-08-28 | 2014-08-29 | 2014-09-10 | 2014-09-22 | 2014-10-07 | JQM CONSTRUCTION AND TRADING
3491 | NC 2014 | K10 (2014) | Region IV-B | PALAWAN | 110976 | Borac ES | CORON | 1 | 1 | 4 | 1STY3CL, 1STY1CL | 2014 K10 BATCH 2 | 3678000 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-03-17 | 4B0414S00209 | 14EE0062 | 2014-10-22 | 2014-10-23 | 2014-11-04 | 2014-11-17 | 2014-11-28 | JQM CONSTRUCTION AND TRADING
3492 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301685 | Borac National High School | CORON | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 4B0414S00269 | 15EE0030 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-08-25 | 2015-09-07 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY (FORMERLY:
3493 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111017 | Bucana ES | EL NIDO (BACUIT) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4B0414S00198 | 14EE0085 | 2014-11-19 | 2014-11-20 | 2014-12-04 | 2014-12-18 | 2014-12-29 | YURICH BUILDERS AND CONSTRUCTION SUPPLY
3494 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110978 | Bulalacao ES | CORON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1082329.43 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4B0414S00201 | 14EE0086 | 2014-11-19 | 2014-11-20 | 2014-12-05 | 2014-12-18 | 2014-12-29 | JQM CONSTRUCTION AND TRADING
3495 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111215 | Busy Bees ES | TAYTAY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2014-12-17 | 2015-01-09 | 4B0414S00073 | 14EE0046 | 2014-09-04 | 2014-09-05 | 2014-09-17 | 2014-09-30 | 2014-10-13 | VCH CONSTRUCTION AND TRADING
3496 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110964 | Cagayancillo CS | CAGAYANCILLO | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-04-10 |  | 4B0414S00299 | 15EE0050 | 2015-10-29 | 2015-10-30 | 2015-11-13 | 2015-11-20 | 2015-11-26 | E.V. VILLAOS TRADING & CONSTRUCTION
3497 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301677 | Cagayancillo NHS | CAGAYANCILLO | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 4B0414S00270 | 15EE0112 | 2015-12-01 | 2015-12-02 | 2015-12-15 | 2015-12-22
3498 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301678 | Calandagan NHS | ARACELI | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4B0414S00255 | 15EE0049 | 2015-12-02 | 2015-12-03 | 2015-12-15 | 2015-12-22 |  | KUDZ TRADING & CONSTRUCTION SUPPLY
3499 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170533 | Calawit PS | BUSUANGA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2015-03-18 | 4B0414S00069 | 14EE0036 | 2014-08-29 | 2014-08-29 | 2014-09-10 | 2014-09-22 | 2014-10-07 | JQM CONSTRUCTION AND TRADING
3500 | NC 2014 | K10 (2014) | Region IV-B | PALAWAN | 110980 | Canipo ES | CORON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1164275 |  |  | COMPLETED | 1
3501 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 301682 | Casian NHS | TAYTAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1827534.9184 |  |  | COMPLETED | 1
3502 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301682 | Casian NHS | TAYTAY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
3503 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 309103 | Central Taytay NHS | TAYTAY | 1 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1 | 2016-03-11 |  | 4B0414S00254 | 15EE0040 | 2015-07-31 | 2015-08-04 | 2015-08-20 | 2015-08-28 | 2015-09-08 | SEVEN DIGIT CONSTRUCTION & SUPPLIES
3504 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170570 | Ching Bing Kao ES | TAYTAY | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 |  |  | 4B0414S00298 | 15EE0052 | 2015-12-02 | 2015-12-03 | 2015-12-15 | 2015-12-21 | 2015-12-28 | A.P. CONSEBIDO CONSTRUCTION AND TRADING
3505 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110981 | Claudio Sandoval ES | CORON | 1 | 1 | 5 | 1STY 3CL & 1STY 2CL | 2014 K10 BATCH 1 | 4920591.69 |  |  | COMPLETED | 1
3506 | NC 2014 | K10 (2014) | Region IV-B | PALAWAN | 110981 | Claudio Sandoval ES | CORON | 1 | 1 | 5 | 1STY4CL, 1STY1CL | 2014 K10 BATCH 2 | 4498000 |  |  | COMPLETED | 1
3507 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301687 | Culion Sanitarium Special NHS | CULION | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
3508 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111002 | Cuyo Miller School | CUYO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737516.0082 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 4B0414S00181 | 14EE0112 | 2014-12-10 | 2014-12-11 | 2015-01-05 | 2015-01-16 | 2015-01-22 | YURICH BUILDERS AND CONSTRUCTION SUPPLY
3509 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301688 | Cuyo NHS | CUYO | 1 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 4B0414S00271 | 15EE0045 | 2015-12-02 | 2015-12-03 | 2015-12-15 | 2015-12-22
3510 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111188 | Decala ES | SAN VICENTE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-01-15 | 4B0414S00015 | 14EE0040 | 2014-10-02 | 2014-10-03 | 2014-10-20 | 2014-10-24 | 2014-11-06 | LEA & SONS TRADING AND CONSTRUCTION
3511 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111022 | Diapila ES | EL NIDO (BACUIT) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 949756.43 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4B0414S00200 | 14EE0086 | 2014-11-19 | 2014-11-20 | 2014-12-05 | 2014-12-18 | 2014-12-29 | JQM CONSTRUCTION AND TRADING
3512 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170541 | Dinet ES | TAYTAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-29 | 4B0414S00070 | 14EE0042 | 2014-09-01 | 2014-09-02 | 2014-09-15 | 2014-09-24 | 2014-10-08 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3513 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111227 | Dipla ES | TAYTAY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-01-14 | 4B0414S00064 | 14EE0041 | 2014-10-02 | 2014-10-03 | 2014-10-20 | 2014-10-24 | 2014-11-06 | LEA & SONS TRADING AND CONSTRUCTION
3514 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301691 | Dumaran NHS | DUMARAN | 1 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1 | 2016-04-05 |  | 4B0414S00260 | 15EE0041 | 2015-07-31 | 2015-08-04 | 2015-09-14 | 2015-09-21 | 2015-10-02 | A.C. RIVERO DEVELOPMENT CORPORATION
3515 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301693 | El Nido NHS | EL NIDO (BACUIT) | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2016-04-09 |  | 4B0414S00259 | 15EE0035 | 2015-09-23 | 2015-09-24 | 2015-10-06 | 2015-10-12 | 2015-10-26 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY (FORMERLY:
3516 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301698 | Gaudencio Abordo Mem. NHS - Rizal NHS | MAGSAYSAY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-08 |  | 4B0414S00258 | 15EE0043 | 2015-08-20 | 2015-08-24 | 2015-09-04 | 2015-09-14 | 2015-09-25 | E.V. VILLAOS TRADING & CONSTRUCTION
3517 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301695 | Gaudencio E. Abordo Mem. NHS | AGUTAYA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 4B0414S00257 | 15EE0047 | 2015-12-02 | 2015-12-03 | 2015-12-15 | 2015-12-22 |  | 12-30 CONSTRUCTION AND SUPPLY
3518 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111146 | Green Island ES | ROXAS | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-29 | 4B0414S00115 | 14EE0039 | 2014-09-01 | 2014-09-02 | 2014-09-15 | 2014-09-24 | 2014-10-08 | JQM CONSTRUCTION AND TRADING
3519 | NC 2014 | K10 (2014) | Region IV-B | PALAWAN | 110985 | Guadalupe ES | CORON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1025000 |  |  | COMPLETED | 1 | 2015-04-17 | 2015-04-17 | 4B0414S00143 | 14EE0064 | 2014-10-22 | 2014-10-23 | 2014-11-04 | 2014-11-17 | 2014-11-28 | JQM CONSTRUCTION AND TRADING
3520 | NC 2014 | K10 (2014) | Region IV-B | PALAWAN | 110942 | Halsey ES | CULION | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1238393.169 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-02-19 | 4B0414S00141 | 14EE0062 | 2014-10-22 | 2014-10-23 | 2014-11-04 | 2014-11-17 | 2014-11-28 | JQM CONSTRUCTION AND TRADING
3521 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111219 | Judge Cesar L. Rodriguez Elementary School | TAYTAY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2088606.04 |  |  | COMPLETED | 1 | 2016-02-23 |  | 4B0414S00297 | 15EE0053 | 2015-10-22 | 2015-10-23 | 2015-11-05 | 2015-11-12 | 2015-11-24 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3522 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110986 | Lajala ES | CORON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2015-03-17 | 4B0414S00038 | 14EE0037 | 2014-08-28 | 2014-08-29 | 2014-09-10 | 2014-09-22 | 2014-10-07 | JQM CONSTRUCTION AND TRADING
3523 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 309123 | Liminangcong NHS - San Jose Ext. | TAYTAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-05-07 | 4B0414S00128 | 14EE0061 | 2014-10-22 | 2014-10-23 | 2014-11-04 | 2014-11-17 | 2014-11-28 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3524 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111151 | Little Caramay ES | ROXAS | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990418 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4B0414S00196 | 14EE0081 | 2014-11-19 | 2014-11-20 | 2014-12-04 | 2014-12-18 | 2014-12-29 | 12-30 CONSTRUCTION AND SUPPLY
3525 | NC 2014 | K10 (2014) | Region IV-B | PALAWAN | 110944 | Luac ES | CULION | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1184786.8347 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-02-19 | 4B0414S00130 | 14EE0062 | 2014-10-22 | 2014-10-23 | 2014-11-04 | 2014-11-17 | 2014-11-28 | JQM CONSTRUCTION AND TRADING
3526 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111004 | Lubid ES | CUYO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2529405.2357 |  |  | COMPLETED | 1 | 2015-05-05 | 2015-05-05 | 4B0414S00184 | 14EE0110 | 2014-12-10 | 2014-12-11 | 2015-01-05 | 2015-01-16 | 2015-01-22 | YURICH BUILDERS AND CONSTRUCTION SUPPLY
3527 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110772 | Madoldolon ES | ARACELI | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-29 | 4B0414S00030 | 14EE0039 | 2014-10-02 | 2014-10-03 | 2014-10-20 | 2014-10-24 | 2014-11-06 | JQM CONSTRUCTION AND TRADING
3528 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301705 | Magara School for Philippine Crafstmen | ROXAS | 1 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1
3529 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110988 | Malbato ES | CORON | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-01-21 | 2015-01-21 | 4B0414S00039 | 14EE0036 | 2014-08-28 | 2014-08-29 | 2014-09-10 | 2014-09-22 | 2014-10-07 | JQM CONSTRUCTION AND TRADING
3530 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301708 | Manamoc NHS | CUYO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 4B0414S00263 | 15EE0046 | 2015-12-02 | 2015-12-03 | 2015-12-15 | 2015-12-22
3531 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111155 | Maragoc ES | ROXAS | 1 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 2 | 2852392.8467 |  |  | COMPLETED | 1 | 2015-06-07 | 2015-05-18 | 4B0414S00122 | 14EE0089 | 2014-11-19 | 2014-11-20 | 2014-12-05 | 2014-12-18 | 2014-12-29 | YURICH BUILDERS AND CONSTRUCTION SUPPLY
3532 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111006 | Maringian ES | CUYO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2529405.2357 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-06 | 4B0414S00183 | 14EE0113 | 2014-12-10 | 2014-12-11 | 2015-01-05 | 2015-01-16 | 2015-01-22 | YURICH BUILDERS AND CONSTRUCTION SUPPLY
3533 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111234 | Maytegued ES | TAYTAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-05-18 | 2015-06-04 | 4B0414S00194 | 14EE0083 | 2014-11-19 | 2014-11-20 | 2014-12-04 | 2014-12-18 | 2014-12-29 | E.C. TIMBANCAYA ENTERPRISES
3534 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110949 | Nangalao ES | LINAPACAN | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2940174.43 |  |  | COMPLETED | 1 | 2015-05-18 | 2015-06-22 | 4B0414S00202 | 14EE0083 | 2014-11-19 | 2014-11-20 | 2014-12-04 | 2014-12-18 | 2014-12-29 | E.C. TIMBANCAYA ENTERPRISES
3535 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301711 | New Busuanga NHS | BUSUANGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 4B0414S00261 | 15EE0031 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-08-25 | 2015-09-07 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY (FORMERLY:
3536 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111195 | New Caruray ES | SAN VICENTE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 854756.43 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4B0414S00195 | 14EE0081 | 2014-11-19 | 2014-11-20 | 2014-12-04 | 2014-12-17 | 2014-12-29 | 12-30 CONSTRUCTION AND SUPPLY
3537 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111236 | New Guinlo ES | TAYTAY | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 | 2014-12-12 | 2015-01-07 | 4B0414S00066 | 14EE0042 | 2014-09-01 | 2014-09-02 | 2014-09-15 | 2014-09-24 | 2014-10-08 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3538 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111003 | P.A.B.N. Funda ES | CUYO | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3316362.1241 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 4B0414S00178 | 14EE0109 | 2014-12-10 | 2014-12-11 | 2015-01-05 | 2015-01-16 | 2015-01-22 | 12-30 CONSTRUCTION AND SUPPLY
3539 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111238 | Pag-asa PS | TAYTAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-04-02 | 2015-04-02 | 4B0414S00125 | 14EE0059 | 2014-10-22 | 2014-10-23 | 2014-11-04 | 2014-11-17 | 2014-11-28 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3540 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111240 | Paly ES | TAYTAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1827535 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4B0414S00186 | 14EE0087 | 2014-11-19 | 2014-11-20 | 2014-12-05 | 2014-12-18 | 2014-12-29 | E.C. TIMBANCAYA ENTERPRISES
3541 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111199 | Panindigan ES | SAN VICENTE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4B0414S00014 | 14EE0082 | 2014-11-19 | 2014-11-20 | 2014-12-04 | 2014-12-18 | 2014-12-29 | YURICH BUILDERS AND CONSTRUCTION SUPPLY
3542 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111010 | Pawa ES | CUYO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969134.5147 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 4B0414S00182 | 14EE0114 | 2014-12-10 | 2014-12-11 | 2015-01-05 | 2015-01-16 | 2015-01-22 | KUDZ TRADING & CONSTRUCTION SUPPLY
3543 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110956 | Pical ES | LINAPACAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-12-17 | 2015-01-13 | 4B0414S00043 | 14EE0043 | 2014-09-04 | 2014-09-05 | 2014-09-17 | 2014-09-30 | 2014-10-13 | GABARDA CONSTRUCTION
3544 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301731 | ROXAS NATIONAL COMPREHENSIVE HIGH SCHOOL | ROXAS | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10927342.5917 |  |  | COMPLETED | 1 | 2016-05-29 |  | 4B0414S00278 | 15EE0033 | 2015-11-15 | 2015-11-16 | 2015-12-01 | 2015-12-08 | 2015-12-15 | A.P. CONSEBIDO CONSTRUCTION AND TRADING
3545 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111164 | Roxas North CS | ROXAS | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1827534.9184 |  |  | COMPLETED | 1 | 2015-03-03 | 2015-03-03 | 4B0414S00123 | 14EE0059 | 2014-10-22 | 2014-10-23 | 2014-11-04 | 2014-11-18 | 2014-11-28 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3546 | NC 2014 | K10 (2014) | Region IV-B | PALAWAN | 301734 | Salvacion NHS | BUSUANGA | 1 | 1 | 4 | 1STY3CL, 1STY1CL | 2014 K10 BATCH 2 | 3796645.4025 |  |  | COMPLETED | 1
3547 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301734 | Salvacion NHS | BUSUANGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
3548 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111011 | San Carlos ES | CUYO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2529405.2357 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 4B0414S00180 | 14EE0111 | 2014-12-10 | 2014-12-11 | 2015-01-05 | 2015-01-16 | 2015-01-22 | YURICH BUILDERS AND CONSTRUCTION SUPPLY
3549 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 301735 | San Carlos NHS | CUYO | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-08 |  | 4B0414S00288 | 15EE0051 | 2015-08-20 | 2015-08-24 | 2015-09-08 | 2015-09-22 | 2015-10-05 | E.V. VILLAOS TRADING & CONSTRUCTION
3550 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111034 | San Fernando ES | EL NIDO (BACUIT) | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2014-12-17 | 2015-01-07 | 4B0414S00018 | 14EE0044 | 2014-09-04 | 2014-09-05 | 2014-09-17 | 2014-09-30 | 2014-10-13 | A.P. CONSEBIDO CONSTRUCTION AND TRADING
3551 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301732 | San Jose (Roxas) NHS | ROXAS | 1 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1
3552 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110991 | San Jose ES | CORON | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4B0414S00040 | 14EE0086 | 2014-11-19 | 2014-11-20 | 2014-12-05 | 2014-12-18 | 2014-12-29 | JQM CONSTRUCTION AND TRADING
3553 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301737 | San Miguel NHS (Gaudencio Abordo NHS) | LINAPACAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
3554 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301738 | San Vicente NHS | SAN VICENTE | 1 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1 | 2016-03-11 |  | 4B0414S00283 | 15EE0039 | 2015-07-31 | 2015-08-04 | 2015-08-20 | 2015-08-28 | 2015-09-08 | SEVEN DIGIT CONSTRUCTION & SUPPLIES
3555 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111172 | Sandoval ES | ROXAS | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-01-13 | 4B0414S00114 | 14EE0041 | 2014-09-01 | 2014-09-02 | 2014-09-15 | 2014-09-24 | 2014-10-08 | LEA & SONS TRADING AND CONSTRUCTION
3556 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 301683 | Sandoval NHS (Casian NHS - Sandoval Annex) | TAYTAY | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2890174.43 |  |  | COMPLETED | 1
3557 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 301740 | Santa Teresita NHS | DUMARAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
3558 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301740 | Santa Teresita NHS | DUMARAN | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
3559 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110993 | Sta. Monica ES | CORON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-29 | 4B0414S00011 | 14EE0038 | 2014-08-28 | 2014-08-29 | 2014-09-10 | 2014-09-22 | 2014-10-07 | JQM CONSTRUCTION AND TRADING
3560 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110994 | Tagum ES | CORON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-29 | 4B0414S00042 | 14EE0037 | 2014-08-28 | 2014-08-29 | 2014-09-10 | 2014-09-22 | 2014-10-07 | JQM CONSTRUCTION AND TRADING
3561 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110995 | Tagumpay ES | CORON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
3562 | NC 2014 | K10 (2014) | Region IV-B | PALAWAN | 110995 | Tagumpay ES | CORON | 1 | 1 | 7 | 2U-1STY3CL, 1STY1CL | 2014 K10 BATCH 2 | 6538340.0272 |  |  | COMPLETED | 1
3563 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111249 | Talog ES | TAYTAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-17 | 2015-01-06 | 4B0414S00041 | 14EE0045 | 2014-09-04 | 2014-09-05 | 2014-09-17 | 2014-09-30 | 2014-10-13 | A.P. CONSEBIDO CONSTRUCTION AND TRADING
3564 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110996 | Tara ES | CORON | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-04-08 | 4B0414S00013 | 14EE0084 | 2014-11-19 | 2014-11-20 | 2014-12-04 | 2014-12-18 | 2014-12-29 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3565 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111036 | Teneguiban ES | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1985418 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-08-12 | 4B0414S00193 | 14EE0085 | 2014-11-19 | 2014-11-20 | 2014-12-04 | 2014-12-18 | 2014-12-29 | YURICH BUILDERS AND CONSTRUCTION SUPPLY
3566 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170566 | Trinidad Cario PS | ROXAS | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4B0414S00197 | 14EE0081 | 2014-11-19 | 2014-11-20 | 2014-12-04 | 2014-12-18 | 2014-12-29 | 12-30 CONSTRUCTION AND SUPPLY
3567 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111251 | Tulduan PS | TAYTAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.84 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4B0414S00189 | 14EE0088 | 2014-11-19 | 2014-11-20 | 2014-12-05 | 2014-12-18 | 2014-12-29 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3568 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111252 | Tumbod ES | TAYTAY | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2014-12-17 | 2015-01-09 | 4B0414S00068 | 14EE0045 | 2014-09-04 | 2014-09-05 | 2014-09-17 | 2014-09-30 | 2014-10-13 | A.P. CONSEBIDO CONSTRUCTION AND TRADING
3569 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111038 | Villa Paz ES | EL NIDO (BACUIT) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
3570 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301657 | Abo-Abo NHS | SOFRONIO ESPAÑOLA | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
3571 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 301659 | Aborlan NHS | ABORLAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1
3572 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301659 | Aborlan NHS | ABORLAN | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
3573 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111090 | Alfonso XIII ES (Bliss ES) | QUEZON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-07-11 | 2015-08-05 | 4B0414S00158 | 14EF0079 | 2014-11-04 | 2014-11-06 | 2015-04-14 | 2015-04-23 | 2015-05-06 | 12-30 CONSTRUCTION AND SUPPLY
3574 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110862 | Amas ES | BROOKE'S POINT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 4B0414S00054 | 14EF0036 | 2014-08-25 | 2014-08-29 | 2014-09-10 | 2014-09-24 | 2014-10-08 | 12-30 CONSTRUCTION AND SUPPLY
3575 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110714 | Apo-aporawan ES | ABORLAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-11-27 | 4B0414S00071 | 14EG0005 | 2014-05-13 | 2014-05-22 | 2014-06-03 | 2014-08-06 | 2014-08-14 | SAMURAI CONSTRUCTION
3576 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301661 | Apurawan NHS | ABORLAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 4B0414S00279 | 15EG0031 | 2015-07-24 | 2015-07-31 | 2015-08-12 | 2015-08-20 | 2015-09-01 | E.C. TIMBANCAYA ENTERPRISES
3577 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 301663 | Aramaywan NHS | NARRA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | REVERTED | 0
3578 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110863 | Aribungos ES | BROOKE'S POINT | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1
3579 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301666 | Balabac NHS | BALABAC | 2 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1 | 2016-06-12 |  | 4B0414S00272 | 15EF0162 | 2015-10-27 | 2015-10-29 | 2015-11-11 | 2015-11-24 | 2015-12-09 | NURBEN ENGINEERING AND BUILDING CONTRACTOR
3580 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111087 | Balite ES | RIZAL (MARCOS) | 2 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 4025835.14 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-02-26 | 4B0414S00024 | 14EF0044 | 2014-08-25 | 2014-08-29 | 2014-09-12 | 2014-09-24 | 2014-10-08 | R.C. TAGALA CONSTRUCTION
3581 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170501 | Barakbarakan ES | BATARAZA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 4B0414S00167 | 14EF0077 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | CRISHELLE CONSTRUCTION
3582 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111056 | Batang-Batang Beach ES | NARRA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 4B0414S00169 | 14EF0081 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | 12-30 CONSTRUCTION AND SUPPLY
3583 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111057 | Batang-Batang Proper ES | NARRA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-13 | 2014-12-13 | 4B0414S00025 | 14EF0040 | 2014-08-25 | 2014-08-29 | 2014-09-11 | 2014-09-24 | 2014-10-08 | PTK GROUP INC.
3584 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110825 | Bataraza CS | BATARAZA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-03-29 | 2015-03-29 | 4B0414S00157 | 14EF0093 | 2014-11-17 | 2014-11-20 | 2014-11-02 | 2014-12-10 | 2014-12-23 | CRISHELLE CONSTRUCTION
3585 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301668 | Bataraza NHS | BATARAZA | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2016-04-24 |  | 4B0414S00277 | 15EF0085 | 2015-07-20 | 2015-07-21 | 2015-10-12 | 2015-11-11 | 2015-11-20 | IVY MICHELLE TRADING & CONTRUCTION
3586 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110865 | Bayog ES | BROOKE'S POINT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-07-11 | 2015-08-05 | 4B0414S00132 | 14EF0078 | 2014-11-04 | 2014-11-06 | 2015-04-14 | 2015-04-23 | 2015-05-06 | 12-30 CONSTRUCTION AND SUPPLY
3587 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110826 | Bono-Bono ES | BATARAZA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 4B0414S00057 | 14EF0033 | 2014-08-25 | 2014-08-29 | 2014-09-10 | 2014-09-24 | 2014-10-08 | 12-30 CONSTRUCTION AND SUPPLY
3588 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301671 | Brooke's Point NHS - Pangobilian NHS | BROOKE'S POINT | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2016-04-24 |  | 4B0414S00287 | 15EF0086 | 2015-07-20 | 2015-07-21 | 2015-10-12 | 2015-11-11 | 2015-11-20 | UGM CONSTRUCTION
3589 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 309113 | Bugsuk NHS - Bancalaan Annex | BALABAC | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2016-04-24 |  | 4B0414S00276 | 15EF0087 | 2015-07-20 | 2015-07-21 | 2015-10-12 | 2015-11-11 | 2015-11-20 | R.C. TAGALA CONSTRUCTION
3590 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301674 | Bugsuk NHS - Mangsee Annex | BALABAC | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | REVERTED | 0 |  |  | 4B0414S00275 | 15EF0093 | 2015-07-20 | 2015-07-21 | 2015-10-21
3591 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170544 | Bulno PS | RIZAL (MARCOS) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 4B0414S00165 | 14EF0080 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | 12-30 CONSTRUCTION AND SUPPLY
3592 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111091 | Bunog ES | RIZAL (MARCOS) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-02-26 | 4B0414S00108 | 14EF0044 | 2014-08-25 | 2014-08-29 | 2014-09-12 | 2014-09-24 | 2014-10-08 | R.C. TAGALA CONSTRUCTION
3593 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110868 | Cabangaan PS | BROOKE'S POINT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-07-11 | 2015-08-05 | 4B0414S00155 | 14EF0078 | 2014-11-04 | 2014-11-06 | 2015-04-14 | 2015-04-23 | 2015-05-06 | 12-30 CONSTRUCTION AND SUPPLY
3594 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110869 | Cabar ES | BROOKE'S POINT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 4B0414S00078 | 14EF0037 | 2014-08-25 | 2014-08-29 | 2014-09-11 | 2014-09-24 | 2014-10-08 | PTK GROUP INC.
3595 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110719 | Cabigaan ES | ABORLAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-11-27 | 4B0414S00049 | 14EG0005 | 2014-05-13 | 2014-05-23 | 2014-06-03 | 2014-08-06 | 2014-08-14 | SAMURAI CONSTRUCTION
3596 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111093 | Cadawan PS | RIZAL (MARCOS) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 4B0414S00162 | 14EF0080 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | 12-30 CONSTRUCTION AND SUPPLY
3597 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110797 | Calogcog ES | BALABAC | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-04-17 | 2015-04-17 | 4B0414S00051 | 14EF0076 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | E.V. VILLAOS TRADING & CONSTRUCTION | Contract Terminated. Limited access to transport materials to the project site. Futher per re-assestment the project site, school site is near the marine zone, hence, considered a no build zone.
3598 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111095 | Campong-Ulay ES | RIZAL (MARCOS) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.19 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 4B0414S00106 | 14EF0094 | 2014-11-17 | 2014-11-20 | 2014-12-02 | 2014-12-10 | 2014-12-23 | CRISHELLE CONSTRUCTION
3599 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301680 | Candawaga NHS | RIZAL (MARCOS) | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2016-04-24 |  | 4B0414S00274 | 15EF0088 | 2015-07-20 | 2015-07-21 | 2015-10-12 | 2015-11-11 | 2015-11-20 | J.N. DELA TORRE CONSTRUCTION
3600 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111098 | Culasian ES (New) | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-02-11 | 2015-02-11 | 4B0414S00102 | 14EF0045 | 2014-08-25 | 2014-08-29 | 2014-09-12 | 2014-09-24 | 2014-10-08 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3601 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170574 | Cumahos ES | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.5 |  |  | COMPLETED | 1
3602 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170574 | Cumahos ES | RIZAL (MARCOS) | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | [10 empty] | To Confirm, Completed but w/ remarks abandoned
3603 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110901 | Eniaran ES | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-03 | 4B0414S00017 | 14EF0038 | 2014-08-25 | 2014-08-29 | 2014-09-11 | 2014-09-24 | 2014-10-08 | J.N. DELA TORRE CONSTRUCTION
3604 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301699 | Gov. Alfredo Abueg MHS | BROOKE'S POINT | 2 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1 | 2016-05-27 |  | 4B0414S00266 | 15EF0123 | 2015-10-06 | 2015-10-07 | 2015-10-20 | 2015-11-10 | 2015-11-23 | UGM CONSTRUCTION
3605 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170572 | Gugnan PS | QUEZON | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-03-25 |  | 4B0414S00302 | 15EF0125 | 2015-10-06 | 2015-10-07 | 2015-10-20 | 2015-11-11 | 2015-11-25 | CRISHELLE CONSTRUCTION
3606 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111101 | Guilingan ES | RIZAL (MARCOS) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-02-16 | 4B0414S00163 | 14EF0080 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | 12-30 CONSTRUCTION AND SUPPLY
3607 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110832 | Igang-Igang ES | BATARAZA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 4B0414S00059 | 14EF0034 | 2014-08-25 | 2014-08-29 | 2014-09-10 | 2014-09-24 | 2014-10-08 | PTK GROUP INC.
3608 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110800 | Indalawan ES | BALABAC | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 | 2015-04-17 | 2015-04-17 | 4B0414S00062 | 14EF0076 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | E.V. VILLAOS TRADING & CONSTRUCTION
3609 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 301702 | J. P. Rizal NHS | RIZAL (MARCOS) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1
3610 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301702 | J. P. Rizal NHS | RIZAL (MARCOS) | 2 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1
3611 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111103 | Kalatabog ES | QUEZON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-07-11 | 2015-08-05 | 4B0414S00149 | 14EF0079 | 2014-11-04 | 2014-11-06 | 2015-04-14 | 2015-04-23 | 2015-05-06 | 12-30 CONSTRUCTION AND SUPPLY
3612 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110834 | Katipunan ES | BATARAZA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2016-04-13 |  | 4B0414S00139 | 15EF0097 | 2015-07-20 | 2015-07-21 | 2015-10-29 | 2015-11-25 | 2015-12-09 | JB & SONS TRADING & CONSTRUCTION | Abandoned
3613 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110905 | Labog ES | SOFRONIO ESPAÑOLA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-12 | 4B0414S00028 | 14EF0038 | 2014-08-25 | 2014-08-29 | 2014-09-11 | 2014-09-24 | 2014-10-08 | J.N. DELA TORRE CONSTRUCTION
3614 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111105 | Lamane ES | QUEZON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1 | 2015-05-14 | 2015-05-14 | 4B0414S00103 | 14EF0100 | 2015-01-27 | 2015-01-28 | 2015-02-13 | 2015-02-20 | 2015-03-09 | LEA & SONS TRADING AND CONSTRUCTION
3615 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110802 | Lindagong ES | BALABAC | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-04-17 | 2015-04-17 | 4B0414S00053 | 14EF0075 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | 12-30 CONSTRUCTION AND SUPPLY
3616 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301704 | Maasin NHS (Bernas NHS) | BROOKE'S POINT | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
3617 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110880 | Mainit ES | BROOKE'S POINT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 4B0414S00076 | 14EF0036 | 2014-08-25 | 2014-08-29 | 2014-09-10 | 2014-09-24 | 2014-10-08 | 12-30 CONSTRUCTION AND SUPPLY
3618 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170575 | Malangsee Hilside ES | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 4B0414S00029 | 14EF0090 | 2014-11-17 | 2014-11-20 | 2014-12-02 | 2014-12-10 | 2014-12-23 | CRISHELLE CONSTRUCTION
3619 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111109 | Malatgao ES | QUEZON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-07-11 | 2015-07-11 | 4B0414S00160 | 14EF0082 | 2014-11-04 | 2014-11-06 | 2015-04-14 | 2015-04-23 | 2015-05-06 | SAMURAI CONSTRUCTION
3620 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110836 | Malihud ES | BATARAZA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 4B0414S00060 | 14EF0033 | 2014-08-25 | 2014-08-29 | 2014-09-10 | 2014-09-24 | 2014-10-08 | 12-30 CONSTRUCTION AND SUPPLY
3621 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 309133 | Malihud National High School | BATARAZA | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-04-08 |  | 4B0414S00301 | 15EF0129 | 2015-10-14 | 2015-10-16 | 2015-10-29 | 2015-11-20 | 2015-12-04 | NURBEN ENGINEERING AND BUILDING CONTRACTOR
3622 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170560 | Maribong PS | SOFRONIO ESPAÑOLA | 2 | 1 | 1 | 1STY 2CL | 2014 K10 BATCH 1 | 883088.45 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-03-30 | 4B0414S00089 | 14EF0091 | 2014-11-17 | 2014-11-20 | 2014-12-02 | 2014-12-10 | 2014-12-23 | 12-30 CONSTRUCTION AND SUPPLY
3623 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110809 | Matangule ES | BALABAC | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-04-27 | 2015-04-27 | 4B0414S00044 | 14EF0074 | 2014-11-04 | 2014-11-06 | 2015-01-29 | 2015-02-06 | 2015-02-20 | R.C. TAGALA CONSTRUCTION
3624 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110884 | Mate ES | BROOKE'S POINT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 4B0414S00133 | 14EF0078 | 2014-11-04 | 2014-11-06 | 2015-04-14 | 2015-04-23 | 2015-05-06 | 12-30 CONSTRUCTION AND SUPPLY
3625 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301710 | Narra NHS | NARRA | 2 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | REVERTED | 0 |  |  | 4B0414S00234 | 15EF0103 | 2015-09-14 | 2015-09-15 | 2015-10-21
3626 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110839 | Narra-Narra ES | BATARAZA | 2 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2264658.24 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 4B0414S00061 | 14EF0034 | 2014-08-25 | 2014-08-29 | 2014-09-10 | 2014-09-24 | 2014-10-08 | PTK GROUP INC.
3627 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110885 | New Panay ES | BROOKE'S POINT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-07-11 | 2015-08-05 | 4B0414S00134 | 14EF0078 | 2014-11-04 | 2014-11-06 | 2014-04-14 | 2015-04-23 | 2015-05-06 | 12-30 CONSTRUCTION AND SUPPLY
3628 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110842 | Panas PS | BATARAZA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 4B0414S00131 | 14EF0077 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | CRISHELLE CONSTRUCTION
3629 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111116 | Panibugon ES | QUEZON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-02-26 | 4B0414S00105 | 14EF0043 | 2014-08-25 | 2014-08-29 | 2014-09-12 | 2014-09-24 | 2014-10-08 | SAMURAI CONSTRUCTION
3630 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111117 | Panitian ES | QUEZON | 2 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3975835.14 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-02-26 | 4B0414S00100 | 14EF0043 | 2014-08-25 | 2014-08-29 | 2014-09-12 | 2014-09-24 | 2014-10-08 | SAMURAI CONSTRUCTION
3631 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110912 | Panitian Interior ES | SOFRONIO ESPAÑOLA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
3632 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110912 | Panitian Interior ES | SOFRONIO ESPAÑOLA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1
3633 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110888 | Paratungon ES | BROOKE'S POINT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 4B0414S00075 | 14EF0036 | 2014-08-25 | 2014-08-29 | 2014-09-10 | 2014-09-24 | 2014-10-08 | 12-30 CONSTRUCTION AND SUPPLY
3634 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111118 | Pinaglabanan ES | QUEZON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-09-15 | 2015-09-15 | 4B0414S00161 | 14EF0079 | 2014-11-04 | 2014-11-06 | 2015-04-14 | 2015-04-23 | 2015-05-06 | 12-30 CONSTRUCTION AND SUPPLY
3635 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 301722 | Plaridel NHS | ABORLAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | REVERTED | 0
3636 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301724 | Princess Urduja NHS | NARRA | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
3637 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110894 | Proyekto Setias Mem. ES (Tagpirara ES) | BROOKE'S POINT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
3638 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110915 | Pulot Interior ES | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-12 | 4B0414S00026 | 14EF0038 | 2014-08-25 | 2014-08-29 | 2014-09-11 | 2014-09-24 | 2014-10-08 | J.N. DELA TORRE CONSTRUCTION
3639 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 301725 | Pulot National High School | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1
3640 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301725 | Pulot National High School | SOFRONIO ESPAÑOLA | 2 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1
3641 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110917 | Punang ES | SOFRONIO ESPAÑOLA | 2 | 1 | 1 | 1STY 2CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-06-23 | 2015-06-23 | 4B0414S00212 | 14EF0091 | 2014-11-17 | 2014-11-20 | 2014-12-02 | 2014-12-10 | 2014-12-23 | 12-30 CONSTRUCTION AND SUPPLY
3642 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301726 | Quezon NHS | QUEZON | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
3643 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301727 | Quezon-Aramaywan NHS | QUEZON | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
3644 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 301728 | Quezon-Panitian NHS | QUEZON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1
3645 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111121 | Quinlogan ES | QUEZON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 4B0414S00107 | 14EF0042 | 2014-08-25 | 2014-08-29 | 2014-09-12 | 2014-09-24 | 2014-10-08 | SAMURAI CONSTRUCTION
3646 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110817 | Rabor PS | BALABAC | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2016-04-13 |  | 4B0414S00168 | 15EF0097 | 2015-07-20 | 2015-07-21 | 2015-10-29 | 2015-11-25 | 2015-12-09 | JB & SONS TRADING & CONSTRUCTION | Abandoned
3647 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111122 | Ransang North ES | RIZAL (MARCOS) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 4B0414S00164 | 14EF0080 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | 12-30 CONSTRUCTION AND SUPPLY
3648 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301730 | Rio Tuba NHS | BATARAZA | 2 | 1 | 12 | 2STY12CL | 2014 SHS BATCH 1 | 14579217.1798 |  |  | COMPLETED | 1 | 2016-06-04 |  | 4B0414S00230 | 15EF0120 | 2015-10-06 | 2015-10-07 | 2015-10-20 | 2015-11-17 | 2015-12-01 | NURBEN ENGINEERING AND BUILDING CONTRACTOR
3649 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110889 | Rizal ES | BROOKE'S POINT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 4B0414S00074 | 14EF0037 | 2014-08-25 | 2014-08-29 | 2014-09-11 | 2014-09-24 | 2014-10-08 | PTK GROUP INC.
3650 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110733 | Sagpangan ES | ABORLAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-11-27 | 4B0414S00050 | 14EG0005 | 2014-05-13 | 2014-05-23 | 2014-06-03 | 2014-08-06 | 2014-08-14 | SAMURAI CONSTRUCTION
3651 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111123 | Salongsong School | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-02-26 | 4B0414S00087 | 14EF0044 | 2014-08-25 | 2014-08-29 | 2014-09-12 | 2014-09-24 | 2014-10-08 | R.C. TAGALA CONSTRUCTION
3652 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110891 | Samariniana ES | BROOKE'S POINT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 4B0414S00135 | 14EF0081 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | 12-30 CONSTRUCTION AND SUPPLY
3653 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110847 | Sandoval ES | BATARAZA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 4B0414S00153 | 14EF0077 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | CRISHELLE CONSTRUCTION
3654 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301739 | Sandoval National High School | NARRA | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
3655 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 301739 | Sandoval National High School | NARRA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
3656 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110848 | Sapa ES | BATARAZA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-27 | 4B0414S00067 | 14EF0035 | 2014-08-25 | 2014-08-29 | 2014-09-10 | 2014-09-24 | 2014-10-08 | RHODAMAY CONSTRUCTION SUPPLY
3657 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 309127 | Sibaring NHS | BALABAC | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-03-23 |  | 4B0414S00294 | 15EF0126 | 2015-10-06 | 2015-10-07 | 2015-10-21 | 2015-11-10 | 2015-11-23 | R.C. TAGALA CONSTRUCTION
3658 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111124 | Sicud ES | RIZAL (MARCOS) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-12 | 4B0414S00110 | 14EF0045 | 2014-08-25 | 2014-08-29 | 2014-09-12 | 2014-09-24 | 2014-10-08 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3659 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170568 | Sincab ES | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-03 | 4B0414S00083 | 14EF0039 | 2014-08-25 | 2014-08-29 | 2014-09-11 | 2014-09-24 | 2014-10-08 | J.N. DELA TORRE CONSTRUCTION
3660 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110820 | Singcab PS | BALABAC | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-04-27 | 2015-04-27 | 4B0414S00055 | 14EF0074 | 2014-11-04 | 2014-11-06 | 2015-01-29 | 2015-02-06 | 2015-02-20 | R.C. TAGALA CONSTRUCTION
3661 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 309129 | Southern Bataraza NHS | BATARAZA | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1
3662 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111126 | Sowangan ES | QUEZON | 2 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 2 | 2049715.8567 |  |  | COMPLETED | 1 | 2015-07-11 | 2015-07-11 | 4B0414S00185 | 14EF0082 | 2014-11-04 | 2014-11-06 | 2015-04-14 | 2015-04-23 | 2015-05-06 | SAMURAI CONSTRUCTION
3663 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110736 | Sto. Niño ES | ABORLAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-11-26 | 4B0414S00152 | 14EG0010 | 2014-07-08 | 2014-07-18 | 2014-07-30 | 2014-09-02 | 2014-09-05 | E.C. TIMBANCAYA ENTERPRISES
3664 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 309115 | Sumbiling NHS | BATARAZA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1
3665 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 309115 | Sumbiling NHS | BATARAZA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
3666 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110821 | Tabodniayo ES | BALABAC | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-04-17 | 2015-04-17 | 4B0414S00056 | 14EF0075 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | 12-30 CONSTRUCTION AND SUPPLY
3667 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111128 | Tabon ES | QUEZON | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2900174.43 |  |  | COMPLETED | 1 | 2015-02-11 | 2015-02-11 | 4B0414S00111 | 14EF0041 | 2014-08-25 | 2014-08-29 | 2014-09-11 | 2014-09-25 | 2014-10-08 | SAMURAI CONSTRUCTION
3668 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110855 | Tabud ES | BATARAZA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2016-04-13 |  | 4B0414S00154 | 15EF0097 | 2015-07-20 | 2015-07-21 | 2015-10-29 | 2015-11-25 | 2015-12-09 | JB & SONS TRADING & CONSTRUCTION
3669 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110857 | Tagnato ES | BATARAZA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 4B0414S00137 | 14EF0077 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | CRISHELLE CONSTRUCTION
3670 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110893 | Tagpinasao ES | BROOKE'S POINT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2016-04-13 |  | 4B0414S00156 | 15EF0097 | 2015-07-20 | 2015-07-21 | 2015-10-29 | 2015-11-25 | 2015-12-09 | JB & SONS TRADING & CONSTRUCTION
3671 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111132 | Tagusao ES | QUEZON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-02-26 | 4B0414S00112 | 14EF0043 | 2014-08-25 | 2014-08-29 | 2014-09-12 | 2014-09-24 | 2014-10-08 | SAMURAI CONSTRUCTION
3672 | NC 2014 | SHS (2014) | Region IV-B | Palawan | 301743 | Tagusao NHS | QUEZON | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2016-04-24 |  | 4B0414S00228 | 15EF0092 | 2015-07-20 | 2015-07-21 | 2015-10-12 | 2015-11-11 | 2015-11-20 | IVY MICHELLE TRADING & CONTRUCTION
3673 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110895 | Tagusao Shore PS | BROOKE'S POINT | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-03-29 | 2015-03-29 | 4B0414S00077 | 14EF0092 | 2014-11-17 | 2014-11-20 | 2014-12-02 | 2014-12-10 | 2014-12-23 | L.B. LEONCIO TRADING & CONSTRUCTION
3674 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110859 | Taratak ES | BATARAZA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 4B0414S00052 | 14EF0033 | 2014-08-25 | 2014-08-29 | 2014-09-10 | 2014-09-24 | 2014-10-08 | 12-30 CONSTRUCTION AND SUPPLY
3675 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170573 | Tarumpitao Point ES | RIZAL (MARCOS) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-04-02 |  | 4B0414S00300 | 15EF0127 | 2015-10-06 | 2015-10-07 | 2015-10-21 | 2015-11-19 | 2015-12-03 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3676 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 110738 | Tigman ES | ABORLAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
3677 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111133 | Tina ES | QUEZON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-12 | 4B0414S00101 | 14EF0042 | 2014-08-25 | 2014-08-29 | 2014-09-12 | 2014-09-24 | 2014-10-08 | SAMURAI CONSTRUCTION
3678 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170545 | Tulafos PS | RIZAL (MARCOS) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-02-16 | 4B0414S00166 | 14EF0081 | 2014-11-04 | 2014-11-06 | 2014-11-19 | 2014-11-28 | 2014-12-12 | 12-30 CONSTRUCTION AND SUPPLY
3679 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 170565 | Tungib PS | QUEZON | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-04-13 |  | 4B0414S00289 | 15EF0130 | 2015-10-14 | 2015-10-16 | 2015-10-29 | 2015-11-25 | 2015-12-09 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
3680 | NC 2014 | K10 (2014) | Region IV-B | Palawan | 111134 | Underground ES | QUEZON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 4B0414S00109 | 14EF0093 | 2014-11-17 | 2014-11-20 | 2014-12-02 | 2014-12-10 | 2014-12-23 | CRISHELLE CONSTRUCTION
3681 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301787 | Babuyan NHS | PUERTO PRINCESA CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6719337.6381 |  |  | COMPLETED | 1
3682 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301779 | Bacungan NHS | PUERTO PRINCESA CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 | 2016-01-13 |  | 4B0414S00226 | 15EG0028 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-14 | 2015-08-24 | LEA & SONS TRADING AND CONSTRUCTION
3683 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301780 | Bahile NHS | PUERTO PRINCESA CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 | 2016-02-18 |  | 4B0414S00224 | 15EG0026 | 2015-09-01 | 2015-09-09 | 2015-09-21 | 2015-09-23 | 2015-09-29 | A.C. RIVERO DEVELOPMENT CORPORATION
3684 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111510 | Buenavista ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-29 | 2014-10-27 | 4B0414S00092 | 14EG0018 | 2014-05-13 | 2014-05-23 | 2014-06-03 | 2014-06-19 | 2014-06-26 | E.C. TIMBANCAYA ENTERPRISES
3685 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301781 | Cabayugan NHS | PUERTO PRINCESA CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 | 2016-02-21 |  | 4B0414S00235 | 15EG0036 | 2015-07-24 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-09-02 | F.F. GALANG CONSTRUCTION
3686 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301782 | Inagawan NHS | PUERTO PRINCESA CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 4B0414S00246 | 15EG0033 | 2015-07-24 | 2015-07-31 | 2015-08-12 | 2015-08-20 | 2015-09-01 | E.C. TIMBANCAYA ENTERPRISES
3687 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111480 | Iratag ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-24 | 4B0414S00098 | 14EG0008 | 2014-07-15 | 2014-07-24 | 2014-08-05 | 2014-08-11 | 2014-08-19 | L.B. LEONCIO TRADING & CONSTRUCTION
3688 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301783 | Irawan NHS | PUERTO PRINCESA CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 | 2016-02-21 |  | 4B0414S00252 | 15EG0038 | 2015-07-24 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-09-02 | E.C. TIMBANCAYA ENTERPRISES
3689 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111481 | Iwahig ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-29 |  | 4B0414S00290 | 15EG0045 | 2015-08-25 | 2015-09-03 | 2015-09-15 | 2015-09-22 | 2015-09-30 | LEA & SONS TRADING AND CONSTRUCTION
3690 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301784 | Langogan NHS | PUERTO PRINCESA CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 | 2016-01-13 |  | 4B0414S00251 | 15EG0025 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-13 | 2015-08-20 | E.C. TIMBANCAYA ENTERPRISES
3691 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301788 | Luzviminda NHS | PUERTO PRINCESA CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 | 2016-01-13 |  | 4B0414S00250 | 15EG0029 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-13 | 2015-08-20 | E.C. TIMBANCAYA ENTERPRISES
3692 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 171505 | Mabuhay PS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-29 |  | 4B0414S00291 | 15EG0043 | 2015-08-25 | 2015-09-03 | 2015-09-15 | 2015-09-22 | 2015-09-30 | PANAAD CONSTRUCTION
3693 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301785 | Macarascas NHS | PUERTO PRINCESA CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 | 2016-02-18 |  | 4B0414S00249 | 15EG0026 | 2015-09-01 | 2015-09-08 | 2015-09-21 | 2015-09-23 | 2015-09-29 | A.C. RIVERO DEVELOPMENT CORPORATION
3694 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111521 | Manalo Elementary school | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-29 |  | 4B0414S00292 | 15EG0044 | 2015-08-25 | 2015-09-03 | 2015-09-15 | 2015-09-22 | 2015-09-30 | R.C. TAGALA CONSTRUCTION
3695 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111487 | Mangingisda Elementary School | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-29 |  | 4B0414S00293 | 15EG0042 | 2015-08-25 | 2015-09-03 | 2015-09-15 | 2015-09-22 | 2015-09-30 | RHODAMAY CONSTRUCTION SUPPLY
3696 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301789 | Mangingisda NHS | PUERTO PRINCESA CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 4B0414S00248 | 15EG0034 | 2015-07-24 | 2015-07-31 | 2015-08-12 | 2015-08-20 | 2015-09-01 | R.C. TAGALA CONSTRUCTION
3697 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111523 | Maranat ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2014-10-29 | 2014-10-27 | 4B0414S00082 | 14EG0018 | 2014-05-13 | 2014-05-23 | 2014-06-03 | 2014-06-19 | 2014-06-26 | E.C. TIMBANCAYA ENTERPRISES
3698 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301792 | Marcelino Abadiano Javarez National High School | PUERTO PRINCESA CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-03-19 |  | 4B0414S00247 | 15EG0035 | 2015-09-01 | 2015-09-09 | 2015-09-21 | 2015-09-23 | 2015-09-29 | E.C. TIMBANCAYA ENTERPRISES
3699 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111490 | Napsan ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2014-11-06 | 2014-11-05 | 4B0414S00088 | 14EG0016 | 2014-05-13 | 2014-05-23 | 2014-06-03 | 2014-06-19 | 2014-07-01 | SAMURAI CONSTRUCTION
3700 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301786 | Napsan National High School | PUERTO PRINCESA CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 | 2016-02-12 |  | 4B0414S00237 | 15EG0027 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-14 | 2015-08-24 | E.C. TIMBANCAYA ENTERPRISES
3701 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 309301 | Palawan National School | PUERTO PRINCESA CITY | 2 | 1 | 16 | 4STY16CL | 2014 SHS BATCH 1 | 26782469.42 |  |  | COMPLETED | 1
3702 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 309301 | Palawan National School | PUERTO PRINCESA CITY | 2 | 1 | 16 | 4STY16CL | 2014 SHS BATCH 1 | 26702469.42 |  |  | COMPLETED | 1
3703 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301791 | Pto. Princesa City Nat. Sci. HS | PUERTO PRINCESA CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 | 2016-03-19 |  | 4B0414S00243 | 15EG0032 | 2015-09-01 | 2015-09-09 | 2015-09-21 | 2015-09-23 | 2015-09-29 | R.C. TAGALA CONSTRUCTION
3704 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301793 | San Jose NHS | PUERTO PRINCESA CITY | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
3705 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301795 | San Rafael National High School | PUERTO PRINCESA CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 | 2016-01-13 |  | 4B0414S00241 | 15EG0025 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-14 | 2015-08-24 | E.C. TIMBANCAYA ENTERPRISES
3706 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301796 | Sicsican NHS | PUERTO PRINCESA CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8344965.051 |  |  | COMPLETED | 1 | 2016-02-21 |  | 4B0414S00240 | 15EG0037 | 2015-07-24 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-09-02 | SEVEN DIGIT CONSTRUCTION & SUPPLIES
3707 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111493 | Simpucan ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-11-06 | 2014-11-05 | 4B0414S00095 | 14EG0016 | 2014-05-13 | 2014-05-23 | 2014-06-03 | 2014-06-19 | 2014-07-01 | SAMURAI CONSTRUCTION
3708 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 309302 | Simpucan NHS (Napsan NHS - Simpucan Annex) | PUERTO PRINCESA CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 | 2016-02-12 |  | 4B0414S00244 | 15EG0027 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-14 | 2015-08-24 | E.C. TIMBANCAYA ENTERPRISES
3709 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111531 | Sta. Cruz ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2014-10-29 | 2014-10-27 | 4B0414S00099 | 14EG0018 | 2014-05-13 | 2014-05-23 | 2014-06-03 | 2014-06-19 | 2014-06-26 | E.C. TIMBANCAYA ENTERPRISES
3710 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111494 | Sta. Lourdes ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-24 | 4B0414S00096 | 14EG0008 | 2014-07-15 | 2014-07-24 | 2014-08-05 | 2014-08-11 | 2014-08-19 | L.B. LEONCIO TRADING & CONSTRUCTION
3711 | NC 2014 | SHS (2014) | Region IV-B | PUERTO PRINCESA CITY | 301790 | Sta. Lourdes NHS | PUERTO PRINCESA CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-13 |  | 4B0414S00238 | 15EG0030 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-13 | 2015-08-20 | E.C. TIMBANCAYA ENTERPRISES
3712 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111496 | Sto. Niño ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-11-06 | 2014-11-05 | 4B0414S00097 | 14EG0016 | 2014-05-13 | 2014-05-23 | 2014-06-03 | 2014-06-19 | 2014-07-01 | SAMURAI CONSTRUCTION
3713 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 171503 | Tagbarungis ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-10 | 4B0414S00090 | 14EG0017 | 2014-05-13 | 2014-05-23 | 2014-06-03 | 2014-06-19 | 2014-06-26 | SAMURAI CONSTRUCTION
3714 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111499 | Tagumpay ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-10 | 4B0414S00086 | 14EG0017 | 2014-05-13 | 2014-05-23 | 2014-06-03 | 2014-06-19 | 2014-06-26 | SAMURAI CONSTRUCTION
3715 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111501 | Tiniguiban ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-24 | 4B0414S00094 | 14EG0008 | 2014-07-15 | 2014-07-24 | 2014-08-05 | 2014-08-11 | 2014-08-19 | L.B. LEONCIO TRADING & CONSTRUCTION
3716 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111502 | Valentin Macasaet MES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-10 | 4B0414S00093 | 14EG0017 | 2014-05-13 | 2014-05-23 | 2014-06-03 | 2014-06-19 | 2014-06-26 | SAMURAI CONSTRUCTION
3717 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 301787 | Babuyan NHS | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1
3718 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111468 | Gregorio Oquendo MES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4342149.6094 |  |  | COMPLETED | 1
3719 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111520 | Makirawa PS | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-06 | 4B0414S00120 | 14EG0009 | 2014-07-08 | 2014-07-18 | 2014-07-30 | 2014-08-07 | 2014-08-14 | E.C. TIMBANCAYA ENTERPRISES
3720 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111524 | Marufinas ES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-06 | 4B0414S00119 | 14EG0009 | 2014-07-08 | 2014-07-18 | 2014-07-30 | 2014-08-07 | 2014-08-14 | E.C. TIMBANCAYA ENTERPRISES
3721 | NC 2014 | K10 (2014) | Region IV-B | Puerto Princesa City | 111525 | Nasuduan ES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024857.9283 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-06 | 4B0414S00118 | 14EG0009 | 2014-07-08 | 2014-07-18 | 2014-07-30 | 2014-08-07 | 2014-08-14 | E.C. TIMBANCAYA ENTERPRISES
3722 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 111365 | Agnaga ES | ROMBLON (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2088606.04 |  |  | COMPLETED | 1 | 2016-01-26 |  | 4B0514S00034 | EH0083 | 2015-08-26 | 2015-08-27 | 2015-09-08 | 2015-10-19 | 2015-10-28 | MA. GINA M. PADOR CONSTRUCTION
3723 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 111320 | Agojo ES | LOOC | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | REVERTED | 0 |  |  | 4B0514S00033
3724 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 111275 | Agsao ES | MAGDIWANG | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-12-19 | 4B0514S00006 | 14EH0039 | 2014-09-11 | 2014-09-12 | 2014-09-24 | 2014-10-10 | 2014-10-20 | MT. GUITING-GUITING CONSTRUCTION
3725 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301750 | Banton NHS | BANTON | 0 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10617131.51 |  |  | REVERTED | 0 |  |  | 4B0514S00026
3726 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301752 | Cajidiocan National High School | CAJIDIOCAN | 0 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22302343.62 |  |  | COMPLETED | 1 | 2016-07-07 |  | 4B0514S00027 | 15EH0107 | 2015-09-30 | 2015-10-01 | 2015-10-13 | 2015-11-23 | 2015-12-10 | CSR CONSTRUCTION & SUPPLY
3727 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 309201 | Calatrava NHS | CALATRAVA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8289965.051 |  |  | COMPLETED | 1 | 2016-03-24 |  | 4B0514S00028 | 15EH0079 | 2015-08-26 | 2015-08-27 | 2015-09-08 | 2015-10-19 | 2015-10-28 | STEVEN CONSTRUCTION & SUPPLY
3728 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301755 | Cambalo NHS | CAJIDIOCAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1 |  |  | 4B0514S00029
3729 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 309205 | Carmen NHS (Cabolutan NHS Ext.) | SAN AGUSTIN | 0 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1 | 2016-06-04 |  | 4B0514S00030 | 15EH0122 | 2015-10-22 | 2015-10-23 | 2015-11-04 | 2015-12-01 | 2015-12-08 | TWIN DRAGON CONSTRUCTION
3730 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301756 | Concepcion NHS (Main) | CONCEPCION | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 7122137.6381 |  |  | COMPLETED | 1 | 2016-04-08 |  | 4B0514S00031 | 15EH0108 | 2015-09-30 | 2015-10-13 | 2015-10-13 | 2015-11-23 | 2015-12-10 | ALNAP CONSTRUCTION AND ENGINEERING
3731 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301757 | Corcuera NHS | CORCUERA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8781965.051 |  |  | COMPLETED | 1 |  |  | 4B0514S00032
3732 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301759 | Don Carlos M. Mejias Memorial NHS | SAN FERNANDO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 4B0514S00024
3733 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301760 | Espana NHS | SAN FERNANDO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8477965.051 |  |  | COMPLETED | 1 |  |  | 4B0514S00018
3734 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301749 | Esteban Madrona NHS | SAN AGUSTIN | 0 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 13232110.093 |  |  | COMPLETED | 1 |  |  | 4B0514S00020
3735 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 171004 | Felipe Madali MES | ALCANTARA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-25 | 2015-01-25 | 4B0514S00001 | 14EH0026 | 2014-10-06 | 2014-10-08 | 2014-10-20 | 2014-11-07 | 2014-11-17 | DADOY FREIGHT SERVICE, CONSTRUCTION & SUPPLY
3736 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301761 | Ferrol National High School | FERROL | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8286965.051 |  |  | COMPLETED | 1 | 2016-03-27 |  | 4B0514S00017 | 15EH0085 | 2015-09-02 | 2015-09-03 | 2015-09-15 | 2015-10-19 | 2015-10-29 | STEVEN CONSTRUCTION & SUPPLY
3737 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 111453 | Guintigbasan ES | SANTA FE | 0 | 1 | 4 | 2U-1STY2CL | 2014 K10 BATCH 2 | 3522000 |  |  | COMPLETED | 1
3738 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 111453 | Guintigbasan ES | SANTA FE | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
3739 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 111455 | Lamberto Antaran MS | SANTA FE | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-12-19 | 4B0514S00002 | 14EH0044 | 2014-09-11 | 2014-09-12 | 2014-09-24 | 2014-10-10 | 2014-10-20 | MT. GUITING-GUITING CONSTRUCTION
3740 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 111457 | Lindero ES | SAN JOSE | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-25 | 2015-01-25 | 4B0514S00009 | 14EH0026 | 2014-10-06 | 2014-10-08 | 2014-10-20 | 2014-11-07 | 2014-11-17 | DADOY FREIGHT SERVICE, CONSTRUCTION & SUPPLY
3741 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301765 | Looc NHS | LOOC | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8475665.051 |  |  | COMPLETED | 1 | 2016-04-02 |  | 4B0514S00016 | 15EH0089 | 2015-09-10 | 2015-09-11 | 2015-09-23 | 2015-10-19 | 2015-11-04 | MA. GINA M. PADOR CONSTRUCTION
3742 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301766 | Mabini NHS | CORCUERA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | REVERTED | 0 |  |  | 4B0514S00015
3743 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301768 | Magdiwang NHS | MAGDIWANG | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 4B0514S00014
3744 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301769 | Odiongan, National High School | ODIONGAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-24 |  | 4B0514S00019 | 15EH0081 | 2015-08-26 | 2015-08-27 | 2015-09-08 | 2015-10-19 | 2015-10-28 | STEVEN CONSTRUCTION & SUPPLY
3745 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 111409 | Pagsangahan ES | CALATRAVA | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | REVERTED | 0 |  |  | 4B0514S00005
3746 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 111410 | Paroyhog ES | SANTA MARIA (IMELDA) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-12-19 | 4B0514S00007 | 14EH0045 | 2014-09-11 | 2014-09-12 | 2014-09-24 | 2014-10-10 | 2014-10-20 | MT. GUITING-GUITING CONSTRUCTION
3747 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 111461 | Pinamihagan ES | SAN JOSE | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-25 | 2015-01-25 | 4B0514S00008 | 14EH0026 | 2014-10-06 | 2014-10-08 | 2014-10-20 | 2014-11-07 | 2014-11-17 | DADOY FREIGHT SERVICE, CONSTRUCTION & SUPPLY
3748 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 111332 | Punta ES | LOOC | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 983000 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 4B0514S00011 | 14EH0026 | 2014-10-06 | 2014-10-08 | 2014-10-20 | 2014-11-07 | 2014-11-17 | DADOY FREIGHT SERVICE, CONSTRUCTION & SUPPLY
3749 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301771 | San Andres NHS | SAN ANDRES | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-27 | 2016-03-27 | 4B0514S00023 | 15EH0080 | 2015-08-26 | 2015-08-27 | 2015-09-08 | 2015-10-12 | 2015-10-29 | R.G. FLORENTINO CONST & TRADING
3750 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301772 | San Jose Agricultural HS | SAN JOSE | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8604715.051 |  |  | REVERTED | 0 |  |  | 4B0514S00025
3751 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301774 | Santa Maria NHS | SANTA MARIA (IMELDA) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8339965.051 |  |  | COMPLETED | 1 | 2016-03-27 |  | 4B0514S00022 | 15EH0084 | 2015-09-02 | 2015-09-03 | 2015-09-15 | 2015-10-19 | 2015-10-29 | STEVEN CONSTRUCTION & SUPPLY
3752 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 111295 | Silum ES | MAGDIWANG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-11-22 | 2015-11-22 | 4B0514S00013 | 15EH0076 | 2015-08-05 | 2015-08-07 | 2015-08-19 | 2015-09-11 | 2015-09-23 | MA. GINA M. PADOR CONSTRUCTION
3753 | NC 2014 | SHS (2014) | Region IV-B | Romblon | 301763 | Sta. Fe NHS | SANTA FE | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 4B0514S00021
3754 | NC 2014 | K10 (2014) | Region IV-B | Romblon | 301776 | Tanagan NHS | SAN ANDRES | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-12-19 | 4B0514S00003 | 14EH0040 | 2014-09-11 | 2014-09-12 | 2014-09-24 | 2014-10-10 | 2014-10-20 | R.G. FLORENTINO CONST & TRADING
10824 | NC 2015 | K10 (2015) | Region IV-B | Marinduque | 109887 | Bamban Elementary School | BOAC (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0115S00001 | 15EA0083 | 2015-08-06 | 2015-08-17 | 2015-08-18 | 2015-08-25 | 2015-09-14 | R.C. TAGALA CONSTRUCTION
10825 | NC 2015 | K10 (2015) | Region IV-B | Marinduque | 109908 | Buenavista CS | BUENAVISTA | 0 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 6 | 12621310.093 |  |  | COMPLETED | 1 |  |  | 4B0115S00002 | 15EA0084 | 2015-08-13 | 2015-08-25 | 2015-08-25 | 2015-08-29 | 2015-09-14 | R.C. TAGALA CONSTRUCTION
10826 | NC 2015 | TECHVOC (2015) | Region IV-B | Occidental Mindoro | 301569 | Abra de Ilog NHS | ABRA DE ILOG | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
10827 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 301572 | Aguas National High School | RIZAL | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 4B0215S00025 | 15EB0098 | 2015-09-16 | 2015-09-18 | 2015-09-29 | 2015-10-30 | 2015-11-12 | R.C. TAGALA CONSTRUCTION
10828 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 169527 | Alacaak Minority School | PALUAN | 0 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  | 4B0215S00019 | 15EB0100 | 2015-09-11 | 2015-09-28 | 2015-10-05 | 2015-10-19 | 2015-11-03 | Hi-Tone Construction
10829 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110276 | Ambulong ES Annex - Bulwang PS | SAN JOSE | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2902592.44 |  |  | COMPLETED | 1 |  |  | 4B0215S00018 | 15EB0103R1 | 2015-11-04 | 2015-11-13 | 2015-11-25 | 2015-11-27 | 2015-12-04 | KINGs BUILDERS & DEVELOPMENT CORPORATION
10830 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 308903 | Ambulong Island IS | SAN JOSE | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2038606 |  |  | COMPLETED | 1 |  |  | 4B0215S00024 | 15EB0098 | 2015-09-16 | 2015-09-18 | 2015-09-29 | 2015-10-30 | 2015-11-12 | R.C. TAGALA CONSTRUCTION
10831 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110228 | Aplaya Elementary School | SABLAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00011 | 15EB0102R1 | 2015-10-09 | 2015-10-23 | 2015-11-04 | 2015-11-19 | 2015-12-23 | R N V CONSTRUCTION
10832 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110251 | Bubog 2 ES | SAN JOSE | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00016 | 15EB0103R1 | 2015-11-04 | 2015-11-13 | 2015-11-25 | 2015-11-27 | 2015-12-04 | KINGs BUILDERS & DEVELOPMENT CORPORATION
10833 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 301570 | Cabacao NHS | ABRA DE ILOG | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1968606 |  |  | COMPLETED | 1 |  |  | 4B0215S00022 | 15EB0098 | 2015-09-16 | 2015-09-18 | 2015-09-29 | 2015-10-26 | 2015-11-12 | R.C. TAGALA CONSTRUCTION
10834 | NC 2015 | TECHVOC (2015) | Region IV-B | Occidental Mindoro | 301574 | CALINTAAN NATIONAL HIGH SCHOOL | CALINTAAN | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2579549.27 |  |  | COMPLETED | 1
10835 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110159 | Casague ES | SANTA CRUZ | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00005 | 15EB0100 | 2015-09-11 | 2015-09-28 | 2015-10-05 | 2015-10-19 | 2015-11-03 | Hi-Tone Construction
10836 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110259 | Danlog Min. Sch. | SAN JOSE | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2013606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00017 | 15EB0103R1 | 2015-11-04 | 2015-11-13 | 2015-11-25 | 2015-11-27 | 2015-12-04 | KINGs BUILDERS & DEVELOPMENT CORPORATION
10837 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110236 | Lagutay Min. Sch. | SABLAYAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2902592.44 |  |  | COMPLETED | 1 |  |  | 4B0215S00012 | 15EB0102R1 | 2015-10-09 | 2015-10-23 | 2015-11-04 | 2015-11-19 | 2015-12-23 | R N V CONSTRUCTION
10838 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110055 | Lucutan Min. Sch. | ABRA DE ILOG | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2013606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00002 | 15EB0100 | 2015-09-11 | 2015-09-28 | 2015-10-05 | 2015-10-19 | 2015-11-03 | Hi-Tone Construction
10839 | NC 2015 | TECHVOC (2015) | Region IV-B | Occidental Mindoro | 301588 | Magsaysay NHS | MAGSAYSAY | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2509549.27 |  |  | COMPLETED | 1
10840 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 301590 | Magsaysay NHS - Purnaga Annex | MAGSAYSAY | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 4B0215S00026 | 15EB0098 | 2015-09-16 | 2015-09-18 | 2015-09-29 | 2015-10-30 | 2015-11-12 | R.C. TAGALA CONSTRUCTION
10841 | NC 2015 | TECHVOC (2015) | Region IV-B | Occidental Mindoro | 301593 | Occidental Mindoro NHS | MAMBURAO (Capital) | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2539549.27 |  |  | COMPLETED | 1
10842 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110176 | Pola ES | SANTA CRUZ | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00006 | 15EB0100 | 2015-09-11 | 2015-09-28 | 2015-10-05 | 2015-10-19 | 2015-11-03 | Hi-Tone Construction
10843 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110204 | Rizal ES | RIZAL | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00010 | 15EB0103R1 | 2015-11-04 | 2015-11-13 | 2015-11-25 | 2015-11-27 | 2015-12-04 | KINGs BUILDERS & DEVELOPMENT CORPORATION
10844 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110241 | Sablayan CS | SABLAYAN | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4B0215S00013 | 15EB0101 | 2015-10-09 | 2015-10-23 | 2015-11-04 | 2015-11-20 | 2015-12-09 | THREE W BUILDERS, INC.
10845 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 308907 | Sablayan NCHS - Sta. Lucia Annex | SABLAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 4B0215S00023 | 15EB0098 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-30 | 2015-11-12 | R.C. TAGALA CONSTRUCTION
10846 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110242 | Sahing ES | SABLAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2013606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00014 | 15EB0102R1 | 2015-10-09 | 2015-10-23 | 2015-11-04 | 2015-11-19 | 2015-12-23 | R N V CONSTRUCTION
10847 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110243 | Salvacion ES | SABLAYAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2877592.44 |  |  | COMPLETED | 1 |  |  | 4B0215S00015 | 15EB0102R1 | 2015-10-09 | 2015-10-23 | 2015-11-04 | 2015-11-19 | 2015-12-23 | R N V CONSTRUCTION
10848 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110218 | San Francisco ES | SABLAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00020 | 15EB0101 | 2015-10-09 | 2015-10-23 | 2015-11-04 | 2015-11-20 | 2015-12-09 | THREE W BUILDERS, INC.
10849 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110221 | San Vicente ES - Annex | SABLAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00021 | 15EB0101 | 2015-10-09 | 2015-10-23 | 2015-11-04 | 2015-11-20 | 2015-12-09 | THREE W BUILDERS, INC.
10850 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110144 | Sibalat ES - Silad ES Annex | MAGSAYSAY | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00004 | 15EB0103R1 | 2015-11-04 | 2015-11-13 | 2015-11-25 | 2015-11-27 | 2015-12-04 | KINGs BUILDERS & DEVELOPMENT CORPORATION
10851 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110226 | Tagumpay ES | SABLAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00009 | 15EB0102R1 | 2015-10-09 | 2015-10-23 | 2015-11-04 | 2015-11-19 | 2015-12-23 | R N V CONSTRUCTION
10852 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110185 | Talabaan ES Proper | MAMBURAO (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1978606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00007 | 15EB0100 | 2015-09-11 | 2015-09-28 | 2015-10-05 | 2015-10-19 | 2015-11-03 | Hi-Tone Construction
10853 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110096 | Tambo ES (Ambl ES-Tambo Site) | LOOC | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00003 | 15EB0104 | 2015-12-07 | 2015-12-09 | 2015-12-21 | 2015-12-28 | 2015-12-29
10854 | NC 2015 | K10 (2015) | Region IV-B | Occidental Mindoro | 110191 | Tuguilan Min. Sch. | MAMBURAO (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 4B0215S00008 | 15EB0100 | 2015-09-11 | 2015-09-28 | 2015-10-05 | 2015-10-19 | 2015-11-03 | Hi-Tone Construction
10855 | NC 2015 | K10 (2015) | Region IV-B | Oriental Mindoro | 110608 | Ambang Mangyan School | PUERTO GALERA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 4B0315S00005
10856 | NC 2015 | TECHVOC (2015) | Region IV-B | Oriental Mindoro | 301613 | Aurelio Arago MNHS | VICTORIA | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2579549.27 |  |  | COMPLETED | 1
10857 | NC 2015 | K10 (2015) | Region IV-B | Oriental Mindoro | 110492 | Leon Garong MS | NAUJAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0315S00011
10858 | NC 2015 | K10 (2015) | Region IV-B | Oriental Mindoro | 110629 | Catalino Dizon Memorial School | ROXAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 4B0315S00009 | 15EI0099 | 2015-09-16 | 2015-09-18 | 2015-09-30 | 2015-12-16
10859 | NC 2015 | K10 (2015) | Region IV-B | Oriental Mindoro | 110393 | Cawayan ES | BONGABONG | 2 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 6 | 13121310.093 |  |  | COMPLETED | 1 |  |  | 4B0315S00006 | 15EI0102 | 2015-09-29 | 2015-10-08 | 2015-10-20
10860 | NC 2015 | K10 (2015) | Region IV-B | Oriental Mindoro | 110446 | Malamig ES | GLORIA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0315S00007 | 15EI0098 | 2015-09-16 | 2015-09-18 | 2015-09-30 | 2015-12-16
10861 | NC 2015 | TECHVOC (2015) | Region IV-B | Oriental Mindoro | 301639 | Marcelo I. Cabrera Vocational High School | ROXAS | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 5079098.54 |  |  | COMPLETED | 1
10862 | NC 2015 | K10 (2015) | Region IV-B | Oriental Mindoro | 110561 | Natividad De Joya MS (Guinhawa) | PINAMALAYAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0315S00008 | 15EI0100 | 2015-09-16 | 2015-09-18 | 2015-09-30 | 2015-12-16
10863 | NC 2015 | K10 (2015) | Region IV-B | Oriental Mindoro | 110648 | Tauga Diit Elementary School | ROXAS | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3867968.78 |  |  | COMPLETED | 1 |  |  | 4B0315S00010 | 15EI0101 | 2015-09-16 | 2015-09-18 | 2015-09-30 | 2015-12-16
10864 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 301656 | Abaroan NHS | ROXAS | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2038606 |  |  | Completed | 1 |  |  | 4B0415S00115 | 15EE0090 | 2015-11-15 | 2015-11-16 | 2015-12-01 | 2015-12-08 | 2015-12-15 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
10865 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170561 | Agustin Ello ES | ROXAS | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | Completed | 1 |  |  | 4B0415S00073 | 15EE0076 | 2015-11-08 | 2015-11-19 | 2015-11-20 | 2015-11-27 | 2015-12-07 | A.P. CONSEBIDO CONSTRUCTION AND TRADING
10866 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301660 | Alimanguan NHS | SAN VICENTE | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10877343 |  |  | Completed | 1
10867 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301660 | Alimanguan NHS | SAN VICENTE | 1 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 12771310 |  |  | Completed | 1
10868 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110749 | Araceli CS | ARACELI | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | 4B0415S00104 | 15EE0083 | 2015-11-12 | 2015-11-13 | 2015-11-25 | 2015-12-03 | 2015-12-11 | YURICH BUILDERS AND CONSTRUCTION SUPPLY
10869 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 309104 | Araceli Western National HS | ARACELI | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2063606 |  |  | Completed | 1 |  |  | 4B0415S00126 | 15EE0091 | 2015-11-15 | 2015-11-16 | 2015-12-01 | 2015-12-08 | 2015-12-15 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
10870 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 309109 | Bacao NHS (Dumaran NHS - Bacao NHS) | DUMARAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8389965 |  |  | COMPLETED | 1 | [10 empty] | scarcity of materials (Gravel, sand, lumber)
10871 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 309109 | Bacao NHS (Dumaran NHS - Bacao NHS) | DUMARAN | 1 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 13021310 |  |  | COMPLETED | 1 | [10 empty] | Abandoned
10872 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301667 | Barotuan NHS | EL NIDO (BACUIT) | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 3179549.27 |  |  | Completed | 1
10873 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170509 | Bayang PS | CORON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | REVERTED | 0 |  |  | 4B0415S00091 | 15EE0085 | 2015-12-29
10874 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170539 | Benecan ES | CORON | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | Completed | 1 |  |  | 4B0415S00088 | 15EE0105 | 2015-12-01 | 2015-12-02 | 2015-12-14 | 2015-12-18 | 2015-12-29 | GABARDA CONSTRUCTION
10875 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111213 | Biton ES | TAYTAY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2902592.44 |  |  | Completed | 1
10876 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110755 | Bolocot ES | ARACELI | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | 4B0415S00105 | 15EE0104 | 2015-12-01 | 2015-12-02 | 2015-12-14 | 2015-12-18 | 2015-12-29 | A.P. CONSEBIDO CONSTRUCTION AND TRADING
10877 | NC 2015 | SHS (2015) | Region IV-B | Palawan |  | Borac NHS-Decalachao Extension | CORON | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 8 | 10977342.5917 |  |  | Completed | 1 |  |  | 4B0415S00132 | 15EE0106 | 2015-12-01 | 2015-12-02 | 2015-12-14 | 2015-12-18 | 2015-12-29 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY (FORMERLY:
10878 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170550 | Buyot ES | CORON | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2902592.44 |  |  | Completed | 1 |  |  | 4B0415S00075 | 15EE0142 | 2015-12-27 | 2015-12-28 |  |  |  |  | scarcity of materials (Gravel, sand, lumber), Transpo of materials
10879 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111142 | Candelaria PS | ROXAS | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2952592.44 |  |  | Completed | 1 |  |  | 4B0415S00110 | 15EE0140 | 2015-12-27 | 2015-12-28
10880 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301681 | Caruray NHS | SAN VICENTE | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2802592 |  |  | Completed | 1 |  |  | 4B0415S00061 | 15EE0147 | 2015-12-29
10881 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301682 | Casian NHS | TAYTAY | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2529549.27 |  |  | Completed | 1
10882 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111224 | Cataban ES | TAYTAY | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3767968.78 |  |  | Completed | 1 |  |  | 4B0415S00113 | 15EE0086 | 2015-11-12 | 2015-11-13 | 2015-11-25 | 2015-12-03 | 2015-12-11 | YURICH BUILDERS AND CONSTRUCTION SUPPLY
10883 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 309120 | Concepcion National High School | AGUTAYA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8364965 |  |  | Completed | 1 |  |  | 4B0415S00054 | 15EE0117 | 2015-12-15 | 2015-12-03 | 2015-12-15 | 2015-12-22
10884 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301684 | Coron SOF | CORON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | Completed | 1 |  |  | 4B0415S00042 | 15EE0029 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-08-25 | 2015-09-07 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY (FORMERLY:
10885 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170557 | Cruz Destura Sr.MES | TAYTAY | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4623636.82 |  |  | Completed | 1 |  |  | 4B0415S00074 | 14EE0148 | 2015-12-29
10886 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301687 | Culion Sanitarium Special NHS | CULION | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2529549.27 |  |  | Completed | 1
10887 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170505 | Danat ES | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | 4B0415S00102 | 15EE0078 | 2015-11-08 | 2015-11-19 | 2015-11-20 | 2015-11-27 | 2015-12-07 | VCH CONSTRUCTION AND TRADING
10888 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301689 | Danawan NHS | MAGSAYSAY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6509338 |  |  | Completed | 1 |  |  | 4B0415S00060 | 15EE0096 | 2015-11-22 | 2015-11-23 | 2015-12-04 | 2015-12-11 | 2015-12-21 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
10889 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170549 | Diandanao PS | CORON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | 4B0415S00103 | 15EE0084 | 2015-11-15
10890 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301692 | Dumaran NHS Mainland | DUMARAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Completed | 1 |  |  | 4B0415S00059
10891 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111045 | Igabas ES | MAGSAYSAY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6419337.6381 |  |  | Completed | 1 |  |  | 4B0415S00109 | 15EE0087 | 2015-10-30 | 2015-11-13 | 2015-11-25
10892 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111024 | Kiminawit Elementary School | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | Completed | 1 |  |  | 4B0415S00101 | 15EE0081 | 2015-11-08 | 2015-11-19 | 2015-11-20 | 2015-11-27 | 2015-12-07 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
10893 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301703 | Liminangcong NHS | TAYTAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | Completed | 1 |  |  | 4B0415S00041 | 15EE0028 | 2015-08-30 | 2015-09-01 | 2015-11-12 | 2015-11-19 | 2015-12-02 | E.V. VILLAOS TRADING & CONSTRUCTION
10894 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301705 | Magara School for Philippine Crafstmen | ROXAS | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | Completed | 1
10895 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110967 | MAGSAYSAY ES | CAGAYANCILLO | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4823636.82 |  |  | Completed | 1 |  |  | 4B0415S00106
10896 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111194 | New Canipo ES | SAN VICENTE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | Completed | 1 |  |  | 4B0415S00111 | 15EE0082 | 2015-11-12 | 2015-11-13 | 2015-11-25 | 2015-12-03 | 2015-12-11 | LEA & SONS TRADING AND CONSTRUCTION
10897 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 309108 | New Canipo NHS (Alimanguan NHS - New Canipo NHS) | SAN VICENTE | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8314965 |  |  | Completed | 1 |  |  | 4B0415S00055 | 15EE0116 | 2015-12-15 | 2015-12-03 | 2015-12-15 | 2015-12-22 |  |  | scarcity of materials (Gravel, sand, lumber), Transpo of materials
10898 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301713 | New Ibajay NHS | EL NIDO (BACUIT) | 1 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 8 | 18442268.79 |  |  | REVERTED | 0 |  |  | 4B0415S00130
10899 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170529 | Nicanor Zabala ES | ROXAS | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | Completed | 1 |  |  | 4B0415S00079 | 15EE0077 | 2015-11-08 | 2015-11-19 | 2015-11-20 | 2015-11-27 | 2015-12-07 | YURICH BUILDERS AND CONSTRUCTION SUPPLY
10900 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 301714 | Nicanor Zabala NHS | ROXAS | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 7 | 10877343 |  |  | Completed | 1 |  |  | 4B0415S00127 | 15EE0092 | 2015-11-15 | 2015-11-16 | 2015-12-01 | 2015-12-08 | 2015-12-15 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY (FORMERLY:
10901 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170546 | Nicolas M. Aborot Sr. MES | MAGSAYSAY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2902592.44 |  |  | Completed | 1 |  |  | 4B0415S00077 | 15EE0139 | 2015-12-27 | 2015-12-28
10902 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110778 | Osmeña ES | ARACELI | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | 4B0415S00114 | 15EE0103 | 2015-12-01 | 2015-12-02 | 2015-12-15 | 2015-12-22 |  | A.P. CONSEBIDO CONSTRUCTION AND TRADING
10903 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 309107 | Pancol Brgy. HS - Banbanan Extension | TAYTAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8314965 |  |  | Completed | 1 |  |  | 4B0415S00066 | 15EE0114 | 2015-12-15 | 2015-12-03 | 2015-12-15 | 2015-12-22 |  | E.V. VILLAOS TRADING & CONSTRUCTION
10904 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301720 | Panlaitan NHS | BUSUANGA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6419337.6381 |  |  | Completed | 1 |  |  | 4B0415S00129 | 15EE0107 | 2015-12-01 | 2015-12-02 | 2015-12-14 | 2015-12-18 | 2015-12-29 |  | scarcity of materials (Gravel, sand, lumber), Transpo of materials
10905 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301721 | Pawa NHS - Caponayan Extension | CUYO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6489338 |  |  | Completed | 1 |  |  | 4B0415S00058 | 15EE0097 | 2015-11-22 | 2015-11-23 | 2015-12-04 | 2015-12-11 | 2015-12-21 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
10906 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301723 | Port Barton NHS | SAN VICENTE | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | Completed | 1 |  |  | 4B0415S00057 | 15EE0100 | 2015-12-01 | 2015-12-02 | 2015-12-14 | 2015-12-21 | 2015-12-29 | LEA & SONS TRADING AND CONSTRUCTION
10907 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301732 | San Jose (Roxas) NHS | ROXAS | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | Completed | 1
10908 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301737 | San Miguel NHS (Gaudencio Abordo NHS) | LINAPACAN | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | Completed | 1
10909 | NC 2015 | SHS (2015) | Region IV-B | Palawan |  | San Miguel NHS-Nangalao Extension | LINAPACAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6519338 |  |  | Completed | 1 |  |  | 4B0415S00053 | 15EE0101 | 2015-12-01 | 2015-12-02 | 2015-12-14 | 2015-12-21 | 2015-12-29 | A.P. CONSEBIDO CONSTRUCTION AND TRADING
10910 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301683 | Sandoval NHS (Casian NHS - Sandoval Annex) | TAYTAY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2922592 |  |  | Completed | 1
10911 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301745 | Tumarbong NHS | ROXAS | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Completed | 1
10912 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301745 | Tumarbong NHS | ROXAS | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10877343 |  |  | Completed | 1
10913 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111037 | Villa Libertad ES | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | 4B0415S00107 | 15EE0080 | 2015-11-08 | 2015-11-19 | 2015-11-20 | 2015-11-27 | 2015-12-07 | YURICH BUILDERS AND CONSTRUCTION SUPPLY
10914 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111038 | Villa Paz ES | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1
10915 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301657 | Abo-Abo NHS | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
10916 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301659 | Aborlan NHS | ABORLAN | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
10917 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170522 | Alfredo Gregorio Memorial ES | BATARAZA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4B0415S00084 | 15EF0153 | 2015-10-25 | 2015-10-29 | 2015-11-10 | 2015-11-23 | 2015-12-07 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
10918 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111084 | Aramaywan ES | QUEZON | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00100 | 15EF0143 | 2015-10-21 | 2015-10-23 | 2015-11-05
10919 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301663 | Aramaywan NHS | NARRA | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 11027343 |  |  | COMPLETED | 1
10920 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110863 | Aribungos ES | BROOKE'S POINT | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1
10921 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 309114 | Berong BHS (Quezon-Aramaywan NHS - Berong Brgy. HS) | QUEZON | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8314965 |  |  | COMPLETED | 1
10922 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 309114 | Berong BHS (Quezon-Aramaywan NHS - Berong Brgy. HS) | QUEZON | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8334965 |  |  | COMPLETED | 1
10923 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 309114 | Berong BHS (Quezon-Aramaywan NHS - Berong Brgy. HS) | QUEZON | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10997343 |  |  | COMPLETED | 1
10924 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110828 | Buliluyan ES | BATARAZA | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  | 4B0415S00080 | 15EF0150 | 2015-10-25 | 2015-10-29 | 2015-11-10 | 2015-11-23 | 2015-12-07 | R.C. TAGALA CONSTRUCTION
10925 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 301675 | Bunog NHS | RIZAL (MARCOS) | 2 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 7 | 4523637 |  |  | COMPLETED | 1 |  |  | 4B0415S00125 | 15EF0183 | 2015-11-22 | 2015-11-24 | 2015-12-08 |  |  | E.V. VILLAOS TRADING & CONSTRUCTION
10926 | NC 2015 | SHS (2015) | Region IV-B | Palawan |  | Candawaga NHS-Panalingaan Extension | RIZAL (MARCOS) | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 8 | 10997342.5917 |  |  | Completed | 1 |  |  | 4B0415S00133 | 15EF0135 | 2015-10-14 | 2015-10-16 | 2015-10-29 | 2015-11-25 | 2015-12-09 | ORANI BUILDERS & SUPPLY | Abandoned
10927 | NC 2015 | SHS (2015) | Region IV-B | Palawan |  | Candawaga NHS-Taburi Extension | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2088606 |  |  | COMPLETED | 1 |  |  | 4B0415S00046 | 15EF0156 | 2015-10-25 | 2015-10-29 | 2015-11-10 | 2015-11-23 | 2015-12-07 | R.C. TAGALA CONSTRUCTION
10928 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110798 | Catagupan ES (Narra) | BALABAC | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4B0415S00070 | 15EF0154 | 2015-10-25 | 2015-10-29 | 2015-11-10 | 2015-11-23 | 2015-12-07 | R.C. TAGALA CONSTRUCTION
10929 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301690 | Dumaguena NHS | NARRA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8314965 |  |  | COMPLETED | 1
10930 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301690 | Dumaguena NHS | NARRA | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10977343 |  |  | COMPLETED | 1
10931 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110902 | Ipaputo Elementary School | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00096 | 15EF0140 | 2015-10-21 | 2015-10-23 | 2015-11-05 |  |  | RHODAMAY CONSTRUCTION SUPPLY
10932 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111067 | Ipilan ES | NARRA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00094 | 15EF0138 | 2015-10-21 | 2015-10-23 | 2015-11-05
10933 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 301700 | Ipilan NHS | BROOKE'S POINT | 2 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 7 | 4573637 |  |  | COMPLETED | 1 |  |  | 4B0415S00124 | 15EF0184 | 2015-11-22 | 2015-11-24 | 2015-12-08 |  |  | E.V. VILLAOS TRADING & CONSTRUCTION
10934 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301701 | Isaub National High school | ABORLAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1968606 |  |  | COMPLETED | 1 |  |  | 4B0415S00052 | 15EG0056 | 2015-10-15 | 2015-10-23 | 2015-11-04 | 2015-11-12 | 2015-11-18 | PANAAD CONSTRUCTION
10935 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 309117 | Isugod NHS | QUEZON | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2827592 |  |  | COMPLETED | 1
10936 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 309117 | Isugod NHS | QUEZON | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1963606 |  |  | COMPLETED | 1
10937 | NC 2015 | SHS (2015) | Region IV-B | Palawan |  | J. P. Rizal NHS-Canipaan Extension | RIZAL (MARCOS) | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 8 | 11047342.5917 |  |  | COMPLETED | 1 |  |  | 4B0415S00131 | 15EF0136 | 2015-10-14 | 2015-10-16 | 2015-10-29
10938 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170519 | Labangan Elementary School | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00085 | 15EF0151 | 2015-10-25 | 2015-10-29 | 2015-11-10 | 2015-11-23 | 2015-12-07 | IVY MICHELLE TRADING & CONTRUCTION
10939 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301704 | Maasin NHS (Bernas NHS) | BROOKE'S POINT | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
10940 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 301706 | Magbabadil NHS | ABORLAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1988606 |  |  | COMPLETED | 1 |  |  | 4B0415S00123 | 15EG0071 | 2015-11-04 | 2015-11-12 | 2015-11-24 | 2015-12-03 | 2015-12-10 | R.C. TAGALA CONSTRUCTION
10941 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170503 | Manaile Elem. School | NARRA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00086 | 15EF0142 | 2015-10-21 | 2015-10-23 | 2015-11-05 | 2015-11-18 | 2015-12-03 | CRISHELLE CONSTRUCTION
10942 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111112 | Nabugsuan ES | QUEZON | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2852592.44 |  |  | COMPLETED | 1 |  |  | 4B0415S00087 | 15EF0144 | 2015-10-21 | 2015-10-23 | 2015-11-05 | 2015-11-18 | 2015-12-03 | CRISHELLE CONSTRUCTION
10943 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110909 | Naltep PS | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00095 | 15EF0141 | 2015-10-21 | 2015-10-23 | 2015-11-05 |  |  | SAMURAI CONSTRUCTION
10944 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111072 | Narra Pilot School | NARRA | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 6 | 10727342.5917 |  |  | COMPLETED | 1
10945 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111072 | Narra Pilot School | NARRA | 2 |  | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1
10946 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110841 | Pajo ES | BATARAZA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4B0415S00071 | 15EF0149 | 2015-10-21 | 2015-10-23 | 2015-11-05 | 2015-11-25 | 2015-12-09 | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
10947 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110815 | Panaan ES | BALABAC | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00072 | 15EF0155 | 2015-10-25 | 2015-10-29 | 2015-11-10 | 2015-11-23 | 2015-12-07 | R.C. TAGALA CONSTRUCTION
10948 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 301718 | Panacan NHS | NARRA | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 7 | 10877343 |  |  | COMPLETED | 1
10949 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301718 | Panacan NHS | NARRA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1
10950 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 301719 | Panitian National High School | SOFRONIO ESPAÑOLA | 2 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 7 | 4673637 |  |  | COMPLETED | 1 |  |  | 4B0415S00121 | 15EF0185 | 2015-11-22 | 2015-11-24 | 2015-12-08 |  |  | KIM HAROLD TRADING, MANUFACTURING & CONSTRUCTION
10951 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301722 | Plaridel NHS | ABORLAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8244965 |  |  | COMPLETED | 1
10952 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301724 | Princess Urduja NHS | NARRA | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
10953 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110894 | Proyekto Setias Mem. ES (Tagpirara ES) | BROOKE'S POINT | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1
10954 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301726 | Quezon NHS | QUEZON | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
10955 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301727 | Quezon-Aramaywan NHS | QUEZON | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
10956 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301728 | Quezon-Panitian NHS | QUEZON | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6399338 |  |  | COMPLETED | 1
10957 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 301729 | Quinlogan NHS | QUEZON | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6399338 |  |  | COMPLETED | 1 |  |  | 4B0415S00049 | 15EF0105 | 2015-09-14 | 2015-09-15 | 2015-09-29 | 2015-10-16 | 2015-10-22 | M.M. RODRIGUEZ TRADING AND CONSTRUCTION
10958 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 309116 | Ransang NHS | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 4B0415S00118 | 15EF0177 | 2015-11-05 | 2015-11-06 | 2015-11-20 | 2015-12-02 | 2015-12-16 | LEA & SONS TRADING AND CONSTRUCTION
10959 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170536 | Reservation Elementary School | QUEZON | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00083 | 15EF0145 | 2015-10-21 | 2015-10-23 | 2015-11-05 | 2015-11-18 | 2015-12-03 | IVY MICHELLE TRADING & CONTRUCTION
10960 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110845 | Rio Tuba Central School | BATARAZA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4B0415S00089 | 15EF0152 | 2015-10-25 | 2015-10-29 | 2015-11-10 | 2015-11-23 | 2015-12-07 | R.C. TAGALA CONSTRUCTION
10961 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 301739 | Sandoval National High School | NARRA | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
10962 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 309129 | Southern Bataraza NHS | BATARAZA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6394338 |  |  | COMPLETED | 1
10963 | NC 2015 | TECHVOC (2015) | Region IV-B | Palawan | 309129 | Southern Bataraza NHS | BATARAZA | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2579549.27 |  |  | COMPLETED | 1
10964 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 110854 | Sumbiling ES | BATARAZA | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 4B0414S00104 | 14EF0035 | 2014-08-25 | 2014-08-29 | 2014-09-10 | 2014-09-24 | 2014-10-08 | RHODAMAY CONSTRUCTION SUPPLY
10965 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 111078 | Tacras ES | NARRA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00081 | 15EF0139 | 2015-10-21 | 2015-10-23 | 2015-11-05 | 2015-11-18 | 2015-12-03 | CRISHELLE CONSTRUCTION
10966 | NC 2015 | SHS (2015) | Region IV-B | Palawan | 309126 | Tarusan NHS | BATARAZA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8324965 |  |  | COMPLETED | 1 |  |  | 4B0415S00063 | 15EF0172 | 2015-11-05 | 2015-11-06 | 2015-11-19 | 2015-12-01 | 2015-12-16 | L.B. LEONCIO TRADING & CONSTRUCTION
10967 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 170551 | Tulatula Primary School | BROOKE'S POINT | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00082 | 15EF0147 | 2015-10-21 | 2015-10-23 | 2015-11-05
10968 | NC 2015 | K10 (2015) | Region IV-B | Palawan | 301733 | Vito Pechangco MNHS (Salogon NHS) | BROOKE'S POINT | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2802592 |  |  | COMPLETED | 1 |  |  | 4B0415S00120 | 15EF0157 | 2015-10-25 | 2015-10-29 | 2015-11-10 | 2015-11-23 | 2015-12-07 | R.C. TAGALA CONSTRUCTION
10969 | NC 2015 | K10 (2015) | Region IV-B | Puerto Princesa City | 111484 | Luzviminda ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00076 | 15EG0055 | 2015-10-15 | 2015-10-23 | 2015-11-04 | 2015-11-12 | 2015-11-18 | LEA & SONS TRADING AND CONSTRUCTION
10970 | NC 2015 | K10 (2015) | Region IV-B | Puerto Princesa City | 171504 | Matahimik-Bucana ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00090 | 15EG0054 | 2015-10-15 | 2015-10-23 | 2015-11-04 | 2015-11-12 | 2015-11-18 | R.C. TAGALA CONSTRUCTION
10971 | NC 2015 | TECHVOC (2015) | Region IV-B | Puerto Princesa City | 309301 | Palawan National School | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4939098.54 |  |  | COMPLETED | 1
10972 | NC 2015 | TECHVOC (2015) | Region IV-B | Puerto Princesa City | 301793 | San Jose NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
10973 | NC 2015 | SHS (2015) | Region IV-B | Puerto Princesa City |  | SHS in Puerto Princesa City | Puerto Princesa | 2 | 1 | 24 | 2STY12CL | 2015 SHS BATCH 5 | 29308434 |  |  | COMPLETED | 1 |  |  | 4B0415S00045 | 15EG0062 | 2015-10-26 | 2015-11-04 | 2015-11-16 | 2015-11-20 | 2015-12-02 | IVY MICHELLE TRADING & CONTRUCTION
10974 | NC 2015 | K10 (2015) | Region IV-B | Puerto Princesa City | 111492 | Sicsican ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0415S00078 | 15EG0054 | 2015-10-15 | 2015-10-23 | 2015-11-04 | 2015-11-12 | 2015-11-18 | R.C. TAGALA CONSTRUCTION
10975 | NC 2015 | SHS (2015) | Region IV-B | Romblon | 301747 | Alcantara NHS | ALCANTARA | 0 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 2 | 21648013.45 |  |  | COMPLETED | 1 |  |  | 4B0515S00007 | 15EH0106 | 2015-09-30 | 2015-10-01 | 2015-10-13 | 2015-11-11 | 2015-11-23 | ARKY CONSTRUCTION AND SUPPLY
10976 | NC 2015 | K10 (2015) | Region IV-B | Romblon | 111321 | Balatucan ES | LOOC | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0515S00011 | 15EH0097 | 2015-09-17 | 2015-09-18 | 2015-09-30 | 2015-11-03 | 2015-11-24 | TWIN DRAGON CONSTRUCTION
10977 | NC 2015 | K10 (2015) | Region IV-B | Romblon | 111268 | Banice ES | BANTON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 4B0515S00010
10978 | NC 2015 | K10 (2015) | Region IV-B | Romblon | 111404 | Fetalvero-Mingoa MS | CALATRAVA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0515S00014 | 15EH0099 | 2015-09-17 | 2015-09-18 | 2015-09-30 | 2015-11-03 | 2015-11-24 | ALNAP CONSTRUCTION AND ENGINEERING
10979 | NC 2015 | K10 (2015) | Region IV-B | Romblon | 111329 | Looc CES | LOOC | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0515S00013 | 15EH0100 | 2015-09-17 | 2015-09-18 | 2015-09-30 | 2015-11-03 | 2015-11-24 | TWIN DRAGON CONSTRUCTION
10980 | NC 2015 | SHS (2015) | Region IV-B | Romblon | 301753 | Lumbang East NHS-(Caj. NHS Ext.) | CAJIDIOCAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6539338 |  |  | COMPLETED | 1 |  |  | 4B0515S00009
10981 | NC 2015 | K10 (2015) | Region IV-B | Romblon | 111356 | Odiongan South CES | ODIONGAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4B0515S00012 | 15EH0098 | 2015-09-17 | 2015-09-18 | 2015-09-30 | 2015-11-03 | 2015-11-24 | TWIN DRAGON CONSTRUCTION
10982 | NC 2015 | SHS (2015) | Region IV-B | Romblon | 301770 | Romblon NHS, Romblon | ROMBLON (Capital) | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22212343.62 |  |  | COMPLETED | 1 |  |  | 4B0515S00008 | 15EH0105 | 2015-11-12 | 2015-11-13 | 2015-11-25 | 2015-12-04 | 2015-12-11 | ARKY CONSTRUCTION AND SUPPLY
17918 | NC 2016 | SHS | Region IV-B | Calapan City | 301798 | Canubing National High School | City Of Calapan (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6777351.59 |  |  | Completed | 1 |  |  | P00073264LZ | 16ED0065 | 2016-06-08 | 2016-06-16 | 2016-08-04 | 2016-08-17 | 2016-08-31 | DK CONSTRUCTION
17919 | NC 2016 | SHS | Region IV-B | Calapan City | 301797 | Community Vocational High School | City Of Calapan (Capital) | 1 | 1 | 16 | 2STY8CL | BATCH 9 CL | 22079735.1834 |  |  | Completed | 1 |  |  | P00073265LZ | 16ED0069 | 2016-07-29 | 2016-08-08 |  | 2016-09-02 | 2016-09-14 | MONOLITHIC CONST. & CONC. PRODUCTS, INC.
17920 | NC 2016 | TECHVOC | Region IV-B | Calapan City | 301797 | Community Vocational High School | City Of Calapan (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 |  |  | P00074446LZ | 16ED0044 | 2016-05-31 | 2016-06-09 | 2016-06-28 | 2016-07-04 | 2016-07-13 | KARANGYAN BLDRS. & TRADERS
17921 | NC 2016 | SHS | Region IV-B | Calapan City | 301805 | Managpi National High School | City Of Calapan (Capital) | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13280440 |  |  | Completed | 1 |  |  | P00073266LZ | 16ED0066 | 2016-07-29 | 2016-08-08 |  | 2016-09-02 | 2016-09-14 | I. A. BOSGUE CONST. CORP.
17922 | NC 2016 | TECHVOC | Region IV-B | Calapan City | 301805 | Managpi National High School | City Of Calapan (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2752716.3457 |  |  | Completed | 1 |  |  | P00074447LZ | 16ED0043 | 2016-05-31 | 2016-06-09 | 2016-06-28 | 2016-07-04 | 2016-07-13 | MARC JILL CONST.
17923 | NC 2016 | SHS | Region IV-B | Calapan City | 301802 | Nag-Iba National High School | City Of Calapan (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.64 |  |  | Completed | 1 |  |  | P00070478LZ | 16ED0059 | -395769 | 2016-06-16 | 2016-08-04 | 2016-08-15 | 2016-08-31 | DEL ROL ENT.
17924 | NC 2016 | SHS | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | City Of Calapan (Capital) | 1 | 1 | 24 | 2STY12CL | BATCH 3 CL | 30322440 |  |  | Completed | 1 |  |  | P00070479LZ | 16ED0060 | -395769 | 2016-06-16 | 2016-07-28 | 2016-08-22 | 2016-09-12 | ETVR TRADING & CONST.
17925 | NC 2016 | SHS | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | City Of Calapan (Capital) | 1 |  | 8 | 2STY8CL | BATCH 3 CL | 11310050 |  |  | Completed | 1 |  |  | P00070480LZ | 16ED0061 | -395769 | 2016-06-16 | 2016-07-28 | 2016-08-09 | 2016-08-17 | ETVR TRADING & CONST.
17926 | NC 2016 | SHS | Region IV-B | Marinduque | 301530 | Balanacan Nhs | Mogpog | 0 | 1 | 9 | 3STY9CL | BATCH 5 CL | 16763095.25 |  |  | Completed | 1
17927 | NC 2016 | SHS | Region IV-B | Marinduque | 301532 | Bognuyan Nhs | Gasan | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6485626.319 |  |  | Completed | 1
17928 | NC 2016 | SHS | Region IV-B | Marinduque | 301532 | Bognuyan Nhs | Gasan | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 9150921.402 |  |  | Completed | 1
17929 | NC 2016 | SHS | Region IV-B | Marinduque | 301533 | Bonliw Nhs | Torrijos | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7059509.662 |  |  | Completed | 1
17930 | NC 2016 | SHS | Region IV-B | Marinduque | 301534 | Botilao Nhs | Santa Cruz | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7059509.662 |  |  | Completed | 1
17931 | NC 2016 | SHS | Region IV-B | Marinduque | 301536 | Buenavista Nhs - Bagacay Annex | Buenavista | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6802407.63 |  |  | Completed | 1
17932 | NC 2016 | SHS | Region IV-B | Marinduque | 301542 | Dolores Nhs | Santa Cruz | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6485626.319 |  |  | Completed | 1
17933 | NC 2016 | K10 | Region IV-B | Marinduque | 301543 | Hupi National High School | Santa Cruz | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7059509.662 |  |  | Completed | 1
17934 | NC 2016 | SHS | Region IV-B | Marinduque | 301544 | Ilaya Nhs | Boac (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 9085667.05 |  |  | Completed | 1
17935 | NC 2016 | SHS | Region IV-B | Marinduque | 301547 | Kilo-Kilo Nhs | Santa Cruz | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9046166.455 |  |  | Completed | 1
17936 | NC 2016 | SHS | Region IV-B | Marinduque | 301548 | Landy National High School | Santa Cruz | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6485626.319 |  |  | Completed | 1
17937 | NC 2016 | SHS | Region IV-B | Marinduque | 301549 | Makapuyat Nhs | Santa Cruz | 0 | 1 | 12 | 2STY6CL | BATCH 1 CL | 21239674.52 |  |  | Completed | 1
17938 | NC 2016 | SHS | Region IV-B | Marinduque | 301550 | Makapuyat Nhs - Masaguisi Annex | Santa Cruz | 0 | 1 | 6 | 2STY6CL | BATCH 1 CL | 10619837.26 |  |  | Completed | 1
17939 | NC 2016 | K10 | Region IV-B | Marinduque | 301557 | Mogpog National Comprehensive High School | Mogpog | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6485626.319 |  |  | Completed | 1
17940 | NC 2016 | K10 | Region IV-B | Marinduque | 301557 | Mogpog National Comprehensive High School | Mogpog | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 16708695.494 |  |  | Completed | 1
17941 | NC 2016 | SHS | Region IV-B | Marinduque | 301558 | Mongpong Nhs | Santa Cruz | 0 | 1 | 4 | 2STY4CL | BATCH 1 CL | 10455499.5981 |  |  | Completed | 1
17942 | NC 2016 | SHS | Region IV-B | Marinduque | 308804 | Paciano A. Sena Mem. Hs (Tabionan Nhs) | Gasan | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7059509.662 |  |  | Completed | 1
17943 | NC 2016 | SHS | Region IV-B | Marinduque | 301560 | Punong Nhs | Santa Cruz | 0 | 1 | 4 | 2STY4CL | BATCH 1 CL | 7525669.4581 |  |  | Completed | 1
17944 | NC 2016 | SHS | Region IV-B | Marinduque | 301565 | Tapuyan Nhs | Gasan | 0 | 1 | 10 | 2STY10CL | BATCH 5 CL | 14733227.22 |  |  | Completed | 1
17945 | NC 2016 | SHS | Region IV-B | Marinduque |  | Tigwi Nhs To Tigwi Shs | Torrijos | 0 | 1 | 12 | 2STY6CL | BATCH 1 CL | 22625402.48 |  |  | Completed | 1
17946 | NC 2016 | SHS | Region IV-B | Marinduque | 301568 | Yook Nhs | Buenavista | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6485626.319 |  |  | Completed | 1
17947 | NC 2016 | SHS | Region IV-B | Occidental Mindoro | 301600 | Central Nhs | San Jose | 0 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10867131.51 |  |  | Completed | 1
17948 | NC 2016 | K10 | Region IV-B | Occidental Mindoro | 110166 | Karyandangan Min. School | Mamburao (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6619337.64 |  |  | Completed | 1
17949 | NC 2016 | SHS | Region IV-B | Occidental Mindoro | 301588 | Magsaysay Nhs | Magsaysay | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8594965.051 |  |  | Completed | 1
17950 | NC 2016 | SHS | Region IV-B | Occidental Mindoro | 301593 | Occidental Mindoro Nhs | Mamburao (Capital) | 0 | 1 | 15 | 3STY15CL | BATCH 11 CL | 21383013.45 |  |  | Completed | 1
17951 | NC 2016 | SHS | Region IV-B | Occidental Mindoro | 301594 | Paluan Nhs | Paluan | 0 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15571327.92 |  |  | Completed | 1
17952 | NC 2016 | K10 | Region IV-B | Occidental Mindoro | 301592 | Pedro T. Mendiola Sr. Memorial National High School | San Jose | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.5917 |  |  | Completed | 1
17953 | NC 2016 | SHS | Region IV-B | Occidental Mindoro | 301595 | Rizal National High School | Rizal | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8564965.051 |  |  | Completed | 1
17954 | NC 2016 | K10 | Region IV-B | Occidental Mindoro | 301596 | Sablayan Nchs | Sablayan | 0 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15121327.92 |  |  | Completed | 1
17955 | NC 2016 | K10 | Region IV-B | Occidental Mindoro | 308901 | San Jose National Agricultural And Industrial High School | San Jose | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8464965.051 |  |  | Completed | 1
17956 | NC 2016 | SHS | Region IV-B | Occidental Mindoro | 301599 | San Jose Nhs | San Jose | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8514965.051 |  |  | Completed | 1
17957 | NC 2016 | SHS | Region IV-B | Occidental Mindoro | 301601 | San Vicente Nhs | Sablayan | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8564965.051 |  |  | Completed | 1
17958 | NC 2016 | K10 | Region IV-B | Occidental Mindoro | 301604 | Santa Cruz Nhs - Pinagturilan Annex | Santa Cruz | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8564965.051 |  |  | Completed | 1
17959 | NC 2016 | K10 | Region IV-B | Oriental Mindoro | 309008 | Anastacio Dela Chica High School | Baco | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 |  |  | P00073274LZ | [5 empty] | 2016-11-16 | King,s Builders & Dev't. Corp./CMSDEL Const. & Developer JV
17960 | NC 2016 | TECHVOC | Region IV-B | Oriental Mindoro | 309008 | Anastacio Dela Chica High School | Baco | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1 |  |  | P00074449LZ | 16ED0045 |  |  |  |  | 2016-07-19 | B5 Builders
17961 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301611 | Apitong Nhs | Naujan | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 |  |  | P00072283LZ | 16ED0058 |  |  |  |  | 2016-07-25 | Anjet Const. Supplies & Labor Services
17962 | NC 2016 | K10 | Region IV-B | Oriental Mindoro | 301628 | Arceli B. Pantilanan - Bacawan High School | Pola | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2904910.93 |  |  | Completed | 1 |  |  | P00072288LZ | [5 empty] | 2016-10-06 | LTDL Builders
17963 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301613 | Aurelio Arago Mnhs | Victoria | 1 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26852469.42 |  |  | Completed | 1 |  |  | P00070477LZ | [5 empty] | 2017-01-15 | St. Gerald Const.
17964 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301614 | Aurora Nhs | Naujan | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.09 |  |  | Completed | 1 |  |  | P00072284LZ | 16ED0062 |  |  |  |  | 2016-08-29 | 811 Trading & Const.
17965 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301616 | Baco Nhs | Baco | 1 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26702469.42 |  |  | Completed | 1 |  |  | P00070474LZ
17966 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301619 | Bayuin Nhs | Socorro | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 |  |  | P00072291LZ | 16ED0057 |  |  |  |  | 2016-07-19 | Anjet Const. Supplies & Labor Services
17967 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301627 | Domingo Yu Chu Nhs | Pola | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 |  |  | P00073289LZ
17968 | NC 2016 | K10 | Region IV-B | Oriental Mindoro | 301630 | Doroteo S. Mendoza Sr. Mnhs | Naujan | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 |  |  | P00072285LZ | 16ED0063 |  |  |  |  | 2016-08-22 | 811 Trading & Const.
17969 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 309001 | Inarawan Nhs | Naujan | 1 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18764436.85 |  |  | Completed | 1 |  |  | P00072286LZ | [5 empty] | 2016-11-17 | King's Builders & Dev't Corp./ CMSDEL Const. & Developer
17970 | NC 2016 | K10 | Region IV-B | Oriental Mindoro | 309025 | Leandro Panganiban, Sr. - Tagumpay High School | Pola | 1 | 1 | 5 | 1STY5CL | BATCH 7 CL | 4700731.46 |  |  | Completed | 1 |  |  | P00072289LZ | 16ED0089
17971 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301634 | Leuteboro Nhs | Socorro | 1 | 1 | 20 | 4STY20CL | BATCH 1 CL | 33110063.69 |  |  | Completed | 1 |  |  | P00070089LZ | [5 empty] | 2017-01-16 | Jasmig Const. Supply
17972 | NC 2016 | K10 | Region IV-B | Oriental Mindoro | 301612 | Macatoc Nhs | Victoria | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072292LZ | 16ED0064 |  |  |  |  | 2016-09-06 | B5 Builders & Supplies/ FS Sugay JV
17973 | NC 2016 | K10 | Region IV-B | Oriental Mindoro | 301629 | Matulatula High School | Pola | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8456914 |  |  | Completed | 1 |  |  | P00073290LZ | 16ED0068 |  |  |  |  | 2016-09-06 | Greatlakes Ent.
17974 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301642 | Melgar Nhs | Naujan | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 |  |  | P00073286LZ | 16ED0067 |  |  |  |  | 2016-09-06 | ETVR Trading & Const.
17975 | NC 2016 | K10 | Region IV-B | Oriental Mindoro | 301645 | Naujan Municipal High School | Naujan | 1 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 |  |  | P00072287LZ | [5 empty] | 2016-11-17 | CMSEL Const. & Developer
17976 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301648 | Porfirio Comia Mnhs | Naujan | 1 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22422484.24 |  |  | Completed | 1 |  |  | P00070475LZ | [5 empty] | 2016-12-08 | Zoe Builders & Supplies Const./ Sanlahi Group JV.
17977 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 309004 | Puerto Galera Nhs | Puerto Galera | 1 | 1 | 9 | 3STY9CL | BATCH 3 CL | 16659208.67 |  |  | Completed | 1 |  |  | P00070476LZ | [5 empty] | 2016-11-16 | FEAJ Const. & Gen. Services
17978 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 309035 | Puerto Galera Nhs - San Isidro Ext. | Puerto Galera | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  | P00072290LZ | [5 empty] | 2016-12-13 | L.N. Salvador Const.
17979 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301651 | San Agustin Nhs | Naujan | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013.45 |  |  | Completed | 1 |  |  | P00073287Z | [5 empty] | 2016-11-17 | RREncabo Contructors, Inc./ Marc Jill Const. JV
17980 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301653 | San Teodoro Nhs | San Teodoro | 1 | 1 | 12 | 3STY6CL | BATCH 9 CL | 20834263.02 |  |  | Completed | 1 |  |  | P00073292LZ | [5 empty] | 2016-11-16 | RR Encabo Constructors, Inc./ Marc Jill Const. JV
17981 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301610 | Alcadesma Nhs | Bansud | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23463848.7681 |  |  | Completed | 1 |  |  | P00073275LZ
17982 | NC 2016 | TECHVOC | Region IV-B | Oriental Mindoro | 301610 | Alcadesma Nhs | Bansud | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2539544.27 |  |  | Completed | 1 |  |  | P00074450LZ | [5 empty] | 2016-08-04 | Alberto Uy Const. & Dev't
17983 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301617 | Balugo Nhs | Mansalay | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11291397.03 |  |  | Completed | 1 |  |  | P00072305LZ
17984 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301618 | Bansud Nhs - Regional Science High School | Bansud | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072293LZ | [7 empty] | With Approved Buffer Fund (2018 Batch 2)
17985 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301623 | Bulbugan Nhs | Gloria | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072303LZ | [7 empty] | With Approved Buffer Fund (2018 Batch 2)
17986 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 309006 | Carmundo Nhs | Bongabong | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072297LZ
17987 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301624 | Cawayan Nhs | Bongabong | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8295614.7 |  |  | Completed | 1 |  |  | P00073276LZ
17988 | NC 2016 | TECHVOC | Region IV-B | Oriental Mindoro | 301624 | Cawayan Nhs | Bongabong | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2539544.27 |  |  | Completed | 1 |  |  | P00074451LZ | [5 empty] | 2016-08-04 | ADL Constrak
17989 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301625 | Dayhagan Nhs | Bongabong | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11423310.398 |  |  | Completed | 1 |  |  | P00073277LZ
17990 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 309027 | Felimon M. Salcedo Sr. Mnhs | Bansud | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072294LZ
17991 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301633 | Kaligtasan Nhs | Bongabong | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072298LZ
17992 | NC 2016 | K10 | Region IV-B | Oriental Mindoro | 309005 | Labasan Nhs | Bongabong | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8295614.7 |  |  | Completed | 1 |  |  | P00072299LZ
17993 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301636 | Malamig Nhs | Gloria | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072304LZ
17994 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301638 | Manaul Nhs | Mansalay | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072306LZ
17995 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301641 | Masaguisi Nhs | Bongabong | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8295614.7 |  |  | Completed | 1 |  |  | P00072299LZ
17996 | NC 2016 | TECHVOC | Region IV-B | Oriental Mindoro | 301621 | Maujao Nhs | Bulalacao (San Pedro) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2539544.27 |  |  | Completed | 1 |  |  | P00074453LZ | [5 empty] | 2016-08-04 | Lumel Glenn Construction
17997 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301621 | Maujao Nhs | Bulalacao (San Pedro) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8295614.7 |  |  | Completed | 1 |  |  | P00073279LZ
17998 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301643 | Morente Nhs | Bongabong | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11291397.03 |  |  | Completed | 1 |  |  | P00072301LZ
17999 | NC 2016 | TECHVOC | Region IV-B | Oriental Mindoro | 309019 | Pag-Asa Nhs | Bansud | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2539544.27 |  |  | Completed | 1 | [8 empty] | 2016-09-13 | D.M. Maliwanag
18000 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 309019 | Pag-Asa Nhs | Bansud | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8295614.7 |  |  | Completed | 1 |  |  | P00072295LZ
18001 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301646 | Pambisan Nhs | Pinamalayan | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11291397.03 |  |  | Completed | 1 |  |  | P00072307LZ | [7 empty] | With Approved Buffer Fund (2018 Batch 2)
18002 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301647 | Pili Nhs | Pinamalayan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072308LZ
18003 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301649 | Quinabigan Nhs | Pinamalayan | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16342775.6863 |  |  | Completed | 1 |  |  | P00073288LZ | [7 empty] | With Approved Buffer Fund (2019)
18004 | NC 2016 | TECHVOC | Region IV-B | Oriental Mindoro | 301652 | San Mariano Nhs | Roxas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2539544.27 |  |  | Completed | 1 |  |  | P00074448LZ | [5 empty] | 2016-08-04 | Green Island Enterprises
18005 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301652 | San Mariano Nhs | Roxas | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20000467.74 |  |  | Completed | 1 |  |  | P00073291LZ
18006 | NC 2016 | TECHVOC | Region IV-B | Oriental Mindoro | 301622 | San Roque Nhs | Bulalacao (San Pedro) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2539544.27 |  |  | Completed | 1 | [8 empty] | 2016-11-20 | SOSEP Builders
18007 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301622 | San Roque Nhs | Bulalacao (San Pedro) | 2 | 1 | 12 | 3STY12CL | BATCH 7 CL | 20000467.74 |  |  | Completed | 1 |  |  | P00072302LZ
18008 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301654 | Vicente B. Ylagan Nhs | Bongabong | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8295614.7 |  |  | Completed | 1 |  |  | P00073278LZ
18009 | NC 2016 | TECHVOC | Region IV-B | Oriental Mindoro | 301654 | Vicente B. Ylagan Nhs | Bongabong | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2539544.27 |  |  | Completed | 1 |  |  | P00074452LZ | [5 empty] | 2016-08-04 | Lumel Glenn Construction
18010 | NC 2016 | TECHVOC | Region IV-B | Oriental Mindoro | 301655 | Villapagasa Nhs | Bansud | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5079088.54 |  |  | Completed | 1 | [8 empty] | 2016-09-11 | Martinez Enterprises
18011 | NC 2016 | SHS | Region IV-B | Oriental Mindoro | 301655 | Villapagasa Nhs | Bansud | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13183972.54 |  |  | Completed | 1 |  |  | P00072296LZ
18012 | NC 2016 | SHS | Region IV-B | Palawan | 301659 | Aborlan Nhs | Aborlan | 2 | 1 | 30 | 3STY15CL | BATCH 9 CL | 47521109.59 |  |  | Completed | 1 |  |  | 16EG0046 | P00073294 LZ CW1 |  |  | 00:00:00 |  | 2016-07-22 | A.R. Lustre Jr.Construction
18013 | NC 2016 | SHS | Region IV-B | Palawan | 301660 | Alimanguan Nhs | San Vicente | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6821377.944 |  |  | Completed | 1 |  |  |  | P00072332LZ 16EE0028 |  |  | 00:00:00 |  | 2016-07-18 | KIM HAROLD TRADING & CONST.
18014 | NC 2016 | K10 | Region IV-B | Palawan | 110715 | Apoc-Apoc Es | Aborlan | 3 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8666522 |  |  | Completed | 1 |  |  |  | 0 |  |  | 2016-06-09 |  | 2016-06-29 | E.V. Villaos Trdg. & Construction
18015 | NC 2016 | K10 | Region IV-B | Palawan | 309109 | Bacao Nhs (Dumaran Nhs - Bacao Nhs) | Dumaran | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1167553.792 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18016 | NC 2016 | SHS | Region IV-B | Palawan | 301661 | Apurawan Nhs | Aborlan | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12129626.8509 |  |  | Completed | 1 |  |  | 16EG0049 | P00073294LZ CW1 |  |  | 00:00:00 |  | 2016-07-22 | PTK Group Inc. & Ivy Michelle T&C (Joint Venture)
18017 | NC 2016 | SHS | Region IV-B | Palawan | 301662 | Araceli Nhs | Araceli | 1 | 1 | 18 | 3STY9CL | BATCH 7 CL | 32455759.32 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18018 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301667 | Barotuan Nhs | El Nido (Bacuit) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2804658.648 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18019 | NC 2016 | K10 | Region IV-B | Palawan | 309138 | Araceli Plainview Nhs | Araceli | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 7053201.888 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18020 | NC 2016 | SHS | Region IV-B | Palawan | 301663 | Aramaywan Nhs | Narra | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21565910 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18021 | NC 2016 | SHS | Region IV-B | Palawan | 301663 | Aramaywan Nhs | Narra | 2 |  | 9 | 3STY9CL | BATCH 9 CL | 15317811 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18022 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301663 | Aramaywan Nhs | Narra | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 |  |  | 16EF0069 | P00074461LZ |  |  | 00:00:00 |  | 00:00:00 | CRISHELLE CONSTRUCTION
18023 | NC 2016 | TECHVOC | Region IV-B | Palawan | 309109 | Bacao Nhs (Dumaran Nhs - Bacao Nhs) | Dumaran | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2819272.06 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18024 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301666 | Balabac Nhs | Balabac | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2924570 |  |  | Completed | 1 |  |  | 16EF0096 | P00075085LZ |  |  | 00:00:00 |  | 2016-10-07 | SYNDITE CONSTRUCTION
18025 | NC 2016 | K10 | Region IV-B | Palawan | 309113 | Bancalaan National High School | Balabac | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 19781260 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18026 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301681 | Caruray Nhs | San Vicente | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2788601.442 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18027 | NC 2016 | K10 | Region IV-B | Palawan | 309113 | Bancalaan National High School | Balabac | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 7233509.4 |  |  | Completed | 1 |  |  | 16EF0112 | P00073298LZ |  |  | 00:00:00 |  | 2016-10-04 | SYNDITE CONSTRUCTION
18028 | NC 2016 | SHS | Region IV-B | Palawan | 301667 | Barotuan Nhs | El Nido (Bacuit) | 1 | 1 | 24 | 3STY12CL | BATCH 7 CL | 37706473.6 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18029 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301668 | Bataraza National High School | Bataraza | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2791635 |  |  | Completed | 1 |  |  | 16EF0073 | P00074456LZ |  |  | 00:00:00 |  | 2016-08-14 | JIBER CONSTRUCTION
18030 | NC 2016 | TECHVOC | Region IV-B | Palawan | 309120 | Concepcion National High School | Agutaya | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2924570 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18031 | NC 2016 | K10 | Region IV-B | Palawan | 301668 | Bataraza National High School | Bataraza | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 22444664.1225 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18032 | NC 2016 | K10 | Region IV-B | Palawan | 301668 | Bataraza National High School | Bataraza | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18033 | NC 2016 | SHS | Region IV-B | Palawan | 301669 | Bato Nhs | Taytay | 1 | 1 | 24 | 3STY12CL | BATCH 7 CL | 37492314.4 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18034 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301669 | Bato Nhs | Taytay | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5577202.884 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18035 | NC 2016 | K10 | Region IV-B | Palawan | 111088 | Berong Es | Quezon | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8961499.2 |  |  | Completed | 1
18036 | NC 2016 | K10 | Region IV-B | Palawan | 301674 | Bugsuk Nhs - Mangsee Annex | Balabac | 2 |  | 8 | 1STY4CL | BATCH 9 CL | 8385025.5115 |  |  | Completed | 1 |  |  | 16EF0129 | 0 |  |  | 00:00:00 |  | 2016-10-07 | SYNDITE CONSTRUCTION
18037 | NC 2016 | K10 | Region IV-B | Palawan | 301674 | Bugsuk Nhs - Mangsee Annex | Balabac | 2 | 1 | 10 | 1STY5CL | BATCH 9 CL | 9401462.9386 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18038 | NC 2016 | K10 | Region IV-B | Palawan | 111214 | Bulalo Es | Taytay | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6898652.592 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18039 | NC 2016 | K10 | Region IV-B | Palawan | 309139 | Cabigaan Nhs | Aborlan | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6248582 |  |  | Completed | 1 |  |  |  | 0 |  |  | 2016-06-24 |  | 2016-07-12 | Samurai Construction
18040 | NC 2016 | K10 | Region IV-B | Palawan | 110751 | Cabugawan Es To Bacao Es | Dumaran | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1154484.16 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18041 | NC 2016 | SHS | Region IV-B | Palawan | 301678 | Calandagan Nhs | Araceli | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 12729237.892 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18042 | NC 2016 | K10 | Region IV-B | Palawan | 110758 | Calasag Es | Dumaran | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1154484.16 |  |  | Completed | 1 |  |  |  | P00072339LZ 16EE0025 |  |  | 00:00:00 |  | 2016-06-27 | 12-30 Construction
18043 | NC 2016 | K10 | Region IV-B | Palawan | 309155 | Calasaguen Nhs | Brooke'S Point | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9129337.28 |  |  | Completed | 1
18044 | NC 2016 | K10 | Region IV-B | Palawan | 301680 | Candawaga National High School | Rizal (Marcos) | 2 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20993211.619 |  |  | Completed | 1
18045 | NC 2016 | SHS | Region IV-B | Palawan | 309160 | Canipaan Nhs | Rizal (Marcos) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7233509 |  |  | Completed | 1 |  |  | 16EF0110 | P00073321LZ |  |  | 00:00:00 |  | 2016-10-03 | SYNDITE CONSTRUCTION
18046 | NC 2016 | TECHVOC | Region IV-B | Palawan | 309160 | Canipaan Nhs | Rizal (Marcos) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2792510 |  |  | Completed | 1 |  |  | 16EF0076 | P00074466LZ |  |  | 00:00:00 |  | 2016-08-14 | CRISHELLE TRADING & CONSTRUCTION
18047 | NC 2016 | SHS | Region IV-B | Palawan | 301681 | Caruray Nhs | San Vicente | 1 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18746157.2 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 | With approved additional funds
18048 | NC 2016 | SHS | Region IV-B | Palawan | 111143 | Casian Nhs To Caramay Es | Taytay | 1 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16922093.1778 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18049 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301682 | Casian Nhs | Taytay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2787157.648 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18050 | NC 2016 | K10 | Region IV-B | Palawan | 309103 | Central Taytay Nhs | Taytay | 1 | 1 | 40 | 4STY20CL | BATCH 7 CL | 65758442.7717 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18051 | NC 2016 | TECHVOC | Region IV-B | Palawan | 309107 | Pancol Brgy. Nhs | Taytay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2787157.648 |  |  | Completed | 1 |  |  |  | P00073348LZ 16EE0054 |  |  | 00:00:00 |  | 00:00:00 | 0
18052 | NC 2016 | K10 | Region IV-B | Palawan | 309107 | Pancol Brgy. Nhs | Taytay | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1141414.528 |  |  | Completed | 1 |  |  |  | P00073348LZ 16EE0054 |  |  | 00:00:00 |  | 00:00:00 | 0
18053 | NC 2016 | K10 | Region IV-B | Palawan | 309103 | Central Taytay Nhs | Taytay | 1 |  | 4 | 2STY4CL | BATCH 7 CL | 6860015.268 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18054 | NC 2016 | K10 | Region IV-B | Palawan | 309134 | Cheey National High School | Busuanga | 1 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10484355.735 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18055 | NC 2016 | K10 | Region IV-B | Palawan | 301684 | Coron Sof | Coron | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 15421785.2089 |  |  | Completed | 1
18056 | NC 2016 | K10 | Region IV-B | Palawan | 110829 | Culandanum Es | Bataraza | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12566775.41 |  |  | Completed | 1
18057 | NC 2016 | K10 | Region IV-B | Palawan | 170506 | San Felipe Es | Araceli | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1167553.792 |  |  | Completed | 1 |  |  |  | P00072337lz 16EE0026 |  |  | 00:00:00 |  | 2016-06-27 | Yurich Builders & Construction
18058 | NC 2016 | K10 | Region IV-B | Palawan | 301686 | Culandanum Nhs | Aborlan | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12129626.8509 |  |  | Completed | 1 |  |  | 16EG0050 | P00073295LZ CW1 |  |  | 00:00:00 |  | 2016-07-22 | Ivy Michelle Trading & Const.
18059 | NC 2016 | K10 | Region IV-B | Palawan | 111002 | Cuyo Miller School | Cuyo | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9378961.5 |  |  | Completed | 1
18060 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301688 | Cuyo National High School | Cuyo | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18061 | NC 2016 | K10 | Region IV-B | Palawan | 170566 | Trinidad Cario Ps | Roxas | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1121810.08 |  |  | Completed | 1 |  |  |  | P0007234LZ 16EE0027 |  |  | 00:00:00 |  | 2016-07-18 | 12-30 CONST.
18062 | NC 2016 | K10 | Region IV-B | Palawan | 301688 | Cuyo National High School | Cuyo | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 14473441 |  |  | Completed | 1
18063 | NC 2016 | K10 | Region IV-B | Palawan | 110983 | Decalachao Es | Coron | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9908607.7105 |  |  | Completed | 1
18064 | NC 2016 | SHS | Region IV-B | Palawan | 301692 | Dumaran Mainland Nhs | Dumaran | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14718750.5423 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18065 | NC 2016 | K10 | Region IV-B | Palawan | 301691 | Dumaran Nhs | Dumaran | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 9045418.24 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18066 | NC 2016 | SHS | Region IV-B | Palawan | 301693 | El Nido Nhs | El Nido (Bacuit) | 1 | 1 | 40 | 4STY20CL | BATCH 9 CL | 66135362.7877 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18067 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301661 | Apurawan Nhs | Aborlan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2698863 |  |  | Completed | 1 |  |  | 16EG0045 | P00074454LZ CW1 |  |  | 00:00:00 |  | 2016-07-13 | 12-30 CONSTRUCTION & SUPPLY
18068 | NC 2016 | SHS | Region IV-B | Palawan | 301693 | El Nido Nhs | El Nido (Bacuit) | 1 |  | 10 | 2STY10CL | BATCH 9 CL | 14718750.5423 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18069 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301693 | El Nido Nhs | El Nido (Bacuit) | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5574315.296 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18070 | NC 2016 | K10 | Region IV-B | Palawan | 301694 | Francisco F. Ponce De Leon Es To F. Lagan Sr. Mem. Nhs | Roxas | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 12172223.668 |  |  | Reverted | 0 |  |  |  | P00072344LZ 16EE0034 |  |  | 00:00:00 |  | 2016-06-27 | A.P. CONSEBIDO CONST.
18071 | NC 2016 | K10 | Region IV-B | Palawan | 110723 | Gogognan Es | Aborlan | 3 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1043078 |  |  | Completed | 1 |  |  |  | 0 |  |  | 2016-06-09 |  | 2016-06-29 | Panaad Construction
18072 | NC 2016 | K10 | Region IV-B | Palawan | 301699 | Gov. Alfredo Abueg Sr. National Technology & Vocational Memorial High School | Brooke'S Point | 2 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16914468.8978 |  |  | Completed | 1 |  |  | 16EF0106 | P0073308LZ |  |  | 00:00:00 |  | 2016-10-02 | UGM CONSTRUCTION
18073 | NC 2016 | K10 | Region IV-B | Palawan | 301699 | Gov. Alfredo Abueg Sr. National Technology & Vocational Memorial High School | Brooke'S Point | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 18888930 |  |  | Completed | 1 |  |  | 16EF0144 | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18074 | NC 2016 | TECHVOC | Region IV-B | Palawan | 309113 | Bancalaan National High School | Balabac | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2924570 |  |  | Completed | 1 |  |  | 16EF0075 | P00074455LZ |  |  | 00:00:00 |  | 2016-08-14 | SYNDITE CONSTRUCTION
18075 | NC 2016 | K10 | Region IV-B | Palawan | 309135 | Ilian Nhs | Dumaran | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6975927.24 |  |  | Completed | 1 |  |  |  | P00072340LZ 16EE0048 |  |  | 00:00:00 |  | 2016-07-14 | 12-30 CONSTRUCTION
18076 | NC 2016 | K10 | Region IV-B | Palawan | 309136 | Inil U. Taha Nhs | Brooke'S Point | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9129337.28 |  |  | Completed | 1
18077 | NC 2016 | K10 | Region IV-B | Palawan | 111148 | Iraan Es | Roxas | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8793661.12 |  |  | Completed | 1 |  |  |  | P00072345LZ 16EE0033 |  |  | 00:00:00 |  | 2016-06-27 | A.P. CONSEBIDO CONST.
18078 | NC 2016 | K10 | Region IV-B | Palawan | 301701 | Isaub National High School | Aborlan | 3 | 1 | 12 | 2STY6CL | BATCH 7 CL | 17333044 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18079 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301671 | Brooke'S Point Nhs - Pangobilian Nhs | Brooke'S Point | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2791635 |  |  | Completed | 1 |  |  | 16EF0095 | P00075084LZ |  |  | 00:00:00 |  | 2016-10-07 | E.V.VILLAOS TARING & CONSTRUCTION
18080 | NC 2016 | K10 | Region IV-B | Palawan | 301671 | Brooke'S Point Nhs - Pangobilian Nhs | Brooke'S Point | 2 | 1 | 40 | 4STY20CL | BATCH 13 CL | 71537358.734 |  |  | Completed | 1
18081 | NC 2016 | K10 | Region IV-B | Palawan | 301702 | J. P. Rizal Nhs | Rizal (Marcos) | 2 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14747305.1023 |  |  | Completed | 1 |  |  | 16EF0109 | P00073322LZ |  |  | 00:00:00 |  | 2016-10-03 | E.V.VILLAOS TRADING & CONSTRUCTION
18082 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301702 | J. P. Rizal Nhs | Rizal (Marcos) | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 8377530 |  |  | Completed | 1 |  |  | 16EF0064 | P00074468LZ |  |  | 00:00:00 |  | 2016-08-14 | KIM HAROLD TRADING & CONSTRUCTION | Abandoned
18083 | NC 2016 | SHS | Region IV-B | Palawan | 111136 | Liminangcong Nhs To Andres Soriano Mem. Es | Taytay | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 19089737.6919 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18084 | NC 2016 | SHS | Region IV-B | Palawan | 301703 | Liminangcong Nhs | Taytay | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18085 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301703 | Liminangcong Nhs | Taytay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2786317.6 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18086 | NC 2016 | K10 | Region IV-B | Palawan | 301704 | Maasin Nhs (Bernas Nhs) | Brooke'S Point | 2 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16854979.8978 |  |  | Completed | 1 |  |  | 16EF0107 | P00073310LZ |  |  | 00:00:00 |  | 2016-10-03 | IVY MICHELLE TRADING & CONSTRUCTION
18087 | NC 2016 | K10 | Region IV-B | Palawan | 301705 | Magara School For Philippine Crafstmen | Roxas | 1 | 1 | 15 | 3STY15CL | BATCH 7 CL | 22079891.84 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18088 | NC 2016 | K10 | Region IV-B | Palawan | 301705 | Magara School For Philippine Crafstmen | Roxas | 1 |  | 4 | 2STY4CL | BATCH 7 CL | 6744103.296 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18089 | NC 2016 | K10 | Region IV-B | Palawan | 110721 | Daan Elementary School | Aborlan | 2 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032060 |  |  | Completed | 1 |  |  | 16EG0038 | P00072311LZ CW1 |  |  | 00:00:00 |  | 2016-06-29 | Panaad Construction
18090 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301690 | Dumangeña Nhs | Narra | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  | 16EF0098 | P00075082LZ |  |  | 00:00:00 |  | 2016-09-27 | HARDROCK CONSTRUCTION
18091 | NC 2016 | K10 | Region IV-B | Palawan | 170582 | Malague Es | Dumaran | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 9095769.664 |  |  | Completed | 1 |  |  |  | P00072341LZ 16EE0031 |  |  | 00:00:00 |  | 2016-06-27 | 12-30 CONSTRUCTION
18092 | NC 2016 | K10 | Region IV-B | Palawan | 110776 | Nagpadalan Es | Dumaran | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1154484.16 |  |  | Completed | 1 |  |  |  | P00072342LZ 16EE0024 |  |  | 00:00:00 |  | 00:00:00 | 0
18093 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301699 | Gov. Alfredo Abueg Sr. National Technology & Vocational Memorial High School | Brooke'S Point | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2792510.05 |  |  | Completed | 1 |  |  | 16EF0070 | P00074459LZ |  |  | 00:00:00 |  | 2016-08-14 | CRISHELLE CONSTRUCTION
18094 | NC 2016 | K10 | Region IV-B | Palawan | 110949 | Nangalao Es | Linapacan | 1 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20983711.459 |  |  | Completed | 1
18095 | NC 2016 | SHS | Region IV-B | Palawan | 301710 | Narra Nhs | Narra | 2 | 1 | 45 | 3STY15CL | BATCH 9 CL | 64697730 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18096 | NC 2016 | K10 | Region IV-B | Palawan | 111176 | New Canipo Nhs (Alimanguan Nhs - New Canipo Nhs) To Tinitian Es | San Vicente | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 12241850.446 |  |  | Completed | 1 |  |  |  | P00072334LZ 16EE0035 |  |  | 00:00:00 |  | 00:00:00 | KUDZ TRADING & CONSTRUCTION SUPPLY
18097 | NC 2016 | SHS | Region IV-B | Palawan | 301713 | New Ibajay Nhs | El Nido (Bacuit) | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 16045865.928 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18098 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301704 | Maasin Nhs (Bernas Nhs) | Brooke'S Point | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2792510.05 |  |  | Completed | 1 |  |  | 16EF0071 | P00074460LZ |  |  | 00:00:00 |  | 2016-08-14 | JB & SONS TRADING & CONSTRUCTION
18099 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301713 | New Ibajay Nhs | El Nido (Bacuit) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2804658.648 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18100 | NC 2016 | SHS | Region IV-B | Palawan | 301710 | Narra Nhs | Narra | 2 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 |  |  | 16EF0114 | P00073314LZ |  |  | 00:00:00 |  | 2016-10-04 | JB & SONS TRADING & CONSTRUCTION
18101 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301710 | Narra Nhs | Narra | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 |  |  | 16EF0067 | P00074462LZ |  |  | 00:00:00 |  | 2016-08-14 | JB & SONS TRADING & CONSTRUCTION
18102 | NC 2016 | SHS | Region IV-B | Palawan | 301718 | Panacan Nhs | Narra | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 |  |  | 16EF0115 | P00073316LZ |  |  | 00:00:00 |  | 2016-08-04 | SYNDITE CONSTRUCTION
18103 | NC 2016 | K10 | Region IV-B | Palawan | 309145 | Pamantolon Nhs | Taytay | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8995066.816 |  |  | Completed | 1 |  |  |  | P00072349LZ 16EE0029 |  |  | 00:00:00 |  | 00:00:00 | 0
18104 | NC 2016 | SHS | Region IV-B | Palawan | 309146 | Panalingaan Nhs | Rizal (Marcos) | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16076201 |  |  | Completed | 1 |  |  | 16EF0123 | P00073323LZ |  |  | 00:00:00 |  | 00:00:00 | IVY MICHELLE TRADING & CONSTRUCTION
18105 | NC 2016 | TECHVOC | Region IV-B | Palawan | 309146 | Panalingaan Nhs | Rizal (Marcos) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2792510 |  |  | Completed | 1 |  |  | 16EF0077 | P00074468LZ |  |  | 00:00:00 |  | 2016-08-14 | KIM HAROLD TRADING & CONSTRUCTION
18106 | NC 2016 | K10 | Region IV-B | Palawan | 301719 | Panitian National High School | Sofronio Española | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12102596.89 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18107 | NC 2016 | K10 | Region IV-B | Palawan | 110955 | Panlaitan Es | Busuanga | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 15421785.2089 |  |  | Completed | 1
18108 | NC 2016 | K10 | Region IV-B | Palawan | 170583 | Paratungon East Es | Brooke'S Point | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8877580.16 |  |  | Completed | 1
18109 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301724 | Princess Urduja Nhs | Narra | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 2016-08-14 | JB & SONS TRADING & CONSTRUCTION
18110 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301725 | Pulot National High School | Sofronio Española | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2738461 |  |  | Completed | 1 |  |  | 16EF0099 | P00075083LZ |  |  | 00:00:00 |  | 2016-09-28 | HARDROCK CONSTRUCTION
18111 | NC 2016 | SHS | Region IV-B | Palawan | 301722 | Plaridel Nhs | Aborlan | 3 | 1 | 48 | 4STY24CL | BATCH 7 CL | 77291040 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18112 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301726 | Quezon Nhs | Quezon | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5585020.1 |  |  | Completed | 1 |  |  | 16EF0066 | P00074465LZ |  |  | 00:00:00 |  | 2016-08-04 | SYNDITE CONSTRUCTION
18113 | NC 2016 | SHS | Region IV-B | Palawan | 301723 | Port Barton Nhs | San Vicente | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11392255.0361 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18114 | NC 2016 | SHS | Region IV-B | Palawan | 301723 | Port Barton Nhs | San Vicente | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8214965.051 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18115 | NC 2016 | SHS | Region IV-B | Palawan | 301724 | Princess Urduja Nhs | Narra | 2 | 1 | 30 | 3STY15CL | BATCH 9 CL | 43131820 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18116 | NC 2016 | SHS | Region IV-B | Palawan | 301730 | Rio Tuba Nhs | Bataraza | 2 | 1 | 30 | 3STY15CL | BATCH 9 CL | 45273411 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18117 | NC 2016 | SHS | Region IV-B | Palawan | 301724 | Princess Urduja Nhs | Narra | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 11754463 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 2016-10-10 | SYNDITE CONSTRUCTION
18118 | NC 2016 | SHS | Region IV-B | Palawan | 301726 | Quezon Nhs | Quezon | 2 | 1 | 48 | 4STY24CL | BATCH 9 CL | 70258644 |  |  | Completed | 1 |  |  | 16EF0128 | P00073320LZ |  |  | 00:00:00 |  | 00:00:00 | 0
18119 | NC 2016 | K10 | Region IV-B | Palawan | 170548 | Ransang South Es | Rizal (Marcos) | 2 | 1 | 2 | 1STY1CL | BATCH 13 CL | 2305812.98 |  |  | Completed | 1
18120 | NC 2016 | K10 | Region IV-B | Palawan | 301739 | Sandoval National High School | Narra | 2 |  | 9 | 3STY9CL | BATCH 9 CL | 15317811 |  |  | Completed | 1 |  |  | 16EF0124 | P00073319LZ |  |  | 00:00:00 |  | 00:00:00 | 0
18121 | NC 2016 | K10 | Region IV-B | Palawan | 170548 | Ransang South Es | Rizal (Marcos) | 2 |  | 4 | 1STY4CL | BATCH 13 CL | 4195351.87 |  |  | Completed | 1
18122 | NC 2016 | SHS | Region IV-B | Palawan | 309129 | Southern Bataraza Nhs | Bataraza | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3110757.6364 |  |  | Completed | 1 |  |  | 16EF0113 | P00073305LZ |  |  | 00:00:00 |  | 2016-10-04 | BETA-J CONSTRUCTION.
18123 | NC 2016 | K10 | Region IV-B | Palawan | 110736 | Sto. Niño Elementary School | Aborlan | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6411877.7026 |  |  | Completed | 1 |  |  | 16EG0043 | P00073296LZ |  |  | 00:00:00 |  | 2016-07-13 | Samurai Construction
18124 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301730 | Rio Tuba Nhs | Bataraza | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2792510.05 |  |  | Completed | 1 |  |  | 16EF0072 | P00074457LZ |  |  | 00:00:00 |  | 2016-08-14 | JB & SONS TRADING & CONSTRUCTION
18125 | NC 2016 | K10 | Region IV-B | Palawan | 301731 | Roxas National Comprehensive High School | Roxas | 1 | 1 | 40 | 4STY20CL | BATCH 7 CL | 64627682.7238 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18126 | NC 2016 | SHS | Region IV-B | Palawan | 301734 | Salvacion Nhs | Busuanga | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 15421785.2089 |  |  | Completed | 1
18127 | NC 2016 | K10 | Region IV-B | Palawan | 309153 | Samariñana Nhs | Brooke'S Point | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8961499.2 |  |  | Completed | 1
18128 | NC 2016 | SHS | Region IV-B | Palawan | 301732 | San Jose (Roxas) Nhs | Roxas | 1 | 1 | 16 | 2STY8CL | BATCH 7 CL | 24205193.78 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18129 | NC 2016 | SHS | Region IV-B | Palawan | 301738 | San Vicente Nhs | San Vicente | 1 | 1 | 30 | 3STY15CL | BATCH 7 CL | 44416774.6 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18130 | NC 2016 | TECHVOC | Region IV-B | Palawan | 309126 | Tarusan National High School | Bataraza | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2844809 |  |  | Completed | 1 |  |  | 16EF0097 | P00075086LZ |  |  | 00:00:00 |  | 2016-09-28 | L.B.LEONCIO TRADING & CONSTRUCTION
18131 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301738 | San Vicente Nhs | San Vicente | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2756487.03 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18132 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301739 | Sandoval National High School | Narra | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5317400 |  |  | Completed | 1 |  |  | 16EF0065 | P00074464LZ |  |  | 00:00:00 |  | 2016-08-14 | CRISHELLE CONSTRUCTION
18133 | NC 2016 | K10 | Region IV-B | Palawan | 301739 | Sandoval National High School | Narra | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21565910 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18134 | NC 2016 | SHS | Region IV-B | Palawan | 301740 | Santa Teresita Nhs | Dumaran | 1 | 1 | 24 | 3STY12CL | BATCH 7 CL | 37706473.6 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18135 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301701 | Isaub National High School | Aborlan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2704275 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18136 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301740 | Santa Teresita Nhs | Dumaran | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2804658.648 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18137 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301722 | Plaridel Nhs | Aborlan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2704275 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18138 | NC 2016 | SHS | Region IV-B | Palawan | 309127 | Sibaring Nhs | Balabac | 2 | 1 | 6 | 1STY3CL | BATCH 9 CL | 6390804.0601 |  |  | Completed | 1 |  |  | 16EF0126 | P00073301LZ |  |  | 00:00:00 |  | 2016-10-12 | SYNDITE CONSTRUCTION
18139 | NC 2016 | K10 | Region IV-B | Palawan | 309152 | Sta Maria Nhs | Dumaran | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6937289.916 |  |  | Completed | 1 |  |  |  | P00072343lz 16EE0052 |  |  | 00:00:00 |  | 2016-07-14 | 12-30 CONSTRUCTION
18140 | NC 2016 | SHS | Region IV-B | Palawan | 309115 | Sumbiling Nhs | Bataraza | 2 | 1 | 12 | 2STY12CL | BATCH 9 CL | 17188116.2978 |  |  | Completed | 1 |  |  | 16EF0108 | P00073306LZ |  |  | 00:00:00 |  | 2016-10-03 | IVY MICHELLE TRADING & CONSTRUCTION
18141 | NC 2016 | SHS | Region IV-B | Palawan | 309115 | Sumbiling Nhs | Bataraza | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 7040322.78 |  |  | Completed | 1 |  |  | 16EF0111 | P00073307LZ |  |  | 00:00:00 |  | 2016-10-03 | L.B.LEONCIO CONSTRUCTION
18142 | NC 2016 | TECHVOC | Region IV-B | Palawan | 309115 | Sumbiling Nhs | Bataraza | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2846034.07 |  |  | Completed | 1 |  |  | 16EF0074 | P00074458LZ |  |  | 00:00:00 |  | 2016-08-14 | SYNDITE CONSTRUCTION | Abandoned
18143 | NC 2016 | SHS | Region IV-B | Palawan | 309149 | Taburi Nhs | Rizal (Marcos) | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12334686 |  |  | Completed | 1 |  |  | 16EF0121 | P00073324LZ |  |  | 00:00:00 |  | 2016-10-10 | L.B.LEONCIO CONSTRUCTION
18144 | NC 2016 | K10 | Region IV-B | Palawan | 110858 | Tagolango Es | Bataraza | 2 | 1 | 4 | 1STY4CL | BATCH 13 CL | 4085837.5025 |  |  | Completed | 1
18145 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301705 | Magara School For Philippine Crafstmen | Roxas | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2740429.824 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18146 | NC 2016 | K10 | Region IV-B | Palawan | 301742 | Tagumpay Nhs | Roxas | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8844012.544 |  |  | Completed | 1 |  |  |  | P00072346LZ 16EE0032 |  |  | 00:00:00 |  | 2016-07-18 | E.V.VILLAOS CONST.
18147 | NC 2016 | K10 | Region IV-B | Palawan | 301731 | Roxas National Comprehensive High School | Roxas | 1 |  | 8 | 2STY8CL | BATCH 7 CL | 12032970.112 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18148 | NC 2016 | TECHVOC | Region IV-B | Palawan | 301731 | Roxas National Comprehensive High School | Roxas | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5480859.648 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18149 | NC 2016 | K10 | Region IV-B | Palawan | 110860 | Tarusan Es | Bataraza | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9129337.28 |  |  | Completed | 1
18150 | NC 2016 | SHS | Region IV-B | Palawan | 301745 | Tumarbong Nhs | Roxas | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2064157.4714 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0
18151 | NC 2016 | K10 | Region IV-B | Palawan | 111252 | Tumbod Es | Taytay | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8995066.816 |  |  | Completed | 1 |  |  |  | P00072350LZ 16EE0030 |  |  | 00:00:00 |  | 2016-07-18 | E.V. VILLAOS
18152 | NC 2016 | K10 | Region IV-B | Palawan | 309125 | Turda National High School | Coron | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 13130084.5339 |  |  | Completed | 1
18153 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 309301 | Palawan National School | Puerto Princesa City (Capital) | 2 | 1 | 32 | 4STY16CL | BATCH 7 CL | 55020000 |  |  | Completed | 1 |  |  | P00072322LZ_CW1 | 16EG0041 | 2016-06-02 | 2016-06-10 | 2016-06-24 |  | 2016-07-13 | E.V. VILLAOS TRADING & CONST.
18154 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 309301 | Palawan National School | Puerto Princesa City (Capital) | 2 |  | 20 | 4STY20CL | BATCH 7 CL | 32982000 |  |  | Completed | 1 |  |  | P00072323LZ_CW1 | 16EG0040 | 2016-06-02 | 2016-06-10 | 2016-06-24 |  | 2016-07-13 | A.R. LUSTRE JR. CONSTRUCTION
18155 | NC 2016 | TECHVOC | Region IV-B | Puerto Princesa City | 301796 | Sicsican Nhs | Puerto Princesa City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2677500 |  |  | Completed | 1 |  |  | P00072620LZ_CW1 | 16EG0029 | 2016-04-15 | 2016-04-22 | 2016-04-01 |  | 2016-05-27 | E.C. Timbancaya Enterprises
18156 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 301796 | Sicsican Nhs | Puerto Princesa City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 7 CL | 27510000 |  |  | Completed | 1 |  |  | P00072324LZ_CW1 | 16EG0037 | 2016-05-13 | 2016-05-23 | 2016-06-03 |  | 2016-06-22 | E.V. Villaos Trading & Const.
18157 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 301796 | Sicsican Nhs | Puerto Princesa City (Capital) | 2 |  | 20 | 4STY20CL | BATCH 7 CL | 32982000 |  |  | Completed | 1 |  |  | P00072325LZ_CW1 | 16EG0044 | 2016-06-02 | 2016-06-10 | 2016-06-24 |  | 2016-07-13 | E.V. VILLAOS TRADING & CONST.
18158 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 301787 | Babuyan Nhs | Puerto Princesa City (Capital) | 3 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14177081.1023 |  |  | Completed | 1 |  |  | P00073329LZ_CW1 | 16EG0058 | 2016-07-19 | 2016-07-28 | 2016-08-09 |  | 2016-08-25 | Ivy Michelle Trading & Construction
18159 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 301779 | Bacungan Nhs | Puerto Princesa City (Capital) | 3 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16189718.8978 |  |  | Completed | 1 |  |  | P00073330LZ_CW1 | 16EG0062 | 2016-08-01 | 2016-08-10 | 2016-08-22 |  | 2016-09-09 | A.R. Lustre Jr. Construction
18160 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 301780 | Bahile Nhs | Puerto Princesa City (Capital) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12069776.8509 |  |  | Completed | 1 |  |  | P00073331LZ_CW1 | 16EG0051 | 2016-06-10 | 2016-06-17 | 2016-06-30 |  | 2016-07-22 | Ivy Michelle Trading & Const.
18161 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 301781 | Cabayugan Nhs | Puerto Princesa City (Capital) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12069776.8509 |  |  | Completed | 1 |  |  | P00073332LZ_CW1 | 16EG0052 | 2016-06-10 | 2016-06-17 | 2016-06-30 |  | 2016-07-22 | Syndtite Construction Corporation
18162 | NC 2016 | K10 | Region IV-B | Puerto Princesa City | 301784 | Langogan National High School | Puerto Princesa City (Capital) | 3 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16189718.8978 |  |  | Completed | 1 |  |  | P00073333LZ_CW1 | 16EG0063 | 2016-08-01 | 2016-08-10 | 2016-08-22 |  | 2016-09-09 | E.V. Villaos Trading & Construction
18163 | NC 2016 | K10 | Region IV-B | Puerto Princesa City | 301788 | Luzviminda National High School | Puerto Princesa City (Capital) | 3 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14177081.1023 |  |  | Completed | 1 |  |  | P00073334LZ_CW1 | 16EG0057 | 2016-07-19 | 2016-07-28 | 2016-08-09 |  | 2016-08-25 | Ivy Michelle Trading & Construction
18164 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 301785 | Macarascas Nhs | Puerto Princesa City (Capital) | 3 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14177081.1023 |  |  | Completed | 1 |  |  | P00073335LZ_CW1 | 16EG0056 | 2016-07-19 | 2016-07-28 | 2016-08-09 |  | 2016-08-25 | E.V. Villaos Trading & Construction
18165 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 301789 | Mangingisda Nhs | Puerto Princesa City (Capital) | 3 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16189718.8978 |  |  | Completed | 1 |  |  | P00073336LZ_CW1 | 16EG0064 | 2016-08-01 | 2016-08-10 | 2016-08-22 |  | 2016-09-09 | JV - PTK Group Inc./Ivy Michelle Trading
18166 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 301786 | Napsan National High School | Puerto Princesa City (Capital) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12069776.8509 |  |  | Completed | 1 |  |  | P00073337LZ_CW1 | 16EG0053 | 2016-06-10 | 2016-06-17 | 2016-06-30 |  | 2016-07-22 | E.V. Villaos Trading & Construction
18167 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 301791 | Pto. Princesa City Nat. Sci. Hs | Puerto Princesa City (Capital) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 |  |  | P00073338LZ_CW1 | 16EG0048 | 2016-06-10 | 2016-06-17 | 2016-06-30 |  | 2016-07-22 | E.V. Villaos Trading & Construction
18168 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 301795 | San Rafael National High School | Puerto Princesa City (Capital) | 3 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14177081.1023 |  |  | Completed | 1 |  |  | P00073339LZ_CW1 | 16EG0055 | 2016-07-19 | 2016-07-28 | 2016-08-09 |  | 2016-08-25 | Kudz Trading & Construction Supply
18169 | NC 2016 | SHS | Region IV-B | Puerto Princesa City |  | Shs In Puerto Princesa City | Puerto Princesa City | 3 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16022138.8978 |  |  | Completed | 1 |  |  | P00073328LZ_CW1 | 16EG0080 | 2016-10-18 | 2016-10-28 | 2016-11-08 |  | 2016-11-25 | Ivy Michelle Trading & Construction
18170 | NC 2016 | SHS | Region IV-B | Puerto Princesa City | 309302 | Simpucan Nhs (Napsan Nhs - Simpucan Annex) | Puerto Princesa City (Capital) | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20234695.669 |  |  | Completed | 1 |  |  | P00073340LZ_CW1 | 16EG0047 | 2016-06-10 | 2016-06-17 | 2016-06-30 |  | 2016-07-22 | Ivy Michelle Trading & Construction
18171 | NC 2016 | TECHVOC | Region IV-B | Romblon | 301750 | Banton Nhs | Banton | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
18172 | NC 2016 | SHS | Region IV-B | Romblon | 301750 | Banton Nhs | Banton | 0 | 1 | 6 | 3STY6CL | BATCH 13 CL | 12573229.1271 |  |  | Completed | 1
18173 | NC 2016 | TECHVOC | Region IV-B | Romblon | 301752 | Cajidiocan National High School | Cajidiocan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
18174 | NC 2016 | K10 | Region IV-B | Romblon | 309201 | Calatrava National High School | Calatrava | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 25800577.982 |  |  | Completed | 1
18175 | NC 2016 | TECHVOC | Region IV-B | Romblon | 301756 | Concepcion Nhs (Main) | Concepcion | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
18176 | NC 2016 | SHS | Region IV-B | Romblon | 301759 | Don Carlos M. Mejias Memorial Nhs | San Fernando | 0 | 1 | 12 | 2STY12CL | BATCH 13 CL | 17609352.7878 |  |  | Completed | 1
18177 | NC 2016 | TECHVOC | Region IV-B | Romblon | 301761 | Ferrol National High School | Ferrol | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
18178 | NC 2016 | SHS | Region IV-B | Romblon | 301764 | Libertad National High School | Odiongan | 0 | 1 | 6 | 3STY6CL | BATCH 11 CL | 12371844.661 |  |  | Completed | 1
18179 | NC 2016 | K10 | Region IV-B | Romblon | 301765 | Looc National High School | Looc | 0 | 1 | 15 | 3STY15CL | BATCH 11 CL | 21443013.45 |  |  | Completed | 1
18180 | NC 2016 | TECHVOC | Region IV-B | Romblon | 301765 | Looc National High School | Looc | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
18181 | NC 2016 | TECHVOC | Region IV-B | Romblon | 301753 | Lumbang East National High School | Cajidiocan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
18182 | NC 2016 | SHS | Region IV-B | Romblon | 301768 | Magdiwang Nhs | Magdiwang | 0 | 1 | 12 | 3STY12CL | BATCH 11 CL | 20029495.669 |  |  | Completed | 1
18183 | NC 2016 | TECHVOC | Region IV-B | Romblon | 301768 | Magdiwang Nhs | Magdiwang | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
18184 | NC 2016 | K10 | Region IV-B | Romblon | 301769 | Odiongan National High School | Odiongan | 0 | 1 | 8 | 4STY8CL | BATCH 11 CL | 16602270.724 |  |  | Completed | 1
18185 | NC 2016 | K10 | Region IV-B | Romblon | 301769 | Odiongan National High School | Odiongan | 0 |  | 12 | 3STY12CL | BATCH 11 CL | 18452268.79 |  |  | Completed | 1
18186 | NC 2016 | TECHVOC | Region IV-B | Romblon | 301769 | Odiongan National High School | Odiongan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
18187 | NC 2016 | SHS | Region IV-B | Romblon | 301772 | San Jose Agricultural Hs | San Jose | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9908607.7105 |  |  | Completed | 1
18188 | NC 2016 | SHS | Region IV-B | Romblon | 301763 | Sta. Fe Nhs | Santa Fe | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 22017445.2359 |  |  | Completed | 1
25786 | NC 2017 | K10 | Region IV-B | Calapan City | 111551 | Balingayan ES | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17ED0119 | 2017-07-07 | 2017-07-14 | 2017-07-27 | 2017-08-22 | 2017-09-05 | CMSEL CONST. & DEVELOPER
25787 | NC 2017 | K10 | Region IV-B | Calapan City | 111536 | Calapan CS | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17ED0120 | 2017-07-07 | 2017-07-14 | 2017-07-27 | 2017-08-22 | 2017-08-30 | DELROL ENTERPRISES
25788 | NC 2017 | K10 | Region IV-B | Calapan City | 111573 | Canubing I ES | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17ED0121 | 2017-07-07 | 2017-07-14 | 2017-07-27 | 2017-08-09 | 2017-08-21 | DELROL ENTERPRISES
25789 | NC 2017 | K10 | Region IV-B | Calapan City | 111574 | Canubing II ES | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17ED0122 | 2017-07-07 | 2017-07-14 | 2017-07-27 | 2017-08-22 | 2017-08-30 | R.R. ENCABO CONST. INC.
25790 | NC 2017 | K10 | Region IV-B | Calapan City | 111575 | F. Samaco MS | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17ED0123 | 2017-07-07 | 2017-07-14 | 2017-07-27 | 2017-08-09 | 2017-08-25 | DELROL ENTERPRISES
25791 | NC 2017 | K10 | Region IV-B | Calapan City | 111580 | T.C. Montellano MS | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17ED0124 | 2017-07-07 | 2017-07-14 | 2017-07-27 | 2017-08-22 | 2017-08-30 | FEAJ CONST. & GEN. SERVICES
25792 | NC 2017 | K10 | Region IV-B | Calapan City | 111570 | Adriatico MS | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3956856.77 |  |  | Completed | 1 |  |  |  | 17ED0136 | 2017-09-05 | 2017-09-12 | 2017-09-25 | 2017-10-24 | 2017-11-03 | DELROL ENTERPRISES
25793 | NC 2017 | K10 | Region IV-B | Calapan City | 111559 | Camilmil Central School | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 1456038.89 |  |  | Completed | 1 |  |  |  | 17ED0150 | 2017-11-08 | 2017-11-16 | 2017-11-29 | 2017-12-12 | 2018-01-02 | FEAJ CONST. & GEN. SERVICES
25794 | NC 2017 | K10 | Region IV-B | Calapan City | 111542 | N. Aboboto MS | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 1456038.89 |  |  | Completed | 1 |  |  |  | 17ED0151 | 2017-11-08 | 2017-11-16 | 2017-11-29 | 2017-12-12 | 2018-01-02 | FEAJ CONST. & GEN. SERVICES
25795 | NC 2017 | K10 | Region IV-B | Calapan City | 111572 | Sta. Rita ES (Bungahan ES) | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17ED0141 | 2017-09-13 | 2017-09-20 | 2017-10-03 | 2017-10-24 | 2017-11-03 | SIALDANG CONST. & ENT.
25796 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110327 | Dulangan I ES | BACO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2744433.216 |  |  | Completed | 1 |  |  | P00172868LZ-CW1 | 17ED0138 |  |  |  |  | 2017-09-11 | Delrol Ent.
25797 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110435 | Banus ES | GLORIA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3826035.02 |  |  | Completed | 1 | [8 empty] | 2017-11-29 | AS Yang Const.
25798 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110491 | Kalinisan ES | NAUJAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2875120.512 |  |  | Completed | 1 |  |  | P00172869LZ-CW1 | 17ED0137 |  |  |  |  | 2017-09-11 | Sialdang Const. & Ent.
25799 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110520 | Malvar ES | Naujan | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2875120.512 |  |  | Completed | 1 |  |  | P00172870LZ-CW1 | 17ED0140 |  |  |  |  | 2017-11-29 | B5 Builders & Supplies
25800 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110599 | Pahilahan ES | POLA | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3956856.871 |  |  | Completed | 1 |  |  | P00172871LZ-CW1 | 17ED0139 |  |  |  |  | 2017-09-11 | B5 Builders & Supplies
25801 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110658 | Lumangbayan ES | SAN TEODORO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00172872LZ-CW1 | 17ED0135 |  |  |  |  | 2017-09-11 | Marc Jill
25802 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110664 | Bagsok ES | SOCORRO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2801298.3468 |  |  | Completed | 1 |  |  | P00172873LZ-CW1 | 17ED0143 |  |  |  |  | 2017-09-11 | Sialdang Const. & Ent.
25803 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110664 | Bagsok ES | SOCORRO | 1 |  | 4 | 1STY4CL | BATCH 4 | 5075903.5768 |  |  | Completed | 1 |  |  | P00172874LZ-CW1 | 17ED0144 |  |  |  |  | 2017-09-11 | Sialdang Const. & Ent.
25804 | NC 2017 | K10 | Region IV-B | Palawan | 110716 | Apurawan Elementary School | ABORLAN | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2704704.28 |  |  | Completed | 1
25805 | NC 2017 | K10 | Region IV-B | Palawan | 309119 | Iraan-Sagpangan NHS | ABORLAN | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2678697.51 |  |  | Completed | 1
25806 | NC 2017 | K10 | Region IV-B | Palawan | 170556 | Tina Elementary School | ABORLAN | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3787088.77 |  |  | Completed | 1
25807 | NC 2017 | K10 | Region IV-B | Palawan | 110794 | Banglos Elementary School | BALABAC | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4038435.02 |  |  | Completed | 1
25808 | NC 2017 | K10 | Region IV-B | Palawan | 170563 | Kambangtule Elementary School | BALABAC | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4038435.02 |  |  | Completed | 1
25809 | NC 2017 | K10 | Region IV-B | Palawan | 110808 | Mangsee Elementary School | BALABAC | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4038435.02 |  |  | Completed | 1
25810 | NC 2017 | K10 | Region IV-B | Palawan | 110813 | Paliisan ES | BALABAC | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2793745.92 |  |  | Completed | 1
25811 | NC 2017 | K10 | Region IV-B | Palawan | 110819 | Sibaring ES | BALABAC | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2793745.92 |  |  | Completed | 1
25812 | NC 2017 | K10 | Region IV-B | Palawan | 110823 | Turong Elementary School | BALABAC | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2793745.92 |  |  | Completed | 1 | [10 empty] | abandoned
25813 | NC 2017 | K10 | Region IV-B | Palawan | 110824 | Barangkas ES | BATARAZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3836506.19 |  |  | Completed | 1 | [10 empty] | abandoned
25814 | NC 2017 | K10 | Region IV-B | Palawan | 170553 | Bato-Bato Elementary School | BATARAZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3836506.19 |  |  | Completed | 1 | [10 empty] | abandoned
25815 | NC 2017 | K10 | Region IV-B | Palawan | 170585 | LUPAK ES | BATARAZA | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 5025445.31 |  |  | Completed | 1
25816 | NC 2017 | K10 | Region IV-B | Palawan | 309133 | Malihud National High School | BATARAZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3871255.64 |  |  | Completed | 1
25817 | NC 2017 | K10 | Region IV-B | Palawan | 110837 | Malitub ES | BATARAZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3871255.64 |  |  | Completed | 1
25818 | NC 2017 | K10 | Region IV-B | Palawan | 170554 | MATYAG ELEMENTARY SCHOOL | BATARAZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3871255.64 |  |  | Completed | 1
25819 | NC 2017 | K10 | Region IV-B | Palawan | 110839 | Narra-Narra ES | BATARAZA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2682293 |  |  | Completed | 1
25820 | NC 2017 | K10 | Region IV-B | Palawan | 110840 | Ocayan ES | BATARAZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3871255.64 |  |  | Completed | 1
25821 | NC 2017 | K10 | Region IV-B | Palawan | 110842 | Panas ES | BATARAZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3836506.19 |  |  | Completed | 1
25822 | NC 2017 | K10 | Region IV-B | Palawan | 309159 | PEACE AND DEVELOPMENT COMMUNITY NATIONAL HIGH SCHOOL | BATARAZA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2659126.7 |  |  | Completed | 1
25823 | NC 2017 | K10 | Region IV-B | Palawan | 309159 | PEACE AND DEVELOPMENT COMMUNITY NATIONAL HIGH SCHOOL | BATARAZA | 2 |  | 2 | 1STY2CL | BATCH 4 | 2659126.7 |  |  | Completed | 1
25824 | NC 2017 | K10 | Region IV-B | Palawan | 110843 | Pinuwasan Elementary School | BATARAZA | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 4979112.71 |  |  | Completed | 1 | [10 empty] | abandoned
25825 | NC 2017 | K10 | Region IV-B | Palawan | 110845 | Rio Tuba Central School | BATARAZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3836506.19 |  |  | Completed | 1
25826 | NC 2017 | K10 | Region IV-B | Palawan | 170552 | Rogelio Verano Esteban Elementary Sch. | BATARAZA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2676989.54 |  |  | Completed | 1
25827 | NC 2017 | K10 | Region IV-B | Palawan | 110847 | Sandoval ES | BATARAZA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2659126.7 |  |  | Completed | 1
25828 | NC 2017 | K10 | Region IV-B | Palawan | 110850 | Sarong ES | BATARAZA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2676989.54 |  |  | Completed | 1
25829 | NC 2017 | K10 | Region IV-B | Palawan | 110853 | Sitio Culandanum ES | BATARAZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3871255.64 |  |  | Completed | 1
25830 | NC 2017 | SHS | Region IV-B | Palawan | 309126 | Tarusan National High School | BATARAZA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2659126.7 |  |  | Completed | 1
25831 | NC 2017 | K10 | Region IV-B | Palawan | 110861 | Abubakar Elementary School | BROOKE'S POINT | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2650958.96 |  |  | Completed | 1
25832 | NC 2017 | K10 | Region IV-B | Palawan | 110865 | Bayog Elementary School | BROOKE'S POINT | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2650958.96 |  |  | Completed | 1
25833 | NC 2017 | K10 | Region IV-B | Palawan | 309155 | CALASAGUEN NHS | BROOKE'S POINT | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2650958.96 |  |  | Completed | 1
25834 | NC 2017 | K10 | Region IV-B | Palawan | 110873 | Imulnod ES | BROOKE'S POINT | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2650958.96 |  |  | Completed | 1
25835 | NC 2017 | K10 | Region IV-B | Palawan | 110875 | Kilala PS | BROOKE'S POINT | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2650958.96 |  |  | Completed | 1 | [10 empty] | abandoned
25836 | NC 2017 | K10 | Region IV-B | Palawan | 110879 | Macagua ES | BROOKE'S POINT | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2650958.96 |  |  | Completed | 1
25837 | NC 2017 | K10 | Region IV-B | Palawan | 110880 | Mainit ES | BROOKE'S POINT | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2650958.96 |  |  | Completed | 1
25838 | NC 2017 | K10 | Region IV-B | Palawan | 110894 | Proyekto Setias Mem. ES (Tagpirara ES) | BROOKE'S POINT | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2650958.96 |  |  | Completed | 1
25839 | NC 2017 | K10 | Region IV-B | Palawan | 110890 | Salogon Elementary School | BROOKE'S POINT | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 4962777.23 |  |  | Completed | 1
25840 | NC 2017 | K10 | Region IV-B | Palawan | 110892 | Saraza Elementary School | BROOKE'S POINT | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3824254.58 |  |  | Completed | 1
25841 | NC 2017 | K10 | Region IV-B | Palawan | 110993 | Sta. Monica Elementary School | CORON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2776961 |  |  | Completed | 1
25842 | NC 2017 | K10 | Region IV-B | Palawan | 110994 | Tagum ES | CORON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2750000 |  |  | Completed | 1
25843 | NC 2017 | K10 | Region IV-B | Palawan | 111013 | Aberawan Elementary School | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2844363 |  |  | Completed | 1
25844 | NC 2017 | K10 | Region IV-B | Palawan | 301664 | Bagong Bayan NHS | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2844363 |  |  | Completed | 1
25845 | NC 2017 | K10 | Region IV-B | Palawan | 301744 | TENEGUIBAN NATIONAL HIGH SCHOOL | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2844363 |  |  | Completed | 1
25846 | NC 2017 | K10 | Region IV-B | Palawan | 110956 | Pical ES | LINAPACAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2871324 |  |  | Completed | 1
25847 | NC 2017 | K10 | Region IV-B | Palawan | 111054 | Aramaywan II ES | NARRA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2735441.37 |  |  | Completed | 1
25848 | NC 2017 | K10 | Region IV-B | Palawan | 111060 | Burirao Annex ES | NARRA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2805442.37 |  |  | Completed | 1
25849 | NC 2017 | K10 | Region IV-B | Palawan | 309102 | Calategas National High School | NARRA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
25850 | NC 2017 | K10 | Region IV-B | Palawan | 111067 | Ipilan ES | NARRA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
25851 | NC 2017 | K10 | Region IV-B | Palawan | 111070 | Maranan Elementary School | NARRA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
25852 | NC 2017 | K10 | Region IV-B | Palawan | 111102 | ISUGOD ELEMENTARY SCHOOL | QUEZON | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3795042.92 |  |  | Completed | 1
25853 | NC 2017 | K10 | Region IV-B | Palawan | 111104 | Kalatagbak ES | QUEZON | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2952407.29 |  |  | Completed | 1
25854 | NC 2017 | K10 | Region IV-B | Palawan | 111105 | Lamane Elementary School | QUEZON | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2631484.52 |  |  | Completed | 1
25855 | NC 2017 | K10 | Region IV-B | Palawan | 309147 | PINAGLABANAN NHS | QUEZON | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4083583.98 |  |  | Completed | 1
25856 | NC 2017 | K10 | Region IV-B | Palawan | 309147 | PINAGLABANAN NHS | QUEZON | 2 |  | 2 | 1STY2CL | BATCH 4 | 2814692.97 |  |  | Completed | 1
25857 | NC 2017 | SHS | Region IV-B | Palawan | 301729 | Quinlogan National High School | QUEZON | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3795042.92 |  |  | Completed | 1
25858 | NC 2017 | K10 | Region IV-B | Palawan | 111129 | Tagbae ES | QUEZON | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4059818.21 |  |  | Completed | 1
25859 | NC 2017 | K10 | Region IV-B | Palawan | 111089 | Bintat Karis Elementary School | RIZAL (MARCOS) | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3829310.75 |  |  | Completed | 1
25860 | NC 2017 | K10 | Region IV-B | Palawan | 111096 | Candawaga Elementary School | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2654329.74 |  |  | Completed | 1
25861 | NC 2017 | K10 | Region IV-B | Palawan | 111097 | Canipaan ES | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2686194 |  |  | Completed | 1
25862 | NC 2017 | K10 | Region IV-B | Palawan | 111131 | Tagpas PS | RIZAL (MARCOS) | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3843828.02 |  |  | Completed | 1
25863 | NC 2017 | K10 | Region IV-B | Romblon | 111283 | Cantagda ES | CAJIDIOCAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00172935LZ | 17EH0088 | 2017-11-09 | 2017-11-16 | 2017-12-04 | 2017-12-13 | 2018-01-23 | MT. GUITING-GUITING CONSTRUCTION
25864 | NC 2017 | K10 | Region IV-B | Romblon | 111285 | Danao ES | CAJIDIOCAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00172936LZ | 17EH0089 | 2017-11-09 | 2017-11-16 | 2017-12-04 | 2017-12-13 | 2018-01-23 | R.G. FLORENTINO CONSTRUCTION & TRADING
25865 | NC 2017 | K10 | Region IV-B | Romblon | 111294 | Panaguintingan ES | CAJIDIOCAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00172937LZ | 17EH0090 | 2017-11-09 | 2017-11-16 | 2017-12-04 | 2017-12-12 | 2018-01-23 | MT. GUITING-GUITING CONSTRUCTION
25866 | NC 2017 | K10 | Region IV-B | Romblon | 111348 | Anahao ES | ODIONGAN | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1 |  |  | P00172938LZ | 17EH0094 | 2017-11-09 | 2017-11-16 | 2017-12-04 | 2017-12-13 | 2018-01-30 | PABLO S. LABASBAS
25867 | NC 2017 | K10 | Region IV-B | Romblon | 111366 | Agnay ES | ROMBLON (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00172939LZ | 17EH0091 | 2017-11-09 | 2017-11-16 | 2017-12-04 | 2017-12-13 | 2018-01-23 | ST. PIUS CONSTRUCTION & SUPPLY
25868 | NC 2017 | K10 | Region IV-B | Romblon | 111389 | San Jose ES | ROMBLON (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00172940LZ | 17EH0092 | 2017-11-09 | 2017-11-16 | 2017-12-04 | 2017-12-13 | 2018-01-25 | ST. PIUS CONSTRUCTION & SUPPLY
25869 | NC 2017 | K10 | Region IV-B | Romblon | 111411 | San Agustin CES | SAN AGUSTIN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00172941LZ | 17EH0093 | 2017-11-09 | 2017-11-16 | 2017-12-04 | 2017-12-18 | 2018-02-05 | R.G. FLORENTINO CONSTRUCTION & TRADING
25870 | NC 2017 | K10 | Region IV-B | Romblon | 111430 | Tan-Agan ES | SAN ANDRES | 0 | 1 | 5 | 1STY5CL | BATCH 4 | 6500000 |  |  | Completed | 1 |  |  | P00172942LZ | 17EH0112 | 2017-11-17 | 2017-11-24 | 2017-12-06 | 2017-12-12 | 2018-02-05 | TWIN DRAGON CONSTRUCTION
25871 | NC 2017 | K10 | Region IV-B | Romblon | 111461 | Pinamihagan Elementary School | SAN JOSE | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00172943LZ | 17EH0111 | 2017-11-17 | 2017-11-24 | 2017-12-06 | 2017-12-15 | 2018-01-29 | RNV CONSTRUCTION
25872 | NC 2017 | K10 | Region IV-B | Romblon | 111402 | Concepcion Sur ES | SANTA MARIA (IMELDA) | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1 |  |  | P00172944LZ | 17EH0095 | 2017-11-09 | 2017-11-16 | 2017-12-04 | 2017-12-13 | 2018-01-23 | MT. GUITING-GUITING CONSTRUCTION
25873 | NC 2017 | K10 | Region IV-B | Palawan | 110826 | Bono-Bono ES | BATARAZA | 2 | 1 | 3 | 1STY3CL | BATCH 5 | 3836506.19 |  |  | Completed | 1
25874 | NC 2017 | K10 | Region IV-B | Palawan | 110828 | Buliluyan ES | BATARAZA | 2 | 1 | 2 | 1STY2CL | BATCH 5 | 2682293 |  |  | Completed | 1
25875 | NC 2017 | K10 | Region IV-B | Calapan City | 111559 | Camilmil Central School | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 1164987.2245 |  |  | Completed | 1 |  |  |  | 17ED0150 | 2017-11-08 | 2017-11-16 | 2017-11-29 | 2017-12-12 | 2018-01-02 | FEAJ CONST. & GEN. SERVICES
25876 | NC 2017 | K10 | Region IV-B | Calapan City | 111542 | N. Aboboto MS | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 1164987.2245 |  |  | Completed | 1 |  |  |  | 17ED0151 | 2017-11-08 | 2017-11-16 | 2017-11-29 | 2017-12-12 | 2018-01-02 | FEAJ CONST. & GEN. SERVICES
25877 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110335 | Lantuyang ES | Baco | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3136495.104 |  |  | Completed | 1 |  |  | P00175619LZ-CW1 | 17ED0162 |  |  |  |  | 2018-02-01 | Rodolfo R. Santiago Const.
25878 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110338 | Malmis Mangyan School | Baco | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3136495.104 |  |  | Completed | 1 |  |  | P00175620LZ-CW1 | 17ED0159 |  |  |  |  | 2017-12-28 | Delrol Ent.
25879 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110348 | Tabucala Mangyan School | Baco | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3136495.104 |  |  | Completed | 1 |  |  | P00175621LZ-CW1 | 17ED0159 |  |  |  |  | 2017-12-28 | Delrol Ent.
25880 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110349 | Tagumpay Primary School | Baco | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  | P00175622LZ-CW1 | 17ED0157 |  |  |  |  | 2018-12-28 | Framecon Builders
25881 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110361 | Manihala ES | BANSUD | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2947222.92 |  |  | Completed | 1 | [8 empty] | 2017-11-30 | Green Island Ent.
25882 | NC 2017 | TVL | Region IV-B | Oriental Mindoro | 309019 | Pag-asa NHS | BANSUD | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2780515.92 |  |  | Completed | 1 | [8 empty] | 2017-11-29 | Martinez Ent.
25883 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110365 | Rosacara ES | BANSUD | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1 | [8 empty] | 2017-11-29 | DM Maliwanag Const.
25884 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 170005 | Aplaya Elementary School | BONGABONG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 | [8 empty] | 2017-05-12 | Green Island Ent.
25885 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 309030 | Batangan Buhid HS | BONGABONG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2780515.92 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Lumel Glenn Const.
25886 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110394 | Braulio Umali Garcia Elem. School | BONGABONG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 | [8 empty] | 2017-03-12 | King,s Builders
25887 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110372 | Bukal ES | BONGABONG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2780615.92 |  |  | Completed | 1 | [8 empty] | 2018-02-02 | MADSAM
25888 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110391 | C. F. Solabo MES (Dayhagan ES) | BONGABONG | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1 | [8 empty] | 2017-11-28 | Marc Jill
25889 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110392 | Camantigue ES | BONGABONG | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 5024091.15 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Lumel Glenn Const.
25890 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110374 | Catalino Lopez MES (Libertad ES) | BONGABONG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2709745.92 |  |  | Completed | 1 | [8 empty] | 2017-12-19 | Sixteen Ent.
25891 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110374 | Catalino Lopez MES (Libertad ES) | BONGABONG | 2 |  | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1 | [8 empty] | 2017-12-19 | Sixteen Ent.
25892 | NC 2017 | TVL | Region IV-B | Oriental Mindoro | 301624 | Cawayan NHS | BONGABONG | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2741615.92 |  |  | Completed | 1 | [8 empty] | 2017-11-28 | 811 Trading
25893 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110387 | Felisa Guevarra Salvacion MES | BONGABONG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2906085.92 |  |  | Completed | 1 | [8 empty] | 2017-11-18 | ADL Constrak
25894 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110402 | Fidel M. Reyes MS (Mina De Oro ES) | BONGABONG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 | [8 empty] | 2017-11-30 | Green Island Ent.
25895 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110376 | Formon ES | BONGABONG | 2 | 1 | 5 | 1STY5CL | BATCH 7 | 6076650.72 |  |  | Completed | 1 | [8 empty] | 2017-11-30 | Green Island Ent.
25896 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110397 | Labonan ES | BONGABONG | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 4888351.15 |  |  | Completed | 1 | [8 empty] | 2017-05-12 | DM Almero
25897 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110381 | Mapang ES | BONGABONG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2681615.92 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Alberto Uy Const.
25898 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110401 | Masaguisi ES | BONGABONG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 | [8 empty] | 2017-05-12 | King,s Builders
25899 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110382 | Morente ES | BONGABONG | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 5086151.15 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Alberto Uy Const.
25900 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110383 | Panluan ES | BONGABONG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Lumel Glenn Const.
25901 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110383 | Panluan ES | BONGABONG | 2 |  | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Lumel Glenn Const.
25902 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110390 | Selda-Lazaro Memorial ES | BONGABONG | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 4888351.15 |  |  | Completed | 1 | [8 empty] | 2018-03-12 | King,s Builders
25903 | NC 2017 | TVL | Region IV-B | Oriental Mindoro | 301654 | Vicente B. Ylagan NHS | BONGABONG | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2681615.92 |  |  | Completed | 1 | [8 empty] | 2017-11-29 | Great Lakes Ent.
25904 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 170034 | Abintang ES | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2780515.92 |  |  | Reverted | 0 | [8 empty] | 2017-04-12 | Lumel Glenn Const. | terminated; not doable
25905 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110413 | Benli ES | BULALACAO (SAN PEDRO) | 2 | 1 | 5 | 1STY5CL | BATCH 7 | 6377500.72 |  |  | Completed | 1 | [8 empty] | 2017-05-12 | Excelsius
25906 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 309022 | Benli NHS | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2779667.92 |  |  | Completed | 1 | [8 empty] | 2018-01-31 | Lumel Glenn Const.
25907 | NC 2017 | TVL | Region IV-B | Oriental Mindoro | 301620 | Bulalacao NHS | BULALACAO (SAN PEDRO) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2681615.92 |  |  | Completed | 1 | [8 empty] | 2018-01-31 | Alberto Uy Const.
25908 | NC 2017 | TVL | Region IV-B | Oriental Mindoro | 301620 | Bulalacao NHS | BULALACAO (SAN PEDRO) | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3237868.09 |  |  | Completed | 1 | [8 empty] | 2018-01-31 | Alberto Uy Const.
25909 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110415 | Cabugao ES | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2780515.92 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Lumel Glenn Const.
25910 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 309033 | Cabugao NHS | BULALACAO (SAN PEDRO) | 2 | 1 | 5 | 1STY5CL | BATCH 7 | 6319900.72 |  |  | Completed | 1 | [8 empty] | 2017-05-12 | Excelsius
25911 | NC 2017 | TVL | Region IV-B | Oriental Mindoro | 301621 | Maujao NHS | BULALACAO (SAN PEDRO) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2766235.92 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Lumel Glenn Const.
25912 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110423 | Milagrosa ES | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2747530.92 |  |  | Completed | 1 | [8 empty] | 2017-12-19 | Excelsius
25913 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110423 | Milagrosa ES | BULALACAO (SAN PEDRO) | 2 |  | 2 | 1STY2CL | BATCH 7 | 2747530.92 |  |  | Completed | 1 | [8 empty] | 2017-12-19 | Excelsius
25914 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110424 | Nasukob ES | BULALACAO (SAN PEDRO) | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3910962.02 |  |  | Completed | 1 | [8 empty] | 2017-05-12 | SOSEP
25915 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110425 | Pawikan ES | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2780515.92 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Lumel Glenn Const.
25916 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110426 | San Isidro ES | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2780515.92 |  |  | Completed | 1 | [8 empty] | 2017-03-12 | Alberto Uy Const.
25917 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110429 | San Roque ES | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2711482.5867 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Lumel Glenn Const.
25918 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110429 | San Roque ES | BULALACAO (SAN PEDRO) | 2 |  | 2 | 1STY2CL | BATCH 7 | 2711482.5867 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Lumel Glenn Const.
25919 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110429 | San Roque ES | BULALACAO (SAN PEDRO) | 2 |  | 2 | 1STY2CL | BATCH 7 | 2711482.5867 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Lumel Glenn Const.
25920 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 170037 | Umabang ES | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3077215.92 |  |  | Reverted | 0 | [8 empty] | 2017-04-12 | Lumel Glenn Const. | Terminated , Very Remote Site
25921 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110430 | Yunot ES (Hanunuo) | BULALACAO (SAN PEDRO) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2746580.92 |  |  | Completed | 1 | [8 empty] | 2017-05-12 | Ansavilla
25922 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110430 | Yunot ES (Hanunuo) | BULALACAO (SAN PEDRO) | 2 |  | 2 | 1STY2CL | BATCH 7 | 2746580.92 |  |  | Completed | 1 | [8 empty] | 2017-05-12 | Ansavilla
25923 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110433 | Almavilla Elementary School | GLORIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2748815.92 |  |  | Completed | 1 | [8 empty] | 2017-11-29 | AS Yang Const.
25924 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110437 | Batingan ES | GLORIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2681615.92 |  |  | Completed | 1 | [8 empty] | 2018-01-30 | AS Yang Const.
25925 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110439 | Buong Lupa ES | GLORIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2780515.92 |  |  | Completed | 1 | [8 empty] | 2017-11-30 | Green Island Ent.
25926 | NC 2017 | TVL | Region IV-B | Oriental Mindoro | 301636 | Malamig NHS | GLORIA | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2744195.92 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Lumel Glenn Const.
25927 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110459 | B. Del Mundo MS | MANSALAY | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1 | [8 empty] | 2017-05-12 | NAMNAMA
25928 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110459 | B. Del Mundo MS | MANSALAY | 2 |  | 4 | 1STY4CL | BATCH 7 | 4888351.15 |  |  | Completed | 1 | [8 empty] | 2017-05-12 | NAMNAMA
25929 | NC 2017 | TVL | Region IV-B | Oriental Mindoro | 301631 | Fe del Mundo NHS | MANSALAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3153030.59 |  |  | Completed | 1 | [8 empty] | 2018-07-02 | DM Maliwanag Const.
25930 | NC 2017 | TVL | Region IV-B | Oriental Mindoro | 301631 | Fe del Mundo NHS | MANSALAY | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3153030.59 |  |  | Completed | 1 | [8 empty] | 2018-07-02 | DM Maliwanag Const.
25931 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110472 | Panaytayan Elementary School | MANSALAY | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3948640.02 |  |  | Completed | 1 | [8 empty] | 2017-04-12 | Lumel Glenn Const.
25932 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110478 | Sta. Maria ES | MANSALAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2662745.92 |  |  | Completed | 1 | [8 empty] | 2018-07-02 | DM Maliwanag Const.
25933 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110478 | Sta. Maria ES | MANSALAY | 2 |  | 3 | 1STY3CL | BATCH 7 | 3817435.02 |  |  | Completed | 1 | [8 empty] | 2018-07-02 | DM Maliwanag Const.
25934 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110509 | Balite Mangyan School | Naujan | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2875120.512 |  |  | Completed | 1 |  |  | P00175623LZ-CW1 | 17ED0163 |  |  |  |  | 2018-02-01 | Lumel Glenn Const.
25935 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110510 | Bucayao Grande Mangyan School | Naujan | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3136495.104 |  |  | Completed | 1 |  |  | P00175624LZ-CW1 | 17ED0163 |  |  |  |  | 2018-02-01 | Lumel Glenn Const.
25936 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 170013 | Bucayao Grande Mangyan School-Annex | Naujan | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2875120.512 |  |  | Completed | 1 |  |  | P00175625LZ-CW1 | 17ED0163 |  |  |  |  | 2018-02-01 | Lumel Glenn Const.
25937 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110511 | Caburo Mangyan School | Naujan | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3136495.104 |  |  | Completed | 1 |  |  | P00175627LZ-CW1 | 17ED0163 |  |  |  |  | 2018-02-01 | Lumel Glenn Const.
25938 | NC 2017 | K10 | Region IV-B | Oriental Mindoro |  | Malvar NHS | NAUJAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2744433.216 |  |  | Completed | 1 |  |  | P00175626LZ-CW1 | 17ED0163 |  |  |  |  | 2018-02-01 | Lumel Glenn Const.
25939 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 170017 | Cacawan ES | PINAMALAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2647680.92 |  |  | Completed | 1 | [8 empty] | 2018-01-31 | IF Blanco Const.
25940 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110608 | Ambang Mangyan School | Puerto Galera | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3136495.104 |  |  | Completed | 1 |  |  | P00175628LZ-CW1 | 17ED0164 |  |  |  |  | 2018-02-01 | Marc Jill Construction
25941 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110610 | Baclayan Mangyan School | Puerto Galera | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4522122.024 |  |  | Completed | 1 |  |  | P00175629LZ-CW1 | 17ED0164 |  |  |  |  | 2018-02-01 | Marc Jill Construction
25942 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 170027 | Lapantay Mangyan School | PUERTO GALERA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2875120.512 |  |  | Completed | 1 |  |  | P00175630LZ-CW1 | 17ED0164 |  |  |  |  | 2018-02-01 | Marc Jill Construction
25943 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110615 | Malago Mangyan School | Puerto Galera | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3136495.104 |  |  | Completed | 1 |  |  | P00175631LZ-CW1 | 17ED0165 |  |  |  |  | 2018-02-01 | Lumel Glenn Const.
25944 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110617 | Pagturian Mangyan School | Puerto Galera | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 7287180.864 |  |  | Completed | 1 |  |  | P00175632LZ-CW1 | 17ED0165 |  |  |  |  | 2018-02-01 | Lumel Glenn Const.
25945 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110621 | San Antonio ES | PUERTO GALERA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3005807.808 |  |  | Completed | 1 |  |  | P00175633LZ-CW1 | 17ED0165 |  |  |  |  | 2018-02-01 | Lumel Glenn Const.
25946 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 170029 | Sipit Saburan Mangyan School | PUERTO GALERA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2875120.512 |  |  | Completed | 1 |  |  | P00175634LZ-CW1 | 17ED0164 |  |  |  |  | 2018-02-01 | Marc Jill Construction
25947 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110628 | Benito P. Garfin ES | ROXAS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2647345.92 |  |  | Completed | 1 | [8 empty] | 2017-11-28 | 811 Trading & Const.
25948 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110628 | Benito P. Garfin ES | ROXAS | 2 |  | 2 | 1STY2CL | BATCH 7 | 2647345.92 |  |  | Completed | 1 | [8 empty] | 2017-11-28 | 811 Trading & Const.
25949 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110632 | Libertad ES | ROXAS | 2 | 1 | 5 | 1STY5CL | BATCH 7 | 6312437.3867 |  |  | Completed | 1 | [8 empty] | 2018-01-30 | Alberto Uy Const.
25950 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110632 | Libertad ES | ROXAS | 2 |  | 2 | 1STY2CL | BATCH 7 | 2853532.5867 |  |  | Completed | 1 | [8 empty] | 2018-01-30 | Alberto Uy Const.
25951 | NC 2017 | TVL | Region IV-B | Oriental Mindoro | 301639 | Marcelo I. Cabrera Vocational High School | ROXAS | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3237868.09 |  |  | Completed | 1 | [8 empty] | 2018-07-02 | DM Maliwanag Const.
25952 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110640 | Roxas CS | ROXAS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2831420.92 |  |  | Completed | 1 | [8 empty] | 2017-12-13 | ADL Constrak
25953 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110640 | Roxas CS | ROXAS | 2 |  | 3 | 1STY3CL | BATCH 7 | 3986110.02 |  |  | Completed | 1 | [8 empty] | 2017-12-13 | ADL Constrak
25954 | NC 2017 | TVL | Region IV-B | Oriental Mindoro | 301652 | San Mariano NHS | ROXAS | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3237868.09 |  |  | Completed | 1 | [8 empty] | 2018-07-02 | MADSAM
25955 | NC 2017 | TVL | Region IV-B | Oriental Mindoro | 301652 | San Mariano NHS | ROXAS | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3237868.09 |  |  | Completed | 1 | [8 empty] | 2018-07-02 | MADSAM
25956 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 309021 | San Mariano NHS - San Vicente Annex | ROXAS | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4018590.02 |  |  | Completed | 1 | [8 empty] | 2017-05-12 | NAMNAMA
25957 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 170012 | Adong Mangyan School | San Teodoro | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3136495.104 |  |  | Completed | 1 |  |  | P00175635LZ-CW1 | 17ED0160 |  |  |  |  | 2017-12-28 | 876 Const. & Supply
25958 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110651 | Arigoy Mangyan School | San Teodoro | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3136495.104 |  |  | Completed | 1 |  |  | P00175636LZ-CW1 | 17ED0160 |  |  |  |  | 2017-12-28 | 876 Const. & Supply
25959 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 170010 | Suyong Mangyan School | San Teodoro | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3136495.104 |  |  | Completed | 1 |  |  | P00175637LZ-CW1 | 17ED0160 |  |  |  |  | 2017-12-28 | 876 Const. & Supply
25960 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110671 | Fortuna ES | SOCORRO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2744433.216 |  |  | Completed | 1 |  |  | P00175638LZ-CW1 | 17ED0166 |  |  |  |  | 2018-02-01 | B5 Builders &Supplies
25961 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110672 | Granvida ES | Socorro | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4522122.024 |  |  | Completed | 1 |  |  | P00175639LZ-CW1 | 17ED0166 |  |  |  |  | 2018-02-01 | B5 Builders &Supplies
25962 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110685 | Tigao ES | Socorro | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3267182.4 |  |  | Completed | 1 |  |  | P00175640LZ-CW1 | 17ED0166 |  |  |  |  | 2018-02-01 | B5 Builders &Supplies
25963 | NC 2017 | K10 | Region IV-B | Oriental Mindoro |  | Concepcion NHS | VICTORIA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  | P00175641LZ-CW1 | 17ED0161 |  |  |  |  | 2017-12-28 | ETVR Trading & Const.
25964 | NC 2017 | K10 | Region IV-B | Oriental Mindoro |  | Concepcion NHS | VICTORIA | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6072650.72 |  |  | Completed | 1 |  |  | P00175642LZ-CW1 | 17ED0168 |  |  |  |  | 2018-10-01 | Kasanga Const. & Supplies
25965 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 170031 | Kisloyan Minority School | Victoria | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3136495.104 |  |  | Completed | 1 |  |  | P00175643LZ-CW1 | 17ED0167 |  |  |  |  | 2018-02-01 | Delrol Ent.
25966 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110705 | Pamuwisan Minority School | Victoria | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3267182.4 |  |  | Completed | 1 |  |  | P00175644LZ-CW1 | 17ED0167 |  |  |  |  | 2018-02-01 | Delrol Ent.
25967 | NC 2017 | SHS | Region IV-B | Palawan | 309120 | Concepcion National High School | AGUTAYA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4193625 |  |  | Completed | 1
25968 | NC 2017 | SHS | Region IV-B | Palawan | 309120 | Concepcion National High School | AGUTAYA | 1 |  | 4 | 1STY4CL | BATCH 7 | 5451185 |  |  | Completed | 1
25969 | NC 2017 | K10 | Region IV-B | Palawan | 110743 | Diit ES | AGUTAYA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2850000 |  |  | Completed | 1
25970 | NC 2017 | SHS | Region IV-B | Palawan | 301695 | Gaudencio E. Abordo Mem. NHS | AGUTAYA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4193625 |  |  | Completed | 1
25971 | NC 2017 | K10 | Region IV-B | Palawan | 110746 | Villa Fria Elementary School | AGUTAYA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4050000 |  |  | Completed | 1
25972 | NC 2017 | K10 | Region IV-B | Palawan | 110749 | Araceli CS | ARACELI | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5500000 |  |  | Completed | 1
25973 | NC 2017 | K10 | Region IV-B | Palawan | 110763 | Dagman ES | ARACELI | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4132095 |  |  | Completed | 1
25974 | NC 2017 | K10 | Region IV-B | Palawan | 170531 | Caguisan Annex | BALABAC | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4038435.02 |  |  | Completed | 1
25975 | NC 2017 | K10 | Region IV-B | Palawan | 170531 | Caguisan Annex | BALABAC | 2 |  | 2 | 1STY2CL | BATCH 7 | 2793745.92 |  |  | Completed | 1
25976 | NC 2017 | K10 | Region IV-B | Palawan | 110830 | Dudungguan ES | BATARAZA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4148144.5 |  |  | Completed | 1
25977 | NC 2017 | K10 | Region IV-B | Palawan | 110830 | Dudungguan ES | BATARAZA | 2 |  | 2 | 1STY2CL | BATCH 7 | 2682293 |  |  | Completed | 1
25978 | NC 2017 | K10 | Region IV-B | Palawan | 110934 | Cheey ES | BUSUANGA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2803922 |  |  | Completed | 1
25979 | NC 2017 | K10 | Region IV-B | Palawan | 110934 | Cheey ES | BUSUANGA | 1 |  | 2 | 1STY2CL | BATCH 7 | 2803922 |  |  | Completed | 1
25980 | NC 2017 | SHS | Region IV-B | Palawan | 309134 | Cheey National High School | BUSUANGA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4294250 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Funds 2018
25981 | NC 2017 | K10 | Region IV-B | Palawan | 110969 | Nusa ES | CAGAYANCILLO | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6633660 |  |  | Completed | 1 |  |  | P00175719LZ | 17EE0143 |  |  |  |  | 2018-01-15 | MARYKNOLL BUILDERS AND SUPPLY
25982 | NC 2017 | SHS | Region IV-B | Palawan | 309168 | Decalachao National High School | CORON | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4094250 |  |  | Completed | 1
25983 | NC 2017 | SHS | Region IV-B | Palawan | 309168 | Decalachao National High School | CORON | 1 |  | 4 | 1STY4CL | BATCH 7 | 5322010 |  |  | Completed | 1
25984 | NC 2017 | K10 | Region IV-B | Palawan | 110920 | Abud-Abod ES | CULION | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2803922 |  |  | Completed | 1
25985 | NC 2017 | K10 | Region IV-B | Palawan | 110920 | Abud-Abod ES | CULION | 1 |  | 2 | 1STY2CL | BATCH 7 | 2803922 |  |  | Completed | 1
25986 | NC 2017 | K10 | Region IV-B | Palawan | 110923 | Balanga Elementary School | CULION | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2803922 |  |  | Completed | 1
25987 | NC 2017 | K10 | Region IV-B | Palawan | 110923 | Balanga Elementary School | CULION | 1 |  | 2 | 1STY2CL | BATCH 7 | 2803922 |  |  | Completed | 1
25988 | NC 2017 | K10 | Region IV-B | Palawan | 170577 | Bulok-bulokan Elementary School | CULION | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4134000 |  |  | Completed | 1
25989 | NC 2017 | K10 | Region IV-B | Palawan | 170577 | Bulok-bulokan Elementary School | CULION | 1 |  | 2 | 1STY2CL | BATCH 7 | 2803922 |  |  | Completed | 1
25990 | NC 2017 | SHS | Region IV-B | Palawan | 301687 | Culion Sanitarium Special NHS | CULION | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4134000 |  |  | Completed | 1
25991 | NC 2017 | SHS | Region IV-B | Palawan | 301687 | Culion Sanitarium Special NHS | CULION | 1 |  | 2 | 1STY2CL | BATCH 7 | 2633280 |  |  | Completed | 1
25992 | NC 2017 | K10 | Region IV-B | Palawan | 170576 | Comminyte Elementary School | DUMARAN | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4213500 |  |  | Completed | 1
25993 | NC 2017 | K10 | Region IV-B | Palawan | 110769 | Itangil ES | DUMARAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2750000 |  |  | Completed | 1
25994 | NC 2017 | K10 | Region IV-B | Palawan | 111027 | Mabini ES | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2844363 |  |  | Completed | 1
25995 | NC 2017 | K10 | Region IV-B | Palawan | 111027 | Mabini ES | EL NIDO (BACUIT) | 1 |  | 3 | 1STY3CL | BATCH 7 | 3850000 |  |  | Completed | 1
25996 | NC 2017 | K10 | Region IV-B | Palawan | 111029 | Maranlao Elementary School | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2844363 |  |  | Completed | 1
25997 | NC 2017 | K10 | Region IV-B | Palawan | 301736 | San Fernando NHS | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2844363 |  |  | Completed | 1
25998 | NC 2017 | K10 | Region IV-B | Palawan | 111037 | Villa Libertad ES | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2844363 |  |  | Completed | 1
25999 | NC 2017 | K10 | Region IV-B | Palawan | 110931 | Cabunlawan ES | LINAPACAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2871324 |  |  | Completed | 1
26000 | NC 2017 | K10 | Region IV-B | Palawan | 110932 | Calibangbangan ES | LINAPACAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2871324 |  |  | Completed | 1
26001 | NC 2017 | K10 | Region IV-B | Palawan | 110938 | Decabaitot ES | LINAPACAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2871324 |  |  | Completed | 1
26002 | NC 2017 | K10 | Region IV-B | Palawan | 110938 | Decabaitot ES | LINAPACAN | 1 |  | 2 | 1STY2CL | BATCH 7 | 2871324 |  |  | Completed | 1
26003 | NC 2017 | K10 | Region IV-B | Palawan | 110948 | Maroyogroyog ES | LINAPACAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2871324 |  |  | Completed | 1
26004 | NC 2017 | K10 | Region IV-B | Palawan | 110948 | Maroyogroyog ES | LINAPACAN | 1 |  | 2 | 1STY2CL | BATCH 7 | 2871324 |  |  | Completed | 1
26005 | NC 2017 | SHS | Region IV-B | Palawan | 309165 | NANGALAO NHS | LINAPACAN | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6677550 |  |  | Completed | 1
26006 | NC 2017 | K10 | Region IV-B | Palawan | 110952 | New Colaylayan ES | LINAPACAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2871324 |  |  | Completed | 1
26007 | NC 2017 | K10 | Region IV-B | Palawan | 110953 | Old Barangonan PS | LINAPACAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2871324 |  |  | Completed | 1
26008 | NC 2017 | K10 | Region IV-B | Palawan | 110960 | San Miguel ES | LINAPACAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2871324 |  |  | Completed | 1
26009 | NC 2017 | SHS | Region IV-B | Palawan | 301737 | San Miguel NHS (Gaudencio Abordo NHS) | LINAPACAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2871324 |  |  | Completed | 1
26010 | NC 2017 | K10 | Region IV-B | Palawan | 110961 | San Nicolas ES | LINAPACAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2871324 |  |  | Completed | 1
26011 | NC 2017 | K10 | Region IV-B | Palawan | 110961 | San Nicolas ES | LINAPACAN | 1 |  | 2 | 1STY2CL | BATCH 7 | 2871324 |  |  | Completed | 1
26012 | NC 2017 | K10 | Region IV-B | Palawan | 111040 | Alcoba ES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2884804 |  |  | Completed | 1
26013 | NC 2017 | K10 | Region IV-B | Palawan | 111042 | Canipo ES | MAGSAYSAY | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4050000 |  |  | Completed | 1
26014 | NC 2017 | K10 | Region IV-B | Palawan | 111043 | Cocoro ES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2884804 |  |  | Completed | 1
26015 | NC 2017 | SHS | Region IV-B | Palawan | 301689 | Danawan NHS | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2884804 |  |  | Completed | 1
26016 | NC 2017 | K10 | Region IV-B | Palawan | 111044 | Emilod ES | MAGSAYSAY | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5500000 |  |  | Completed | 1
26017 | NC 2017 | K10 | Region IV-B | Palawan | 301696 | Gaudencio E. Abordo Mem. NHS - Balaguen NHS | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2884804 |  |  | Completed | 1
26018 | NC 2017 | K10 | Region IV-B | Palawan | 301696 | Gaudencio E. Abordo Mem. NHS - Balaguen NHS | MAGSAYSAY | 1 |  | 2 | 1STY2CL | BATCH 7 | 2884804 |  |  | Completed | 1
26019 | NC 2017 | K10 | Region IV-B | Palawan | 111048 | Lucbuan ES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2884804 |  |  | Completed | 1
26020 | NC 2017 | K10 | Region IV-B | Palawan | 111048 | Lucbuan ES | MAGSAYSAY | 1 |  | 2 | 1STY2CL | BATCH 7 | 2884804 |  |  | Completed | 1
26021 | NC 2017 | K10 | Region IV-B | Palawan | 170546 | Nicolas M. Aborot Sr. MES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2884804 |  |  | Completed | 1
26022 | NC 2017 | K10 | Region IV-B | Palawan | 111051 | Rizal North ES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2884804 |  |  | Completed | 1
26023 | NC 2017 | K10 | Region IV-B | Palawan | 170544 | Bulno PS | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2654329.74 |  |  | Completed | 1
26024 | NC 2017 | K10 | Region IV-B | Palawan | 170547 | Canipaan ES extension | RIZAL (MARCOS) | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3877107.14 |  |  | Completed | 1
26025 | NC 2017 | K10 | Region IV-B | Palawan | 170547 | Canipaan ES extension | RIZAL (MARCOS) | 2 |  | 2 | 1STY2CL | BATCH 7 | 2686194 |  |  | Completed | 1
26026 | NC 2017 | K10 | Region IV-B | Palawan | 170507 | Colandanum Elementay School | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2664007.92 |  |  | Completed | 1
26027 | NC 2017 | K10 | Region IV-B | Palawan | 111098 | Culasian ES (New) | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2664007.92 |  |  | Completed | 1 | [10 empty] | Abandoned
26028 | NC 2017 | K10 | Region IV-B | Palawan | 170508 | Dignuzon PS | RIZAL (MARCOS) | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4041828.02 |  |  | Completed | 1
26029 | NC 2017 | K10 | Region IV-B | Palawan | 170513 | Latud ES | RIZAL (MARCOS) | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 4988875.15 |  |  | Completed | 1
26030 | NC 2017 | K10 | Region IV-B | Palawan | 111115 | Panalingaan ES | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2664007.92 |  |  | Completed | 1
26031 | NC 2017 | K10 | Region IV-B | Palawan | 170567 | Rancho II Elementary School | RIZAL (MARCOS) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2654329.74 |  |  | Completed | 1
26032 | NC 2017 | K10 | Region IV-B | Palawan | 309116 | Ransang NHS | RIZAL (MARCOS) | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3843828.02 |  |  | Completed | 1
26033 | NC 2017 | K10 | Region IV-B | Palawan | 170561 | Agustin Ello Elementary School | ROXAS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2750000 |  |  | Completed | 1
26034 | NC 2017 | K10 | Region IV-B | Palawan | 309105 | Dumarao Brgy. HS | ROXAS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2750000 |  |  | Completed | 1
26035 | NC 2017 | K10 | Region IV-B | Palawan | 111152 | Magara ES | ROXAS | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3800000 |  |  | Completed | 1
26036 | NC 2017 | K10 | Region IV-B | Palawan | 111157 | Maykawayan ES | ROXAS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2750000 |  |  | Completed | 1
26037 | NC 2017 | K10 | Region IV-B | Palawan | 170586 | NANABU INDIGENOUS PEOPLE ES | ROXAS | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5347845 |  |  | Completed | 1 | [10 empty] | Abandoned
26038 | NC 2017 | K10 | Region IV-B | Palawan |  | NANABU INDIGENOUS PEOPLE ES | ROXAS | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5500000 |  |  | Completed | 1
26039 | NC 2017 | K10 | Region IV-B | Palawan | 111163 | Rodriguez Elementary School | ROXAS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2750000 |  |  | Completed | 1
26040 | NC 2017 | K10 | Region IV-B | Palawan | 111168 | San Isidro ES | ROXAS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2750000 |  |  | Completed | 1
26041 | NC 2017 | K10 | Region IV-B | Palawan | 111171 | San Nicolas ES | ROXAS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2750000 |  |  | Completed | 1
26042 | NC 2017 | K10 | Region IV-B | Palawan | 111172 | Sandoval ES | ROXAS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2700000 |  |  | Completed | 1
26043 | NC 2017 | K10 | Region IV-B | Palawan | 111187 | Cauban ES | SAN VICENTE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2763480 |  |  | Completed | 1
26044 | NC 2017 | K10 | Region IV-B | Palawan | 111194 | New Canipo ES | SAN VICENTE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2763480 |  |  | Completed | 1
26045 | NC 2017 | K10 | Region IV-B | Palawan | 111198 | Pamuayan ES | SAN VICENTE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2798529 |  |  | Completed | 1
26046 | NC 2017 | SHS | Region IV-B | Palawan | 301738 | San Vicente NHS | SAN VICENTE | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3850000 |  |  | Completed | 1
26047 | NC 2017 | SHS | Region IV-B | Palawan | 301738 | San Vicente NHS | SAN VICENTE | 1 |  | 3 | 1STY3CL | BATCH 7 | 3850000 |  |  | Completed | 1
26048 | NC 2017 | K10 | Region IV-B | Palawan | 111189 | Tranquilino L. Oblan Elementary School | SAN VICENTE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2798529 |  |  | Completed | 1
26049 | NC 2017 | K10 | Region IV-B | Palawan | 170502 | Bidang Elementary School | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2632990.34 |  |  | Completed | 1 | [10 empty] | Abandoned
26050 | NC 2017 | K10 | Region IV-B | Palawan | 110902 | Ipaputo Elementary School | SOFRONIO ESPAÑOLA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3797301.65 |  |  | Completed | 1 | [10 empty] | abandoned
26051 | NC 2017 | K10 | Region IV-B | Palawan | 110908 | Malanap Interior PS | SOFRONIO ESPAÑOLA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3797301.65 |  |  | Reverted | 0 | [10 empty] | Project was not implemented by this office due to the fund was reverted as of December 31, 2017. Failure of bidding for projects funded under BEFF CY 2017 with SARO No. 2017-10-013684 dated October 26, 2017 (Batch 7) received by this office on November 24, 2017 due to NO INTERESTED BIDDER.
26052 | NC 2017 | K10 | Region IV-B | Palawan | 170575 | Malangse Hillside ES | SOFRONIO ESPAÑOLA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3797301.65 |  |  | Completed | 1
26053 | NC 2017 | K10 | Region IV-B | Palawan | 170560 | Maribong Elementary School | SOFRONIO ESPAÑOLA | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 4926839.99 |  |  | Completed | 1
26054 | NC 2017 | K10 | Region IV-B | Palawan | 170559 | Pangatban Primary School | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2632990.34 |  |  | Completed | 1
26055 | NC 2017 | K10 | Region IV-B | Palawan | 110912 | Panitian Interior ES | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2632990.34 |  |  | Completed | 1
26056 | NC 2017 | K10 | Region IV-B | Palawan | 170568 | Sincab ES | SOFRONIO ESPAÑOLA | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 4926839.99 |  |  | Completed | 1
26057 | NC 2017 | K10 | Region IV-B | Palawan | 301658 | Abongan National High School | TAYTAY | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6450890 |  |  | Completed | 1
26058 | NC 2017 | K10 | Region IV-B | Palawan | 111216 | Calabucay ES | TAYTAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2776961 |  |  | Completed | 1
26059 | NC 2017 | K10 | Region IV-B | Palawan | 111217 | Calabugtong ES | TAYTAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2776961 |  |  | Completed | 1
26060 | NC 2017 | K10 | Region IV-B | Palawan | 301679 | Calawag NHS | TAYTAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2750000 |  |  | Completed | 1
26061 | NC 2017 | K10 | Region IV-B | Palawan | 111221 | Canique Elementary School | TAYTAY | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3800000 |  |  | Completed | 1
26062 | NC 2017 | K10 | Region IV-B | Palawan | 309122 | Canique NHS | TAYTAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2776961 |  |  | Completed | 1
26063 | NC 2017 | K10 | Region IV-B | Palawan | 111222 | Caroroy ES | TAYTAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2776961 |  |  | Completed | 1
26064 | NC 2017 | K10 | Region IV-B | Palawan | 170570 | Ching Bing Kao Elementary School | TAYTAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2776961 |  |  | Completed | 1
26065 | NC 2017 | K10 | Region IV-B | Palawan | 170541 | Dinet ElementarySchool | TAYTAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2776961 |  |  | Completed | 1
26066 | NC 2017 | K10 | Region IV-B | Palawan | 111227 | Dipla ES | TAYTAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2776961 |  |  | Completed | 1
26067 | NC 2017 | K10 | Region IV-B | Palawan | 309123 | Liminangcong NHS - San Jose Ext. | TAYTAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2750000 |  |  | Completed | 1
26068 | NC 2017 | K10 | Region IV-B | Palawan | 301712 | New Guinlo NHS | TAYTAY | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2750000 |  |  | Completed | 1
26069 | NC 2017 | K10 | Region IV-B | Palawan | 111245 | San Jose ES | TAYTAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2776961 |  |  | Completed | 1
26070 | NC 2017 | K10 | Region IV-B | Puerto Princesa City | 111511 | Cabayugan ES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2666020.84 |  |  | Completed | 1 | [6 empty] | 2017-11-13 |  | 2017-12-20 | PJ CONSTRUCTION AND SUPPLY
26071 | NC 2017 | K10 | Region IV-B | Puerto Princesa City | 111478 | Inagawan ES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3843803.72 |  |  | Completed | 1 | [6 empty] | 2017-11-13 |  | 2017-12-20 | BONIFACIO M. CARLOS CONSTRUCTION CORPORATION
26072 | NC 2017 | SHS | Region IV-B | Puerto Princesa City | 301783 | Irawan NHS | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2639383.38 |  |  | Completed | 1 | [6 empty] | 2017-11-13 |  | 2017-12-20 | ST. PIUS CONSTRUCTION AND SUPPLY
26073 | NC 2017 | SHS | Region IV-B | Puerto Princesa City | 301783 | Irawan NHS | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 8 | 2STY8CL | BATCH 7 | 17294538.16 |  |  | Completed | 1 | [6 empty] | 2017-12-27 |  | 2018-01-12 | KUDZ TRADING AND CONSTRUCTION SUPPLY
26074 | NC 2017 | K10 | Region IV-B | Puerto Princesa City | 111482 | Kamuning ES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2666020.84 |  |  | Completed | 1 | [6 empty] | 2017-11-13 |  | 2017-12-20 | HARDROCK PLATINUM DEV. CORPORATION
26075 | NC 2017 | K10 | Region IV-B | Puerto Princesa City | 111515 | Kayasan ES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 4 | 1STY4CL | BATCH 7 | 4986118.17 |  |  | Completed | 1 | [6 empty] | 2017-11-13 |  | 2017-12-20 | MARYKNOLL BUILDERS AND SUPPLY
26076 | NC 2017 | K10 | Region IV-B | Puerto Princesa City | 111483 | Labtay ES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 4 | 1STY4CL | BATCH 7 | 4986118.17 |  |  | Completed | 1 | [6 empty] | 2017-11-13 |  | 2017-12-20 | MARYKNOLL BUILDERS AND SUPPLY
26077 | NC 2017 | K10 | Region IV-B | Puerto Princesa City | 111519 | Makandring ES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2666020.84 |  |  | Completed | 1 | [6 empty] | 2017-11-13 |  | 2017-12-20 | HARDSHELL DESIGN AND CONSTRUCTION
26078 | NC 2017 | K10 | Region IV-B | Puerto Princesa City | 111529 | San Carlos ES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3843803.72 |  |  | Completed | 1 | [6 empty] | 2017-11-13 |  | 2017-12-20 | HARDROCK PLATINUM DEV. CORPORATION
26079 | NC 2017 | SHS | Region IV-B | Puerto Princesa City | 301793 | San Jose NHS | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 24 | 4STY24CL | BATCH 7 | 52618229.5 |  |  | Completed | 1 | [6 empty] | 2017-12-27 |  | 2018-01-12 | A.R. LUSTRE JR. CONSTRUCTION
26080 | NC 2017 | SHS | Region IV-B | Puerto Princesa City | 301790 | Sta. Lourdes NHS | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 8 | 2STY8CL | BATCH 7 | 17294538.16 |  |  | Completed | 1 | [6 empty] | 2017-12-27 |  | 2018-01-12 | KUDZ TRADING AND CONSTRUCTION SUPPLY
26081 | NC 2017 | K10 | Region IV-B | Marinduque | 109911 | Daykitin ES | BUENAVISTA | 0 | 1 | 2 | 1STY2CL | BATCH 8 | 4528800 |  |  | Completed | 1
26082 | NC 2017 | K10 | Region IV-B | Marinduque | 109929 | Gasan CS | GASAN | 0 | 1 | 2 | 1STY2CL | BATCH 8 | 4715460 |  |  | Completed | 1
26083 | NC 2017 | K10 | Region IV-B | Marinduque | 109943 | Capayang ES | MOGPOG | 0 | 1 | 2 | 1STY2CL | BATCH 8 | 4459950 |  |  | Completed | 1
26084 | NC 2017 | K10 | Region IV-B | Marinduque | 109975 | Tamayo ES | SANTA CRUZ | 0 | 1 | 2 | 1STY2CL | BATCH 8 | 4907475 |  |  | Completed | 1
26085 | NC 2017 | K10 | Region IV-B | Marinduque | 110023 | Malibago ES | TORRIJOS | 0 | 1 | 2 | 1STY2CL | BATCH 8 | 4922010 |  |  | Completed | 1
26086 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110332 | Julio R. Hernandez MS | BACO | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00179484LZ-CW1 | 17ED0152 |  |  |  |  | 2018-02-01 | Delrol Ent
26087 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110340 | Mangangan I ES | BACO | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3956856.871 |  |  | Completed | 1 |  |  | P00179485LZ-CW1 | 17ED0156 |  |  |  |  | 2018-02-01 | Delrol Ent
26088 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110347 | Tabon - Tabon ES | BACO | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3956856.771 |  |  | Completed | 1 |  |  | P00179486LZ-CW1 | 17ED0152 |  |  |  |  | 2018-02-01 | Delrol Ent
26089 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110347 | Tabon - Tabon ES | BACO | 1 |  | 3 | 1STY3CL | BATCH 10 | 3956856.771 |  |  | Completed | 1 |  |  | P00179487LZ-CW1 | 17ED0152 |  |  |  |  | 2018-02-01 | Delrol Ent
26090 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110368 | Tiguisan Elementary School | BANSUD | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3844035.02 |  |  | Completed | 1 | [8 empty] | 2018-01-23 | Martinez Ent.
26091 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110507 | Bagong Buhay ES | NAUJAN | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00179492LZ-CW1 | 17ED0153 |  |  |  |  | 2018-09-01 | Framecon Builders
26092 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110512 | Del Pilar ES | NAUJAN | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00179493LZ-CW1 | 17ED0153 |  |  |  |  | 2018-09-01 | Framecon Builders
26093 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110490 | Jose L. Basa Memorial School | NAUJAN | 1 | 1 | 4 | 1STY4CL | BATCH 10 | 5377186.265 |  |  | Completed | 1 |  |  | P00179488LZ-CW1 | 17ED0170 |  |  |  |  | 2018-11-01 | Framecon Builders/Great Lakes Ent. JV
26094 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110490 | Jose L. Basa Memorial School | NAUJAN | 1 |  | 4 | 1STY4CL | BATCH 10 | 5377186.265 |  |  | Completed | 1 |  |  | P00179489LZ-CW1 | 17ED0170 |  |  |  |  | 2018-11-01 | Framecon Builders/Great Lakes Ent. JV
26095 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110490 | Jose L. Basa Memorial School | NAUJAN | 1 |  | 4 | 1STY4CL | BATCH 10 | 5377186.265 |  |  | Completed | 1 |  |  | P00179490LZ-CW1 | 17ED0170 |  |  |  |  | 2018-11-01 | Framecon Builders/Great Lakes Ent. JV
26096 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110539 | Juan Luna MES | NAUJAN | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3927989.5435 |  |  | Completed | 1 |  |  | P00179494LZ-CW1 | 17ED0171 |  |  |  |  | 2018-02-01 | Framecon Builders
26097 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110539 | Juan Luna MES | NAUJAN | 1 |  | 2 | 1STY2CL | BATCH 10 | 2773300.4435 |  |  | Completed | 1 |  |  | P00179495LZ-CW1 | 17ED0171 |  |  |  |  | 2018-02-01 | Framecon Builders
26098 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110498 | Montelago ES | NAUJAN | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3956856.871 |  |  | Completed | 1 |  |  | P00179491LZ-CW1 | 17ED0155 |  |  |  |  | 2018-02-01 | LN Salvador Const. Corp.
26099 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110601 | Pola CS | POLA | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3956856.871 |  |  | Completed | 1 |  |  | P00179496LZ-CW1 | 17ED0154 |  |  |  |  | 2018-09-01 | Marc Jill Const
26100 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110611 | Balatero ES | PUERTO GALERA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2715490.5403 |  |  | Completed | 1 |  |  | P00179497LZ-CW1 | 17ED0173 |  |  |  |  | 2018-01-14 | FEAJ Const & Gen Services
26101 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110687 | Alialy Roldan MES | VICTORIA | 1 | 1 | 4 | 1STY4CL | BATCH 10 | 5162376.1968 |  |  | Completed | 1 |  |  | P00179498LZ-CW1 | 17ED0169 |  |  |  |  | 2018-10-01 | Great Lakes Ent
26102 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 110687 | Alialy Roldan MES | VICTORIA | 1 |  | 5 | 1STY5CL | BATCH 10 | 6346675.7667 |  |  | Completed | 1 |  |  | P00179499LZ-CW1 | 17ED0172 |  |  |  |  | 2018-02-01 | ETVR Trading & Const
26103 | NC 2017 | K10 | Region IV-B | Oriental Mindoro | 170033 | Sigkuran Mangyan School | Victoria | 1 | 1 | 4 | 1STY4CL | BATCH 10 | 5621603.8225 |  |  | Completed | 1 |  |  | P00179500LZ-CW1 | 17ED0172 |  |  |  |  | 2018-02-01 | ETVR Trading & Const
26104 | NC 2017 | K10 | Region IV-B | Palawan | 110740 | Agutaya Central School | AGUTAYA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844363 |  |  | Completed | 1
26105 | NC 2017 | K10 | Region IV-B | Palawan | 110741 | Algeciras Elementry School | AGUTAYA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844363 |  |  | Completed | 1
26106 | NC 2017 | K10 | Region IV-B | Palawan | 110742 | Concepcion ES | AGUTAYA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844363 |  |  | Completed | 1
26107 | NC 2017 | K10 | Region IV-B | Palawan | 110745 | Matarawis ES | AGUTAYA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844363 |  |  | Completed | 1
26108 | NC 2017 | K10 | Region IV-B | Palawan | 309104 | Araceli Western National HS | ARACELI | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2817402 |  |  | Completed | 1
26109 | NC 2017 | K10 | Region IV-B | Palawan | 110753 | Balogo Elementary School | ARACELI | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2696078 |  |  | Completed | 1
26110 | NC 2017 | TVL | Region IV-B | Palawan | 301666 | Balabac National High School | BALABAC | 2 | 1 | 1 | TVL-RW | BATCH 10 | 3025120.51 |  |  | Completed | 1
26111 | NC 2017 | TVL | Region IV-B | Palawan | 301666 | Balabac National High School | BALABAC | 2 |  | 2 | TVL-UW | BATCH 10 | 6683206.32 |  |  | Completed | 1
26112 | NC 2017 | K10 | Region IV-B | Palawan | 170533 | Calawit Elementary School | BUSUANGA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2803922 |  |  | Completed | 1
26113 | NC 2017 | K10 | Region IV-B | Palawan | 110936 | Concepcion ES | BUSUANGA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2803922 |  |  | Completed | 1
26114 | NC 2017 | SHS | Region IV-B | Palawan | 309167 | Concepcion National High School | BUSUANGA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2803922 |  |  | Completed | 1
26115 | NC 2017 | K10 | Region IV-B | Palawan | 110950 | New Busuanga ES | BUSUANGA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2803922 |  |  | Completed | 1
26116 | NC 2017 | K10 | Region IV-B | Palawan | 110951 | New Calawit Elementary School | BUSUANGA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2803922 |  |  | Completed | 1
26117 | NC 2017 | K10 | Region IV-B | Palawan | 110955 | Panlaitan ES | BUSUANGA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2803922 |  |  | Completed | 1
26118 | NC 2017 | K10 | Region IV-B | Palawan | 110972 | Balisungan Elementary School | CORON | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2776961 |  |  | Completed | 1
26119 | NC 2017 | K10 | Region IV-B | Palawan | 170509 | Bayang Elementary School | CORON | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2776961 |  |  | Completed | 1
26120 | NC 2017 | K10 | Region IV-B | Palawan | 110975 | Bintuan Elementary School | CORON | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2776961 |  |  | Completed | 1
26121 | NC 2017 | K10 | Region IV-B | Palawan | 110977 | Buenavista Elementary School | CORON | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2776961 |  |  | Completed | 1
26122 | NC 2017 | K10 | Region IV-B | Palawan | 110979 | Cabugao Elementary School | CORON | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2776961 |  |  | Completed | 1
26123 | NC 2017 | K10 | Region IV-B | Palawan | 170532 | Claudio Sandoval South annex | CORON | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2776961 |  |  | Completed | 1
26124 | NC 2017 | K10 | Region IV-B | Palawan | 110982 | Decabobo Elementary School | CORON | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2776961 |  |  | Completed | 1
26125 | NC 2017 | K10 | Region IV-B | Palawan | 110983 | Decalachao Elementary School | CORON | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2776961 |  |  | Completed | 1
26126 | NC 2017 | K10 | Region IV-B | Palawan | 110987 | Malawig Elementary School | CORON | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2776961 |  |  | Completed | 1
26127 | NC 2017 | K10 | Region IV-B | Palawan | 110996 | Tara Elementary School | CORON | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2776961 |  |  | Completed | 1
26128 | NC 2017 | K10 | Region IV-B | Palawan | 110926 | Binudac ES | CULION | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2803922 |  |  | Completed | 1
26129 | NC 2017 | K10 | Region IV-B | Palawan | 110935 | Chindonan Elementary School | CULION | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2803922 |  |  | Completed | 1
26130 | NC 2017 | K10 | Region IV-B | Palawan | 110939 | Detopiak PS | CULION | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2803922 |  |  | Completed | 1
26131 | NC 2017 | K10 | Region IV-B | Palawan | 110944 | Luac Elementary School | CULION | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2803922 |  |  | Completed | 1
26132 | NC 2017 | K10 | Region IV-B | Palawan | 110748 | Aguinaldo Elementary School | DUMARAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2857843 |  |  | Completed | 1
26133 | NC 2017 | K10 | Region IV-B | Palawan | 170517 | Bolo Elementary School | DUMARAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2857843 |  |  | Completed | 1
26134 | NC 2017 | K10 | Region IV-B | Palawan | 309135 | Ilian National High School | DUMARAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2857843 |  |  | Completed | 1
26135 | NC 2017 | K10 | Region IV-B | Palawan | 301707 | Magsaysay National High School | DUMARAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2857843 |  |  | Completed | 1
26136 | NC 2017 | K10 | Region IV-B | Palawan | 110776 | Nagpadalan Elementary School | DUMARAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2857843 |  |  | Completed | 1 | [10 empty] | Abandoned
26137 | NC 2017 | K10 | Region IV-B | Palawan | 110781 | San Jose ES | DUMARAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2857843 |  |  | Completed | 1
26138 | NC 2017 | K10 | Region IV-B | Palawan | 110782 | San Juan ES | DUMARAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2857843 |  |  | Completed | 1
26139 | NC 2017 | K10 | Region IV-B | Palawan | 301672 | Bucana NHS | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844363 |  |  | Completed | 1
26140 | NC 2017 | K10 | Region IV-B | Palawan | 111018 | Buluang Elementary School | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844363 |  |  | Completed | 1
26141 | NC 2017 | K10 | Region IV-B | Palawan | 170505 | Danat Elementary School | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844363 |  |  | Completed | 1
26142 | NC 2017 | K10 | Region IV-B | Palawan | 111025 | Lamoro ES | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844363 |  |  | Completed | 1
26143 | NC 2017 | K10 | Region IV-B | Palawan | 309132 | Mabini National High School | EL NIDO (BACUIT) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844363 |  |  | Completed | 1
26144 | NC 2017 | TVL | Region IV-B | Palawan | 301728 | Quezon-Panitian National High School | QUEZON | 2 | 1 | 2 | TVL-UW | BATCH 10 | 6672068.73 |  |  | Completed | 1
26145 | NC 2017 | TVL | Region IV-B | Palawan | 301657 | Abo-Abo National High School | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | TVL-UW | BATCH 10 | 6429206.32 |  |  | Reverted | 0 | [10 empty] | Abandoned
26146 | NC 2017 | TVL | Region IV-B | Palawan | 301725 | Pulot National High School | SOFRONIO ESPAÑOLA | 2 | 1 | 3 | TVL-UW | BATCH 10 | 9649809.48 |  |  | Completed | 1
26147 | NC 2017 | TVL | Region IV-B | Palawan | 301725 | Pulot National High School | SOFRONIO ESPAÑOLA | 2 |  | 1 | TVL-RW | BATCH 10 | 2912120.51 |  |  | Completed | 1
26148 | NC 2017 | SHS | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2744433.22 |  |  | Completed | 1
26149 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110037 | Abra de Ilog CS | ABRA DE ILOG | 0 | 1 | 5 | 1STY5CL | BATCH 12 | 5930447.04 |  |  | Completed | 1
26150 | NC 2017 | TVL | Region IV-B | Occidental Mindoro | 301569 | Abra de Ilog NHS | ABRA DE ILOG | 0 | 1 | 9 | 1STY2CL, GRADE 1-10 CL, 1STY3CL REG WORKSHOP, 1STY2CL SCI. LAB, 1STY2CL ICT LAB | BATCH 12 | 12348808.63 |  |  | Completed | 1
26151 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 301571 | Abra de Ilog NHS - Camurong Annex | ABRA DE ILOG | 0 | 1 | 2 | 1STY2CL, GRADE 1-10 CL | BATCH 12 | 3082757.14 |  |  | Completed | 1
26152 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110042 | Cabacao ES | ABRA DE ILOG | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2873295.88 |  |  | Completed | 1
26153 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110071 | Santo Tomas Min. ES | ABRA DE ILOG | 0 | 1 | 2 | 1STY2CL, GRADE 1-10 CL | BATCH 12 | 3258397.1 |  |  | Completed | 1
26154 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110084 | Filomeno Jimenez MS | CALINTAAN | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 4436968.1 |  |  | Completed | 1
26155 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110091 | New Dagupan ES | CALINTAAN | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2939591.25 |  |  | Completed | 1
26156 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110136 | Magsaysay Central School | MAGSAYSAY | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 4758522.92 |  |  | Completed | 1
26157 | NC 2017 | TVL | Region IV-B | Occidental Mindoro | 301605 | Sta Teresa NHS | MAGSAYSAY | 0 | 1 | 4 | 1STY2CL SCI. LABS, 1STY2CL ICT LABS | BATCH 12 | 4499589.14 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund (2018 Batch 4)
26158 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110151 | Balansay Elementary School | MAMBURAO (Capital) | 0 | 1 | 5 | 1STY5CL | BATCH 12 | 5137252.86 |  |  | completed | 1
26159 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110164 | Fatima ES | MAMBURAO (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 3147592.44 |  |  | Completed | 1
26160 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110166 | Karyandangan Min. School | MAMBURAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 1967320 |  |  | Completed | 1
26161 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110185 | Talabaan ES Proper | MAMBURAO (Capital) | 0 | 1 | 5 | 1STY2CL, 1STY3CL | BATCH 12 | 4924912.44 |  |  | Completed | 1
26162 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110197 | Hacienda Yap ES | RIZAL | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 3527592.44 |  |  | Completed | 1
26163 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110206 | Salvacion ES | RIZAL | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 4452062.7 |  |  | Completed | 1
26164 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110208 | Sto. Niño ES | RIZAL | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2852766.09 |  |  | Completed | 1
26165 | NC 2017 | TVL | Region IV-B | Occidental Mindoro | 301582 | Paulino Legaspi, Sr. Memorial. NHS | SABLAYAN | 0 | 1 | 4 | 1STY2CL SCI. LABS, 1STY2CL ICT LABS | BATCH 12 | 5694908.58 |  |  | Completed | 1
26166 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110216 | Rang-ayan ES | SABLAYAN | 0 | 1 | 1 | 1STY2CL, KINDER CL | BATCH 12 | 2874403.02 |  |  | Completed | 1
26167 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110220 | San Vicente ES | SABLAYAN | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 4291649.29 |  |  | Completed | 1
26168 | NC 2017 | TVL | Region IV-B | Occidental Mindoro | 110224 | Sta. Rosa Elementary School | SABLAYAN | 0 | 1 | 3 | 1STY3CL, GRADE 1-10 CL | BATCH 12 | 4439085.01 |  |  | Completed | 1
26169 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110234 | General E. Aguinaldo Elementary School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2117320 |  |  | Completed | 1
26170 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110238 | Malisbong Elementary School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2107320 |  |  | Completed | 1
26171 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110222 | Selina Elementary School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2107320 |  |  | Completed | 1
26172 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110223 | Sotero Baluyot Elementary School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2047320 |  |  | Completed | 1
26173 | NC 2017 | K10 | Region IV-B | Occidental Mindoro |  | Taobuid Elementary School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 1867320 |  |  | Completed | 1
26174 | NC 2017 | K10 | Region IV-B | Occidental Mindoro |  | Taobuid High School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 1867320 |  |  | Completed | 1
26175 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110247 | Tuban Elementary School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2067320 |  |  | Completed | 1
26176 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110263 | La Curva ES | SAN JOSE | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 3134373.4 |  |  | Completed | 1
26177 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110312 | Pag-asa Central School | SAN JOSE | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 4391251.04 |  |  | Completed | 1
26178 | NC 2017 | SHS | Region IV-B | Occidental Mindoro | 301592 | Pedro T. Mendiola Sr. Memorial National High School | SAN JOSE | 0 | 1 | 4 | 1STY4CL | BATCH 12 | 6269452.73 |  |  | Completed | 1
26179 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110244 | San Nicolas Elem. School | San Nicolas, Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2107320 |  |  | Completed | 1
26180 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110171 | Mulawin ES | SANTA CRUZ | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 4737649.15 |  |  | Completed | 1
26181 | NC 2017 | TVL | Region IV-B | Palawan | 301674 | Bugsuk National High School - Mangsee Annex | BALABAC | 2 | 1 | 2 | TVL-RW | BATCH 12 | 6050241.02 |  |  | Completed | 1
26182 | NC 2017 | TVL | Region IV-B | Palawan | 301674 | Bugsuk National High School - Mangsee Annex | BALABAC | 2 |  | 2 | TVL-UW | BATCH 12 | 6683206.32 |  |  | Completed | 1
26183 | NC 2017 | TVL | Region IV-B | Palawan | 301674 | Bugsuk National High School - Mangsee Annex | BALABAC | 2 |  | 2 | 1CL ICT LAB | BATCH 12 | 6021176.59 |  |  | Completed | 1
26184 | NC 2017 | TVL | Region IV-B | Palawan | 309127 | Sibaring National High School | BALABAC | 2 | 1 | 1 | TVL-RW | BATCH 12 | 3025120.51 |  |  | Completed | 1 | [10 empty] | Abandoned
26185 | NC 2017 | TVL | Region IV-B | Palawan | 309127 | Sibaring National High School | BALABAC | 2 |  | 1 | TVL-UW | BATCH 12 | 3341603.165 |  |  | Completed | 1
26186 | NC 2017 | TVL | Region IV-B | Palawan | 301668 | Bataraza National High School | BATARAZA | 2 | 1 | 2 | TVL-UW | BATCH 12 | 6513206.32 |  |  | Completed | 1
26187 | NC 2017 | TVL | Region IV-B | Palawan | 301730 | Rio Tuba National High School | BATARAZA | 2 | 1 | 3 | TVL-RW | BATCH 12 | 9799809.48 |  |  | Completed | 1
26188 | NC 2017 | TVL | Region IV-B | Palawan | 309129 | Southern Bataraza National High School | BATARAZA | 2 | 1 | 1 | TVL-WU | BATCH 12 | 3390034.36 |  |  | Completed | 1
26189 | NC 2017 | TVL | Region IV-B | Palawan | 309115 | Sumbiling National High School | BATARAZA | 2 | 1 | 1 | TVL-RW | BATCH 12 | 3366862.02 |  |  | Completed | 1
26190 | NC 2017 | TVL | Region IV-B | Palawan | 309126 | Tarusan National High School | BATARAZA | 2 | 1 | 1 | TVL-UW | BATCH 12 | 3266603.16 |  |  | Completed | 1
26191 | NC 2017 | TVL | Region IV-B | Palawan | 301671 | Brooke's Point National High School - Pangobilian NHS | BROOKE'S POINT | 2 | 1 | 2 | TVL-UW | BATCH 12 | 6449206.32 |  |  | Completed | 1
26192 | NC 2017 | TVL | Region IV-B | Palawan | 301699 | Gov. Alfredo Abueg Sr. National Technology & Vocational Memorial High School | BROOKE'S POINT | 2 | 1 | 1 | TVL-UW | BATCH 12 | 3224603.16 |  |  | Completed | 1
26193 | NC 2017 | TVL | Region IV-B | Palawan | 301704 | Maasin National High School (Bernas NHS) | BROOKE'S POINT | 2 | 1 | 1 | TVL-UW | BATCH 12 | 3224603.16 |  |  | Completed | 1
26194 | NC 2017 | TVL | Region IV-B | Palawan | 301663 | Aramaywan National High School | NARRA | 2 | 1 | 1 | TVL-UW | BATCH 12 | 3171603.16 |  |  | Completed | 1
26195 | NC 2017 | TVL | Region IV-B | Palawan | 301690 | Dumangeña National High School | NARRA | 2 | 1 | 1 | TVL-RW | BATCH 12 | 2875120.51 |  |  | Reverted | 0 | [10 empty] | Project was not implemented by this office due to the fund was reverted as of December 31, 2017. Failure of bidding for projects funded under BEFF CY 2017 with SARO No. 2017-11-014265 dated November 10, 2017 (Batch 12) received by this office on November 24, 2017 due to NO INTERESTED BIDDER.
26196 | NC 2017 | TVL | Region IV-B | Palawan | 301710 | Narra National High School | NARRA | 2 | 1 | 2 | TVL-UW | BATCH 12 | 6343206.32 |  |  | Completed | 1
26197 | NC 2017 | TVL | Region IV-B | Palawan | 301726 | Quezon National High School | QUEZON | 2 | 1 | 1 | TVL-UW | BATCH 12 | 3212603.16 |  |  | Completed | 1
26198 | NC 2017 | TVL | Region IV-B | Palawan | 301727 | Quezon-Aramaywan National High School | QUEZON | 2 | 1 | 1 | TVL-RW | BATCH 12 | 2912120.51 |  |  | Completed | 1
26199 | NC 2017 | TVL | Region IV-B | Palawan | 301729 | Quinlogan National High School | QUEZON | 2 | 1 | 1 | TVL-UW | BATCH 12 | 3212603.16 |  |  | Completed | 1
26200 | NC 2017 | TVL | Region IV-B | Palawan | 301678 | Calandagan National High School | ARACELI | 1 | 1 | 2 | 1STY2CL ( 1 REG WORKSHOP) | BATCH 13 | 2803332 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Funds 2018
26201 | NC 2017 | TVL | Region IV-B | Palawan | 301711 | New Busuanga National High School | BUSUANGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3316873 |  |  | Completed | 1
26202 | NC 2017 | TVL | Region IV-B | Palawan | 301711 | New Busuanga National High School | BUSUANGA | 1 |  | 1 | 1STY2CL ( 1 REG WORKSHOP) | BATCH 13 | 2755720 |  |  | Completed | 1 | [10 empty] | Abandoned
26203 | NC 2017 | TVL | Region IV-B | Palawan | 301684 | Coron School of Fisheries | CORON | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3116873 |  |  | Completed | 1 | [10 empty] | Abandoned
26204 | NC 2017 | TVL | Region IV-B | Palawan | 301708 | Manamoc National High School | CUYO | 1 | 1 | 2 | 1STY4CL ( 2 SCI. LAB) | BATCH 13 | 5612310 |  |  | Completed | 1
26205 | NC 2017 | TVL | Region IV-B | Palawan | 301708 | Manamoc National High School | CUYO | 1 |  | 1 | 1STY2CL (1 ICT LAB) | BATCH 13 | 2774588 |  |  | Completed | 1
26206 | NC 2017 | TVL | Region IV-B | Palawan | 309109 | Bacao National High School (Dumaran NHS - Bacao NHS) | DUMARAN | 1 |  | 1 | 1STY2CL (1 ICT LAB) | BATCH 13 | 2774588 |  |  | Completed | 1
26207 | NC 2017 | TVL | Region IV-B | Palawan | 301691 | Dumaran National High School | DUMARAN | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 6332500 |  |  | Completed | 1
26208 | NC 2017 | TVL | Region IV-B | Palawan | 301729 | Quinlogan National High School | QUEZON | 2 | 1 | 1 | TVL-RW | BATCH 13 | 2912120.51 |  |  | Completed | 1
26209 | NC 2017 | TVL | Region IV-B | Palawan | 301743 | Tagusao National High School | QUEZON | 2 | 1 | 2 | TVL-UW | BATCH 13 | 6425206.32 |  |  | Reverted | 0 | [10 empty] | Project was not implemented by this office due to the fund was reverted as of December 31, 2017. Failure of bidding for projects funded under BEFF CY 2017 with SARO No. 2017-11-014359 dated November 10, 2017 (Batch 13) received by this office on November 24, 2017 due to NO INTERESTED BIDDER.
26210 | NC 2017 | TVL | Region IV-B | Palawan | 301743 | Tagusao National High School | QUEZON | 2 |  | 1 | TVL-RW | BATCH 13 | 2912120.51 |  |  | Reverted | 0 | [10 empty] | Project was not implemented by this office due to the fund was reverted as of December 31, 2017. Failure of bidding for projects funded under BEFF CY 2017 with SARO No. 2017-11-014359 dated November 10, 2017 (Batch 13) received by this office on November 24, 2017 due to NO INTERESTED BIDDER.
26211 | NC 2017 | TVL | Region IV-B | Palawan | 301680 | Candawaga National High School | RIZAL (MARCOS) | 2 | 1 | 4 | TVL-UW | BATCH 13 | 12990412.64 |  |  | Completed | 1
26212 | NC 2017 | TVL | Region IV-B | Palawan | 301702 | Jose P. Rizal National High School | RIZAL (MARCOS) | 2 | 1 | 1 | TVL-UW | BATCH 13 | 3240603.16 |  |  | Completed | 1
26213 | NC 2017 | TVL | Region IV-B | Palawan | 301705 | Magara School for Philippine Craftsmen | ROXAS | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3125811 |  |  | Completed | 1
26214 | NC 2017 | TVL | Region IV-B | Palawan | 301731 | Roxas National Comprehensive High School | ROXAS | 1 | 1 | 1 | 1STY2CL (1 REG WORKSHOP) | BATCH 13 | 2892916 |  |  | Completed | 1
26215 | NC 2017 | TVL | Region IV-B | Palawan | 301660 | Alimanguan National High School | SAN VICENTE | 1 | 1 | 1 | 1STY2CL (1 REG WORKSHOP) | BATCH 13 | 2908314 |  |  | Completed | 1
26216 | NC 2017 | TVL | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3150643 |  |  | Completed | 1
26217 | NC 2017 | TVL | Region IV-B | Palawan | 301719 | Panitian National High School | SOFRONIO ESPAÑOLA | 2 | 1 | 1 | TVL-UW | BATCH 13 | 3214603.16 |  |  | Completed | 1
26218 | NC 2017 | TVL | Region IV-B | Palawan | 301719 | Panitian National High School | SOFRONIO ESPAÑOLA | 2 |  | 1 | TVL-RW | BATCH 13 | 2908120.51 |  |  | Completed | 1
26219 | NC 2017 | TVL | Region IV-B | Palawan | 309107 | PANCOL NATIONAL HIGH SCHOOL - BANBANAN EXTENSION | TAYTAY | 1 | 1 | 1 | 1STY2CL (1 REG WORKSHOP) | BATCH 13 | 2755720 |  |  | Completed | 1
26220 | NC 2017 | TVL | Region IV-B | Palawan | 301683 | Sandoval National High School | TAYTAY | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 6357938 |  |  | Completed | 1
26221 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110151 | Balansay Elementary School | MAMBURAO (Capital) | 0 | 1 | 5 | 1STY5CL | BATCH 14 | 935397.86 |  |  | Completed | 1
26222 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110164 | Fatima ES | MAMBURAO (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 14 | 620842.58 |  |  | Completed | 1
26223 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110166 | Karyandangan Min. School | MAMBURAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 14 | 646425.92 |  |  | Completed | 1
26224 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110222 | Selina Elementary School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 14 | 506425.92 |  |  | Completed | 1
26225 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110223 | Sotero Baluyot Elementary School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 14 | 566425.92 |  |  | Completed | 1
26226 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110234 | General E. Aguinaldo Elementary School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 14 | 496425.92 |  |  | Completed | 1
26227 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110238 | Malisbong Elementary School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 14 | 506425.92 |  |  | Completed | 1
26228 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110244 | San Nicolas Elem. School | San Nicolas, Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 14 | 506425.92 |  |  | Completed | 1
26229 | NC 2017 | K10 | Region IV-B | Occidental Mindoro | 110247 | Tuban Elementary School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 14 | 546425.92 |  |  | Completed | 1
26230 | NC 2017 | K10 | Region IV-B | Occidental Mindoro |  | Taobuid Elementary School | Sablayan | 0 | 1 | 2 | 1STY2CL | BATCH 14 | 746425.92 |  |  | Completed | 1
26231 | NC 2017 | K10 | Region IV-B | Occidental Mindoro |  | Taobuid High School | Sablayan | 0 |  | 2 | 1STY2CL | BATCH 14 | 746425.92 |  |  | Completed | 1
36115 | NC 2018 | K10 | Region IV-B | Calapan City | 111539 | Lazareto ES | CITY OF CALAPAN (Capital) | 1 | 1 | 10 | 2STY10CL | BATCH 1 | 20693563.45 |  |  | Completed | 1 |  |  |  | 18ED0118 | 2018-04-12 | 2018-04-19 | 2018-05-18 | 2018-05-30 | 2018-06-06 | LN SALVADOR CONST CORP.
36116 | NC 2018 | TVL | Region IV-B | Calapan City | 301798 | Canubing National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 1 | 1 SCI LAB | BATCH 1 | 2744433.22 |  |  | Completed | 1 |  |  |  | 18ED0119 | 2018-04-12 | 2018-04-19 | 2018-05-02 | 2018-05-28 | 2018-06-01 | DELROL ENTERPRISES
36117 | NC 2018 | SHS | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 12 | 2units 2STY6CL | BATCH 1 | 24477952.84 |  |  | Completed | 1 |  |  |  | 18ED0120 | 2018-04-12 | 2018-04-19 | 2018-05-18 | 2018-05-30 | 2018-06-06 | ETVR TRADING & CONST.
36118 | NC 2018 | SHS | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1 |  | 12 | 2units 2STY6CL | BATCH 1 | 24477952.84 |  |  | Completed | 1 |  |  |  | 18ED0121 | 2018-04-12 | 2018-04-19 | 2018-05-18 | 2018-05-30 | 2018-06-06 | FRAMECON BLDRS
36119 | NC 2018 | TVL | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1 |  | 6 | 6 REG WORKSHOPS | BATCH 1 | 14576599.3 |  |  | Completed | 1 |  |  |  | 18ED0122 | 2018-04-12 | 2018-04-19 | 2018-05-18 | 2018-05-30 | 2018-06-06 | HIGH & MILES CONST.
36120 | NC 2018 | TVL | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1 |  | 2 | 2 SCI LAB | BATCH 1 | 5488866.43 |  |  | Completed | 1 |  |  |  | 18ED0123 | 2018-04-12 | 2018-04-19 | 2018-05-18 | 2018-05-30 | 2018-06-06 | SIALDANG CONST. & ENTERPRISES
36121 | NC 2018 | TVL | Region IV-B | Calapan City | 301802 | Nag-iba National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 1 | 1 REG WORKSHOP | BATCH 1 | 2429433.22 |  |  | Completed | 1 |  |  |  | 18ED0124 | 2018-04-12 | 2018-04-19 | 2018-05-02 | 2018-05-28 | 2018-06-01 | DELROL ENTERPRISES
36122 | NC 2018 | TVL | Region IV-B | Calapan City | 301802 | Nag-iba National High School | CITY OF CALAPAN (Capital) | 1 |  | 1 | 1 SCI LAB | BATCH 1 | 2744433.22 |  |  | Completed | 1 |  |  |  | 18ED0125 | 2018-04-12 | 2018-04-19 | 2018-05-02 | 2018-05-28 | 2018-06-01 | DELROL ENTERPRISES
36123 | NC 2018 | TVL | Region IV-B | Marinduque | 301553 | Maranlig National High School | TORRIJOS | 0 | 1 | 8 | 2STY 4 LAB (2 SCI & 2 ICT LAB) | Batch 3 | 40385299.28 |  |  | Completed | 1 |  |  | P00274161LZ | 18EA0215 | 2018-10-18 | 2018-10-25 | 2018-11-07 | 2018-11-20 | 2018-11-27 | Monolithic Construction and Concrete Products Inc.
36124 | NC 2018 | SHS | Region IV-B | Marinduque | 301554 | Marinduque NHS | BOAC (Capital) | 0 | 1 | 28 | 4STY28CL | Batch 3 | 114425984.56 |  |  | Completed | 1 |  |  | P00274162LZ | 18EA0216 | 2018-10-18 | 2018-10-25 | 2018-11-07 | 2018-11-21 | 2018-12-28 | Sargasso Construction and Development Corp.
36125 | NC 2018 | TVL | Region IV-B | Marinduque | 308801 | Poctoy NHS (Bonliw NHS-Poctoy Annex) | TORRIJOS | 0 | 1 | 8 | 2STY 4 LAB (2 SCI & 2 ICT LAB) | Batch 3 | 39388854.57 |  |  | Completed | 1 |  |  | P00274163LZ | 18EA0214 | 2018-10-18 | 2018-10-25 | 2018-11-07 | 2018-11-20 | 2018-11-27 | Monolithic Construction and Concrete Products Inc.
36126 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 110042 | Cabacao ES | ABRA DE ILOG | 0 | 1 | 4 | 2STY4CL | Batch 6 Realignment | 11128832.8 |  |  | Completed | 1 | [10 empty] | The Project is already delayed , Calibrated Action issued to contractor per Do 193,series of 2016.
36127 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 110081 | Calintaan CS | CALINTAAN | 0 | 1 | 6 | 2STY6CL | Batch 3 | 13669397.62 |  |  | Completed | 1
36128 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 110087 | Malpalon ES | CALINTAAN | 0 | 1 | 10 | 2STY10CL | Batch 3 | 21708523.23 |  |  | Completed | 1
36129 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 110102 | Binakas ES | LUBANG | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3001900 |  |  | Completed | 1
36130 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 110104 | Cabra ES | LUBANG | 0 | 1 | 12 | 2STY12CL | Batch 3 | 34781755.12 |  |  | Completed | 1 | [10 empty] | Calibrated Action issued to Contractor per DO 193, series of 2016 ( copy attached)/Proposed Revised Expiry date December 5,2019 if WSO is approved (Time extention for RD approval
36131 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 110110 | Maliig ES | LUBANG | 0 | 1 | 5 | 1STY5CL | Batch 3 | 12268004.75 |  |  | Completed | 1 | [10 empty] | Calibrated Action issued to Contractor per DO 193, series of 2016 ( copy attached)/Proposed Revised Expiry date October 6,2019 if WSO is approved (Time extention for RD approval)
36132 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 110112 | Tangal ES | LUBANG | 0 | 1 | 5 | 1STY5CL | Batch 3 | 12268004.75 |  |  | Completed | 1 | [10 empty] | Calibrated Action issued to Contractor per DO 193, series of 2016 ( copy attached)/Proposed Revised Expiry date October 6,2019 if WSO is approved (Time extention for RD approval)
36133 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 110113 | Tilik Elementary School | LUBANG | 0 | 1 | 12 | 2STY12CL | Batch 3 | 18300000 |  |  | Completed | 1 | [10 empty] | Completion of 12 cl
36134 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 110178 | San Luis ES | MAMBURAO (Capital) | 0 | 1 | 4 | 2STY4CL | Batch 3 | 10802770.61 |  |  | Completed | 1
36135 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 110210 | Buenavista ES | SABLAYAN | 0 | 1 | 6 | 2STY6CL | Batch 3 | 12506404.51 |  |  | Completed | 1
36136 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 110240 | Poblacion ES | SABLAYAN | 0 | 1 | 18 | 2units 3STY9CL | Batch 3 | 65337258.06 |  |  | Completed | 1
36137 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 169510 | Maliig ES - Balaguin PS | LUBANG | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3001900 |  |  | Completed | 1
36138 | NC 2018 | SHS | Region IV-B | Occidental Mindoro | 301574 | Calintaan NHS | CALINTAAN | 0 | 1 | 4 | 2STY4CL | Batch 3 | 11123513.89 |  |  | Completed | 1
36139 | NC 2018 | SHS | Region IV-B | Occidental Mindoro | 301586 | LUBANG VOCATIONAL HIGH SCHOOL | LUBANG | 0 | 1 | 10 | 2 UNITS 1STY5CL | Batch 3 | 24009386.7 |  |  | Completed | 1
36140 | NC 2018 | K10 | Region IV-B | Occidental Mindoro | 301587 | Lubang Vocational High School-Cabra | LUBANG | 0 | 1 | 12 | 2STY12CL | Batch 3 | 34781755.12 |  |  | Completed | 1 | [10 empty] | Calibrated Action issued to Contractor per DO 193, series of 2016 ( copy attached)/Proposed Revised Expiry date December 5,2019 if WSO is approved (Time extention for RD approval)
36141 | NC 2018 | SHS | Region IV-B | Occidental Mindoro | 301588 | Magsaysay National High School | MAGSAYSAY | 0 | 1 | 15 | 3STY15CL | Batch 3 | 37025603.17 |  |  | Completed | 1
36142 | NC 2018 | SHS | Region IV-B | Occidental Mindoro | 301593 | Occidental Mindoro NHS | MAMBURAO (Capital) | 0 | 1 | 4 | 2STY4CL | Batch 3 | 10229001.38 |  |  | Completed | 1
36143 | NC 2018 | SHS | Region IV-B | Occidental Mindoro | 301595 | RIZAL NATIONAL HIGH SCHOOL | RIZAL | 0 | 1 | 4 | 2STY4CL | Batch 3 | 10240852.96 |  |  | Completed | 1
36144 | NC 2018 | SHS | Region IV-B | Occidental Mindoro | 301596 | Sablayan NATIONAL COMPREHENSIVE HIGH SCHOOL | SABLAYAN | 0 | 1 | 6 | 2STY6CL | Batch 3 | 12504995.66 |  |  | Completed | 1
36145 | NC 2018 | SHS | Region IV-B | Occidental Mindoro | 301606 | Tanyag NHS | CALINTAAN | 0 | 1 | 4 | 2STY4CL | Batch 3 | 10371071.17 |  |  | Completed | 1
36146 | NC 2018 | SHS | Region IV-B | Occidental Mindoro | 308901 | San Jose National Agricultural and Industrial High School | SAN JOSE | 0 | 1 | 4 | 2STY4CL | Batch 3 | 10298223.79 |  |  | Completed | 1
36147 | NC 2018 | SHS | Region IV-B | Occidental Mindoro | 308904 | Manoot National High School | RIZAL | 0 | 1 | 4 | 2STY4CL | Batch 3 | 10235837.96 |  |  | Completed | 1
36148 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301611 | Apitong NHS | NAUJAN | 1 | 1 | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 17891803.52 |  |  | Completed | 1 |  |  |  | 18ED0126 |  |  |  | 2018-06-10 | 2018-06-16 | LN Salvador Constrcution
36149 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301612 | Macatoc NHS | VICTORIA | 1 | 1 | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 17891803.52 |  |  | Completed | 1 |  |  |  | 18ED0127 |  |  |  | 2018-06-12 | 2018-06-20 | B5 Builders & Supplies
36150 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301613 | Aurelio Arago MNHS | VICTORIA | 1 | 1 | 12 | 3 UNITS 2STY ICT LAB, 2STY SCI LAB, 1-2STY REG. WORKSHOP | BATCH 1 | 26837705.28 |  |  | Completed | 1 |  |  |  | 18ED0128 |  |  |  | 2018-06-12 | 2018-06-20 | Monolithic Const. & Concrete Products Inc.
36151 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301613 | Aurelio Arago MNHS | VICTORIA | 1 |  | 6 | 1 UNIT 3STY6CL REGULAR WORKSHOPS | BATCH 1 | 13739515.1 |  |  | Completed | 1 |  |  |  | 18ED0129 |  |  |  | 2018-05-28 | 2018-06-01 | Marc Jill Construction
36152 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301614 | Aurora NHS | NAUJAN | 1 | 1 | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 17891803.52 |  |  | Completed | 1 |  |  |  | 18ED0130 |  |  |  | 2018-05-28 | 2018-06-01 | Framecon Builders
36153 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301616 | Baco NHS | BACO | 1 | 1 | 12 | 3 UNITS 2STY ICT LAB, 2STY SCI LAB, 2STY REG. WORKSHOP | BATCH 1 | 26837705.28 |  |  | Completed | 1 |  |  |  | 18ED0131 |  |  |  | 2018-07-12 | 2018-07-20 | Orient Star Const. Inc.
36154 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301619 | Bayuin NHS | SOCORRO | 1 | 1 | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 17891803.52 |  |  | Completed | 1 |  |  |  | 18ED0132 |  |  |  | 2018-05-28 | 2018-06-01 | Framecon Builders
36155 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301627 | Domingo Yu Chu NHS | POLA | 1 | 1 | 6 | 3STY6CL REG. WORKSHOP | BATCH 1 | 13739515.1 |  |  | Completed | 1 |  |  |  | 18ED0133 |  |  |  | 2018-06-18 | 2018-06-24 | St. Gerard Const. Gen. Contractor & Devt. Corp
36156 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301627 | Domingo Yu Chu NHS | POLA | 1 |  | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 17891803.52 |  |  | Completed | 1 |  |  |  | 18ED0134 |  |  |  | 2018-06-12 | 2018-06-20 | St. Gerard Const. Gen. Contractor & Devt. Corp
36157 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301628 | Araceli B. Pantilanan - Bacawan High School | POLA | 1 | 1 | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 18786393.7 |  |  | Completed | 1 |  |  |  | 18ED0135 |  |  |  | 2018-07-12 | 2018-07-20 | C.B. Tampengco Const. & Supply
36158 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301629 | Matulatula High School | POLA | 1 | 1 | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 18091803.52 |  |  | Completed | 1 |  |  |  | 18ED0136 |  |  |  | 2018-07-12 | 2018-07-20 | DZEE Builders & Const. Supply
36159 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301629 | Matulatula High School | POLA | 1 |  | 1 | 1STY UNIQUE WORKSHOP | BATCH 1 | 2313745.92 |  |  | Completed | 1 |  |  |  | 18ED0137 |  |  |  | 2018-07-19 | 2018-07-25 | DZEE Builders & Const. Supply
36160 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301630 | Doroteo S. Mendoza Sr. MNHS | NAUJAN | 1 | 1 | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 17891803.52 |  |  | Completed | 1 |  |  |  | 18ED0138 |  |  |  | 2018-07-10 | 2018-07-16 | Framecon Builders
36161 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301634 | Leuteboro NHS | SOCORRO | 1 | 1 | 8 | 1 UNIT 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 17424790.26 |  |  | Completed | 1 |  |  |  | 18ED0139 |  |  |  | 2018-07-18 | 2018-07-24 | Framecon Builders
36162 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301634 | Leuteboro NHS | SOCORRO | 1 |  | 12 | 1 UNIT 3STY12CL REG. WORKSHOP | BATCH 1 | 29809267.25 |  |  | Completed | 1 |  |  |  | 18ED0103 |  |  |  | 2018-08-10 | 2018-08-20 | Framecon Builders
36163 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301634 | Leuteboro NHS | SOCORRO | 1 |  | 6 | 3 UNITS 1STY2CL UNIQUE WORKSHOP | BATCH 1 | 6941237.76 |  |  | Completed | 1 |  |  |  | 18ED0104 |  |  |  | 2018-07-19 | 2018-07-25 | Marc Jill Construction
36164 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301635 | Fortuna NHS | SOCORRO | 1 | 1 | 8 | 1 UNIT 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 17159570.67 |  |  | Completed | 1 |  |  |  | 18ED0105 |  |  |  | 2018-07-12 | 2018-07-20 | C.B. Tampengco Const. & Supply
36165 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301642 | Melgar NHS | NAUJAN | 1 | 1 | 8 | 4STY 8CL ICT & SCI. LAB | BATCH 1 | 17459570.67 |  |  | Completed | 1 |  |  |  | 18ED0106 |  |  |  | 2018-07-18 | 2018-07-24 | Delrol Enterprises
36166 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301642 | Melgar NHS | NAUJAN | 1 |  | 6 | 3STY 6CL REG. WORKSHOP | BATCH 1 | 13739515.1 |  |  | Completed | 1 |  |  |  | 18ED0107 |  |  |  | 2018-07-10 | 2018-07-16 | Delrol Enterprises
36167 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301645 | Naujan Municipal High School | NAUJAN | 1 | 1 | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 18091303.52 |  |  | Completed | 1 |  |  |  | 18ED0108 |  |  |  | 2018-07-10 | 2018-07-16 | Framecon Builders
36168 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301648 | Porfirio Comia MNHS | NAUJAN | 1 | 1 | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 18091803.52 |  |  | Completed | 1 |  |  |  | 18ED0109 |  |  |  | 2018-07-10 | 2018-07-16 | Orient Star Const. Inc.
36169 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301651 | San Agustin NHS | NAUJAN | 1 | 1 | 12 | 3 UNITS 2STY ICT LAB, 2STY SCI LAB, 1-2STY REG. WORKSHOP | BATCH 1 | 26837705.28 |  |  | Completed | 1 |  |  |  | 18ED0110 |  |  |  | 2018-05-28 | 2018-06-01 | Framecon Builders
36170 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301651 | San Agustin NHS | NAUJAN | 1 |  | 6 | 1-3STY6CL REG. WORKSHOP | BATCH 1 | 13739515.1 |  |  | Completed | 1 |  |  |  | 18ED0111 |  |  |  | 2018-05-28 | 2018-06-01 | Marc Jill Construction
36171 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301653 | San Teodoro NHS | SAN TEODORO | 1 | 1 | 8 | 1 UNIT 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 17359570.67 |  |  | Completed | 1 |  |  |  | 18ED0112 |  |  |  | 2018-07-18 | 2018-07-24 | Framecon Builders
36172 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 309001 | Inarawan NHS | NAUJAN | 1 | 1 | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 17891803.52 |  |  | Completed | 1 |  |  |  | 18ED0113 |  |  |  | 2018-06-11 | 2018-06-19 | Framecon Builders
36173 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 309001 | Inarawan NHS | NAUJAN | 1 |  | 8 | 4STY 8CL REG. WORKSHOP | BATCH 1 | 17159570.67 |  |  | Completed | 1 |  |  |  | 18ED0114 |  |  |  | 2018-07-12 | 2018-07-20 | C.B. Tampengco Const. & Supply
36174 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 309008 | Anastacio Dela Chica High School | BACO | 1 | 1 | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 17891803.52 |  |  | Completed | 1 |  |  |  | 18ED0115 |  |  |  | 2018-07-12 | 2018-07-20 | ETVR Trading & Const.
36175 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 309008 | Anastacio Dela Chica High School | BACO | 1 |  | 2 | 1STY REG. WORKSHOP | BATCH 1 | 2313745.92 |  |  | Completed | 1 |  |  |  | 18ED0116 |  |  |  | 2018-05-28 | 2018-06-01 | C.B. Tampengco Const. & Supply
36176 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 309025 | Leandro Panganiban Sr. - Tagumpay High School | POLA | 1 | 1 | 8 | 2 UNITS 2STY ICT LAB, 2STY SCI LAB | BATCH 1 | 18786393.7 |  |  | Completed | 1 |  |  |  | 18ED0117 |  |  |  | 2018-07-12 | 2018-07-20 | DZEE Builders & Const. Supply
36177 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301617 | Balugo NHS | MANSALAY | 2 | 1 | 8 | 2 UNITS 2STY ICT & 2STY SCI LAB | BATCH 1 | 18509024.32 |  |  | Completed | 1
36178 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301621 | Maujao NHS | BULALACAO (SAN PEDRO) | 2 | 1 | 8 | 2 UNITS 2STY ICT & SCI LAB | BATCH 1 | 18678233.12 |  |  | Completed | 1
36179 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301622 | San Roque NHS | BULALACAO (SAN PEDRO) | 2 | 1 | 8 | 1 UNIT 4STY ICT & SCI LAB. | BATCH 1 | 17311645.36 |  |  | Completed | 1
36180 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301623 | Bulbugan NHS | GLORIA | 2 | 1 | 8 | 1 UNIT 4STY ICT & SCI LAB | BATCH 1 | 21909440.79 |  |  | Completed | 1
36181 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301633 | Kaligtasan NHS | BONGABONG | 2 | 1 | 8 | 1 UNIT 4STY ICT & SCI LAB. | BATCH 1 | 17418454.16 |  |  | Completed | 1
36182 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301636 | Malamig NHS | GLORIA | 2 | 1 | 4 | 1 UNIT 2STY ICT & SCI LAB | BATCH 1 | 9146880.26 |  |  | Completed | 1
36183 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301638 | Manaul National High School | MANSALAY | 2 | 1 | 8 | 2 UNITS ICT &2STY SCI LAB | BATCH 1 | 18299996.72 |  |  | Completed | 1
36184 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301652 | San Mariano NHS | ROXAS | 2 | 1 | 12 | 1 UNIT 1 STY UNIQUE WORKSHOP, 2STY REG WORKSHOP, ICT & SCI. LAB | BATCH 1 | 22793736.94 |  |  | Completed | 1 | [8 empty] | 2018-06-25 | Orient Star Const. Inc./CMCS Builders JV
36185 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 301655 | Villapagasa NHS | BANSUD | 2 | 1 | 16 | 2 UNITS 2STY ICT & SCI LAB., 2STY REG. WORKSHOP | BATCH 1 | 35248880.92 |  |  | Completed | 1 | [8 empty] | 2018-07-30 | JO Builders
36186 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 309019 | Pag-asa NHS | BANSUD | 2 | 1 | 8 | 1 UNIT 2STY ICT & SCI. LAB | BATCH 1 | 23198146 |  |  | Completed | 1 | [8 empty] | 2018-07-24 | Sixteen Enterprises | With Approved Buffer Fund (2018 Batch 4)
36187 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 309027 | Felimon M. Salcedo Sr. MNHS | BANSUD | 2 | 1 | 8 | 1UNIT 2STY8CL ICT & SCI LAB | BATCH 1 | 17418454.16 |  |  | Completed | 1 | [8 empty] | 2018-07-23 | Orient Star Const. Inc.
36188 | NC 2018 | K10 | Region IV-B | Oriental Mindoro | 110442 | Gloria CS | GLORIA | 2 | 1 | 8 | 2 UNITS 2STY4CL | Batch 3 | 24923151.5 |  |  | Completed | 1
36189 | NC 2018 | TVL | Region IV-B | Oriental Mindoro | 110471 | Mansalay CS | MANSALAY | 2 | 1 | 5 | 1 unit 1STY2CL & 1 UNIT 1STY3CL | Batch 3 | 6987081.7 |  |  | Completed | 1
36190 | NC 2018 | K10 | Region IV-B | Oriental Mindoro | 300448 | Bongabong Technical and Vocational High School | BONGABONG | 2 | 1 | 2 | Construction of ALS Bldg. | Batch 3 | 3795771.45 |  |  | Completed | 1
36191 | NC 2018 | SHS | Region IV-B | Palawan | 301657 | Abo-Abo National High School | SOFRONIO ESPAÑOLA | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17291790.26 |  |  | Completed | 1
36192 | NC 2018 | TVL | Region IV-B | Palawan | 301657 | Abo-Abo National High School | SOFRONIO ESPAÑOLA | 2 |  | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 16906790.26 |  |  | Reverted | 0
36193 | NC 2018 | TVL | Region IV-B | Palawan | 301657 | Abo-Abo National High School | SOFRONIO ESPAÑOLA | 2 |  | 2 | 2STY2CL RW | BATCH 1 | 18153803.52 |  |  | Reverted | 0
36194 | NC 2018 | TVL | Region IV-B | Palawan | 301659 | Aborlan NHS | ABORLAN | 3 | 1 | 2 | 2STY SCI LAB | BATCH 1 | 14282325.89 |  |  | Reverted | 0
36195 | NC 2018 | TVL | Region IV-B | Palawan | 301659 | Aborlan NHS | ABORLAN | 3 |  | 2 | 2STY ICT LAB | BATCH 1 | 14282325.89 |  |  | Reverted | 0
36196 | NC 2018 | TVL | Region IV-B | Palawan | 301659 | Aborlan NHS | ABORLAN | 3 |  | 2 | 2STY REG WORKSHOP | BATCH 1 | 14282325.89 |  |  | Reverted | 0
36197 | NC 2018 | TVL | Region IV-B | Palawan | 301659 | Aborlan NHS | ABORLAN | 3 |  | 2 | 2STY REG WORKSHOP | BATCH 1 | 14282325.89 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
36198 | NC 2018 | K10 | Region IV-B | Palawan | 170522 | Alfredo Gregorio Memorial Elementary School | BATARAZA | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12067168.02 |  |  | Completed | 1
36199 | NC 2018 | TVL | Region IV-B | Palawan | 301660 | Alimanguan National High School | SAN VICENTE | 1 | 1 | 4 | 2STY8CL (4 REG WORKSHOPS) | BATCH 1 | 15798140 |  |  | Completed | 1
36200 | NC 2018 | TVL | Region IV-B | Palawan | 301660 | Alimanguan National High School | SAN VICENTE | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9136100 |  |  | Completed | 1
36201 | NC 2018 | TVL | Region IV-B | Palawan | 301660 | Alimanguan National High School | SAN VICENTE | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9136100 |  |  | Completed | 1
36202 | NC 2018 | TVL | Region IV-B | Palawan | 301661 | Apurawan NHS | ABORLAN | 3 | 1 | 2 | 2STY SCI LAB & ICT LAB | BATCH 1 | 14282325.89 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
36203 | NC 2018 | TVL | Region IV-B | Palawan | 301662 | Araceli National High School | ARACELI | 1 | 1 | 5 | 2STY10CL ( 5 REG. WORKSHOP) | BATCH 1 | 21211820 |  |  | Completed | 1
36204 | NC 2018 | TVL | Region IV-B | Palawan | 301662 | Araceli National High School | ARACELI | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 10355620 |  |  | Completed | 1
36205 | NC 2018 | TVL | Region IV-B | Palawan | 301662 | Araceli National High School | ARACELI | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 10355620 |  |  | Completed | 1
36206 | NC 2018 | TVL | Region IV-B | Palawan | 301663 | Aramaywan National High School | NARRA | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 16939790.26 |  |  | Reverted | 0
36207 | NC 2018 | TVL | Region IV-B | Palawan | 301663 | Aramaywan National High School | NARRA | 2 |  | 3 | 3STY3CL RW | BATCH 1 | 13604515.1 |  |  | Completed | 1
36208 | NC 2018 | TVL | Region IV-B | Palawan | 309109 | Bacao National High School (Dumaran NHS - Bacao NHS) | DUMARAN | 1 | 1 | 4 | 2STY8CL (3REG WORKSHOP AND 1 ICT LAB) | BATCH 1 | 17668620 |  |  | Reverted | 0 | [10 empty] | removed in backlog; no need additional fund; With Approved Buffer Fund (2018 Batch 4); No buildable space as per letter of School Division Superintindent Servillano A. Arzaga CESO IV dated 6/29/2018. Request for negotiation dated 7/31/2018. Funds negated due to 3 times bidding failure.
36209 | NC 2018 | TVL | Region IV-B | Palawan | 309109 | Bacao National High School (Dumaran NHS - Bacao NHS) | DUMARAN | 1 |  | 2 | 2STY4CL (2UNITS SCI. LAB) | BATCH 1 | 9494540 |  |  | Completed | 1
36210 | NC 2018 | TVL | Region IV-B | Palawan | 301666 | Balabac National High School | BALABAC | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 17967714 |  |  | Completed | 1
36211 | NC 2018 | TVL | Region IV-B | Palawan | 309113 | Bancalaan National High School | BALABAC | 2 | 1 | 2 | 2STY1CL SCI. LAB & 1CL ICT LAB | BATCH 1 | 9656278.81 |  |  | Reverted | 0
36212 | NC 2018 | TVL | Region IV-B | Palawan | 309113 | Bancalaan National High School | BALABAC | 2 |  | 2 | 2STY2CL RW | BATCH 1 | 9491278.81 |  |  | Reverted | 0
36213 | NC 2018 | TVL | Region IV-B | Palawan | 301667 | Barotuan National High School | EL NIDO (BACUIT) | 1 | 1 | 9 | 3STY18CL (9 REG. WORKSHOP) | BATCH 1 | 42017820 |  |  | Completed | 1
36214 | NC 2018 | TVL | Region IV-B | Palawan | 301667 | Barotuan National High School | EL NIDO (BACUIT) | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9370940 |  |  | Reverted | 0
36215 | NC 2018 | TVL | Region IV-B | Palawan | 301667 | Barotuan National High School | EL NIDO (BACUIT) | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9370940 |  |  | Reverted | 0
36216 | NC 2018 | K10 | Region IV-B | Palawan | 110825 | Bataraza CS | BATARAZA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9109901.76 |  |  | Completed | 1
36217 | NC 2018 | TVL | Region IV-B | Palawan | 301668 | Bataraza National High School | BATARAZA | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 17239790.26 |  |  | Completed | 1
36218 | NC 2018 | TVL | Region IV-B | Palawan | 301668 | Bataraza National High School | BATARAZA | 2 |  | 2 | 2STY2CL RW | BATCH 1 | 18171803.52 |  |  | Completed | 1
36219 | NC 2018 | TVL | Region IV-B | Palawan | 301669 | Bato National High School | TAYTAY | 1 | 1 | 4 | 2STY8CL (4 REG WORKSHOPS) | BATCH 1 | 15850000.5 |  |  | Reverted | 0 | [10 empty] | Unfinished
36220 | NC 2018 | TVL | Region IV-B | Palawan | 301669 | Bato National High School | TAYTAY | 1 |  | 2 | 2STY4CL (2 REG WORKSHOPS) | BATCH 1 | 9146400 |  |  | Reverted | 0
36221 | NC 2018 | TVL | Region IV-B | Palawan | 301669 | Bato National High School | TAYTAY | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9146400 |  |  | Reverted | 0
36222 | NC 2018 | TVL | Region IV-B | Palawan | 301669 | Bato National High School | TAYTAY | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9146400 |  |  | Reverted | 0
36223 | NC 2018 | TVL | Region IV-B | Palawan | 301685 | Borac National High School | CORON | 1 | 1 | 4 | 2STY8CL (4 REG WORKSHOPS) | BATCH 1 | 17484250 |  |  | Reverted | 0
36224 | NC 2018 | TVL | Region IV-B | Palawan | 301685 | Borac National High School | CORON | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9282875 |  |  | Completed | 1
36225 | NC 2018 | TVL | Region IV-B | Palawan | 301685 | Borac National High School | CORON | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9282875 |  |  | Completed | 1
36226 | NC 2018 | TVL | Region IV-B | Palawan | 301671 | Brooke's Point National High School - Pangobilian NHS | BROOKE'S POINT | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 17131790.26 |  |  | Completed | 1
36227 | NC 2018 | TVL | Region IV-B | Palawan | 301671 | Brooke's Point National High School - Pangobilian NHS | BROOKE'S POINT | 2 |  | 6 | 3STY3CL RW | BATCH 1 | 27497030.2 |  |  | Completed | 1
36228 | NC 2018 | K10 | Region IV-B | Palawan | 111017 | Bucana ES | EL NIDO (BACUIT) | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 33372000 |  |  | Completed | 1
36229 | NC 2018 | TVL | Region IV-B | Palawan | 309128 | Bulawit National High School (Gaudencio Abordo NHS R.A.6992) | LINAPACAN | 1 | 1 | 4 | 3STY15CL (4 REG WORKSHOP AND 7 REG CL) | BATCH 1 | 36551610 |  |  | Reverted | 0
36230 | NC 2018 | TVL | Region IV-B | Palawan | 309128 | Bulawit National High School (Gaudencio Abordo NHS R.A.6992) | LINAPACAN | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 10305150 |  |  | Reverted | 0
36231 | NC 2018 | TVL | Region IV-B | Palawan | 309128 | Bulawit National High School (Gaudencio Abordo NHS R.A.6992) | LINAPACAN | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 10305150 |  |  | Reverted | 0
36232 | NC 2018 | TVL | Region IV-B | Palawan | 301677 | Cagayancillo National High School | CAGAYANCILLO | 1 | 1 | 4 | 2STY8CL (4 REG WORKSHOPS) | BATCH 1 | 17915820 |  |  | Completed | 1
36233 | NC 2018 | TVL | Region IV-B | Palawan | 301677 | Cagayancillo National High School | CAGAYANCILLO | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 10820150 |  |  | Reverted | 0
36234 | NC 2018 | TVL | Region IV-B | Palawan | 301677 | Cagayancillo National High School | CAGAYANCILLO | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 10820150 |  |  | Reverted | 0
36235 | NC 2018 | TVL | Region IV-B | Palawan | 301678 | Calandagan National High School | ARACELI | 1 | 1 | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 10355620 |  |  | Reverted | 0
36236 | NC 2018 | TVL | Region IV-B | Palawan | 301678 | Calandagan National High School | ARACELI | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 10355620 |  |  | Reverted | 0
36237 | NC 2018 | K10 | Region IV-B | Palawan | 110870 | Calasaguen Highway ES (Calasaguen ES) | BROOKE'S POINT | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11824168.02 |  |  | Completed | 1
36238 | NC 2018 | TVL | Region IV-B | Palawan | 301680 | Candawaga National High School | RIZAL (MARCOS) | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 17219790.26 |  |  | Completed | 1
36239 | NC 2018 | TVL | Region IV-B | Palawan | 301680 | Candawaga National High School | RIZAL (MARCOS) | 2 |  | 3 | 3STY3CL RW | BATCH 1 | 13649515.1 |  |  | Reverted | 0
36240 | NC 2018 | SHS | Region IV-B | Palawan | 309140 | CAPONAYAN NHS | CUYO | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 14038900 |  |  | Reverted | 0
36241 | NC 2018 | TVL | Region IV-B | Palawan | 301681 | Caruray National High School | SAN VICENTE | 1 | 1 | 3 | 3STY6CL (3 REG WORKSHOPS) | BATCH 1 | 13609390 |  |  | Completed | 1
36242 | NC 2018 | TVL | Region IV-B | Palawan | 301681 | Caruray National High School | SAN VICENTE | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9146400 |  |  | Completed | 1
36243 | NC 2018 | TVL | Region IV-B | Palawan | 301681 | Caruray National High School | SAN VICENTE | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9146400 |  |  | Completed | 1
36244 | NC 2018 | SHS | Region IV-B | Palawan | 342752 | Central Taytay Senior High School | TAYTAY | 1 | 1 | 10 | 2STY10CL | BATCH 1 | 20146800 |  |  | Completed | 1
36245 | NC 2018 | SHS | Region IV-B | Palawan | 342752 | Central Taytay Senior High School | TAYTAY | 1 |  | 8 | 2STY8CL | BATCH 1 | 17484250 |  |  | Completed | 1
36246 | NC 2018 | TVL | Region IV-B | Palawan | 342752 | Central Taytay Senior High School | TAYTAY | 1 |  | 6 | 3STY12CL (6 REG WORKSHOPS) | BATCH 1 | 26996300 |  |  | Completed | 1
36247 | NC 2018 | TVL | Region IV-B | Palawan | 342752 | Central Taytay Senior High School | TAYTAY | 1 |  | 7 | 3STY12CL (5 REG WORKSHOPS AND 2 REG CLASSROOMS) | BATCH 1 | 26996300 |  |  | Completed | 1
36248 | NC 2018 | TVL | Region IV-B | Palawan | 342752 | Central Taytay Senior High School | TAYTAY | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9146400 |  |  | Completed | 1
36249 | NC 2018 | TVL | Region IV-B | Palawan | 342752 | Central Taytay Senior High School | TAYTAY | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9146400 |  |  | Completed | 1
36250 | NC 2018 | TVL | Region IV-B | Palawan | 309134 | Cheey National High School | BUSUANGA | 1 | 1 | 6 | 3STY12CL (6 REG WORKSHOPS) | BATCH 1 | 27948020 |  |  | Completed | 1 | [10 empty] | Unfinished
36251 | NC 2018 | TVL | Region IV-B | Palawan | 309134 | Cheey National High School | BUSUANGA | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 10887100 |  |  | Completed | 1
36252 | NC 2018 | TVL | Region IV-B | Palawan | 309134 | Cheey National High School | BUSUANGA | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 10887100 |  |  | Completed | 1
36253 | NC 2018 | TVL | Region IV-B | Palawan | 309120 | Concepcion National High School | AGUTAYA | 1 | 1 | 9 | 3STY9CL (2 REG WORKSHOP AND 5 REG CLASSROOMS) | BATCH 1 | 25641850 |  |  | Completed | 1
36254 | NC 2018 | TVL | Region IV-B | Palawan | 309120 | Concepcion National High School | AGUTAYA | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 10989070 |  |  | Completed | 1
36255 | NC 2018 | TVL | Region IV-B | Palawan | 309120 | Concepcion National High School | AGUTAYA | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 10989070 |  |  | Completed | 1
36256 | NC 2018 | TVL | Region IV-B | Palawan | 309170 | Concepcion National High School | BUSUANGA | 1 | 1 | 2 | 2STY4CL (2 REG WORKSHOPS) | BATCH 1 | 9291527 |  |  | Completed | 1 | [10 empty] | for reversion
36257 | NC 2018 | TVL | Region IV-B | Palawan | 309170 | Concepcion National High School | BUSUANGA | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9291527 |  |  | Completed | 1 | [10 empty] | for reversion
36258 | NC 2018 | TVL | Region IV-B | Palawan | 309170 | Concepcion National High School | BUSUANGA | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9291527 |  |  | Completed | 1
36259 | NC 2018 | TVL | Region IV-B | Palawan | 301684 | Coron School of Fisheries | CORON | 1 | 1 | 6 | 3STY9CL (3 REG WORKSHOP AND 3 REG CLASSROOMS) | BATCH 1 | 25305040 |  |  | Completed | 1
36260 | NC 2018 | TVL | Region IV-B | Palawan | 301684 | Coron School of Fisheries | CORON | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9274120 |  |  | Completed | 1
36261 | NC 2018 | TVL | Region IV-B | Palawan | 301684 | Coron School of Fisheries | CORON | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9274120 |  |  | Completed | 1
36262 | NC 2018 | K10 | Region IV-B | Palawan | 110720 | Culandanum ES | ABORLAN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9214278.81 |  |  | Completed | 1
36263 | NC 2018 | K10 | Region IV-B | Palawan | 110937 | Culion ES | CULION | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 33990000 |  |  | Completed | 1
36264 | NC 2018 | TVL | Region IV-B | Palawan | 301687 | Culion Sanitarium Special National High School | CULION | 1 | 1 | 5 | 2STY10CL ( 5 REG. WORKSHOP) | BATCH 1 | 22302590 |  |  | Completed | 1
36265 | NC 2018 | TVL | Region IV-B | Palawan | 301687 | Culion Sanitarium Special National High School | CULION | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 10850020 |  |  | Completed | 1
36266 | NC 2018 | TVL | Region IV-B | Palawan | 301687 | Culion Sanitarium Special National High School | CULION | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 10850020 |  |  | Completed | 1
36267 | NC 2018 | K10 | Region IV-B | Palawan | 111001 | CUYO CENTRAL SCHOOL | CUYO | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17819000 |  |  | Completed | 1
36268 | NC 2018 | TVL | Region IV-B | Palawan | 301688 | Cuyo National High School | CUYO | 1 | 1 | 6 | 3STY9CL (1 REG WORKSHOP, 1 ICT LAB, 1 SCI. LAB AND 3 REG CLASSROOM) | BATCH 1 | 25876690 |  |  | Completed | 1
36269 | NC 2018 | K10 | Region IV-B | Palawan | 110872 | Danadio Elementary School | BROOKE'S POINT | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11824168.02 |  |  | Completed | 1
36270 | NC 2018 | TVL | Region IV-B | Palawan | 301689 | Danawan National High School | MAGSAYSAY | 1 | 1 | 4 | 2STY8CL (4 REG WORKSHOPS) | BATCH 1 | 17256620 |  |  | Completed | 1
36271 | NC 2018 | TVL | Region IV-B | Palawan | 301689 | Danawan National High School | MAGSAYSAY | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 10301030 |  |  | Completed | 1
36272 | NC 2018 | TVL | Region IV-B | Palawan | 301689 | Danawan National High School | MAGSAYSAY | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 10301030 |  |  | Completed | 1
36273 | NC 2018 | TVL | Region IV-B | Palawan | 309168 | Decalachao National High School | CORON | 1 | 1 | 4 | 2STY8CL (4 REG WORKSHOPS) | BATCH 1 | 16480000 |  |  | Completed | 1
36274 | NC 2018 | TVL | Region IV-B | Palawan | 309168 | Decalachao National High School | CORON | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9291527 |  |  | Completed | 1
36275 | NC 2018 | TVL | Region IV-B | Palawan | 309168 | Decalachao National High School | CORON | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9137037 |  |  | Completed | 1
36276 | NC 2018 | TVL | Region IV-B | Palawan | 301690 | Dumangeña National High School | NARRA | 2 | 1 | 2 | 2STY1CL SCI. LAB & 1CL ICT LAB | BATCH 1 | 9010901.76 |  |  | Completed | 1
36277 | NC 2018 | TVL | Region IV-B | Palawan | 301692 | Dumaran Mainland National High School | DUMARAN | 1 | 1 | 4 | 2STY8CL (4REG. WORKSHOPS) | BATCH 1 | 17197910 |  |  | Completed | 1
36278 | NC 2018 | TVL | Region IV-B | Palawan | 301692 | Dumaran Mainland National High School | DUMARAN | 1 |  | 2 | 2STY4CL (1 SCI. LAB AND 1 ICT LAB) | BATCH 1 | 9494540 |  |  | Completed | 1
36279 | NC 2018 | TVL | Region IV-B | Palawan | 301691 | Dumaran National High School | DUMARAN | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9494540 |  |  | Completed | 1 | [10 empty] | Abandoned (With Approved Buffer Fund)
36280 | NC 2018 | TVL | Region IV-B | Palawan | 301691 | Dumaran National High School | DUMARAN | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9494540 |  |  | Completed | 1 | [10 empty] | Abandoned (With Approved Buffer Fund)
36281 | NC 2018 | TVL | Region IV-B | Palawan | 301693 | El Nido National High School | EL NIDO (BACUIT) | 1 | 1 | 12 | 3STY12CL (12 REG WORKSHOPS) | BATCH 1 | 29978150 |  |  | Completed | 1
36282 | NC 2018 | TVL | Region IV-B | Palawan | 301693 | El Nido National High School | EL NIDO (BACUIT) | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9324590 |  |  | Completed | 1
36283 | NC 2018 | TVL | Region IV-B | Palawan | 301693 | El Nido National High School | EL NIDO (BACUIT) | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9324590 |  |  | Completed | 1
36284 | NC 2018 | SHS | Region IV-B | Palawan | 309141 | ELISEO A. LAGRADA OBLIAN NHS | BROOKE'S POINT | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11989168.02 |  |  | Completed | 1
36285 | NC 2018 | TVL | Region IV-B | Palawan | 301695 | Gaudencio E. Abordo Mem. National High School | AGUTAYA | 1 | 1 | 5 | 2STY10CL ( 5 REG. WORKSHOP) | BATCH 1 | 22080110 |  |  | Completed | 1
36286 | NC 2018 | TVL | Region IV-B | Palawan | 301695 | Gaudencio E. Abordo Mem. National High School | AGUTAYA | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 10989070 |  |  | Completed | 1
36287 | NC 2018 | TVL | Region IV-B | Palawan | 301695 | Gaudencio E. Abordo Mem. National High School | AGUTAYA | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 10989070 |  |  | Completed | 1
36288 | NC 2018 | TVL | Region IV-B | Palawan | 301699 | Gov. Alfredo Abueg Sr. National Technology & Vocational Memorial High School | BROOKE'S POINT | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 17131790.26 |  |  | Completed | 1
36289 | NC 2018 | TVL | Region IV-B | Palawan | 301699 | Gov. Alfredo Abueg Sr. National Technology & Vocational Memorial High School | BROOKE'S POINT | 2 |  | 6 | 3STY6CL RW | BATCH 1 | 29212267.25 |  |  | Completed | 1
36290 | NC 2018 | TVL | Region IV-B | Palawan | 301701 | ISAUB NATIONAL HIGH SCHOOL | ABORLAN | 3 | 1 | 2 | 2STY SCI LAB & ICT LAB | BATCH 1 | 14422348.69 |  |  | Completed | 1
36291 | NC 2018 | TVL | Region IV-B | Palawan | 301701 | ISAUB NATIONAL HIGH SCHOOL | ABORLAN | 3 |  | 1 | REG WORKSHOP | BATCH 1 | 2812981.5 |  |  | Completed | 1
36292 | NC 2018 | TVL | Region IV-B | Palawan | 301701 | ISAUB NATIONAL HIGH SCHOOL | ABORLAN | 3 |  | 1 | UNIQUE WORKSHOP | BATCH 1 | 2812981.5 |  |  | Completed | 1
36293 | NC 2018 | TVL | Region IV-B | Palawan | 301701 | ISAUB NATIONAL HIGH SCHOOL | ABORLAN | 3 |  | 1 | UNIQUE WORKSHOP | BATCH 1 | 2812981.5 |  |  | Completed | 1
36294 | NC 2018 | TVL | Region IV-B | Palawan | 301702 | Jose P. Rizal National High School | RIZAL (MARCOS) | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 17199790.26 |  |  | Completed | 1
36295 | NC 2018 | TVL | Region IV-B | Palawan | 301702 | Jose P. Rizal National High School | RIZAL (MARCOS) | 2 |  | 3 | 3STY3CL RW | BATCH 1 | 13799515.1 |  |  | Completed | 1
36296 | NC 2018 | K10 | Region IV-B | Palawan | 111250 | Julio Arzaga MES | TAYTAY | 1 | 1 | 10 | 2STY10CL | BATCH 1 | 20146800 |  |  | Completed | 1
36297 | NC 2018 | K10 | Region IV-B | Palawan | 111048 | Lucbuan ES | MAGSAYSAY | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17819000 |  |  | Completed | 1
36298 | NC 2018 | K10 | Region IV-B | Palawan | 111106 | MAASIN ELEMENTARY SCHOOL | QUEZON | 2 | 1 | 10 | 2STY10CL | BATCH 1 | 20587861.6 |  |  | Completed | 1
36299 | NC 2018 | TVL | Region IV-B | Palawan | 301704 | Maasin National High School (Bernas NHS) | BROOKE'S POINT | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 17131790.26 |  |  | Completed | 1
36300 | NC 2018 | TVL | Region IV-B | Palawan | 301704 | Maasin National High School (Bernas NHS) | BROOKE'S POINT | 2 |  | 4 | 2STY4CL RW | BATCH 1 | 17131790.26 |  |  | Completed | 1
36301 | NC 2018 | TVL | Region IV-B | Palawan | 301705 | Magara School for Philippine Craftsmen | ROXAS | 1 | 1 | 6 | 3STY12CL (6 REG WORKSHOPS) | BATCH 1 | 26373150 |  |  | Completed | 1
36302 | NC 2018 | TVL | Region IV-B | Palawan | 301705 | Magara School for Philippine Craftsmen | ROXAS | 1 |  | 6 | 3STY12CL (6 REG WORKSHOPS) | BATCH 1 | 26373150 |  |  | Completed | 1
36303 | NC 2018 | TVL | Region IV-B | Palawan | 301705 | Magara School for Philippine Craftsmen | ROXAS | 1 |  | 2 | 2STY4CL (2 REG WORKSHOPS) | BATCH 1 | 9136100 |  |  | Completed | 1 | [10 empty] | Ongoing (fr Reverted)
36304 | NC 2018 | TVL | Region IV-B | Palawan | 301705 | Magara School for Philippine Craftsmen | ROXAS | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9136100 |  |  | Completed | 1 | [10 empty] | Ongoing (fr Reverted)
36305 | NC 2018 | TVL | Region IV-B | Palawan | 301705 | Magara School for Philippine Craftsmen | ROXAS | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9136100 |  |  | Completed | 1
36306 | NC 2018 | SHS | Region IV-B | Palawan | 309158 | MAINIT NHS | BROOKE'S POINT | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11989168.02 |  |  | Completed | 1
36307 | NC 2018 | SHS | Region IV-B | Palawan | 309163 | MALATGAO NHS | QUEZON | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11782168.02 |  |  | Completed | 1
36308 | NC 2018 | SHS | Region IV-B | Palawan | 309144 | MALIS NHS | BROOKE'S POINT | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17198790.26 |  |  | Completed | 1
36309 | NC 2018 | K10 | Region IV-B | Palawan | 111005 | Manamoc ES | CUYO | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 14420000 |  |  | Completed | 1
36310 | NC 2018 | TVL | Region IV-B | Palawan | 301708 | Manamoc National High School | CUYO | 1 | 1 | 4 | 2STY8CL (3 REG WORKSHOPS AND 1 ICT LAB) | BATCH 1 | 18915950 |  |  | Completed | 1
36311 | NC 2018 | TVL | Region IV-B | Palawan | 301710 | Narra National High School | NARRA | 2 | 1 | 2 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 16939790.26 |  |  | Completed | 1
36312 | NC 2018 | TVL | Region IV-B | Palawan | 301710 | Narra National High School | NARRA | 2 |  | 3 | 3STY3CL RW | BATCH 1 | 27209030.2 |  |  | Completed | 1
36313 | NC 2018 | TVL | Region IV-B | Palawan | 301711 | New Busuanga National High School | BUSUANGA | 1 | 1 | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 10275280 |  |  | Completed | 1 | [10 empty] | Unfinished
36314 | NC 2018 | TVL | Region IV-B | Palawan | 301711 | New Busuanga National High School | BUSUANGA | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 10275280 |  |  | Completed | 1 | [10 empty] | Unfinished
36315 | NC 2018 | SHS | Region IV-B | Palawan | 301713 | New Ibajay National High School | EL NIDO (BACUIT) | 1 | 1 | 12 | 3STY12CL | BATCH 1 | 30086300 |  |  | Completed | 1
36316 | NC 2018 | TVL | Region IV-B | Palawan | 301713 | New Ibajay National High School | EL NIDO (BACUIT) | 1 |  | 3 | 2STY6CL (3 REG. WORKSHOP) | BATCH 1 | 12885300 |  |  | Completed | 1 | [10 empty] | Unfinished
36317 | NC 2018 | TVL | Region IV-B | Palawan | 301713 | New Ibajay National High School | EL NIDO (BACUIT) | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9564580 |  |  | Completed | 1
36318 | NC 2018 | TVL | Region IV-B | Palawan | 301713 | New Ibajay National High School | EL NIDO (BACUIT) | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9564580 |  |  | Completed | 1
36319 | NC 2018 | TVL | Region IV-B | Palawan | 301718 | Panacan National High School | NARRA | 2 | 1 | 2 | 2STY2CL RW | BATCH 1 | 9010901.76 |  |  | Completed | 1
36320 | NC 2018 | TVL | Region IV-B | Palawan | 301718 | Panacan National High School | NARRA | 2 |  | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 16774790.26 |  |  | Completed | 1
36321 | NC 2018 | TVL | Region IV-B | Palawan | 309107 | PANCOL NATIONAL HIGH SCHOOL - BANBANAN EXTENSION | TAYTAY | 1 | 1 | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9514110 |  |  | Completed | 1
36322 | NC 2018 | TVL | Region IV-B | Palawan | 309107 | PANCOL NATIONAL HIGH SCHOOL - BANBANAN EXTENSION | TAYTAY | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9514110 |  |  | Completed | 1
36323 | NC 2018 | K10 | Region IV-B | Palawan | 110911 | Panitian Elementary School | SOFRONIO ESPAÑOLA | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11947168.02 |  |  | Completed | 1
36324 | NC 2018 | TVL | Region IV-B | Palawan | 301719 | Panitian National High School | SOFRONIO ESPAÑOLA | 2 | 1 | 2 | 2STY1CL SCI. LAB & 1CL ICT LAB | BATCH 1 | 9076901.76 |  |  | Completed | 1
36325 | NC 2018 | TVL | Region IV-B | Palawan | 301720 | Panlaitan National High School | BUSUANGA | 1 | 1 | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 10275280 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund (2018 Batch 4)
36326 | NC 2018 | TVL | Region IV-B | Palawan | 301720 | Panlaitan National High School | BUSUANGA | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 10275280 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund (2018 Batch 4)
36327 | NC 2018 | SHS | Region IV-B | Palawan | 301721 | Pawa NHS | CUYO | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 14214000 |  |  | Completed | 1
36328 | NC 2018 | TVL | Region IV-B | Palawan | 301722 | Plaridel NHS | ABORLAN | 2 | 1 | 2 | UNIQUE WORKSHOP | BATCH 1 | 5625963 |  |  | Reverted | 0
36329 | NC 2018 | TVL | Region IV-B | Palawan | 301723 | Port Barton National High School | SAN VICENTE | 1 | 1 | 4 | 2STY8CL (4 REG WORKSHOPS) | BATCH 1 | 15862000 |  |  | Completed | 1
36330 | NC 2018 | TVL | Region IV-B | Palawan | 301723 | Port Barton National High School | SAN VICENTE | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9146400 |  |  | Completed | 1
36331 | NC 2018 | TVL | Region IV-B | Palawan | 301723 | Port Barton National High School | SAN VICENTE | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9146400 |  |  | Completed | 1
36332 | NC 2018 | TVL | Region IV-B | Palawan | 301724 | Princess Urduja National High School | NARRA | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 16939790.26 |  |  | Completed | 1
36333 | NC 2018 | TVL | Region IV-B | Palawan | 301724 | Princess Urduja National High School | NARRA | 2 |  | 3 | 3STY3CL RW | BATCH 1 | 26879030.2 |  |  | Completed | 1
36334 | NC 2018 | TVL | Region IV-B | Palawan | 301725 | Pulot National High School | SOFRONIO ESPAÑOLA | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 17087790.26 |  |  | Completed | 1
36335 | NC 2018 | SHS | Region IV-B | Palawan | 309166 | PUNANG NATIONAL HIGH SCHOOL | SOFRONIO ESPAÑOLA | 2 | 1 | 10 | 2STY10CL | BATCH 1 | 19898155.67 |  |  | Completed | 1 | [10 empty] | Mutual Termination of Contract due to Failure in Soil Test
36336 | NC 2018 | TVL | Region IV-B | Palawan | 301726 | Quezon National High School | QUEZON | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 17087790.26 |  |  | Completed | 1
36337 | NC 2018 | TVL | Region IV-B | Palawan | 301726 | Quezon National High School | QUEZON | 2 |  | 3 | 3STY3CL RW | BATCH 1 | 27431030.2 |  |  | Completed | 1
36338 | NC 2018 | TVL | Region IV-B | Palawan | 301727 | Quezon-Aramaywan National High School | QUEZON | 2 | 1 | 2 | 2STY1CL SCI. LAB & 1CL ICT LAB | BATCH 1 | 8919901.76 |  |  | Completed | 1
36339 | NC 2018 | SHS | Region IV-B | Palawan | 301728 | Quezon-Panitian National High School | QUEZON | 2 | 1 | 10 | 2STY10CL | BATCH 1 | 20083155.67 |  |  | Completed | 1
36340 | NC 2018 | TVL | Region IV-B | Palawan | 301728 | Quezon-Panitian National High School | QUEZON | 2 |  | 2 | 2STY1CL SCI. LAB & 1CL ICT LAB | BATCH 1 | 9084901.76 |  |  | Completed | 1
36341 | NC 2018 | TVL | Region IV-B | Palawan | 301728 | Quezon-Panitian National High School | QUEZON | 2 |  | 3 | 3STY3CL RW | BATCH 1 | 13550515.1 |  |  | Completed | 1
36342 | NC 2018 | TVL | Region IV-B | Palawan | 301729 | Quinlogan National High School | QUEZON | 2 | 1 | 2 | 2STY1CL SCI. LAB & 1CL ICT LAB | BATCH 1 | 8919901.76 |  |  | Completed | 1
36343 | NC 2018 | TVL | Region IV-B | Palawan | 301730 | Rio Tuba National High School | BATARAZA | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 17239790.26 |  |  | Completed | 1
36344 | NC 2018 | TVL | Region IV-B | Palawan | 301730 | Rio Tuba National High School | BATARAZA | 2 |  | 3 | 3STY3CL RW | BATCH 1 | 13829515.1 |  |  | Completed | 1
36345 | NC 2018 | K10 | Region IV-B | Palawan | 110846 | Rio Tuba South ES | BATARAZA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9274901.76 |  |  | Completed | 1
36346 | NC 2018 | K10 | Region IV-B | Palawan | 111050 | Rizal ES | MAGSAYSAY | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17819000 |  |  | Completed | 1
36347 | NC 2018 | TVL | Region IV-B | Palawan | 301731 | Roxas National Comprehensive High School | ROXAS | 1 | 1 | 6 | 3STY12CL (6 REG WORKSHOPS) | BATCH 1 | 26373150 |  |  | Completed | 1
36348 | NC 2018 | TVL | Region IV-B | Palawan | 301731 | Roxas National Comprehensive High School | ROXAS | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9136100 |  |  | Completed | 1
36349 | NC 2018 | TVL | Region IV-B | Palawan | 301731 | Roxas National Comprehensive High School | ROXAS | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9136100 |  |  | Completed | 1
36350 | NC 2018 | K10 | Region IV-B | Palawan | 111164 | Roxas North Central School | ROXAS | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17098000 |  |  | Completed | 1
36351 | NC 2018 | TVL | Region IV-B | Palawan | 301734 | Salvacion National High School | BUSUANGA | 1 | 1 | 6 | 3STY12CL (6 REG WORKSHOPS) | BATCH 1 | 26997330 |  |  | Completed | 1
36352 | NC 2018 | TVL | Region IV-B | Palawan | 301734 | Salvacion National High School | BUSUANGA | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9275150 |  |  | Completed | 1
36353 | NC 2018 | TVL | Region IV-B | Palawan | 301734 | Salvacion National High School | BUSUANGA | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9275150 |  |  | Completed | 1
36354 | NC 2018 | SHS | Region IV-B | Palawan | 309170 | Salvacion NHS- Concepcion Annex | BUSUANGA | 1 |  | 6 | 2STY6CL | BATCH 1 | 13609390 |  |  | Completed | 1
36355 | NC 2018 | K10 | Region IV-B | Palawan | 111011 | San Carlos ES | CUYO | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17819000 |  |  | Completed | 1
36356 | NC 2018 | TVL | Region IV-B | Palawan | 301732 | San Jose (Roxas) National High School | ROXAS | 1 | 1 | 3 | 3STY6CL (3 REG WORKSHOPS) | BATCH 1 | 12003620 |  |  | Completed | 1
36357 | NC 2018 | TVL | Region IV-B | Palawan | 301732 | San Jose (Roxas) National High School | ROXAS | 1 |  | 2 | 2STY4CL (1 SCI. LAB AND 1 ICT LAB) | BATCH 1 | 9136100 |  |  | Completed | 1
36358 | NC 2018 | TVL | Region IV-B | Palawan | 301737 | San Miguel National High School (Gaudencio Abordo NHS) | LINAPACAN | 1 | 1 | 3 | 2STY6CL (3 REG. WORKSHOP) | BATCH 1 | 15302710 |  |  | Completed | 1
36359 | NC 2018 | TVL | Region IV-B | Palawan | 301737 | San Miguel National High School (Gaudencio Abordo NHS) | LINAPACAN | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 10305150 |  |  | Completed | 1
36360 | NC 2018 | TVL | Region IV-B | Palawan | 301737 | San Miguel National High School (Gaudencio Abordo NHS) | LINAPACAN | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 10305150 |  |  | Completed | 1
36361 | NC 2018 | TVL | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1 | 1 | 4 | 2STY8CL (4 REG WORKSHOPS) | BATCH 1 | 15862000 |  |  | Completed | 1
36362 | NC 2018 | TVL | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1 |  | 3 | 3STY6CL (3 REG WORKSHOPS) | BATCH 1 | 12051000 |  |  | Completed | 1
36363 | NC 2018 | TVL | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9146400 |  |  | Reverted | 0
36364 | NC 2018 | TVL | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9146400 |  |  | Reverted | 0
36365 | NC 2018 | TVL | Region IV-B | Palawan | 301683 | Sandoval National High School | TAYTAY | 1 | 1 | 2 | 2STY4CL (2 REG WORKSHOPS) | BATCH 1 | 9514110 |  |  | Completed | 1
36366 | NC 2018 | TVL | Region IV-B | Palawan | 301683 | Sandoval National High School | TAYTAY | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9514110 |  |  | Completed | 1
36367 | NC 2018 | TVL | Region IV-B | Palawan | 301683 | Sandoval National High School | TAYTAY | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9514110 |  |  | Completed | 1
36368 | NC 2018 | TVL | Region IV-B | Palawan | 301739 | Sandoval National High School | NARRA | 2 | 1 | 2 | 2STY1CL SCI. LAB & 1CL ICT LAB | BATCH 1 | 9010901.76 |  |  | Completed | 1
36369 | NC 2018 | TVL | Region IV-B | Palawan | 301739 | Sandoval National High School | NARRA | 2 |  | 2 | 2STY2CL RW | BATCH 1 | 18021803.52 |  |  | Reverted | 0
36370 | NC 2018 | SHS | Region IV-B | Palawan | 309156 | SARONG NHS | BATARAZA | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11902168.02 |  |  | Completed | 1
36371 | NC 2018 | TVL | Region IV-B | Palawan | 309127 | Sibaring National High School | BALABAC | 2 | 1 | 2 | 2STY1CL SCI. LAB & 1CL ICT LAB | BATCH 1 | 9225901.76 |  |  | Completed | 1
36372 | NC 2018 | K10 | Region IV-B | Palawan | 110914 | Sofronio Española CS | SOFRONIO ESPAÑOLA | 2 | 1 | 10 | 2STY10CL | BATCH 1 | 19898155.67 |  |  | Completed | 1
36373 | NC 2018 | TVL | Region IV-B | Palawan | 309129 | Southern Bataraza National High School | BATARAZA | 2 | 1 | 2 | 2STY1CL SCI. LAB & 1CL ICT LAB | BATCH 1 | 9261176.13 |  |  | Completed | 1
36374 | NC 2018 | SHS | Region IV-B | Palawan | 309148 | SOWANGAN NHS | QUEZON | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11782168.02 |  |  | Completed | 1
36375 | NC 2018 | TVL | Region IV-B | Palawan | 301740 | Sta. Teresita National High School | DUMARAN | 1 | 1 | 6 | 3STY12CL (6 REG WORKSHOPS) | BATCH 1 | 30240800 |  |  | Completed | 1
36376 | NC 2018 | TVL | Region IV-B | Palawan | 301740 | Sta. Teresita National High School | DUMARAN | 1 |  | 2 | 2STY4CL (2 UNITS SCI. LAB) | BATCH 1 | 9309140 |  |  | Completed | 1
36377 | NC 2018 | TVL | Region IV-B | Palawan | 301740 | Sta. Teresita National High School | DUMARAN | 1 |  | 2 | 2STY4CL (2 UNITS ICT LAB) | BATCH 1 | 9309140 |  |  | Completed | 1
36378 | NC 2018 | K10 | Region IV-B | Palawan | 111012 | Suba ES | CUYO | 1 | 1 | 10 | 2STY10CL | BATCH 1 | 20600000 |  |  | Completed | 1 | [10 empty] | Terminated (With Approved Buffer Fund)
36379 | NC 2018 | SHS | Region IV-B | Palawan | 309111 | Suba NHS | CUYO | 1 | 1 | 10 | 2STY10CL | BATCH 1 | 20600000 |  |  | Completed | 1
36380 | NC 2018 | TVL | Region IV-B | Palawan | 309115 | Sumbiling National High School | BATARAZA | 2 | 1 | 2 | 2STY1CL SCI. LAB & 1CL ICT LAB | BATCH 1 | 9543587.69 |  |  | Completed | 1
36381 | NC 2018 | TVL | Region IV-B | Palawan | 309115 | Sumbiling National High School | BATARAZA | 2 |  | 2 | 2STY2CL RW | BATCH 1 | 9388950.5 |  |  | Completed | 1
36382 | NC 2018 | TVL | Region IV-B | Palawan | 309149 | Taburi National High School | RIZAL (MARCOS) | 2 | 1 | 2 | 2STY1CL SCI. LAB & 1CL ICT LAB | BATCH 1 | 9150901.76 |  |  | Completed | 1
36383 | NC 2018 | K10 | Region IV-B | Palawan | 111130 | Tagbita ES | RIZAL (MARCOS) | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11890168.02 |  |  | Completed | 1
36384 | NC 2018 | TVL | Region IV-B | Palawan | 301743 | Tagusao National High School | QUEZON | 2 | 1 | 4 | 2STY2CL SCI. LAB & 2CL ICT LAB | BATCH 1 | 16922790.26 |  |  | Completed | 1
36385 | NC 2018 | TVL | Region IV-B | Palawan | 309126 | Tarusan National High School | BATARAZA | 2 | 1 | 2 | 2STY1CL SCI. LAB & 1CL ICT LAB | BATCH 1 | 8995901.76 |  |  | Completed | 1
36386 | NC 2018 | TVL | Region IV-B | Palawan | 309126 | Tarusan National High School | BATARAZA | 2 |  | 2 | 2STY2CL RW | BATCH 1 | 9160901.76 |  |  | Completed | 1
36387 | NC 2018 | TVL | Region IV-B | Palawan | 301745 | Tumarbong National High School | ROXAS | 1 | 1 | 6 | 3STY12CL (2 REG WORKSHOPS, 2 SCI. LAB, AND 2 ICT LABS) | BATCH 1 | 26777940 |  |  | Completed | 1
36388 | NC 2018 | K10 | Region IV-B | Puerto Princesa City | 111516 | Langogan Elementary School | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 8 | 2UNITS 2STY4CL | BATCH 1 | 18249639.59 |  |  | Completed | 1 | [6 empty] | 2018-09-13 |  | 2018-10-11 | F.F. GALANG CONSTRUCTION
36389 | NC 2018 | TVL | Region IV-B | Puerto Princesa City | 301779 | Bacungan NHS | Puerto Princesa City | 3 | 1 | 1 | Unique Workshop | BATCH 1 | 2970319.34 |  |  | Completed | 1 | [6 empty] | 2018-07-30 |  | 2018-09-03 | L.B. LEONCIO TRADING & CONSTRUCTION
36390 | NC 2018 | TVL | Region IV-B | Puerto Princesa City | 301780 | Bahile NHS | Puerto Princesa City | 3 | 1 | 1 | Unique Workshop | BATCH 1 | 2970319.34 |  |  | Completed | 1 | [6 empty] | 2018-07-30 |  | 2018-09-03 | LOUISE TRADING AND CONSTRUCTION
36391 | NC 2018 | TVL | Region IV-B | Puerto Princesa City | 301783 | Irawan NHS | Puerto Princesa City | 3 | 1 | 1 | Unique Workshop | BATCH 1 | 2941198.56 |  |  | Completed | 1 | [6 empty] | 2018-07-30 |  | 2018-09-03 | F.F. GALANG CONSTRUCTION
36392 | NC 2018 | SHS | Region IV-B | Puerto Princesa City | 301784 | Langogan NHS | Puerto Princesa City | 3 | 1 | 12 | 2STY - 12CL | BATCH 1 | 22769786.54 |  |  | Completed | 1 | [6 empty] | 2018-08-31 |  | 2018-09-03 | L.B. LEONCIO TRADING & CONSTRUCTION
36393 | NC 2018 | TVL | Region IV-B | Puerto Princesa City | 301784 | Langogan NHS | Puerto Princesa City | 3 |  | 2 | 2 Unique Workshop | BATCH 1 | 5571342 |  |  | Completed | 1 | [6 empty] | 2018-07-30 |  | 2018-09-28 | CHAD LOURENCE TRADING & CONSTRUCTION SERVICES
36394 | NC 2018 | TVL | Region IV-B | Puerto Princesa City | 301787 | Babuyan NHS | Puerto Princesa City | 3 | 1 | 1 | Unique Workshop | BATCH 1 | 2970319.34 |  |  | Completed | 1 | [6 empty] | 2018-07-30 |  | 2018-09-03 | RAK TRADING AND CONSTRUCTION
36395 | NC 2018 | TVL | Region IV-B | Puerto Princesa City | 301788 | Luzviminda NHS | Puerto Princesa City | 3 | 1 | 1 | Unique Workshop | BATCH 1 | 2970319.34 |  |  | Completed | 1 | [6 empty] | 2018-07-30 |  | 2018-09-03 | JFR CONSTRUCTION
36396 | NC 2018 | TVL | Region IV-B | Puerto Princesa City | 301789 | Mangingisda NHS | Puerto Princesa City | 3 | 1 | 1 | Unique Workshop | BATCH 1 | 2970319.34 |  |  | Completed | 1 | [6 empty] | 2018-07-30 |  | 2018-09-03 | F.F. GALANG CONSTRUCTION
36397 | NC 2018 | SHS | Region IV-B | Puerto Princesa City | 301792 | Marcelino Abadiano Javarez NHS | Puerto Princesa City | 3 | 1 | 12 | 2STY - 12CL | BATCH 1 | 22546533.34 |  |  | Completed | 1 | [6 empty] | 2018-08-17 |  | 2018-09-12 | F.F. GALANG CONSTRUCTION
36398 | NC 2018 | TVL | Region IV-B | Puerto Princesa City | 301792 | Marcelino Abadiano Javarez NHS | Puerto Princesa City | 3 |  | 1 | Unique Workshop | BATCH 1 | 2941198.56 |  |  | Completed | 1 | [6 empty] | 2018-07-30 |  | 2018-09-03 | RAK TRADING AND CONSTRUCTION
36399 | NC 2018 | SHS | Region IV-B | Puerto Princesa City | 309301 | Palawan National School | Puerto Princesa City | 3 | 1 | 12 | 2STY - 12CL | BATCH 1 | 22769786.54 |  |  | Completed | 1 | [6 empty] | 2018-08-17 |  | 2018-09-12 | YURICH BUILDERS & CONSTRUCTION SUPPLY
36400 | NC 2018 | SHS | Region IV-B | Puerto Princesa City | 309301 | Palawan National School | Puerto Princesa City | 3 |  | 12 | 2STY - 12CL | BATCH 1 | 22546533.34 |  |  | Completed | 1 | [6 empty] | 2018-09-13 |  | 2018-10-11 | A.R. LUSTRE JR. CONSTRUCTION
36401 | NC 2018 | SHS | Region IV-B | Romblon | 301749 | Esteban Madrona National High School | SAN AGUSTIN | 0 | 1 | 12 | 3STY12CL | BATCH 1 | 27660585.4 |  |  | Completed | 1 |  |  | P00271248LZ-CW1 | 18EH0137 | 2018-08-16 | 2018-08-23 | 2018-09-04 | 2018-10-18 | 2018-11-12 | LEGACY CONSTRUCTION CORPORATION
36402 | NC 2018 | SHS | Region IV-B | Romblon | 301753 | Lumbang East National High School | CAJIDIOCAN | 0 | 1 | 12 | 3STY12CL | BATCH 1 | 28255933.49 |  |  | Completed | 1 |  |  | P00271249LZ-CW1 | 18EH0117-R1 | 2018-08-17 | 2018-08-24 | 2018-09-05 | 2018-10-18 | 2018-11-12 | LEGACY CONSTRUCTION CORPORATION
36403 | NC 2018 | SHS | Region IV-B | Romblon | 301755 | Cambalo NHS | CAJIDIOCAN | 0 | 1 | 12 | 3STY12CL | BATCH 1 | 28363596.45 |  |  | Completed | 1 |  |  | P00271250LZ-CW1 | 18EH0139 | 2018-08-16 | 2018-08-23 | 2018-09-04 | 2018-10-23 | 2018-11-12 | MT. GUITING-GUITING CONSTRUCTION
36404 | NC 2018 | SHS | Region IV-B | Romblon | 301760 | Espana NHS | SAN FERNANDO | 0 | 1 | 12 | 3STY12CL | BATCH 1 | 28183640.34 |  |  | Completed | 1 |  |  | P00271251LZ-CW1 | 18EH0115-R1 | 2018-08-17 | 2018-08-24 | 2018-09-05 | 2018-10-18 | 2018-11-12 | LEGACY CONSTRUCTION CORPORATION
36405 | NC 2018 | SHS | Region IV-B | Romblon | 301766 | Mabini NHS | CORCUERA | 0 | 1 | 12 | 3STY12CL | BATCH 1 | 28218227.95 |  |  | Completed | 1 |  |  | P00271252LZ-CW1 | 18EH0116-R1 | 2018-08-17 | 2018-08-24 | 2018-09-05 | 2018-10-15 | 2018-11-16 | TWIN DRAGON CONSTRUCTION
36406 | NC 2018 | TVL | Region IV-B | Romblon | 301766 | Mabini NHS | CORCUERA | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 3000000 |  |  | Completed | 1
36407 | NC 2018 | SHS | Region IV-B | Romblon | 301768 | Magdiwang NHS | MAGDIWANG | 0 | 1 | 12 | 3STY12CL | BATCH 1 | 28060483.04 |  |  | Completed | 1 |  |  | P00271254LZ-CW1 | 18EH0114-R1 | 2018-08-17 | 2018-08-24 | 2018-09-05 | 2018-10-15 | 2018-11-16 | TWIN DRAGON CONSTRUCTION
36408 | NC 2018 | SHS | Region IV-B | Romblon | 301774 | Santa Maria NHS | SANTA MARIA (IMELDA) | 0 | 1 | 12 | 3STY12CL | BATCH 1 | 27498777.74 |  |  | Completed | 1 |  |  | P00271255LZ-CW1 | 18EH0138 | 2018-08-16 | 2018-08-23 | 2018-09-04 | 2018-10-11 | 2018-11-05 | TWIN DRAGON CONSTRUCTION
36409 | NC 2018 | SHS | Region IV-B | Romblon | 301771 | San Andres NHS | SAN ANDRES | 0 | 1 | 12 | 4STY12CL | Batch 3 | 31697655.57 |  |  | Completed | 1
36410 | NC 2018 | K10 | Region IV-B | Romblon |  | Cultural Community High School | SAN ANDRES | 0 | 1 | 6 | 2STY6CL | Batch 3 | 11998811.61 |  |  | Completed | 1
39606 | NC 2019 | K10 | Region IV-B | CALAPAN CITY | 111572 | Sta. Rita ES (Bungahan ES) | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | 1STY3CL |  | 6175822.0926 |  | Completed | 1 | [11 empty] | 0
39607 | NC 2019 | K10 | Region IV-B | Marinduque | 109895 | Cawit ES | BOAC (Capital) | 0 | 1 | 4 | 2STY4CL |  | 27211617.786 |  | Completed | 1 |  |  |  | 19EA0103 | 4/9/2019 | 2019-11-09 | 2019-09-23 |  |  |  |  | 0
39608 | NC 2019 | TVL | Region IV-B | Marinduque | 301557 | Mogpog National Comprehensive High School | MOGPOG | 0 | 1 | 8 | 2STY 4 LAB (2 SCI & 2 ICT LAB) |  | 37636918.6725 |  | Completed | 1 |  |  |  | 19EA0104 | 4/9/2019 | 2019-11-09 | 2019-09-23 |  |  |  |  | 0
39609 | NC 2019 | K10 | Region IV-B | Marinduque | 109995 | Santa Cruz North CS (Landy ES) | SANTA CRUZ | 0 | 1 | 4 | 2STY4CL |  | 27283081.2591 |  | Completed | 1 |  |  |  | 19EA0105 | 4/9/2019 | 2019-11-09 | 2019-09-23 |  |  |  |  | 0
39610 | NC 2019 | SHS | Region IV-B | Marinduque | 301562 | Sibuyao NHS | TORRIJOS | 0 | 1 | 6 | 3STY6CL |  | 14743773.6654 |  | Completed | 1 |  |  |  | 19EA0106 | 4/9/2019 | 2019-11-09 | 2019-09-23 |  |  |  |  | 0
39611 | NC 2019 | K10 | Region IV-B | Occidental Mindoro | 110046 | Hebron Min. Sch. | ABRA DE ILOG | 0 | 1 | 5 | 1STY5CL |  | 10293036.821 |  | Completed | 1 | [11 empty] | 0
39612 | NC 2019 | K10 | Region IV-B | Oriental Mindoro | 110465 | Cabuyao PS | MANSALAY | 2 | 1 | 4 | 1STY4CL |  | 8234429.4568 |  | Completed | 1 | [11 empty] | 0
39613 | NC 2019 | K10 | Region IV-B | Oriental Mindoro | 110561 | Natividad De Joya MS (Guinhawa) | PINAMALAYAN | 2 | 1 | 2 | 1STY2CL |  | 4117214.7284 |  | Completed | 1 | [11 empty] | 0
39614 | NC 2019 | K10 | Region IV-B | Oriental Mindoro | 110580 | Pambisan Munti ES | PINAMALAYAN | 2 | 1 | 3 | 1STY3CL |  | 4141496.9125 |  | Completed | 1 | [11 empty] | 0
39615 | NC 2019 | K10 | Region IV-B | Oriental Mindoro | 110477 | Sta. Brigida ES | MANSALAY | 2 | 1 | 2 | 1STY2CL |  | 4117214.7284 |  | Completed | 1 | [11 empty] | 0
39616 | NC 2019 | K10 | Region IV-B | Puerto Princesa City | 111483 | Labtay ES - Pagasa Ext. * | Puerto Princesa City | 3 | 1 | 3 | 1STY3CL |  | 6175822.0926 |  | Completed | 1 | [11 empty] | 0
39617 | NC 2019 | SHS | Region IV-B | Romblon | 301747 | Alcantara NHS | ALCANTARA | 0 | 1 | 4 | 2STY4CL |  | 13616957.5 |  | Completed | 1 | [11 empty] | 0
40283 | NC 2020 | K10 | Region IV-B | Calapan City | 111535 | Bulusan ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | 2STY4CL |  | 10827000 |  |  | Completed | 1
40284 | NC 2020 | K10 | Region IV-B | Marinduque | 109918 | Tungib ES | BUENAVISTA | 0 | 1 | 3 | 1STY3CL |  | 6015000 |  |  | Completed | 1
40285 | NC 2020 | SHS | Region IV-B | Marinduque | 301541 | Cawit NHS | BOAC (Capital) | 0 | 1 | 3 | 1STY3CL |  | 6015000 |  |  | Completed | 1
40286 | NC 2020 | K10 | Region IV-B | Occidental Mindoro | 110306 | Mapaya II ES | SAN JOSE | 0 | 1 | 4 | 2STY4CL |  | 11672860.17 |  |  | Completed | 1
40287 | NC 2020 | SHS | Region IV-B | Occidental Mindoro | 301577 | Concepcion NHS | Calintaan | 0 | 1 | 6 | 2STY6CL |  | 13389639.83 |  |  | Completed | 1 | [10 empty] | delayed due to revision of design based on actual soil exploration result. Proposed revised expiration is on 09/06/2021
40288 | NC 2020 | K10 | Region IV-B | Oriental Mindoro | 110613 | Isidoro Suzara Memorial School | PUERTO GALERA | 1 | 1 | 6 | 3STY6CL |  | 16245634.45 |  |  | Completed | 1
40289 | NC 2020 | SHS | Region IV-B | Oriental Mindoro | 301639 | Marcelo I. Cabrera Vocational HS | ROXAS | 2 | 1 | 6 | 2STY6CL |  | 18308332.66 |  |  | Completed | 1
40290 | NC 2020 | K10 | Region IV-B | Palawan | 110968 | Mampio Elementary School | CAGAYANCILLO | 1 | 1 | 2 | 1STY2CL |  | 5074655 |  |  | completed | 1
40291 | NC 2020 | K10 | Region IV-B | Palawan | 110970 | Sta. Cruz Elementary School | CAGAYANCILLO | 1 | 1 | 4 | 2UNITS 1STY2CL |  | 9801442.5 |  |  | Completed | 1
40292 | NC 2020 | K10 | Region IV-B | Palawan | 110866 | Brooke's Point Central School SPED Center | BROOKE'S POINT | 2 | 1 | 10 | 2sty10CL |  | 25653049.73 |  |  | Completed | 1
40293 | NC 2020 | K10 | Region IV-B | Puerto Princesa City | 111485 | Mateo Jagmis MES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 4 | 2STY4CL |  | 12531250 |  |  | Completed | 1
40294 | NC 2020 | K10 | Region IV-B | Romblon | 111385 | Palje PS | ROMBLON (Capital) | 0 | 1 | 6 | 2STY6CL |  | 17543750 |  |  | Completed | 1
41053 | NC 2021 | SHS | Region IV-B | Marinduque | 301562 | Sibuyao National High School | Torrijos | 0 | 1 | 6 | Construction/Completion (3STY6CL) |  | 35087500 | 35000000 |  | Completed | 1
41054 | NC 2021 | K10 | Region IV-B | Occidental Mindoro | 110113 | Tilik Elementary School | LUBANG | 0 | 1 | 12 | Construction/Completion (2STY12CL) |  | 7006371.2675 | 6988899.02 |  | Completed | 1
41055 | NC 2021 | SHS | Region IV-B | Oriental Mindoro | 301625 | DAYHAGAN NHS | BONGABONG | 2 | 1 | 6 | Construction/Completion (3STY6CL) |  | 5143987.499 | 5131159.6 |  | Completed | 1
41056 | NC 2021 | SHS | Region IV-B | Oriental Mindoro | 305782 | Gatol HS | BULALACAO (SAN PEDRO) | 2 | 1 | 8 | Construction/Completion (2STY8CL) |  | 24060000 | 24000000 |  | Completed | 1
41057 | NC 2021 | K10 | Region IV-B | Palawan | 111158 | Mendoza Elementary School | ROXAS | 1 | 1 |  | Construction of Slope Protection |  | 3571666.9 | 3562760 |  | Completed | 1
41058 | NC 2021 | K10 | Region IV-B | Palawan | 111166 | Salvador Elementary School | ROXAS | 1 | 1 |  | Construction of Slope Protection |  | 3130506.75 | 3122700 |  | Completed | 1
41059 | NC 2021 | TVL | Region IV-B | Palawan | 301667 | Barotuan National High school | EL NIDO (BACUIT) | 1 | 1 | 9 | Construction/Completion (3STY18CL (9 REG WORKSHOPS)) |  | 1904750 | 1900000 |  | Completed | 1
41060 | NC 2021 | SHS | Region IV-B | Palawan | 301681 | Caruray National High School | SAN VICENTE | 1 | 1 | 12 | Construction/Completion (3STY12CL) |  | 4010000 | 4000000 |  | Completed | 1
41061 | NC 2021 | TVL | Region IV-B | Palawan | 301681 | Caruray National High School | SAN VICENTE | 1 |  | 2 | Construction/Completion (2STY4CL (2 UNITS ICT LAB)) |  | 1002500 | 1000000 |  | Completed | 1
41062 | NC 2021 | TVL | Region IV-B | Palawan | 301705 | Magara School for Philippine Craftsmen | ROXAS | 1 | 1 | 2 | Construction/Completion (2STY4CL (2 REG WORKSHOPS)) |  | 1704250 | 1700000 |  | Completed | 1
41063 | NC 2021 | TVL | Region IV-B | Palawan | 301711 | New Busuanga National High School | BUSUANGA | 1 | 1 | 2 | Construction/Completion (2STY4CL (2 UNITS ICT LAB)) |  | 451125 | 450000 |  | Completed | 1 | [10 empty] | rebid
41064 | NC 2021 | TVL | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1 | 1 | 2 | Construction/Completion (2STY4CL (2 UNITS ICT LAB)) |  | 1253125 | 1250000 |  | Completed | 1
41065 | NC 2021 | TVL | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1 |  | 2 | Construction/Completion (2STY4CL (2 UNITS SCI. LAB)) |  | 1253125 | 1250000 |  | COMPLETED | 1
41066 | NC 2021 | TVL | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1 |  | 4 | Construction/Completion (2STY8CL (4 REG WORKSHOPS)) |  | 3007500 | 3000000 |  | Completed | 1
41067 | NC 2021 | TVL | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1 |  | 3 | Construction/Completion (3STY6CL (3 REG WORKSHOPS)) |  | 3007500 | 3000000 |  | Completed | 1
41068 | NC 2021 | SHS | Region IV-B | Palawan | 301740 | Sta. Teresita National High School | DUMARAN | 1 | 1 |  | Construction of Slope Protection |  | 6015000 | 6000000 |  | Completed | 1
41069 | NC 2021 | TVL | Region IV-B | Palawan | 309120 | Concepcion National High School | AGUTAYA | 1 | 1 | 7 | Construction/Completion (3STY9CL (2 REG WORKSHOP AND 5 REG CLASSROOMS)) |  | 651625 | 650000 |  | Completed | 1
41070 | NC 2021 | TVL | Region IV-B | Palawan | 309134 | Cheey National High School | BUSUANGA | 1 | 1 | 6 | Construction/Completion (3STY12CL (6 REG WORKSHOPS)) |  | 2005000 | 2000000 |  | COMPLETED | 1
41662 | NC 2022 | K10 | Region IV-B | Occidental Mindoro | 110094 | Agkawayan ES | LOOC | 0 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4937246.88 | Completed | 1 | 2022-04-27 | 2022-04-27 | 22EB0116 | 22EB0116 | 2022-11-25 | 2022-02-12 | 2022-12-13 | 2022-12-20 |  | FAAA Const. & Trading
41663 | NC 2022 | K10 | Region IV-B | Occidental Mindoro | 110126 | Canabang ES | MAGSAYSAY | 0 | 1 | 6 | 2STY6CL | 2 |  | 17543750 | 17126346.72 | Completed | 1 | 2023-08-10 | 2023-08-10 | 22EB0117 | 22EB0117 | 2022-11-25 | 2022-02-12 | 2022-12-13 | 2022-12-20 |  | Kejamarenik const & const supply
41664 | NC 2022 | K10 | Region IV-B | Palawan | 110747 | Villa Sol Elementary School | Agutaya | 1 | 1 | 2 | 1STY2CL | 2 |  | 6766875 |  | Completed | 1
41665 | NC 2022 | K10 | Region IV-B | Palawan | 110971 | Talaga Elementary School | Cagayancillo | 1 | 1 | 2 | 1STY2CL | 2 |  | 6917250 |  | Completed | 1
41666 | NC 2022 | K10 | Region IV-B | Palawan | 305744 | Pical National High School | Linapacan | 1 | 1 | 2 | 1STY2CL | 2 |  | 6516250 |  | Completed | 1
41667 | NC 2022 | K10 | Region IV-B | Palawan | 111041 | Balaguen Elementary School | Magsaysay | 1 | 1 | 2 | 1STY2CL | 2 |  | 6766875 |  | Completed | 1
41668 | NC 2022 | K10 | Region IV-B | Palawan | 111197 | Pagdanan Elementary School | San Vicente | 1 | 1 | 2 | 1STY2CL | 2 |  | 6516250 |  | Completed | 1 | 2023-04-24
41669 | NC 2022 | K10 | Region IV-B | Romblon | 111259 | Camili ES | ALCANTARA | 0 | 1 | 2 | 1STY2CL | 2 |  | 4010000 |  | Completed | 1 | 2023-05-14 | 2023-03-06 | P00675145LZ | 22EH0165 | 2022-11-25 |  | 2022-12-14 |  | 2023-02-02 |  | Booked (July 24,2023)
41670 | NC 2022 | K10 | Region IV-B | Romblon | 301778 | TUNGONAN NATIONAL HIGH SCHOOL | BANTON | 0 | 1 | 2 | 1STY2CL | 2 |  | 4511250 |  | Completed | 1 | 2023-05-14 | 2023-05-14 | P00675146LZ | 22EH0166 | 2022-11-25 |  | 2022-12-14 |  | 2023-02-02 |  | Booked (July 24,2023)
41671 | NC 2022 | K10 | Region IV-B | Romblon | 111404 | Fetalvero-Mingoa MS | CALATRAVA | 0 | 1 | 2 | 1STY2CL | 2 |  | 4210500 |  | Completed | 1 | 2023-05-14 | 2023-07-01 | P00675147LZ | 22EH0167 | 2022-11-25 |  | 2022-12-14 |  | 2023-02-02 |  | Booked (November 10,2023)
41672 | NC 2022 | K10 | Region IV-B | Romblon | 111307 | Alegria ES | CORCUERA | 0 | 1 | 2 | 1STY2CL | 2 |  | 4411000 |  | Completed | 1 | 2023-05-14 | 2023-06-14 | P00675148LZ | 22EH0168 | 2022-11-25 |  | 2022-12-14 |  | 2023-02-02 |  | Booked (July 24,2023)
41673 | NC 2022 | K10 | Region IV-B | Romblon | 111350 | Bunsoran ES | FERROL | 0 | 1 | 2 | 1STY2CL | 2 |  | 4010000 |  | Completed | 1 | 2023-05-14 | 2023-05-14 | P00675149LZ | 22EH0169 | 2022-11-25 |  | 2022-12-14 |  | 2023-02-02 |  | Booked (February 15,2024)
41674 | NC 2022 | K10 | Region IV-B | Romblon | 111295 | Silum ES | MAGDIWANG | 0 | 1 | 2 | 1STY2CL | 2 |  | 4010000 |  | Completed | 1 | 2023-05-14 | 2023-05-14 | P00675150LZ | 22EH0170 | 2022-11-25 |  | 2022-12-14 |  | 2023-02-02 |  | Booked (July 24,2023)
41675 | NC 2022 | K10 | Region IV-B | Romblon | 111402 | Concepcion Sur ES | SANTA MARIA (IMELDA) | 0 | 1 | 2 | 1STY2CL | 2 |  | 4010000 |  | Completed | 1 | 2023-05-14 | 2023-07-10 | P00675151LZ | 22EH0171 | 2022-11-25 |  | 2022-12-14 |  | 2023-02-02 |  | Booked (February 15,2024)
42302 | NC 2023 | SHS | Region IV-B | Calapan City | 301803 | Pedro V. Panaligan Memorial National High School | CITY OF CALAPAN (Capital) |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9600069.6 | Completed | 1 | 2023-12-24 | 2023-12-22 | P00775385LZ-CW1 | 23ED0116 | 2023-06-29 | 2023-07-06 | 2023-07-19 | 2023-07-25 | 2023-07-27 | KOLZACE Construction
42303 | NC 2023 | K10 | Region IV-B | Calapan City |  | Personas National High School | CITY OF CALAPAN (Capital) |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9699619.22 | Completed | 1 | 2023-12-24 | 2023-12-22 | P00775386LZ-CW1 | 23ED0117 | 2023-06-29 | 2023-07-06 | 2023-07-19 | 2023-07-25 | 2023-07-27 | HEAZ, CONSTRUCTION
42304 | NC 2023 | K10 | Region IV-B | Marinduque | 169011 | Aurora Sevilla Sotto Libtangin Elementary School | GASAN |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 5043750 | Completed | 1 | 2024-03-14 | 2024-03-14 | P00775387LZ-CW1 | 23EA0087 | 2023-06-07 | 2023-06-14 | 2023-06-29 | 2023-12-05 | 2023-12-15 | G.T.J. CONSTRUCTION
42305 | NC 2023 | K10 | Region IV-B | Marinduque | 169001 | Ino ES | MOGPOG |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Reverted | 0
42306 | NC 2023 | K10 | Region IV-B | Marinduque | 169009 | Malayak Elementary School | MOGPOG |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 5043750 | Completed | 1 | 2024-05-13 | 2024-09-24 | P00775390LZ-CW1 | 23EA0088 | 2023-06-07 | 2023-06-14 | 2023-06-26 | 2023-12-05 | 2023-12-15 | G.T.J. CONSTRUCTION
42307 | NC 2023 | K10 | Region IV-B | Marinduque | 109952 | Mogpog Central School | MOGPOG |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 5043750 | Ongoing | 0.98 | 2024-04-23 |  | P00775388LZ-CW1 | 23EA0090 | 2023-06-07 | 2023-06-14 | 2023-06-29 | 2023-12-05 | 2023-12-15 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | Upon joint inspection with the DepEd inspectors, there were findings observed that need rectifications
42308 | NC 2023 | K10 | Region IV-B | Marinduque | 109960 | Alobo ES | SANTA CRUZ |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 5043750 | Completed | 1 | 2024-05-29 |  | 23EA0089 | 6/7/2023 | 2023-06-14 | 2023-06-26 | 2023-12-05 | 2023-12-15
42309 | NC 2023 | K10 | Region IV-B | Marinduque | 110003 | Maniwaya Elementary School | SANTA CRUZ |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 5043750 | Completed | 1 | 2024-06-06 |  | 23EA0086 | 7/13/2023 | 2023-07-20 | 2023-08-01 | 2023-12-05 | 2023-12-15
42310 | NC 2023 | K10 | Region IV-B | Marinduque | 110027 | Matuyatuya ES | TORRIJOS |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 5043750 | Completed | 1 | 2024-05-29 |  | 23EA0091 | 6/7/2023 | 2023-06-14 | 2023-06-26 | 2023-12-05 | 2023-12-15
42311 | NC 2023 | K10 | Region IV-B | Marinduque | 110036 | Torrijos CS | TORRIJOS |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 5043750 | Completed | 1 | 2024-05-20 |  | 23EA0092 | 6/7/2023 | 2023-06-14 | 2023-06-26 | 2023-12-05 | 2023-12-15
42312 | NC 2023 | K10 | Region IV-B | Occidental Mindoro | 110084 | Filomeno Jimenez ES | CALINTAAN |  | 1 | 6 |  | Batch 1 | 12105000 | 12000000 | 11513736.3 | Completed | 1 | 2024-05-13 | 2024-05-13 | 23EB0098R1 | 23EB0098R1 | 2023-08-17 | 2023-08-24 | 2023-09-06 | 2023-09-13 | 2023-11-21 | Bao-Idang const.gen. building engg
42313 | NC 2023 | K10 | Region IV-B | Occidental Mindoro | 110088 | Nayong Kalikasan Elementary School | CALINTAAN |  | 1 | 2 |  | Batch 1 | 4539375 | 4500000 | 4494612.17 | Completed | 1 | 2023-12-12 | 2023-12-12 | 23EB0097 | 23EB0097 | 2023-06-15 | 2023-06-26 | 2023-07-18 | 2023-07-25 | 2023-08-18 | Bao-Idang const.gen. building engg
42314 | NC 2023 | K10 | Region IV-B | Oriental Mindoro |  | Baco National High School Tabon-tabon Annex | BACO |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9650319.24 | Completed | 1 | 2023-12-24 | 2023-12-22 | P00775398LZ-CW1 | 23ED0118 | 2023-06-29 | 2023-07-06 | 2023-07-19 | 2023-07-25 | 2023-07-27 | 876 Construction and Supply
42315 | NC 2023 | K10 | Region IV-B | Oriental Mindoro | 110320 | Benito Villar MS | BACO |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9838259.62 | Completed | 1 | 2023-12-24 | 2024-01-31 | P00775397LZ-CW1 | 23ED0115 | 2023-06-29 | 2023-07-06 | 2023-07-19 | 2023-07-25 | 2023-07-27 | DelRol Construction Corporation
42316 | NC 2023 | SHS | Region IV-B | Oriental Mindoro | 300448 | Bongabong Technical and Vocational High School | BONGABONG |  | 1 | 3 |  | Batch 1 | 9304104.75 | 9223400 | 8992774.84 | Completed | 1 | 2023-12-13 | 2023-12-13 | P00775399LZ-CW1 | 23EI0090 | 2023-06-08 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2023-07-11 | Green Island Enterprises
42317 | NC 2023 | SHS | Region IV-B | Oriental Mindoro | 301632 | Formon NHS | BONGABONG |  | 1 | 3 |  | Batch 1 | 9100034.63 | 9021100 | 9100034.63 | Completed | 1 | 2023-12-13 | 2023-12-13 | P00775400LZ-CW1 | 23EI0091 | 2023-06-08 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2023-07-11 | EE Construction
42318 | NC 2023 | K10 | Region IV-B | Oriental Mindoro | 305922 | Bagong Sikat High School | BULALACAO (SAN PEDRO) |  | 1 | 4 |  | Batch 1 | 11858360.63 | 11755500 | 11370123.47 | Completed | 1 | 2023-12-13 | 2023-12-15 | P00775401LZ-CW1 | 23EI0089 | 2023-06-08 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2023-07-11 | WTL Construction
42319 | NC 2023 | SHS | Region IV-B | Palawan | 301695 | Gaudencio E. Abordo Mem. National High School | AGUTAYA |  | 1 | 4 |  | Batch 1 | 11638768.81 | 6790778 | 11487756.93 | Completed | 1 | 2024-02-12 | 2024-02-09 | P00775403LZ | 23EE0109 | 2023-06-05 | 2023-06-16 | 2023-06-27 | 2023-07-10 | 2023-07-17 | New Space Trdg. & Const.
42320 | NC 2023 | K10 | Region IV-B | Palawan | 110747 | Villa Sol Elementary School | AGUTAYA |  | 1 | 2 |  | Batch 1 | 6821064.61 | 6761898 | 6729668.45 | Completed | 1 | 2024-01-13 | 2023-12-20 | P00775402LZ | 23EE0110 | 2023-06-09 | 2023-06-16 | 2023-06-27 | 2023-07-10 | 2023-07-17 | C-Jairus Construction
42321 | NC 2023 | K10 | Region IV-B | Palawan | 110989 | Marcilla Elementary School | CORON |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4675829.59 | Completed | 1 | 2024-01-12 | 2024-05-17 | P00775405LZ | 23EE0115 | 2023-06-09 | 2023-06-19 | 2023-06-30 | 2023-07-11 | 2023-07-18 | MAC Builders Civil Eng'g. Const.
42322 | NC 2023 | K10 | Region IV-B | Palawan | 502203 | Pag-asa Integrated School | KALAYAAN |  | 1 | 10 |  | Batch 2 | 40846887.94 | 39465592.21 | 39465590 | Ongoing | 0.65 | 2024-11-03 |  | P00775950LZ | 23EE0131 | 2023-09-29 | 2023-10-09 | 2023-10-20 | 2023-11-03 | 2023-11-10 | Mamsar Cont. & Industrial Corp
42323 | NC 2023 | K10 | Region IV-B | Palawan | 111046 | Lacaren Elementary School | MAGSAYSAY |  | 1 | 2 |  | Batch 1 | 6740854.31 | 6682383.45 | 6623524.48 | Completed | 1 | 2024-01-13 | 2023-12-20 | P00775406LZ | 23EE0107 | 2023-06-05 | 2023-06-16 | 2023-06-27 | 2023-07-10 | 2023-07-17 | Maryknoll Builders
42324 | NC 2023 | K10 | Region IV-B | Palawan | 111047 | Los Angeles Elementary School | MAGSAYSAY |  | 1 | 3 |  | Batch 1 | 9793873.27 | 9708920.22 | 9692700.27 | Completed | 1 | 2024-03-18 | 2024-03-14 | P00775407LZ | 23EE0106 | 2023-06-05 | 2023-06-16 | 2023-06-27 | 2023-07-10 | 2023-07-17 | Kayano Trdg & Const.
42325 | NC 2023 | K10 | Region IV-B | Palawan | 111049 | Magsaysay Central School | MAGSAYSAY |  | 1 | 4 |  | Batch 1 | 12846892.24 | 12735456.99 | 12673977.35 | Completed | 1 | 2024-03-04 | 2024-02-19 | P00775408LZ | 23EE0113 | 2023-06-05 | 2023-06-16 | 2023-06-27 | 2023-07-11 | 2023-07-18 | Maryknoll Builders
42326 | NC 2023 | K10 | Region IV-B | Palawan | 111050 | Rizal Elementary School | MAGSAYSAY |  | 1 | 2 |  | Batch 1 | 6769986.93 | 6711263.37 | 6645673.88 | Completed | 1 | 2023-12-14 | 2023-10-26 | P00775409LZ | 23EE0108 | 2023-06-05 | 2023-06-16 | 2023-06-27 | 2023-07-10 | 2023-07-17 | Maryknoll Builders
42327 | NC 2023 | K10 | Region IV-B | Palawan | 170540 | Pedro Baquiao Memorial Elementary School | ROXAS |  | 1 | 1 |  | Batch 1 | 2394285.75 | 2373517.47 | 2336610.05 | Completed | 1 | 2023-10-19 | 2023-10-18 | P00775411LZ | 23EE0117 | 2023-06-09 | 2023-06-19 | 2023-06-30 | 2023-07-11 | 2023-07-18 | Apollo Const. & Ent.
42328 | NC 2023 | K10 | Region IV-B | Palawan | 111167 | San Dionisio Elementary School | ROXAS |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4647347.21 | Completed | 1 | 2023-11-18 | 2023-11-18 | P00775410LZ | 23EE0116 | 2023-06-09 | 2023-06-09 | 2023-06-30 | 2023-07-10 | 2023-07-18 | AFG Const. Corp.
42329 | NC 2023 | K10 | Region IV-B | Palawan | 111190 | Irawan Elementary School | SAN VICENTE |  | 1 | 4 |  | Batch 1 | 11455231.2 | 6608832.42 | 11310565.76 | Completed | 1 | 2023-12-13 | 2023-12-10 | P00775413LZ | 23EE0118 | 2023-06-05 | 2023-06-16 | 2023-06-27 | 2023-07-10 | 2023-07-17 | E.V.Villaos Trdg. & Const.
42330 | NC 2023 | K10 | Region IV-B | Palawan | 111195 | New Caruray Elementary School | SAN VICENTE |  | 1 | 2 |  | Batch 1 | 6666659.7 | 6608832.42 | 6562797.18 | Completed | 1 | 2024-01-02 | 2024-01-22 | P00775414LZ | 23EE0111 | 2023-06-05 | 2023-06-16 | 2023-06-27 | 2023-07-10 | 2023-07-17 | E.V.Villaos Trdg. & Const.
42331 | NC 2023 | K10 | Region IV-B | Palawan | 301712 | New Guinlo National High School | TAYTAY |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4175519.19 | Completed | 1 | 2024-02-22 | 2024-02-20 | P00775416LZ | 23EE0123 | 2023-06-30 | 2024-02-20 | 2023-07-21 | 2023-08-29 | 2023-09-14 | Reinastar Trading & Const.
42332 | NC 2023 | K10 | Region IV-B | Palawan | 170558 | Taytay West Elementary School | TAYTAY |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4788571.5 | Completed | 1 | 2023-12-16 | 2023-12-10 | P00775415LZ | 23EE0119 | 2023-06-09 | 2023-06-19 | 2023-06-30 | 2023-07-11 | 2023-07-18 | MAC Builders Civil Eng'g. Const.
42333 | NC 2023 | K10 | Region IV-B | Palawan | 110725 | Isaub Elementary School | ABORLAN |  | 1 | 6 |  | Batch 1 | 18157500 | 18000000 | 17820071.49 | Completed | 1 | 2024-03-04 | 2025-03-15 | P00775417LZ-CW1 | 23EG0065 | 2023-06-30 | 2023-07-07 | 2023-07-21 | 2023-08-10 | 2023-08-22 | Leon John Great Builders
42334 | NC 2023 | K10 | Region IV-B | Palawan | 111076 | San Isidro Elementary School | NARRA |  | 1 | 6 |  | Batch 1 | 15131250 | 15000000 | 14674716.1 | Completed | 1 | 2024-04-19 | 2024-03-01 |  | 23EF0101 | 2023-06-13 | 2023-06-26 | 2023-07-23 | 2023-08-14 | 2023-08-16 | Cutting Edge Builders and Trading Inc.
42335 | NC 2023 | K10 | Region IV-B | Palawan | 110657 | Calupisan Elementary School | RIZAL (MARCOS) |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4899998.38 | Completed | 1 | 2023-12-21 | 2024-06-01 |  | 23EF0105 | 2023-06-13 | 2023-06-26 | 2023-07-23 | 2023-08-14 | 2023-08-16 | Palbic Construction and Supply
42336 | NC 2023 | K10 | Region IV-B | Palawan | 110322 | Imbo Elementary School | RIZAL (MARCOS) |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4249895.12 | Completed | 1 | 2024-01-11 | 2024-12-01 |  | 23EF0102 | 2023-06-13 | 2023-06-26 | 2023-07-23 | 2023-09-04 | 2023-09-06 | PTK Group, Inc.
42337 | NC 2023 | K10 | Region IV-B | Palawan | 170567 | Rancho II Elementary School | RIZAL (MARCOS) |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4849678.97 | Completed | 1 | 2023-11-25 | 2024-01-01 |  | 23EF0106 | 2023-06-13 | 2023-06-26 | 2023-07-23 | 2023-07-19 | 2023-07-21 | L&M Rodriguez Construction & Trading, Inc.
42338 | NC 2023 | K10 | Region IV-B | Palawan | 111119 | Rizal Central School | RIZAL (MARCOS) |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4949826.9 | Completed | 1 | 2023-11-25 | 2024-01-01 |  | 23EF0103 | 2023-06-13 | 2023-06-26 | 2023-07-23 | 2023-07-19 | 2023-07-21 | JN Dela Torre Construction
42339 | NC 2023 | K10 | Region IV-B | Palawan | 170545 | Tulapos Elementary School | RIZAL (MARCOS) |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 3870260.2 | Completed | 1 | 2024-01-19 | 2024-05-01 |  | 23EF0104 | 2023-06-13 | 2023-06-26 | 2023-07-23 | 2023-09-12 | 2023-09-14 | Trigun Construction
42340 | NC 2023 | K10 | Region IV-B | Palawan | 110905 | Labog Elementary School | SOFRONIO ESPAÑOLA |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 14699508.56 | Completed | 1 | 2024-04-19 | 2024-11-01 |  | 23EF0107 | 2023-06-13 | 2023-06-26 | 2023-07-23 | 2023-08-14 | 2023-08-16 | Hardrock Platinum Development Corp.
42341 | NC 2023 | K10 | Region IV-B | Puerto Princesa City | 111497 | Tagburos ES | PUERTO PRINCESA CITY (Capital) |  | 1 | 4 |  | Batch 1 | 12105000 | 12000000 | 11879427.29 | Completed | 1 | 2024-04-25 | 2024-04-25 | 23EG0071 | 23EG0071 | 2023-06-30 | 2023-07-07 | 2023-07-21 | 2023-11-03 | 2023-11-28 | F.F. Galang Construction
42342 | NC 2023 | K10 | Region IV-B | Romblon | 302080 | Melodias Imperial, Sr. National High School | ALCANTARA |  | 1 | 3 |  | Batch 1 | 5805356.25 | 5755000 | 5639887.96 | Completed | 1 | 2023-12-05 | 2023-12-05 | P00775426LZ | 23EHO159 | 2023-06-21 |  | 2023-07-10 |  | 2023-08-16 |  | Booked(February 15,2024)
42343 | NC 2023 | K10 | Region IV-B | Romblon | 301758 | Danao National High School | CAJIDIOCAN |  | 1 | 2 |  | Batch 1 | 4135875 | 4100000 | 4135875 | Completed | 1 | 2023-11-20 | 2023-12-02 | P00775427LZ | 23EHO160 | 2023-06-16 |  | 2023-07-05 |  | 2023-08-16 |  | Booked(February 15,2024)
42344 | NC 2023 | K10 | Region IV-B | Romblon | 306045 | Victorio Sixon Balogo National High School | CALATRAVA |  | 1 | 2 |  | Batch 1 | 4135875 | 4100000 | 4135875 | Completed | 1 | 2023-11-12 | 2023-11-12 | P00775428LZ | 23EHO161 | 2023-06-16 |  | 2023-07-05 |  | 2023-08-10 |  | Booked(February 15,2024)
42345 | NC 2023 | K10 | Region IV-B | Romblon | 309210 | Mauricio F. Fabito National High School | CORCUERA |  | 1 | 4 |  | Batch 1 | 17653125 | 17500000 | 17150000 | Completed | 1 | 2024-01-14 | 2024-03-13 | P00775429LZ | 23EHO162 | 2023-06-21 |  | 2023-07-10 |  | 2023-08-15 |  | Booked ( April 30,2024)
42346 | NC 2023 | K10 | Region IV-B | Romblon | 309204 | EDUARDO M. MORENO NATIONAL HIGH SCHOOL | SAN AGUSTIN |  | 1 | 2 |  | Batch 1 | 4186312.5 | 4150000 | 4066942.52 | Completed | 1 | 2023-11-12 | 2023-11-12 | P00775430LZ | 23EHO163 | 2023-06-16 |  | 2023-07-05 |  | 2023-08-10 |  | Booked(February 15,2024)
42347 | NC 2023 | K10 | Region IV-B | Romblon | 305694 | Armin Rios-Marin National High School | SAN FERNANDO |  | 1 | 2 |  | Batch 1 | 4135875 | 4100000 | 4003473.36 | Completed | 1 | 2023-11-20 | 2023-12-06 | P00775431LZ | 23EHO164 | 2023-06-16 |  | 2023-07-05 |  | 2023-08-16 |  | Booked ( April 30,2024)
42348 | NC 2023 | K10 | Region IV-B | Romblon | 309212 | Tranquilino Cawaling Sr. National High School | SANTA FE |  | 1 | 3 |  | Batch 1 | 7863206.25 | 7795000 | 7638953.93 | Completed | 1 | 2023-12-25 | 2023-11-24 | P00775432LZ | 23EHO165 | 2023-06-21 |  | 2023-07-10 |  | 2023-08-10 |  | Booked(February 15,2024)
43767 | NC 2024 |  | Region IV-B | Calapan City | 111536 | Calapan Central School | CITY OF CALAPAN (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 16740000 |  | 16121641.78 | Completed | 1 | 2025-02-24 | 2025-02-24 | 24ED0150 | 24ED0150 | 2024-02-29 | 2024-07-03 | 2024-03-20 | 2024-03-26 | 2024-01-04 | MIDR Construction and Supplies
43768 | NC 2024 |  | Region IV-B | Calapan City | 301797 | Community Vocational High School | CITY OF CALAPAN (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9515616.45 | Completed | 1 | 2025-05-01 | 2025-05-01 | 24ED0151 | 24ED0151 | 2024-02-29 | 2024-07-03 | 2024-03-20 | 2024-03-26 | 2024-01-04 | Kolzace Construction
43769 | NC 2024 |  | Region IV-B | Marinduque | 169001 | Ino ES | MOGPOG |  | 1 | 2 | 1STY2CL | GAA 17B | 6600000 |  | 6424839.06 | Completed | 1 | 2024-06-24 | 2024-06-24 | P00875470LZ-CW1 | 24EA0065 | 2024-01-17 | 2024-01-24 | 2024-02-13 | 2024-02-20 | 2024-03-18 | TRIPLE JOHNES Q. CONST.
43770 | NC 2024 |  | Region IV-B | Marinduque | 308803 | Puting Buhangin NHS | MOGPOG |  | 1 | 3 | 1STY3CL | GAA 17B | 9300000 |  | 9105499.94 | Ongoing | 1 | 2024-10-19 | 2024-01-12 | P00875473LZ-CW1 | 24EA0069 | 2024-01-17 | 2024-01-24 | 2024-02-13 | 2024-02-29 | 2024-05-04 | TRIPLE JOHNES Q. CONST. | Upon joint inspection with the DepEd inspectors, there were findings observed that need rectifications
43771 | NC 2024 |  | Region IV-B | Marinduque | 301561 | Sayao National High School | MOGPOG |  | 1 | 3 | 1STY3CL | GAA 17B | 8700000 |  | 8474260.09 | Completed | 1 | 2024-09-28 | 2024-12-16 | P00875474LZ-CW1 | 24EA0067 | 2024-01-17 | 2024-01-24 | 2024-02-13 | 2024-02-20 | 2024-03-15 | TRI-DANJ CONST.
43772 | NC 2024 |  | Region IV-B | Marinduque | 301555 | Matalaba NHS | SANTA CRUZ |  | 1 | 2 | 1STY2CL | GAA 17B | 6700000 |  | 8474260.09 | Completed | 1 | 2024-09-28 | 2024-09-10 | P00875474LZ-CW1 | 24EA0067 | 2024-01-17 | 2024-01-24 | 2024-02-13 | 2024-02-20 | 2024-03-15 | TRI-DANJ CONST.
43773 | NC 2024 |  | Region IV-B | Marinduque | 110030 | Payanas ES | TORRIJOS |  | 1 | 3 | 1STY3CL | GAA 17B | 8700000 |  | 8460561.77 | Ongoing | 0.9 | 2024-07-09 |  | P00875471LZ-CW1 | 24EA0068 | 2024-01-17 | 2024-01-24 | 2024-02-23 | 2024-02-20 | 2024-03-18 | TRIPLE JOHNES Q. CONST. | Upon joint inspection with the DepEd inspectors, there were findings observed that need rectifications
43774 | NC 2024 |  | Region IV-B | Marinduque | 110036 | Torrijos CS | TORRIJOS |  | 1 | 12 | 2STY12CL | GAA 17B | 40000000 |  | 39186390.21 | Completed | 1 | 2024-01-12 | 2024-12-19 | P00875475LZ-CW1 | 24EA0070 | 2024-01-17 | 2024-01-24 | 2024-02-13 | 2024-02-20 | 2024-03-13 | RAPID FOREMOST CONST. CO.
43775 | NC 2024 |  | Region IV-B | Occidental Mindoro | 110085 | Iriron ES | CALINTAAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4832293.44 | Completed | 1 | 2024-05-08 | 2024-05-08 | 24EB0110 | 24EB0110 | 2024-02-28 | 2024-06-03 | 2024-03-19 | 2024-03-27 | 2024-08-04 | Kejamarenik const.& const. supply
43776 | NC 2024 |  | Region IV-B | Occidental Mindoro | 110097 | Balikyas ES | LOOC |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4948888.88 | Completed | 1 | 2024-05-08 | 2024-05-08 | 24EB0106 | 24EB0106 | 2024-02-28 | 2024-06-03 | 2024-03-19 | 2024-03-27 | 2024-08-04 | FAAA Const
43777 | NC 2024 |  | Region IV-B | Occidental Mindoro | 110098 | Bulacan ES | LOOC |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4922971.82 | Completed | 1 | 2024-05-08 | 2024-05-08 | 24EB0107 | 24EB0107 | 2024-02-28 | 2024-06-03 | 2024-03-19 | 2024-03-27 | 2024-08-04 | Kejamarenik const.& const. supply
43778 | NC 2024 |  | Region IV-B | Occidental Mindoro |  | Magarang National High School | MAGSAYSAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4852014.63 | Completed | 1 | 2024-05-08 | 2024-08-20 | 24EB0111 | 24EB0111 | 2024-02-28 | 2024-06-03 | 2024-03-19 | 2024-03-27 | 2024-08-04 | Kejamarenik const.& const. supply
43779 | NC 2024 |  | Region IV-B | Occidental Mindoro | 301594 | Paluan NHS | PALUAN |  | 1 | 12 | 3STY12CL | BATCH 1 | 30000000 |  | 29798789.7 | Ongoing | 0.7 | 2025-06-01 |  | 24EB0115 | 24EB0115 | 2024-01-03 | 2024-08-03 | 2024-03-21 | 2024-01-04 | 2024-07-05 | Koejean const & devt corp.
43780 | NC 2024 |  | Region IV-B | Occidental Mindoro | 110231 | Burgos ES | SABLAYAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4817028.1 | Completed | 1 | 2024-05-08 | 2024-05-08 | 24EB0108 | 24EB0108 | 2024-02-28 | 2024-06-03 | 2024-03-19 | 2024-03-27 | 2024-08-04 | KGB Engg & const.
43781 | NC 2024 |  | Region IV-B | Occidental Mindoro | 110265 | Monte Claro ES | SAN JOSE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4929019.7 | Completed | 1 | 2024-05-08 | 2024-05-08 | 24EB0112 | 24EB0112 | 2024-02-28 | 2024-06-03 | 2024-03-19 | 2024-03-27 | 2024-08-04 | Mighty Dragon Builder
43782 | NC 2024 |  | Region IV-B | Occidental Mindoro | 110266 | Naibuan Elementary School | SAN JOSE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4854646.59 | Completed | 1 | 2024-05-08 | 2024-08-20 | 24EB0113 | 24EB0113 | 2024-02-28 | 2024-06-03 | 2024-03-19 | 2024-03-27 | 2024-08-04 | AMM const, & const, supply
43783 | NC 2024 |  | Region IV-B | Occidental Mindoro |  | Dapdap Cultural Elementary School | SANTA CRUZ |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4833074.98 | Completed | 1 | 2024-09-08 | 2024-09-08 | 24EB0109 | 24EB0109 | 2024-02-28 | 2024-06-03 | 2024-03-19 | 2024-03-27 | 2024-12-04 | Juan Antonio const.
43784 | NC 2024 |  | Region IV-B | Oriental Mindoro | 110619 | Puerto Galera CS | PUERTO GALERA |  | 1 | 9 | 3STY9CL | GAA 17B | 23260000 |  | 22402713.64 | Completed | 1 | 2025-04-24 | 2024-12-16 | P00875485LZ-CW1 | 24ED0152 | 2024-02-29 | 2024-07-03 | 2024-03-20 | 2024-04-19 | 2024-04-25 | Innovative Mangyan Builders Corp.
43785 | NC 2024 |  | Region IV-B | Oriental Mindoro | 110350 | Apnagan ES | BANSUD |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5879543.52 | Completed | 1 | 2024-09-13 | 2024-09-20 | P00875486LZ-CW1 | 24EI0119 | 2024-03-15 | 2024-03-22 | 2024-04-04 | 2024-04-18 | 2024-07-05 | D.M. Almero Enterprises
43786 | NC 2024 |  | Region IV-B | Oriental Mindoro | 305822 | Balatasan National High School | BULALACAO (SAN PEDRO) |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5870344.51 | Completed | 1 | 2024-09-13 | 2024-09-22 | P00875490LZ-CW1 | 24EI0118 | 2024-03-15 | 2024-03-22 | 2024-04-04 | 2024-04-18 | 2024-07-05 | EE Construction
43787 | NC 2024 |  | Region IV-B | Oriental Mindoro | 305820 | Milagrosa National High School | BULALACAO (SAN PEDRO) |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5877667.58 | Completed | 1 | 2024-09-13 | 2024-09-22 | P00875489LZ-CW1 | 24EI0117 | 2024-03-15 | 2024-03-22 | 2024-04-04 | 2024-04-18 | 2024-07-05 | Alberto Uy Construction and Development
43788 | NC 2024 |  | Region IV-B | Oriental Mindoro | 305921 | San Vicente High School | BULALACAO (SAN PEDRO) |  | 1 | 4 | 1STY4CL | BATCH 1 | 12647000 |  | 12383394.71 | Completed | 1 | 2024-11-22 | 2024-01-12 | P00875878LZ-CW1 | 24EI0120 | 2024-03-15 | 2024-03-22 | 2024-04-04 | 2024-04-18 | 2024-07-05 | Kentaru Construction and Supplies
43789 | NC 2024 |  | Region IV-B | Oriental Mindoro | 301647 | Pili NHS | PINAMALAYAN |  | 1 | 4 | 2STY4CL | GAA 17B | 13000000 |  | 12712556.18 | Completed | 1 | 2024-02-11 | 2024-12-16 | P00875487LZ-CW1 | 24EI0121 | 2024-03-15 | 2024-03-22 | 2024-04-04 | 2024-04-18 | 2024-07-05 | WTL Construction
43790 | NC 2024 |  | Region IV-B | Oriental Mindoro |  | B. T. Lazaro MHS | ROXAS |  | 1 | 3 | 1STY3CL | GAA 17B | 9000000 |  | 8813187.13 | Ongoing | 0.93 | 2025-06-05 |  | P00875488LZ-CW1 | 24EI0122 | 2024-04-24 | 2024-02-05 | 2024-05-14 | 2024-12-19 | 2025-07-01 | LEWIS GJANN Construction
43791 | NC 2024 |  | Region IV-B | Palawan | 110750 | Araceli North Central School | ARACELI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970287.5 | Completed | 1 | 2024-10-10 | 2025-05-02 | P00875496LZ | 24EE0143 | 2024-05-03 | 2024-03-14 | 2024-03-26 | 2024-04-15 | 2024-04-26 | MAC Builders Civil Eng'g. Const.
43792 | NC 2024 |  | Region IV-B | Palawan | 110753 | Balogo Elementary School | ARACELI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970287.5 | Completed | 1 | 2024-11-11 | 2025-05-02 | P00875497LZ | 24EE0143 | 2024-05-03 | 2024-03-14 | 2024-03-26 | 2024-04-15 | 2024-04-26 | MAC Builders Civil Eng'g. Const.
43793 | NC 2024 |  | Region IV-B | Palawan | 110986 | Lajala Elementary School | CORON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969923.96 | Completed | 1 | 2024-09-23 | 2024-12-15 | P00875501LZ | 24EE0145 | 2024-05-03 | 2024-03-14 | 2024-03-26 | 2024-04-15 | 2024-04-26 | MAC Builders Civil Eng'g. Const.
43794 | NC 2024 |  | Region IV-B | Palawan | 110924 | Baldat Elementary School | CULION |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969818 | Completed | 1 | 2024-09-23 | 2024-12-15 | P00875499LZ | 24EE0145 | 2024-05-03 | 2024-03-14 | 2024-03-26 | 2024-04-15 | 2024-04-26 | MAC Builders Civil Eng'g. Const.
43795 | NC 2024 |  | Region IV-B | Palawan |  | Biong Elementary School | CULION |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970448.8 | Completed | 1 | 2024-09-23 | 2024-12-15 | P00875498LZ | 24EE0145 | 2024-05-03 | 2024-03-14 | 2024-03-26 | 2024-04-15 | 2024-04-26 | MAC Builders Civil Eng'g. Const.
43796 | NC 2024 |  | Region IV-B | Palawan | 305624 | Diapila National High School | EL NIDO (BACUIT) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4973303.9 | Completed | 1 | 2024-09-25 | 2024-11-22 | P00875494LZ | 24EE0144 | 2024-05-03 | 2024-03-14 | 2024-03-26 | 2024-04-15 | 2024-04-26 | E.V.Villaos Trdg. & Const.
43797 | NC 2024 |  | Region IV-B | Palawan | 301736 | San Fernando National High School | EL NIDO (BACUIT) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970448.81 | Completed | 1 | 2024-09-25 | 2024-11-22 | P00875495LZ | 24EE0144 | 2024-05-03 | 2024-03-14 | 2024-03-26 | 2024-04-15 | 2024-04-26 | E.V.Villaos Trdg. & Const.
43798 | NC 2024 |  | Region IV-B | Palawan | 502203 | Pag-asa Integrated School | KALAYAAN |  | 1 |  | Construction of School Building | GAA 17B | 50000000 |  | 49738703.45 | Ongoing | 0.5 | 2025-05-27 |  | P00875520LZ | 24EE0151 | 2024-05-03 | 2024-03-14 | 2024-03-26 | 2024-04-15 | 2024-04-26 | Jasmig Construction Corporation
43799 | NC 2024 |  | Region IV-B | Palawan | 111200 | Port Barton Elementary School | SAN VICENTE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972357.15 | Completed | 1 | 2024-09-13 | 2024-10-18 | P00875500LZ | 24EE0142 | 2024-05-03 | 2024-03-14 | 2024-03-26 | 2024-04-15 | 2024-04-26 | E.V.Villaos Trdg. & Const.
43800 | NC 2024 |  | Region IV-B | Palawan | 110792 | Balabac Central School | BALABAC |  | 1 | 8 | 2STY8CL | BATCH 1 | 24000000 |  | 23880000 | Ongoing | 0.75 | 2025-02-22 |  | 24EF0094 | 24EF0094 | 2024-03-05 | 2024-10-05 | 2024-05-22 | 2024-06-18 | 2024-06-20 | Brels Construction
43801 | NC 2024 |  | Region IV-B | Palawan | 110858 | Tagolango Elementary School | BATARAZA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-08-20 |  | 24EF0090 | 24EF0090 | 2024-01-03 | 2024-08-03 | 2024-03-21 | 2024-04-04 | 2024-04-15 | BJ-RAM Construction
43802 | NC 2024 |  | Region IV-B | Palawan | 110868 | Cabangaan Elementary School | BROOKE'S POINT |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-08-20 |  | 24EF0087 | 24EF0087 | 2024-01-03 | 2024-08-03 | 2024-03-21 | 2024-04-04 | 2024-04-15 | JAS Trading and Construction
43803 | NC 2024 |  | Region IV-B | Palawan |  | Balintik PS | NARRA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4921395.87 | Ongoing | 0.1 | 2025-08-08 |  | 24EF0100 | 24EF0100 | 2024-07-06 | 2024-06-18 | 2024-02-07 |  |  | CM77 Construction Trading | Late started due to conflict of school site.
43804 | NC 2024 |  | Region IV-B | Palawan | 111063 | Calategas Elementary School | NARRA |  | 1 |  | Construction of School Building | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-08-20 | 2024-08-01 | 24EF0085 | 24EF0085 | 2024-01-03 | 2024-08-03 | 2024-03-21 | 2024-04-04 | 2024-04-15 | RDF Trading and Construction
43805 | NC 2024 |  | Region IV-B | Palawan | 111069 | Malinao Elementary School | NARRA |  | 1 |  | Construction of School Building | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-09-27 |  | 24EF0088 | 24EF0088 | 2024-04-16 | 2024-04-23 | 2024-07-05 | 2024-05-13 | 2024-05-23 | Trigun Construction
43806 | NC 2024 |  | Region IV-B | Palawan |  | Minalaki PS | NARRA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 |  |  | 24EF0099 | 24EF0099 | 2024-07-06 | 2024-06-18 | 2024-02-07 |  |  |  | Issue with school site (school is not yet establish)
43807 | NC 2024 |  | Region IV-B | Palawan | 111104 | Kalatagbak Elementary School | QUEZON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-08-20 | 2025-04-01 | 24EF0086 | 24EF0086 | 2024-01-03 | 2024-08-03 | 2024-03-21 | 2024-04-04 | 2024-04-15 | CM77 Construction Trading
43808 | NC 2024 |  | Region IV-B | Palawan | 130295 | Marnek Elementary School | QUEZON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2025-01-22 |  | 24EF0098 | 24EF0098 | 2024-07-06 | 2024-06-18 | 2024-02-07 | 2024-10-09 | 2024-09-17 | Kim and Twin Construction Services | Late procurement due to modification of school name
43809 | NC 2024 |  | Region IV-B | Palawan | 111126 | Sowangan Elementary School | QUEZON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Ongoing | 0.75 | 2024-08-20 |  | 24EF0089 | 24EF0089 | 2024-01-03 | 2024-08-03 | 2024-03-21 | 2024-04-04 | 2024-04-15 | Leon John Great Builders Construction Corporation
43810 | NC 2024 |  | Region IV-B | Palawan | 170565 | Tungib Elementary School | QUEZON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2025-01-22 |  | 24EF0095 | 24EF0095 | 2024-07-06 | 2024-06-18 | 2024-02-07 | 2024-10-09 | 2024-09-17 | Cutting Edge Builders and Trading, Inc. | Late procurement due to modification of school name
43811 | NC 2024 |  | Region IV-B | Palawan | 109746 | Molid Elementary School | RIZAL (MARCOS) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2025-01-22 |  | 24EF0097 | 24EF0097 | 2024-07-06 | 2024-06-18 | 2024-02-07 | 2024-10-09 | 2024-09-17 | Jorich Construction Services | Late procurement due to modification of school name
43812 | NC 2024 |  | Region IV-B | Palawan | 111131 | Tagpas Elementary School | RIZAL (MARCOS) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Ongoing | 0.8 | 2025-01-22 |  | 24EF0096 | 24EF0096 | 2024-07-06 | 2024-06-18 | 2024-02-07 | 2024-10-09 | 2024-09-17 | JN Dela Torre Construction | Late procurement due to modification of school name
43813 | NC 2024 |  | Region IV-B | Palawan | 110917 | Punang Elementary School | SOFRONIO ESPAÑOLA |  | 1 |  | Construction of School Building | GAA 17B | 20000000 |  | 19900000 | Ongoing | 0.85 | 2024-12-18 |  | 24EF0084 | 24EF0084 | 2024-01-03 | 2024-08-03 | 2024-03-21 | 2024-04-04 | 2024-04-15 | KIR Konstruction Builders and Supply, Inc. | Late start due to Construction site issue
43814 | NC 2024 |  | Region IV-B | Palawan | 110712 | Aborlan Central School | ABORLAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5700000 |  | 5671450.98 | Completed | 1 | 2024-01-09 | 2024-08-13 | P00875515LZ-CW1 | 24EG0080 | 2024-02-29 | 2024-07-03 | 2024-03-21 | 2024-12-04 | 2024-04-23 | KAYANO TRADING AND CONSTRUCTION
43815 | NC 2024 |  | Region IV-B | Palawan | 110719 | Cabigaan Elementary School | ABORLAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5700000 |  | 5671494.45 | Completed | 1 | 2024-01-09 | 2024-01-09 | P00875516LZ-CW1 | 24EG0082 | 2024-02-29 | 2024-07-03 | 2024-03-21 | 2024-12-04 | 2024-04-23 | KIR KONSTRUCTICON BUILDERS AND SUPPLY INC.
43816 | NC 2024 |  | Region IV-B | Palawan | 110731 | Plaridel Elementary School | ABORLAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5700000 |  | 5670112.73 | Completed | 1 | 2024-01-09 | 2025-05-01 | P00875512LZ-CW1 | 24EG0081 | 2024-02-29 | 2024-07-03 | 2024-03-21 | 2024-01-08 | 2024-04-23 | NEW SPACE TRADINGA ND CONSTRUCTION CORP.
43817 | NC 2024 |  | Region IV-B | Palawan | 170555 | Sitio Morzon Elementary School | ABORLAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5800000 |  | 5770849.51 | Completed | 1 | 2024-01-09 | 2024-01-12 | P00875513LZ-CW1 | 24EG0083 | 2024-02-29 | 2024-07-03 | 2024-03-21 | 2024-12-04 | 2024-04-23 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY
43818 | NC 2024 |  | Region IV-B | Puerto Princesa City | 111517 | Lucbuan ES | PUERTO PRINCESA CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5700000 |  | 5614825.31 | Completed | 1 | 2024-09-24 | 2024-12-09 | 24EG0078 | 24EG0078 | 2024-02-29 | 2024-07-03 | 2024-03-21 | 2024-04-15 | 2024-05-13 | Maryknoll Builders and Supply
43819 | NC 2024 |  | Region IV-B | Puerto Princesa City | 111485 | Mateo Jagmis MES | PUERTO PRINCESA CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5700000 |  | 5586155.94 | Completed | 1 | 2024-11-09 | 2024-11-09 | 24EG0079 | 24EG0079 | 2024-02-29 | 2024-07-03 | 2024-03-21 | 2024-12-04 | 2024-04-23 | JAS Trading and Construction
43820 | NC 2024 |  | Region IV-B | Puerto Princesa City | 111530 | San Rafael ES | PUERTO PRINCESA CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5700000 |  | 5614792.65 | Completed | 1 | 2024-06-09 | 2024-11-09 | 24EG0077 | 24EG0077 | 2024-02-29 | 2024-07-03 | 2024-03-21 | 2024-12-04 | 2024-04-23 | Maryknoll Builders and Supply
43821 | NC 2024 |  | Region IV-B | Puerto Princesa City | 111497 | Tagburos ES | PUERTO PRINCESA CITY (Capital) |  | 1 | 10 | 2STY10CL | BATCH 1 | 33000000 |  | 32754999.98 | Ongoing | 0.995 | 2025-09-01 |  | 24EG0085 | 24EG0085 | 2024-08-03 | 2024-07-03 | 2024-03-27 | 2024-04-15 | 2024-04-29 | RAK Trading and Construction | Revised Completion: March 22, 2025
43822 | NC 2024 |  | Region IV-B | Puerto Princesa City | 111502 | Valentin Macasaet Sr. MES | PUERTO PRINCESA CITY (Capital) |  | 1 | 6 | 2STY6CL | BATCH 1 | 23611000 |  | 23427552.21 | Completed | 1 | 2024-11-22 | 2024-06-12 | 24EG0084 | 24EG0084 | 2024-08-03 | 2024-03-15 | 2024-03-27 | 2024-04-15 | 2024-04-29 | YNZON Construction and Trading Incorporated | Revised Completion: December 8, 2024
43823 | NC 2024 |  | Region IV-B | Romblon |  | Sinapawan Elementary School | CAJIDIOCAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4900262.49 | Completed | 1 | 2024-08-24 | 2024-09-18 | P00875526LZ |  | 2024-06-03 |  | 2024-03-25 |  | 2024-06-05 | EMQ DESIGN & CONSTRUCTION
43824 | NC 2024 |  | Region IV-B | Romblon | 502325 | Agojo Integrated School | LOOC |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4900374.94 | Completed | 1 | 2024-08-29 | 2024-08-29 | P00875523LZ |  | 2024-06-03 |  | 2024-03-25 |  | 2024-05-21 | RNV CONSTRUCTION
43825 | NC 2024 |  | Region IV-B | Romblon | 305627 | Limon Norte National High School | LOOC |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4900335.75 | Completed | 1 | 2024-08-24 | 2024-08-24 | P00875522LZ |  | 2024-03-14 |  | 2024-02-04 |  | 2024-05-16 | EMQ DESIGN & CONSTRUCTION
43826 | NC 2024 |  | Region IV-B | Romblon | 301765 | LOOC NATIONAL HIGH SCHOOL | LOOC |  | 1 | 20 | 4STY20CL | BATCH 1 | 63625000 |  | 62356920.52 | Ongoing | 0.4 | 2025-02-08 |  | P00875882LZ |  | 2024-08-14 |  | 2024-02-09 |  | 2024-05-12 | ROLCO CONSTRUCTION DEVELOPMENT CORPORATION
43827 | NC 2024 |  | Region IV-B | Romblon | 111276 | Agutay ES | MAGDIWANG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4890324.73 | Completed | 1 | 2024-08-18 | 2024-06-09 | P00875521LZ |  | 2024-06-03 |  | 2024-03-25 |  | 2024-10-05 | MT. GUITING-GUITING CONSTRUCTION
43828 | NC 2024 |  | Region IV-B | Romblon | 111383 | Lonos ES | ROMBLON (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925160.93 | Completed | 1 | 2024-08-09 | 2024-04-09 | P00875528LZ |  | 2024-06-03 |  | 2024-03-25 |  | 2024-06-05 | E.K. CO CONSTRUCTION & SUPPLY
43829 | NC 2024 |  | Region IV-B | Romblon | 171001 | Maximino Mazo Motin Elementary School | ROMBLON (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4900308.64 | Completed | 1 | 2024-08-18 | 2024-08-25 | P00875527LZ |  | 2024-06-03 |  | 2024-03-25 |  | 2024-10-05 | MT. GUITING-GUITING CONSTRUCTION
43830 | NC 2024 |  | Region IV-B | Romblon | 301751 | Cabolutan NHS | SAN AGUSTIN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4900280 | Completed | 1 | 2024-11-15 | 2024-11-15 | P00875526LZ |  | 2024-09-03 |  | 2024-03-25 |  | 2024-05-08 | DNM BUILDERS AND DEVELOPMENT CORPORATION
43831 | NC 2024 |  | Region IV-B | Romblon | 111392 | Esteban Minon Madrona ES | SAN AGUSTIN |  | 1 | 9 | 3STY9CL | GAA 17B | 40000000 |  | 39202226.69 | Completed | 1 | 2024-10-12 | 2025-03-04 | P00875529LZ |  | 2024-04-04 |  | 2024-04-23 |  | 2024-05-24 | ROLCO CONSTRUCTION DEVELOPMENT CORPORATION
43832 | NC 2024 |  | Region IV-B | Romblon | 502265 | Linawan Integrated School | SAN ANDRES |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925555.07 | Completed | 1 | 2024-08-29 | 2024-10-17 | P00875524LZ |  | 2024-06-03 |  | 2024-03-25 |  | 2024-05-21 | R.G. FLORENTINO CONST. & TRADING INC.

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.