## Sheet1
INDEX (DO NOT MODIFY) | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
1432 | REPAIR 2020 | Region IV-B | Calapan City | 111535 | Bulusan ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1415523 | 1 | 1415523 | COMPLETED | 1 | 2021-02-11 | 2021-02-15 |  | 2020-019 | 2019-11-07 | 2019-11-29 | 2019-12-11 | 2019-12-19 | 2020-09-28 | KARANGYAN BUILDERS AND TRADERS
1433 | REPAIR 2020 | Region IV-B | Calapan City | 111545 | Salong Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 1 | Repair of Classroom | 475673 | 1 | 475673 | COMPLETED | 1 | 2021-02-11 | 2021-02-15 |  | 2020-019 | 2019-11-07 | 2019-11-29 | 2019-12-11 | 2019-12-19 | 2020-09-28 | KARANGYAN BUILDERS AND TRADERS
1434 | REPAIR 2020 | Region IV-B | Calapan City | 111547 | Silonay ES | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2685813 | 1 | 2685813 | COMPLETED | 1 | 2021-02-11 | 2021-02-15 |  | 2020-019 | 2019-11-07 | 2019-11-29 | 2019-12-11 | 2019-12-19 | 2020-09-28 | KARANGYAN BUILDERS AND TRADERS
1435 | REPAIR 2020 | Region IV-B | Marinduque | 109865 | Agot ES | BOAC (Capital) | 0 | 1 | 1 | Repair of Classroom | 297000 | 1 | 291967.5 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1436 | REPAIR 2020 | Region IV-B | Marinduque | 109884 | Amoingon ES | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 675000 | 1 | 665245.78 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1437 | REPAIR 2020 | Region IV-B | Marinduque | 109885 | Balagasan ES | BOAC (Capital) | 0 | 1 | 5 | Repair of Classrooms | 773000 | 1 | 764237.51 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1438 | REPAIR 2020 | Region IV-B | Marinduque | 109886 | Balaring-Caganhao ES | BOAC (Capital) | 0 | 1 | 7 | Repair of Classrooms | 1933000 | 1 | 1885073.89 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1439 | REPAIR 2020 | Region IV-B | Marinduque | 109867 | Balimbing ES | BOAC (Capital) | 0 | 1 | 1 | Repair of Classroom | 432000 | 1 | 426212.23 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1440 | REPAIR 2020 | Region IV-B | Marinduque | 109888 | Bangbangalon ES | BOAC (Capital) | 0 | 1 | 2 | Repair of Classrooms | 508000 | 1 | 500584.7 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1441 | REPAIR 2020 | Region IV-B | Marinduque | 109868 | Bantauyan PS | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 632000 | 1 | 622068.79 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1442 | REPAIR 2020 | Region IV-B | Marinduque | 109889 | Bantay ES | BOAC (Capital) | 0 | 1 | 2 | Repair of Classrooms | 539000 | 1 | 533019.43 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1443 | REPAIR 2020 | Region IV-B | Marinduque | 109892 | Boi ES | BOAC (Capital) | 0 | 1 | 2 | Repair of Classrooms | 404000 | 1 | 394368.57 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1444 | REPAIR 2020 | Region IV-B | Marinduque | 109869 | Buliasnin ES | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 699000 | 1 | 688711.73 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1445 | REPAIR 2020 | Region IV-B | Marinduque | 109893 | Canat ES | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 699000 | 1 | 690931.48 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1446 | REPAIR 2020 | Region IV-B | Marinduque | 109871 | Hinapulan ES | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 787000 | 1 | 776584.3 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1447 | REPAIR 2020 | Region IV-B | Marinduque | 109872 | Lupac-Tabigue ES | BOAC (Capital) | 0 | 1 | 12 | Repair of Classrooms | 1760000 | 1 | 1703521.64 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1448 | REPAIR 2020 | Region IV-B | Marinduque | 109874 | Maligaya ES | BOAC (Capital) | 0 | 1 | 2 | Repair of Classrooms | 329000 | 1 | 325103.61 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1449 | REPAIR 2020 | Region IV-B | Marinduque | 109875 | Pawa ES | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 421000 | 1 | 416841.96 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1450 | REPAIR 2020 | Region IV-B | Marinduque | 109878 | Poras ES | BOAC (Capital) | 0 | 1 | 15 | Repair of Classrooms | 8714094 | 1 | 8531773.04 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1451 | REPAIR 2020 | Region IV-B | Marinduque | 109880 | Puyog ES | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 829000 | 1 | 809404.96 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1452 | REPAIR 2020 | Region IV-B | Marinduque | 109881 | Sawi ES | BOAC (Capital) | 0 | 1 | 1 | Repair of Classroom | 172000 | 1 | 170057.74 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1453 | REPAIR 2020 | Region IV-B | Marinduque | 109882 | Tanza ES | BOAC (Capital) | 0 | 1 | 5 | Repair of Classrooms | 1425000 | 1 | 1381910.99 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1454 | REPAIR 2020 | Region IV-B | Marinduque | 109883 | Tumagabok ES | BOAC (Capital) | 0 | 1 | 4 | Repair of Classrooms | 1359000 | 1 | 1318907.69 | COMPLETED | 1 | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR
1455 | REPAIR 2020 | Region IV-B | Marinduque | 301561 | Sayao NHS | MOGPOG | 0 | 1 | 6 | Repair of Classrooms | 1702423 | 1 | 1675251.92 | COMPLETED | 1 | 2021-08-31 | [7 empty] | 2021-01-04 | GS MOTAR
1456 | REPAIR 2020 | Region IV-B | Marinduque | 110002 | Makulapnit ES | SANTA CRUZ | 0 | 1 | 6 | Repair of Classrooms | 3877194 | 1 | 3815939.26 | COMPLETED | 1 | 2021-08-31 | [7 empty] | 2021-01-04 | GS MOTAR
1457 | REPAIR 2020 | Region IV-B | Marinduque | 109968 | Masalukot ES | SANTA CRUZ | 0 | 1 | 2 | Repair of Classrooms | 2059805 | 1 | 2013292.22 | COMPLETED | 1 | 2021-08-31 | [7 empty] | 2021-01-04 | GS MOTAR
1458 | REPAIR 2020 | Region IV-B | Marinduque | 301563 | Tagum NHS | SANTA CRUZ | 0 | 1 | 8 | Repair of Classrooms | 4659654 | 1 | 4393285.75 | COMPLETED | 1 | 2021-08-31 | [7 empty] | 2021-01-04 | GS MOTAR
1459 | REPAIR 2020 | Region IV-B | Occidental Mindoro | 110080 | Bulangcog ES | CALINTAAN | 0 | 1 | 6 | Repair of Classrooms | 1883062 | 1 | 1881767.04 | COMPLETED | 1 | 2021-01-25 | 2021-01-15 |  |  | Sept.20,2020 | Sept.27,2020 | Oct.11,2020 | Oct.18,2020 | Oct.25,2020 | hawkstow construction and development
1460 | REPAIR 2020 | Region IV-B | Occidental Mindoro | 110091 | New Dagupan ES | CALINTAAN | 0 | 1 | 6 | Repair of Classrooms | 1903503 | 1 | 1902146.31 | COMPLETED | 1 | 2021-01-25 | 2021-01-15 |  |  | Sept.20,2020 | Sept.27,2020 | Oct.11,2020 | Oct.18,2020 | Oct.25,2020 | hawkstow construction and development
1461 | REPAIR 2020 | Region IV-B | Occidental Mindoro | 110090 | Poypoy Elementary School | CALINTAAN | 0 | 1 | 6 | Repair of Classrooms | 1897071 | 1 | 1877504.53 | COMPLETED | 1 | 2021-01-25 | 2021-01-15 |  |  | Sept.20,2020 | Sept.27,2020 | Oct.11,2020 | Oct.18,2020 | Oct.25,2020 | hawkstow construction and development
1462 | REPAIR 2020 | Region IV-B | Occidental Mindoro | 110131 | Guballa ES | MAGSAYSAY | 0 | 1 | 6 | Repair of Classrooms | 1999086 | 1 | 1997544.35 | COMPLETED | 1 | 2021-01-25 | 2021-01-15 |  |  | Sept.20,2020 | Sept.27,2020 | Oct.11,2020 | Oct.18,2020 | Oct.25,2020 | hawkstow construction and development
1463 | REPAIR 2020 | Region IV-B | Occidental Mindoro | 110258 | Curanta ES | SAN JOSE | 0 | 1 | 4 | Repair of Classrooms | 1283416 | 1 | 1281441.72 | COMPLETED | 1 | 2021-01-25 | 2021-01-15 |  |  | Sept.20,2020 | Sept.27,2020 | Oct.11,2020 | Oct.18,2020 | Oct.25,2020 | hawkstow construction and development
1464 | REPAIR 2020 | Region IV-B | Occidental Mindoro | 110263 | La Curva ES | SAN JOSE | 0 | 1 | 6 | Repair of Classrooms | 1929434 | 1 | 1927130.12 | COMPLETED | 1 | 2021-01-25 | 2021-01-15 |  |  | Sept.20,2020 | Sept.27,2020 | Oct.11,2020 | Oct.18,2020 | Oct.25,2020 | hawkstow construction and development
1465 | REPAIR 2020 | Region IV-B | Oriental Mindoro | 110330 | Felix Hernandez MS | BACO | 1 | 1 | 7 | Repair of Classrooms | 2481425 | 1 | 2481424.93 | COMPLETED | 1 | 2020-03-16 | 2021-02-09 | REPAIR 2020 - R IVB - Oriental Mindoro-030 | 009-2020 | 2019-11-20 | 2019-11-27 | 2020-03-12 | 2020-05-28 | 2020-11-09 | Kasanga Const. and Supplies
1466 | REPAIR 2020 | Region IV-B | Oriental Mindoro | 110516 | Karumangit ES | NAUJAN | 1 | 1 | 7 | Repair of Classrooms | 1753519 | 1 | 1753518.05 | COMPLETED | 1 | 2020-03-17 | 2021-03-11 | REPAIR 2020 - R IVB - Oriental Mindoro-034 | 010-2020 | 2019-11-20 | 2019-11-27 | 2020-03-12 | 2020-05-28 | 2020-11-09 | CMSEL Const. & Developer
1467 | REPAIR 2020 | Region IV-B | Oriental Mindoro | 110521 | Masagana ES | NAUJAN | 1 | 1 | 5 | Repair of Classrooms | 1818210 | 1 | 1818209.57 | COMPLETED | 1 | 2020-03-17 | 2021-03-11 | REPAIR 2020 - R IVB - Oriental Mindoro-035 | 010-2020 | 2019-11-20 | 2019-11-27 | 2020-03-12 | 2020-05-28 | 2020-11-09 | CMSEL Const. & Developer
1468 | REPAIR 2020 | Region IV-B | Oriental Mindoro | 110594 | CASILIGAN ELEMENTARY SCHOOL | POLA | 1 | 1 | 11 | Repair of Classrooms | 3410706 | 1 | 3410705.24 | COMPLETED | 1 | 2020-03-16 | 2021-02-24 | REPAIR 2020 - R IVB - Oriental Mindoro-042 | 011-2020 | 2019-11-20 | 2019-11-27 | 2020-03-12 | 2020-05-28 | 2020-11-09 | ETVR Trading & Const.
1469 | REPAIR 2020 | Region IV-B | Oriental Mindoro | 110697 | LOYAL ELEMENTARY SCHOOL | VICTORIA | 1 | 1 | 8 | Repair of Classrooms | 2966591 | 1 | 2966590.5641 | COMPLETED | 1 | 2020-03-17 | 2021-02-17 | REPAIR 2020 - R IVB - Oriental Mindoro-039 | 012-2020 | 2019-11-20 | 2019-11-27 | 2020-03-12 | 2020-05-28 | 2020-11-09 | DK Const.
1470 | REPAIR 2020 | Region IV-B | Oriental Mindoro | 110432 | Agsalin ES | GLORIA | 2 | 1 | 5 | Repair of Classrooms | 2020000 | 1 | 2020000 | COMPLETED | 1 | 2020-03-17 | 2021-01-22 | REPAIR 2020 - R IVB - Oriental Mindoro-012 | 013-2020 | 2019-11-20 | 2019-11-27 | 2019-12-12 | 2020-03-04 | 2020-11-09 | ADL Constrak
1471 | REPAIR 2020 | Region IV-B | Oriental Mindoro | 170040 | BULAKLAKAN ELEMENTARY SCHOOL | GLORIA | 2 | 1 | 1 | Repair of Classroom | 555000 | 1 | 555000 | COMPLETED | 1 | 2020-03-17 | 2021-01-22 | REPAIR 2020 - R IVB - Oriental Mindoro-038 | 013-2020 | 2019-11-20 | 2019-11-27 | 2019-12-12 | 2020-03-04 | 2020-11-09 | ADL Constrak
1472 | REPAIR 2020 | Region IV-B | Oriental Mindoro | 110444 | Langgang ES | GLORIA | 2 | 1 | 6 | Repair of Classrooms | 2088323 | 1 | 2088322.0363 | COMPLETED | 1 | 2020-03-16 | 2021-01-20 | REPAIR 2020 - R IVB - Oriental Mindoro-009 | 014-2020 | 2019-11-20 | 2019-11-27 | 2019-12-12 | 2020-03-04 | 2020-11-09 | ETVR Trading & Const.
1473 | REPAIR 2020 | Region IV-B | Oriental Mindoro | 110460 | Bait ES | MANSALAY | 2 | 1 | 9 | Repair of Classrooms | 3345001 | 1 | 3345000.0049 | COMPLETED | 1 | 2020-03-17 | 2021-03-01 | REPAIR 2020 - R IVB - Oriental Mindoro-013 | 015-2020 | 2019-11-20 | 2019-11-27 | 2019-12-12 | 2020-03-04 | 2020-11-09 | ADL Constrak
1474 | REPAIR 2020 | Region IV-B | Oriental Mindoro | 110477 | Sta. Brigida ES | MANSALAY | 2 | 1 | 7 | Repair of Classrooms | 2810001 | 1 | 2810000.0047 | COMPLETED | 1 | 2020-03-17 | 2021-03-01 | REPAIR 2020 - R IVB - Oriental Mindoro-019 | 016-2020 | 2019-11-20 | 2019-11-27 | 2019-12-12 | 2020-03-04 | 2020-11-09 | ADL Constrak
1475 | REPAIR 2020 | Region IV-B | Palawan | 110750 | Araceli North Central School | ARACELI | 1 | 1 | 3 | Repair of Classrooms | 1134132 | 1 | 1134131.66 | COMPLETED | 1 | 2021-02-28 | 2021-02-12 | 2020-09-001 | 2020-09-001 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply
1476 | REPAIR 2020 | Region IV-B | Palawan | 110999 | BALADING ES | CUYO | 1 | 1 | 5 | Repair of Classrooms | 1430836 | 1 | 1233608.77 | COMPLETED | 1 | 2021-03-30 | 2021-02-28 | 2020-09-002 | 2020-09-002 | 2020-02-08 | 2020-02-21 | 2020-03-04 | 2020-11-10 | 2020-11-20 | Futuristic Trdg. And Construction
1477 | REPAIR 2020 | Region IV-B | Palawan | 111008 | BISUCAY ES | CUYO | 1 | 1 | 3 | Repair of Classrooms | 1312119 | 1 | 1149086.13 | COMPLETED | 1 | 2021-03-30 | 2021-02-28 | 2020-09-002 | 2020-09-002 | 2020-02-08 | 2020-02-21 | 2020-03-04 | 2020-11-10 | 2020-11-20 | Futuristic Trdg. And Construction
1478 | REPAIR 2020 | Region IV-B | Palawan | 110754 | Bohol Elementary School | DUMARAN | 1 | 1 | 4 | Repair of Classrooms | 1271997 | 1 | 1271996.8 | COMPLETED | 1 | 2021-02-28 | 2021-02-12 | 2020-09-001 | 2020-09-001 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply
1479 | REPAIR 2020 | Region IV-B | Palawan | 110767 | Dumaran Central School | DUMARAN | 1 | 1 | 7 | Repair of Classrooms | 1406107 | 1 | 1406106.04 | COMPLETED | 1 | 2021-02-28 | 2021-02-12 | 2020-09-001 | 2020-09-001 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply
1480 | REPAIR 2020 | Region IV-B | Palawan | 111022 | Diapila Elementary School | EL NIDO (BACUIT) | 1 | 1 | 2 | Repair of Classrooms | 982614 | 1 | 982613.11 | COMPLETED | 1 | 2021-02-28 | 2021-02-12 | 2020-09-003 | 2020-09-003 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Ian Jason Const. & Supply
1481 | REPAIR 2020 | Region IV-B | Palawan | 110952 | New Colaylayan Elementary School | LINAPACAN | 1 | 1 | 3 | Repair of Classrooms | 1236637 | 1 | 1236636.94 | COMPLETED | 1 | 2021-02-28 | 2021-01-08 | 2020-09-003 | 2020-09-003 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Ian Jason Const. & Supply
1482 | REPAIR 2020 | Region IV-B | Palawan | 111040 | ALCOBA ES | MAGSAYSAY | 1 | 1 | 4 | Repair of Classrooms | 1730748 | 1 | 1494874.25 | COMPLETED | 1 | 2021-03-30 | 2021-02-28 | 2020-09-002 | 2020-09-002 | 2020-02-08 | 2020-02-21 | 2020-03-04 | 2020-11-10 | 2020-11-20 | Futuristic Trdg. And Construction
1483 | REPAIR 2020 | Region IV-B | Palawan | 111047 | LOS ANGELES ES | MAGSAYSAY | 1 | 1 | 4 | Repair of Classrooms | 1666717 | 1 | 1439253 | COMPLETED | 1 | 2021-03-30 | 2021-02-28 | 2020-09-002 | 2020-09-002 | 2020-02-08 | 2020-02-21 | 2020-03-04 | 2020-11-10 | 2020-11-20 | Futuristic Trdg. And Construction
1484 | REPAIR 2020 | Region IV-B | Palawan | 111150 | Jolo Elementary School | ROXAS | 1 | 1 | 5 | Repair of Classrooms | 1920534 | 1 | 1920533.09 | COMPLETED | 1 | 2021-02-28 | 2021-02-12 | 2020-09-003 | 2020-09-003 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Ian Jason Const. & Supply
1485 | REPAIR 2020 | Region IV-B | Palawan | 301723 | Port Barton National High School | SAN VICENTE | 1 | 1 | 6 | Repair of Classrooms | 2270817 | 1 | 2270816.65 | COMPLETED | 1 | 2021-02-28 | 2020-12-18 | 2020-09-003 | 2020-09-003 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Ian Jason Const. & Supply
1486 | REPAIR 2020 | Region IV-B | Palawan | 301712 | New Guinlo National High School | TAYTAY | 1 | 1 | 9 | Repair of Classrooms | 3029810 | 1 | 3029809.84 | COMPLETED | 1 | 2021-02-28 | 2021-02-12 | 2020-09-001 | 2020-09-001 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply
1487 | REPAIR 2020 | Region IV-B | Palawan | 110803 | Look Dahu ES | BALABAC | 2 | 1 | 2 | Repair of Classrooms | 933961 | 1 | 933960.83 | COMPLETED | 1 | 2021-03-13 | 2021-03-13 | 2020-09-004 | 2020-09-004 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply
1488 | REPAIR 2020 | Region IV-B | Palawan | 110810 | Marabon ES | BALABAC | 2 | 1 | 4 | Repair of Classrooms | 1579290 | 1 | 1579289.24 | COMPLETED | 1 | 2021-03-13 | 2021-03-10 | 2020-09-004 | 2020-09-004 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply
1489 | REPAIR 2020 | Region IV-B | Palawan | 110809 | Matangule ES | BALABAC | 2 | 1 | 3 | Repair of Classrooms | 1204568 | 1 | 1204567.45 | COMPLETED | 1 | 2021-03-13 | 2021-03-10 | 2020-09-004 | 2020-09-004 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply
1490 | REPAIR 2020 | Region IV-B | Palawan | 110840 | Ocayan ES | BATARAZA | 2 | 1 | 2 | Repair of Classrooms | 874843 | 1 | 874842.86 | COMPLETED | 1 | 2021-03-13 | 2021-02-12 | 2020-09-004 | 2020-09-004 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply
1491 | REPAIR 2020 | Region IV-B | Palawan | 110852 | Sayab II ES | BATARAZA | 2 | 1 | 2 | Repair of Classrooms | 776021 | 1 | 776020.08 | COMPLETED | 1 | 2021-03-13 | 2021-02-11 | 2020-09-004 | 2020-09-004 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply
1492 | REPAIR 2020 | Region IV-B | Palawan | 111057 | Batang-Batang Proper ES | NARRA | 2 | 1 | 1 | Repair of Classroom | 339300 | 1 | 339299.96 | COMPLETED | 1 | 2021-02-28 | Dec.31,2020 | 2020-09-005 | 2020-09-005 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | A.A. Padua Design & Const.
1493 | REPAIR 2020 | Region IV-B | Palawan | 111065 | Elvita ES | NARRA | 2 | 1 | 8 | Repair of Classrooms | 2361371 | 1 | 2361370.5 | COMPLETED | 1 | 2021-02-28 | Dec.31,2020 | 2020-09-005 | 2020-09-005 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | A.A. Padua Design & Const.
1494 | REPAIR 2020 | Region IV-B | Palawan | 111070 | Maranan Elementary School | NARRA | 2 | 1 | 2 | Repair of Classrooms | 625732 | 1 | 625731.56 | COMPLETED | 1 | 2021-02-28 | 2021-02-25 | 2020-09-005 | 2020-09-005 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | A.A. Padua Design & Const.
1495 | REPAIR 2020 | Region IV-B | Palawan | 111071 | Mariwara ES | NARRA | 2 | 1 | 2 | Repair of Classrooms | 724068 | 1 | 724067.53 | COMPLETED | 1 | 2021-02-28 | 2021-02-25 | 2020-09-005 | 2020-09-005 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | A.A. Padua Design & Const.
1496 | REPAIR 2020 | Region IV-B | Palawan | 111090 | Alfonzo XIII ES | Quezon | 2 | 1 | 6 | Repair of Classrooms | 1944224 | 1 | 1944223.5995 | COMPLETED | 1 | 2021-02-28 | 2021-02-12 | 2020-09-006 | 2020-09-006 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | E.M. Abin Trdg. & Const.
1497 | REPAIR 2020 | Region IV-B | Palawan | 304876 | Labog National High School | SOFRONIO ESPAÑOLA | 2 | 1 | 3 | Repair of Classrooms | 1287265 | 1 | 1287264.797 | COMPLETED | 1 | 2021-02-28 | 2021-02-12 | 2020-09-006 | 2020-09-006 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | E.M. Abin Trdg. & Const.
1498 | REPAIR 2020 | Region IV-B | Palawan | 110725 | Isaub ES | ABORLAN | 3 | 1 | 4 | Repair of Classrooms | 1109401 | 1 | 1109400.383 | COMPLETED | 1 | 2021-02-28 | 2021-02-12 | 2020-09-006 | 2020-09-006 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | E.M. Abin Trdg. & Const.
1499 | REPAIR 2020 | Region IV-B | Palawan | 110731 | Plaridel ES | ABORLAN | 3 | 1 | 5 | Repair of Classrooms | 1527056 | 1 | 1527055.0386 | COMPLETED | 1 | 2021-02-28 | 2021-02-12 | 2020-09-006 | 2020-09-006 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | E.M. Abin Trdg. & Const.
1500 | REPAIR 2020 | Region IV-B | Puerto Princesa City | 111506 | Bacungan Elementary School | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1815720 | 1 | 1815719.8 | COMPLETED | 1 | 2021-03-08 | 2020-12-22 |  |  | 2019-11-26 | 2020-12-03 | 2019-12-16 | 2020-03-02 | 2020-09-28 | Don Virgilio Builders
1501 | REPAIR 2020 | Region IV-B | Puerto Princesa City | 301783 | Irawan NHS | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 12 | Repair of Classrooms | 5658033 | 1 | 5658032.14 | COMPLETED | 1 | 2021-03-08 | 2021-01-07 |  |  | 2019-11-26 | 2020-12-03 | 2019-12-16 | 2020-03-02 | 2020-09-28 | Don Virgilio Builders
1502 | REPAIR 2020 | Region IV-B | Puerto Princesa City | 111502 | Valentin Macasaet MES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 11 | Repair of Classrooms | 4926275 | 1 | 4926274.03 | COMPLETED | 1 | 2021-03-08 | 2020-12-10 |  |  | 2019-11-26 | 2020-12-03 | 2019-12-16 | 2020-03-02 | 2020-09-28 | Don Virgilio Builders
1503 | REPAIR 2020 | Region IV-B | Romblon | 111267 | Balogo Elementary School | BANTON | 0 | 1 | 1 | Repair of Classroom | 551971 | 1 | 551970.96 | COMPLETED | 1 | 2021-04-08 | 2022-08-04 |  | SBP-2020-001 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-11-03 | RMR CONSTRUCTION AND TRADING
1504 | REPAIR 2020 | Region IV-B | Romblon | 301750 | Banton NHS | BANTON | 0 | 1 | 10 | Repair of Classrooms | 1822330 | 1 | 1822329.84 | COMPLETED | 1 | 2021-04-08 | 2022-08-04 |  | SBP-2020-001 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-11-03 | RMR CONSTRUCTION AND TRADING
1505 | REPAIR 2020 | Region IV-B | Romblon | 111288 | Haguimit Cult. Min. Sch. | CAJIDIOCAN | 0 | 1 | 4 | Repair of Classrooms | 2338840 | 1 | 2338839.42 | COMPLETED | 1 | 2021-04-08 | 2022-08-04 |  | SBP-2020-001 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-11-03 | RMR CONSTRUCTION AND TRADING
1506 | REPAIR 2020 | Region IV-B | Romblon | 111298 | Agbatang ES | CONCEPCION | 0 | 1 | 4 | Repair of Classrooms | 617419 | 1 | 617418.47 | COMPLETED | 1 | 2021-04-08 | 2022-04-26 |  | SBP-2020-002 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-11-03 | NMDC CONSTRUCTION CORPORATION
1507 | REPAIR 2020 | Region IV-B | Romblon | 301756 | Concepcion NHS (Main) | CONCEPCION | 0 | 1 | 19 | Repair of Classrooms | 6559615 | 1 | 6559614.3 | COMPLETED | 1 | 2021-04-08 | 2022-04-26 |  | SBP-2020-002 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-11-03 | NMDC CONSTRUCTION CORPORATION
1508 | REPAIR 2020 | Region IV-B | Romblon | 309206 | Concepcion NHS Annex (Bakhawan) | CONCEPCION | 0 | 1 | 6 | Repair of Classrooms | 1945800 | 1 | 1945799.38 | COMPLETED | 1 | 2021-04-08 | 2022-04-26 |  | SBP-2020-002 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-11-03 | NMDC CONSTRUCTION CORPORATION
1509 | REPAIR 2020 | Region IV-B | Romblon | 111352 | FERROL CES | FERROL | 0 | 1 | 15 | Repair of Classrooms | 5343473 | 1 | 5343472.9 | COMPLETED | 1 | 2021-04-04 | 2021-08-05 |  | SBP-2020-004 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-10-30 | RG FLORENTINO CONSTRUCTION AND TRADING
1510 | REPAIR 2020 | Region IV-B | Romblon | 111339 | LIBERTAD ES | ODIONGAN | 0 | 1 | 15 | Repair of Classrooms | 3448533 | 1 | 3448532.75 | COMPLETED | 1 | 2021-04-04 | 2021-08-05 |  | SBP-2020-003 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-10-30 | RG FLORENTINO CONSTRUCTION AND TRADING
1511 | REPAIR 2020 | Region IV-B | Romblon | 111355 | MAYHA ES | ODIONGAN | 0 | 1 | 10 | Repair of Classrooms | 3019280 | 1 | 3019279.02 | COMPLETED | 1 | 2021-04-04 | 2021-08-05 |  | SBP-2020-003 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-10-30 | RG FLORENTINO CONSTRUCTION AND TRADING
1512 | REPAIR 2020 | Region IV-B | Romblon | 111381 | Li-O ES | ROMBLON (Capital) | 0 | 1 | 11 | Repair of Classrooms | 2620341 | 1 | 2620340.11 | COMPLETED | 1 | 2021-04-03 | 2021-05-04 |  | SBP-2020-005 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-10-29 | CSR CONSTRUCTION & SUPPLY
1513 | REPAIR 2020 | Region IV-B | Romblon | 111389 | San Jose ES | ROMBLON (Capital) | 0 | 1 | 11 | Repair of Classrooms | 2605071 | 1 | 2605070.54 | COMPLETED | 1 | 2021-04-03 | 2021-05-04 |  | SBP-2020-005 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-10-29 | CSR CONSTRUCTION & SUPPLY
1514 | REPAIR 2020 | Region IV-B | Romblon | 111428 | Ben G. Talamisan ES | SAN ANDRES | 0 | 1 | 7 | Repair of Classrooms | 2804039 | 1 | 2804038.45 | COMPLETED | 1 | 2021-04-04 | 2021-08-05 |  | SBP-2020-004 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-10-30
3229 | REPAIR 2021 | Region IV-B | Calapan City | 111551 | Balingayan Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2474624.27 | 1 | 2444928.78 | COMPLETED | 1 | 2022-02-17 | 2022-02-03 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION & DEVELOPER | CLUSTER 2
3230 | REPAIR 2021 | Region IV-B | Calapan City | 111554 | Bayanan II Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | Repair of Classroom | 2877595.37 | 1 | 2843064.23 | COMPLETED | 1 | 2022-02-17 | 2022-02-03 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION & DEVELOPER | CLUSTER 2
3231 | REPAIR 2021 | Region IV-B | Calapan City | 111538 | Ibaba Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | Repair of Classrooms | 3439014.07 | 1 | 3397745.9 | COMPLETED | 1 | 2022-02-17 | 2022-02-03 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION & DEVELOPER | CLUSTER 2
3232 | REPAIR 2021 | Region IV-B | Calapan City | 111541 | Maidlang Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | Repair of Classrooms | 3640206.39 | 1 | 3626200 | COMPLETED | 1 | 2022-01-18 | 2022-01-18 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | F.S. SUGAY CONSTRUCTION & SUPPLIES | CLUSTER 3
3233 | REPAIR 2021 | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 33 | Repair of Classrooms | 13728793.6 | 1 | 13600795.33 | COMPLETED | 1 | 2022-08-22 | 2022-08-23 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | KARANGYAN BUILDERS & TRADERS
3234 | REPAIR 2021 | Region IV-B | Calapan City | 111544 | Parang Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | Repair of Classrooms | 3019943.63 | 1 | 3003900 | COMPLETED | 1 | 2022-01-18 | 2022-01-18 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | F.S. SUGAY CONSTRUCTION & SUPPLIES | CLUSTER 3
3235 | REPAIR 2021 | Region IV-B | Calapan City | 111580 | Teresa C. Montellano Memorial School | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | Repair of Classrooms | 2359103.61 | 1 | 2328069.67 | COMPLETED | 1 | 2022-08-22 | 2021-12-01 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | KARANGYAN BUILDERS & TRADERS | CLUSTER 1
3236 | REPAIR 2021 | Region IV-B | Marinduque | 109889 | Bantay ES | BOAC (Capital) | 0 | 1 | 1 | Repair of Classroom | 623119.83 | 1 | 618201.17 | COMPLETED | 1 | 2022-01-18 |  |  | 2021-09-015 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING
3237 | REPAIR 2021 | Region IV-B | Marinduque | 109925 | Banot-Mahunig ES | GASAN | 0 | 1 | 5 | Repair of Classrooms | 2246556.4 | 1 | 2198750.75 | COMPLETED | 1 | 2022-01-18 |  |  | 2021-09-015 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING
3238 | REPAIR 2021 | Region IV-B | Marinduque | 308804 | Paciano A. Sena Mem. HS (Tabionan NHS) | GASAN | 0 | 1 | 6 | Repair of Classrooms | 1178249.53 | 1 | 1152608.32 | COMPLETED | 1 | 2022-01-18 |  |  | 2021-09-015 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING
3239 | REPAIR 2021 | Region IV-B | Marinduque | 301567 | Tiguion National High School | GASAN | 0 | 1 | 3 | Repair of Classrooms | 1608932.66 | 1 | 1400998.39 | COMPLETED | 1 | 2022-01-18 |  |  | 2021-09-015 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING
3240 | REPAIR 2021 | Region IV-B | Marinduque | 301530 | Balanacan NHS | MOGPOG | 0 | 1 | 10 | Repair of Classrooms | 3044390.9 | 1 | 2949869.21 | COMPLETED | 1 | 2021-12-28 |  |  | 2021-09-016 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING
3241 | REPAIR 2021 | Region IV-B | Marinduque | 109941 | Bocboc ES | MOGPOG | 0 | 1 | 4 | Repair of Classrooms | 1776895.7 | 1 | 1753309.11 | COMPLETED | 1 | 2021-12-28 |  |  | 2021-09-016 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING
3242 | REPAIR 2021 | Region IV-B | Marinduque | 109952 | Mogpog Central School | MOGPOG | 0 | 1 | 4 | Repair of Classrooms | 1883818.07 | 1 | 1858671.03 | COMPLETED | 1 | 2021-12-28 |  |  | 2021-09-016 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING
3243 | REPAIR 2021 | Region IV-B | Marinduque | 308803 | Puting Buhangin NHS | MOGPOG | 0 | 1 | 1 | Repair of Classroom | 682937.11 | 1 | 677356.29 | COMPLETED | 1 | 2021-12-28 |  |  | 2021-09-016 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING
3244 | REPAIR 2021 | Region IV-B | Marinduque | 110006 | Mongpong Elementary School | SANTA CRUZ | 0 | 1 | 4 | Repair of Classrooms | 1969331.88 | 1 | 1926298.51 | COMPLETED | 1 | 2022-01-18 |  |  | 2021-09-013 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-06 | 2021-09-23 | GS MOTAR COSTRUCTION BUILDERS AND TRADING
3245 | REPAIR 2021 | Region IV-B | Marinduque | 301551 | Malibago National High School | TORRIJOS | 0 | 1 | 2 | Repair of Classrooms | 998885.26 | 1 | 998885.26 | COMPLETED | 1 | 2022-01-18 |  |  | 2021-09-013 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-06 | 2021-09-23 | GS MOTAR COSTRUCTION BUILDERS AND TRADING
3246 | REPAIR 2021 | Region IV-B | Marinduque | 110032 | Sibuyao ES | TORRIJOS | 0 | 1 | 1 | Repair of Classroom | 672976.6 | 1 | 663668.29 | COMPLETED | 1 | 2022-01-18 |  |  | 2021-09-013 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-06 | 2021-09-23 | GS MOTAR COSTRUCTION BUILDERS AND TRADING
3247 | REPAIR 2021 | Region IV-B | Occidental Mindoro | 110056 | Lumangbayan ES (Abra) | ABRA DE ILOG | 0 | 1 | 4 | Repair of Classrooms | 1977857 | 1 |  | COMPLETED | 1 | 2021-11-10 | December 17.2021 |  |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development
3248 | REPAIR 2021 | Region IV-B | Occidental Mindoro | 110070 | San Vicente ES | ABRA DE ILOG | 0 | 1 | 6 | Repair of Classrooms | 2928582.16 | 1 |  | COMPLETED | 1 | 2021-11-10 | December 17.2021 |  |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development
3249 | REPAIR 2021 | Region IV-B | Occidental Mindoro | 301574 | CALINTAAN NATIONAL HIGH SCHOOL | CALINTAAN | 0 | 1 | 10 | Repair of Classrooms | 4849583.8 | 1 |  | COMPLETED | 1 | 2021-11-10 | December 17.2021 |  |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development
3250 | REPAIR 2021 | Region IV-B | Occidental Mindoro | 301590 | Magsaysay NHS - Purnaga Annex | MAGSAYSAY | 0 | 1 | 12 | Repair of Classrooms | 5805954.86 | 1 |  | COMPLETED | 1 | 2021-11-10 | December 17.2021 |  |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development
3251 | REPAIR 2021 | Region IV-B | Occidental Mindoro | 110169 | Mamburao CS | MAMBURAO (Capital) | 0 | 1 | 7 | Repair of Classrooms | 3417380.11 | 1 |  | COMPLETED | 1 | 2021-11-10 | December 17.2021 |  |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development
3252 | REPAIR 2021 | Region IV-B | Occidental Mindoro | 110301 | Mabini I ES | SAN JOSE | 0 | 1 | 4 | Repair of Classrooms | 1985850.92 | 1 |  | COMPLETED | 1 | 2021-11-10 | December 17.2021 |  |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development
3253 | REPAIR 2021 | Region IV-B | Occidental Mindoro | 110272 | San Isidro ES | SAN JOSE | 0 | 1 | 8 | Repair of Classrooms | 3895006.17 | 1 |  | COMPLETED | 1 | 2021-11-10 | December 17.2021 |  |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development
3254 | REPAIR 2021 | Region IV-B | Occidental Mindoro | 110162 | Cuarenta ES | SANTA CRUZ | 0 | 1 | 6 | Repair of Classrooms | 2940428.55 | 1 |  | COMPLETED | 1 | 2021-11-10 | December 17.2021 |  |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development
3255 | REPAIR 2021 | Region IV-B | Occidental Mindoro | 110171 | Mulawin ES | SANTA CRUZ | 0 | 1 | 5 | Repair of Classrooms | 2453219.58 | 1 |  | COMPLETED | 1 | 2021-11-10 | December 17.2021 |  |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development
3256 | REPAIR 2021 | Region IV-B | Oriental Mindoro | 110325 | Burbuli ES | BACO | 1 | 1 | 4 | Repair of Classrooms | 1556187.91 | 1 | 1541042.35 | COMPLETED | 1 | 2021-11-02 | 2021-10-26 | REPAIR 2021-R IVB-Oriental Mindoro-003 | 004-2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-06 | 2021-07-22 | ETVR Trading and Construction
3257 | REPAIR 2021 | Region IV-B | Oriental Mindoro | 110328 | Dulangan II ES | BACO | 1 | 1 | 15 | Repair of Classroom | 5627150.71 | 1 | 5581256.7 | COMPLETED | 1 | 2021-12-30 | 2021-12-13 | REPAIR 2021-R IVB-Oriental Mindoro-008 | 006-2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-06 | 2021-07-22 | CMSEL Constuction and Developer
3258 | REPAIR 2021 | Region IV-B | Oriental Mindoro | 110517 | Mabini ES | NAUJAN | 1 | 1 | 5 | Repair of Classrooms | 1846256.38 | 1 | 1833888 | COMPLETED | 1 | 2022-03-29 | 2022-03-11 | REPAIR 2021-R IVB-Oriental Mindoro-005 | 005-2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-12-06 | 2021-12-22 | DK Construction | For termination
3259 | REPAIR 2021 | Region IV-B | Oriental Mindoro | 110665 | Batong Dalig ES | SOCORRO | 1 | 1 | 6 | Repair of Classrooms | 2257389.82 | 1 | 2198888.88 | COMPLETED | 1 | 2021-12-12 | 2021-11-14 | REPAIR 2021-R IVB-Oriental Mindoro-006 | 016-2021 | 2021-07-06 | 2021-07-14 | 2021-07-27 | 2021-08-11 | Sept. 03, 2021 | GDB Masterbuilders Corporation
3260 | REPAIR 2021 | Region IV-B | Oriental Mindoro | 110688 | Antonino ES | VICTORIA | 1 | 1 | 7 | Repair of Classrooms | 2291994.35 | 1 | 2273301.57 | COMPLETED | 1 | 2021-10-30 | 2021-10-26 | REPAIR 2021-R IVB-Oriental Mindoro-001 | 003-2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-06 | 2021-07-22 | DK Construction
3261 | REPAIR 2021 | Region IV-B | Palawan | 301720 | Panlaitan National High School | BUSUANGA | 1 | 1 | 4 | Repair of Classrooms | 2859559.56 | 1 | 2076383.88 | COMPLETED | 1 | 2022-02-01 | 2022-02-02 | 2021-08-001 | 2021-08-001 | 2021-07-13 | 2021-07-21 | 2021-08-02 | 2021-09-17 | 2021-09-27 | Maryknol Builders and Supply
3262 | REPAIR 2021 | Region IV-B | Palawan | 111190 | IRAWAN ELEMENTARY SCHOOL | SAN VICENTE | 1 | 1 | 4 | Repair of Classrooms | 2861892.98 | 1 | 2027037.8 | COMPLETED | 1 | 2022-02-01 | 2022-01-31 | 2021-09-002 | 2021-09-002 | 2021-07-13 | 2021-07-21 | 2021-08-02 | 2021-09-17 | 2021-09-27 | Maryknol Builders and Supply
3263 | REPAIR 2021 | Region IV-B | Palawan | 111123 | Salongsong Elementary School | RIZAL (MARCOS) | 2 | 1 | 4 | Repair of Classrooms | 2747499.38 | 1 | 2018792.85 | COMPLETED | 1 | 2022-02-01 | 2022-01-25 | 2021-09-003 | 2021-09-003 | 2021-07-13 | 2021-07-21 | 2021-08-02 | 2021-09-17 | 2021-09-27 | Maryknol Builders and Supply
3264 | REPAIR 2021 | Region IV-B | Puerto Princesa City | 301791 | Pto. Princesa City Nat. Sci. HS | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 6 | Repair of Classrooms | 3192370.19 | 1 | 2155813.35 | COMPLETED | 1 | 2021-12-15 | 2021-11-09 |  | Infra 2021-02 | 2021-06-03 | 2021-06-22 | 2021-07-05 | August 5, 2021 | 2021-08-09 | Ian Jason Construction and Supply
3265 | REPAIR 2021 | Region IV-B | Puerto Princesa City | 111494 | Sta. Lourdes Elementary School | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 2 | Repair of Classrooms | 1098015.32 | 1 | 877783.49 | COMPLETED | 1 | 2021-12-15 | 2021-11-09 |  | Infra 2021-02 | 2021-06-03 | 2021-06-22 | 2021-07-05 | August 5, 2021 | 2021-08-09 | Ian Jason Construction and Supply
3266 | REPAIR 2021 | Region IV-B | Romblon | 111353 | Hinag-oman ES | FERROL | 0 | 1 | 14 | Repair of Classrooms | 6181753.01 | 1 | 5431177.85 | COMPLETED | 1 | 2022-03-21 | 2022-06-15 |  | INF-SBR-2021-01 | 2021-07-20 | 2021-07-27 | 2021-08-08 | 2021-11-09 | 2021-12-14 | RMR CONSTRUCTION AND TRADING
3267 | REPAIR 2021 | Region IV-B | Romblon | 111345 | Tumingad ES | ODIONGAN | 0 | 1 | 12 | Repair of Classrooms | 5533793.95 | 1 | 4299005.83 | COMPLETED | 1 | 2022-03-26 | 2022-04-16 |  | INF-SBR-2021-02 | 2021-07-20 | 2021-07-27 | 2021-08-08 | 2021-11-09 | 2021-12-14 | TRIPLE PEAK MOUNTAIN CONSTRUCTION AND SUPPLY
3268 | REPAIR 2021 | Region IV-B | Romblon | 301749 | Esteban Madrona National High School | SAN AGUSTIN | 0 | 1 | 19 | Repair of Classrooms | 5106874 | 1 | 4582963.83 | COMPLETED | 1 | 2022-10-31 |  |  | INF-SBR-2021-03 | 2021-07-20 | 2021-07-27 | 2021-08-08 | 2021-11-09 | 2021-12-14 | RG FLORENTINO CONSTRUCTION AND TRADING INC.
3984 | REPAIR 2022 | Region IV-B | Occidental Mindoro | 110094 | Agkawayan ES | LOOC | 0 | 1 | 5 | Repair of Classrooms | 2576920.34 | 1 |  | COMPLETED | 1
3985 | REPAIR 2022 | Region IV-B | Occidental Mindoro | 110123 | Caguray ES | MAGSAYSAY | 0 | 1 | 6 | Repair of Classrooms | 2942555.87 | 1 |  | COMPLETED | 1
3986 | REPAIR 2022 | Region IV-B | Palawan | 110741 | Algeciras Elementry School | AGUTAYA | 1 | 1 | 4 | Repair of Classrooms | 2642335.47 | 1 | 2638211.6921 | COMPLETED | 1 | October 2022 |  | 2022-02-002_INFRA | 2022-02-002_INFRA-LOT 1 | 2022-02-16 | 2022-02-23 | 2022-03-08 | 2022-03-14 | 2022-06-09 | MARYKNOLL BUILDERS AMD SUPPLY
3987 | REPAIR 2022 | Region IV-B | Palawan | 110966 | Cawili Elementary School | CAGAYANCILLO | 1 | 1 | 2 | Repair of Classrooms | 1590148.61 | 1 | 1587192.7184 | COMPLETED | 1 | October 2022 | 2022-08-31 | 2022-02-002_INFRA | 2022-02-002_INFRA-LOT 2 | 2022-02-16 | 2022-02-23 | 2022-03-08 | 2022-03-14 | 2022-06-09 | MARYKNOLL BUILDERS AMD SUPPLY
3988 | REPAIR 2022 | Region IV-B | Palawan | 110931 | Cabunlawan Elementary School | LINAPACAN | 1 | 1 | 3 | Repair of Classrooms | 2108116.42 | 1 | 2104826.3811 | COMPLETED | 1 | October 2022 | 2022-06-16 | 2022-02-002_INFRA | 2022-02-002_INFRA-LOT 1 | 2022-02-16 | 2022-02-23 | 2022-03-08 | 2022-03-14 | 2022-06-09 | MARYKNOLL BUILDERS AMD SUPPLY
3989 | REPAIR 2022 | Region IV-B | Palawan | 111051 | Rizal North Elementary School | MAGSAYSAY | 1 | 1 | 2 | Repair of Classrooms | 1657115 | 1 | 1654528.8146 | COMPLETED | 1 | October 2022 |  | 2022-02-002_INFRA | 2022-02-002_INFRA-LOT 1 | 2022-02-16 | 2022-02-23 | 2022-03-08 | 2022-03-14 | 2022-06-09 | MARYKNOLL BUILDERS AMD SUPPLY
3990 | REPAIR 2022 | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1 | 1 | 8 | Repair of Classrooms | 3789443.32 | 1 | 3682524.8033 | COMPLETED | 1 | October 2022 |  | 2022-02-002_INFRA | 2022-02-002_INFRA-LOT 2 | 2022-02-16 | 2022-02-23 | 2022-03-08 | 2022-03-14 | 2022-06-09 | MARYKNOLL BUILDERS AMD SUPPLY
3991 | REPAIR 2022 | Region IV-B | Romblon | 111262 | Gui-ob Elementary School | ALCANTARA | 0 | 1 | 3 | Repair of Classrooms | 1521993.82 | 1 |  | COMPLETED | 1 |  |  |  | INF-SBR-2022-01 | 2022-07-29 | 2022-08-10 | 2022-08-23 | 2022-11-21 | 2022-12-20 | RMR CONSTRUCTION AND TRADING
3992 | REPAIR 2022 | Region IV-B | Romblon | 111270 | Libtong ES | BANTON | 0 | 1 | 2 | Repair of Classrooms | 1059276.74 | 1 |  | COMPLETED | 1 |  |  |  | INF-SBR-2022-02 | 2022-07-29 | 2022-08-10 | 2022-08-23 | 2022-11-21 | 2022-12-20 | RMR CONSTRUCTION AND TRADING
3993 | REPAIR 2022 | Region IV-B | Romblon | 171003 | Cabibihan ES | CALATRAVA | 0 | 1 | 3 | Repair of Classrooms | 1590953 | 1 |  | COMPLETED | 1 |  |  |  | INF-SBR-2022-07 | 2022-07-29 | 2022-08-10 | 2022-08-23 | 2022-11-21 | 2022-12-20 | TRIPLE PEAK MOUNTAIN CONSTRUCTION AND SUPPLY | Tawid dagat through maliit lang na bangka, hindi pa matawid, parati masama ang panahon, contractor had requested letter for time suspension. we attempted twice to reach the school but unfortunately palaging failure
3994 | REPAIR 2022 | Region IV-B | Romblon | 111308 | Ambulong ES | CORCUERA | 0 | 1 | 2 | Repair of Classrooms | 1060635 | 1 |  | COMPLETED | 1 |  |  |  | INF-SBR-2022-06 | 2022-07-29 | 2022-08-10 | 2022-08-23 | 2022-11-21 | 2022-12-20 | RMR CONSTRUCTION AND TRADING
3995 | REPAIR 2022 | Region IV-B | Romblon | 111351 | Claro M. Recto ES | FERROL | 0 | 1 | 3 | Repair of Classrooms | 1060635 | 1 |  | COMPLETED | 1 |  |  |  | INF-SBR-2022-03 | 2022-07-29 | 2022-08-10 | 2022-08-23 | 2022-11-21 | 2022-12-20 | TRIPLE PEAK MOUNTAIN CONSTRUCTION AND SUPPLY
3996 | REPAIR 2022 | Region IV-B | Romblon | 111290 | Jao-Asan ES | MAGDIWANG | 0 | 1 | 4 | Repair of Classrooms | 2120799.3 | 1 |  | COMPLETED | 1 |  |  |  | INF-SBR-2022-04 | 2022-07-29 | 2022-08-10 | 2022-08-23 |  |  |  | 2ND FAILURE OF BIDDING - FOR NEGOTIATED PROCUREMENT
3997 | REPAIR 2022 | Region IV-B | Romblon | 111394 | Bonga ES | SANTA MARIA (IMELDA) | 0 | 1 | 3 | Repair of Classrooms | 1590953 | 1 |  | COMPLETED | 1 |  |  |  | INF-SBR-2022-05 | 2022-07-29 | 2022-08-10 | 2022-08-23 | 2022-11-21 | 2022-12-20 | TRIPLE PEAK MOUNTAIN CONSTRUCTION AND SUPPLY
4645 | REPAIR 2023 | Region IV-B | Occidental Mindoro | 110098 | Bulacan ES | LOOC | Lone | 1 | 2 | Repair of Classrooms | 1950000 | DPWH (Batch 1) |  | COMPLETED | 1
4646 | REPAIR 2023 | Region IV-B | Occidental Mindoro | 110095 | Tabao ES (Ambil ES-Tabao Site) | LOOC | Lone | 1 | 2 | Repair of Classrooms | 2250000 | DPWH (Batch 1) | 0 | COMPLETED | 1
4647 | REPAIR 2023 | Region IV-B | Oriental Mindoro | 110351 | Bansud CS | BANSUD | 2nd | 1 | 8 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4771925.35 | COMPLETED | 1 | 2024-07-05 | 2024-07-05 | P00775756NP | 23EI0099 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | Lumel Glenn Construction
4648 | REPAIR 2023 | Region IV-B | Oriental Mindoro | 110370 | Bagong Bayan CS | BONGABONG | 2nd | 1 | 8 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4767177.72 | COMPLETED | 1 | 2024-07-05 | 2024-07-05 | P00775760NP | 23EI0102 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | Archidus Development Corporation
4649 | REPAIR 2023 | Region IV-B | Oriental Mindoro | 110457 | Melecio D. Cantos ES | GLORIA | 2nd | 1 | 8 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4757447.18 | COMPLETED | 1 | 2024-07-05 | 2024-07-05 | P00775761NP | 23EI0105 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | LED Reyes Constructio (LCR) OPC
4650 | REPAIR 2023 | Region IV-B | Oriental Mindoro | 300412 | Don Pedro High School | MANSALAY | 2nd | 1 | 6 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4771925.35 | COMPLETED | 1 | 2024-07-05 | 2024-07-05 | P00775762NP | 23EI0103 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | Lumel Glenn Construction
4651 | REPAIR 2023 | Region IV-B | Oriental Mindoro | 110557 | Doña Asuncion Reyes MES | PINAMALAYAN | 2nd | 1 | 8 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4757620.02 | COMPLETED | 1 | 2024-07-05 | 2024-07-05 | P00775757NP | 23EI0101 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | LED Reyes Constructio (LCR) OPC
4652 | REPAIR 2023 | Region IV-B | Oriental Mindoro | 110558 | Juan Morente, Sr. Mem. Pilot Sch. | PINAMALAYAN | 2nd | 1 | 8 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4778986.54 | COMPLETED | 1 | 2024-07-05 | 2024-07-05 | P00775758NP | 23EI0098 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | RM Sescar Enterprises
4653 | REPAIR 2023 | Region IV-B | Oriental Mindoro | 110574 | M. Ansaldo Sr. MES | PINAMALAYAN | 2nd | 1 | 8 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4787243.96 | COMPLETED | 1 | 2024-07-05 | 2024-07-05 | P00775759NP | 23EI0104 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | D.M. Almero Enterprises
4654 | REPAIR 2023 | Region IV-B | Oriental Mindoro | 110644 | San Mariano ES | ROXAS | 2nd | 1 | 18 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4822773.34 | COMPLETED | 1 | 2025-02-17 | 2025-02-17 | P007757563NP | 24EI0123 | 2024-03-20 | 2024-03-27 | 2024-04-11 | 2024-04-23 | 2024-08-19 | Lewis Gjann Construction | with modification - from 18 CL to 8 CL physical target
4655 | REPAIR 2023 | Region IV-B | Palawan | 309138 | Araceli Plainview National High School | ARACELI | 1st | 1 | 1 | Repair of Classrooms | 833858.17 | DEPED (Batch 1) |  | COMPLETED | 1 |  |  | 2023-11-002_INFRA | 2023-11-002_INFRA | 2023-11-17 | - | 2023-11-28 | 2024-01-17 | 2024-05-09 | Futuristic Trading and Construction
4656 | REPAIR 2023 | Region IV-B | Palawan | 110751 | Bacao Elementary School | DUMARAN | 1st | 1 | 4 | Repair of Classroom | 556936.16 | DEPED (Batch 2) | 531665.75 | COMPLETED | 1 | 2024-12-24 | 2024-09-19 | 2024-04-002_INFRA | 45440 | 2024-06-04 | 2024-06-18 | 2024-07-19 | 2024-08-14 | 2024-08-19 | RBM2 Construction
4657 | REPAIR 2023 | Region IV-B | Palawan | 110751 | Bacao ES | Dumaran | 1st | 1 | 4 | Repair of Classrooms | 2922012 | DPWH (Batch 1) | 2805465.86 | COMPLETED | 1 | 2024-02-20 | 2024-02-16 | P00775137NP | 23EE0126 | 2023-08-29 | 2023-09-08 | 2023-09-19 | 2023-09-25 | 2023-04-28 | Bats Construction Services
4658 | REPAIR 2023 | Region IV-B | Palawan | 309109 | Bacao National High School (Dumaran NHS - Bacao NHS) | DUMARAN | 1st | 1 | 4 | Repair of Classrooms | 3786972.66 | DPWH (Batch 2) | 3615565.98 | COMPLETED | 1 | 2024-04-12 | 2024-04-05 | P00775138NP | 23EE0124 | 2023-09-29 | 2023-10-09 | 2023-10-20 | 2023-11-07 | 2024-01-08 | Maryknoll Builders and Supply
4659 | REPAIR 2023 | Region IV-B | Palawan | 309109 | Bacao NHS | Dumaran | 1st | 1 | 18 | Repair of Classrooms | 6557856.34 | DPWH (Batch 1) | 6296307.04 | COMPLETED | 1 | 2024-04-12 | 2024-04-05 | P00775138NP | 23EE0124 | 2023-08-29 | 2023-09-08 | 2023-09-19 | 2023-09-25 | 2023-04-28 | BJ-RAM Const. Services
4660 | REPAIR 2023 | Region IV-B | Palawan | 111136 | Andres Soriano Memorial Elementary School | ROXAS | 1st | 1 | 33 | Repair of Classrooms | 9793897.14 | DPWH (Batch 2) | 9434852.5 | COMPLETED | 1 | 2024-05-12 | 2024-09-20 | P00775765NP | 23EE0134 | 2023-09-29 | 2023-10-09 | 2023-10-20 | 2023-11-07 | 2024-01-08 | E.V.Villaos Trdg. & Const.
4661 | REPAIR 2023 | Region IV-B | Palawan | 111136 | Andres Soriano Memorial ES | Roxas | 1st | 1 | 27 | Repair of Classrooms | 13879004.19 | DPWH (Batch 1) | 13353149.63 | COMPLETED | 1 | 2024-06-28 | 2024-07-22 | P00775139NP | 23EE0125 | 2023-08-29 | 2023-09-08 | 2023-09-19 | 2023-09-25 | 2023-04-28 | E.M.Abin Trading & Const.
4662 | REPAIR 2023 | Region IV-B | Palawan | 170540 | Pedro Baquiao Memorial Elementary School | ROXAS | 1st | 1 | 4 | Repair of Classrooms | 3663871.54 | DPWH (Batch 2) | 3266926.49 | COMPLETED | 1 | 2024-04-04 | 2024-04-04 | P00775766NP | 23EE0132 | 2023-09-29 | 2023-10-09 | 2023-10-20 | 2023-12-13 | 2024-01-30 | AFG Construction Corporation
4663 | REPAIR 2023 | Region IV-B | Palawan | 170540 | Pedro Baquiao Memorial ES | Roxas | 1st | 1 | 4 | Repair of Classrooms | 1690974.06 | DPWH (Batch 1) | 1626506.9 | COMPLETED | 1 | 2023-12-02 | 2023-12-02 | P00775140NP | 23EE0127 | 2023-08-29 | 2023-09-08 | 2023-09-19 | 2023-09-25 | 2023-04-28 | New Space Trdg & Const. Corp.
4664 | REPAIR 2023 | Region IV-B | Palawan | 301660 | Alimanguan National High School | SAN VICENTE | 1st | 1 | 7 | Repair of Classroom | 491022.98 | DEPED (Batch 2) | 471660.02 | COMPLETED | 1 | 2024-12-24 | 2024-09-23 | 2024-04-002_INFRA | 45440 | 2024-06-04 | 2024-06-18 | 2024-07-19 | 2024-08-14 | 2024-08-19 | RBM2 Construction
4665 | REPAIR 2023 | Region IV-B | Palawan | 301660 | Alimanguan National High School | SAN VICENTE | 1st | 1 | 7 | Repair of Classrooms | 6071208.02 | DPWH (Batch 1) | 5777399.72 | COMPLETED | 1 | 2024-01-11 | 2024-08-30 | P00775141NP | 23EE0128 | 2023-08-29 | 2023-09-08 | 2023-09-19 | 2023-09-25 | 2023-04-28 | E.V.Villaos Trdg. & Const.
4666 | REPAIR 2023 | Region IV-B | Puerto Princesa City | 301787 | Babuyan NHS | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 17 | Repair of Classrooms | 13700000 | DPWH (Batch 1) | 0 | COMPLETED | 1
4667 | REPAIR 2023 | Region IV-B | Puerto Princesa City | 111509 | Binduyan ES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 6 | Repair of Classrooms | 4300000 | DPWH (Batch 1) | 0 | COMPLETED | 1
4668 | REPAIR 2023 | Region IV-B | Puerto Princesa City | 305540 | Buenavista HS | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 4 | Repair of Classrooms | 4000000 | DPWH (Batch 1) | 0 | COMPLETED | 1
4669 | REPAIR 2023 | Region IV-B | Puerto Princesa City | 111533 | Tagnipa ES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 2 | Repair of Classrooms | 1900000 | DPWH (Batch 1) | 0 | COMPLETED | 1
5399 | REPAIR 2024 | Region IV-B | Calapan City | 111536 | Calapan Central School | CITY OF CALAPAN (Capital) | 1st | 1 | 10 | Repair of Classrooms | 8461616.16 | 1 | 7376203.963 | Ongoing | 0.7 | 2025-08-20 |  | PBD-2025-01-BEFF-01 | 2025-027 | 2025-01-22 | 2025-01-20 | 2025-02-12 | 2025-02-26 | 2025-03-27 | MARJO CONSTRUCTION AND BUILDERS CORPORATION | with approved realignment scope of works from 7 classrooms to 10classrooms
5400 | REPAIR 2024 | Region IV-B | Occidental Mindoro | 308904 | Manoot National High School | RIZAL | Lone | 1 | 8 | Repair of Classrooms | 4828311.9 | 1 |  | COMPLETED | 1 |  | 2025-01-21 | DepEd-OccMdo-2024-07 |  | 2024-08-07 | 2024-08-15 | 2024-08-27 | 2024-09-02 | 2024-10-21 | Hawkstow Construction and Development
5401 | REPAIR 2024 | Region IV-B | Occidental Mindoro | 110256 | Batasan ES | SAN JOSE | Lone | 1 | 8 | Repair of Classrooms | 5050505.05 | 1 |  | COMPLETED | 1 |  |  | DepEd-OccMdo-2024-07 |  | 2024-08-07 | 2024-08-15 | 2024-08-27 | 2024-09-02 | 2024-10-21 | Hawkstow Construction and Development
5402 | REPAIR 2024 | Region IV-B | Occidental Mindoro | 110251 | Bubog 2 ES | SAN JOSE | Lone | 1 | 6 | Repair of Classrooms | 3647426.72 | 1 |  | COMPLETED | 1 |  |  | DepEd-OccMdo-2024-07 |  | 2024-08-07 | 2024-08-15 | 2024-08-27 | 2024-09-02 | 2024-10-21 | Hawkstow Construction and Development
5403 | REPAIR 2024 | Region IV-B | Occidental Mindoro | 110307 | Mapaya III ES - Ong-Ong | SAN JOSE | Lone | 1 | 4 | Repair of Classrooms | 2433914.26 | 1 |  | COMPLETED | 1 |  |  | DepEd-OccMdo-2024-07 |  | 2024-08-07 | 2024-08-15 | 2024-08-27 | 2024-09-02 | 2024-10-21 | Hawkstow Construction and Development
5404 | REPAIR 2024 | Region IV-B | Occidental Mindoro | 110274 | Tugtugin ES | SAN JOSE | Lone | 1 | 2 | Repair of Classrooms | 1211559.24 | 1 |  | COMPLETED | 1 |  |  | DepEd-OccMdo-2024-07 |  | 2024-08-07 | 2024-08-15 | 2024-08-27 | 2024-09-02 | 2024-10-21 | Hawkstow Construction and Development
5405 | REPAIR 2024 | Region IV-B | Oriental Mindoro | 110341 | Mangangan II ES | BACO | 1st | 1 | 3 | Repair of Classrooms | 2132504.79 | 1 | 2037924.36 | COMPLETED | 1 | 2024-12-14 | 2024-12-02 | CY 2024 BEFF Repair-001 | 31-2024 | 2024-07-09 | 2024-07-17 | 2024-07-30 | 2024-08-14 | 2024-10-02 | Kasanga Construction and Supplies
5406 | REPAIR 2024 | Region IV-B | Oriental Mindoro | 110588 | Biga Elementary School | POLA | 1st | 1 | 5 | Repair of Classrooms | 3142359.65 | 1 | 3086221.65 | COMPLETED | 1 | 2025-01-12 | 2024-12-11 | CY 2024 BEFF Repair-002 | 32-2024 | 2024-07-09 | 2024-07-17 | 2024-07-30 | 2024-08-14 | 2024-10-02 | FS Sugay Construction & Supplies
5407 | REPAIR 2024 | Region IV-B | Oriental Mindoro | 110677 | Mabuhay II Elementary School | SOCORRO | 1st | 1 | 8 | Repair of Classrooms | 6571347.07 | 1 | 6500903 | COMPLETED | 1 | 2025-03-13 | 2025-01-02 | CY 2024 BEFF Repair-003 | 33-2024 | 2024-07-09 | 2024-07-17 | 2024-07-30 | 2024-08-14 | 2024-10-02 | ETVR Trading and Construction
5408 | REPAIR 2024 | Region IV-B | Oriental Mindoro | 110443 | Kawit ES | GLORIA | 2nd | 1 | 3 | Repair of Classrooms | 1228614.24 | 1 | 1215000 | COMPLETED | 1 | 2025-03-14 | 2025-01-15 | CY 2024 BEFF Repair-004 | 35-2024 | Sept. 14, 2024 | Sept. 23, 2024 | Oct. 7, 2024 | 2024-10-22 | 2024-11-07 | ADL Constrak OPC
5409 | REPAIR 2024 | Region IV-B | Oriental Mindoro | 110569 | Anoling ES | PINAMALAYAN | 2nd | 1 | 2 | Repair of Classrooms | 1500799.47 | 1 | 1485000 | COMPLETED | 1 | 2025-03-14 | 2025-01-15 | CY 2024 BEFF Repair-004 | 35-2024 | Sept. 14, 2024 | Sept. 23, 2024 | Oct. 7, 2024 | 2024-10-22 | 2024-11-07 | ADL Constrak OPC
5410 | REPAIR 2024 | Region IV-B | Oriental Mindoro | 110555 | Banilad ES | PINAMALAYAN | 2nd | 1 | 2 | Repair of Classrooms | 1244999.31 | 1 | 1232000 | COMPLETED | 1 | 2025-03-14 | 2025-01-15 | CY 2024 BEFF Repair-004 | 35-2024 | Sept. 14, 2024 | Sept. 23, 2024 | Oct. 7, 2024 | 2024-10-22 | 2024-11-07 | ADL Constrak OPC
5411 | REPAIR 2024 | Region IV-B | Oriental Mindoro | 110559 | Lumambayan ES | PINAMALAYAN | 2nd | 1 | 2 | Repair of Classrooms | 1170750.59 | 1 | 1158000 | COMPLETED | 1 | 2025-03-14 | 2025-01-15 | CY 2024 BEFF Repair-004 | 35-2024 | Sept. 14, 2024 | Sept. 23, 2024 | Oct. 7, 2024 | 2024-10-22 | 2024-11-07 | ADL Constrak OPC
5412 | REPAIR 2024 | Region IV-B | Palawan | 309135 | Ilian National High School | DUMARAN | 1st | 1 | 4 | Repair of Classrooms | 3204863.59 | 1 | 3162752.06 | COMPLETED | 1 | 2024-03-29 | 2025-02-28 | 2024-07-007-INFRA | 2024-11-006_INFRA | 2024-08-03 | 2024-08-09 | 2024-08-22 | 2024-11-04 | 2024-11-20 | RBM2 Construction
5413 | REPAIR 2024 | Region IV-B | Palawan | 170515 | Magsasaka Elementary School | DUMARAN | 1st | 1 | 4 | Repair of Classrooms | 3797857.66 | 1 | 3756431.84 | Ongoing | 0.45 | 2025-07-30 |  | 2024-07-006-INFRA | 2025-03-002_INFRA | 2024-12-31 | 2025-01-07 | 2025-01-20 | 2025-02-24 | 2025-03-24 | Em Abin Trading and Construction
5414 | REPAIR 2024 | Region IV-B | Palawan | 110777 | Nala Elementary School | DUMARAN | 1st | 1 | 4 | Repair of Classrooms | 3785615.85 | 1 | 3736878.46 | COMPLETED | 1 | 2024-03-11 | 2025-02-10 | 2024-07-005-INFRA | 2024-09-004_INFRA | 2024-08-03 | 2024-08-09 | 2024-08-22 | 2024-09-23 | 2024-10-30 | RBM2 Construction
5415 | REPAIR 2024 | Region IV-B | Palawan | 110724 | Iraan Elementary School | ABORLAN | 3rd | 1 | 8 | Repair of Classrooms | 5809406.02 | 1 | 5740368.11 | COMPLETED | 1 | 2024-03-29 | 2025-03-24 | 2024-07-008-INFRA | 2024-11-007_INFRA | 2024-08-03 | 2024-08-09 | 2024-08-22 | 2024-11-04 | 2024-11-20 | RBM2 Construction
5416 | REPAIR 2024 | Region IV-B | Puerto Princesa City | 301782 | Inagawan NHS | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 8 | Repair of Classrooms | 6146907.21 | 1 | 6034137.17 | COMPLETED | 1 | Jul. 2, 2025 |  |  | INFRA 2024-09-02 | Sept. 26, 2024 | Oct. 2, 2024 | Oct. 14, 2024 | Oct. 21, 2024 | Oct. 28, 2024 | MARYJONICA CONSTRUCTION | REALIGNED FROM STA MONICA HS TO INAGAWAN NHS
5417 | REPAIR 2024 | Region IV-B | Puerto Princesa City | 111490 | Napsan ES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 1 | Repair of Classrooms | 747782.83 | 1 | 735350.16 | COMPLETED | 1 | Jul. 2, 2025 |  |  | INFRA 2024-09-02 | Sept. 26, 2024 | Oct. 2, 2024 | Oct. 14, 2024 | Oct. 21, 2024 | Oct. 28, 2024 | MARYJONICA CONSTRUCTION | For Final Inspection
5418 | REPAIR 2024 | Region IV-B | Puerto Princesa City | 111497 | Tagburos ES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 11 | Repair of Classrooms | 7363916.44 | 1 | 7226527.24 | COMPLETED | 1 | Jul. 2, 2025 |  |  | INFRA 2024-09-02 | Sept. 26, 2024 | Oct. 2, 2024 | Oct. 14, 2024 | Oct. 21, 2024 | Oct. 28, 2024 | MARYJONICA CONSTRUCTION
5419 | REPAIR 2024 | Region IV-B | Romblon | 111292 | Magdiwang ES | MAGDIWANG | Lone | 1 | 2 | Repair of Classrooms | 3030303.03 | 1 | 2999981.91 | Ongoing | 0.4985 | March 1,2025 |  | BEFF-REF-2024-02 | BEFF-REF-2024-02 | Sept. 03, 2024 | Sept. 11, 2024 | Sept. 23, 2024 | Nov. 14, 2024 | 2024-12-04 | RMR Construction & Trading
5420 | REPAIR 2024 | Region IV-B | Romblon | 111347 | Amatong (Orlina) Elementary School | ODIONGAN | Lone | 1 | 6 | Repair of Classrooms | 3535353.54 | 1 | 3389028.61 | Ongoing | 0.22 | May 13,2025 |  | BEFF-REF-2024-03 | BEFF-REF-2024-03 | Sept. 03, 2024 | Sept. 11, 2024 | Sept. 23, 2024 | Nov. 22, 2024 | 2024-12-09 | RMR Construction & Trading
5421 | REPAIR 2024 | Region IV-B | Romblon | 111334 | Boliganay ES | ODIONGAN | Lone | 1 | 4 | Repair of Classrooms | 3535353.54 | 1 | 3303927.38 | Ongoing | 0.43 | May 13,2025 |  | BEFF-REF-2024-03 | BEFF-REF-2024-03 | Sept. 03, 2024 | Sept. 11, 2024 | Sept. 23, 2024 | Nov. 22, 2024 | 2024-12-09 | RMR Construction & Trading
5422 | REPAIR 2024 | Region IV-B | Romblon | 111359 | PROGRESO OESTE ELEMENTARY SCHOOL | ODIONGAN | Lone | 1 | 7 | Repair of Classrooms | 3030303.03 | 1 | 2804196.62 | Ongoing | 0.3439 | May 13,2025 |  | BEFF-REF-2024-03 | BEFF-REF-2024-03 | Sept. 03, 2024 | Sept. 11, 2024 | Sept. 23, 2024 | Nov. 22, 2024 | 2024-12-09 | RMR Construction & Trading
5423 | REPAIR 2024 | Region IV-B | Romblon | 111368 | Agpanabat ES | ROMBLON (Capital) | Lone | 1 | 7 | Repair of Classrooms | 3030303.03 | 1 | 2997442.23 | Ongoing | 0.5 | March 1,2025 |  | BEFF-REF-2024-01 | BEFF-REF-2024-01 | Sept. 03, 2024 | Sept. 11, 2024 | Sept. 23, 2024 | Nov. 14, 2024 | 2024-12-04 | RMR Construction & Trading

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%