## Sheet1
INDEX (DO NOT MODIFY) | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
57 | LMS 2020 | Region V | Camarines Sur | 112696 | Tampuhan ES | LIBMANAN | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 8580284.0651 | 0 | Reverted | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | resolution to cancel due to time constraint for procurement activities
58 | LMS 2020 | Region V | Catanduanes | 113171 | San Miguel Elementary School | BARAS | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m) | 8140400.6798 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
59 | LMS 2020 | Region V | Catanduanes | 113339 | Dugui San Isidro Elementary School | VIRAC (Capital) | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 8140400.6798 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
60 | LMS 2020 | Region V | Masbate | 113458 | Mapitogo Elementary School | BALUD | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 10351655.5952 | 10298568.14 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 3R3M Const. and Supply | 0
141 | LMS 2021 | Region V | Camarines Norte | 501259 | Malaya IS | LABO WEST | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SOLAR ENERGY AND WATER SYSTEMS AND SCHOOL FURNITURE AND FENCING AND SLOPE PROTECTION | 29291757.9847 | 0 | TERMINATED | 0.3 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CENTRAL OFFICE IMPLEMENTED
142 | LMS 2021 | Region V | Camarines Sur | 113033 | Bagong Sirang Elementary School | SIRUMA | 4 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR,SCHOOL FURNITURE, WATER SANITATION AND WATER SYSTEM | 10580022.8319 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
143 | LMS 2021 | Region V | Camarines Sur | 113107 | San Rafael ES | TIGAON | 4 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 10240762.8319 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
144 | LMS 2021 | Region V | Camarines Sur | 112358 | Santiago Elementary School | BALATAN | 5 | 1 | 4 | PROPOSED CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 14849440.7976 | 0 | Ongoing | 0.99 |  |  | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
145 | LMS 2021 | Region V | Catanduanes | 113214 | Sabloyon Elementary School | CARAMORAN | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, PERIMETER FENCE (1 BAY = 3.0m) | 10114683.1467 | 0 | terminated | 0.0505 | [10 empty] | FOR TERMINATION
146 | LMS 2021 | Region V | Catanduanes | 113356 | Buenavista ES | VIRAC (Capital) | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, PERIMETER FENCE (1 BAY = 3.0m) | 10114683.1467 | 0 | terminated | 0.55 | [10 empty] | FOR TERMINATION
147 | LMS 2021 | Region V | Sorsogon | 114142 | Cristo Elementary School | DONSOL | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 7538498.756 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Inaugurated (November)
148 | LMS 2021 | Region V | Sorsogon | 114296 | Malbog Elementary School | MAGALLANES | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR,SCHOOL FURNITURE,WATER SANITATION AND WATER SYSTEM | 10174305.4412 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
244 | LMS 2022 | Region V | Catanduanes | 302074 | Bato RDHS | BATO | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, AND WATER SYSTEM | 13040244.7845 | 17798245.81 | Completed | 1 | 2023-11-01 | 00:00:00 | 0 | 0 | 2023-05-08 | 2023-05-15 | 2023-06-05 | 2023-06-16 | 2023-06-29 | 0 | 0
245 | LMS 2022 | Region V | Catanduanes | 302087 | Dororian NHS | GIGMOTO | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, AND WATER SYSTEM | 23006293.5345 | 19137563.67 | Completed | 1 | 2023-02-23 | 00:00:00 | 0 | 44743 | 00:00:00 | 00:00:00 | 2022-05-26 | 00:00:00 | 2022-07-26 | Hi-Tone Construction & Devt. Corp. | 0
326 | LMS 2023 | Region V | Camarines Norte | 112269 | Resettlement ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF, SCHOOL FURNITURE, CONCRETE PATHWAY (WIDTH = 4.0m), PERIMETER FENCE 150.0m FRONTAGE (1 BAY = 3.0m) AND REPAIR OF 2CL BLSB TYPE 1 | 17976228.27 | 17729608.63 | COMPLETED | 1 | 2023-11-11 | 2024-02-26 | INFRA02-05 2023CN | INFRA02-05 2023CN | 2023-05-08 | 2023-05-15 | 2023-06-05 | 2023-06-16 | 2023-06-29 | RidersCorner Construction & Gen. Mdse. | COMPLETED
327 | LMS 2023 | Region V | Catanduanes | 113214 | Sabloyon Elementary School | CARAMORAN | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE WITH HAULING COST | 7587681.68 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
328 | LMS 2023 | Region V | Masbate | 136922 | Arriesgado Elementary School | CLAVERIA | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SANITATION AND WATER SYSTEM WITH HAULING COST | 12784616.01 | 12631866.08 | Completed | 1 | 2023-12-07 | 2024-01-10 | INFRA 2023-05-002 | 2023-07-001 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-10 | NJNY Const. & Supply | 0
329 | LMS 2023 | Region V | Masbate | 113662 | Tabuk Elementary School | MANDAON | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SANITATION AND WATER SYSTEM WITH HAULING COST | 12784616.01 | 12631638.76 | Completed | 1 | 2023-12-03 | 2024-01-16 | INFRA 2023-05-002 | 2023-07-002 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-06 | EJ Cantoria Const. & Supply | 0
330 | LMS 2023 | Region V | Masbate | 501528 | Tugbo Integrated School | MOBO | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SANITATION AND WATER SYSTEM WITH HAULING COST | 12784616.01 | 12632137.16 | Completed | 1 | 2023-12-10 | 2024-04-01 | INFRA 2023-05-002 | 2023-07-038 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-13 | Square N Const & Supply | 0
331 | LMS 2023 | Region V | Masbate | 501545 | Madamba Integrated School | CATAINGAN | 3 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SANITATION AND WATER SYSTEM WITH HAULING COST | 14029531.76 | 13867265.99 | Completed | 1 | 2023-12-02 | 2024-01-15 | INFRA 2023-05-002 | 2023-07-039 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-05 | 3R3M Const & Supply | 0
332 | LMS 2023 | Region V | Masbate | 113531 | Calapayan Elementary School | CAWAYAN | 3 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE WITH HAULING COST | 8597681.69 | 8496949.85 | Completed | 1 | 2023-12-10 | 2023-12-12 | INFRA 2023-05-002 | 2023-07-040 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-13 | Square N Const & Supply | 0
333 | LMS 2023 | Region V | Masbate | 302123 | Buracan National High School | DIMASALANG | 3 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SANITATION AND WATER SYSTEM WITH HAULING COST | 13996557.55 | 13831624.51 | Completed | 1 | 2024-12-10 | 2024-01-15 | INFRA 2023-05-002 | 2023-07-041 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-13 | Square N Const & Supply | 0
454 | LMS 2024 | Region V | Camarines Norte | 501259 | Malaya Integrated School | LABO | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND RAIN WATER COLLECTOR TWO (2) SETS | 17467038.05 | 10339297.77 | COMPLETED | 1 | 2024-12-11 | 2025-02-09 | INFRA06-11-2023CN | INFRA06-11-2023CN | 2023-11-07 | 2023-11-15 | 2023-12-06 | 2024-01-16 | 2024-06-14 | RIDERS CORNER BUILDING AND REALTY DEVELOPMENT CORPORATION | COMPLETED
455 | LMS 2024 | Region V | Camarines Norte | 112308 | Mangcawayan Island Elementary School | VINZONS | 2nd | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND RAIN WATER COLLECTOR TWO (2) SETS - TRIPLE HAULING | 13898660.22 | 9599009.6 | COMPLETED | 1 | 2024-11-11 | 2025-01-10 | INFRA06-11-2023CN | INFRA06-11-2023CN | 2023-11-07 | 2023-11-15 | 2023-12-06 | 2024-01-16 | 2024-06-14 | RIDERS CORNER BUILDING AND REALTY DEVELOPMENT CORPORATION | WITH RETIFICATION
456 | LMS 2024 | Region V | Camarines Sur | 300315 | Salvacion High School | SIPOCOT | 1st | 1 | 8 | PROPOSED CONSTRUCTION OF 2 UNITS, 1 STOREY, 4 CLASSROOM SCHOOL BUILDING W/ 2 UNITS, 4 SEATER WATER AND SANITATION FACILITIES, 2 UNITS RAINWATER COLLECTOR, AND SCHOOL FURNITURE FOR 2 UNITS, 1 STOREY, 4 CLASSROOM SCHOOL BUILDING | 34039259.84 | 33361240.37 | COMPLETED | 1 | 2024-12-08 | 2025-03-11 | 2024-05-043 | 2024-05-043 | 2023-11-23 | 2023-12-01 | 2023-12-13 | 2024-01-10 | 2024-06-11 | Honeyville Construction | approved time extension
457 | LMS 2024 | Region V | Camarines Sur | 112696 | Tampuhan ES | LIBMANAN | 2nd | 1 | 2 | PROPOSED CONSTRUCTION OF 1 UNIT, 1 STOREY, 2 CLASSROOM SCHOOL BUILDING W/ 1 UNIT, 4 SEATER WATER AND SANITATION FACILITIES, 1 UNIT RAINWATER COLLECTOR, AND SCHOOL FURNITURE FOR 1 UNIT, 1 STO - 2 CL (7m x 9m) SCHOOL BUILDING | 10803221.3 | 9474512.96 | Ongoing | 0.99 | 2024-10-26 |  | 2024-05-044 | 2024-05-044 | 2023-11-23 | 2023-12-01 | 2023-12-13 | 2024-01-22 | 2024-06-13 | TGME Construction and Supply
458 | LMS 2024 | Region V | Camarines Sur | 112757 | Barobaybay ES | MAGARAO | 3rd | 1 | 2 | PROPOSED CONSTRUCTION OF 1 UNIT, 1 STOREY, 2 CLASSROOM SCHOOL BUILDING W/ 1 UNIT, 4 SEATER WATER AND SANITATION FACILITIES, 1 UNIT RAINWATER COLLECTOR, AND SCHOOL FURNITURE FOR 1 UNIT, 1 STO - 2 CL (7m x 9m) SCHOOL BUILDING | 10728585.06 | 10342846.08 | Completed | 1 | 2024-10-09 |  | 2024-05-045 | 2024-05-045 | 2023-11-23 | 2023-12-01 | 2023-12-13 | 2024-01-18 | 2024-06-11 | TRDV Construction and Supply | 0
459 | LMS 2024 | Region V | Camarines Sur | 112556 | Oring ES | CARAMOAN | 4th | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS, 1 STOREY, 2 CLASSROOM SCHOOL BUILDING W/ 1 UNIT, 4 SEATER WATER AND SANITATION FACILITIES, 1 UNIT RAINWATER COLLECTOR, AND SCHOOL FURNITURE FOR 2 UNITS, 1 STO - 2 CL (7m x 9m) SCHOOL BUILDING | 22399589.68 | 22130242.21 | Completed | 1 | 2024-10-11 |  | 2024-05-046 | 2024-05-046 | 2023-11-23 | 2023-12-01 | 2023-12-13 | 2023-12-29 | 2024-06-13 | TGME Construction and Supply | 0
460 | LMS 2024 | Region V | Camarines Sur | 500468 | Harrison Integrated School | GARCHITORENA | 4th | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11795242.42 | 11526923.04 | Ongoing | 0.99 | 2024-10-19 |  | 2024-05-047 | 2024-05-047 | 2023-11-23 | 2023-12-01 | 2023-12-13 | 2024-01-18 | 2024-06-21 | MARAKESH ENTERPRISES
461 | LMS 2024 | Region V | Camarines Sur | 112324 | Cristo Rey Elementary School | BAAO | 5th | 1 | 2 | PROPOSED CONSTRUCTION OF 1 UNIT, 1 STOREY, 2 CLASSROOM SCHOOL BUILDING W/ 1 UNIT, 4 SEATER WATER AND SANITATION FACILITIES, 1 UNIT RAINWATER COLLECTOR, AND SCHOOL FURNITURE FOR 1 UNIT, 1 STO - 2 CL (7m x 9m) SCHOOL BUILDING | 10792740.79 | 8646767.36 | Ongoing | 0.99 | 2024-10-08 |  | 2024-05-048 | 2024-05-048 | 2023-11-23 | 2023-12-01 | 2023-12-13 | 2024-01-22 | 2024-06-10 | RIDERS CORNER BUILDING AND REALTY DEVELOPMENT CORPORATION
462 | LMS 2024 | Region V | Catanduanes | 174016 | Pananaogan Elementary School | BATO | Lone | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17171717.17 | 16742770.61 | Completed | 1 | 2024-10-22 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 2024-05-24 | STEVEN CONSTRUCTION& SUPPLY | 0
463 | LMS 2024 | Region V | Catanduanes | 113296 | Siay Elementery School | SAN MIGUEL | Lone | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY THREE (3) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17637171.72 | 17186395.36 | Ongoing | 0.95 | 2024-10-22 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 2024-05-24 | NGS CONSTRUCTION& SUPPLY | 0
464 | LMS 2024 | Region V | Masbate | 113866 | Daplian ES | SAN FERNANDO | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 12273116.16 | 12130990.29 | Ongoing | 0.9 | 2025-05-27 | 00:00:00 | INFRA 2024-08-002 | 2024-026 | 2024-08-12 | 2024-08-20 | 2024-09-02 | 2024-09-20 | 2024-12-28 | JOHNCB CONSTRUCTION & SUPPLY | 0
465 | LMS 2024 | Region V | Masbate | 113893 | Jagna-an ES | SAN JACINTO | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 12273116.16 | 12131339.29 | Ongoing | 0.8 | 2025-05-27 | 00:00:00 | INFRA 2024-08-002 | 2024-027 | 2024-08-12 | 2024-08-20 | 2024-09-02 | 2024-09-20 | 2024-12-28 | JOHNCB CONSTRUCTION & SUPPLY | 0
466 | LMS 2024 | Region V | Masbate | 113896 | Mabini Elementary School | SAN JACINTO | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11598060.61 | 11468418.82 | Ongoing | 0.85 | 2025-05-27 | 00:00:00 | INFRA 2024-09-003 | 2024-021 | 2024-09-10 | 2024-09-18 | 2024-09-30 | 2024-10-22 | 2024-12-28 | SMDF CONSTRUCTION | 0
467 | LMS 2024 | Region V | Masbate | 113898 | Roosevelt Elementary School | SAN JACINTO | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 12015834.81 | 11839039.3 | Ongoing | 0.9 | 2025-05-27 | 00:00:00 | INFRA 2024-08-002 | 2024-028 | 2024-08-12 | 2024-08-20 | 2024-09-02 | 2024-09-20 | 2024-12-28 | JOHNCB CONSTRUCTION & SUPPLY | 0
468 | LMS 2024 | Region V | Masbate | 113902 | Tutuban Elementary School | SAN JACINTO | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11598060.61 | 11469699.82 | Ongoing | 0.9 | 2025-05-27 | 00:00:00 | INFRA 2024-09-003 | 2024-022 | 2024-09-10 | 2024-09-18 | 2024-09-30 | 2024-10-22 | 2024-12-28 | SMDF CONSTRUCTION | 0
469 | LMS 2024 | Region V | Masbate City | 500393 | Alejandro Delos Reyes Integrated School | CITY OF MASBATE (Capital) | 2nd | 1 | 4 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 20202020.2 | 19798704.92 | COMPLETED | 1 | 2025-04-20 | 2025-04-18 | LMS 2024 - RV - MASBATE CITY - 001 | LMS 2024 - RV - MASBATE CITY - 001 | 2024-03-07 | 2024-03-15 | 2024-04-01 | 2024-07-01 | 2024-07-15 | GINA'S CONSTRUCTION SERVICES | 0
470 | LMS 2024 | Region V | Sorsogon | 114136 | Sto. Nino Elementary School | CASTILLA | 1st | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM, SOLAR PV ENERGY SYSTEM | 18030049.99 | 16059049.82 | Ongoing | 0.2 | 2025-08-10 | 00:00:00 | 24-04-004 | 24-04-004 | 2024-04-30 | 2024-05-08 | 2024-05-20 | 2024-12-06 | 2025-03-14 | 144 Cubits Builders and Supply | 0
471 | LMS 2024 | Region V | Sorsogon | 302769 | Sablayan High School | JUBAN | 2nd | 1 | 4 | CONSTRUCTION OF 1STY4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM, SOLAR PV ENERGY SYSTEM, SLOPE PROTECTION PROTECTION | 20447749.05 | 18206941.63 | Ongoing | 0.1 | 2025-09-09 | 00:00:00 | 24-04-004 | 24-04-004 | 2024-04-30 | 2024-05-08 | 2024-05-20 | 2024-12-06 | 2025-03-14 | 144 Cubits Builders and Supply | 0

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.