## Sheet1
INDEX (DO NOT MODIFY) | PROGRAM-YEAR | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | BATCH | TOTAL PROJECT ALLOCATION | TOTAL PROJECT COST | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
4191 | NC 2014 | SHS (2014) | Region V | ALBAY | 309506 | Alimsog IS | SANTO DOMINGO (LIBOG) | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-30 | 050114S00147 | 15FA0047 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-26 | 2015-08-05 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO
4192 | NC 2014 | K10 (2014) | Region V | Albay | 172515 | Bagatangki ES | MALINAO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1015208.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050114S00047 | 14FA0013 | 2014-07-09 | 2014-07-21 | 2014-07-22 |  | 2014-08-25 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
4193 | NC 2014 | K10 (2014) | Region V | Albay | 111878 | Balza ES | MALINAO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 985209 |  |  | REVERTED | 0
4194 | NC 2014 | K10 (2014) | Region V | Albay | 111602 | Bariw ES | BACACAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050114S00051 | 14FA0013 | 2014-07-09 | 2014-07-21 | 2014-07-22 |  | 2014-08-25 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
4195 | NC 2014 | SHS (2014) | Region V | ALBAY | 301815 | Bical HS | SANTO DOMINGO (LIBOG) | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6420639.1381 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-30 | 050114S00146 | 15FA0047 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-26 | 2015-07-31 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO
4196 | NC 2014 | K10 (2014) | Region V | Albay | 111586 | Bogna ES | BACACAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1035208.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050114S00063 | 14FA0013 | 2014-07-09 | 2014-07-21 | 2014-07-22 |  | 2014-08-25 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
4197 | NC 2014 | SHS (2014) | Region V | ALBAY | 301816 | Bonga NHS | BACACAY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-30 |  | 050114S00145 | 15FA0037 | 2015-07-08 | 2015-07-09 | 2015-07-21 | 2015-07-25 | 2015-07-31 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO
4198 | NC 2014 | SHS (2014) | Region V | ALBAY | 301818 | Cabasan NHS | BACACAY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8442982.051 |  |  | COMPLETED | 1 |  |  | 050114S00144 | 15FA0082 | 2015-08-05 | 2015-08-17 | 2015-11-18
4199 | NC 2014 | SHS (2014) | Region V | ALBAY | 301821 | Cawayan National High School | BACACAY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8442982.051 |  |  | COMPLETED | 1
4200 | NC 2014 | K10 (2014) | Region V | Albay | 301821 | Cawayan National High School | BACACAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
4201 | NC 2014 | K10 (2014) | Region V | Albay | 172516 | Diaro ES | MALINAO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050114S00046 | 14FA0013 | 2014-07-09 | 2014-07-21 | 2014-07-22 |  | 2014-08-25 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
4202 | NC 2014 | SHS (2014) | Region V | ALBAY | 301827 | Estancia NHS | MALINAO | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6353262.6381 |  |  | COMPLETED | 1 | 2016-01-02 |  | 050114S00156 | 15FA0050 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-26 | 2015-08-05 | WIND RIVER COURT CONSTRUCTION AND DEVELOPMENT
4203 | NC 2014 | SHS (2014) | Region V | ALBAY | 301881 | Joroan HS | TIWI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8316098.501 |  |  | COMPLETED | 1 | 2016-01-03 | 2015-12-31 | 050114S00167 | 15FA0051 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-26 | 2015-08-05 | LSL CONSTRUCTION & SUPPLY
4204 | NC 2014 | SHS (2014) | Region V | ALBAY | 301831 | Labnig NHS | MALINAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8248890.051 |  |  | COMPLETED | 1 | 2016-01-03 | 2015-12-31 | 050114S00168 | 15FA0052 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-26 | 2015-08-05 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
4205 | NC 2014 | SHS (2014) | Region V | ALBAY | 309515 | Malilipot NHS | MALILIPOT | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 | 2015-12-30 |  | 050114S00169 | 15FA0053 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-26 | 2015-07-31 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO
4206 | NC 2014 | SHS (2014) | Region V | ALBAY | 301810 | Malinao NHS | MALINAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8319965.051 |  |  | COMPLETED | 1
4207 | NC 2014 | K10 (2014) | Region V | Albay | 111593 | Manaet ES | BACACAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050114S00050 | 14FA0013 | 2014-07-09 | 2014-07-21 | 2014-07-22 |  | 2014-08-25 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
4208 | NC 2014 | K10 (2014) | Region V | Albay | 112073 | Mayong ES | TIWI | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050114S00048 | 14FA0013 | 2014-07-09 | 2014-07-21 | 2014-07-22 |  | 2014-08-25 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
4209 | NC 2014 | SHS (2014) | Region V | ALBAY | 301853 | Naga National High School | TIWI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-26 |  | 050114S00171 | 15FA0038 | 2015-07-08 | 2015-07-09 | 2015-07-21 | 2015-07-25 | 2015-08-05 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
4210 | NC 2014 | SHS (2014) | Region V | ALBAY | 301863 | Pili NHS | BACACAY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8298315.051 |  |  | COMPLETED | 1 | 2016-01-29 |  | 050114S00179 | 15FA0043 | 2015-07-08 | 2015-07-09 | 2015-07-21 | 2015-07-25 | 2015-07-31 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO
4211 | NC 2014 | SHS (2014) | Region V | ALBAY | 301871 | San Antonio NHS, Malilipot | MALILIPOT | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8319965.051 |  |  | COMPLETED | 1 |  |  | 050114S00173 | 15FA0082 | 2015-08-05 | 2015-08-17 | 2015-11-18
4212 | NC 2014 | SHS (2014) | Region V | ALBAY | 301872 | San Fernando NHS | SANTO DOMINGO (LIBOG) | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-04 |  | 050114S00166 | 15FA0044 | 2015-07-08 | 2015-07-09 | 2015-07-21 | 2015-07-25 | 2015-08-05 | ATHENA CONSTRUCTION AND DEVELOPMENT
4213 | NC 2014 | SHS (2014) | Region V | ALBAY | 309505 | San Francisco NHS | MALILIPOT | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-03 |  | 050114S00175 | 15FA0045 | 2015-07-08 | 2015-07-09 | 2015-07-21 | 2015-07-25 | 2015-08-05 | ZKR CONSTRUCTION & SUPPLY
4214 | NC 2014 | SHS (2014) | Region V | ALBAY | 301876 | San Isidro NHS, Malilipot | MALILIPOT | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 050114S00176 | 15FA0039 | 2015-07-08 | 2015-07-09 | 2015-07-21 | 2015-07-25 | 2015-08-05 | QDC CONSTRUCTION AND SUPPLY
4215 | NC 2014 | SHS (2014) | Region V | ALBAY | 301875 | San Jose NHS, Malilipot | MALILIPOT | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8252715.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 050114S00177 | 15FA0048 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-26 | 2015-08-05 | QDC CONSTRUCTION AND SUPPLY
4216 | NC 2014 | SHS (2014) | Region V | ALBAY | 309502 | San Pablo HS | BACACAY | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6579337.6381 |  |  | COMPLETED | 1 |  |  | 050114S00178 | 15FA0082 | 2015-08-05 | 2015-08-17 | 2015-11-18
4217 | NC 2014 | SHS (2014) | Region V | ALBAY | 301878 | Sogod NHS | BACACAY | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-02 |  | 050114S00153 | 15FA0046 | 2015-07-08 | 2015-07-09 | 2015-07-21 | 2015-07-25 | 2015-08-05 | EUGE CONSTRUCTION AND SUPPLY
4218 | NC 2014 | SHS (2014) | Region V | ALBAY | 301879 | Sto. Domingo NHS | SANTO DOMINGO (LIBOG) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
4219 | NC 2014 | K10 (2014) | Region V | Albay | 111621 | Tambilagao ES | BACACAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 985209 |  |  | REVERTED | 0
4220 | NC 2014 | K10 (2014) | Region V | Albay | 111622 | Tambongon ES | BACACAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050114S00058 | 14FA0013 | 2014-07-09 | 2014-07-21 | 2014-07-22 |  | 2014-08-25 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
4221 | NC 2014 | SHS (2014) | Region V | ALBAY | 301880 | Tiwi Agro-Ind'L Sch. | TIWI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1
4222 | NC 2014 | K10 (2014) | Region V | Albay | 301885 | Vinisitahan NHS | BACACAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4223 | NC 2014 | SHS (2014) | Region V | ALBAY | 301885 | Vinisitahan NHS | BACACAY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
4224 | NC 2014 | K10 (2014) | Region V | Albay | 301808 | Anislag NHS | DARAGA (LOCSIN) | 2 | 1 | 11 | 2UNITS 1STY2CL, 1STY 3CL & 2STY4CL | 2014 K10 BATCH 3 | 12129367.8688 |  |  | COMPLETED | 1
4225 | NC 2014 | SHS (2014) | Region V | ALBAY | 309508 | Anislag NHS - Bascaran HS Ext. | DARAGA (LOCSIN) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 | 2016-01-09 |  | 050114S00163 | 15FB0047 | 2015-07-08 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-08-06 | PEDXING BUILDERS
4226 | NC 2014 | SHS (2014) | Region V | ALBAY | 301809 | Anislag NHS - San Vicente Grande Ext. | DARAGA (LOCSIN) | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-09 |  | 050114S00162 | 15FB0047 | 2015-07-08 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-08-06 | PEDXING BUILDERS
4227 | NC 2014 | K10 (2014) | Region V | Albay | 112017 | Bagaobawan ES | RAPU-RAPU | 2 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2127537.69 |  |  | COMPLETED | 1 | 2014-10-22 | 2014-12-27 | 050114S00068 | 14FB0015 | 2014-06-04 | 2014-06-06 | 2014-06-19 | 2014-07-04 | 2014-07-09 | BLACKRAM BUILDERS, INC.
4228 | NC 2014 | K10 (2014) | Region V | Albay | 111889 | Bamban ES | MANITO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-22 | 2015-01-15 | 050114S00070 | 14FB0024 | 2014-06-19 | 2014-06-23 | 2014-07-04 | 2014-07-18 | 2014-07-25 | EUGE CONSTRUCTION AND SUPPLY
4229 | NC 2014 | SHS (2014) | Region V | ALBAY | 301812 | Bariw NHS | CAMALIG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-02-14 |  | 050114S00159 | 15FB0064 | 2015-08-11 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-11 | STEVEN CONSTRUCTION & SUPPLY
4230 | NC 2014 | SHS (2014) | Region V | ALBAY | 301813 | Batan National High School | RAPU-RAPU | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6537687.6381 |  |  | COMPLETED | 1 | 2016-02-20 |  | 050114S00164 | 15FB0068 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-04 | 2015-09-17 | ALXM CONSTRUCTION
4231 | NC 2014 | SHS (2014) | Region V | ALBAY | 309509 | Bilbao National High School | RAPU-RAPU | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6537687.6381 |  |  | COMPLETED | 1 | 2016-02-20 |  | 050114S00155 | 15FB0069 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-04 | 2015-09-17 | ZKR CONSTRUCTION & SUPPLY
4232 | NC 2014 | K10 (2014) | Region V | Albay | 112022 | Buenavista ES | RAPU-RAPU | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-22 | 2015-01-15 | 050114S00067 | 14FB0023 | 2014-06-19 | 2014-06-23 | 2014-07-04 | 2014-07-18 | 2014-07-25 | STEVEN CONSTRUCTION & SUPPLY
4233 | NC 2014 | K10 (2014) | Region V | Albay | 112023 | Buhatan ES | RAPU-RAPU | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-22 | 2014-12-29 | 050114S00059 | 14FB0021 | 2014-06-19 | 2014-06-23 | 2014-06-27 | 2014-07-14 | 2014-07-21 | STEVEN CONSTRUCTION & SUPPLY
4234 | NC 2014 | K10 (2014) | Region V | Albay | 111629 | Cabraran Pequeno ES | CAMALIG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 985209 |  |  | REVERTED | 0
4235 | NC 2014 | SHS (2014) | Region V | ALBAY | 301819 | Caguiba NHS | CAMALIG | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050114S00157 | 15FB0053 | 2015-07-15 | 2015-07-10 | 2015-07-23 | 2015-08-19 | 2015-08-28 | RCDS CONSTRUCTION & SUPPLY, INC.(FOR RCDS CONST.
4236 | NC 2014 | SHS (2014) | Region V | ALBAY | 301846 | Cawayan HS | MANITO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 | 2016-01-01 | 2015-12-31 | 050114S00158 | 15FB0059 | 2015-07-22 | 2015-07-23 | 2015-08-04 | 2015-08-18 | 2015-08-28 | GROSIN CONSTRUCTION & SUPPLY
4237 | NC 2014 | SHS (2014) | Region V | ALBAY | 301822 | Cotmon NHS | CAMALIG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-01-09 |  | 050114S00160 | 15FB0048 | 2015-07-08 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-08-06 | RCDS CONSTRUCTION & SUPPLY, INC.(FOR RCDS CONST.
4238 | NC 2014 | K10 (2014) | Region V | Albay | 301825 | Daraga NHS | DARAGA (LOCSIN) | 2 | 1 | 10 | Completion of 3STY15CL | 2014 K10 BATCH 4A | 8997302.7 |  |  | COMPLETED | 1
4239 | NC 2014 | SHS (2014) | Region V | ALBAY | 301823 | Ilawod National High School | CAMALIG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050114S00161 | 15FB0053 | 2015-07-15 | 2015-07-10 | 2015-07-23 | 2015-08-19 | 2015-08-28 | RCDS CONSTRUCTION & SUPPLY, INC.(FOR RCDS CONST.
4240 | NC 2014 | K10 (2014) | Region V | Albay | 309518 | Kilicao HS | DARAGA (LOCSIN) | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
4241 | NC 2014 | K10 (2014) | Region V | Albay | 111690 | Kinawitan ES | DARAGA (LOCSIN) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.24 |  |  | REVERTED | 0
4242 | NC 2014 | SHS (2014) | Region V | ALBAY | 301832 | Lacag NHS | DARAGA (LOCSIN) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6499337.6381 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 050114S00135 | 15FB0052 | 2015-07-15 | 2015-07-10 | 2015-07-23 | 2015-08-04 | 2015-08-17 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
4243 | NC 2014 | K10 (2014) | Region V | Albay | 112032 | Lagundi ES | RAPU-RAPU | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-22 | 2014-12-29 | 050114S00066 | 14FB0022 | 2014-06-19 | 2014-06-23 | 2014-07-04 | 2014-07-18 | 2014-07-25 | STEVEN CONSTRUCTION & SUPPLY
4244 | NC 2014 | SHS (2014) | Region V | ALBAY | 301841 | Malabog NHS | DARAGA (LOCSIN) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050114S00120 | 15FB0051 | 2015-07-15 | 2015-07-10 | 2015-07-23 | 2015-08-04 | 2015-08-17 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
4245 | NC 2014 | SHS (2014) | Region V | ALBAY | 301884 | Mancao National High School | RAPU-RAPU | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6572687.6381 |  |  | COMPLETED | 1
4246 | NC 2014 | K10 (2014) | Region V | Albay | 301884 | Mancao National High School | RAPU-RAPU | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4247 | NC 2014 | K10 (2014) | Region V | Albay | 301845 | Manito NHS | MANITO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329 |  |  | COMPLETED | 1
4248 | NC 2014 | K10 (2014) | Region V | Albay | 111900 | Manumbalay ES | MANITO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-22 | 2015-01-15 | 050114S00069 | 14FB0025 | 2014-06-19 | 2014-06-23 | 2014-07-04 | 2014-07-18 | 2014-07-25 | EUGE CONSTRUCTION AND SUPPLY
4249 | NC 2014 | K10 (2014) | Region V | Albay | 111673 | Maroroy ES | DARAGA (LOCSIN) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-25 | 2014-09-25 | 050114S00072 | 14FB0028 | 2014-06-19 | 2014-06-23 | 2014-07-04 | 2014-07-18 | 2014-07-25 | GRELIPS CONSTRUCTION & DEVELOPMENT
4250 | NC 2014 | K10 (2014) | Region V | Albay | 112038 | Masaga ES | RAPU-RAPU | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-22 | 2014-12-29 | 050114S00062 | 14FB0027 | 2014-06-19 | 2014-06-23 | 2014-07-04 | 2014-07-18 | 2014-07-25 | STEVEN CONSTRUCTION & SUPPLY
4251 | NC 2014 | K10 (2014) | Region V | Albay | 111674 | Matnog ES | DARAGA (LOCSIN) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 985208.57 |  |  | REVERTED | 0
4252 | NC 2014 | K10 (2014) | Region V | Albay | 111648 | Miti ES | CAMALIG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 050114S00073 | 14FB0017 | 2014-06-12 | 2014-06-16 | 2014-06-27 | 2014-07-15 | 2014-07-25 | EUGE CONSTRUCTION AND SUPPLY
4253 | NC 2014 | SHS (2014) | Region V | ALBAY | 301847 | Nagotgot HS | MANITO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6449337.6381 |  |  | COMPLETED | 1 | 2016-01-09 |  | 050114S00090 | 15FB0048 | 2015-07-08 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-08-06 | RCDS CONSTRUCTION & SUPPLY, INC.(FOR RCDS CONST.
4254 | NC 2014 | SHS (2014) | Region V | ALBAY | 301824 | Panoypoy HS | CAMALIG | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-12-08 | 050114S00096 | 15FB0065 | 2015-08-11 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-11 | PEDXING BUILDERS
4255 | NC 2014 | SHS (2014) | Region V | ALBAY | 301861 | Pariaan NHS | CAMALIG | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6449337.6381 |  |  | COMPLETED | 1 | 2015-12-09 |  | 050114S00099 | 15FB0049 | 2015-07-08 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-08-06 | ZKR CONSTRUCTION & SUPPLY
4256 | NC 2014 | SHS (2014) | Region V | ALBAY | 301869 | Rapu-Rapu NHS | RAPU-RAPU | 2 | 1 | 6 | 1STY6CL | 2014 SHS BATCH 1 | 5396910.09 |  |  | COMPLETED | 1 | 2016-02-20 |  | 050114S00118 | 15FB0069 | 2015-08-12 | 2015-08-13 | 2015-08-26 | 2015-09-04 | 2015-09-17 | ZKR CONSTRUCTION & SUPPLY
4257 | NC 2014 | K10 (2014) | Region V | Albay | 112044 | Sagrada ES | RAPU-RAPU | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-22 | 2014-12-15 | 050114S00061 | 14FB0014 | 2014-06-04 | 2014-06-06 | 2014-06-19 | 2014-07-04 | 2014-07-09 | BLACKRAM BUILDERS, INC.
4258 | NC 2014 | SHS (2014) | Region V | ALBAY | 309519 | Tinopan HS | RAPU-RAPU | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-01 | 2015-12-31 | 050114S00094 | 15FB0061 | 2015-08-05 | 2015-07-31 | 2015-08-13 | 2015-08-19 | 2015-08-28 | ZKR CONSTRUCTION & SUPPLY
4259 | NC 2014 | K10 (2014) | Region V | Albay | 112048 | Viga ES | RAPU-RAPU | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1035209 |  |  | COMPLETED | 1 | 2014-11-24 | 2015-01-15 | 050114S00060 | 14FB0016 | 2014-06-12 | 2014-06-16 | 2014-06-27 | 2014-07-14 | 2014-07-21 | ALXM CONSTRUCTION
4260 | NC 2014 | SHS (2014) | Region V | ALBAY | 301882 | Villahermosa NHS | RAPU-RAPU | 2 | 1 | 6 | 1STY6CL | 2014 SHS BATCH 1 | 5351002.09 |  |  | COMPLETED | 1 | 2016-02-20 |  | 050114S00152 | 15FB0068 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-04 | 2015-09-17 | ALXM CONSTRUCTION
4261 | NC 2014 | SHS (2014) | Region V | ALBAY | 301883 | Villahermosa NHS - Bogtong HS | RAPU-RAPU | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6507687.6381 |  |  | COMPLETED | 1 | 2016-02-20 |  | 050114S00093 | 15FB0068 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-04 | 2015-09-17 | ALXM CONSTRUCTION
4262 | NC 2014 | SHS (2014) | Region V | ALBAY | 309503 | Alabangpuro HS | PIO DURAN | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050114S00092 | 15FO0022 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-24 | 2015-09-16 | ZKR CONSTRUCTION & SUPPLY
4263 | NC 2014 | K10 (2014) | Region V | Albay | 172525 | Anopol ES | POLANGUI | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4264 | NC 2014 | K10 (2014) | Region V | Albay | 172525 | Anopol ES | POLANGUI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1
4265 | NC 2014 | K10 (2014) | Region V | Albay | 111738 | Bagacay ES | JOVELLAR | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 050114S00007 | 14FO0011 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-05 | CPR CONSTRUCTION AND SUPPLY
4266 | NC 2014 | K10 (2014) | Region V | Albay | 111785 | Balinsayawan ES | LIBON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 050114S00021 | 14FO0012 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-26 | QDC CONSTRUCTION AND SUPPLY
4267 | NC 2014 | SHS (2014) | Region V | ALBAY | 301866 | Balogo HS | OAS | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8459965.051 |  |  | COMPLETED | 1
4268 | NC 2014 | K10 (2014) | Region V | Albay | 111949 | Basicao Interior ES | PIO DURAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 050114S00005 | 14FO0013 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-05 | WEARR ENTERPRISES & DEVELOPMENT CORP.
4269 | NC 2014 | SHS (2014) | Region V | ALBAY | 301843 | Batbat HS | GUINOBATAN | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050114S00088 | 15FO0022 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-24 | 2015-09-16 | ZKR CONSTRUCTION & SUPPLY
4270 | NC 2014 | K10 (2014) | Region V | Albay | 301834 | Bonbon NHS | LIBON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1
4271 | NC 2014 | SHS (2014) | Region V | ALBAY | 301835 | Buga NHS | LIBON | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8444965.051 |  |  | COMPLETED | 1 | 2016-07-01 |  | 050114S00087 | 15FO0032 | 2015-08-18 | 2015-08-19 | 2015-09-01 | 2015-10-23 | 2015-12-28 | 6RM CONSTRUCTION AND DEVT. CORP. (FORMERLY R.R. MA
4272 | NC 2014 | K10 (2014) | Region V | Albay | 111911 | Cagmanaba ES | OAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 985209 |  |  | REVERTED | 0
4273 | NC 2014 | K10 (2014) | Region V | Albay | 111932 | Coliat ES | OAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 050114S00074 | 14FO0014 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-18 | CPR CONSTRUCTION AND SUPPLY
4274 | NC 2014 | K10 (2014) | Region V | Albay | 111983 | Danao ES | POLANGUI | 3 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2234658.24 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 050114S00033 | 14FO0014 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-18 | CPR CONSTRUCTION AND SUPPLY
4275 | NC 2014 | K10 (2014) | Region V | Albay | 111933 | Gumabao ES | OAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 985208.57 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 050114S00016 | 14FO0014 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-18 | CPR CONSTRUCTION AND SUPPLY
4276 | NC 2014 | SHS (2014) | Region V | ALBAY | 301836 | Interior 8 HS, San Pascual | LIBON | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-15 |  | 050114S00086 | 15FO0023 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-24 | 2015-09-11 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
4277 | NC 2014 | SHS (2014) | Region V | ALBAY | 301829 | Itaran NHS - Maysua Ext. | POLANGUI | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6509337.6381 |  |  | COMPLETED | 1 | 2016-08-18 |  | 050114S00085 | 15FO0051 | 2015-09-08 | 2015-09-09 | 2015-09-22 | 2015-10-23 | 2015-12-16 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
4278 | NC 2014 | K10 (2014) | Region V | Albay | 301830 | Jovellar NHS | JOVELLAR | 3 | 1 | 2 | 2STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1
4279 | NC 2014 | SHS (2014) | Region V | ALBAY | 301867 | La Medalla HS | POLANGUI | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-04-17 |  | 050114S00089 | 15FO0034 | 2015-08-18 | 2015-08-19 | 2015-09-01 | 2015-09-15 | 2015-10-14 | ELKANKONSTRAK DEVELOPMENT CORPORATION
4280 | NC 2014 | K10 (2014) | Region V | Albay | 112006 | La Purisima ES | POLANGUI | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 050114S00038 | 14FO0014 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-18 | CPR CONSTRUCTION AND SUPPLY
4281 | NC 2014 | K10 (2014) | Region V | Albay | 111958 | Lagaan ES | PIO DURAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 050114S00004 | 14FO0013 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-05 | WEARR ENTERPRISES & DEVELOPMENT CORP.
4282 | NC 2014 | K10 (2014) | Region V | Albay | 309513 | Lanigay HS | POLANGUI | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4283 | NC 2014 | K10 (2014) | Region V | Albay | 301833 | Libon Agro-Industrial HS | LIBON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
4284 | NC 2014 | K10 (2014) | Region V | Albay | 111795 | Libtong ES | LIBON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 050114S00020 | 14FO0012 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-26 | QDC CONSTRUCTION AND SUPPLY
4285 | NC 2014 | K10 (2014) | Region V | Albay | 111747 | Lilibdon ES | JOVELLAR | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 050114S00008 | 14FO0011 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-05 | CPR CONSTRUCTION AND SUPPLY
4286 | NC 2014 | K10 (2014) | Region V | Albay | 301850 | Lower Binogsacan HS | GUINOBATAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
4287 | NC 2014 | SHS (2014) | Region V | ALBAY | 301850 | Lower Binogsacan HS | GUINOBATAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8459965.051 |  |  | COMPLETED | 1
4288 | NC 2014 | K10 (2014) | Region V | Albay | 111796 | Macabugos ES | LIBON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 050114S00019 | 14FO0012 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-26 | QDC CONSTRUCTION AND SUPPLY
4289 | NC 2014 | K10 (2014) | Region V | Albay | 309514 | Macabugos HS (Pantao NHS - Macabugos HS (Ext.)) | LIBON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4290 | NC 2014 | SHS (2014) | Region V | ALBAY | 309514 | Macabugos HS (Pantao NHS - Macabugos HS (Ext.)) | LIBON | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
4291 | NC 2014 | SHS (2014) | Region V | ALBAY | 301840 | Magpanambo NHS | POLANGUI | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-05-17 |  | 050114S00123 | 15FO0042 | 2015-08-26 | 2015-08-27 | 2015-09-09 | 2015-09-24 | 2015-10-14 | ELKANKONSTRAK DEVELOPMENT CORPORATION
4292 | NC 2014 | K10 (2014) | Region V | Albay | 111766 | Malabiga ES | LIBON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 050114S00022 | 14FO0012 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-26 | QDC CONSTRUCTION AND SUPPLY
4293 | NC 2014 | SHS (2014) | Region V | ALBAY | 309520 | Malabiga HS | LIBON | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-15 |  | 050114S00122 | 15FO0023 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-24 | 2015-09-11 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
4294 | NC 2014 | SHS (2014) | Region V | ALBAY | 301839 | Malapay HS | PIO DURAN | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050114S00121 | 15FO0022 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-24 | 2015-09-16 | ZKR CONSTRUCTION & SUPPLY
4295 | NC 2014 | SHS (2014) | Region V | ALBAY | 309516 | Malidong National High School | PIO DURAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8459965.051 |  |  | COMPLETED | 1 | 2016-05-19 |  | 050114S00111 | 15FO0049 | 2015-08-31 | 2015-09-04 | 2015-09-17 | 2015-10-02 | 2015-10-16 | INFRA BUILDERS AND SELLERS, PHILIPPINES
4296 | NC 2014 | K10 (2014) | Region V | Albay | 111748 | Mamlad ES | JOVELLAR | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1049209 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 050114S00009 | 14FO0011 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-05 | CPR CONSTRUCTION AND SUPPLY
4297 | NC 2014 | K10 (2014) | Region V | Albay | 111963 | Mamlad ES | PIO DURAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 050114S00003 | 14FO0013 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-05 | WEARR ENTERPRISES & DEVELOPMENT CORP.
4298 | NC 2014 | K10 (2014) | Region V | Albay | 301848 | Maramba NHS | OAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4299 | NC 2014 | SHS (2014) | Region V | ALBAY | 301848 | Maramba NHS | OAS | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1
4300 | NC 2014 | SHS (2014) | Region V | ALBAY | 309507 | Maramba NHS - Cagmanaba HS | OAS | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 | 2016-05-14 |  | 050114S00097 | 15FO0053 | 2015-09-08 | 2015-09-09 | 2015-09-22 | 2015-10-29 | 2015-12-10 | PRECIOUS CONSTRUCTION
4301 | NC 2014 | K10 (2014) | Region V | Albay | 301849 | Marcial O. Rañola Memorial School | GUINOBATAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4302 | NC 2014 | SHS (2014) | Region V | ALBAY | 301854 | Marigondon National High School | PIO DURAN | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6504337.6381 |  |  | COMPLETED | 1 | 2016-05-19 |  | 050114S00117 | 15FO0049 | 2015-08-31 | 2015-09-04 | 2015-09-17 | 2015-10-02 | 2015-10-16 | INFRA BUILDERS AND SELLERS, PHILIPPINES
4303 | NC 2014 | SHS (2014) | Region V | ALBAY | 301851 | Masarawag NHS | GUINOBATAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-05-23 |  | 050114S00116 | 15FO0043 | 2015-08-27 | 2015-08-28 | 2015-09-14 | 2015-09-30 | 2015-10-20 | STEVEN CONSTRUCTION & SUPPLY
4304 | NC 2014 | SHS (2014) | Region V | ALBAY | 301852 | Matacon NHS | POLANGUI | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8554965.051 |  |  | COMPLETED | 1 | 2016-04-25 |  | 050114S00115 | 15FO0045 | 2015-08-27 | 2015-08-28 | 2015-09-14 | 2015-09-29 | 2015-10-22 | PEDXING BUILDERS
4305 | NC 2014 | SHS (2014) | Region V | ALBAY | 309517 | Matara HS | LIBON | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-15 |  | 050114S00114 | 15FO0023 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-24 | 2015-09-11 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
4306 | NC 2014 | K10 (2014) | Region V | Albay | 301844 | Mauraro HS | GUINOBATAN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4307 | NC 2014 | K10 (2014) | Region V | Albay | 111989 | Maynaga ES | POLANGUI | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 050114S00041 | 14FO0014 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-18 | CPR CONSTRUCTION AND SUPPLY
4308 | NC 2014 | K10 (2014) | Region V | Albay | 111750 | Medalla Milagrosa ES | JOVELLAR | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 986208.57 |  |  | REVERTED | 0
4309 | NC 2014 | K10 (2014) | Region V | Albay | 111991 | Mendez PS | POLANGUI | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 050114S00040 | 14FO0014 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-18 | CPR CONSTRUCTION AND SUPPLY
4310 | NC 2014 | K10 (2014) | Region V | Albay | 111992 | Napo ES | POLANGUI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2016-01-19 |  | 050114S00083 | 15FO0026 | 2015-08-04 | 2015-08-05 | 2015-08-17 | 2015-09-03 | 2015-09-15 | EUGE CONSTRUCTION AND SUPPLY
4311 | NC 2014 | K10 (2014) | Region V | Albay | 111769 | Natasan ES | LIBON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 050114S00013 | 14FO0012 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-26 | QDC CONSTRUCTION AND SUPPLY
4312 | NC 2014 | SHS (2014) | Region V | ALBAY | 301855 | Oas Polytechnic School | OAS | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8459965.051 |  |  | COMPLETED | 1 | 2016-05-17 |  | 050114S00100 | 15FO0034 | 2015-08-18 | 2015-08-19 | 2015-09-01 | 2015-09-15 | 2015-10-20 | ELKANKONSTRAK DEVELOPMENT CORPORATION
4313 | NC 2014 | K10 (2014) | Region V | Albay | 301864 | Pioduran National High School | PIO DURAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4314 | NC 2014 | SHS (2014) | Region V | ALBAY | 301865 | Polangui General Comprehensive HS | POLANGUI | 3 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11227342.5917 |  |  | COMPLETED | 1
4315 | NC 2014 | SHS (2014) | Region V | ALBAY | 309504 | Rawis High School | LIBON | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6554337.6381 |  |  | COMPLETED | 1 | 2016-04-13 |  | 050114S00124 | 15FO0050 | 2015-08-31 | 2015-09-04 | 2015-09-17 | 2015-10-02 | 2015-12-29 | 6RM CONSTRUCTION AND DEVT. CORP. (FORMERLY R.R. MA
4316 | NC 2014 | K10 (2014) | Region V | Albay | 301870 | Saban NHS | OAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
4317 | NC 2014 | SHS (2014) | Region V | ALBAY | 301870 | Saban NHS | OAS | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8459965.051 |  |  | COMPLETED | 1
4318 | NC 2014 | SHS (2014) | Region V | ALBAY | 301857 | Sabino Rebagay Mem. HS | OAS | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050114S00109 | 15FO0022 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-24 | 2015-09-16 | ZKR CONSTRUCTION & SUPPLY
4319 | NC 2014 | K10 (2014) | Region V | Albay | 111773 | Sampongan ES | LIBON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 050114S00012 | 14FO0012 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-26 | QDC CONSTRUCTION AND SUPPLY
4320 | NC 2014 | K10 (2014) | Region V | Albay | 111774 | San Agustin ES | LIBON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 050114S00014 | 14FO0012 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-26 | QDC CONSTRUCTION AND SUPPLY
4321 | NC 2014 | SHS (2014) | Region V | ALBAY | 309511 | San Agustin IHS | LIBON | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8459965.051 |  |  | COMPLETED | 1 | 2016-07-01 |  | 050114S00108 | 15FO0032 | 2015-08-18 | 2015-08-19 | 2015-09-01 | 2015-10-23 | 2015-12-28 | 6RM CONSTRUCTION AND DEVT. CORP. (FORMERLY R.R. MA
4322 | NC 2014 | K10 (2014) | Region V | Albay | 111921 | San Antonio ES | OAS | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2006417.57 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 050114S00025 | 14FO0014 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-18 | CPR CONSTRUCTION AND SUPPLY
4323 | NC 2014 | SHS (2014) | Region V | ALBAY | 301873 | San Isidro NHS | JOVELLAR | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050114S00107 | 15FO0022 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-24 | 2015-09-16 | ZKR CONSTRUCTION & SUPPLY
4324 | NC 2014 | SHS (2014) | Region V | ALBAY | 301874 | San Jose NHS, Libon | LIBON | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1 | 2016-07-01 |  | 050114S00106 | 15FO0050 | 2015-08-31 | 2015-09-14 | 2015-09-17 | 2015-10-02 | 2015-12-28 | 6RM CONSTRUCTION AND DEVT. CORP. (FORMERLY R.R. MA
4325 | NC 2014 | SHS (2014) | Region V | ALBAY | 301856 | San Juan HS | OAS | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8459965.051 |  |  | COMPLETED | 1 | 2016-05-17 |  | 050114S00105 | 15FO0042 | 2015-08-26 | 2015-08-27 | 2015-09-09 | 2015-09-24 | 2015-10-14 | ELKANKONSTRAK DEVELOPMENT CORPORATION
4326 | NC 2014 | SHS (2014) | Region V | ALBAY | 309512 | San Miguel HS | OAS | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6554337.6381 |  |  | COMPLETED | 1 | 2016-08-18 |  | 050114S00104 | 15FO0051 | 2015-09-08 | 2015-09-09 | 2015-09-22 | 2015-10-23 | 2015-12-29 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
4327 | NC 2014 | SHS (2014) | Region V | ALBAY | 309521 | San Ramon HS | LIBON | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-15 |  | 050114S00103 | 15FO0023 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-24 | 2015-09-11 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
4328 | NC 2014 | K10 (2014) | Region V | Albay | 111754 | San Vicente ES | JOVELLAR | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 050114S00010 | 14FO0011 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-05 | CPR CONSTRUCTION AND SUPPLY
4329 | NC 2014 | K10 (2014) | Region V | Albay | 111944 | San Vicente ES | OAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 050114S00006 | 14FO0014 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-18 | CPR CONSTRUCTION AND SUPPLY
4330 | NC 2014 | SHS (2014) | Region V | ALBAY | 301877 | San Vicente NHS | LIBON | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6394337.6381 |  |  | COMPLETED | 1 | 2016-05-14 |  | 050114S00102 | 15FO0053 | 2015-09-08 | 2015-09-09 | 2015-09-22 | 2015-10-29 | 2015-12-10 | PRECIOUS CONSTRUCTION
4331 | NC 2014 | K10 (2014) | Region V | Albay | 111998 | Sta. Cruz ES | POLANGUI | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 050114S00039 | 14FO0014 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-18 | CPR CONSTRUCTION AND SUPPLY
4332 | NC 2014 | K10 (2014) | Region V | Albay | 111975 | Sto. Cristo ES | PIO DURAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1874740.174 |  |  | COMPLETED | 1 | 2016-01-19 |  | 050114S00081 | 15FO0026 | 2015-08-04 | 2015-08-05 | 2015-08-17 | 2015-09-03 | 2015-09-15 | EUGE CONSTRUCTION AND SUPPLY
4333 | NC 2014 | K10 (2014) | Region V | Albay | 111999 | Sugcad ES | POLANGUI | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 050114S00031 | 14FO0014 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-18 | CPR CONSTRUCTION AND SUPPLY
4334 | NC 2014 | K10 (2014) | Region V | Albay | 111756 | Tagas ES | JOVELLAR | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 050114S00011 | 14FO0011 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-05 | CPR CONSTRUCTION AND SUPPLY
4335 | NC 2014 | K10 (2014) | Region V | Albay | 111805 | Tagbac ES | LIBON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 050114S00018 | 14FO0012 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-26 | QDC CONSTRUCTION AND SUPPLY
4336 | NC 2014 | K10 (2014) | Region V | Albay | 111926 | Tobgon ES | OAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 050114S00017 | 14FO0014 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-18 | CPR CONSTRUCTION AND SUPPLY
4337 | NC 2014 | SHS (2014) | Region V | ALBAY | 309501 | Tobog High School | OAS | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6504337.6381 |  |  | COMPLETED | 1 | 2016-08-18 |  | 050114S00101 | 15FO0051 | 2015-09-08 | 2015-09-09 | 2015-09-22 | 2015-10-23 | 2015-12-28 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
4338 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112241 | Alfonso Dasco ES | PARACALE | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-11-23 | 050214S00038 | 14FC0060 | 2014-07-22 | 2014-07-31 | 2014-08-07 | 2014-08-18 | 2014-08-26 | YSA CONSTRUCTION AND SUPPLY
4339 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301886 | Bagong Silang I HS | LABO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 050214S00077 | 15FC0132 | 2015-07-16 | 2015-07-24 | 2015-08-07 | 2015-08-14 | 2015-08-28 | M.J. APIN BUILDERS
4340 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301887 | Bagong Silang II NHS | LABO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-21 |  | 050214S00078 | 15FC0133 | 2015-07-16 | 2015-07-24 | 2015-08-07 | 2015-08-13 | 2015-08-25 | EUS CONSTRUCTION
4341 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112278 | Basiad ES | SANTA ELENA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 050214S00039 | 14FC0057 | 2014-07-22 | 2014-07-31 | 2014-08-07 | 2014-09-16 | 2014-09-22 | SHEAR CONSTRUCTION AND SUPPLY
4342 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301890 | Batobalani NHS | PARACALE | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8270565.051 |  |  | COMPLETED | 1 | 2016-01-23 |  | 050214S00079 | 15FC0139 | 2015-07-16 | 2015-07-24 | 2015-08-10 | 2015-08-17 | 2015-08-27 | YSA CONSTRUCTION AND SUPPLY
4343 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309616 | Bulala HS | SANTA ELENA | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-21 |  | 050214S00080 | 15FC0161 | 2015-07-23 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-17 | YSA CONSTRUCTION AND SUPPLY
4344 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112149 | Calero ES | JOSE PANGANIBAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 050214S00040 | 14FC0044 | 2014-07-22 | 2014-07-31 | 2014-07-31 | 2014-08-13 | 2014-08-18 | SHEAR CONSTRUCTION AND SUPPLY
4345 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112215 | Cleofas R. Dando ES (Malangcao Basud) | LABO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-11-23 | 050214S00041 | 14FC0040 | 2014-07-22 | 2014-07-31 | 2014-07-31 | 2014-08-08 | 2014-08-18 | JCO CONSTRUCTION AND SUPPLY
4346 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112206 | Daguit ES | LABO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-11-23 | 050214S00042 | 14FC0041 | 2014-07-22 | 2014-07-31 | 2014-07-31 | 2014-08-08 | 2014-08-18 | SHEAR CONSTRUCTION AND SUPPLY
4347 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301893 | Daguit NHS | LABO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-03 |  | 050214S00081 | 15FC0134 | 2015-07-16 | 2015-07-24 | 2015-09-07 | 2015-09-18 | 2015-09-29 | HERBANA BUILDERS AND SUPPLY
4348 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 173013 | Dancalan ES | PARACALE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1151329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 050214S00049 | 14FC0080 | 2014-08-07 | 2014-08-27 | 2014-08-27 | 2014-09-08 | 2014-09-11 | YSA CONSTRUCTION AND SUPPLY
4349 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301897 | Delia Diezmo NHS | CAPALONGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 050214S00082 | 15FC0129 | 2015-07-16 | 2015-07-24 | 2015-08-07 | 2015-08-13 | 2015-08-25 | M.J. APIN BUILDERS
4350 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309617 | Dumagmang IS | LABO | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-08 |  | 050214S00093 | 15FC0159 | 2015-07-23 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-11 | JURASSIC CONSTRUCTION & SUPPLIES
4351 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301888 | E.P. Borja HS (Basiad NHS) | SANTA ELENA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4352 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301888 | E.P. Borja HS (Basiad NHS) | SANTA ELENA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
4353 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112281 | Earth'S Bounty ES | SANTA ELENA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-11-23 | 050214S00035 | 14FC0058 | 2014-07-22 | 2014-07-28 | 2014-08-07 | 2014-08-18 | 2014-08-26 | SHEAR CONSTRUCTION AND SUPPLY
4354 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112204 | F. Caudilla E/S | LABO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1866830.1109 |  |  | COMPLETED | 1 | 2015-11-24 |  | 050214S00066 | 15FC0146 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-17 | 2015-08-27 | JCO CONSTRUCTION AND SUPPLY
4355 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112209 | Florence ES | LABO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 050214S00044 | 14FC0083 | 2014-08-07 | 2014-08-15 | 2014-08-27 | 2014-09-08 | 2014-09-12 | SHEAR CONSTRUCTION AND SUPPLY
4356 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112116 | Francisco V. Aler ES | CAPALONGA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1156329.12 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 050214S00045 | 14FC0092 | 2014-08-08 | 2014-08-15 | 2014-08-29 | 2014-09-18 | 2014-09-23 | SHEAR CONSTRUCTION AND SUPPLY
4357 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112184 | Gavino Vinzons ES | LABO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 050214S00046 | 14FC0042 | 2014-07-22 | 2014-07-31 | 2014-07-31 | 2014-08-08 | 2014-08-18 | LAHDETH CONSTRUCTION AND SUPPLY
4358 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309619 | Gawad Kalinga HS | JOSE PANGANIBAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-08 |  | 050214S00074 | 15FC0158 | 2015-07-24 | 2015-08-20 | 2015-08-20 | 2015-09-01 | 2015-09-11 | R.G. VILLAFUERTE CONSTRUCTION
4359 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112247 | Gumaus ES | PARACALE | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-12-09 | 2014-12-09 | 050214S00047 | 14FC0081 | 2014-08-07 | 2014-08-15 | 2014-08-27 | 2014-09-08 | 2014-09-11 | JCO CONSTRUCTION AND SUPPLY
4360 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301911 | Gumaus NHS | PARACALE | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-23 |  | 050214S00076 | 15FC0140 | 2015-07-16 | 2015-07-24 | 2015-08-10 | 2015-08-17 | 2015-08-27 | M.J. APIN BUILDERS
4361 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4362 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15390827.92 |  |  | COMPLETED | 1
4363 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112112 | Jueves-Talento ES (Catabaguangan) | CAPALONGA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 050214S00058 | 14FC0045 | 2014-07-15 | 2014-07-31 | 2014-07-31 | 2014-08-08 | 2014-08-18 | SHEAR CONSTRUCTION AND SUPPLY
4364 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112210 | Kabatuhan ES | LABO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 050214S00057 | 14FC0093 | 2014-08-08 | 2014-08-15 | 2014-08-29 | 2014-09-18 | 2014-09-23 | ARIK CONSTRUCTION
4365 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301899 | Labo National High School | LABO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4366 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301899 | Labo National High School | LABO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
4367 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301894 | Labo Science and Tech. HS | LABO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1
4368 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301894 | Labo Science and Tech. HS | LABO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8748965.051 |  |  | COMPLETED | 1
4369 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301901 | Larap NHS with Annex (CNCEA) | JOSE PANGANIBAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-21 |  | 050214S00088 | 15FC0131 | 2015-07-16 | 2015-07-24 | 2015-08-07 | 2015-08-14 | 2015-08-25 | SHEAR CONSTRUCTION AND SUPPLY
4370 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301917 | Leocadio Alejo Entienza HS | SANTA ELENA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 050214S00059 | 14FC0090 | 2014-08-08 | 2014-08-15 | 2014-08-29 | 2014-09-18 | 2014-09-23 | LAHDETH CONSTRUCTION AND SUPPLY
4371 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112117 | Lukbanan ES | CAPALONGA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 050214S00052 | 14FC0074 | 2014-08-07 | 2014-08-15 | 2014-08-27 | 2014-09-08 | 2014-09-11 | JCO CONSTRUCTION AND SUPPLY
4372 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112153 | Luna ES | JOSE PANGANIBAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 050214S00051 | 14FC0078 | 2014-08-07 | 2014-08-15 | 2014-08-27 | 2014-09-08 | 2014-09-12 | GOLDEN CONSTRUCTION AND SUPPLY
4373 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112216 | Malatap ES | LABO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1047049.6543 |  |  | COMPLETED | 1 | 2015-11-27 |  | 050214S00067 | 15FC0147 | 2015-07-16 | 2015-07-24 | 2015-09-07 | 2015-09-18 | 2015-09-29 | VC VARIN CONSTRUCTION AND HARDWARE SUPPLY
4374 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112217 | Malaya ES | LABO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 050214S00054 | 14FC0084 | 2014-08-07 | 2014-08-15 | 2014-08-27 | 2014-09-08 | 2014-09-12 | LAHDETH CONSTRUCTION AND SUPPLY
4375 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309602 | Maulawin HS | SANTA ELENA | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-14 |  | 050214S00089 | 15FC0162 | 2015-07-23 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-17 | SHEAR CONSTRUCTION AND SUPPLY
4376 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309621 | MAXIMO MANARANG HIGH SCHOOL | PARACALE | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-14 |  | 050214S00090 | 15FC0160 | 2015-07-23 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-17 | M.J. APIN BUILDERS
4377 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112121 | Necio Olila ES | CAPALONGA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-11-23 | 050214S00048 | 14FC0063 | 2014-07-22 | 2014-07-28 | 2014-08-07 | 2014-08-18 | 2014-08-26 | SHEAR CONSTRUCTION AND SUPPLY
4378 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112154 | Osmena ES (Lukban ES) | JOSE PANGANIBAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-11-12 | 2014-11-10 | 050214S00056 | 14FC0075 | 2014-08-07 | 2014-08-15 | 2014-08-27 | 2014-09-05 | 2014-09-10 | JCO CONSTRUCTION AND SUPPLY
4379 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301908 | Pag-Asa High School | LABO | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-18 |  | 050214S00091 | 15FC0136 | 2015-07-16 | 2015-07-24 | 2015-09-18 | 2015-10-14 | 2015-10-15 | BRENTMIN ROOFING ENTERPRISE
4380 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112220 | Palali ES | LABO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 050214S00036 | 14FC0082 | 2014-08-07 | 2014-08-15 | 2014-08-27 | 2014-09-10 | 2014-09-12 | EUS CONSTRUCTION
4381 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112254 | Paracale Central School | PARACALE | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-08 |  | 050214S00063 | 15FC0163 | 2015-07-23 | 2015-08-18 | 2015-08-20 | 2015-09-01 | 2015-09-11 | JOMAR BUILDERS & SUPPLY
4382 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301910 | Paracale NHS | PARACALE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4383 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301910 | Paracale NHS | PARACALE | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11069842.5917 |  |  | COMPLETED | 1
4384 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112283 | Pulongguit-Guit ES | SANTA ELENA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1116329.12 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 050214S00015 | 14FC0089 | 2014-08-08 | 2014-08-15 | 2014-08-29 | 2014-09-18 | 2014-09-22 | LAHDETH CONSTRUCTION AND SUPPLY
4385 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112237 | Quinapaguian ES | MERCEDES | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2843319.8632 |  |  | COMPLETED | 1 | 2015-12-24 |  | 050214S00064 | 15FC0148 | 2015-07-16 | 2015-07-24 | 2015-08-10 | 2015-08-17 | 2015-08-27 | SHEAR CONSTRUCTION AND SUPPLY
4386 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112284 | R. Oquindo ES | SANTA ELENA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2018417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-11-20 | 050214S00014 | 14FC0088 | 2014-08-08 | 2014-08-15 | 2014-08-29 | 2014-09-17 | 2014-09-22 | LAHDETH CONSTRUCTION AND SUPPLY
4387 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112152 | Regino A. Yet ES (Luklukan Sur ES) | JOSE PANGANIBAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 050214S00004 | 14FC0077 | 2014-08-07 | 2014-08-15 | 2014-08-27 | 2014-09-09 | 2014-09-11 | VC VARIN CONSTRUCTION AND HARDWARE SUPPLY
4388 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301913 | Rizal NHS | SANTA ELENA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8492965.051 |  |  | COMPLETED | 1 | 2016-01-23 |  | 050214S00085 | 15FC0143 | 2015-07-16 | 2015-07-24 | 2015-08-10 | 2015-08-17 | 2015-08-27 | SHEAR CONSTRUCTION AND SUPPLY
4389 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112286 | Salvacion ES | SANTA ELENA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1148329.12 |  |  | COMPLETED | 1 | 2014-12-05 | 2014-12-05 | 050214S00013 | 14FC0091 | 2014-08-08 | 2014-08-15 | 2014-08-29 | 2014-09-22 | 2014-09-23 | SHEAR CONSTRUCTION AND SUPPLY
4390 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112167 | San Jose ES | JOSE PANGANIBAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 050214S00018 | 14FC0076 | 2014-08-08 | 2014-08-15 | 2014-08-27 | 2014-09-05 | 2014-09-11 | VC VARIN CONSTRUCTION AND HARDWARE SUPPLY
4391 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309618 | San Pedro-Domingo Llarena HS | SANTA ELENA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-23 |  | 050214S00072 | 15FC0144 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-17 | 2015-08-27 | SHEAR CONSTRUCTION AND SUPPLY
4392 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112125 | San Roque ES | CAPALONGA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1140329.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 050214S00012 | 14FC0073 | 2014-08-07 | 2014-08-15 | 2014-08-27 | 2014-09-05 | 2014-09-12 | ARIK CONSTRUCTION
4393 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112126 | Sotero Mago ES | CAPALONGA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-24 | 2014-11-24 | 050214S00011 | 14FC0062 | 2014-07-22 | 2014-07-31 | 2014-08-07 | 2014-08-18 | 2014-08-27 | GOLDEN CONSTRUCTION AND SUPPLY
4394 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112258 | Sta. Catalina ES | PARACALE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 050214S00009 | 14FC0048 | 2014-07-22 | 2014-07-31 | 2014-07-31 | 2014-08-08 | 2014-08-18 | LAHDETH CONSTRUCTION AND SUPPLY
4395 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301920 | Sta. Cruz NHS | JOSE PANGANIBAN | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-04-23 |  | 050214S00070 | 15FC0128 | 2015-07-16 | 2015-07-24 | 2015-08-07 | 2015-08-14 | 2015-08-25 | SHEAR CONSTRUCTION AND SUPPLY
4396 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301912 | Tabas NHS | PARACALE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4397 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301912 | Tabas NHS | PARACALE | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
4398 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-21 |  | 050214S00075 | 15FC0137 | 2015-07-16 | 2015-07-24 | 2015-08-07 | 2015-08-12 | 2015-08-25 | SHEAR CONSTRUCTION AND SUPPLY
4399 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301921 | Tigbinan NHS | LABO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-23 |  | 050214S00073 | 15FC0138 | 2015-07-16 | 2015-07-24 | 2015-08-10 | 2015-08-14 | 2015-08-27 | SHEAR CONSTRUCTION AND SUPPLY
4400 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301922 | Tulay Na Lupa NHS | LABO | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10888242.5917 |  |  | COMPLETED | 1
4401 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112174 | Ulipanan ELementary School | JOSE PANGANIBAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 050214S00008 | 14FC0079 | 2014-08-07 | 2014-08-15 | 2014-08-27 | 2014-09-08 | 2014-09-12 | SHEAR CONSTRUCTION AND SUPPLY
4402 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112175 | V. Gabo ES | JOSE PANGANIBAN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2015-12-24 |  | 050214S00065 | 15FC0145 | 2015-07-16 | 2015-07-24 | 2015-08-10 | 2015-08-17 | 2015-08-27 | SHEAR CONSTRUCTION AND SUPPLY
4403 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309610 | Victoria Tuacar HS | CAPALONGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-19 |  | 050214S00095 | 15FC0130 | 2015-07-16 | 2015-07-24 | 2015-09-18 | 2015-10-05 | 2015-10-15 | SHEAR CONSTRUCTION AND SUPPLY
4404 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112298 | Banocboc ES | VINZONS | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3820258.5709 |  |  | COMPLETED | 1 | 2015-05-10 | 2015-05-10 | 050214S00060 | 14FC0151 | 2014-11-03 | 2014-11-07 | 2014-11-19 | 2014-11-26 | 2014-12-10 | JCO CONSTRUCTION AND SUPPLY
4405 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301889 | Basud NHS | BASUD | 2 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 | 2016-06-21 |  | 050214S00109 | 15FC0171 | 2015-07-30 | 2015-08-18 | 2015-08-19 | 2015-11-23 | 2015-11-25 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
4406 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301891 | Camarines Norte National HS | DAET (Capital) | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-04-21 |  | 050214S00112 | 15FC0127 | 2015-07-16 | 2015-07-24 | 2015-08-07 | 2015-08-14 | 2015-08-24 | EUS CONSTRUCTION
4407 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 309603 | Caringo HS (San Roque NHS Annex) | MERCEDES | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2098417.57 |  |  | COMPLETED | 1
4408 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309603 | Caringo HS (San Roque NHS Annex) | MERCEDES | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
4409 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112222 | Cayucyucan ES | MERCEDES | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 050214S00007 | 14FC0050 | 2014-07-22 | 2014-07-31 | 2014-07-31 | 2014-08-08 | 2014-08-18 | LAHDETH CONSTRUCTION AND SUPPLY
4410 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301892 | D. Q. Liwag NHS | VINZONS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-21 |  | 050214S00108 | 15FC0124 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-14 | 2015-08-24 | JCO CONSTRUCTION AND SUPPLY
4411 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309611 | Dominador Narido HS | BASUD | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050214S00114 | 15FC0114 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-14 | 2015-08-24 | ARIK CONSTRUCTION
4412 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309604 | Eugenia M. Quintela Memorial HS | VINZONS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-04-13 |  | 050214S00119 | 15FC0216 | 2015-10-08 | 2015-10-16 | 2015-10-28 | 2015-11-06 | 2015-11-16 | KV CONSTRUCTION & SUPPLY
4413 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309605 | Fabrica HS | SAN VICENTE | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-31 |  | 050214S00116 | 15FC0155 | 2015-07-23 | 2015-08-19 | 2015-08-20 | 2015-08-24 | 2015-09-02 | JCO CONSTRUCTION AND SUPPLY
4414 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301919 | Froilan Lopez HS ( V) | SAN VICENTE | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050214S00117 | 15FC0123 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-12 | 2015-08-24 | SHEAR CONSTRUCTION AND SUPPLY
4415 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301895 | Gonzalez Ascutia HS | TALISAY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-04 |  | 050214S00118 | 15FC0156 | 2015-07-23 | 2015-08-19 | 2015-08-20 | 2015-08-28 | 2015-09-07 | PRECIOUS CONSTRUCTION
4416 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112089 | Guinatungan ES | BASUD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 050214S00006 | 14FC0054 | 2014-07-22 | 2014-07-31 | 2014-07-31 | 2014-08-13 | 2014-08-18 | LAHDETH CONSTRUCTION AND SUPPLY
4417 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112090 | Hinampacan ES | BASUD | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2018417.57 |  |  | COMPLETED | 1 | 2014-12-13 | 2014-12-13 | 050214S00010 | 14FC0096 | 2014-08-08 | 2014-08-15 | 2014-08-29 | 2014-09-05 | 2014-09-15 | GOLDEN CONSTRUCTION AND SUPPLY
4418 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112227 | Hinipaan Elementary School | MERCEDES | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 050214S00003 | 14FC0053 | 2014-07-22 | 2014-07-31 | 2014-07-31 | 2014-08-08 | 2014-08-18 | GOLDEN CONSTRUCTION AND SUPPLY
4419 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112228 | Lalawigan ES | MERCEDES | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-12-13 | 2014-12-13 | 050214S00005 | 14FC0099 | 2014-08-08 | 2014-08-15 | 2014-08-29 | 2014-09-05 | 2014-09-15 | GREAT WALL ENGINEERING
4420 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301900 | Lalawigan NHS | MERCEDES | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2170417.57 |  |  | COMPLETED | 1
4421 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301900 | Lalawigan NHS | MERCEDES | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
4422 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309607 | Lazaro Cabezudo HS | TALISAY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-14 |  | 050214S00096 | 15FC0157 | 2015-07-23 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-17 | SHEAR CONSTRUCTION AND SUPPLY
4423 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112230 | Lope Manlangit ES | MERCEDES | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2082417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 050214S00027 | 14FC0098 | 2014-08-08 | 2014-08-15 | 2014-08-29 | 2014-09-16 | 2014-09-23 | GOLDEN CONSTRUCTION AND SUPPLY
4424 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112231 | Mambungalon ES | MERCEDES | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 050214S00033 | 14FC0049 | 2014-07-15 | 2014-07-24 | 2014-07-31 | 2014-08-13 | 2014-08-18 | SHEAR CONSTRUCTION AND SUPPLY
4425 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112092 | Mampili ES | BASUD | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-11-23 | 050214S00032 | 14FC0064 | 2014-07-22 | 2014-07-31 | 2014-08-07 | 2014-08-18 | 2014-08-26 | SHEAR CONSTRUCTION AND SUPPLY
4426 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112309 | Mangcayo ES | VINZONS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2066417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 050214S00031 | 14FC0095 | 2014-08-08 | 2014-08-15 | 2014-08-29 | 2014-09-22 | 2014-09-22 | VC VARIN CONSTRUCTION AND HARDWARE SUPPLY
4427 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112232 | Manguisoc ES | MERCEDES | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 050214S00030 | 14FC0051 | 2014-07-15 | 2014-07-28 | 2014-07-31 | 2014-08-13 | 2014-08-18 | GREAT WALL ENGINEERING
4428 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301902 | Manguisoc NHS | MERCEDES | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4429 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301902 | Manguisoc NHS | MERCEDES | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
4430 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301904 | MATANGO NATIONAL HIGH SCHOOL | VINZONS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
4431 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301904 | Matango NHS | VINZONS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4432 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
4433 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
4434 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301907 | Pablo S. Villafuerte HS | MERCEDES | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
4435 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301907 | Pablo S. Villafuerte HS | MERCEDES | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
4436 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112236 | Pambuhan ES | MERCEDES | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2937174.43 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 050214S00034 | 14FC0102 | 2014-08-08 | 2014-08-15 | 2014-08-29 | 2014-09-16 | 2014-09-22 | GOLDEN CONSTRUCTION AND SUPPLY
4437 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301909 | Pambuhan NHS | MERCEDES | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050214S00106 | 15FC0121 | 2015-07-16 | 2015-07-24 | 2015-08-11 | 2015-08-14 | 2015-08-24 | SHEAR CONSTRUCTION AND SUPPLY
4438 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 112313 | Pinagtigasan ES | VINZONS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2130417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 050214S00025 | 14FC0086 | 2014-08-07 | 2014-08-15 | 2014-08-27 | 2014-09-05 | 2014-09-12 | JCO CONSTRUCTION AND SUPPLY
4439 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309612 | Porfirio R. Ponayo HS | DAET (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050214S00105 | 15FC0116 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-14 | 2015-08-24 | PING-ANNs CONSTRUCTION & TRADING
4440 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301914 | Sabang NHS | VINZONS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1
4441 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301914 | Sabang NHS | VINZONS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
4442 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301915 | San Felipe NHS | BASUD | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1
4443 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301915 | San Felipe NHS | BASUD | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8353965.051 |  |  | COMPLETED | 1
4444 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301916 | San Francisco NHS | TALISAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4445 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301916 | San Francisco NHS | TALISAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8492965.051 |  |  | COMPLETED | 1
4446 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309606 | San Isidro HS (Alcantara) | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-31 |  | 050214S00101 | 15FC0153 | 2015-07-23 | 2015-08-13 | 2015-08-14 | 2015-08-24 | 2015-09-03 | YSA CONSTRUCTION AND SUPPLY
4447 | NC 2014 | K10 (2014) | Region V | Camarines Norte | 301903 | San Lorenzo Ruiz NHS (Matacong NHS) | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4448 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301903 | San Lorenzo Ruiz NHS (Matacong NHS) | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1
4449 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301918 | San Roque National High School | MERCEDES | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8409565.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 050214S00099 | 15FC0150 | 2015-07-23 | 2015-08-13 | 2015-08-14 | 2015-08-24 | 2015-09-03 | EUS CONSTRUCTION
4450 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309620 | Sarah Jane Ferrer HS | VINZONS | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6602337.6381 |  |  | COMPLETED | 1 | 2016-02-03 |  | 050214S00094 | 15FC0178 | 2015-08-14 | 2015-09-04 | 2015-09-07 | 2015-09-18 | 2015-10-07 | JCO CONSTRUCTION AND SUPPLY
4451 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 309608 | Tuaca HS | BASUD | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050214S00098 | 15FC0113 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-12 | 2015-08-24 | SHEAR CONSTRUCTION AND SUPPLY
4452 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301924 | Vicente L. Basit Mem. HS (Awitan NHS) | DAET (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 050214S00110 | 15FC0115 | 2015-07-16 | 2015-07-24 | 2015-08-05 | 2015-08-12 | 2015-08-24 | ARIK CONSTRUCTION
4453 | NC 2014 | SHS (2014) | Region V | Camarines Norte | 301925 | Vinzons Pilot High School | VINZONS | 2 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 | [10 empty] | With Approved Buffer Fund (2018 Batch 4)
4454 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112457 | Biong ES | CABUSAO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-23 | 2014-12-23 | 050314S00176 | 14FN0017 | 2014-07-08 | 2014-07-09 | 2014-07-22 | 2014-08-13 | 2014-08-26 | PBL BUILDERS & SUPPLY
4455 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112955 | Caditaan PS | RAGAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1894740.174 |  |  | COMPLETED | 1 | 2015-12-06 | 2015-12-04 | 050314S00271 | 15FN0047 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-09-04 | 2015-09-08 | DREAM BUILDERS AND TECH DEV. CORP.
4456 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301958 | Casay PHS | LUPI | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
4457 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112745 | Lupi CS | LUPI | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-12-23 | 2014-12-23 | 050314S00167 | 14FN0017 | 2014-07-08 | 2014-07-09 | 2014-07-22 | 2014-08-13 | 2014-08-26 | PBL BUILDERS & SUPPLY
4458 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301996 | Mansalaya National High School | DEL GALLEGO | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-12-07 | 050314S00295 | 15FN0042 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-07 | 2015-08-11 | A.B. OPENA BUILDERS
4459 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309750 | RNAFS - Cristobal D. Aquino Memorial Annex High School | RAGAY | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-12-07 | 050314S00287 | 15FN0042 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-07 | 2015-08-11 | A.B. OPENA BUILDERS
4460 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112970 | Salvacion ES | RAGAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1052049.6543 |  |  | COMPLETED | 1 | 2015-12-06 | 2015-12-04 | 050314S00270 | 15FN0047 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-09-04 | 2015-09-08 | DREAM BUILDERS AND TECH DEV. CORP.
4461 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309717 | San Vicente HS | SIPOCOT | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-02-04 |  | 050314S00286 | 15FN0046 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-09-04 | 2015-09-08 | A.B. OPENA BUILDERS
4462 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113069 | Sta. Cruz ES | SIPOCOT | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | REVERTED | 0
4463 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113093 | Tara ES | SIPOCOT | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-10-02 | 2014-10-02 | 050314S00151 | 14FN0016 | 2014-07-03 | 2014-07-04 | 2014-07-17 | 2014-07-22 | 2014-08-04 | AE BELLEZA BUILDERS
4464 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112700 | Bagamelon ES | LIBMANAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 050314S00156 | 14FD0013 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-01 | 2014-09-18 | HRB CONSTRUCTION
4465 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112791 | Bagongbong ES | MINALABAC | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-14 | 050314S00168 | 14FD0016 | 2014-07-10 | 2014-07-10 | 2014-07-24 | 2014-08-05 | 2014-08-20 | EDROX CONSTRUCTION, INC.
4466 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112701 | Bahao ES | LIBMANAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-12-15 | 050314S00157 | 14FD0015 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-02 | 2014-09-18 | MEGAY CONSTRUCTION AND SUPPLY
4467 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112672 | Bahay ES | LIBMANAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-12-15 | 050314S00153 | 14FD0015 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-02 | 2014-09-18 | MEGAY CONSTRUCTION AND SUPPLY
4468 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301936 | Bahay PHS | LIBMANAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1
4469 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112772 | Bal-Flor ES | MILAOR | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-14 | 050314S00164 | 14FD0012 | 2014-07-10 | 2014-07-10 | 2014-07-24 | 2014-07-28 | 2014-09-18 | BOROBUDUR CONSTRUCTION
4470 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112704 | Bikal ES | LIBMANAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1
4471 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112997 | Bocal ES | SAN FERNANDO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 050314S00124 | 14FD0018 | 2014-07-13 | 2014-07-15 | 2014-07-28 | 2014-08-05 | 2014-08-20 | R.K.X. ODIAMAR CONSTRUCTION
4472 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309757 | Cagbibi HS | PAMPLONA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-29 | 2015-10-29 | 050314S00285 | 15FD0021 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-07 | 2015-07-22 | ROLA CONSTRUCTION
4473 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112868 | Cagbunga ES | PAMPLONA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 050314S00175 | 14FD0018 | 2014-07-13 | 2014-07-15 | 2014-07-28 | 2014-08-05 | 2014-08-20 | R.K.X. ODIAMAR CONSTRUCTION
4474 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112706 | Calabnigan ES | LIBMANAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 050314S00159 | 14FD0013 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-01 | 2014-09-18 | HRB CONSTRUCTION
4475 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112776 | Capucnasan ES | MILAOR | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-14 | 050314S00150 | 14FD0012 | 2014-07-10 | 2014-07-10 | 2014-07-24 | 2014-07-28 | 2014-09-18 | BOROBUDUR CONSTRUCTION
4476 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112902 | Caranan ES (North) | PASACAO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-03-25 | 050314S00136 | 14FD0019 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-02 | 2014-09-18 | GRELIPS CONSTRUCTION & DEVELOPMENT
4477 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112903 | Caranan ES (South) | PASACAO | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8298803.2031 |  |  | COMPLETED | 1 | 2015-07-17 | 2015-07-15 | 050314S00247 | 14FD0035 | 2014-12-07 | 2014-12-09 | 2014-12-22 | 2014-12-29 | 2015-01-05 | V.S. CERDON IRON WORKS & CONSTRUCTION
4478 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112676 | Concepcion ES | LIBMANAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 050314S00154 | 14FD0013 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-01 | 2014-09-18 | HRB CONSTRUCTION
4479 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112905 | Cuco ES | PASACAO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-03-25 | 050314S00165 | 14FD0019 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-02 | 2014-09-18 | GRELIPS CONSTRUCTION & DEVELOPMENT
4480 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309723 | Del Rosario National HS | PAMPLONA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-29 | 2015-10-29 | 050314S00284 | 15FD0021 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-09 | 2015-07-22 | ROLA CONSTRUCTION
4481 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112796 | Del Socorro ES | MINALABAC | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 050314S00169 | 14FD0017 | 2014-07-13 | 2014-07-15 | 2014-07-28 | 2014-08-05 | 2014-08-20 | R.K.X. ODIAMAR CONSTRUCTION
4482 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309744 | Don Mariano C. San Juan HS | LIBMANAN | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-29 | 2015-10-29 | 050314S00274 | 15FD0022 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-07 | 2015-07-22 | CHA CONSTRUCTION & SUPPLY
4483 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301968 | Don Mariano C. Veneracion HS | PAMPLONA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1
4484 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112799 | Irayang Solong ES | MINALABAC | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-14 | 050314S00170 | 14FD0016 | 2014-07-10 | 2014-07-10 | 2014-07-24 | 2014-08-05 | 2014-08-20 | EDROX CONSTRUCTION, INC.
4485 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112800 | Magadap ES | MINALABAC | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-14 | 050314S00171 | 14FD0016 | 2014-07-10 | 2014-07-10 | 2014-07-24 | 2014-08-05 | 2014-08-20 | EDROX CONSTRUCTION, INC.
4486 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112801 | Malitbog ES | MINALABAC | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-12-20 | 2015-12-20 | 050314S00268 | 15FD0030 | 2015-07-08 | 2015-07-09 | 2015-07-22 | 2015-07-28 | 2015-08-13 | V.S. CERDON IRON WORKS & CONSTRUCTION
4487 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301993 | Mambayawas HS | LIBMANAN | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-29 | 2015-10-29 | 050314S00276 | 15FD0023 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-07 | 2015-07-22 | CHA CONSTRUCTION & SUPPLY
4488 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112802 | Manapao ES | MINALABAC | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 050314S00172 | 14FD0017 | 2014-07-13 | 2014-07-15 | 2014-07-28 | 2014-08-05 | 2014-08-20 | R.K.X. ODIAMAR CONSTRUCTION
4489 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309711 | Mantalisay HS | LIBMANAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1
4490 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112689 | Padlos ES | LIBMANAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-07 | 050314S00155 | 14FD0014 | 2014-08-12 | 2014-08-13 | 2014-08-16 | 2014-09-01 | 2014-09-15 | E.N. DADUYA CONSTRUCTION SUPPLIES
4491 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302009 | Palangon High School | LIBMANAN | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-29 | 2015-10-29 | 050314S00277 | 15FD0022 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-07 | 2015-07-22 | CHA CONSTRUCTION & SUPPLY
4492 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112911 | Pasacao CS | PASACAO | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-20 | 2015-12-20 | 050314S00269 | 15FD0030 | 2015-07-08 | 2015-07-09 | 2015-07-22 | 2015-07-28 | 2015-08-13 | V.S. CERDON IRON WORKS & CONSTRUCTION
4493 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309705 | Pinamasagan HS | SAN FERNANDO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2035417.57 |  |  | COMPLETED | 1
4494 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309764 | R.T. Subastil Memorial HS | MILAOR | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-23 | 2015-09-23 | 050314S00283 | 15FD0024 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-07 | 2015-07-16 | E.S. BIHAG CONSTRUCTION & SUPPLY
4495 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112717 | Salvacion ES | LIBMANAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-12-15 | 050314S00160 | 14FD0015 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-02 | 2014-09-18 | MEGAY CONSTRUCTION AND SUPPLY
4496 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112913 | Salvacion ES | PASACAO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-03-25 | 050314S00163 | 14FD0019 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-02 | 2014-09-18 | GRELIPS CONSTRUCTION & DEVELOPMENT
4497 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112786 | Sampaloc ES | GAINZA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-14 | 050314S00166 | 14FD0012 | 2014-07-10 | 2014-07-10 | 2014-07-24 | 2014-07-28 | 2014-09-18 | BOROBUDUR CONSTRUCTION
4498 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112914 | San Antonio Elementary School | PASACAO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-03-25 | 050314S00123 | 14FD0019 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-02 | 2014-09-18 | GRELIPS CONSTRUCTION & DEVELOPMENT
4499 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112807 | San Antonio ES | MINALABAC | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-14 | 050314S00173 | 14FD0016 | 2014-07-10 | 2014-07-10 | 2014-07-24 | 2014-08-05 | 2014-08-20 | EDROX CONSTRUCTION, INC.
4500 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113010 | San Joaquin ES | SAN FERNANDO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 050314S00125 | 14FD0018 | 2014-07-13 | 2014-07-15 | 2014-07-28 | 2014-08-05 | 2014-08-20 | R.K.X. ODIAMAR CONSTRUCTION
4501 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112720 | Sogod PS | LIBMANAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-12-15 | 050314S00161 | 14FD0015 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-02 | 2014-09-18 | MEGAY CONSTRUCTION AND SUPPLY
4502 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112813 | Upper Anayan PS | MINALABAC | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 050314S00174 | 14FD0017 | 2014-07-13 | 2014-07-15 | 2014-07-28 | 2014-08-05 | 2014-08-20 | R.K.X. ODIAMAR CONSTRUCTION
4503 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112724 | Villa Socorro PS | LIBMANAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-07 | 050314S00162 | 14FD0014 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-01 | 2014-09-15 | E.N. DADUYA CONSTRUCTION SUPPLIES
4504 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112725 | Villadima ES | LIBMANAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-07 | 050314S00178 | 14FD0014 | 2014-08-12 | 2014-08-13 | 2014-08-26 | 2014-09-01 | 2014-09-15 | E.N. DADUYA CONSTRUCTION SUPPLIES
4505 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302067 | Villamayor HS - Bagolatao Annex HS | MINALABAC | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-23 | 2015-09-23 | 050314S00279 | 15FD0024 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-07 | 2015-07-16 | E.S. BIHAG CONSTRUCTION & SUPPLY
4506 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 173513 | A. Manaog ES (Hacienda Salamat) | PILI (Capital) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-08 | 2014-12-08 | 050314S00209 | 14FE0037 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-06 | AE BELLEZA BUILDERS
4507 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112919 | Bagong Sirang ES | PILI (Capital) | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-17 | 2014-12-17 | 050314S00145 | 14FE0038 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-22 | 2014-08-14 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
4508 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 173511 | Binaliw ES | CALABANGA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-12-16 | 050314S00177 | 14FE0039 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-14 | HONEYVILLE CONSTRUCTION
4509 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112468 | Binanuaanan (P) ES | CALABANGA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 050314S00130 | 14FE0036 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-11 | CPR CONSTRUCTION AND SUPPLY
4510 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112922 | Binobong ES | PILI (Capital) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-17 | 2014-12-17 | 050314S00146 | 14FE0038 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-22 | 2014-08-14 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
4511 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112848 | Cabariwan ES | OCAMPO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-17 | 2014-10-17 | 050314S00139 | 14FE0041 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-22 | 2014-08-14 | HONEYVILLE CONSTRUCTION
4512 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112471 | Calabanga CDPS | CALABANGA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-17 | 2014-10-17 | 050314S00131 | 14FE0039 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-14 | HONEYVILLE CONSTRUCTION
4513 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301952 | Calabanga NHS | CALABANGA | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6094 |  |  | COMPLETED | 1
4514 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302052 | Camaligan National High School | CAMALIGAN | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1
4515 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309763 | Camarines Sur Sports Academy | PILI (Capital) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4516 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309763 | Camarines SurSports Academy | PILI (Capital) | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
4517 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112924 | Caroyroyan ES | PILI (Capital) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-08 | 2014-12-08 | 050314S00147 | 14FE0037 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-06 | AE BELLEZA BUILDERS
4518 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112478 | Domingo G. Gutierrez Sr ES (Frmr:Harobay ES) | CALABANGA | 3 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3062746.69 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 050314S00132 | 14FE0036 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-11 | CPR CONSTRUCTION AND SUPPLY
4519 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309719 | Doña Basilia S. Quilon Memorial High School | PILI (Capital) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4520 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112851 | Gatbo ES | OCAMPO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-17 | 2014-10-17 | 050314S00140 | 14FE0041 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-22 | 2014-08-14 | HONEYVILLE CONSTRUCTION
4521 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112852 | Guinaban ES | OCAMPO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-17 | 2014-10-17 | 050314S00141 | 14FE0041 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-22 | 2014-08-14 | HONEYVILLE CONSTRUCTION
4522 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309704 | Hanawan National HS | OCAMPO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4523 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112855 | La Purisima Nuevo ES | OCAMPO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-17 | 2014-10-17 | 050314S00142 | 14FE0041 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-22 | 2014-08-14 | HONEYVILLE CONSTRUCTION
4524 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112481 | Lugsad ES | CALABANGA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 050314S00133 | 14FE0036 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-11 | CPR CONSTRUCTION AND SUPPLY
4525 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112513 | Palo ES | CANAMAN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4526 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302018 | Pili NHS, Pili - V. Bagasina Sr. Annex MHS | PILI (Capital) | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1
4527 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309712 | Ponong Integrated School | MAGARAO | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-24 | 2015-10-24 | 050314S00278 | 15FE0079 | 2015-06-15 | 2015-06-19 | 2015-06-30 | 2015-07-06 | 2015-07-20 | PHIL MANNA CONSTRUCTION & SUPPLY
4528 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112487 | Quinale ES | CALABANGA | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 050314S00149 | 14FE0036 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-11 | CPR CONSTRUCTION AND SUPPLY
4529 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301953 | Quipayo HS | CALABANGA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4530 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112934 | R. Malanyaon ES | PILI (Capital) | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-08 | 2014-12-08 | 050314S00148 | 14FE0037 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-06 | AE BELLEZA BUILDERS
4531 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112863 | San Roque (Communal) Com Sch | OCAMPO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-17 | 2014-12-17 | 050314S00143 | 14FE0042 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-22 | 2014-08-14 | GRELIPS CONSTRUCTION & DEVELOPMENT
4532 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309707 | Siembre HS | BOMBON | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-24 | 2015-10-24 | 050314S00282 | 15FE0076 | 2015-06-15 | 2015-06-19 | 2015-06-30 | 2015-07-06 | 2015-07-20 | LAHDETH CONSTRUCTION AND SUPPLY
4533 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112939 | Soledad Marasigan ES | PILI (Capital) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-08 | 2014-12-08 | 050314S00180 | 14FE0037 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-06 | AE BELLEZA BUILDERS
4534 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112864 | Sta. Cruz ES | OCAMPO | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-17 | 2014-12-17 | 050314S00144 | 14FE0042 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-22 | 2014-08-14 | GRELIPS CONSTRUCTION & DEVELOPMENT
4535 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309735 | Sta. Cruz HS - Northern Canaman Annex HS | CANAMAN | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
4536 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309735 | Sta. Cruz HS (Northern Canaman Annex HS) | CANAMAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4537 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112520 | Sua Elementary School | CANAMAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-18 | 2014-12-18 | 050314S00137 | 14FE0040 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-14 | BOROBUDUR CONSTRUCTION
4538 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112522 | Tacolod ES - Annex | CANAMAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-18 | 2014-12-18 | 050314S00138 | 14FE0040 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-14 | BOROBUDUR CONSTRUCTION
4539 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112941 | Tagbong ES | PILI (Capital) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-17 | 2014-12-17 | 050314S00134 | 14FE0038 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-22 | 2014-08-14 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
4540 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112523 | Talidtid PS | CANAMAN | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-04-19 |  | 050314S00246 | 14FE0061 | 2014-11-27 | 2014-12-01 | 2014-12-12 | 2014-12-29 | 2015-01-13 | PHIL MANNA CONSTRUCTION & SUPPLY
4541 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112496 | Tomagodtod ES | CALABANGA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 050314S00135 | 14FE0036 | 2014-06-19 | 2014-06-26 | 2014-07-08 | 2014-07-21 | 2014-08-11 | CPR CONSTRUCTION AND SUPPLY
4542 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302065 | Union NHS | CALABANGA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4543 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301955 | West Coast HS | CALABANGA | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-24 | 2015-10-24 | 050314S00292 | 15FE0077 | 2015-06-15 | 2015-06-19 | 2015-06-30 | 2015-07-06 | 2015-07-20 | PHIL MANNA CONSTRUCTION & SUPPLY
4544 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113112 | Agay-ayan ES | TINAMBAC | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 050314S00018 | 14FF0023 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4545 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309724 | Agay-ayan NHS | TINAMBAC | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-24 |  | 050314S00308 | 15FF0011 | 2015-06-21 | 2015-06-23 | 2015-07-07 | 2015-07-15 | 2015-07-21 | PARTIDO CONSTRUCTION & SUPPLY
4546 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112651 | Agosais PS | LAGONOY | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-06-09 | 050314S00199 | 14FF0021 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | PRECIOUS CONSTRUCTION
4547 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112652 | Amoguis PS | LAGONOY | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00200 | 14FF0021 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | PRECIOUS CONSTRUCTION
4548 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112976 | Aniog ES | SAGÑAY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-01 | 2015-01-01 | 050314S00049 | 14FF0014 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | QDC CONSTRUCTION AND SUPPLY
4549 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113113 | Antipolo ES | TINAMBAC | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-18 | 050314S00044 | 14FF0017 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | HONEYVILLE CONSTRUCTION
4550 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301928 | Antipolo HS, Tinambac | TINAMBAC | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4551 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301928 | Antipolo HS, Tinambac | TINAMBAC | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6569337.6381 |  |  | COMPLETED | 1
4552 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112525 | Antolon ES | CARAMOAN | 4 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3624886.575 |  |  | COMPLETED | 1 | 2016-01-31 |  | 050314S00262 | 15FF0027 | 2015-07-26 | 2015-07-28 | 2015-08-11 | 2015-08-24 | 2015-08-28 | JM-COFER CONSTRUCTION AND SUPPLY
4553 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112977 | Atulayan ES | SAGÑAY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-01 | 2015-01-01 | 050314S00089 | 14FF0014 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | QDC CONSTRUCTION AND SUPPLY
4554 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112881 | Ayugao PS | PRESENTACION (PARUBCAN) | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-03-02 | 050314S00201 | 14FF0022 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4555 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113134 | Bagacay ES | TINAMBAC | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 050314S00056 | 14FF0023 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4556 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301934 | Bagacay HS | TINAMBAC | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 | 2016-03-26 |  | 050314S00339 | 15FF0045 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-09-04 | 2015-09-14 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
4557 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112882 | Bagongsirang ES | PRESENTACION (PARUBCAN) | 4 | 1 | 3 | 3UNITS 1STY 1CL | 2014 K10 BATCH 1 | 3276987.36 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 050314S00202 | 14FF0022 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4558 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301937 | Bahi HS | GARCHITORENA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4559 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301937 | Bahi HS | GARCHITORENA | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1
4560 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301939 | Balaton NHS | LAGONOY | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6919337.6381 |  |  | COMPLETED | 1 | 2016-02-13 |  | 050314S00337 | 15FF0042 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-09-03 | 2015-09-10 | JM-COFER CONSTRUCTION AND SUPPLY
4561 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301941 | Banga HS | TINAMBAC | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-24 |  | 050314S00318 | 15FF0011 | 2015-06-21 | 2015-06-23 | 2015-07-07 | 2015-07-15 | 2015-07-21 | PARTIDO CONSTRUCTION & SUPPLY
4562 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309739 | Bantugan NHS | PRESENTACION (PARUBCAN) | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4563 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309739 | Bantugan NHS | PRESENTACION (PARUBCAN) | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
4564 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301943 | Bikal Fisheries School | CARAMOAN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 | 2015-04-22 |  | 050314S00336 | 15FF0076 | 2015-09-13 | 2015-09-15 | 2015-09-29 | 2015-10-12 | 2015-10-19 | JM-COFER CONSTRUCTION AND SUPPLY
4565 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112591 | Binagasbasan ES | GARCHITORENA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00230 | 14FF0019 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4566 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301944 | Binagasbasan NHS | GARCHITORENA | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 7019337.6381 |  |  | COMPLETED | 1 |  |  | 050314S00335 | 15FF0049 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-12-29 |  | JM-COFER CONSTRUCTION AND SUPPLY
4567 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301945 | Binagasbasan NHS - Denrica Annex HS | GARCHITORENA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4568 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301945 | Binagasbasan NHS - Denrica Annex HS | GARCHITORENA | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 7019337.6381 |  |  | COMPLETED | 1
4569 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113135 | Binalay ES | TINAMBAC | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-18 | 050314S00057 | 14FF0017 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | HONEYVILLE CONSTRUCTION
4570 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309703 | Bitaogan NHS | PRESENTACION (PARUBCAN) | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-02 | 2015-12-02 | 050314S00341 | 15FF0013 | 2015-06-25 | 2015-06-30 | 2015-07-14 | 2015-07-23 | 2015-07-29 | HRB CONSTRUCTION
4571 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112638 | Bocogan ES | LAGONOY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00191 | 14FF0021 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | PRECIOUS CONSTRUCTION
4572 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113136 | Bolaobalite ES | TINAMBAC | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 050314S00058 | 14FF0023 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4573 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302061 | Bonifacio D. Borebor Sr. HS - Eastern Coast Annex HS | CARAMOAN | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6719337.6381 |  |  | COMPLETED | 1 | 2016-02-20 |  | 050314S00333 | 15FF0062 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-10 | 2015-09-17 | JM-COFER CONSTRUCTION AND SUPPLY
4574 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302062 | Bonifacio D. Borebor Sr. HS - Northern Peninsula Annex HS | CARAMOAN | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1
4575 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302062 | Bonifacio D. Borebor Sr. HS - Northern Peninsula Annex HS | CARAMOAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4576 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302060 | Bonifacio D. Borebor Sr. HS (formerly:Tawog NHS) | CARAMOAN | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4577 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302060 | Bonifacio D. Borebor Sr. HS (formerly:Tawog NHS) | CARAMOAN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
4578 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113137 | Buenavista ES | TINAMBAC | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-06-09 | 050314S00059 | 14FF0024 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4579 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309734 | Buenavista HS | TINAMBAC | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4580 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309734 | Buenavista HS | TINAMBAC | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
4581 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309713 | Buenavista NHS | PRESENTACION (PARUBCAN) | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
4582 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309713 | Buenavista NHS | PRESENTACION (PARUBCAN) | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4583 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301949 | Burabod NHS | GARCHITORENA | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6969337.6381 |  |  | COMPLETED | 1 |  |  | 050314S00342 | 15FF0047 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-12-29 |  | JM-COFER CONSTRUCTION AND SUPPLY
4584 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112980 | Buracan ES | SAGÑAY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-01 | 2015-01-01 | 050314S00048 | 14FF0014 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | QDC CONSTRUCTION AND SUPPLY
4585 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113138 | Buyo ES | TINAMBAC | 4 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3940835.14 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 050314S00046 | 14FF0023 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4586 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113139 | Caaluan ES | TINAMBAC | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-03-13 | 050314S00020 | 14FF0024 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4587 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112529 | Cabacongan ES | CARAMOAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00216 | 14FF0018 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4588 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309768 | Cabotonan High School | LAGONOY | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1 | 2016-03-22 |  | 050314S00329 | 15FF0044 | 2015-08-06 | 2015-08-20 | 2015-10-22 | 2015-11-04 | 2015-11-16 | HRB CONSTRUCTION
4589 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112530 | Cadong PS | CARAMOAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 050314S00217 | 14FF0013 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | J-MARBELA CONSTRUCTION & SUPPLY
4590 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112593 | Cagamutan PS | GARCHITORENA | 4 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3062746.69 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00231 | 14FF0019 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4591 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113140 | Cagliliog ES | TINAMBAC | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-04-07 | 050314S00012 | 14FF0024 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4592 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113142 | Canayonan ES | TINAMBAC | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-18 | 050314S00013 | 14FF0023 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4593 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309742 | Canayonan NHS | TINAMBAC | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1 | 2016-03-26 |  | 050314S00328 | 15FF0045 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-09-04 | 2015-09-14 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
4594 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112595 | Canlong ES | GARCHITORENA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00232 | 14FF0018 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4595 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112618 | Catagbacan ES | GOA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-04-03 | 050314S00185 | 14FF0020 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | ALXM CONSTRUCTION
4596 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112981 | Catalotoan ES | SAGÑAY | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-01-01 | 2015-01-01 | 050314S00205 | 14FF0014 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | QDC CONSTRUCTION AND SUPPLY
4597 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309708 | Catalotoan HS | SAGÑAY | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 | 2016-01-30 |  | 050314S00327 | 15FF0033 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-08-27 | ZKR CONSTRUCTION & SUPPLY
4598 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113143 | Cawaynan ES | TINAMBAC | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 050314S00009 | 14FF0023 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4599 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112535 | Colongcogong | CARAMOAN | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00218 | 14FF0018 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4600 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 173535 | Consocep PS | TIGAON | 4 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3062746.69 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-25 | 050314S00003 | 14FF0016 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | CPR CONSTRUCTION AND SUPPLY
4601 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113098 | Coyaoyao ES | TIGAON | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-25 | 050314S00043 | 14FF0016 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | CPR CONSTRUCTION AND SUPPLY
4602 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112596 | Culapnit ES | GARCHITORENA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00233 | 14FF0018 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4603 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301963 | Dahat National Vocational HS | LAGONOY | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 | 2016-02-27 |  | 050314S00326 | 15FF0023 | 2015-07-21 | 2015-07-23 | 2015-08-04 | 2015-08-17 | 2015-08-20 | HRB CONSTRUCTION
4604 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113038 | Daldagon PS | SIRUMA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-03-13 | 050314S00037 | 14FF0015 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | QDC CONSTRUCTION AND SUPPLY
4605 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113119 | Daligan ES | TINAMBAC | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-04-07 | 050314S00050 | 14FF0024 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4606 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112597 | Dangla ES | GARCHITORENA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00234 | 14FF0019 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4607 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112639 | Del Carmen ES | LAGONOY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00207 | 14FF0021 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | PRECIOUS CONSTRUCTION
4608 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112599 | Denrica ES | GARCHITORENA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00194 | 14FF0019 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4609 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112619 | Digdigon ES | GOA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-04-02 | 050314S00186 | 14FF0020 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | ALXM CONSTRUCTION
4610 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301969 | Don Servillano Platon Memorial NHS | TINAMBAC | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-03-12 |  | 050314S00325 | 15FF0040 | 2015-08-02 | 2015-08-04 | 2015-08-18 | 2015-08-28 | 2015-09-08 | M.J. APIN BUILDERS
4611 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 173517 | Don Tomas Garchitorena ES (Gubat) | TIGAON | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-25 | 050314S00001 | 14FF0016 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | CPR CONSTRUCTION AND SUPPLY
4612 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309752 | Dr. Rodolfo V. Pamor Jr. MNHS -Sagñay Western Annex HS | SAGÑAY | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1 | 2016-01-17 |  | 050314S00324 | 15FF0022 | 2015-07-21 | 2015-07-23 | 2015-08-04 | 2015-08-17 | 2015-08-20 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
4613 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309714 | Dr. Rodolfo V. Pamor MHS - Sagñay Southeastern Annex HS | SAGÑAY | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8914965.051 |  |  | COMPLETED | 1 | 2016-03-15 |  | 050314S00323 | 15FF0034 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-08-27 | ALXM CONSTRUCTION
4614 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301989 | Federico P. Condat NHS (frmerly: Maangas HS ) | PRESENTACION (PARUBCAN) | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8814965.051 |  |  | COMPLETED | 1 | 2016-03-01 |  | 050314S00322 | 15FF0026 | 2015-07-26 | 2015-07-28 | 2015-08-11 | 2015-08-24 | 2015-08-28 | HNR CONSTRUCTION & SUPPLY
4615 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113099 | Gaao ES | TIGAON | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-25 | 050314S00060 | 14FF0016 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | CPR CONSTRUCTION AND SUPPLY
4616 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301974 | Gibgos National High School | CARAMOAN | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 7069337.6381 |  |  | COMPLETED | 1 | 2016-02-20 |  | 050314S00353 | 15FF0064 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-10 | 2015-09-17 | JM-COFER CONSTRUCTION AND SUPPLY
4617 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112621 | Goa CS | GOA | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-04-02 | 050314S00187 | 14FF0020 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | ALXM CONSTRUCTION
4618 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301975 | Goa NHS | GOA | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2016-03-01 |  | 050314S00330 | 15FF0020 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-06 | 2015-08-13 | PARTIDO CONSTRUCTION & SUPPLY
4619 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112539 | Gogon Elementary School | CARAMOAN | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00219 | 14FF0018 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4620 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301950 | Gregorio Ocampo Bercasio MHS (frmerly: Cagliliog HS) | TINAMBAC | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6719337.6381 |  |  | COMPLETED | 1 | 2016-02-27 |  | 050314S00332 | 15FF0052 | 2015-08-09 | 2015-08-11 | 2015-08-25 | 2015-09-17 | 2015-09-24 | HONEYVILLE CONSTRUCTION
4621 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112540 | Guijalo ES | CARAMOAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 050314S00235 | 14FF0013 | 2014-07-13 | 2014-07-16 | 2014-08-07 | 2014-08-19 | 2014-08-29 | J-MARBELA CONSTRUCTION & SUPPLY
4622 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301978 | Guijalo NHS | CARAMOAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4623 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301978 | Guijalo NHS | CARAMOAN | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1
4624 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112622 | Halawig-Gogon PS | GOA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-04-03 | 050314S00188 | 14FF0020 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | ALXM CONSTRUCTION
4625 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112542 | Hanopol PS | CARAMOAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 050314S00221 | 14FF0013 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | J-MARBELA CONSTRUCTION & SUPPLY
4626 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112601 | Harrison PS | GARCHITORENA | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00192 | 14FF0018 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4627 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301940 | Himanag NationaL High School | LAGONOY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4628 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301940 | Himanag NationaL High School | LAGONOY | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6869337.6381 |  |  | COMPLETED | 1
4629 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309721 | Huyonhuyon HS | TIGAON | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-29 |  | 050314S00362 | 15FF0032 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-08-27 | HNR CONSTRUCTION & SUPPLY
4630 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309741 | Juan L. Filipino MHS | GOA | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8914965.051 |  |  | COMPLETED | 1 | 2016-03-12 |  | 050314S00361 | 15FF0039 | 2015-08-02 | 2015-08-04 | 2015-08-18 | 2015-08-28 | 2015-09-08 | M.J. APIN BUILDERS
4631 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 173516 | Kinahulogan CS | LAGONOY | 4 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3062746.69 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 050314S00004 | 14FF0022 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4632 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301986 | La Salvacion NHS | TIGAON | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-02 |  | 050314S00360 | 15FF0024 | 2015-07-21 | 2015-07-23 | 2015-08-04 | 2015-08-17 | 2015-08-20 | ALXM CONSTRUCTION
4633 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112890 | Lagha ES | PRESENTACION (PARUBCAN) | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 050314S00204 | 14FF0022 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4634 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112624 | Laki-Laki ES | GOA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-06-17 | 050314S00189 | 14FF0020 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | ALXM CONSTRUCTION
4635 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112891 | Lidong ES | PRESENTACION (PARUBCAN) | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 050314S00206 | 14FF0022 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4636 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309772 | Lidong High School | PRESENTACION (PARUBCAN) | 4 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3584886.575 |  |  | COMPLETED | 1
4637 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309772 | Lidong High School | PRESENTACION (PARUBCAN) | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
4638 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 173515 | Lip-ac ES (Sitio Catagbacan) | GOA | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-05-18 | 050314S00005 | 14FF0020 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | ALXM CONSTRUCTION
4639 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113144 | Lupi ES | TINAMBAC | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-13 | 050314S00014 | 14FF0017 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | HONEYVILLE CONSTRUCTION
4640 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302024 | Magsaysay NHS | TINAMBAC | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1 | 2016-03-25 |  | 050314S00359 | 15FF0051 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-10-26 | 2015-11-04 | HONEYVILLE CONSTRUCTION
4641 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112551 | Malindog PS | CARAMOAN | 4 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3624886.575 |  |  | COMPLETED | 1 | 2016-01-31 |  | 050314S00273 | 15FF0027 | 2015-07-26 | 2015-07-28 | 2015-08-11 | 2015-08-24 | 2015-08-28 | JM-COFER CONSTRUCTION AND SUPPLY
4642 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112552 | Mampirao ES | CARAMOAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 050314S00208 | 14FF0013 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | J-MARBELA CONSTRUCTION & SUPPLY
4643 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113146 | Mananao ES | TINAMBAC | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 050314S00008 | 14FF0023 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4644 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112553 | Mandiclom ES | CARAMOAN | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 050314S00223 | 14FF0013 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | J-MARBELA CONSTRUCTION & SUPPLY
4645 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112643 | Mangogon ES | LAGONOY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-04-07 | 050314S00193 | 14FF0021 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | PRECIOUS CONSTRUCTION
4646 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112644 | Mapid ES | LAGONOY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-04-07 | 050314S00179 | 14FF0021 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | PRECIOUS CONSTRUCTION
4647 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113103 | May-anao ES | TIGAON | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-25 | 050314S00045 | 14FF0016 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | CPR CONSTRUCTION AND SUPPLY
4648 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112555 | Minalaba PS | CARAMOAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 050314S00224 | 14FF0013 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | J-MARBELA CONSTRUCTION & SUPPLY
4649 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113042 | Nalayahan ES | SIRUMA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-03-13 | 050314S00036 | 14FF0015 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | QDC CONSTRUCTION AND SUPPLY
4650 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309715 | Nato National High School | SAGÑAY | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4651 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309715 | Nato National High School | SAGÑAY | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1
4652 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112645 | Olas ES | LAGONOY | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-04-07 | 050314S00195 | 14FF0021 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | PRECIOUS CONSTRUCTION
4653 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302008 | Oring NHS | CARAMOAN | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 7069337.6381 |  |  | COMPLETED | 1 | 2016-04-06 |  | 050314S00357 | 15FF0043 | 2015-08-06 | 2015-08-20 | 2015-10-22 | 2015-11-05 | 2015-11-16 | JM-COFER CONSTRUCTION AND SUPPLY
4654 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112894 | Pagsangaan ES | PRESENTACION (PARUBCAN) | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-03-02 | 050314S00203 | 14FF0022 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4655 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112647 | Pagsimbugan ES | LAGONOY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-06-09 | 050314S00196 | 14FF0021 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | PRECIOUS CONSTRUCTION
4656 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302011 | Pambuhan NHS | GARCHITORENA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4657 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302011 | Pambuhan NHS | GARCHITORENA | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1
4658 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112604 | Pambuhan Primary School | GARCHITORENA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00220 | 14FF0018 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4659 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302040 | Panagan HS | LAGONOY | 4 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2184658.24 |  |  | COMPLETED | 1
4660 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302040 | Panagan HS | LAGONOY | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
4661 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 173556 | Panagan PS | TIGAON | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-25 | 050314S00010 | 14FF0016 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | CPR CONSTRUCTION AND SUPPLY
4662 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112560 | Paniman ES | CARAMOAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 050314S00225 | 14FF0013 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | J-MARBELA CONSTRUCTION & SUPPLY
4663 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8914965.051 |  |  | COMPLETED | 1 | 2016-02-29 |  | 050314S00343 | 15FF0035 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-08-27 | HNR CONSTRUCTION & SUPPLY
4664 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112561 | Patag-Guijalo ES | CARAMOAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00226 | 14FF0018 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4665 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112630 | Payatan ES | GOA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-04-04 | 050314S00190 | 14FF0020 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | ALXM CONSTRUCTION
4666 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309738 | Payatan HS | GOA | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1 | 2016-03-12 |  | 050314S00321 | 15FF0039 | 2015-08-02 | 2015-08-04 | 2015-08-18 | 2015-08-28 | 2015-09-08 | M.J. APIN BUILDERS
4667 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113043 | Penitan ES | SIRUMA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-18 | 050314S00035 | 14FF0015 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | QDC CONSTRUCTION AND SUPPLY
4668 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112896 | Pili Community School | PRESENTACION (PARUBCAN) | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-03-02 | 050314S00088 | 14FF0022 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4669 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112563 | Pili-Centro PS | CARAMOAN | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 050314S00227 | 14FF0013 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | J-MARBELA CONSTRUCTION & SUPPLY
4670 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301976 | Pinaglabanan High School | GOA | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2016-03-01 |  | 050314S00354 | 15FF0020 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-06 | 2015-08-13 | PARTIDO CONSTRUCTION & SUPPLY
4671 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113025 | Ponglon PS | SAN JOSE | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-04-02 | 050314S00038 | 14FF0020 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | ALXM CONSTRUCTION
4672 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302019 | Presentacion NHS (formerly:Pili NHS) | PRESENTACION (PARUBCAN) | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4673 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302019 | Presentacion NHS (formerly:Pili NHS) | PRESENTACION (PARUBCAN) | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 9114965.051 |  |  | COMPLETED | 1
4674 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302035 | Rangas-Ramos NHS (frmerly:Sn Jose Fish.Sch.) | SAN JOSE | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 | 2016-02-11 |  | 050314S00352 | 15FF0041 | 2015-08-02 | 2015-08-04 | 2015-08-18 | 2015-08-28 | 2015-09-08 | M.J. APIN BUILDERS
4675 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113126 | Refugio ES. | TINAMBAC | 4 | 1 | 3 | 3UNITS 1STY 1CL | 2014 K10 BATCH 1 | 3276987.36 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-23 | 050314S00051 | 14FF0017 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | HONEYVILLE CONSTRUCTION
4676 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112989 | Sagnay CS | SAGÑAY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-01 | 2015-01-01 | 050314S00041 | 14FF0014 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | QDC CONSTRUCTION AND SUPPLY
4677 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302023 | Sagrada NHS, Tinambac | TINAMBAC | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4678 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302023 | Sagrada NHS, Tinambac | TINAMBAC | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
4679 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112605 | Sagrada PS | GARCHITORENA | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00181 | 14FF0019 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4680 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309753 | Salogon HS | SAN JOSE | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 | 2016-02-22 |  | 050314S00351 | 15FF0021 | 2015-07-21 | 2015-07-23 | 2015-08-04 | 2015-08-17 | 2015-08-20 | SAINT BERNARD CONSTRUCTION
4681 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113044 | Salvacion ES | SIRUMA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-03-13 | 050314S00034 | 14FF0015 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | QDC CONSTRUCTION AND SUPPLY
4682 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113148 | Salvacion ES | TINAMBAC | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-13 | 050314S00007 | 14FF0017 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | HONEYVILLE CONSTRUCTION
4683 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113105 | San Antonio ES | TIGAON | 4 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3062746.69 |  |  | COMPLETED | 1
4684 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113128 | San Antonio ES | TINAMBAC | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-25 | 050314S00031 | 14FF0016 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | CPR CONSTRUCTION AND SUPPLY
4685 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112648 | San Isidro ES | LAGONOY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-06-09 | 050314S00197 | 14FF0021 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | PRECIOUS CONSTRUCTION
4686 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302036 | San Jose NHS, San Jose | SAN JOSE | 4 | 1 | 11 | 1STY1CL , 1STY2CL & 2STY8CL | 2014 K10 BATCH 3 | 13893732.3364 |  |  | COMPLETED | 1
4687 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302036 | San Jose NHS, San Jose | SAN JOSE | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1
4688 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113107 | San Rafael ES | TIGAON | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-25 | 050314S00047 | 14FF0016 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | CPR CONSTRUCTION AND SUPPLY
4689 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309766 | San Rafael National High School - Cabalinadan Annex HS | TIGAON | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4690 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309766 | San Rafael National High School - Cabalinadan Annex HS | TIGAON | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
4691 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302038 | San Rafael NHS | TIGAON | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8714965.051 |  |  | COMPLETED | 1
4692 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113130 | San Ramon ES | TINAMBAC | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4693 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302042 | San Ramon PHS, Tinambac | TINAMBAC | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4694 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302042 | San Ramon PHS, Tinambac | TINAMBAC | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1
4695 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302039 | San Ramon Pilot NHS, Lagonoy (frmerly:Sn.Ramon Pilot HS) | LAGONOY | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8714965.051 |  |  | COMPLETED | 1 | 2016-03-30 |  | 050314S00347 | 15FF0054 | 2015-08-09 | 2015-08-11 | 2015-08-25 | 2015-09-02 | 2015-09-17 | HONEYVILLE CONSTRUCTION
4696 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113131 | San Roque ES | TINAMBAC | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4697 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112607 | San Vicente ES | GARCHITORENA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00182 | 14FF0018 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4698 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113132 | San Vicente ES | TINAMBAC | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-04-07 | 050314S00055 | 14FF0024 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4699 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302045 | Sibaguan Agro-Industrial HS | SAGÑAY | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-28 |  | 050314S00346 | 15FF0061 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-10 | 2015-09-24 | BIMBO CONSTRUCTION AND SUPPLY (FORMERLY BIMBO CONS
4700 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112990 | Sibaguan ES | SAGÑAY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-01 | 2015-01-01 | 050314S00040 | 14FF0014 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | QDC CONSTRUCTION AND SUPPLY
4701 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302048 | Siruma NHS | SIRUMA | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8714965.051 |  |  | COMPLETED | 1 | 2016-04-03 |  | 050314S00345 | 15FF0055 | 2015-08-09 | 2015-08-11 | 2015-08-25 | 2015-09-04 | 2015-10-05 | SHEAR CONSTRUCTION AND SUPPLY
4702 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301972 | Siruma NHS - Fundado Annex High School | SIRUMA | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6919337.6381 |  |  | COMPLETED | 1 | 2016-02-12 |  | 050314S00344 | 15FF0046 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-09-03 | 2015-09-09 | ROLA CONSTRUCTION
4703 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113149 | Sogod ES | TINAMBAC | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-18 | 050314S00006 | 14FF0023 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-11 | 2014-09-17 | HONEYVILLE CONSTRUCTION
4704 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112569 | Sta. Cruz ES | CARAMOAN | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 050314S00228 | 14FF0013 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | J-MARBELA CONSTRUCTION & SUPPLY
4705 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112650 | Sta. Cruz ES | LAGONOY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-06-09 | 050314S00198 | 14FF0021 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | PRECIOUS CONSTRUCTION
4706 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113046 | Sulpa ES | SIRUMA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-03-13 | 050314S00042 | 14FF0015 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | QDC CONSTRUCTION AND SUPPLY
4707 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112608 | Sumaoy ES | GARCHITORENA | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-18 | 050314S00183 | 14FF0019 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4708 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112570 | Tabgon ES | CARAMOAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 050314S00229 | 14FF0013 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | J-MARBELA CONSTRUCTION & SUPPLY
4709 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302055 | Tabgon HS | CARAMOAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4710 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302055 | Tabgon HS | CARAMOAN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8714965.051 |  |  | COMPLETED | 1
4711 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302054 | Tabgon HS, Goa | GOA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4712 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302054 | Tabgon HS, Goa | GOA | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6819337.6381 |  |  | COMPLETED | 1
4713 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302056 | Tamban NHS | TINAMBAC | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-02-22 |  | 050314S00294 | 15FF0019 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-17 | 2015-08-20 | SAINT BERNARD CONSTRUCTION
4714 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112609 | Tamiawon ES | GARCHITORENA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-20 | 050314S00184 | 14FF0019 | 2014-08-03 | 2014-08-06 | 2014-08-20 | 2014-09-04 | 2014-09-10 | J-MARBELA CONSTRUCTION & SUPPLY
4715 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302058 | Tandoc HS | SIRUMA | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6769337.6381 |  |  | COMPLETED | 1 | 2016-01-30 |  | 050314S00291 | 15FF0030 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-08-27 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
4716 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113150 | Tierra Nevada ES | TINAMBAC | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-02-13 | 050314S00002 | 14FF0017 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | HONEYVILLE CONSTRUCTION
4717 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302063 | Tierra Nevada HS | TINAMBAC | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 | 2016-03-13 |  | 050314S00290 | 15FF0040 | 2015-08-02 | 2015-08-04 | 2015-08-18 | 2015-08-28 | 2015-09-08 | M.J. APIN BUILDERS
4718 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 113152 | Tinambac South CS II | TINAMBAC | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-05-19 | 2015-05-18 | 050314S00243 | 14FF0044 | 2014-12-10 | 2014-12-12 | 2015-11-23 | 2015-01-05 | 2015-01-13 | HGG BUILDERS & SUPPLY
4719 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302029 | Tinawagan NHS | TIGAON | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4720 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302029 | Tinawagan NHS | TIGAON | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1
4721 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112993 | Turague ES | SAGÑAY | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-01 | 2015-01-01 | 050314S00039 | 14FF0014 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-29 | QDC CONSTRUCTION AND SUPPLY
4722 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 309771 | Villafuerte-Peña High School | SAN JOSE | 4 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1
4723 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309771 | Villafuerte-Peña High School | SAN JOSE | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
4724 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309740 | Visita De Salog HS | GOA | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-20 | 050314S00311 | 15FF0014 | 2015-06-25 | 2015-06-30 | 2015-07-14 | 2015-07-23 | 2015-07-30 | ZKR CONSTRUCTION & SUPPLY
4725 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302069 | Vito HS | SIRUMA | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
4726 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 302069 | Vito HS | SIRUMA | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6769337.6381 |  |  | COMPLETED | 1
4727 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301984 | Vivencio Obias - Kinalansan NHS (formerly: Kinalansan NHS) | SAN JOSE | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
4728 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301984 | Vivencio Obias - Kinalansan NHS (formerly: Kinalansan NHS) | SAN JOSE | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
4729 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301926 | Agdangan HS | BAAO | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1
4730 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112318 | Antipolo ES | BAAO | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 050314S00097 | 14FG0023 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4731 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 173548 | Antipolo Young ES | NABUA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 050314S00071 | 14FG0023 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4732 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 301931 | Baao National HS | BAAO | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1
4733 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112343 | Bagong Lipunan ES | BALATAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00099 | 14FG0026 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | HGG BUILDERS & SUPPLY
4734 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112425 | Bagumbayan ES | BULA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00108 | 14FG0024 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | R.K.X. ODIAMAR CONSTRUCTION
4735 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112390 | Buhi CS | BUHI | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 050314S00116 | 14FG0027 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4736 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 309709 | Buhi SPED Integrated School | BUHI | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-21 |  | 050314S00310 | 15FG0040 | 2015-06-30 | 2015-07-07 | 2015-07-08 | 2015-09-22 | 2015-09-24 | GRELIPS CONSTRUCTION & DEVELOPMENT
4737 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301948 | Bula NHS - Caorasan Annex HS | BULA | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-21 |  | 050314S00309 | 15FG0040 | 2015-06-30 | 2015-07-07 | 2015-07-08 | 2015-09-22 | 2015-09-24 | GRELIPS CONSTRUCTION & DEVELOPMENT
4738 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112322 | Buluang ES | BAAO | 5 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6313739.7656 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-06 | 050314S00242 | 14FG0035 | 2014-11-19 | 2014-11-21 | 2014-12-04 | 2014-12-09 | 2014-12-12 | IA FERRER CONSTRUCTION & SUPPLY
4739 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112346 | Cabungan ES | BALATAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117829.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00100 | 14FG0026 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | HGG BUILDERS & SUPPLY
4740 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112394 | Cagmaslog ES | BUHI | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2008917.57 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 050314S00115 | 14FG0027 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4741 | NC 2014 | SHS (2014) | Region V | Camarines Sur | 301956 | Caranday HS | BAAO | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-21 |  | 050314S00306 | 15FG0040 | 2015-06-30 | 2015-07-07 | 2015-07-08 | 2015-09-22 | 2015-09-24 | GRELIPS CONSTRUCTION & DEVELOPMENT
4742 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112367 | Carlos Nardo Elementary School | BATO | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2006917.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00104 | 14FG0026 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | HGG BUILDERS & SUPPLY
4743 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112370 | Dr. H. A. Guballa ES | BATO | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1115829.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00112 | 14FG0026 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | HGG BUILDERS & SUPPLY
4744 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112431 | Fabrica ES | BULA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1105829.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00076 | 14FG0024 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | R.K.X. ODIAMAR CONSTRUCTION
4745 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112398 | Ibayugan ES | BUHI | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 050314S00106 | 14FG0027 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4746 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112432 | Inoyonan ES | BULA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-01-11 | 2015-01-11 | 050314S00120 | 14FG0025 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | DONBER CONSTRUCTION & SUPPLY
4747 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112433 | Itangon ES | BULA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1993417.57 |  |  | COMPLETED | 1 | 2015-01-11 | 2015-01-11 | 050314S00105 | 14FG0025 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | DONBER CONSTRUCTION & SUPPLY
4748 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112434 | Kinalabasahan ES | BULA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-10 | 050314S00062 | 14FG0025 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | DONBER CONSTRUCTION & SUPPLY
4749 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112437 | La Victoria ES | BULA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117829.12 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-10 | 050314S00063 | 14FG0025 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | DONBER CONSTRUCTION & SUPPLY
4750 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112371 | Lobong ES | BATO | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1116829.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00114 | 14FG0026 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | HGG BUILDERS & SUPPLY
4751 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112438 | Lopez Palsong ES | BULA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00064 | 14FG0024 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | R.K.X. ODIAMAR CONSTRUCTION
4752 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112439 | Lubgan ES | BULA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2015-01-11 | 2015-01-11 | 050314S00065 | 14FG0025 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | DONBER CONSTRUCTION & SUPPLY
4753 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112836 | Madawon ES | NABUA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 050314S00070 | 14FG0023 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4754 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112352 | Maguiron ES | BALATAN | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915674.43 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00101 | 14FG0026 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | HGG BUILDERS & SUPPLY
4755 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112406 | Maybatang ES | BUHI | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1116329.12 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 050314S00113 | 14FG0027 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4756 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112443 | Ombao Heights ES | BULA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112829.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00066 | 14FG0024 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | R.K.X. ODIAMAR CONSTRUCTION
4757 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302010 | Palsong NHS | BULA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1104329.12 |  |  | COMPLETED | 1
4758 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112333 | Sagrada ES | BAAO | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 050314S00098 | 14FG0023 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4759 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112380 | Sagrada ES | BATO | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112829.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00091 | 14FG0026 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | HGG BUILDERS & SUPPLY
4760 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112447 | Salles ES | BULA | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2016-01-14 |  | 050314S00265 | 15FG0041 | 2015-07-23 | 2015-08-06 | 2015-08-07 | 2015-08-12 | 2015-08-18 | JURASSIC CONSTRUCTION & SUPPLIES
4761 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112381 | Salvacion ES | BATO | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107829.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00119 | 14FG0026 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | HGG BUILDERS & SUPPLY
4762 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112411 | Salvacion ES | BUHI | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1973917.57 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 050314S00121 | 14FG0027 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4763 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112357 | San Francisco ES | BALATAN | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005917.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00102 | 14FG0026 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | HGG BUILDERS & SUPPLY
4764 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112449 | San Francisco ES | BULA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1128829.12 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-10 | 050314S00067 | 14FG0025 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | DONBER CONSTRUCTION & SUPPLY
4765 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112412 | San Isidro ES | BUHI | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1839740.174 |  |  | COMPLETED | 1 | 2016-01-14 |  | 050314S00264 | 15FG0041 | 2015-07-23 | 2015-08-06 | 2015-08-07 | 2015-08-12 | 2015-08-18 | JURASSIC CONSTRUCTION & SUPPLIES
4766 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112383 | San Miguel ES | BATO | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1104329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00118 | 14FG0024 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | R.K.X. ODIAMAR CONSTRUCTION
4767 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112413 | San Rafael ES | BUHI | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 050314S00111 | 14FG0027 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4768 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112414 | San Ramon ES | BUHI | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2006917.57 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 050314S00110 | 14FG0027 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4769 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302027 | San Roque High School | BATO | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1115829.12 |  |  | COMPLETED | 1
4770 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112385 | San Vicente | BATO | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107829.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00117 | 14FG0024 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | R.K.X. ODIAMAR CONSTRUCTION
4771 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112338 | San Vicente ES | BAAO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2016-01-14 |  | 050314S00263 | 15FG0041 | 2015-07-23 | 2015-08-06 | 2015-08-07 | 2015-08-12 | 2015-08-18 | JURASSIC CONSTRUCTION & SUPPLIES
4772 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302043 | San Vicente NHS | BUHI | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
4773 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 302050 | Sta. Justina HS | BUHI | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
4774 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112454 | Sto. Nino ES | BULA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1105829.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00068 | 14FG0024 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | R.K.X. ODIAMAR CONSTRUCTION
4775 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112420 | Sto. Nino PS | BUHI | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117829.12 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 050314S00109 | 14FG0027 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4776 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112455 | Taisan ES | BULA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2006917.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00069 | 14FG0024 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | R.K.X. ODIAMAR CONSTRUCTION
4777 | NC 2014 | K10 (2014) | Region V | Camarines Sur | 112360 | Tomatarayo ES | BALATAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1113829.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050314S00103 | 14FG0026 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-08-18 | 2014-09-03 | HGG BUILDERS & SUPPLY
4778 | NC 2014 | K10 (2014) | Region V | Catanduanes | 302070 | Agban NHS | BARAS | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1
4779 | NC 2014 | K10 (2014) | Region V | Catanduanes | 302077 | Buyo Integrated School | VIRAC (Capital) | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4780 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113336 | Calabnigan ES | VIRAC (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-10-25 | 2015-10-25 | 050414S00018 | By Administration 9 | 2015-07-26 | 2015-07-27 | 2015-07-28 | 2015-07-31 | 2015-08-05 | By Administration
4781 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113235 | Catamban ES | PANDAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-11-05 |  | 050414S00017 | By Administration 8 | 2015-07-26 | 2015-07-27 | 2015-07-28 | 2015-07-31 | 2015-08-05 | By Administration
4782 | NC 2014 | SHS (2014) | Region V | CATANDUANES | 309802 | Cobo IS | PANDAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-12-04 | 050414S00020 | 15FH0027 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-05 | 2015-08-13 | SULVIR ENGINEERING AND CONSTRUCTION
4783 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113219 | Dororian E/S | GIGMOTO | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
4784 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113219 | Dororian E/S | GIGMOTO | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2088606.04 |  |  | COMPLETED | 1
4785 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113207 | Guiamlong ES | CARAMORAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1022411.1325 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-18 | 050414S00009 | 14FH0036 | 2014-12-27 | 2014-11-28 | 2014-12-11 | 2014-12-22 | 2014-12-29 | FDS Construction & Supply
4786 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113209 | Inalmasinan ES | CARAMORAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1062049.6543 |  |  | COMPLETED | 1 | 2015-11-01 | 2015-10-23 | 050414S00015 | By Administration 6 | 2015-07-26 | 2015-07-27 | 2015-07-28 | 2015-07-31 | 2015-08-05 | By Administration
4787 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113210 | Iyao ES | CARAMORAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1753672.338 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-05-14 | 050414S00006 | 14FH0036 | 2014-11-27 | 2014-11-28 | 2014-12-11 | 2014-12-22 | 2014-12-29 | FDS Construction & Supply
4788 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113345 | Juan M. Alberto Memorial ES | VIRAC (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-04-20 |  | 050414S00021 | By Contract | 2015-10-13 | 2015-10-13 | 2015-10-27 | 2015-11-10 | 2015-11-16 | ZEUS TRADING & CONSTRUCTION
4789 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113262 | Lictin IS | SAN ANDRES (CALOLBON) | 0 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2015-12-25 |  | 050414S00024 | 15FH0028 | 2015-07-16 | 2015-07-17 | 2015-08-03 | 2015-08-12 | 2015-08-21 | TRI-DOM TRADING & CONSTRUCTION
4790 | NC 2014 | K10 (2014) | Region V | Catanduanes | 302092 | Mayngaway NHS | SAN ANDRES (CALOLBON) | 0 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 050414S00025 | By Contract | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-09-11 | 2015-09-18 | ZEUS TRADING & CONSTRUCTION
4791 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113213 | Obi ES | CARAMORAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1062049.6543 |  |  | COMPLETED | 1 | 2015-11-05 | 2015-11-03 | 050414S00013 | By Administration 4 | 2015-07-26 | 2015-07-27 | 2015-07-28 | 2015-07-31 | 2015-08-05 | By Administration
4792 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113322 | Ogbong ES | VIGA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-02-18 | 050414S00002 | 14FH0011 | 2014-07-31 | 2014-08-01 | 2014-08-14 | 2014-09-05 | 2014-09-18 | ALJON CONSTRUCTION & SUPPLY
4793 | NC 2014 | K10 (2014) | Region V | CATANDUANES | 302095 | Panganiban NHS | PANGANIBAN (PAYO) | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4794 | NC 2014 | SHS (2014) | Region V | CATANDUANES | 302095 | Panganiban NHS | PANGANIBAN (PAYO) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
4795 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113303 | Patagan ES | SAN MIGUEL | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-03-10 | 050414S00003 | 14FH0011 | 2014-07-31 | 2014-08-01 | 2014-08-14 | 2014-09-05 | 2014-09-18 | ALJON CONSTRUCTION & SUPPLY
4796 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113281 | San Isidro ES | SAN ANDRES (CALOLBON) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
4797 | NC 2014 | K10 (2014) | Region V | Catanduanes | 113281 | San Isidro ES | SAN ANDRES (CALOLBON) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1102049.6543 |  |  | COMPLETED | 1
4798 | NC 2014 | K10 (2014) | Region V | Catanduanes | 174006 | San Isidro Village ES | VIRAC (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 987236.1325 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-17 | 050414S00007 | 14FH0036 | 2014-11-27 | 2014-11-28 | 2014-12-11 | 2014-12-22 | 2014-12-29 | FDS Construction & Supply
4799 | NC 2014 | K10 (2014) | Region V | Catanduanes | 174014 | San Rafael PS | PANDAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1904740.174 |  |  | COMPLETED | 1 | 2015-12-05 |  | 050414S00012 | By Administration 3 | 2015-07-26 | 2015-07-27 | 2015-07-28 | 2015-07-31 | 2015-08-05 | By Administration
4800 | NC 2014 | K10 (2014) | Region V | Catanduanes | 302100 | San Vicente NHS | BAGAMANOC | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1017386.1325 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-05-12 | 050414S00008 | 14FH0036 | 2014-11-27 | 2014-11-28 | 2014-12-11 | 2014-12-22 | 2014-12-29 | FDS Construction & Supply
4801 | NC 2014 | K10 (2014) | Region V | Iriga City | 114430 | Cawayan ES | IRIGA CITY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-12-15 | 050314S00367 | 15FG0044 | 2015-07-23 | 2015-08-06 | 2015-08-07 | 2015-08-12 | 2015-08-18 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
4802 | NC 2014 | SHS (2014) | Region V | Iriga City | 310103 | Cristo Rey IS | IRIGA CITY | 5 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2665828.124 |  |  | COMPLETED | 1 | 2016-02-16 |  | 050314S00307 | 15FG0038 | 2015-06-30 | 2015-07-07 | 2015-09-02 | 2015-09-24 | 2015-10-19 | DONBER CONSTRUCTION & SUPPLY
4803 | NC 2014 | K10 (2014) | Region V | Iriga City | 114418 | Don Lazaro Madara Memorial School | IRIGA CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 050314S00061 | 14FG0023 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4804 | NC 2014 | SHS (2014) | Region V | Iriga City | 302251 | Rinconada National Technical Vocational School | IRIGA CITY | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8299965.051 |  |  | COMPLETED | 1 | 2016-04-06 |  | 050314S00293 | 15FG0039 | 2015-06-30 | 2015-09-01 | 2015-09-02 | 2015-09-24 | 2015-11-09 | R.K.X. ODIAMAR CONSTRUCTION
4805 | NC 2014 | K10 (2014) | Region V | Iriga City | 310101 | Rinconada National Technical Vocational School Annex, San Francisco ES Campus | IRIGA CITY | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 050314S00079 | 14FG0023 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4806 | NC 2014 | SHS (2014) | Region V | Iriga City | 302252 | Sagrada NHS | IRIGA CITY | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6429337.6381 |  |  | COMPLETED | 1 | 2016-02-16 |  | 050314S00305 | 15FG0038 | 2015-06-30 | 2015-07-07 | 2015-09-02 | 2015-09-24 | 2015-10-19 | DONBER CONSTRUCTION & SUPPLY
4807 | NC 2014 | SHS (2014) | Region V | Iriga City | 302254 | San Antonio NHS | IRIGA CITY | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8299965.051 |  |  | COMPLETED | 1 | 2016-04-06 |  | 050314S00304 | 15FG0039 | 2015-06-30 | 2015-07-07 | 2015-09-02 | 2015-09-24 | 2015-11-09 | R.K.X. ODIAMAR CONSTRUCTION
4808 | NC 2014 | K10 (2014) | Region V | Iriga City | 114438 | San Ramon ES | IRIGA CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 050314S00077 | 14FG0023 | 2014-07-17 | 2014-08-04 | 2014-08-08 | 2014-09-24 | 2014-10-03 | NVF CONSTRUCTION
4809 | NC 2014 | SHS (2014) | Region V | Iriga City | 302250 | Sta. Maria HS | IRIGA CITY | 5 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2685828.124 |  |  | COMPLETED | 1 | 2016-01-21 |  | 050314S00303 | 15FG0040 | 2015-06-30 | 2015-07-07 | 2015-07-08 | 2015-09-22 | 2015-09-24 | GRELIPS CONSTRUCTION & DEVELOPMENT
4810 | NC 2014 | SHS (2014) | Region V | Iriga City | 302256 | Sto. Niño NHS | IRIGA CITY | 5 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10482131.51 |  |  | COMPLETED | 1 | 2016-04-06 |  | 050314S00302 | 15FG0082 | 2015-09-29 | 2015-10-12 | 2015-10-13 | 2015-10-20 | 2015-11-09 | HRB CONSTRUCTION
4811 | NC 2014 | K10 (2014) | Region V | Iriga City | 302253 | Zeferino Arroyo HS | IRIGA CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4812 | NC 2014 | K10 (2014) | Region V | Iriga City | 302253 | Zeferino Arroyo HS | IRIGA CITY | 5 | 1 | 6 | Completion of 3STY/9CL(Construction of remaining 6CL) | 2014 K10 BATCH 4B | 6750000 |  |  | COMPLETED | 1
4813 | NC 2014 | SHS (2014) | Region V | Legaspi City | 310201 | Arimbay High School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 050114S00137 | 15FB0060 | 2015-07-22 | 2015-07-23 | 2015-08-04 | 2015-08-18 | 2015-08-28 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
4814 | NC 2014 | SHS (2014) | Region V | Legaspi City | 302257 | Banquerohan NHS | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 050114S00126 | 15FB0067 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-04 | 2015-09-17 | ALXM CONSTRUCTION
4815 | NC 2014 | SHS (2014) | Region V | Legaspi City | 302260 | Cabangan High School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10477131.51 |  |  | REVERTED | 0 | 2016-05-03 |  | 050114S00127 | 15FB0095 | 2015-11-15 | 2015-11-12 | 2015-11-24 | 2015-12-03 | 2015-12-14 | QDC CONSTRUCTION AND SUPPLY
4816 | NC 2014 | SHS (2014) | Region V | Legaspi City | 310206 | Cagbacong High School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6499337.6381 |  |  | COMPLETED | 1 | 2016-02-14 |  | 050114S00128 | 15FB0066 | 2015-08-11 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-11 | ALXM CONSTRUCTION
4817 | NC 2014 | SHS (2014) | Region V | Legaspi City | 302262 | Gogon High School | LEGAZPI CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15221327.92 |  |  | COMPLETED | 1 | 2016-04-30 |  | 050114S00129 | 15FB0092 | 2015-10-28 | 2015-10-23 | 2015-11-05 | 2015-11-16 | 2015-11-26 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY
4818 | NC 2014 | SHS (2014) | Region V | Legaspi City | 302259 | Homapon High School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-14 |  | 050114S00130 | 15FB0066 | 2015-08-11 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-11 | ALXM CONSTRUCTION
4819 | NC 2014 | K10 (2014) | Region V | Legaspi City | 114479 | Ibalon CS | LEGAZPI CITY (Capital) | 2 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 31900584.375 |  |  | COMPLETED | 1 | 2016-02-22 |  | 050114S00076 | 15FB0046 | 2015-07-01 | 2015-06-26 | 2015-07-09 | 2015-07-20 | 2015-07-31 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY
4820 | NC 2014 | SHS (2014) | Region V | Legaspi City | 310202 | Legaspi City HS | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8319965.051 |  |  | COMPLETED | 1 | 2016-02-19 |  | 050114S00131 | 15FB0071 | 2015-08-18 | 2015-08-14 | 2015-08-26 | 2015-09-08 | 2015-09-16 | AMEG CONSTRUCTION & SUPPLY
4821 | NC 2014 | SHS (2014) | Region V | Legaspi City | 310205 | Maslog National High School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6549337.6381 |  |  | COMPLETED | 1 | 2016-02-19 |  | 050114S00132 | 15FB0071 | 2015-08-18 | 2015-08-14 | 2015-08-26 | 2015-09-08 | 2015-09-16 | AMEG CONSTRUCTION & SUPPLY
4822 | NC 2014 | K10 (2014) | Region V | Legaspi City | 302258 | Oro Site High School | LEGAZPI CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4A | 14045118.3984 |  |  | COMPLETED | 1
4823 | NC 2014 | SHS (2014) | Region V | Legaspi City | 302258 | Oro Site High School | LEGAZPI CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15281327.92 |  |  | COMPLETED | 1
4824 | NC 2014 | SHS (2014) | Region V | Legaspi City | 302261 | Pagasa NHS | LEGAZPI CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15271327.92 |  |  | COMPLETED | 1
4825 | NC 2014 | SHS (2014) | Region V | Legaspi City | 302263 | Pawa High School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 050114S00139 | 15FB0060 | 2015-07-22 | 2015-07-23 | 2015-08-04 | 2015-08-18 | 2015-08-28 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
4826 | NC 2014 | SHS (2014) | Region V | Legaspi City | 310204 | Taysan Resettlement Integrated School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 050114S00136 | 15FB0067 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-04 | 2015-09-17 | ALXM CONSTRUCTION
4827 | NC 2014 | K10 (2014) | Region V | Ligao City | 111809 | Amtic ES | CITY OF LIGAO | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 050114S00042 | 14FO0013 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-05 | WEARR ENTERPRISES & DEVELOPMENT CORP.
4828 | NC 2014 | SHS (2014) | Region V | Ligao City | 301814 | Bicol Regional Science HS | CITY OF LIGAO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8409965.051 |  |  | COMPLETED | 1 | 2016-06-24 |  | 050114S00154 | 15FO0033 | 2015-08-18 | 2015-08-19 | 2015-09-01 | 2015-10-23 | 2015-12-21 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
4829 | NC 2014 | K10 (2014) | Region V | Ligao City | 111816 | Bonga ES | CITY OF LIGAO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 050114S00043 | 14FO0013 | 2014-07-16 | 2014-07-17 | 2014-07-30 | 2014-08-15 | 2014-09-05 | WEARR ENTERPRISES & DEVELOPMENT CORP.
4830 | NC 2014 | SHS (2014) | Region V | Ligao City | 301817 | Cabarian NHS | CITY OF LIGAO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8409965.051 |  |  | COMPLETED | 1 | 2016-06-24 |  | 050114S00138 | 15FO0044 | 2015-08-27 | 2015-08-28 | 2015-09-14 | 2015-09-30 | 2015-12-21 | HERBANA BUILDERS AND SUPPLY
4831 | NC 2014 | SHS (2014) | Region V | Ligao City | 301820 | Deogracias P. Princesa Memorial HS | CITY OF LIGAO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8409965.051 |  |  | COMPLETED | 1 | 2016-04-21 |  | 050114S00125 | 15FO0044 | 2015-08-27 | 2015-08-28 | 2015-09-14 | 2015-09-30 | 2015-12-21 | HERBANA BUILDERS AND SUPPLY
4832 | NC 2014 | K10 (2014) | Region V | Ligao City | 301837 | Ligao NHS | CITY OF LIGAO | 3 | 1 | 10 | 2STY10CL | 2014 K10 BATCH 4A | 13037519.5312 |  |  | COMPLETED | 1
4833 | NC 2014 | SHS (2014) | Region V | Ligao City | 301837 | Ligao NHS | CITY OF LIGAO | 3 | 1 | 16 | 4STY16CL | 2014 SHS BATCH 1 | 27117469.42 |  |  | COMPLETED | 1
4834 | NC 2014 | SHS (2014) | Region V | Ligao City | 301837 | Ligao NHS | CITY OF LIGAO | 3 | 1 | 16 | 4STY16CL | 2014 SHS BATCH 1 | 27117469.42 |  |  | COMPLETED | 1
4835 | NC 2014 | K10 (2014) | Region V | Ligao City | 111824 | Oma-Oma ES | CITY OF LIGAO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 050114S00180 | 15FO0025 | 2015-08-04 | 2015-08-05 | 2015-08-17 | 2015-09-03 | 2015-09-16 | EUGE CONSTRUCTION AND SUPPLY
4836 | NC 2014 | K10 (2014) | Region V | Ligao City | 301862 | Paulba NHS | CITY OF LIGAO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
4837 | NC 2014 | SHS (2014) | Region V | Ligao City | 301862 | Paulba NHS | CITY OF LIGAO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8424965.051 |  |  | COMPLETED | 1
4838 | NC 2014 | K10 (2014) | Region V | Masbate | 113857 | Altavista ES | SAN FERNANDO | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 050514S00208 | 14FM0025 | 2014-08-12 | 2014-07-30 | 2014-08-12 | 2014-09-28 | 2014-10-02 | MAGDA CONSTRUCTION AND SUPPLY
4839 | NC 2014 | SHS (2014) | Region V | Masbate | 309919 | Antonio Lee Llacer Sr. Integrated School | BATUAN | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-15 | 2015-10-15 | 050514S00254 | 15FM0010 | 2015-06-18 | 2015-06-18 | 2015-07-02 | 2015-08-11 | 2015-08-17 | C.L. CARANDANG ENTERPRISES
4840 | NC 2014 | K10 (2014) | Region V | Masbate | 113884 | Bagacay ES | SAN JACINTO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-05 | 2014-11-05 | 050514S00158 | 14FM0013 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4841 | NC 2014 | K10 (2014) | Region V | Masbate | 113570 | Balete ES | CLAVERIA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1
4842 | NC 2014 | K10 (2014) | Region V | Masbate | 113859 | Benitinan ES | SAN FERNANDO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
4843 | NC 2014 | K10 (2014) | Region V | Masbate | 113908 | Boca Chica ES | SAN PASCUAL | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 050514S00118 | 14FM0015 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4844 | NC 2014 | K10 (2014) | Region V | Masbate | 113478 | Burgos ES | BATUAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 050514S00138 | 14FM0016 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-26 | 2014-09-15 | ALXM CONSTRUCTION
4845 | NC 2014 | K10 (2014) | Region V | Masbate | 113910 | Busing ES | SAN PASCUAL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 050514S00119 | 14FM0023 | 2014-08-28 | 2014-08-14 | 2014-08-28 | 2014-09-22 | 2014-10-13 | GRELIPS CONSTRUCTION & DEVELOPMENT
4846 | NC 2014 | K10 (2014) | Region V | Masbate | 113888 | Calipat-an ES | SAN JACINTO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-05 | 2014-11-05 | 050514S00126 | 14FM0013 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4847 | NC 2014 | K10 (2014) | Region V | Masbate | 113479 | Canares ES | BATUAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 050514S00139 | 14FM0016 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-26 | 2014-09-15 | ALXM CONSTRUCTION
4848 | NC 2014 | K10 (2014) | Region V | Masbate | 113865 | Canelas ES | SAN FERNANDO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 050514S00214 | 14FM0026 | 2014-08-12 | 2014-07-30 | 2014-08-12 | 2014-09-09 | 2014-10-02 | MAGDA CONSTRUCTION AND SUPPLY
4849 | NC 2014 | K10 (2014) | Region V | Masbate | 113577 | Claveria CS | CLAVERIA | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 050514S00144 | 14FM0029 | 2014-08-12 | 2014-07-30 | 2014-08-12 | 2014-09-09 | 2014-10-02 | RHYMAC CONSTRUCTION & SUPPLY
4850 | NC 2014 | K10 (2014) | Region V | Masbate | 174511 | Cogon ES | MONREAL | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-10-15 | 2015-09-20 | 050514S00226 | 15FM0011 | 2015-06-18 | 2015-06-18 | 2015-07-02 | 2015-08-11 | 2015-08-17 | C.L. CARANDANG ENTERPRISES
4851 | NC 2014 | K10 (2014) | Region V | Masbate | 113480 | Costa Rica Integrated School | BATUAN | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | REVERTED | 0
4852 | NC 2014 | K10 (2014) | Region V | Masbate | 113889 | Danao ES | SAN JACINTO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-12 | 050514S00149 | 14FM0018 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-26 | 2014-09-15 | ALXM CONSTRUCTION
4853 | NC 2014 | K10 (2014) | Region V | Masbate | 113912 | Dancalan ES | SAN PASCUAL | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 050514S00184 | 14FM0015 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4854 | NC 2014 | K10 (2014) | Region V | Masbate | 113578 | Dapdap ES | CLAVERIA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 050514S00145 | 14FM0029 | 2014-08-12 | 2014-07-30 | 2014-08-12 | 2014-09-09 | 2014-10-02 | RHYMAC CONSTRUCTION & SUPPLY
4855 | NC 2014 | K10 (2014) | Region V | Masbate | 113913 | Donato Dela Pena PS | SAN PASCUAL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 050514S00120 | 14FM0023 | 2014-08-28 | 2014-08-14 | 2014-08-28 | 2014-09-22 | 2014-10-13 | GRELIPS CONSTRUCTION & DEVELOPMENT
4856 | NC 2014 | K10 (2014) | Region V | Masbate | 113914 | Dr.Antero M. Nazareno ES | SAN PASCUAL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-01-09 | 050514S00159 | 14FM0024 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-26 | 2014-09-15 | ALXM CONSTRUCTION
4857 | NC 2014 | K10 (2014) | Region V | Masbate | 309928 | EMILIO LEE LLACER SR. HIGH SCHOOL | SAN JACINTO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1
4858 | NC 2014 | K10 (2014) | Region V | Masbate | 309930 | Gerardo C. Cardiño Sr. HS | MONREAL | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1
4859 | NC 2014 | K10 (2014) | Region V | Masbate | 174522 | Gregorio T. Vilar Primary School | SAN PASCUAL | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1 | 2015-12-14 |  | 050514S00224 | 15FM0012 | 2015-06-18 | 2015-06-18 | 2015-07-02 | 2015-08-11 | 2015-08-17 | C.L. CARANDANG ENTERPRISES
4860 | NC 2014 | K10 (2014) | Region V | Masbate | 113766 | Guinhadap ES | MONREAL | 1 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4915592 |  |  | COMPLETED | 1 | 2015-02-05 | 2015-02-05 | 050514S00151 | 14FM0020 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-26 | 2014-09-15 | ALXM CONSTRUCTION
4861 | NC 2014 | K10 (2014) | Region V | Masbate | 113581 | Mabiton ES | CLAVERIA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 050514S00146 | 14FM0014 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4862 | NC 2014 | K10 (2014) | Region V | Masbate | 113583 | Malacbalac ES | CLAVERIA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 050514S00160 | 14FM0021 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-26 | 2014-09-15 | ALXM CONSTRUCTION
4863 | NC 2014 | K10 (2014) | Region V | Masbate | 113584 | Manapao ES | CLAVERIA | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 050514S00148 | 14FM0030 | 2014-08-12 | 2014-07-30 | 2014-08-12 | 2014-09-09 | 2014-10-02 | RHYMAC CONSTRUCTION & SUPPLY
4864 | NC 2014 | K10 (2014) | Region V | Masbate | 113924 | Mapanique ES | SAN PASCUAL | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 050514S00121 | 14FM0015 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4865 | NC 2014 | K10 (2014) | Region V | Masbate | 113484 | Matabao ES | BATUAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 050514S00141 | 14FM0017 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-26 | 2014-09-15 | ALXM CONSTRUCTION
4866 | NC 2014 | K10 (2014) | Region V | Masbate | 113771 | Morocborocan ES | MONREAL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 050514S00152 | 14FM0027 | 2014-08-12 | 2014-07-30 | 2014-08-12 | 2014-09-09 | 2014-10-02 | MAGDA CONSTRUCTION AND SUPPLY
4867 | NC 2014 | K10 (2014) | Region V | Masbate | 113872 | P. Basas ES | SAN FERNANDO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-05 | 2014-11-05 | 050514S00213 | 14FM0011 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4868 | NC 2014 | K10 (2014) | Region V | Masbate | 113486 | Panisihan ES | BATUAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 050514S00142 | 14FM0039 | 2014-09-30 | 2014-09-13 | 2014-09-30 | 2014-10-09 | 2014-10-30 | GRELIPS CONSTRUCTION & DEVELOPMENT
4869 | NC 2014 | K10 (2014) | Region V | Masbate | 113929 | Paral ES | SAN PASCUAL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 050514S00122 | 14FM0022 | 2014-08-28 | 2014-08-14 | 2014-08-28 | 2014-09-22 | 2014-10-13 | GRELIPS CONSTRUCTION & DEVELOPMENT
4870 | NC 2014 | K10 (2014) | Region V | Masbate | 174520 | Patrocenio G. Dela Torre Sr. PS | SAN PASCUAL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 050514S00125 | 14FM0022 | 2014-08-28 | 2014-08-14 | 2014-08-28 | 2014-09-22 | 2014-10-13 | GRELIPS CONSTRUCTION & DEVELOPMENT
4871 | NC 2014 | K10 (2014) | Region V | Masbate | 113897 | Pina ES | SAN JACINTO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 050514S00147 | 14FM0026 | 2014-08-12 | 2014-07-30 | 2014-08-12 | 2014-09-09 | 2014-10-02 | MAGDA CONSTRUCTION AND SUPPLY
4872 | NC 2014 | K10 (2014) | Region V | Masbate | 113873 | Progreso ES | SAN FERNANDO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 050514S00212 | 14FM0012 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4873 | NC 2014 | K10 (2014) | Region V | Masbate | 113931 | Ramona PS | SAN PASCUAL | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 050514S00123 | 14FM0015 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4874 | NC 2014 | K10 (2014) | Region V | Masbate | 113772 | Real ES | MONREAL | 1 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4915592 |  |  | COMPLETED | 1 | 2015-02-05 | 2015-02-05 | 050514S00153 | 14FM0019 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-26 | 2014-09-15 | ALXM CONSTRUCTION
4875 | NC 2014 | K10 (2014) | Region V | Masbate | 113773 | Rizal ES | MONREAL | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 050514S00154 | 14FM0027 | 2014-08-12 | 2014-07-30 | 2014-08-12 | 2014-09-09 | 2014-10-02 | MAGDA CONSTRUCTION AND SUPPLY
4876 | NC 2014 | K10 (2014) | Region V | Masbate | 113591 | Sampinitan ES | CLAVERIA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 050514S00137 | 14FM0014 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4877 | NC 2014 | K10 (2014) | Region V | Masbate | 113876 | San Fernando CS | SAN FERNANDO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-05 | 2014-11-05 | 050514S00211 | 14FM0011 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4878 | NC 2014 | K10 (2014) | Region V | Masbate | 113899 | San Isidro ES | SAN JACINTO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 050514S00115 | 14FM0026 | 2014-08-12 | 2014-07-30 | 2014-08-12 | 2014-09-09 | 2014-10-02 | MAGDA CONSTRUCTION AND SUPPLY
4879 | NC 2014 | K10 (2014) | Region V | Masbate | 302166 | San Isidro NHS | CLAVERIA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
4880 | NC 2014 | K10 (2014) | Region V | Masbate | 113906 | San Rafael ES (Alimango ES) | SAN PASCUAL | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 050514S00117 | 14FM0031 | 2014-08-12 | 2014-07-30 | 2014-08-12 | 2014-09-09 | 2014-10-02 | RHYMAC CONSTRUCTION & SUPPLY
4881 | NC 2014 | K10 (2014) | Region V | Masbate | 174523 | Segundina L. Rivera Primary School | SAN PASCUAL | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1 | 2015-12-14 |  | 050514S00225 | 15FM0012 | 2015-06-18 | 2015-06-18 | 2015-07-02 | 2015-08-11 | 2015-08-17 | C.L. CARANDANG ENTERPRISES
4882 | NC 2014 | K10 (2014) | Region V | Masbate | 113936 | Sta. Cruz ES | SAN PASCUAL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-01-09 | 050514S00136 | 14FM0024 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-26 | 2014-09-15 | ALXM CONSTRUCTION
4883 | NC 2014 | K10 (2014) | Region V | Masbate | 113901 | Tacdugan ES | SAN JACINTO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-05 | 2014-11-05 | 050514S00116 | 14FM0013 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4884 | NC 2014 | K10 (2014) | Region V | Masbate | 113595 | Taguilid ES | CLAVERIA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 050514S00150 | 14FM0014 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4885 | NC 2014 | K10 (2014) | Region V | Masbate | 113880 | Talisay ES | SAN FERNANDO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 050514S00210 | 14FM0025 | 2014-08-12 | 2014-07-30 | 2014-08-12 | 2014-09-09 | 2014-10-02 | MAGDA CONSTRUCTION AND SUPPLY
4886 | NC 2014 | K10 (2014) | Region V | Masbate | 113775 | Togoron ES | MONREAL | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 050514S00155 | 14FM0028 | 2014-08-12 | 2014-07-30 | 2014-08-12 | 2014-09-09 | 2014-10-02 | TUASON CONSTRUCTION AND SUPPLIES
4887 | NC 2014 | K10 (2014) | Region V | Masbate | 113881 | Valparaiso ES | SAN FERNANDO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 050514S00209 | 14FM0012 | 2014-07-17 | 2014-07-03 | 2014-07-17 | 2014-08-04 | 2014-08-22 | MAGDA CONSTRUCTION AND SUPPLY
4888 | NC 2014 | K10 (2014) | Region V | Masbate | 113637 | Alas ES | MANDAON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2008417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00198 | 14FI0035 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4889 | NC 2014 | K10 (2014) | Region V | Masbate | 309931 | Amador-Bello HS | BALENO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1
4890 | NC 2014 | K10 (2014) | Region V | Masbate | 113393 | Amoroy ES | AROROY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00134 | 14FI0040 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4891 | NC 2014 | K10 (2014) | Region V | Masbate | 113394 | Amotag ES | AROROY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1106829.12 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-04-03 | 050514S00135 | 14FI0042 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4892 | NC 2014 | K10 (2014) | Region V | Masbate | 302111 | Aroroy NHS | AROROY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2910174.43 |  |  | COMPLETED | 1
4893 | NC 2014 | SHS (2014) | Region V | Masbate | 302111 | Aroroy NHS | AROROY | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11318022.5917 |  |  | COMPLETED | 1
4894 | NC 2014 | K10 (2014) | Region V | Masbate | 113638 | Ayat ES | MANDAON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-02-25 | 050514S00199 | 14FI0035 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4895 | NC 2014 | K10 (2014) | Region V | Masbate | 302115 | Baleno NHS | BALENO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1
4896 | NC 2014 | SHS (2014) | Region V | Masbate | 302115 | Baleno NHS | BALENO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8336625.051 |  |  | COMPLETED | 1
4897 | NC 2014 | SHS (2014) | Region V | Masbate | 302116 | Balud NHS | BALUD | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8383285.051 |  |  | COMPLETED | 1 |  |  | 050514S00257 | 15FI0092 | 2015-11-03 | 2015-11-04 | 2015-11-16 | 2015-12-03 | 2015-12-16 | SHA SHA LUMBER & CONSTRUCTION
4898 | NC 2014 | K10 (2014) | Region V | Masbate | 113720 | Bonbon ES | MILAGROS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2006417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00164 | 14FI0031 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4899 | NC 2014 | SHS (2014) | Region V | Masbate | 302156 | Briccio A. Aninang, Sr. Mem. HS | BALUD | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8423285.051 |  |  | COMPLETED | 1 |  |  | 050514S00258 | 15FI0067 | 2015-09-14 | 2015-09-14 | 2015-09-28 | 2015-10-23 | 2015-11-05 | SHA SHA LUMBER & CONSTRUCTION
4900 | NC 2014 | K10 (2014) | Region V | Masbate | 113639 | Bugtong ES | MANDAON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2003417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00202 | 14FI0035 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4901 | NC 2014 | SHS (2014) | Region V | Masbate | 309910 | Cabitan National High School | MANDAON | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8369540.051 |  |  | COMPLETED | 1 |  |  | 050514S00259 | 15FI0061 | 2015-09-14 | 2015-09-14 | 2015-09-28 | 2015-10-23 | 2015-11-05 | SHA SHA LUMBER & CONSTRUCTION
4902 | NC 2014 | SHS (2014) | Region V | Masbate | 302125 | Cleofe A. Arce Memorial High School | MANDAON | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6444901.6381 |  |  | COMPLETED | 1 |  |  | 050514S00260 | 15FI0082 | 2015-10-19 | 2015-10-20 | 2015-11-03 | 2015-11-20 | 2015-12-03 | SHA SHA LUMBER & CONSTRUCTION
4903 | NC 2014 | K10 (2014) | Region V | Masbate | 113381 | Concepcion ES | AROROY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1998917.57 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-04-03 | 050514S00130 | 14FI0042 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4904 | NC 2014 | SHS (2014) | Region V | Masbate | 309925 | Damaso R. Rubia MHS | AROROY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8406625.051 |  |  | COMPLETED | 1 |  |  | 050514S00261 | 15FI0098 | 2015-11-03 | 2015-11-04 | 2015-11-16 | 2015-12-03 | 2015-12-16 | SHA SHA LUMBER & CONSTRUCTION
4905 | NC 2014 | K10 (2014) | Region V | Masbate | 113403 | Dayhagan ES | AROROY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1997417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00124 | 14FI0040 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-26 | SHA SHA LUMBER & CONSTRUCTION
4906 | NC 2014 | SHS (2014) | Region V | Masbate | 309901 | Delavin-Rubia National High School | AROROY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6671217.6381 |  |  | COMPLETED | 1 |  |  | 050514S00262 | 15FI0107 | 2015-11-09 | 2015-11-10 | 2015-11-23 | 2015-12-10 | 2015-12-21
4907 | NC 2014 | K10 (2014) | Region V | Masbate | 113646 | Diogenes R. Cabarles ES | MANDAON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-02-25 | 050514S00206 | 14FI0034 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4908 | NC 2014 | K10 (2014) | Region V | Masbate | 113429 | Docol ES | BALENO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1987417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00189 | 14FI0038 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4909 | NC 2014 | K10 (2014) | Region V | Masbate | 174507 | Dominador D. Trabado ES | MILAGROS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1104329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00161 | 14FI0032 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4910 | NC 2014 | K10 (2014) | Region V | Masbate | 113430 | Eastern Capsay ES | BALENO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00190 | 14FI0038 | 2014-08-14 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4911 | NC 2014 | K10 (2014) | Region V | Masbate | 113377 | Elisa E. Corpus Elementary School | AROROY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1105329.12 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-08-15 | 050514S00129 | 14FI0041 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4912 | NC 2014 | SHS (2014) | Region V | Masbate | 302145 | Federico A. Estipona Memorial High School | MANDAON | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8370370.051 |  |  | COMPLETED | 1 |  |  | 050514S00263 | 15FI0066 | 2015-09-14 | 2015-09-14 | 2015-09-28 | 2015-10-23 | 2015-11-05 | SHA SHA LUMBER & CONSTRUCTION
4913 | NC 2014 | K10 (2014) | Region V | Masbate | 113452 | Guinbanuahan ES | BALUD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1110829.12 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-05-31 | 050514S00195 | 14FI0036 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4914 | NC 2014 | K10 (2014) | Region V | Masbate | 174517 | Isidro F. Calimotan, Sr. ES | AROROY | 2 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2244658.24 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-08-15 | 050514S00175 | 14FI0041 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4915 | NC 2014 | K10 (2014) | Region V | Masbate | 113382 | Jaboyoan ES | AROROY | 2 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3087746.69 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-04-03 | 050514S00131 | 14FI0042 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4916 | NC 2014 | SHS (2014) | Region V | Masbate | 302139 | Jamorawon National High School | MILAGROS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8544945.051 |  |  | COMPLETED | 1 |  |  | 050514S00265 | 15FI0114
4917 | NC 2014 | K10 (2014) | Region V | Masbate | 113724 | John Miller ES | MILAGROS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1983417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00165 | 14FI0031 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4918 | NC 2014 | K10 (2014) | Region V | Masbate | 113405 | Ladiawan PS | AROROY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1108329.12 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-04-03 | 050514S00169 | 14FI0042 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4919 | NC 2014 | SHS (2014) | Region V | Masbate | 302140 | Lagta NHS | BALENO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8336625.051 |  |  | COMPLETED | 1 |  |  | 050514S00273 | 15FI0093 | 2015-11-03 | 2015-11-04 | 2015-11-16 | 2015-12-03 | 2015-12-16 | SHA SHA LUMBER & CONSTRUCTION
4920 | NC 2014 | K10 (2014) | Region V | Masbate | 113434 | Lahong Int. ES | BALENO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2013417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00191 | 14FI0038 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4921 | NC 2014 | SHS (2014) | Region V | Masbate | 302141 | Lahong National High School | BALENO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8306965.051 |  |  | COMPLETED | 1 |  |  | 050514S00272 | 15FI0097 | 2015-11-03 | 2015-11-04 | 2015-11-16 | 2015-12-03 | 2015-12-16 | SHA SHA LUMBER & CONSTRUCTION
4922 | NC 2014 | SHS (2014) | Region V | Masbate | 309939 | Lantangan High School | MANDAON | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6451901.6381 |  |  | COMPLETED | 1 |  |  | 050514S00271 | 15FI0081 | 2015-10-19
4923 | NC 2014 | K10 (2014) | Region V | Masbate | 302161 | Liberato P. Tacurda Sr. HS | BALUD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1128829.12 |  |  | COMPLETED | 1
4924 | NC 2014 | SHS (2014) | Region V | Masbate | 302161 | Liberato P. Tacurda Sr. HS | BALUD | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8500370.051 |  |  | COMPLETED | 1
4925 | NC 2014 | K10 (2014) | Region V | Masbate | 113456 | Lomocab ES | BALUD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1109329.12 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-05-31 | 050514S00196 | 14FI0036 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4926 | NC 2014 | K10 (2014) | Region V | Masbate | 113744 | Lomocloc ES | MOBO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1115329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00173 | 14FI0037 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4927 | NC 2014 | SHS (2014) | Region V | Masbate | 302143 | Luy-a NHS | AROROY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8446285.051 |  |  | COMPLETED | 1 |  |  | 050514S00269 | 15FI0075 | 2015-09-30 | 2015-10-06 | 2015-10-19 | 2015-11-05 | 2015-11-16 | SHA SHA LUMBER & CONSTRUCTION
4928 | NC 2014 | K10 (2014) | Region V | Masbate | 113652 | Mabato-bato ES | MANDAON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-02-25 | 050514S00207 | 14FI0034 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4929 | NC 2014 | K10 (2014) | Region V | Masbate | 113436 | Madancalan PS | BALENO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00192 | 14FI0039 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | HKP CONSTRUCTION AND SUPPLY
4930 | NC 2014 | SHS (2014) | Region V | Masbate | 302144 | Magdalena NHS | BALENO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8468285.051 |  |  | COMPLETED | 1 |  |  | 050514S00268 | 15FI0095 | 2015-11-03 | 2015-11-04 | 2015-11-16 | 2015-12-03 | 2015-12-16 | SHA SHA LUMBER & CONSTRUCTION
4931 | NC 2014 | K10 (2014) | Region V | Masbate | 113697 | Magsalangi ES | MILAGROS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1108829.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00204 | 14FI0032 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4932 | NC 2014 | K10 (2014) | Region V | Masbate | 113407 | Malubago ES | AROROY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1996417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00201 | 14FI0040 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4933 | NC 2014 | K10 (2014) | Region V | Masbate | 113387 | Manamoc ES | AROROY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1104329.12 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-08-15 | 050514S00132 | 14FI0041 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4934 | NC 2014 | K10 (2014) | Region V | Masbate | 113438 | Manoboc PS | BALENO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00193 | 14FI0038 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4935 | NC 2014 | SHS (2014) | Region V | Masbate | 302146 | Marintoc National High School | MOBO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8586965.051 |  |  | COMPLETED | 1 | 2016-04-09 |  | 050514S00267 | 15FI0064 | 2015-09-14 | 2015-09-14 | 2015-09-28 | 2015-10-23 | 2015-11-05 | SHA SHA LUMBER & CONSTRUCTION
4936 | NC 2014 | K10 (2014) | Region V | Masbate | 309908 | Mary Perpetua E. Brioso MHS | MILAGROS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
4937 | NC 2014 | SHS (2014) | Region V | Masbate | 302147 | Masbate School of Fisheries | MILAGROS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8362455.051 |  |  | COMPLETED | 1 |  |  | 050514S00264 | 15FI0112 | 2015-11-09 | 2015-11-10 | 2015-11-23 | 2015-12-10 | 2015-12-21 | ARKY CONSTRUCTION AND SUPPLY
4938 | NC 2014 | SHS (2014) | Region V | Masbate | 309916 | Mataba Integrated School | AROROY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439713.6381 |  |  | COMPLETED | 1 |  |  | 050514S00266 | 15FI0104 | 2015-11-09 | 2015-11-10 | 2015-11-23 | 2015-12-10 | 2015-12-21 | SHA SHA LUMBER & CONSTRUCTION
4939 | NC 2014 | K10 (2014) | Region V | Masbate | 113699 | Matagbac ES | MILAGROS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00203 | 14FI0033 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4940 | NC 2014 | K10 (2014) | Region V | Masbate | 113727 | Matiporon ES | MILAGROS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1983417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00166 | 14FI0031 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4941 | NC 2014 | SHS (2014) | Region V | Masbate | 302119 | Melchor B. Burlaos Memorial High School | MILAGROS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8377455.051 |  |  | COMPLETED | 1 |  |  | 050514S00255 | 15FI0071 | 2015-09-30 | 2015-10-06 | 2015-10-19 | 2015-11-05 | 2015-11-16 | SHA SHA LUMBER & CONSTRUCTION
4942 | NC 2014 | SHS (2014) | Region V | Masbate | 302150 | Milagros National High School | MILAGROS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8668929.051 |  |  | COMPLETED | 1 |  |  | 050514S00241 | 15FI0069 | 2015-09-14 | 2015-09-14 | 2015-09-28 | 2015-10-23 | 2015-11-05 | SHA SHA LUMBER & CONSTRUCTION
4943 | NC 2014 | SHS (2014) | Region V | Masbate | 302151 | Mobo National High School | MOBO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8333101.051 |  |  | COMPLETED | 1 |  |  | 050514S00233 | 15FI0113 | 2015-11-09 | 2015-11-10 | 2015-11-23 | 2015-12-08 | 2015-12-21 | A.C. RIVERO DEVELOPMENT CORPORATION
4944 | NC 2014 | K10 (2014) | Region V | Masbate | 113729 | Moises R. ESpinosa ES | MILAGROS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1992417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00167 | 14FI0031 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4945 | NC 2014 | K10 (2014) | Region V | Masbate | 113654 | Montano P. Estipona MES | MANDAON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00205 | 14FI0034 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4946 | NC 2014 | K10 (2014) | Region V | Masbate | 309932 | Nabongsoran High School | AROROY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1986417.57 |  |  | COMPLETED | 1
4947 | NC 2014 | K10 (2014) | Region V | Masbate | 113459 | Nicasio Descalzo MES | BALUD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-03-31 | 050514S00087 | 14FI0036 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4948 | NC 2014 | K10 (2014) | Region V | Masbate | 113389 | Pangle ES | AROROY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1106329.12 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-04-03 | 050514S00133 | 14FI0042 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4949 | NC 2014 | SHS (2014) | Region V | Masbate | 302157 | Panique NHS | AROROY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8438285.051 |  |  | COMPLETED | 1 | 2016-04-20 |  | 050514S00234 | 15FI0074 | 2015-09-29 | 2015-10-06 | 2015-10-19 | 2015-11-05 | 2015-11-16 | SHA SHA LUMBER & CONSTRUCTION
4950 | NC 2014 | K10 (2014) | Region V | Masbate | 113732 | Paraiso ES | MILAGROS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1105329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00168 | 14FI0031 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4951 | NC 2014 | SHS (2014) | Region V | Masbate | 302117 | Pedro C. Sese, Sr. Mem. HS | BALUD | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8296625.051 |  |  | COMPLETED | 1 |  |  | 050514S00235 | 15FI0065 | 2015-09-14 | 2015-09-14 | 2015-09-28 | 2015-10-23 | 2015-11-05 | SHA SHA LUMBER & CONSTRUCTION
4952 | NC 2014 | K10 (2014) | Region V | Masbate | 113718 | Pedro Y. Bautista ES | MILAGROS | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2739828.124 |  |  | COMPLETED | 1 | 2016-03-05 |  | 050514S00228 | 15FI0039 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-18 | 2015-10-01 | GACT ENTERPRISES
4953 | NC 2014 | K10 (2014) | Region V | Masbate | 113751 | Pinamalatican PS | MOBO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1115329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00170 | 14FI0037 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4954 | NC 2014 | K10 (2014) | Region V | Masbate | 113440 | Potoson ES | BALENO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00194 | 14FI0039 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | HKP CONSTRUCTION AND SUPPLY
4955 | NC 2014 | K10 (2014) | Region V | Masbate | 113464 | Pulanduta ES | BALUD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1103829.12 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-05-31 | 050514S00197 | 14FI0036 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4956 | NC 2014 | SHS (2014) | Region V | Masbate | 302162 | Puro HS | AROROY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8392455.051 |  |  | COMPLETED | 1 | 2016-04-20 |  | 050514S00236 | 15FI0076 | 2015-09-30 | 2015-10-06 | 2015-10-19 | 2015-11-05 | 2015-11-16 | SHA SHA LUMBER & CONSTRUCTION
4957 | NC 2014 | SHS (2014) | Region V | Masbate | 302164 | Quinayangan National High School | BALUD | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8495775.051 |  |  | COMPLETED | 1 |  |  | 050514S00237 | 15FI0062 | 2015-09-14 | 2015-09-14 | 2015-09-28 | 2015-10-21 | 2015-11-05 | SHA SHA LUMBER & CONSTRUCTION
4958 | NC 2014 | SHS (2014) | Region V | Masbate | 302160 | Salvador Arollado, Sr. MHS | BALUD | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8296625.051 |  |  | COMPLETED | 1 |  |  | 050514S00238 | 15FI0068 | 2015-09-14 | 2015-09-14 | 2015-09-28 | 2015-10-23 | 2015-11-05 | SHA SHA LUMBER & CONSTRUCTION
4959 | NC 2014 | K10 (2014) | Region V | Masbate | 113413 | San Agustin ES | AROROY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1111329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00187 | 14FI0040 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4960 | NC 2014 | K10 (2014) | Region V | Masbate | 113467 | San Andres PS | BALUD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-05-31 | 050514S00156 | 14FI0036 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4961 | NC 2014 | K10 (2014) | Region V | Masbate | 113705 | San Antonio ES | MILAGROS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00188 | 14FI0033 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4962 | NC 2014 | K10 (2014) | Region V | Masbate | 113706 | San Carlos ES | MILAGROS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00171 | 14FI0032 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4963 | NC 2014 | K10 (2014) | Region V | Masbate | 113708 | San Jose ES | MILAGROS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1988417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00162 | 14FI0032 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4964 | NC 2014 | SHS (2014) | Region V | Masbate | 309907 | San Pablo National High School | MANDAON | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414115.051 |  |  | COMPLETED | 1 |  |  | 050514S00239 | 15FI0060 | 2015-09-14 | 2015-09-14 | 2015-09-28 | 2015-10-23 | 2015-11-05 | SHA SHA LUMBER & CONSTRUCTION
4965 | NC 2014 | K10 (2014) | Region V | Masbate | 113710 | Sawmill ES | MILAGROS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1115329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00163 | 14FI0033 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4966 | NC 2014 | K10 (2014) | Region V | Masbate | 113755 | Sawmill ES | MOBO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1115329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00186 | 14FI0037 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4967 | NC 2014 | SHS (2014) | Region V | Masbate | 309906 | Serafin C. Rosero Mem. HS | MILAGROS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8349540.051 |  |  | COMPLETED | 1 |  |  | 050514S00243 | 15FI0063 | 2015-09-14 | 2015-09-14 | 2015-09-28 | 2015-10-23 | 2015-11-05 | SHA SHA LUMBER & CONSTRUCTION
4968 | NC 2014 | K10 (2014) | Region V | Masbate | 113756 | Sta. Maria ES | MOBO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2007417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00172 | 14FI0037 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4969 | NC 2014 | K10 (2014) | Region V | Masbate | 113662 | Tabuk PS | MANDAON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1347329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00200 | 14FI0034 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-19 | 2014-09-29 | SHALJOMAR CONSTRUCTION & SUPPLY
4970 | NC 2014 | K10 (2014) | Region V | Masbate | 113470 | Tambobo ES | BALUD | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3691386.575 |  |  | COMPLETED | 1 | 2016-02-04 |  | 050514S00227 | 15FI0038 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-18 | 2015-10-01 | SHA SHA LUMBER & CONSTRUCTION
4971 | NC 2014 | SHS (2014) | Region V | Masbate | 309909 | Teresita C. Young MHS | AROROY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8382455.051 |  |  | COMPLETED | 1 |  |  | 050514S00240 | 15FI0091 | 2015-11-03 | 2015-11-04 | 2015-11-16 | 2015-12-03 | 2015-12-16 | SHA SHA LUMBER & CONSTRUCTION
4972 | NC 2014 | K10 (2014) | Region V | Masbate | 174508 | Tesa ES | MILAGROS | 2 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3127746.69 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00174 | 14FI0033 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4973 | NC 2014 | K10 (2014) | Region V | Masbate | 113417 | Tigbao ES | AROROY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00185 | 14FI0040 | 2014-08-15 | 2014-08-14 | 2014-08-27 | 2014-09-19 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
4974 | NC 2014 | SHS (2014) | Region V | Masbate | 309917 | Tigbao Integrated School | AROROY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6464901.6381 |  |  | COMPLETED | 1 |  |  | 050514S00253 | 15FI0108 | 2015-11-09 | 2015-11-10 | 2015-11-23 | 2015-12-10 | 2015-12-21 | SHA SHA LUMBER & CONSTRUCTION
4975 | NC 2014 | SHS (2014) | Region V | Masbate | 302174 | Tinigban National High School | AROROY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8412455.051 |  |  | COMPLETED | 1 |  |  | 050514S00251 | 15FI0090 | 2015-11-03 | 2015-11-04 | 2015-11-16 | 2015-12-03 | 2015-12-16 | SHA SHA LUMBER & CONSTRUCTION
4976 | NC 2014 | K10 (2014) | Region V | Masbate | 113505 | Abaca ES | CATAINGAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 050514S00083 | 14FJ0019 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
4977 | NC 2014 | K10 (2014) | Region V | Masbate | 309902 | Allanaraiz-Marfil National High School | ESPERANZA | 3 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4885592 |  |  | COMPLETED | 1
4978 | NC 2014 | K10 (2014) | Region V | Masbate | 113791 | Aniano Almanzor ES | PALANAS | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00006 | 14FJ0031 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
4979 | NC 2014 | K10 (2014) | Region V | Masbate | 113798 | Apolinario Etang ES | PALANAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00002 | 14FJ0031 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
4980 | NC 2014 | K10 (2014) | Region V | Masbate | 113941 | Aurora ES | USON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-02-26 | 050514S00091 | 14FJ0026 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
4981 | NC 2014 | K10 (2014) | Region V | Masbate | 113597 | Balocawe ES | DIMASALANG | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 050514S00046 | 14FJ0021 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
4982 | NC 2014 | K10 (2014) | Region V | Masbate | 113821 | Ban-ao ES | PLACER | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00019 | 14FJ0037 | 2014-08-22 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
4983 | NC 2014 | K10 (2014) | Region V | Masbate | 113788 | Banco ES | PALANAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00008 | 14FJ0030 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
4984 | NC 2014 | K10 (2014) | Region V | Masbate | 113789 | Biga-a Elem. School | PALANAS | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 050514S00007 | 14FJ0029 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
4985 | NC 2014 | K10 (2014) | Region V | Masbate | 113777 | Bontod ES | PALANAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00012 | 14FJ0030 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
4986 | NC 2014 | K10 (2014) | Region V | Masbate | 113962 | Buenasuerte ES | USON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-03-31 | 050514S00085 | 14FJ0028 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
4987 | NC 2014 | K10 (2014) | Region V | Masbate | 309927 | Buenasuerte Integrated School | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 9 | 3UNITS 1STY 3CL | 2014 K10 BATCH 1 | 8685523.29 |  |  | COMPLETED | 1
4988 | NC 2014 | K10 (2014) | Region V | Masbate | 302121 | Buenavista National High School | USON | 3 | 1 | 7 | 2UNITS 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 6876009.57 |  |  | COMPLETED | 1
4989 | NC 2014 | K10 (2014) | Region V | Masbate | 113839 | Bugtong Cawayan ES | PLACER | 3 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4905592 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00027 | 14FJ0035 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
4990 | NC 2014 | K10 (2014) | Region V | Masbate | 113805 | Bugtong ES | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-07-11 | 2015-07-11 | 050514S00017 | 15FJ0004 | 2014-11-26 | 2014-11-25 | 2015-03-19 | 2015-03-27 | 2015-04-06 | SHA SHA LUMBER & CONSTRUCTION
4991 | NC 2014 | K10 (2014) | Region V | Masbate | 113599 | Buracan ES | DIMASALANG | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-04-04 | 2015-04-04 | 050514S00047 | 14FJ0020 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | YOYEN ENTERPRISES
4992 | NC 2014 | K10 (2014) | Region V | Masbate | 302123 | Buracan National High School | DIMASALANG | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1
4993 | NC 2014 | K10 (2014) | Region V | Masbate | 113840 | Cabangcalan ES | PLACER | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00112 | 14FJ0035 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
4994 | NC 2014 | K10 (2014) | Region V | Masbate | 113600 | Cabanuyoan ES | DIMASALANG | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-04-04 | 2015-04-04 | 050514S00048 | 14FJ0020 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | YOYEN ENTERPRISES
4995 | NC 2014 | K10 (2014) | Region V | Masbate | 113508 | Cagbatang ES | CATAINGAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 050514S00030 | 14FJ0019 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
4996 | NC 2014 | K10 (2014) | Region V | Masbate | 113603 | Calabad ES | DIMASALANG | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-04-04 | 2015-04-04 | 050514S00049 | 14FJ0020 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | YOYEN ENTERPRISES
4997 | NC 2014 | K10 (2014) | Region V | Masbate | 113823 | Calumpang ES | PLACER | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050514S00020 | 14FJ0039 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
4998 | NC 2014 | K10 (2014) | Region V | Masbate | 113944 | Campana ES | USON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-02-26 | 050514S00092 | 14FJ0027 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
4999 | NC 2014 | K10 (2014) | Region V | Masbate | 302129 | Cataingan National High School | CATAINGAN | 3 | 1 | 8 | 2UNITS 1STY 4CL | 2014 K10 BATCH 1 | 7601610.98 |  |  | COMPLETED | 1
5000 | NC 2014 | K10 (2014) | Region V | Masbate | 113842 | Celera-Inocencio CS | PLACER | 3 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4905592 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00069 | 14FJ0037 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5001 | NC 2014 | K10 (2014) | Region V | Masbate | 113534 | Chico ES | CAWAYAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00035 | 14FJ0033 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5002 | NC 2014 | K10 (2014) | Region V | Masbate | 113510 | Curvada ES | CATAINGAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 050514S00031 | 14FJ0019 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5003 | NC 2014 | K10 (2014) | Region V | Masbate | 113844 | Dangpanan ES | PLACER | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 050514S00086 | 14FJ0038 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5004 | NC 2014 | K10 (2014) | Region V | Masbate | 113947 | Del Carmen ES | USON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-03-31 | 050514S00093 | 14FJ0028 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5005 | NC 2014 | K10 (2014) | Region V | Masbate | 302131 | Del Carmen National High School | USON | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1
5006 | NC 2014 | K10 (2014) | Region V | Masbate | 113948 | Del Rosario ES | USON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-27 | 050514S00094 | 14FJ0027 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5007 | NC 2014 | K10 (2014) | Region V | Masbate | 302132 | Dimasalang National High School | DIMASALANG | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
5008 | NC 2014 | K10 (2014) | Region V | Masbate | 113824 | Doroteo B. Presno ES | PLACER | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050514S00021 | 14FJ0039 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5009 | NC 2014 | K10 (2014) | Region V | Masbate | 113513 | Emilio S. Boro Sr. CS | CATAINGAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1723791.2257 |  |  | COMPLETED | 1 | 2015-05-03 | 2015-05-03 | 050514S00217 | 14FJ0053 | 2014-12-03 | 2014-12-04 | 2014-12-16 | 2014-12-19 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5010 | NC 2014 | K10 (2014) | Region V | Masbate | 113515 | Eulogio C. Adoptante ES | CATAINGAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1723791.2257 |  |  | COMPLETED | 1 | 2015-05-03 | 2015-05-03 | 050514S00220 | 14FJ0053 | 2014-12-03 | 2014-12-04 | 2014-12-16 | 2014-12-19 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5011 | NC 2014 | K10 (2014) | Region V | Masbate | 113538 | F. Jumao-as ES | CAWAYAN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00036 | 14FJ0034 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5012 | NC 2014 | K10 (2014) | Region V | Masbate | 113846 | Felomino Yray ES | PLACER | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050514S00055 | 14FJ0039 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5013 | NC 2014 | K10 (2014) | Region V | Masbate | 113618 | Florencio Y. Francisco ES | ESPERANZA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-04-04 | 2015-04-04 | 050514S00052 | 14FJ0024 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-19 | HENSO CONSTRUCTION
5014 | NC 2014 | K10 (2014) | Region V | Masbate | 302118 | G. Bangalisan National High School | PLACER | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
5015 | NC 2014 | K10 (2014) | Region V | Masbate | 113622 | Guadalupe ES | ESPERANZA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 050514S00053 | 14FJ0023 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | YOYEN ENTERPRISES
5016 | NC 2014 | K10 (2014) | Region V | Masbate | 113966 | Ilihan PS | USON | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2789328.124 |  |  | COMPLETED | 1 | 2015-11-19 | 2015-11-19 | 050514S00230 | 15FJ0022 | 2015-06-19 | 2015-06-19 | 2015-07-02 | 2015-07-09 | 2015-07-15 | C.L. CARANDANG ENTERPRISES
5017 | NC 2014 | K10 (2014) | Region V | Masbate | 113541 | Iraya ES | CAWAYAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00037 | 14FJ0034 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5018 | NC 2014 | K10 (2014) | Region V | Masbate | 113542 | Itombato ES | CAWAYAN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00038 | 14FJ0034 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5019 | NC 2014 | K10 (2014) | Region V | Masbate | 113779 | Jose A. Abenir Sr. ES | PALANAS | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00011 | 14FJ0031 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5020 | NC 2014 | K10 (2014) | Region V | Masbate | 113624 | Labrador ES | ESPERANZA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-04-04 | 2015-04-04 | 050514S00054 | 14FJ0024 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | HENSO CONSTRUCTION
5021 | NC 2014 | K10 (2014) | Region V | Masbate | 113812 | Lampuyang ES | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-06-11 | 2015-06-11 | 050514S00018 | 15FJ0005 | 2014-11-27 | 2014-11-25 | 2015-03-19 | 2015-03-27 | 2015-04-06 | SHA SHA LUMBER & CONSTRUCTION
5022 | NC 2014 | K10 (2014) | Region V | Masbate | 113967 | Libertad ES | USON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-02-26 | 050514S00101 | 14FJ0026 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5023 | NC 2014 | SHS (2014) | Region V | Masbate | 309934 | Libertad High School | CAWAYAN | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-19 | 2015-12-15 | 050514S00242 | 15FJ0018 | 2015-06-19 | 2015-06-19 | 2015-07-02 | 2015-07-09 | 2015-07-15 | C.L. CARANDANG ENTERPRISES
5024 | NC 2014 | K10 (2014) | Region V | Masbate | 113516 | Libtong ES | CATAINGAN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 050514S00032 | 14FJ0019 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5025 | NC 2014 | K10 (2014) | Region V | Masbate | 302142 | Liong National High School | CATAINGAN | 3 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3810805.49 |  |  | COMPLETED | 1
5026 | NC 2014 | K10 (2014) | Region V | Masbate | 113827 | Locso-an ES | PLACER | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050514S00023 | 14FJ0039 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5027 | NC 2014 | K10 (2014) | Region V | Masbate | 113826 | Lt. Nilo R. Inocencio ES | PLACER | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050514S00022 | 14FJ0039 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5028 | NC 2014 | K10 (2014) | Region V | Masbate | 113849 | Luna ES | PLACER | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 050514S00088 | 14FJ0039 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5029 | NC 2014 | K10 (2014) | Region V | Masbate | 113518 | Maanahao ES | CATAINGAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1723791.2257 |  |  | COMPLETED | 1 | 2015-05-03 | 2015-05-03 | 050514S00222 | 14FJ0053 | 2014-12-03 | 2014-12-04 | 2014-12-16 | 2014-12-19 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5030 | NC 2014 | K10 (2014) | Region V | Masbate | 113792 | Maanahao ES | PALANAS | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00005 | 14FJ0031 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5031 | NC 2014 | K10 (2014) | Region V | Masbate | 113793 | Mabini Elem. School | PALANAS | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00004 | 14FJ0031 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5032 | NC 2014 | K10 (2014) | Region V | Masbate | 113968 | Madao ES | USON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-02-26 | 050514S00102 | 14FJ0027 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5033 | NC 2014 | K10 (2014) | Region V | Masbate | 113626 | Magsaysay ES | ESPERANZA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-04-04 | 2015-04-04 | 050514S00016 | 14FJ0024 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | HENSO CONSTRUCTION
5034 | NC 2014 | K10 (2014) | Region V | Masbate | 113828 | Mahayag ES | PLACER | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00024 | 14FJ0037 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5035 | NC 2014 | K10 (2014) | Region V | Masbate | 113550 | Malbug ES | CAWAYAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00040 | 14FJ0034 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5036 | NC 2014 | K10 (2014) | Region V | Masbate | 113495 | Malobago ES | CATAINGAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 050514S00182 | 14FJ0019 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5037 | NC 2014 | K10 (2014) | Region V | Masbate | 113611 | Mambog ES | DIMASALANG | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 050514S00050 | 14FJ0021 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5038 | NC 2014 | K10 (2014) | Region V | Masbate | 309926 | MARAVILLA HS | PALANAS | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1
5039 | NC 2014 | K10 (2014) | Region V | Masbate | 302128 | Marcelo A. Anonuevo Memorial High School | CATAINGAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
5040 | NC 2014 | K10 (2014) | Region V | Masbate | 113831 | Matagangtang ES | PLACER | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00025 | 14FJ0036 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5041 | NC 2014 | K10 (2014) | Region V | Masbate | 302136 | Matagangtang National High School | PLACER | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
5042 | NC 2014 | K10 (2014) | Region V | Masbate | 113520 | Matubinao ES | CATAINGAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1723791.2257 |  |  | COMPLETED | 1 | 2015-05-03 | 2015-05-03 | 050514S00219 | 14FJ0053 | 2014-12-03 | 2014-12-04 | 2014-12-16 | 2014-12-19 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5043 | NC 2014 | K10 (2014) | Region V | Masbate | 113795 | Matugnao ES | PALANAS | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 050514S00003 | 14FJ0029 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5044 | NC 2014 | K10 (2014) | Region V | Masbate | 309914 | Mayor Tomas V. Rivera MHS | CAWAYAN | 3 | 1 | 11 | 3UNITS 1STY 3CL & 1STY 2CL | 2014 K10 BATCH 1 | 10675940.86 |  |  | COMPLETED | 1
5045 | NC 2014 | K10 (2014) | Region V | Masbate | 309911 | Miabas National High School | PALANAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
5046 | NC 2014 | K10 (2014) | Region V | Masbate | 113951 | Miaga ES | USON | 3 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3980835.14 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-02-26 | 050514S00095 | 14FJ0026 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5047 | NC 2014 | K10 (2014) | Region V | Masbate | 113952 | Mongahay ES | USON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-03-31 | 050514S00096 | 14FJ0028 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5048 | NC 2014 | K10 (2014) | Region V | Masbate | 113970 | Morocborocan ES | USON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-03-31 | 050514S00103 | 14FJ0028 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5049 | NC 2014 | K10 (2014) | Region V | Masbate | 113953 | Nabuhay ES | USON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-27 | 050514S00097 | 14FJ0027 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5050 | NC 2014 | K10 (2014) | Region V | Masbate | 174501 | Nagarao ES | PLACER | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00105 | 14FJ0037 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5051 | NC 2014 | K10 (2014) | Region V | Masbate | 302154 | Naro National High School | CAWAYAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
5052 | NC 2014 | K10 (2014) | Region V | Masbate | 113522 | Osmena ES | CATAINGAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1723791.2257 |  |  | COMPLETED | 1 | 2015-05-03 | 2015-05-03 | 050514S00216 | 14FJ0053 | 2014-12-03 | 2014-12-04 | 2014-12-16 | 2014-12-19 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5053 | NC 2014 | K10 (2014) | Region V | Masbate | 113552 | Palobandera ES | CAWAYAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00056 | 14FJ0033 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5054 | NC 2014 | K10 (2014) | Region V | Masbate | 113554 | Pena ES | CAWAYAN | 3 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4B | 2195099.3086 |  |  | COMPLETED | 1 | 2015-10-20 | 2015-10-20 | 050514S00229 | 15FJ0021 | 2015-06-19 | 2015-06-19 | 2015-07-02 | 2015-07-09 | 2015-07-15 | C.L. CARANDANG ENTERPRISES
5055 | NC 2014 | K10 (2014) | Region V | Masbate | 113853 | Puro ES | PLACER | 3 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4905592 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00089 | 14FJ0036 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5056 | NC 2014 | K10 (2014) | Region V | Masbate | 113524 | Quezon ES | CATAINGAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1723791.2257 |  |  | COMPLETED | 1 | 2015-05-03 | 2015-05-03 | 050514S00218 | 14FJ0053 | 2014-12-03 | 2014-12-04 | 2014-12-16 | 2014-12-19 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5057 | NC 2014 | K10 (2014) | Region V | Masbate | 113833 | Quibrada ES | PLACER | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 050514S00026 | 14FJ0038 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5058 | NC 2014 | K10 (2014) | Region V | Masbate | 113558 | R.M. Magbalon ES | CAWAYAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00042 | 14FJ0033 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5059 | NC 2014 | K10 (2014) | Region V | Masbate | 113614 | Rizal ES | DIMASALANG | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 050514S00051 | 14FJ0021 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5060 | NC 2014 | K10 (2014) | Region V | Masbate | 302165 | Rodolfo Z. Titong National High School | PLACER | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
5061 | NC 2014 | K10 (2014) | Region V | Masbate | 113799 | Salvacion Elem. School | PALANAS | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 050514S00028 | 14FJ0030 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5062 | NC 2014 | K10 (2014) | Region V | Masbate | 309929 | Salvacion National High School | PALANAS | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1
5063 | NC 2014 | K10 (2014) | Region V | Masbate | 113800 | San Carlos Elem. School | PALANAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00015 | 14FJ0031 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5064 | NC 2014 | K10 (2014) | Region V | Masbate | 113784 | San Isidro ES | PALANAS | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 050514S00010 | 14FJ0030 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5065 | NC 2014 | K10 (2014) | Region V | Masbate | 113526 | San Jose ES | CATAINGAN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1
5066 | NC 2014 | K10 (2014) | Region V | Masbate | 113560 | San Jose ES | CAWAYAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-06-03 | 2015-06-03 | 050514S00033 | 14FJ0018 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5067 | NC 2014 | K10 (2014) | Region V | Masbate | 113956 | San Mateo ES | USON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-02-26 | 050514S00113 | 14FJ0027 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5068 | NC 2014 | K10 (2014) | Region V | Masbate | 113500 | San Pedro e-IMPACTLearning Center | CATAINGAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1723791.2257 |  |  | COMPLETED | 1 | 2015-05-03 | 2015-05-03 | 050514S00221 | 14FJ0053 | 2014-12-03 | 2014-12-04 | 2014-12-16 | 2014-12-19 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5069 | NC 2014 | K10 (2014) | Region V | Masbate | 302170 | San Ramon National High School | USON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
5070 | NC 2014 | K10 (2014) | Region V | Masbate | 113631 | San Roque ES | ESPERANZA | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1950740.174 |  |  | COMPLETED | 1 | 2015-10-20 | 2015-10-20 | 050514S00231 | 15FJ0023 | 2015-06-19 | 2015-06-19 | 2015-07-02 | 2015-07-09 | 2015-07-15 | C.L. CARANDANG ENTERPRISES
5071 | NC 2014 | K10 (2014) | Region V | Masbate | 113958 | San Vicente ES | USON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
5072 | NC 2014 | K10 (2014) | Region V | Masbate | 113632 | Santiago ES | ESPERANZA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-04-04 | 2015-04-04 | 050514S00043 | 14FJ0024 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | HENSO CONSTRUCTION
5073 | NC 2014 | K10 (2014) | Region V | Masbate | 302171 | Santos E. Conag National High School | ESPERANZA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1
5074 | NC 2014 | K10 (2014) | Region V | Masbate | 113975 | Simawa ES | USON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-02-26 | 050514S00104 | 14FJ0027 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5075 | NC 2014 | K10 (2014) | Region V | Masbate | 113501 | Sta. Teresita ES | CATAINGAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-06-03 | 2015-06-03 | 050514S00183 | 14FJ0018 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5076 | NC 2014 | K10 (2014) | Region V | Masbate | 113562 | Taberna ES | CAWAYAN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00044 | 14FJ0034 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5077 | NC 2014 | K10 (2014) | Region V | Masbate | 113504 | Tagboan ES | CATAINGAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-06-03 | 2015-06-03 | 050514S00157 | 14FJ0018 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5078 | NC 2014 | K10 (2014) | Region V | Masbate | 113563 | Talisay ES | CAWAYAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00045 | 14FJ0034 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5079 | NC 2014 | K10 (2014) | Region V | Masbate | 113855 | Tan-awan ES | PLACER | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00090 | 14FJ0036 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5080 | NC 2014 | K10 (2014) | Region V | Masbate | 113634 | Tawad ES | ESPERANZA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 050514S00041 | 14FJ0023 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | YOYEN ENTERPRISES
5081 | NC 2014 | K10 (2014) | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Mem. HS | USON | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1
5082 | NC 2014 | K10 (2014) | Region V | Masbate | 113801 | Teofilo T. Tambago Elem. School | PALANAS | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 050514S00009 | 14FJ0029 | 2014-08-06 | 2014-08-04 | 2014-08-19 | 2014-09-01 | 2014-09-29 | YOYEN ENTERPRISES
5083 | NC 2014 | K10 (2014) | Region V | Masbate | 113635 | Tunga ES | ESPERANZA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-04-04 | 2015-04-04 | 050514S00013 | 14FJ0024 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | HENSO CONSTRUCTION
5084 | NC 2014 | K10 (2014) | Region V | Masbate | 302176 | Verdida-Sabrido National High School | PLACER | 3 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3980835.14 |  |  | COMPLETED | 1
5085 | NC 2014 | K10 (2014) | Region V | Masbate | 113547 | Victor M. Diano ES | CAWAYAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 050514S00039 | 14FJ0033 | 2014-08-06 | 2014-08-04 | 2014-08-22 | 2014-09-03 | 2014-09-29 | YOYEN ENTERPRISES
5086 | NC 2014 | K10 (2014) | Region V | Masbate | 302177 | Villahermosa NHS | CAWAYAN | 3 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4885592 |  |  | COMPLETED | 1
5087 | NC 2014 | K10 (2014) | Region V | Masbate | 113527 | Villapogado ES | CATAINGAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 050514S00034 | 14FJ0019 | 2014-11-27 | 2014-11-25 | 2014-12-04 | 2014-12-18 | 2014-12-29 | C.L. CARANDANG ENTERPRISES
5088 | NC 2014 | K10 (2014) | Region V | Masbate | 302178 | Vivencio P. Casas, Sr. Memorial High School | PLACER | 3 | 1 | 6 | 2UNITS 1STY 3CL | 2014 K10 BATCH 1 | 5790348.86 |  |  | COMPLETED | 1
5089 | NC 2014 | K10 (2014) | Region V | Masbate City | 321806 | Nursery High School | CITY OF MASBATE (Capital) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1
5090 | NC 2014 | SHS (2014) | Region V | Masbate CITY | 321803 | A. delos Reyes Integrated School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-02-04 |  | 050514S00244 | 15FI0029 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-18 | 2015-10-01 | SHA SHA LUMBER & CONSTRUCTION
5091 | NC 2014 | K10 (2014) | Region V | Masbate City | 113685 | Antonio Dela Rosa ES | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1988917.57 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00079 | 14FI0030 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | HKP CONSTRUCTION AND SUPPLY
5092 | NC 2014 | K10 (2014) | Region V | Masbate City | 113667 | B. TITONG ELEMENTARY SCHOOL | CITY OF MASBATE (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00072 | 14FI0029 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
5093 | NC 2014 | K10 (2014) | Region V | Masbate City | 321805 | Bantigue High School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1998417.57 |  |  | COMPLETED | 1
5094 | NC 2014 | SHS (2014) | Region V | Masbate City | 321805 | Bantigue High School | CITY OF MASBATE (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6349337.6381 |  |  | COMPLETED | 1
5095 | NC 2014 | K10 (2014) | Region V | Masbate City | 113672 | Bayombon ES | CITY OF MASBATE (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00073 | 14FI0030 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | HKP CONSTRUCTION AND SUPPLY
5096 | NC 2014 | SHS (2014) | Region V | Masbate City | 321804 | Bayombon High School | CITY OF MASBATE (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6533247.6381 |  |  | COMPLETED | 1 |  |  | 050514S00246 | 15FI0106 | 2015-11-09 | 2015-11-10 | 2015-11-23 | 2015-12-10 | 2015-12-21 | HKP CONSTRUCTION AND SUPPLY
5097 | NC 2014 | SHS (2014) | Region V | Masbate City | 321801 | Bolo National High School | CITY OF MASBATE (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8296625.051 |  |  | COMPLETED | 1 |  |  | 050514S00247 | 15FI0096 | 2015-11-03 | 2015-11-04 | 2015-11-16 | 2015-12-03 | 2015-12-16 | A.C. RIVERO DEVELOPMENT CORPORATION
5098 | NC 2014 | SHS (2014) | Region V | Masbate City | 302133 | Capitolina O. Legaspi MHS | CITY OF MASBATE (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8276625.051 |  |  | COMPLETED | 1
5099 | NC 2014 | K10 (2014) | Region V | Masbate City | 113677 | Espinosa ES | CITY OF MASBATE (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1098329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00076 | 14FI0028 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | HKP CONSTRUCTION AND SUPPLY
5100 | NC 2014 | K10 (2014) | Region V | Masbate City | 113678 | Florentino C. Versoza (Pawa ES) | CITY OF MASBATE (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00077 | 14FI0029 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
5101 | NC 2014 | K10 (2014) | Region V | Masbate City | 113676 | Gov. Rafael Letada Mem. ES (Circulo ES) | CITY OF MASBATE (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1116329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00075 | 14FI0030 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | HKP CONSTRUCTION AND SUPPLY
5102 | NC 2014 | K10 (2014) | Region V | Masbate City | 113679 | Igang ES | CITY OF MASBATE (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00078 | 14FI0030 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | HKP CONSTRUCTION AND SUPPLY
5103 | NC 2014 | SHS (2014) | Region V | Masbate City | 302148 | Masbate National Comprehensive High School | CITY OF MASBATE (Capital) | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10934942.5917 |  |  | COMPLETED | 1 |  |  | 050514S00249 | 15FI0101 | 2015-11-03 | 2015-11-04 | 2015-11-16 | 2015-12-03 | 2015-12-16 | A.C. RIVERO DEVELOPMENT CORPORATION
5104 | NC 2014 | K10 (2014) | Region V | Masbate City | 113701 | N. De Los Santos ES (C. Delos Santos ) | CITY OF MASBATE (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1106329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00080 | 14FI0028 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | HKP CONSTRUCTION AND SUPPLY
5105 | NC 2014 | SHS (2014) | Region V | Masbate City | 321806 | Nursery High School | CITY OF MASBATE (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8524965.051 |  |  | COMPLETED | 1
5106 | NC 2014 | K10 (2014) | Region V | Masbate City | 113704 | Rene.T. Malvar ES | CITY OF MASBATE (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1110829.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00082 | 14FI0030 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | HKP CONSTRUCTION AND SUPPLY
5107 | NC 2014 | K10 (2014) | Region V | Masbate City | 113675 | Timoteo T. Buncaras ES (Cawayan Interior ES) | CITY OF MASBATE (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1114329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 050514S00074 | 14FI0029 | 2014-08-14 | 2014-08-14 | 2014-08-26 | 2014-09-17 | 2014-09-29 | SHA SHA LUMBER & CONSTRUCTION
5108 | NC 2014 | K10 (2014) | Region V | Masbate City | 321802 | Usab High School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2011917.57 |  |  | COMPLETED | 1
5109 | NC 2014 | SHS (2014) | Region V | Masbate City | 321802 | Usab High School | CITY OF MASBATE (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6588247.6381 |  |  | COMPLETED | 1
5110 | NC 2014 | K10 (2014) | Region V | Naga City | 302264 | Camarines Sur National High School | NAGA CITY | 3 | 1 | 18 | 2UNITS 3STY9CL | 2014 K10 BATCH 4A | 28090236.7969 |  |  | COMPLETED | 1
5111 | NC 2014 | SHS (2014) | Region V | NAGA CITY | 302265 | Cararayan National High School | NAGA CITY | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8714965.051 |  |  | COMPLETED | 1 | 2016-04-09 |  | 050314S00301 | 15FE0115 | 2015-09-24 | 2015-09-28 | 2015-10-09 | 2015-10-19 | 2015-11-02 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
5112 | NC 2014 | SHS (2014) | Region V | NAGA CITY | 302266 | Carolina National High School | NAGA CITY | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 | 2015-12-31 | 2015-12-31 | 050314S00300 | 15FE0083 | 2015-06-30 | 2015-07-03 | 2015-07-15 | 2015-07-21 | 2015-08-03 | R.D. MANDANAS CONSTRUCTION
5113 | NC 2014 | SHS (2014) | Region V | NAGA CITY | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2015-12-31 | 2015-12-31 | 050314S00299 | 15FE0082 | 2015-06-30 | 2015-07-03 | 2015-07-15 | 2015-07-21 | 2015-08-03 | HNR CONSTRUCTION & SUPPLY
5114 | NC 2014 | SHS (2014) | Region V | NAGA CITY | 302269 | Naga City School of Arts and Trades | NAGA CITY | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1
5115 | NC 2014 | SHS (2014) | Region V | NAGA CITY | 302268 | Naga City Science High School | NAGA CITY | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-31 | 2015-12-12 | 050314S00297 | 15FE0081 | 2015-06-30 | 2015-07-03 | 2015-07-15 | 2015-07-20 | 2015-08-03 | HNR CONSTRUCTION & SUPPLY
5116 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114336 | Abas ES | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-11 | 050614S00074 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-11 | 2014-07-17 | TR CONSTRUCTION
5117 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302183 | Bagatao NHS | MAGALLANES (34 BRGYS) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-11 | 050614S00117 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5118 | NC 2014 | K10 (2014) | Region V | Sorsogon | 310005 | Bagong Sirang HS | CASTILLA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-08 | 050614S00104 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5119 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114138 | Banban ES | DONSOL | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-07 | 050614S00084 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5120 | NC 2014 | K10 (2014) | Region V | Sorsogon | 310006 | Bantayan High School | PILAR | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1007570.4383 |  |  | COMPLETED | 1 | 2015-04-02 | 2015-04-02 | 050614S00126 | 14FK0026 | 2014-10-27 | 2014-11-08 | 2014-11-10 | 2014-11-22 | 2014-12-03 | HKP CONSTRUCTION AND SUPPLY
5121 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302186 | Biriran NHS | JUBAN | 1 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-11-11 | 2015-11-11 | 050614S00152 | 15FL0023 | 2015-07-12 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | ZKR CONSTRUCTION & SUPPLY
5122 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114101 | Bogna ES | CASTILLA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-12 | 050614S00093 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5123 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114118 | Buenavista ES | CASTILLA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-08 | 050614S00089 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5124 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114119 | Burabod ES | CASTILLA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-15 | 050614S00088 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5125 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114120 | Caburacan ES | CASTILLA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-09 | 050614S00087 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5126 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114368 | Cagdongon ES | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-12 | 050614S00111 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5127 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114277 | Cagtalaba ES | MAGALLANES (34 BRGYS) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-12 | 050614S00079 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-04 | 2014-07-17 | TR CONSTRUCTION
5128 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302196 | Calao NHS | PRIETO DIAZ | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 7044087.6381 |  |  | COMPLETED | 1 | 2016-01-21 |  | 050614S00156 | 15FL0041 | 2015-07-27 | 2015-08-05 | 2015-08-18 | 2015-09-08 | 2015-09-24 | RGE CONSTRUCTION & SUPPLY
5129 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114121 | Canjela ES | CASTILLA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-12 | 050614S00086 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5130 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302197 | Casiguran Technical Vocational School | CASIGURAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1
5131 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302198 | Castilla NHS | CASTILLA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 | 2016-04-28 |  | 050614S00154 | 15FK0049 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-07-29 | 2015-09-01 | AL NINO CONSTRUCTION & SUPPLY
5132 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114103 | Cogon ES | CASTILLA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5133 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302201 | Cumadcad NHS | CASTILLA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
5134 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302201 | Cumadcad NHS | CASTILLA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
5135 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114160 | Dancalan ES | DONSOL | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-11 | 050614S00095 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5136 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114372 | Del Rosario ES | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-12 | 050614S00108 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5137 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114123 | Dinapa ES | CASTILLA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-10-24 | 2015-10-21 | 050614S00136 | 15FK0048 | 2015-06-19 | 2015-06-24 | 2015-07-02 | 2015-07-20 | 2015-07-27 | RMH CONSTRUCTION & SUPPLY
5138 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302205 | Donsol National Comprehensive HS - Banuang Gurang Extension HS | DONSOL | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-04-28 |  | 050614S00153 | 15FK0049 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-08-12 | 2015-09-01 | AL NINO CONSTRUCTION & SUPPLY
5139 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302211 | Gabao NHS | IROSIN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-08 |  | 050614S00158 | 15FL0036 | 2015-07-26 | 2015-08-05 | 2015-08-17 | 2015-09-22 | 2015-10-02 | BLACKRAM BUILDERS, INC.
5140 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302212 | Gallanosa National High School | IROSIN | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
5141 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114346 | Guiron ES | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-15 | 050614S00073 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5142 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302215 | Irosin North HS | IROSIN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
5143 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114107 | Libtong ES | CASTILLA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-08 | 050614S00091 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5144 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114377 | Lourdes ES | PILAR | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-10 | 050614S00113 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5145 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114350 | Lungib ES | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 050614S00072 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-04 | 2014-07-17 | TR CONSTRUCTION
5146 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302217 | Lungib NHS | PILAR | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1768057.4859 |  |  | COMPLETED | 1 | 2015-04-02 | 2015-04-02 | 050614S00123 | 14FK0026 | 2014-10-27 | 2014-11-08 | 2014-11-10 | 2014-11-22 | 2014-12-03 | HKP CONSTRUCTION AND SUPPLY
5147 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302224 | Manuel T. Sia MHS | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-08 | 050614S00119 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5148 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302226 | Mayon NHS | CASTILLA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5149 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114379 | Mercedes ES | PILAR | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-08 | 050614S00114 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5150 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114381 | Millabas ES | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-10 | 050614S00115 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5151 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114148 | Nagalon ES | DONSOL | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-10 | 050614S00070 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5152 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302228 | Oras National High School | CASTILLA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-13 | 050614S00107 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5153 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114170 | Pangpang ES | DONSOL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-09 | 050614S00080 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-04 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5154 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114355 | Pangpang ES | PILAR | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
5155 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114384 | Pinagsalog ES | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-13 | 050614S00116 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5156 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114357 | Pineda ES | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-10 | 050614S00081 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5157 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114358 | Provenir ES | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-11 | 050614S00101 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5158 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114130 | Quirapi ES | CASTILLA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-12 | 050614S00085 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5159 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302234 | Rizal National High School | GUBAT | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
5160 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114113 | Saclayan ES | CASTILLA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 957320.4383 |  |  | COMPLETED | 1 | 2015-04-02 | 2015-04-02 | 050614S00121 | 14FK0026 | 2014-10-27 | 2014-11-08 | 2014-11-10 | 2014-11-21 | 2014-12-03 | HKP CONSTRUCTION AND SUPPLY
5161 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114298 | Salvacion ES | MAGALLANES (34 BRGYS) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-13 | 050614S00075 | 14FK0014 | 2014-06-11 | 2014-06-23 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5162 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302236 | Salvacion NHS | PILAR | 1 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3770805.49 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-10 | 050614S00106 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5163 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114359 | San Antonio ES | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5164 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302240 | San Juan NHS | CASIGURAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-09 | 050614S00105 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5165 | NC 2014 | K10 (2014) | Region V | Sorsogon | 310008 | San Rafael High School | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-10 | 050614S00096 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5166 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114153 | San Ramon ES | DONSOL | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788157.4859 |  |  | COMPLETED | 1 | 2015-04-02 | 2015-04-02 | 050614S00122 | 14FK0026 | 2014-10-27 | 2014-11-08 | 2014-11-10 | 2014-11-23 | 2014-12-03 | HKP CONSTRUCTION AND SUPPLY
5167 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114154 | San Vicente ES | DONSOL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-10 | 050614S00082 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5168 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114283 | Sta. Elena ES | MAGALLANES (34 BRGYS) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-09 | 050614S00078 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-04 | 2014-07-17 | TR CONSTRUCTION
5169 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114284 | Sta. Lourdes ES | MAGALLANES (34 BRGYS) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-11 | 050614S00077 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-04 | 2014-07-17 | TR CONSTRUCTION
5170 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114285 | Tagas ES | MAGALLANES (34 BRGYS) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-12 | 050614S00076 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-07 | 2014-07-17 | TR CONSTRUCTION
5171 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114362 | Tinago ES | PILAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-09 | 050614S00120 | 14FK0014 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | TR CONSTRUCTION
5172 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114116 | Tomalaytay ES | CASTILLA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-09 | 050614S00090 | 14FK0015 | 2014-06-11 | 2014-06-24 | 2014-06-25 | 2014-07-08 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5173 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114156 | Tongdol ES | DONSOL | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-10-24 | 2015-10-24 | 050614S00137 | 15FK0048 | 2015-06-19 | 2015-06-24 | 2015-07-03 | 2015-07-13 | 2015-07-27 | RMH CONSTRUCTION & SUPPLY
5174 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114157 | Tres Maria ES | DONSOL | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 977420.4383 |  |  | COMPLETED | 1 | 2015-04-02 | 2015-04-02 | 050614S00124 | 14FK0026 | 2014-10-27 | 2014-11-08 | 2014-11-10 | 2014-11-23 | 2014-12-03 | HKP CONSTRUCTION AND SUPPLY
5175 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302238 | (Consul) Louella G. Alcoba NHS | BULAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2907699.43 |  |  | COMPLETED | 1
5176 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302238 | (Consul) Louella G. Alcoba NHS | BULAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8284265.051 |  |  | COMPLETED | 1
5177 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114250 | Anog ES | JUBAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-13 | 050614S00015 | 14FL0015 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-09 | 2014-09-16 | ELKANKONSTRAK DEVELOPMENT CORPORATION
5178 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302182 | Bagacay National High School | GUBAT | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
5179 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302182 | Bagacay National High School | GUBAT | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8284265.051 |  |  | COMPLETED | 1
5180 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114223 | Bagsangan ES | IROSIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00005 | 14FL0011 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
5181 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302184 | Barcelona National Comprehensive High School | BARCELONA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5182 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302184 | Barcelona National Comprehensive HS | BARCELONA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8249615.051 |  |  | COMPLETED | 1
5183 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302191 | Beguin High School | BULAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00036 | 14FL0010 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | STEVEN CONSTRUCTION & SUPPLY
5184 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302185 | Bentuco NHS | GUBAT | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-12 | 050614S00040 | 14FL0014 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-02 | 2014-09-15 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU
5185 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114001 | Bical ES | BULAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1997317.57 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-01-19 | 050614S00099 | 14FL0009 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5186 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114252 | Biriran ES | JUBAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-13 | 050614S00016 | 14FL0015 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-09 | 2014-09-16 | ELKANKONSTRAK DEVELOPMENT CORPORATION
5187 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114033 | Bliss ES | BULAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00018 | 14FL0010 | 2014-07-09 | 2014-08-15 | 2014-08-22 | 2014-09-23 | 2014-09-25 | STEVEN CONSTRUCTION & SUPPLY
5188 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114304 | Bolo ES | MATNOG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 050614S00055 | 14FL0012 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-08 | 2014-09-16 | CPR CONSTRUCTION AND SUPPLY
5189 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114225 | Bolos ES | IROSIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00006 | 14FL0011 | 2014-07-10 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
5190 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114305 | Bon-ot (Big) ES | MATNOG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 050614S00056 | 14FL0012 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-08 | 2014-09-16 | CPR CONSTRUCTION AND SUPPLY
5191 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114207 | Buenavista ES | GUBAT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1105829.12 |  |  | COMPLETED | 1
5192 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302188 | Buhang NHS | BULUSAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8305055.051 |  |  | COMPLETED | 1 | 2016-01-18 |  | 050614S00145 | 15FL0035 | 2015-07-26 | 2015-08-05 | 2015-08-17 | 2015-09-04 | 2015-09-11 | BLACKRAM BUILDERS, INC.
5193 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302189 | Bulacao NHS | GUBAT | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6344087.6381 |  |  | COMPLETED | 1 |  |  | 050614S00144 | 15FL0040 | 2015-07-27 | 2015-08-05 | 2015-08-18
5194 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302190 | Bulan NHS | BULAN | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11015942.5917 |  |  | COMPLETED | 1 | 2016-01-18 |  | 050614S00143 | 15FL0027 | 2015-07-14 | 2015-07-16 | 2015-07-30 | 2015-08-18 | 2015-08-27 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
5195 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114004 | Bulan North CS-B | BULAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2881374.43 |  |  | REVERTED | 0
5196 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302192 | Bulusan NHS | BULUSAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5197 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302192 | Bulusan NHS | BULUSAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8249615.051 |  |  | COMPLETED | 1
5198 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114005 | C.M. Recto ES | BULAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2017917.57 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-01-19 | 050614S00097 | 14FL0009 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5199 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114188 | Cabiguhan ES | GUBAT | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2880174.43 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-12 | 050614S00025 | 14FL0014 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-02 | 2014-09-15 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU
5200 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114006 | Cadandanan ES | BULAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1104929.12 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-01-19 | 050614S00103 | 14FL0009 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5201 | NC 2014 | K10 (2014) | Region V | Sorsogon | 310001 | Cadandanan NHS | BULAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-01-19 | 050614S00048 | 14FL0009 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5202 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302221 | Cagbolo National Vocational HS | MAGALLANES (34 BRGYS) | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
5203 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114253 | Calateo ES | JUBAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-13 | 050614S00010 | 14FL0015 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-09 | 2014-09-16 | ELKANKONSTRAK DEVELOPMENT CORPORATION
5204 | NC 2014 | K10 (2014) | Region V | Sorsogon | 175009 | Calayuan ES | MATNOG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 050614S00067 | 14FL0012 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-08 | 2014-09-16 | CPR CONSTRUCTION AND SUPPLY
5205 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114007 | Calomagon ES | BULAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1101779.12 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-01-19 | 050614S00083 | 14FL0009 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5206 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114060 | Capiricohan ES | BULUSAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 050614S00031 | 14FL0016 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5207 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114258 | Cogon ES | JUBAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995617.57 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-13 | 050614S00001 | 14FL0015 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-09 | 2014-09-16 | ELKANKONSTRAK DEVELOPMENT CORPORATION
5208 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114010 | Daganas ES | BULAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2914974.43 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-01-19 | 050614S00061 | 14FL0009 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5209 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114012 | Dolos ES | BULAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-01-19 | 050614S00026 | 14FL0009 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5210 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114013 | E. Quirino ES | BULAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2880174.43 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-01-19 | 050614S00034 | 14FL0009 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5211 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114259 | Embarcadero ES | JUBAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-13 | 050614S00003 | 14FL0015 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-09 | 2014-09-16 | ELKANKONSTRAK DEVELOPMENT CORPORATION
5212 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302210 | Faustino G. Glua High School | BULAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00059 | 14FL0010 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | STEVEN CONSTRUCTION & SUPPLY
5213 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302213 | Gate NHS | BULAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5214 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302213 | Gate NHS | BULAN | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
5215 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114313 | Genablan Occ. ES | MATNOG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 050614S00057 | 14FL0012 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-08 | 2014-09-16 | CPR CONSTRUCTION AND SUPPLY
5216 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114260 | Grefalda ES | JUBAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-06-04 | 2015-06-04 | 050614S00020 | 14FL0064 | 2014-12-25 | 2014-12-23 | 2015-01-09 | 2015-01-26 | 2015-02-05 | CBC CONSTRUCTION & SUPPLY
5217 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2 | 1 | 12 | 2STY12CL | 2014 K10 BATCH 3 | 15225278.9062 |  |  | COMPLETED | 1
5218 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302214 | Gubat National High School | GUBAT | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10976342.5917 |  |  | COMPLETED | 1
5219 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114234 | Gumapia ES | IROSIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00007 | 14FL0011 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
5220 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302215 | Irosin North HS | IROSIN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
5221 | NC 2014 | SHS (2014) | Region V | SORSOGON | 310002 | J. P. Laurel HS | BULAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8353565.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 050614S00160 | 15FL0037 | 2015-07-26 | 2015-08-05 | 2015-08-17 | 2015-09-08 | 2015-09-24 | ZKR CONSTRUCTION & SUPPLY
5222 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114016 | Jamorawon ES | BULAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-01-19 | 050614S00024 | 14FL0009 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5223 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114316 | Jose C. Frencillo ES | MATNOG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2902284.43 |  |  | COMPLETED | 1 | 2015-04-10 | 2015-04-10 | 050614S00058 | 14FL0025 | 2014-10-17 | 2014-10-23 | 2014-11-04 | 2014-12-04 | 2014-12-11 | QDC CONSTRUCTION AND SUPPLY
5224 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302187 | JUBAN NHS | JUBAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5225 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302187 | Juban NHS | JUBAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
5226 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302235 | Jupi National High School | GUBAT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-12 | 050614S00019 | 14FL0014 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-02 | 2014-09-15 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU
5227 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114317 | Laboy ES | MATNOG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 050614S00069 | 14FL0012 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-08 | 2014-09-16 | CPR CONSTRUCTION AND SUPPLY
5228 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114018 | M. L. Roxas ES | BULAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-01-19 | 050614S00023 | 14FL0009 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5229 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114319 | Mambajog ES | MATNOG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 050614S00060 | 14FL0012 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-08 | 2014-09-16 | CPR CONSTRUCTION AND SUPPLY
5230 | NC 2014 | K10 (2014) | Region V | Sorsogon | 113988 | Mapapac ES | BARCELONA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-13 | 2014-12-13 | 050614S00102 | 14FL0013 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-02 | 2014-09-15 | RMH CONSTRUCTION & SUPPLY
5231 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114238 | Mapaso ES | IROSIN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
5232 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114265 | Mario G. Guarina ES | JUBAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-13 | 050614S00068 | 14FL0015 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-09 | 2014-09-16 | ELKANKONSTRAK DEVELOPMENT CORPORATION
5233 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114239 | Monbon ES | IROSIN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-10-12 | 050614S00135 | 15FL0022 | 2015-07-12 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | BLACKRAM BUILDERS, INC.
5234 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114022 | Nasuje ES | BULAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00022 | 14FL0010 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | STEVEN CONSTRUCTION & SUPPLY
5235 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114196 | Ogao ES | GUBAT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-12 | 050614S00033 | 14FL0014 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-02 | 2014-09-15 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU
5236 | NC 2014 | K10 (2014) | Region V | Sorsogon | 175014 | Omagom PS | IROSIN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 050614S00043 | 14FL0022 | 2014-10-07 | 2014-10-09 | 2014-10-21 | 2014-11-05 | 2014-11-14 | WIND RIVER COURT CONSTRUCTION AND DEVELOPMENT
5237 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114023 | Padre Diaz ES | BULAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1989317.57 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00021 | 14FL0010 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | STEVEN CONSTRUCTION & SUPPLY
5238 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114324 | Pange ES | MATNOG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1118874.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 050614S00052 | 14FL0012 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-08 | 2014-09-16 | CPR CONSTRUCTION AND SUPPLY
5239 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114198 | Patag ES | GUBAT | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-12 | 050614S00027 | 14FL0014 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-02 | 2014-09-15 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU
5240 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114326 | Poropandan ES | MATNOG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 050614S00062 | 14FL0012 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-08 | 2014-09-16 | CPR CONSTRUCTION AND SUPPLY
5241 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302232 | Prieto Diaz NHS | PRIETO DIAZ | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-11-11 | 2015-11-11 | 050614S00167 | 15FL0023 | 2015-07-12 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | ZKR CONSTRUCTION & SUPPLY
5242 | NC 2014 | K10 (2014) | Region V | Sorsogon | 113991 | Putiao ES | BARCELONA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-13 | 2014-12-13 | 050614S00109 | 14FL0013 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-02 | 2014-09-15 | RMH CONSTRUCTION & SUPPLY
5243 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114266 | Putingsapa ES | JUBAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-13 | 050614S00053 | 14FL0015 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-09 | 2014-09-16 | ELKANKONSTRAK DEVELOPMENT CORPORATION
5244 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302233 | Quezon NHS | BULAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5245 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302233 | Quezon NHS | BULAN | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6529337.6381 |  |  | COMPLETED | 1
5246 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302234 | Rizal National High School | GUBAT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5247 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114048 | Sagrada ES | BULAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00028 | 14FL0010 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | STEVEN CONSTRUCTION & SUPPLY
5248 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114249 | San Agustin PS | IROSIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00014 | 14FL0011 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
5249 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114067 | San Antonio ES | BULUSAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1101779.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 050614S00012 | 14FL0016 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5250 | NC 2014 | K10 (2014) | Region V | Sorsogon | 310009 | San Antonio NHS | BARCELONA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-10-12 | 050614S00133 | 15FL0022 | 2015-07-12 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | BLACKRAM BUILDERS, INC.
5251 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302237 | San Francisco NHS | BULAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8235755.051 |  |  | COMPLETED | 1 | 2016-02-04 |  | 050614S00171 | 15FL0032 | 2015-07-26 | 2015-07-29 | 2015-08-10 | 2015-09-17 | 2015-09-28 | GRELIPS CONSTRUCTION & DEVELOPMENT
5252 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114242 | San Isidro ES | IROSIN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
5253 | NC 2014 | K10 (2014) | Region V | Sorsogon | 175013 | San Pedro ES | IROSIN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00035 | 14FL0011 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
5254 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114050 | San Rafael ES | BULAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00029 | 14FL0010 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | STEVEN CONSTRUCTION & SUPPLY
5255 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114073 | San Rafael ES | BULUSAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 050614S00032 | 14FL0016 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-11 | 2014-09-22 | STEVEN CONSTRUCTION & SUPPLY
5256 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114402 | San Rafael ES | PRIETO DIAZ | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5257 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302242 | San Roque NHS | BULUSAN | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6353987.6381 |  |  | COMPLETED | 1 | 2016-01-29 |  | 050614S00170 | 15FL0038 | 2015-07-27 | 2015-08-05 | 2015-08-18 | 2015-09-21 | 2015-10-02 | RMH CONSTRUCTION & SUPPLY
5258 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114052 | San Vicente ES | BULAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1998767.57 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00030 | 14FL0010 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | STEVEN CONSTRUCTION & SUPPLY
5259 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114216 | Sangat ES | GUBAT | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-12 | 050614S00004 | 14FL0014 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-02 | 2014-09-15 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU
5260 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114329 | Sinebaran ES | MATNOG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 050614S00063 | 14FL0012 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-08 | 2014-09-16 | CPR CONSTRUCTION AND SUPPLY
5261 | NC 2014 | K10 (2014) | Region V | Sorsogon | 113995 | Sta. Cruz ES | BARCELONA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-13 | 2014-12-13 | 050614S00100 | 14FL0013 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-02 | 2014-09-15 | RMH CONSTRUCTION & SUPPLY
5262 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302246 | Sua HS | MATNOG | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2697828.124 |  |  | COMPLETED | 1 | 2015-11-11 | 2015-11-11 | 050614S00169 | 15FL0023 | 2015-07-12 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | ZKR CONSTRUCTION & SUPPLY
5263 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114244 | Tabon-Tabon ES | IROSIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00008 | 14FL0011 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
5264 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114201 | Tagaytay Elementary School | GUBAT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1101779.12 |  |  | COMPLETED | 1
5265 | NC 2014 | K10 (2014) | Region V | Sorsogon | 302247 | Talaonga NHS | SANTA MAGDALENA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
5266 | NC 2014 | SHS (2014) | Region V | SORSOGON | 302247 | Talaonga NHS | SANTA MAGDALENA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
5267 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114271 | Tampi ES | JUBAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-06-05 | 2015-06-05 | 050614S00054 | 14FL0065 | 2014-12-25 | 2014-12-23 | 2015-01-09 | 2015-01-26 | 2015-02-05 | CBC CONSTRUCTION & SUPPLY
5268 | NC 2014 | SHS (2014) | Region V | SORSOGON | 310010 | Tiong Hen So MHS | MATNOG | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-04-28 |  | 050614S00148 | 15FK0049 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-08-11 | 2015-09-01 | AL NINO CONSTRUCTION & SUPPLY
5269 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114334 | Tugas ES | MATNOG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010617.57 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 050614S00064 | 14FL0012 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-08 | 2014-09-16 | CPR CONSTRUCTION AND SUPPLY
5270 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114247 | Tulay ES | IROSIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1105829.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 050614S00013 | 14FL0011 | 2014-07-09 | 2014-07-11 | 2014-08-15 | 2014-09-17 | 2014-09-25 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
5271 | NC 2014 | K10 (2014) | Region V | Sorsogon | 114417 | Uson ES | SANTA MAGDALENA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1989317.57 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 050614S00066 | 14FL0017 | 2014-07-10 | 2014-07-11 | 2014-08-19 | 2014-09-09 | 2014-09-16 | AVIC CONSTRUCTION AND SUPPLY(FOR. AVIC CONST.)
5272 | NC 2014 | SHS (2014) | Region V | Sorsogon City | 302271 | Buenavista National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 | 2016-05-18 |  | 050614S00172 | 15FK0050 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-08-26 | 2015-09-01 | TR CONSTRUCTION
5273 | NC 2014 | SHS (2014) | Region V | Sorsogon City | 310403 | Buhatan Integrated National School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6349337.6381 |  |  | COMPLETED | 1 | 2016-05-18 |  | 050614S00166 | 15FK0050 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-08-18 | 2015-09-01 | TR CONSTRUCTION
5274 | NC 2014 | SHS (2014) | Region V | SORSOGON CITY | 302273 | Gatbo National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-04-28 | 2015-11-14 | 050614S00165 | 15FK0049 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-08-18 | 2015-09-01 | AL NINO CONSTRUCTION & SUPPLY
5275 | NC 2014 | K10 (2014) | Region V | Sorsogon City | 114557 | Marinas I Elmentary School | CITY OF SORSOGON (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
5276 | NC 2014 | SHS (2014) | Region V | SORSOGON CITY | 302274 | Osiao Paglingap National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-04-28 | 2015-12-21 | 050614S00164 | 15FK0049 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-08-12 | 2015-09-01 | AL NINO CONSTRUCTION & SUPPLY
5277 | NC 2014 | SHS (2014) | Region V | Sorsogon City | 310406 | Pamurayan Integrated School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1 | 2016-05-18 |  | 050614S00159 | 15FK0050 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-07-22 | 2015-09-01 | TR CONSTRUCTION
5278 | NC 2014 | K10 (2014) | Region V | Sorsogon City | 114578 | Pio Jebulan Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-15 | 050614S00050 | 14FK0015 | 2014-06-11 | 2014-06-23 | 2014-06-25 | 2014-07-02 | 2014-07-17 | STEVEN CONSTRUCTION & SUPPLY
5279 | NC 2014 | K10 (2014) | Region V | Sorsogon City | 302276 | Rizal Integrated National School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1
5280 | NC 2014 | SHS (2014) | Region V | Sorsogon City | 302277 | San Isidro National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10477131.51 |  |  | COMPLETED | 1 | 2016-05-18 |  | 050614S00163 | 15FK0050 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-08-03 | 2015-09-01 | TR CONSTRUCTION
5281 | NC 2014 | SHS (2014) | Region V | Sorsogon City | 302278 | Sawanga National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10447131.51 |  |  | COMPLETED | 1 | 2016-06-17 |  | 050614S00173 | 15FK0050 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-08-25 | 2015-09-01 | TR CONSTRUCTION
5282 | NC 2014 | K10 (2014) | Region V | Sorsogon City | 114581 | Sorsogon Pilot Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1
5283 | NC 2014 | SHS (2014) | Region V | Sorsogon City | 310404 | Sto. Niño Integrated School | CITY OF SORSOGON (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-05-18 |  | 050614S00162 | 15FK0050 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-07-29 | 2015-09-01 | TR CONSTRUCTION
5284 | NC 2014 | SHS (2014) | Region V | Tabaco City | 302281 | Bantayan NHS | CITY OF TABACO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8254140.051 |  |  | COMPLETED | 1 | 2015-12-30 |  | 050114S00148 | 15FA0049 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-26 | 2015-07-31 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO
5285 | NC 2014 | K10 (2014) | Region V | Tabaco City | 310501 | Bogñabong High School | CITY OF TABACO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
5286 | NC 2014 | K10 (2014) | Region V | Tabaco City | 114616 | Hacienda ES | CITY OF TABACO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-15 | 050114S00055 | 14FA0012 | 2014-07-09 | 2014-07-21 | 2014-07-22 |  | 2014-08-20 | ATHENA CONSTRUCTION AND DEVELOPMENT
5287 | NC 2014 | K10 (2014) | Region V | Tabaco City | 310503 | Hacienda High School | CITY OF TABACO | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2014 K10 BATCH 4C | 4673636.82 |  |  | COMPLETED | 1 | [10 empty] | Reverted, to confirm
5288 | NC 2014 | K10 (2014) | Region V | Tabaco City | 310504 | Mariroc High School | CITY OF TABACO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-30 | 2015-10-30 | 050114S00082 | 15FA0056 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-31 | 2015-08-26 | BLACKRAM BUILDERS, INC.
5289 | NC 2014 | K10 (2014) | Region V | Tabaco City | 302282 | San Antonio NHS, Tabaco | CITY OF TABACO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5290 | NC 2014 | SHS (2014) | Region V | Tabaco City | 302282 | San Antonio NHS, Tabaco | CITY OF TABACO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
5291 | NC 2014 | SHS (2014) | Region V | Tabaco City | 302283 | San Lorenzo NHS | CITY OF TABACO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 050114S00150 | 15FA0042 | 2015-07-08 | 2015-07-09 | 2015-07-21 | 2015-07-25 | 2015-08-05 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
5292 | NC 2014 | SHS (2014) | Region V | Tabaco City | 302284 | San Miguel NHS | CITY OF TABACO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8573343.991 |  |  | COMPLETED | 1 |  |  | 050114S00151 | 15FA0082 | 2015-08-05 | 2015-08-17 | 2015-11-18
5293 | NC 2014 | K10 (2014) | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5294 | NC 2014 | K10 (2014) | Region V | Tabaco City | 114604 | Tabaco Northwest CS - (Panal-Bangkilingan ES) | CITY OF TABACO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-15 | 050114S00054 | 14FA0012 | 2014-07-09 | 2014-07-21 | 2014-07-22 |  | 2014-08-20 | ATHENA CONSTRUCTION AND DEVELOPMENT
11385 | NC 2015 | K10 (2015) | Region V | Albay | 111878 | Balza ES | MALINAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
11386 | NC 2015 | K10 (2015) | Region V | Albay | 111604 | Cagbulacao ES | BACACAY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | COMPLETED | 1 |  |  | 050115S00057 | 15FA0084 | 2015-11-13 | 2015-11-20 | 2015-12-08
11387 | NC 2015 | K10 (2015) | Region V | Albay | 111605 | Cagraray ES | BACACAY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3022592.44 |  |  | COMPLETED | 1 |  |  | 050115S00055 | 15FA0084 | 2015-11-13 | 2015-11-20 | 2015-12-08
11388 | NC 2015 | K10 (2015) | Region V | Albay | 111873 | Comun ES | MALINAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050115S00060 | 15FA0084 | 2015-11-13 | 2015-11-20 | 2015-12-08
11389 | NC 2015 | K10 (2015) | Region V | Albay | 172510 | Libod ES | MALINAO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050115S00022 | 15FA0057 | 2015-07-21 | 2015-07-17 | 2015-08-03 | 2015-08-07 | 2015-08-28 | MAGDA CONSTRUCTION AND SUPPLY
11390 | NC 2015 | TECHVOC (2015) | Region V | Albay | 301810 | Malinao NHS | MALINAO | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4884098.54 |  |  | COMPLETED | 1
11391 | NC 2015 | K10 (2015) | Region V | Albay | 111612 | Mataas ES | BACACAY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2008606.04 |  |  | COMPLETED | 1 |  |  | 050115S00047 | 15FA0084 | 2015-11-13 | 2015-11-20 | 2015-12-08
11392 | NC 2015 | K10 (2015) | Region V | Albay | 111614 | Nahapunan ES | BACACAY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050115S00059 | 15FA0084 | 2015-11-13 | 2015-11-20 | 2015-12-08
11393 | NC 2015 | K10 (2015) | Region V | Albay | 111864 | San Jose ES | MALILIPOT | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 050115S00026 | 15FA0059 | 2015-08-05 | 2015-08-17 | 2015-08-18 | 2015-08-22 | 2015-09-04 | STEVEN CONSTRUCTION & SUPPLY
11394 | NC 2015 | TECHVOC (2015) | Region V | Albay | 301879 | Sto. Domingo NHS | SANTO DOMINGO (LIBOG) | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
11395 | NC 2015 | K10 (2015) | Region V | Albay | 111620 | Sula ES | BACACAY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2008606.04 |  |  | COMPLETED | 1 |  |  | 050115S00056 | 15FA0084 | 2015-11-13 | 2015-11-20 | 2015-12-08
11396 | NC 2015 | TECHVOC (2015) | Region V | Albay | 301880 | Tiwi Agro-Ind'L Sch. | TIWI | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4879098.54 |  |  | COMPLETED | 1
11397 | NC 2015 | SHS (2015) | Region V | ALBAY | 301808 | Anislag NHS | DARAGA (LOCSIN) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10617131.51 |  |  | COMPLETED | 1
11398 | NC 2015 | SHS (2015) | Region V | Albay | 301826 | Banadero HS | DARAGA (LOCSIN) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 050115S00066 | 15FB0077 | 2015-08-25 | 2015-08-20 | 2015-09-02 | 2015-10-12 | 2015-10-21 | WIND RIVER COURT CONSTRUCTION AND DEVELOPMENT
11399 | NC 2015 | K10 (2015) | Region V | Albay | 112020 | Binosawan ES | RAPU-RAPU | 2 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 3 | 4673636.82 |  |  | COMPLETED | 1 |  |  | 050115S00027 | 15FB0087 | 2015-09-29 | 2015-09-24 | 2015-10-07 | 2015-10-15 | 2015-10-26 | ZKR CONSTRUCTION & SUPPLY
11400 | NC 2015 | K10 (2015) | Region V | Albay | 112026 | Carogcog ES | RAPU-RAPU | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 050115S00058 | 15FB0081 | 2015-08-31 | 2015-08-28 | 2015-09-18 | 2015-09-24 | 2015-10-05 | SULVIR ENGINEERING AND CONSTRUCTION
11401 | NC 2015 | SHS (2015) | Region V | ALBAY | 301825 | Daraga NHS | DARAGA (LOCSIN) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
11402 | NC 2015 | K10 (2015) | Region V | Albay | 112029 | Galicia ES | RAPU-RAPU | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050115S00031 | 15FB0087 | 2015-09-29 | 2015-09-24 | 2015-10-07 | 2015-10-15 | 2015-10-26 | ZKR CONSTRUCTION & SUPPLY
11403 | NC 2015 | K10 (2015) | Region V | Albay | 112030 | Guinanayan ES | RAPU-RAPU | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 050115S00046 | 15FB0081 | 2015-08-31 | 2015-08-28 | 2015-09-18 | 2015-09-24 | 2015-10-05 | SULVIR ENGINEERING AND CONSTRUCTION
11404 | NC 2015 | SHS (2015) | Region V | ALBAY | 309518 | Kilicao HS | DARAGA (LOCSIN) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8344965.051 |  |  | COMPLETED | 1
11405 | NC 2015 | K10 (2015) | Region V | Albay | 111632 | Kinuartilan ES | CAMALIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
11406 | NC 2015 | K10 (2015) | Region V | Albay | 111632 | Kinuartilan ES | CAMALIG | 2 |  | 1 | 1STY1CL (Toilet Attached) | 2015 K10 BATCH 3 | 1248449.69 |  |  | COMPLETED | 1
11407 | NC 2015 | SHS (2015) | Region V | Albay | 301845 | Manito NHS | MANITO | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 8 | 10877342.5917 |  |  | COMPLETED | 1
11408 | NC 2015 | K10 (2015) | Region V | Albay | 111694 | Mayon ES | DARAGA (LOCSIN) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050115S00061 | 15FB0080 | 2015-08-31 | 2015-08-28 | 2015-09-18 | 2015-09-24 | 2015-10-05 | ZKR CONSTRUCTION & SUPPLY
11409 | NC 2015 | K10 (2015) | Region V | Albay | 112039 | Minso ES | RAPU-RAPU | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 050115S00034 | 15FB0087 | 2015-09-29 | 2015-09-24 | 2015-10-07 | 2015-10-15 | 2015-10-26 | ZKR CONSTRUCTION & SUPPLY
11410 | NC 2015 | K10 (2015) | Region V | Albay | 111700 | San Vicente Grande ES | DARAGA (LOCSIN) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 050115S00035 | 15FB0074 | 2015-08-18 | 2015-08-13 | 2015-08-26 | 2015-10-12 | 2015-10-22 | PEDXING BUILDERS
11411 | NC 2015 | K10 (2015) | Region V | Albay | 111652 | Tagoytoy ES | CAMALIG | 2 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 3 | 4673636.82 |  |  | COMPLETED | 1 |  |  | 050115S00023 | 15FB0083 | 2015-09-17 | 2015-09-17 | 2015-09-29 | 2015-10-19 | 2015-10-28 | QDC CONSTRUCTION AND SUPPLY | No Remarks
11412 | NC 2015 | K10 (2015) | Region V | Albay | 112002 | Balangibang ES | POLANGUI | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050115S00051 | 15FO0058 | 2015-09-29 | 2015-09-30 | 2015-10-13 | 2015-10-29 | 2015-12-11 | QDC CONSTRUCTION AND SUPPLY
11413 | NC 2015 | TECHVOC (2015) | Region V | Albay | 301866 | Balogo HS | OAS | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4879098.54 |  |  | COMPLETED | 1
11414 | NC 2015 | K10 (2015) | Region V | Albay | 111787 | Bonbon ES | LIBON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050115S00036 | 15FO0027 | 2015-08-04 | 2015-08-05 | 2015-08-17 | 2015-09-03 | 2015-09-11 | SULVIR ENGINEERING AND CONSTRUCTION
11415 | NC 2015 | SHS (2015) | Region V | ALBAY | 301834 | Bonbon NHS | LIBON | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6579337.6381 |  |  | COMPLETED | 1
11416 | NC 2015 | K10 (2015) | Region V | Albay | 111956 | Flores ES | PIO DURAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2033606.04 |  |  | COMPLETED | 1 |  |  | 050115S00052 | 15FO0058 | 2015-09-29 | 2015-09-30 | 2015-10-13 | 2015-10-29 | 2015-12-11 | QDC CONSTRUCTION AND SUPPLY
11417 | NC 2015 | SHS (2015) | Region V | ALBAY | 301828 | Itaran NHS | POLANGUI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6999337.6381 |  |  | COMPLETED | 1 |  |  | 050115S00016 | 15FO0052 | 2015-09-08 | 2015-09-09 | 2015-09-22 | 2015-10-23 | 2015-12-11 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR
11418 | NC 2015 | SHS (2015) | Region V | ALBAY | 301830 | Jovellar NHS | JOVELLAR | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8447465.051 |  |  | COMPLETED | 1
11419 | NC 2015 | SHS (2015) | Region V | Albay | 309513 | Lanigay HS | POLANGUI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1
11420 | NC 2015 | SHS (2015) | Region V | ALBAY | 301833 | Libon Agro-Industrial HS | LIBON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8459965.051 |  |  | COMPLETED | 1
11421 | NC 2015 | SHS (2015) | Region V | ALBAY | 301842 | Malipo NHS | GUINOBATAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 050115S00014 | 15FO0046 | 2015-08-27 | 2015-08-28 | 2015-09-14 | 2015-09-28 | 2015-10-12 | PEDXING BUILDERS
11422 | NC 2015 | SHS (2015) | Region V | ALBAY | 309510 | Mamlad HS | JOVELLAR | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6604337.6381 |  |  | COMPLETED | 1 |  |  | 050115S00020 | 15FO0037 | 2015-08-19 | 2015-08-20 | 2015-09-03 | 2015-09-21 | 2015-10-22 | QDC CONSTRUCTION AND SUPPLY
11423 | NC 2015 | SHS (2015) | Region V | ALBAY | 301849 | Marcial O. Rañola Memorial School | GUINOBATAN | 3 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18517268.79 |  |  | COMPLETED | 1
11424 | NC 2015 | SHS (2015) | Region V | ALBAY | 301849 | Marcial O. Rañola Memorial School | GUINOBATAN | 3 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18517268.79 |  |  | COMPLETED | 1
11425 | NC 2015 | TECHVOC (2015) | Region V | Albay | 301849 | Marcial O. Rañola Memorial School | GUINOBATAN | 3 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
11426 | NC 2015 | SHS (2015) | Region V | ALBAY | 301844 | Mauraro HS | GUINOBATAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10467131.51 |  |  | COMPLETED | 1
11427 | NC 2015 | K10 (2015) | Region V | Albay | 111918 | Nagas ES | OAS | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 050115S00054 | 15FO0058 | 2015-09-29 | 2015-09-30 | 2015-10-13 | 2015-10-29 | 2015-12-11 | QDC CONSTRUCTION AND SUPPLY
11428 | NC 2015 | SHS (2015) | Region V | ALBAY | 301860 | Pantao NHS | LIBON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8337465.051 |  |  | COMPLETED | 1
11429 | NC 2015 | SHS (2015) | Region V | ALBAY | 301860 | Pantao NHS | LIBON | 3 |  | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6441837.6381 |  |  | COMPLETED | 1
11430 | NC 2015 | SHS (2015) | Region V | ALBAY | 301864 | Pioduran National High School | PIO DURAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10467131.51 |  |  | COMPLETED | 1
11431 | NC 2015 | TECHVOC (2015) | Region V | Albay | 301865 | Polangui General Comprehensive HS | POLANGUI | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
11432 | NC 2015 | SHS (2015) | Region V | ALBAY | 301868 | Ponso National HS | POLANGUI | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10737131.51 |  |  | COMPLETED | 1 |  |  | 050115S00008 | 15FO0041 | 2015-08-26 | 2015-08-27 | 2015-09-09 | 2015-10-23 |  | ZKR CONSTRUCTION & SUPPLY
11433 | NC 2015 | K10 (2015) | Region V | Albay | 111938 | Ramay ES | OAS | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 050115S00053 | 15FO0058 | 2015-09-29 | 2015-09-30 | 2015-10-13 | 2015-10-29 | 2015-12-11 | QDC CONSTRUCTION AND SUPPLY
11434 | NC 2015 | K10 (2015) | Region V | Albay | 111924 | Talisay ES | OAS | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 3052592.44 |  |  | COMPLETED | 1 |  |  | 050115S00024 | 15FO0027 | 2015-08-04 | 2015-08-05 | 2015-08-17 | 2015-09-03 | 2015-09-11 | SULVIR ENGINEERING AND CONSTRUCTION
11435 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 173017 | Bagumbayan ES | PARACALE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1
11436 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 173017 | Bagumbayan ES | PARACALE | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
11437 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112279 | Bulala Elementary School | SANTA ELENA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2208606.04 |  |  | COMPLETED | 1
11438 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112279 | Bulala Elementary School | SANTA ELENA | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
11439 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112111 | Casiano Florendo ES | CAPALONGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050215S00027 | 15FC0195 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-14 | 2015-10-26 | BRENTMIN ROOFING ENTERPRISE
11440 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112245 | Dagang ES | PARACALE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 050215S00030 | 15FC0193 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-14 | 2015-10-26 | 128 DRAGON CONSTRUCTION AND SUPPLIES
11441 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112207 | Dumagmang IS | LABO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 050215S00033 | 15FC0192 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-14 | 2015-10-26 | BRENTMIN ROOFING ENTERPRISE
11442 | NC 2015 | TECHVOC (2015) | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2699049.27 |  |  | COMPLETED | 1
11443 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112185 | L. Villamonte ES | LABO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050215S00031 | 15FC0198 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-14 | 2015-10-26 | BRENTMIN ROOFING ENTERPRISE
11444 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112191 | Marcos Pimentel ES | LABO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050215S00032 | 15FC0202 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-14 | 2015-10-26 | BRENTMIN ROOFING ENTERPRISE
11445 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112256 | Pinagbirayan ES | PARACALE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 050215S00028 | 15FC0194 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-14 | 2015-10-26 | BRENTMIN ROOFING ENTERPRISE
11446 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112157 | San Rafael ES | JOSE PANGANIBAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050215S00025 | 15FC0196 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-14 | 2015-10-26 | GOLDEN EGG BUILDER
11447 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112158 | Segundo Aguirre (Sta Rosa Norte.) | JOSE PANGANIBAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050215S00029 | 15FC0197 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-14 | 2015-10-26 | SHEAR CONSTRUCTION AND SUPPLY
11448 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112173 | Tawig ES | JOSE PANGANIBAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050215S00034 | 15FC0191 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-23 | 2015-10-26 | JOMAR BUILDERS & SUPPLY
11449 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112260 | Tugos ES | PARACALE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 050215S00024 | 15FC0190 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-14 | 2015-10-26 | VC VARIN CONSTRUCTION AND HARDWARE SUPPLY
11450 | NC 2015 | TECHVOC (2015) | Region V | Camarines Norte | 301922 | Tulay Na Lupa NHS | LABO | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
11451 | NC 2015 | SHS (2015) | Region V | Camarines Norte | 309613 | Alawihao HS | DAET (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8564965 |  |  | COMPLETED | 1 |  |  | 050215S00015 | 15FC0219 | 2015-09-21 | 2015-10-20 | 2015-10-28 | 2015-11-06 | 2015-11-16 | VC VARIN CONSTRUCTION AND HARDWARE SUPPLY
11452 | NC 2015 | SHS (2015) | Region V | Camarines Norte |  | Camarines Norte NHS-Annex | DAET (Capital) | 2 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 12821310 |  |  | COMPLETED | 1 |  |  | 050215S00017 | 15FC0217 | 2015-09-21 | 2015-10-20 | 2015-10-28 | 2015-11-12 | 2015-11-16 | M.J. APIN BUILDERS
11453 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112234 | Claro E. Ibasco ES | MERCEDES | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 050215S00019 | 15FC0204 | 2015-09-14 | 2015-09-22 | 2015-09-29 | 2015-10-14 | 2015-10-26 | 128 DRAGON CONSTRUCTION AND SUPPLIES
11454 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112223 | Colasi ES | MERCEDES | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 3102592.44 |  |  | COMPLETED | 1 |  |  | 050215S00007 | 15FC0203 | 2015-09-14 | 2015-09-22 | 2015-09-28 | 2015-10-16 | 2015-10-26 | 128 DRAGON CONSTRUCTION AND SUPPLIES
11455 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112303 | El Trino P. Zenarosa ES | VINZONS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 050215S00026 | 15FC0205 | 2015-09-14 | 2015-09-22 | 2015-09-29 | 2015-10-14 | 2015-10-26 | RUR CONSTRUCTION AND SUPPLY
11456 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112145 | F. Baldovino ES | DAET (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050215S00018 | 15FC0201 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-14 | 2015-10-26 | BRENTMIN ROOFING ENTERPRISE
11457 | NC 2015 | TECHVOC (2015) | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
11458 | NC 2015 | SHS (2015) | Region V | Camarines Norte | 301906 | Moreno Integrated School | DAET (Capital) | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 11477343 |  |  | COMPLETED | 1 |  |  | 050215S00016 | 15FC0218 | 2015-09-21 | 2015-10-20 | 2015-10-28 | 2015-11-06 | 2015-11-16 | SHEAR CONSTRUCTION AND SUPPLY
11459 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112098 | Pagsangahan ES | BASUD | 2 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 050215S00011 | 15FC0174 | 2015-08-17 | 2015-08-25 | 2015-09-07 | 2015-11-09 | 2015-11-19 | M.J. APIN BUILDERS
11460 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112138 | Pandan Elementary School | DAET (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6219337.6381 |  |  | COMPLETED | 1 |  |  | 050215S00020 | 15FC0183 | 2015-08-20 | 2015-09-18 | 2015-09-22 | 2015-10-14 | 2015-10-15 | EUS CONSTRUCTION
11461 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112099 | Pedro Rada ES (San Pascual) | BASUD | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050215S00014 | 15FC0199 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-14 | 2015-10-26 | B2K LUMBER, CONSTRUCTION SUPPLIES AND SERVICES
11462 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112104 | San Jose ES | BASUD | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050215S00021 | 15FC0200 | 2015-09-07 | 2015-09-15 | 2015-09-29 | 2015-10-14 | 2015-10-26 | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
11463 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112316 | Vinzons Pilot ES | VINZONS | 2 | 1 | 12 | 2STY12CL | 2015 K10 BATCH 3 | 14579217.1798 |  |  | COMPLETED | 1
11464 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112316 | Vinzons Pilot ES | VINZONS | 2 |  | 12 | 2STY12CL | 2015 K10 BATCH 3 | 14579217.1798 |  |  | COMPLETED | 1
11465 | NC 2015 | K10 (2015) | Region V | Camarines Norte | 112316 | Vinzons Pilot ES | VINZONS | 2 |  | 12 | 2STY12CL | 2015 K10 BATCH 3 | 14579217.1798 |  |  | COMPLETED | 1
11466 | NC 2015 | TECHVOC (2015) | Region V | Camarines Norte | 301925 | Vinzons Pilot High School | VINZONS | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
11467 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 113051 | Alteza ES | SIPOCOT | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050315S00158 | 15FN0048 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-09-04 | 2015-09-08 | A.B. OPENA BUILDERS
11468 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301927 | Anib NHS | SIPOCOT | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050315S00092 | 15FN0062 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-09-30 | 2015-10-02 | ROLA CONSTRUCTION
11469 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301942 | Barcelonita Fisheries School | CABUSAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 050315S00091 | 15FN0053 | 2015-09-02 | 2015-09-10 | 2015-09-22 | 2015-09-28 | 2015-09-30 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
11470 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309743 | Bolo Norte HS | SIPOCOT | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00090 | 15FN0055 | 2015-09-09 | 2015-09-10 | 2015-09-22 | 2015-09-28 | 2015-09-30 | JURASSIC CONSTRUCTION & SUPPLIES
11471 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 113054 | Bolo Sur ES | SIPOCOT | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050315S00140 | 15FN0048 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-09-04 | 2015-09-08 | A.B. OPENA BUILDERS
11472 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301951 | Caima National High School | SIPOCOT | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050315S00089 | 15FN0054 | 2015-09-09 | 2015-09-10 | 2015-09-22 | 2015-10-05 | 2015-10-07 | ALXM CONSTRUCTION
11473 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301958 | Casay PHS | LUPI | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1
11474 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301961 | Colacling HS | LUPI | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00088 | 15FN0061 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-09-30 | 2015-10-02 | HGG BUILDERS & SUPPLY
11475 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301966 | Del Gallego NHS | DEL GALLEGO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 050315S00080 | 15FN0074 | 2015-12-16 | 2015-12-17 | 2015-12-29
11476 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301967 | Don M. Gonzalvo MHS | RAGAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050315S00087 | 15FN0058 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-09-30 | 2015-10-02 | A.B. OPENA BUILDERS
11477 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 113083 | Gabi ES | SIPOCOT | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2030606.04 |  |  | COMPLETED | 1 |  |  | 050315S00202 | 15FN0067 | 2015-11-05 | 2015-11-06 | 2015-11-19 | 2015-11-24 | 2015-12-02 | HGG BUILDERS & SUPPLY
11478 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301977 | Godofredo Reyes, Sr. National HS | RAGAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 050315S00086 | 15FN0057 | 2015-09-09 | 2015-09-10 | 2015-09-22 | 2015-09-28 | 2015-09-30 | JURASSIC CONSTRUCTION & SUPPLIES
11479 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301979 | Haluban NHS | LUPI | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00085 | 15FN0050 | 2015-08-27 | 2015-08-28 | 2015-09-10 | 2015-09-15 | 2015-09-17 | JURASSIC CONSTRUCTION & SUPPLIES
11480 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301988 | Lupi-Iligan HS | LUPI | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00084 | 15FN0050 | 2015-08-27 | 2015-08-28 | 2015-09-10 | 2015-09-15 | 2015-09-17 | JURASSIC CONSTRUCTION & SUPPLIES
11481 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309767 | Manangle High School | SIPOCOT | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00083
11482 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302020 | Ragay Nat'l Agr'l & Fisheries School (RNAFS) | RAGAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00067 | 15FN0059 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-09-30 | 2015-10-02 | A.B. OPENA BUILDERS
11483 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309751 | RNAFS- Ragay Science and Math Oriented Annex HS | RAGAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 050315S00081 | 15FN0063
11484 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309755 | Sacred Heart HS | SIPOCOT | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 050315S00095 | 15FN0061 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-09-30 | 2015-10-02 | HGG BUILDERS & SUPPLY
11485 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112971 | Samay ES | RAGAY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 050315S00189 | 15FN0067 | 2015-11-05 | 2015-11-06 | 2015-11-19 | 2015-11-24 | 2015-12-02 | HGG BUILDERS & SUPPLY
11486 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301980 | San Jose (Alanao) HS | LUPI | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6494337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00079 | 15FN0052 | 2015-09-09 | 2015-09-10 | 2015-09-22 | 2015-09-28 | 2015-09-30 | PBL BUILDERS & SUPPLY
11487 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301929 | Simeon Tycangco MHS | RAGAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 050315S00078 | 15FN0057 | 2015-09-09 | 2015-09-10 | 2015-09-22 | 2015-09-28 | 2015-09-30 | JURASSIC CONSTRUCTION & SUPPLIES
11488 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302046 | Sinuknipan NHS | DEL GALLEGO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00077 | 15FN0056 | 2015-09-09 | 2015-09-10 | 2015-09-22 | 2015-09-28 | 2015-09-30 | ROLA CONSTRUCTION
11489 | NC 2015 | TECHVOC (2015) | Region V | Camarines Sur | 302047 | Sipocot NHS | SIPOCOT | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
11490 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302047 | Sipocot NHS | SIPOCOT | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8514965.051 |  |  | COMPLETED | 1
11491 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 113067 | Sipocot North CS | SIPOCOT | 1 | 1 | 30 | 2STY10CL | 2015 K10 BATCH 6 | 37863930.2791 |  |  | COMPLETED | 1 |  |  | 050315S00190 | 15FN0067 | 2015-11-05 | 2015-11-06 | 2015-11-19 | 2015-11-24 | 2015-12-02 | HGG BUILDERS & SUPPLY
11492 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301930 | Sisa Feliciano MHS | RAGAY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00075 | 15FN0051 | 2015-08-27 | 2015-08-28 | 2015-09-10 | 2015-09-15 | 2015-09-17 | DREAM BUILDERS AND TECH DEV. CORP.
11493 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302051 | Sta. Lutgarda HS | CABUSAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 050315S00074 | 15FN0062 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-09-30 | 2015-10-02 | ROLA CONSTRUCTION
11494 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112588 | Tabion Munti ES | DEL GALLEGO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050315S00188 | 15FN0067 | 2015-11-05 | 2015-11-06 | 2015-11-19 | 2015-11-24 | 2015-12-02 | HGG BUILDERS & SUPPLY
11495 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302064 | Tomas A. Andaya, Sr. NHS | RAGAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8864965.051 |  |  | COMPLETED | 1 |  |  | 050315S00073
11496 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302068 | Villazar NHS | SIPOCOT | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00072 | 15FN0055 | 2015-09-09 | 2015-09-10 | 2015-09-22 | 2015-09-28 | 2015-09-30 | JURASSIC CONSTRUCTION & SUPPLIES
11497 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112898 | Antipolo ES | PASACAO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2902592.44 |  |  | COMPLETED | 1 |  |  | 050315S00204 | 15FD0068 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-09-14 | 2015-10-02 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY (FORMERLY:
11498 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309731 | Antipolo HS, Minalabac | MINALABAC | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050314S00023 | 14FF0017 | 2014-07-13 | 2014-07-16 | 2014-08-08 | 2014-08-19 | 2014-08-28 | HONEYVILLE CONSTRUCTION
11499 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 173501 | Aslong ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2025606.04 |  |  | COMPLETED | 1 |  |  | 050315S00208 | 15FD0066 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-11-20 | 2015-12-02 | ROLA CONSTRUCTION
11500 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301935 | Bahao HS | LIBMANAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00070 | 15FD0053 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-26 | 2015-09-14 | 3RB CONSTRUCTION & SUPPLY
11501 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301936 | Bahay PHS | LIBMANAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
11502 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112866 | Batang ES | PAMPLONA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050315S00199 | 15FD0071 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-14 | 2015-10-02 | R.D. MANDANAS CONSTRUCTION
11503 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112867 | Burabod ES | PAMPLONA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050315S00139 | 15FD0045 | 2015-07-27 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-09-08 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
11504 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112675 | Candato Elementary School | LIBMANAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0
11505 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309747 | Carmel HS | LIBMANAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00068 | 15FD0060 | 2015-08-02 | 2015-08-03 | 2015-08-18 | 2015-08-25 | 2015-09-15 | 3-L CONSTRUCTION
11506 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112708 | Cawayan ES | LIBMANAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2902592.44 |  |  | COMPLETED | 1 |  |  | 050315S00195 | 15FD0072 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-14 | 2015-10-02 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY (FORMERLY:
11507 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112904 | Compra Elementary School | PASACAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050315S00210 | 15FD0072 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-14 | 2015-10-02 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY (FORMERLY:
11508 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112999 | Cotmo ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 050315S00211 | 15FD0070 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-14 | 2015-10-02 | HGG BUILDERS & SUPPLY
11509 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 113000 | Daculang Tubig ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050315S00207 | 15FD0070 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-14 | 2015-10-02 | HGG BUILDERS & SUPPLY
11510 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301964 | Dalupaon National High School | PASACAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 050315S00109 | 15FD0036 | 2015-07-19 | 2015-07-21 | 2015-08-03 | 2015-08-17 | 2015-09-07 | M.J. APIN BUILDERS
11511 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309718 | Dalupaon NHS - Tinalmud Annex PHS | PASACAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00111 | 15FD0037 | 2015-07-19 | 2015-07-21 | 2015-08-03 | 2015-08-17 | 2015-09-07 | M.J. APIN BUILDERS
11512 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301968 | Don Mariano C. Veneracion HS | PAMPLONA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
11513 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301970 | Don Teofilo H. Dilanco MHS | LIBMANAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 050315S00123 | 15FD0052 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-09-07 | R.K.X. ODIAMAR CONSTRUCTION
11514 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309732 | Dr. Lorenzo P. Ziga MHS | PASACAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00122 | 15FD0036 | 2015-07-19 | 2015-07-21 | 2015-08-03 | 2015-08-17 | 2015-09-07 | M.J. APIN BUILDERS
11515 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309736 | Dr. Nelson A. Mejia HS | LIBMANAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00121 | 15FD0057 | 2015-08-02 | 2015-08-03 | 2015-08-18 | 2015-08-28 | 2015-09-11 | PHIL MANNA CONSTRUCTION & SUPPLY
11516 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309758 | Eduardo V. Agomaa HS | LIBMANAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00120 | 15FD0038 | 2015-07-19 | 2015-07-21 | 2015-08-03 | 2015-08-20 | 2015-09-07 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST
11517 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301973 | Gainza National HS | GAINZA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00119 | 15FD0079 | 2015-10-14 | 2015-10-15
11518 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112798 | Hobo ES | MINALABAC | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 050315S00198 | 15FD0067 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-09-14 | 2015-10-02 | HGG BUILDERS & SUPPLY
11519 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301981 | Hobo HS | MINALABAC | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050315S00118 | 15FD0048 | 2015-07-28 | 2015-07-30 | 2015-08-11 | 2015-08-24 | 2015-09-08 | 3-L CONSTRUCTION
11520 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309702 | Juan F. Trivino MHS (frmerly: Pasacao Sch. of Fisheries) | PASACAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00117 | 15FD0037 | 2015-07-19 | 2015-07-21 | 2015-08-03 | 2015-08-17 | 2015-09-07 | M.J. APIN BUILDERS
11521 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112680 | Labao ES | LIBMANAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050315S00129 | 15FD0046 | 2015-07-28 | 2015-07-30 | 2015-08-11 | 2015-08-17 | 2015-09-09 | AE BELLEZA BUILDERS
11522 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301987 | Lupi National High School | SAN FERNANDO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 050315S00116 | 15FD0056 | 2015-08-02 | 2015-08-03 | 2015-08-18 | 2015-08-25 | 2015-09-07 | HGG BUILDERS & SUPPLY
11523 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112909 | Macad ES | PASACAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 050315S00209 | 15FD0068 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-09-14 | 2015-10-02 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY (FORMERLY:
11524 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112682 | Malansad Nuevo ES | LIBMANAN | 2 | 1 | 8 | 2STY4CL | 2015 K10 BATCH 6 | 12338675.2761 |  |  | COMPLETED | 1 |  |  | 050315S00186 | 15FD0065 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-09-14 | 2015-10-02 | HGG BUILDERS & SUPPLY
11525 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301990 | Malansad Nuevo HS | LIBMANAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00115 | 15FD0033 | 2015-07-16 | 2015-07-16 | 2015-07-30 | 2015-08-24 | 2015-09-07 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST
11526 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112713 | Mambulo Nuevo ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050315S00196 | 15FD0067 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-09-14 | 2015-10-02 | HGG BUILDERS & SUPPLY
11527 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301994 | Mambulo Nuevo High School | LIBMANAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 050315S00114 | 15FD0050 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-09-07 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST
11528 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309711 | Mantalisay HS | LIBMANAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6519337.6381 |  |  | COMPLETED | 1
11529 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112803 | Mataoroc ES | MINALABAC | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050315S00133 | 15FD0044 | 2015-07-27 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-09-08 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
11530 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302032 | Maura N. Sibulo National HS | PAMPLONA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00127 | 15FD0034 | 2015-07-16 | 2015-07-16 | 2015-07-30 | 2015-08-12 | 2015-08-28 | HONEYVILLE CONSTRUCTION
11531 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112782 | Mayaopayawan ES | MILAOR | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050315S00134 | 15FD0044 | 2015-07-27 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-09-08 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
11532 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301999 | Milaor NHS | MILAOR | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 050315S00112 | 15FD0089 | 2015-12-10 | 2015-12-10
11533 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309748 | Milaor NHS - Dalipay Annex HS | MILAOR | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 050315S00094 | 15FD0063 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-08-25 | 2015-09-15 | V.S. CERDON IRON WORKS & CONSTRUCTION
11534 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302000 | Minalabac NHS | MINALABAC | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 050315S00096 | 15FD0051 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-09-09 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
11535 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309745 | Northern Plain HS | LIBMANAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00110 | 15FD0060 | 2015-08-02 | 2015-08-03 | 2015-08-18 | 2015-08-25 | 2015-09-15 | 3-L CONSTRUCTION
11536 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309765 | Pag-Oring Nuevo HS | LIBMANAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6619337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00125 | 15FD0055 | 2015-08-02 | 2015-08-03 | 2015-08-18 | 2015-08-25 | 2015-09-07 | ROLA CONSTRUCTION
11537 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302012 | Pamplona NHS | PAMPLONA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 050315S00108 | 15FD0073 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-14 | 2015-10-02 | GRELIPS CONSTRUCTION & DEVELOPMENT
11538 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302013 | Pamukid National High School | SAN FERNANDO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 050315S00107 | 15FD0049 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-09-07 | HGG BUILDERS & SUPPLY
11539 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309769 | Pasacao Municipal High School | PASACAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00106 | 15FD0035 | 2015-07-16 | 2015-07-16 | 2015-08-28 | 2015-09-07 | 2015-09-28 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY (FORMERLY:
11540 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112691 | Patag ES | LIBMANAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00192 | 15FD0065 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-09-14 | 2015-10-02 | HGG BUILDERS & SUPPLY
11541 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309705 | Pinamasagan NHS | SAN FERNANDO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6569337.6381 |  |  | COMPLETED | 1
11542 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302021 | Ramon B. Felipe Sr. NHS (frmerly: San Vicente HS) | PAMPLONA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00104 | 15FD0062 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-08-25 | 2015-09-15 | GRELIPS CONSTRUCTION & DEVELOPMENT
11543 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301965 | Rolando R. Andaya, Sr. MHS | PASACAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00103 | 15FD0035 | 2015-07-16 | 2015-07-16 | 2015-08-28 | 2015-09-07 | 2015-09-28 | E.P.L. GENERAL CONSTRUCTION AND SUPPLY (FORMERLY:
11544 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302025 | Sagrada Familia High School | MINALABAC | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 050315S00102 | 15FD0061 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-08-25 | 2015-09-15 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST
11545 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302030 | San Antonio NHS | MILAOR | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00101 | 15FD0064 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-25 | 2015-09-14 | V.S. CERDON IRON WORKS & CONSTRUCTION
11546 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302031 | San Fernando NHS | SAN FERNANDO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 050315S00100 | 15FD0049 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-09-07 | HGG BUILDERS & SUPPLY
11547 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302033 | San Isidro NHS | LIBMANAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050315S00099 | 15FD0050 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-09-07 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST
11548 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112788 | San Jose ES | MILAOR | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050315S00131 | 15FD0044 | 2015-07-27 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-09-08 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
11549 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302037 | San Juan National High School | LIBMANAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 050315S00098 | 15FD0059 | 2015-08-02 | 2015-08-03 | 2015-08-18 | 2015-08-25 | 2015-09-15 | 3-L CONSTRUCTION
11550 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309770 | San Pablo Integrated School | LIBMANAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00097 | 15FD0038 | 2015-07-19 | 2015-07-21 | 2015-08-03 | 2015-08-20 | 2015-09-07 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST
11551 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 113012 | Tagpocol ES | SAN FERNANDO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2852592.44 |  |  | COMPLETED | 1 |  |  | 050315S00212 | 15FD0070 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-14 | 2015-10-02 | HGG BUILDERS & SUPPLY
11552 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112722 | Tanag ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050315S00197 | 15FD0066 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-11-20 | 2015-12-01 | ROLA CONSTRUCTION
11553 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112811 | Tariric ES | MINALABAC | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050315S00132 | 15FD0047 | 2015-07-28 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-09-08 | CHA CONSTRUCTION & SUPPLY
11554 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112697 | Tarum ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050315S00193 | 15FD0069 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-09-14 | 2015-10-02 | HRB CONSTRUCTION
11555 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112699 | Uson ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2041106.04 |  |  | COMPLETED | 1 |  |  | 050315S00194 | 15FD0069 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-09-14 | 2015-10-02 | HRB CONSTRUCTION
11556 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302066 | Villamayor HS | MINALABAC | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00124 | 15FD0061 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-08-25 | 2015-09-15 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST
11557 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301962 | Altamarino-Clasio High School (formerly Curry High School) | PILI (Capital) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00040 | 15FE0087 | 2015-07-02 | 2015-07-06 | 2015-07-16 | 2015-07-22 | 2015-08-03 | AE BELLEZA BUILDERS
11558 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301946 | Binanuaanan NHS | PILI (Capital) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050315S00026 | 15FE0086 | 2015-07-02 | 2015-07-06 | 2015-07-16 | 2015-07-22 | 2015-08-03 | HGG BUILDERS & SUPPLY
11559 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309762 | Binanuaanan NHS - Sagurong Annex HS | PILI (Capital) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050315S00029 | 15FE0096 | 2015-07-03 | 2015-07-06 | 2015-07-20 | 2015-07-28 | 2015-08-03 | HGG BUILDERS & SUPPLY
11560 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309749 | Binobong HS | PILI (Capital) | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00035 | 15FE0100 | 2015-07-03 | 2015-07-06 | 2015-07-20 | 2015-07-28 | 2015-08-03 | ROLA CONSTRUCTION
11561 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 173537 | BLISS Community School | PILI (Capital) | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050315S00187 | 15FE0112 | 2015-09-14 | 2015-09-18 | 2015-09-29 | 2015-10-06 | 2015-11-04 | HRB CONSTRUCTION
11562 | NC 2015 | TECHVOC (2015) | Region V | Camarines Sur | 301952 | Calabanga NHS | CALABANGA | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
11563 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301952 | Calabanga NHS | CALABANGA | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1
11564 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302052 | Camaligan National High School | CAMALIGAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1
11565 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112761 | Casuray ES | MAGARAO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050315S00141 | 15FE0105 | 2015-07-03 | 2015-07-06 | 2015-07-20 | 2015-07-28 | 2015-08-03 | PRECIOUS CONSTRUCTION
11566 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309719 | Doña Basilia S. Quilon Memorial High School | PILI (Capital) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
11567 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301957 | Doroteo Federis, Sr. NHS (frmerly: Carangcang HS) | MAGARAO | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00031 | 15FE0101 | 2015-07-03 | 2015-07-06 | 2015-07-20 | 2015-07-28 | 2015-08-03 | PRECIOUS CONSTRUCTION
11568 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112507 | Fundado ES | CANAMAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | REVERTED | 0 |  |  | 050315S00203
11569 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112477 | G. Dumalasa ES | CALABANGA | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 050315S00206 | 15FE0114 | 2015-09-22 | 2015-09-25 | 2015-10-07 | 2015-10-19 | 2015-11-04 | PHIL MANNA CONSTRUCTION & SUPPLY
11570 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112479 | Guillermo B. Azanes ES (Hinaguianan ES) | CALABANGA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050315S00205 | 15FE0111 | 2015-09-14 | 2015-09-18 | 2015-09-29 | 2015-10-06 | 2015-11-04 | JELAY CONSTRUCTION AND SUPPLY
11571 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309704 | Hanawan National HS | OCAMPO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1
11572 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112510 | Iquin ES | CANAMAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050315S00184
11573 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301983 | Jose De Villa NHS | CALABANGA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00028 | 15FE0091 | 2015-07-02 | 2015-07-06 | 2015-07-16 | 2015-07-22 | 2015-08-03 | R.D. MANDANAS CONSTRUCTION
11574 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302034 | Magarao NHS (formerly San Isidro NHS) | MAGARAO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 050315S00018 | 15FE0127 | 2015-10-19 | 2015-10-23 | 2015-11-03 | 2015-11-10 | 2015-12-01 | STEVEN CONSTRUCTION & SUPPLY
11575 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301995 | Mangayawan High School | CANAMAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6489337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00037
11576 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301998 | Medroso-Mendoza NHS | CALABANGA | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00025 | 15FE0102 | 2015-07-03 | 2015-07-06 | 2015-07-20 | 2015-07-28 | 2015-08-03 | HRB CONSTRUCTION
11577 | NC 2015 | TECHVOC (2015) | Region V | Camarines Sur | 302006 | Ocampo NHS | OCAMPO | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
11578 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302006 | Ocampo NHS | OCAMPO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1
11579 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302016 | Pili NHS, Pili | PILI (Capital) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 050314S00245 | 14FE0059 | 2014-11-27 | 2014-12-01 | 2014-12-12 | 2014-12-29 | 2015-01-13 | KCS CONSTRUCTION & SUPPLY
11580 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302017 | Pili NHS, Pili - Gov.Mariano E. Villafuerte Annex HS | PILI (Capital) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050315S00016 | 15FE0088 | 2015-07-02 | 2015-07-06 | 2015-07-16 | 2015-07-22 | 2015-08-03 | HONEYVILLE CONSTRUCTION
11581 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112933 | Pili West CS | PILI (Capital) | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050315S00136 | 15FE0104 | 2015-07-03 | 2015-07-06 | 2015-07-20 | 2015-07-28 | 2015-08-03 | PRECIOUS CONSTRUCTION
11582 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112485 | Pinada ES | CALABANGA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 050315S00200 | 15FE0110 | 2015-09-14 | 2015-09-18 | 2015-09-29 | 2015-10-06 | 2015-11-04 | JELAY CONSTRUCTION AND SUPPLY
11583 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301953 | Quipayo HS | CALABANGA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1
11584 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302022 | Rodriguez NHS | PILI (Capital) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050315S00011 | 15FE0094 | 2015-07-03 | 2015-07-06 | 2015-07-20 | 2015-07-28 | 2015-08-03 | AE BELLEZA BUILDERS
11585 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301954 | Sabang National HS | CALABANGA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 050315S00012
11586 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309716 | San Jose Pili NHS | PILI (Capital) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 050315S00013 | 15FE0084 | 2015-07-02 | 2015-07-06 | 2015-07-16 | 2015-07-22 | 2015-08-03 | HONEYVILLE CONSTRUCTION
11587 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112517 | San Juan Community School | CANAMAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 050315S00201
11588 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302049 | Sta. Cruz HS | CANAMAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 050315S00014 | 15FE0125 | 2015-10-19 | 2015-10-23 | 2015-11-03 | 2015-11-10 | 2015-12-01 | M.J. APIN BUILDERS
11589 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302053 | Sulpicio A. Roco MHS | BOMBON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 050315S00015 | 15FE0099 | 2015-07-03 | 2015-07-06 | 2015-07-20 | 2015-07-28 | 2015-08-03 | AE BELLEZA BUILDERS
11590 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302065 | Union NHS | CALABANGA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1
11591 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112613 | Abucayan Elementary School | GOA | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050315S00135 | 15FF0066 | 2015-08-16 | 2015-08-18 | 2015-09-01 | 2015-09-24 | 2015-10-07 | HRB CONSTRUCTION
11592 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112614 | Aroro ES | GOA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050315S00172 | 15FF0074 | 2015-09-06 | 2015-09-08 | 2015-09-22 | 2015-10-06 | 2015-10-16 | ZKR CONSTRUCTION & SUPPLY
11593 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112590 | Bahi ES | GARCHITORENA | 4 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 050315S00137 | 15FF0077 | 2015-09-13 | 2015-09-15 | 2015-09-29 | 2015-10-12 | 2015-10-19 | JM-COFER CONSTRUCTION AND SUPPLY
11594 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112889 | Cagnipa ES | PRESENTACION (PARUBCAN) | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050315S00130 | 15FF0072 | 2015-09-02 | 2015-09-03 | 2015-09-15 | 2015-09-28 | 2015-10-16 | BUILDWAYS CONSTRUCTION & SUPPLY
11595 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 113118 | Caloco ES | TINAMBAC | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 050315S00173 | 15FF0079 | 2015-09-13 | 2015-09-15 | 2015-09-29 | 2015-10-13 | 2015-10-20 | P.R. HIZO CONSTRUCTION AND SUPPLY
11596 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 173541 | Gignaroy E.S. | TIGAON | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 050315S00174 | 15FF0073 | 2015-09-06 | 2015-09-08 | 2015-09-22 | 2015-10-05 | 2015-10-16 | ZKR CONSTRUCTION & SUPPLY
11597 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112640 | Guibahoy ES | LAGONOY | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050315S00142 | 15FF0065 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-10 | 2015-09-24 | HRB CONSTRUCTION
11598 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112541 | Guinahoan Elementary School | CARAMOAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050315S00183 | 15FF0080 | 2015-09-20 | 2015-09-22 | 2015-10-06 | 2015-10-21 | 2015-10-30 | JM-COFER CONSTRUCTION AND SUPPLY
11599 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112641 | HIMANAG ELEMENTARY SCHOOL | LAGONOY | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050315S00153 | 15FF0065 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-10 | 2015-09-24 | HRB CONSTRUCTION
11600 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112623 | Hiwacloy CS | GOA | 4 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 3 | 4673636.82 |  |  | COMPLETED | 1 |  |  | 050315S00159 | 15FF0066 | 2015-08-16 | 2015-08-18 | 2015-09-01 | 2015-09-24 | 2015-10-07 | HRB CONSTRUCTION
11601 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112546 | Ilawod Elementary School | CARAMOAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050315S00149 | 15FF0072 | 2015-09-02 | 2015-09-03 | 2015-09-15 | 2015-09-28 | 2015-10-16 | BUILDWAYS CONSTRUCTION & SUPPLY
11602 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112625 | Lamon ES | GOA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050315S00166 | 15FF0074 | 2015-09-06 | 2015-09-06 | 2015-09-22 | 2015-10-06 | 2015-10-16 | ZKR CONSTRUCTION & SUPPLY
11603 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 113101 | Libod ES | TIGAON | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050315S00161 | 15FF0073 | 2015-09-06 | 2015-09-08 | 2015-09-22 | 2015-10-05 | 2015-10-16 | ZKR CONSTRUCTION & SUPPLY
11604 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112892 | Liwacsa ES | PRESENTACION (PARUBCAN) | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 050315S00163 | 15FF0075 | 2015-09-06 | 2015-09-08 | 2015-09-22 | 2015-10-06 | 2015-10-16 | HRB CONSTRUCTION
11605 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112983 | Mabca ES. | SAGÑAY | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 050315S00162 | 15FF0096 | 2015-11-30 | 2015-12-04 | 2015-12-15 | 2015-12-29
11606 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112602 | Magsaysay PS | GARCHITORENA | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050315S00156 | 15FF0077 | 2015-09-13 | 2015-09-15 | 2015-09-29 | 2015-10-12 | 2015-10-19 | JM-COFER CONSTRUCTION AND SUPPLY
11607 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112549 | Malabog Elementary School | CARAMOAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050315S00155 | 15FF0072 | 2015-09-02 | 2015-09-03 | 2015-09-15 | 2015-09-28 | 2015-10-16 | BUILDWAYS CONSTRUCTION & SUPPLY
11608 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112550 | Maligaya ES | CARAMOAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 050315S00170 | 15FF0080 | 2015-09-20 | 2015-09-22 | 2015-10-06 | 2015-10-21 | 2015-10-30 | JM-COFER CONSTRUCTION AND SUPPLY
11609 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112662 | Manamoc ES | LAGONOY | 4 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 3 | 4673636.82 |  |  | COMPLETED | 1 |  |  | 050315S00154 | 15FF0065 | 2015-08-12 | 2015-08-13 | 2015-08-27 | 2015-09-10 | 2015-09-24 | HRB CONSTRUCTION
11610 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112603 | Mansangat ES | GARCHITORENA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050315S00152 | 15FF0077 | 2015-09-13 | 2015-09-15 | 2015-09-29 | 2015-10-12 | 2015-10-19 | JM-COFER CONSTRUCTION AND SUPPLY
11611 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 113147 | Olag Grande ES | TINAMBAC | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050315S00151 | 15FF0059 | 2015-08-09 | 2015-08-11 | 2015-08-25 | 2015-09-11 | 2015-09-24 | MAGDA CONSTRUCTION AND SUPPLY
11612 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112562 | Patag-Poloan ES | CARAMOAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 050315S00169 | 15FF0080 | 2015-09-20 | 2015-09-22 | 2015-10-06 | 2015-10-21 | 2015-10-30 | JM-COFER CONSTRUCTION AND SUPPLY
11613 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 173545 | Pawican PS | CARAMOAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 050315S00175 | 15FF0080 | 2015-09-20 | 2015-09-22 | 2015-10-06 | 2015-10-21 | 2015-10-30 | JM-COFER CONSTRUCTION AND SUPPLY
11614 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112606 | San Antonio PS | GARCHITORENA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050315S00168 | 15FF0075 | 2015-09-06 | 2015-09-08 | 2015-09-22 | 2015-10-06 | 2015-10-16 | HRB CONSTRUCTION
11615 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 113129 | San Jose ES | TINAMBAC | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050315S00150 | 15FF0059 | 2015-08-09 | 2015-08-11 | 2015-08-25 | 2015-09-11 | 2015-09-24 | MAGDA CONSTRUCTION AND SUPPLY
11616 | NC 2015 | TECHVOC (2015) | Region V | Camarines Sur | 302038 | San Rafael NHS | TIGAON | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2929549.27 |  |  | COMPLETED | 1
11617 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112635 | Tagongtong ES | GOA | 4 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4523636.82 |  |  | COMPLETED | 1 |  |  | 050315S00165 | 15FF0074 | 2015-09-06 | 2015-09-08 | 2015-09-22 | 2015-10-06 | 2015-10-16 | ZKR CONSTRUCTION & SUPPLY
11618 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112637 | Taytay ES | GOA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050315S00164 | 15FF0074 | 2015-09-06 | 2015-09-08 | 2015-09-22 | 2015-10-06 | 2015-10-16 | ZKR CONSTRUCTION & SUPPLY
11619 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 113110 | Tinawagan ES | TIGAON | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2852592.44 |  |  | COMPLETED | 1 |  |  | 050315S00171 | 15FF0073 | 2015-09-06 | 2015-09-08 | 2015-09-22 | 2015-10-05 | 2015-10-16 | ZKR CONSTRUCTION & SUPPLY
11620 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112574 | Toboan PS | CARAMOAN | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2902592.44 |  |  | COMPLETED | 1 |  |  | 050315S00167 | 15FF0080 | 2015-09-20 | 2015-09-22 | 2015-10-06 | 2015-10-21 | 2015-10-30 | JM-COFER CONSTRUCTION AND SUPPLY
11621 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301926 | Agdangan HS | BAAO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1
11622 | NC 2015 | TECHVOC (2015) | Region V | Camarines Sur | 301931 | Baao National HS | BAAO | 5 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
11623 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301931 | Baao National HS | BAAO | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10442131.51 |  |  | COMPLETED | 1
11624 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301938 | Balaogan National HS | BULA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00019 | 15FG0056 | 2015-09-08 | 2015-09-21 | 2015-09-22 | 2015-09-28 | 2015-10-20 | HRB CONSTRUCTION
11625 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302044 | Bato NHS | BATO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 050315S00020 | 15FG0064 | 2015-09-21 | 2015-09-30 | 2015-10-01 | 2015-10-12 | 2015-10-27 | JURASIC ENTERPRISES
11626 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112364 | Bato North CS | BATO | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00177 | 15FG0080 | 2015-09-28 | 2015-10-09 | 2015-10-12 | 2015-10-19 | 2015-10-29 | NVF CONSTRUCTION
11627 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301947 | Bula NHS | BULA | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8309965.051 |  |  | COMPLETED | 1 |  |  | 050315S00021 | 15FG0062 | 2015-09-17 | 2015-09-29 | 2015-09-30 | 2015-10-15 |  | A.B. OPENA BUILDERS
11628 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112393 | Cabatuan ES | BUHI | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050315S00179 | 15FG0079 | 2015-09-28 | 2015-10-09 | 2015-10-12 | 2015-10-19 | 2015-10-29 | HRB CONSTRUCTION
11629 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301959 | Casugad HS | BULA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6354337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00027 | 15FG0052 | 2015-09-02 | 2015-09-15 | 2015-09-16 | 2015-09-24 | 2015-10-19 | NGS CONSTRUCTION SUPPLY
11630 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301960 | Coguit HS | BALATAN | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8259965.051 |  |  | COMPLETED | 1 |  |  | 050315S00053 | 15FG0068 | 2015-09-21 | 2015-09-30 | 2015-10-01 | 2015-10-12 | 2015-10-21 | P.R. HIZO CONSTRUCTION AND SUPPLY
11631 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301933 | Eusebia Paz Arroyo Mem. NHS | BAAO | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10492131.51 |  |  | COMPLETED | 1 |  |  | 050315S00065 | 15FG0084 | 2015-09-30 | 2015-10-13 | 2015-10-14 | 2015-10-21 | 2015-11-09 | JURASIC ENTERPRISES
11632 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301971 | Fabrica HS | BULA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00064 | 15FG0054 | 2015-09-08 | 2015-09-21 | 2015-09-22 | 2015-09-28 | 2015-10-21 | SPRING STAR CONSTRUCTION & SUPPLY
11633 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309760 | Fabrica HS - La Victoria Annex HS | BULA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6464337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00063 | 15FG0054 | 2015-09-08 | 2015-09-21 | 2015-09-22 | 2015-09-28 | 2015-10-21 | SPRING STAR CONSTRUCTION & SUPPLY
11634 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112834 | Gorong-Gorong ES | NABUA | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 050315S00182 | 15FG0080 | 2015-09-28 | 2015-10-09 | 2015-10-12 | 2015-10-19 | 2015-10-29 | NVF CONSTRUCTION
11635 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301982 | Inoyonan HS | BULA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00062 | 15FG0054 | 2015-09-08 | 2015-09-21 | 2015-09-22 | 2015-09-28 | 2015-10-12 | SPRING STAR CONSTRUCTION & SUPPLY
11636 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112400 | Ipil ES | BUHI | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050315S00180 | 15FG0079 | 2015-09-28 | 2015-10-09 | 2015-10-12 | 2015-10-19 | 2015-10-29 | HRB CONSTRUCTION
11637 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112401 | Iraya ES | BUHI | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
11638 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112401 | Iraya ES | BUHI | 5 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
11639 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112327 | Iyagan ES | BAAO | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050315S00147 | 15FG0043 | 2015-07-23 | 2015-08-06 | 2015-08-07 | 2015-08-12 | 2015-08-20 | JURASSIC CONSTRUCTION & SUPPLIES
11640 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112816 | La Opinion ES | NABUA | 5 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1
11641 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112816 | La Opinion ES | NABUA | 5 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
11642 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301985 | La Purisima HS | NABUA | 5 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 2 | 21383013.45 |  |  | COMPLETED | 1 |  |  | 050315S00061 | 15FG0089 | 2015-10-08 | 2015-10-20 | 2015-10-21 | 2015-10-26 | 2015-11-10 | BRK CONSTRUCTION
11643 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309725 | Laganac HS | BALATAN | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6414337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00060 | 15FG0053 | 2015-09-02 | 2015-09-15 | 2015-09-16 | 2015-09-21 | 2015-09-24 | CHA CONSTRUCTION & SUPPLY
11644 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112404 | Lourdes ES | BUHI | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050315S00185 | 15FG0079 | 2015-09-28 | 2015-10-09 | 2015-10-12 | 2015-10-19 | 2015-10-29 | HRB CONSTRUCTION
11645 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112817 | Lourdes ES | NABUA | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050315S00145 | 15FG0043 | 2015-07-23 | 2015-08-06 | 2015-08-07 | 2015-08-12 | 2015-08-20 | JURASSIC CONSTRUCTION & SUPPLIES
11646 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302002 | Lourdes PHS | NABUA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6354337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00059 | 15FG0051 | 2015-09-02 | 2015-09-15 | 2015-09-16 | 2015-09-24 | 2015-10-26 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
11647 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301991 | Malawag National High School | NABUA | 5 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10897342.5917 |  |  | COMPLETED | 1 |  |  | 050315S00058 | 15FG0071 | 2015-09-22 | 2015-10-02 | 2015-10-05 | 2015-10-13 | 2015-10-28 | HRB CONSTRUCTION
11648 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112375 | Masoli ES | BATO | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050315S00178 | 15FG0080 | 2015-09-28 | 2015-10-09 | 2015-10-12 | 2015-10-19 | 2015-10-29 | NVF CONSTRUCTION
11649 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301997 | Masoli HS | BATO | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6364337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00057 | 15FG0074 | 2015-09-23 | 2015-10-05 | 2015-10-06 | 2015-10-14 | 2015-10-28 | P.R. HIZO CONSTRUCTION AND SUPPLY
11650 | NC 2015 | TECHVOC (2015) | Region V | Camarines Sur | 302001 | Nabua NHS | NABUA | 5 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
11651 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302001 | Nabua NHS | NABUA | 5 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11027342.5917 |  |  | COMPLETED | 1
11652 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301932 | Nonito Paz Arroyo MNHS | BAAO | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00055 | 15FG0055 | 2015-09-08 | 2015-09-21 | 2015-09-22 | 2015-09-28 | 2015-10-26 | JURASIC ENTERPRISES
11653 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302007 | Ombao HS | BULA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6459337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00054 | 15FG0057 | 2015-09-16 | 2015-09-24 | 2015-09-28 | 2015-10-05 | 2015-10-21 | JURASSIC CONSTRUCTION & SUPPLIES
11654 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302010 | Palsong NHS | BULA | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8239965.051 |  |  | COMPLETED | 1
11655 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302014 | Pararao HS | BALATAN | 5 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11007342.5917 |  |  | COMPLETED | 1 |  |  | 050315S00052 | 15FG0069 | 2015-09-22 | 2015-10-02 | 2015-10-05 | 2015-10-12 | 2015-10-21 | P.R. HIZO CONSTRUCTION AND SUPPLY
11656 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112332 | Pugay ES | BAAO | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 050315S00176 | 15FG0079 | 2015-09-28 | 2015-10-09 | 2015-10-12 | 2015-10-19 | 2015-10-29 | HRB CONSTRUCTION
11657 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309759 | Pulang Daga High School | BALATAN | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6384337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00066 | 15FG0059 | 2015-09-16 | 2015-09-25 | 2015-09-28 | 2015-10-05 | 2015-10-21 | P.R. HIZO CONSTRUCTION AND SUPPLY
11658 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302026 | Salvacion HS, Bato | BATO | 5 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11037342.5917 |  |  | COMPLETED | 1 |  |  | 050315S00050 | 15FG0076 | 2015-09-23 | 2015-10-05 | 2015-10-06 | 2015-10-14 | 2015-10-23 | P.R. HIZO CONSTRUCTION AND SUPPLY
11659 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 309746 | Salvacion HS, Bato - Payak Annex HS | BATO | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00049 | 15FG0060 | 2015-09-17 | 2015-09-29 | 2015-09-30 | 2015-10-05 | 2015-10-21 | CHA CONSTRUCTION & SUPPLY
11660 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112451 | San Ramon ES | BULA | 5 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 050315S00144 | 15FG0043 | 2015-07-23 | 2015-08-06 | 2015-08-07 | 2015-08-12 | 2015-08-20 | JURASSIC CONSTRUCTION & SUPPLIES
11661 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302041 | San Ramon HS, Bula | BULA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6354337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00048 | 15FG0058 | 2015-09-16 | 2015-09-24 | 2015-09-28 | 2015-10-05 | 2015-10-21 | P.R. HIZO CONSTRUCTION AND SUPPLY
11662 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302027 | San Roque High School | BATO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8264965.051 |  |  | COMPLETED | 1
11663 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302043 | San Vicente NHS | BUHI | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8349965.051 |  |  | COMPLETED | 1
11664 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112842 | Sogod ES | NABUA | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 050315S00181 | 15FG0080 | 2015-09-28 | 2015-10-09 | 2015-10-12 | 2015-10-19 | 2015-10-29 | NVF CONSTRUCTION
11665 | NC 2015 | K10 (2015) | Region V | Camarines Sur | 112416 | Sta. Cruz ES | BUHI | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050314S00152 | 14FN0017 | 2014-07-08 | 2014-07-09 | 2014-07-22 | 2014-08-13 | 2014-08-26 | PBL BUILDERS & SUPPLY
11666 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302050 | Sta. Justina HS | BUHI | 5 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10927342.5917 |  |  | COMPLETED | 1
11667 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302057 | Tambo NHS | BUHI | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8279965.051 |  |  | COMPLETED | 1 |  |  | 050315S00044 | 15FG0067 | 2015-09-21 | 2015-09-30 | 2015-10-01 | 2015-10-12 | 2015-10-21 | P.R. HIZO CONSTRUCTION AND SUPPLY
11668 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 301992 | Tandaay Provincial HS | NABUA | 5 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10897342.5917 |  |  | COMPLETED | 1 |  |  | 050315S00043 | 15FG0072 | 2015-09-22 | 2015-10-05 | 2015-10-05 | 2015-10-13 | 2015-10-28 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST
11669 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302059 | Tapayas HS | BALATAN | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 050315S00042 | 15FG0086 | 2015-10-02 | 2015-10-15 | 2015-10-16 | 2015-10-22 | 2015-11-09 | MQR CONSTRUCTION AND SUPPLIES
11670 | NC 2015 | SHS (2015) | Region V | Camarines Sur | 302003 | Victor Bernal Provincial High School | NABUA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 050315S00041 | 15FG0061 | 2015-09-17 | 2015-09-29 | 2015-09-30 | 2015-10-05 | 2015-10-27 | A.B. OPENA BUILDERS
11671 | NC 2015 | SHS (2015) | Region V | Catanduanes | 302070 | Agban NHS | BARAS | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6819338 |  |  | COMPLETED | 1
11672 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302071 | Antipolo NHS | VIRAC (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6399337.6381 |  |  | COMPLETED | 1 |  |  | 050415S00040 | 15FH0032 | 2015-08-05 | 2015-08-05 | 2015-08-20 | 2015-11-17 | 2015-11-20 | CHRISMAN CONSTRUCTION AND SUPPLIES
11673 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302072 | Bagamanoc Rural DHS | BAGAMANOC | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 050415S00039 | 15FH0041 | 2015-08-05 | 2015-08-05
11674 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302073 | Baras Rural DHS | BARAS | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 050415S00038 | 15FH0056 | 2015-08-10 | 2015-08-13
11675 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302074 | Bato Rural DHS | BATO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050415S00037 | 15FH0037 | 2015-08-05 | 2015-08-05 | 2015-08-20 | 2015-11-17 | 2015-11-20 | JASMIN CONSTRUCTION
11676 | NC 2015 | K10 (2015) | Region V | Catanduanes | 113167 | Benticayan ES | BARAS | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1948606.04 |  |  | COMPLETED | 1 |  |  | 050415S00048 | PL#29 | 2015-10-08 |  | 2015-10-15 | 2015-10-27 | 2015-11-02 | By Administration
11677 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302075 | Bote IS | BATO | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6459337.6381 |  |  | COMPLETED | 1 |  |  | 050415S00036 | 15FH0038 | 2015-08-05 | 2015-08-05 | 2015-08-20 | 2015-11-17 | 2015-11-20 | MBT CONSTRUCTION
11678 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302076 | Bugao NHS | BAGAMANOC | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 050415S00035 | 15FH0044 | 2015-08-07 | 2015-08-11 | 2015-08-25 | 2015-11-17 | 2015-11-20 | TRI-DOM TRADING & CONSTRUCTION
11679 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302077 | Buyo Integrated School | VIRAC (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8224965.051 |  |  | COMPLETED | 1
11680 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302078 | Cabcab NHS | SAN ANDRES (CALOLBON) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050415S00033 | 15FH0036 | 2015-08-05 | 2015-08-05 | 2015-08-20 | 2015-11-17 | 2015-11-20 | CHRISMAN CONSTRUCTION AND SUPPLIES
11681 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302079 | Cabugao IS | BATO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 050415S00042 | 15FH0039 | 2015-10-28 | 2015-10-29 | 2015-11-17 | 2015-12-01 | 2015-12-04 | CHRISMAN CONSTRUCTION AND SUPPLIES
11682 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302084 | Calatagan High School | VIRAC (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050415S00032 | 15FH0032 | 2015-08-05 | 2015-08-05 | 2015-08-20 | 2015-11-17 | 2015-11-20 | CHRISMAN CONSTRUCTION AND SUPPLIES
11683 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302081 | Caramoran Rural Development High School | CARAMORAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 050415S00031 | 15FH0048 | 2015-08-07 | 2015-08-11
11684 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302082 | Caramoran School of Fisheries | CARAMORAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 050415S00024 | 15FH0047 | 2015-09-09 | 2015-09-10 | 2015-09-24 | 2015-11-17 | 2015-11-20 | JAG-VAIL CONSTRUCTION & SUPPLY
11685 | NC 2015 | K10 (2015) | Region V | Catanduanes | 174009 | Caruyo PS | PANDAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050415S00049 | PL#030 | 2015-10-08 | 2015-10-15 | 2015-10-15 | 2015-10-27 | 2015-11-02 | By Administration
11686 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302083 | Catanduanes NHS | VIRAC (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1
11687 | NC 2015 | TECHVOC (2015) | Region V | Catanduanes | 302083 | Catanduanes NHS | VIRAC (Capital) | 0 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7278647.81 |  |  | COMPLETED | 1
11688 | NC 2015 | K10 (2015) | Region V | Catanduanes | 113300 | Dayawa ES | SAN MIGUEL | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050415S00046 | PL#028 | 2015-10-08 |  | 2015-10-15 | 2015-10-27 | 2015-11-02 | By Administration
11689 | NC 2015 | K10 (2015) | Region V | Catanduanes | 113320 | Del Pilar PS | VIGA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050415S00047 | PL#031 | 2015-10-08 |  | 2015-10-15 | 2015-10-27 | 2015-11-02 | By Administration
11690 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302088 | Gigmoto Rural DHS | GIGMOTO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 050415S00041 | 15FH0045 | 2015-09-09 | 2015-09-10 | 2015-09-24 | 2015-11-17 | 2015-11-20 | ORANI BUILDERS & SUPPLY
11691 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302099 | Mabato NHS (SMRDHS Annex) | SAN MIGUEL | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 050415S00022 | 15FH0042 | 2015-08-07 | 2015-08-11 | 2015-08-25 | 2015-11-17 | 2015-11-20 | SULVIR ENGINEERING AND CONSTRUCTION
11692 | NC 2015 | SHS (2015) | Region V | Catanduanes | 302090 | Magnesia National High School | VIRAC (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6619338 |  |  | REVERTED | 0 |  |  | 050415S00044
11693 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302091 | Manambrag NHS | SAN ANDRES (CALOLBON) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050415S00017 | 15FH0034 | 2015-08-05 | 2015-08-05
11694 | NC 2015 | K10 (2015) | Region V | Catanduanes | 309803 | MILAVIGA INTEGRATED SCHOOL | CARAMORAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1948606 |  |  | COMPLETED | 1 |  |  | 050415S00050
11695 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302093 | Palta NHS | VIRAC (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050415S00018 | 15FH0058 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-11-17 | 2015-11-20 | NQA CONSTRUCTION & SUPPLY
11696 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302094 | Pandan SAT | PANDAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1
11697 | NC 2015 | TECHVOC (2015) | Region V | Catanduanes | 302094 | Pandan SAT | PANDAN | 0 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4879098.54 |  |  | COMPLETED | 1
11698 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 309801 | Panganiban NHS (CAIC Compound) | PANGANIBAN (PAYO) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050415S00020 | 15FH0046 | 2015-08-07 | 2015-08-11 | 2015-08-25 | 2015-11-17 | 2015-11-20 | TRI-DOM TRADING & CONSTRUCTION
11699 | NC 2015 | TECHVOC (2015) | Region V | Catanduanes | 302096 | San Andres Vocational School | SAN ANDRES (CALOLBON) | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
11700 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302096 | San Andres Vocational School | SAN ANDRES (CALOLBON) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1
11701 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302097 | San Jose NHS | VIGA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8394965.051 |  |  | COMPLETED | 1 |  |  | 050415S00028 | 15FH0054 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-11-17 | 2015-11-20 | JASMIN CONSTRUCTION
11702 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302098 | San Miguel Rural DHS | SAN MIGUEL | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 050415S00023 | 15FH0049 | 2015-08-07 | 2015-08-11 | 2015-08-25 | 2015-11-17 | 2015-11-20 | VIRAC NRC CONSTRUCTION
11703 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302101 | Sicmil IS | GIGMOTO | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 050415S00016 | 15FH0043 | 2015-08-07 | 2015-08-11 | 2015-08-25 | 2015-11-17 | 2015-11-20 | JR CONTRACTOR
11704 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302102 | Supang-Datag NHS | CARAMORAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050415S00025 | 15FH0053 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-11-17 | 2015-11-20 | FDS Construction & Supply
11705 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302103 | Tabugoc NHS | PANDAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 050415S00026 | 15FH0057 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-11-17 | 2015-11-20 | FDS Construction & Supply
11706 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302104 | Tambognon NHS | VIGA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050415S00027 | 15FH0040 | 2015-09-09 | 2015-09-10 | 2015-09-24 | 2015-11-17 | 2015-11-20 | ORANI BUILDERS & SUPPLY
11707 | NC 2015 | SHS (2015) | Region V | CATANDUANES | 302106 | Tubli NHS | CARAMORAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050415S00029 | 15FH0050 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-11-17 | 2015-11-20 | FDS Construction & Supply
11708 | NC 2015 | SHS (2015) | Region V | Catanduanes | 302107 | Viga Rural DHS | VIGA | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | COMPLETED | 1 |  |  | 050415S00043
11709 | NC 2015 | SHS (2015) | Region V | Iriga City | 302249 | Perpetual Help NHS | IRIGA CITY | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10502131.51 |  |  | COMPLETED | 1 |  |  | 050315S00045 | 15FG0085 | 2015-10-02 | 2015-10-15 | 2015-10-16 | 2015-10-22 | 2015-11-09 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
11710 | NC 2015 | SHS (2015) | Region V | Iriga City |  | SHS within San Agustin ES | IRIGA CITY | 5 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  | 050315S00160 | 15FG0091 | 2015-11-03 | 2015-11-13 | 2015-11-16 | 2015-11-24 |  | IRIGA JETSTONE CONSTRUCTION
11711 | NC 2015 | K10 (2015) | Region V | Legaspi City | 114457 | Albay CS | LEGAZPI CITY (Capital) | 2 | 1 | 32 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1
11712 | NC 2015 | K10 (2015) | Region V | Legaspi City | 114457 | Albay CS | LEGAZPI CITY (Capital) | 2 |  |  | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | COMPLETED | 1
11713 | NC 2015 | K10 (2015) | Region V | Legaspi City | 114467 | Banquerohan ES | LEGAZPI CITY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 050115S00048 | 15FB0080 | 2015-08-31 | 2015-08-28 | 2015-09-18 | 2015-09-24 | 2015-10-05 | ZKR CONSTRUCTION & SUPPLY
11714 | NC 2015 | K10 (2015) | Region V | Legaspi City | 114475 | Bitano ES | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 050115S00030 | 15FB0088 | 2015-10-06 | 2015-10-03 | 2015-10-14 | 2015-10-23 | 2015-11-03 | STEVEN CONSTRUCTION & SUPPLY
11715 | NC 2015 | K10 (2015) | Region V | Legaspi City | 114481 | Legazpi Port Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 15 | 3STY15CL | 2015 K10 BATCH 3 | 21383013.45 |  |  | COMPLETED | 1 |  |  | 050115S00037 | 15FB0089 | 2015-10-06 | 2015-10-02 | 2015-10-14 | 2015-10-29 | 2015-11-09 | ALXM CONSTRUCTION
11716 | NC 2015 | TECHVOC (2015) | Region V | Legaspi City | 302258 | Oro Site High School | LEGAZPI CITY (Capital) | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4939098.54 |  |  | REVERTED | 0
11717 | NC 2015 | TECHVOC (2015) | Region V | Legaspi City | 302261 | Pag-asa NHS | LEGAZPI CITY (Capital) | 2 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7278647.81 |  |  | REVERTED | 0
11718 | NC 2015 | K10 (2015) | Region V | Ligao City | 301807 | Amtic HS | CITY OF LIGAO | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 7 | 3717969 |  |  | COMPLETED | 1 |  |  | 050115S00062 | 15FO0060 | 2015-10-22 | 2015-10-23 | 2015-11-04 | 2015-11-23 | 2015-12-28
11719 | NC 2015 | K10 (2015) | Region V | Ligao City | 301811 | Barayong NHS | CITY OF LIGAO | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8264965 |  |  | COMPLETED | 1 |  |  | 050115S00063
11720 | NC 2015 | SHS (2015) | Region V | Ligao City |  | Ligao City National Technical Vocational High School | CITY OF LIGAO | 3 | 1 | 16 | 2STY8CL | 2015 SHS BATCH 5 | 22354685 |  |  | COMPLETED | 1 |  |  | 050115S00042 | 15FO0057 | 2015-09-29 | 2015-09-30 | 2015-10-22 | 2015-11-06 | 2015-12-11 | PRECIOUS CONSTRUCTION
11721 | NC 2015 | K10 (2015) | Region V | Ligao City | 231002 | Macalidong ES | CITY OF LIGAO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050115S00049 | 15FO0059 | 2015-10-22 | 2015-10-23 | 2015-11-04 | 2015-11-19 | 2015-12-21 | WIND RIVER COURT CONSTRUCTION AND DEVELOPMENT
11722 | NC 2015 | K10 (2015) | Region V | Ligao City | 231004 | Nabonton ES, Buga Ext. | CITY OF LIGAO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 050115S00050 | 15FO0059 | 2015-10-22 | 2015-10-23 | 2015-11-04 | 2015-11-19 | 2015-12-21 | WIND RIVER COURT CONSTRUCTION AND DEVELOPMENT
11723 | NC 2015 | K10 (2015) | Region V | Ligao City | 301859 | Palapas NHS | CITY OF LIGAO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1988606 |  |  | COMPLETED | 1 |  |  | 050115S00064 | 15FO0060 | 2015-10-22 | 2015-10-23 | 2015-11-04 | 2015-11-23 | 2015-12-28
11724 | NC 2015 | TECHVOC (2015) | Region V | Ligao City | 301862 | Paulba NHS | CITY OF LIGAO | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4989098.54 |  |  | COMPLETED | 1
11725 | NC 2015 | K10 (2015) | Region V | Masbate | 113904 | Abner Buro ES | SAN PASCUAL | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6209337.6381 |  |  | REVERTED | 0 |  |  | 050515S00119
11726 | NC 2015 | K10 (2015) | Region V | Masbate | 113905 | Acacia Elementary School | SAN PASCUAL | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050515S00062 | 15FM0020 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-09-25 | 2015-10-09 | ALXM CONSTRUCTION
11727 | NC 2015 | SHS (2015) | Region V | Masbate | 302108 | Adelina P. Laurio Mem. HS | SAN PASCUAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 050515S00048
11728 | NC 2015 | K10 (2015) | Region V | Masbate | 309936 | Amado P. Lazaro High School | SAN PASCUAL | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1
11729 | NC 2015 | SHS (2015) | Region V | Masbate | 309936 | Amado P. Lazaro High School | SAN PASCUAL | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6559338 |  |  | REVERTED | 0
11730 | NC 2015 | SHS (2015) | Region V | Masbate | 302109 | Andres Clemente Jr.National HS | SAN FERNANDO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 050515S00047 | 15FM0012
11731 | NC 2015 | K10 (2015) | Region V | Masbate | 113883 | Anita P. Altarejos PS | SAN JACINTO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050515S00073 | 15FM0019 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-09-25 | 2015-10-09 | MUNTOPAR BUILDERS
11732 | NC 2015 | SHS (2015) | Region V | Masbate | 302113 | Bagahanglad NHS | SAN JACINTO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8434965 |  |  | COMPLETED | 1 |  |  | 050515S00093
11733 | NC 2015 | K10 (2015) | Region V | Masbate | 113907 | Bayanihan ES | SAN PASCUAL | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2842592.44 |  |  | COMPLETED | 1 |  |  | 050515S00115 | 15FM0026 | 2015-10-29 | 2015-10-29
11734 | NC 2015 | K10 (2015) | Region V | Masbate | 309943 | Buenavista IS | SAN FERNANDO | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050515S00074 | 15FM0019 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-09-25 | 2015-10-09 | MUNTOPAR BUILDERS
11735 | NC 2015 | SHS (2015) | Region V | Masbate | 302124 | Burgos National High School | BATUAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 050515S00046 | 15FM0014 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-09-25 | 2015-10-09 | STEVEN CONSTRUCTION & SUPPLY
11736 | NC 2015 | SHS (2015) | Region V | Masbate | 302127 | Buyo NHS | SAN FERNANDO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8429965 |  |  | COMPLETED | 1 |  |  | 050515S00087
11737 | NC 2015 | K10 (2015) | Region V | Masbate | 113864 | Cabug ES | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00128 | 15FM0024 | 2015-10-29 | 2015-10-29
11738 | NC 2015 | SHS (2015) | Region V | Masbate | 302130 | Cawayan National High School | CLAVERIA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | REVERTED | 0 |  |  | 050515S00045
11739 | NC 2015 | SHS (2015) | Region V | Masbate | 309923 | Cogon High School | MONREAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8344965.051 |  |  | COMPLETED | 1 |  |  | 050515S00044 | 15FM0016 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-10-01 | 2015-10-08 | ALXM CONSTRUCTION
11740 | NC 2015 | SHS (2015) | Region V | Masbate | 309918 | Costa Rica Integrated School | BATUAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8354965.051 |  |  | REVERTED | 0 |  |  | 050515S00043
11741 | NC 2015 | K10 (2015) | Region V | Masbate | 174509 | Curvada ES | CLAVERIA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1978606.04 |  |  | COMPLETED | 1 |  |  | 050515S00121 | 15FM0025 | 2015-10-29 | 2015-10-29
11742 | NC 2015 | SHS (2015) | Region V | Masbate | 302114 | Don Benito Maristela Mem. HS | MONREAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8334965.051 |  |  | REVERTED | 0 |  |  | 050515S00042
11743 | NC 2015 | SHS (2015) | Region V | Masbate | 309928 | EMILIO LEE LLACER SR. HIGH SCHOOL | SAN JACINTO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2033606 |  |  | COMPLETED | 1
11744 | NC 2015 | SHS (2015) | Region V | Masbate | 302134 | F. Alindogan National High School | BATUAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 050515S00041 | 15FM0014 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-09-25 | 2015-10-09 | STEVEN CONSTRUCTION & SUPPLY
11745 | NC 2015 | SHS (2015) | Region V | Masbate | 302135 | F. del Rosario MHS | CLAVERIA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6529338 |  |  | COMPLETED | 1 |  |  | 050515S00094
11746 | NC 2015 | K10 (2015) | Region V | Masbate | 113916 | Gemino Elementary School | SAN PASCUAL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1978606.04 |  |  | COMPLETED | 1 |  |  | 050515S00120 | 15FM0026 | 2015-10-29 | 2015-10-29
11747 | NC 2015 | SHS (2015) | Region V | Masbate | 309930 | Gerardo C. Cardiño Sr. HS | MONREAL | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6469337.6381 |  |  | COMPLETED | 1
11748 | NC 2015 | SHS (2015) | Region V | Masbate | 302137 | Halabangbaybay NHS | SAN PASCUAL | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6399337.6381 |  |  | COMPLETED | 1 |  |  | 050515S00040
11749 | NC 2015 | SHS (2015) | Region V | Masbate | 309912 | Iniwaran Integrated School | SAN PASCUAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | REVERTED | 0 |  |  | 050515S00053
11750 | NC 2015 | SHS (2015) | Region V | Masbate | 302138 | Ipil NHS | SAN FERNANDO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 050515S00038 | 15FM0015 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-09-25 | 2015-10-09 | MUNTOPAR BUILDERS
11751 | NC 2015 | K10 (2015) | Region V | Masbate | 309938 | Labangco High School | SAN PASCUAL | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
11752 | NC 2015 | SHS (2015) | Region V | Masbate | 309938 | Labangco High School | SAN PASCUAL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2038606 |  |  | COMPLETED | 1
11753 | NC 2015 | K10 (2015) | Region V | Masbate | 113580 | Mababangbaybay ES | CLAVERIA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1978606.04 |  |  | COMPLETED | 1 |  |  | 050515S00118 | 15FM0025 | 2015-10-29 | 2015-10-29
11754 | NC 2015 | SHS (2015) | Region V | Masbate | 309935 | Mababangbaybay NHS | CLAVERIA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6399337.6381 |  |  | COMPLETED | 1 |  |  | 050515S00037
11755 | NC 2015 | SHS (2015) | Region V | Masbate | 309913 | Malaking Ilog NHS | SAN PASCUAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 050515S00036 | 15FM0018 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-10-01 | 2015-10-08 | ALXM CONSTRUCTION
11756 | NC 2015 | SHS (2015) | Region V | Masbate | 302152 | Monreal NHS | MONREAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | REVERTED | 0 |  |  | 050515S00035
11757 | NC 2015 | SHS (2015) | Region V | Masbate | 309905 | Osmena NHS | CLAVERIA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 050515S00034
11758 | NC 2015 | SHS (2015) | Region V | Masbate | 302155 | Palanas High School | SAN PASCUAL | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6559338 |  |  | COMPLETED | 1 |  |  | 050515S00095
11759 | NC 2015 | SHS (2015) | Region V | Masbate | 302159 | Pinamandayan Integrated School | SAN PASCUAL | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6399337.6381 |  |  | REVERTED | 0 |  |  | 050515S00033
11760 | NC 2015 | SHS (2015) | Region V | Masbate | 302163 | Quezon NHS | CLAVERIA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6529338 |  |  | COMPLETED | 1 |  |  | 050515S00096
11761 | NC 2015 | SHS (2015) | Region V | Masbate | 302166 | San Isidro NHS | CLAVERIA | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3767969 |  |  | COMPLETED | 1
11762 | NC 2015 | SHS (2015) | Region V | Masbate | 302167 | San Jacinto NHS | SAN JACINTO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 050515S00032 | 15FM0016 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-10-01 | 2015-10-08 | ALXM CONSTRUCTION
11763 | NC 2015 | SHS (2015) | Region V | Masbate | 302168 | San Pascual NHS | SAN PASCUAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 050515S00031
11764 | NC 2015 | SHS (2015) | Region V | Masbate | 302169 | San Pedro NHS | SAN PASCUAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | REVERTED | 0 |  |  | 050515S00030
11765 | NC 2015 | K10 (2015) | Region V | Masbate | 113937 | Sulficio Elliot ES | SAN PASCUAL | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050515S00064 | 15FM0020 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-09-25 | 2015-10-09 | ALXM CONSTRUCTION
11766 | NC 2015 | SHS (2015) | Region V | Masbate | 302173 | Tiburcio A. Berdida, Sr. NHS | CLAVERIA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 050515S00029 | 15FM0012
11767 | NC 2015 | SHS (2015) | Region V | Masbate | 302126 | Tito R. Espinosa Mem. Nat'l Agric'l. HS | CLAVERIA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050515S00003 | 15FM0017 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-10-01 | 2015-10-08 | ALXM CONSTRUCTION
11768 | NC 2015 | K10 (2015) | Region V | Masbate | 309937 | Vicente D. Alburo High School | SAN PASCUAL | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1
11769 | NC 2015 | SHS (2015) | Region V | Masbate | 309937 | Vicente D. Alburo High School | SAN PASUCAL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2038606 |  |  | COMPLETED | 1
11770 | NC 2015 | K10 (2015) | Region V | Masbate | 113903 | Washington ES | SAN JACINTO | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | REVERTED | 0 |  |  | 050515S00069
11771 | NC 2015 | SHS (2015) | Region V | Masbate | 309931 | Amador Bello HS | BALENO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1988606 |  |  | COMPLETED | 1
11772 | NC 2015 | K10 (2015) | Region V | Masbate | 113375 | Balawing Elem. School | AROROY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00122 | 15FI0051 | 2015-08-22 | 2015-08-20 | 2015-09-03 | 2015-09-18 | 2015-10-02 | SHA SHA LUMBER & CONSTRUCTION
11773 | NC 2015 | K10 (2015) | Region V | Masbate | 113378 | Bienvenido R. Bulalacao MES | AROROY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00127 | 15FI0044 | 2015-08-22 | 2015-08-20 | 2015-09-03 | 2015-09-18 | 2015-10-02 | SHA SHA LUMBER & CONSTRUCTION
11774 | NC 2015 | SHS (2015) | Region V | Masbate | 302122 | Bugtong NHS | MANDAON | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6484338 |  |  | COMPLETED | 1 |  |  | 050515S00085 | 15FI0117
11775 | NC 2015 | K10 (2015) | Region V | Masbate | 113689 | Capaclan PS | MILAGROS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00116 | 15FI0049 | 2015-08-22 | 2015-08-20 | 2015-09-03 | 2015-09-18 | 2015-10-02 | GACT ENTERPRISES
11776 | NC 2015 | K10 (2015) | Region V | Masbate | 309941 | Cristeta Bagano MHS | MOBO | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1
11777 | NC 2015 | SHS (2015) | Region V | Masbate | 309941 | Cristeta Bagano MHS | MOBO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2837592 |  |  | COMPLETED | 1
11778 | NC 2015 | K10 (2015) | Region V | Masbate | 113645 | Dayao ES | MANDAON | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00125 | 15FI0053 | 2015-08-22 | 2015-08-20 | 2015-09-03 | 2015-09-18 | 2015-10-02 | SHA SHA LUMBER & CONSTRUCTION
11779 | NC 2015 | K10 (2015) | Region V | Masbate | 113446 | Enrique A. Bayola, Sr. Mem. ES | BALUD | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00126 | 15FI0054 | 2015-08-22 | 2015-08-20 | 2015-09-03 | 2015-09-18 | 2015-10-02 | SHA SHA LUMBER & CONSTRUCTION
11780 | NC 2015 | K10 (2015) | Region V | Masbate | 113749 | Fabian R. De Mesa Elementary School | MOBO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050515S00067 | 15FI0036 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-17 | 2015-10-01 | SHA SHA LUMBER & CONSTRUCTION
11781 | NC 2015 | SHS (2015) | Region V | Masbate | 309922 | Floro L. Medina MHS | MOBO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1986606 |  |  | COMPLETED | 1 |  |  | 050515S00082 | 15FI0056 | 2015-10-19 | 2015-10-30 | 2015-10-31 |  |  | SHA SHA LUMBER & CONSTRUCTION
11782 | NC 2015 | SHS (2015) | Region V | Masbate | 309915 | Francisca Conag Lavisto MHS | AROROY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1998606 |  |  | COMPLETED | 1 |  |  | 050515S00083 | 15FI0058 | 2015-10-19 | 2015-10-31 | 2015-10-31 |  |  | SHA SHA LUMBER & CONSTRUCTION
11783 | NC 2015 | K10 (2015) | Region V | Masbate | 113707 | Francisco D. Lareta ES | MILAGROS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050515S00066 | 15FI0031 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-17 | 2015-10-01 | SHA SHA LUMBER & CONSTRUCTION
11784 | NC 2015 | K10 (2015) | Region V | Masbate | 113431 | Gabi ES | BALENO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00123 | 15FI0043 | 2015-08-22 | 2015-08-20 | 2015-09-03 | 2015-09-18 | 2015-10-02 | SHALJOMAR CONSTRUCTION & SUPPLY
11785 | NC 2015 | K10 (2015) | Region V | Masbate | 113742 | Holjogon ES | MOBO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00103 | 15FI0046 | 2015-08-22 | 2015-08-20 | 2015-09-03 | 2015-09-18 | 2015-10-02 | SHA SHA LUMBER & CONSTRUCTION
11786 | NC 2015 | K10 (2015) | Region V | Masbate | 113454 | Ilaya ES | BALUD | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050515S00065 | 15FI0035 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-17 | 2015-10-01 | SHA SHA LUMBER & CONSTRUCTION
11787 | NC 2015 | K10 (2015) | Region V | Masbate | 113455 | Jangan Elementary School | BALUD | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050515S00061 | 15FI0034 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-17 | 2015-10-01 | SHA SHA LUMBER & CONSTRUCTION
11788 | NC 2015 | K10 (2015) | Region V | Masbate | 174521 | JOSE ANINANG PS | MILAGROS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00105 | 15FI0047 | 2015-08-22 | 2015-08-20 | 2015-09-03 | 2015-09-18 | 2015-10-02 | GACT ENTERPRISES
11789 | NC 2015 | K10 (2015) | Region V | Masbate | 113435 | Lipata ES | BALENO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00124 | 15FI0052 | 2015-08-22 | 2015-08-20 | 2015-09-03 | 2015-09-18 | 2015-10-02 | SHALJOMAR CONSTRUCTION & SUPPLY
11790 | NC 2015 | K10 (2015) | Region V | Masbate | 174504 | Lomocloc ES | AROROY | 2 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3897212.08 |  |  | COMPLETED | 1 |  |  | 050515S00104 | 15FI0045 | 2015-08-22 | 2015-08-20 | 2015-09-03 | 2015-09-18 | 2015-10-02 | SHA SHA LUMBER & CONSTRUCTION
11791 | NC 2015 | K10 (2015) | Region V | Masbate | 113725 | Luacan ES | MILAGROS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2822592.44 |  |  | COMPLETED | 1 |  |  | 050515S00101 | 15FI0040 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-18 | 2015-10-01 | GACT ENTERPRISES
11792 | NC 2015 | K10 (2015) | Region V | Masbate | 113408 | Mariposa ES | AROROY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050515S00054 | 15FI0033 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-17 | 2015-10-01 | SHA SHA LUMBER & CONSTRUCTION
11793 | NC 2015 | SHS (2015) | Region V | Masbate | 309908 | Mary Perpetua E. Brioso MHS | MILAGROS | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6499338 |  |  | COMPLETED | 1
11794 | NC 2015 | SHS (2015) | Region V | Masbate | 309932 | Nabongsoran High School | AROROY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6451338 |  |  | COMPLETED | 1
11795 | NC 2015 | K10 (2015) | Region V | Masbate | 113461 | Palani PS | BALUD | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 050515S00055 | 15FI0037 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-17 | 2015-10-01 | SHA SHA LUMBER & CONSTRUCTION
11796 | NC 2015 | K10 (2015) | Region V | Masbate | 113462 | Panguiranan ES | BALUD | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00129 | 15FI0048 | 2015-08-22 | 2015-08-20 | 2015-09-03 | 2015-09-18 | 2015-10-02 | SHA SHA LUMBER & CONSTRUCTION
11797 | NC 2015 | K10 (2015) | Region V | Masbate | 113466 | Sampad ES | BALUD | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050515S00057 | 15FI0030 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-17 | 2015-10-01 | SHA SHA LUMBER & CONSTRUCTION
11798 | NC 2015 | K10 (2015) | Region V | Masbate | 113709 | San Vicente ES | MILAGROS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00112 | 15FI0050 | 2015-08-22 | 2015-08-20 | 2015-09-03 | 2015-09-18 | 2015-10-02 | GACT ENTERPRISES
11799 | NC 2015 | K10 (2015) | Region V | Masbate | 113441 | Sog-ong ES | BALENO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050515S00058 | 15FI0032 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-17 | 2015-10-01 | SHALJOMAR CONSTRUCTION & SUPPLY
11800 | NC 2015 | K10 (2015) | Region V | Masbate | 309944 | Taisan HS | MILAGROS | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 050515S00056 | 15FI0099 | 2015-10-31
11801 | NC 2015 | K10 (2015) | Region V | Masbate | 113713 | Tigbao Elementary School | MILAGROS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00102 | 15FI0041 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-18 | 2015-10-01 | GACT ENTERPRISES
11802 | NC 2015 | K10 (2015) | Region V | Masbate | 309940 | Tumalaytay High School | MANDAON | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1
11803 | NC 2015 | SHS (2015) | Region V | Masbate | 309940 | Tumalaytay High School | MANDAON | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1968606 |  |  | COMPLETED | 1
11804 | NC 2015 | SHS (2015) | Region V | Masbate | 309902 | Allanaraiz-Marfil National High School | ESPERANZA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1
11805 | NC 2015 | SHS (2015) | Region V | Masbate | 309903 | Arriesgado-Sevilleno High School | PLACER | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 050515S00051 | 15FJ0056 | 2015-11-10 | 2015-11-24 | 2015-12-07 | 2015-12-14 | 2015-12-22 | C.L. CARANDANG ENTERPRISES
11806 | NC 2015 | SHS (2015) | Region V | Masbate | 302112 | Badiang National High School | CATAINGAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 050515S00052 | 15FJ0039 | 2015-10-12 | 2015-10-14 | 2015-10-27 | 2015-11-02 | 2015-11-19 | C.L. CARANDANG ENTERPRISES
11807 | NC 2015 | K10 (2015) | Region V | Masbate | 113961 | Bonifacio ES | USON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00111 | 15FJ0032 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-08 | 2015-10-19 | C.L. CARANDANG ENTERPRISES
11808 | NC 2015 | SHS (2015) | Region V | Masbate | 309927 | Buenasuerte Integrated School | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1
11809 | NC 2015 | SHS (2015) | Region V | Masbate | 302121 | Buenavista National High School | USON | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | COMPLETED | 1
11810 | NC 2015 | K10 (2015) | Region V | Masbate | 302121 | Buenavista National High School | USON | 3 | 1 | 1 | Completion of 2 units 1STY2CL & Completion of 1STY3CL | 2015 COMPLETION BATCH 4 | 184008.96 |  |  | COMPLETED | 1
11811 | NC 2015 | SHS (2015) | Region V | Masbate | 302123 | Buracan National High School | DIMASALANG | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1
11812 | NC 2015 | K10 (2015) | Region V | Masbate | 113530 | Cabungahan ES | CAWAYAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00113 | 15FJ0031 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-07 | 2015-09-16 | C.L. CARANDANG ENTERPRISES
11813 | NC 2015 | SHS (2015) | Region V | Masbate | 302129 | Cataingan National High School | CATAINGAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8274965.051 |  |  | COMPLETED | 1
11814 | NC 2015 | K10 (2015) | Region V | Masbate | 113535 | Cobre ES | CAWAYAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00106 | 15FJ0034 | 2015-09-25 | 2015-09-28 | 2015-10-13 | 2015-10-19 | 2015-10-28 | C.L. CARANDANG ENTERPRISES
11815 | NC 2015 | SHS (2015) | Region V | Masbate | 309920 | Conrada Tero Kho Memorial High School | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 050515S00005 | 15FJ0057 | 2015-11-10 | 2015-11-24 | 2015-12-07 | 2015-12-14 | 2015-12-22 | GACT ENTERPRISES
11816 | NC 2015 | SHS (2015) | Region V | Masbate | 309933 | Dalipe High School | CAWAYAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6399337.6381 |  |  | COMPLETED | 1 |  |  | 050515S00006 | 15FJ0058 | 2015-11-10 | 2015-11-24 | 2015-12-07 | 2015-12-14 | 2015-12-22 | C.L. CARANDANG ENTERPRISES
11817 | NC 2015 | SHS (2015) | Region V | Masbate | 302131 | Del Carmen National High School | USON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8284965.051 |  |  | COMPLETED | 1
11818 | NC 2015 | SHS (2015) | Region V | Masbate | 302132 | Dimasalang National High School | DIMASALANG | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8254965.051 |  |  | COMPLETED | 1
11819 | NC 2015 | SHS (2015) | Region V | Masbate | 309921 | Feliciano Samonte NHS | CATAINGAN | 3 | 1 | 12 | 2STY6CL | 2015 SHS BATCH 5 | 16639930 |  |  | COMPLETED | 1 |  |  | 050515S00088 | 15FJ0073 | 2015-12-17 | 2015-12-17 | 2015-12-29
11820 | NC 2015 | K10 (2015) | Region V | Masbate | 113965 | Felix S. Merioles ES | USON | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050515S00060 | 15FJ0025 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-09-07 | 2015-09-16 | C.L. CARANDANG ENTERPRISES
11821 | NC 2015 | SHS (2015) | Region V | Masbate | 302118 | G. Bangalisan National High School | PLACER | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1
11822 | NC 2015 | K10 (2015) | Region V | Masbate | 113539 | Gilotongan ES | CAWAYAN | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8084965.051 |  |  | COMPLETED | 1 |  |  | 050515S00117 | 15FJ0072 | 2015-12-14 | 2015-12-17 | 2015-12-29 |  |  |  | terminated
11823 | NC 2015 | K10 (2015) | Region V | Masbate | 113609 | Gregorio Alino ES | DIMASALANG | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00109 | 15FJ0033 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-08 | 2015-10-19 | C.L. CARANDANG ENTERPRISES
11824 | NC 2015 | SHS (2015) | Region V | Masbate | 302142 | Liong National High School | CATAINGAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1
11825 | NC 2015 | K10 (2015) | Region V | Masbate | 113548 | Mahayahay ES | CAWAYAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00107 | 15FJ0030 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-07 | 2015-09-16 | C.L. CARANDANG ENTERPRISES
11826 | NC 2015 | SHS (2015) | Region V | Masbate | 309924 | Malbug National High School | CAWAYAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 050515S00011 | 15FJ0080 | 2015-12-31
11827 | NC 2015 | SHS (2015) | Region V | Masbate | 309926 | MARAVILLA HS | PALANAS | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6359338 |  |  | COMPLETED | 1
11828 | NC 2015 | SHS (2015) | Region V | Masbate | 302128 | Marcelo A. Anonuevo Memorial High School | CATAINGAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8284965.051 |  |  | COMPLETED | 1 | [10 empty] | Suspended, For Termination
11829 | NC 2015 | SHS (2015) | Region V | Masbate | 302136 | Matagangtang National High School | PLACER | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1
11830 | NC 2015 | SHS (2015) | Region V | Masbate | 309914 | Mayor Tomas V. Rivera Memorial High School | CAWAYAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8324965.051 |  |  | COMPLETED | 1
11831 | NC 2015 | SHS (2015) | Region V | Masbate | 309911 | Miabas National High School | PALANAS | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6409337.6381 |  |  | COMPLETED | 1
11832 | NC 2015 | SHS (2015) | Region V | Masbate | 302154 | Naro National High School | CAWAYAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1
11833 | NC 2015 | SHS (2015) | Region V | Masbate | 309904 | Palanas National Agriculture High School | PALANAS | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 050515S00019 | 15FJ0063 | 2015-11-25 | 2015-11-26 | 2015-12-08 | 2015-12-14 | 2015-12-22
11834 | NC 2015 | SHS (2015) | Region V | Masbate | 302158 | Pawican National High School | CATAINGAN | 3 | 1 | 12 | 2STY4CL | 2015 SHS BATCH 5 | 19118013 |  |  | COMPLETED | 1 |  |  | 050515S00089 | 15FJ0065 | 2015-11-25 | 2015-11-26 | 2015-12-08 | 2015-12-14 | 2015-12-22 | YAKAL CONSTRUCTION
11835 | NC 2015 | K10 (2015) | Region V | Masbate | 113556 | Pulot ES | CAWAYAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00108 | 15FJ0029 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-07 | 2015-09-16 | C.L. CARANDANG ENTERPRISES
11836 | NC 2015 | SHS (2015) | Region V | Masbate | 302165 | Rodolfo Z. Titong National High School | PLACER | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | COMPLETED | 1
11837 | NC 2015 | SHS (2015) | Region V | Masbate | 302153 | Rondina-Atendido National High School | PALANAS | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 050515S00021 | 15FJ0037 | 2015-10-12 | 2015-10-14 | 2015-10-27 | 2015-11-02 | 2015-11-19 | C.L. CARANDANG ENTERPRISES
11838 | NC 2015 | SHS (2015) | Region V | Masbate | 309929 | Salvacion National High School | PALANAS | 3 | 1 | 12 | 2STY4CL | 2015 SHS BATCH 5 | 19013013 |  |  | COMPLETED | 1
11839 | NC 2015 | K10 (2015) | Region V | Masbate | 113854 | San Pero ES | PLACER | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 050515S00114 | 15FJ0035 | 2015-09-25 | 2015-09-28 | 2015-10-13 | 2015-10-19 | 2015-10-28 | C.L. CARANDANG ENTERPRISES
11840 | NC 2015 | SHS (2015) | Region V | Masbate | 302170 | San Ramon National High School | USON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8344965.051 |  |  | COMPLETED | 1
11841 | NC 2015 | SHS (2015) | Region V | Masbate | 302171 | Santos E. Conag National High School | ESPERANZA | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2932592 |  |  | COMPLETED | 1
11842 | NC 2015 | SHS (2015) | Region V | Masbate | 302172 | Tanque National High School | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 050515S00023 | 15FJ0054 | 2015-11-10 | 2015-11-24 | 2015-12-07 | 2015-12-14 | 2015-12-22 | C.L. CARANDANG ENTERPRISES
11843 | NC 2015 | SHS (2015) | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | USON | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6534338 |  |  | COMPLETED | 1
11844 | NC 2015 | K10 (2015) | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | USON | 3 | 1 | 1 | Completion of 1STY3CL | 2015 COMPLETION BATCH 4 | 79591.67 |  |  | COMPLETED | 1
11845 | NC 2015 | SHS (2015) | Region V | Masbate | 302175 | Uson National High School | USON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 050515S00024 | 15FJ0038 | 2015-10-12 | 2015-10-14 | 2015-10-27 | 2015-11-02 | 2015-11-19 | SHA SHA LUMBER & CONSTRUCTION
11846 | NC 2015 | SHS (2015) | Region V | Masbate | 302176 | Verdida-Sabrido National High School | PLACER | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | COMPLETED | 1
11847 | NC 2015 | SHS (2015) | Region V | Masbate | 302177 | VillaHermosa NHS | CAWAYAN | 3 | 1 | 12 | 2STY6CL | 2015 SHS BATCH 5 | 16659930 |  |  | COMPLETED | 1
11848 | NC 2015 | SHS (2015) | Region V | Masbate | 302178 | Vivencio P. Casas, Sr. Memorial High School | PLACER | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8334965.051 |  |  | COMPLETED | 1
11849 | NC 2015 | K10 (2015) | Region V | Masbate City | 113674 | Cawayan Exterior ES | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 050515S00100 | 15FI0042 | 2015-08-20 | 2015-08-20 | 2015-09-02 | 2015-09-18 | 2015-10-01 | SHA SHA LUMBER & CONSTRUCTION
11850 | NC 2015 | K10 (2015) | Region V | Masbate City | 113680 | Julian V. Antonio (Bolo ES) | CITY OF MASBATE (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6189337.6381 |  |  | COMPLETED | 1 |  |  | 050515S00110 | 15FI0110
11851 | NC 2015 | K10 (2015) | Region V | Masbate City | 113716 | Usab ES | CITY OF MASBATE (Capital) | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 050515S00059 | 15FI0102 | 2015-10-31
11852 | NC 2015 | K10 (2015) | Region V | Naga City | 302264 | Camarines Sur National High School | NAGA CITY | 3 | 1 | 2 | Completion of 2 Units 3STY9CL | 2015 COMPLETION BATCH 4 | 2932447 |  |  | COMPLETED | 1
11853 | NC 2015 | SHS (2015) | Region V | NAGA CITY | 302264 | Camarines Sur National High School | NAGA CITY | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26827469.42 |  |  | COMPLETED | 1
11854 | NC 2015 | SHS (2015) | Region V | NAGA CITY | 302264 | Camarines Sur National High School | NAGA CITY | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26827469.42 |  |  | COMPLETED | 1
11855 | NC 2015 | TECHVOC (2015) | Region V | Naga City | 302264 | Camarines Sur National High School | NAGA CITY | 3 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
11856 | NC 2015 | SHS (2015) | Region V | NAGA CITY | 302267 | Concepcion Pequeña National High School | NAGA CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 050315S00128 | 15FE0098 | 2015-07-03 | 2015-07-06 | 2015-07-20 | 2015-07-28 | 2015-08-03 | AE BELLEZA BUILDERS
11857 | NC 2015 | TECHVOC (2015) | Region V | Naga City | 302269 | Naga City School of Arts and Trades | NAGA CITY | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
11858 | NC 2015 | SHS (2015) | Region V | NAGA CITY | 310301 | Tinago National High School | NAGA CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 050315S00126 | 15FE0126 | 2015-10-19 | 2015-10-23 | 2015-11-03 | 2015-11-10 | 2015-12-01 | V.S. CERDON IRON WORKS & CONSTRUCTION
11859 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114117 | Amomonting ES | CASTILLA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2764446.04 |  |  | COMPLETED | 1 |  |  | 050615S00103 | 15FK0072 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | 2015-11-23 | SPRING STAR CONSTRUCTION & SUPPLY
11860 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114273 | Anibong ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2830710.84 |  |  | COMPLETED | 1 |  |  | 050615S00102 | 15FK0072 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | 2015-11-23 | SPRING STAR CONSTRUCTION & SUPPLY
11861 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114139 | Banuang-Gurang ES | DONSOL | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050615S00015 | 15FK0054 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-27 | 2015-09-04 | AL NINO CONSTRUCTION & SUPPLY
11862 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114365 | Bayasong ES | PILAR | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
11863 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114365 | Bayasong ES | PILAR | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
11864 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114141 | Bayawas ES | DONSOL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00088 | 15FK0067 | 2015-10-05 | 2015-10-16 | 2015-10-19
11865 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114288 | Biton ES | MAGALLANES (34 BRGYS) | 1 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1
11866 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114288 | Biton ES | MAGALLANES (34 BRGYS) | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
11867 | NC 2015 | K10 (2015) | Region V | Sorsogon | 310007 | Biton High School | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2210817 |  |  | COMPLETED | 1 |  |  | 050615S00130 | 15-GOODS-012 | [5 empty] | By Administration
11868 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114080 | Burgos ES | CASIGURAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 050615S00096 | 15FK0067 | 2015-10-05 | 2015-10-16 | 2015-10-19
11869 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114290 | Busay ES | MAGALLANES (34 BRGYS) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 050615S00119 | 15FK0072 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-09 | 2015-11-23 | SPRING STAR CONSTRUCTION & SUPPLY
11870 | NC 2015 | K10 (2015) | Region V | Sorsogon | 302194 | Cabugao NHS | DONSOL | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050615S00018 | 15FK0054 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-27 | 2015-09-04 | AL NINO CONSTRUCTION & SUPPLY
11871 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114367 | Cagbacong ES | PILAR | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00100 | 15FK0071 | 2015-10-15 | 2015-10-28 | 2015-10-29 | 2015-11-12 | 2015-11-23 | AL NINO CONSTRUCTION & SUPPLY
11872 | NC 2015 | TECHVOC (2015) | Region V | Sorsogon | 302197 | Casiguran Technical Vocational School | CASIGURAN | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
11873 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114102 | Castilla East CS | CASTILLA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00104 | 15FK0072 | 2015-10-15 | 2015-10-27 | 2015-10-30 | 2015-11-11 | 2015-11-23 | SPRING STAR CONSTRUCTION & SUPPLY
11874 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114343 | Dapdap ES | PILAR | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00125 | 15FK0069 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-11-05 | 2015-11-12 | Hi-Tone Construction
11875 | NC 2015 | SHS (2015) | Region V | SORSOGON | 302202 | Dinapa NHS | CASTILLA | 1 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18372268.79 |  |  | COMPLETED | 1 |  |  | 050615S00010 | 15FK0073 | 2015-11-02 | 2015-11-13 | 2015-11-16
11876 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114278 | Dona O. De C. Mella ES | MAGALLANES (34 BRGYS) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
11877 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114278 | Dona O. De C. Mella ES | MAGALLANES (34 BRGYS) | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
11878 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114292 | Eduardo Lee Chan MS (Magallanes South) | MAGALLANES (34 BRGYS) | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 050615S00021 | 15FK0054 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-28 | 2015-09-04 | AL NINO CONSTRUCTION & SUPPLY
11879 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114293 | Ginangra ES | MAGALLANES (34 BRGYS) | 1 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1 |  |  | 050615S00126 | 15FK0072 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-10 | 2015-11-23 | SPRING STAR CONSTRUCTION & SUPPLY
11880 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114163 | Girawan Elementary School | DONSOL | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050615S00022 | 15FK0054 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-28 | 2015-09-04 | AL NINO CONSTRUCTION & SUPPLY
11881 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114375 | Inang ES | PILAR | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00127 | 15FK0069 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-11-03 | 2015-11-12 | Hi-Tone Construction
11882 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114347 | Inapugan ES | PILAR | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
11883 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114347 | Inapugan ES | PILAR | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
11884 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114347 | Inapugan ES | PILAR | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
11885 | NC 2015 | SHS (2015) | Region V | SORSOGON | 302220 | Magallanes National Vocational HS | MAGALLANES (34 BRGYS) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00009 | 15FK0057 | 2015-08-10 | 2015-08-20 | 2015-08-24 | 2015-09-17 | 2015-09-21 | SPRING STAR CONSTRUCTION & SUPPLY
11886 | NC 2015 | SHS (2015) | Region V | SORSOGON | 302222 | Magallanes NHS | MAGALLANES (34 BRGYS) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10447131.51 |  |  | COMPLETED | 1 |  |  | 050615S00006 | 15FK0073 | 2015-11-02 | 2015-11-14 | 2015-11-16
11887 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114281 | Magallanes North CS | MAGALLANES (34 BRGYS) | 1 | 1 | 8 | 2STY4CL | 2015 K10 BATCH 6 | 12338675.2761 |  |  | COMPLETED | 1 |  |  | 050615S00094 | 15FK0072 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-10 | 2015-11-23 | SPRING STAR CONSTRUCTION & SUPPLY
11888 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114167 | Malinao ES | DONSOL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00087 | 15FK0067 | 2015-10-05 | 2015-10-16 | 2015-10-19
11889 | NC 2015 | SHS (2015) | Region V | SORSOGON | 302226 | Mayon NHS | CASTILLA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6349337.6381 |  |  | COMPLETED | 1
11890 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114353 | Palanas ES | PILAR | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 050615S00123 | 15FK0071 | 2015-10-15 | 2015-10-28 | 2015-10-29 | 2015-11-11 | 2015-11-23 | AL NINO CONSTRUCTION & SUPPLY
11891 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114112 | Pandan ES | CASTILLA | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 7335937.56 |  |  | COMPLETED | 1 |  |  | 050615S00089 | 15FK0072 | 2015-10-15 | 2015-11-03 | 2015-11-05 | 2015-11-17 | 2015-11-23 | SPRING STAR CONSTRUCTION & SUPPLY
11892 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114386 | Pudo ES | PILAR | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 050615S00118 | 15FK0069 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-11-03 | 2015-11-12 | Hi-Tone Construction
11893 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114175 | San Jose ES | DONSOL | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
11894 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114175 | San Jose ES | DONSOL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
11895 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114360 | San Rafael ES | PILAR | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 050615S00101 | 15FK0071 | 2015-10-15 | 2015-10-28 | 2015-10-29 | 2015-11-13 | 2015-11-23 | AL NINO CONSTRUCTION & SUPPLY
11896 | NC 2015 | SHS (2015) | Region V | SORSOGON | 302241 | San Rafael NHS | CASTILLA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 050615S00012 | 15FK0057 | 2015-08-10 | 2015-08-20 | 2015-08-24 | 2015-09-16 | 2015-09-21 | SPRING STAR CONSTRUCTION & SUPPLY
11897 | NC 2015 | SHS (2015) | Region V | SORSOGON | 302243 | Siuton NHS | MAGALLANES (34 BRGYS) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6349337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00004 | 15FK0057 | 2015-08-10 | 2015-08-20 | 2015-08-24 | 2015-09-18 | 2015-09-21 | SPRING STAR CONSTRUCTION & SUPPLY
11898 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114361 | Sta. Fe ES | PILAR | 1 | 1 | 6 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 5605184.88 |  |  | COMPLETED | 1 |  |  | 050615S00122 | 15FK0071 | 2015-10-15 | 2015-10-27 | 2015-10-29 | 2015-11-13 | 2015-11-23 | AL NINO CONSTRUCTION & SUPPLY
11899 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114180 | Tagbac ES | DONSOL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
11900 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114180 | Tagbac ES | DONSOL | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
11901 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114363 | Tingco ES | PILAR | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00121 | 15FK0069 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-11-05 | 2015-11-12 | Hi-Tone Construction
11902 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114224 | Batang ES | IROSIN | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 6 | 10727342.5917 |  |  | COMPLETED | 1 |  |  | 050615S00064 | 15FL0062 | 2015-08-24 | 2015-08-27 | 2015-09-08 | 2015-09-22 |  | FLFB ENTERPRISES AND CONSTRUCTION SERVICES
11903 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114204 | Benguet ES | GUBAT | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00106 | 15FL0048 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-09-14 | 2015-10-01 | STEVEN CONSTRUCTION & SUPPLY
11904 | NC 2015 | K10 (2015) | Region V | Sorsogon | 113983 | Bugtong ES | BARCELONA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00117 | 15FL0051 | 2015-08-13 | 2015-08-13 | 2015-08-27 | 2015-09-14 | 2015-10-01 | STEVEN CONSTRUCTION & SUPPLY
11905 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114004 | Bulan North CS-B | BULAN | 2 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 14971327.92 |  |  | COMPLETED | 1
11906 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114390 | Bulawan ES | PRIETO DIAZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00093 | 15FL0047 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-09-14 | 2015-10-01 | DREAM BUILDERS AND TECH DEV. CORP.
11907 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114254 | Calmayon ES | JUBAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00055 | 15FL0055 | 2015-08-16 | 2015-08-20 | 2015-09-03 | 2015-09-21 | 2015-10-02 | DREAM BUILDERS AND TECH DEV. CORP.
11908 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114008 | Calpi ES | BULAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1978606.04 |  |  | COMPLETED | 1 |  |  | 050615S00098 | 15FL0049 | 2015-08-12 | 2015-08-13 | 2015-08-26 | 2015-09-21 | 2015-10-02 | BLACKRAM BUILDERS, INC.
11909 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114255 | Caruhayon ES | JUBAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00090 | 15FL0055 | 2015-08-16 | 2015-08-20 | 2015-09-03 | 2015-09-21 | 2015-10-02 | DREAM BUILDERS AND TECH DEV. CORP.
11910 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114230 | Cawayan ES | IROSIN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 050615S00060
11911 | NC 2015 | SHS (2015) | Region V | Sorsogon | 302200 | Culasi NHS | MATNOG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6519338 |  |  | COMPLETED | 1 |  |  | 050615S00031 | 15FL0057 | 2015-08-16 | 2015-08-20 | 2015-10-22 | 2015-11-03 | 2015-11-11 | RMH CONSTRUCTION & SUPPLY
11912 | NC 2015 | SHS (2015) | Region V | SORSOGON | 302203 | Danao NHS | BULAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1978606.04 |  |  | REVERTED | 0 |  |  | 050615S00008
11913 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114062 | Dancalan ES | BULUSAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
11914 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114062 | Dancalan ES | BULUSAN | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
11915 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114191 | Dita ES | GUBAT | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00110 | 15FL0048 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-09-14 | 2015-10-01 | STEVEN CONSTRUCTION & SUPPLY
11916 | NC 2015 | SHS (2015) | Region V | SORSOGON | 302207 | Donsol Vocational HS | DONSOL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8114965.051 |  |  | COMPLETED | 1 |  |  | 050615S00007 | 15FK0057 | 2015-08-10 | 2015-08-20 | 2015-08-24 | 2015-09-15 | 2015-09-21 | SPRING STAR CONSTRUCTION & SUPPLY
11917 | NC 2015 | TECHVOC (2015) | Region V | Sorsogon | 302212 | Gallanosa National High School | IROSIN | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4979098.54 |  |  | COMPLETED | 1
11918 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114314 | Genablan Or. ES | MATNOG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 050615S00061 | 15FL0059 | 2015-08-16 | 2015-08-20 | 2015-09-03 | 2015-09-22 | 2015-10-02 | GROSIN CONSTRUCTION & SUPPLY
11919 | NC 2015 | TECHVOC (2015) | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4879098.54 |  |  | COMPLETED | 1
11920 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114233 | Gulang-Gulang ES | IROSIN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00057 | 15FL0054 | 2015-08-16 | 2015-08-20 | 2015-09-01 | 2015-09-21 | 2015-10-02 | DREAM BUILDERS AND TECH DEV. CORP.
11921 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114014 | Inararan ES | BULAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
11922 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114014 | Inararan ES | BULAN | 2 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
11923 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114015 | J.P. Laurel ES | BULAN | 2 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1 |  |  | 050615S00107 | 15FL0050 | 2015-08-12 | 2015-08-13 | 2015-08-26 | 2015-09-14 | 2015-10-01 | BLACKRAM BUILDERS, INC.
11924 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114212 | Manapao ES | GUBAT | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00108 | 15FL0048 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-09-14 | 2015-10-01 | STEVEN CONSTRUCTION & SUPPLY
11925 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114238 | Mapaso ES | IROSIN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
11926 | NC 2015 | SHS (2015) | Region V | Sorsogon | 302225 | Matnog NHS | MATNOG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8369965 |  |  | REVERTED | 0 |  |  | 050615S00036 | 15FL0056 | 2015-08-16 | 2015-08-20
11927 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114214 | Nazareno ES | GUBAT | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00092 | 15FL0048 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-09-14 | 2015-10-01 | STEVEN CONSTRUCTION & SUPPLY
11928 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114044 | Obrero ES | BULAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 050615S00111 | 15FL0050 | 2015-08-12 | 2015-08-13 | 2015-08-26 | 2015-09-14 | 2015-10-01 | BLACKRAM BUILDERS, INC.
11929 | NC 2015 | K10 (2015) | Region V | Sorsogon | 302181 | Olimpio A. Guarin Jr. NHS | JUBAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2088606 |  |  | COMPLETED | 1 |  |  | 050615S00131 | 15FL0052 | 2015-08-13 | 2015-08-13 | 2015-08-27 | 2015-10-08 | 2015-10-17 | RMH CONSTRUCTION & SUPPLY
11930 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114240 | Patag ES | IROSIN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 050615S00063 | 15FL0053 | 2015-08-16 | 2015-08-20 | 2015-09-01 | 2015-09-16 | 2015-10-02 | SPRING STAR CONSTRUCTION & SUPPLY
11931 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114025 | R. Gerona ES | BULAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2108606.04 |  |  | COMPLETED | 1 |  |  | 050615S00097 | 15FL0050 | 2015-08-12 | 2015-08-13 | 2015-08-26 | 2015-09-14 | 2015-10-01 | BLACKRAM BUILDERS, INC.
11932 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114241 | Salvacion ES | IROSIN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00046 | 15FL0054 | 2015-08-16 | 2015-08-20 | 2015-09-01 | 2015-09-21 | 2015-10-02 | DREAM BUILDERS AND TECH DEV. CORP.
11933 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114069 | San Francisco ES | BULUSAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00112 | 15FL0051 | 2015-08-13 | 2015-08-13 | 2015-08-27 | 2015-09-14 | 2015-10-01 | STEVEN CONSTRUCTION & SUPPLY
11934 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114049 | San Isidro ES | BULAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00128 | 15FL0049 | 2015-08-12 | 2015-08-13 | 2015-08-26 | 2015-09-21 | 2015-10-02 | BLACKRAM BUILDERS, INC.
11935 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114070 | San Isidro ES | BULUSAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00095 | 15FL0051 | 2015-08-13 | 2015-08-13 | 2015-08-27 | 2015-09-14 | 2015-10-01 | STEVEN CONSTRUCTION & SUPPLY
11936 | NC 2015 | K10 (2015) | Region V | Sorsogon | 302239 | San Juan (Bag-o) HS | BULAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2802592 |  |  | COMPLETED | 1 |  |  | 050615S00129 | 15FL0052 | 2015-08-13 | 2015-08-13 | 2015-08-27 | 2015-10-08 | 2015-10-17 | RMH CONSTRUCTION & SUPPLY
11937 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114028 | San Juan Bago ES | BULAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00114 | 15FL0049 | 2015-08-12 | 2015-08-13 | 2015-08-26 | 2015-09-21 | 2015-10-02 | BLACKRAM BUILDERS, INC.
11938 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114401 | San Juan ES | PRIETO DIAZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00113 | 15FL0047 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-09-14 | 2015-10-01 | DREAM BUILDERS AND TECH DEV. CORP.
11939 | NC 2015 | K10 (2015) | Region V | Sorsogon | 113994 | San Ramon ES | BARCELONA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1978606.04 |  |  | COMPLETED | 1 |  |  | 050615S00099 | 15FL0051 | 2015-08-13 | 2015-08-13 | 2015-08-27 | 2015-09-14 | 2015-10-01 | STEVEN CONSTRUCTION & SUPPLY
11940 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114327 | Sinang-Atan Elementary School | MATNOG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | REVERTED | 0 |  |  | 050615S00105
11941 | NC 2015 | K10 (2015) | Region V | Sorsogon | 175007 | Sipaya ES | JUBAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2852592.44 |  |  | COMPLETED | 1 |  |  | 050615S00091 | 15FL0055 | 2015-08-16 | 2015-08-20 | 2015-09-03 | 2015-09-21 | 2015-10-02 | DREAM BUILDERS AND TECH DEV. CORP.
11942 | NC 2015 | SHS (2015) | Region V | Sorsogon | 302245 | Sta. Magdalena NHS | SANTA MAGDALENA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2907592 |  |  | COMPLETED | 1 |  |  | 050615S00037 | 15FL0058 | 2015-08-16 | 2015-08-20 | 2015-09-03 | 2015-11-05 | 2015-11-14 | GRELIPS CONSTRUCTION & DEVELOPMENT
11943 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114031 | Sta. Remedios ES | BULAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 050615S00030 | 15FL0021 | 2015-07-12 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | BLACKRAM BUILDERS, INC.
11944 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114201 | Tagaytay Elementary School | GUBAT | 2 | 1 | 6 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 5605184.88 |  |  | COMPLETED | 1
11945 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114055 | TAROMATA I | BULAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00085 | 15FL0049 | 2015-08-12 | 2015-08-13 | 2015-08-26 | 2015-09-21 | 2015-10-02 | BLACKRAM BUILDERS, INC.
11946 | NC 2015 | K10 (2015) | Region V | Sorsogon | 114245 | Tinampo ES | IROSIN | 2 | 1 | 6 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 5605184.88 |  |  | COMPLETED | 1 |  |  | 050615S00058 | 15FL0053 | 2015-08-16 | 2015-08-20 | 2015-09-01 | 2015-09-16 | 2015-10-01 | SPRING STAR CONSTRUCTION & SUPPLY
11947 | NC 2015 | SHS (2015) | Region V | Sorsogon City | 302270 | Abuyog NHS | CITY OF SORSOGON (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10517132 |  |  | COMPLETED | 1 |  |  | 050615S00033 | 15FK0078 | 2015-11-05 | 2015-11-17 | 2015-11-18 |  |  | B. VICENCIO CONSTRUCTION
11948 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114561 | Ambrosio J. Labrador Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 050615S00076 | 15FK0070 | 2015-10-15 | 2015-10-28 | 2015-10-29 | 2015-11-11 | 2015-11-23 | STEVEN CONSTRUCTION & SUPPLY
11949 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114520 | Bacon East Central School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00049 | 15FK0067 | 2015-10-05 | 2015-10-16 | 2015-10-19
11950 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114534 | Bacon West Central School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00048 | 15FK0067 | 2015-10-05 | 2015-10-16 | 2015-10-19
11951 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114553 | Balogo Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00045 | 15FK0067 | 2015-10-05 | 2015-10-16 | 2015-10-19
11952 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114565 | Basud Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00062 | 15FK0070 | 2015-10-15 | 2015-10-28 | 2015-10-29 | 2015-11-10 | 2015-11-23 | STEVEN CONSTRUCTION & SUPPLY
11953 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114522 | Bato Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00040 | 15FK0067 | 2015-10-05 | 2015-10-16 | 2015-10-19
11954 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114525 | Buenavista Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 050615S00041 | 15FK0067 | 2015-10-05 | 2015-10-16 | 2015-10-19
11955 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114555 | Buhatan Integrated National School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00072 | 15FK0072 | 2015-10-15 | 2015-10-27 | 2015-10-29 | 2015-11-11 | 2015-11-23 | SPRING STAR CONSTRUCTION & SUPPLY
11956 | NC 2015 | SHS (2015) | Region V | Sorsogon City | 310401 | Buhatan NHS | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | COMPLETED | 1 |  |  | 050615S00035 | 15FK0078 | 2015-11-05 | 2015-11-17 | 2015-11-18 |  |  | B. VICENCIO CONSTRUCTION
11957 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114556 | Cabid-an Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00078 | 15FK0071 | 2015-10-15 | 2015-10-28 | 2015-10-29 | 2015-11-11 | 2015-11-23 | AL NINO CONSTRUCTION & SUPPLY
11958 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114570 | Cambulaga Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 050615S00073 | 15FK0070 | 2015-10-15 | 2015-10-28 | 2015-10-29 | 2015-11-10 | 2015-11-23 | STEVEN CONSTRUCTION & SUPPLY
11959 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114571 | Capuy Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00084 | 15FK0070 | 2015-10-15 | 2015-10-28 | 2015-10-29 | 2015-11-10 | 2015-11-23 | STEVEN CONSTRUCTION & SUPPLY
11960 | NC 2015 | SHS (2015) | Region V | Sorsogon City | 302272 | Celestino G. Tabuena Memorial NHS | CITY OF SORSOGON (Capital) | 1 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 12871310 |  |  | COMPLETED | 1 |  |  | 050615S00032 | 15FK0078 | 2015-11-05 | 2015-11-17 | 2015-11-18 |  |  | B. VICENCIO CONSTRUCTION
11961 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114536 | Del Rosario Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00044 | 15FK0067 | 2015-10-05 | 2015-10-16 | 2015-10-19
11962 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114557 | Marinas I Elmentary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
11963 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114574 | Pamurayan Integrated School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00071 | 15FK0070 | 2015-10-15 | 2015-10-28 | 2015-10-29 | 2015-11-13 | 2015-11-23 | STEVEN CONSTRUCTION & SUPPLY
11964 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114576 | Panlayaan Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
11965 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114576 | Panlayaan Elementary School | CITY OF SORSOGON (Capital) | 1 |  | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1
11966 | NC 2015 | SHS (2015) | Region V | Sorsogon City | 310402 | Panlayaan Technical Vocational High School | CITY OF SORSOGON (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 050615S00005 | 15FK0057 | 2015-08-10 | 2015-08-20 | 2015-08-24 | 2015-09-16 | 2015-09-21 | SPRING STAR CONSTRUCTION & SUPPLY
11967 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114577 | Penafrancia Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | REVERTED | 0
11968 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114577 | Penafrancia Elementary School | CITY OF SORSOGON (Capital) | 1 |  | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1
11969 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114577 | Penafrancia Elementary School | CITY OF SORSOGON (Capital) | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
11970 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 177002 | Quirino Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | REVERTED | 0 |  |  | 050615S00050 | 15FK0067 | 2015-10-05 | 2015-10-16
11971 | NC 2015 | SHS (2015) | Region V | Sorsogon City | 302276 | Rizal Integrated National School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | COMPLETED | 1
11972 | NC 2015 | TECHVOC (2015) | Region V | Sorsogon City | 302276 | Rizal Integrated National School | CITY OF SORSOGON (Capital) | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2629549.27 |  |  | COMPLETED | 1
11973 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114560 | Rosa T. Arellano Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00077 | 15FK0072 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-11 | 2015-11-23 | SPRING STAR CONSTRUCTION & SUPPLY
11974 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114580 | Salvacion Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00042 | 15FK0067 | 2015-10-05 | 2015-10-16 | 2015-10-19
11975 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114543 | San Juan Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00039 | 15FK0068 | 2015-10-06 | 2015-10-16 | 2015-10-19 | 2015-11-05 | 2015-11-12 | RLS CONSTRUCTION
11976 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114562 | San Lorenzo Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00075 | 15FK0070 | 2015-10-15 | 2015-10-28 | 2015-10-29 | 2015-11-10 | 2015-11-23 | STEVEN CONSTRUCTION & SUPPLY
11977 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114544 | San Pascual Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
11978 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114544 | San Pascual Elementary School | CITY OF SORSOGON (Capital) | 1 |  | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1
11979 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114545 | San Ramon Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
11980 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114545 | San Ramon Elementary School | CITY OF SORSOGON (Capital) | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
11981 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114546 | San Roque Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00082 | 15FK0069 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-11-03 | 2015-11-12 | Hi-Tone Construction
11982 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114547 | San Vicente Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1 |  |  | 050615S00081 | 15FK0069 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-11-03 | 2015-11-12 | Hi-Tone Construction
11983 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114530 | Sawanga Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 050615S00043 | 15FK0067 | 2015-10-05 | 2015-10-16 | 2015-10-19
11984 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114563 | Sorsogon East Central School | CITY OF SORSOGON (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | COMPLETED | 1
11985 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114563 | Sorsogon East Central School | CITY OF SORSOGON (Capital) | 1 |  | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1
11986 | NC 2015 | SHS (2015) | Region V | Sorsogon City | 302279 | Sorsogon NHS | CITY OF SORSOGON (Capital) | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31302890 |  |  | COMPLETED | 1 |  |  | 050615S00038 | 15FK0077 | 2015-11-05 | 2015-11-17 | 2015-11-18 |  |  | B. VICENCIO CONSTRUCTION
11987 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114581 | Sorsogon Pilot Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1
11988 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114548 | Sta. Cruz Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 050615S00080 | 15FK0069 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-11-03 | 2015-11-12 | Hi-Tone Construction
11989 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114549 | Sto. Domingo Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 050615S00079 | 15FK0069 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-11-04 | 2015-11-12 | Hi-Tone Construction
11990 | NC 2015 | K10 (2015) | Region V | Sorsogon City | 114583 | Tublijon Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 050615S00065 | 15FK0075 | 2015-11-04 | 2015-11-16 | 2015-11-17
11991 | NC 2015 | SHS (2015) | Region V | Tabaco City | 310501 | Bongabong High School | CITY OF TABACO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2982592 |  |  | COMPLETED | 1
11992 | NC 2015 | SHS (2015) | Region V | Tabaco City | 310501 | Bongabong High School | CITY OF TABACO | 1 |  | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6559338 |  |  | COMPLETED | 1
11993 | NC 2015 | SHS (2015) | Region V | Tabaco City | 310501 | Bongabong High School | CITY OF TABACO | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2058606 |  |  | COMPLETED | 1
11994 | NC 2015 | SHS (2015) | Region V | Tabaco City | 310503 | Hacienda High School | CITY OF TABACO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2058606 |  |  | REVERTED | 0
11995 | NC 2015 | SHS (2015) | Region V | Tabaco City | 310503 | Hacienda High School | CITY OF TABACO | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2982592 |  |  | REVERTED | 0
11996 | NC 2015 | SHS (2015) | Region V | Tabaco City | 310503 | Hacienda High School | CITY OF TABACO | 1 |  | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3907969 |  |  | REVERTED | 0
11997 | NC 2015 | SHS (2015) | Region V | Tabaco City | 310503 | Hacienda High School | CITY OF TABACO | 1 |  | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6559338 |  |  | COMPLETED | 1
11998 | NC 2015 | SHS (2015) | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
11999 | NC 2015 | TECHVOC (2015) | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
18404 | NC 2016 | TECHVOC | Region V | Albay | 301816 | Bonga National High School | Bacacay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
18405 | NC 2016 | K10 | Region V | Albay | 309515 | Cabasan National High School To Malilipot Nhs | Bacacay | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6910526.07 |  |  | Completed | 1
18406 | NC 2016 | SHS | Region V | Albay | 301880 | Cawayan National High School To Tiwi Agro-Industrial School | Bacacay | 1 |  | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1
18407 | NC 2016 | TECHVOC | Region V | Albay | 301821 | Cawayan National High School | Bacacay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1
18408 | NC 2016 | TECHVOC | Region V | Albay | 301810 | Malinao National High School | Malinao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
18409 | NC 2016 | K10 | Region V | Albay | 301810 | Malinao National High School | Malinao | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8860595.15 |  |  | Completed | 1
18410 | NC 2016 | TECHVOC | Region V | Albay | 301853 | Naga National High School | Tiwi | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
18411 | NC 2016 | SHS | Region V | Albay | 301853 | Naga National High School | Tiwi | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6782016.72 |  |  | Completed | 1
18412 | NC 2016 | TECHVOC | Region V | Albay | 301863 | Pili National High School | Bacacay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
18413 | NC 2016 | SHS | Region V | Albay | 301875 | San Jose National High School | Malilipot | 1 | 1 | 20 | 4STY20CL | BATCH 1 CL | 50013141.81 |  |  | Completed | 1
18414 | NC 2016 | SHS | Region V | Albay | 301875 | San Jose National High School | Malilipot | 1 |  | 6 | 2STY6CL | BATCH 1 CL | 8928770.16 |  |  | Completed | 1
18415 | NC 2016 | TECHVOC | Region V | Albay | 301875 | San Jose National High School | Malilipot | 1 | 1 | 4 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 11252547.49 |  |  | Completed | 1
18416 | NC 2016 | TECHVOC | Region V | Albay | 309515 | Malilipot National High School |  | 1 | 1 | 2 | SHS UNIQUE WORKSHOP |  | 5626273.74 |  |  | Completed | 1
18417 | NC 2016 | TECHVOC | Region V | Albay | 301879 | Sto. Domingo National High School |  | 1 | 1 | 1 | SHS UNIQUE WORKSHOP |  | 2813136.87 |  |  | Completed | 1
18418 | NC 2016 | TECHVOC | Region V | Albay | 301810 | Malinao National High School |  | 1 | 1 | 1 | SHS UNIQUE WORKSHOP |  | 2813136.87 |  |  | Completed | 1
18419 | NC 2016 | K10 | Region V | Albay | 301816 | San Pablo High School To Bonga Nhs | Bacacay | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
18420 | NC 2016 | K10 | Region V | Albay | 301878 | Sogod National High School | Bacacay | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
18421 | NC 2016 | TECHVOC | Region V | Albay | 301879 | Sto. Domingo National High School | Santo Domingo (Libog) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
18422 | NC 2016 | K10 | Region V | Albay | 301879 | Sto. Domingo National High School | Santo Domingo (Libog) | 1 | 1 | 8 | 2STY4CL | BATCH 13 CL | 13585698.5 |  |  | Completed | 1
18423 | NC 2016 | K10 | Region V | Albay | 301879 | Sto. Domingo National High School | Santo Domingo (Libog) | 1 |  | 6 | 2STY6CL | BATCH 13 CL | 8892671.82 |  |  | Completed | 1
18424 | NC 2016 | K10 | Region V | Albay | 301880 | Tiwi Agro-Industrial School | Tiwi | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8890910.7 |  |  | Completed | 1
18425 | NC 2016 | K10 | Region V | Albay | 301885 | Vinisitahan National High School | Bacacay | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9002029.2 |  |  | Completed | 1
18426 | NC 2016 | K10 | Region V | Albay | 301808 | Anislag National High School | Daraga (Locsin) | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23656314.795 |  |  | Completed | 1
18427 | NC 2016 | TECHVOC | Region V | Albay | 301808 | Anislag National High School | Daraga (Locsin) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2465078.77 |  |  | Completed | 1
18428 | NC 2016 | K10 | Region V | Albay | 301825 | Daraga National High School | Daraga (Locsin) | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1
18429 | NC 2016 | K10 | Region V | Albay | 301841 | Malabog National High School | Daraga (Locsin) | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1
18430 | NC 2016 | K10 | Region V | Albay | 301845 | Manito National High School | Manito | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23506314.795 |  |  | Completed | 1
18431 | NC 2016 | TECHVOC | Region V | Albay |  | Manito National High School | Manito | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7443652.41 |  |  | Completed | 1
18432 | NC 2016 | K10 | Region V | Albay | 301869 | Rapu-Rapu National High School | Rapu-Rapu | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 11531152.7485 |  |  | Completed | 1
18433 | NC 2016 | K10 | Region V | Albay | 301828 | Itaran National High School | Polangui | 3 | 1 | 12 | 4STY12CL | BATCH 3 CL | 20767107.46 |  |  | Completed | 1 |  |  | P00070495LZ | 16FO0088 | 2017-10-26 | 2017-11-03 | 2017-11-15 | 2017-12-15 | 2017-12-17 | HI-TONE CONST. & DEV'T. CORP
18434 | NC 2016 | TECHVOC | Region V | Albay | 301833 | Libon Agro-Industrial High School | Libon | 3 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 7318809.93 |  |  | Completed | 1
18435 | NC 2016 | K10 | Region V | Albay | 301833 | Libon Agro-Industrial High School | Libon | 3 | 1 | 20 | 4STY20CL | BATCH 3 CL | 28520975.67 |  |  | Completed | 1
18436 | NC 2016 | K10 | Region V | Albay | 301833 | Libon Agro-Industrial High School | Libon | 3 |  | 3 | 1STY3CL | BATCH 3 CL | 2686101.03 |  |  | Completed | 1
18437 | NC 2016 | K10 | Region V | Albay | 301865 | Polangui General Comprehensive High School | Polangui | 3 | 1 | 48 | 4STY16CL | BATCH 9 CL | 73169025.93 |  |  | Completed | 1 |  |  | P00073556LZ | 17FO0062 | 2017-09-08 | 2017-09-15 | 2017-09-27 | 2017-09-30 | 2017-10-18 | HERBANA BUILDERS & SUPPLY
18438 | NC 2016 | K10 | Region V | Camarines Norte | 112206 | Daguit Es | Labo | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6519337.64 |  |  | Completed | 1
18439 | NC 2016 | K10 | Region V | Camarines Norte | 173013 | Dancalan Es | Paracale | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1964740.17 |  |  | Completed | 1
18440 | NC 2016 | K10 | Region V | Camarines Norte | 112114 | Diezmo-Urena Es | Capalonga | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6469337.64 |  |  | Completed | 1
18441 | NC 2016 | K10 | Region V | Camarines Norte | 112209 | Florence Es | Labo | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1
18442 | NC 2016 | K10 | Region V | Camarines Norte | 112203 | G. Cale Es | Labo | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1062049.65 |  |  | Completed | 1
18443 | NC 2016 | SHS | Region V | Camarines Norte | 301896 | Gonzalo Aler Nhs | Capalonga | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6376848.0401 |  |  | Completed | 1
18444 | NC 2016 | SHS | Region V | Camarines Norte | 301896 | Gonzalo Aler Nhs | Capalonga | 1 |  | 2 | 1STY2CL | BATCH 11 CL | 1978606.04 |  |  | Completed | 1
18445 | NC 2016 | K10 | Region V | Camarines Norte | 112247 | Gumaus Es | Paracale | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2815828.12 |  |  | Completed | 1
18446 | NC 2016 | SHS | Region V | Camarines Norte | 301898 | Jose Panganiban Nhs | Jose Panganiban | 1 | 1 | 30 | 3STY15CL | BATCH 9 CL | 42766026.9 |  |  | Completed | 1
18447 | NC 2016 | SHS | Region V | Camarines Norte | 301898 | Jose Panganiban Nhs | Jose Panganiban | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8214965.05 |  |  | Completed | 1
18448 | NC 2016 | TECHVOC | Region V | Camarines Norte | 301898 | Jose Panganiban Nhs | Jose Panganiban | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4859098.54 |  |  | Completed | 1
18449 | NC 2016 | K10 | Region V | Camarines Norte | 112210 | Kabatuhan Es | Labo | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6369337.64 |  |  | Completed | 1
18450 | NC 2016 | SHS | Region V | Camarines Norte | 301917 | Leocadio Alejo Entienza Hs | Sta Elena | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10517131.51 |  |  | Completed | 1
18451 | NC 2016 | TECHVOC | Region V | Camarines Norte | 301917 | Leocadio Alejo Entienza Hs | Sta Elena | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2509549.27 |  |  | Completed | 1
18452 | NC 2016 | K10 | Region V | Camarines Norte | 112117 | Lukbanan Es | Capalonga | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1889740.17 |  |  | Completed | 1
18453 | NC 2016 | SHS | Region V | Camarines Norte | 309614 | Magsaysay Nhs | Capalonga | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6369337.64 |  |  | Completed | 1
18454 | NC 2016 | K10 | Region V | Camarines Norte | 112217 | Malaya Es | Labo | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2690828.12 |  |  | Completed | 1
18455 | NC 2016 | K10 | Region V | Camarines Norte | 112219 | Maligaya Es | Labo | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2572332.196 |  |  | Completed | 1
18456 | NC 2016 | K10 | Region V | Camarines Norte | 112119 | Marca-Murillo Es | Capalonga | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2695828.12 |  |  | Completed | 1
18457 | NC 2016 | K10 | Region V | Camarines Norte | 112253 | Mateo Era Es | Paracale | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1087049.65 |  |  | Completed | 1
18458 | NC 2016 | K10 | Region V | Camarines Norte | 112220 | Palali Es | Labo | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1889740.17 |  |  | Completed | 1
18459 | NC 2016 | K10 | Region V | Camarines Norte | 112284 | R. Oquindo Es | Santa Elena | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1883458.7763 |  |  | Completed | 1
18460 | NC 2016 | K10 | Region V | Camarines Norte | 112152 | Regino A. Yet Es (Luklukan Es) | Jose Panganiban | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6469337.64 |  |  | Completed | 1
18461 | NC 2016 | SHS | Region V | Camarines Norte | 301913 | Rizal Nhs | Sta Elena | 1 | 1 | 12 | 3STY12CL | BATCH 3 CL | 18422268.79 |  |  | Completed | 1
18462 | NC 2016 | SHS | Region V | Camarines Norte | 301922 | Tulay Na Lupa Nhs | Labo | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21408013.45 |  |  | Completed | 1
18463 | NC 2016 | SHS | Region V | Camarines Norte | 301922 | Tulay Na Lupa Nhs | Labo | 1 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1
18464 | NC 2016 | TECHVOC | Region V | Camarines Norte | 301922 | Tulay Na Lupa Nhs | Labo | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2509549.27 |  |  | Completed | 1
18465 | NC 2016 | K10 | Region V | Camarines Norte | 112175 | V. Gabo Es | Jose Panganiban | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1062049.65 |  |  | Completed | 1
18466 | NC 2016 | K10 | Region V | Camarines Norte | 173014 | Villa San Isidro Es | Santa Elena | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1087049.65 |  |  | Completed | 1
18467 | NC 2016 | K10 | Region V | Camarines Norte | 309613 | Alawihao Nhs | Daet (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
18468 | NC 2016 | TECHVOC | Region V | Camarines Norte | 309613 | Alawihao Nhs | Daet (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429549.27 |  |  | Completed | 1
18469 | NC 2016 | K10 | Region V | Camarines Norte | 173019 | Anita V. Romero | Daet (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1814740.17 |  |  | Completed | 1
18470 | NC 2016 | K10 | Region V | Camarines Norte | 112298 | Banocboc Es | Vinzons | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2740828.12 |  |  | Completed | 1 | [10 empty] | Terminated
18471 | NC 2016 | SHS | Region V | Camarines Norte | 301889 | Basud Nhs | Basud | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013.45 |  |  | Completed | 1
18472 | NC 2016 | SHS | Region V | Camarines Norte | 301889 | Basud Nhs | Basud | 2 |  | 12 | 3STY6CL | BATCH 9 CL | 20834263.02 |  |  | Completed | 1
18473 | NC 2016 | TECHVOC | Region V | Camarines Norte | 301889 | Basud Nhs | Basud | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7288647.81 |  |  | Completed | 1
18474 | NC 2016 | K10 | Region V | Camarines Norte | 301891 | Camarines Norte Nhs | Daet (Capital) | 2 | 1 | 30 | 3STY15CL | BATCH 9 CL | 42766026.9 |  |  | Reverted | 0
18475 | NC 2016 | TECHVOC | Region V | Camarines Norte | 301891 | Camarines Norte Nhs | Daet (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2479549.27 |  |  | Completed | 1
18476 | NC 2016 | K10 | Region V | Camarines Norte | 112222 | Cayucyucan Es | Mercedes | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1
18477 | NC 2016 | K10 | Region V | Camarines Norte | 301892 | D.Q. Liwag Nhs | Vinzons | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
18478 | NC 2016 | TECHVOC | Region V | Camarines Norte | 301892 | D.Q. Liwag Nhs | Vinzons | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429549.27 |  |  | Completed | 1
18479 | NC 2016 | K10 | Region V | Camarines Norte | 301919 | Froilan Lopez Hs (V) | San Vicente | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8264965.05 |  |  | Completed | 1
18480 | NC 2016 | K10 | Region V | Camarines Norte | 112090 | Hinampacan Es | Basud | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1914740.17 |  |  | Completed | 1
18481 | NC 2016 | K10 | Region V | Camarines Norte | 173002 | Julia A. Abilgos Es | Daet (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1814740.17 |  |  | Completed | 1
18482 | NC 2016 | K10 | Region V | Camarines Norte | 112230 | Lope Manlangit Es | Mercedes | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2790828.12 |  |  | Completed | 1
18483 | NC 2016 | K10 | Region V | Camarines Norte | 112231 | Mambungalon Es | Mercedes | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2690828.12 |  |  | Completed | 1
18484 | NC 2016 | SHS | Region V | Camarines Norte | 301902 | Manguisoc Nhs | Mercedes | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6519337.64 |  |  | Completed | 1
18485 | NC 2016 | SHS | Region V | Camarines Norte | 301905 | Mercedes Hs | Mercedes | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1
18486 | NC 2016 | SHS | Region V | Camarines Norte | 301906 | Moreno Integrated School | Daet (Capital) | 2 | 1 | 24 | 3STY12CL | BATCH 9 CL | 36444537.58 |  |  | Completed | 1
18487 | NC 2016 | TECHVOC | Region V | Camarines Norte | 301906 | Moreno Integrated School | Daet (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2479549.27 |  |  | Completed | 1
18488 | NC 2016 | K10 | Region V | Camarines Norte | 173018 | Paciano A. Magana Es | Daet (Capital) | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1012049.65 |  |  | Completed | 1
18489 | NC 2016 | K10 | Region V | Camarines Norte | 112236 | Pambuhan Es | Mercedes | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2740828.12 |  |  | Completed | 1
18490 | NC 2016 | K10 | Region V | Camarines Norte | 112237 | Quinapaguian Es | Mercedes | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1919740.17 |  |  | Completed | 1
18491 | NC 2016 | K10 | Region V | Camarines Norte | 112269 | Resettlement Es | San Lorenzo Ruiz (Imelda) | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1087049.65 |  |  | Completed | 1
18492 | NC 2016 | SHS | Region V | Camarines Norte | 301914 | Sabang Nhs | Vinzons | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6519337.64 |  |  | Completed | 1
18493 | NC 2016 | SHS | Region V | Camarines Norte | 301918 | San Roque Nhs | Mercedes | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15121327.92 |  |  | Completed | 1
18494 | NC 2016 | K10 | Region V | Camarines Norte | 112139 | Up Alawihao Resettlement Es | Daet (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1889740.17 |  |  | Completed | 1
18495 | NC 2016 | K10 | Region V | Camarines Norte | 301925 | Vinzons Pilot Nhs | Vinzons | 2 | 1 | 30 | 3STY15CL | BATCH 3 CL | 42766026.9 |  |  | Completed | 1
18496 | NC 2016 | SHS | Region V | Camarines Sur | 309724 | Agay-Ayan Nhs | Tinambac | 4 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2650000 |  |  | Completed | 1 |  |  | P0070520LZ | 16FF0034 |  | 2016-06-14 | 2016-06-28 | 2016-07-18 | 2016-08-01 | Grosin Const. & Supply
18497 | NC 2016 | K10 | Region V | Camarines Sur | 301928 | Antipolo National High School, Tinambac | Tinambac | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6681000 |  |  | Completed | 1 |  |  | P00070521LZ | 16FF0044 |  | 2016-06-21 | 2016-07-05 | 2016-08-05
18498 | NC 2016 | K10 | Region V | Camarines Sur | 309774 | Antipolo Heights Integrated School | Pasacao | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-07-05 | 2016-07-13 | 2016-07-26
18499 | NC 2016 | K10 | Region V | Camarines Sur | 112525 | Antolon Es | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  | P00073462LZ | 16FF0055 |  | 2016-08-16 | 2016-08-30
18500 | NC 2016 | K10 | Region V | Camarines Sur | 112881 | Ayugao Ps | Presentacion (Parubcan) | 4 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1939740 |  |  | Completed | 1 |  |  | P00070527LZ | 16FF0035 |  | 2016-06-14 | 2016-06-28 | 2016-07-18 | 2016-08-03 | HRB Const.
18501 | NC 2016 | K10 | Region V | Camarines Sur | 301931 | Baao National High School | Baao | 5 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
18502 | NC 2016 | K10 | Region V | Camarines Sur | 112526 | Bacgong Ps | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  | P00073463LZ | 16FF0055 |  | 2016-08-16 | 2016-08-30
18503 | NC 2016 | SHS | Region V | Camarines Sur | 301934 | Bagacay Hs | Tinambac | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6451273.8579 |  |  | Completed | 1 |  |  | P00073536LZ
18504 | NC 2016 | K10 | Region V | Camarines Sur | 112700 | Bagamelon Es | Libmanan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2146214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-12 | 2016-07-20 | 2016-08-02
18505 | NC 2016 | K10 | Region V | Camarines Sur | 112790 | Bagolatao Es | Minalabac | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-12 | 2016-07-20 | 2016-08-02
18506 | NC 2016 | K10 | Region V | Camarines Sur | 301937 | Bahi National Hs | Garchitorena | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 9374965 |  |  | Completed | 1 |  |  | P00070511LZ | 16FF0047 |  | 2016-06-21 | 2016-07-05
18507 | NC 2016 | K10 | Region V | Camarines Sur | 112772 | Bal-Flor Es | Milaor | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 2016-05-31 | E. GARCIA CONST. CORP.
18508 | NC 2016 | SHS | Region V | Camarines Sur | 301941 | Banga Hs | Tinambac | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6685000 |  |  | Completed | 1 |  |  | P00070522LZ | 16FF0044 |  | 2016-06-21 | 2016-07-05 | 2016-08-05
18509 | NC 2016 | SHS | Region V | Camarines Sur | 301942 | Barcelonita Fisheries School | Cabusao | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9081461.5561 |  |  | Completed | 1
18510 | NC 2016 | SHS | Region V | Camarines Sur | 301942 | Barcelonita Fisheries School | Cabusao | 1 |  | 2 | 1STY1CL | BATCH 9 CL | 2246509.2394 |  |  | Completed | 1
18511 | NC 2016 | SHS | Region V | Camarines Sur | 301944 | Binagasbasan Nhs | Garchitorena | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 7170500 |  |  | Completed | 1 |  |  | P00070512LZ | 16FF0041 |  | 2016-06-21 | 2016-07-05
18512 | NC 2016 | K10 | Region V | Camarines Sur | 112794 | Bingcay Es | Minalabac | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 2016-05-31 | E. GARCIA CONST. CORP.
18513 | NC 2016 | K10 | Region V | Camarines Sur | 309703 | Bitaogan National High School | Presentacion (Parubcan) | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 7190500 |  |  | Completed | 1 |  |  | P00070513LZ | 16FF0046 |  | 2016-06-21 | 2016-07-05 | 2016-08-08
18514 | NC 2016 | K10 | Region V | Camarines Sur | 112638 | Bocogan Es | Lagonoy | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073491LZ | 16FF0059 |  | 2016-08-16 | 2016-08-30
18515 | NC 2016 | SHS | Region V | Camarines Sur | 302060 | Bonifacio D. Borebor Sr. Hs (Formerly:Tawog Nhs) | Caramoan | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8550000 |  |  | Completed | 1
18516 | NC 2016 | SHS | Region V | Camarines Sur | 309734 | Buenavista National Hs | Tinambac | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6446953.9604 |  |  | Completed | 1 |  |  | P00073537LZ
18517 | NC 2016 | SHS | Region V | Camarines Sur | 301947 | Bula Nhs | Bula | 5 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
18518 | NC 2016 | SHS | Region V | Camarines Sur | 309768 | Cabotonan High School | Lagonoy | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6494205.4849 |  |  | Completed | 1 |  |  | P00073492LZ
18519 | NC 2016 | K10 | Region V | Camarines Sur | 112530 | Cadong Ps | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1929758.9174 |  |  | Completed | 1 |  |  | P00073464LZ | 16FF0055 |  | 2016-08-16 | 2016-08-30
18520 | NC 2016 | K10 | Region V | Camarines Sur | 112593 | Cagamutan Ps | Garchitorena | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073484LZ | 16FF0058 |  | 2016-08-16 | 2016-08-30
18521 | NC 2016 | K10 | Region V | Camarines Sur | 309757 | Cagbibi National High School | Pamplona | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6529337.64 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 2016-06-05 | HGG BUILDERS & SUPPLY
18522 | NC 2016 | K10 | Region V | Camarines Sur | 112707 | Camdilancha Elementary School | Libmanan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 2016-05-31 | E. GARCIA CONST. CORP.
18523 | NC 2016 | K10 | Region V | Camarines Sur | 173525 | Candami Elementary School | Libmanan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 2016-06-05 | HGG BUILDERS & SUPPLY
18524 | NC 2016 | K10 | Region V | Camarines Sur | 112902 | Caranan Es (North) | Pasacao | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-12 | 2016-07-20 | 2016-08-02
18525 | NC 2016 | K10 | Region V | Camarines Sur | 112903 | Caranan Es (South) | Pasacao | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6356887.0226 |  |  | Completed | 1 |  |  |  |  | 2016-02-19 | 2016-02-29 | 2016-03-15 |  | 2016-06-07 | ROLA CONST.
18526 | NC 2016 | SHS | Region V | Camarines Sur | 309708 | Catalotoan Hs | Sagñay | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8274000 |  |  | Completed | 1 |  |  | P00070515LZ | 16FF0040 |  | 2016-06-21 | 2016-07-05 | 2016-07-18 | 2016-08-01 | ZKR Construction & Supply
18527 | NC 2016 | TECHVOC | Region V | Camarines Sur | 301960 | Coguit High School | Balatan | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2741627.1841 |  |  | Completed | 1 |  |  |  |  | 2016-07-19 | 2016-07-29 | 2016-08-09
18528 | NC 2016 | K10 | Region V | Camarines Sur | 301961 | Colacling High School | Lupi | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9061461.5561 |  |  | Completed | 1
18529 | NC 2016 | K10 | Region V | Camarines Sur | 301961 | Colacling High School | Lupi | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1123254.6197 |  |  | Completed | 1
18530 | NC 2016 | SHS | Region V | Camarines Sur | 301963 | Dahat National Vocational Hs | Lagonoy | 4 | 1 | 6 | 3STY6CL | BATCH 9 CL | 9600418.359 |  |  | Completed | 1 |  |  | P00073493LZ
18531 | NC 2016 | K10 | Region V | Camarines Sur | 112778 | Dalipay Es | Milaor | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2046214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-05 | 2016-07-13 | 2016-07-26
18532 | NC 2016 | SHS | Region V | Camarines Sur | 301964 | Dalupaon National High School | Pasacao | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8514965.05 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 2016-06-05 | HGG BUILDERS & SUPPLY
18533 | NC 2016 | K10 | Region V | Camarines Sur | 309718 | Dalupaon Nhs - Tinalmud Phs Annex | Pasacao | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8614965.05 |  |  | Completed | 1
18534 | NC 2016 | K10 | Region V | Camarines Sur | 112536 | Daraga Es | Caramoan | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073465LZ | 16FF0056 |  | 2016-08-16 | 2016-08-30
18535 | NC 2016 | K10 | Region V | Camarines Sur | 112639 | Del Carmen Es | Lagonoy | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073494LZ | 16FF0059 |  | 2016-08-16 | 2016-08-30
18536 | NC 2016 | K10 | Region V | Camarines Sur | 301966 | Del Gallego National High School | Del Gallego | 1 | 1 | 20 | 2STY10CL | BATCH 9 CL | 28246882.2047 |  |  | Completed | 1
18537 | NC 2016 | K10 | Region V | Camarines Sur | 301966 | Del Gallego National High School | Del Gallego | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1133254.6197 |  |  | Completed | 1
18538 | NC 2016 | SHS | Region V | Camarines Sur | 309723 | Del Rosario National Hs | Pamplona | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6519337.64 |  |  | Completed | 1 |  |  |  |  | 2016-07-05 | 2016-07-13 | 2016-07-26
18539 | NC 2016 | SHS | Region V | Camarines Sur | 309744 | Don Mariano C. San Juan Hs | Libmanan | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6589337.64 |  |  | Completed | 1 |  |  |  |  | 2016-07-05 | 2016-07-13 | 2016-07-26
18540 | NC 2016 | K10 | Region V | Camarines Sur | 301967 | Don Mariano Gonzalvo Memorial High School | Ragay | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14153441.1023 |  |  | Completed | 1
18541 | NC 2016 | K10 | Region V | Camarines Sur | 301967 | Don Mariano Gonzalvo Memorial High School | Ragay | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6986271.4019 |  |  | Completed | 1
18542 | NC 2016 | SHS | Region V | Camarines Sur | 301969 | Don Servillano Platon Memorial Nhs | Tinambac | 4 | 1 | 12 | 2STY6CL | BATCH 13 CL | 17898494.67 |  |  | Completed | 1
18543 | NC 2016 | K10 | Region V | Camarines Sur | 309758 | Eduardo V. Agomaa National High School | Libmanan | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6529337.64 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27
18544 | NC 2016 | SHS | Region V | Camarines Sur | 301989 | Federico P. Condat Nhs (Frmerly: Maangas Hs ) | Presentacion (Parubcan) | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 9065748.78 |  |  | Completed | 1 |  |  | P00070514LZ | 16FF0046 |  | 2016-06-21 | 2016-07-05 | 2016-08-08
18545 | NC 2016 | SHS | Region V | Camarines Sur | 301974 | Gibgos National High School | Caramoan | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7614898.5421 |  |  | Completed | 1 |  |  | P00073466LZ
18546 | NC 2016 | K10 | Region V | Camarines Sur | 301975 | Goa National High School | Goa | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9361461.555 |  |  | Completed | 1
18547 | NC 2016 | K10 | Region V | Camarines Sur | 301977 | Godofredo Reyes Sr. National High School | Ragay | 1 | 1 | 12 | 2STY6CL | BATCH 9 CL | 18162923.1122 |  |  | Completed | 1
18548 | NC 2016 | K10 | Region V | Camarines Sur | 112539 | Gogon Elementary School | Caramoan | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073467LZ | 16FF0056 |  | 2016-08-16 | 2016-08-30
18549 | NC 2016 | SHS | Region V | Camarines Sur | 301950 | Gregorio Ocampo Bercasio Mhs (Frmerly: Cagliliog Hs) | Tinambac | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8780000 |  |  | Completed | 1 |  |  | P00070523LZ | 16FF0039 |  | 2016-06-21 | 2016-07-05 | 2016-08-09
18550 | NC 2016 | K10 | Region V | Camarines Sur | 301978 | Guijalo National High School | Caramoan | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6930000 |  |  | Completed | 1 |  |  | P00070509LZ | 16FF0045 |  | 2016-06-21 | 2016-07-05 | 2016-08-08
18551 | NC 2016 | K10 | Region V | Camarines Sur | 112622 | Halawig-Gogon Elementary School | Goa | 4 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2020417 |  |  | Completed | 1 |  |  | P0070526LZ | 16FF0034 |  | 2016-06-14 | 2016-06-28 | 2016-07-18 | 2016-08-01 | Grosin Const. & Supply
18552 | NC 2016 | SHS | Region V | Camarines Sur | 309721 | Huyonhuyon Hs | Tigaon | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6381638.831 |  |  | Completed | 1 |  |  | P00073535LZ
18553 | NC 2016 | K10 | Region V | Camarines Sur | 309741 | Juan L. Filipino Memorial High School | Goa | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6444716.2139 |  |  | Completed | 1 |  |  | P00073490LZ
18554 | NC 2016 | K10 | Region V | Camarines Sur | 173516 | Kinahulogan Cs | Lagonoy | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2146214.1914 |  |  | Completed | 1 |  |  | P00073495LZ | 16FF0061 |  | 2016-08-23 | 2016-09-06
18555 | NC 2016 | K10 | Region V | Camarines Sur | 112547 | Lidong Es | Caramoan | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073468LZ | 16fFF0060 |  | 2016-08-16 | 2016-08-30
18556 | NC 2016 | K10 | Region V | Camarines Sur | 112548 | Lubas Ps | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1955318.6381 |  |  | Completed | 1 |  |  | P00073469LZ
18557 | NC 2016 | K10 | Region V | Camarines Sur | 301990 | Malansad Nuevo High School | Libmanan | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8424965.05 |  |  | Completed | 1 |  |  |  |  | 2016-02-19 | 2016-02-29 | 2016-03-15 |  | 2016-06-05 | CHA CONST. AND SUPPLY
18558 | NC 2016 | K10 | Region V | Camarines Sur | 112551 | Malindog Ps | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  | P00073470LZ | 16FF0053 |  | 2016-08-16 | 2016-08-30
18559 | NC 2016 | SHS | Region V | Camarines Sur | 301993 | Mambayawas Hs | Libmanan | 2 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10910000 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27
18560 | NC 2016 | SHS | Region V | Camarines Sur | 309767 | Manangle High School | Sipocot | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9081461.5561 |  |  | Completed | 1
18561 | NC 2016 | K10 | Region V | Camarines Sur | 112802 | Manapao Es | Minalabac | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2046214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-14 | 2016-07-21 | 2016-08-04
18562 | NC 2016 | K10 | Region V | Camarines Sur | 112553 | Mandiclom Es | Caramoan | 4 | 1 | 3 | 1STY3CL | BATCH 3 CL | 3060000 |  |  | Completed | 1 |  |  | P00070525LZ | 16FF0035 |  | 2016-06-14 | 2016-06-28 | 2016-07-18 | 2016-08-03 | HRB Const.
18563 | NC 2016 | SHS | Region V | Camarines Sur | 301996 | Mansalaya National High School | Del Gallego | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9101461.5561 |  |  | Completed | 1
18564 | NC 2016 | SHS | Region V | Camarines Sur | 301996 | Mansalaya National High School | Del Gallego | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1133254.6197 |  |  | Completed | 1
18565 | NC 2016 | K10 | Region V | Camarines Sur | 302032 | Maura N. Sibulo High School | Pamplona | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8414965.05 |  |  | Completed | 1 |  |  |  |  | 2016-07-05 | 2016-07-13 | 2016-07-26
18566 | NC 2016 | K10 | Region V | Camarines Sur | 112555 | Minalaba Es | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  | P00073471LZ
18567 | NC 2016 | SHS | Region V | Camarines Sur | 302000 | Minalabac Nhs | Minalabac | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8364965.05 |  |  | Completed | 1
18568 | NC 2016 | K10 | Region V | Camarines Sur | 302001 | Nabua National High School | Nabua | 5 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
18569 | NC 2016 | SHS | Region V | Camarines Sur | 309715 | Nato National High School | Sagñay | 4 | 1 | 12 | 2STY6CL | BATCH 13 CL | 17190000 |  |  | Completed | 1
18570 | NC 2016 | SHS | Region V | Camarines Sur | 309745 | Northern Plain Hs | Libmanan | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6589337.64 |  |  | Completed | 1 |  |  |  |  | 2016-07-05 | 2016-07-13 | 2016-07-26
18571 | NC 2016 | K10 | Region V | Camarines Sur | 112645 | Olas Es | Lagonoy | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2948000 |  |  | Completed | 1 |  |  | P00073496LZ | 16FF0059 |  | 2016-08-16 | 2016-08-30
18572 | NC 2016 | K10 | Region V | Camarines Sur | 302008 | Oring National High School | Caramoan | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7245000 |  |  | Completed | 1 |  |  | P00073472LZ
18573 | NC 2016 | K10 | Region V | Camarines Sur | 112689 | Padlos Es | Libmanan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2046214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-14 | 2016-07-21 | 2016-08-04
18574 | NC 2016 | K10 | Region V | Camarines Sur | 309765 | Pag-Oring Nuevo National Hs | Libmanan | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6589337.64 |  |  | Completed | 1 |  |  |  |  | 2016-02-19 | 2016-02-29 | 2016-03-15 |  | 2016-06-05 | R.K.X ODIAMAR CONST.
18575 | NC 2016 | K10 | Region V | Camarines Sur | 112911 | Pasacao Cs | Pasacao | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6356887.0226 |  |  | Completed | 1 |  |  |  |  | 2016-02-19 | 2016-02-29 | 2016-03-15 |  | 2016-05-31 | PHIL MANNA CONST. AND SUPPLY
18576 | NC 2016 | SHS | Region V | Camarines Sur | 309769 | Pasacao Municipal High School | Pasacao | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8404965.05 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 2016-06-05 | E.P.L. GENERAL CONST. & SUPPLY
18577 | NC 2016 | K10 | Region V | Camarines Sur | 112896 | Pili Elementary School | Presentacion (Parubcan) | 4 | 1 | 3 | 1STY3CL | BATCH 3 CL | 3035610 |  |  | Completed | 1 |  |  | P00070528LZ | 16FF0035 |  | 2016-06-14 | 2016-06-28 | 2016-07-18 | 2016-08-03 | HRB Const.
18578 | NC 2016 | K10 | Region V | Camarines Sur | 112563 | Pili-Centro Ps | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1955318.6381 |  |  | Completed | 1 |  |  | P00073473LZ
18579 | NC 2016 | SHS | Region V | Camarines Sur | 301976 | Pinaglabanan High School | Goa | 4 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9071461.5561 |  |  | Completed | 1 |  |  | P00073488LZ
18580 | NC 2016 | SHS | Region V | Camarines Sur | 301976 | Pinaglabanan High School | Goa | 4 |  | 1 | 1STY1CL | BATCH 9 CL | 1142329 |  |  | Completed | 1 |  |  | P00073488LZ
18581 | NC 2016 | SHS | Region V | Camarines Sur | 302019 | Presentacion Nhs (Formerly:Pili Nhs) | Presentacion (Parubcan) | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9324965.84 |  |  | Completed | 1
18582 | NC 2016 | K10 | Region V | Camarines Sur | 309764 | R.T. Subastil Memorial Hs | Milaor | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6529337.64 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27
18583 | NC 2016 | K10 | Region V | Camarines Sur | 302020 | Ragay National Agricultural And Fisheries School (Rnafs) | Ragay | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14153441.1023 |  |  | Completed | 1
18584 | NC 2016 | K10 | Region V | Camarines Sur | 302020 | Ragay National Agricultural And Fisheries School (Rnafs) | Ragay | 1 |  | 3 | 1STY1CL | BATCH 9 CL | 3399763.8591 |  |  | Completed | 1
18585 | NC 2016 | K10 | Region V | Camarines Sur | 309714 | Sagñay Southeastern Hs | Sagñay | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6480000 |  |  | Completed | 1 |  |  | P00070516LZ | 16FF0048 |  | 2016-06-28 | 2016-07-12 | 2016-08-15
18586 | NC 2016 | K10 | Region V | Camarines Sur | 309714 | Sagñay Southeastern Hs | Sagñay | 4 |  | 6 | 2STY6CL | BATCH 3 CL | 8404000 |  |  | Completed | 1 |  |  | P00070516LZ | 16FF0048 |  | 2016-06-28 | 2016-07-12 | 2016-08-15
18587 | NC 2016 | SHS | Region V | Camarines Sur | 302023 | Sagrada Nhs, Tinambac | Tinambac | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6465703.8928 |  |  | Completed | 1 |  |  | P00073538LZ
18588 | NC 2016 | K10 | Region V | Camarines Sur | 112605 | Sagrada Ps | Garchitorena | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073485LZ | 16FF0058 |  | 2016-08-16 | 2016-08-30
18589 | NC 2016 | K10 | Region V | Camarines Sur | 112717 | Salvacion Es | Libmanan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27
18590 | NC 2016 | K10 | Region V | Camarines Sur | 112913 | Salvacion Es | Pasacao | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-07-14 | 2016-07-21 | 2016-08-04
18591 | NC 2016 | K10 | Region V | Camarines Sur | 309770 | San Pablo Integrated School | Libmanan | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6529337.64 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 2016-05-31 | E.P.L. GENERAL CONST. & SUPPLY
18592 | NC 2016 | K10 | Region V | Camarines Sur | 112807 | San Antonio Es | Minalabac | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 2016-05-31 | E.P.L. GENERAL CONST. & SUPPLY
18593 | NC 2016 | K10 | Region V | Camarines Sur | 112914 | San Antonio Es | Pasacao | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-07-14 | 2016-07-21 | 2016-08-04
18594 | NC 2016 | K10 | Region V | Camarines Sur | 112567 | San Francisco Es | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2146214.1914 |  |  | Completed | 1 |  |  | P00073474LZ | 16FF0057 |  | 2016-08-16 | 2016-08-30
18595 | NC 2016 | K10 | Region V | Camarines Sur | 113010 | San Joaquin Es | San Fernando | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1
18596 | NC 2016 | K10 | Region V | Camarines Sur | 112809 | San Jose - Annex Ps | Minalabac | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27
18597 | NC 2016 | SHS | Region V | Camarines Sur | 302036 | San Jose Nhs | San Jose | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8684965 |  |  | Completed | 1
18598 | NC 2016 | K10 | Region V | Camarines Sur | 302037 | San Juan National Hs | Libmanan | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8424965.05 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27
18599 | NC 2016 | SHS | Region V | Camarines Sur | 302038 | San Rafael National High School | Tigaon | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8950197.9 |  |  | Completed | 1
18600 | NC 2016 | SHS | Region V | Camarines Sur | 302039 | San Ramon Pilot Nhs, Lagonoy (Frmerly:Sn.Ramon Pilot Hs) | Lagonoy | 4 | 1 | 6 | 2STY6CL | BATCH 9 CL | 15026937.0918 |  |  | Completed | 1 |  |  | P00073497LZ
18601 | NC 2016 | SHS | Region V | Camarines Sur | 302039 | San Ramon Pilot Nhs, Lagonoy (Frmerly:Sn.Ramon Pilot Hs) | Lagonoy | 4 |  | 4 | 2STY4CL |  |  |  |  | Completed | 1
18602 | NC 2016 | K10 | Region V | Camarines Sur | 302042 | San Ramon Provincial High School | Tinambac | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6781000 |  |  | Completed | 1 |  |  | P00070524LZ | 16FF0039 |  | 2016-06-21 | 2016-07-05 | 2016-08-09
18603 | NC 2016 | K10 | Region V | Camarines Sur | 302046 | Sinuknipan National High School | Del Gallego | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13972542.8037 |  |  | Completed | 1
18604 | NC 2016 | K10 | Region V | Camarines Sur | 302046 | Sinuknipan National High School | Del Gallego | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1133254.6197 |  |  | Completed | 1
18605 | NC 2016 | SHS | Region V | Camarines Sur | 302047 | Sipocot Nhs | Sipocot | 1 | 1 | 30 | 2STY10CL | BATCH 1 CL | 39063930.2791 |  |  | Completed | 1
18606 | NC 2016 | SHS | Region V | Camarines Sur | 301930 | Sisa Feliciano Mhs | Ragay | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14153441.1023 |  |  | Completed | 1
18607 | NC 2016 | SHS | Region V | Camarines Sur | 301930 | Sisa Feliciano Mhs | Ragay | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1133254.6197 |  |  | Completed | 1
18608 | NC 2016 | K10 | Region V | Camarines Sur | 112720 | Sogod Es | Libmanan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27
18609 | NC 2016 | K10 | Region V | Camarines Sur | 112569 | Sta. Cruz Es | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2176214.1914 |  |  | Completed | 1 |  |  | P00073475LZ | 16FF0057 |  | 2016-08-16 | 2016-08-30
18610 | NC 2016 | K10 | Region V | Camarines Sur | 112608 | Sumaoy Es | Garchitorena | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073486LZ | 16FF0058 |  | 2016-08-16 | 2016-08-30
18611 | NC 2016 | K10 | Region V | Camarines Sur | 302055 | Tabgon Nhs, Caramoan | Caramoan | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8900000 |  |  | Completed | 1 |  |  | P00070510LZ | 16FF0045 |  | 2016-06-21 | 2016-07-05 | 2016-08-08
18612 | NC 2016 | K10 | Region V | Camarines Sur | 112571 | Tabiguian Es | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  | P00073476LZ | 16FF0057 |  | 2016-08-16 | 2016-08-30
18613 | NC 2016 | K10 | Region V | Camarines Sur | 112572 | Tabog Es | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  | P00073477LZ | 16FF0057 |  | 2016-08-16 | 2016-08-30
18614 | NC 2016 | SHS | Region V | Camarines Sur | 302029 | Tinawagan Nhs | Tigaon | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 9072000 |  |  | Completed | 1 |  |  | P00070519LZ | 16FF0042 |  | 2016-06-21 | 2016-07-05 | 2016-07-18 | 2016-08-07 | ZKR Construction & Supply
18615 | NC 2016 | K10 | Region V | Camarines Sur | 302064 | Tomas A. Andaya Sr. National High School | Ragay | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14153441.1023 |  |  | Completed | 1
18616 | NC 2016 | K10 | Region V | Camarines Sur | 302064 | Tomas A. Andaya Sr. National High School | Ragay | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 9093461.5561 |  |  | Completed | 1
18617 | NC 2016 | K10 | Region V | Camarines Sur | 302064 | Tomas A. Andaya Sr. National High School | Ragay | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1133254.6197 |  |  | Completed | 1
18618 | NC 2016 | SHS | Region V | Camarines Sur | 309771 | Villafuerte-Peña High School | San Jose | 4 | 1 | 12 | 2STY6CL | BATCH 3 CL | 17369930 |  |  | Completed | 1 |  |  | P00070518LZ | 16FF0043 |  | 2016-06-21 | 2016-07-05 | 2016-08-05
18619 | NC 2016 | K10 | Region V | Camarines Sur | 302068 | Villazar National High School | Sipocot | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14133441.1023 |  |  | Completed | 1
18620 | NC 2016 | K10 | Region V | Camarines Sur | 302068 | Villazar National High School | Sipocot | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6976271.4019 |  |  | Completed | 1
18621 | NC 2016 | K10 | Region V | Camarines Sur | 302068 | Villazar National High School | Sipocot | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1128254.6197 |  |  | Completed | 1
18622 | NC 2016 | SHS | Region V | Camarines Sur | 309740 | Visita De Salog Hs | Goa | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6444641.316 |  |  | Completed | 1 |  |  | P00073490LZ
18623 | NC 2016 | SHS | Region V | Catanduanes | 302074 | Bato Rural Dhs | Bato | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 14033442.099 |  |  | Completed | 1
18624 | NC 2016 | SHS | Region V | Catanduanes | 302082 | Caramoran School Of Fisheries | Caramoran | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 11693844.661 |  |  | Completed | 1
18625 | NC 2016 | SHS | Region V | Catanduanes | 302083 | Catanduanes Nhs | Virac (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198180.297 |  |  | Completed | 1
18626 | NC 2016 | SHS | Region V | Catanduanes | 302094 | Pandan Sat | Pandan | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 39225883.854 |  |  | Completed | 1
18627 | NC 2016 | K10 | Region V | Catanduanes | 302096 | San Andres Vocational School | San Andres (Calolbon) | 0 | 1 | 18 | 3STY18CL | BATCH 9 CL | 44059741.754 |  |  | Completed | 1
18628 | NC 2016 | SHS | Region V | Catanduanes | 302107 | Viga Rural Dhs | Viga | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 14088442.099 |  |  | Completed | 1
18629 | NC 2016 | SHS | Region V | Iriga City | 500167 | Cristo Rey Is | Iriga City | 5 | 1 | 5 | 1STY5CL | BATCH 9 CL | 4700731.4693 |  |  | Completed | 1
18630 | NC 2016 | K10 | Region V | Iriga City | 114453 | Iriga City Division Integrated Special School (Sped) To Santiago Is | Iriga City | 5 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6635102.46 |  |  | Completed | 1
18631 | NC 2016 | SHS | Region V | Iriga City | 302249 | Perpetual Help Nhs | Iriga City | 5 | 1 | 12 | 3STY12CL | BATCH 5 CL | 18222268.79 |  |  | Completed | 1
18632 | NC 2016 | SHS | Region V | Iriga City | 302252 | Sagrada Nhs | Iriga City | 5 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6635102.46 |  |  | Completed | 1
18633 | NC 2016 | TECHVOC | Region V | Iriga City | 302252 | Sagrada Nhs | Iriga City | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2565263.64 |  |  | Completed | 1
18634 | NC 2016 | K10 | Region V | Iriga City | 114422 | San Agustin Es | Iriga City | 5 | 1 | 18 | 3STY9CL | BATCH 9 CL | 27248390.256 |  |  | Completed | 1
18635 | NC 2016 | SHS | Region V | Iriga City | 302254 | San Antonio Nhs | Iriga City | 5 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.6381 |  |  | Completed | 1
18636 | NC 2016 | TECHVOC | Region V | Iriga City | 302254 | San Antonio Nhs | Iriga City | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2565263.64 |  |  | Completed | 1
18637 | NC 2016 | SHS | Region V | Iriga City | 302255 | San Pedro Nhs | Iriga City | 5 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1945386.46 |  |  | Completed | 1
18638 | NC 2016 | K10 | Region V | Iriga City | 114438 | San Ramon Es | Iriga City | 5 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1945386.46 |  |  | Completed | 1
18639 | NC 2016 | SHS | Region V | Iriga City | 302250 | Sta. Maria Hs | Iriga City | 5 | 1 | 6 | 3STY6CL | BATCH 3 CL | 10692131.51 |  |  | Completed | 1
18640 | NC 2016 | TECHVOC | Region V | Iriga City | 302250 | Sta. Maria Hs | Iriga City | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2565263.64 |  |  | Completed | 1
18641 | NC 2016 | SHS | Region V | Iriga City | 302256 | Sto. Niño Nhs | Iriga City | 5 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6635102.46 |  |  | Completed | 1
18642 | NC 2016 | SHS | Region V | Legaspi City | 310201 | Arimbay High School | Legazpi City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936272.404 |  |  | Completed | 1
18643 | NC 2016 | SHS | Region V | Legaspi City | 302257 | Banquerohan Nhs | Legazpi City (Capital) | 2 | 1 | 18 | 2STY6CL | BATCH 7 CL | 25660155.15 |  |  | Completed | 1
18644 | NC 2016 | TECHVOC | Region V | Legaspi City | 302257 | Banquerohan Nhs | Legazpi City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2444549.27 |  |  | Completed | 1
18645 | NC 2016 | SHS | Region V | Legaspi City | 302262 | Gogon High School | Legazpi City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11443844.661 |  |  | Completed | 1
18646 | NC 2016 | SHS | Region V | Legaspi City | 302262 | Gogon High School | Legazpi City (Capital) | 2 |  | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1
18647 | NC 2016 | SHS | Region V | Legaspi City | 302259 | Homapon High School | Legazpi City (Capital) | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13260088.91 |  |  | Completed | 1
18648 | NC 2016 | TECHVOC | Region V | Legaspi City | 302259 | Homapon High School | Legazpi City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2444549.27 |  |  | Completed | 1
18649 | NC 2016 | SHS | Region V | Legaspi City | 114475 | Legaspi City Hs To Bitano Es | Legazpi City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6670639.14 |  |  | Completed | 1
18650 | NC 2016 | SHS | Region V | Legaspi City | 114474 | Maslog National High School To Taysan Es | Legazpi City (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8553385.05 |  |  | Completed | 1
18651 | NC 2016 | K10 | Region V | Legaspi City | 302261 | Pag-Asa National High School | Legazpi City (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1
18652 | NC 2016 | SHS | Region V | Legaspi City | 302263 | Pawa High School | Legazpi City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6670639.14 |  |  | Completed | 1
18653 | NC 2016 | K10 | Region V | Legaspi City | 114483 | Puro Elementary School | Legazpi City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11443844.661 |  |  | Completed | 1
18654 | NC 2016 | SHS | Region V | Legaspi City | 310204 | Taysan Resettlement Integrated School | Legazpi City (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021462.555 |  |  | Completed | 1
18655 | NC 2016 | K10 | Region V | Ligao City | 301838 | Bacong Hs | City Of Ligao | 3 | 1 | 20 | 2STY20CL | BATCH 1 CL | 30521475.67 |  |  | Completed | 1 |  |  | P00070100LZ | 17FO0063 | 2017-09-08 | 2017-09-15 | 2017-10-26 | 2017-10-30 | 2017-11-16 | HERBANA BUILDERS & SUPPLY
18656 | NC 2016 | TECHVOC | Region V | Ligao City | 301838 | Bacong Hs | City Of Ligao | 3 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 8123309.93 |  |  | Completed | 1 |  |  | P00070208LZ | 16FO0056 | 2016-07-06 | 2016-07-14 | 2016-07-26 | 2016-08-11 | 2016-08-30 | WATERTON CONST. & REALTY CORP
18657 | NC 2016 | K10 | Region V | Ligao City | 111813 | Basag Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1054558.55 |  |  | Completed | 1 |  |  | P00071052LZ | 16FO0054 | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-28 | 2016-08-08 | GROSIN CONSTRUCTION & SUPPLY
18658 | NC 2016 | SHS | Region V | Ligao City | 301814 | Bicol Regional Science Hs | City Of Ligao | 3 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 |  |  | P00071062LZ | 16FO0073 | 2016-08-22 | 2016-08-30 | 2016-09-19 | 2016-10-06 | 2016-10-14 | AVIC CONST. & SUPPLY
18659 | NC 2016 | SHS | Region V | Ligao City | 301817 | Cabarian Nhs | City Of Ligao | 3 | 1 | 15 | 3STY15CL | BATCH 5 CL | 23011987.88 |  |  | Completed | 1 |  |  | P00071063LZ | 16FO0086 | 2016-10-26 | 2016-11-03 | 2016-11-15 | 2017-01-09 | 2017-02-06 | ELKAN KONSTRAK & DEV'T. CORP.
18660 | NC 2016 | TECHVOC | Region V | Ligao City | 301817 | Cabarian Nhs | City Of Ligao | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 5122706.62 |  |  | Completed | 1 |  |  | P00071671LZ | 16FO0059 | 2016-07-06 | 2016-07-14 | 2016-07-26 | 2016-08-12 | 2016-08-26 | AVIC CONST. & SUPPLY
18661 | NC 2016 | K10 | Region V | Ligao City | 111839 | Catburawan Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1120558.55 |  |  | Completed | 1 |  |  | P00073552LZ | 16FO0066 | 2016-07-27 | 2016-08-04 | 2016-08-16 | 2016-09-03 | 2016-09-16 | EMRA CONST. & SUPPLY
18662 | NC 2016 | TECHVOC | Region V | Ligao City | 301820 | Deogracias P. Princesa Memorial Hs | City Of Ligao | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2463603.31 |  |  | Completed | 1 |  |  | P00074508LZ | 16FOO0061 | 2016-07-06 | 2016-07-14 | 2016-07-26 | 2016-08-12 | 2016-08-26 | GROSIN CONST. & SUPPLY
18663 | NC 2016 | K10 | Region V | Ligao City | 301820 | Deogracias P. Princesa Memorial Hs | City Of Ligao | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18422268.79 |  |  | Completed | 1 |  |  | P00073553LZ | 17FO0064 | 2016-07-21 | 2016-07-29 | 2016-08-10 | 2016-08-26 | 2016-09-07 | HERBANA BUILDERS & SUPPLY
18664 | NC 2016 | K10 | Region V | Ligao City | 111819 | Herrera Es | City Of Ligao | 3 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1902266.47 |  |  | Completed | 1 |  |  | P00071053LZ | 16FO0072 | 2016-08-22 | 2016-08-30 | 2016-09-13 | 2016-09-29 | 2016-10-13 | NGS CONST. & SUPPLY
18665 | NC 2016 | K10 | Region V | Ligao City | 321701 | Ligao City National Technical -Vocational High School | City Of Ligao | 3 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8753465.051 |  |  | Completed | 1 |  |  | P00070096LZ | 16FO0036 | 2016-03-31 | 2016-04-08 | 2016-04-12 | 2016-05-23 | 2016-06-02 | ALXM CONST.
18666 | NC 2016 | TECHVOC | Region V | Ligao City | 321701 | Ligao City National Technical -Vocational High School | City Of Ligao | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 5208206.62 |  |  | Completed | 1 |  |  | P00070205LZ | 16FOO0058 | 2016-07-06 | 2016-07-14 | 2016-07-26 | 2016-08-11 | 2016-08-26 | EMRA CONST. & SUPPLY
18667 | NC 2016 | SHS | Region V | Ligao City | 301837 | Ligao Nhs | City Of Ligao | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00073554LZ | 17FO0067 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-12 | 2017-10-30 | HI-TONE CONST. & DEV'T. CORP.
18668 | NC 2016 | SHS | Region V | Ligao City | 301837 | Ligao Nhs | City Of Ligao | 3 |  | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 |  |  | P00073555LZ | 17FO0068 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-12 | 2017-10-30 | WCS CONST. & SUPPLY
18669 | NC 2016 | SHS | Region V | Ligao City | 301837 | Ligao Nhs | City Of Ligao | 3 |  | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00073556LZ | 17FO0066 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-12 | 2017-10-30 | PEDXING BUILDERS
18670 | NC 2016 | K10 | Region V | Ligao City | 111844 | Ligao West Ces (Binatagan) | Ligao City | 3 | 1 | 30 | 3STY15CL | BATCH 11 CL | 43066026.9 |  |  | Completed | 1 |  |  | P00074832LZ | 16FO0087 | 2016-10-26 | 2016-11-03 | 2016-11-15 | 2017-02-07 | 2017-02-23 | HI-TONE CONST. & DEV'T. CORP.
18671 | NC 2016 | K10 | Region V | Ligao City | 111845 | Mahaba Es | City Of Ligao | 3 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6374451.05 |  |  | Completed | 1 |  |  | P00071059LZ | 16FO0071 | 2016-08-22 | 2016-08-30 | 2016-09-13 | 2016-09-29 | 2016-10-13 | QDC CONST. & SUPPLY
18672 | NC 2016 | K10 | Region V | Ligao City | 111845 | Mahaba Es | City Of Ligao | 3 |  | 8 | 2STY8CL | BATCH 5 CL | 11513897.03 |  |  | Completed | 1 |  |  | P00071060LZ | 16FO0070 | 2016-08-22 | 2016-08-30 | 2016-09-13 | 2016-09-29 | 2016-10-13 | ATHENA CONST. & DEV'T.
18673 | NC 2016 | K10 | Region V | Ligao City | 231008 | Malama Es, Bagacay Ext. | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1126058.55 |  |  | Completed | 1 |  |  | P00071061LZ | 16FO0065 | 2016-07-21 | 2016-07-29 | 2016-08-10 | 2016-08-26 | 2016-09-07 | EMRA CONST. & SUPPLY
18674 | NC 2016 | SHS | Region V | Ligao City | 301858 | Oma-Oma Nhs | City Of Ligao | 3 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8980471.77 |  |  | Completed | 1 |  |  | P00070097LZ | 16FO0060 | 2016-07-06 | 2016-07-14 | 2016-07-26 | 2016-08-12 | 2016-08-25 | ZKR CONST. & SUPPLY
18675 | NC 2016 | TECHVOC | Region V | Ligao City | 301858 | Oma-Oma Nhs | City Of Ligao | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2743603.31 |  |  | Completed | 1 |  |  | P00070206LZ | 16FO0067 | 2016-07-27 | 2016-08-04 | 2016-08-16 | 2016-09-05 | 2016-09-19 | AVIC CONST. & SUPPLY
18676 | NC 2016 | K10 | Region V | Ligao City | 111826 | Paulba Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1105558.55 |  |  | Completed | 1 |  |  | P00071054LZ | 16FO0064 | 2016-07-21 | 2016-07-29 | 2016-08-10 | 2016-08-26 | 2016-09-07 | EMRA CONST. & SUPPLY
18677 | NC 2016 | SHS | Region V | Ligao City | 301862 | Paulba Nhs | City Of Ligao | 3 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11736897.03 |  |  | Completed | 1 |  |  | P00070485LZ | 16FO0075 | 2016-09-07 | 2016-09-15 | 2016-09-27 | 2016-10-11 | 2016-10-24 | MAKAPA CORP.
18678 | NC 2016 | SHS | Region V | Ligao City | 301862 | Paulba Nhs | City Of Ligao | 3 |  | 12 | 2STY6CL | BATCH 3 CL | 16894943.54 |  |  | Completed | 1 |  |  | P00070486LZ | 16FO0076 | 2016-09-07 | 2016-09-15 | 2016-09-27 | 2016-10-11 | 2016-10-24 | WCS CONST. INC
18679 | NC 2016 | K10 | Region V | Ligao City | 111828 | Pinamaniquian Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1095558.55 |  |  | Completed | 1 |  |  | P00071055LZ | 16FO0063 | 2016-07-21 | 2016-07-29 | 2016-08-10 | 2016-08-26 | 2016-09-07 | HERBANA BUILDERS & SUPPLY
18680 | NC 2016 | K10 | Region V | Ligao City | 111829 | Tambo Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1054558.55 |  |  | Completed | 1 |  |  | P00071056LZ | 16FO0055 | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-28 | 2016-08-28 | GROSIN CONST. & SUPPLY
18681 | NC 2016 | K10 | Region V | Ligao City | 111832 | Tiongson Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1126058.55 |  |  | Completed | 1 |  |  | P00071057LZ | 16FO0053 | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-28 | 2016-08-28 | GROSIN CONST. & SUPPLY
18682 | NC 2016 | K10 | Region V | Ligao City | 111833 | Tupas Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1126058.55 |  |  | Completed | 1 |  |  | P00071058LZ | 16FO0062 | 2016-07-21 | 2016-07-29 | 2016-08-10 | 2016-10-26 | 2016-09-07 | EMRA CONST. & SUPPLY
18683 | NC 2016 | SHS | Region V | Masbate | 302121 | Buenavista National High School | Uson | 3 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8567395.36 |  |  | Completed | 1
18684 | NC 2016 | SHS | Region V | Masbate | 302129 | Cataingan National High School | Cataingan | 3 | 1 | 30 | 2STY10CL | BATCH 9 CL | 38562931.8577 |  |  | Completed | 1
18685 | NC 2016 | SHS | Region V | Masbate | 302131 | Del Carmen National High School | Uson | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9056462.555 |  |  | Completed | 1
18686 | NC 2016 | SHS | Region V | Masbate | 302131 | Del Carmen National High School | Uson | 3 |  | 12 | 2STY12CL | BATCH 9 CL | 15872795.92 |  |  | Completed | 1
18687 | NC 2016 | SHS | Region V | Masbate | 302129 | Del Carmen National High School To Catingan Nhs | Uson | 3 |  | 8 | 2STY8CL | BATCH 9 CL | 11883466.88 |  |  | Completed | 1
18688 | NC 2016 | SHS | Region V | Masbate | 302132 | Dimasalang National High School | Dimasalang | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6334066.1721 |  |  | Completed | 1
18689 | NC 2016 | SHS | Region V | Masbate | 302132 | Dimasalang National High School | Dimasalang | 3 |  | 18 | 2STY6CL | BATCH 9 CL | 25642186.08 |  |  | Completed | 1
18690 | NC 2016 | SHS | Region V | Masbate | 309914 | Mayor Tomas V. Rivera Memorial High School | Cawayan | 3 | 1 | 20 | 2STY4CL | BATCH 3 CL | 32962868.01 |  |  | Completed | 1
18691 | NC 2016 | K10 | Region V | Masbate | 309942 | San Carlos Nhs | Palanas | 3 | 1 | 6 | 1STY3CL | BATCH 9 CL | 5869821.8728 |  |  | Completed | 1
18692 | NC 2016 | SHS | Region V | Masbate | 302171 | Santos E. Conag National High School | Esperanza | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22847878.13 |  |  | Completed | 1
18693 | NC 2016 | SHS | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | Uson | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8559395.36 |  |  | Completed | 1
18694 | NC 2016 | SHS | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | Uson | 3 |  | 6 | 2STY6CL | BATCH 9 CL | 8562395.36 |  |  | Completed | 1
18695 | NC 2016 | SHS | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | Uson | 3 |  | 4 | 2STY4CL | BATCH 9 CL | 6582573.6 |  |  | Completed | 1
18696 | NC 2016 | TECHVOC | Region V | Masbate City | 321803 | A. Delos Reyes Integrated School | City Of Masbate (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2567708.3333 |  |  | Completed | 1
18697 | NC 2016 | TECHVOC | Region V | Masbate City | 321805 | Bantigue High School | City Of Masbate (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2536458.3333 |  |  | Completed | 1
18698 | NC 2016 | TECHVOC | Region V | Masbate City | 321804 | Bayombon High School | City Of Masbate (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2557291.6667 |  |  | Completed | 1
18699 | NC 2016 | TECHVOC | Region V | Masbate City | 302133 | Capitolina O. Legaspi Mhs | City Of Masbate (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2536458.3333 |  |  | Completed | 1
18700 | NC 2016 | SHS | Region V | Masbate City | 302148 | Masbate National Comprehensive High School | City Of Masbate (Capital) | 2 | 1 | 15 | 3STY15CL | BATCH 11 CL | 21650000 |  |  | Completed | 1
18701 | NC 2016 | SHS | Region V | Masbate City | 302148 | Masbate National Comprehensive High School | City Of Masbate (Capital) | 2 |  | 9 | 3STY9CL | BATCH 11 CL | 15150000 |  |  | Completed | 1
18702 | NC 2016 | SHS | Region V | Masbate City | 302148 | Masbate National Comprehensive High School | City Of Masbate (Capital) | 2 |  | 8 | 2STY8CL | BATCH 11 CL | 11950076.849 |  |  | Completed | 1
18703 | NC 2016 | TECHVOC | Region V | Masbate City | 321806 | Nursery High School | City Of Masbate (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
18704 | NC 2016 | SHS | Region V | Naga City | 302264 | Camarines Sur National High School | Naga City | 3 | 1 | 48 | 4STY24CL | BATCH 11 CL | 71192514.28 |  |  | Completed | 1
18705 | NC 2016 | SHS | Region V | Naga City | 302265 | Cararayan National High School | Naga City | 3 | 1 | 12 | 2STY6CL | BATCH 9 CL | 17300000 |  |  | Completed | 1
18706 | NC 2016 | TECHVOC | Region V | Naga City | 302265 | Cararayan National High School | Naga City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1
18707 | NC 2016 | SHS | Region V | Naga City | 302268 | Naga City Science High School | Naga City | 3 | 1 | 9 | 3STY9CL | BATCH 9 CL | 14150000 |  |  | Completed | 1
18708 | NC 2016 | SHS | Region V | Naga City | 310301 | Tinago National High School | Naga City | 3 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8650000 |  |  | Completed | 1
18709 | NC 2016 | SHS | Region V | Sorsogon | 302179 | Abucay Nhs | Pilar | 1 | 1 | 8 | 2STY8CL | BATCH 11 CL | 12379170.5527 |  |  | Completed | 1
18710 | NC 2016 | SHS | Region V | Sorsogon | 302179 | Abucay Nhs | Pilar | 1 |  | 4 | 2STY4CL | BATCH 11 CL | 7365365.1077 |  |  | Completed | 1
18711 | NC 2016 | K10 | Region V | Sorsogon | 114137 | Alin Elementary School | Donsol | 1 | 1 | 6 | 1STY3CL | BATCH 13 CL | 5605184.88 |  |  | Completed | 1
18712 | NC 2016 | K10 | Region V | Sorsogon | 114137 | Alin Elementary School | Donsol | 1 |  | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
18713 | NC 2016 | SHS | Region V | Sorsogon | 302183 | Bagatao Nhs | Magallanes (34 Brgys) | 1 | 1 | 4 | 1STY4CL | BATCH 11 CL | 3811375.2325 |  |  | Completed | 1
18714 | NC 2016 | K10 | Region V | Sorsogon | 114338 | Banuyo Es | Pilar | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1974900.8435 |  |  | Completed | 1
18715 | NC 2016 | K10 | Region V | Sorsogon | 114274 | Behia Elementary School | Magallanes (34 Brgys) | 1 | 1 | 6 | 1STY3CL | BATCH 13 CL | 6133350.5048 |  |  | Completed | 1
18716 | NC 2016 | K10 | Region V | Sorsogon | 114275 | Biga Es | Magallanes (34 Brgys) | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2120080.0574 |  |  | Completed | 1
18717 | NC 2016 | SHS | Region V | Sorsogon | 310007 | Biton High School | Magallanes (34 Brgys) | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6319337.6381 |  |  | Completed | 1
18718 | NC 2016 | SHS | Region V | Sorsogon | 302199 | Buenavista Nhs | Castilla | 1 | 1 | 6 | 2STY6CL | BATCH 11 CL | 9021461.555 |  |  | Completed | 1
18719 | NC 2016 | K10 | Region V | Sorsogon | 114366 | Cabiguan Es | Pilar | 1 | 1 | 4 | 1STY2CL | BATCH 13 CL | 3986096.4904 |  |  | Completed | 1
18720 | NC 2016 | SHS | Region V | Sorsogon | 302194 | Cabugao Nhs | Donsol | 1 | 1 | 6 | 1STY3CL | BATCH 11 CL | 6782273.7048 |  |  | Completed | 1
18721 | NC 2016 | SHS | Region V | Sorsogon | 302221 | Cagbolo National Vocational Hs | Magallanes (34 Brgys) | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6936271.4019 |  |  | Completed | 1
18722 | NC 2016 | K10 | Region V | Sorsogon | 114082 | Casay Es | Casiguran | 1 | 1 | 6 | 1STY3CL | BATCH 13 CL | 5605184.88 |  |  | Completed | 1
18723 | NC 2016 | K10 | Region V | Sorsogon | 114082 | Casay Es | Casiguran | 1 |  | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
18724 | NC 2016 | SHS | Region V | Sorsogon | 302197 | Casiguran Technical Vocational School | Casiguran | 1 | 1 | 32 | 2STY8CL | BATCH 13 CL | 43509370.3668 |  |  | Completed | 1
18725 | NC 2016 | K10 | Region V | Sorsogon | 114370 | Comapo-Capo Es | Pilar | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
18726 | NC 2016 | K10 | Region V | Sorsogon | 114122 | Cumadcad Cs | Castilla | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1974900.8435 |  |  | Completed | 1
18727 | NC 2016 | SHS | Region V | Sorsogon | 302201 | Cumadcad Nhs | Castilla | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.051 |  |  | Completed | 1
18728 | NC 2016 | SHS | Region V | Sorsogon | 302201 | Cumadcad Nhs | Castilla | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.6381 |  |  | Completed | 1
18729 | NC 2016 | K10 | Region V | Sorsogon | 114372 | Del Rosario Es | Pilar | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.051 |  |  | Completed | 1
18730 | NC 2016 | SHS | Region V | Sorsogon | 302206 | Donsol National Comprehensive Hs - Sta. Cruz Extension Hs | Donsol | 1 | 1 | 6 | 2STY6CL | BATCH 11 CL | 9021461.5561 |  |  | Completed | 1
18731 | NC 2016 | SHS | Region V | Sorsogon | 302207 | Donsol Vocational Hs | Donsol | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 17217313.8288 |  |  | Completed | 1
18732 | NC 2016 | K10 | Region V | Sorsogon | 114146 | Gura Elementary School | Donsol | 1 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1
18733 | NC 2016 | K10 | Region V | Sorsogon | 114294 | Lapinig Es | Magallanes (34 Brgys) | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2029343.0487 |  |  | Completed | 1
18734 | NC 2016 | K10 | Region V | Sorsogon | 114349 | Lumbang Es | Pilar | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
18735 | NC 2016 | K10 | Region V | Sorsogon | 302222 | Magallanes National High School | Magallanes (34 Brgys) | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.5917 |  |  | Completed | 1
18736 | NC 2016 | SHS | Region V | Sorsogon | 302220 | Magallanes National Vocational Hs | Magallanes (34 Brgys) | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1
18737 | NC 2016 | K10 | Region V | Sorsogon | 114352 | Marifosque Es | Pilar | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
18738 | NC 2016 | K10 | Region V | Sorsogon | 114126 | Mayon Es | Castilla | 1 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1
18739 | NC 2016 | K10 | Region V | Sorsogon | 302226 | Mayon National High School | Castilla | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1
18740 | NC 2016 | K10 | Region V | Sorsogon | 114149 | Ogod Es | Donsol | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.051 |  |  | Completed | 1
18741 | NC 2016 | K10 | Region V | Sorsogon | 114149 | Ogod Es | Donsol | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.6381 |  |  | Completed | 1
18742 | NC 2016 | SHS | Region V | Sorsogon | 302229 | Palanas Nhs | Pilar | 1 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8376264.352 |  |  | Completed | 1
18743 | NC 2016 | SHS | Region V | Sorsogon | 302230 | Pilar National Comprehensive Hs | Pilar | 1 | 1 | 10 | 2STY10CL | BATCH 11 CL | 13149949.3958 |  |  | Completed | 1
18744 | NC 2016 | SHS | Region V | Sorsogon | 302230 | Pilar National Comprehensive Hs | Pilar | 1 |  | 8 | 2STY8CL | BATCH 11 CL | 11199162.8695 |  |  | Completed | 1
18745 | NC 2016 | SHS | Region V | Sorsogon | 302230 | Pilar National Comprehensive Hs | Pilar | 1 |  | 6 | 2STY6CL | BATCH 11 CL | 8456914.0025 |  |  | Completed | 1
18746 | NC 2016 | K10 | Region V | Sorsogon | 114282 | Pili Es | Magallanes (34 Brgys) | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1993048.2452 |  |  | Completed | 1
18747 | NC 2016 | K10 | Region V | Sorsogon | 114385 | Poctol Es | Pilar | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
18748 | NC 2016 | K10 | Region V | Sorsogon | 114150 | Rawis Elementary School | Donsol | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.6381 |  |  | Completed | 1
18749 | NC 2016 | K10 | Region V | Sorsogon | 114131 | Rosal Es | Castilla | 1 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1
18750 | NC 2016 | K10 | Region V | Sorsogon | 114388 | Salvacion Es | Pilar | 1 | 1 | 6 | 1STY3CL | BATCH 13 CL | 5710818.005 |  |  | Completed | 1
18751 | NC 2016 | SHS | Region V | Sorsogon | 302236 | Salvacion Nhs | Pilar | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 7150818.2558 |  |  | Completed | 1
18752 | NC 2016 | SHS | Region V | Sorsogon | 302236 | Salvacion Nhs | Pilar | 1 |  | 6 | 2STY6CL | BATCH 11 CL | 8376264.352 |  |  | Completed | 1
18753 | NC 2016 | K10 | Region V | Sorsogon | 114152 | San Isidro Es | Donsol | 1 | 1 | 3 | 1STY3CL | BATCH 13 CL | 3082851.684 |  |  | Completed | 1
18754 | NC 2016 | K10 | Region V | Sorsogon | 114152 | San Isidro Es | Donsol | 1 |  | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
18755 | NC 2016 | K10 | Region V | Sorsogon | 114093 | San Juan Es | Casiguran | 1 | 1 | 6 | 1STY3CL | BATCH 13 CL | 5605184.88 |  |  | Completed | 1
18756 | NC 2016 | K10 | Region V | Sorsogon | 114093 | San Juan Es | Casiguran | 1 |  | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
18757 | NC 2016 | SHS | Region V | Sorsogon | 310008 | San Rafael Nhs | Pilar | 1 | 1 | 3 | 1STY3CL | BATCH 11 CL | 3391136.8524 |  |  | Completed | 1
18758 | NC 2016 | SHS | Region V | Sorsogon | 310008 | San Rafael Nhs | Pilar | 1 |  | 4 | 1STY2CL | BATCH 11 CL | 3670964.8894 |  |  | Completed | 1
18759 | NC 2016 | K10 | Region V | Sorsogon | 114134 | San Vicente Es | Castilla | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.6381 |  |  | Completed | 1
18760 | NC 2016 | K10 | Region V | Sorsogon | 114135 | Sogoy Es | Castilla | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
18761 | NC 2016 | K10 | Region V | Sorsogon | 114181 | Tinanogan Es | Donsol | 1 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1
18762 | NC 2016 | K10 | Region V | Sorsogon | 114185 | Bagacay Es | Gubat | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1
18763 | NC 2016 | K10 | Region V | Sorsogon | 302184 | Barcelona National Comprehensive High School | Barcelona | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8380614.751 |  |  | Completed | 1
18764 | NC 2016 | K10 | Region V | Sorsogon | 114206 | Bongsaran Es | Gubat | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1
18765 | NC 2016 | SHS | Region V | Sorsogon | 302190 | Bulan Nhs | Bulan | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11275889.3917 |  |  | Completed | 1
18766 | NC 2016 | SHS | Region V | Sorsogon | 302190 | Bulan Nhs | Bulan | 2 |  | 30 | 2STY10CL | BATCH 13 CL | 39204569.5791 |  |  | Completed | 1
18767 | NC 2016 | SHS | Region V | Sorsogon | 302192 | Bulusan Nhs | Bulusan | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6442031.0381 |  |  | Completed | 1
18768 | NC 2016 | K10 | Region V | Sorsogon | 114209 | Cabigaan Es | Gubat | 2 | 1 | 4 | 1STY2CL | BATCH 13 CL | 3999905.48 |  |  | Completed | 1
18769 | NC 2016 | K10 | Region V | Sorsogon | 114391 | Calao Es | Prieto Diaz | 2 | 1 | 4 | 1STY2CL | BATCH 13 CL | 3877212.08 |  |  | Completed | 1
18770 | NC 2016 | K10 | Region V | Sorsogon | 114189 | Carriedo Es | Gubat | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1
18771 | NC 2016 | K10 | Region V | Sorsogon | 114228 | Carriedo Es | Irosin | 2 | 1 | 6 | 1STY2CL | BATCH 13 CL | 6009618.12 |  |  | Completed | 1
18772 | NC 2016 | K10 | Region V | Sorsogon | 114190 | Cogon Es | Gubat | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1
18773 | NC 2016 | K10 | Region V | Sorsogon | 114011 | Danao Es | Bulan | 2 | 1 | 9 | 1STY3CL | BATCH 13 CL | 9172777.32 |  |  | Completed | 1
18774 | NC 2016 | K10 | Region V | Sorsogon | 114038 | G. Del Pilar Es | Bulan | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2061299.44 |  |  | Completed | 1
18775 | NC 2016 | K10 | Region V | Sorsogon | 114232 | Gabao Es | Irosin | 2 | 1 | 6 | 1STY2CL | BATCH 13 CL | 5815818.12 |  |  | Completed | 1
18776 | NC 2016 | K10 | Region V | Sorsogon | 302212 | Gallanosa National High School | Irosin | 2 | 1 | 16 | 2STY8CL | BATCH 13 CL | 22145232.0334 |  |  | Completed | 1
18777 | NC 2016 | K10 | Region V | Sorsogon | 302212 | Gallanosa National High School | Irosin | 2 |  | 6 | 2STY6CL | BATCH 13 CL | 8389614.751 |  |  | Completed | 1
18778 | NC 2016 | K10 | Region V | Sorsogon | 302214 | Gubat National High School | Gubat | 2 | 1 | 24 | 2STY8CL | BATCH 13 CL | 33217847.9751 |  |  | Completed | 1
18779 | NC 2016 | K10 | Region V | Sorsogon | 302187 | Juban National High School | Juban | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6422031.0381 |  |  | Completed | 1
18780 | NC 2016 | K10 | Region V | Sorsogon | 114193 | Jupi Es | Gubat | 2 | 1 | 6 | 1STY3CL | BATCH 13 CL | 5798984.88 |  |  | Completed | 1
18781 | NC 2016 | K10 | Region V | Sorsogon | 114318 | Lajong Es | Matnog | 2 | 1 | 4 | 1STY2CL | BATCH 13 CL | 4122598.08 |  |  | Completed | 1
18782 | NC 2016 | K10 | Region V | Sorsogon | 302225 | Matnog Nhs | Matnog | 2 | 1 | 12 | 2STY4CL | BATCH 13 CL | 19275092.92 |  |  | Completed | 1
18783 | NC 2016 | K10 | Region V | Sorsogon | 114020 | Monte Calvario E/S | Bulan | 2 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2986550.94 |  |  | Completed | 1
18784 | NC 2016 | K10 | Region V | Sorsogon | 114043 | N. Roque Es | Bulan | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2061299.44 |  |  | Completed | 1
18785 | NC 2016 | K10 | Region V | Sorsogon | 175006 | Nenita E. Oandasan Mem. Sch. | Prieto Diaz | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
18786 | NC 2016 | K10 | Region V | Sorsogon | 114199 | Payawin Es | Gubat | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1
18787 | NC 2016 | SHS | Region V | Sorsogon | 302232 | Prieto Diaz Nhs | Prieto Diaz | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8380614.751 |  |  | Completed | 1
18788 | NC 2016 | SHS | Region V | Sorsogon | 302232 | Prieto Diaz Nhs | Prieto Diaz | 2 |  | 4 | 2STY4CL | BATCH 13 CL | 6422031.0381 |  |  | Completed | 1
18789 | NC 2016 | K10 | Region V | Sorsogon | 175016 | Severino E. Fortes Mem. School Es | Irosin | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2061299.44 |  |  | Completed | 1
18790 | NC 2016 | K10 | Region V | Sorsogon | 114030 | Somagongsong Es | Bulan | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2061299.44 |  |  | Completed | 1
18791 | NC 2016 | K10 | Region V | Sorsogon | 114217 | Sta. Ana Es | Gubat | 2 | 1 | 4 | 1STY2CL | BATCH 13 CL | 3999905.48 |  |  | Completed | 1
18792 | NC 2016 | K10 | Region V | Sorsogon | 113996 | Sta. Lourdes Elementary School | Barcelona | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2061299.44 |  |  | Completed | 1
18793 | NC 2016 | K10 | Region V | Sorsogon | 302245 | Sta. Magdalena Nhs | Santa Magdalena | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12871755.3761 |  |  | Completed | 1
18794 | NC 2016 | K10 | Region V | Sorsogon | 114054 | Sta. Teresita Es | Bulan | 2 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1163049.69 |  |  | Completed | 1
18795 | NC 2016 | K10 | Region V | Sorsogon | 114269 | Taboc Es | Juban | 2 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1208294.659 |  |  | Completed | 1
18796 | NC 2016 | K10 | Region V | Sorsogon | 114202 | Tiris Es | Gubat | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1
18797 | NC 2016 | K10 | Region V | Sorsogon | 114246 | Tongdol Es | Irosin | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1
18798 | NC 2016 | K10 | Region V | Sorsogon City | 310405 | Bogña Integrated School | City Of Sorsogon (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6319337.6381 |  |  | Completed | 1
18799 | NC 2016 | K10 | Region V | Sorsogon City | 302272 | Celestino G. Tabuena Memorial Nhs | City Of Sorsogon (Capital) | 1 | 1 | 10 | 2STY10CL | BATCH 11 CL | 12771310.09 |  |  | Completed | 1
18800 | NC 2016 | K10 | Region V | Sorsogon City | 302280 | Lydia D. Martinez Memorial High School | City Of Sorsogon (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6319337.64 |  |  | Completed | 1
18801 | NC 2016 | K10 | Region V | Sorsogon City | 302275 | Rawis National High School | City Of Sorsogon (Capital) | 1 | 1 | 10 | 2STY10CL | BATCH 11 CL | 12771310.093 |  |  | Completed | 1
18802 | NC 2016 | K10 | Region V | Sorsogon City | 302279 | Sorsogon National High School | City Of Sorsogon (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22937798.35 |  |  | Completed | 1
18803 | NC 2016 | K10 | Region V | Sorsogon City | 302279 | Sorsogon National High School | City Of Sorsogon (Capital) | 1 |  | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1
18804 | NC 2016 | K10 | Region V | Sorsogon City | 302279 | Sorsogon National High School | City Of Sorsogon (Capital) | 1 |  | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1
18805 | NC 2016 | SHS | Region V | Tabaco City | 302281 | Bantayan Nhs | City Of Tabaco | 1 | 1 | 2 | 1STY1CL | BATCH 9 CL | 2226509.2394 |  |  | Completed | 1
18806 | NC 2016 | SHS | Region V | Tabaco City | 302281 | Bantayan Nhs | City Of Tabaco | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
18807 | NC 2016 | SHS | Region V | Tabaco City | 302281 | Bantayan Nhs | City Of Tabaco | 1 |  | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1
18808 | NC 2016 | TECHVOC | Region V | Tabaco City | 310501 | Bogñabong High School | City Of Tabaco | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
18809 | NC 2016 | K10 | Region V | Tabaco City | 302282 | San Antonio Nhs, Tabaco | City Of Tabaco | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1
18810 | NC 2016 | K10 | Region V | Tabaco City | 114599 | San Carlos Es | City Of Tabaco | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
18811 | NC 2016 | K10 | Region V | Tabaco City | 302283 | San Lorenzo Nhs | City Of Tabaco | 1 | 1 | 2 | 1STY1CL | BATCH 9 CL | 2226509.2394 |  |  | Completed | 1
18812 | NC 2016 | K10 | Region V | Tabaco City | 302283 | San Lorenzo Nhs | City Of Tabaco | 1 |  | 12 | 3STY6CL | BATCH 9 CL | 22887689.322 |  |  | Completed | 1
18813 | NC 2016 | TECHVOC | Region V | Tabaco City | 302283 | San Lorenzo Nhs | City Of Tabaco | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1
18814 | NC 2016 | SHS | Region V | Tabaco City | 302285 | Tabaco National High School | City Of Tabaco | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1
18815 | NC 2016 | SHS | Region V | Tabaco City | 302285 | Tabaco National High School | City Of Tabaco | 1 |  | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1
18816 | NC 2016 | SHS | Region V | Tabaco City | 302285 | Tabaco National High School | City Of Tabaco | 1 |  | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1
18817 | NC 2016 | SHS | Region V | Tabaco City | 302285 | Tabaco National High School | City Of Tabaco | 1 |  | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1
18818 | NC 2016 | SHS | Region V | Tabaco City | 302285 | Tabaco National High School | City Of Tabaco | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8665776.7976 |  |  | Completed | 1
18819 | NC 2016 | SHS | Region V | Tabaco City | 302285 | Tabaco National High School | City Of Tabaco | 1 |  | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1
18820 | NC 2016 | K10 | Region V | Camarines Norte | 112156 | San Mauricio Es | Jose Panganiban | 1 | 1 | 4 | 1STY4CL w/ toilet attached | BATCH 14 CL | 3767968.78 |  |  | Completed | 1
18821 | NC 2016 | K10 | Region V | Albay | 111667 | Daraga North Cs | Daraga (Locsin) | 2 | 1 | 6 | 2STY6CL | BATCH 14 CL | 9021461.555 |  |  | Completed | 1
18822 | NC 2016 | K10 | Region V | Albay | 301809 | Anislag Nhs - San Vicente Grande Ext. | Daraga (Locsin) | 2 | 1 | 2 | 1STY2CL w/ toilet attached | BATCH 14 CL | 2132466.644 |  |  | Completed | 1
27035 | NC 2017 | K10 | Region V | Camarines Sur | 112319 | Baao CS | BAAO | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3933000 |  |  | Completed | 1
27036 | NC 2017 | K10 | Region V | Camarines Sur | 112320 | Baao West CS | BAAO | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 4043000 |  |  | Completed | 1
27037 | NC 2017 | K10 | Region V | Camarines Sur | 112323 | Caranday Elementary School | BAAO | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2799418.04 |  |  | Completed | 1
27038 | NC 2017 | K10 | Region V | Camarines Sur | 112334 | Salvacion ES | BAAO | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2962082.46 |  |  | Completed | 1
27039 | NC 2017 | K10 | Region V | Camarines Sur | 112335 | San Isidro-Santa Teresita ES | BAAO | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 4043000 |  |  | Completed | 1
27040 | NC 2017 | K10 | Region V | Camarines Sur | 112337 | San Juan ES | BAAO | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2965053.04 |  |  | Completed | 1
27041 | NC 2017 | K10 | Region V | Camarines Sur | 112346 | Cabungan ES | BALATAN | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3782000 |  |  | Completed | 1
27042 | NC 2017 | TVL | Region V | Camarines Sur | 301960 | Coguit HS | BALATAN | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3401625.81 |  |  | Completed | 1
27043 | NC 2017 | TVL | Region V | Camarines Sur | 309725 | Laganac High School | BALATAN | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3283738.38 |  |  | Completed | 1
27044 | NC 2017 | K10 | Region V | Camarines Sur | 112355 | Pararao ES | BALATAN | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3824000 |  |  | Completed | 1
27045 | NC 2017 | TVL | Region V | Camarines Sur | 302014 | Pararao High School | BALATAN | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3283738.38 |  |  | Completed | 1
27046 | NC 2017 | K10 | Region V | Camarines Sur | 112359 | Tapayas ES | BALATAN | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3824000 |  |  | Completed | 1
27047 | NC 2017 | K10 | Region V | Camarines Sur | 112361 | Agos ES | BATO | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 3303459.42 |  |  | Completed | 1
27048 | NC 2017 | K10 | Region V | Camarines Sur | 112361 | Agos ES | BATO | 5 |  | 3 | 1STY3CL | BATCH 2 | 4090000 |  |  | Completed | 1
27049 | NC 2017 | K10 | Region V | Camarines Sur | 112362 | ATIPOLO ELEM. SCHOOL | BATO | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2772045.12 |  |  | Completed | 1
27050 | NC 2017 | K10 | Region V | Camarines Sur | 112365 | Bato South CS | BATO | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3791000 |  |  | Completed | 1
27051 | NC 2017 | K10 | Region V | Camarines Sur | 112367 | Carlos Nardo Elementary School | BATO | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2940788.49 |  |  | Completed | 1
27052 | NC 2017 | K10 | Region V | Camarines Sur | 173546 | Del Rosario PS | BATO | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3782000 |  |  | Completed | 1
27053 | NC 2017 | K10 | Region V | Camarines Sur | 112369 | Don Teofilo Landagan PS (Caricot) | BATO | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2830536.13 |  |  | Completed | 1
27054 | NC 2017 | TVL | Region V | Camarines Sur | 301997 | Masoli High School | BATO | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3283738.38 |  |  | Completed | 1
27055 | NC 2017 | K10 | Region V | Camarines Sur | 112379 | Palo ES | BATO | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 3046619.77 |  |  | Completed | 1
27056 | NC 2017 | K10 | Region V | Camarines Sur | 112381 | Salvacion ES | BATO | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3783000 |  |  | Completed | 1
27057 | NC 2017 | TVL | Region V | Camarines Sur | 302026 | Salvacion HS, Bato | BATO | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3419487.53 |  |  | Completed | 1
27058 | NC 2017 | K10 | Region V | Camarines Sur | 112384 | San Roque ES | BATO | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3824000 |  |  | Completed | 1
27059 | NC 2017 | TVL | Region V | Camarines Sur | 302027 | San Roque High School | BATO | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3369923.29 |  |  | Completed | 1
27060 | NC 2017 | K10 | Region V | Camarines Sur |  | Sooc ES | BATO | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3782000 |  |  | Completed | 1
27061 | NC 2017 | TVL | Region V | Camarines Sur | 302053 | Sulpicio A. Roco MHS | BOMBON | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3546311.77 |  |  | Completed | 1
27062 | NC 2017 | K10 | Region V | Camarines Sur | 112389 | Antipolo ES | BUHI | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2940788.49 |  |  | Completed | 1
27063 | NC 2017 | K10 | Region V | Camarines Sur | 112389 | Antipolo ES | BUHI | 5 |  | 2 | 1STY2CL | BATCH 2 | 2940788.49 |  |  | Completed | 1
27064 | NC 2017 | K10 | Region V | Camarines Sur | 112390 | Buhi CS | BUHI | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3868000 |  |  | Completed | 1
27065 | NC 2017 | K10 | Region V | Camarines Sur | 112391 | Buhi North CS | BUHI | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3886000 |  |  | Completed | 1
27066 | NC 2017 | K10 | Region V | Camarines Sur | 112399 | Igbac ES | BUHI | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 4028000 |  |  | Completed | 1
27067 | NC 2017 | K10 | Region V | Camarines Sur | 112404 | Lourdes ES | BUHI | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3908000 |  |  | Completed | 1
27068 | NC 2017 | K10 | Region V | Camarines Sur | 112406 | Maybatang ES | BUHI | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 4090000 |  |  | Completed | 1
27069 | NC 2017 | K10 | Region V | Camarines Sur | 112422 | Penafrancia ES (Tawagan ES) | BUHI | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2819385.79 |  |  | Completed | 1
27070 | NC 2017 | K10 | Region V | Camarines Sur | 112411 | Salvacion ES | BUHI | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 3002819.39 |  |  | Completed | 1
27071 | NC 2017 | K10 | Region V | Camarines Sur | 112415 | San Vicente ES | BUHI | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3845000 |  |  | Completed | 1
27072 | NC 2017 | TVL | Region V | Camarines Sur | 302043 | San Vicente NHS | BUHI | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3283738.38 |  |  | Completed | 1
27073 | NC 2017 | K10 | Region V | Camarines Sur | 112417 | Sta. Isabel ES | BUHI | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 4090000 |  |  | Completed | 1
27074 | NC 2017 | K10 | Region V | Camarines Sur | 112418 | Sta. Justina East ES | BUHI | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2833426.42 |  |  | Completed | 1
27075 | NC 2017 | K10 | Region V | Camarines Sur | 112418 | Sta. Justina East ES | BUHI | 5 |  | 3 | 1STY3CL | BATCH 2 | 3824000 |  |  | Completed | 1
27076 | NC 2017 | TVL | Region V | Camarines Sur | 302050 | Sta. Justina High School | BUHI | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3283738.38 |  |  | Completed | 1
27077 | NC 2017 | TVL | Region V | Camarines Sur | 302057 | Tambo National High School | BUHI | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3413065.23 |  |  | Completed | 1
27078 | NC 2017 | K10 | Region V | Camarines Sur | 112426 | Balaogan ES | BULA | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3870000 |  |  | Completed | 1
27079 | NC 2017 | SHS | Region V | Camarines Sur | 301947 | Bula NHS | BULA | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2951828.13 |  |  | Completed | 1
27080 | NC 2017 | TVL | Region V | Camarines Sur | 301947 | Bula NHS | BULA | 5 |  | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3456104.24 |  |  | Completed | 1
27081 | NC 2017 | TVL | Region V | Camarines Sur | 301959 | Casugad High School | BULA | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3413011.27 |  |  | Completed | 1
27082 | NC 2017 | TVL | Region V | Camarines Sur | 309760 | Fabrica HS - La Victoria Annex HS | BULA | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3413065.23 |  |  | Completed | 1
27083 | NC 2017 | TVL | Region V | Camarines Sur | 302010 | Palsong NHS | BULA | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3369923.29 |  |  | Completed | 1
27084 | NC 2017 | TVL | Region V | Camarines Sur | 301953 | Quipayo National High School | CALABANGA | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3372014.42 |  |  | Completed | 1
27085 | NC 2017 | TVL | Region V | Camarines Sur | 301954 | Sabang National HS | CALABANGA | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3453633.99 |  |  | Completed | 1
27086 | NC 2017 | TVL | Region V | Camarines Sur | 302065 | Union National High School | CALABANGA | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3528464.87 |  |  | Completed | 1
27087 | NC 2017 | TVL | Region V | Camarines Sur | 301955 | West Coast High School | CALABANGA | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3727634.24 |  |  | Completed | 1
27088 | NC 2017 | K10 | Region V | Camarines Sur | 112740 | Colacling ES | LUPI | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2958767.945 |  |  | Completed | 1
27089 | NC 2017 | K10 | Region V | Camarines Sur | 112740 | Colacling ES | LUPI | 1 |  | 2 | 1STY2CL | BATCH 2 | 2958767.945 |  |  | Completed | 1
27090 | NC 2017 | K10 | Region V | Camarines Sur | 112745 | Lupi CS | LUPI | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2779736.69 |  |  | Completed | 1
27091 | NC 2017 | TVL | Region V | Camarines Sur | 302034 | Magarao NHS (formerly: San Isidro NHS) | MAGARAO | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3549074.4 |  |  | Completed | 1
27092 | NC 2017 | K10 | Region V | Camarines Sur | 112815 | Bustrac ES | NABUA | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3812000 |  |  | Completed | 1
27093 | NC 2017 | K10 | Region V | Camarines Sur | 112833 | Don Telesforo Llorin ES | NABUA | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3803000 |  |  | Completed | 1
27094 | NC 2017 | TVL | Region V | Camarines Sur | 301985 | La Purisima HS | NABUA | 5 | 1 | 1 | 1STY Unique Workshop Bldg. | BATCH 2 | 3456104.24 |  |  | Completed | 1
27095 | NC 2017 | SHS | Region V | Camarines Sur | 301985 | La Purisima HS | NABUA | 5 |  | 2 | 1STY2CL | BATCH 2 | 3136236.83 |  |  | Completed | 1
27096 | NC 2017 | K10 | Region V | Camarines Sur | 112837 | Malawag Elementary School | NABUA | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2772045.12 |  |  | Completed | 1
27097 | NC 2017 | K10 | Region V | Camarines Sur | 112837 | Malawag Elementary School | NABUA | 5 |  | 3 | 1STY3CL | BATCH 2 | 3844000 |  |  | Completed | 1
27098 | NC 2017 | K10 | Region V | Camarines Sur | 112819 | Naipitan ES | NABUA | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3933000 |  |  | Completed | 1
27099 | NC 2017 | K10 | Region V | Camarines Sur | 112820 | Ogbon ES | NABUA | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3803000 |  |  | Completed | 1
27100 | NC 2017 | K10 | Region V | Camarines Sur | 112822 | Paloyon ES | NABUA | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2783084.76 |  |  | Completed | 1
27101 | NC 2017 | K10 | Region V | Camarines Sur | 112825 | San Vicente ES | NABUA | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3803000 |  |  | Completed | 1
27102 | NC 2017 | K10 | Region V | Camarines Sur | 112826 | Santiago Old ES | NABUA | 5 | 1 | 5 | 1STY5CL | BATCH 2 | 5851000 |  |  | Completed | 1
27103 | NC 2017 | K10 | Region V | Camarines Sur | 112827 | Santiago Young ES | NABUA | 5 | 1 | 5 | 1STY5CL | BATCH 2 | 6146000 |  |  | Completed | 1
27104 | NC 2017 | K10 | Region V | Camarines Sur | 112845 | Tandaay ES | NABUA | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3782000 |  |  | Completed | 1
27105 | NC 2017 | TVL | Region V | Camarines Sur | 301962 | Altamarino-Clasio High School (formerly Curry High School) | PILI (Capital) | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3383397.34 |  |  | Completed | 1
27106 | NC 2017 | TVL | Region V | Camarines Sur | 309719 | Doña Basilia S. Quilon Memorial High School (formerly:Bagong Sirang HS) | PILI (Capital) | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3593926.13 |  |  | Completed | 1
27107 | NC 2017 | TVL | Region V | Camarines Sur | 309719 | Doña Basilia S. Quilon Memorial High School (formerly:Bagong Sirang HS) | PILI (Capital) | 3 |  | 1 | Unique Workshop Bldg. | BATCH 2 | 3608885.17 |  |  | Completed | 1
27108 | NC 2017 | TVL | Region V | Camarines Sur | 302016 | Pili NHS, Pili | PILI (Capital) | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3570248.67 |  |  | Completed | 1
27109 | NC 2017 | SHS | Region V | Camarines Sur | 309750 | Cristobal D. Aquino Memorial High School | RAGAY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2867029.29 |  |  | Completed | 1
27110 | NC 2017 | K10 | Region V | Camarines Sur | 112960 | Liboro ES | RAGAY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2806962.51 |  |  | Completed | 1
27111 | NC 2017 | SHS | Region V | Camarines Sur | 302020 | Ragay National Agricultural and Fisheries School (RNAFS) | RAGAY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2805306.9 |  |  | Completed | 1
27112 | NC 2017 | K10 | Region V | Camarines Sur | 112972 | San Rafael Elementary School | RAGAY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2833585.92 |  |  | Completed | 1
27113 | NC 2017 | K10 | Region V | Camarines Sur | 113083 | Gabi ES | SIPOCOT | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2760079.23 |  |  | Completed | 1
27114 | NC 2017 | K10 | Region V | Camarines Sur | 113086 | Lubigan Jr. ES | SIPOCOT | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2740829.8 |  |  | Completed | 1
27115 | NC 2017 | K10 | Region V | Camarines Sur | 309975 | Lubigan Sr. HS-SNHS Annex | SIPOCOT | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2767542.95 |  |  | Completed | 1
27116 | NC 2017 | K10 | Region V | Camarines Sur | 113073 | North Villazar ES | SIPOCOT | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3006360.63 |  |  | Completed | 1
27117 | NC 2017 | K10 | Region V | Camarines Sur | 113067 | Sipocot North CS | SIPOCOT | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2834040.86 |  |  | Completed | 1
27118 | NC 2017 | K10 | Region V | Camarines Sur | 113093 | Tara ES | SIPOCOT | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2749231.02 |  |  | Completed | 1
27119 | NC 2017 | K10 | Region V | Ligao City | 111836 | Bacong ES | CITY OF LIGAO | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2798745.92 |  |  | Completed | 1
27120 | NC 2017 | TVL | Region V | Ligao City | 321701 | Ligao City National Technical -Vocational High School | CITY OF LIGAO | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 2439603.31 |  |  | Completed | 1
27121 | NC 2017 | TVL | Region V | Naga City | 302264 | Camarines Sur National High School | NAGA CITY | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3574711.09 |  |  | Completed | 1
27122 | NC 2017 | TVL | Region V | Naga City | 302265 | Cararayan National High School | NAGA CITY | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3378688 |  |  | Completed | 1
27123 | NC 2017 | TVL | Region V | Naga City | 302265 | Cararayan National High School | NAGA CITY | 3 |  | 1 | Unique Workshop Bldg. | BATCH 2 | 3361709.67 |  |  | Completed | 1
27124 | NC 2017 | TVL | Region V | Naga City | 302266 | Carolina National High School | NAGA CITY | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3370542.32 |  |  | Completed | 1
27125 | NC 2017 | TVL | Region V | Naga City | 302266 | Carolina National High School | NAGA CITY | 3 |  | 1 | Unique Workshop Bldg. | BATCH 2 | 3434052.31 |  |  | Completed | 1
27126 | NC 2017 | TVL | Region V | Naga City | 302266 | Carolina National High School | NAGA CITY | 3 |  | 1 | Unique Workshop Bldg. | BATCH 2 | 3436551.19 |  |  | Completed | 1
27127 | NC 2017 | TVL | Region V | Naga City | 302266 | Carolina National High School | NAGA CITY | 3 |  | 1 | Unique Workshop Bldg. | BATCH 2 | 3419750.88 |  |  | Completed | 1
27128 | NC 2017 | TVL | Region V | Naga City | 302266 | Carolina National High School | NAGA CITY | 3 |  | 1 | Unique Workshop Bldg. | BATCH 2 | 3407532.47 |  |  | Completed | 1
27129 | NC 2017 | TVL | Region V | Naga City | 302266 | Carolina National High School | NAGA CITY | 3 |  | 1 | Unique Workshop Bldg. | BATCH 2 | 3367598.11 |  |  | Completed | 1
27130 | NC 2017 | TVL | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3461990.76 |  |  | Completed | 1
27131 | NC 2017 | TVL | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 |  | 1 | Unique Workshop Bldg. | BATCH 2 | 3361709.67 |  |  | Completed | 1
27132 | NC 2017 | TVL | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 |  | 1 | Unique Workshop Bldg. | BATCH 2 | 3361709.67 |  |  | Completed | 1
27133 | NC 2017 | TVL | Region V | Tabaco City | 302281 | Bantayan NHS | CITY OF TABACO | 1 | 1 | 1 | Unique Workshop Bldg. | BATCH 2 | 3203176.95 |  |  | Completed | 1
27134 | NC 2017 | TVL | Region V | Tabaco City | 302281 | Bantayan NHS | CITY OF TABACO | 1 |  | 1 | Regular Workshop Bldg. | BATCH 2 | 3026581.48 |  |  | Completed | 1
27135 | NC 2017 | TVL | Region V | Tabaco City | 302284 | San Miguel NHS | CITY OF TABACO | 1 | 1 | 1 | Regular Workshop Bldg. | BATCH 2 | 3693314.58 |  |  | Completed | 1
27136 | NC 2017 | TVL | Region V | Albay | 301818 | Cabasan National High School | BACACAY | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3832499.56 |  |  | Completed | 1
27137 | NC 2017 | TVL | Region V | Albay | 301818 | Cabasan National High School | BACACAY | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3853757.57 |  |  | Completed | 1
27138 | NC 2017 | TVL | Region V | Albay | 309502 | San Pablo High School | BACACAY | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 4006789.54 |  |  | Completed | 1
27139 | NC 2017 | TVL | Region V | Albay | 309502 | San Pablo High School | BACACAY | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 4006789.54 |  |  | Completed | 1
27140 | NC 2017 | TVL | Region V | Albay | 301878 | Sogod National High school | BACACAY | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3010826.66 |  |  | Completed | 1
27141 | NC 2017 | TVL | Region V | Albay | 301885 | Vinisitahan National High School | BACACAY | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3017660.08 |  |  | Completed | 1
27142 | NC 2017 | K10 | Region V | Albay | 111637 | Quirangay ES | CAMALIG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3422538.32 |  |  | Completed | 1
27143 | NC 2017 | TVL | Region V | Albay | 301850 | Lower Binogsacan National High School | GUINOBATAN | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2638745.92 |  |  | Completed | 1 |  |  | P00173103LZ-CW1 | 17FO0083 | 2017-09-15 | 2017-09-22 | 2017-10-04 | 2017-10-23 | 2017-10-30 | 4Dove Builders Corp.
27144 | NC 2017 | K10 | Region V | Albay | 111716 | Masarawag ES | GUINOBATAN | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2733745.92 |  |  | Completed | 1 |  |  | P00173102LZ-CW1 | 17FO0069 | 2017-09-12 | 2017-09-19 | 2017-10-02 | 2017-10-23 | 2017-11-09 | MQR Const. & Supplies
27145 | NC 2017 | TVL | Region V | Albay | 309520 | Malabiga High School | LIBON | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3003745.92 |  |  | Completed | 1 |  |  | P00173108LZ-CW1 | 17FO0086 | 2017-09-18 | 2017-09-27 | 2017-10-09 | 2017-10-17 | 2017-11-02 | Brix Const. & Supply
27146 | NC 2017 | TVL | Region V | Albay | 301860 | Pantao National High School | LIBON | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2968745.92 |  |  | Completed | 1 |  |  | P00173106LZ-CW1 | 17FO0085 | 2017-09-18 | 2017-09-27 | 2017-10-09 | 2017-10-13 | 2017-10-30 | 4Dove Builders Corp.
27147 | NC 2017 | TVL | Region V | Albay | 309504 | Rawis High School | LIBON | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3013745.92 |  |  | Completed | 1 |  |  | P00173107LZ-CW1 | 17FO0087 | 2017-09-20 | 2017-09-27 | 2017-10-09 | 2017-10-18 | 2018-11-02 | Brix Const. & Supply
27148 | NC 2017 | K10 | Region V | Albay | 111774 | San Agustin ES | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00173104LZ-CW1 | 17FO0070 | 2017-09-12 | 2017-09-19 | 2017-10-02 | 2017-10-20 | 2017-10-30 | Brix Const. & Supply
27149 | NC 2017 | K10 | Region V | Albay | 111779 | San Vicente ES | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2728745.92 |  |  | Completed | 1 |  |  | P00173105LZ-CW1 | 17FO0074 | 2017-09-13 | 2017-09-20 | 2017-10-03 | 2017-10-24 | 2017-10-30 | Sulvir Engineering & Construction
27150 | NC 2017 | TVL | Region V | Albay | 301871 | San Antonio National High School | MALILIPOT | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3384342.82 |  |  | Completed | 1
27151 | NC 2017 | TVL | Region V | Albay | 301871 | San Antonio National High School | MALILIPOT | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3405885.49 |  |  | Completed | 1
27152 | NC 2017 | TVL | Region V | Albay | 301876 | San Isidro National High School | MALILIPOT | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3004788.02 |  |  | Completed | 1
27153 | NC 2017 | K10 | Region V | Albay | 111867 | Sta. Teresa ES | MALILIPOT | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2929732.59 |  |  | Completed | 1
27154 | NC 2017 | K10 | Region V | Albay | 111868 | Balading ES | MALINAO | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 4220840.21 |  |  | Completed | 1
27155 | NC 2017 | K10 | Region V | Albay | 111868 | Balading ES | MALINAO | 1 |  | 2 | 1STY2CL | BATCH 4 | 2917869.33 |  |  | Completed | 1
27156 | NC 2017 | TVL | Region V | Albay | 301831 | Labnig National High School | MALINAO | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3019368.43 |  |  | Completed | 1
27157 | NC 2017 | TVL | Region V | Albay | 301831 | Labnig National High School | MALINAO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3040626.44 |  |  | Completed | 1
27158 | NC 2017 | TVL | Region V | Albay | 301857 | Sabino Rebagay Memorial High School | OAS | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2773745.92 |  |  | Completed | 1 |  |  | P00173109LZ-CW1 | 17FO0089 | 2017-09-20 | 2017-09-27 | 2017-10-09 | 2017-10-18 | 2017-11-02 | 4Dove Builders Corp.
27159 | NC 2017 | K10 | Region V | Albay | 111950 | Binodegahan ES | PIO DURAN | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 4068435.02 |  |  | Completed | 1 |  |  | P00173110LZ-CW1 | 17FO0091 | 2017-09-20 | 2017-09-27 | 2017-10-09 | 2017-10-18 | 2017-11-02 | 4Dove Builders Corp.
27160 | NC 2017 | TVL | Region V | Albay | 309516 | Malidong National High School | PIO DURAN | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2903745.92 |  |  | Completed | 1 |  |  | P00182943LZ-CW1 | 17FO0082 | 2017-09-15 | 2017-09-23 | 2017-10-04 | 2017-10-13 | 2017-10-30 | 4Dove Builders Corp.
27161 | NC 2017 | TVL | Region V | Albay | 301864 | Pio Duran National High School | PIO DURAN | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2778745.92 |  |  | Completed | 1 |  |  | P00173112LZ-CW1 | 17FO0088 | 2017-09-20 | 2017-09-27 | 2017-10-09 | 2017-10-18 | 2017-11-02 | 4Dove Builders Corp.
27162 | NC 2017 | K10 | Region V | Albay | 111972 | Pioduran West CS | PIO DURAN | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2883745.92 |  |  | Completed | 1 |  |  | P00173111LZ-CW1 | 17FO0073 | 2017-09-12 | 2017-09-19 | 2017-10-02 | 2017-10-13 | 2017-10-30 | 9LEAVES BUILDERS & SUPPLY CORP.
27163 | NC 2017 | K10 | Region V | Albay | 111979 | Balaba ES | POLANGUI | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3953435.02 |  |  | Completed | 1 |  |  | P00173114LZ-CW1 | 17FO0092 | 2017-09-20 | 2017-09-27 | 2017-10-09 | 2017-10-18 | 2017-11-06 | Zheantelle Const. Corp.
27164 | NC 2017 | K10 | Region V | Albay | 111980 | Balinad ES | POLANGUI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2708745.92 |  |  | Completed | 1 |  |  | P00173115LZ-CW1 | 17FO0075 | 2017-09-13 | 2017-09-20 | 2017-10-03 | 2017-10-23 | 2017-10-30 | GRANDRISE CONSTRUCTION AND DEVELOPMENT CORP.
27165 | NC 2017 | K10 | Region V | Albay | 111983 | Danao Elementary School | POLANGUI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2723745.92 |  |  | Completed | 1 |  |  | P00173116LZ-CW1 | 17FO0072 | 2017-09-12 | 2017-09-19 | 2017-10-02 | 2017-10-13 | 2017-10-30 | Zheantelle Const. Corp.
27166 | NC 2017 | K10 | Region V | Albay | 112004 | Kinale ES | POLANGUI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2918745.92 |  |  | Completed | 1 |  |  | P00173119LZ-CW1 | 17FO0077 | 2017-09-13 | 2017-09-20 | 2017-10-03 | 2017-10-23 | 2017-10-30 | NGS CONST. SUPPLY
27167 | NC 2017 | TVL | Region V | Albay | 301867 | La Medalla High School | POLANGUI | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2793745.92 |  |  | Completed | 1 |  |  | P00173122LZ-CW1 | 17FO0084 | 2017-09-15 | 2017-09-22 | 2017-10-04 | 2017-10-23 | 2017-10-30 | GRANDRISE CONSTRUCTION AND DEVELOPMENT CORP.
27168 | NC 2017 | K10 | Region V | Albay | 111987 | Lidong ES | POLANGUI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2713745.92 |  |  | Completed | 1 |  |  | P00173117LZ-CW1 | 17FO0071 | 2017-09-12 | 2017-09-19 | 2017-10-02 | 2017-10-20 | 2017-10-30 | Zheantelle Const. Corp.
27169 | NC 2017 | TVL | Region V | Albay | 301852 | Matacon National High School | POLANGUI | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3013745.92 |  |  | Completed | 1 |  |  | P00173121LZ-CW1 | 17FO0090 | 2017-09-20 | 2017-09-27 | 2017-10-09 | 2017-10-18 | 2017-11-02 | Zheantelle Const. Corp.
27170 | NC 2017 | K10 | Region V | Albay | 111994 | Pintor ES | POLANGUI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2708745.92 |  |  | Completed | 1 |  |  | P00173118LZ-CW1 | 17FO0078 | 2017-09-13 | 2017-09-20 | 2017-10-03 | 2017-10-13 | 2017-10-30 | MQR CONST. AND SUPPLIES
27171 | NC 2017 | K10 | Region V | Albay | 112012 | Salvacion ES | POLANGUI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2753745.92 |  |  | Completed | 1 |  |  | P00173120LZ-CW1 | 17FO0076 | 2017-09-13 | 2017-09-20 | 2017-10-03 | 2017-10-23 | 2017-10-30 | GRANDRISE CONSTRUCTION AND DEVELOPMENT CORP.
27172 | NC 2017 | TVL | Region V | Albay | 301815 | Bical High School | SANTO DOMINGO (LIBOG) | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3035040.38 |  |  | Completed | 1
27173 | NC 2017 | K10 | Region V | Albay | 112052 | Buhatan ES | SANTO DOMINGO (LIBOG) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2945647.76 |  |  | Completed | 1
27174 | NC 2017 | K10 | Region V | Albay | 112056 | Salvacion ES | SANTO DOMINGO (LIBOG) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2944394.77 |  |  | Completed | 1
27175 | NC 2017 | K10 | Region V | Albay | 112058 | San Andres ES | SANTO DOMINGO (LIBOG) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2934888.64 |  |  | Completed | 1
27176 | NC 2017 | TVL | Region V | Albay | 301872 | San Fernando National High School | SANTO DOMINGO (LIBOG) | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3036791.51 |  |  | Completed | 1
27177 | NC 2017 | TVL | Region V | Albay | 301872 | San Fernando National High School | SANTO DOMINGO (LIBOG) | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3036791.51 |  |  | Completed | 1
27178 | NC 2017 | K10 | Region V | Albay | 112063 | Bariis ES | TIWI | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 4254249.14 |  |  | Completed | 1
27179 | NC 2017 | TVL | Region V | Albay | 301881 | Joroan High School | TIWI | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3035842.24 |  |  | Completed | 1
27180 | NC 2017 | TVL | Region V | Albay | 301881 | Joroan High School | TIWI | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3057100.25 |  |  | Completed | 1
27181 | NC 2017 | K10 | Region V | Albay | 112080 | Sugod ES | TIWI | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2938817.08 |  |  | Completed | 1
27182 | NC 2017 | TVL | Region V | Camarines Norte | 309611 | Dominador Narido High School | BASUD | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 5982806.56 |  |  | Completed | 1
27183 | NC 2017 | TVL | Region V | Camarines Norte | 301915 | San Felipe NHS | BASUD | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3569567.28 |  |  | Completed | 1
27184 | NC 2017 | TVL | Region V | Camarines Norte | 309608 | Tuaca HS | BASUD | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3569567.28 |  |  | Completed | 1
27185 | NC 2017 | TVL | Region V | Camarines Norte | 309608 | Tuaca HS | BASUD | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3369567.28 |  |  | Completed | 1
27186 | NC 2017 | TVL | Region V | Camarines Norte | 301900 | Lalawigan National High School | MERCEDES | 2 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 4 | 9343523.97 |  |  | Completed | 1
27187 | NC 2017 | TVL | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3369567.28 |  |  | Completed | 1
27188 | NC 2017 | TVL | Region V | Camarines Norte | 309606 | San Isidro HS (Alcantara) | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3659567.28 |  |  | Completed | 1
27189 | NC 2017 | TVL | Region V | Camarines Norte | 301903 | San Lorenzo Ruiz National High School | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3419567.28 |  |  | Completed | 1
27190 | NC 2017 | TVL | Region V | Camarines Norte | 301903 | San Lorenzo Ruiz National High School | SAN LORENZO RUIZ (IMELDA) | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3619567.28 |  |  | Completed | 1
27191 | NC 2017 | TVL | Region V | Camarines Norte | 309605 | Fabrica HS | SAN VICENTE | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3614567.28 |  |  | Completed | 1
27192 | NC 2017 | TVL | Region V | Camarines Norte | 309605 | Fabrica HS | SAN VICENTE | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3414567.28 |  |  | Completed | 1
27193 | NC 2017 | TVL | Region V | Camarines Norte | 301919 | Froilan D. Lopez HS | SAN VICENTE | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3589567.28 |  |  | Completed | 1
27194 | NC 2017 | K10 | Region V | Camarines Norte | 112276 | V. Orendain ES | SAN VICENTE | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
27195 | NC 2017 | K10 | Region V | Camarines Norte | 173004 | Cahabaan Elementary School | TALISAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
27196 | NC 2017 | TVL | Region V | Camarines Norte | 301895 | Gonzalez-Ascutia HS | TALISAY | 2 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 4 | 12323073.24 |  |  | Completed | 1
27197 | NC 2017 | K10 | Region V | Camarines Norte | 112291 | M. Cacho ES | TALISAY | 2 | 1 | 5 | 1STY5CL | BATCH 4 | 6072650.72 |  |  | Completed | 1
27198 | NC 2017 | TVL | Region V | Camarines Norte | 301916 | San Francisco National High School | TALISAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3369567.28 |  |  | Completed | 1
27199 | NC 2017 | K10 | Region V | Camarines Norte | 112297 | Zantua-Abordo ES | TALISAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
27200 | NC 2017 | K10 | Region V | Camarines Norte | 112298 | Banocboc ES | Vinzons | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 5288351.15 |  |  | Completed | 1
27201 | NC 2017 | K10 | Region V | Camarines Norte | 112298 | Banocboc ES | Vinzons | 2 |  | 4 | 1STY4CL | BATCH 4 | 5288351.15 |  |  | Completed | 1
27202 | NC 2017 | TVL | Region V | Camarines Norte | 301892 | D. Q. Liwag NHS | VINZONS | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3569567.28 |  |  | Completed | 1
27203 | NC 2017 | TVL | Region V | Camarines Norte | 309604 | Eugenia M. Quintela Memorial High School | VINZONS | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3769567.28 |  |  | Completed | 1
27204 | NC 2017 | TVL | Region V | Camarines Norte | 309604 | Eugenia M. Quintela Memorial High School | VINZONS | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3569567.28 |  |  | Completed | 1
27205 | NC 2017 | TVL | Region V | Camarines Norte | 301914 | Sabang NHS | VINZONS | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3394567.28 |  |  | Completed | 1
27206 | NC 2017 | TVL | Region V | Camarines Norte | 309620 | Sarah Jane Ferrer HS | VINZONS | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 6032806.56 |  |  | Completed | 1
27207 | NC 2017 | K10 | Region V | Camarines Norte | 112315 | Trino P. Zenarosa ES | VINZONS | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3868435.02 |  |  | Completed | 1
27208 | NC 2017 | TVL | Region V | Camarines Norte | 301925 | Vinzons Pilot High School | VINZONS | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3369567.28 |  |  | Completed | 1
27209 | NC 2017 | K10 | Region V | Camarines Sur | 112528 | Bikal ES | CARAMOAN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 3023254.17 |  |  | Completed | 1
27210 | NC 2017 | SHS | Region V | Camarines Sur | 301943 | Bikal Fisheries School | CARAMOAN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 3238254.17 |  |  | Completed | 1
27211 | NC 2017 | K10 | Region V | Camarines Sur | 112540 | Guijalo ES | CARAMOAN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 3263254.17 |  |  | Completed | 1
27212 | NC 2017 | K10 | Region V | Camarines Sur | 173545 | Pawican ES | CARAMOAN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 3098254.17 |  |  | Completed | 1
27213 | NC 2017 | K10 | Region V | Camarines Sur | 112572 | Tabog ES | CARAMOAN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2988254.17 |  |  | Completed | 1
27214 | NC 2017 | TVL | Region V | Camarines Sur | 301973 | Gainza National HS | GAINZA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3945623.17 |  |  | Completed | 1
27215 | NC 2017 | K10 | Region V | Camarines Sur | 112589 | Ason ES | GARCHITORENA | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 4811402.87 |  |  | Completed | 1
27216 | NC 2017 | K10 | Region V | Camarines Sur | 112589 | Ason ES | GARCHITORENA | 4 |  | 2 | 1STY2CL | BATCH 4 | 3023254.17 |  |  | Completed | 1
27217 | NC 2017 | K10 | Region V | Camarines Sur | 112604 | Pambuhan Elementary School | GARCHITORENA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2299332.57 |  |  | Completed | 1
27218 | NC 2017 | K10 | Region V | Camarines Sur | 112604 | Pambuhan Elementary School | GARCHITORENA | 4 |  | 2 | 1STY2CL | BATCH 4 | 2299332.57 |  |  | Completed | 1
27219 | NC 2017 | K10 | Region V | Camarines Sur | 112611 | Tinawagan PS | GARCHITORENA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2304332.57 |  |  | Completed | 1
27220 | NC 2017 | K10 | Region V | Camarines Sur | 112611 | Tinawagan PS | GARCHITORENA | 4 |  | 2 | 1STY2CL | BATCH 4 | 2299332.57 |  |  | Completed | 1
27221 | NC 2017 | K10 | Region V | Camarines Sur | 112617 | Cagaycay ES | GOA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2788254.17 |  |  | Completed | 1
27222 | NC 2017 | K10 | Region V | Camarines Sur | 112631 | Pinaglabanan ES | GOA | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 4181402.87 |  |  | Completed | 1
27223 | NC 2017 | K10 | Region V | Camarines Sur | 112632 | Salog ES | GOA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2788254.17 |  |  | Completed | 1
27224 | NC 2017 | K10 | Region V | Camarines Sur | 112655 | Burabod ES | LAGONOY | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2938254.17 |  |  | Completed | 1
27225 | NC 2017 | K10 | Region V | Camarines Sur | 173516 | Kinahulogan CS | LAGONOY | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2968254.17 |  |  | Completed | 1
27226 | NC 2017 | TVL | Region V | Camarines Sur | 301936 | Homobono H. Gonzalez National High School | LIBMANAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3689718.54 |  |  | Completed | 1
27227 | NC 2017 | TVL | Region V | Camarines Sur | 301994 | Mambulo Nuevo High School | LIBMANAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4008888.31 |  |  | Completed | 1
27228 | NC 2017 | TVL | Region V | Camarines Sur | 302009 | Palangon High School | LIBMANAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3926080.61 |  |  | Completed | 1
27229 | NC 2017 | TVL | Region V | Camarines Sur | 302033 | San Isidro NHS | LIBMANAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3731099.19 |  |  | Completed | 1
27230 | NC 2017 | SHS | Region V | Camarines Sur | 302033 | San Isidro NHS | LIBMANAN | 2 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2553034.27 |  |  | Completed | 1
27231 | NC 2017 | TVL | Region V | Camarines Sur | 302037 | San Juan National HS | LIBMANAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3676500.2 |  |  | Completed | 1
27232 | NC 2017 | TVL | Region V | Camarines Sur | 302037 | San Juan National HS | LIBMANAN | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3676500.2 |  |  | Completed | 1
27233 | NC 2017 | K10 | Region V | Camarines Sur | 112718 | Sigamot ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2485030.09 |  |  | Completed | 1
27234 | NC 2017 | K10 | Region V | Camarines Sur | 112723 | Tinalmud ES | LIBMANAN | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3674606.26 |  |  | Completed | 1
27235 | NC 2017 | K10 | Region V | Camarines Sur | 112772 | Bal-Flor ES | MILAOR | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3569631.54 |  |  | Completed | 1
27236 | NC 2017 | K10 | Region V | Camarines Sur | 112782 | Mayaopayawan ES | MILAOR | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2456209.02 |  |  | Completed | 1
27237 | NC 2017 | K10 | Region V | Camarines Sur | 112785 | Milaor CS | MILAOR | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2508351.9 |  |  | Completed | 1
27238 | NC 2017 | TVL | Region V | Camarines Sur | 301999 | Milaor National High School | MILAOR | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3882559.32 |  |  | Completed | 1
27239 | NC 2017 | K10 | Region V | Camarines Sur | 112787 | San Antonio ES | MILAOR | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2525956.62 |  |  | Completed | 1
27240 | NC 2017 | TVL | Region V | Camarines Sur | 302030 | San Antonio NHS | MILAOR | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3656274.5 |  |  | Completed | 1
27241 | NC 2017 | TVL | Region V | Camarines Sur | 309731 | Antipolo HS, Minalabac | MINALABAC | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3681451.04 |  |  | Completed | 1
27242 | NC 2017 | K10 | Region V | Camarines Sur | 112792 | Baliuag Nuevo ES | MINALABAC | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2538566.6 |  |  | Completed | 1
27243 | NC 2017 | K10 | Region V | Camarines Sur | 112798 | Hobo ES | MINALABAC | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2531623.62 |  |  | Completed | 1
27244 | NC 2017 | TVL | Region V | Camarines Sur | 301981 | Hobo National High School | MINALABAC | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3676509.44 |  |  | Completed | 1
27245 | NC 2017 | K10 | Region V | Camarines Sur | 112803 | Mataoroc ES | MINALABAC | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3624871.28 |  |  | Completed | 1
27246 | NC 2017 | TVL | Region V | Camarines Sur | 302000 | Minalabac NHS | MINALABAC | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3986123.15 |  |  | Completed | 1
27247 | NC 2017 | TVL | Region V | Camarines Sur | 302025 | Sagrada Familia High School | MINALABAC | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3706627.57 |  |  | Completed | 1
27248 | NC 2017 | TVL | Region V | Camarines Sur | 302066 | Villamayor HS | MINALABAC | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3702675.02 |  |  | Completed | 1
27249 | NC 2017 | K10 | Region V | Camarines Sur | 112869 | Calawat PS | PAMPLONA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2466508.1 |  |  | Completed | 1
27250 | NC 2017 | TVL | Region V | Camarines Sur | 301968 | Don Mariano C. Veneracion NHS | PAMPLONA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3702359.66 |  |  | Completed | 1
27251 | NC 2017 | K10 | Region V | Camarines Sur | 112871 | Pamplona Central School | PAMPLONA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2537302.93 |  |  | Completed | 1
27252 | NC 2017 | TVL | Region V | Camarines Sur | 302012 | Pamplona NHS | PAMPLONA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3789400.08 |  |  | Completed | 1
27253 | NC 2017 | TVL | Region V | Camarines Sur | 302012 | Pamplona NHS | PAMPLONA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3789400.08 |  |  | Completed | 1
27254 | NC 2017 | K10 | Region V | Camarines Sur | 112874 | San Gabriel ES | PAMPLONA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2531623.62 |  |  | Completed | 1
27255 | NC 2017 | K10 | Region V | Camarines Sur | 112878 | Taguilid ES | PAMPLONA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2531623.62 |  |  | Completed | 1
27256 | NC 2017 | K10 | Region V | Camarines Sur | 112880 | Tampadong ES | PAMPLONA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2478552.52 |  |  | Completed | 1
27257 | NC 2017 | K10 | Region V | Camarines Sur | 112902 | Caranan ES (North) | PASACAO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2547483.68 |  |  | Completed | 1
27258 | NC 2017 | K10 | Region V | Camarines Sur | 112903 | Caranan ES (South) | PASACAO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2577040.02 |  |  | Completed | 1
27259 | NC 2017 | K10 | Region V | Camarines Sur | 112905 | Cuco ES | PASACAO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2473916.49 |  |  | Completed | 1
27260 | NC 2017 | K10 | Region V | Camarines Sur | 112908 | Itulan ES | PASACAO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2470096.9 |  |  | Completed | 1
27261 | NC 2017 | TVL | Region V | Camarines Sur | 309702 | Juan F. Trivino MHS (frmerly: Pasacao Sch. of Fisheries) | PASACAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3688179.3367 |  |  | Completed | 1
27262 | NC 2017 | TVL | Region V | Camarines Sur | 309702 | Juan F. Trivino MHS (frmerly: Pasacao Sch. of Fisheries) | PASACAO | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3688179.3367 |  |  | Completed | 1
27263 | NC 2017 | TVL | Region V | Camarines Sur | 309702 | Juan F. Trivino MHS (frmerly: Pasacao Sch. of Fisheries) | PASACAO | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3688179.3367 |  |  | Completed | 1
27264 | NC 2017 | TVL | Region V | Camarines Sur | 309769 | Pasacao Municipal High School | PASACAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3546271.98 |  |  | Completed | 1
27265 | NC 2017 | TVL | Region V | Camarines Sur | 301965 | Rolando R. Andaya Sr. Memorial High School | PASACAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3731099.19 |  |  | Completed | 1
27266 | NC 2017 | K10 | Region V | Camarines Sur | 112893 | Maangas ES | PRESENTACION (PARUBCAN) | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 4081402.87 |  |  | Completed | 1
27267 | NC 2017 | K10 | Region V | Camarines Sur | 112895 | Parubcan CS | PRESENTACION (PARUBCAN) | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 4081402.87 |  |  | Completed | 1
27268 | NC 2017 | TVL | Region V | Camarines Sur | 301987 | Lupi National High School | SAN FERNANDO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3779586.24 |  |  | Completed | 1
27269 | NC 2017 | TVL | Region V | Camarines Sur | 302013 | PAMUKID NATIONAL HIGH SCHOOL | SAN FERNANDO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4142284.36 |  |  | Completed | 1
27270 | NC 2017 | K10 | Region V | Camarines Sur | 113007 | Pipian ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2463617.41 |  |  | Completed | 1
27271 | NC 2017 | K10 | Region V | Camarines Sur | 113008 | Planza ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2529776.21 |  |  | Completed | 1
27272 | NC 2017 | K10 | Region V | Camarines Sur | 113009 | San Fernando Central School | San Fernando | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3619156.9 |  |  | Completed | 1
27273 | NC 2017 | K10 | Region V | Camarines Sur | 113013 | Adiangao ES | SAN JOSE | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2988254.17 |  |  | Completed | 1
27274 | NC 2017 | K10 | Region V | Camarines Sur |  | Adiangao HS | SAN JOSE | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2988254.17 |  |  | Completed | 1
27275 | NC 2017 | K10 | Region V | Camarines Sur |  | Adiangao HS | SAN JOSE | 4 |  | 2 | 1STY2CL | BATCH 4 | 2988254.17 |  |  | Completed | 1
27276 | NC 2017 | K10 | Region V | Camarines Sur | 113014 | Bagacay Elementary School | SAN JOSE | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2803254.17 |  |  | Completed | 1
27277 | NC 2017 | K10 | Region V | Camarines Sur | 113014 | Bagacay Elementary School | SAN JOSE | 4 |  | 2 | 1STY2CL | BATCH 4 | 2803254.17 |  |  | Completed | 1
27278 | NC 2017 | K10 | Region V | Camarines Sur | 113015 | Bahay PS | SAN JOSE | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2988254.17 |  |  | Completed | 1
27279 | NC 2017 | K10 | Region V | Camarines Sur | 113016 | Calalahan ES | SAN JOSE | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 4016402.87 |  |  | Completed | 1
27280 | NC 2017 | K10 | Region V | Camarines Sur | 113016 | Calalahan ES | SAN JOSE | 4 |  | 2 | 1STY2CL | BATCH 4 | 2778254.17 |  |  | Completed | 1
27281 | NC 2017 | K10 | Region V | Camarines Sur | 113016 | Calalahan ES | SAN JOSE | 4 |  | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
27282 | NC 2017 | K10 | Region V | Camarines Sur | 173518 | Calawit Community School | SAN JOSE | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2928254.17 |  |  | Completed | 1
27283 | NC 2017 | K10 | Region V | Camarines Sur | 173518 | Calawit Community School | SAN JOSE | 4 |  | 2 | 1STY2CL | BATCH 4 | 2928254.17 |  |  | Completed | 1
27284 | NC 2017 | K10 | Region V | Camarines Sur | 113018 | Catalotoan Community School | SAN JOSE | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2808254.17 |  |  | Completed | 1
27285 | NC 2017 | K10 | Region V | Camarines Sur | 113020 | Dolo Elementary School | SAN JOSE | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2753254.17 |  |  | Completed | 1
27286 | NC 2017 | K10 | Region V | Camarines Sur | 113020 | Dolo Elementary School | SAN JOSE | 4 |  | 2 | 1STY2CL | BATCH 4 | 2753254.17 |  |  | Completed | 1
27287 | NC 2017 | K10 | Region V | Camarines Sur | 113020 | Dolo Elementary School | SAN JOSE | 4 |  | 2 | 1STY2CL | BATCH 4 | 2753254.17 |  |  | Completed | 1
27288 | NC 2017 | K10 | Region V | Camarines Sur | 113021 | Kinalansan ES | SAN JOSE | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 4281402.87 |  |  | Completed | 1
27289 | NC 2017 | K10 | Region V | Camarines Sur | 113023 | Minoro PS | SAN JOSE | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 3976402.87 |  |  | Completed | 1
27290 | NC 2017 | K10 | Region V | Camarines Sur | 173519 | Palale CS | SAN JOSE | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2783254.17 |  |  | Completed | 1
27291 | NC 2017 | K10 | Region V | Camarines Sur | 113027 | Salogon ES | SAN JOSE | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2988254.17 |  |  | Completed | 1
27292 | NC 2017 | K10 | Region V | Camarines Sur | 113032 | Tominawog ES | SAN JOSE | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2823254.17 |  |  | Completed | 1
27293 | NC 2017 | SHS | Region V | Camarines Sur | 301984 | Vivencio Obias - Kinalansan NHS (formerly: Kinalansan NHS) | SAN JOSE | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2838254.17 |  |  | Completed | 1
27294 | NC 2017 | K10 | Region V | Camarines Sur | 113047 | Tandoc ES | SIRUMA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 3038254.17 |  |  | Completed | 1
27295 | NC 2017 | K10 | Region V | Camarines Sur | 113095 | Eulalia A.Fuentebella Elementary School (Cabalinadan PS) | TIGAON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 3023254.17 |  |  | Completed | 1
27296 | NC 2017 | K10 | Region V | Camarines Sur | 113095 | Eulalia A.Fuentebella Elementary School (Cabalinadan PS) | TIGAON | 4 |  | 2 | 1STY2CL | BATCH 4 | 3023254.17 |  |  | Completed | 1
27297 | NC 2017 | K10 | Region V | Camarines Sur | 113104 | Salvacion ES | TIGAON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2788254.17 |  |  | Completed | 1
27298 | NC 2017 | K10 | Region V | Camarines Sur | 113108 | Tigaon CPS | TIGAON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2938254.17 |  |  | Completed | 1
27299 | NC 2017 | K10 | Region V | Camarines Sur | 113110 | Tinawagan ES | TIGAON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2788254.17 |  |  | Completed | 1
27300 | NC 2017 | K10 | Region V | Camarines Sur | 113124 | Pag-asa ES | TINAMBAC | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2808254.17 |  |  | Completed | 1
27301 | NC 2017 | K10 | Region V | Camarines Sur | 113127 | Sagrada ES | TINAMBAC | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2808254.17 |  |  | Completed | 1
27302 | NC 2017 | K10 | Region V | Camarines Sur | 113127 | Sagrada ES | TINAMBAC | 4 |  | 2 | 1STY2CL | BATCH 4 | 2808254.17 |  |  | Completed | 1
27303 | NC 2017 | K10 | Region V | Camarines Sur | 113133 | Tambang CS | TINAMBAC | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2958254.17 |  |  | Completed | 1
27304 | NC 2017 | K10 | Region V | Camarines Sur | 113150 | Tierra Nevada ES | TINAMBAC | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2780754.17 |  |  | Completed | 1
27305 | NC 2017 | K10 | Region V | Camarines Sur | 113150 | Tierra Nevada ES | TINAMBAC | 4 |  | 2 | 1STY2CL | BATCH 4 | 2760754.17 |  |  | Completed | 1
27306 | NC 2017 | K10 | Region V | Camarines Sur | 113151 | Tinambac CS I | TINAMBAC | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 3931402.87 |  |  | Completed | 1
27307 | NC 2017 | K10 | Region V | Camarines Sur | 113152 | Tinambac South CS II | TINAMBAC | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2888254.17 |  |  | Completed | 1
27308 | NC 2017 | K10 | Region V | Catanduanes | 113161 | Bagamanoc CES | BAGAMANOC | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3165817.38 |  |  | Completed | 1
27309 | NC 2017 | TVL | Region V | Catanduanes | 302072 | Bagamanoc Rural DHS | BAGAMANOC | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4644315.15 |  |  | Completed | 1
27310 | NC 2017 | TVL | Region V | Catanduanes | 302076 | Bugao NHS | BAGAMANOC | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4631854.75 |  |  | Completed | 1
27311 | NC 2017 | TVL | Region V | Catanduanes | 302076 | Bugao NHS | BAGAMANOC | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3035817.06 |  |  | Completed | 1
27312 | NC 2017 | K10 | Region V | Catanduanes | 174001 | San Rafael ES | BAGAMANOC | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2901272.22 |  |  | Completed | 1
27313 | NC 2017 | TVL | Region V | Catanduanes | 302073 | Baras Rural DHS | BARAS | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4546913.675 |  |  | Completed | 1
27314 | NC 2017 | TVL | Region V | Catanduanes | 302073 | Baras Rural DHS | BARAS | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4546913.675 |  |  | Completed | 1
27315 | NC 2017 | SHS | Region V | Catanduanes | 302073 | Baras Rural DHS | BARAS | 0 |  | 2 | 1STY2CL | BATCH 4 | 2815561.09 |  |  | Completed | 1
27316 | NC 2017 | TVL | Region V | Catanduanes | 500032 | Cabugao IS | BATO | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4625523.68 |  |  | Completed | 1
27317 | NC 2017 | TVL | Region V | Catanduanes | 500032 | Cabugao IS | BATO | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4625523.68 |  |  | Completed | 1
27318 | NC 2017 | K10 | Region V | Catanduanes | 113187 | Libjo ES | BATO | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2918258.36 |  |  | Completed | 1
27319 | NC 2017 | TVL | Region V | Catanduanes | 302081 | Caramoran Rural Development High School | CARAMORAN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4598432.67 |  |  | Completed | 1
27320 | NC 2017 | TVL | Region V | Catanduanes | 302082 | Caramoran School of Fisheries | CARAMORAN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4633045.9867 |  |  | Completed | 1
27321 | NC 2017 | TVL | Region V | Catanduanes | 302082 | Caramoran School of Fisheries | CARAMORAN | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4633045.9867 |  |  | Completed | 1
27322 | NC 2017 | TVL | Region V | Catanduanes | 302082 | Caramoran School of Fisheries | CARAMORAN | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4633045.9867 |  |  | Completed | 1
27323 | NC 2017 | K10 | Region V | Catanduanes | 113212 | Milaviga IS | CARAMORAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3255113.29 |  |  | Completed | 1
27324 | NC 2017 | TVL | Region V | Catanduanes | 302102 | Supang-Datag National High School | CARAMORAN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4613441.955 |  |  | Completed | 1
27325 | NC 2017 | TVL | Region V | Catanduanes | 302102 | Supang-Datag National High School | CARAMORAN | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4613441.955 |  |  | Completed | 1
27326 | NC 2017 | SHS | Region V | Catanduanes | 302106 | Tubli National High School | CARAMORAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2921791.25 |  |  | Completed | 1
27327 | NC 2017 | SHS | Region V | Catanduanes | 302106 | Tubli National High School | CARAMORAN | 0 |  | 2 | 1STY2CL | BATCH 4 | 2921791.25 |  |  | Completed | 1
27328 | NC 2017 | TVL | Region V | Catanduanes | 302106 | Tubli National High School | CARAMORAN | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4868914.87 |  |  | Completed | 1
27329 | NC 2017 | TVL | Region V | Catanduanes | 302088 | Gigmoto Rural DHS | GIGMOTO | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2976233.3 |  |  | Completed | 1
27330 | NC 2017 | TVL | Region V | Catanduanes | 500159 | Cobo Integrated School | PANDAN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4695950.25 |  |  | Completed | 1
27331 | NC 2017 | TVL | Region V | Catanduanes | 500159 | Cobo Integrated School | PANDAN | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4695950.25 |  |  | Completed | 1
27332 | NC 2017 | TVL | Region V | Catanduanes | 500159 | Cobo Integrated School | PANDAN | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 5901151.97 |  |  | Completed | 1
27333 | NC 2017 | TVL | Region V | Catanduanes | 500159 | Cobo Integrated School | PANDAN | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3275249 |  |  | Completed | 1
27334 | NC 2017 | TVL | Region V | Catanduanes | 302103 | Leandro I.Verceles Sr. NHS | PANDAN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4689263.16 |  |  | Completed | 1
27335 | NC 2017 | TVL | Region V | Catanduanes | 302094 | Pandan SAT | PANDAN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4680706.14 |  |  | Completed | 1
27336 | NC 2017 | TVL | Region V | Catanduanes | 309801 | Panganiban NHS (CAIC Compound) | PANGANIBAN (PAYO) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4639039.51 |  |  | Completed | 1
27337 | NC 2017 | TVL | Region V | Catanduanes | 302091 | Manambrag NHS | SAN ANDRES (CALOLBON) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4605725.55 |  |  | Completed | 1
27338 | NC 2017 | TVL | Region V | Catanduanes | 302092 | Mayngaway NHS | SAN ANDRES (CALOLBON) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4604934.42 |  |  | Completed | 1
27339 | NC 2017 | TVL | Region V | Catanduanes | 302096 | San Andres Vocational School | SAN ANDRES (CALOLBON) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4591943.85 |  |  | Completed | 1
27340 | NC 2017 | TVL | Region V | Catanduanes | 302098 | San Miguel Rural DHS | SAN MIGUEL | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4666177.66 |  |  | Completed | 1
27341 | NC 2017 | TVL | Region V | Catanduanes | 302104 | Tambogñon NHS | VIGA | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3000795.14 |  |  | Completed | 1
27342 | NC 2017 | K10 | Region V | Catanduanes | 113315 | Tinago Elementary School | VIGA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2829714.53 |  |  | Completed | 1
27343 | NC 2017 | TVL | Region V | Catanduanes | 302107 | Viga Rural DHS | VIGA | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4674505.18 |  |  | Completed | 1
27344 | NC 2017 | TVL | Region V | Catanduanes | 302107 | Viga Rural DHS | VIGA | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3299328.14 |  |  | Completed | 1
27345 | NC 2017 | TVL | Region V | Catanduanes | 302071 | Antipolo NHS | VIRAC (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4665020.21 |  |  | Completed | 1
27346 | NC 2017 | TVL | Region V | Catanduanes | 302071 | Antipolo NHS | VIRAC (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3354953.9 |  |  | Completed | 1
27347 | NC 2017 | K10 | Region V | Catanduanes | 113335 | Buyo ES | VIRAC (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3911548.22 |  |  | Completed | 1
27348 | NC 2017 | TVL | Region V | Catanduanes | 302084 | Calatagan High School | VIRAC (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4560762.1467 |  |  | Completed | 1
27349 | NC 2017 | TVL | Region V | Catanduanes | 302084 | Calatagan High School | VIRAC (Capital) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4560762.1467 |  |  | Completed | 1
27350 | NC 2017 | TVL | Region V | Catanduanes | 302084 | Calatagan High School | VIRAC (Capital) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4560762.1467 |  |  | Completed | 1
27351 | NC 2017 | K10 | Region V | Catanduanes | 113358 | Casoocan ES | VIRAC (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2977997.95 |  |  | Completed | 1
27352 | NC 2017 | TVL | Region V | Catanduanes | 302083 | Catanduanes NHS | VIRAC (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4482834.3267 |  |  | Completed | 1
27353 | NC 2017 | TVL | Region V | Catanduanes | 302083 | Catanduanes NHS | VIRAC (Capital) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4482834.3267 |  |  | Completed | 1
27354 | NC 2017 | TVL | Region V | Catanduanes | 302083 | Catanduanes NHS | VIRAC (Capital) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4482834.3267 |  |  | Completed | 1
27355 | NC 2017 | K10 | Region V | Catanduanes | 113339 | Dugui San Isidro ES | VIRAC (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2812989.21 |  |  | Completed | 1
27356 | NC 2017 | K10 | Region V | Catanduanes | 113343 | Hicming ES | VIRAC (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2792998.99 |  |  | Completed | 1
27357 | NC 2017 | TVL | Region V | Catanduanes | 302090 | Magnesia National High School | VIRAC (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4601134.795 |  |  | Completed | 1
27358 | NC 2017 | TVL | Region V | Catanduanes | 302090 | Magnesia National High School | VIRAC (Capital) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4601134.795 |  |  | Completed | 1
27359 | NC 2017 | K10 | Region V | Catanduanes | 113348 | Sogod Simamla ES | VIRAC (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2825696.73 |  |  | Completed | 1
27360 | NC 2017 | K10 | Region V | Catanduanes | 113350 | Sto. Nino ES | VIRAC (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2791619.46 |  |  | Completed | 1
27361 | NC 2017 | K10 | Region V | Catanduanes | 113373 | Virac CES | VIRAC (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3841762.02 |  |  | Completed | 1
27362 | NC 2017 | K10 | Region V | Catanduanes | 113352 | Virac Pilot Elementary School | VIRAC (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 4257241.58 |  |  | Completed | 1
27363 | NC 2017 | K10 | Region V | Iriga City | 114451 | San Juan ES | IRIGA CITY | 5 | 1 | 3 | 1STY3CL | BATCH 4 | 4043000 |  |  | Completed | 1
27364 | NC 2017 | K10 | Region V | Iriga City | 114437 | San Rafael ES | IRIGA CITY | 5 | 1 | 3 | 1STY3CL | BATCH 4 | 5145000 |  |  | Completed | 1
27365 | NC 2017 | TVL | Region V | Legaspi City | 310206 | Cagbacong High School | LEGAZPI CITY (Capital) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3685053 |  |  | Completed | 1 |  |  | 17FB0162
27366 | NC 2017 | K10 | Region V | Legaspi City | 114461 | Imalnod ES | LEGAZPI CITY (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3402682.56 |  |  | Completed | 1 |  |  | 17FB0163
27367 | NC 2017 | K10 | Region V | Legaspi City | 114480 | Lamba ES | LEGAZPI CITY (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3216428.32 |  |  | Completed | 1 |  |  | 17FB0164
27368 | NC 2017 | K10 | Region V | Legaspi City | 114482 | Maslog ES | LEGAZPI CITY (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3291776.575 |  |  | Completed | 1 |  |  | 17FB0165
27369 | NC 2017 | K10 | Region V | Legaspi City | 114482 | Maslog ES | LEGAZPI CITY (Capital) | 2 |  | 2 | 1STY2CL | BATCH 4 | 3291776.575 |  |  | Completed | 1 |  |  | 17FB0166
27370 | NC 2017 | K10 | Region V | Sorsogon City | 114565 | Basud Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
27371 | NC 2017 | K10 | Region V | Sorsogon City | 114573 | Guinlajon Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
27372 | NC 2017 | K10 | Region V | Sorsogon City | 114569 | Patricia Jesalva Delgado Memorial Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2628978.41 |  |  | Completed | 1
27373 | NC 2017 | K10 | Region V | Sorsogon City | 114563 | Sorsogon East Central School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2670924.94 |  |  | Completed | 1
27374 | NC 2017 | K10 | Region V | Sorsogon City | 114563 | Sorsogon East Central School | CITY OF SORSOGON (Capital) | 1 |  | 2 | 1STY2CL | BATCH 4 | 2648477.44 |  |  | Completed | 1
27375 | NC 2017 | K10 | Region V | Sorsogon City | 114581 | Sorsogon Pilot Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2670913.25 |  |  | Completed | 1
27376 | NC 2017 | K10 | Region V | Camarines Norte | 112106 | Tacad ES | BASUD | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27377 | NC 2017 | TVL | Region V | Camarines Norte | 301897 | Delia Diezmo National High School | CAPALONGA | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3444567.28 |  |  | Completed | 1
27378 | NC 2017 | K10 | Region V | Camarines Norte | 112112 | Jueves-Talento ES (Catabaguangan) | Capalonga | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
27379 | NC 2017 | TVL | Region V | Camarines Norte | 309614 | Magsaysay National High School | CAPALONGA | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6363974.7 |  |  | Completed | 1
27380 | NC 2017 | TVL | Region V | Camarines Norte | 309614 | Magsaysay National High School | CAPALONGA | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6209098.54 |  |  | Completed | 1
27381 | NC 2017 | K10 | Region V | Camarines Norte | 112121 | Necio Olila ES | CAPALONGA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
27382 | NC 2017 | K10 | Region V | Camarines Norte | 112126 | Sotero Mago ES | CAPALONGA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
27383 | NC 2017 | TVL | Region V | Camarines Norte | 309610 | Victoria J. Tuacar National HS | CAPALONGA | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6032806.56 |  |  | Completed | 1
27384 | NC 2017 | TVL | Region V | Camarines Norte | 309610 | Victoria J. Tuacar National HS | CAPALONGA | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6313974.7 |  |  | Completed | 1
27385 | NC 2017 | TVL | Region V | Camarines Norte | 309610 | Victoria J. Tuacar National HS | CAPALONGA | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6159098.54 |  |  | Completed | 1
27386 | NC 2017 | K10 | Region V | Camarines Norte | 112130 | A. Pabico Abordo ES | DAET (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27387 | NC 2017 | K10 | Region V | Camarines Norte | 112144 | Don S. Carranceja MS | DAET (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27388 | NC 2017 | K10 | Region V | Camarines Norte | 112146 | Goito Pimentel ES | DAET (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27389 | NC 2017 | K10 | Region V | Camarines Norte | 112134 | Daet ES | Daet North | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2688745.92 |  |  | Completed | 1
27390 | NC 2017 | K10 | Region V | Camarines Norte | 112134 | Daet ES | Daet North | 2 |  | 2 | 1STY2CL | BATCH 7 | 2688745.92 |  |  | Completed | 1
27391 | NC 2017 | K10 | Region V | Camarines Norte | 112160 | D. Albonia ES | JOSE PANGANIBAN | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3868435.02 |  |  | Completed | 1
27392 | NC 2017 | TVL | Region V | Camarines Norte | 309619 | Gawad Kalinga HS | JOSE PANGANIBAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3399567.28 |  |  | Completed | 1
27393 | NC 2017 | TVL | Region V | Camarines Norte | 309619 | Gawad Kalinga HS | JOSE PANGANIBAN | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6293974.7 |  |  | Completed | 1
27394 | NC 2017 | TVL | Region V | Camarines Norte | 309619 | Gawad Kalinga HS | JOSE PANGANIBAN | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6139098.54 |  |  | Completed | 1
27395 | NC 2017 | K10 | Region V | Camarines Norte | 112174 | Ulipanan ELementary School | Jose Panganiban West | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2863745.92 |  |  | Completed | 1
27396 | NC 2017 | TVL | Region V | Camarines Norte | 301886 | Bagong Silang I HS | LABO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3629567.28 |  |  | Completed | 1
27397 | NC 2017 | TVL | Region V | Camarines Norte | 301886 | Bagong Silang I HS | LABO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3429567.28 |  |  | Completed | 1
27398 | NC 2017 | TVL | Region V | Camarines Norte | 301893 | Daguit NHS | LABO | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3449567.28 |  |  | Completed | 1
27399 | NC 2017 | TVL | Region V | Camarines Norte | 301893 | Daguit NHS | LABO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6343974.7 |  |  | Completed | 1
27400 | NC 2017 | TVL | Region V | Camarines Norte | 301893 | Daguit NHS | LABO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6189098.54 |  |  | Completed | 1
27401 | NC 2017 | TVL | Region V | Camarines Norte | 301899 | Labo National High School | LABO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3604567.28 |  |  | Completed | 1
27402 | NC 2017 | TVL | Region V | Camarines Norte | 301899 | Labo National High School | LABO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3404567.28 |  |  | Completed | 1
27403 | NC 2017 | TVL | Region V | Camarines Norte | 301908 | Pag-Asa High School | LABO | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6263974.7 |  |  | Completed | 1
27404 | NC 2017 | TVL | Region V | Camarines Norte | 301908 | Pag-Asa High School | LABO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6109098.54 |  |  | Completed | 1
27405 | NC 2017 | K10 | Region V | Camarines Norte | 112195 | Severino Francisco Elementary Sch. | LABO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
27406 | NC 2017 | TVL | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 6182101.07 |  |  | Completed | 1
27407 | NC 2017 | TVL | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3419567.28 |  |  | Completed | 1
27408 | NC 2017 | TVL | Region V | Camarines Norte | 301922 | Tulay Na Lupa National High School | LABO | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3394567.28 |  |  | Completed | 1
27409 | NC 2017 | TVL | Region V | Camarines Norte | 301922 | Tulay Na Lupa National High School | LABO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6313974.7 |  |  | Completed | 1
27410 | NC 2017 | TVL | Region V | Camarines Norte | 301922 | Tulay Na Lupa National High School | LABO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6159098.54 |  |  | Completed | 1
27411 | NC 2017 | K10 | Region V | Camarines Norte | 112201 | Bayabas ES | Labo West | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
27412 | NC 2017 | K10 | Region V | Camarines Norte | 112203 | G. Cale ES | Labo West | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
27413 | NC 2017 | K10 | Region V | Camarines Norte | 112211 | Kabungahan ES | Labo West | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
27414 | NC 2017 | K10 | Region V | Camarines Norte | 112229 | Lanot ES | MERCEDES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2813745.92 |  |  | Completed | 1
27415 | NC 2017 | K10 | Region V | Camarines Norte | 112231 | Mambungalon ES | MERCEDES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2693745.92 |  |  | Completed | 1
27416 | NC 2017 | K10 | Region V | Camarines Norte | 112233 | Masalongsalong ES | MERCEDES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2693745.92 |  |  | Completed | 1
27417 | NC 2017 | K10 | Region V | Camarines Norte | 112235 | Mercedes Elementary School | MERCEDES | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3868435.02 |  |  | Completed | 1
27418 | NC 2017 | K10 | Region V | Camarines Norte | 112237 | Quinapaguian ES | MERCEDES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
27419 | NC 2017 | K10 | Region V | Camarines Norte | 112240 | Tarum ES | MERCEDES | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3968435.02 |  |  | Completed | 1
27420 | NC 2017 | K10 | Region V | Camarines Norte | 112241 | Alfonso Dasco ES | PARACALE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2693745.92 |  |  | Completed | 1
27421 | NC 2017 | K10 | Region V | Camarines Norte | 173017 | Bagumbayan ES | PARACALE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27422 | NC 2017 | TVL | Region V | Camarines Norte | 301890 | Batobalani National High School | PARACALE | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3599567.28 |  |  | Completed | 1
27423 | NC 2017 | TVL | Region V | Camarines Norte | 301890 | Batobalani National High School | PARACALE | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6037806.56 |  |  | Completed | 1
27424 | NC 2017 | K10 | Region V | Camarines Norte | 112243 | Calaburnay ES | PARACALE | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
27425 | NC 2017 | K10 | Region V | Camarines Norte | 112245 | Dagang ES | PARACALE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2673745.92 |  |  | Completed | 1
27426 | NC 2017 | TVL | Region V | Camarines Norte | 301911 | Gumaus NHS | PARACALE | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6343974.7 |  |  | Completed | 1
27427 | NC 2017 | TVL | Region V | Camarines Norte | 301911 | Gumaus NHS | PARACALE | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6189098.54 |  |  | Completed | 1
27428 | NC 2017 | K10 | Region V | Camarines Norte | 112248 | Igang ES | PARACALE | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3828435.02 |  |  | Completed | 1
27429 | NC 2017 | K10 | Region V | Camarines Norte | 112249 | Labnig ES | PARACALE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
27430 | NC 2017 | K10 | Region V | Camarines Norte | 112250 | Macolabo ES | PARACALE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2728745.92 |  |  | Completed | 1
27431 | NC 2017 | K10 | Region V | Camarines Norte | 112252 | Mampungo ES | PARACALE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2728745.92 |  |  | Completed | 1
27432 | NC 2017 | K10 | Region V | Camarines Norte | 112253 | Mateo Era ES | PARACALE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2693745.92 |  |  | Completed | 1
27433 | NC 2017 | TVL | Region V | Camarines Norte | 309621 | MAXIMO MANARANG HIGH SCHOOL | PARACALE | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3669567.28 |  |  | Completed | 1
27434 | NC 2017 | TVL | Region V | Camarines Norte | 309621 | MAXIMO MANARANG HIGH SCHOOL | PARACALE | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3469567.28 |  |  | Completed | 1
27435 | NC 2017 | TVL | Region V | Camarines Norte | 301910 | PARACALE NATIONAL HIGH SCHOOL | PARACALE | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3629567.28 |  |  | Completed | 1
27436 | NC 2017 | TVL | Region V | Camarines Norte | 301910 | PARACALE NATIONAL HIGH SCHOOL | PARACALE | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3424567.28 |  |  | Completed | 1
27437 | NC 2017 | K10 | Region V | Camarines Norte | 112256 | Pinagbirayan ES | PARACALE | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3848435.02 |  |  | Completed | 1
27438 | NC 2017 | K10 | Region V | Camarines Norte | 112258 | Sta. Catalina ES | PARACALE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27439 | NC 2017 | K10 | Region V | Camarines Norte | 112272 | Salvacion (S) ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27440 | NC 2017 | TVL | Region V | Camarines Norte | 301888 | E.P. Borja HS (Basiad NHS) | SANTA ELENA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3669567.28 |  |  | Completed | 1
27441 | NC 2017 | TVL | Region V | Camarines Norte | 301888 | E.P. Borja HS (Basiad NHS) | SANTA ELENA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3449567.28 |  |  | Completed | 1
27442 | NC 2017 | TVL | Region V | Camarines Norte | 301917 | Leocadio Alejo Entienza HS | SANTA ELENA | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3449567.28 |  |  | Completed | 1
27443 | NC 2017 | TVL | Region V | Camarines Norte | 301917 | Leocadio Alejo Entienza HS | SANTA ELENA | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6363974.7 |  |  | Completed | 1
27444 | NC 2017 | TVL | Region V | Camarines Norte | 301917 | Leocadio Alejo Entienza HS | SANTA ELENA | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6209098.54 |  |  | Completed | 1
27445 | NC 2017 | K10 | Region V | Camarines Norte | 112284 | R. Oquindo ES | SANTA ELENA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
27446 | NC 2017 | K10 | Region V | Camarines Norte | 112281 | Earth'S Bounty ES | Sta. Elena | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3868435.02 |  |  | Completed | 1
27447 | NC 2017 | K10 | Region V | Camarines Sur | 112779 | Gainza CS - Gainza | GAINZA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2508351.9 |  |  | Completed | 1
27448 | NC 2017 | K10 | Region V | Camarines Sur | 112671 | Bagadion ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2522893.07 |  |  | Completed | 1
27449 | NC 2017 | K10 | Region V | Camarines Sur | 112701 | Bahao ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2511991.33 |  |  | Completed | 1
27450 | NC 2017 | K10 | Region V | Camarines Sur | 112703 | Beguito Viejo ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2491625.88 |  |  | Completed | 1
27451 | NC 2017 | K10 | Region V | Camarines Sur | 112704 | Bikal ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2487804.37 |  |  | Completed | 1
27452 | NC 2017 | K10 | Region V | Camarines Sur | 112709 | Don Jose Ursua ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2485030.09 |  |  | Completed | 1
27453 | NC 2017 | K10 | Region V | Camarines Sur | 112678 | Ibid ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2494283.86 |  |  | Completed | 1
27454 | NC 2017 | K10 | Region V | Camarines Sur | 112683 | Malansad Viejo ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2481324.87 |  |  | Completed | 1
27455 | NC 2017 | K10 | Region V | Camarines Sur | 112691 | Patag ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2494283.86 |  |  | Completed | 1
27456 | NC 2017 | K10 | Region V | Camarines Sur | 112693 | San Juan ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2562651.49 |  |  | Completed | 1
27457 | NC 2017 | K10 | Region V | Camarines Sur | 112695 | San Vicente ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2499150.67 |  |  | Completed | 1
27458 | NC 2017 | K10 | Region V | Camarines Sur | 112699 | Uson ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2490464.27 |  |  | Completed | 1
27459 | NC 2017 | K10 | Region V | Catanduanes | 113220 | Gigmoto CES | GIGMOTO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2967612.96 |  |  | Completed | 1
27460 | NC 2017 | K10 | Region V | Catanduanes | 113224 | Baldoc ES | PANDAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2989229.34 |  |  | Completed | 1
27461 | NC 2017 | K10 | Region V | Catanduanes | 113228 | Lourdes ES | PANDAN | 0 | 1 | 3 | 1STY3CL | BATCH 7 | 4039965.02 |  |  | Completed | 1
27462 | NC 2017 | K10 | Region V | Catanduanes | 113229 | Marambong ES | PANDAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2988692.13 |  |  | Completed | 1
27463 | NC 2017 | K10 | Region V | Catanduanes | 113230 | Porot ES | PANDAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2857095.41 |  |  | Completed | 1
27464 | NC 2017 | K10 | Region V | Catanduanes | 113241 | San Andres ES | PANDAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2859509.2 |  |  | Completed | 1
27465 | NC 2017 | K10 | Region V | Catanduanes | 113243 | Tariwara ES | PANDAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2989840.86 |  |  | Completed | 1
27466 | NC 2017 | K10 | Region V | Catanduanes | 113248 | Cabuyoan ES | PANGANIBAN (PAYO) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3126391.14 |  |  | Completed | 1
27467 | NC 2017 | K10 | Region V | Catanduanes | 113249 | Cagdarao ES | PANGANIBAN (PAYO) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2839814.99 |  |  | Completed | 1
27468 | NC 2017 | K10 | Region V | Catanduanes | 113251 | Maculiw Comm. Sch. | PANGANIBAN (PAYO) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2839814.99 |  |  | Completed | 1
27469 | NC 2017 | K10 | Region V | Catanduanes | 113254 | San Miguel ES | PANGANIBAN (PAYO) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3072656.42 |  |  | Completed | 1
27470 | NC 2017 | K10 | Region V | Catanduanes | 113276 | Datag ES | SAN ANDRES (CALOLBON) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2800499.87 |  |  | Completed | 1
27471 | NC 2017 | K10 | Region V | Catanduanes | 113279 | Maygnaway ES | SAN ANDRES (CALOLBON) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2964428.73 |  |  | Completed | 1
27472 | NC 2017 | K10 | Region V | Catanduanes | 113279 | Maygnaway ES | SAN ANDRES (CALOLBON) | 0 |  | 2 | 1STY2CL | BATCH 7 | 2964428.73 |  |  | Completed | 1
27473 | NC 2017 | K10 | Region V | Catanduanes | 113285 | Alma ES | SAN MIGUEL | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2949233.31 |  |  | Completed | 1
27474 | NC 2017 | K10 | Region V | Catanduanes | 113290 | Mabato CES | SAN MIGUEL | 0 | 1 | 3 | 1STY3CL | BATCH 7 | 3919414.9 |  |  | Completed | 1
27475 | NC 2017 | SHS | Region V | Catanduanes | 302099 | Mabato NHS (SMRDHS Annex) | SAN MIGUEL | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2978514.63 |  |  | Completed | 1
27476 | NC 2017 | K10 | Region V | Iriga City | 114454 | Sta. Elena ES | IRIGA CITY | 5 | 1 | 3 | 1STY3CL | BATCH 7 | 3980000 |  |  | Completed | 1
27477 | NC 2017 | K10 | Region V | Legaspi City | 114489 | Dita Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3305681.4 |  |  | Completed | 1 |  |  | 17FB0156
27478 | NC 2017 | K10 | Region V | Legaspi City | 114489 | Dita Elementary School | LEGAZPI CITY (Capital) | 2 |  | 2 | 1STY2CL | BATCH 7 | 3305681.4 |  |  | Completed | 1 |  |  | 17FB0157
27479 | NC 2017 | K10 | Region V | Masbate | 113374 | Aroroy East CS | AROROY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2549460 |  |  | Completed | 1
27480 | NC 2017 | SHS | Region V | Masbate | 500163 | Tigbao ES | AROROY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2552260 |  |  | Completed | 1
27481 | NC 2017 | SHS | Region V | Masbate | 500163 | Tigbao ES | AROROY | 2 |  | 2 | 1STY2CL | BATCH 7 | 2547200 |  |  | Completed | 1
27482 | NC 2017 | K10 | Region V | Masbate | 113420 | Baleno CS | BALENO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2518460 |  |  | Completed | 1
27483 | NC 2017 | SHS | Region V | Masbate | 302156 | Briccio A. Aninang Sr. Mem. HS | BALUD | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2572155 |  |  | Completed | 1
27484 | NC 2017 | SHS | Region V | Masbate | 500165 | Antonio Lee Llacer Sr. Integrated School | BATUAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2258472.05 |  |  | Completed | 1
27485 | NC 2017 | TVL | Region V | Masbate | 302112 | Badiang National High School | CATAINGAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4356691.12 |  |  | Completed | 1
27486 | NC 2017 | TVL | Region V | Masbate | 302112 | Badiang National High School | CATAINGAN | 3 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 7 | 12622262.34 |  |  | Completed | 1
27487 | NC 2017 | K10 | Region V | Masbate | 113512 | Domorog ES | CATAINGAN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4151402.87 |  |  | Completed | 1
27488 | NC 2017 | K10 | Region V | Masbate | 113512 | Domorog ES | CATAINGAN | 3 |  | 3 | 1STY3CL | BATCH 7 | 4151402.87 |  |  | Completed | 1
27489 | NC 2017 | K10 | Region V | Masbate | 113515 | Eulogio C. Adoptante ES | CATAINGAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2928254.17 |  |  | Completed | 1
27490 | NC 2017 | K10 | Region V | Masbate | 113516 | Libtong ES | CATAINGAN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4081402.87 |  |  | Completed | 1
27491 | NC 2017 | TVL | Region V | Masbate | 302142 | Liong National High School | CATAINGAN | 3 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 7 | 12622262.34 |  |  | Completed | 1
27492 | NC 2017 | TVL | Region V | Masbate | 302128 | Marcelo A. Anonuevo -Cadulawan National High School | CATAINGAN | 3 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 7 | 16829683.12 |  |  | Completed | 1
27493 | NC 2017 | TVL | Region V | Masbate | 302158 | Pawican National High School | CATAINGAN | 3 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 7 | 12622262.34 |  |  | Completed | 1
27494 | NC 2017 | TVL | Region V | Masbate | 302158 | Pawican National High School | CATAINGAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4356691.12 |  |  | Completed | 1
27495 | NC 2017 | TVL | Region V | Masbate | 309933 | Dalipe National High School | CAWAYAN | 3 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 7 | 16749683.12 |  |  | Completed | 1
27496 | NC 2017 | K10 | Region V | Masbate | 113539 | Gilotongan ES | CAWAYAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2958254.17 |  |  | Completed | 1
27497 | NC 2017 | K10 | Region V | Masbate | 113543 | Lague-Lague ES | CAWAYAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2908254.17 |  |  | Completed | 1
27498 | NC 2017 | TVL | Region V | Masbate | 309934 | Libertad National High School | CAWAYAN | 3 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 7 | 12562262.34 |  |  | Completed | 1
27499 | NC 2017 | K10 | Region V | Masbate | 113550 | Malbug Elementary School | CAWAYAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2908254.17 |  |  | Completed | 1
27500 | NC 2017 | TVL | Region V | Masbate | 309924 | Malbug National High School | CAWAYAN | 3 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 7 | 12712262.34 |  |  | Completed | 1
27501 | NC 2017 | TVL | Region V | Masbate | 309914 | Mayor Tomas V. Rivera Memorial High School | CAWAYAN | 3 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 8374841.56 |  |  | Completed | 1
27502 | NC 2017 | K10 | Region V | Masbate | 113560 | San Jose ES | CAWAYAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2898254.17 |  |  | Completed | 1
27503 | NC 2017 | K10 | Region V | Masbate | 113561 | San Vicente ES | CAWAYAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2858254.17 |  |  | Completed | 1
27504 | NC 2017 | K10 | Region V | Masbate |  | Sulpicio Condor Sr. NHS | CAWAYAN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4151402.87 |  |  | Completed | 1
27505 | NC 2017 | K10 | Region V | Masbate | 113566 | Vienteriales ES | CAWAYAN | 3 | 1 | 4 | 1STY4CL | BATCH 7 | 5442814.7 |  |  | Completed | 1
27506 | NC 2017 | K10 | Region V | Masbate | 113566 | Vienteriales ES | CAWAYAN | 3 |  | 4 | 1STY4CL | BATCH 7 | 5382814.7 |  |  | Completed | 1
27507 | NC 2017 | K10 | Region V | Masbate | 113572 | Bodega ES | CLAVERIA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2673679.13 |  |  | Completed | 1
27508 | NC 2017 | K10 | Region V | Masbate | 113592 | San Isidro ES | CLAVERIA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2680388.9 |  |  | Completed | 1
27509 | NC 2017 | K10 | Region V | Masbate | 113592 | San Isidro ES | CLAVERIA | 1 |  | 3 | 1STY3CL | BATCH 7 | 4060411.02 |  |  | Completed | 1
27510 | NC 2017 | K10 | Region V | Masbate | 113593 | San Ramon ES | CLAVERIA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4054002.16 |  |  | Completed | 1
27511 | NC 2017 | K10 | Region V | Masbate | 113595 | Taguilid ES | CLAVERIA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4044016.12 |  |  | Completed | 1
27512 | NC 2017 | K10 | Region V | Masbate | 113597 | Balocawe ES | DIMASALANG | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4431402.87 |  |  | Completed | 1
27513 | NC 2017 | K10 | Region V | Masbate | 113606 | Dimasalang CS | DIMASALANG | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2898254.17 |  |  | Completed | 1
27514 | NC 2017 | TVL | Region V | Masbate | 302132 | Dimasalang National High School | DIMASALANG | 3 | 1 | 5 | WORKSHOP BLDG (7x18) | BATCH 7 | 20887103.9 |  |  | Completed | 1
27515 | NC 2017 | K10 | Region V | Masbate | 113608 | Gaid ES | DIMASALANG | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2898254.17 |  |  | Completed | 1
27516 | NC 2017 | SHS | Region V | Masbate | 309902 | Allanaraiz-Marfil National High School | ESPERANZA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2868254.17 |  |  | Completed | 1
27517 | NC 2017 | TVL | Region V | Masbate | 309902 | Allanaraiz-Marfil National High School | ESPERANZA | 3 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 8574841.56 |  |  | Completed | 1
27518 | NC 2017 | SHS | Region V | Masbate | 309940 | Tumalaytay National High School | MANDAON | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2542120 |  |  | Completed | 1
27519 | NC 2017 | K10 | Region V | Masbate | 113693 | Amado Beluso ES | MILAGROS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2503190 |  |  | Completed | 1
27520 | NC 2017 | K10 | Region V | Masbate | 113723 | Cayabon ES | MILAGROS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2503190 |  |  | Completed | 1
27521 | NC 2017 | K10 | Region V | Masbate | 174507 | Dominador D. Trabado ES | MILAGROS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2512450 |  |  | Completed | 1
27522 | NC 2017 | K10 | Region V | Masbate | 113694 | Jamorawon ES | MILAGROS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2501860 |  |  | Completed | 1
27523 | NC 2017 | K10 | Region V | Masbate | 113700 | Milagros East CS | MILAGROS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2501700 |  |  | Completed | 1
27524 | NC 2017 | SHS | Region V | Masbate | 309941 | Cristeta Bagano MHS | MOBO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2491690 |  |  | Completed | 1
27525 | NC 2017 | K10 | Region V | Masbate | 113789 | Biga-a Elem. School | PALANAS | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2928254.17 |  |  | Completed | 1
27526 | NC 2017 | K10 | Region V | Masbate | 113777 | Bontod ES | PALANAS | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4191402.87 |  |  | Completed | 1
27527 | NC 2017 | TVL | Region V | Masbate | 309904 | Palanas National Agriculture High School | PALANAS | 3 | 1 | 5 | WORKSHOP BLDG (7x18) | BATCH 7 | 20937103.9 |  |  | Completed | 1
27528 | NC 2017 | TVL | Region V | Masbate | 309929 | Salvacion National High School | PALANAS | 3 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 7 | 16949683.12 |  |  | Completed | 1
27529 | NC 2017 | TVL | Region V | Masbate | 309942 | San Carlos NHS | PALANAS | 3 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 7 | 12712262.34 |  |  | Completed | 1
27530 | NC 2017 | TVL | Region V | Masbate | 309927 | Buenasuerte Integrated School | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 7 | 16949683.12 |  |  | Completed | 1
27531 | NC 2017 | TVL | Region V | Masbate | 309920 | Conrada Tero Kho Memorial High School | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 8474841.56 |  |  | Completed | 1
27532 | NC 2017 | TVL | Region V | Masbate | 302172 | Tanque National High School | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4386691.12 |  |  | Completed | 1
27533 | NC 2017 | TVL | Region V | Masbate | 302172 | Tanque National High School | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 4317420.78 |  |  | Completed | 1
27534 | NC 2017 | K10 | Region V | Masbate | 113840 | Cabangcalan ES | PLACER | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4331402.87 |  |  | Completed | 1
27535 | NC 2017 | K10 | Region V | Masbate | 113841 | Camayabsan ES | PLACER | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 3138254.17 |  |  | Completed | 1
27536 | NC 2017 | K10 | Region V | Masbate | 113844 | Dangpanan ES | PLACER | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4421402.87 |  |  | Completed | 1
27537 | NC 2017 | K10 | Region V | Masbate | 113824 | Doroteo B. Presno ES | PLACER | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4151402.87 |  |  | Completed | 1
27538 | NC 2017 | K10 | Region V | Masbate | 113846 | Felomino Yray ES | PLACER | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4331402.87 |  |  | Completed | 1
27539 | NC 2017 | K10 | Region V | Masbate | 113825 | Guin-awayan ES | PLACER | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4281402.87 |  |  | Completed | 1
27540 | NC 2017 | K10 | Region V | Masbate | 113827 | Locso-an ES | PLACER | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4521402.87 |  |  | Completed | 1
27541 | NC 2017 | K10 | Region V | Masbate | 113849 | Luna ES | PLACER | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 3138254.17 |  |  | Completed | 1
27542 | NC 2017 | K10 | Region V | Masbate | 113850 | M & R Lecciones ES | PLACER | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 3198254.17 |  |  | Completed | 1
27543 | NC 2017 | K10 | Region V | Masbate | 113828 | Mahayag ES | PLACER | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4421402.87 |  |  | Completed | 1
27544 | NC 2017 | K10 | Region V | Masbate | 113832 | Naocondiot ES | PLACER | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4521402.87 |  |  | Completed | 1
27545 | NC 2017 | K10 | Region V | Masbate | 113837 | Tubod ES | PLACER | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4471402.87 |  |  | Completed | 1
27546 | NC 2017 | K10 | Region V | Masbate | 113837 | Tubod ES | PLACER | 3 |  | 2 | 1STY2CL | BATCH 7 | 3188254.17 |  |  | Completed | 1
27547 | NC 2017 | K10 | Region V | Masbate | 113920 | Laurente ES | SAN PASCUAL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2664508.82 |  |  | Completed | 1
27548 | NC 2017 | SHS | Region V | Masbate | 309937 | Vicente D. Alburo High School | SAN PASCUAL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2663681.11 |  |  | Completed | 1
27549 | NC 2017 | K10 | Region V | Masbate | 113964 | Dapdap ES | USON | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 3078254.17 |  |  | Completed | 1
27550 | NC 2017 | K10 | Region V | Masbate | 113949 | Mabini ES | USON | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2958254.17 |  |  | Completed | 1
27551 | NC 2017 | K10 | Region V | Masbate | 113957 | San Ramon ES | USON | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2888254.17 |  |  | Completed | 1
27552 | NC 2017 | K10 | Region V | Masbate | 113957 | San Ramon ES | USON | 3 |  | 2 | 1STY2CL | BATCH 7 | 2888254.17 |  |  | Completed | 1
27553 | NC 2017 | K10 | Region V | Masbate | 113957 | San Ramon ES | USON | 3 |  | 2 | 1STY2CL | BATCH 7 | 2888254.17 |  |  | Completed | 1
27554 | NC 2017 | K10 | Region V | Masbate | 113958 | San Vicente ES | USON | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2958254.17 |  |  | Completed | 1
27555 | NC 2017 | K10 | Region V | Sorsogon | 113978 | Alegria ES | BARCELONA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3130270.95 |  |  | Completed | 1
27556 | NC 2017 | K10 | Region V | Sorsogon | 113979 | Badang ES | BARCELONA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3280270.95 |  |  | Completed | 1
27557 | NC 2017 | K10 | Region V | Sorsogon | 113981 | Bangate ES | BARCELONA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3060270.95 |  |  | Completed | 1
27558 | NC 2017 | TVL | Region V | Sorsogon | 302184 | Barcelona National Comprehensive High School | BARCELONA | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 8257484.71 |  |  | Completed | 1
27559 | NC 2017 | K10 | Region V | Sorsogon | 113984 | Cagang ES | BARCELONA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4351830.2 |  |  | Completed | 1
27560 | NC 2017 | K10 | Region V | Sorsogon | 113987 | Macabari ES | BARCELONA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4401830.2 |  |  | Completed | 1
27561 | NC 2017 | K10 | Region V | Sorsogon | 113988 | Mapapac ES | BARCELONA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3030270.95 |  |  | Completed | 1
27562 | NC 2017 | K10 | Region V | Sorsogon | 113994 | San Ramon ES | BARCELONA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3030270.95 |  |  | Completed | 1
27563 | NC 2017 | K10 | Region V | Sorsogon | 113999 | Antipolo ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3015270.95 |  |  | Completed | 1
27564 | NC 2017 | K10 | Region V | Sorsogon | 113999 | Antipolo ES | BULAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 3015270.95 |  |  | Completed | 1
27565 | NC 2017 | K10 | Region V | Sorsogon | 114002 | Bonifacio ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3110270.95 |  |  | Completed | 1
27566 | NC 2017 | TVL | Region V | Sorsogon | 302190 | Bulan NHS | BULAN | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 8161340.9 |  |  | Completed | 1
27567 | NC 2017 | TVL | Region V | Sorsogon | 302190 | Bulan NHS | BULAN | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 8161340.9 |  |  | Completed | 1
27568 | NC 2017 | K10 | Region V | Sorsogon | 114004 | Bulan North CS-B | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3030270.95 |  |  | Completed | 1
27569 | NC 2017 | K10 | Region V | Sorsogon | 114035 | Bunga ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3200270.95 |  |  | Completed | 1
27570 | NC 2017 | K10 | Region V | Sorsogon | 114035 | Bunga ES | BULAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 3180270.95 |  |  | Completed | 1
27571 | NC 2017 | K10 | Region V | Sorsogon | 114035 | Bunga ES | BULAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 3180270.95 |  |  | Completed | 1
27572 | NC 2017 | K10 | Region V | Sorsogon | 114036 | Butag ES | BULAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4326830.2 |  |  | Completed | 1
27573 | NC 2017 | K10 | Region V | Sorsogon | 114006 | Cadandanan ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3120270.95 |  |  | Completed | 1
27574 | NC 2017 | K10 | Region V | Sorsogon | 114007 | Calomagon ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3170270.95 |  |  | Completed | 1
27575 | NC 2017 | K10 | Region V | Sorsogon | 114008 | Calpi ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3155270.95 |  |  | Completed | 1
27576 | NC 2017 | TVL | Region V | Sorsogon | 310002 | J. P. Laurel HS | BULAN | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 7126725.26 |  |  | Completed | 1
27577 | NC 2017 | K10 | Region V | Sorsogon | 114015 | J.P. Laurel ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3022770.95 |  |  | Completed | 1
27578 | NC 2017 | K10 | Region V | Sorsogon | 114015 | J.P. Laurel ES | BULAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 3072770.95 |  |  | Completed | 1
27579 | NC 2017 | TVL | Region V | Sorsogon | 302238 | Louella Gotladera Alcoba NHS | BULAN | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 4182598.55 |  |  | Completed | 1
27580 | NC 2017 | K10 | Region V | Sorsogon | 114042 | Marinab ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3155270.95 |  |  | Completed | 1
27581 | NC 2017 | K10 | Region V | Sorsogon | 114042 | Marinab ES | BULAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 3005270.95 |  |  | Completed | 1
27582 | NC 2017 | K10 | Region V | Sorsogon | 114045 | Osmena ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3380270.95 |  |  | Completed | 1
27583 | NC 2017 | K10 | Region V | Sorsogon | 114045 | Osmena ES | BULAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4876830.2 |  |  | Completed | 1
27584 | NC 2017 | K10 | Region V | Sorsogon | 114046 | Otavi ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3105270.95 |  |  | Completed | 1
27585 | NC 2017 | K10 | Region V | Sorsogon | 114023 | Padre Diaz ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2880270.95 |  |  | Completed | 1
27586 | NC 2017 | K10 | Region V | Sorsogon | 114025 | R. Gerona ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3550270.95 |  |  | Completed | 1
27587 | NC 2017 | K10 | Region V | Sorsogon | 114027 | San Francisco ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3105270.95 |  |  | Completed | 1
27588 | NC 2017 | SHS | Region V | Sorsogon | 302237 | San Francisco NHS | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3055270.95 |  |  | Completed | 1
27589 | NC 2017 | TVL | Region V | Sorsogon | 302237 | San Francisco NHS | BULAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4203742.36 |  |  | Completed | 1
27590 | NC 2017 | K10 | Region V | Sorsogon | 114049 | San Isidro ES | BULAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4351830.2 |  |  | Completed | 1
27591 | NC 2017 | K10 | Region V | Sorsogon | 114049 | San Isidro ES | BULAN | 2 |  | 3 | 1STY3CL | BATCH 7 | 4451830.2 |  |  | Completed | 1
27592 | NC 2017 | K10 | Region V | Sorsogon | 175017 | San Jose PS | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3270270.95 |  |  | Completed | 1
27593 | NC 2017 | K10 | Region V | Sorsogon | 175017 | San Jose PS | BULAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 3270270.95 |  |  | Completed | 1
27594 | NC 2017 | K10 | Region V | Sorsogon | 114051 | San Ramon ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3230270.95 |  |  | Completed | 1
27595 | NC 2017 | K10 | Region V | Sorsogon | 114030 | Somagongsong ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3155270.95 |  |  | Completed | 1
27596 | NC 2017 | K10 | Region V | Sorsogon | 114030 | Somagongsong ES | BULAN | 2 |  | 3 | 1STY3CL | BATCH 7 | 4476830.2 |  |  | Completed | 1
27597 | NC 2017 | K10 | Region V | Sorsogon | 114031 | Sta. Remedios ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3180270.95 |  |  | Completed | 1
27598 | NC 2017 | K10 | Region V | Sorsogon | 114055 | Taromata I ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3250270.95 |  |  | Completed | 1
27599 | NC 2017 | K10 | Region V | Sorsogon | 114056 | Taromata II ES | BULAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3580270.95 |  |  | Completed | 1
27600 | NC 2017 | TVL | Region V | Sorsogon | 302192 | Bulusan NHS | BULUSAN | 2 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 12186227.07 |  |  | Completed | 1
27601 | NC 2017 | K10 | Region V | Sorsogon | 114063 | Lalud ES | BULUSAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3030270.95 |  |  | Completed | 1
27602 | NC 2017 | K10 | Region V | Sorsogon | 114063 | Lalud ES | BULUSAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 3030270.95 |  |  | Completed | 1
27603 | NC 2017 | K10 | Region V | Sorsogon | 114068 | San Bernardo ES | BULUSAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4426830.2 |  |  | Completed | 1
27604 | NC 2017 | K10 | Region V | Sorsogon | 114094 | San Pascual ES | CASIGURAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27605 | NC 2017 | K10 | Region V | Sorsogon | 114097 | Tiris ES | CASIGURAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2642123.42 |  |  | Completed | 1
27606 | NC 2017 | K10 | Region V | Sorsogon | 114117 | Amomonting ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2633610.17 |  |  | Completed | 1
27607 | NC 2017 | K10 | Region V | Sorsogon | 114099 | Bagalayag ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3266839.03 |  |  | Completed | 1
27608 | NC 2017 | K10 | Region V | Sorsogon | 310005 | Bagong Sirang HS | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2882606.53 |  |  | Completed | 1
27609 | NC 2017 | K10 | Region V | Sorsogon | 114118 | Buenavista ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3021949.78 |  |  | Completed | 1
27610 | NC 2017 | K10 | Region V | Sorsogon | 114119 | Burabod ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2730062.28 |  |  | Completed | 1
27611 | NC 2017 | K10 | Region V | Sorsogon | 114120 | Caburacan ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2671904.1 |  |  | Completed | 1
27612 | NC 2017 | K10 | Region V | Sorsogon | 114121 | Canjela ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2730062.28 |  |  | Completed | 1
27613 | NC 2017 | K10 | Region V | Sorsogon | 114122 | Cumadcad CS | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2730062.28 |  |  | Completed | 1
27614 | NC 2017 | K10 | Region V | Sorsogon | 114123 | Dinapa ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2675402.95 |  |  | Completed | 1
27615 | NC 2017 | K10 | Region V | Sorsogon | 114107 | Libtong ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2675119.1 |  |  | Completed | 1
27616 | NC 2017 | K10 | Region V | Sorsogon | 114124 | Loreto ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2671904.1 |  |  | Completed | 1
27617 | NC 2017 | K10 | Region V | Sorsogon | 114108 | Maracabac ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2652518.04 |  |  | Completed | 1
27618 | NC 2017 | K10 | Region V | Sorsogon | 114127 | Maypangi ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2674315.34 |  |  | Completed | 1
27619 | NC 2017 | K10 | Region V | Sorsogon | 302227 | Milagrosa NHS | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2730062.28 |  |  | Completed | 1
27620 | NC 2017 | K10 | Region V | Sorsogon | 114110 | Monte Carmelo ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27621 | NC 2017 | SHS | Region V | Sorsogon | 302228 | Oras National High School | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2730062.28 |  |  | Completed | 1
27622 | NC 2017 | K10 | Region V | Sorsogon | 310004 | Pandan HS | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2730062.28 |  |  | Completed | 1
27623 | NC 2017 | K10 | Region V | Sorsogon | 114130 | Quirapi ES | CASTILLA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4044173.94 |  |  | Completed | 1
27624 | NC 2017 | K10 | Region V | Sorsogon | 114131 | Rosal ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2730062.28 |  |  | Completed | 1
27625 | NC 2017 | K10 | Region V | Sorsogon | 114113 | Saclayan ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3143354.63 |  |  | Completed | 1
27626 | NC 2017 | K10 | Region V | Sorsogon | 114132 | Salvacion ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2730062.28 |  |  | Completed | 1
27627 | NC 2017 | K10 | Region V | Sorsogon | 114133 | San Roque ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2730062.28 |  |  | Completed | 1
27628 | NC 2017 | K10 | Region V | Sorsogon | 114134 | San Vicente ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2730062.28 |  |  | Completed | 1
27629 | NC 2017 | K10 | Region V | Sorsogon | 114140 | Baras ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2891202.57 |  |  | Completed | 1
27630 | NC 2017 | K10 | Region V | Sorsogon | 114141 | Bayawas ES | DONSOL | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3935220.98 |  |  | Completed | 1
27631 | NC 2017 | K10 | Region V | Sorsogon | 114160 | Dancalan ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27632 | NC 2017 | K10 | Region V | Sorsogon | 114163 | Girawan ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27633 | NC 2017 | K10 | Region V | Sorsogon | 114146 | Gura ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27634 | NC 2017 | K10 | Region V | Sorsogon | 114164 | Juan Adre ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3364905.7 |  |  | Completed | 1
27635 | NC 2017 | K10 | Region V | Sorsogon | 114166 | Malapoc ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27636 | NC 2017 | K10 | Region V | Sorsogon | 114148 | Nagalon ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2846707.26 |  |  | Completed | 1
27637 | NC 2017 | K10 | Region V | Sorsogon | 114169 | Orange ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2787113.69 |  |  | Completed | 1
27638 | NC 2017 | K10 | Region V | Sorsogon | 114170 | Pangpang ES | DONSOL | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3930002.71 |  |  | Completed | 1
27639 | NC 2017 | K10 | Region V | Sorsogon | 114152 | San Isidro ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3087912.96 |  |  | Completed | 1
27640 | NC 2017 | K10 | Region V | Sorsogon | 114175 | San Jose ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3415985.2 |  |  | Completed | 1
27641 | NC 2017 | K10 | Region V | Sorsogon | 114153 | San Ramon ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2759019.96 |  |  | Completed | 1
27642 | NC 2017 | K10 | Region V | Sorsogon | 114154 | San Vicente ES | DONSOL | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3891749.09 |  |  | Completed | 1
27643 | NC 2017 | K10 | Region V | Sorsogon | 114178 | Suguian ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3415985.2 |  |  | Completed | 1
27644 | NC 2017 | K10 | Region V | Sorsogon | 114156 | Tongdol ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27645 | NC 2017 | K10 | Region V | Sorsogon | 114157 | Tres Maria ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27646 | NC 2017 | K10 | Region V | Sorsogon | 114183 | Vinisitahan ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2709527.41 |  |  | Completed | 1
27647 | NC 2017 | TVL | Region V | Sorsogon | 302182 | Bagacay NHS | GUBAT | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 4032598.55 |  |  | Completed | 1
27648 | NC 2017 | K10 | Region V | Sorsogon | 114189 | Carriedo ES | GUBAT | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4351830.2 |  |  | Completed | 1
27649 | NC 2017 | SHS | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3080270.95 |  |  | Completed | 1
27650 | NC 2017 | TVL | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4128742.36 |  |  | Completed | 1
27651 | NC 2017 | K10 | Region V | Sorsogon | 114211 | Gubat South CS | GUBAT | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2880270.95 |  |  | Completed | 1
27652 | NC 2017 | K10 | Region V | Sorsogon | 114213 | Naagtan ES | GUBAT | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3180270.95 |  |  | Completed | 1
27653 | NC 2017 | K10 | Region V | Sorsogon | 114214 | Nazareno ES | GUBAT | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3000270.95 |  |  | Completed | 1
27654 | NC 2017 | K10 | Region V | Sorsogon | 114219 | Tigkiw ES | GUBAT | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3130270.95 |  |  | Completed | 1
27655 | NC 2017 | K10 | Region V | Sorsogon | 114219 | Tigkiw ES | GUBAT | 2 |  | 3 | 1STY3CL | BATCH 7 | 4376830.2 |  |  | Completed | 1
27656 | NC 2017 | K10 | Region V | Sorsogon | 114223 | Bagsangan ES | IROSIN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3020270.95 |  |  | Completed | 1
27657 | NC 2017 | K10 | Region V | Sorsogon | 114223 | Bagsangan ES | IROSIN | 2 |  | 2 | 1STY2CL | BATCH 7 | 3005270.95 |  |  | Completed | 1
27658 | NC 2017 | K10 | Region V | Sorsogon | 114229 | Casini ES | IROSIN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2935270.95 |  |  | Completed | 1
27659 | NC 2017 | K10 | Region V | Sorsogon | 114229 | Casini ES | IROSIN | 2 |  | 2 | 1STY2CL | BATCH 7 | 2930270.95 |  |  | Completed | 1
27660 | NC 2017 | K10 | Region V | Sorsogon | 114231 | Cogon ES | IROSIN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2980270.95 |  |  | Completed | 1
27661 | NC 2017 | TVL | Region V | Sorsogon | 302211 | Gabao NHS | IROSIN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4128742.36 |  |  | Completed | 1
27662 | NC 2017 | SHS | Region V | Sorsogon | 302212 | Gallanosa National High School | IROSIN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4276830.2 |  |  | Completed | 1
27663 | NC 2017 | TVL | Region V | Sorsogon | 302212 | Gallanosa National High School | IROSIN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4128742.36 |  |  | Completed | 1
27664 | NC 2017 | K10 | Region V | Sorsogon | 114236 | Liang ES | IROSIN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3015270.95 |  |  | Completed | 1
27665 | NC 2017 | K10 | Region V | Sorsogon | 114236 | Liang ES | IROSIN | 2 |  | 2 | 1STY2CL | BATCH 7 | 3005270.95 |  |  | Completed | 1
27666 | NC 2017 | K10 | Region V | Sorsogon | 114242 | San Isidro ES | IROSIN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3035270.95 |  |  | Completed | 1
27667 | NC 2017 | K10 | Region V | Sorsogon | 114242 | San Isidro ES | IROSIN | 2 |  | 2 | 1STY2CL | BATCH 7 | 3005270.95 |  |  | Completed | 1
27668 | NC 2017 | K10 | Region V | Sorsogon | 114243 | Sto. Domingo ES (Lamboon) | IROSIN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3210270.95 |  |  | Completed | 1
27669 | NC 2017 | K10 | Region V | Sorsogon | 114244 | Tabon-Tabon ES | IROSIN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3155270.95 |  |  | Completed | 1
27670 | NC 2017 | K10 | Region V | Sorsogon | 114247 | Tulay ES | IROSIN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3130270.95 |  |  | Completed | 1
27671 | NC 2017 | TVL | Region V | Sorsogon | 302186 | Biriran NHS | JUBAN | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 4107598.55 |  |  | Completed | 1
27672 | NC 2017 | K10 | Region V | Sorsogon | 114264 | Maalo ES | JUBAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3220270.95 |  |  | Completed | 1
27673 | NC 2017 | K10 | Region V | Sorsogon | 175007 | Sipaya ES | JUBAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4546830.2 |  |  | Completed | 1
27674 | NC 2017 | K10 | Region V | Sorsogon | 114273 | Anibong ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27675 | NC 2017 | K10 | Region V | Sorsogon | 114275 | Biga ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2795219.94 |  |  | Completed | 1
27676 | NC 2017 | K10 | Region V | Sorsogon | 114289 | Bulala ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2685257.22 |  |  | Completed | 1
27677 | NC 2017 | K10 | Region V | Sorsogon | 114290 | Busay ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27678 | NC 2017 | K10 | Region V | Sorsogon | 114291 | Caditaan ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27679 | NC 2017 | K10 | Region V | Sorsogon | 302195 | Caditaan NHS | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27680 | NC 2017 | K10 | Region V | Sorsogon | 114277 | Cagtalaba ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2788220.46 |  |  | Completed | 1
27681 | NC 2017 | K10 | Region V | Sorsogon | 114293 | Ginangra ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27682 | NC 2017 | K10 | Region V | Sorsogon | 114296 | Malbog ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2730459.43 |  |  | Completed | 1
27683 | NC 2017 | K10 | Region V | Sorsogon | 114297 | Pawik ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27684 | NC 2017 | K10 | Region V | Sorsogon | 114299 | Siuton ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
27685 | NC 2017 | K10 | Region V | Sorsogon | 114284 | Sta. Lourdes ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2744313.56 |  |  | Completed | 1
27686 | NC 2017 | K10 | Region V | Sorsogon | 114301 | Balocawe ES | MATNOG | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4376830.2 |  |  | Completed | 1
27687 | NC 2017 | K10 | Region V | Sorsogon | 175009 | Calayuan ES | MATNOG | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4446830.2 |  |  | Completed | 1
27688 | NC 2017 | K10 | Region V | Sorsogon | 114309 | Calpi Elementary School | MATNOG | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4776830.2 |  |  | Completed | 1
27689 | NC 2017 | K10 | Region V | Sorsogon | 114311 | Culasi ES | MATNOG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3155270.95 |  |  | Completed | 1
27690 | NC 2017 | K10 | Region V | Sorsogon | 114313 | Genablan Occ. ES | MATNOG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2980270.95 |  |  | Completed | 1
27691 | NC 2017 | K10 | Region V | Sorsogon | 114322 | Matnog CS | MATNOG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3140270.95 |  |  | Completed | 1
27692 | NC 2017 | TVL | Region V | Sorsogon | 302225 | Matnog NHS | MATNOG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4203742.36 |  |  | Completed | 1
27693 | NC 2017 | K10 | Region V | Sorsogon | 114323 | Paghuliran ES | MATNOG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3080270.95 |  |  | Completed | 1
27694 | NC 2017 | K10 | Region V | Sorsogon | 114328 | Sinag-atan ES | MATNOG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3080270.95 |  |  | Completed | 1
27695 | NC 2017 | K10 | Region V | Sorsogon | 114328 | Sinag-atan ES | MATNOG | 2 |  | 3 | 1STY3CL | BATCH 7 | 4346830.2 |  |  | Completed | 1
27696 | NC 2017 | K10 | Region V | Sorsogon | 114331 | Sta. Isabel ES | MATNOG | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4306830.2 |  |  | Completed | 1
27697 | NC 2017 | K10 | Region V | Sorsogon | 114331 | Sta. Isabel ES | MATNOG | 2 |  | 3 | 1STY3CL | BATCH 7 | 4266830.2 |  |  | Completed | 1
27698 | NC 2017 | K10 | Region V | Sorsogon | 114331 | Sta. Isabel ES | MATNOG | 2 |  | 2 | 1STY2CL | BATCH 7 | 3170270.95 |  |  | Completed | 1
27699 | NC 2017 | TVL | Region V | Sorsogon | 310010 | Tiong Hen So MHS | MATNOG | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 4030670.45 |  |  | Completed | 1
27700 | NC 2017 | TVL | Region V | Sorsogon | 310010 | Tiong Hen So MHS | MATNOG | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4030670.45 |  |  | Completed | 1
27701 | NC 2017 | K10 | Region V | Sorsogon | 114336 | Abas ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2737132.67 |  |  | Completed | 1
27702 | NC 2017 | K10 | Region V | Sorsogon | 310006 | Bantayan National High School | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2737132.67 |  |  | Completed | 1
27703 | NC 2017 | K10 | Region V | Sorsogon | 302180 | Bayasong NHS | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2801004.02 |  |  | Completed | 1
27704 | NC 2017 | K10 | Region V | Sorsogon | 114339 | Binanuahan ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2737132.67 |  |  | Completed | 1
27705 | NC 2017 | K10 | Region V | Sorsogon | 114342 | Calpi ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2748219.655 |  |  | Completed | 1
27706 | NC 2017 | K10 | Region V | Sorsogon | 114342 | Calpi ES | PILAR | 1 |  | 2 | 1STY2CL | BATCH 7 | 2748219.655 |  |  | Completed | 1
27707 | NC 2017 | K10 | Region V | Sorsogon | 114343 | Dapdap ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2746072.86 |  |  | Completed | 1
27708 | NC 2017 | K10 | Region V | Sorsogon | 114343 | Dapdap ES | PILAR | 1 |  | 3 | 1STY3CL | BATCH 7 | 4086072.01 |  |  | Completed | 1
27709 | NC 2017 | K10 | Region V | Sorsogon | 114373 | Esmerada ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2767787.92 |  |  | Completed | 1
27710 | NC 2017 | K10 | Region V | Sorsogon | 114373 | Esmerada ES | PILAR | 1 |  | 2 | 1STY2CL | BATCH 7 | 2767787.92 |  |  | Completed | 1
27711 | NC 2017 | K10 | Region V | Sorsogon | 114346 | Guiron ES | PILAR | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4085612.34 |  |  | Completed | 1
27712 | NC 2017 | K10 | Region V | Sorsogon | 114376 | Leona ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2826758.56 |  |  | Completed | 1
27713 | NC 2017 | K10 | Region V | Sorsogon | 114348 | Lipason ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2737132.67 |  |  | Completed | 1
27714 | NC 2017 | K10 | Region V | Sorsogon | 114377 | Lourdes ES | PILAR | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3975417.31 |  |  | Completed | 1
27715 | NC 2017 | K10 | Region V | Sorsogon | 114349 | Lungib ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2737132.67 |  |  | Completed | 1
27716 | NC 2017 | K10 | Region V | Sorsogon | 302217 | Lungib National High School | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2737132.67 |  |  | Completed | 1
27717 | NC 2017 | SHS | Region V | Sorsogon | 302224 | Manuel T. Sia MHS | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2737132.67 |  |  | Completed | 1
27718 | NC 2017 | K10 | Region V | Sorsogon | 114381 | Millabas ES | PILAR | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3947527.9 |  |  | Completed | 1
27719 | NC 2017 | K10 | Region V | Sorsogon | 114353 | Palanas ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2737132.67 |  |  | Completed | 1
27720 | NC 2017 | K10 | Region V | Sorsogon | 114354 | Palaypay PS | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2799173.5867 |  |  | Completed | 1
27721 | NC 2017 | K10 | Region V | Sorsogon | 114384 | Pinagsalog ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2747068.98 |  |  | Completed | 1
27722 | NC 2017 | K10 | Region V | Sorsogon | 114357 | Pineda ES | PILAR | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3975417.31 |  |  | Completed | 1
27723 | NC 2017 | K10 | Region V | Sorsogon | 114358 | Provenir ES | PILAR | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4165215.42 |  |  | Completed | 1
27724 | NC 2017 | K10 | Region V | Sorsogon | 114387 | Sacnangan ES | PILAR | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3964261.55 |  |  | Completed | 1
27725 | NC 2017 | K10 | Region V | Sorsogon | 114359 | San Antonio ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2737132.67 |  |  | Completed | 1
27726 | NC 2017 | K10 | Region V | Sorsogon | 114389 | San Jose ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2760276.72 |  |  | Completed | 1
27727 | NC 2017 | K10 | Region V | Sorsogon | 114362 | Tinago ES | PILAR | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4200011.74 |  |  | Completed | 1
27728 | NC 2017 | K10 | Region V | Sorsogon | 302248 | Tingco NHS | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2898438.87 |  |  | Completed | 1
27729 | NC 2017 | K10 | Region V | Sorsogon | 302248 | Tingco NHS | PILAR | 1 |  | 2 | 1STY2CL | BATCH 7 | 2898438.87 |  |  | Completed | 1
27730 | NC 2017 | K10 | Region V | Sorsogon | 114396 | Prieto Diaz CS | PRIETO DIAZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2880270.95 |  |  | Completed | 1
27731 | NC 2017 | TVL | Region V | Sorsogon | 302232 | Prieto Diaz National High School | PRIETO DIAZ | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 4028742.36 |  |  | Completed | 1
27732 | NC 2017 | TVL | Region V | Sorsogon | 302232 | Prieto Diaz National High School | PRIETO DIAZ | 2 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 7911340.9 |  |  | Completed | 1
27733 | NC 2017 | K10 | Region V | Sorsogon | 114398 | San Antonio ES | PRIETO DIAZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2980270.95 |  |  | Completed | 1
27734 | NC 2017 | K10 | Region V | Sorsogon | 114402 | San Rafael ES | PRIETO DIAZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2930270.95 |  |  | Completed | 1
27735 | NC 2017 | K10 | Region V | Sorsogon | 114402 | San Rafael ES | PRIETO DIAZ | 2 |  | 2 | 1STY2CL | BATCH 7 | 2930270.95 |  |  | Completed | 1
27736 | NC 2017 | K10 | Region V | Sorsogon | 114407 | Ulag ES | PRIETO DIAZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3020270.95 |  |  | Completed | 1
27737 | NC 2017 | K10 | Region V | Sorsogon | 114407 | Ulag ES | PRIETO DIAZ | 2 |  | 2 | 1STY2CL | BATCH 7 | 2930270.95 |  |  | Completed | 1
27738 | NC 2017 | K10 | Region V | Sorsogon | 114408 | Alig-igan ES | SANTA MAGDALENA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3230270.95 |  |  | Completed | 1
27739 | NC 2017 | TVL | Region V | Sorsogon | 302245 | Sta. Magdalena National High School | SANTA MAGDALENA | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 8257484.71 |  |  | Completed | 1
27740 | NC 2017 | SHS | Region V | Sorsogon | 302247 | Talaonga National High School | SANTA MAGDALENA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3255270.95 |  |  | Completed | 1
27741 | NC 2017 | SHS | Region V | Catanduanes | 302094 | Pandan SAT | PANDAN | 0 | 1 | 5 | 1STY5CL | BATCH 8 | 7343170.38 |  |  | Completed | 1
27742 | NC 2017 | TVL | Region V | Masbate City | 500393 | Alejandro Delos Reyes Integrated School | CITY OF MASBATE (Capital) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2573100 |  |  | Completed | 1
27743 | NC 2017 | TVL | Region V | Masbate City | 500393 | Alejandro Delos Reyes Integrated School | CITY OF MASBATE (Capital) | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3060890 |  |  | Completed | 1
27744 | NC 2017 | K10 | Region V | Masbate City | 113665 | AMANCIO AGUILAR ELEMENTARY SCHOOL | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 2469670 |  |  | Completed | 1
27745 | NC 2017 | TVL | Region V | Masbate City | 321805 | Bantigue High School | CITY OF MASBATE (Capital) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2560610 |  |  | Completed | 1
27746 | NC 2017 | K10 | Region V | Masbate City | 113670 | Batuhan East ES | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 2501370 |  |  | Completed | 1
27747 | NC 2017 | TVL | Region V | Masbate City | 321804 | Bayombon High School | CITY OF MASBATE (Capital) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2559040 |  |  | Completed | 1
27748 | NC 2017 | TVL | Region V | Masbate City | 321801 | Bolo National High School | CITY OF MASBATE (Capital) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2641840 |  |  | Completed | 1
27749 | NC 2017 | K10 | Region V | Masbate City | 113695 | Jose Zurbito Sr. ES | CITY OF MASBATE (Capital) | 2 | 1 | 3 | 1STY3CL | BATCH 8 | 3417930 |  |  | Completed | 1
27750 | NC 2017 | SHS | Region V | Masbate City | 302148 | Masbate National Comprehensive High School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 2471860 |  |  | Completed | 1
27751 | NC 2017 | K10 | Region V | Masbate City | 113698 | Mayngaran Elementary School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 2458120 |  |  | Completed | 1
27752 | NC 2017 | TVL | Region V | Camarines Norte | 301897 | Delia Diezmo National High School | CAPALONGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3644567.28 |  |  | Completed | 1
27753 | NC 2017 | TVL | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3409567.28 |  |  | Completed | 1
27754 | NC 2017 | TVL | Region V | Camarines Norte | 301901 | Larap NHS with Annex (CNCEA) | JOSE PANGANIBAN | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 6182101.07 |  |  | Completed | 1
27755 | NC 2017 | TVL | Region V | Camarines Norte | 301920 | Sta. Cruz NHS | JOSE PANGANIBAN | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 6062806.56 |  |  | Completed | 1
27756 | NC 2017 | TVL | Region V | Camarines Norte | 301887 | Bagong Silang II NHS | LABO | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3414567.28 |  |  | Completed | 1
27757 | NC 2017 | TVL | Region V | Camarines Norte | 301894 | Labo Science and Tech. HS | LABO | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6027806.56 |  |  | Completed | 1
27758 | NC 2017 | TVL | Region V | Camarines Norte | 301921 | Tigbinan NHS | LABO | 1 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 9292201.02 |  |  | Completed | 1
27759 | NC 2017 | TVL | Region V | Camarines Norte | 301912 | Tabas National High School | PARACALE | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 6232101.07 |  |  | Completed | 1
27760 | NC 2017 | TVL | Region V | Masbate | 302129 | Cataingan National High School | CATAINGAN | 3 | 1 | 8 | WORKSHOP BLDG (7x18) | BATCH 10 | 35179366.24 |  |  | Completed | 1
27761 | NC 2017 | K10 | Region V | Sorsogon | 114078 | Banawang ES | CASIGURAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
27762 | NC 2017 | K10 | Region V | Sorsogon | 114079 | Boton ES | CASIGURAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2698404.27 |  |  | Completed | 1
27763 | NC 2017 | K10 | Region V | Sorsogon | 114086 | Gogon ES | CASIGURAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2652518.04 |  |  | Completed | 1
27764 | NC 2017 | K10 | Region V | Sorsogon | 114087 | Inlagadian ES | CASIGURAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2681118.91 |  |  | Completed | 1
27765 | NC 2017 | K10 | Region V | Sorsogon | 114089 | Ponong ES | CASIGURAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2726052.56 |  |  | Completed | 1
27766 | NC 2017 | K10 | Region V | Sorsogon | 114090 | Rizal Elementary School | CASIGURAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2641584.46 |  |  | Completed | 1
27767 | NC 2017 | K10 | Region V | Sorsogon | 114093 | San Juan ES | CASIGURAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2666347.73 |  |  | Completed | 1
27768 | NC 2017 | K10 | Region V | Sorsogon | 114093 | San Juan ES | CASIGURAN | 1 |  | 2 | 1STY2CL | BATCH 10 | 2646632.8 |  |  | Completed | 1
27769 | NC 2017 | K10 | Region V | Sorsogon | 302240 | San Juan NHS | CASIGURAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
27770 | NC 2017 | TVL | Region V | Sorsogon | 302199 | Buenavista NHS | CASTILLA | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3678440 |  |  | Completed | 1
27771 | NC 2017 | K10 | Region V | Sorsogon | 114102 | Castilla East CS | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
27772 | NC 2017 | TVL | Region V | Sorsogon | 302202 | Dinapa NHS | CASTILLA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2945971.55 |  |  | Completed | 1
27773 | NC 2017 | TVL | Region V | Sorsogon | 302202 | Dinapa NHS | CASTILLA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2677311.52 |  |  | Completed | 1
27774 | NC 2017 | K10 | Region V | Sorsogon | 114125 | Macalaya ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2652025.92 |  |  | Completed | 1
27775 | NC 2017 | K10 | Region V | Sorsogon | 114109 | Milagrosa ES | CASTILLA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2652025.92 |  |  | Completed | 1
27776 | NC 2017 | K10 | Region V | Sorsogon | 114144 | Donsol East CS | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2694639.68 |  |  | Completed | 1
27777 | NC 2017 | SHS | Region V | Sorsogon | 302204 | Donsol National Comprehensive HS | DONSOL | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3808881.9 |  |  | Completed | 1
27778 | NC 2017 | SHS | Region V | Sorsogon | 302205 | Donsol National Comprehensive HS - Banuang Gurang Extension HS | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3057441.06 |  |  | Completed | 1
27779 | NC 2017 | K10 | Region V | Sorsogon | 114161 | Donsol West CS | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2632645.92 |  |  | Completed | 1
27780 | NC 2017 | K10 | Region V | Sorsogon | 114149 | Ogod ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2654192.8 |  |  | Completed | 1
27781 | NC 2017 | K10 | Region V | Sorsogon | 114174 | San Francisco ES | DONSOL | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2839399.72 |  |  | Completed | 1
27782 | NC 2017 | K10 | Region V | Sorsogon | 114280 | Bartolome G. Lee, Sr. ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
27783 | NC 2017 | K10 | Region V | Sorsogon | 114274 | Behia Elementary School | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2671414.53 |  |  | Completed | 1
27784 | NC 2017 | TVL | Region V | Sorsogon | 310007 | Biton High School | MAGALLANES (34 BRGYS) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3412488.73 |  |  | Completed | 1
27785 | NC 2017 | TVL | Region V | Sorsogon | 310007 | Biton High School | MAGALLANES (34 BRGYS) | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3126234.65 |  |  | Completed | 1
27786 | NC 2017 | K10 | Region V | Sorsogon | 114286 | Iluminado Carranza Elem.School | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2656312.17 |  |  | Completed | 1
27787 | NC 2017 | K10 | Region V | Sorsogon | 114281 | Magallanes North CS | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
27788 | NC 2017 | TVL | Region V | Sorsogon | 302243 | Siuton NHS | MAGALLANES (34 BRGYS) | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2718927.89 |  |  | Completed | 1
27789 | NC 2017 | K10 | Region V | Sorsogon | 114300 | Tula-Tula Sur ES | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2685257.22 |  |  | Completed | 1
27790 | NC 2017 | K10 | Region V | Sorsogon | 114364 | Abucay ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2689479.31 |  |  | Completed | 1
27791 | NC 2017 | K10 | Region V | Sorsogon | 114382 | Naspi Elementary School | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2688942.98 |  |  | Completed | 1
27792 | NC 2017 | K10 | Region V | Sorsogon | 114383 | Pilar II C/S | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2743497.19 |  |  | Completed | 1
27793 | NC 2017 | K10 | Region V | Albay | 111601 | Banao ES | BACACAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3240014.93 |  |  | Completed | 1
27794 | NC 2017 | K10 | Region V | Albay | 111602 | Bariw ES | BACACAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3247941.83 |  |  | Completed | 1
27795 | NC 2017 | K10 | Region V | Albay | 111604 | Cagbulacao ES | BACACAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3266572.93 |  |  | Completed | 1
27796 | NC 2017 | K10 | Region V | Albay | 111607 | Damacan ES | BACACAY | 1 | 1 | 3 | 1STY3CL | BATCH 12 | 4726133.83 |  |  | Completed | 1
27797 | NC 2017 | K10 | Region V | Albay | 111609 | Hindi ES | BACACAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3228262.55 |  |  | Completed | 1
27798 | NC 2017 | K10 | Region V | Albay | 111611 | Mapulang Daga ES | BACACAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3358016.64 |  |  | Completed | 1
27799 | NC 2017 | K10 | Region V | Albay | 111612 | Mataas ES | BACACAY | 1 | 1 | 3 | 1STY3CL | BATCH 12 | 4646558.48 |  |  | Completed | 1
27800 | NC 2017 | K10 | Region V | Albay | 111613 | Misibis ES | BACACAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3266572.93 |  |  | Completed | 1
27801 | NC 2017 | K10 | Region V | Albay | 111614 | Nahapunan ES | BACACAY | 1 | 1 | 3 | 1STY3CL | BATCH 12 | 4984906.51 |  |  | Completed | 1
27802 | NC 2017 | K10 | Region V | Albay | 111616 | Namantao ES | BACACAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3599757.99 |  |  | Completed | 1
27803 | NC 2017 | K10 | Region V | Albay | 111620 | Sula ES | BACACAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3246270.88 |  |  | Completed | 1
27804 | NC 2017 | K10 | Region V | Albay | 111622 | Tambongon ES | BACACAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3862040.15 |  |  | Completed | 1
27805 | NC 2017 | K10 | Region V | Albay | 111623 | Upper Bonga ES | BACACAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3230182.61 |  |  | Completed | 1
27806 | NC 2017 | K10 | Region V | Albay | 111721 | Balite ES | GUINOBATAN | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2753745.92 |  |  | Completed | 1 |  |  | P00181601LZ-CW1 | 17FO0182 - Cluster XVII | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-05 | Brix Const. & Supply
27807 | NC 2017 | K10 | Region V | Albay | 111707 | Bubulusan ES | GUINOBATAN | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 3998435.02 |  |  | Completed | 1 |  |  | P00181597LZ-CW1 | 17FO0181 - Cluster XVI | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | AVIC CONST. & SUPPLY
27808 | NC 2017 | K10 | Region V | Albay | 111709 | Dr. Felipe Cevallos ES | GUINOBATAN | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2753745.92 |  |  | Completed | 1 |  |  | P00181598LZ-CW1 | 17FO0181 - Cluster XV | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | AVIC CONST. & SUPPLY
27809 | NC 2017 | K10 | Region V | Albay | 111729 | Lomacao ES | GUINOBATAN | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 3908435.02 |  |  | Completed | 1 |  |  | P00181602LZ-CW1 | 17FO0182 - Cluster XVII | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-05 | Brix Const. & Supply
27810 | NC 2017 | K10 | Region V | Albay | 111713 | Malabnig ES | GUINOBATAN | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2733745.92 |  |  | Completed | 1 |  |  | P00181599LZ-CW1 | 17FO0181 - Cluster XV | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | AVIC CONST. & SUPPLY
27811 | NC 2017 | K10 | Region V | Albay | 111717 | Muladbucad ES | GUINOBATAN | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 3998435.02 |  |  | Completed | 1 |  |  | P00181600LZ-CW1 | 17FO0182 - Cluster XVI | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-05 | Brix Const. & Supply
27812 | NC 2017 | K10 | Region V | Albay | 111741 | Del Rosario ES | JOVELLAR | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 3998435.02 |  |  | Completed | 1 |  |  | P00181603LZ-CW1 | 7FO0183 - Cluster XVIII | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | ZKR CONST. & SUPPLY
27813 | NC 2017 | K10 | Region V | Albay | 111747 | Lilibdon Elementary School | JOVELLAR | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 4003435.02 |  |  | Completed | 1 |  |  | P00181604LZ-CW1 | 17FO0183 - Cluster XVIII- | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | ZKR CONST. & SUPPLY
27814 | NC 2017 | K10 | Region V | Albay | 111748 | Mamlad ES | JOVELLAR | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 4128435.02 |  |  | Completed | 1 |  |  | P00181605LZ-CW1 | 17FO0183 - Cluster XVIII | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | ZKR CONST. & SUPPLY
27815 | NC 2017 | K10 | Region V | Albay | 111750 | Medalla Milagrosa ES | JOVELLAR | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2743745.92 |  |  | Completed | 1 |  |  | P00181606LZ-CW1 | 17FO0184- Cluster XIX | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | SULVIR ENG'G. & CONST.
27816 | NC 2017 | K10 | Region V | Albay | 111751 | Salvacion ES | JOVELLAR | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2838745.92 |  |  | Completed | 1 |  |  | P00181607LZ-CW1 | 17FO0184- Cluster XIX | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | SULVIR ENG'G. & CONST.
27817 | NC 2017 | K10 | Region V | Albay | 111752 | San Isidro ES | JOVELLAR | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2743745.92 |  |  | Completed | 1 |  |  | P00181608LZ-CW1 | 17FO0184- Cluster XIX | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | SULVIR ENG'G. & CONST.
27818 | NC 2017 | K10 | Region V | Albay | 111753 | San Roque ES | JOVELLAR | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2743745.92 |  |  | Completed | 1 |  |  | P00181608LZ-CW1 | 17FO0185 - Cluster XX | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | AVIC CONST. & SUPPLY
27819 | NC 2017 | K10 | Region V | Albay | 111757 | Tinaldukan ES | JOVELLAR | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2758745.92 |  |  | Completed | 1 |  |  | P00181610LZ-CW1 | 17FO0185 - Cluster XX | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | AVIC CONST. & SUPPLY
27820 | NC 2017 | K10 | Region V | Albay | 111758 | Villa Paz ES | JOVELLAR | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 4043435.02 |  |  | Completed | 1 |  |  | P00181611LZ-CW1 | 17FO0185 - Cluster XX | 2017-11-19 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | AVIC CONST. & SUPPLY
27821 | NC 2017 | K10 | Region V | Albay | 111783 | Alongong ES | LIBON | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 4013435.02 |  |  | Completed | 1 |  |  | P00181623LZ-CW1 | 17FO0189 - Cluster XXIV | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | SR518 CONST. & SUPPLY
27822 | NC 2017 | K10 | Region V | Albay | 111759 | Bacolod ES | LIBON | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 3963435.02 |  |  | Completed | 1 |  |  | P00181612LZ-CW1 | 17FO0186 - Cluster XXI | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | AVIC CONST. & SUPPLY
27823 | NC 2017 | K10 | Region V | Albay | 111787 | Bonbon ES | LIBON | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 3978435.02 |  |  | Completed | 1 |  |  | P00181624LZ-CW1 | 17FO0190 - Cluster XXV | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | WATERTON CONSTRUCTION & REALTY DEV'T. CORP.
27824 | NC 2017 | K10 | Region V | Albay | 111788 | Buga ES | LIBON | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 4008435.02 |  |  | Completed | 1 |  |  | P00181625LZ-CW1 | 17FO0190 - Cluster XXV | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | WATERTON CONSTRUCTION & REALTY DEV'T. CORP.
27825 | NC 2017 | K10 | Region V | Albay | 111789 | Bulusan ES | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2748745.92 |  |  | Completed | 1 |  |  | P00181626LZ-CW1 | 17FO0190 - Cluster XXV | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | WATERTON CONSTRUCTION & REALTY DEV'T. CORP.
27826 | NC 2017 | K10 | Region V | Albay | 111760 | Burabod ES | LIBON | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 3973435.02 |  |  | Completed | 1 |  |  | P00181613LZ-CW1 | 17FO0186 - Cluster XXI | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | AVIC CONST. & SUPPLY
27827 | NC 2017 | K10 | Region V | Albay | 111761 | East Carisac ES | LIBON | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 4023435.02 |  |  | Completed | 1 |  |  | P00181614LZ-CW1 | 17FO0186 - Cluster XXI | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | AVIC CONST. & SUPPLY
27828 | NC 2017 | K10 | Region V | Albay | 111793 | Harigue ES | LIBON | 3 | 1 | 4 | 1STY4CL | BATCH 12 | 5188351.015 |  |  | Completed | 1 |  |  | P00181627LZ-CW1 | 17FO0191 - Cluster XXV | 2017-11-22 | 2017-11-28 | 2017-12-12 | 2017-12-22 | 2018-01-08 | ZHEANTELLE CONST. CORP.
27829 | NC 2017 | K10 | Region V | Albay | 111795 | Libtong ES | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2748745.92 |  |  | Completed | 1 |  |  | P00181628LZ-CW1 | 17FO0191 - Cluster XXV | 2017-11-22 | 2017-11-28 | 2017-12-12 | 2017-12-22 | 2018-01-08 | ZHEANTELLE CONST. CORP.
27830 | NC 2017 | K10 | Region V | Albay | 111765 | Magallang ES | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2748745.92 |  |  | Completed | 1 |  |  | P00181615LZ-CW1 | 17FO0187 - Cluster XXI | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | 4DOVE BUILDERS CORP.
27831 | NC 2017 | K10 | Region V | Albay | 111767 | Marayag ES | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2748745.92 |  |  | Completed | 1 |  |  | P00181616LZ-CW1 | 17FO0187 - Cluster XXII | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | 4DOVE BUILDERS CORP.
27832 | NC 2017 | K10 | Region V | Albay | 111768 | Matara ES | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2748745.92 |  |  | Completed | 1 |  |  | P00181617LZ-CW1 | 17FO0187 - Cluster XXII | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | 4DOVE BUILDERS CORP.
27833 | NC 2017 | K10 | Region V | Albay | 111769 | Natasan ES | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2748745.92 |  |  | Completed | 1 |  |  | P00181618LZ-CW1 | 17FO0188 - Cluster XXIII | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | 4DOVE BUILDERS CORP.
27834 | NC 2017 | K10 | Region V | Albay | 111801 | Rawis ES | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2758745.92 |  |  | Completed | 1 |  |  | P00181629LZ-CW1 | 17FO0191 - Cluster XXVI | 2017-11-22 | 2017-11-28 | 2017-12-12 | 2017-12-22 | 2018-01-08 | ZHEANTELLE CONST. CORP.
27835 | NC 2017 | K10 | Region V | Albay | 111772 | Salvacion ES | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2748745.92 |  |  | Completed | 1 |  |  | P00173120LZ-CW1 | 17FO0188 - Cluster XXII | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | 4DOVE BUILDERS CORP.
27836 | NC 2017 | K10 | Region V | Albay | 111775 | San Antonio ES | LIBON | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 4023435.02 |  |  | Completed | 1 |  |  | P00181620LZ-CW1 | 17FO0188 - Cluster XXI | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | 4DOVE BUILDERS CORP.
27837 | NC 2017 | K10 | Region V | Albay | 111777 | San Pascual ES | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 4023435.02 |  |  | Completed | 1 |  |  | P00181621LZ-CW1 | 17FO0189 - Cluster XXIV | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | SR518 CONST. & SUPPLY
27838 | NC 2017 | K10 | Region V | Albay | 111778 | San Ramon ES | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2748745.92 |  |  | Completed | 1 |  |  | P00181622LZ-CW1 | 17FO0189 - Cluster XXIV | 2017-11-20 | 2017-11-28 | 2017-12-11 | 2017-12-20 | 2018-01-08 | SR518 CONST. & SUPPLY
27839 | NC 2017 | SHS | Region V | Albay | 301877 | San Vicente NHS | LIBON | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2683745.92 |  |  | Completed | 1 |  |  | P00181650LZ-CW1 | 17FO0192 - Cluster XXVII | 2017-11-22 | 2017-11-28 | 2017-12-12 | 2017-12-22 | 2018-01-08 | ZHEANTELLE CONST. CORP.
27840 | NC 2017 | K10 | Region V | Albay | 111806 | Talin-Talin ES | LIBON | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 3953435.02 |  |  | Completed | 1 |  |  | P00181630LZ-CW1 | 17FO0192 - Cluster XXVII | 2017-11-22 | 2017-11-28 | 2017-12-12 | 2017-12-22 | 2018-01-08 | ZHEANTELLE CONST. CORP.
27841 | NC 2017 | K10 | Region V | Albay | 111807 | Tambo ES | LIBON | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 4013435.02 |  |  | Completed | 1 |  |  | P00181631LZ-CW1 | 17FO0192 - Cluster XXV | 2017-11-22 | 2017-11-28 | 2017-12-12 | 2017-12-22 | 2018-01-08 | ZHEANTELLE CONST. CORP.
27842 | NC 2017 | K10 | Region V | Albay | 111856 | Calbayog ES | Malilipot | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3237513.73 |  |  | Completed | 1
27843 | NC 2017 | K10 | Region V | Albay | 111859 | Salvacion ES | Malilipot | 1 | 1 | 3 | 1STY3CL | BATCH 12 | 5109800.72 |  |  | Completed | 1
27844 | NC 2017 | K10 | Region V | Albay | 111860 | San Antonio ES | Malilipot | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3676551.39 |  |  | Completed | 1
27845 | NC 2017 | K10 | Region V | Albay | 111865 | San Roque ES | Malilipot | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3034546.37 |  |  | Completed | 1
27846 | NC 2017 | K10 | Region V | Albay | 111874 | Estancia ES | Malinao | 1 | 1 | 4 | 2STY4CL | BATCH 12 | 9570367.47 |  |  | Completed | 1
27847 | NC 2017 | K10 | Region V | Albay | 111875 | Jonop Elementary School | Malinao | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3243972.09 |  |  | Completed | 1
27848 | NC 2017 | K10 | Region V | Albay | 111876 | Labnig ES | Malinao | 1 | 1 | 4 | 2STY4CL | BATCH 12 | 9573272.22 |  |  | Completed | 1
27849 | NC 2017 | K10 | Region V | Albay | 111905 | Badian ES | OAS | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 4098435.02 |  |  | Completed | 1 |  |  | P00181639LZ-CW1 | 17FO0197 -Cluster XXXII | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | 4DOVE BUILDERS CORP.
27850 | NC 2017 | SHS | Region V | Albay | 301866 | Balogo HS | OAS | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2683745.92 |  |  | Completed | 1 |  |  | P00181648LZ-CW1 | 17FO0200 - Cluster XXXV | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | SR518 CONST. & SUPPLY
27851 | NC 2017 | K10 | Region V | Albay | 111906 | Banao ES | OAS | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 4023435.02 |  |  | Completed | 1 |  |  | P00181640LZ-CW1 | 17FO0197 -Cluster XXXII | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | 4DOVE BUILDERS CORP.
27852 | NC 2017 | K10 | Region V | Albay | 111911 | Cagmanaba ES | OAS | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2853745.92 |  |  | Completed | 1 |  |  | P00181641LZ-CW1 | 17FO0197 -Cluster XXXI | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | 4DOVE BUILDERS CORP.
27853 | NC 2017 | K10 | Region V | Albay | 111932 | Coliat ES | OAS | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2723745.92 |  |  | Completed | 1 |  |  | P00181646LZ-CW1 | 17FO0199 - Cluster XXXIV | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-12 | 4DOVE BUILDERS CORP.
27854 | NC 2017 | K10 | Region V | Albay | 111920 | Saban ES | OAS | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2763745.92 |  |  | Completed | 1 |  |  | P00181649LZ-CW1 | 17FO0198 - Cluster XXXIII | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | 4DOVE BUILDERS CORP.
27855 | NC 2017 | SHS | Region V | Albay | 301870 | Saban National High School | OAS | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2773745.92 |  |  | Completed | 1 |  |  | P00181649LZ-CW1 | 17FO0200 - Cluster XXXV- | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-27 | 2018-01-12 | SR518 CONST. & SUPPLY
27856 | NC 2017 | K10 | Region V | Albay | 111939 | San Agustin ES | OAS | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2728745.92 |  |  | Completed | 1 |  |  | P00181647LZ-CW1 | 17FO0199 - Cluster XXXIV | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-27 | 2018-01-12 | 4DOVE BUILDERS CORP.
27857 | NC 2017 | K10 | Region V | Albay | 111925 | Tapel ES | OAS | 3 | 1 | 3 | 1STY3CL | BATCH 12 | 4108435.02 |  |  | Completed | 1 |  |  | P00181643LZ-CW1 | 17FO0198 - Cluster XXXII | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | 4DOVE BUILDERS CORP.
27858 | NC 2017 | K10 | Region V | Albay | 111925 | Tapel ES | OAS | 3 |  | 3 | 1STY3CL | BATCH 12 | 4108435.02 |  |  | Completed | 1 |  |  | P00181644LZ-CW1 | 17FO0198 - Cluster XXXII | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | 4DOVE BUILDERS CORP.
27859 | NC 2017 | K10 | Region V | Albay | 111926 | Tobgon ES | OAS | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2753745.92 |  |  | Completed | 1 |  |  | P00181645LZ-CW1 | 17FO0199 - Cluster XXXIV | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-12 | 4DOVE BUILDERS CORP.
27860 | NC 2017 | TVL | Region V | Camarines Norte | 301916 | San Francisco National High School | TALISAY | 2 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3369567.28 |  |  | Completed | 1
27861 | NC 2017 | TVL | Region V | Camarines Norte | 301916 | San Francisco National High School | TALISAY | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 200000 |  |  | Completed | 1
27862 | NC 2017 | TVL | Region V | Camarines Sur | 301942 | Barcelonita Fisheries School | CABUSAO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3686685.49 |  |  | Completed | 1
27863 | NC 2017 | SHS | Region V | Camarines Sur | 301942 | Barcelonita Fisheries School | CABUSAO | 1 |  | 2 | 1STY2CL | BATCH 12 | 2789033.54 |  |  | Completed | 1
27864 | NC 2017 | K10 | Region V | Camarines Sur | 112461 | Pandan ES | CABUSAO | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2770805.81 |  |  | Completed | 1
27865 | NC 2017 | TVL | Region V | Camarines Sur | 301943 | Bikal Fisheries School | CARAMOAN | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3860246.16 |  |  | Completed | 1
27866 | NC 2017 | TVL | Region V | Camarines Sur | 301943 | Bikal Fisheries School | CARAMOAN | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3860246.16 |  |  | Completed | 1
27867 | NC 2017 | TVL | Region V | Camarines Sur | 301943 | Bikal Fisheries School | CARAMOAN | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3861246.16 |  |  | Completed | 1
27868 | NC 2017 | K10 | Region V | Camarines Sur | 112552 | Mampirao ES | CARAMOAN | 4 | 1 | 2 | 1STY2CL | BATCH 12 | 3023254.17 |  |  | Completed | 1
27869 | NC 2017 | TVL | Region V | Camarines Sur | 302008 | Oring National High School | CARAMOAN | 4 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 4118148.29 |  |  | Completed | 1
27870 | NC 2017 | TVL | Region V | Camarines Sur | 301966 | Del Gallego National High School | DEL GALLEGO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3834921.18 |  |  | Completed | 1
27871 | NC 2017 | TVL | Region V | Camarines Sur | 301996 | Mansalaya National High School | DEL GALLEGO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3853925.22 |  |  | Completed | 1
27872 | NC 2017 | TVL | Region V | Camarines Sur | 301937 | Bahi National HS | GARCHITORENA | 4 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3993148.29 |  |  | Completed | 1
27873 | NC 2017 | K10 | Region V | Camarines Sur | 112596 | Culapnit ES | GARCHITORENA | 4 | 1 | 2 | 1STY2CL | BATCH 12 | 3023254.17 |  |  | Completed | 1
27874 | NC 2017 | K10 | Region V | Camarines Sur | 112603 | Mansangat ES | GARCHITORENA | 4 | 1 | 2 | 1STY2CL | BATCH 12 | 3023254.17 |  |  | Completed | 1
27875 | NC 2017 | TVL | Region V | Camarines Sur | 302011 | Pambuhan National High School | GARCHITORENA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 4402246.16 |  |  | Completed | 1
27876 | NC 2017 | TVL | Region V | Camarines Sur | 302011 | Pambuhan National High School | GARCHITORENA | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3968148.29 |  |  | Completed | 1
27877 | NC 2017 | TVL | Region V | Camarines Sur | 301975 | Goa National High School | GOA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3952246.16 |  |  | Completed | 1
27878 | NC 2017 | TVL | Region V | Camarines Sur | 301975 | Goa National High School | GOA | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3952246.16 |  |  | Completed | 1
27879 | NC 2017 | TVL | Region V | Camarines Sur | 309741 | Juan L. Filipino Memorial High School | GOA | 4 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3518148.29 |  |  | Completed | 1
27880 | NC 2017 | TVL | Region V | Camarines Sur | 301976 | Pinaglabanan High School | GOA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3902246.16 |  |  | Completed | 1
27881 | NC 2017 | TVL | Region V | Camarines Sur | 301939 | Balaton National High School | LAGONOY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 4002246.16 |  |  | Completed | 1
27882 | NC 2017 | TVL | Region V | Camarines Sur | 301939 | Balaton National High School | LAGONOY | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3568148.29 |  |  | Completed | 1
27883 | NC 2017 | TVL | Region V | Camarines Sur | 301963 | Dahat National Vocational HS | LAGONOY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3752246.16 |  |  | Completed | 1
27884 | NC 2017 | TVL | Region V | Camarines Sur | 301963 | Dahat National Vocational HS | LAGONOY | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3318148.29 |  |  | Completed | 1
27885 | NC 2017 | TVL | Region V | Camarines Sur | 301940 | Himanag National High School | LAGONOY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3952246.16 |  |  | Completed | 1
27886 | NC 2017 | TVL | Region V | Camarines Sur | 301940 | Himanag National High School | LAGONOY | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3518148.29 |  |  | Completed | 1
27887 | NC 2017 | TVL | Region V | Camarines Sur | 302039 | San Ramon Pilot NHS, Lagonoy (frmerly:Sn.Ramon Pilot HS) | LAGONOY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3927246.16 |  |  | Completed | 1
27888 | NC 2017 | TVL | Region V | Camarines Sur | 302039 | San Ramon Pilot NHS, Lagonoy (frmerly:Sn.Ramon Pilot HS) | LAGONOY | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3493148.29 |  |  | Completed | 1
27889 | NC 2017 | TVL | Region V | Camarines Sur | 301958 | Casay National High School | LUPI | 1 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 2744949.93 |  |  | Completed | 1
27890 | NC 2017 | TVL | Region V | Camarines Sur | 301958 | Casay National High School | LUPI | 1 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 2744949.93 |  |  | Completed | 1
27891 | NC 2017 | K10 | Region V | Camarines Sur | 112745 | Lupi CS | LUPI | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2779736.69 |  |  | Completed | 1
27892 | NC 2017 | TVL | Region V | Camarines Sur | 309713 | Buenavista National High School | PRESENTACION (PARUBCAN) | 4 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3964694.08 |  |  | Completed | 1
27893 | NC 2017 | TVL | Region V | Camarines Sur | 301989 | Federico P. Condat NHS (frmerly: Maangas HS ) | PRESENTACION (PARUBCAN) | 4 | 1 | 1 | ICT WORKSHOP BLDG (7x18) | BATCH 12 | 3964963.12 |  |  | Completed | 1
27894 | NC 2017 | TVL | Region V | Camarines Sur | 309772 | Lidong High School | PRESENTACION (PARUBCAN) | 4 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3618148.29 |  |  | Completed | 1
27895 | NC 2017 | TVL | Region V | Camarines Sur | 309772 | Lidong High School | PRESENTACION (PARUBCAN) | 4 |  | 1 | Science Lab WORKSHOP BLDG (7x18) | BATCH 12 | 3939963.12 |  |  | Completed | 1
27896 | NC 2017 | TVL | Region V | Camarines Sur | 309772 | Lidong High School | PRESENTACION (PARUBCAN) | 4 |  | 1 | ICT WORKSHOP BLDG (7x18) | BATCH 12 | 3939963.12 |  |  | Completed | 1
27897 | NC 2017 | K10 | Region V | Camarines Sur | 112951 | Buenasuerte ES | RAGAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2803245.07 |  |  | Completed | 1
27898 | NC 2017 | SHS | Region V | Camarines Sur | 301977 | Godofredo Reyes Sr. National HS | RAGAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2859122.09 |  |  | Completed | 1
27899 | NC 2017 | K10 | Region V | Camarines Sur | 112960 | Liboro ES | RAGAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2806962.51 |  |  | Completed | 1
27900 | NC 2017 | K10 | Region V | Camarines Sur | 112968 | Pugod ES | RAGAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2844908.33 |  |  | Completed | 1
27901 | NC 2017 | K10 | Region V | Camarines Sur | 112969 | Ragay CS | RAGAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2789093.35 |  |  | Completed | 1
27902 | NC 2017 | SHS | Region V | Camarines Sur | 302020 | Ragay National Agricultural and Fisheries School (RNAFS) | RAGAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2805306.9 |  |  | Completed | 1
27903 | NC 2017 | K10 | Region V | Camarines Sur | 112972 | San Rafael Elementary School | RAGAY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2833585.92 |  |  | Completed | 1
27904 | NC 2017 | TVL | Region V | Camarines Sur | 301929 | Simeon Tycangco Memorial High School | RAGAY | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3762459.68 |  |  | Completed | 1
27905 | NC 2017 | TVL | Region V | Camarines Sur | 301929 | Simeon Tycangco Memorial High School | RAGAY | 1 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 2779715.47 |  |  | Completed | 1
27906 | NC 2017 | TVL | Region V | Camarines Sur | 301929 | Simeon Tycangco Memorial High School | RAGAY | 1 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 2779715.47 |  |  | Completed | 1
27907 | NC 2017 | TVL | Region V | Camarines Sur | 301930 | Sisa Feliciano MHS | RAGAY | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3782565.26 |  |  | Completed | 1
27908 | NC 2017 | TVL | Region V | Camarines Sur | 302064 | Tomas A. Andaya, Sr. National High School | RAGAY | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3753257.11 |  |  | Completed | 1
27909 | NC 2017 | TVL | Region V | Camarines Sur | 309715 | Nato National High School | SAGÑAY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3752246.16 |  |  | Completed | 1
27910 | NC 2017 | TVL | Region V | Camarines Sur | 309715 | Nato National High School | SAGÑAY | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3318148.29 |  |  | Completed | 1
27911 | NC 2017 | TVL | Region V | Camarines Sur | 309714 | Sagñay Southeastern HS | SAGÑAY | 4 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3418148.29 |  |  | Completed | 1
27912 | NC 2017 | TVL | Region V | Camarines Sur | 302035 | Rangas-Ramos NHS (frmerly:Sn Jose Fish.Sch.) | SAN JOSE | 4 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3368148.29 |  |  | Completed | 1
27913 | NC 2017 | TVL | Region V | Camarines Sur | 302036 | San Jose NHS | SAN JOSE | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 4002246.16 |  |  | Completed | 1
27914 | NC 2017 | TVL | Region V | Camarines Sur | 309771 | Villafuerte-Peña High School | SAN JOSE | 4 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3243148.29 |  |  | Completed | 1
27915 | NC 2017 | TVL | Region V | Camarines Sur | 309771 | Villafuerte-Peña High School | SAN JOSE | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3243148.29 |  |  | Completed | 1
27916 | NC 2017 | TVL | Region V | Camarines Sur | 301984 | Vivencio Obias - Kinalansan NHS (formerly: Kinalansan NHS) | SAN JOSE | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3902246.16 |  |  | Completed | 1
27917 | NC 2017 | TVL | Region V | Camarines Sur | 301984 | Vivencio Obias - Kinalansan NHS (formerly: Kinalansan NHS) | SAN JOSE | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3468148.29 |  |  | Completed | 1
27918 | NC 2017 | TVL | Region V | Camarines Sur | 301927 | Anib National High School | SIPOCOT | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3736095.19 |  |  | Completed | 1
27919 | NC 2017 | TVL | Region V | Camarines Sur | 301927 | Anib National High School | SIPOCOT | 1 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 2756988.68 |  |  | Completed | 1
27920 | NC 2017 | TVL | Region V | Camarines Sur | 301927 | Anib National High School | SIPOCOT | 1 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 2756988.68 |  |  | Completed | 1
27921 | NC 2017 | TVL | Region V | Camarines Sur | 309743 | Bolo Norte HS | SIPOCOT | 1 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 2733500.06 |  |  | Completed | 1
27922 | NC 2017 | TVL | Region V | Camarines Sur | 309743 | Bolo Norte HS | SIPOCOT | 1 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 2733500.06 |  |  | Completed | 1
27923 | NC 2017 | K10 | Region V | Camarines Sur | 113059 | Cotmo ES | SIPOCOT | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2996329.62 |  |  | Completed | 1
27924 | NC 2017 | K10 | Region V | Camarines Sur | 113073 | North Villazar ES | SIPOCOT | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 3006360.63 |  |  | Completed | 1
27925 | NC 2017 | TVL | Region V | Camarines Sur | 309755 | Sacred Heart High School | SIPOCOT | 1 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 2825648.91 |  |  | Completed | 1
27926 | NC 2017 | TVL | Region V | Camarines Sur | 309755 | Sacred Heart High School | SIPOCOT | 1 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 2825648.91 |  |  | Completed | 1
27927 | NC 2017 | K10 | Region V | Camarines Sur | 113067 | Sipocot North CS | SIPOCOT | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2834040.86 |  |  | Completed | 1
27928 | NC 2017 | TVL | Region V | Camarines Sur | 302068 | Villazar National High School | SIPOCOT | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3702626.89 |  |  | Completed | 1
27929 | NC 2017 | TVL | Region V | Camarines Sur | 302048 | Siruma NHS | SIRUMA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3952246.16 |  |  | Completed | 1
27930 | NC 2017 | TVL | Region V | Camarines Sur | 302048 | Siruma NHS | SIRUMA | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3952246.16 |  |  | Completed | 1
27931 | NC 2017 | TVL | Region V | Camarines Sur | 302048 | Siruma NHS | SIRUMA | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3952246.16 |  |  | Completed | 1
27932 | NC 2017 | TVL | Region V | Camarines Sur | 302058 | Tandoc HS | SIRUMA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 4187246.16 |  |  | Completed | 1
27933 | NC 2017 | TVL | Region V | Camarines Sur | 302058 | Tandoc HS | SIRUMA | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3703148.29 |  |  | Completed | 1
27934 | NC 2017 | TVL | Region V | Camarines Sur | 302069 | Vito HS | SIRUMA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 4552246.16 |  |  | Completed | 1
27935 | NC 2017 | TVL | Region V | Camarines Sur | 309721 | Huyonhuyon HS | TIGAON | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3677246.16 |  |  | Completed | 1
27936 | NC 2017 | TVL | Region V | Camarines Sur | 309721 | Huyonhuyon HS | TIGAON | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3243148.29 |  |  | Completed | 1
27937 | NC 2017 | TVL | Region V | Camarines Sur | 301986 | La Salvacion NHS | TIGAON | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3802246.16 |  |  | Completed | 1
27938 | NC 2017 | TVL | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3727246.16 |  |  | Completed | 1
27939 | NC 2017 | TVL | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3727246.16 |  |  | Completed | 1
27940 | NC 2017 | TVL | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3727246.16 |  |  | Completed | 1
27941 | NC 2017 | TVL | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3727246.16 |  |  | Completed | 1
27942 | NC 2017 | TVL | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3318148.29 |  |  | Completed | 1
27943 | NC 2017 | TVL | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3318148.29 |  |  | Completed | 1
27944 | NC 2017 | TVL | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3318148.29 |  |  | Completed | 1
27945 | NC 2017 | TVL | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 |  | 1 | Science Lab WORKSHOP BLDG (7x18) | BATCH 12 | 3614963.12 |  |  | Completed | 1
27946 | NC 2017 | TVL | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 |  | 1 | Science Lab WORKSHOP BLDG (7x18) | BATCH 12 | 3614963.12 |  |  | Completed | 1
27947 | NC 2017 | TVL | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 |  | 1 | ICT WORKSHOP BLDG (7x18) | BATCH 12 | 3614963.12 |  |  | Completed | 1
27948 | NC 2017 | TVL | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 |  | 1 | ICT WORKSHOP BLDG (7x18) | BATCH 12 | 3614963.12 |  |  | Completed | 1
27949 | NC 2017 | TVL | Region V | Camarines Sur | 302038 | San Rafael National High School | TIGAON | 4 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3468148.29 |  |  | Completed | 1
27950 | NC 2017 | TVL | Region V | Camarines Sur | 301928 | Antipolo National High School, Tinambac | TINAMBAC | 4 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3318148.29 |  |  | Completed | 1
27951 | NC 2017 | TVL | Region V | Camarines Sur | 301934 | BAGACAY NATIONAL HIGH SCHOOL | TINAMBAC | 4 | 1 | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3408148.29 |  |  | Completed | 1
27952 | NC 2017 | TVL | Region V | Camarines Sur | 301969 | Don Servillano Platon Memorial NHS | TINAMBAC | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3677246.16 |  |  | Completed | 1
27953 | NC 2017 | TVL | Region V | Camarines Sur | 301969 | Don Servillano Platon Memorial NHS | TINAMBAC | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3677246.16 |  |  | Completed | 1
27954 | NC 2017 | TVL | Region V | Camarines Sur | 301969 | Don Servillano Platon Memorial NHS | TINAMBAC | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3243148.29 |  |  | Completed | 1
27955 | NC 2017 | TVL | Region V | Camarines Sur | 301969 | Don Servillano Platon Memorial NHS | TINAMBAC | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3243148.29 |  |  | Completed | 1
27956 | NC 2017 | TVL | Region V | Camarines Sur | 302024 | Magsaysay National High School | TINAMBAC | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3802246.16 |  |  | Completed | 1
27957 | NC 2017 | TVL | Region V | Camarines Sur | 302024 | Magsaysay National High School | TINAMBAC | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3368148.29 |  |  | Completed | 1
27958 | NC 2017 | TVL | Region V | Camarines Sur | 302056 | Tamban NHS | TINAMBAC | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3812246.16 |  |  | Completed | 1
27959 | NC 2017 | TVL | Region V | Camarines Sur | 302063 | Tierra Nevada HS | TINAMBAC | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3737246.16 |  |  | Completed | 1
27960 | NC 2017 | TVL | Region V | Camarines Sur | 302063 | Tierra Nevada HS | TINAMBAC | 4 |  | 1 | Regular WORKSHOP BLDG (7x18) | BATCH 12 | 3303148.29 |  |  | Completed | 1
27961 | NC 2017 | TVL | Region V | Sorsogon City | 302272 | Celestino G. Tabuena Memorial NHS | CITY OF SORSOGON (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2932762.77 |  |  | Completed | 1
27962 | NC 2017 | TVL | Region V | Sorsogon City | 310402 | Panlayaan Technical Vocational High School | CITY OF SORSOGON (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2900000 |  |  | Completed | 1
27963 | NC 2017 | TVL | Region V | Tabaco City | 310501 | Bognabong High School | CITY OF TABACO | 1 | 1 | 3 | 3STY3 Regular Workshop | BATCH 12 | 16901464.47 |  |  | Completed | 1
27964 | NC 2017 | SHS | Region V | Tabaco City | 302282 | San Antonio NHS, Tabaco | CITY OF TABACO | 1 | 1 | 15 | 3STY15CL | BATCH 12 | 53352042.54 |  |  | Completed | 1
27965 | NC 2017 | SHS | Region V | Tabaco City | 302284 | San Miguel NHS | CITY OF TABACO | 1 | 1 | 6 | 2STY6CL | BATCH 12 | 13205460.98 |  |  | Completed | 1
27966 | NC 2017 | K10 | Region V | Albay | 111941 | San Juan ES | OAS | 3 | 1 | 2 | 1STY2CL | BATCH 13 | 2738745.92 |  |  | Completed | 1 |  |  | P00182942LZ-CW1 | 17FO0200 - Cluster XXXV- | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-27 | 2018-01-12 | SR518 CONST. & SUPPLY
27967 | NC 2017 | K10 | Region V | Albay | 111962 | Malidong ES | PIO DURAN | 3 | 1 | 2 | 1STY2CL | BATCH 13 | 2808745.92 |  |  | Completed | 1 |  |  | P00182943LZ-CW1 | 17FO0193 - Cluster XXVIII | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | 9 LEAVES BUILDERS & SUPPLY CORP.
27968 | NC 2017 | K10 | Region V | Albay | 111967 | Nablangbulod ES | PIO DURAN | 3 | 1 | 2 | 1STY2CL | BATCH 13 | 2783745.92 |  |  | Completed | 1 |  |  | P00182944LZ-CW1 | 17FO0193 - Cluster XXVII | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | 9 LEAVES BUILDERS & SUPPLY CORP.
27969 | NC 2017 | K10 | Region V | Albay | 112000 | Agos ES | POLANGUI | 3 | 1 | 2 | 1STY2CL | BATCH 13 | 2708745.92 |  |  | Completed | 1 |  |  | P00182947LZ-CW1 | 17FO0195 - Cluster XXX | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | ZHEANTELLE CONST. CORP.
27970 | NC 2017 | K10 | Region V | Albay | 112005 | La Medalla ES | POLANGUI | 3 | 1 | 3 | 1STY3CL | BATCH 13 | 4058435.02 |  |  | Completed | 1 |  |  | P00182948LZ-CW1 | 17FO0195 - Cluster XXX | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | ZHEANTELLE CONST. CORP.
27971 | NC 2017 | K10 | Region V | Albay | 112009 | Magurang ES | POLANGUI | 3 | 1 | 2 | 1STY2CL | BATCH 13 | 2773745.92 |  |  | Completed | 1 |  |  | P00182949LZ-CW1 | 17FO0195 - Cluster XXX | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | ZHEANTELLE CONST. CORP.
27972 | NC 2017 | K10 | Region V | Albay | 112010 | Matacon ES | POLANGUI | 3 | 1 | 3 | 1STY3CL | BATCH 13 | 4018435.02 |  |  | Completed | 1 |  |  | P00182950LZ-CW1 | 17FO0196 - Cluster XXXI | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | 4DOVE BUILDERS CORP.
27973 | NC 2017 | K10 | Region V | Albay | 111990 | Maysua ES | POLANGUI | 3 | 1 | 3 | 1STY3CL | BATCH 13 | 3998435.02 |  |  | Completed | 1 |  |  | P00182945LZ-CW1 | 17FO0194- Cluster XX | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | ZHEANTELLE CONST. CORP.
27974 | NC 2017 | K10 | Region V | Albay | 111995 | Polangui North CS | POLANGUI | 3 | 1 | 3 | 1STY3CL | BATCH 13 | 3908435.02 |  |  | Completed | 1 |  |  | P00182946LZ-CW1 | 17FO0194 - Cluster XXIX | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | ZHEANTELLE CONST. CORP.
27975 | NC 2017 | K10 | Region V | Albay | 112014 | Santicon ES | POLANGUI | 3 | 1 | 3 | 1STY3CL | BATCH 13 | 3968435.02 |  |  | Completed | 1 |  |  | P00182951LZ-CW1 | 17FO0196 - Cluster XXXI- | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | 4DOVE BUILDERS CORP.
27976 | NC 2017 | K10 | Region V | Albay | 112015 | Sta. Teresita ES | POLANGUI | 3 | 1 | 2 | 1STY2CL | BATCH 13 | 2748745.92 |  |  | Completed | 1 |  |  | P00182952LZ-CW1 | 17FO0196 - Cluster XXXI- | 2017-11-22 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-08 | 4DOVE BUILDERS CORP.
27977 | NC 2017 | TVL | Region V | Sorsogon | 302198 | Castilla NHS | CASTILLA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 2900000 |  |  | Completed | 1
27978 | NC 2017 | TVL | Region V | Sorsogon | 302201 | Cumadcad NHS | CASTILLA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 2999237.62 |  |  | Completed | 1
27979 | NC 2017 | TVL | Region V | Sorsogon | 302194 | Cabugao NHS | DONSOL | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 4195822 |  |  | Completed | 1
27980 | NC 2017 | TVL | Region V | Sorsogon | 302207 | Donsol Vocational HS | DONSOL | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3593386.21 |  |  | Completed | 1
27981 | NC 2017 | TVL | Region V | Sorsogon | 302183 | Bagatao NHS | MAGALLANES (34 BRGYS) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3287284.1 |  |  | Completed | 1
27982 | NC 2017 | TVL | Region V | Sorsogon | 302222 | Magallanes National High School | MAGALLANES (34 BRGYS) | 1 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 9280800 |  |  | Completed | 1
27983 | NC 2017 | TVL | Region V | Sorsogon | 302179 | Abucay National High School | PILAR | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3096823.05 |  |  | Completed | 1
27984 | NC 2017 | TVL | Region V | Sorsogon | 302236 | Salvacion National High School | PILAR | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 2998562.54 |  |  | Completed | 1
27985 | NC 2017 | K10 | Region V | Tabaco City | 114594 | Oson ES | CITY OF TABACO | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9533150.61 |  |  | Completed | 1
27986 | NC 2017 | K10 | Region V | Tabaco City | 114595 | Pawa ES | CITY OF TABACO | 1 | 1 | 6 | 3STY6CL | BATCH 13 | 17658246.46 |  |  | Completed | 1
27987 | NC 2017 | K10 | Region V | Tabaco City | 114595 | Pawa ES | CITY OF TABACO | 1 |  | 6 | 2STY6CL | BATCH 13 | 11602343.77 |  |  | Completed | 1
27988 | NC 2017 | TVL | Region V | Tabaco City | 302282 | San Antonio NHS, Tabaco | CITY OF TABACO | 1 | 1 | 3 | 3STY3 Workshop Bldg | BATCH 13 | 17405985.8 |  |  | Completed | 1
27989 | NC 2017 | K10 | Region V | Tabaco City | 114599 | San Carlos ES | CITY OF TABACO | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9676147.87 |  |  | Completed | 1
27990 | NC 2017 | TVL | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 | 1 | 3 | 3STY3 Regular Workshop | BATCH 13 | 16901464.47 |  |  | Completed | 1
27991 | NC 2017 | TVL | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 |  | 3 | 3STY3 Regular Workshop | BATCH 13 | 16901464.47 |  |  | Completed | 1
27992 | NC 2017 | TVL | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 |  | 3 | 3STY3 Regular Workshop | BATCH 13 | 16901464.47 |  |  | Completed | 1
27993 | NC 2017 | K10 | Region V | Tabaco City | 114624 | Tabaco South CES | CITY OF TABACO | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 11427784.89 |  |  | Completed | 1
27994 | NC 2017 | K10 | Region V | Albay | 111626 | Bariw ES | CAMALIG | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9956472.97 |  |  | Completed | 1
27995 | NC 2017 | K10 | Region V | Albay | 111665 | Busay ES | DARAGA (LOCSIN) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9459287.7 |  |  | Completed | 1
27996 | NC 2017 | K10 | Region V | Albay | 111677 | Tagas Elementary School | DARAGA (LOCSIN) | 2 | 1 | 12 | 3STY12CL | BATCH 14 | 47713202.97 |  |  | Completed | 1
27997 | NC 2017 | K10 | Region V | Albay | 111678 | Upper Malabog ES | DARAGA (LOCSIN) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9719903.45 |  |  | Completed | 1
27998 | NC 2017 | K10 | Region V | Albay | 111686 | Gabawan ES | DARAGA (LOCSIN) | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 12542930.49 |  |  | Completed | 1
27999 | NC 2017 | K10 | Region V | Albay | 111691 | Lacag ES | DARAGA (LOCSIN) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9795516.96 |  |  | Completed | 1
28000 | NC 2017 | K10 | Region V | Camarines Norte | 112108 | Calabaca ES | CAPALONGA | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 15064500 |  |  | Completed | 1
28001 | NC 2017 | K10 | Region V | Camarines Norte | 112110 | Capalonga CS | CAPALONGA | 1 | 1 | 12 | 2STY12CL | BATCH 14 | 28719199.87 |  |  | Completed | 1
28002 | NC 2017 | K10 | Region V | Camarines Norte | 112110 | Capalonga CS | CAPALONGA | 1 |  | 4 | 2STY4CL | BATCH 14 | 11392000 |  |  | Completed | 1
28003 | NC 2017 | K10 | Region V | Camarines Norte | 112125 | San Roque ES | Capalonga | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 11292000 |  |  | Completed | 1
28004 | NC 2017 | K10 | Region V | Camarines Norte | 112151 | Jose Panganiban ES | Jose Panganiban East | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 11442000 |  |  | Completed | 1
28005 | NC 2017 | K10 | Region V | Camarines Norte | 112179 | Bulhao ES | LABO | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 11192000 |  |  | Completed | 1
28006 | NC 2017 | K10 | Region V | Camarines Norte | 112186 | Labo Elementary school | LABO | 1 | 1 | 12 | 2STY12CL | BATCH 14 | 28519199.87 |  |  | Completed | 1
28007 | NC 2017 | K10 | Region V | Camarines Norte | 112186 | Labo Elementary school | LABO | 1 |  | 12 | 2STY12CL | BATCH 14 | 28519199.87 |  |  | Completed | 1
28008 | NC 2017 | K10 | Region V | Camarines Norte | 112196 | Tulay Na Lupa ES | LABO | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 15014500 |  |  | Completed | 1
28009 | NC 2017 | K10 | Region V | Camarines Norte | 112202 | Calabasa ES | Labo West | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 14764500 |  |  | Completed | 1
28010 | NC 2017 | K10 | Region V | Camarines Norte | 112208 | Felix Asis ES | LABO | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 11242000 |  |  | Completed | 1
28011 | NC 2017 | K10 | Region V | Camarines Norte | 112242 | Batobalani Elementary School | PARACALE | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 11292000 |  |  | Completed | 1
28012 | NC 2017 | K10 | Region V | Camarines Norte | 112244 | Capacuan ES | PARACALE | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 14864500 |  |  | Completed | 1
28013 | NC 2017 | K10 | Region V | Camarines Norte | 112246 | Dalnac ES | PARACALE | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 11292000 |  |  | Completed | 1
28014 | NC 2017 | K10 | Region V | Camarines Norte | 112247 | Gumaus ES | PARACALE | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 11292000 |  |  | Completed | 1
28015 | NC 2017 | K10 | Region V | Camarines Norte | 112251 | Ignacio Español ES | PARACALE | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 11342000 |  |  | Completed | 1
28016 | NC 2017 | K10 | Region V | Camarines Norte | 112254 | Paracale Central School | PARACALE | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 15014500 |  |  | Completed | 1
28017 | NC 2017 | K10 | Region V | Camarines Norte | 112255 | Pedro V. Moreno (Malaguit) ES | PARACALE | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 14864500 |  |  | Completed | 1
28018 | NC 2017 | K10 | Region V | Camarines Norte | 112257 | S. Basilio ES | PARACALE | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 11292000 |  |  | Completed | 1
28019 | NC 2017 | K10 | Region V | Camarines Norte | 112259 | Tawig ES | PARACALE | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 11092000 |  |  | Completed | 1
28020 | NC 2017 | K10 | Region V | Camarines Norte | 112260 | Tugos ES | PARACALE | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 11142000 |  |  | Completed | 1
28021 | NC 2017 | K10 | Region V | Camarines Norte | 112288 | Sta. Elena ES | SANTA ELENA | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 15114500 |  |  | Completed | 1
28022 | NC 2017 | K10 | Region V | Camarines Norte | 173005 | Guitol ES | SANTA ELENA | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 11242000 |  |  | Completed | 1
28023 | NC 2017 | TVL | Region V | Camarines Norte | 301886 | Bagong Silang I HS | LABO | 1 | 1 | 2 | 2STY2CL Regular Workshop | BATCH 14 | 11351972.94 |  |  | Completed | 1
28024 | NC 2017 | TVL | Region V | Camarines Norte | 301886 | Bagong Silang I HS | LABO | 1 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21432657.49 |  |  | Completed | 1
28025 | NC 2017 | TVL | Region V | Camarines Norte | 301887 | Bagong Silang II NHS | LABO | 1 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 16052147.49 |  |  | Completed | 1
28026 | NC 2017 | TVL | Region V | Camarines Norte | 301888 | E.P. Borja HS (Basiad NHS) | SANTA ELENA | 1 | 1 | 2 | 2STY2CL Science Lab | BATCH 14 | 11547972.94 |  |  | Completed | 1
28027 | NC 2017 | TVL | Region V | Camarines Norte | 301888 | E.P. Borja HS (Basiad NHS) | SANTA ELENA | 1 |  | 2 | 2STY2CL ICT Lab | BATCH 14 | 11426972.94 |  |  | Completed | 1
28028 | NC 2017 | TVL | Region V | Camarines Norte | 301890 | Batobalani National High School | PARACALE | 1 | 1 | 4 | 2STY4CL Regular Workshop | BATCH 14 | 21467657.49 |  |  | Completed | 1
28029 | NC 2017 | TVL | Region V | Camarines Norte | 301890 | Batobalani National High School | PARACALE | 1 |  | 2 | 2STY2CL Science Lab | BATCH 14 | 11416972.94 |  |  | Completed | 1
28030 | NC 2017 | TVL | Region V | Camarines Norte | 301890 | Batobalani National High School | PARACALE | 1 |  | 2 | 2STY2CL ICT Lab | BATCH 14 | 11301972.94 |  |  | Completed | 1
28031 | NC 2017 | SHS | Region V | Camarines Norte | 301890 | Batobalani NHS | PARACALE | 1 |  | 4 | 2STY4CL | BATCH 14 | 11242000 |  |  | Completed | 1
28032 | NC 2017 | TVL | Region V | Camarines Norte | 301893 | Daguit NHS | LABO | 1 |  | 4 | 2STY4CL Regular Workshop | BATCH 14 | 16087147.49 |  |  | Completed | 1
28033 | NC 2017 | TVL | Region V | Camarines Norte | 301894 | Labo Science and Tech. HS | LABO | 1 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21407657.49 |  |  | Completed | 1
28034 | NC 2017 | TVL | Region V | Camarines Norte | 301896 | Gonzalo Aler NHS | CAPALONGA | 1 | 1 | 4 | 2STY4CL Regular Workshop | BATCH 14 | 21567657.49 |  |  | Completed | 1
28035 | NC 2017 | TVL | Region V | Camarines Norte | 301896 | Gonzalo Aler NHS | CAPALONGA | 1 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21532657.49 |  |  | Completed | 1
28036 | NC 2017 | TVL | Region V | Camarines Norte | 301897 | Delia Diezmo National High School | CAPALONGA | 1 | 1 | 4 | 2STY4CL Regular Workshop | BATCH 14 | 21517657.49 |  |  | Completed | 1
28037 | NC 2017 | TVL | Region V | Camarines Norte | 301897 | Delia Diezmo National High School | CAPALONGA | 1 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21482657.49 |  |  | Completed | 1
28038 | NC 2017 | TVL | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1 | 1 | 4 | 2STY4CL Regular Workshop | BATCH 14 | 21442657.49 |  |  | Completed | 1
28039 | NC 2017 | TVL | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21407657.49 |  |  | Completed | 1
28040 | NC 2017 | SHS | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1 |  | 12 | 3STY12CL | BATCH 14 | 32160418.69 |  |  | Completed | 1
28041 | NC 2017 | TVL | Region V | Camarines Norte | 301899 | Labo National High School | LABO | 1 | 1 | 2 | 2STY2CL Science Lab | BATCH 14 | 11416972.94 |  |  | Completed | 1
28042 | NC 2017 | TVL | Region V | Camarines Norte | 301899 | Labo National High School | LABO | 1 |  | 2 | 2STY2CL ICT Lab | BATCH 14 | 11301972.94 |  |  | Completed | 1
28043 | NC 2017 | TVL | Region V | Camarines Norte | 301901 | Larap NHS with Annex (CNCEA) | JOSE PANGANIBAN | 1 | 1 | 6 | 2STY6CL Regular Workshop | BATCH 14 | 28235449.87 |  |  | Completed | 1
28044 | NC 2017 | TVL | Region V | Camarines Norte | 301901 | Larap NHS with Annex (CNCEA) | JOSE PANGANIBAN | 1 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21407657.49 |  |  | Completed | 1
28045 | NC 2017 | TVL | Region V | Camarines Norte | 301912 | Tabas National High School | PARACALE | 1 | 1 | 2 | 2STY2CL Regular Workshop | BATCH 14 | 11401972.94 |  |  | Completed | 1
28046 | NC 2017 | TVL | Region V | Camarines Norte | 301912 | Tabas National High School | PARACALE | 1 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21482657.49 |  |  | Completed | 1
28047 | NC 2017 | TVL | Region V | Camarines Norte | 301913 | Rizal NATIONAL HIGH SCHOOL | SANTA ELENA | 1 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21482657.49 |  |  | Completed | 1
28048 | NC 2017 | TVL | Region V | Camarines Norte | 301920 | Sta. Cruz NHS | JOSE PANGANIBAN | 1 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21532657.59 |  |  | Completed | 1
28049 | NC 2017 | TVL | Region V | Camarines Norte | 301921 | Tigbinan NHS | LABO | 1 | 1 | 2 | 2STY2CL Regular Workshop | BATCH 14 | 11451972.94 |  |  | Completed | 1
28050 | NC 2017 | TVL | Region V | Camarines Norte | 301921 | Tigbinan NHS | LABO | 1 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21532657.49 |  |  | Completed | 1
28051 | NC 2017 | TVL | Region V | Camarines Norte | 301922 | Tulay Na Lupa National High School | LABO | 1 | 1 | 4 | 2STY4CL Regular Workshop | BATCH 14 | 16037147.49 |  |  | Completed | 1
28052 | NC 2017 | TVL | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1 | 1 | 2 | 2STY2CL Science Lab | BATCH 14 | 11416972.94 |  |  | Completed | 1
28053 | NC 2017 | TVL | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1 |  | 2 | 2STY2CL ICT Lab | BATCH 14 | 11301972.94 |  |  | Completed | 1
28054 | NC 2017 | TVL | Region V | Camarines Norte | 309602 | Maulawin National High School | SANTA ELENA | 1 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21482657.49 |  |  | Completed | 1
28055 | NC 2017 | TVL | Region V | Camarines Norte | 309616 | Bulala HS | SANTA ELENA | 1 | 1 | 2 | 2STY2CL Science Lab | BATCH 14 | 11547972.94 |  |  | Completed | 1
28056 | NC 2017 | TVL | Region V | Camarines Norte | 309616 | Bulala HS | SANTA ELENA | 1 |  | 2 | 2STY2CL ICT Lab | BATCH 14 | 11426972.94 |  |  | Completed | 1
28057 | NC 2017 | TVL | Region V | Camarines Norte | 309618 | San Pedro-Domingo Llarena HS | SANTA ELENA | 1 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21482657.49 |  |  | Completed | 1
28058 | NC 2017 | TVL | Region V | Camarines Norte | 309621 | MAXIMO MANARANG HIGH SCHOOL | PARACALE | 1 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21532657.49 |  |  | Completed | 1
28059 | NC 2017 | TVL | Region V | Camarines Norte | 500156 | Dumagmang IS | LABO | 1 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21582657.49 |  |  | Completed | 1
28060 | NC 2017 | K10 | Region V | Camarines Norte | 112083 | Balce ES | BASUD | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 11192000 |  |  | Completed | 1
28061 | NC 2017 | K10 | Region V | Camarines Norte | 112084 | Basud CS | BASUD | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 14864500 |  |  | Completed | 1
28062 | NC 2017 | K10 | Region V | Camarines Norte | 112100 | Pinagwarasan ES | BASUD | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8379000 |  |  | Completed | 1
28063 | NC 2017 | K10 | Region V | Camarines Norte | 112107 | Tuaca ES | BASUD | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 11192000 |  |  | Completed | 1
28064 | NC 2017 | K10 | Region V | Camarines Norte | 112131 | Alawihao ES | DAET (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 14864500 |  |  | Completed | 1
28065 | NC 2017 | K10 | Region V | Camarines Norte | 112132 | Awitan ES | DAET (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8179000 |  |  | Completed | 1
28066 | NC 2017 | K10 | Region V | Camarines Norte | 112133 | Bagasbas ES | DAET (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 11192000 |  |  | Completed | 1
28067 | NC 2017 | K10 | Region V | Camarines Norte | 112134 | Daet ES | Daet North | 2 | 1 | 12 | 2STY12CL | BATCH 14 | 28519199.87 |  |  | Completed | 1
28068 | NC 2017 | K10 | Region V | Camarines Norte | 112134 | Daet ES | Daet North | 2 |  | 8 | 2STY8CL | BATCH 14 | 21359147.49 |  |  | Completed | 1
28069 | NC 2017 | K10 | Region V | Camarines Norte | 112135 | Dogongan ES | DAET (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 11192000 |  |  | Completed | 1
28070 | NC 2017 | K10 | Region V | Camarines Norte | 112136 | Mantagbac Elem School | DAET (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 14864500 |  |  | Completed | 1
28071 | NC 2017 | K10 | Region V | Camarines Norte | 112138 | Pandan Elementary School | DAET (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 11192000 |  |  | Completed | 1
28072 | NC 2017 | K10 | Region V | Camarines Norte | 112141 | Calasgasan ES | DAET (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 11092000 |  |  | Completed | 1
28073 | NC 2017 | K10 | Region V | Camarines Norte | 112148 | ZURBANO ELEMENTARY SCHOOL | DAET (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8179000 |  |  | Completed | 1
28074 | NC 2017 | K10 | Region V | Camarines Norte | 112223 | Colasi ES | MERCEDES | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 15064500 |  |  | Completed | 1
28075 | NC 2017 | K10 | Region V | Camarines Norte | 112232 | Manguisoc ES | Mercedes | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 11242000 |  |  | Completed | 1
28076 | NC 2017 | K10 | Region V | Camarines Norte | 112235 | Mercedes Elementary School | MERCEDES | 2 | 1 | 8 | 2STY8CL | BATCH 14 | 21459147.49 |  |  | Completed | 1
28077 | NC 2017 | K10 | Region V | Camarines Norte | 112239 | Tagongtong ES | MERCEDES | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8179000 |  |  | Completed | 1
28078 | NC 2017 | K10 | Region V | Camarines Norte | 112271 | Salvacion (B) ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8329000 |  |  | Completed | 1
28079 | NC 2017 | K10 | Region V | Camarines Norte | 112273 | San Isidro ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8329000 |  |  | Completed | 1
28080 | NC 2017 | K10 | Region V | Camarines Norte | 112275 | San Vicente CS | SAN VICENTE | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 14814500 |  |  | Completed | 1
28081 | NC 2017 | K10 | Region V | Camarines Norte | 112289 | F. David ES | TALISAY | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 11142000 |  |  | Completed | 1
28082 | NC 2017 | K10 | Region V | Camarines Norte | 112292 | Ramon Magsaysay ES | TALISAY | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 11242000 |  |  | Completed | 1
28083 | NC 2017 | K10 | Region V | Camarines Norte | 112293 | San Isidro ES | TALISAY | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8179000 |  |  | Completed | 1
28084 | NC 2017 | K10 | Region V | Camarines Norte | 112308 | Mangcawayan Island ES | VINZONS | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 11462000 |  |  | Completed | 1
28085 | NC 2017 | K10 | Region V | Camarines Norte | 112313 | Pinagtigasan ES | VINZONS | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 11462000 |  |  | Completed | 1
28086 | NC 2017 | K10 | Region V | Camarines Norte | 112314 | Sto. Domingo ES | VINZONS | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8179000 |  |  | Completed | 1
28087 | NC 2017 | K10 | Region V | Camarines Norte | 112316 | Vinzons Pilot ES | VINZONS | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 11462000 |  |  | Completed | 1
28088 | NC 2017 | TVL | Region V | Camarines Norte | 301889 | Basud National High School | BASUD | 2 | 1 | 2 | 2STY2CL Science Lab | BATCH 14 | 11241972.94 |  |  | Completed | 1
28089 | NC 2017 | TVL | Region V | Camarines Norte | 301889 | Basud National High School | BASUD | 2 |  | 2 | 2STY2CL Science Lab | BATCH 14 | 11241972.94 |  |  | Completed | 1
28090 | NC 2017 | TVL | Region V | Camarines Norte | 301889 | Basud National High School | BASUD | 2 |  | 6 | 2STY6CL Regular Workshop | BATCH 14 | 28160449.87 |  |  | Completed | 1
28091 | NC 2017 | TVL | Region V | Camarines Norte | 301892 | D. Q. Liwag NHS | VINZONS | 2 | 1 | 4 | 2STY4CL Regular Workshop | BATCH 14 | 21367657.49 |  |  | Completed | 1
28092 | NC 2017 | TVL | Region V | Camarines Norte | 301892 | D. Q. Liwag NHS | VINZONS | 2 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21332657.49 |  |  | Completed | 1
28093 | NC 2017 | TVL | Region V | Camarines Norte | 301902 | Manguisoc NHS | MERCEDES | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21482657.49 |  |  | Completed | 1
28094 | NC 2017 | TVL | Region V | Camarines Norte | 301903 | San Lorenzo Ruiz National High School | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 15962147.49 |  |  | Completed | 1
28095 | NC 2017 | TVL | Region V | Camarines Norte | 301903 | San Lorenzo Ruiz National High School | SAN LORENZO RUIZ (IMELDA) | 2 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 15962147.49 |  |  | Completed | 1
28096 | NC 2017 | TVL | Region V | Camarines Norte | 301903 | San Lorenzo Ruiz National High School | SAN LORENZO RUIZ (IMELDA) | 2 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21392657.49 |  |  | Completed | 1
28097 | NC 2017 | TVL | Region V | Camarines Norte | 301904 | MATANGO NATIONAL HIGH SCHOOL | VINZONS | 2 | 1 | 2 | 2STY2CL Regular Workshop | BATCH 14 | 11351972.94 |  |  | Completed | 1
28098 | NC 2017 | TVL | Region V | Camarines Norte | 301904 | MATANGO NATIONAL HIGH SCHOOL | VINZONS | 2 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21432657.49 |  |  | Completed | 1
28099 | NC 2017 | TVL | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21332657.49 |  |  | Completed | 1
28100 | NC 2017 | TVL | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 |  | 4 | 2STY4CL Regular Workshop | BATCH 14 | 21367657.49 |  |  | Completed | 1
28101 | NC 2017 | TVL | Region V | Camarines Norte | 301907 | Pablo S. Villafuerte HS | MERCEDES | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21432657.49 |  |  | Completed | 1
28102 | NC 2017 | TVL | Region V | Camarines Norte | 301909 | Pambuhan National High School | MERCEDES | 2 | 1 | 4 | 2STY4CL Regular Workshop | BATCH 14 | 16187147.49 |  |  | Completed | 1
28103 | NC 2017 | TVL | Region V | Camarines Norte | 301909 | Pambuhan National High School | MERCEDES | 2 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 16052147.49 |  |  | Completed | 1
28104 | NC 2017 | TVL | Region V | Camarines Norte | 301914 | Sabang NHS | VINZONS | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21482657.49 |  |  | Completed | 1
28105 | NC 2017 | SHS | Region V | Camarines Norte | 301915 | San Felipe NHS | BASUD | 2 | 1 | 5 | 2STY4CL 3Regular Workshop & 2cl | BATCH 14 | 21417657.49 |  |  | Completed | 1
28106 | NC 2017 | TVL | Region V | Camarines Norte | 301915 | San Felipe NHS | BASUD | 2 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 15987147.49 |  |  | Completed | 1
28107 | NC 2017 | TVL | Region V | Camarines Norte | 301916 | San Francisco National High School | TALISAY | 2 | 1 | 3 | 3STY3CL Regular, ICT & Science Lab | BATCH 14 | 12972338.21 |  |  | Completed | 1
28108 | NC 2017 | TVL | Region V | Camarines Norte | 301916 | San Francisco National High School | TALISAY | 2 |  | 3 | 3STY3CL Regular, ICT & Science Lab | BATCH 14 | 12972338.21 |  |  | Completed | 1
28109 | NC 2017 | TVL | Region V | Camarines Norte | 301918 | San Roque National High School | MERCEDES | 2 | 1 | 2 | 2STY2CL Science Lab | BATCH 14 | 11191972.94 |  |  | Completed | 1
28110 | NC 2017 | TVL | Region V | Camarines Norte | 301918 | San Roque National High School | MERCEDES | 2 |  | 2 | 2STY2CL Science Lab | BATCH 14 | 11185972.94 |  |  | Completed | 1
28111 | NC 2017 | TVL | Region V | Camarines Norte | 301919 | Froilan D. Lopez HS | SAN VICENTE | 2 | 1 | 4 | 2STY4CL Regular Workshop | BATCH 14 | 21442657.49 |  |  | Completed | 1
28112 | NC 2017 | TVL | Region V | Camarines Norte | 301919 | Froilan D. Lopez HS | SAN VICENTE | 2 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21407657.49 |  |  | Completed | 1
28113 | NC 2017 | TVL | Region V | Camarines Norte | 301924 | Vicente L. Basit Memorial High School | DAET (Capital) | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 16002147.49 |  |  | Completed | 1
28114 | NC 2017 | TVL | Region V | Camarines Norte | 301925 | Vinzons Pilot High School | VINZONS | 2 | 1 | 6 | 2STY6CL Regular Workshop | BATCH 14 | 28160449.87 |  |  | Completed | 1
28115 | NC 2017 | TVL | Region V | Camarines Norte | 301925 | Vinzons Pilot High School | VINZONS | 2 |  | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21332657.49 |  |  | Completed | 1
28116 | NC 2017 | TVL | Region V | Camarines Norte | 309603 | Caringo High School | MERCEDES | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21482657.49 |  |  | Completed | 1
28117 | NC 2017 | TVL | Region V | Camarines Norte | 309604 | Eugenia M. Quintela Memorial High School | VINZONS | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21582657.49 |  |  | Completed | 1
28118 | NC 2017 | TVL | Region V | Camarines Norte | 309605 | Fabrica HS | SAN VICENTE | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 15977147.49 |  |  | Completed | 1
28119 | NC 2017 | TVL | Region V | Camarines Norte | 309606 | San Isidro HS (Alcantara) | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 3 | 3STY3CL Regular & Science Lab | BATCH 14 | 17370938.21 |  |  | Completed | 1
28120 | NC 2017 | TVL | Region V | Camarines Norte | 309606 | San Isidro HS (Alcantara) | SAN LORENZO RUIZ (IMELDA) | 2 |  | 2 | 2STY2CL ICT Lab | BATCH 14 | 11326972.94 |  |  | Completed | 1
28121 | NC 2017 | TVL | Region V | Camarines Norte | 309608 | Tuaca HS | BASUD | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21432657.49 |  |  | Completed | 1
28122 | NC 2017 | TVL | Region V | Camarines Norte | 309611 | Dominador Narido High School | BASUD | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21332657.49 |  |  | Completed | 1
28123 | NC 2017 | TVL | Region V | Camarines Norte | 309612 | Porfirio R. Ponayo HS | DAET (Capital) | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21282657.49 |  |  | Completed | 1
28124 | NC 2017 | TVL | Region V | Camarines Norte | 309620 | Sarah Jane Ferrer HS | VINZONS | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 15902147.49 |  |  | Completed | 1
28125 | NC 2017 | TVL | Region V | Camarines Norte | 309622 | Camarines Norte NHS-Annex | DAET (Capital) | 2 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 14 | 21332657.49 |  |  | Completed | 1
28126 | NC 2017 | SHS | Region V | Camarines Sur | 301964 | Dalupaon National High School | PASACAO | 2 | 1 | 12 | 2STY12CL | BATCH 14 | 24147665.35 |  |  | Completed | 1
28127 | NC 2017 | SHS | Region V | Camarines Sur | 309718 | Dalupaon NHS - Tinalmud PHS Annex | PASACAO | 2 | 1 | 12 | 2STY12CL | BATCH 14 | 24147665.35 |  |  | Completed | 1
28128 | NC 2017 | K10 | Region V | Camarines Sur | 112490 | Sabang ES | CALABANGA | 3 | 1 | 6 | 2STY6CL | BATCH 14 | 1673634.92 |  |  | Completed | 1
28129 | NC 2017 | SHS | Region V | Sorsogon City | 302279 | Sorsogon National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 36 | 3units 4STY12CL | BATCH 14 | 103129369.16 |  |  | Completed | 1
28130 | NC 2017 | SHS | Region V | Sorsogon City | 302279 | Sorsogon National High School | CITY OF SORSOGON (Capital) | 1 |  | 20 | 4STY20CL | BATCH 14 | 45908409.74 |  |  | Completed | 1
36592 | NC 2018 | SHS | Region V | Albay | 301810 | Malinao National High School | MALINAO | 1 | 1 | 2 | 2storey - 2 Regular Workshop | BATCH 1 | 8337294.14 |  |  | Completed | 1
36593 | NC 2018 | SHS | Region V | Albay | 301810 | Malinao National High School | MALINAO | 1 |  | 2 | 2storey - 1 Science and 1CT | BATCH 1 | 8337294.14 |  |  | Completed | 1
36594 | NC 2018 | SHS | Region V | Albay | 301827 | Estancia National High School | MALINAO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8343672.1 |  |  | Completed | 1
36595 | NC 2018 | SHS | Region V | Albay | 301831 | Labnig National High School | MALINAO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9583164.27 |  |  | Completed | 1
36596 | NC 2018 | SHS | Region V | Albay | 301853 | Naga National High School | TIWI | 1 | 1 | 20 | 4STY20CL | BATCH 1 | 52629548.84 |  |  | Completed | 1
36597 | NC 2018 | SHS | Region V | Albay | 301863 | Pili National High School | BACACAY | 1 | 1 | 12 | 4STY12CL | BATCH 1 | 47175579.77 |  |  | Completed | 1
36598 | NC 2018 | SHS | Region V | Albay | 301871 | San Antonio National High School | MALILIPOT | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 19511359.78 |  |  | Completed | 1
36599 | NC 2018 | SHS | Region V | Albay | 301872 | San Fernando National High School | SANTO DOMINGO (LIBOG) | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 7364628.95 |  |  | Completed | 1
36600 | NC 2018 | SHS | Region V | Albay | 309502 | San Pablo High School | BACACAY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 11453926.53 |  |  | Completed | 1
36601 | NC 2018 | K10 | Region V | Albay | 111628 | Cabangan Elementary School | Camalig | 2 | 1 | 6 | 2sty6cl | BATCH 1 | 12691959.919 |  |  | Completed | 1 |  |  | P00271397LZ-CW1 | 18FB0138
36602 | NC 2018 | K10 | Region V | Albay | 111630 | Camalig North Central School | Camalig | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 10265317.6677 |  |  | Completed | 1 |  |  | P00271398LZ-CW1 | 18FB0153
36603 | NC 2018 | K10 | Region V | Albay | 111633 | Libod Elementary School | Camalig | 2 | 1 | 6 | 2sty6cl | BATCH 1 | 12509893.639 |  |  | Completed | 1 |  |  | P00271399LZ-CW1 | 18FB0139
36604 | NC 2018 | K10 | Region V | Albay | 111637 | Quirangay Elementary School | Camalig | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 10082705.48 |  |  | Completed | 1 |  |  | P00271400LZ-CW1 | 18FB0152
36605 | NC 2018 | K10 | Region V | Albay | 111641 | Camalig South CS | CAMALIG | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12755698.92 |  |  | Completed | 1 |  |  | P00271401LZ-CW1 | 18FB0154
36606 | NC 2018 | K10 | Region V | Albay | 111653 | Taladong ES | CAMALIG | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12624908.29 |  |  | Completed | 1 |  |  | P00271402LZ-CW1 | 18FB0142
36607 | NC 2018 | K10 | Region V | Albay | 111660 | Banadero ES | DARAGA (LOCSIN) | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12542930.49 |  |  | Completed | 1 |  |  | P002703LZ-CW1 | 18FB0167
36608 | NC 2018 | K10 | Region V | Albay | 111694 | Mayon Elementary School | Daraga (Locsin) | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 9894241.784 |  |  | Completed | 1 |  |  | P00271404LZ-CW1 | 18FB0168
36609 | NC 2018 | K10 | Region V | Albay | 111699 | San Ramon Elementary School | Daraga (Locsin) | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 9840949.43 |  |  | Completed | 1 |  |  | P00271405LZ-CW1 | 18FB0137
36610 | NC 2018 | K10 | Region V | Albay | 111704 | Villahermosa Elementary School | DARAGA (LOCSIN) | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12745804.99 |  |  | Completed | 1 |  |  | P00271406LZ-CW1 | 18FB0180
36611 | NC 2018 | K10 | Region V | Albay | 111901 | Nagotgot ES | MANITO | 2 | 1 | 8 | 2units-2STY4CL | BATCH 1 | 23023580.32 |  |  | Completed | 1 |  |  | P00271407LZ-CW1 | 18FB0165
36612 | NC 2018 | SHS | Region V | Albay | 301813 | Batan National High School | Rapu-Rapu | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 11303665.62 |  |  | Completed | 1 |  |  | P00271408LZ-CW1 | 18FB0199
36613 | NC 2018 | SHS | Region V | Albay | 301819 | Caguiba National High School | CAMALIG | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 13342930 |  |  | Completed | 1 |  |  | P00271409LZ-CW1 | 18FB0179
36614 | NC 2018 | SHS | Region V | Albay | 301826 | Bañadero High School | Daraga (Locsin) | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 9821865.25 |  |  | Completed | 1 |  |  | P00271410LZ-CW1 | 18FB0164
36615 | NC 2018 | SHS | Region V | Albay | 301832 | Lacag National High School | Daraga (Locsin) | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 10047075.2141 |  |  | Completed | 1 |  |  | P00271411LZ-CW1 | 18FB0201
36616 | NC 2018 | SHS | Region V | Albay | 301847 | Nagotgot High School | MANITO | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 13724646.95 |  |  | Completed | 1 |  |  | P00271412LZ-CW1 | 18FB0216
36617 | NC 2018 | SHS | Region V | Albay | 301882 | Villahermosa National High School | Rapu-Rapu | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 11383238.5677 |  |  | Completed | 1 |  |  | P00271413LZ-CW1 | 18FB0215
36618 | NC 2018 | SHS | Region V | Albay | 301884 | Mancao National High School | Rapu-Rapu | 2 | 1 | 8 | 2-2sty4cl | BATCH 1 | 22923461.3 |  |  | Completed | 1 |  |  | P00271414LZ-CW1 | 18FB0200
36619 | NC 2018 | SHS | Region V | Albay | 309509 | Bilbao National High School | Rapu-Rapu | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 11621962.74 |  |  | Completed | 1 |  |  | P00271415LZ-CW1 | 18FB0198
36620 | NC 2018 | K10 | Region V | Albay | 112011 | Polangui South CS | POLANGUI | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9108274.67 |  |  | Completed | 1
36621 | NC 2018 | TVL | Region V | Albay | 301840 | Magpanambo NHS | POLANGUI | 3 | 1 | 2 | 2STY4CL (2reg ws) | BATCH 1 | 9378274.67 |  |  | Completed | 1
36622 | NC 2018 | TVL | Region V | Albay | 301840 | Magpanambo NHS | POLANGUI | 3 |  | 2 | 2STY4CL (2ict) | BATCH 1 | 9458274.67 |  |  | Completed | 1
36623 | NC 2018 | TVL | Region V | Albay | 301840 | Magpanambo NHS | POLANGUI | 3 |  | 2 | 2STY4CL (2sci) | BATCH 1 | 9533274.67 |  |  | Completed | 1
36624 | NC 2018 | TVL | Region V | Albay | 301850 | Lower Binogsacan National High School | GUINOBATAN | 3 | 1 | 4 | 2STY8CL (4units Regular ws) | BATCH 1 | 18207500.33 |  |  | Completed | 1
36625 | NC 2018 | TVL | Region V | Albay | 301850 | Lower Binogsacan National High School | GUINOBATAN | 3 |  | 4 | 2STY8CL (2sci, 2ict) | BATCH 1 | 18357500.33 |  |  | Completed | 1
36626 | NC 2018 | TVL | Region V | Albay | 301851 | Masarawag National High School | GUINOBATAN | 3 | 1 | 4 | 2STY8CL (4units Regular ws) | BATCH 1 | 18507500.33 |  |  | Completed | 1
36627 | NC 2018 | TVL | Region V | Albay | 301851 | Masarawag National High School | GUINOBATAN | 3 |  | 4 | 2STY8CL (2sci, 2ict) | BATCH 1 | 18667500.33 |  |  | Completed | 1
36628 | NC 2018 | TVL | Region V | Albay | 301855 | Oas Polytechnic School | OAS | 3 | 1 | 9 | 4STY16CL (7regular, 2shs) | BATCH 1 | 38714108.94 |  |  | Completed | 1
36629 | NC 2018 | TVL | Region V | Albay | 301855 | Oas Polytechnic School | OAS | 3 |  | 4 | 2STY6CL (2sci, 2shs) | BATCH 1 | 11950503.1 |  |  | Completed | 1
36630 | NC 2018 | TVL | Region V | Albay | 301855 | Oas Polytechnic School | OAS | 3 |  | 2 | 2STY4CL (2ict) | BATCH 1 | 9243274.67 |  |  | Completed | 1
36631 | NC 2018 | TVL | Region V | Albay | 301868 | Ponso National HS | POLANGUI | 3 | 1 | 8 | 4STY16CL (4regular,2science,2ict) | BATCH 1 | 40452942.01 |  |  | Completed | 1
36632 | NC 2018 | TVL | Region V | Albay | 301870 | Saban National High School | OAS | 3 | 1 | 2 | 2STY4CL (2ict) | BATCH 1 | 13640851.76 |  |  | Completed | 1
36633 | NC 2018 | SHS | Region V | Albay | 301885 | Vinisitahan National High School | BACACAY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 47095121.08 |  |  | Completed | 1
36634 | NC 2018 | TVL | Region V | Albay | 301828 | Itaran National High School | POLANGUI | 3 | 1 | 6 | 3STY12CL (2reg, 2sci, 2ict) | Batch 3 | 38124267.25 |  |  | Completed | 1
36635 | NC 2018 | TVL | Region V | Albay | 301829 | Maysua High School | POLANGUI | 3 |  | 2 | 2STY4CL (2sci) | Batch 3 | 15575851.76 |  |  | Completed | 1
36636 | NC 2018 | TVL | Region V | Albay | 301836 | San Pascual National High School | LIBON | 3 | 1 | 4 | 2STY8CL (2sci, 2ict) | Batch 3 | 27555050.26 |  |  | Completed | 1
36637 | NC 2018 | TVL | Region V | Albay | 301839 | Malapay High School | PIO DURAN | 3 |  | 2 | 2STY4CL (2sci) | Batch 3 | 11260901.76 |  |  | Completed | 1
36638 | NC 2018 | TVL | Region V | Albay | 301842 | Malipo National High School | GUINOBATAN | 3 |  | 8 | 4STY16CL (4regular,2science,2ict) | Batch 3 | 45880737.96 |  |  | Completed | 1
36639 | NC 2018 | TVL | Region V | Albay | 301844 | Mauraro High School | GUINOBATAN | 3 |  | 3 | 2STY4CL (1regular ,2shs) | Batch 3 | 10720901.76 |  |  | Completed | 1
36640 | NC 2018 | SHS | Region V | Albay | 301849 | Marcial O. RAñola Memorial School | GUINOBATAN | 3 |  | 4 | 2STY4CL | Batch 3 | 10520901.76 |  |  | Completed | 1
36641 | NC 2018 | TVL | Region V | Albay | 301852 | Matacon National High School | POLANGUI | 3 | 1 | 2 | 2STY4CL (2reg ws) | Batch 3 | 11025901.76 |  |  | Completed | 1
36642 | NC 2018 | TVL | Region V | Albay | 301854 | Marigondon National High School | PIO DURAN | 3 | 1 | 4 | 2STY6CL (2shs,2reg) | Batch 3 | 12821168.02 |  |  | Completed | 1
36643 | NC 2018 | TVL | Region V | Albay | 301860 | Pantao National High School | LIBON | 3 |  | 2 | 2STY4CL (2sci) | Batch 3 | 11490901.76 |  |  | Completed | 1
36644 | NC 2018 | SHS | Region V | Albay | 301823 | Ilawod National High School | CAMALIG | 2 | 1 | 16 | 4STY16CL | Batch 5 | 51778073 |  |  | Completed | 1 |  |  | P00275962LZ-CW1 | 18FB0306
36645 | NC 2018 | K10 | Region V | Albay | 111657 | Alcala ES | DARAGA (LOCSIN) | 2 | 1 | 12 | 3STY12CL | Batch 5 | 47857100 |  |  | Completed | 1 |  |  | P00275963LZ-CW1 | 18FB0305
36646 | NC 2018 | SHS | Region V | Camarines Norte | 301910 | PARACALE NATIONAL HIGH SCHOOL | PARACALE | 1 | 1 | 6 | 3STY6CL Regular Workshop | BATCH 1 | 31757518.69 |  |  | COMPLETED | 1
36647 | NC 2018 | SHS | Region V | Camarines Norte | 301910 | PARACALE NATIONAL HIGH SCHOOL | PARACALE | 1 |  | 8 | 2STY8CL | BATCH 1 | 21484147.49 |  |  | COMPLETED | 1
36648 | NC 2018 | SHS | Region V | Camarines Norte | 301910 | PARACALE NATIONAL HIGH SCHOOL | PARACALE | 1 | 1 | 4 | 2STY4CL Science Lab and ICT | BATCH 1 | 21407657.49 |  |  | COMPLETED | 1
36649 | NC 2018 | K10 | Region V | Camarines Norte | 112123 | PORTUGAL CHAVEZ ES | CAPALONGA | 1 | 1 | 3 | 1STY3CL | Batch 3 | 4214985 |  |  | COMPLETED | 1
36650 | NC 2018 | K10 | Region V | Camarines Norte | 112149 | Calero ES | JOSE PANGANIBAN | 1 | 1 | 2 | 1STY2CL | Batch 3 | 3310819.34 |  |  | COMPLETED | 1
36651 | NC 2018 | K10 | Region V | Camarines Norte | 112154 | OSMENA ES | JOSE PANGANIBAN | 1 | 1 | 3 | 1STY3CL | Batch 3 | 4269985 |  |  | Completed | 1
36652 | NC 2018 | K10 | Region V | Camarines Norte | 112160 | D. ALBONIA ES | JOSE PANGANIBAN | 1 | 1 | 2 | 1STY2CL | Batch 3 | 3235819.34 |  |  | COMPLETED | 1
36653 | NC 2018 | K10 | Region V | Camarines Norte | 112161 | DAHICAN ES | JOSE PANGANIBAN | 1 | 1 | 3 | 1STY3CL | Batch 3 | 4269985 |  |  | Completed | 1
36654 | NC 2018 | K10 | Region V | Camarines Norte | 112163 | LARAP ES | JOSE PANGANIBAN | 1 | 1 | 6 | 2STY6CL | Batch 3 | 15508045.37 |  |  | Completed | 1
36655 | NC 2018 | K10 | Region V | Camarines Norte | 112164 | NAKALAYA ES | JOSE PANGANIBAN | 1 | 1 | 2 | 1STY2CL | Batch 3 | 3165819.34 |  |  | Completed | 1
36656 | NC 2018 | K10 | Region V | Camarines Norte | 112166 | San Isidro ES | JOSE PANGANIBAN | 1 | 1 | 2 | 1STY2CL | Batch 3 | 3160819.34 |  |  | Completed | 1
36657 | NC 2018 | K10 | Region V | Camarines Norte | 112169 | SAN PEDRO ES | JOSE PANGANIBAN | 1 | 1 | 2 | 1STY2CL | Batch 3 | 3160819.34 |  |  | COMPLETED | 1
36658 | NC 2018 | K10 | Region V | Camarines Norte | 112171 | STA. ELENA ES | JOSE PANGANIBAN | 1 | 1 | 3 | 1STY3CL | Batch 3 | 4299985 |  |  | Completed | 1
36659 | NC 2018 | K10 | Region V | Camarines Norte | 112193 | NAPAOD ES | LABO | 1 | 1 | 2 | 1STY2CL | Batch 3 | 3165819.34 |  |  | COMPLETED | 1
36660 | NC 2018 | K10 | Region V | Camarines Norte | 112194 | PAMPANG ES | LABO EAST | 1 | 1 | 2 | 1STY2CL | Batch 3 | 3165819.34 |  |  | COMPLETED | 1
36661 | NC 2018 | K10 | Region V | Camarines Norte | 112200 | BAGONG SILANG III | LABO WEST | 1 | 1 | 3 | 1STY3CL | Batch 3 | 4114985 |  |  | Completed | 1
36662 | NC 2018 | K10 | Region V | Camarines Norte | 112204 | F. CAUDILLA ES | LABO WEST | 1 | 1 | 6 | 2STY6CL | Batch 3 | 16556374.25 |  |  | Completed | 1
36663 | NC 2018 | K10 | Region V | Camarines Norte | 112207 | DUMAGMANG I.S. | LABO WEST | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10363139.39 |  |  | Completed | 1
36664 | NC 2018 | K10 | Region V | Camarines Norte | 173008 | DON TOMAS ES | STA. ELENA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10193139.39 |  |  | COMPLETED | 1
36665 | NC 2018 | K10 | Region V | Camarines Norte | 173009 | JUAN A. AMPARO ES | STA. ELENA | 1 | 1 | 6 | 2STY6CL | Batch 3 | 16611374.25 |  |  | Completed | 1
36666 | NC 2018 | K10 | Region V | Camarines Norte | 173020 | PALANAS ES | PARACALE | 1 | 1 | 6 | 2STY6CL | Batch 3 | 19031155.85 |  |  | Completed | 1
36667 | NC 2018 | SHS | Region V | Camarines Norte | 301913 | RIZAL NHS | STA. ELENA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 14250311.79 |  |  | COMPLETED | 1
36668 | NC 2018 | SHS | Region V | Camarines Norte | 301922 | Tulay Na Lupa National High School | LABO | 1 | 1 | 3 | 1STY3CL | Batch 3 | 4414985 |  |  | COMPLETED | 1
36669 | NC 2018 | K10 | Region V | Camarines Norte | 112082 | ANGAS ES | BASUD | 2 | 1 | 3 | 1STY3CL | Batch 3 | 4284985 |  |  | COMPLETED | 1
36670 | NC 2018 | K10 | Region V | Camarines Norte | 112089 | GUINATUNGAN ES | BASUD | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3260819.34 |  |  | COMPLETED | 1
36671 | NC 2018 | K10 | Region V | Camarines Norte | 112089 | GUINATUNGAN ES | BASUD | 2 |  | 2 | 1STY2CL | Batch 3 | 3010819.34 |  |  | COMPLETED | 1
36672 | NC 2018 | K10 | Region V | Camarines Norte | 112096 | MOCONG ES | BASUD | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3060819.34 |  |  | COMPLETED | 1
36673 | NC 2018 | K10 | Region V | Camarines Norte | 112099 | PEDRO RADA ES | BASUD | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3260819.34 |  |  | COMPLETED | 1
36674 | NC 2018 | K10 | Region V | Camarines Norte | 112102 | PR SAMONTE ES | BASUD | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3410819.34 |  |  | COMPLETED | 1
36675 | NC 2018 | K10 | Region V | Camarines Norte | 112142 | COBANGBANG ES | DAET | 2 | 1 | 4 | 2STY4CL | Batch 3 | 13525311.79 |  |  | Completed | 1
36676 | NC 2018 | K10 | Region V | Camarines Norte | 112147 | GREGORIO P.M.S. | DAET | 2 | 1 | 4 | 2STY4CL | Batch 3 | 14360854.89 |  |  | COMPLETED | 1
36677 | NC 2018 | K10 | Region V | Camarines Norte | 112227 | HINIPAAN ES | BASUD | 2 | 1 | 4 | 2STY4CL | Batch 3 | 14780854.89 |  |  | COMPLETED | 1
36678 | NC 2018 | K10 | Region V | Camarines Norte | 112263 | IMELDA ES | SAN VICENTE-SAN LORENZO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 10593139.39 |  |  | COMPLETED | 1
36679 | NC 2018 | K10 | Region V | Camarines Norte | 112270 | S. DELOS SANTOS ES | SAN VICENTE-SAN LORENZO | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3060819.34 |  |  | COMPLETED | 1
36680 | NC 2018 | K10 | Region V | Camarines Norte | 112274 | San Ramon ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3260819.34 |  |  | COMPLETED | 1
36681 | NC 2018 | K10 | Region V | Camarines Norte | 112296 | TALISAY ES | TALISAY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 14670854.89 |  |  | Completed | 1
36682 | NC 2018 | K10 | Region V | Camarines Norte | 112305 | GORGONIO OBUSAN ES | VINZONS | 2 | 1 | 3 | 1STY3CL | Batch 3 | 4414985 |  |  | Completed | 1
36683 | NC 2018 | K10 | Region V | Camarines Norte | 112310 | MATANGO ES | VINZONS | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9897777.14 |  |  | Completed | 1
36684 | NC 2018 | SHS | Region V | Camarines Norte | 301891 | Camarines Norte National HS | DAET (Capital) | 2 | 1 | 30 | 2UNITS-3STY15CL | Batch 3 | 82685199.28 |  |  | COMPLETED | 1
36685 | NC 2018 | SHS | Region V | Camarines Norte | 301925 | VINZONS PILOT HS | VINZONS | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12269497.14 |  |  | COMPLETED | 1
36686 | NC 2018 | SHS | Region V | Camarines Norte | 309608 | TUACA HS | BASUD | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12699768.69 |  |  | COMPLETED | 1
36687 | NC 2018 | k10 | Region V | Camarines Sur | 112969 | Ragay CS | RAGAY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 12501288.95 |  |  | Completed | 1
36688 | NC 2018 | TVL | Region V | Camarines Sur | 301977 | Godofredo Reyes Sr. National HS | RAGAY | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 12892956.92 |  |  | Completed | 1
36689 | NC 2018 | TVL | Region V | Camarines Sur | 301979 | Haluban NHS | LUPI | 1 | 1 | 2 | 2storey - 2 science lab | BATCH 1 | 12513302.71 |  |  | Completed | 1
36690 | NC 2018 | TVL | Region V | Camarines Sur | 301979 | Haluban NHS | LUPI | 1 |  | 2 | 2storey - 2 ICT lab | BATCH 1 | 12513302.71 |  |  | Completed | 1
36691 | NC 2018 | k10 | Region V | Camarines Sur | 112724 | Villa Socorro ES | LIBMANAN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9670237.13 |  |  | Completed | 1
36692 | NC 2018 | SHS | Region V | Camarines Sur | 301987 | Lupi National High School | SAN FERNANDO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9255093.56 |  |  | Completed | 1
36693 | NC 2018 | SHS | Region V | Camarines Sur | 302030 | San Antonio NHS | MILAOR | 2 | 1 | 12 | 2STY12CL | BATCH 1 | 22378502.72 |  |  | Completed | 1
36694 | NC 2018 | SHS | Region V | Camarines Sur | 302066 | Villamayor HS | MINALABAC | 2 | 1 | 12 | 2STY12CL | BATCH 1 | 22636577.77 |  |  | Completed | 1
36695 | NC 2018 | SHS | Region V | Camarines Sur | 309702 | Juan F. Trivino MHS (frmerly: Pasacao Sch. of Fisheries) | PASACAO | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17214601.92 |  |  | Completed | 1
36696 | NC 2018 | SHS | Region V | Camarines Sur | 309731 | Antipolo HS, Minalabac | MINALABAC | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17467124.67 |  |  | Completed | 1
36697 | NC 2018 | SHS | Region V | Camarines Sur | 309736 | Dr. Nelson A. Mejia HS | LIBMANAN | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17275906.68 |  |  | Completed | 1
36698 | NC 2018 | SHS | Region V | Camarines Sur | 309757 | Cagbibi National High School | PAMPLONA | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17769996.07 |  |  | Completed | 1
36699 | NC 2018 | SHS | Region V | Camarines Sur | 309758 | Eduardo V. Agomaa National High School | LIBMANAN | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17395833.17 |  |  | Completed | 1
36700 | NC 2018 | k10 | Region V | Camarines Sur | 112854 | Hibago ES | OCAMPO | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11695532.5 |  |  | Completed | 1
36701 | NC 2018 | k10 | Region V | Camarines Sur | 112856 | May-Ogob ES | OCAMPO | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11121193.99 |  |  | Completed | 1
36702 | NC 2018 | k10 | Region V | Camarines Sur | 112860 | Pinit ES | OCAMPO | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8650916.76 |  |  | Completed | 1
36703 | NC 2018 | k10 | Region V | Camarines Sur | 112861 | San Antonio ES | OCAMPO | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9176673.68 |  |  | Completed | 1
36704 | NC 2018 | k10 | Region V | Camarines Sur | 112918 | Anayan Sagrada ES | PILI (Capital) | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11554899.84 |  |  | Completed | 1
36705 | NC 2018 | k10 | Region V | Camarines Sur | 112918 | Anayan Sagrada ES | PILI (Capital) | 3 |  | 6 | 2STY6CL | BATCH 1 | 11554899.84 |  |  | Completed | 1
36706 | NC 2018 | k10 | Region V | Camarines Sur | 112925 | Curry ES | PILI (Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9244403.02 |  |  | Completed | 1
36707 | NC 2018 | k10 | Region V | Camarines Sur | 112925 | Curry ES | PILI (Capital) | 3 |  | 6 | 2STY6CL | BATCH 1 | 11464706.42 |  |  | Completed | 1
36708 | NC 2018 | k10 | Region V | Camarines Sur | 112926 | Del Rosario ES | PILI (Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 13053851.04 |  |  | Completed | 1
36709 | NC 2018 | k10 | Region V | Camarines Sur | 112932 | Pili CS | PILI (Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 13123131.89 |  |  | Completed | 1
36710 | NC 2018 | k10 | Region V | Camarines Sur | 112479 | Guillermo B. Azanes ES (Hinaguianan ES) | CALABANGA | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 14177628.83 |  |  | Completed | 1
36711 | NC 2018 | k10 | Region V | Camarines Sur | 112937 | San Jose South ES | PILI (Capital) | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11950160.25 |  |  | Completed | 1
36712 | NC 2018 | k10 | Region V | Camarines Sur | 173502 | Villaflorida Elementary School | OCAMPO | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11358334.49 |  |  | Completed | 1
36713 | NC 2018 | TVL | Region V | Camarines Sur | 301998 | Medroso-Mendoza NHS | CALABANGA | 3 | 1 | 2 | 2storey - 2 Science Lab | BATCH 1 | 13024364.23 |  |  | Completed | 1
36714 | NC 2018 | TVL | Region V | Camarines Sur | 301998 | Medroso-Mendoza NHS | CALABANGA | 3 |  | 2 | 2storey - 2ICT Lab | BATCH 1 | 13318507.26 |  |  | Completed | 1
36715 | NC 2018 | SHS | Region V | Camarines Sur | 309704 | Hanawan National HS | OCAMPO | 3 | 1 | 9 | 3STY9CL | BATCH 1 | 24104142.69 |  |  | Completed | 1
36716 | NC 2018 | TVL | Region V | Camarines Sur | 309749 | BINOBONG HIGH SCHOOL | PILI (Capital) | 3 | 1 | 2 | 2storey - 2 ICT Lab | BATCH 1 | 11183401.75 |  |  | Completed | 1
36717 | NC 2018 | k10 | Region V | Camarines Sur | 112600 | Garchitorena CS | GARCHITORENA | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9764676.68 |  |  | Completed | 1
36718 | NC 2018 | k10 | Region V | Camarines Sur | 112621 | Goa CS | GOA | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 12145349.15 |  |  | Completed | 1
36719 | NC 2018 | k10 | Region V | Camarines Sur | 112660 | Lagonoy South Central School | LAGONOY | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9212791.02 |  |  | Completed | 1
36720 | NC 2018 | k10 | Region V | Camarines Sur | 112667 | San Ramon ES | LAGONOY | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 12145349.15 |  |  | Completed | 1
36721 | NC 2018 | k10 | Region V | Camarines Sur | 112893 | Maangas ES | PRESENTACION (PARUBCAN) | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9635834.49 |  |  | Completed | 1
36722 | NC 2018 | k10 | Region V | Camarines Sur | 112895 | Parubcan CS | PRESENTACION (PARUBCAN) | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9701408.41 |  |  | Completed | 1
36723 | NC 2018 | k10 | Region V | Camarines Sur | 112989 | Sagnay CS | SAGÑAY | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 12145349.15 |  |  | Completed | 1
36724 | NC 2018 | k10 | Region V | Camarines Sur | 113018 | Catalotoan Community School | SAN JOSE | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9134399.42 |  |  | Completed | 1
36725 | NC 2018 | k10 | Region V | Camarines Sur | 113028 | San Jose CS | SAN JOSE | 4 | 1 | 8 | 2STY8CL | BATCH 1 | 16296567.86 |  |  | Completed | 1
36726 | NC 2018 | k10 | Region V | Camarines Sur | 113109 | Tigaon North CS | TIGAON | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9212791.02 |  |  | Completed | 1
36727 | NC 2018 | SHS | Region V | Camarines Sur | 301975 | Goa National High School | GOA | 4 | 1 | 8 | 2STY8CL | BATCH 1 | 16169474.58 |  |  | Completed | 1
36728 | NC 2018 | SHS | Region V | Camarines Sur | 301986 | La Salvacion NHS | TIGAON | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9134399.42 |  |  | Completed | 1
36729 | NC 2018 | k10 | Region V | Camarines Sur | 112378 | Pagatpatan ES | BATO | 5 | 1 | 6 | 2STY6CL | BATCH 1 | 11244485.77 |  |  | Completed | 1
36730 | NC 2018 | k10 | Region V | Camarines Sur | 112427 | Bula CS | BULA | 5 | 1 | 8 | 2STY8CL | BATCH 1 | 15835426.45 |  |  | Completed | 1
36731 | NC 2018 | k10 | Region V | Camarines Sur | 112444 | Palsong ES | BULA | 5 | 1 | 6 | 2STY6CL | BATCH 1 | 11394853.03 |  |  | Completed | 1
36732 | NC 2018 | k10 | Region V | Camarines Sur | 112452 | Sta. Elena ES | BULA | 5 | 1 | 4 | 2STY4CL | BATCH 1 | 8009262.67 |  |  | Completed | 1
36733 | NC 2018 | k10 | Region V | Camarines Sur | 112818 | Nabua East CS (Pilot) | NABUA | 5 | 1 | 4 | 2STY4CL | BATCH 1 | 8833959.41 |  |  | Completed | 1
36734 | NC 2018 | k10 | Region V | Camarines Sur | 112838 | Nabua West CS | NABUA | 5 | 1 | 4 | 2STY4CL | BATCH 1 | 8751417.27 |  |  | Completed | 1
36735 | NC 2018 | k10 | Region V | Camarines Sur | 112844 | Sto. Domingo ES | NABUA | 5 | 1 | 6 | 2STY6CL | BATCH 1 | 11276879.55 |  |  | Completed | 1
36736 | NC 2018 | TVL | Region V | Camarines Sur | 301926 | Agdangan National High School | BAAO | 5 | 1 | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9890035.33 |  |  | Completed | 1
36737 | NC 2018 | TVL | Region V | Camarines Sur | 301926 | Agdangan National High School | BAAO | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9959170.96 |  |  | Completed | 1
36738 | NC 2018 | SHS | Region V | Camarines Sur | 301931 | Baao National High School | BAAO | 5 | 1 | 9 | 3STY9CL | BATCH 1 | 22983878.03 |  |  | Completed | 1
36739 | NC 2018 | TVL | Region V | Camarines Sur | 301933 | Eusebia Paz Arroyo Mem. NHS | BAAO | 5 | 1 | 4 | 4storey - 2 Regular Workshop ,1 ICT Lab, 1 science lab | BATCH 1 | 19815532.24 |  |  | Completed | 1
36740 | NC 2018 | TVL | Region V | Camarines Sur | 301938 | Balaogan National High School | BULA | 5 | 1 | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9547002.97 |  |  | Completed | 1
36741 | NC 2018 | TVL | Region V | Camarines Sur | 301938 | Balaogan National High School | BULA | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9143507.03 |  |  | Completed | 1
36742 | NC 2018 | TVL | Region V | Camarines Sur | 301947 | Bula NHS | BULA | 5 | 1 | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 12350655.78 |  |  | Completed | 1
36743 | NC 2018 | TVL | Region V | Camarines Sur | 301947 | Bula NHS | BULA | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 12036404.4 |  |  | Completed | 1
36744 | NC 2018 | TVL | Region V | Camarines Sur | 301948 | Bula NHS - Caorasan Annex HS | BULA | 5 | 1 | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9599927.47 |  |  | Completed | 1
36745 | NC 2018 | TVL | Region V | Camarines Sur | 301948 | Bula NHS - Caorasan Annex HS | BULA | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9115976.14 |  |  | Completed | 1
36746 | NC 2018 | SHS | Region V | Camarines Sur | 301956 | Caranday HS | BAAO | 5 | 1 | 15 | 3STY15CL | BATCH 1 | 32077452.24 |  |  | Completed | 1
36747 | NC 2018 | TVL | Region V | Camarines Sur | 301959 | Casugad High School | BULA | 5 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 9143507.03 |  |  | Completed | 1
36748 | NC 2018 | TVL | Region V | Camarines Sur | 301959 | Casugad High School | BULA | 5 |  | 2 | 2sty (1ict, 1sci) | BATCH 1 | 8422306.28 |  |  | Completed | 1
36749 | NC 2018 | TVL | Region V | Camarines Sur | 301960 | Coguit HS | BALATAN | 5 | 1 | 3 | 3storey - 1 Regular Workshop ,1 ICT Lab, 1 science lab | BATCH 1 | 14752338.21 |  |  | Completed | 1
36750 | NC 2018 | SHS | Region V | Camarines Sur | 301960 | Coguit HS | BALATAN | 5 |  | 9 | 3STY9CL | BATCH 1 | 23556686.56 |  |  | Completed | 1
36751 | NC 2018 | TVL | Region V | Camarines Sur | 301971 | Fabrica HS | BULA | 5 | 1 | 3 | 3storey - 1 Regular Workshop ,2 ICT Lab | BATCH 1 | 14752338.21 |  |  | Completed | 1
36752 | NC 2018 | TVL | Region V | Camarines Sur | 301971 | Fabrica HS | BULA | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9143507.03 |  |  | Completed | 1
36753 | NC 2018 | TVL | Region V | Camarines Sur | 301982 | Inoyonan National HS | BULA | 5 | 1 | 2 | 2sty (1ict, 1sci) | BATCH 1 | 9427621.95 |  |  | Completed | 1
36754 | NC 2018 | TVL | Region V | Camarines Sur | 301982 | Inoyonan National HS | BULA | 5 |  | 2 | 2sty (2reg ws) | BATCH 1 | 9393578.38 |  |  | Completed | 1
36755 | NC 2018 | TVL | Region V | Camarines Sur | 301985 | La Purisima National High School | NABUA | 5 | 1 | 3 | 3sty (1sci, 1ct, 1Reg ws) | BATCH 1 | 14752338.21 |  |  | Completed | 1
36756 | NC 2018 | TVL | Region V | Camarines Sur | 301991 | Malawag National High School | NABUA | 5 | 1 | 3 | 3sty (1sci, 1ct, 1Reg ws) | BATCH 1 | 14752338.21 |  |  | Completed | 1
36757 | NC 2018 | TVL | Region V | Camarines Sur | 301992 | Tandaay Provincial HS | NABUA | 5 | 1 | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9568688.43 |  |  | Completed | 1
36758 | NC 2018 | TVL | Region V | Camarines Sur | 301992 | Tandaay Provincial HS | NABUA | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9329830.37 |  |  | Completed | 1
36759 | NC 2018 | TVL | Region V | Camarines Sur | 301997 | Masoli High School | BATO | 5 | 1 | 6 | 3sty (2ict, 2sci, 2Regular workshop) | BATCH 1 | 29504676.42 |  |  | Completed | 1
36760 | NC 2018 | TVL | Region V | Camarines Sur | 302001 | Nabua National High School | NABUA | 5 | 1 | 6 | 3sty (2ict, 2sci, 2Regular workshop) | BATCH 1 | 36354676.42 |  |  | Completed | 1
36761 | NC 2018 | TVL | Region V | Camarines Sur | 302002 | Lourdes PHS | NABUA | 5 | 1 | 2 | 2sty (1ict, 1sci) | BATCH 1 | 8682756.94 |  |  | Completed | 1
36762 | NC 2018 | TVL | Region V | Camarines Sur | 302003 | Victor Bernal High School | NABUA | 5 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 8682756.94 |  |  | Completed | 1
36763 | NC 2018 | TVL | Region V | Camarines Sur | 302003 | Victor Bernal High School | NABUA | 5 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9089383.86 |  |  | Completed | 1
36764 | NC 2018 | TVL | Region V | Camarines Sur | 302003 | Victor Bernal High School | NABUA | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 8682756.94 |  |  | Completed | 1
36765 | NC 2018 | TVL | Region V | Camarines Sur | 302007 | Ombao HS | BULA | 5 | 1 | 3 | 3sty - 3regular Workshop | BATCH 1 | 14752338.21 |  |  | Completed | 1
36766 | NC 2018 | TVL | Region V | Camarines Sur | 302007 | Ombao HS | BULA | 5 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9325913.68 |  |  | Completed | 1
36767 | NC 2018 | TVL | Region V | Camarines Sur | 302007 | Ombao HS | BULA | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9127002.9 |  |  | Completed | 1
36768 | NC 2018 | TVL | Region V | Camarines Sur | 302010 | Palsong NHS | BULA | 5 | 1 | 3 | 3sty - 3regular Workshop | BATCH 1 | 17752338.21 |  |  | Completed | 1
36769 | NC 2018 | TVL | Region V | Camarines Sur | 302010 | Palsong NHS | BULA | 5 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 12125913.68 |  |  | Completed | 1
36770 | NC 2018 | TVL | Region V | Camarines Sur | 302010 | Palsong NHS | BULA | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 11812184.11 |  |  | Completed | 1
36771 | NC 2018 | SHS | Region V | Camarines Sur | 302010 | Palsong NHS | BULA | 5 |  | 6 | 2STY6CL | BATCH 1 | 15203211.95 |  |  | Completed | 1
36772 | NC 2018 | TVL | Region V | Camarines Sur | 302014 | Pararao High School | BALATAN | 5 | 1 | 3 | 3sty (1ict, 1sci, 1Regular workshop) | BATCH 1 | 14852338.21 |  |  | Completed | 1
36773 | NC 2018 | TVL | Region V | Camarines Sur | 302026 | Salvacion HS, Bato | BATO | 5 | 1 | 6 | 3sty (2ict, 2sci, 2Regular workshop) | BATCH 1 | 29504676.42 |  |  | Completed | 1
36774 | NC 2018 | TVL | Region V | Camarines Sur | 302027 | San Roque High School | BATO | 5 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 9143507.03 |  |  | Completed | 1
36775 | NC 2018 | TVL | Region V | Camarines Sur | 302027 | San Roque High School | BATO | 5 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9836457.29 |  |  | Completed | 1
36776 | NC 2018 | TVL | Region V | Camarines Sur | 302027 | San Roque High School | BATO | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9568740.93 |  |  | Completed | 1
36777 | NC 2018 | TVL | Region V | Camarines Sur | 302041 | San Ramon HS | BULA | 5 | 1 | 3 | 3sty - 3 Regular Workshop Bldg. | BATCH 1 | 14752338.21 |  |  | Completed | 1
36778 | NC 2018 | TVL | Region V | Camarines Sur | 302041 | San Ramon HS | BULA | 5 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9325913.68 |  |  | Completed | 1
36779 | NC 2018 | TVL | Region V | Camarines Sur | 302041 | San Ramon HS | BULA | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 8774190.33 |  |  | Completed | 1
36780 | NC 2018 | TVL | Region V | Camarines Sur | 302043 | San Vicente NHS | BUHI | 5 | 1 | 3 | 3sty (1ict, 1sci, 1Regular workshop) | BATCH 1 | 14552338.21 |  |  | Completed | 1
36781 | NC 2018 | TVL | Region V | Camarines Sur | 302044 | Bato National High School | BATO | 5 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 9329830.37 |  |  | Completed | 1
36782 | NC 2018 | TVL | Region V | Camarines Sur | 302044 | Bato National High School | BATO | 5 |  | 3 | 3sty (1ict, 1sci, 1Regular workshop) | BATCH 1 | 14752338.21 |  |  | Completed | 1
36783 | NC 2018 | SHS | Region V | Camarines Sur | 302044 | Bato National High School | BATO | 5 |  | 4 | 2STY4CL | BATCH 1 | 8109262.67 |  |  | Completed | 1
36784 | NC 2018 | TVL | Region V | Camarines Sur | 302050 | Sta. Justina High School | BUHI | 5 | 1 | 3 | 3sty (1ict, 1sci, 1Regular workshop) | BATCH 1 | 14552338.21 |  |  | Completed | 1
36785 | NC 2018 | SHS | Region V | Camarines Sur | 302050 | Sta. Justina High School | BUHI | 5 |  | 9 | 3STY9CL | BATCH 1 | 22721960.13 |  |  | Completed | 1
36786 | NC 2018 | TVL | Region V | Camarines Sur | 302057 | Tambo National High School | BUHI | 5 | 1 | 3 | 3sty (1ict, 1sci, 1Regular workshop) | BATCH 1 | 14752338.21 |  |  | Completed | 1
36787 | NC 2018 | SHS | Region V | Camarines Sur | 302057 | Tambo National High School | BUHI | 5 |  | 9 | 3STY9CL | BATCH 1 | 22790779.49 |  |  | Completed | 1
36788 | NC 2018 | TVL | Region V | Camarines Sur | 302059 | Tapayas High School | BALATAN | 5 | 1 | 3 | 3sty (1ict, 1sci, 1Regular workshop) | BATCH 1 | 14752338.21 |  |  | Completed | 1
36789 | NC 2018 | TVL | Region V | Camarines Sur | 309725 | Laganac High School | BALATAN | 5 | 1 | 6 | 3sty (2ict, 2sci, 2Regular workshop) | BATCH 1 | 28704676.42 |  |  | Completed | 1
36790 | NC 2018 | TVL | Region V | Camarines Sur | 309746 | PAYAK HIGH SCHOOL | BATO | 5 | 1 | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9599927.47 |  |  | Completed | 1
36791 | NC 2018 | TVL | Region V | Camarines Sur | 309746 | PAYAK HIGH SCHOOL | BATO | 5 |  | 3 | 3sty (2sci, 1Regular workshop) | BATCH 1 | 14752338.21 |  |  | Completed | 1
36792 | NC 2018 | TVL | Region V | Camarines Sur | 309759 | Pulang Daga High School | BALATAN | 5 | 1 | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9699927.47 |  |  | Completed | 1
36793 | NC 2018 | TVL | Region V | Camarines Sur | 309759 | Pulang Daga High School | BALATAN | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9493578.38 |  |  | Completed | 1
36794 | NC 2018 | TVL | Region V | Camarines Sur | 309759 | Pulang Daga High School | BALATAN | 5 |  | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 9493578.38 |  |  | Completed | 1
36795 | NC 2018 | TVL | Region V | Camarines Sur | 309760 | Fabrica HS - La Victoria Annex HS | BULA | 5 | 1 | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9113051.1 |  |  | Completed | 1
36796 | NC 2018 | TVL | Region V | Camarines Sur | 309760 | Fabrica HS - La Victoria Annex HS | BULA | 5 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9143507.03 |  |  | Completed | 1
36797 | NC 2018 | SHS | Region V | Camarines Sur |  | Buhi HS | Buhi | 5 | 1 | 20 | 2units 2STY10CL | BATCH 1 | 36072718.69 |  |  | Completed | 1
36798 | NC 2018 | TVL | Region V | Camarines Sur | 301929 | Simeon Tycangco Memorial High School | RAGAY | 1 | 1 | 4 | 2storey - 2 science lab & 2 ICT | Batch 3 | 36955055.12 |  |  | Completed | 1
36799 | NC 2018 | TVL | Region V | Camarines Sur | 301961 | Colacling National High School | LUPI | 1 | 1 | 3 | 3storey - 1 Regular, 1 science lab, 1 ICT | Batch 3 | 28049934.2 |  |  | Completed | 1
36800 | NC 2018 | TVL | Region V | Camarines Sur | 302020 | Ragay National Agricultural and Fisheries School (RNAFS) | RAGAY | 1 | 1 | 3 | 3units UNIQUE WORKSHOP (7x22.5) | Batch 3 | 16594896.03 |  |  | Completed | 1
36801 | NC 2018 | TVL | Region V | Camarines Sur | 302047 | Sipocot NHS | SIPOCOT | 1 | 1 | 6 | 2units 3storey - 1 Regular, 1 science lab, 1 ICT | Batch 3 | 50389390.76 |  |  | Completed | 1
36802 | NC 2018 | SHS | Region V | Camarines Sur | 302064 | Tomas A. Andaya, Sr. NHS | RAGAY | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4003787.8 |  |  | Completed | 1
36803 | NC 2018 | K10 | Region V | Camarines Sur | 112677 | Fundado ES | LIBMANAN | 2 | 1 | 6 | 2STY6CL | Batch 3 | 15488052.29 |  |  | Completed | 1
36804 | NC 2018 | K10 | Region V | Camarines Sur | 112874 | San Gabriel ES | PAMPLONA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12163046.81 |  |  | Completed | 1
36805 | NC 2018 | K10 | Region V | Camarines Sur | 112911 | Pasacao CS | PASACAO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 15418930.44 |  |  | Completed | 1
36806 | NC 2018 | SHS | Region V | Camarines Sur | 301935 | Bahao HS | LIBMANAN | 2 | 1 | 8 | 2STY8CL | Batch 3 | 24145748.29 |  |  | Completed | 1
36807 | NC 2018 | SHS | Region V | Camarines Sur | 301936 | Homobono H. Gonzalez National High School | LIBMANAN | 2 | 1 | 8 | 2STY8CL | Batch 3 | 21119289.24 |  |  | Completed | 1
36808 | NC 2018 | SHS | Region V | Camarines Sur | 302031 | San Fernando NHS | SAN FERNANDO | 2 | 1 | 8 | 2STY8CL | Batch 3 | 23680957.5 |  |  | Completed | 1
36809 | NC 2018 | K10 | Region V | Camarines Sur | 112466 | Balongay ES | CALABANGA | 3 | 1 | 3 | 1STY3CL | Batch 3 | 6763610.27 |  |  | Completed | 1
36810 | NC 2018 | K10 | Region V | Camarines Sur | 112472 | Calabanga West Central School | CALABANGA | 3 | 1 | 5 | 1STY5CL | Batch 3 | 10045577.37 |  |  | Completed | 1
36811 | NC 2018 | K10 | Region V | Camarines Sur | 112475 | Dominorog Elementary School | CALABANGA | 3 | 1 | 4 | 1STY4CL | Batch 3 | 8538647.6 |  |  | Completed | 1
36812 | NC 2018 | K10 | Region V | Camarines Sur | 112484 | Manuel Y. Garza Sr. ES | CALABANGA | 3 | 1 | 8 | 2STY8CL | Batch 3 | 27840749.11 |  |  | Completed | 1
36813 | NC 2018 | K10 | Region V | Camarines Sur | 112488 | Quipayo ES | CALABANGA | 3 |  | 5 | 1STY5CL | Batch 3 | 10045577.37 |  |  | Completed | 1
36814 | NC 2018 | K10 | Region V | Camarines Sur | 112488 | Quipayo ES | CALABANGA | 3 |  | 3 | 1STY3CL | Batch 3 | 6837958.17 |  |  | Completed | 1
36815 | NC 2018 | K10 | Region V | Camarines Sur | 112489 | Ratay ES | CALABANGA | 3 | 1 | 6 | 2STY6CL | Batch 3 | 23802796.83 |  |  | Completed | 1
36816 | NC 2018 | K10 | Region V | Camarines Sur | 112490 | Sabang ES | CALABANGA | 3 | 1 | 6 | 2STY6CL | Batch 3 | 22599838.71 |  |  | Completed | 1
36817 | NC 2018 | K10 | Region V | Catanduanes | 113201 | Palumbanes IS | Caramoran | 0 | 1 | 6 | 2STY - 6CL (7x9) | BATCH 1 | 13792766.7296 |  |  | COMPLETED | 1
36818 | NC 2018 | TVL | Region V | Catanduanes | 302070 | Agban NHS | Baras | 0 | 1 | 4 | 2STY-4CL (7 x 18), 2unit-Science Lab. & 2unit- (7 x 18) ICT Lab | BATCH 1 | 18708549.8397 |  |  | COMPLETED | 1
36819 | NC 2018 | TVL | Region V | Catanduanes | 302071 | Antipolo NHS | Virac (Capital) | 0 | 1 | 8 | 3STY-12CL, 2unit- (7x18) Science Lab, 2unit- (7x18) ICT & 4CL (7x9) SHS | BATCH 1 | 31959367.57 |  |  | COMPLETED | 1
36820 | NC 2018 | TVL | Region V | Catanduanes | 302072 | Bagamanoc RDHS | Bagamanoc | 0 | 1 | 4 | 2STY-4CL, 2unit- (7x18) Science Lab. & 2unit- (7x9) SHS | BATCH 1 | 13460904.3176 |  |  | COMPLETED | 1
36821 | NC 2018 | TVL | Region V | Catanduanes | 302072 | Bagamanoc RDHS | Bagamanoc | 0 |  | 8 | 4STY-8CL, 6 unit - (7x18) Regular Workshop & 2 unit - (7x18) ICT Lab | BATCH 1 | 37404094.2135 |  |  | Terminated | 0 | [10 empty] | Terminated (With Approved Buffer Fund); Contract Terminated. Prepared POW/DUPA for funding to complete the project
36822 | NC 2018 | TVL | Region V | Catanduanes | 302073 | Baras RDHS | Baras | 0 | 1 | 12 | 4STY-12CL, 2unit- (7x18) Science Lab, 2unit- (7x18) ICT & 8CL (7x9) SHS | BATCH 1 | 37908633.6 |  |  | COMPLETED | 1
36823 | NC 2018 | TVL | Region V | Catanduanes | 302073 | Baras RDHS | Baras | 0 |  | 10 | 4STY-16CL, 6unit- (7x18) Regular Workshop & 4CL (7x9) SHS | BATCH 1 | 36623946.1736 |  |  | COMPLETED | 1
36824 | NC 2018 | TVL | Region V | Catanduanes | 302075 | Bote Integrated School | BATO | 0 | 1 | 12 | 4STY- 12CL, - 2unit (7 x 18) Science Lab., 2unit (7 x 18) ICT Lab, & 8CL (7x9) SHS | BATCH 1 | 39812448.27 |  |  | Terminated | 1 | [10 empty] | Project Substantially Completed. with unpaid obligation amounting to 7,296,396.21 to the contractor per letter dated April 13, 2023.
36825 | NC 2018 | TVL | Region V | Catanduanes | 302076 | Bugao NHS | Bagamanoc | 0 | 1 | 4 | 2STY-4CL (7 x 18), 2unit-Science Lab. & 2unit- (7 x 18) ICT Lab | BATCH 1 | 18890811.1013 |  |  | COMPLETED | 1
36826 | NC 2018 | TVL | Region V | Catanduanes | 302078 | Cabcab NHS | San Andres (Calolbon) | 0 | 1 | 10 | 4STY- 10CL, 2unit (7 x 18) Science Lab., 2unit (7 x 18) ICT Lab, 2unit (7x18) Regular Workshop, 4CL (7x9) SHS | BATCH 1 | 37632406.0106 |  |  | COMPLETED | 1
36827 | NC 2018 | TVL | Region V | Catanduanes | 302081 | Caramoran RDHS | Caramoran | 0 | 1 | 6 | 3STY- 6CL, 6unit - (7x18) Regular Workshop | BATCH 1 | 29451572.5977 |  |  | COMPLETED | 1
36828 | NC 2018 | TVL | Region V | Catanduanes | 302081 | Caramoran RDHS | Caramoran | 0 |  | 8 | 3STY-12CL, 2unit (7x18) Science Lab., 2unit (7x18) ICT Lab., & 4CL (7x9) SHS | BATCH 1 | 29353716.1121 |  |  | COMPLETED | 1
36829 | NC 2018 | TVL | Region V | Catanduanes | 302082 | Caramoran SF | Caramoran | 0 | 1 | 4 | 2STY- 4CL, 4unit (7x18) Regular Workshop | BATCH 1 | 18624122.2197 |  |  | COMPLETED | 1
36830 | NC 2018 | TVL | Region V | Catanduanes | 302082 | Caramoran SF | Caramoran | 0 |  | 4 | 2STY-4CL (7 x 18), 2unit-Science Lab. & 2unit- (7 x 18) ICT Lab | BATCH 1 | 19030509.8739 |  |  | COMPLETED | 1
36831 | NC 2018 | TVL | Region V | Catanduanes | 302083 | Catanduanes NHS | Virac (Capital) | 0 | 1 | 12 | 4STY- 24CL, 12unit (7 x 18)Regular Workshop | BATCH 1 | 48371101.4111 |  |  | COMPLETED | 1
36832 | NC 2018 | TVL | Region V | Catanduanes | 302083 | Catanduanes NHS | Virac (Capital) | 0 |  | 12 | 3STY- 15CL, 2unit (7 x 18) ICT lab, 1unit (7x18) Regular Workshop & 9cl (7x9) SHS | BATCH 1 | 34368803.71 |  |  | COMPLETED | 1
36833 | NC 2018 | TVL | Region V | Catanduanes | 302083 | Catanduanes NHS | Virac (Capital) | 0 |  | 13 | 3STY- 15CL, 2units (7 x 18) Science lab, & 11cl (7x9) SHS | BATCH 1 | 34152487.74 |  |  | COMPLETED | 1
36834 | NC 2018 | TVL | Region V | Catanduanes | 302084 | Calatagan High School | Virac (Capital) | 0 | 1 | 17 | 4STY- 28CL, 2unit (7 x 18) Science Lab., 2unit (7 x 18) ICT Lab, 7unit (7 x 18)Regular Workshop & 6 CL (7x9) SHS | BATCH 1 | 58681682.6765 |  |  | COMPLETED | 1
36835 | NC 2018 | TVL | Region V | Catanduanes | 302088 | Gigmoto RDHS | Gigmoto | 0 | 1 | 8 | 4STY- 16CL, - 2unit (7 x 18) Science Lab., 2unit- (7 x 18) ICT Lab, & 4unit- (7 x 18) Regular Workshop | BATCH 1 | 36974575.4001 |  |  | Terminated | 0 | [10 empty] | Terminated (With Approved Buffer Fund); Contract Terminated. Prepared POW/DUPA for funding to complete the project
36836 | NC 2018 | TVL | Region V | Catanduanes | 302090 | Magnesia NHS | Virac (Capital) | 0 | 1 | 2 | 2STY -2CL, 2unit (7x18) Regular Workshop | BATCH 1 | 9721317.45 |  |  | COMPLETED | 1
36837 | NC 2018 | TVL | Region V | Catanduanes | 302090 | Magnesia NHS | Virac (Capital) | 0 |  | 4 | 2STY- 4CL, - 2unit (7 x 18) Science Lab. & 2unit (7 x 18) ICT Lab | BATCH 1 | 18625251.9261 |  |  | COMPLETED | 1
36838 | NC 2018 | SHS | Region V | Catanduanes | 302090 | Magnesia NHS | Virac (Capital) | 0 |  | 4 | 2STY4CL | BATCH 1 | 9912430.27 |  |  | COMPLETED | 1
36839 | NC 2018 | TVL | Region V | Catanduanes | 302091 | Manambrag NHS | San Andres (Calolbon) | 0 | 1 | 6 | 3STY- 6CL, - 2unit (7 x 18) Science Lab., 2unit (7 x 18) ICT Lab, & 2unit (7 x 18) CL Regular Workshop | BATCH 1 | 29638559.5035 |  |  | COMPLETED | 1
36840 | NC 2018 | TVL | Region V | Catanduanes | 302092 | Mayngaway NHS | San Andres (Calolbon) | 0 | 1 | 5 | 3STY- 6CL, - 1unit (7 x 18)Regular Workshop & 4CL (7x9) SHS | BATCH 1 | 17281280.8075 |  |  | COMPLETED | 1
36841 | NC 2018 | TVL | Region V | Catanduanes | 302092 | Mayngaway NHS | San Andres (Calolbon) | 0 |  | 12 | 4STY- 20CL, - 2unit (7 x 18) Science Lab., 2unit (7 x 18) ICT Lab, 4unit (7 x 18)Regular Workshop & 4CL (7x9) SHS | BATCH 1 | 48142676.6184 |  |  | COMPLETED | 1
36842 | NC 2018 | TVL | Region V | Catanduanes | 302093 | Palta NHS | Virac (Capital) | 0 | 1 | 4 | 2STY- 4CL, - 2unit (7 x 18) ICT Lab, & 2unit (7 x 18) Regular Workshop | BATCH 1 | 17961843.8572 |  |  | COMPLETED | 1
36843 | NC 2018 | TVL | Region V | Catanduanes | 302093 | Palta NHS | Virac (Capital) | 0 |  | 2 | 2STY-2CL, 2unit (7 x 18) Science Lab | BATCH 1 | 10105481.8408 |  |  | COMPLETED | 1
36844 | NC 2018 | TVL | Region V | Catanduanes | 302094 | Pandan SAT | Pandan | 0 | 1 | 6 | 2STY- 6CL, 6unit (7x18) Regular Workshop | BATCH 1 | 30560180.8511 |  |  | COMPLETED | 1
36845 | NC 2018 | TVL | Region V | Catanduanes | 302094 | Pandan SAT | Pandan | 0 |  | 4 | 2STY- 4CL - 2unit (7 x 18) Science Lab. & 2unit (7 x 18) ICT Lab | BATCH 1 | 23369665.2988 |  |  | COMPLETED | 1
36846 | NC 2018 | TVL | Region V | Catanduanes | 302095 | Panganiban NHS | Panganiban (Payo) | 0 | 1 | 4 | 4STY - 4CL, 2unit (7x18) Science Lab., 2unit (7x18) ICT Lab. | BATCH 1 | 19170653.9494 |  |  | Completed | 1 | [10 empty] | Terminated
36847 | NC 2018 | TVL | Region V | Catanduanes | 302096 | San Andres VS | San Andres (Calolbon) | 0 | 1 | 9 | 4STY- 16CL , 7unit (7x18) Regular Workshop & 2CL (7x9) SHS with micropiles | BATCH 1 | 47840961.7066 |  |  | COMPLETED | 1
36848 | NC 2018 | TVL | Region V | Catanduanes | 302096 | San Andres VS | San Andres (Calolbon) | 0 |  | 12 | 4STY- 16CL , 2unit (7x18) Regular Workshop, 2unit (7x18) ICT Lab & 8CL (7x9) SHS | BATCH 1 | 47203716.58 |  |  | COMPLETED | 1
36849 | NC 2018 | TVL | Region V | Catanduanes | 302097 | San Jose NHS | VIGA | 0 | 1 | 10 | 4STY- 10CL, - 2unit (7 x 18) Science Lab., 2unit (7 x 18) ICT Lab, 2unit (7x18) Regular Workshop & 4cl (7x9) SHS | BATCH 1 | 37266180.25 |  |  | COMPLETED | 1
36850 | NC 2018 | TVL | Region V | Catanduanes | 302098 | San Miguel Rural DHS | SAN MIGUEL | 0 | 1 | 8 | 4STY- 8CL, - 2unit (7 x 18) Science Lab., 2unit (7 x 18) ICT Lab & 4unit (7x18) Regular Workshop | BATCH 1 | 37754660.17 |  |  | COMPLETED | 1
36851 | NC 2018 | TVL | Region V | Catanduanes | 302099 | Mabato NHS (SMRDHS Annex) | SAN MIGUEL | 0 | 1 | 6 | 3STY- 6CL, - 2unit (7 x 18) Science Lab., 2unit (7 x 18) ICT Lab & 2unit (7x18) Regular Workshop | BATCH 1 | 30301620.81 |  |  | COMPLETED | 1
36852 | NC 2018 | TVL | Region V | Catanduanes | 302102 | Supang-Datag NHS | Caramoran | 0 | 1 | 3 | 3STY- 3CL Regular Workshop | BATCH 1 | 15459408.9139 |  |  | COMPLETED | 1
36853 | NC 2018 | TVL | Region V | Catanduanes | 302102 | Supang-Datag NHS | Caramoran | 0 |  | 8 | 4STY- 8CL, - 2unit (7 x 18) Science Lab., 2unit- (7 x 18) ICT Lab, & 4unit- (7 x 18) Regular Workshop | BATCH 1 | 37055827.3504 |  |  | Completed | 1 | [10 empty] | Terminated (With Approved Buffer Fund)
36854 | NC 2018 | TVL | Region V | Catanduanes | 302103 | Leandro I. Verceles Sr. NHS | Pandan | 0 | 1 | 4 | 2STY- 4CL - 2unit (7 x 18) Science Lab. & 2unit (7 x 18) ICT Lab | BATCH 1 | 19442148.8729 |  |  | COMPLETED | 1
36855 | NC 2018 | TVL | Region V | Catanduanes | 302103 | Leandro I. Verceles Sr. NHS | Pandan | 0 |  | 4 | 2STY- 4CL, 4unit (7x18) Regular Workshop | BATCH 1 | 19035761.2174 |  |  | COMPLETED | 1
36856 | NC 2018 | TVL | Region V | Catanduanes | 302104 | Tambongon NHS | Viga | 0 | 1 | 17 | 4STY- 24CL, 2unit (7 x 18) Science Lab., 2unit (7 x 18) ICT Lab, 3unit (7x18) Regular Workshop, 10CL (7x9) SHS | BATCH 1 | 49766950.7638 |  |  | COMPLETED | 1
36857 | NC 2018 | TVL | Region V | Catanduanes | 302106 | Tubli NHS | Caramoran | 0 | 1 | 8 | 4STY- 8CL, - 2unit (7 x 18) Science Lab., 2unit- (7 x 18) ICT Lab, & 4unit- (7 x 18) Regular Workshop | BATCH 1 | 37440130.8862 |  |  | COMPLETED | 1
36858 | NC 2018 | TVL | Region V | Catanduanes | 302106 | Tubli NHS | Caramoran | 0 |  | 3 | 2STY3CL, 1unit (7x18) Regular Workshop & 2cl (7x9) SHS | BATCH 1 | 10718603.78 |  |  | COMPLETED | 1
36859 | NC 2018 | TVL | Region V | Catanduanes | 302107 | Viga RDHS | Viga | 0 | 1 | 10 | 4STY- 10CL, 2unit (7 x 18) Science Lab., 2unit (7 x 18) ICT Lab, 2unit (7x18) Regular Workshop, 4CL (7x9) SHS | BATCH 1 | 36960085.6769 |  |  | Terminated | 0 | [10 empty] | Terminated (With Approved Buffer Fund); Contract Terminated. Prepared POW/DUPA for funding to complete the project
36860 | NC 2018 | TVL | Region V | Catanduanes | 309801 | Panganiban NHS (CAIC Compound) | Panganiban (Payo) | 0 | 1 | 6 | 3STY- 6CL, - 2unit (7 x 18) Science Lab., 2unit (7 x 18) ICT Lab, & 2unit (7 x 18) CL Regular Workshop | BATCH 1 | 29961052.7799 |  |  | COMPLETED | 1
36861 | NC 2018 | SHS | Region V | Catanduanes | 309803 | Milaviga IS | Caramoran | 0 | 1 | 10 | 2STY - 10CL (7x9) | BATCH 1 | 21554379.714 |  |  | COMPLETED | 1
36862 | NC 2018 | TVL | Region V | Catanduanes | 500031 | Buyo IS | Virac (Capital) | 0 | 1 | 6 | 3STY- 6CL, - 2unit (7 x 18) Science Lab, 2unit (7 x 18) ICT Lab, & 2unit (7 x 18) Regular Workshop | BATCH 1 | 28829639.269 |  |  | COMPLETED | 1
36863 | NC 2018 | TVL | Region V | Catanduanes | 500032 | Cabugao IS | Bato | 0 | 1 | 8 | 4STY - 8CL, 8unit (7x18) Regular Workshop | BATCH 1 | 37008095.0398 |  |  | COMPLETED | 1
36864 | NC 2018 | TVL | Region V | Catanduanes | 500032 | Cabugao IS | Bato | 0 |  | 4 | 2STY- 4CL, - 2unit (7 x 18) Science Lab. & 2unit (7 x 18) ICT Lab | BATCH 1 | 19303602.4478 |  |  | COMPLETED | 1
36865 | NC 2018 | TVL | Region V | Catanduanes | 500033 | Sicmil IS | Gigmoto | 0 | 1 | 4 | 2STY- 4CL, - 2unit (7 x 18) Science Lab. & 2unit (7 x 18) ICT Lab | BATCH 1 | 18717184.9123 |  |  | COMPLETED | 1
36866 | NC 2018 | TVL | Region V | Catanduanes | 500159 | Cobo IS | Pandan | 0 | 1 | 4 | 2STY- 4CL, - 2unit (7 x 18) Science Lab. & 2unit (7 x 18) ICT Lab | BATCH 1 | 19582787.1951 |  |  | COMPLETED | 1
36867 | NC 2018 | SHS | Region V | Iriga City | 302251 | Rinconada National Technical Vocational School | IRIGA CITY | 5 | 1 | 6 | 3STY6CL | BATCH 1 | 14001787.26 |  |  | COMPLETED | 1
36868 | NC 2018 | K10 | Region V | Iriga City | 302253 | Zeferino Arroyo HS | IRIGA CITY | 5 | 1 | 15 | 3STY15CL | BATCH 1 | 31777452.24 |  |  | COMPLETED | 1
36869 | NC 2018 | K10 | Region V | Iriga City | 114422 | San Agustin ES | IRIGA CITY | 5 | 1 | 6 | 3STY6CL | Batch 3 | 16260760.33 |  |  | COMPLETED | 1
36870 | NC 2018 | SHS | Region V | Iriga City | 302251 | Rinconada National Technical Vocational School | IRIGA CITY | 5 | 1 | 4 | 2STY4CL | Batch 3 | 9874937.22 |  |  | COMPLETED | 1
36871 | NC 2018 | K10 | Region V | Legaspi City | 114458 | Bogna Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9636312.47 |  |  | Completed | 1 |  |  | P00271595LZ-CW1 | 18FB0158
36872 | NC 2018 | K10 | Region V | Legaspi City | 114459 | Bogtong ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 1 | 17559419 |  |  | Completed | 1 |  |  | P00271596LZ-CW1 | 18FB0140
36873 | NC 2018 | K10 | Region V | Legaspi City | 114464 | Pawa ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 1 | 17200514 |  |  | Completed | 1 |  |  | P00271597LZ-CW1 | 18FB0141
36874 | NC 2018 | K10 | Region V | Legaspi City | 114467 | Banquerohan Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 9719903.4541 |  |  | Completed | 1 |  |  | P00271598LZ-CW1 | 18FB0162
36875 | NC 2018 | K10 | Region V | Legaspi City | 114468 | Bariis ES | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9636812.47 |  |  | Completed | 1 |  |  | P00271599LZ-CW1 | 18FB0161
36876 | NC 2018 | K10 | Region V | Legaspi City | 114469 | Buenavista Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 10095721.2041 |  |  | Completed | 1 |  |  | P00271600LZ-CW1 | 18FB0163
36877 | NC 2018 | K10 | Region V | Legaspi City | 114472 | Eztanza Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 9719903.45 |  |  | Completed | 1 |  |  | P00271601LZ-CW1 | 18FB0214
36878 | NC 2018 | K10 | Region V | Legaspi City | 114473 | San Francisco ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12539686.62 |  |  | Completed | 1 |  |  | P00271602LZ-CW1 | 18FB0218
36879 | NC 2018 | K10 | Region V | Legaspi City | 114485 | Arimbay ES | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9402915.23 |  |  | Completed | 1 |  |  | P00271603LZ-CW1 | 18FB0143
36880 | NC 2018 | K10 | Region V | Legaspi City | 114487 | Bigaa Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 2sty6cl | BATCH 1 | 12299074.41 |  |  | Completed | 1 |  |  | P00271604LZ-CW1 | 18FB0186
36881 | NC 2018 | K10 | Region V | Legaspi City | 114488 | Buyoan Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 2sty6cl | BATCH 1 | 12270170.53 |  |  | Completed | 1 |  |  | P00271605LZ-CW1 | 18FB0197
36882 | NC 2018 | K10 | Region V | Legaspi City | 114490 | Gogon Central School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 9719903.45 |  |  | Completed | 1 |  |  | P00271606LZ-CW1 | 18FB0199
36883 | NC 2018 | K10 | Region V | Legaspi City | 114491 | Matanag Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 9796216.21 |  |  | Completed | 1 |  |  | P00271607LZ-CW1 | 18FB01590
36884 | NC 2018 | SHS | Region V | Legaspi City | 302257 | Banquerohan National High School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2sty4cl | BATCH 1 | 10095721.2041 |  |  | Completed | 1 |  |  | P00271608LZ-CW1 | 18FB0160
36885 | NC 2018 | K10 | Region V | Legaspi City | 114465 | Bagacay ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 2STY6CL | Batch 3 | 17181099 |  |  | COMPLETED | 1 |  |  | P00274308LZ-CW1 | 18FB0291
36886 | NC 2018 | K10 | Region V | Legaspi City | 114488 | Buyoan ES | LEGAZPI CITY (Capital) | 2 | 1 | 12 | 4STY12CL | Batch 6 Realignment | 44721641 |  |  | COMPLETED | 1 |  |  | P00274307LZ-CW1 | 18FB0292
36887 | NC 2018 | SHS | Region V | Legaspi City | 302261 | Pag-asa National High School | LEGAZPI CITY (Capital) | 2 | 1 | 8 | 4STY8CL | Batch 5 | 38313225 |  |  | COMPLETED | 1 |  |  | P00275964LZ-CW1 | 18FB0308
36888 | NC 2018 | SHS | Region V | Legaspi City | 302261 | Pag-Asa National High School | LEGAZPI CITY (Capital) | 2 |  | 12 | 4STY12CL | Batch 5 | 64581381 |  |  | COMPLETED | 1 |  |  | P00275965LZ-CW1 | 18FB0307
36889 | NC 2018 | TVL | Region V | Ligao City | 301817 | Cabarian NHS | CITY OF LIGAO | 3 | 1 | 6 | 3STY12CL (2reg 2ict 2sci) | Batch 3 | 36824267.25 |  |  | COMPLETED | 1
36890 | NC 2018 | K10 | Region V | Ligao City | 301859 | Palapas NHS | CITY OF LIGAO | 3 | 1 | 6 | 2STY6CL | Batch 3 | 19892768.02 |  |  | COMPLETED | 1
36891 | NC 2018 | TVL | Region V | Ligao City | 301862 | Paulba NHS | CITY OF LIGAO | 3 | 1 | 8 | 2STY8CL (2reg 1sci 1ict) | Batch 3 | 21579790.26 |  |  | COMPLETED | 1
36892 | NC 2018 | TVL | Region V | Ligao City | 321701 | Ligao City National Technical -Vocational High School | CITY OF LIGAO | 3 | 1 | 6 | 3STY12CL (2reg 2ict 2sci) | Batch 3 | 37699267.25 |  |  | COMPLETED | 1
36893 | NC 2018 | SHS | Region V | Masbate | 302108 | Adelina P. Laurio National HS | SAN PASCUAL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 10008606.69 |  |  | COMPLETED | 1
36894 | NC 2018 | SHS | Region V | Masbate | 302109 | Andres Clemente Jr.National HS | SAN FERNANDO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9538507.79 |  |  | COMPLETED | 1
36895 | NC 2018 | SHS | Region V | Masbate | 302113 | Bagahanglad NHS | SAN JACINTO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9656892.14 |  |  | COMPLETED | 1
36896 | NC 2018 | SHS | Region V | Masbate | 302124 | Burgos National High School | BATUAN | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9625884.35 |  |  | COMPLETED | 1
36897 | NC 2018 | SHS | Region V | Masbate | 302126 | Tito R. Espinosa Memorial National Agricultural School | CLAVERIA | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9911894.03 |  |  | COMPLETED | 1
36898 | NC 2018 | SHS | Region V | Masbate | 302127 | Buyo NHS | SAN FERNANDO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9503770.78 |  |  | COMPLETED | 1
36899 | NC 2018 | SHS | Region V | Masbate | 302138 | Ipil NHS | SAN FERNANDO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9677404.86 |  |  | COMPLETED | 1
36900 | NC 2018 | SHS | Region V | Masbate | 302167 | San Jacinto NHS | SAN JACINTO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9653758.57 |  |  | COMPLETED | 1
36901 | NC 2018 | SHS | Region V | Masbate | 302168 | San Pascual NHS | SAN PASCUAL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9879135.2 |  |  | COMPLETED | 1
36902 | NC 2018 | SHS | Region V | Masbate | 302173 | Tiburcio A. Berdida, Sr. NHS | CLAVERIA | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9986382.75 |  |  | COMPLETED | 1
36903 | NC 2018 | SHS | Region V | Masbate | 309923 | Cogon High School | MONREAL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9630252.49 |  |  | COMPLETED | 1
36904 | NC 2018 | SHS | Region V | Masbate | 309928 | Emilio Lee-Llacer Sr. HS | SAN JACINTO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9634592.78 |  |  | COMPLETED | 1
36905 | NC 2018 | SHS | Region V | Masbate | 309930 | Gerardo C. Cardiño Sr. HS | MONREAL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 10619043.44 |  |  | COMPLETED | 1
36906 | NC 2018 | SHS | Region V | Masbate | 309935 | MABABANGBAYBAY NHS | CLAVERIA | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 10085251.34 |  |  | COMPLETED | 1
36907 | NC 2018 | SHS | Region V | Masbate | 309937 | Vicente D. Alburo High School | SAN PASCUAL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9890570.9 |  |  | COMPLETED | 1
36908 | NC 2018 | SHS | Region V | Masbate | 309938 | Labangco National High School | SAN PASCUAL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 10361342.89 |  |  | COMPLETED | 1
36909 | NC 2018 | SHS | Region V | Masbate | 500165 | Antonio Lee Llacer Sr. Integrated School | BATUAN | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9832523.69 |  |  | COMPLETED | 1
36910 | NC 2018 | TVL | Region V | Masbate | 302111 | Aroroy NHS | AROROY | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9627110 |  |  | COMPLETED | 1
36911 | NC 2018 | TVL | Region V | Masbate | 302111 | Aroroy NHS | AROROY | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9498770 |  |  | COMPLETED | 1
36912 | NC 2018 | SHS | Region V | Masbate | 302111 | Aroroy NHS | AROROY | 2 |  | 12 | 2UNITS 2STY6CL | BATCH 1 | 23572410 |  |  | COMPLETED | 1 | [10 empty] | suspended
36913 | NC 2018 | TVL | Region V | Masbate | 302115 | Baleno National High School | BALENO | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9552470 |  |  | COMPLETED | 1 | [10 empty] | suspended
36914 | NC 2018 | TVL | Region V | Masbate | 302115 | Baleno National High School | BALENO | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9369230 |  |  | COMPLETED | 1
36915 | NC 2018 | TVL | Region V | Masbate | 302116 | Balud NHS | BALUD | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9754870 |  |  | COMPLETED | 1 | [10 empty] | suspended
36916 | NC 2018 | TVL | Region V | Masbate | 302116 | Balud NHS | BALUD | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9621700 |  |  | COMPLETED | 1 | [10 empty] | suspended
36917 | NC 2018 | TVL | Region V | Masbate | 302117 | Pedro C. Sese, Sr. Mem. HS | BALUD | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9661520 |  |  | COMPLETED | 1
36918 | NC 2018 | TVL | Region V | Masbate | 302117 | Pedro C. Sese, Sr. Mem. HS | BALUD | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9532820 |  |  | COMPLETED | 1
36919 | NC 2018 | TVL | Region V | Masbate | 302119 | Melchor B. Burlaos Memorial High School | MILAGROS | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 11914250 |  |  | COMPLETED | 1 | [10 empty] | suspended
36920 | NC 2018 | TVL | Region V | Masbate | 302119 | Melchor B. Burlaos Memorial High School | MILAGROS | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 11786010 |  |  | COMPLETED | 1 | [10 empty] | suspended
36921 | NC 2018 | TVL | Region V | Masbate | 302122 | Bugtong National High School | MANDAON | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9671060 |  |  | COMPLETED | 1
36922 | NC 2018 | TVL | Region V | Masbate | 302122 | Bugtong National High School | MANDAON | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9541480 |  |  | COMPLETED | 1
36923 | NC 2018 | TVL | Region V | Masbate | 302125 | Cleofe A. Arce Memorial High School | MANDAON | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9673440 |  |  | COMPLETED | 1
36924 | NC 2018 | TVL | Region V | Masbate | 302125 | Cleofe A. Arce Memorial High School | MANDAON | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9534280 |  |  | COMPLETED | 1
36925 | NC 2018 | TVL | Region V | Masbate | 302139 | Jamorawon National High School | MILAGROS | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 11748750 |  |  | COMPLETED | 1 | [10 empty] | suspended
36926 | NC 2018 | TVL | Region V | Masbate | 302139 | Jamorawon National High School | MILAGROS | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 11637610 |  |  | COMPLETED | 1 | [10 empty] | suspended
36927 | NC 2018 | TVL | Region V | Masbate | 302140 | Lagta National High School | BALENO | 2 | 1 | 2 | 2STY2CL ICT LAB | BATCH 1 | 10135370 |  |  | COMPLETED | 1
36928 | NC 2018 | TVL | Region V | Masbate | 302143 | Luy-a National High School | AROROY | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 11986320 |  |  | COMPLETED | 1
36929 | NC 2018 | TVL | Region V | Masbate | 302143 | Luy-a National High School | AROROY | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 11813290 |  |  | COMPLETED | 1
36930 | NC 2018 | TVL | Region V | Masbate | 302145 | Federico A. Estipona Memorial High School | MANDAON | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9627090 |  |  | COMPLETED | 1
36931 | NC 2018 | TVL | Region V | Masbate | 302145 | Federico A. Estipona Memorial High School | MANDAON | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9524420 |  |  | COMPLETED | 1
36932 | NC 2018 | SHS | Region V | Masbate | 302145 | Federico A. Estipona Memorial High School | MANDAON | 2 |  | 12 | 2UNITS 2STY6CL | BATCH 1 | 23626550 |  |  | COMPLETED | 1
36933 | NC 2018 | TVL | Region V | Masbate | 302146 | Marintoc National High School | MOBO | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9334780 |  |  | COMPLETED | 1
36934 | NC 2018 | TVL | Region V | Masbate | 302146 | Marintoc National High School | MOBO | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9249430 |  |  | COMPLETED | 1
36935 | NC 2018 | TVL | Region V | Masbate | 302147 | Masbate School of Fisheries | MILAGROS | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 11650960 |  |  | COMPLETED | 1
36936 | NC 2018 | TVL | Region V | Masbate | 302147 | Masbate School of Fisheries | MILAGROS | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 11510280 |  |  | COMPLETED | 1
36937 | NC 2018 | TVL | Region V | Masbate | 302147 | Masbate School of Fisheries | MILAGROS | 2 |  | 3 | 3STY3CL RW | BATCH 1 | 15018380 |  |  | COMPLETED | 1
36938 | NC 2018 | TVL | Region V | Masbate | 302147 | Masbate School of Fisheries | MILAGROS | 2 |  | 9 | 3STY9CL RW | BATCH 1 | 42436580 |  |  | COMPLETED | 1 | [10 empty] | suspended
36939 | NC 2018 | TVL | Region V | Masbate | 302150 | Milagros National High School | MILAGROS | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9528550 |  |  | COMPLETED | 1
36940 | NC 2018 | TVL | Region V | Masbate | 302150 | Milagros National High School | MILAGROS | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9423330 |  |  | COMPLETED | 1
36941 | NC 2018 | TVL | Region V | Masbate | 302151 | Mobo National High School | MOBO | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9677150 |  |  | COMPLETED | 1
36942 | NC 2018 | TVL | Region V | Masbate | 302151 | Mobo National High School | MOBO | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9490800 |  |  | COMPLETED | 1
36943 | NC 2018 | TVL | Region V | Masbate | 302156 | Briccio A. Aninang Sr. Mem. HS | BALUD | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9620770 |  |  | COMPLETED | 1
36944 | NC 2018 | TVL | Region V | Masbate | 302156 | Briccio A. Aninang Sr. Mem. HS | BALUD | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9493640 |  |  | COMPLETED | 1
36945 | NC 2018 | TVL | Region V | Masbate | 302157 | Panique National High School | AROROY | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 10661730 |  |  | COMPLETED | 1
36946 | NC 2018 | TVL | Region V | Masbate | 302157 | Panique National High School | AROROY | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 10536550 |  |  | COMPLETED | 1
36947 | NC 2018 | TVL | Region V | Masbate | 302160 | Salvador Arollado, Sr. MHS | BALUD | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9799350 |  |  | COMPLETED | 1
36948 | NC 2018 | TVL | Region V | Masbate | 302160 | Salvador Arollado, Sr. MHS | BALUD | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9667460 |  |  | COMPLETED | 1
36949 | NC 2018 | TVL | Region V | Masbate | 302161 | Liberato P. Tacurda Sr. HS | BALUD | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9711240 |  |  | COMPLETED | 1
36950 | NC 2018 | TVL | Region V | Masbate | 302161 | Liberato P. Tacurda Sr. HS | BALUD | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9581380 |  |  | COMPLETED | 1
36951 | NC 2018 | TVL | Region V | Masbate | 302162 | PURO NATIONAL HIGH SCHOOL | AROROY | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 10659310 |  |  | COMPLETED | 1
36952 | NC 2018 | TVL | Region V | Masbate | 302162 | PURO NATIONAL HIGH SCHOOL | AROROY | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 10533320 |  |  | COMPLETED | 1
36953 | NC 2018 | TVL | Region V | Masbate | 302164 | Quinayangan National High School | BALUD | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9741960 |  |  | COMPLETED | 1 | [10 empty] | suspended
36954 | NC 2018 | TVL | Region V | Masbate | 302164 | Quinayangan National High School | BALUD | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9611280 |  |  | COMPLETED | 1
36955 | NC 2018 | TVL | Region V | Masbate | 302174 | Tinigban National High School | AROROY | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9624120 |  |  | COMPLETED | 1
36956 | NC 2018 | TVL | Region V | Masbate | 302174 | Tinigban National High School | AROROY | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9496590 |  |  | COMPLETED | 1
36957 | NC 2018 | TVL | Region V | Masbate | 309901 | Delavin-Rubia National High School | AROROY | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9626540 |  |  | COMPLETED | 1
36958 | NC 2018 | TVL | Region V | Masbate | 309901 | Delavin-Rubia National High School | AROROY | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9498260 |  |  | COMPLETED | 1
36959 | NC 2018 | TVL | Region V | Masbate | 309906 | Serafin C. Rosero Memorial High School | MILAGROS | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 10560640 |  |  | COMPLETED | 1
36960 | NC 2018 | TVL | Region V | Masbate | 309906 | Serafin C. Rosero Memorial High School | MILAGROS | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 10390440 |  |  | COMPLETED | 1
36961 | NC 2018 | TVL | Region V | Masbate | 309907 | San Pablo National High School | MANDAON | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9710560 |  |  | COMPLETED | 1
36962 | NC 2018 | TVL | Region V | Masbate | 309907 | San Pablo National High School | MANDAON | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9612240 |  |  | COMPLETED | 1
36963 | NC 2018 | TVL | Region V | Masbate | 309908 | Mary Perpetua E. Brioso Memorial High School | MILAGROS | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 10706380 |  |  | COMPLETED | 1
36964 | NC 2018 | TVL | Region V | Masbate | 309908 | Mary Perpetua E. Brioso Memorial High School | MILAGROS | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 10568380 |  |  | COMPLETED | 1
36965 | NC 2018 | TVL | Region V | Masbate | 309909 | Teresita C. Young Memorial High School | AROROY | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9624120 |  |  | COMPLETED | 1
36966 | NC 2018 | TVL | Region V | Masbate | 309909 | Teresita C. Young Memorial High School | AROROY | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9496590 |  |  | COMPLETED | 1
36967 | NC 2018 | TVL | Region V | Masbate | 309910 | Cabitan National High School | MANDAON | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9658460 |  |  | COMPLETED | 1
36968 | NC 2018 | TVL | Region V | Masbate | 309910 | Cabitan National High School | MANDAON | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9526770 |  |  | COMPLETED | 1
36969 | NC 2018 | TVL | Region V | Masbate | 309922 | Floro L. Medina MHS | MOBO | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9334550 |  |  | COMPLETED | 1 | [10 empty] | suspended
36970 | NC 2018 | TVL | Region V | Masbate | 309922 | Floro L. Medina MHS | MOBO | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9215200 |  |  | COMPLETED | 1 | [10 empty] | suspended
36971 | NC 2018 | TVL | Region V | Masbate | 309931 | Amador-Bello HS | BALENO | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9449330 |  |  | COMPLETED | 1
36972 | NC 2018 | TVL | Region V | Masbate | 309931 | Amador-Bello HS | BALENO | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9330080 |  |  | COMPLETED | 1
36973 | NC 2018 | TVL | Region V | Masbate | 309932 | Nabongsoran High School | AROROY | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9621870 |  |  | COMPLETED | 1
36974 | NC 2018 | TVL | Region V | Masbate | 309932 | Nabongsoran High School | AROROY | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9495140 |  |  | COMPLETED | 1
36975 | NC 2018 | TVL | Region V | Masbate | 309939 | Lantangan High School | MANDAON | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9599970 |  |  | COMPLETED | 1
36976 | NC 2018 | TVL | Region V | Masbate | 309939 | Lantangan High School | MANDAON | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9476060 |  |  | COMPLETED | 1
36977 | NC 2018 | TVL | Region V | Masbate | 309940 | Tumalaytay National High School | MANDAON | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9655110 |  |  | COMPLETED | 1
36978 | NC 2018 | TVL | Region V | Masbate | 309940 | Tumalaytay National High School | MANDAON | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9535710 |  |  | COMPLETED | 1
36979 | NC 2018 | TVL | Region V | Masbate | 309941 | Cristeta Bagano MHS | MOBO | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9444800 |  |  | COMPLETED | 1
36980 | NC 2018 | TVL | Region V | Masbate | 309941 | Cristeta Bagano MHS | MOBO | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9315520 |  |  | COMPLETED | 1
36981 | NC 2018 | K10 | Region V | Masbate | 500163 | Tigbao ES | AROROY | 2 | 1 | 8 | 2UNITS 2STY4CL | BATCH 1 | 18142490 |  |  | COMPLETED | 1 | [10 empty] | suspended
36982 | NC 2018 | K10 | Region V | Masbate | 113539 | Gilotongan ES | CAWAYAN | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9041645.03 |  |  | COMPLETED | 1
36983 | NC 2018 | K10 | Region V | Masbate | 113560 | San Jose ES | CAWAYAN | 3 | 1 | 3 | 1STY3CL | BATCH 1 | 4081379.45 |  |  | COMPLETED | 1
36984 | NC 2018 | SHS | Region V | Masbate | 113803 | Buenasuerte Integrated School | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11413810.35 |  |  | COMPLETED | 1
36985 | NC 2018 | K10 | Region V | Masbate | 113836 | Tomas M. Conde CS | PLACER | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11584782.26 |  |  | COMPLETED | 1
36986 | NC 2018 | K10 | Region V | Masbate | 113836 | Tomas M. Conde CS | PLACER | 3 |  | 4 | 2STY4CL | BATCH 1 | 8979356.57 |  |  | COMPLETED | 1
36987 | NC 2018 | TVL | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | USON | 3 | 1 | 2 | 2units 1sty2cl Regular Workshop 7x18 | BATCH 1 | 7496049.57 |  |  | COMPLETED | 1
36988 | NC 2018 | TVL | Region V | Masbate | 302118 | G. Bangalisan National High School | PLACER | 3 | 1 | 3 | 3units 1sty2cl Regular Workshop 7x18 | BATCH 1 | 10107961.64 |  |  | COMPLETED | 1
36989 | NC 2018 | TVL | Region V | Masbate | 302131 | Del Carmen National High School | USON | 3 | 1 | 4 | 4units 1sty2cl Regular Workshop 7x18 | BATCH 1 | 13414079.19 |  |  | COMPLETED | 1
36990 | NC 2018 | TVL | Region V | Masbate | 302136 | Matagangtang National High School | PLACER | 3 | 1 | 3 | 3units 1sty2cl Regular Workshop 7x18 | BATCH 1 | 10107961.64 |  |  | COMPLETED | 1
36991 | NC 2018 | SHS | Region V | Masbate | 302153 | Rondina-Atendido National High School | PALANAS | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 12201066.03 |  |  | COMPLETED | 1
36992 | NC 2018 | SHS | Region V | Masbate | 302154 | Naro National High School | CAWAYAN | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9011233.43 |  |  | COMPLETED | 1
36993 | NC 2018 | SHS | Region V | Masbate | 302154 | Naro National High School | CAWAYAN | 3 |  | 4 | 2STY4CL | BATCH 1 | 9011233.43 |  |  | COMPLETED | 1
36994 | NC 2018 | SHS | Region V | Masbate | 302154 | Naro National High School | CAWAYAN | 3 |  | 12 | 2UNITS 2STY6CL | BATCH 1 | 23463734.53 |  |  | COMPLETED | 1 | [10 empty] | suspended
36995 | NC 2018 | SHS | Region V | Masbate | 302154 | Naro National High School | CAWAYAN | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9152886.38 |  |  | COMPLETED | 1
36996 | NC 2018 | SHS | Region V | Masbate | 302154 | Naro National High School | CAWAYAN | 3 |  | 4 | 2STY4CL | BATCH 1 | 9152886.38 |  |  | COMPLETED | 1
36997 | NC 2018 | TVL | Region V | Masbate | 302165 | Rodolfo Z. Titong National High School | PLACER | 3 | 1 | 2 | 2units 1sty2cl Regular Workshop 7x18 | BATCH 1 | 7761323.63 |  |  | COMPLETED | 1
36998 | NC 2018 | SHS | Region V | Masbate | 302172 | Tanque National High School | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 12171747.81 |  |  | COMPLETED | 1
36999 | NC 2018 | TVL | Region V | Masbate | 302175 | Uson National High School | USON | 3 | 1 | 4 | 4units 1sty2cl Regular Workshop 7x18 | BATCH 1 | 13414079.19 |  |  | COMPLETED | 1
37000 | NC 2018 | TVL | Region V | Masbate | 302176 | Verdida-Sabrido National High School | PLACER | 3 | 1 | 3 | 3units 1sty2cl Regular Workshop 7x18 | BATCH 1 | 10216608.86 |  |  | COMPLETED | 1
37001 | NC 2018 | SHS | Region V | Masbate | 302177 | Villahermosa National High School | CAWAYAN | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 12216968.42 |  |  | COMPLETED | 1
37002 | NC 2018 | TVL | Region V | Masbate | 302178 | Vivencio P. Casas Sr. Memorial High School | PLACER | 3 | 1 | 3 | 3units 1sty2cl Regular Workshop 7x18 | BATCH 1 | 10133256.39 |  |  | COMPLETED | 1
37003 | NC 2018 | SHS | Region V | Masbate | 309902 | Allanaraiz-Marfil National High School | ESPERANZA | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8968978.89 |  |  | COMPLETED | 1
37004 | NC 2018 | TVL | Region V | Masbate | 309903 | Arriesgado-Sevilleno National High School | PLACER | 3 | 1 | 3 | 3units 1sty2cl Regular Workshop 7x18 | BATCH 1 | 10027138.66 |  |  | COMPLETED | 1
37005 | NC 2018 | TVL | Region V | Masbate | 309911 | Miabas National High School | PALANAS | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 3959324.08 |  |  | COMPLETED | 1
37006 | NC 2018 | TVL | Region V | Masbate | 309911 | Miabas National High School | PALANAS | 3 |  | 3 | 3units 1sty2cl Regular Workshop 7x18 | BATCH 1 | 10103223.78 |  |  | COMPLETED | 1
37007 | NC 2018 | SHS | Region V | Masbate | 309914 | Mayor Tomas V. Rivera Memorial High School | CAWAYAN | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8797058.61 |  |  | COMPLETED | 1
37008 | NC 2018 | SHS | Region V | Masbate | 309921 | Feliciano S. Samonte Memorial High School | CATAINGAN | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8797058.61 |  |  | COMPLETED | 1
37009 | NC 2018 | SHS | Region V | Masbate | 309926 | Maravilla National High School | PALANAS | 3 | 1 | 8 | 4STY8CL | BATCH 1 | 16776794.29 |  |  | COMPLETED | 1 | [10 empty] | suspended
37010 | NC 2018 | SHS | Region V | Masbate | 302108 | Adelina P. Laurio National HS | SAN PASCUAL | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10685775.79 |  |  | COMPLETED | 1
37011 | NC 2018 | SHS | Region V | Masbate | 302109 | Andres Clemente Jr.National HS | SAN FERNANDO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10177194.46 |  |  | COMPLETED | 1
37012 | NC 2018 | SHS | Region V | Masbate | 302113 | Bagahanglad NHS | SAN JACINTO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10300468.04 |  |  | COMPLETED | 1
37013 | NC 2018 | SHS | Region V | Masbate | 302114 | Don Benito Maristela Mem. HS | MONREAL | 1 | 1 | 4 | 2STY4CL | Batch 3 | 13192088.3 |  |  | COMPLETED | 1
37014 | NC 2018 | SHS | Region V | Masbate City | 302133 | Capitolina O. Legaspi Memorial High School | CITY OF MASBATE (Capital) | 2 | 1 | 15 | 3STY15CL | BATCH 1 | 35357860 |  |  | COMPLETED | 1
37015 | NC 2018 | TVL | Region V | Masbate City | 302148 | Masbate National Comprehensive High School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 10411480 |  |  | COMPLETED | 1
37016 | NC 2018 | TVL | Region V | Masbate City | 302148 | Masbate National Comprehensive High School | CITY OF MASBATE (Capital) | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 10190140 |  |  | COMPLETED | 1
37017 | NC 2018 | TVL | Region V | Masbate City | 302148 | Masbate National Comprehensive High School | CITY OF MASBATE (Capital) | 2 |  | 3 | 3STY3CL RW | BATCH 1 | 14856450 |  |  | COMPLETED | 1
37018 | NC 2018 | TVL | Region V | Masbate City | 321801 | Bolo National High School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9710750 |  |  | COMPLETED | 1
37019 | NC 2018 | TVL | Region V | Masbate City | 321801 | Bolo National High School | CITY OF MASBATE (Capital) | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9491090 |  |  | COMPLETED | 1
37020 | NC 2018 | TVL | Region V | Masbate City | 321802 | Usab High School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 11987640 |  |  | COMPLETED | 1
37021 | NC 2018 | TVL | Region V | Masbate City | 321802 | Usab High School | CITY OF MASBATE (Capital) | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 11760860 |  |  | COMPLETED | 1
37022 | NC 2018 | TVL | Region V | Masbate City | 321804 | Bayombon High School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9471550 |  |  | COMPLETED | 1
37023 | NC 2018 | TVL | Region V | Masbate City | 321804 | Bayombon High School | CITY OF MASBATE (Capital) | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9351670 |  |  | COMPLETED | 1
37024 | NC 2018 | TVL | Region V | Masbate City | 321805 | Bantigue High School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 10399680 |  |  | COMPLETED | 1
37025 | NC 2018 | TVL | Region V | Masbate City | 321805 | Bantigue High School | CITY OF MASBATE (Capital) | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 10279210 |  |  | COMPLETED | 1
37026 | NC 2018 | TVL | Region V | Masbate City | 321806 | Nursery High School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 10896350 |  |  | COMPLETED | 1
37027 | NC 2018 | TVL | Region V | Masbate City | 321806 | Nursery High School | CITY OF MASBATE (Capital) | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 10674740 |  |  | COMPLETED | 1
37028 | NC 2018 | TVL | Region V | Masbate City | 321806 | Nursery High School | CITY OF MASBATE (Capital) | 2 |  | 4 | 2STY2CL RW | BATCH 1 | 10454210 |  |  | COMPLETED | 1
37029 | NC 2018 | TVL | Region V | Masbate City | 321806 | Nursery High School | CITY OF MASBATE (Capital) | 2 |  | 3 | 3STY3CL RW | BATCH 1 | 16916540 |  |  | COMPLETED | 1
37030 | NC 2018 | TVL | Region V | Masbate City | 500393 | Alejandro Delos Reyes Integrated School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | 2STY2CL SCI LAB | BATCH 1 | 9410390 |  |  | COMPLETED | 1
37031 | NC 2018 | TVL | Region V | Masbate City | 500393 | Alejandro Delos Reyes Integrated School | CITY OF MASBATE (Capital) | 2 |  | 2 | 2STY2CL ICT LAB | BATCH 1 | 9286340 |  |  | COMPLETED | 1
37032 | NC 2018 | K10 | Region V | Masbate City | 113702 | Nursery Elementary School | CITY OF MASBATE (Capital) | 2 | 1 | 8 | 2STY8CL | Batch 5 | 22167696.5829 |  |  | COMPLETED | 1
37033 | NC 2018 | K10 | Region V | Naga City | 114498 | Carolina Elementary School | NAGA CITY | 3 | 1 | 9 | 3STY9CL | BATCH 1 | 23032431.58 |  |  | COMPLETED | 1 | [5 empty] | 2018-04-27 | 2018-05-09 | 2018-05-28 | 2018-06-19 | Honneyville Construction
37034 | NC 2018 | K10 | Region V | Naga City | 114500 | Naga Central School I | NAGA CITY | 3 | 1 | 9 | 3STY9CL | BATCH 1 | 26382377.89 |  |  | COMPLETED | 1 | [9 empty] | EPL General Construction and Supply
37035 | NC 2018 | K10 | Region V | Naga City | 114517 | Sta.Cruz Elementary School | NAGA CITY | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 19800590.16 |  |  | COMPLETED | 1 | [5 empty] | 2018-05-10 | 2018-05-22 | 2018-06-05 | 2018-07-02 | 301 Engineers
37036 | NC 2018 | K10 | Region V | Naga City | 114517 | Sta.Cruz Elementary School | NAGA CITY | 3 |  | 6 | 2STY6CL | BATCH 1 | 19801433.48 |  |  | COMPLETED | 1 | [5 empty] | 2018-05-11 | 2018-05-23 | 2018-06-05 | 2018-07-02 | 301 Engineers
37037 | NC 2018 | TVL | Region V | Naga City | 302267 | Concepcion Pequeña National High School | NAGA CITY | 3 | 1 | 5 | 2STY4CL w 1 Regular TVL Unit | BATCH 1 | 11333694.43 |  |  | COMPLETED | 1 | [5 empty] | 2018-04-20 | 2018-05-02 | 2018-05-28 | 2018-06-19 | CHA Construction and Supply
37038 | NC 2018 | TVL | Region V | Naga City | 302267 | Concepcion Pequeña National High School | NAGA CITY | 3 |  | 3 | 3storey - 1 Regular Workshop ,1 ICT Lab, 1 science lab | BATCH 1 | 16911439.01 |  |  | COMPLETED | 1 | [5 empty] | 2018-05-10 | 2018-05-22 | 2018-06-05 | 2018-06-28 | AE Belleza Builders
37039 | NC 2018 | TVL | Region V | Naga City | 302267 | Concepcion Pequeña National High School | NAGA CITY | 3 |  | 3 | 3storey - 1 Regular Workshop ,1 ICT Lab, 1 science lab | BATCH 1 | 16911439.01 |  |  | COMPLETED | 1 | [5 empty] | 2018-05-11 | 2018-05-23 | 2018-06-05 | 2018-07-02 | AE Belleza Builders
37040 | NC 2018 | TVL | Region V | Naga City | 302268 | Naga City Science High School | NAGA CITY | 3 | 1 | 6 | 3storey - 2 Regular Workshop ,2 ICT Lab, 2 science lab | BATCH 1 | 30402639.87 |  |  | COMPLETED | 1 | [5 empty] | 2018-05-03 | 2018-05-15 | 2018-05-28 | 2018-06-19 | RD Mandanas Construction
37041 | NC 2018 | TVL | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 | 1 | 6 | 3storey - 2 Regular Workshop ,2 ICT Lab, 2 science lab | BATCH 1 | 30750049.43 |  |  | COMPLETED | 1 | [5 empty] | 2018-05-03 | 2018-05-15 | 2018-05-28 | 2018-07-02 | Precious Construction
37042 | NC 2018 | TVL | Region V | Sorsogon | 302179 | Abucay National High School | PILAR | 1 | 1 | 4 | 2storey - 4 Regular Workshop 7x18 | BATCH 1 | 18921859.36 |  |  | COMPLETED | 1
37043 | NC 2018 | TVL | Region V | Sorsogon | 302179 | Abucay National High School | PILAR | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9959469.83 |  |  | COMPLETED | 1
37044 | NC 2018 | TVL | Region V | Sorsogon | 302179 | Abucay National High School | PILAR | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 10280469.83 |  |  | COMPLETED | 1
37045 | NC 2018 | K10 | Region V | Sorsogon | 113980 | Bagacay ES | BARCELONA | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3106206.99 |  |  | Completed | 1
37046 | NC 2018 | TVL | Region V | Sorsogon | 302183 | Bagatao NHS | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 10321263.05 |  |  | COMPLETED | 1
37047 | NC 2018 | TVL | Region V | Sorsogon | 302183 | Bagatao NHS | MAGALLANES (34 BRGYS) | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 10321263.05 |  |  | COMPLETED | 1
37048 | NC 2018 | K10 | Region V | Sorsogon | 114078 | Banawang ES | CASIGURAN | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12698667.33 |  |  | COMPLETED | 1
37049 | NC 2018 | K10 | Region V | Sorsogon | 310006 | Bantayan National High School | PILAR | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 10279352.54 |  |  | COMPLETED | 1
37050 | NC 2018 | K10 | Region V | Sorsogon | 302180 | Bayasong NHS | PILAR | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 10042003.64 |  |  | COMPLETED | 1
37051 | NC 2018 | TVL | Region V | Sorsogon | 310007 | Biton High School | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 10137376.85 |  |  | COMPLETED | 1
37052 | NC 2018 | TVL | Region V | Sorsogon | 310007 | Biton High School | MAGALLANES (34 BRGYS) | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 10137376.85 |  |  | COMPLETED | 1
37053 | NC 2018 | TVL | Region V | Sorsogon | 302199 | Buenavista NHS | CASTILLA | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 10677255.84 |  |  | COMPLETED | 1
37054 | NC 2018 | TVL | Region V | Sorsogon | 302199 | Buenavista NHS | CASTILLA | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 10417447.96 |  |  | COMPLETED | 1
37055 | NC 2018 | TVL | Region V | Sorsogon | 302199 | Buenavista NHS | CASTILLA | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 10362804.69 |  |  | COMPLETED | 1
37056 | NC 2018 | K10 | Region V | Sorsogon | 114003 | Bulan North CS - A | BULAN | 2 | 1 | 9 | 3STY9CL | Batch 3 | 31906917.54 |  |  | Completed | 1
37057 | NC 2018 | K10 | Region V | Sorsogon | 114059 | Bulusan CS | BULUSAN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 11188819.64 |  |  | Completed | 1
37058 | NC 2018 | TVL | Region V | Sorsogon City | 500462 | Bogña Integrated School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2units 2storey - 2 Regular Workshop 7x18 | BATCH 3 Realignment | 22296562.66 |  |  | COMPLETED | 1
37059 | NC 2018 | TVL | Region V | Sorsogon City | 310405 | Bogña Integrated School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9691066.44 |  |  | COMPLETED | 1
37060 | NC 2018 | K10 | Region V | Sorsogon City | 114524 | Bon-ot Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12546518.89 |  |  | COMPLETED | 1
37061 | NC 2018 | SHS | Region V | Sorsogon | 302192 | Bulusan NHS | BULUSAN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 11138819.64 |  |  | Completed | 1
37062 | NC 2018 | K10 | Region V | Sorsogon | 302195 | Caditaan NHS | MAGALLANES (34 BRGYS) | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9740351.18 |  |  | COMPLETED | 1
37063 | NC 2018 | K10 | Region V | Sorsogon | 114007 | Calomagon ES | BULAN | 2 | 1 | 3 | 1STY3CL | Batch 3 | 4503199.62 |  |  | Completed | 1
37064 | NC 2018 | TVL | Region V | Sorsogon | 302197 | Casiguran Technical Vocational School | CASIGURAN | 1 | 1 | 2 | 2units UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 6213121.85 |  |  | COMPLETED | 1
37065 | NC 2018 | TVL | Region V | Sorsogon | 302197 | Casiguran Technical Vocational School | CASIGURAN | 1 |  | 8 | 2units 2storey - 4 Regular Workshop 7x18 | BATCH 1 | 36336733.94 |  |  | COMPLETED | 1
37066 | NC 2018 | TVL | Region V | Sorsogon | 302197 | Casiguran Technical Vocational School | CASIGURAN | 1 |  | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 9579236.73 |  |  | COMPLETED | 1
37067 | NC 2018 | TVL | Region V | Sorsogon | 302197 | Casiguran Technical Vocational School | CASIGURAN | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9579236.73 |  |  | COMPLETED | 1
37068 | NC 2018 | TVL | Region V | Sorsogon | 302197 | Casiguran Technical Vocational School | CASIGURAN | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9900236.73 |  |  | Completed | 1
37069 | NC 2018 | TVL | Region V | Sorsogon | 302198 | Castilla NHS | CASTILLA | 1 | 1 | 8 | 2units 2storey - 4 Regular Workshop 7x18 | BATCH 1 | 36528907.06 |  |  | COMPLETED | 1
37070 | NC 2018 | TVL | Region V | Sorsogon | 302198 | Castilla NHS | CASTILLA | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9767128.94 |  |  | COMPLETED | 1
37071 | NC 2018 | TVL | Region V | Sorsogon | 302198 | Castilla NHS | CASTILLA | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9767128.94 |  |  | COMPLETED | 1
37072 | NC 2018 | K10 | Region V | Sorsogon | 114190 | Cogon ES | GUBAT | 2 | 1 | 6 | 2STY6CL | Batch 3 | 16256385 |  |  | COMPLETED | 1
37073 | NC 2018 | TVL | Region V | Sorsogon | 302201 | Cumadcad NHS | CASTILLA | 1 | 1 | 6 | 3units 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 28981127.61 |  |  | COMPLETED | 1
37074 | NC 2018 | TVL | Region V | Sorsogon | 302201 | Cumadcad NHS | CASTILLA | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9934308.83 |  |  | COMPLETED | 1
37075 | NC 2018 | TVL | Region V | Sorsogon | 302201 | Cumadcad NHS | CASTILLA | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9853415.07 |  |  | COMPLETED | 1
37076 | NC 2018 | TVL | Region V | Sorsogon | 302202 | Dinapa NHS | CASTILLA | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 10031029.53 |  |  | COMPLETED | 1
37077 | NC 2018 | TVL | Region V | Sorsogon | 302202 | Dinapa NHS | CASTILLA | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9664057.98 |  |  | COMPLETED | 1
37078 | NC 2018 | TVL | Region V | Sorsogon | 302202 | Dinapa NHS | CASTILLA | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9710029.53 |  |  | COMPLETED | 1
37079 | NC 2018 | TVL | Region V | Sorsogon | 302204 | Donsol National Comprehensive HS | DONSOL | 1 | 1 | 6 | 3units 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 29199196.74 |  |  | COMPLETED | 1
37080 | NC 2018 | TVL | Region V | Sorsogon | 302204 | Donsol National Comprehensive HS | DONSOL | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 10054157.19 |  |  | COMPLETED | 1
37081 | NC 2018 | TVL | Region V | Sorsogon | 302204 | Donsol National Comprehensive HS | DONSOL | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9733157.19 |  |  | COMPLETED | 1
37082 | NC 2018 | SHS | Region V | Sorsogon | 302204 | Donsol National Comprehensive HS | DONSOL | 1 |  | 9 | 3STY9CL | BATCH 1 | 28734780.59 |  |  | COMPLETED | 1
37083 | NC 2018 | TVL | Region V | Sorsogon | 302205 | Donsol National Comprehensive HS - Banuang Gurang Extension HS | DONSOL | 1 | 1 | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 10860653.71 |  |  | COMPLETED | 1
37084 | NC 2018 | TVL | Region V | Sorsogon | 302205 | Donsol National Comprehensive HS - Banuang Gurang Extension HS | DONSOL | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 10539653.71 |  |  | COMPLETED | 1
37085 | NC 2018 | TVL | Region V | Sorsogon | 302206 | Donsol National Comprehensive HS - Sta. Cruz Extension HS | DONSOL | 1 | 1 | 6 | 3units 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 31140285.36 |  |  | COMPLETED | 1
37086 | NC 2018 | TVL | Region V | Sorsogon | 302206 | Donsol National Comprehensive HS - Sta. Cruz Extension HS | DONSOL | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 10699611.4 |  |  | COMPLETED | 1
37087 | NC 2018 | TVL | Region V | Sorsogon | 302206 | Donsol National Comprehensive HS - Sta. Cruz Extension HS | DONSOL | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 10378611.4 |  |  | COMPLETED | 1
37088 | NC 2018 | TVL | Region V | Sorsogon | 302207 | Donsol Vocational HS | DONSOL | 1 | 1 | 4 | 2units 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 20930237.61 |  |  | COMPLETED | 1
37089 | NC 2018 | TVL | Region V | Sorsogon | 302207 | Donsol Vocational HS | DONSOL | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 10786118.8 |  |  | COMPLETED | 1
37090 | NC 2018 | TVL | Region V | Sorsogon | 302207 | Donsol Vocational HS | DONSOL | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 10465118.8 |  |  | COMPLETED | 1
37091 | NC 2018 | K10 | Region V | Sorsogon | 302208 | Donsol Vocational HS - Gimagaan Annex | DONSOL | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12838170.27 |  |  | COMPLETED | 1
37092 | NC 2018 | K10 | Region V | Sorsogon | 113985 | Fabrica ES | BARCELONA | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3181206.99 |  |  | Completed | 1
37093 | NC 2018 | K10 | Region V | Sorsogon | 114039 | Gabod ES | BULAN | 2 | 1 | 4 | 2UNITS-1STY2CL | Batch 3 | 7680237.02 |  |  | Completed | 1
37094 | NC 2018 | SHS | Region V | Sorsogon | 302212 | Gallanosa National High School | IROSIN | 2 | 1 | 24 | 3UNITS-2STY8CL | Batch 3 | 67735972.18 |  |  | COMPLETED | 1
37095 | NC 2018 | K10 | Region V | Sorsogon | 114040 | Gate Elementary School | BULAN | 2 | 1 | 4 | 2UNITS-1STY2CL | Batch 3 | 5999010 |  |  | Completed | 1
37096 | NC 2018 | SHS | Region V | Sorsogon | 302213 | Gate NHS | BULAN | 2 | 1 | 16 | 4STY16CL | Batch 3 | 45007495.81 |  |  | COMPLETED | 1
37097 | NC 2018 | K10 | Region V | Sorsogon | 114234 | Gumapia ES | IROSIN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 18124651.38 |  |  | Completed | 1
37098 | NC 2018 | K10 | Region V | Sorsogon | 114235 | Irosin CS | IROSIN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12358128.66 |  |  | Completed | 1
37099 | NC 2018 | K10 | Region V | Sorsogon | 114016 | Jamorawon ES | BULAN | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3089946.91 |  |  | Completed | 1
37100 | NC 2018 | K10 | Region V | Sorsogon | 114263 | Jose Alindogan CS | JUBAN | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 14491891.86 |  |  | Completed | 1
37101 | NC 2018 | K10 | Region V | Sorsogon | 302216 | Lajong NHS | JUBAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 13856071.54 |  |  | Completed | 1
37102 | NC 2018 | K10 | Region V | Sorsogon | 114194 | Lapinig ES | GUBAT | 2 | 1 | 3 | 1STY3CL | Batch 3 | 4216722.47 |  |  | Completed | 1
37103 | NC 2018 | K10 | Region V | Sorsogon | 114018 | M.A Roxas ES | BULAN | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3181206.99 |  |  | Completed | 1
37104 | NC 2018 | TVL | Region V | Sorsogon | 302222 | Magallanes National High School | MAGALLANES (34 BRGYS) | 1 | 1 | 4 | 2units 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 19328115.97 |  |  | COMPLETED | 1
37105 | NC 2018 | TVL | Region V | Sorsogon | 302222 | Magallanes National High School | MAGALLANES (34 BRGYS) | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9985057.98 |  |  | COMPLETED | 1
37106 | NC 2018 | TVL | Region V | Sorsogon | 302222 | Magallanes National High School | MAGALLANES (34 BRGYS) | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9664057.98 |  |  | COMPLETED | 1
37107 | NC 2018 | TVL | Region V | Sorsogon | 302220 | Magallanes National Vocational HS | MAGALLANES (34 BRGYS) | 1 | 1 | 4 | 2units 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 19328115.97 |  |  | COMPLETED | 1
37108 | NC 2018 | TVL | Region V | Sorsogon | 302220 | Magallanes National Vocational HS | MAGALLANES (34 BRGYS) | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9985057.98 |  |  | COMPLETED | 1
37109 | NC 2018 | TVL | Region V | Sorsogon | 302220 | Magallanes National Vocational HS | MAGALLANES (34 BRGYS) | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9664057.98 |  |  | Completed | 1
37110 | NC 2018 | K10 | Region V | Sorsogon | 114281 | Magallanes North CS | MAGALLANES (34 BRGYS) | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 16453927.51 |  |  | COMPLETED | 1
37111 | NC 2018 | K10 | Region V | Sorsogon | 114166 | Malapoc ES | DONSOL | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 13336882.87 |  |  | COMPLETED | 1
37112 | NC 2018 | SHS | Region V | Sorsogon | 302223 | Manlabong NHS | PRIETO DIAZ | 2 | 1 | 4 | 2STY4CL | Batch 3 | 13904396.54 |  |  | Completed | 1
37113 | NC 2018 | SHS | Region V | Sorsogon | 302224 | Manuel T. Sia MHS | PILAR | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9967631.89 |  |  | COMPLETED | 1
37114 | NC 2018 | TVL | Region V | Sorsogon | 302225 | Matnog NHS | MATNOG | 2 | 1 | 2 | 2STY4CL (2ict) | Batch 3 | 12792811.05 |  |  | COMPLETED | 1
37115 | NC 2018 | K10 | Region V | Sorsogon | 114126 | Mayon ES | CASTILLA | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9572114.88 |  |  | COMPLETED | 1
37116 | NC 2018 | K10 | Region V | Sorsogon | 302227 | Milagrosa NHS | CASTILLA | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9572114.88 |  |  | COMPLETED | 1
37117 | NC 2018 | K10 | Region V | Sorsogon | 114044 | Obrero ES | BULAN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 12289681.56 |  |  | Completed | 1
37118 | NC 2018 | SHS | Region V | Sorsogon | 302228 | Oras National High School | CASTILLA | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9745501.63 |  |  | COMPLETED | 1
37119 | NC 2018 | TVL | Region V | Sorsogon | 302229 | Palanas NHS | PILAR | 1 | 1 | 4 | 2units 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 19482946.38 |  |  | COMPLETED | 1 |  |  | `
37120 | NC 2018 | TVL | Region V | Sorsogon | 302229 | Palanas NHS | PILAR | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9897776.45 |  |  | COMPLETED | 1
37121 | NC 2018 | TVL | Region V | Sorsogon | 302229 | Palanas NHS | PILAR | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 10053462.71 |  |  | COMPLETED | 1
37122 | NC 2018 | K10 | Region V | Sorsogon | 310004 | Pandan HS | CASTILLA | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9695501.08 |  |  | COMPLETED | 1
37123 | NC 2018 | K10 | Region V | Sorsogon | 114356 | Pilar I CS | PILAR | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9857390.29 |  |  | COMPLETED | 1
37124 | NC 2018 | TVL | Region V | Sorsogon | 302230 | Pilar National Comprehensive HS | PILAR | 1 | 1 | 2 | 2units UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 6362367.06 |  |  | COMPLETED | 1
37125 | NC 2018 | TVL | Region V | Sorsogon | 302230 | Pilar National Comprehensive HS | PILAR | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 10108444.73 |  |  | COMPLETED | 1
37126 | NC 2018 | TVL | Region V | Sorsogon | 302230 | Pilar National Comprehensive HS | PILAR | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9787444.73 |  |  | COMPLETED | 1
37127 | NC 2018 | SHS | Region V | Sorsogon | 302232 | Prieto Diaz National High School | PRIETO DIAZ | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 11038819.64 |  |  | Completed | 1
37128 | NC 2018 | K10 | Region V | Sorsogon | 114026 | Sabang ES | BULAN | 2 | 1 | 3 | 1STY3CL | Batch 3 | 5220922.47 |  |  | Completed | 1
37129 | NC 2018 | K10 | Region V | Sorsogon | 302769 | Sablayan HS | JUBAN | 2 | 1 | 2 | 1STY2CL | Batch 3 | 4057941.55 |  |  | Completed | 1
37130 | NC 2018 | K10 | Region V | Sorsogon | 114132 | Salvacion ES | CASTILLA | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12714048.73 |  |  | COMPLETED | 1
37131 | NC 2018 | TVL | Region V | Sorsogon | 302236 | Salvacion National High School | PILAR | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 10186766.63 |  |  | COMPLETED | 1
37132 | NC 2018 | TVL | Region V | Sorsogon | 302236 | Salvacion National High School | PILAR | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9776057.98 |  |  | COMPLETED | 1
37133 | NC 2018 | TVL | Region V | Sorsogon | 302236 | Salvacion National High School | PILAR | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9787444.73 |  |  | COMPLETED | 1
37134 | NC 2018 | K10 | Region V | Sorsogon | 114072 | San Jose (Upper) ES | BULUSAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12183128.66 |  |  | Completed | 1
37135 | NC 2018 | K10 | Region V | Sorsogon | 114029 | San Juan Daan ES | BULAN | 2 | 1 | 3 | 1STY3CL | Batch 3 | 4467763.92 |  |  | Completed | 1
37136 | NC 2018 | K10 | Region V | Sorsogon | 302240 | San Juan NHS | CASIGURAN | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9572114.88 |  |  | Completed | 1
37137 | NC 2018 | K10 | Region V | Sorsogon | 114094 | San Pascual ES | CASIGURAN | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9736217.81 |  |  | COMPLETED | 1
37138 | NC 2018 | K10 | Region V | Sorsogon | 175013 | San Pedro ES | IROSIN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 11158819.64 |  |  | Completed | 1
37139 | NC 2018 | K10 | Region V | Sorsogon | 114050 | San Rafael ES | BULAN | 2 | 1 | 3 | 1STY3CL | Batch 3 | 4818822.47 |  |  | Completed | 1
37140 | NC 2018 | TVL | Region V | Sorsogon | 302241 | San Rafael NHS | CASTILLA | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 10097057.98 |  |  | Completed | 1
37141 | NC 2018 | TVL | Region V | Sorsogon | 302241 | San Rafael NHS | CASTILLA | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9787444.73 |  |  | Completed | 1
37142 | NC 2018 | TVL | Region V | Sorsogon | 302241 | San Rafael NHS | CASTILLA | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9787444.73 |  |  | Completed | 1
37143 | NC 2018 | TVL | Region V | Sorsogon | 310008 | San Rafael NHS | PILAR | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 10926833.79 |  |  | COMPLETED | 1
37144 | NC 2018 | TVL | Region V | Sorsogon | 310008 | San Rafael NHS | PILAR | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 10409576.91 |  |  | COMPLETED | 1
37145 | NC 2018 | TVL | Region V | Sorsogon | 310008 | San Rafael NHS | PILAR | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 10369130.03 |  |  | COMPLETED | 1
37146 | NC 2018 | K10 | Region V | Sorsogon | 113994 | San Ramon ES | BARCELONA | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3012295.47 |  |  | Completed | 1
37147 | NC 2018 | K10 | Region V | Sorsogon | 114133 | San Roque ES | CASTILLA | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9799380.62 |  |  | COMPLETED | 1
37148 | NC 2018 | TVL | Region V | Sorsogon | 302243 | Siuton NHS | MAGALLANES (34 BRGYS) | 1 | 1 | 2 | 2units UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 6311181.97 |  |  | COMPLETED | 1
37149 | NC 2018 | TVL | Region V | Sorsogon | 302243 | Siuton NHS | MAGALLANES (34 BRGYS) | 1 |  | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 10710216.69 |  |  | COMPLETED | 1
37150 | NC 2018 | TVL | Region V | Sorsogon | 302243 | Siuton NHS | MAGALLANES (34 BRGYS) | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9891507.12 |  |  | COMPLETED | 1
37151 | NC 2018 | TVL | Region V | Sorsogon | 302243 | Siuton NHS | MAGALLANES (34 BRGYS) | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9891507.12 |  |  | COMPLETED | 1
37152 | NC 2018 | K10 | Region V | Sorsogon | 114097 | Tiris ES | CASIGURAN | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9600492.38 |  |  | Completed | 1
37153 | NC 2018 | K10 | Region V | Sorsogon | 114156 | Tongdol ES | DONSOL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 10387197.33 |  |  | COMPLETED | 1
37154 | NC 2018 | TVL | Region V | Sorsogon City | 302271 | Buenavista National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9843220.18 |  |  | COMPLETED | 1
37155 | NC 2018 | TVL | Region V | Sorsogon City | 310403 | Buhatan Integrated National School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 9691066.44 |  |  | COMPLETED | 1
37156 | NC 2018 | TVL | Region V | Sorsogon City | 310403 | Buhatan Integrated National School | CITY OF SORSOGON (Capital) | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9691066.44 |  |  | COMPLETED | 1
37157 | NC 2018 | TVL | Region V | Sorsogon City | 310401 | Buhatan National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 10286504.14 |  |  | COMPLETED | 1
37158 | NC 2018 | TVL | Region V | Sorsogon City | 310401 | Buhatan National High School | CITY OF SORSOGON (Capital) | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9913033.07 |  |  | COMPLETED | 1
37159 | NC 2018 | TVL | Region V | Sorsogon City | 310401 | Buhatan National High School | CITY OF SORSOGON (Capital) | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9851651.16 |  |  | COMPLETED | 1
37160 | NC 2018 | TVL | Region V | Sorsogon City | 302272 | Celestino G. Tabuena Memorial NHS | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 10164220.18 |  |  | COMPLETED | 1
37161 | NC 2018 | TVL | Region V | Sorsogon City | 302272 | Celestino G. Tabuena Memorial NHS | CITY OF SORSOGON (Capital) | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 11402641.95 |  |  | COMPLETED | 1
37162 | NC 2018 | TVL | Region V | Sorsogon City | 302272 | Celestino G. Tabuena Memorial NHS | CITY OF SORSOGON (Capital) | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9843220.18 |  |  | COMPLETED | 1
37163 | NC 2018 | TVL | Region V | Sorsogon City | 302273 | Gatbo National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9607389.35 |  |  | COMPLETED | 1
37164 | NC 2018 | TVL | Region V | Sorsogon City | 302280 | Lydia D. Martinez Memorial High School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9789646.31 |  |  | COMPLETED | 1
37165 | NC 2018 | TVL | Region V | Sorsogon City | 302280 | Lydia D. Martinez Memorial High School | CITY OF SORSOGON (Capital) | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9789646.31 |  |  | COMPLETED | 1
37166 | NC 2018 | TVL | Region V | Sorsogon City | 310406 | Pamurayan Integrated School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 9691066.44 |  |  | COMPLETED | 1
37167 | NC 2018 | TVL | Region V | Sorsogon City | 310406 | Pamurayan Integrated School | CITY OF SORSOGON (Capital) | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9691066.44 |  |  | COMPLETED | 1
37168 | NC 2018 | TVL | Region V | Sorsogon City | 302276 | Rizal Integrated National School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 9987259.56 |  |  | COMPLETED | 1
37169 | NC 2018 | TVL | Region V | Sorsogon City | 302276 | Rizal Integrated National School | CITY OF SORSOGON (Capital) | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9666259.56 |  |  | COMPLETED | 1
37170 | NC 2018 | TVL | Region V | Sorsogon City | 302276 | Rizal Integrated National School | CITY OF SORSOGON (Capital) | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9666259.56 |  |  | COMPLETED | 1
37171 | NC 2018 | K10 | Region V | Sorsogon City | 114542 | San Isidro Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 18257289.5 |  |  | COMPLETED | 1
37172 | NC 2018 | TVL | Region V | Sorsogon City | 302277 | San Isidro NHS | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 2storey - 2 Science Lab 7x18 | BATCH 3 Realignment | 11148281.33 |  |  | COMPLETED | 1
37173 | NC 2018 | TVL | Region V | Sorsogon City | 302277 | San Isidro NHS | CITY OF SORSOGON (Capital) | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 3 Realignment | 11148281.33 |  |  | COMPLETED | 1
37174 | NC 2018 | TVL | Region V | Sorsogon City | 302278 | Sawanga National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 9987259.56 |  |  | COMPLETED | 1
37175 | NC 2018 | TVL | Region V | Sorsogon City | 302278 | Sawanga National High School | CITY OF SORSOGON (Capital) | 1 |  | 2 | 2storey - 2 Science Lab 7x18 | BATCH 1 | 9666259.56 |  |  | COMPLETED | 1
37176 | NC 2018 | TVL | Region V | Sorsogon City | 302278 | Sawanga National High School | CITY OF SORSOGON (Capital) | 1 |  | 2 | 2storey - 2 ICT Lab 7x18 | BATCH 1 | 9666259.56 |  |  | COMPLETED | 1
37177 | NC 2018 | TVL | Region V | Sorsogon City | 310404 | Sto. Niño Integrated School | CITY OF SORSOGON (Capital) | 1 | 1 | 2 | 2storey - 2 Regular Workshop 7x18 | BATCH 1 | 10241781.65 |  |  | COMPLETED | 1
37178 | NC 2018 | K10 | Region V | Tabaco City | 114595 | Pawa ES | CITY OF TABACO | 1 | 1 | 6 | COMPLETION 3STY6CL | Batch 3 | 7548651.64 |  |  | Completed | 1
37179 | NC 2018 | TVL | Region V | Tabaco City | 302282 | San Antonio NHS, Tabaco | CITY OF TABACO | 1 | 1 | 3 | COMPLETION (3STY3CL Regular Workshop Bldg.) | Batch 3 | 9194704.45 |  |  | Completed | 1
37180 | NC 2018 | TVL | Region V | Tabaco City | 302283 | San Lorenzo NHS | CITY OF TABACO | 1 | 1 | 3 | 3STY3CL Regular Workshop Bldg. |  | 29766510.63 |  |  | Completed | 1
37181 | NC 2018 | TVL | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 | 1 | 3 | COMPLETION (3STY3CL Regular Workshop Bldg.) | Batch 3 | 11454940.71 |  |  | Completed | 1
37182 | NC 2018 | TVL | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 |  | 3 | COMPLETION (3STY3CL Regular Workshop Bldg.) | Batch 3 | 11454940.71 |  |  | Completed | 1
37183 | NC 2018 | TVL | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 |  | 3 | COMPLETION (3STY3CL Regular Workshop Bldg.) | Batch 3 | 11454940.71 |  |  | Completed | 1
37184 | NC 2018 | TVL | Region V | Tabaco City | 310501 | Bongabong High School | CITY OF TABACO | 1 | 1 | 3 | COMPLETION (3STY3CL Regular Workshop Bldg.) | Batch 3 | 10893882.85 |  |  | Completed | 1
39641 | NC 2019 | K10 | Region V | Albay | 111585 | Basud Elementary School | BACACAY | 1 | 1 | 2 | 1STY2CL |  | 2781949.0488 |  | completed | 1 | [11 empty] | 0
39642 | NC 2019 | K10 | Region V | Albay | 111603 | Bayandong Elementary School | BACACAY | 1 | 1 | 3 | 1STY3CL |  | 4223610.5146 |  | completed | 1 | [11 empty] | 0
39643 | NC 2019 | K10 | Region V | Albay | 111680 | Anislag Elementary School | Daraga (Locsin) | 2 | 1 | 12 | 3STY12CL |  | 45408618.45 |  | completed | 1 | [11 empty] | 0
39644 | NC 2019 | K10 | Region V | Albay | 111662 | Binitayan Elementary School | Daraga (Locsin) | 2 | 1 | 9 | 3STY9CL |  | 42544988.2275 |  | completed | 1 | [11 empty] | 0
39645 | NC 2019 | SHS | Region V | Albay | 301846 | Cawayan High School | MANITO | 2 | 1 | 4 | 2STY4CL |  | 16913981.505 |  | completed | 1 | [11 empty] | 0
39646 | NC 2019 | SHS | Region V | Albay | 301822 | Cotmon National High School | CAMALIG | 2 | 1 | 12 | 4STY12CL |  | 46078597.22 |  | completed | 1 | [11 empty] | 0
39647 | NC 2019 | SHS | Region V | Albay | 301825 | Daraga National High School | DARAGA (LOCSIN) | 2 | 1 | 12 | 4STY12CL |  | 62409892.6425 |  | completed | 1 | [11 empty] | 0
39648 | NC 2019 | K10 | Region V | Albay | 111667 | Daraga North Central School | DARAGA (LOCSIN) | 2 | 1 | 16 | 4STY16CL |  | 69938443.0825 |  | completed | 1 | [11 empty] | 0
39649 | NC 2019 | SHS | Region V | Albay | 301823 | Ilawod National High School | CAMALIG | 2 | 1 | 20 | 4STY20CL |  | 55948459.3425 |  | completed | 1 | [11 empty] | 0
39650 | NC 2019 | SHS | Region V | Albay | 309518 | Kilicao High School | Daraga (Locsin) | 2 | 1 | 20 | 4STY20CL |  | 59339411.5825 |  | completed | 1 | [11 empty] | 0
39651 | NC 2019 | K10 | Region V | Albay | 112036 | Mancao Elementary School | RAPURAPU | 2 | 1 | 4 | 2STY4CL |  | 14350841.9358 |  | completed | 1 | [11 empty] | 0
39652 | NC 2019 | K10 | Region V | Legaspi City | 114475 | Bitano Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | 2STY4CL ATTACHED |  | 11002039.8584 |  | completed | 1 | [11 empty] | 0
39653 | NC 2019 | SHS | Region V | Albay | 301845 | Manito National High School | MANITO | 2 | 1 | 20 | 4STY20CL |  | 61255829.68 |  | completed | 1 | [11 empty] | 0
39654 | NC 2019 | K10 | Region V | Legaspi City | 114463 | Mariawa Elementary School | LEGAZPI CITY | 2 | 1 | 2 | 1STY2CL |  | 4998265.1216 |  | completed | 1 | [11 empty] | 0
39655 | NC 2019 | TVL | Region V | Albay | 301839 | Malapay High School | PIO DURAN | 3 | 1 | 2 | 2STY4CL (2reg ws) |  | 13048441.5144 |  | Completed | 1 | [11 empty] | 0
39656 | NC 2019 | TVL | Region V | Albay | 301864 | Pio Duran National High School | PIO DURAN | 3 | 1 | 6 | 4STY8CL (6sci,4shs) |  | 22806444.5967 |  | Completed | 1 | [11 empty] | 0
39657 | NC 2019 | K10 | Region V | Camarines Norte | 112216 | Malatap ES | LABO | 1 | 1 | 4 | 2STY4CL |  | 15555779.6279 |  | Completed | 1 | [11 empty] | 0
39658 | NC 2019 | K10 | Region V | Camarines Norte | 112260 | Tugos ES | PARACALE | 1 | 1 | 4 | 2STY4CL |  | 13819427.1719 |  | Completed | 1 | [11 empty] | 0
39659 | NC 2019 | K10 | Region V | Camarines Norte | 112307 | Juanita Balon ES | VINZONS | 2 | 1 | 4 | 2STY4CL |  | 13344394.6923 |  | Completed | 1 | [11 empty] | 0
39660 | NC 2019 | TVL | Region V | Camarines Sur | 301942 | Barcelonita Fisheries School | CABUSAO | 1 | 1 | 6 | 3storey - 2 Regular, 2 science lab, 2 ICT |  | 53084410.3657 |  | Completed | 1 | [11 empty] | 0
39661 | NC 2019 | K10 | Region V | Camarines Sur | 112789 | Antipolo ES | MINALABAC | 2 | 1 | 2 | 1STY2CL |  | 2640396.6002 |  | completed | 1 | [11 empty] | 0
39662 | NC 2019 | K10 | Region V | Camarines Sur | 112790 | Bagolatao ES | MINALABAC | 2 | 1 | 2 | 1STY2CL |  | 2752705.011 |  | completed | 1 | [11 empty] | 0
39663 | NC 2019 | K10 | Region V | Camarines Sur | 112868 | Cagbunga ES | PAMPLONA | 2 | 1 | 2 | 1STY2CL |  | 2845576.5509 |  | completed | 1 | [11 empty] | 0
39664 | NC 2019 | K10 | Region V | Camarines Sur | 112877 | San Vicente ES | PAMPLONA | 2 | 1 | 2 | 1STY2CL |  | 2659833.4712 |  | completed | 1 | [11 empty] | 0
39665 | NC 2019 | SHS | Region V | Camarines Sur | 301952 | Calabanga NHS | CALABANGA | 3 | 1 | 24 | 4STY24CL |  | 62537498.8825 |  | Completed | 1 | [11 empty] | 0
39666 | NC 2019 | K10 | Region V | Camarines Sur | 112770 | Sta. Lucia ES | MAGARAO | 3 | 1 | 9 | 3STY9CL |  | 43216033.036 |  | completed | 1 | [11 empty] | 0
39667 | NC 2019 | K10 | Region V | Camarines Sur | 112986 | Odiongan ES | SAGÑAY | 4 | 1 | 4 | 2STY4CL |  | 11792333.1947 |  | completed | 1 | [11 empty] | 0
39668 | NC 2019 | K10 | Region V | Camarines Sur | 113028 | San Jose CS | SAN JOSE | 4 | 1 | 6 | 2STY6CL |  | 15582864.3609 |  | completed | 1 | [11 empty] | 0
39669 | NC 2019 | K10 | Region V | Camarines Sur | 113045 | Siruma Central School | SIRUMA | 4 | 1 | 4 | 2STY4CL |  | 11782308.1947 |  | completed | 1 | [11 empty] | 0
39670 | NC 2019 | K10 | Region V | Camarines Sur | 113150 | Tierra Nevada Elementary School | TINAMBAC | 4 | 1 | 4 | 2STY4CL |  | 11891951.6197 |  | completed | 1 | [11 empty] | 0
39671 | NC 2019 | TVL | Region V | Iriga City | 302251 | Rinconada National Technical Vocational School | IRIGA CITY | 5 | 1 | 3 | 1unit 3sty (1Reg, 1Science & 1ICT Lab) |  | 14388219.0555 |  | COMPLETED | 1 | [11 empty] | 0
39672 | NC 2019 | K10 | Region V | Legaspi City | 114466 | Bagumbayan Central School | LEGAZPI CITY (Capital) | 2 | 1 | 16 | 4STY16CL |  | 68681760.21 |  | completed | 1 | [11 empty] | 0
39673 | NC 2019 | K10 | Region V | Legaspi City | 114477 | Cabagnan ES | LEGAZPI CITY (Capital) | 2 | 1 | 12 | 4STY12CL |  | 59439248.5525 |  | completed | 1 | [11 empty] | 0
39674 | NC 2019 | K10 | Region V | Legaspi City | 114478 | Dapdap Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 8 | 2STY8CL |  | 23197709.65 |  | completed | 1 | [11 empty] | 0
39675 | NC 2019 | SHS | Region V | Legaspi City | 310202 | Legazpi City Science High School | LEGAZPI CITY (Capital) | 2 | 1 | 12 | 4STY12CL |  | 57993386.9125 |  | Completed | 1 | [11 empty] | 0
39676 | NC 2019 | SHS | Region V | Legaspi City | 302263 | Pawa High School | LEGAZPI CITY (Capital) | 2 | 1 | 12 | 3STY12CL |  | 49187041.9525 |  | completed | 1 | [11 empty] | 0
39677 | NC 2019 | SHS | Region V | Legaspi City | 500169 | Taysan Resettlement Integrated School | LEGAZPI CITY (Capital) | 2 | 1 | 12 | 4STY12CL |  | 46428990.0175 |  | completed | 1 | [11 empty] | 0
39678 | NC 2019 | TVL | Region V | Ligao City | 301820 | Deogracias P. Princesa Memorial HS | CITY OF LIGAO | 3 | 1 | 2 | 2STY4CL (2units sci) |  | 11815366.5144 |  | Completed | 1 | [11 empty] | 0
39679 | NC 2019 | SHS | Region V | Masbate | 302176 | Verdida-Sabrido NHS | PLACER | 3 | 1 | 8 | 2STY8CL |  | 26685440.2325 |  | COMPLETED | 1 | [11 empty] | 0
39680 | NC 2019 | SHS | Region V | Sorsogon | 302186 | Biriran NHS | JUBAN | 2 | 1 | 8 | 2STY8CL |  | 25062500 |  | COMPLETED | 1 | [11 empty] | 0
39681 | NC 2019 | TVL | Region V | Sorsogon | 302211 | Gabao NHS | IROSIN | 2 | 1 | 6 | 3STY12CL (2reg,2sci,2ict) |  | 36974934.1784 |  | COMPLETED | 1 | [11 empty] | 0
39682 | NC 2019 | TVL | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2 | 1 | 4 | 2STY8CL (2sci,2ict) |  | 23733306.3626 |  | COMPLETED | 1 | [11 empty] | 0
39683 | NC 2019 | SHS | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2 |  | 16 | 4STY16CL |  | 45590437.5542 |  | COMPLETED | 1 | [11 empty] | 0
39684 | NC 2019 | TVL | Region V | Sorsogon | 302237 | San Francisco NHS | BULAN | 2 | 1 | 4 | 2STY6CL (1reg,1sci,2shs) |  | 16627787.8952 |  | COMPLETED | 1 | [11 empty] | 0
39685 | NC 2019 | SHS | Region V | Sorsogon | 302242 | San Roque NHS | BULUSAN | 2 | 1 | 12 | 3STY12CL |  | 45408618.45 |  | COMPLETED | 1 | [11 empty] | 0
39686 | NC 2019 | K10 | Region V | Sorsogon City | 114554 | Bibincahan Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 6 | 2STY6CL |  | 20350750 |  | Completed | 1 | [11 empty] | 0
39687 | NC 2019 | K10 | Region V | Sorsogon City | 114582 | Ticol Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 6 | 3STY6CL |  | 18046901.7024 |  | COMPLETED | 1 | [11 empty] | 0
39688 | NC 2019 | K10 | Region V | Tabaco City | 114597 | Quinastillojan ES | CITY OF TABACO | 1 | 1 | 3 | 1STY3CL |  | 3999565.2181 |  | COMPLETED | 1 | [11 empty] | 0
40316 | NC 2020 | K10 | Region V | Albay | 111610 | Lower Bonga Elementary School | BACACAY | 1 | 1 | 4 | 2STY4CL |  | 14145618.54 |  |  | Completed | 1
40317 | NC 2020 | K10 | Region V | Albay | 112053 | Calayucay Elementary School | SANTO DOMINGO (LIBOG) | 1 | 1 | 4 | 2STY4CL |  | 13700301.99 |  |  | Completed | 1
40318 | NC 2020 | K10 | Region V | Albay | 111650 | Solong Elementary School | CAMALIG | 2 | 1 | 9 | 3STY9CL |  | 41785956.38 |  |  | Completed | 1
40319 | NC 2020 | K10 | Region V | Albay | 111890 | Buyo Elementary School | MANITO | 2 | 1 | 4 | 2STY4CL |  | 17184075.06 |  |  | Completed | 1
40320 | NC 2020 | K10 | Region V | Albay | 111720 | Travesia ES | GUINOBATAN | 3 | 1 | 6 | 2STY6CL |  | 15739250 |  |  | Completed | 1
40321 | NC 2020 | SHS | Region V | Albay | 301849 | Marcial O. Rañola Memorial School | GUINOBATAN | 3 | 1 | 6 | 2STY6CL |  | 15839500 |  |  | Completed | 1
40322 | NC 2020 | K10 | Region V | Camarines Norte | 112282 | M. Hebrado ES | SANTA ELENA | 1 | 1 | 4 | 2STY4CL |  | 15037500 |  |  | Completed | 1
40323 | NC 2020 | SHS | Region V | Camarines Norte | 309607 | Lazaro Cabezudo HS | TALISAY | 2 | 1 | 1 | 1 Unique WS(7x22.5) |  | 5702069.08 |  |  | Completed | 1
40324 | NC 2020 | TVL | Region V | Camarines Norte | 309607 | Lazaro Cabezudo HS | TALISAY | 2 |  | 2 | 2STY2 SCI & ICT LAB |  | 12211716.94 |  |  | Completed | 1
40325 | NC 2020 | K10 | Region V | Camarines Sur | 112577 | Del Gallego CS | DEL GALLEGO | 1 | 1 | 4 | 1STY4CL |  | 12531250 |  |  | completed | 1
40326 | NC 2020 | K10 | Region V | Camarines Sur | 112688 | Mantalisay Elementary School | LIBMANAN | 2 | 1 | 4 | 2STY4CL |  | 12935991.71 |  |  | completed | 1
40327 | NC 2020 | K10 | Region V | Camarines Sur | 112698 | Umalo ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL |  | 5026984.65 |  |  | completed | 1
40328 | NC 2020 | K10 | Region V | Camarines Sur | 112700 | Bagamelon ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL |  | 5343645.17 |  |  | completed | 1
40329 | NC 2020 | K10 | Region V | Camarines Sur | 112705 | Caima Elementary School | LIBMANAN | 2 | 1 | 2 | 1STY2CL |  | 5377385.3 |  |  | completed | 1
40330 | NC 2020 | K10 | Region V | Camarines Sur | 112714 | Odoc ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL |  | 5327734.65 |  |  | completed | 1
40331 | NC 2020 | K10 | Region V | Camarines Sur | 112717 | Salvacion ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL |  | 5367792.37 |  |  | completed | 1
40332 | NC 2020 | K10 | Region V | Camarines Sur | 112724 | Villa Socorro ES | LIBMANAN | 2 | 1 | 2 | 1STY2CL |  | 5328346.04 |  |  | completed | 1
40333 | NC 2020 | K10 | Region V | Camarines Sur | 112801 | Malitbog ES | MINALABAC | 2 | 1 | 4 | 2STY4CL |  | 12935991.71 |  |  | Completed | 1
40334 | NC 2020 | K10 | Region V | Camarines Sur | 112869 | Calawat PS/Elementary School | PAMPLONA | 2 | 1 | 2 | 1STY2CL |  | 5185464.43 |  |  | completed | 1
40335 | NC 2020 | K10 | Region V | Camarines Sur | 112876 | San Ramon ES | PAMPLONA | 2 | 1 | 2 | 1STY2CL |  | 5043164.91 |  |  | completed | 1
40336 | NC 2020 | K10 | Region V | Camarines Sur | 112899 | Bagong Silang Elementary School | PASACAO | 2 | 1 | 2 | 1STY2CL |  | 5520023.06 |  |  | Completed | 1
40337 | NC 2020 | K10 | Region V | Camarines Sur | 112907 | Hubo ES | PASACAO | 2 | 1 | 2 | 1STY2CL |  | 5570148.06 |  |  | completed | 1
40338 | NC 2020 | K10 | Region V | Camarines Sur | 112913 | Salvacion ES | PASACAO | 2 | 1 | 2 | 1STY2CL |  | 5971148.06 |  |  | completed | 1
40339 | NC 2020 | K10 | Region V | Camarines Sur | 112915 | Tilnac Elementary School | PASACAO | 2 | 1 | 2 | 1STY2CL |  | 5766954.98 |  |  | Completed | 1
40340 | NC 2020 | K10 | Region V | Camarines Sur | 112994 | Alianza ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL |  | 5206752.82 |  |  | completed | 1
40341 | NC 2020 | K10 | Region V | Camarines Sur | 112996 | BICAL ELEMENTARY SCHOOL | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL |  | 5218642.79 |  |  | completed | 1
40342 | NC 2020 | K10 | Region V | Camarines Sur | 112998 | Calascagas PS | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL |  | 5456225.94 |  |  | completed | 1
40343 | NC 2020 | K10 | Region V | Camarines Sur | 113001 | Gñaran ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL |  | 5180848.58 |  |  | completed | 1
40344 | NC 2020 | K10 | Region V | Camarines Sur | 113011 | Sta. Cruz ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL |  | 5206752.82 |  |  | completed | 1
40345 | NC 2020 | K10 | Region V | Camarines Sur | 173508 | Tinanquihan Primary School | LIBMANAN | 2 | 1 | 4 | 2STY4CL |  | 12935991.71 |  |  | completed | 1
40346 | NC 2020 | SHS | Region V | Camarines Sur | 302012 | Pamplona NHS | PAMPLONA | 2 | 1 | 8 | 2STY8CL |  | 25898780.85 |  |  | completed | 1
40347 | NC 2020 | SHS | Region V | Camarines Sur | 302012 | Pamplona NHS | PAMPLONA | 2 |  | 8 | 2STY8CL |  | 28202886.99 |  |  | completed | 1
40348 | NC 2020 | SHS | Region V | Camarines Sur | 302013 | PAMUKID NATIONAL HIGH SCHOOL | SAN FERNANDO | 2 | 1 | 4 | 2STY4CL |  | 12935991.71 |  |  | Completed | 1
40349 | NC 2020 | SHS | Region V | Camarines Sur | 302037 | San Juan National HS | LIBMANAN | 2 | 1 | 4 | 2STY4CL |  | 28002056.22 |  |  | Completed | 1
40350 | NC 2020 | SHS | Region V | Camarines Sur | 309705 | Pinamasagan National High School | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL |  | 5206752.82 |  |  | completed | 1
40351 | NC 2020 | SHS | Region V | Camarines Sur | 500158 | Antipolo Heights Integrated School | PASACAO | 2 | 1 | 2 | 1STY2CL |  | 5206752.82 |  |  | COMPLETED | 1
40352 | NC 2020 | K10 | Region V | Camarines Sur |  | Bagadion High School (Mambulo Nuevo HS Annex) | LIBMANAN | 2 | 1 | 2 | 1STY2CL |  | 5110971.65 |  |  | completed | 1
40353 | NC 2020 | K10 | Region V | Camarines Sur | 112762 | Magarao Central School | Magarao | 3 | 1 | 8 | 2STY8CL |  | 25680727.28 |  |  | Completed | 1
40354 | NC 2020 | SHS | Region V | Camarines Sur | 300496 | New Partido HS | Goa | 4 | 1 | 6 | 2STY6CL |  | 13388150.06 |  |  | completed | 1
40355 | NC 2020 | SHS | Region V | Camarines Sur | 305545 | Goa Science NHS | Goa | 4 | 1 | 4 | 2STY4CL |  | 15750045.94 |  |  | completed | 1
40356 | NC 2020 | SHS | Region V | Camarines Sur | 309753 | SALOGON HS | San Jose | 4 | 1 | 4 | 2STY4CL |  | 13388150.06 |  |  | Completed | 1
40357 | NC 2020 | K10 | Region V | Camarines Sur | 112383 | San Miguel ES | BATO | 5 | 1 | 4 | 2STY4CL |  | 12605055.72 |  |  | Completed | 1
40358 | NC 2020 | SHS | Region V | Camarines Sur | 302001 | Nabua National High School | NABUA | 5 | 1 | 15 | 3STY15CL |  | 46062149.84 |  |  | Completed | 1
40359 | NC 2020 | K10 | Region V | Camarines Sur | 305484 | Iraya High School | BUHI | 5 | 1 | 5 | 1STY5CL |  | 15090350.16 |  |  | Completed | 1
40360 | NC 2020 | SHS | Region V | Catanduanes | 302105 | Tinago NHS | Viga | 0 | 1 | 6 | 2STY6CL |  | 15037500 |  |  | COMPLETED | 1 | [10 empty] | Mobilization
40361 | NC 2020 | K10 | Region V | Legaspi City | 114496 | Tamaoyan ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | 3STY6CL |  | 24941837.1 |  |  | COMPLETED | 1
40362 | NC 2020 | K10 | Region V | Legaspi City | 100182 | Banquerohan Resettlement Elementary School | Legazpi City | 2 | 1 | 6 | 2STY6CL |  | 20342950.55 |  |  | Completed | 1
40363 | NC 2020 | K10 | Region V | Ligao City | 231004 | Nabonton ES, Buga Ext. | Ligao City | 3 | 1 | 6 | 2STY6CL |  | 16541250 |  |  | COMPLETED | 1 | [10 empty] | For Issuance of Notice to proceed
40364 | NC 2020 | K10 | Region V | Masbate | 174511 | Cogon ES | MONREAL | 1 | 1 | 4 | 1STY4CL |  | 8037873.16 |  |  | Completed | 1
40365 | NC 2020 | SHS | Region V | Masbate | 302152 | Monreal National High School | MONREAL | 1 | 1 | 4 | 1STY4CL |  | 10107376.84 |  |  | Completed | 1
40366 | NC 2020 | K10 | Region V | Masbate | 113440 | Potoson ES | BALENO | 2 | 1 | 4 | 2STY4CL |  | 16982931.03 |  |  | Completed | 1
40367 | NC 2020 | SHS | Region V | Masbate | 309951 | AMOTAG NATIONAL HIGH SCHOOL | AROROY | 2 | 1 | 4 | 2STY4CL |  | 16350193.97 |  |  | Completed | 1
40368 | NC 2020 | K10 | Region V | Masbate | 113505 | Abaca ES | CATAINGAN | 3 | 1 | 3 | 1STY3CL |  | 8260128.81 |  |  | Completed | 1
40369 | NC 2020 | K10 | Region V | Masbate | 113506 | Bagumbayan ES | CATAINGAN | 3 | 1 | 1 | 1STY1CL |  | 3265225.11 |  |  | Completed | 1
40370 | NC 2020 | K10 | Region V | Masbate | 113509 | Chimenea ES | CATAINGAN | 3 | 1 | 1 | 1STY1CL |  | 3265225.11 |  |  | Completed | 1
40371 | NC 2020 | K10 | Region V | Masbate | 113525 | San Isidro Elementary School | CATAINGAN | 3 | 1 | 1 | 1STY1CL |  | 3265225.11 |  |  | Completed | 1
40372 | NC 2020 | K10 | Region V | Masbate | 113543 | Dalipe ES | CAWAYAN | 3 | 1 | 6 | 2STY6CL |  | 18224071.79 |  |  | Completed | 1
40373 | NC 2020 | K10 | Region V | Masbate | 113603 | Calabad ES | DIMASALANG | 3 | 1 | 1 | 1STY1CL |  | 3265225.11 |  |  | Completed | 1
40374 | NC 2020 | K10 | Region V | Masbate | 113612 | N.B. Cabrera ES | DIMASALANG | 3 | 1 | 1 | 1STY1CL |  | 3265225.11 |  |  | Completed | 1
40375 | NC 2020 | K10 | Region V | Masbate | 113636 | VILLA ELEMENTARY SCHOOL | ESPERANZA | 3 | 1 | 4 | 1STY4CL |  | 10073259.79 |  |  | Completed | 1
40376 | NC 2020 | K10 | Region V | Masbate | 113782 | Pedro A. Basas ES | PALANAS | 3 | 1 | 4 | 1STY4CL |  | 10073259.79 |  |  | Completed | 1
40377 | NC 2020 | K10 | Region V | Masbate | 113823 | Calumpang ES | PLACER | 3 | 1 | 4 | 1STY4CL |  | 10063601.03 |  |  | Completed | 1
40378 | NC 2020 | K10 | Region V | Sorsogon | 114106 | La Union ES | Castilla | 1 | 1 | 4 | 2UNITS 1STY2CL |  | 8985196.98 |  |  | completed | 1 | [10 empty] | Mobilization
40379 | NC 2020 | TVL | Region V | Sorsogon | 302226 | Mayon NHS | Castilla | 1 | 1 | 1 | 1STY UNIQUE WORKSHOP |  | 5310217.91 |  |  | completed | 1
40380 | NC 2020 | SHS | Region V | Sorsogon | 302230 | Pilar National Comprehensive HS | PILAR | 1 | 1 | 4 | 2STY4CL |  | 12545957.68 |  |  | completed | 1 | [10 empty] | Mobilization
40381 | NC 2020 | SHS | Region V | Sorsogon | 302231 | PILI NATIONAL HIGH SCHOOL | MAGALLANES | 1 | 1 | 4 | 2STY4CL |  | 13533750 |  |  | completed | 1 | [10 empty] | Mobilization
40382 | NC 2020 | TVL | Region V | Sorsogon | 302240 | San Juan NHS | Casiguran | 1 | 1 | 8 | 2sty 8cl (2 Reg 1 Scie & 1 ICT Lab) |  | 23567447.28 |  |  | Completed | 1 | [10 empty] | Mobilization
40383 | NC 2020 | K10 | Region V | Sorsogon | 114006 | Cadandanan ES | Bulan | 2 | 1 | 2 | 1STY2CL |  | 5077255.7 |  |  | completed | 1
40384 | NC 2020 | K10 | Region V | Sorsogon | 114192 | Gubat North CS | GUBAT | 2 | 1 | 8 | 2STY8CL |  | 23757922.69 |  |  | completed | 1
40385 | NC 2020 | K10 | Region V | Sorsogon | 114307 | Cabagahan ES | Matnog | 2 | 1 | 2 | 1STY2CL |  | 6248930.09 |  |  | completed | 1 | [10 empty] | Mobilization
40386 | NC 2020 | SHS | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2 | 1 | 21 | 3STY21CL |  | 64867899.34 |  |  | Completed | 1 | [10 empty] | Mobilization
40387 | NC 2020 | SHS | Region V | Sorsogon | 302223 | Manlabong NHS | PRIETO DIAZ | 2 | 1 | 6 | 2STY6CL |  | 21315832.66 |  |  | completed | 1 | [10 empty] | Mobilization
40388 | NC 2020 | K10 | Region V | Sorsogon City | 114561 | Ambrosio J. Labrador Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL |  | 14550957.68 |  |  | COMPLETED | 1
40389 | NC 2020 | K10 | Region V | Sorsogon City | 114568 | Buenavista Elementary School (Sorsogon West) | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | 2STY4CL |  | 13047207.68 |  |  | COMPLETED | 1 | [10 empty] | Mobilization
40390 | NC 2020 | K10 | Region V | Tabaco City | 114604 | Tabaco Northwest Central School | CITY OF TABACO | 1 | 1 | 6 | 2STY6CL |  | 20026939.67 |  |  | completed | 1
41111 | NC 2021 | K10 | Region V | Albay | 111643 | Cotmon Elementary School | CAMALIG | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 23954557.05 | 23894820 |  | COMPLETED | 1
41112 | NC 2021 | SHS | Region V | Albay | 301836 | San Pascual National High School | LIBON | 3 | 1 | 4 | Construction/Completion (2STY8CL (2sci, 2ict)) |  | 841294.6316 | 839196.64 |  | Completed | 1
41113 | NC 2021 | SHS | Region V | Albay | 301839 | Malapay High School | PIO DURAN | 3 | 1 | 2 | Construction/Completion (2STY4CL (2sci)) |  | 1133353.3175 | 1130527 |  | COMPLETED | 1
41114 | NC 2021 | SHS | Region V | Albay | 301854 | Marigondon National High School | PIO DURAN | 3 | 1 | 4 | Construction/Completion (2STY6CL (2shs,2reg)) |  | 902250 | 900000 |  | COMPLETED | 1
41115 | NC 2021 | SHS | Region V | Albay | 301860 | Pantao National High School | LIBON | 3 | 1 | 2 | Construction/Completion (2STY4CL (2sci)) |  | 2145193.3895 | 2139843.78 |  | completed | 1
41116 | NC 2021 | TVL | Region V | Camarines Norte | 301893 | Daguit NHS | LABO | 1 | 1 | 4 | Construction/Completion (2STY4CL Regular Workshop) |  | 1980338.8108 | 1975400.31 |  | COMPLETED | 1
41117 | NC 2021 | K10 | Region V | Camarines Norte | 112223 | Colasi ES | MERCEDES | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 4498874.6087 | 4487655.47 |  | COMPLETED | 1
41118 | NC 2021 | TVL | Region V | Camarines Norte | 301907 | Pablo S. Villafuerte HS | MERCEDES | 2 | 1 | 4 | Construction/Completion (2STY4CL Science Lab and ICT) |  | 2462255.498 | 2456115.21 |  | Completed | 1
41119 | NC 2021 | SHS | Region V | Camarines Norte | 309613 | Alawihao National High School (Annex) | DAET (Capital) | 2 | 1 |  | Construction of Slope Protection |  | 35048243.4634 | 34960841.36 |  | Completed | 1
41120 | NC 2021 | TVL | Region V | Camarines Norte | 309622 | Camarines Norte NHS-Annex | DAET (Capital) | 2 | 1 | 4 | Construction/Completion (2STY4CL Science Lab and ICT) |  | 1491369.7766 | 1487650.65 |  | COMPLETED | 1
41121 | NC 2021 | TVL | Region V | Camarines Sur | 301942 | Barcelonita Fisheries School | CABUSAO | 1 | 1 | 6 | Construction/Completion (3storey - 2 Regular, 2 science lab, 2 ICT) |  | 37816954.0185 | 37722647.4 |  | COMPLETED | 1
41122 | NC 2021 | SHS | Region V | Camarines Sur | 301961 | Colacling National High School | LUPI | 1 | 1 | 1 | Construction/Completion (Electrical installation and transformer) |  | 652627.5 | 651000 |  | Completed | 1
41123 | NC 2021 | K10 | Region V | Camarines Sur | 137076 | Sitio Lipata ES | CARAMOAN | 4 | 1 | 6 | 2UNITS 1STY3CL |  | 16405413.8364 | 16364502.58 |  | Completed | 1
41124 | NC 2021 | SHS | Region V | Catanduanes | 302071 | Antipolo NHS | Virac (Capital) | 0 | 1 | 8 | Construction of Slope Protection |  | 32062747.4061 | 31982790.43 |  | Completed | 1
41125 | NC 2021 | SHS | Region V | Catanduanes | 302073 | Baras RDHS | Baras | 0 | 1 | 10 | Construction of Slope Protection |  | 11174843.2696 | 11146975.83 |  | Completed | 1
41126 | NC 2021 | SHS | Region V | Catanduanes | 302073 | Baras RDHS | Baras | 0 |  | 12 | Construction of Slope Protection |  | 10824748.8461 | 10797754.46 |  | Completed | 1
41127 | NC 2021 | SHS | Region V | Catanduanes | 302088 | Gigmoto RDHS | Gigmoto | 0 | 1 | 8 | Construction of Slope Protection |  | 7907922.7356 | 7888202.23 |  | Completed | 1
41128 | NC 2021 | SHS | Region V | Catanduanes | 302099 | Mabato NHS (SMRDHS Annex) | San Miguel | 0 | 1 | 6 | Construction of Slope Protection |  | 6383818.1861 | 6367898.44 |  | Completed | 1
41129 | NC 2021 | K10 | Region V | Legaspi City | 100182 | Banquerohan Resettlement Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 1002500 | 1000000 |  | COMPLETED | 1
41130 | NC 2021 | K10 | Region V | Legaspi City | 114496 | Tamaoyan ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | Construction/Completion (3STY6CL) |  | 1002500 | 1000000 |  | COMPLETED | 1
41131 | NC 2021 | SHS | Region V | Ligao City | 301862 | Paulba NHS | CITY OF LIGAO | 3 | 1 | 8 | Construction/Completion (2STY8CL (2reg 1sci 1ict)) |  | 781566.634 | 779617.59 |  | COMPLETED | 1
41132 | NC 2021 | SHS | Region V | Ligao City | 301862 | Paulba NHS | CITY OF LIGAO | 3 |  |  | Construction of Slope Protection |  | 1904750 | 1900000 |  | COMPLETED | 1
41133 | NC 2021 | SHS | Region V | Masbate | 302115 | Baleno National High School | BALENO | 2 | 1 | 2 | Construction of Slope Protection |  | 446828.7662 | 445714.48 |  | COMPLETED | 1
41134 | NC 2021 | SHS | Region V | Masbate | 302140 | Lagta National High School | BALENO | 2 | 1 | 2 | Construction of Slope Protection |  | 1114209.7279 | 1111431.15 |  | COMPLETED | 1
41135 | NC 2021 | SHS | Region V | Masbate | 309901 | Delavin-Rubia National High School | AROROY | 2 | 1 | 2 | Construction of Slope Protection |  | 852034.6748 | 849909.9 |  | COMPLETED | 1
41136 | NC 2021 | SHS | Region V | Masbate | 309931 | Amador-Bello HS | BALENO | 2 | 1 | 2 | Construction of Slope Protection |  | 569581.6431 | 568161.24 |  | COMPLETED | 1
41137 | NC 2021 | SHS | Region V | Masbate | 309931 | Amador-Bello HS | BALENO | 2 |  | 2 | Construction of Slope Protection |  | 554718.0468 | 553334.71 |  | COMPLETED | 1
41138 | NC 2021 | SHS | Region V | Masbate City | 302133 | Capitolina O. Legaspi Memorial High School | CITY OF MASBATE (Capital) | 2 | 1 | 15 | Construction/Completion (3STY15CL) |  | 2668396.2146 | 2661741.86 |  | COMPLETED | 1
41139 | NC 2021 | K10 | Region V | Sorsogon | 114144 | Donsol East CS | DONSOL | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 25894716.0417 | 25830140.69 | 25043013.82 | Completed | 1 | 2022-06-24 |  | P00575869LZ-CW1 | 21FK0064 | 2021-06-25 | 2021-07-02 | 2021-07-14 | 2021-09-22 | 2021-09-27 | RODA Construction & Gen. Supply
41140 | NC 2021 | SHS | Region V | Sorsogon | 302218 | Celso F. Falcotelo National High School | BARCELONA | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 16393355.4356 | 16352474.25 | 15854760.77 | COMPLETED | 1 | 2022-03-02 | 2022-08-25 | P00575870LZ-CW1 | 21FL0073 | 2021-07-13 | 2021-07-22 | 2021-08-03 | 2021-09-21 | 2021-09-29 | Alhadrax Construction and Supply
41141 | NC 2021 | SHS | Region V | Sorsogon | 302235 | Jupi National High School | GUBAT | 2 | 1 | 8 | Construction/Completion (2STY8CL) |  | 24561250 | 24500000 | 23635254.71 | COMPLETED | 1 | 2022-07-31 |  | P00575871LZ-CW1 | 21FL0074 | 2021-07-13 | 2021-07-22 | 2021-08-03 | 2021-09-21 | 2021-10-01 | RMH Construction & Supply
41142 | NC 2021 | TVL | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 | 1 | 2 | Construction/Completion (2 units - Construction of 2 Workshop Buildings (Standard Technical Vocational Building)) |  | 9882.645 | 9858 |  | COMPLETED | 1
41143 | NC 2021 | TVL | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 |  | 3 | Construction/Completion (3STY3 Regular Workshop) |  | 3817281.7659 | 3807762.36 |  | COMPLETED | 1
41144 | NC 2021 | SHS | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 |  | 20 | Construction/Completion (4STY20CL) |  | 13273144.3406 | 13240044.23 |  | COMPLETED | 1
41145 | NC 2021 | SHS | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 |  | 6 | Construction/Completion (2STY6CL) |  | 891213.0264 | 888990.55 |  | COMPLETED | 1
41146 | NC 2021 | SHS | Region V | Tabaco City | 302286 | Tabaco National High School | CITY OF TABACO | 1 |  | 20 | Construction/Completion (4STY20CL PAGCOR BLDG) |  | 6166506.9027 | 6151129.08 |  | COMPLETED | 1
41683 | NC 2022 | K10 | Region V | Camarines Norte | 112266 | Mampurog ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4796241.5 | Completed | 1 | 2023-03-29 | 2023-01-11 | P00675152LZ-CW1 | 22FC0264 | [5 empty] | 128 DRAGON CONSTRUCTION AND SUPPLIES | other details not provided by the concerned DEO
41684 | NC 2022 | K10 | Region V | Camarines Norte | 112275 | San Vicente CS | SAN VICENTE | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4980213.75 | Completed | 1 | 2023-06-22 | 2023-01-12 | P00675153LZ-CW1 | 22FC0265 | [5 empty] | 888RV CONSTRUCTION AND SUPPLIES | other details not provided by the concerned DEO
41685 | NC 2022 | K10 | Region V | Camarines Sur | 112779 | Gainza CS - Gainza | GAINZA | 2 | 1 | 2 | 1STY2CL | 2 |  | 5293867.3442 | 5215298.26 | Completed | 1 | 2023-07-04 |  | P00675155LZ-CW1 | 22FE0095 |  | 2022-01-12 | 2022-12-13 | 2022-12-19 | 2022-12-29 | ADSL CONST. & TRADING | 100% completed
41686 | NC 2022 | K10 | Region V | Camarines Sur | 112771 | Sto. Domingo Elementary School | BOMBON | 3 | 1 | 2 | 1STY2CL | 2 |  | 5412764.0447 | 5412000.76 | Completed | 1 |  | 2023-04-15 | P00575857LZ-CW1 | 22FF0082 |  | 2022-02-12 | 2022-12-15 | 2022-12-23 | 2023-10-01 | MEGA ANT BUIDERS | 100% completed
41687 | NC 2022 | K10 | Region V | Camarines Sur | 112498 | Camaligan Central School | CAMALIGAN | 3 | 1 | 2 | 1STY2CL | 2 |  | 5685547.7333 | 5686000.55 | Completed | 1 |  | 2023-04-15 | P00575859LZ-CW1 | 22FF0083 |  | 2022-02-12 | 2022-12-15 | 2022-12-23 | 2023-10-01 | MEGA ANT BUIDERS | 100% completed
41688 | NC 2022 | K10 | Region V | Catanduanes | 113173 | Baras CES | BARAS | 0 | 1 | 4 | 2STY4CL | 2 |  | 16582679.5456 |  | Completed | 1
41689 | NC 2022 | K10 | Region V | Masbate | 113477 | Batuan CS | BATUAN | 1 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | 2023-11-04 | 2023-11-04 | P00675160LZ-0 | 22FM0037 | 2022-11-26 | 2022-12-06 | 2022-12-02 | 2022-12-27 | 2023-06-01 | JOHNCB CONSTRUCTION & SUPPLIES | 100% completed based on Contract and with request for additional fund to full completion of project
41690 | NC 2022 | K10 | Region V | Masbate | 113633 | Sorosimbahan ES | ESPERANZA | 3 | 1 | 2 | 1STY2CL | 2 |  | 6210487.5 |  | Completed | 1
41691 | NC 2022 | K10 | Region V | Sorsogon | 114200 | San Ignacio Elementary School | GUBAT | 2 | 1 | 6 | 3STY6CL | 2 |  | 25263000 | 24761614.66 | Completed | 1 | 2023-07-11 | 2025-01-21 | P0067163LZ-CW1 | 22FL0081 | 2023-01-24 | 2023-01-31 | 2023-02-15 | 2023-02-03 | 2023-03-13 | RMH Construction and Supply
41692 | NC 2022 | K10 | Region V | Sorsogon | 114415 | Sta. Magdalena CS | SANTA MAGDALENA | 2 | 1 | 4 | 2STY4CL | 2 |  | 16911684.587 | 16576084.91 | Completed | 1 | 2023-07-11 | 2025-01-21 | P0067165LZ-CW1 | 22FL0081 | 2023-01-24 | 2023-01-31 | 2023-02-15 | 2023-02-03 | 2023-03-13 | RMH Construction and Supply
41818 | NC 2022 | SHS | Region V | Camarines Sur | 302051 | Sta. Lutgarda National High School | Cabusao | 1 | 1 | 2 | 1STY2CL | 2 |  | 5604948.7182 | 5585955.94 | Completed | 1 | 2023-04-21 | 2023-05-18 | P00675154LZ-CW1 | 22FD0042 | 2022-11-25 | 2022-02-12 | 2022-12-15 | 2022-12-23 | 2022-12-28 | PHIMANA CONST. | 100% completed
41819 | NC 2022 | SHS | Region V | Catanduanes | 302074 | Bato Rural Development High School | BATO | 0 | 1 | 4 | 2STY4CL | 2 |  | 15069898.6947 |  | Completed | 1
41820 | NC 2022 | SHS | Region V | Masbate | 501273 | Buenavista Integrated School | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | 2023-11-04 | 2023-11-04 | P00675161LZ-0 | 22FM0038 | 2022-11-26 | 2022-12-06 | 2022-12-02 | 2022-12-27 | 2023-06-01 | JOHNCB CONSTRUCTION & SUPPLIES | 100% completed based on Contract and with request for additional fund to full completion of project
41821 | NC 2022 | SHS | Region V | Sorsogon | 302196 | Calao National High School | PRIETO DIAZ | 2 | 1 | 4 | 2STY4CL | 2 |  | 16911684.587 | 16573122.71 | Completed | 1 | 2023-07-11 | 2025-01-16 | P0067164LZ-CW1 | 22FL0081 | 2023-01-24 | 2023-01-31 | 2023-02-15 | 2023-02-03 | 2023-03-13 | RMH Construction and Supply
42409 | NC 2023 | K10 | Region V | Albay | 111874 | Estancia Elementary School | MALINAO |  | 1 | 6 |  | Batch 1 | 18422474.39 | 18262675.97 | 17898256.21 | Completed | 1 | 2024-01-22 |  | 300101000000000 | 23FA0091 | 2024-04-17 | 2024-04-25 | 2024-07-05 | 2024-06-06 | 2023-10-04 | JORMAND CONST. & SUPPLY | Not Yet Turned-Over, COC - not yet signed due to balance building permits
42410 | NC 2023 | K10 | Region V | Albay | 112064 | Baybay Elementary School | TIWI |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 | 11122372.74 | Completed | 1 | 2025-05-21 | 2025-05-21 | 300101000000000 | 23FA0091 | 2024-04-17 | 2024-04-25 | 2024-07-05 | 2024-06-06 | 2023-10-04 | JORMAND CONST. & SUPPLY
42411 | NC 2023 | K10 | Region V | Albay | 112072 | Maynonong Elementary School | TIWI |  | 1 | 4 |  | Batch 2 | 18112500 | 17500000 | 17059599.34 | Completed | 1 | 2024-04-19 | 2024-04-19 | 300101000000000 | 23FA0077 | 2023-10-19 | 2023-10-27 | 2023-08-11 | 2023-11-20 | 2023-12-20 | RCDS CONSTRUCTION & SUPPLY, INC.
42412 | NC 2023 | K10 | Region V | Albay | 112080 | Sugod Elementary School | TIWI |  | 1 | 3 |  | Batch 1 | 5178986.1 | 5134063.05 | 5178986.1 | Completed | 1 | 2025-05-21 | 2025-05-21 | 300101000000000 | 23FA0091 | 2024-04-17 | 2024-04-25 | 2024-07-05 | 2024-06-06 | 2023-10-04 | JORMAND CONST. & SUPPLY
42413 | NC 2023 | K10 | Region V | Albay | 111651 | TAGAYTAY ELEMENTARY SCHOOL | CAMALIG |  | 1 | 15 |  | Batch 1 | 84954081.59 | 54217181.25 | 52854003 | Completed | 1 | 2024-06-15 | 2024-06-15 | 23FB0209 | 23FB0209 |  | 2023-03-08 | 2023-08-15 | 2023-08-30 | 2023-09-14 | GRELIPS CONSTRUCTION & DEVELOPMENT / HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (JV) | NONE
42414 | NC 2023 | K10 | Region V | Albay | 111763 | Linao Elementary School | LIBON |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 | 11451808.4 | Completed | 1 | 2024-12-22 | 2024-12-18 | P00775438LZ | 23FO0122 |  | 2024-07-24 |  |  | 2024-04-09 | EMIRAM Construction and Supply | COMPLETED
42415 | NC 2023 | K10 | Region V | Albay | 111766 | Malabiga Elementary School | LIBON |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 | 11451391.82 | Completed | 1 | 2024-12-22 | 2024-12-18 | P00775439LZ | 23FO0121 |  | 2024-07-24 |  |  | 2024-04-09 | J-NAC Construction and Supply | COMPLETED
42416 | NC 2023 | K10 | Region V | Camarines Norte | 112172 | Sta. Milagrosa ES | JOSE PANGANIBAN | 1 | 1 | 2 |  | Batch 1 | 7089349.39 | 7027855.65 | 6811442 | Completed | 1 | 2023-11-02 | 2024-04-01 | P00775440LZ | 23FC0095 | 2023-06-21 | 2023-07-04 | 2023-07-18 | 2023-07-26 | 2023-08-04 | GREAT WALL Engineering
42417 | NC 2023 | K10 | Region V | Camarines Norte | 500909 | Kabatuhan Integrated School | LABO | 1 | 1 | 2 |  | Batch 1 | 7757736.74 | 7690445.34 | 7458683.94 | Completed | 1 | 2023-11-02 | 2024-04-01 | P00775441LZ | 23FC0096 | 2023-06-21 | 2023-07-04 | 2023-07-18 | 2023-07-26 | 2023-08-04 | GREAT WALL Engineering
42418 | NC 2023 | K10 | Region V | Camarines Norte | 112094 | Mangcamagong Elem. School | BASUD | 2 | 1 | 3 |  | Batch 1 | 8761459.34 | 8685461.55 | 8685461.55 | Completed | 1 | 2024-04-06 | 2024-07-01 | P00775442LZ-CW1 | 23F00379 | 2023-10-24 | 2023-11-03 | 2023-11-17 | 2023-12-19 | 2023-12-28 | BRENTMIN ROOFING ENTERPRISE
42419 | NC 2023 | K10 | Region V | Camarines Norte | 112313 | Pinagtigasan ES | VINZONS | 2 | 1 | 3 |  | Batch 1 | 9005628.01 | 8927512.28 | 8649559.73 | Completed | 1 | 2024-04-06 | 2024-10-01 | P00775443-CW1 | 23F00380 | 2023-10-24 | 2023-11-03 | 2023-11-17 | 2023-12-19 | 2023-12-28 | BRENTMIN ROOFING ENTERPRISE
42420 | NC 2023 | K10 | Region V | Camarines Norte | 112159 | Roman V. Heraldo ES | JOSE PANGANIBAN |  | 1 | 4 |  | Batch 1 | 19166250 | 19000000 | 18426577.63 | Completed | 1 | 2024-02-09 | 2024-08-07 | P00775444LZ | 23FC0098 | 2023-07-21 | 2023-08-04 | 2023-08-17 | 2023-08-31 | 2023-09-08 | JAEJR Electrical, Construction and Supply
42421 | NC 2023 | K10 | Region V | Camarines Norte | 112197 | Agapito Racelis ES | LABO |  | 1 | 2 |  | Batch 1 | 11096250 | 11000000 | 10665592.53 | Completed | 1 | 2023-11-07 | 2024-05-05 | P00775879LZ | 23FC0097 | 2023-06-21 | 2023-07-04 | 2023-08-17 | 2023-07-26 | 2023-08-04 | JAEJR Electrical, Construction and Supply
42422 | NC 2023 | SHS | Region V | Camarines Norte | 301925 | Vinzons Pilot High School | VINZONS |  | 1 | 2 |  | Batch 1 | 30262500 | 30000000 | 29072901.66 | Ongoing | 0.9 | 2024-10-20 |  | P00775880LZ-Cw1 | 23F00417 | 2023-10-24 | 2024-01-12 | 2024-01-25 | 2024-03-08 | 2024-03-21 | 128 Dragon Construction and Supplies | constant follow-up to fast track the construction of school building
42423 | NC 2023 | SHS | Region V | Camarines Sur | 302051 | Sta. Lutgarda National High School | CABUSAO |  | 1 | 3 |  | Batch 1 | 10087500 | 10000000 | 9951335.73 | Completed | 1 | 2024-02-06 | 2024-07-01 | P6007755881LZ-CW1 | 23FD0054 |  | 2023-07-20 | 2023-08-01 | 2023-08-03 | 2023-08-11 | HGG BUILDERS | 180cd
42424 | NC 2023 | K10 | Region V | Camarines Sur | 112584 | San Juan ES | DEL GALLEGO |  | 1 | 3 |  | Batch 1 | 10087500 | 10000000 | 9939017.63 | Completed | 1 | 2024-02-06 | 2024-03-01 | P6007755882LZ-CW1 | 23FD0054 |  | 2023-07-20 | 2023-08-01 | 2023-08-03 | 2023-08-11 | HGG BUILDERS | 180cd
42425 | NC 2023 | K10 | Region V | Camarines Sur | 173534 | San Rafael Norte ES | LUPI |  | 1 | 3 |  | Batch 1 | 10087500 | 10000000 | 10009381.26 | Completed | 1 | 2024-02-06 | 2024-09-01 | P6007755883LZ-CW1 | 23FD0054 |  | 2023-07-20 | 2023-08-01 | 2023-08-03 | 2023-08-11 | HGG BUILDERS | 180cd
42426 | NC 2023 | K10 | Region V | Camarines Sur | 112672 | Bahay ES | LIBMANAN |  | 1 | 3 |  | Batch 1 | 7565625 | 7500000 | 7385960.78 | Completed | 1 | 2023-12-23 | 2023-12-22 | P00775884LZ-CWI | 23FE0115 |  | 2023-07-19 | 2023-07-31 | 2023-08-14 |  | Bicol Goldrock | 100cd
42427 | NC 2023 | K10 | Region V | Camarines Sur | 112681 | Libmanan North CS | LIBMANAN |  | 1 | 3 |  | Batch 1 | 10087500 | 10000000 | 9892784.16 | Completed | 1 | 2023-12-05 | 2023-12-05 | P00775885LZ-CWI | 23FE0117 |  | 2023-07-21 | 2023-08-03 | 2023-08-14 | 2023-08-18 | DATZLAV CONST | 110 cd
42428 | NC 2023 | SHS | Region V | Camarines Sur | 302037 | San Juan National High School | LIBMANAN |  | 1 | 3 |  | Batch 1 | 7565625 | 7500000 | 7394320.61 | Completed | 1 | 2023-12-23 | 2023-12-22 | P00775886LZ-CWI | 23FE0116 |  | 2023-07-19 | 2023-07-31 | 2023-08-14 |  | SHLA CONST | 100CD
42429 | NC 2023 | K10 | Region V | Camarines Sur | 112789 | Antipolo ES | MINALABAC |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4910502.11 | Completed | 1 | 2023-12-13 | 2023-12-07 | P00775887LZ-CWI | 23FE0112 |  | 2023-07-14 | 2023-07-26 | 2023-08-14 |  | Bicol Goldrock | 100CD
42430 | NC 2023 | K10 | Region V | Camarines Sur | 112797 | Hamoraon ES | MINALABAC |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4948117.44 | Completed | 1 | 2023-12-13 | 2023-12-13 | P00775888LZ-CWI | 23FE0113 |  | 2023-07-14 | 2023-07-26 | 2023-08-14 |  | SHLA CONST | 100CD
42431 | NC 2023 | K10 | Region V | Camarines Sur | 112798 | Hobo ES | MINALABAC |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4948122.02 | Completed | 1 | 2023-12-13 | 2023-12-13 | P00775889LZ-CWI | 23FE0114 |  | 2023-07-14 | 2023-07-26 | 2023-08-14 |  | Bicol Goldrock | 100cd
42432 | NC 2023 | SHS | Region V | Camarines Sur | 302021 | Ramon B. Felipe Sr. NHS (frmerly: San Vicente HS) | PAMPLONA |  | 1 | 3 |  | Batch 1 | 10087500 | 10000000 | 9898258.98 | Completed | 1 | 2023-12-05 | 2023-12-05 | P00775890LZ-CWI | 23FE0118 |  | 2023-07-21 | 2023-08-03 | 2023-08-14 | 2023-08-18 | DATZLAV CONST | 110 cd
42433 | NC 2023 | SHS | Region V | Camarines Sur | 309769 | Pasacao National High School | PASACAO |  | 1 | 3 |  | Batch 1 | 10087500 | 10000000 | 9887625.9 | Completed | 1 | 2023-12-23 | 2023-12-22 | P00775891LZ-CWI | 23FE0119 |  | 2023-07-21 | 2023-08-03 | 2023-08-14 |  | SHLA CONST | 110 cd
42434 | NC 2023 | K10 | Region V | Camarines Sur | 112766 | San Antonio ES | BOMBON |  | 1 | 4 |  | Batch 1 | 15491317.61 | 15356944.35 | 15310902.6 | Completed | 1 | 2024-05-07 | 2024-04-01 | P00775892LZ-CWI | 23FF0101 |  |  | 2023-12-11 | 2023-12-21 | 2024-01-03 | DONLEE CONST.
42435 | NC 2023 | SHS | Region V | Camarines Sur | 302052 | Camaligan National High School (formerly: Santo Tomas NHS) | CAMALIGAN |  | 1 | 12 |  | Batch 1 | 67730557.39 | 67143055.65 | 66404400 | Ongoing | 0.75 | 2024-11-03 |  | P00775893LZ | 23FF0100 |  |  | 2023-12-11 | 2023-12-21 | 2024-01-03 | STEVEN COSNT/ REI-TECH CONST
42436 | NC 2023 | K10 | Region V | Camarines Sur | 112537 | Gata ES | CARAMOAN |  | 1 | 2 |  | Batch 1 | 7190067.38 | 7127700 | 6946233.43 | Completed | 1 | 2023-11-27 | 2024-02-14 | P00775894LZ-CW1 | 23FG0097 |  | 2023-06-09 | 2023-07-04 | 2023-07-18 | 2023-07-25 | J.C NIETO CONSTRUCTION | 120 CD
42437 | NC 2023 | K10 | Region V | Camarines Sur | 501283 | Lip-Ac Integrated School | GOA |  | 1 | 2 |  | Batch 1 | 6685692.38 | 6627700 | 6460000.42 | Completed | 1 |  | 2023-12-09 | P00775895LZ-CW1 | 23FG0098 |  | 2023-06-09 | 2023-07-04 | 2023-07-18 | 2023-07-25 | J.C NIETO CONSTRUCTION | 60 cd
42438 | NC 2023 | K10 | Region V | Camarines Sur | 112629 | Napawon ES | GOA |  | 1 | 4 |  | Batch 2 | 7497566.77 | 7244025.86 | 7018710.92 | Completed | 1 | 2024-05-27 | 2024-05-27 | P00776457LZ-CW1 | 23FG0102 | 2023-11-20 | 2023-11-28 | 2023-12-13 | 2024-01-03 | 2024-03-08 | J.C NIETO CONSTRUCTION
42439 | NC 2023 | K10 | Region V | Camarines Sur | 305911 | Mabca National High School | SAGÑAY |  | 1 | 3 |  | Batch 1 | 8088839.79 | 8018676.37 | 6946233.43 | Completed | 1 | 2023-11-02 | 2023-12-22 | P00775896LZ-CW1 | 23FG0099 |  | 2023-06-09 | 2023-07-04 | 2023-07-18 | 2023-07-25 | LIMCORE CONST. | 95 CD
42440 | NC 2023 | SHS | Region V | Camarines Sur | 309766 | Cabalinadan High School | TIGAON |  | 1 | 2 |  | Batch 1 | 6685692.38 | 6627700 | 6457132.77 | Completed | 1 |  | 2024-01-25 | P00775897LZ-CW1 | 23FG0100 |  | 2023-06-09 | 2023-07-04 | 2023-07-18 | 2023-07-25 | J.C NIETO CONSTRUCTION | 60 CD
42441 | NC 2023 | K10 | Region V | Camarines Sur | 112344 | Balatan CS | BALATAN |  | 1 | 5 |  | Batch 1 | 10732989.77 | 10639890.72 | 10501463.56 | Completed | 1 | 2024-04-27 | 2024-04-26 | P00775898LZ-CW1 | 23FN0077 | 2023-08-15 | 2023-08-22 |  | 2023-12-15 | 2023-12-29 | TGME | 121CD
42442 | NC 2023 | K10 | Region V | Camarines Sur | 112354 | Nacacale ES | BALATAN |  | 1 | 4 |  | Batch 1 | 8687799.44 | 8612440.58 | 8500334.34 | Completed | 1 | 2024-04-13 | 2024-04-12 | P00775899LZ-CW1 | 23FN0078 | 2023-08-15 | 2023-08-22 |  | 2023-12-15 | 2023-12-29 | TGME | 107CD
42443 | NC 2023 | K10 | Region V | Camarines Sur | 112427 | Bula Central School | BULA |  | 1 | 5 |  | Batch 1 | 10732989.77 | 10639890.72 | 10500801.09 | Completed | 1 | 2024-04-27 | 2024-04-26 | P00775900LZCW1 | 23FN0079 | 2023-08-15 | 2023-08-22 |  | 2023-12-15 | 2023-12-29 | TGME | 121CD
42444 | NC 2023 | K10 | Region V | Catanduanes | 113173 | Baras CES | BARAS |  | 1 | 10 |  | Batch 1 | 30262500 | 30000000 |  | Completed | 1
42445 | NC 2023 | SHS | Region V | Catanduanes | 302073 | Baras Rural DHS | BARAS |  | 1 | 2 |  | Batch 1 | 8408068.56 | 8335136.12 |  | Completed | 1
42446 | NC 2023 | K10 | Region V | Catanduanes | 113181 | Batalay ES | BATO |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 |  | Ongoing | 0.83
42447 | NC 2023 | K10 | Region V | Catanduanes | 500412 | Bote IS | Bato |  | 1 | 2 |  | Batch 1 | 8408068.56 | 8335136.12 |  | Completed | 1
42448 | NC 2023 | K10 | Region V | Catanduanes | 500414 | Palumbanes Integrated School | CARAMORAN |  | 1 | 6 |  | Batch 1 | 18422474.39 | 18262675.97 |  | Ongoing | 0.7
42449 | NC 2023 | SHS | Region V | Catanduanes | 302087 | Dororian NHS | GIGMOTO |  | 1 | 4 |  | Batch 1 | 15545149.12 | 15410308.92 |  | Completed | 1
42450 | NC 2023 | K10 | Region V | Catanduanes | 113305 | San Miguel CES | SAN MIGUEL |  | 1 | 8 |  | Batch 1 | 30328460.07 | 30065387.92 |  | Completed | 1
42451 | NC 2023 | SHS | Region V | Catanduanes | 302089 | Hawan National High School | VIRAC (Capital) |  | 1 | 0 |  | Batch 1 | 15131250 | 15000000 |  | Completed | 1
42452 | NC 2023 | SHS | Region V | Catanduanes | 302090 | Magnesia National High School | VIRAC (Capital) |  | 1 | 0 |  | Batch 1 | 15131250 | 15000000 |  | Completed | 1
42453 | NC 2023 | SHS | Region V | Legaspi City | 302261 | Legazpi City National High School | LEGAZPI CITY (Capital) |  | 1 | 12 |  | Batch 1 | 79988586.63 | 79294757.5 | 76892150.48 | Ongoing | 0.98 | 2024-07-10 |  | 23FB0207 | 23FB0207 |  |  | 2023-08-15 |  | 2023-09-14 | NEXT GENERATION CONSTRUCTION AND SUPPLY / 3RB CONSTRUCTION AND SUPPLY (JV)
42454 | NC 2023 | SHS | Region V | Ligao City | 301837 | Ligao National High School | CITY OF LIGAO |  | 1 | 9 |  | Batch 1 | 30262500 | 30000000 |  | Under Procurement | 0
42455 | NC 2023 | K10 | Region V | Masbate | 113477 | Batuan CS | BATUAN |  | 1 | 2 |  | Batch 1 | 5536728.17 | 5488702.03 | 5406396 | Completed | 1 | 2023-11-04 | 2023-11-04 |  | 23FM0045 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-01 | JOHNCB Construction
42456 | NC 2023 | K10 | Region V | Masbate | 113478 | Burgos Elementary School | BATUAN |  | 1 | 5 |  | Batch 1 | 13506592.18 | 13389434.63 | 13389402.62 | Completed | 1 | 2024-04-02 | 2024-05-15 |  | 23FM0054 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-01 | REI-TECH Construction and Supply
42457 | NC 2023 | K10 | Region V | Masbate | 500164 | Costa Rica Integrated School | BATUAN |  | 1 | 2 |  | Batch 1 | 5961554.9 | 5909843.77 | 5909832.3 | Completed | 1 | 2023-11-04 | 2023-11-04 | P00775915LZ | 23FM0047 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-01 | C.L Carandang Enterprises
42458 | NC 2023 | SHS | Region V | Masbate | 302134 | F. Alindogan National High School | BATUAN |  | 1 | 4 |  | Batch 1 | 13003247.83 | 12890456.34 | 12890452.38 | Completed | 1 | 2024-03-03 | 2024-05-02 | P00775914LZ | 23FM0044 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-01 | C.L Carandang Enterprises
42459 | NC 2023 | K10 | Region V | Masbate | 113775 | Togoron ES | MONREAL |  | 1 | 2 |  | Batch 1 | 5896529.3 | 5845382.2 | 5751812.09 | Completed | 1 | 2023-12-04 | 2024-02-10 | P00775916LZ | 23FM0051 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-01 | 3R3M Construction and Supply
42460 | NC 2023 | K10 | Region V | Masbate | 113862 | Buenos Aires ES | SAN FERNANDO |  | 1 | 3 |  | Batch 1 | 8495568.44 | 8421877.01 | 8337608.08 | Completed | 1 | 2023-12-04 | 2024-01-10 | P00775917LZ | 23FM0052 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-01 | HKP Construction and Supply
42461 | NC 2023 | K10 | Region V | Masbate | 113863 | Buyo ES | SAN FERNANDO |  | 1 | 2 |  | Batch 1 | 5889405.4 | 5838320.1 | 5753663.49 | Completed | 1 | 2023-12-04 | 2024-02-08 | P00775918LZ | 23FM0046 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-01 | 3R3M Construction and Supply
42462 | NC 2023 | K10 | Region V | Masbate | 113865 | Canelas ES | SAN FERNANDO |  | 1 | 3 |  | Batch 1 | 8521066.52 | 8447153.92 | 8331796.59 | Completed | 1 | 2023-12-04 | 2023-12-01 | P00775919LZ | 23FM0053 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-01 | C.L Carandang Enterprises
42463 | NC 2023 | K10 | Region V | Masbate | 113873 | Progreso ES | SAN FERNANDO |  | 1 | 2 |  | Batch 1 | 5924953.8 | 5873560.15 | 5740543.7 | Completed | 1 | 2023-11-04 | 2023-11-04 | P00775920LZ | 23FM0048 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-01 | REI-TECH Construction and Supply
42464 | NC 2023 | K10 | Region V | Masbate | 501527 | Roxas Integrated High School | SAN PASCUAL |  | 1 | 2 |  | Batch 1 | 5750122.15 | 5700245 | 5698513.55 | Completed | 1 | 2023-12-10 | 2023-12-18 | P00775922LZ | 23FM0049 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-01 | 3R3M Construction and Supply
42465 | NC 2023 | K10 | Region V | Masbate | 113935 | San Pedro ES | SAN PASCUAL |  | 1 | 2 |  | Batch 1 | 5616952.01 | 5568230 | 5566235.17 | Completed | 1 | 2023-12-10 | 2023-12-18 | P00775921LZ | 23FM0050 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-01 | 3R3M Construction and Supply
42466 | NC 2023 | K10 | Region V | Masbate | 113620 | Baras ES | ESPERANZA |  | 1 | 2 |  | Batch 1 | 7905219.15 | 7836648.47 |  | Completed | 1 | 2024-01-23
42467 | NC 2023 | K10 | Region V | Masbate | 113626 | Magsaysay Elementary School | ESPERANZA |  | 1 | 2 |  | Batch 1 | 7905219.15 | 7836648.47 |  | Completed | 1 | 2024-01-14
42468 | NC 2023 | K10 | Region V | Masbate | 113627 | Masbaranon ES | ESPERANZA |  | 1 | 3 |  | Batch 1 | 10788640.11 | 10695058.35 |  | Completed | 1 | 2024-01-18
42469 | NC 2023 | K10 | Region V | Masbate | 113628 | Pablo .M. Conag CS | ESPERANZA |  | 1 | 3 |  | Batch 1 | 10785009.9 | 10691459.63 |  | Completed | 1 | 2024-02-02
42470 | NC 2023 | K10 | Region V | Masbate | 113621 | Prudencio Martinez ES | ESPERANZA |  | 1 | 3 |  | Batch 1 | 7905219.24 | 7836648.56 |  | Ongoing | 1 | 2024-03-26
42471 | NC 2023 | SHS | Region V | Masbate | 302131 | Del Carmen National High School | USON |  | 1 | 3 |  | Batch 1 | 10627499.07 | 10535315.06 |  | Completed | 1 | 2024-12-22
42472 | NC 2023 | SHS | Region V | Masbate | 309950 | SIMAWA NATIONAL HIGH SCHOOL | USON |  | 1 | 3 |  | Batch 1 | 10818063.28 | 10724226.3 |  | Completed | 1 | 2024-01-06
42473 | NC 2023 | SHS | Region V | Masbate | 302175 | Uson National High School | USON |  | 1 | 3 |  | Batch 1 | 10556252.08 | 10464686.08 |  | Completed | 1 | 2023-12-10
42474 | NC 2023 | K10 | Region V | Masbate City | 113665 | Amancio Aguilar Elementary School | CITY OF MASBATE (Capital) |  | 1 | 9 |  | Batch 1 | 30451990.68 | 30187847.02 |  | Under Procurement | 0
42475 | NC 2023 | K10 | Region V | Naga City | 114514 | Jose Rizal Elementary School | NAGA CITY |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 |  | Completed | 1 |  |  | 23FF0087 | 23FF0087 | [5 empty] | VIRGO CONSTRUCTION | Turned over
42476 | NC 2023 | SHS | Region V | Sorsogon | 302201 | Cumadcad National High School | CASTILLA |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 | 11011625.42 | Completed | 1 | 2024-06-23 | 2024-10-02 | P00775933LZ-CW1 | 23FK0107 |  | 2023-08-08 | 2023-08-22 | 2023-08-30 | 2023-09-07 | TR Construction Corporation
42477 | NC 2023 | K10 | Region V | Sorsogon | 114145 | Gogon ES | DONSOL |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4604747.27 | Completed | 1 | 2024-06-23 | 2024-10-02 | P00775934LZ-CW1 | 23FK0107 |  | 2023-08-08 | 2023-08-22 | 2023-08-30 | 2023-09-07 | TR Construction Corporation
42478 | NC 2023 | K10 | Region V | Sorsogon | 114285 | Tagas ES | MAGALLANES |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4604831.39 | Completed | 1 | 2024-06-23 | 2024-10-02 | P00775935LZ-CW1 | 23FK0107 |  | 2023-08-08 | 2023-08-22 | 2023-08-30 | 2023-09-07 | TR Construction Corporation
42479 | NC 2023 | K10 | Region V | Sorsogon | 114376 | Leona ES | PILAR |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4604739.39 | Completed | 1 | 2024-06-23 | 2024-10-02 | P00775936LZ-CW1 | 23FK0107 |  | 2023-08-08 | 2023-08-22 | 2023-08-30 | 2023-09-07 | TR Construction Corporation
42480 | NC 2023 | K10 | Region V | Sorsogon | 114352 | Marifosque ES | PILAR |  | 1 | 4 |  | Batch 2 | 18946644.14 | 18305936.37 | 18305279.17 | Completed | 1 | 2024-11-30 | 2025-05-30 | P00775352LZ-CW1 | 23FK0122 |  | 2023-10-26 | 2023-11-08 | 2023-11-23 | 2023-12-06 | RMH Construction and Supply
42481 | NC 2023 | K10 | Region V | Sorsogon | 114382 | Naspi Elementary School | PILAR |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4604495.91 | Completed | 1 | 2024-06-23 | 2024-10-02 | P00775937LZ-CW1 | 23FK0107 |  | 2023-08-08 | 2023-08-22 | 2023-08-30 | 2023-09-07 | TR Construction Corporation
42482 | NC 2023 | K10 | Region V | Sorsogon | 302230 | Pilar National Comprehensive High School | PILAR |  | 1 | 4 |  | Batch 2 | 18946644.14 | 18305936.37 | 18304928.79 | Completed | 1 | 2024-11-30 | 2025-05-30 | P00775353LZ-CW1 | 23FK0122 |  | 2023-10-26 | 2023-11-08 | 2023-11-23 | 2023-12-06 | RMH Construction and Supply
42483 | NC 2023 | K10 | Region V | Sorsogon | 113978 | Alegria Elementary School | BARCELONA |  | 1 | 5 |  | Batch 1 | 11600625 | 11500000 | 11152911.66 | Completed | 1 | 2024-05-24 | 2025-04-28 | P00775938LZ-CW1 | 23FL0067 | 2023-07-15 | 2023-07-24 | 2023-08-28 | 2023-08-18 | 2023-08-25 | Fulleros Botox Builders and Design
42484 | NC 2023 | K10 | Region V | Sorsogon | 113982 | Barcelona Central School | BARCELONA |  | 1 | 4 |  | Batch 1 | 9330937.5 | 9250000 | 8984419.09 | Completed | 1 | 2024-05-24 | 2025-04-28 | P00775939LZ-CW1 | 23FL0067 | 2023-07-15 | 2023-07-24 | 2023-08-28 | 2023-08-18 | 2023-08-25 | Fulleros Botox Builders and Design
42485 | NC 2023 | SHS | Region V | Sorsogon | 302184 | Barcelona National Comprehensive High School | BARCELONA |  | 1 | 21 |  | Batch 1 | 69640346.93 | 69036279.48 | 67650141.66 | Completed | 1 | 2024-07-29 | 2025-05-30 | P00775594-CW1 | 23FL0069 | 2023-07-27 | 2023-08-03 | 2023-08-16 | 2023-08-30 | 2023-09-08 | Steven Const. and Supply / Kyla Const. Supply (JV)
42486 | NC 2023 | K10 | Region V | Sorsogon | 113987 | Macabari Elementary School | BARCELONA |  | 1 | 4 |  | Batch 1 | 9330937.5 | 9250000 | 9064910 | Completed | 1 | 2024-02-02 | 2024-06-03 |  | 23FL0075 | 2023-08-18 | 2023-08-25 | 2023-09-14 | 2023-09-28 | 2023-10-06 | Kyla Construction
42487 | NC 2023 | K10 | Region V | Sorsogon | 114262 | Jagusara ES | JUBAN |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29253515.5 | Completed | 1 | 2024-05-24 | 2025-03-28 | P00775941LZ-CW1 | 23FL0067 | 2023-07-15 | 2023-07-24 | 2023-08-28 | 2023-08-18 | 2023-08-25 | Fulleros Botox Builders and Design
42488 | NC 2023 | SHS | Region V | Sorsogon | 302223 | Manlabong National High School | PRIETO DIAZ |  | 1 | 6 |  | Batch 1 | 22587586.7 | 22391659.68 | 21941660.47 | Completed | 1 | 2024-07-29 | 2025-01-16 | P00775944-CW1 | 23FL0069 | 2023-07-27 | 2023-08-03 | 2023-08-16 | 2023-08-30 | 2023-09-08 | Steven Const. and Supply / Kyla Const. Supply (JV)
42489 | NC 2023 | K10 | Region V | Sorsogon | 114396 | Prieto Diaz CS | PRIETO DIAZ |  | 1 | 12 |  | Batch 1 | 30262500 | 30000000 | 29191813.94 | Ongoing | 0.75 | 2024-12-31 |  | P00775943LZ-CW1 | 23FL0080 | 2024-03-06 | 2024-03-13 | 2024-04-03 | 2024-04-22 | 2024-05-02 | Alphard Primecon Construction | 2STY8CL Phase 1
42490 | NC 2023 | K10 | Region V | Tabaco City | 114618 | Rawis ES | CITY OF TABACO |  | 1 | 3 |  | Batch 1 | 6661039.51 | 6603260.98 | 6470811.57 | Completed | 1 |  |  | 300101000000000 | 23FA0091 | 2024-04-17 | 2024-04-25 | 2024-05-07 | 2024-06-06 | 2024-06-25 | JORMAND CONST. & SUPPLY | Design modified to 1STY1CL due to budget limitation
42491 | NC 2023 | SHS | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO |  | 1 | 12 |  | Batch 1 | 21278183.9 | 21093614.77 | 20377249.16 | Completed | 1 |  |  | 300101000000000 | 23FA0080 | 2023-11-10 | 2023-11-17 | 2023-12-12 | 2023-03-15 | 2023-04-01 | 3RB CONSTRUCTION & SUPPLY | Design modified to 2STY6CL due to budget limitation
43895 | NC 2024 |  | Region V | Albay | 111584 | Bacacay East Central School | BACACAY |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19302626.62 | Ongoing | 0.97 |  |  | 24FA0062 | 24FA0062 | 2024-08-14 | 2024-08-22 | 2024-09-04 | 2024-09-18 | 2024-09-25 | 8AR Construction and Development Corp.
43896 | NC 2024 |  | Region V | Albay | 111858 | Malilipot Central School | MALILIPOT |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19303043.59 | Ongoing | 0.97 |  |  | 24FA0062 | 24FA0062 | 2024-08-14 | 2024-08-22 | 2024-09-04 | 2024-09-18 | 2024-09-25 | 8AR Construction and Development Corp.
43897 | NC 2024 |  | Region V | Albay | 111880 | Ogob Elementary School | MALINAO |  | 1 | 6 | 2STY6CL | BATCH 1 | 35860381.36 |  | 34610420.28 | Ongoing | 0.57 |  |  | 300101000000000 | 24FA0063 | 2024-08-22 | 2024-08-29 | 2024-09-10 | 2024-09-24 | 2024-10-04 | JORMAND CONST. & SUPPLY
43898 | NC 2024 |  | Region V | Albay |  | COTMON HIGH SCHOOL | CAMALIG |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19341303.12 | Ongoing | 0.32 | 2025-04-21 |  | 24FB0249 | 24FB0249 |  | 2024-04-11 | 2024-11-12 | 2024-02-12 | 2024-12-17 | HI-TONE CONSTRUCTION AND DEVELOPMENT CORPORATION | NONE
43899 | NC 2024 |  | Region V | Albay |  | TALOTO INTEGRATED SCHOOL | CAMALIG |  | 1 | 8 | 2STY8CL | GAA 17B | 40000000 |  | 38905907.39 | Ongoing | 0.85 | 2025-05-07 |  | 24FB0247 | 24FB0247 |  | 2024-04-11 | 2024-11-12 | 2024-02-12 | 2024-12-17 | HI-TONE CONSTRUCTION AND DEVELOPMENT CORPORATION | NONE
43900 | NC 2024 |  | Region V | Albay |  | TUMPA HIGH SCHOOL | CAMALIG |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  |  | Not Yet Started | 0 |  |  | 24FB0243 | 24FB0243 |  | 2024-09-26 | 2024-08-10 |  |  |  | the project is on procurement (short of award)
43901 | NC 2024 |  | Region V | Albay | 301808 | Anislag National High School | DARAGA (LOCSIN) |  | 1 | 6 | 2STY6CL | GAA 17B | 40000000 |  | 38604413.57 | Ongoing | 0.7 | 2024-06-15 | 2024-06-15 | 23FB0209 | 23FB0209 |  | 2023-03-08 | 2023-08-15 | 2023-08-30 | 2023-09-14 | GRELIPS CONSTRUCTION & DEVELOPMENT / HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (JV) | NONE
43902 | NC 2024 |  | Region V | Albay | 111662 | Binitayan Elementary School | DARAGA (LOCSIN) |  | 1 | 9 | 3STY9CL | GAA 17B | 50000000 |  | 48256006.2 | Not Yet Started | 0 | 2025-11-11 |  | 24FB0284 | 24FB0284 |  | 2025-06-03 | 2025-03-18 | 2025-03-27 | 2025-10-04 | KNJ CONSTRUCTION AND SUPPLY/HI-TONE CONSTRUCTION AND DEVELOPMENT CORPORATION(JV) | NONE
43903 | NC 2024 |  | Region V | Albay | 111683 | Burgos Elementary School | DARAGA (LOCSIN) |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0 | [10 empty] | on procurement
43904 | NC 2024 |  | Region V | Albay | 111687 | Gapo Elementary School | DARAGA (LOCSIN) |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0 | [10 empty] | on procurement
43905 | NC 2024 |  | Region V | Albay |  | Gotob Elementary School | DARAGA (LOCSIN) |  | 1 | 6 | 2STY6CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0 | [10 empty] | on procurement
43906 | NC 2024 |  | Region V | Albay | 111690 | Kinawitan Elementary School | DARAGA (LOCSIN) |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0 | [10 empty] | on procurement
43907 | NC 2024 |  | Region V | Albay | 111671 | Kiwalo Elementary School | DARAGA (LOCSIN) |  | 1 | 12 | 3STY12CL | GAA 17B | 60000000 |  | 38905907.39 | Ongoing | 0.29 | 2025-08-19 |  | 24FB0248 | 24FB0248 |  | 2024-04-11 | 2024-11-12 | 2024-02-12 | 2024-12-17 | KNJ CONSTRUCTION & SUPPLY / HI-TONE CONSTRUCTION AND DEVELOPMENT CORPORATION (JV) | NONE
43908 | NC 2024 |  | Region V | Albay | 111692 | Mabini Elementary School | DARAGA (LOCSIN) |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0 | [10 empty] | on procurement
43909 | NC 2024 |  | Region V | Albay | 111674 | Matnog Elementary School | DARAGA (LOCSIN) |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 38678433.07 | Ongoing | 0.11 | 2025-08-13 |  | 24FB0294 | 24FB0294 |  | 2025-07-03 | 2025-03-20 | 2025-03-27 | 2025-10-04 | HI-TONE CONSTRUCTION AND DEVELOPMENT CORPORATION | NONE
43910 | NC 2024 |  | Region V | Albay | 111676 | Penafrancia Elementary School | DARAGA (LOCSIN) |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 38678433.07 | Ongoing | 0.11 | 2025-08-13 |  | 24FB0294 | 24FB0294 |  | 2025-07-03 | 2025-03-20 | 2025-03-27 | 2025-10-04 | HI-TONE CONSTRUCTION AND DEVELOPMENT CORPORATION | NONE
43911 | NC 2024 |  | Region V | Albay | 111702 | Tabontabon Elementary School | DARAGA (LOCSIN) |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 38678433.07 | Ongoing | 0.11 | 2025-08-13 |  | 24FB0294 | 24FB0294 |  | 2025-07-03 | 2025-03-20 | 2025-03-27 | 2025-10-04 | HI-TONE CONSTRUCTION AND DEVELOPMENT CORPORATION | NONE
43912 | NC 2024 |  | Region V | Albay | 301849 | Marcial O. RaÃ±ola Memorial School | GUINOBATAN |  | 1 | 20 | 4STY20CL | GAA 17B | 150000000 |  | 145373625.26 | Ongoing | 0.15 |  |  | P00875566LZ | 24FO0139 |  | 2025-01-24 |  |  |  | TWINCARE BUILDERS INC.
43913 | NC 2024 |  | Region V | Albay | 301844 | Mauraro High School | GUINOBATAN |  | 1 | 8 | 2STY8CL | GAA 17B | 40000000 |  | 35748373.26 | Ongoing | 0.08 | 2025-04-11 |  | P00875553LZ | 24FO0127 |  | 2024-09-05 | 2024-09-17 | 2024-09-26 | 2024-07-10 | WCS Construction, Inc.
43914 | NC 2024 |  | Region V | Albay | 111737 | Pood Elementary School | GUINOBATAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Ongoing | 0.91 | 2025-03-08 | 2025-04-15 | P00875554LZ | 24FO0137 |  | 2024-09-25 | 2024-08-10 | 2024-10-28 | 2024-08-11 | 417 LP Construction Corporation
43915 | NC 2024 |  | Region V | Albay | 111742 | Estrella Elementary School | JOVELLAR |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4842646.43 | Not Yet Started | 0 | 2025-02-26 |  | P00875560LZ | 24FO0132 |  | 2024-09-20 | 2024-02-10 | 2024-10-16 | 2024-10-28 | CAMSUR BICOL Trading, Inc.
43916 | NC 2024 |  | Region V | Albay | 111755 | Sinagaran Elementary School | JOVELLAR |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4824068.89 | Not Yet Started | 0 | 2025-02-26 |  | P00875561LZ | 24FO0133 |  | 2024-09-20 | 2024-02-10 | 2024-10-16 | 2024-10-28 | CAMSUR BICOL Trading, Inc.
43917 | NC 2024 |  | Region V | Albay | 111908 | Bogtong Elementary School | OAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4886959.39 | Not Yet Started | 0 | 2024-08-03 |  | P00875557LZ | 24FO0130 |  | 2024-09-20 | 2024-02-10 | 2024-10-16 | 2024-10-28 | SAMARINA Construction | Project is SUSPENDED as of 11/04/2024 pending issuance of permit from DENR
43918 | NC 2024 |  | Region V | Albay | 111910 | Cadawag Elementary School | OAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4822746.9 | Not Yet Started | 0 | 2025-02-26 |  | P00875559LZ | 24FO0134 |  | 2024-09-25 | 2024-08-10 | 2024-10-28 | 2024-08-11 | LJDB Construction
43919 | NC 2024 |  | Region V | Albay | 111917 | Moroponros Elementary School | OAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4826745.5 | Ongoing | 0.06 | 2025-02-26 |  | P00875558LZ | 24FO0136 |  | 2024-09-25 | 2024-08-10 | 2024-10-28 | 2024-08-11 | J-NAC Construction and Supply
43920 | NC 2024 |  | Region V | Albay | 111925 | Tapel Elementary School | OAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4820867.56 | Ongoing | 0.41 | 2025-03-08 | 2025-04-25 | P00875556LZ | 24FO0135 |  | 2024-09-25 | 2024-08-10 | 2024-10-28 | 2024-08-11 | 417 LP Construction Corporation
43921 | NC 2024 |  | Region V | Albay | 111954 | Cuyaoyao Elementary School | PIO DURAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4820867.56 | Completed | 1 | 2024-08-03 | 2025-04-15 | P00875555LZ | 24FO0131 |  | 2024-09-20 | 2024-02-10 | 2024-10-16 | 2024-10-28 | 417 LP Construction Corporation
43922 | NC 2024 |  | Region V | Albay | 112007 | Lanigay Elementary School | POLANGUI |  | 1 | 4 | 2STY4CL | BATCH 1 | 24361842.72 |  | 24240033.5 | Ongoing | 0.75 | 2025-03-06 | 2025-05-18 | P00875886LZ | 24FO0116 |  | 2024-06-11 | 2024-07-25 | 2024-07-30 | 2024-08-12 | HKP Construction and Supply
43923 | NC 2024 |  | Region V | Albay | 112008 | Magpanambo Elementary School | POLANGUI |  | 1 | 6 | 2STY6CL | BATCH 1 | 33422579.81 |  | 29543365.71 | Ongoing | 0.6 | 2026-05-01 |  | P00875887LZ | 24FO0126 |  | 2024-08-30 | 2024-11-09 | 2024-09-26 | 2024-07-10 | STEVEN Construction and Supply/417 LP Construction Corporation (JV)
43924 | NC 2024 |  | Region V | Albay | 111990 | Maysua Elementary School | POLANGUI |  | 1 | 4 | 2STY4CL | BATCH 1 | 17701842.72 |  | 17075767.08 | Completed | 1 | 2025-03-21 | 2025-03-21 | P00875884LZ | 24FO0120 |  | 2024-06-27 | 2024-07-26 | 2024-08-19 | 2024-08-28 | BRIX Construction and Supply
43925 | NC 2024 |  | Region V | Albay | 111992 | Napo Elementary School | POLANGUI |  | 1 | 4 | 2STY4CL | BATCH 1 | 22331689.16 |  | 18905300.06 | Ongoing | 0.75 | 2025-03-06 | 2025-04-21 | P00875885LZ | 24FO0117 |  | 2024-06-11 | 2024-07-25 | 2024-07-30 | 2024-08-12 | HKP Construction and Supply
43926 | NC 2024 |  | Region V | Albay | 112014 | Santicon Elementary School | POLANGUI |  | 1 | 12 | 3STY12CL | BATCH 1 | 60065067.48 |  | 57971799.36 | Ongoing | 0.3 | 2026-05-01 |  | P00875888LZ | 24FO0129 |  | 2024-09-05 | 2024-09-17 | 2024-09-26 | 2024-07-10 | HKP Construction and Supply
43927 | NC 2024 |  | Region V | Camarines Norte | 112120 | Melquiades Caldit Elementary School | CAPALONGA |  | 1 | 2 | 1STY2CL | BATCH 1 | 8825948.21 |  | 8518633.14 | Completed | 1 | 2024-10-10 | 2025-01-04 | P00875889LZ | 24FC0064 | 2024-05-15 | 2024-05-28 | 2024-10-06 | 2024-06-27 | 2024-12-07 | JAEJR Electrical, Construction and Supply
43928 | NC 2024 |  | Region V | Camarines Norte | 112129 | Villa Aurora Elementary School | CAPALONGA |  | 1 | 2 | 1STY2CL | GAA 17B | 9000000 |  | 8685596.36 | Completed | 1 | 2024-08-09 | 2025-02-19 | P00875572LZ | 24FC0053 | 2024-03-18 | 2024-01-04 | 2024-04-16 | 2024-09-05 | 2024-05-21 | JAEJR Electrical, Construction and Supply
43929 | NC 2024 |  | Region V | Camarines Norte | 112206 | Daguit Elementary School | LABO |  | 1 | 2 | 1STY2CL | GAA 17B | 7500000 |  | 7235261.67 | Completed | 1 | 2024-08-19 | 2025-02-19 | P00875570LZ | 24FC0050 | 2024-03-18 | 2024-01-04 | 2024-04-16 | 2024-09-05 | 2024-05-21 | JAEJR Electrical, Construction and Supply
43930 | NC 2024 |  | Region V | Camarines Norte | 501259 | Malaya Integrated School | LABO |  | 1 | 4 | 2STY4CL | BATCH 1 | 18380000.35 |  | 17732271.83 | Ongoing | 0.8 | 2024-12-14 |  | P00875890LZ | 24FC0063 | 2024-05-15 | 2024-05-28 | 2024-10-06 | 2024-06-27 | 2024-12-07 | GREAT WALL Engineering
43931 | NC 2024 |  | Region V | Camarines Norte | 112242 | Batobalani Elementary School | PARACALE |  | 1 | 2 | 1STY2CL | GAA 17B | 7500000 |  | 7235261.67 | Completed | 1 | 2024-08-19 | 2025-02-19 | P00875571LZ | 24FC0051 | 2024-03-18 | 2024-01-04 | 2024-04-16 | 2024-09-05 | 2024-05-21 | JAEJR Electrical, Construction and Supply
43932 | NC 2024 |  | Region V | Camarines Norte | 306067 | Dominador G. Mendoza High School | SANTA ELENA |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7718915.46 | Completed | 1 | 2024-08-19 | 2025-02-19 | P00875569LZ | 24FC0052 | 2024-03-18 | 2024-01-04 | 2024-04-16 | 2024-09-05 | 2024-05-21 | JAEJR Electrical, Construction and Supply
43933 | NC 2024 |  | Region V | Camarines Norte | 173009 | Juan A. Amparo Elementary School | SANTA ELENA |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7711722 | Completed | 1 | 2024-08-19 |  | P00875568LZ | 24FC0054 | 2024-03-18 | 2024-01-04 | 2024-04-16 | 2024-09-05 | 2024-05-21 | JAEJR Electrical, Construction and Supply | with major rectification
43934 | NC 2024 |  | Region V | Camarines Norte | 112094 | Mangcamagong Elem. School | BASUD |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9638847.63 | Ongoing | 0.9 | 2025-02-13 |  | P00875660LZ | 24F00407 | 2024-08-16 | 2024-08-29 | 2024-09-13 | 2024-10-15 | 2024-05-11 | 128 DRAGON CONSTRUCTION AND SUPPLIES | slow progress
43935 | NC 2024 |  | Region V | Camarines Norte | 112131 | Alawihao Elementary School | DAET (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19281778.74 | Ongoing | 0.8 | 2025-03-27 |  | P00875658LZ | 24F00405 | 2024-08-16 | 2024-08-29 | 2024-09-13 | 2024-10-15 | 2024-05-11 | 128 DRAGON CONSTRUCTION AND SUPPLIES | slow progress
43936 | NC 2024 |  | Region V | Camarines Norte | 112133 | Bagasbas Elementary School | DAET (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | waiting for approval of modification
43937 | NC 2024 |  | Region V | Camarines Norte | 112134 | Daet Elementary School | DAET (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  | 38603181.4 | Ongoing | 0.6 | 2025-05-26 |  | P00875654LZ | 24F00406 | 2024-08-16 | 2024-08-29 | 2024-09-13 | 2024-10-15 | 2024-05-11 | WIZARD CONCRETE SOLUTIONS AND CONSTRUCTION CORP. | slow progress
43938 | NC 2024 |  | Region V | Camarines Norte | 112136 | Mantagbac Elementary School | DAET (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | waiting for approval of modification
43939 | NC 2024 |  | Region V | Camarines Norte | 112235 | Mercedes Elementary School | MERCEDES |  | 1 | 10 | 2STY4CL & 2STY6CL | BATCH 1 | 46288293.13 |  | 44774557.11 | Ongoing | 0.9 | 2025-04-16 |  | P00875891LZ | 24F00269 | 2024-11-03 | 2024-03-25 | 2024-12-04 | 2024-05-22 | 2024-05-31 | EUS CONSTRUCTION | slow progress
43940 | NC 2024 |  | Region V | Camarines Norte | 112296 | Talisay Elementary School | TALISAY |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0 | [10 empty] | waiting for approval of modification
43941 | NC 2024 |  | Region V | Camarines Norte | 112316 | Vinzons Pilot Elementary School | VINZONS |  | 1 | 5 | 2STY5CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0 | [10 empty] | waiting for approval of modification
43942 | NC 2024 |  | Region V | Camarines Sur | 112586 | Sinuknipan Elementary School | DEL GALLEGO |  | 1 | 2 | 2STY2CL | GAA 17B | 8000000 |  | 7825351.5 | Completed | 1 | 2024-11-22 |  | P00875577LZ-CW1 | 24FD0071 |  | 2024-05-24 | 2024-05-06 | 2024-06-14 | 2024-06-26 | MPIRE NINE CONST.
43943 | NC 2024 |  | Region V | Camarines Sur | 301961 | Colacling National High School | LUPI |  | 1 | 2 | 2STY2CL | GAA 17B | 8000000 |  | 7818983.6 | Completed | 1 | 2024-11-22 |  | P00875576LZ-CW1 | 24FD0069 |  | 2024-05-24 | 2024-05-06 | 2024-06-14 | 2024-06-26 | MPIRE NINE CONST.
43944 | NC 2024 |  | Region V | Camarines Sur | 112957 | Cawayan ES | RAGAY |  | 1 | 2 | 2STY2CL | GAA 17B | 8000000 |  | 7838883.28 | Completed | 1 | 2024-11-22 |  | P00875575LZ-CW1 | 24FD0070 |  | 2024-05-24 | 2024-05-06 | 2024-06-14 | 2024-06-26 | PRIMARCH CONST
43945 | NC 2024 |  | Region V | Camarines Sur | 113057 | Calagbangan ES | SIPOCOT |  | 1 | 2 | 2STY2CL | GAA 17B | 8000000 |  | 7815236.8 | Completed | 1 | 2024-11-22 |  | P00875574LZ-CW1 | 24FD0068 |  | 2024-05-24 | 2024-05-06 | 2024-06-14 | 2024-06-26 | SHLA CONST.
43946 | NC 2024 |  | Region V | Camarines Sur | 113087 | Lubigan Sr. ES | SIPOCOT |  | 1 | 2 | 2STY2CL | GAA 17B | 8000000 |  | 7952230.77 | Completed | 1 | 2024-11-22 |  | P00875573LZ-CW1 | 24FD0067 |  | 2024-05-24 | 2024-05-06 | 2024-06-14 | 2024-06-26 | DREAM BUILDERS
43947 | NC 2024 |  | Region V | Camarines Sur | 302047 | Sipocot National High School | SIPOCOT |  | 1 | 4 | 2STY4CL | BATCH 2 | 20000000 |  | 19593156.69 | Ongoing | 0.83 | 2025-05-25 |  | P00876032LZ-CW1 | 24FD0095 | 2024-11-13 | 2024-11-20 | 2024-03-12 | 2024-10-12 | 2024-12-27 | BOLALIN EO CONSTRUCTION
43948 | NC 2024 |  | Region V | Camarines Sur | 113075 | Yabo - Salanda ES | SIPOCOT |  | 1 | 3 | 1STY3CL | BATCH 1 | 7242922 |  | 7098443.12 | Ongoing | 0.55 | 2025-06-25 |  | P00875892LZ-CW1 | 24FD0104 |  | 2025-07-02 | 2025-02-19 |  | 2025-02-26 | PREMIUM ROCK | 120
43949 | NC 2024 |  | Region V | Camarines Sur | 301994 | Mambulo Nuevo High School | LIBMANAN |  | 1 | 8 | CONSTRUCTION OF 8-CLASSROOMS | GAA 17B | 40000000 |  | 39405940.59 | Ongoing | 0.45 | 2024-11-18 |  | P00875578LZ-CW1 | 24FE0049 | 2024-03-15 | 2024-03-22 | 2024-04-04 | 2024-12-04 | 2024-04-22 | SCHEIRMAN CONST.
43950 | NC 2024 |  | Region V | Camarines Sur | 112867 | Burabod ES | PAMPLONA |  | 1 | 8 | CONSTRUCTION OF 8-CLASSROOMS | GAA 17B | 40000000 |  | 39405940.59 | Ongoing | 0.2 | 2024-11-18 |  | P0087559LZ-CW1 | 24FE0048 | 2024-03-15 | 2024-03-22 | 2024-04-04 | 2024-12-04 | 2024-04-22 | SCHEIRMAN CONST.
43951 | NC 2024 |  | Region V | Camarines Sur | 500158 | Antipolo Heights Integrated School | PASACAO |  | 1 | 8 | CONSTRUCTION OF 8-CLASSROOMS | GAA 17B | 40000000 |  | 39405940.59 | Ongoing | 0.15 | 2024-11-18 |  | P00875580LZ-CW1 | 24FE0047 | 2024-03-15 | 2024-03-22 | 2024-04-04 | 2024-12-04 | 2024-04-22 | SCHEIRMAN CONST.
43952 | NC 2024 |  | Region V | Camarines Sur | 112480 | Ilihan CS | CALABANGA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4920822.5 | Completed | 1 | 2024-12-12 | 2025-01-22 | P00875585LZ | 24FF0087 |  | 2024-09-05 | 2024-05-21 | 2024-06-27 | 2024-10-07 | MEGA-ANT BUILDERS
43953 | NC 2024 |  | Region V | Camarines Sur | 112499 | Dugcal ES | CAMALIGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4918027.5 | Completed | 1 | 2024-12-12 | 2025-01-28 | P00875583LZ | 24FF0087 |  | 2024-09-05 | 2024-05-21 | 2024-06-27 | 2024-10-07 | MEGA-ANT BUILDERS
43954 | NC 2024 |  | Region V | Camarines Sur | 112515 | San Francisco Elementary School | CANAMAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4917613.36 | Completed | 1 | 2024-12-12 | 2025-01-28 | P00875581LZ | 24FF0087 |  | 2024-09-05 | 2024-05-21 | 2024-06-27 | 2024-10-07 | MEGA-ANT BUILDERS
43955 | NC 2024 |  | Region V | Camarines Sur | 500157 | Ponong Integrated School | MAGARAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4855585 | Completed | 1 | 2024-07-11 | 2025-01-28 | P00875582LZ | 24FF0075 |  | 2024-11-04 | 2024-04-23 | 2024-06-25 | 2024-05-07 | MRBAY CONSTRUCTION
43956 | NC 2024 |  | Region V | Camarines Sur | 112859 | Ocampo Central School | OCAMPO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4887700 | Completed | 1 | 2024-08-11 | 2024-01-12 | P00875586LZ | 24FF0079 |  | 2024-12-04 | 2024-04-24 | 2024-06-25 | 2024-08-07 | PHILMANNA CONSTRUCTION & SUPPLY
43957 | NC 2024 |  | Region V | Camarines Sur | 112932 | Pili Central School | PILI (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4918636.64 | Completed | 1 | 2024-12-12 | 2025-01-22 | P00875584LZ | 24FF0087 |  | 2024-09-05 | 2024-05-21 | 2024-06-27 | 2024-10-07 | MEGA-ANT BUILDERS
43958 | NC 2024 |  | Region V | Camarines Sur | 309716 | San Jose Pili National High School | PILI (Capital) |  | 1 | 15 | Construction of School Building | BATCH 1 | 38286473 |  | 38190756.82 | Ongoing | 0.2
43959 | NC 2024 |  | Region V | Camarines Sur |  | BALIGUIAN HIGH SCHOOL | PRESENTACION (PARUBCAN) |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 9281159.49 | Completed | 1 | 2024-08-26 | 2024-11-01 | P00875590LZ-CW1 | 24FG0084 | 2024-03-18 | 2024-03-26 | 2024-10-04 | 2024-04-22 | 2024-04-29 | J.C. NIETO
43960 | NC 2024 |  | Region V | Camarines Sur | 112897 | Tanawan Elementary School | PRESENTACION (PARUBCAN) |  | 1 | 2 | 1STY2CL | GAA 17B | 7500000 |  | 7313250 | Completed | 1 | 2024-08-26 | 2024-08-01 | P00875591LZ-CW1 |  | 2024-03-18 | 2024-03-26 | 2024-10-04 | 2024-04-22 | 2024-04-29 | S&RV CONST
43961 | NC 2024 |  | Region V | Camarines Sur | 309715 | Nato National High School | SAGÑAY |  | 1 | 3 | 1STY3CL | GAA 17B | 9500000 |  | 7809830.52 | Completed | 1 | 2024-08-26 |  | P00875589LZ-CW1 | 24FG0085 | 2024-03-18 | 2024-03-26 | 2024-10-04 | 2024-04-22 | 2024-04-29 | J.C. NIETO
43962 | NC 2024 |  | Region V | Camarines Sur | 302045 | Sibaguan Agro-Industrial High School | SAGÑAY |  | 1 | 8 | 2STY8CL | BATCH 2 | 32000000 |  | 31203200 | Ongoing | 0.665 | 2025-01-07 |  | P00876033LZ-CW1 | 24FG0134 |  | 2024-11-20 | 2024-05-12 | 2024-12-23 | 2024-12-27 | ZKR Construction and Supply | with 3 time extensions for approval
43963 | NC 2024 |  | Region V | Camarines Sur | 113025 | CLEMENTE PEÑA ELEMENTARY SCHOOL | SAN JOSE |  | 1 | 2 | 1STY2CL | GAA 17B | 7500000 |  | 7272988.11 | Completed | 1 | 2024-08-26 |  | P00875593LZ-CW1 | 24FG0086 | 2024-03-18 | 2024-03-26 | 2024-10-04 | 2024-04-22 | 2024-04-29 | JC NIETO
43964 | NC 2024 |  | Region V | Camarines Sur | 309721 | Huyonhuyon High School | TIGAON |  | 1 | 2 | 1STY2CL | GAA 17B | 7500000 |  | 7201312.5 | Completed | 1 | 2024-08-26 | 2025-01-03 | P00875592LZ-CW1 | 24FG0087 | 2024-03-18 | 2024-03-26 | 2024-10-04 | 2024-04-22 | 2024-04-29 | BESTECH CONST
43965 | NC 2024 |  | Region V | Camarines Sur | 305483 | Buhi High School | BUHI |  | 1 | 8 | CONSTRUCTION OF 8-CLASSROOMS | GAA 17B | 40000000 |  | 38963440.83 | Ongoing | 0.8 |  |  | P00875595LZ-CWI | 24FN0061 | 2024-06-25 | 2024-02-07 | 2024-07-15 | 2024-07-22 | 2024-07-26 | C.T. Leoncio Const. and Tading
43966 | NC 2024 |  | Region V | Camarines Sur | 302001 | Nabua National High School | NABUA |  | 1 | 8 | CONSTRUCTION OF 8-CLASSROOMS | GAA 17B | 40000000 |  | 38962440.83 | Ongoing | 0.5 |  |  | P00875594LZ-CW1 | 24FN0061 | 2024-06-25 | 2024-02-07 | 2024-07-15 | 2024-07-22 | 2024-07-26 | C.T. Leoncio Const. and Tading
43967 | NC 2024 |  | Region V | Catanduanes | 302084 | Calatagan High School | Virac (Capital) |  | 1 | 17 | Completion of 4STY 28CL - 2unit (7 x 18) Science Lab., 2unit (7 x 18) ICT Lab, 7unit (7 x 18)Regular Workshop & 6 CL (7x9) SHS | BATCH 1 | 16490113.16 |  | 14037412.21 | Ongoing | 0.41 | 2024-06-04
43968 | NC 2024 |  | Region V | Catanduanes | 113165 | Suchan ES | BAGAMANOC |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 9072385.32 | Ongoing | 0.58 | 2025-03-13
43969 | NC 2024 |  | Region V | Catanduanes |  | SITIO BARRIO SITE ELEMENTARY SCHOOL | BATO |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 8095666.7 | Ongoing | 0.52 | 2025-03-25
43970 | NC 2024 |  | Region V | Catanduanes |  | BALDOC INTEGRATED SCHOOL | PANDAN |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 9431768.3 | Ongoing | 0.74 | 2025-11-03
43971 | NC 2024 |  | Region V | Catanduanes | 113275 | Codon ES | SAN ANDRES (CALOLBON) |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 9367731.49 | Ongoing | 0.62 | 2025-05-03
43972 | NC 2024 |  | Region V | Catanduanes | 502056 | Pagsangahan Integrated School | SAN MIGUEL |  | 1 | 8 | Construction of School Building | BATCH 1 | 20000000 |  | 17797499.98 | Ongoing | 0.06 | 2025-12-09
43973 | NC 2024 |  | Region V | Legaspi City | 114476 | Buraguis ES | LEGAZPI CITY (Capital) |  | 1 | 4 | 1STY4CL | GAA 17B | 20000000 |  | 19281571.55 | Ongoing | 0.3 | 2025-05-28 |  | 24FB0252 | 24FB0252 |  | 2024-11-29 | 2024-11-12 | 2025-09-01 | 2025-01-29 | FIRST OMB CONSTRUCTION AND DEVELOPMENT CORP. | NONE
43974 | NC 2024 |  | Region V | Legaspi City | 114472 | Estanza ES | LEGAZPI CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 9669903.12 | Ongoing | 0.05 | 2025-08-13 |  | 24FB0294 | 24FB0294 |  | 2025-07-03 | 2025-03-20 | 2025-03-27 | 2025-10-04 | HI-TONE CONSTRUCTION AND DEVELOPMENT CORPORATION | NONE
43975 | NC 2024 |  | Region V | Legaspi City | 302262 | Gogon High School | LEGAZPI CITY (Capital) |  | 1 | 12 | 4STY12CL | GAA 17B | 60000000 |  | 58146771.16 | Not Yet Started | 0 |  |  | 24FB0250 | 24FB0250 |  | 2024-12-27 | 2024-12-11 |  |  | GRELIPS CONSTRUCTION & DEVELOPMENT/HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (JV) | under procurement (Bid-out) , Short of Award, with Request for Modification by DPWH from 4sty12CL to 3sty9CL
43976 | NC 2024 |  | Region V | Legaspi City | 302259 | Homapon High School | LEGAZPI CITY (Capital) |  | 1 | 8 | 2STY8CL | GAA 17B | 40000000 |  | 38604506.2 | Ongoing | 0.05 | 2025-09-27 |  | 24FB0254 | 24FB0254 |  | 2024-12-27 | 2025-05-02 | 2025-02-24 | 2025-11-03 | STEVEN CONSTRUCTION AND SUPPLY/JEJAN CONSTRUCTION AND SUPPLY (JV) | NONE
43977 | NC 2024 |  | Region V | Legaspi City | 114479 | Ibalon Central School | LEGAZPI CITY (Capital) |  | 1 | 20 | 4STY20CL | GAA 17B | 150000000 |  | 127718406.2 | Ongoing | 0.05 | 2026-10-01 |  | 24FB0293 | 24FB0293 |  | 2025-07-03 | 2025-03-20 | 2025-03-27 | 2025-10-04 | HI-TONE CONSTRUCTION AND DEVELOPMENT CORPORATION | NONE
43978 | NC 2024 |  | Region V | Legaspi City | 114464 | Pawa ES | LEGAZPI CITY (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19301506.22 | Ongoing | 0.15 | 2025-03-26 |  | 24FB0245 | 24FB0245 |  | 2024-04-10 | 2024-10-16 | 2024-06-11 | 2024-11-21 | FIRST OMB CONSTRUCTION AND DEVELOPMENT CORP. | NONE
43979 | NC 2024 |  | Region V | Legaspi City | 302263 | Pawa High School | LEGAZPI CITY (Capital) |  | 1 | 8 | 2STY8CL | GAA 17B | 40000000 |  | 38604506.2 | Ongoing | 0.2 | 2025-09-06 |  | 24FB0246 | 24FB0246 |  | 2024-04-10 | 2024-10-16 | 2024-06-11 | 2024-11-21 | FIRST OMB CONSTRUCTION AND DEVELOPMENT CORP. | NONE
43980 | NC 2024 |  | Region V | Legaspi City | 114483 | Puro Elementary School | LEGAZPI CITY (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  | 38604273.39 | Ongoing | 0.05 | 2025-09-09 |  | 24FB0255 | 24FB0255 |  | 2024-12-27 | 2025-08-01 | 2025-01-22 | 2025-06-02 | MARCIVAN CONSTRUCTION AND SUPPLY | NONE
43981 | NC 2024 |  | Region V | Legaspi City | 114493 | Rawis ES | LEGAZPI CITY (Capital) |  | 1 | 8 | 2STY8CL | GAA 17B | 40000000 |  | 38604506.2 | Ongoing | 0.15 | 2025-08-25 |  | 24FB0256 | 24FB0256 |  | 2024-12-27 | 2025-08-01 | 2025-01-22 | 2025-06-02 | HI-TONE CONSTRUCTION AND DEVELOPMENT CORPORATION | NONE
43982 | NC 2024 |  | Region V | Legaspi City | 114473 | San Francisco ES | LEGAZPI CITY (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19410387.9 | Ongoing | 0.1 | 2025-11-06 |  | 24FB0257 | 24FB0257 |  | 2024-12-27 | 2025-08-01 | 2025-01-22 | 2025-06-02 | HI-TONE CONSTRUCTION AND DEVELOPMENT CORPORATION | NONE
43983 | NC 2024 |  | Region V | Ligao City | 321702 | Maonon High School | CITY OF LIGAO |  | 1 | 5 | 2STY4CL, 1STY1CL (UNIQUE WORKSHOP) | BATCH 1 | 24000000 |  | 23131107.93 | Ongoing | 0.52 | 2025-05-31 |  | 24FO0124 | 24FO0124 |  |  |  |  | 2024-10-14 | Sulvir Engineering & Construction | Formally requested key project data from DPWH. However, timeline data was omitted. DPWH has since informed us that these omitted data will be provided "to follow". Also, the DPWH informed the SDO that this project has an approved time extension.
43984 | NC 2024 |  | Region V | Masbate | 302126 | Tito R. Espinosa Memorial National Agricultural School | CLAVERIA |  | 1 | 4 | 2STY4CL | GAA 17B | 16000000 |  | 15444705.19 | Completed | 1 | 2024-03-11 | 2025-01-31 | P00875601LZ-CW1 | 24FM0045 | 2024-03-22 | 2024-01-04 | 2024-04-16 | 2024-04-24 | 2024-03-05 | 3R3M CONSTRUCTION AND SUPPLY
43985 | NC 2024 |  | Region V | Masbate | 309936 | Amado E. Lazaro High School | SAN PASCUAL |  | 1 | 6 | 2STY6CL | GAA 17B | 24000000 |  | 23401770.58 | Ongoing | 0.9 | 2025-01-14 |  | P00875600LZ-CW1 | 24FM0046 | 2024-03-22 | 2024-01-04 | 2024-04-16 | 2024-04-24 | 2024-03-05 | TOUGHCHIC CONSTRUCTION
43986 | NC 2024 |  | Region V | Masbate | 502252 | Victory Integrated School | BALUD |  | 1 | 3 | 1STY3CL | GAA 17B | 9500000 |  |  | Not Yet Started | 0
43987 | NC 2024 |  | Region V | Masbate | 113641 | Cabitan Central School | MANDAON |  | 1 | 4 | 2STY4CL | BATCH 1 | 16650617.07 |  |  | Not Yet Started | 0
43988 | NC 2024 |  | Region V | Masbate | 309949 | Revil-Bajar National High School | MILAGROS |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  |  | Not Yet Started | 0
43989 | NC 2024 |  | Region V | Masbate | 309941 | Cristeta Bagano Memorial High School | MOBO |  | 1 | 3 | 1STY3CL | GAA 17B | 9000000 |  |  | Not Yet Started | 0
43990 | NC 2024 |  | Region V | Masbate | 113515 | Eulogio C. Adoptante ES | CATAINGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 7500000 |  | 7481250 | Completed | 1 | 2024-10-11
43991 | NC 2024 |  | Region V | Masbate | 309903 | Arriesgado-Sevilleno High School | PLACER |  | 1 | 4 | 2UNITS 1STY2CL | BATCH 1 | 15736989.05 |  | 15697646.57 | Completed | 1 | 2024-11-28
43992 | NC 2024 |  | Region V | Masbate | 113941 | Aurora ES | USON |  | 1 | 2 | 1STY2CL | GAA 17B | 7500000 |  | 7481250 | Completed | 1 | 2024-11-13
43993 | NC 2024 |  | Region V | Masbate | 501640 | Centro Integrated School | USON |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9975000 | Completed | 1 | 2024-12-11
43994 | NC 2024 |  | Region V | Masbate | 113947 | Del Carmen ES | USON |  | 1 | 2 | 1STY2CL | GAA 17B | 7500000 |  | 7481250 | Completed | 1 | 2024-07-10
43995 | NC 2024 |  | Region V | Masbate | 113953 | Nabuhay ES | USON |  | 1 | 2 | 1STY2CL | GAA 17B | 7500000 |  | 7481250 | Completed | 1 | 2024-07-10
43996 | NC 2024 |  | Region V | Masbate City | 113680 | Julian V. Antonio Elementary School | CITY OF MASBATE (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 15500000 |  | 15110770.49 | Completed | 1 | 2025-06-03 | 2025-06-03 |  | 24FI0072 | 2024-05-20 | 2024-05-27 | 2024-10-06 | 2024-06-28 | 2024-05-07 | 3R3M Construction and Supply
43997 | NC 2024 |  | Region V | Naga City | 114497 | Calauag Elementary School | NAGA CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 |  |  | 24FF0082 | 24FF0082 | [6 empty] | Turned over
43998 | NC 2024 |  | Region V | Naga City | 114501 | Naga Central School II | Naga City |  | 1 | 4 | 2STY4CL | BATCH 1 | 22002405.9 |  |  | Ongoing | 0.7 |  |  | 24FF0095 | 24FF0095 | [6 empty] | ON-GOING
43999 | NC 2024 |  | Region V | Naga City | 176505 | SAN RAFAEL ELEMENTARY SCHOOL SPED CENTER | NAGA CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | Reverted
44000 | NC 2024 |  | Region V | Sorsogon | 114081 | Cagdagat ES | CASIGURAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4290437.32 | Ongoing | 0.8 | 2025-11-08 |  | P00875611LZ-CW1 | 24FK0075 |  | 2024-07-18 | 2024-08-01 | 2024-08-22 |  | MUNTOPAR BUILDERS CORPORATION
44001 | NC 2024 |  | Region V | Sorsogon | 114083 | Casiguran CS | CASIGURAN |  | 1 | 12 | 2STY12CL | GAA 17B | 63600000 |  | 62172175.91 | Ongoing | 0.6 | 2025-01-04 |  | P00875626LZ-CW1 | 24FK0095 |  | 2024-08-23 |  |  | 2024-10-03 | MUNTOPAR BUILDERS CORPORATION / FULLEROS BOTOX BUILDERS AND DESIGN (JV)
44002 | NC 2024 |  | Region V | Sorsogon | 114088 | Mabini ES | CASIGURAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4290437.32 | Ongoing | 0.75 | 2025-11-08 |  | P00875612LZ-CW1 | 24FK0075 |  | 2024-07-18 | 2024-08-01 | 2024-08-22 |  | MUNTOPAR BUILDERS CORPORATION
44003 | NC 2024 |  | Region V | Sorsogon | 114122 | Cumadcad CS | CASTILLA |  | 1 | 12 | 2STY12CL | GAA 17B | 63600000 |  | 62331575.06 | Ongoing | 0.5 | 2025-01-04 |  | P00875625LZ-CW1 | 24FK0087 |  | 2024-08-19 |  |  | 2024-10-03 | Al Nino Construction Corporation
44004 | NC 2024 |  | Region V | Sorsogon |  | BINISITAHAN ELEMENTARY SCHOOL | DONSOL |  | 1 | 12 | 2STY12CL | GAA 17B | 63600000 |  | 61379478.66 | Ongoing | 0.1 | 2025-01-04 |  | P00875631LZ-CW1 | 24FK0089 |  | 2024-08-20 |  |  | 2024-10-03 | TR Construction Corporation/KM88 Construction Inc. (JV)
44005 | NC 2024 |  | Region V | Sorsogon | 114159 | Cabugao ES | DONSOL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4290439.9 | Ongoing | 0.8 | 2025-11-08 |  | P00875613LZ-CW1 | 24FK0075 |  | 2024-07-18 | 2024-08-01 | 2024-08-22 |  | MUNTOPAR BUILDERS CORPORATION
44006 | NC 2024 |  | Region V | Sorsogon |  | DONSOL HIGH SCHOOL | DONSOL |  | 1 | 12 | 2STY12CL | GAA 17B | 63600000 |  | 61380991.62 | Ongoing | 0.1 | 2025-01-04 |  | P00875629LZ-CW1 | 24FK0093 |  | 2024-08-22 |  |  | 2024-10-03 | TR Construction Corporation/KM88 Construction Inc. (JV)
44007 | NC 2024 |  | Region V | Sorsogon | 114275 | Biga ES | MAGALLANES |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4290439.9 | Ongoing | 0.45 | 2025-11-08 |  | P00875614LZ-CW1 | 24FK0075 |  | 2024-07-18 | 2024-08-01 | 2024-08-22 |  | MUNTOPAR BUILDERS CORPORATION
44008 | NC 2024 |  | Region V | Sorsogon | 114281 | Magallanes North CS | MAGALLANES |  | 1 | 12 | 2STY12CL | GAA 17B | 63600000 |  | 62332762.35 | Ongoing | 0.35 | 2025-01-04 |  | P00875627LZ-CW1 | 24FK0096 |  | 2024-08-23 |  |  | 2024-10-03 | MUNTOPAR BUILDERS CORPORATION
44009 | NC 2024 |  | Region V | Sorsogon | 114356 | Pilar I Central School | PILAR |  | 1 | 12 | 2STY12CL | GAA 17B | 63600000 |  | 62330293.11 | Ongoing | 0.35 | 2025-01-04 |  | P00875630LZ-CW1 | 24FK0092 |  | 2024-08-20 |  |  | 2024-10-03 | Al Nino Construction Corporation | With tree cutting issue
44010 | NC 2024 |  | Region V | Sorsogon | 113982 | Barcelona Central School | BARCELONA |  | 1 | 12 | 2STY12CL | GAA 17B | 63600000 |  | 19301506.22 | Ongoing | 0.8 | 2025-12-04 |  | P00875632LZ-CW1 | 24FL0100 | 2024-05-29 | 2024-05-20 | 2024-06-18 | 2024-03-07 | 2024-07-15 | Muntopar Builders Corporation/ T. Las Inc. (JV)
44011 | NC 2024 |  | Region V | Sorsogon | 113992 | San Antonio Elemlentary School | BARCELONA |  | 1 | 2 | 1STY2CL | GAA 17B | 6040000 |  | 5889606.2 | Ongoing | 0.95 | 2024-01-11 |  | P00875618LZ-CW1 | 24FL0071 | 2024-05-04 | 2024-03-04 | 2024-04-25 | 2024-05-24 | 2024-03-06 | RMH Construction & Supply
44012 | NC 2024 |  | Region V | Sorsogon | 114003 | Bulan North Central School-A | BULAN |  | 1 | 12 | 2STY12CL | GAA 17B | 63600000 |  | 62016359.99 | Ongoing | 0.85 | 2025-03-21 |  | P00875633LZ-CW1 | 24FL0101 | 2024-05-16 | 2024-05-13 | 2024-05-06 | 2024-06-18 | 2024-06-24 | Muntopar Builders Corp.
44013 | NC 2024 |  | Region V | Sorsogon | 310001 | Cadandanan National High School | BULAN |  | 1 | 4 | 2STY4CL | BATCH 1 | 20668176.31 |  | 20243527.9 | Ongoing | 0.6 | 2025-04-14 |  | P00875901LZ-CW1 | 24FL0105 | 2024-07-18 | 2024-03-04 | 2024-07-08 | 2024-05-09 | 2024-09-16 | Muntopar Builders Corp.
44014 | NC 2024 |  | Region V | Sorsogon | 502339 | Calpi Integrated School | BULAN |  | 1 | 3 | 1STY3CL | GAA 17B | 9037000 |  | 8805677.99 | Ongoing | 0.9 | 2024-01-11 |  | P00875619LZ-CW1 | 24FL0071 | 2024-05-04 | 2024-03-04 | 2024-04-25 | 2024-05-24 | 2024-03-06 | RMH Construction & Supply
44015 | NC 2024 |  | Region V | Sorsogon | 302210 | Faustino G. Glua High School | BULAN |  | 1 | 10 | 2STY10CL (INCLUDING ICT & SCI. LAB.) | BATCH 1 | 36142581.44 |  | 35422440.5 | Ongoing | 0.4 | 2025-04-14 |  | P00875900LZ-CW1 | 24FL0105 | 2024-07-18 | 2024-07-15 | 2024-07-08 | 2024-05-09 | 2024-09-16 | Muntopar Builders Corp.
44016 | NC 2024 |  | Region V | Sorsogon | 114059 | Bulusan CS | BULUSAN |  | 1 | 12 | 2STY12CL | GAA 17B | 63600000 |  | 62016359.31 | Ongoing | 0.75 | 2025-04-24 |  | P00875634LZ-CW1 | 24FL0099 | 2024-05-29 | 2024-05-24 | 2024-06-24 | 2024-07-17 | 2024-07-26 | Fulleros Botox Builders and Design
44017 | NC 2024 |  | Region V | Sorsogon | 114073 | San Rafael ES | BULUSAN |  | 1 | 2 | 1STY2CL | GAA 17B | 6040000 |  | 5889613.54 | Completed | 1 | 2024-01-11 | 2025-12-02 | P00875620LZ-CW1 | 24FL0071 | 2024-05-04 | 2024-03-04 | 2024-04-25 | 2024-05-24 | 2024-03-06 | RMH Construction & Supply
44018 | NC 2024 |  | Region V | Sorsogon | 114192 | Gubat North CS | GUBAT |  | 1 | 12 | 2STY12CL | GAA 17B | 63600000 |  | 62054620.62 | Ongoing | 0.9 | 2025-03-21 |  | P00875636LZ-CW1 | 24FL0102 | 2024-05-16 | 2024-05-13 | 2024-05-06 | 2024-06-18 | 2024-06-24 | Legazpi Premium Dev't. Corp.
44019 | NC 2024 |  | Region V | Sorsogon | 114211 | Gubat South CS | GUBAT |  | 1 | 12 | 2STY12CL | GAA 17B | 63600000 |  | 62016360 | Ongoing | 0.75 | 2025-03-21 |  | P00875635LZ-CW1 | 24FL0103 | 2024-05-16 | 2024-05-13 | 2024-05-06 | 2024-06-18 | 2024-06-25 | Muntopar Builders Corp.
44020 | NC 2024 |  | Region V | Sorsogon | 114197 | Paco ES | GUBAT |  | 1 | 2 | 1STY2CL | GAA 17B | 6040000 |  | 5889604.42 | Completed | 1 | 2024-01-11 | 2025-12-02 | P00875621LZ-CW1 | 24FL0071 | 2024-05-04 | 2024-03-04 | 2024-04-25 | 2024-05-24 | 2024-03-06 | RMH Construction & Supply
44021 | NC 2024 |  | Region V | Sorsogon | 114227 | Bulawan ES | IROSIN |  | 1 | 2 | 1STY2CL | GAA 17B | 6438000 |  | 6277695.62 | Ongoing | 0.8 | 2024-01-11 |  | P00875622LZ-CW1 | 24FL0071 | 2024-05-04 | 2024-03-04 | 2024-04-25 | 2024-05-24 | 2024-03-06 | RMH Construction & Supply
44022 | NC 2024 |  | Region V | Sorsogon | 114251 | Bacolod ES | JUBAN |  | 1 | 2 | 1STY2CL | GAA 17B | 6405000 |  | 6245521.31 | Completed | 1 | 2024-01-11 | 2025-12-02 | P00875623LZ-CW1 | 24FL0071 | 2024-05-04 | 2024-03-04 | 2024-04-25 | 2024-05-24 | 2024-03-06 | RMH Construction & Supply
44023 | NC 2024 |  | Region V | Sorsogon | 302187 | Juban High School | JUBAN |  | 1 | 12 | 3STY12CL | GAA 17B | 40000000 |  | 39043411.75 | Ongoing | 0.85 | 2025-12-02 |  | P00875624LZ-CW1 | 24FL0097 | 2024-03-05 | 2024-04-29 | 2024-05-23 | 2024-07-06 | 2025-12-02 | Fulleros Botox Builders and Design
44024 | NC 2024 |  | Region V | Sorsogon | 501782 | Sisigon Integrated School | MATNOG |  | 1 | 10 | 3STY15CL (Including ICT, Sci. Lab. & Regular Workshop) Phase I 10CL | BATCH 1 | 47708608.66 |  | 46520664.32 | Ongoing | 0.25 | 2025-07-04 |  | P00875902LZ-CW1 | 24FL0106 | 2024-07-18 | 2024-07-15 | 2024-07-08 | 2024-08-29 | 2024-09-09 | Muntopar Builders Corp.
44025 | NC 2024 |  | Region V | Sorsogon City | 114520 | Bacon East Central School | CITY OF SORSOGON (Capital) |  | 1 | 12 | 2STY12CL | GAA 17B | 63600000 |  | 62016329.51 | Ongoing | 0.94 | 2025-06-30 |  | P00875628LZ-CW1 | 24FK0094 | 2024-08-15 | 2024-08-22 | 2024-09-05 | 2024-09-23 | 2024-10-03 | Muntopar Builders Corporation | with Contract Time Extension (90cd)
44026 | NC 2024 |  | Region V | Sorsogon City | 114558 | Melecio J. Larosa Elementary School | CITY OF SORSOGON (Capital) |  | 1 | 8 | 2STY8CL | GAA 17B | 20000000 |  | 19302823.05 | Ongoing | 0.3 | 2025-09-30 |  | P00875617LZ-CW1 | 24FK0105-Repost | 2025-01-09 | 2025-01-16 | 2025-01-28 | 2025-12-02 | 2025-02-24 | Ajan Jeada Inc. | approved from 2sty-8classroom to 2sty-6 classroom
44027 | NC 2024 |  | Region V | Sorsogon City | 114559 | Our Lady's Village Elementary School | CITY OF SORSOGON (Capital) |  | 1 | 8 | 2STY8CL | GAA 17B | 20000000 |  | 19302823.67 | Ongoing | 0.31 | 2025-09-30 |  | P00875615LZ-CW1 | 24FK0105-Repost | 2025-01-09 | 2025-01-16 | 2025-01-28 | 2025-12-02 | 2025-02-24 | Ajan Jeada Inc. | approved from 2sty-8classroom to 2sty-6 classroom
44028 | NC 2024 |  | Region V | Sorsogon City | 114560 | Rosa T. Arellano Elementary School | CITY OF SORSOGON (Capital) |  | 1 | 8 | 2STY8CL | GAA 17B | 20000000 |  | 19302823.05 | Ongoing | 0.31 | 2025-09-30 |  | P00875616LZ-CW1 | 24FK0105-Repost | 2025-01-09 | 2025-01-16 | 2025-01-28 | 2025-12-02 | 2025-02-24 | Ajan Jeada Inc. | approved from 2sty-8classroom to 2sty-6 classroom
44029 | NC 2024 |  | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO |  | 1 | 16 | 2STY16CL | GAA 17B | 40000000 |  | 38605871.05 | Not Yet Started | 0 |  |  |  | 24FA0065 | 2025-03-24 | 2025-02-04 | 2025-02-05 | 2025-05-26 | 2025-05-06 | SANRHO BUILDERS, INC | Design changed to 2STY10CL
44030 | NC 2024 |  | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO |  |  | 12 | 4STY12CL | GAA 17B | 30000000 |  | 29253789 | Not Yet Started | 0 |  |  |  | 24FA0066 | 2025-03-24 | 2025-03-04 | 2025-06-05 | 2025-05-26 | 2025-05-06 | OMEGA CONTRACTING AND DEVELOPMENT CORP. | Design changed to 2STY8CL

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.