## Sheet1
INDEX (DO NOT MODIFY) | PROGRAM-YEAR | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | BATCH | TOTAL PROJECT ALLOCATION | TOTAL PROJECT COST | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
1253 | NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 234005 | Bulo ES | Tanjay City | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2547363.8262 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-12 | 070314S00188 | 14HK0039 | 2014-11-06 | 2014-11-18 | 2014-11-19 | 2014-12-22 | 2014-12-29 | RICHFIELD BUILDERS
1254 | NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 120407 | Abante ES | PAMPLONA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | REVERTED | 0 |  |  | 070314S00020 | 14HK0037 | 2014-08-07 | 2014-08-22 | 2014-11-19 | 2014-12-02 |  | RICHFIELD BUILDERS
1255 | NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 120414 | Fatima ES | PAMPLONA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2014-12-19 | 070314S00032 | 14HK0014 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-11 | 2014-09-30 | RICHFIELD BUILDERS
1257 | NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 120415 | Hunop ES | PAMPLONA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-07 | 2014-12-18 | 070314S00033 | 14HK0013 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-12 | 2014-09-22 | R.E. SINGSON CONSTRUCTION
1258 | NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 312911 | Hunop HS | PAMPLONA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
1259 | NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 120417 | Inawasan ES | PAMPLONA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1037049.6543 |  |  | COMPLETED | 1 | 2015-12-03 |  | 070314S00232 | 15HK0076 | 2015-08-11 | 2015-08-14 | 2015-08-18 | 2015-08-24 | 2015-08-27 | ZION CONSTRUCTION(FORMERLY MASTERPIECE CONST. & SU
1260 | NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 303274 | Isidoro Salma MHS (Balayong ) | PAMPLONA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
1264 | NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 120424 | Samoyao Elem. School | PAMPLONA | 2 | 1 | 4 | 1STY 1CL & 1STY 3CL | 2014 K10 BATCH 1 | 3972503.55 |  |  | COMPLETED | 1 | 2015-01-27 | 2014-12-22 | 070314S00034 | 14HK0014 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-11 | 2014-09-30 | RICHFIELD BUILDERS
1265 | NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 303273 | Sta. Agueda NHS | PAMPLONA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2240417.57 |  |  | COMPLETED | 1
5714 | NC 2014 | K10 (2014) | Region VII | BOGO CITY | 302930 | BANBAN NHS | BOGO | 4 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 2935000 |  |  | COMPLETED | 1
5715 | NC 2014 | K10 (2014) | Region VII | BOGO CITY | 119117 | BINABAG ES | BOGO | 4 | 1 | 6 | 1STY3CL, 1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 5659000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00172 | 14HD0018 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | GOLDFIN CONSTRUCTION
5716 | NC 2014 | K10 (2014) | Region VII | Bogo City | 119107 | Bogo Central School 111 | CITY OF BOGO | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-07-05 | 2015-07-05 | 070214S00197 | 15HD0014 | 2015-02-04 | 2015-02-16 | 2015-02-17 | 2015-02-20 | 2015-03-02 | GONZALODO ENTERPRISES
5717 | NC 2014 | K10 (2014) | Region VII | Bogo City | 256501 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1
5718 | NC 2014 | K10 (2014) | Region VII | Bogo City | 325001 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1
5719 | NC 2014 | K10 (2014) | Region VII | BOGO CITY | 119121 | DAKIT ES | BOGO | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1073000 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-25 | 070214S00187 | 14HD0017 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
5720 | NC 2014 | K10 (2014) | Region VII | BOGO CITY | 119123 | LAPAZ ES | BOGO | 4 | 1 | 7 | 2U-1STY1CL, 1STY2CL, 1STY3CL | 2014 K10 BATCH 2 | 6702000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00183 | 14HD0018 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | GOLDFIN CONSTRUCTION
5721 | NC 2014 | K10 (2014) | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
5722 | NC 2014 | K10 (2014) | Region VII | BOGO CITY | 119124 | MALINGIN ES | BOGO | 4 | 1 | 4 | 1STY3CL, 1STY1CL | 2014 K10 BATCH 2 | 3797000 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-25 | 070214S00185 | 14HD0017 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
5723 | NC 2014 | K10 (2014) | Region VII | Bohol | 118630 | Abehilan ES | San Isidro | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-09-17 | 2015-09-17 | 070114S00364 | 15HC0032 | 2015-03-31 | 2015-04-12 | 2015-04-13 | 2015-04-17 | 2015-04-21 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
5724 | NC 2014 | K10 (2014) | Region VII | Bohol | 118532 | Agahay ES | Maribojoc | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-09-30 | 070114S00357 | 14HA0046 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-21 | 2015-04-06 | LM CONSTRUCTION AND GENERAL MARKETING
5725 | NC 2014 | K10 (2014) | Region VII | Bohol | 118162 | Alegria ES | Catigbian | 1 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 3 | 2003537.6289 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00396 | 14HA0056 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5726 | NC 2014 | K10 (2014) | Region VII | Bohol | 117967 | Angilan ES | Antequera | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2016-01-29 | 2015-09-30 | 070114S00402 | 14HA0052 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-05-27 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5727 | NC 2014 | K10 (2014) | Region VII | Bohol | 118788 | Atty. Maximo C. Lasco Mem. ES | TUBIGON | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-06 | 070114S00168 | 14HA0021 | 2014-09-29 | 2014-09-15 | 2014-09-29 | 2014-10-03 | 2014-11-18 | GAIL CONSTRUCTION AND SUPPLY
5728 | NC 2014 | K10 (2014) | Region VII | Bohol | 118164 | Baang ES | Catigbian | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00397 | 14HA0054 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5729 | NC 2014 | K10 (2014) | Region VII | Bohol | 117983 | Baclayon Central ES | Baclayon | 1 | 1 | 10 | 2STY8CL & 2STY2CL | 2014 K10 BATCH 3 | 15569883.9844 |  |  | COMPLETED | 1 | 2016-04-15 |  | 070114S00442 | 15HA0063 | 2015-06-19 | 2015-06-10 | 2015-06-19 | 2015-06-25 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5730 | NC 2014 | K10 (2014) | Region VII | Bohol | 118491 | Badbad Elementary School | Loon South | 1 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 3576429.1398 |  |  | COMPLETED | 1 | 2016-01-01 | 2015-12-30 | 070114S00427 | 15HA0003 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-06-26 | 2015-09-03 | IJK CONSTRUCTION
5731 | NC 2014 | K10 (2014) | Region VII | Bohol | 118471 | Bagacay ES | Loon North | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3404228.7213 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00451 | 15HA0004 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5732 | NC 2014 | K10 (2014) | Region VII | Bohol | 118165 | Bagtic ES | Catigbian | 1 | 1 | 8 | 2UNITS 1STY2CL, 1STY3CL & 1STY1CL | 2014 K10 BATCH 3 | 7176993.2239 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00398 | 14HA0056 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5733 | NC 2014 | K10 (2014) | Region VII | Bohol | 117930 | Bahi PS | ALBURQUERQUE | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1838464.5699 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-09-30 | 070114S00382 | 14HA0044 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-28 | 2015-05-04 | LM CONSTRUCTION AND GENERAL MARKETING
5734 | NC 2014 | K10 (2014) | Region VII | Bohol | 118553 | Balicasag ES | PANGLAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1112049.6543 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00481 | 15HA0079 | 2015-07-24 | 2015-07-13 | 2015-07-24 | 2015-08-05 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5735 | NC 2014 | K10 (2014) | Region VII | Bohol | 302907 | Bantolinao National High School | ANTEQUERA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
5736 | NC 2014 | K10 (2014) | Region VII | Bohol | 118492 | Basac Elementary School | Loon South | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-12-15 | 070114S00372 | 15HA0002 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5737 | NC 2014 | K10 (2014) | Region VII | Bohol | 118534 | Bayacabac ES | MARIBOJOC | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1
5738 | NC 2014 | K10 (2014) | Region VII | Bohol | 118534 | Bayacabac ES | Maribojoc | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
5739 | NC 2014 | K10 (2014) | Region VII | Bohol | 302817 | Biking Tech-Voc HS | DAUIS | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1
5740 | NC 2014 | K10 (2014) | Region VII | Bohol | 118774 | Bilang-Bilangan ES | TUBIGON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1112049.6543 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00484 | 15HA0086 | 2015-08-11 | 2015-07-30 | 2015-08-11 | 2015-08-19 | 2015-09-21 | PUREGOLD CONSTRUCTION & DEVT. CORP.
5741 | NC 2014 | K10 (2014) | Region VII | Bohol | 117997 | Boctol ES | BALILIHAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-20 | 070114S00165 | 14HA0018 | 2014-09-03 | 2014-08-22 | 2014-09-03 | 2014-09-10 | 2014-11-06 | GAIL CONSTRUCTION AND SUPPLY
5742 | NC 2014 | K10 (2014) | Region VII | Bohol | 118089 | Bonbon Catmonan ES | Calape | 1 | 1 | 4 | 1STY1CL & 1STY3CL | 2014 K10 BATCH 3 | 3600564.0842 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00401 | 14HA0055 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5743 | NC 2014 | K10 (2014) | Region VII | Bohol | 118776 | Buenos Aires ES | TUBIGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-27 | 070114S00131 | 14HA0020 | 2014-09-29 | 2014-09-15 | 2014-09-29 | 2014-10-03 | 2014-11-18 | GAIL CONSTRUCTION AND SUPPLY
5744 | NC 2014 | K10 (2014) | Region VII | Bohol | 117972 | Bungahan ES | Antequera | 1 | 1 | 5 | 2UNITS 1STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 4578197.9542 |  |  | COMPLETED | 1 | 2016-01-29 | 2015-09-30 | 070114S00388 | 14HA0052 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-05-27 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5745 | NC 2014 | K10 (2014) | Region VII | Bohol | 186504 | Cabacungan ES | LOON | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2890828.124 |  |  | COMPLETED | 1 | 2016-03-31 |  | 070114S00483 | 15HA0081 | 2015-07-24 | 2015-07-13 | 2015-07-24 | 2015-08-05 | 2015-09-03 | GAIL CONSTRUCTION AND SUPPLY
5746 | NC 2014 | K10 (2014) | Region VII | Bohol | 118537 | Cabawan ES | Maribojoc | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-09-30 | 070114S00355 | 14HA0046 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-21 | 2015-04-06 | LM CONSTRUCTION AND GENERAL MARKETING
5747 | NC 2014 | K10 (2014) | Region VII | Bohol | 118090 | Cabayugan ES | Calape | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-09-30 | 070114S00394 | 15HA0001 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-01-30 | 2015-03-16 | BNYU ENTERPRISES & CONSTRUCTION
5748 | NC 2014 | K10 (2014) | Region VII | Bohol | 118495 | Cabug PS | Loon South | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
5749 | NC 2014 | K10 (2014) | Region VII | Bohol | 118778 | Cabulijan ES | Tubigon | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00367 | 14HA0049 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5750 | NC 2014 | K10 (2014) | Region VII | Bohol | 118475 | Calayugan ES | Loon | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-10-30 | 2015-09-30 | 070114S00455 | 15HA0006 | 2015-04-28 | 2015-03-16 | 2015-04-28 | 2015-05-07 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5751 | NC 2014 | K10 (2014) | Region VII | Bohol | 118167 | Cambailan ES | CATIGBIAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1
5752 | NC 2014 | K10 (2014) | Region VII | Bohol | 118167 | Cambailan ES | Catigbian | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1
5753 | NC 2014 | K10 (2014) | Region VII | Bohol | 117984 | Cambanac PS | Baclayon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-09-30 | 070114S00454 | 14HA0044 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-28 | 2015-05-04 | LM CONSTRUCTION AND GENERAL MARKETING
5754 | NC 2014 | K10 (2014) | Region VII | Bohol | 118698 | Cambuac Norte PS | Sikatuna | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-08-28 | 2015-08-25 | 070114S00365 | 14HA0045 | 2015-03-02 | 2015-03-02 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5755 | NC 2014 | K10 (2014) | Region VII | Bohol | 118094 | Camias ES | Calape | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00393 | 14HA0055 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5756 | NC 2014 | K10 (2014) | Region VII | Bohol | 118496 | Campatud Elementary School | Loon South | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00432 | 15HA0004 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5757 | NC 2014 | K10 (2014) | Region VII | Bohol | 500212 | Canangcaan Integrated School | CORELLA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1
5758 | NC 2014 | K10 (2014) | Region VII | Bohol |  | Canangcaan IS | CORELLA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-03-28 | 2015-03-27 | 070114S00126 | 14HA0014 | 2014-08-29 | 2014-08-15 | 2014-08-29 | 2014-09-25 | 2014-12-18 | A.A. DE VERA CONSTRUCTION
5759 | NC 2014 | K10 (2014) | Region VII | Bohol | 118202 | Cancatac ES | Corella | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-08-28 | 2015-08-25 | 070114S00350 | 14HA0045 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5760 | NC 2014 | K10 (2014) | Region VII | Bohol | 118095 | Canguha ES | CALAPE | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00480 | 15HA0082 | 2015-08-10 | 2015-07-27 | 2015-08-10 | 2015-08-14 | 2015-09-21 | PUREGOLD CONSTRUCTION & DEVT. CORP.
5761 | NC 2014 | K10 (2014) | Region VII | Bohol | 118477 | Canhangdon PS | Loon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-01 | 2015-09-30 | 070114S00453 | 15HA0005 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-01-30 | 2015-03-16 | BNYU ENTERPRISES & CONSTRUCTION
5762 | NC 2014 | K10 (2014) | Region VII | Bohol | 118478 | Caniga-an-Ubojan Elementary School | Loon | 1 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 3 | 5197590.5394 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-09-30 | 070114S00456 | 15HA0059 | 2015-05-25 | 2015-05-12 | 2015-05-25 | 2015-05-29 | 2015-07-03 | GAIL CONSTRUCTION AND SUPPLY
5763 | NC 2014 | K10 (2014) | Region VII | Bohol | 118480 | Cantam Is ES | Loon North | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00449 | 15HA0004 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5764 | NC 2014 | K10 (2014) | Region VII | Bohol | 118481 | Cantaongon ES | LOON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
5765 | NC 2014 | K10 (2014) | Region VII | Bohol | 118481 | Cantaongon ES | Loon North | 1 | 1 | 4 | 1STY3CL & 1STY1CL | 2014 K10 BATCH 3 | 3600564.0842 |  |  | COMPLETED | 1
5766 | NC 2014 | K10 (2014) | Region VII | Bohol | 118169 | Catigbian Central ES | Catigbian | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-08-25 | 070114S00400 | 14HA0053 | 2014-12-23 | 2014-12-11 | 2014-12-23 | 2015-01-07 | 2015-03-03 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
5767 | NC 2014 | K10 (2014) | Region VII | Bohol | 302833 | Catigbian NHS | Catigbian | 1 | 1 | 8 | 4UNITS 1STY2CL | 2014 K10 BATCH 3 | 7152858.2796 |  |  | COMPLETED | 1
5768 | NC 2014 | K10 (2014) | Region VII | Bohol | 118170 | Catigbian West Central ES | Catigbian | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-08-28 | 070114S00360 | 14HA0053 | 2014-12-23 | 2014-12-11 | 2014-12-23 | 2015-01-07 | 2015-03-03 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
5769 | NC 2014 | K10 (2014) | Region VII | Bohol | 118781 | Cawayanan ES | Tubigon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-12-05 | 2015-09-30 | 070114S00407 | 14HA0049 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5770 | NC 2014 | K10 (2014) | Region VII | Bohol | 118556 | Danao ES | PANGLAO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-28 | 2015-03-27 | 070114S00130 | 14HA0014 | 2014-08-29 | 2014-08-15 | 2014-08-29 | 2014-09-25 | 2014-12-18 | A.A. DE VERA CONSTRUCTION
5771 | NC 2014 | K10 (2014) | Region VII | Bohol | 118004 | Dorol ES | BALILIHAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-01-20 | 070114S00166 | 14HA0018 | 2014-09-03 | 2014-08-22 | 2014-09-03 | 2014-09-10 | 2014-11-06 | GAIL CONSTRUCTION AND SUPPLY
5772 | NC 2014 | K10 (2014) | Region VII | Bohol | 118208 | Fatima ES | Cortes | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-08-28 | 2015-08-25 | 070114S00348 | 14HA0045 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5773 | NC 2014 | K10 (2014) | Region VII | Bohol | 118782 | Genonocan PS | Tubigon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00404 | 14HA0049 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5774 | NC 2014 | K10 (2014) | Region VII | Bohol | 117986 | Guiwanon ES | Baclayon | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-09-30 | 070114S00446 | 14HA0044 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-28 | 2015-05-04 | LM CONSTRUCTION AND GENERAL MARKETING
5775 | NC 2014 | K10 (2014) | Region VII | Bohol | 118005 | Haguilanan Grande ES | BALILIHAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-05 | 070114S00167 | 14HA0019 | 2014-09-29 | 2014-09-15 | 2014-09-29 | 2014-10-03 | 2014-11-18 | GAIL CONSTRUCTION AND SUPPLY
5776 | NC 2014 | K10 (2014) | Region VII | Bohol | 312320 | Haguilanan HS | CATIGBIAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1
5777 | NC 2014 | K10 (2014) | Region VII | Bohol | 118775 | Isaac Lopoz ES | TUBIGON | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1
5778 | NC 2014 | K10 (2014) | Region VII | Bohol | 118775 | Isaac Lopoz ES | Tubigon | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
5779 | NC 2014 | K10 (2014) | Region VII | Bohol | 118541 | Jandig ES | Maribojoc | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-08-17 | 2015-08-15 | 070114S00373 | 14HA0047 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2014-12-21 | 2015-02-18 | ASCENTIA CONSTRUCTION, INC.
5780 | NC 2014 | K10 (2014) | Region VII | Bohol | 118785 | Jose Boja ES | Tubigon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00405 | 14HA0048 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5781 | NC 2014 | K10 (2014) | Region VII | Bohol | 118097 | Labuun ES | Calape | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-09-30 | 070114S00395 | 15HA0001 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-01-30 | 2015-03-16 | BNYU ENTERPRISES & CONSTRUCTION
5782 | NC 2014 | K10 (2014) | Region VII | Bohol | 118542 | Lagtangon ES | Maribojoc | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-09-30 | 070114S00354 | 14HA0046 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-21 | 2015-04-06 | LM CONSTRUCTION AND GENERAL MARKETING
5783 | NC 2014 | K10 (2014) | Region VII | Bohol | 118484 | Lawis ES | Loon | 1 | 1 | 7 | 2UNITS 1STY3CL & 1STY1CL | 2014 K10 BATCH 3 | 6199359.3538 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00352 | 15HA0002 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5784 | NC 2014 | K10 (2014) | Region VII | Bohol | 118558 | Libaong ES | PANGLAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1052049.6543 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00487 | 15HA0079 | 2015-07-24 | 2015-07-13 | 2015-07-24 | 2015-08-05 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5785 | NC 2014 | K10 (2014) | Region VII | Bohol | 118499 | Lintuan ES | Loon South | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-10-17 | 2015-10-15 | 070114S00436 | 15HA0029 | 2015-03-16 | 2015-03-04 | 2015-03-16 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5786 | NC 2014 | K10 (2014) | Region VII | Bohol | 118500 | Loon South Central ES | Loon South | 1 | 1 | 7 | 2STY6CL & 1STY1CL | 2014 K10 BATCH 3 | 9230222.0176 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-09-30 | 070114S00441 | 15HA0005 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-01-30 | 2015-03-16 | BNYU ENTERPRISES & CONSTRUCTION
5787 | NC 2014 | K10 (2014) | Region VII | Bohol | 302871 | Loon South National H.S. | Loon South | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3404228.7213 |  |  | COMPLETED | 1
5788 | NC 2014 | K10 (2014) | Region VII | Bohol | 118209 | Loreto ES | Cortes | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-08-28 | 2015-08-25 | 070114S00349 | 14HA0045 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5789 | NC 2014 | K10 (2014) | Region VII | Bohol | 312355 | Lourdes High School | CORTES | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1843489.5699 |  |  | COMPLETED | 1 | 2015-08-28 | 2015-08-25 | 070114S00386 | 14HA0045 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5790 | NC 2014 | K10 (2014) | Region VII | Bohol | 302872 | Lourdes NHS | PANGLAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1965466.749 |  |  | COMPLETED | 1
5791 | NC 2014 | K10 (2014) | Region VII | Bohol | 118177 | Mahayag Norte ES | CATIGBIAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1032049.6543 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00485 | 15HA0082 | 2015-08-10 | 2015-07-27 | 2015-08-10 | 2015-08-14 | 2015-09-21 | PUREGOLD CONSTRUCTION & DEVT. CORP.
5792 | NC 2014 | K10 (2014) | Region VII | Bohol | 118179 | Maitum ES | CATIGBIAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
5793 | NC 2014 | K10 (2014) | Region VII | Bohol | 118179 | Maitum ES | Catigbian | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1
5794 | NC 2014 | K10 (2014) | Region VII | Bohol | 118099 | Mandaug Gamay ES | Calape | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-08-25 | 070114S00391 | 15HA0001 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-01-30 | 2015-03-16 | BNYU ENTERPRISES & CONSTRUCTION
5795 | NC 2014 | K10 (2014) | Region VII | Bohol | 118100 | Mantatao ES | CALAPE | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-04-07 | 2015-04-06 | 070114S00136 | 14HA0021 | 2014-09-29 | 2014-09-15 | 2014-09-29 | 2014-10-03 | 2014-11-18 | GAIL CONSTRUCTION AND SUPPLY
5796 | NC 2014 | K10 (2014) | Region VII | Bohol | 118544 | Maribojoc CES | Maribojoc | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-08-17 | 2015-08-15 | 070114S00362 | 14HA0047 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2014-12-21 | 2015-02-18 | ASCENTIA CONSTRUCTION, INC.
5797 | NC 2014 | K10 (2014) | Region VII | Bohol | 117989 | Miguel Oppus MES | Baclayon | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-09-30 | 070114S00444 | 14HA0044 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-28 | 2015-05-04 | LM CONSTRUCTION AND GENERAL MARKETING
5798 | NC 2014 | K10 (2014) | Region VII | Bohol | 118486 | Mocpoc Elementary School | Loon | 1 | 1 | 6 | 3UNITS 1STY2CL | 2014 K10 BATCH 3 | 5364643.7097 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-09-30 | 070114S00458 | 15HA0058 | 2015-05-25 | 2015-05-12 | 2015-05-25 | 2015-05-29 | 2015-07-03 | YU CONSTRUCTION
5799 | NC 2014 | K10 (2014) | Region VII | Bohol | 118501 | Nagtubo Elementary School | Loon South | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1 | 2015-07-31 | 2015-09-30 | 070114S00434 | 15HA0060 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-29 | 2015-07-03 | GAIL CONSTRUCTION AND SUPPLY
5800 | NC 2014 | K10 (2014) | Region VII | Bohol | 118213 | New Lourdes ES | CORTES | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-12-17 | 2015-12-15 | 070114S00482 | 15HA0080 | 2015-07-24 | 2015-07-13 | 2015-07-24 | 2015-08-05 | 2015-09-18 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5801 | NC 2014 | K10 (2014) | Region VII | Bohol | 118487 | Nueva Vida ES | Loon North | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-29 | 070114S00452 | 15HA0027 | 2015-03-16 | 2015-03-04 | 2015-03-16 | 2015-05-27 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5802 | NC 2014 | K10 (2014) | Region VII | Bohol | 118545 | Pagnitoan ES | Maribojoc | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-08-17 | 2015-08-15 | 070114S00359 | 14HA0047 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2014-12-24 | 2015-02-18 | ASCENTIA CONSTRUCTION, INC.
5803 | NC 2014 | K10 (2014) | Region VII | Bohol | 302881 | Pagnito-an NHS | MARIBOJOC | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 1001768.8144 |  |  | COMPLETED | 1
5804 | NC 2014 | K10 (2014) | Region VII | Bohol | 118790 | Pandan ES | TUBIGON | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2689245.2697 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00383 | 14HA0048 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5805 | NC 2014 | K10 (2014) | Region VII | Bohol | 118562 | Panglao Central Elementary School | Panglao | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-11-19 | 070114S00439 | 14HA0044 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-28 | 2015-05-04 | LM CONSTRUCTION AND GENERAL MARKETING
5806 | NC 2014 | K10 (2014) | Region VII | Bohol | 118214 | Patrocinio ES | CORTES | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-20 | 070114S00127 | 14HA0015 | 2014-08-29 | 2014-08-15 | 2014-08-29 | 2014-09-25 | 2014-11-06 | GAIL CONSTRUCTION AND SUPPLY
5807 | NC 2014 | K10 (2014) | Region VII | Bohol | 118503 | Pig-ot ES | Loon South | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1 | 2015-10-01 | 2015-07-30 | 070114S00435 | 15HA0005 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-01-30 | 2015-03-16 | BNYU ENTERPRISES & CONSTRUCTION
5808 | NC 2014 | K10 (2014) | Region VII | Bohol | 118792 | Pinayagan Norte ES | Tubigon | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2016-01-16 |  | 070114S00370 | 15HA0061 | 2015-05-25 | 2015-05-12 | 2015-05-25 | 2015-05-29 | 2015-07-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5809 | NC 2014 | K10 (2014) | Region VII | Bohol | 118793 | Pinayagan Sur ES | Tubigon | 1 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 3 | 5197590.5394 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00369 | 15HA0010 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5810 | NC 2014 | K10 (2014) | Region VII | Bohol | 118488 | Pondol ES | Loon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00351 | 15HA0002 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5811 | NC 2014 | K10 (2014) | Region VII | Bohol | 118181 | Rizal PS | Catigbian | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00387 | 14HA0054 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5812 | NC 2014 | K10 (2014) | Region VII | Bohol | 118008 | Sagasa ES | Balilihan | 1 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-08-25 | 070114S00428 | 14HA0053 | 2014-12-23 | 2014-12-11 | 2014-12-23 | 2015-01-07 | 2015-03-03 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
5813 | NC 2014 | K10 (2014) | Region VII | Bohol | 118547 | San Isidro PS | Maribojoc | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-08-17 | 2015-08-15 | 070114S00346 | 14HA0047 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2014-12-21 | 2015-02-18 | ASCENTIA CONSTRUCTION, INC.
5814 | NC 2014 | K10 (2014) | Region VII | Bohol | 118548 | San Roque ES | Maribojoc | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-09-30 | 070114S00356 | 14HA0046 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-21 | 2015-04-06 | LM CONSTRUCTION AND GENERAL MARKETING
5815 | NC 2014 | K10 (2014) | Region VII | Bohol | 500211 | San Roque Integrated School | BALILIHAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
5816 | NC 2014 | K10 (2014) | Region VII | Bohol | 302900 | San Roque NHS | ALBURQUERQUE | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1102703.8954 |  |  | COMPLETED | 1
5817 | NC 2014 | K10 (2014) | Region VII | Bohol | 302902 | Sandingan NHS | Loon | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3404228.7213 |  |  | COMPLETED | 1
5818 | NC 2014 | K10 (2014) | Region VII | Bohol | 118489 | Sondol Primary School | Loon | 1 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2015-10-27 | 2015-09-30 | 070114S00457 | 15HA0006 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-03-18 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5819 | NC 2014 | K10 (2014) | Region VII | Bohol | 118550 | Sta. Cruz ES | Maribojoc | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3404228.7213 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-09-30 | 070114S00353 | 14HA0046 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-21 | 2015-04-06 | LM CONSTRUCTION AND GENERAL MARKETING
5820 | NC 2014 | K10 (2014) | Region VII | Bohol | 117978 | Sto Rosario PS | Antequera | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2016-01-29 | 2015-09-30 | 070114S00433 | 14HA0052 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-05-27 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5821 | NC 2014 | K10 (2014) | Region VII | Bohol | 118126 | Tambongan ES | Candijay | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-07-31 | 2015-07-31 | 070114S00448 | 15HB0002 | 2015-02-01 | 2015-02-04 | 2015-02-16 | 2015-02-25 | 2015-03-18 | FIRST BUILDERS AND DEVELOPERS
5822 | NC 2014 | K10 (2014) | Region VII | Bohol | 117985 | Tanday ES | BACLAYON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-12-17 | 2015-12-15 | 070114S00486 | 15HA0080 | 2015-07-24 | 2015-07-13 | 2015-07-24 | 2015-08-05 | 2015-09-18 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5823 | NC 2014 | K10 (2014) | Region VII | Bohol | 118564 | Tawala ES | PANGLAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1052049.6543 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00478 | 15HA0079 | 2015-07-24 | 2015-07-13 | 2015-07-24 | 2015-08-05 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5824 | NC 2014 | K10 (2014) | Region VII | Bohol | 118506 | Ticugan Elementary School | Loon South | 1 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00358 | 15HA0002 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5825 | NC 2014 | K10 (2014) | Region VII | Bohol | 118796 | Tinangnan ES | Tubigon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00368 | 14HA0049 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5826 | NC 2014 | K10 (2014) | Region VII | Bohol | 118105 | Tinibgan ES | Calape | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-09-30 | 070114S00390 | 14HA0055 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5827 | NC 2014 | K10 (2014) | Region VII | Bohol | 118507 | Tiwi PS | Loon South | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-29 | 070114S00438 | 15HA0060 | 2015-05-25 | 2015-05-12 | 2015-05-25 | 2015-05-29 | 2015-07-03 | GAIL CONSTRUCTION AND SUPPLY
5828 | NC 2014 | K10 (2014) | Region VII | Bohol | 118552 | Toril PS | Maribojoc | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-09-30 | 070114S00363 | 14HA0046 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-21 | 2015-04-06 | LM CONSTRUCTION AND GENERAL MARKETING
5829 | NC 2014 | K10 (2014) | Region VII | Bohol | 118787 | Tubigon East Central ES | Tubigon | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00366 | 15HA0010 | 2015-03-02 | 2015-02-18 | 2015-03-03 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5830 | NC 2014 | K10 (2014) | Region VII | Bohol | 118508 | Tubodacu Elementary School | Loon South | 1 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2016-01-01 | 2015-12-30 | 070114S00440 | 15HA0003 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-06-26 | 2015-09-03 | IJK CONSTRUCTION
5831 | NC 2014 | K10 (2014) | Region VII | Bohol | 118509 | Tubodio ES | Loon South | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2016-01-01 | 2015-12-30 | 070114S00445 | 15HA0003 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-06-26 | 2015-09-03 | IJK CONSTRUCTION
5832 | NC 2014 | K10 (2014) | Region VII | Bohol | 118799 | Ubujan ES | Tubigon | 1 | 1 | 4 | 2UNITS 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 3791752.1988 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00416 | 14HA0048 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5833 | NC 2014 | K10 (2014) | Region VII | Bohol | 118107 | Ulbujan ES | CALAPE | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052703.8954 |  |  | COMPLETED | 1
5834 | NC 2014 | K10 (2014) | Region VII | Bohol | 118107 | Uldujan ES | Calape | 1 | 1 | 6 | 1STY2CL, 1STY3CL & 1STY1CL | 2014 K10 BATCH 3 | 5388778.6541 |  |  | COMPLETED | 1
5835 | NC 2014 | K10 (2014) | Region VII | Bohol | 117981 | Viga PS | Antequera | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2016-01-29 |  | 070114S00374 | 14HA0052 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-05-27 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5836 | NC 2014 | K10 (2014) | Region VII | Bohol | 118744 | A.P. Gurrea Mem. ES | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00176 | 14HC0027 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | DINAH JANE CONSTRUCTION SUPPLY
5837 | NC 2014 | K10 (2014) | Region VII | Bohol | 118801 | Achila ES | UBAY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2669145.2697 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-15 | 070114S00420 | 15HC0016 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | MAI CONSTRUCTION & SUPPLY
5838 | NC 2014 | K10 (2014) | Region VII | Bohol | 118586 | Aguining ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-20 | 070114S00186 | 14HC0042 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | MAI CONSTRUCTION & SUPPLY
5839 | NC 2014 | K10 (2014) | Region VII | Bohol | 118365 | Anonang ES | INABANGA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-15 | 070114S00173 | 14HC0018 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | MAI CONSTRUCTION & SUPPLY
5840 | NC 2014 | K10 (2014) | Region VII | Bohol | 118184 | Bacani ES | CLARIN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00199 | 14HC0012 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
5841 | NC 2014 | K10 (2014) | Region VII | Bohol | 118391 | Badiang PS | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-22 | 2015-02-22 | 070114S00200 | 14HC0040 | 2014-09-30 | 2014-10-12 | 2014-10-13 | 2014-10-17 | 2014-10-21 | SLP CONSTRUCTION
5842 | NC 2014 | K10 (2014) | Region VII | Bohol | 186512 | Bagacay Annex ES | TALIBON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-24 | 070114S00028 | 14HC0046 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | WILTAN CONSTRUCTION
5843 | NC 2014 | K10 (2014) | Region VII | Bohol | 118733 | Bagacay ES | TALIBON | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-24 | 070114S00037 | 14HC0046 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | WILTAN CONSTRUCTION
5844 | NC 2014 | K10 (2014) | Region VII | Bohol | 118366 | Baguhan E/S | Inabanga | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-11-27 | 2015-12-31 | 070114S00281 | 15HC0047 | 2015-06-10 | 2015-06-22 | 2015-06-23 | 2015-06-27 | 2015-07-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5845 | NC 2014 | K10 (2014) | Region VII | Bohol | 118392 | Bahan P/S | Inabanga | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-18 | 070114S00286 | 15HC0049 | 2015-06-10 | 2015-06-22 | 2015-06-23 | 2015-06-27 | 2015-07-01 | 3N CONSTRUCTION & SUPPLY
5846 | NC 2014 | K10 (2014) | Region VII | Bohol | 118322 | Banacon ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-24 | 070114S00213 | 14HC0017 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | EDANNA CONSTRUCTION
5847 | NC 2014 | K10 (2014) | Region VII | Bohol | 118062 | Bantuan PS | BUENAVISTA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-02 | 070114S00139 | 14HC0009 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | P.B. OBIAL CONSTRUCTION
5848 | NC 2014 | K10 (2014) | Region VII | Bohol | 118588 | Baud ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-02-04 | 2015-02-04 | 070114S00187 | 14HC0020 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | MAI CONSTRUCTION & SUPPLY
5849 | NC 2014 | K10 (2014) | Region VII | Bohol | 118591 | Bayog ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1212329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-20 | 070114S00189 | 14HC0042 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | MAI CONSTRUCTION & SUPPLY
5850 | NC 2014 | K10 (2014) | Region VII | Bohol | 118642 | Bayongan ES | SAN MIGUEL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1833439.5699 |  |  | COMPLETED | 1 | 2015-10-10 | 2015-05-31 | 070114S00417 | 15HC0015 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | BNYU ENTERPRISES & CONSTRUCTION
5851 | NC 2014 | K10 (2014) | Region VII | Bohol | 118028 | Bilangbilangan Daku ES | BIEN UNIDO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2690828.124 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-15 | 070114S00474 | 15HC0056 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | DINAH JANE CONSTRUCTION SUPPLY
5852 | NC 2014 | K10 (2014) | Region VII | Bohol | 118029 | Bilangbilangan East PS | BIEN UNIDO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-08-03 | 2015-07-31 | 070114S00135 | S-00135 | 2015-03-16 | 2015-03-28 | 2015-03-29 | 2015-04-02 | 2015-04-06 | By Administration
5853 | NC 2014 | K10 (2014) | Region VII | Bohol | 118589 | Bogo ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 070114S00188 | 14HC0021 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-06 | 2014-12-10 | MAI CONSTRUCTION & SUPPLY
5854 | NC 2014 | K10 (2014) | Region VII | Bohol | 118185 | Bogtongbod E/S | Clarin | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
5855 | NC 2014 | K10 (2014) | Region VII | Bohol | 118185 | Bogtongbod ES | CLARIN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1
5856 | NC 2014 | K10 (2014) | Region VII | Bohol | 118186 | Bonbon ES | CLARIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1
5857 | NC 2014 | K10 (2014) | Region VII | Bohol | 118186 | Bonbon ES | Clarin | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
5858 | NC 2014 | K10 (2014) | Region VII | Bohol | 312324 | Bonbonon HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1177329.12 |  |  | COMPLETED | 1
5859 | NC 2014 | K10 (2014) | Region VII | Bohol | 118806 | Bood ES | UBAY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1848514.5699 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-15 | 070114S00443 | 15HC0016 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | MAI CONSTRUCTION & SUPPLY
5860 | NC 2014 | K10 (2014) | Region VII | Bohol | 118189 | Buangan ES | CLARIN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
5861 | NC 2014 | K10 (2014) | Region VII | Bohol | 118189 | Buangan ES | Clarin | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
5862 | NC 2014 | K10 (2014) | Region VII | Bohol | 118065 | Buenavista CES | BUENAVISTA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2930174.43 |  |  | COMPLETED | 1
5863 | NC 2014 | K10 (2014) | Region VII | Bohol | 118065 | Buenavista CES | Buenavista | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
5864 | NC 2014 | K10 (2014) | Region VII | Bohol | 118807 | Buenavista ES | UBAY | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3850805.49 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070114S00013 | 14HC0054 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | WILTAN CONSTRUCTION
5865 | NC 2014 | K10 (2014) | Region VII | Bohol | 118368 | Bugang PS | Inabanga | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-05 | 2015-11-05 | 070114S00287 | 15HC0042 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | MAI CONSTRUCTION & SUPPLY
5866 | NC 2014 | K10 (2014) | Region VII | Bohol | 118718 | Burgos ES | TALIBON | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1868614.5699 |  |  | COMPLETED | 1 | 2015-10-19 | 2015-08-31 | 070114S00403 | 15HC0015 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | BNYU ENTERPRISES & CONSTRUCTION
5867 | NC 2014 | K10 (2014) | Region VII | Bohol | 118734 | Busalian ES | TALIBON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00039 | 14HC0027 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | DINAH JANE CONSTRUCTION SUPPLY
5868 | NC 2014 | K10 (2014) | Region VII | Bohol | 118592 | Butan ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070114S00190 | 14HC0021 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-06 | 2014-12-10 | MAI CONSTRUCTION & SUPPLY
5869 | NC 2014 | K10 (2014) | Region VII | Bohol | 118644 | Cabangahan PS | SAN MIGUEL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00040 | 14HC0024 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | VIRLO CONSTRUCTION
5870 | NC 2014 | K10 (2014) | Region VII | Bohol |  | Cabanugan IS | San Isidro | 2 | 1 | 7 | 1STY4CL & 1STY3CL | 2014 K10 BATCH 3 | 6003023.991 |  |  | COMPLETED | 1 | 2016-01-11 |  | 070114S00311 | 15HC0050 | 2015-06-11 | 2015-06-23 | 2015-06-24 | 2015-06-28 | 2015-07-02 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
5871 | NC 2014 | K10 (2014) | Region VII | Bohol |  | Cabasakan ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00212 | 14HC0016 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | EDANNA CONSTRUCTION
5872 | NC 2014 | K10 (2014) | Region VII | Bohol | 118234 | Cabatuan ES | DANAO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-10-19 | 2015-10-19 | 070114S00277 | 15HC0003 | 2015-04-02 | 2015-04-14 | 2015-04-15 | 2015-04-19 | 2015-04-23 | RAMONA CONSTRUCTION & ENTERPRISES
5873 | NC 2014 | K10 (2014) | Region VII | Bohol | 118190 | Cabog E/S | Clarin | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2015-11-30 |  | 070114S00275 | 15HC0002 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | PUREGOLD CONSTRUCTION & DEVT. CORP.
5874 | NC 2014 | K10 (2014) | Region VII | Bohol | 118191 | Caboy E/S | Clarin | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
5875 | NC 2014 | K10 (2014) | Region VII | Bohol | 118191 | Caboy ES | CLARIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
5876 | NC 2014 | K10 (2014) | Region VII | Bohol | 118068 | Cabul-an ES | BUENAVISTA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070114S00141 | 14HC0036 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | WILTAN CONSTRUCTION
5877 | NC 2014 | K10 (2014) | Region VII | Bohol | 118219 | Cagawasan ES | DAGOHOY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
5878 | NC 2014 | K10 (2014) | Region VII | Bohol | 118219 | Cagawasan ES | Dagohoy | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
5879 | NC 2014 | K10 (2014) | Region VII | Bohol | 118394 | Cagawasan ES | INABANGA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-22 | 070114S00181 | 14HC0039 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | MAI CONSTRUCTION & SUPPLY
5880 | NC 2014 | K10 (2014) | Region VII | Bohol | 118809 | Cagting ES | UBAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1032049.6543 |  |  | COMPLETED | 1 | 2015-10-24 | 2015-10-24 | 070114S00473 | 15HC0055 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-07-18 | 2015-07-22 | MAI CONSTRUCTION & SUPPLY
5881 | NC 2014 | K10 (2014) | Region VII | Bohol | 118634 | Caimbang ES | San Isidro | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-08-31 | 070114S00263 | 15HC0005 | 2015-04-11 | 2015-04-23 | 2015-04-24 | 2015-04-28 | 2015-05-02 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5882 | NC 2014 | K10 (2014) | Region VII | Bohol | 118395 | Cainsican P/S | Inabanga | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
5883 | NC 2014 | K10 (2014) | Region VII | Bohol | 118395 | Cainsican PS | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
5884 | NC 2014 | K10 (2014) | Region VII | Bohol | 118810 | Calanggaman ES | UBAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 070114S00012 | 14HC0056 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-11-01 | 2014-11-05 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
5885 | NC 2014 | K10 (2014) | Region VII | Bohol | 118811 | California ES | UBAY | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6358964.7656 |  |  | COMPLETED | 1 | 2015-11-29 | 2015-11-29 | 070114S00421 | 15HC0033 | 2015-04-13 | 2015-04-25 | 2015-04-26 | 2015-04-30 | 2015-05-04 | MAI CONSTRUCTION & SUPPLY
5886 | NC 2014 | K10 (2014) | Region VII | Bohol | 118735 | Calituban ES | TALIBON | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070114S00061 | 14HC0045 | 2014-10-16 | 2014-10-28 | 2014-10-29 | 2014-11-02 | 2014-11-06 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
5887 | NC 2014 | K10 (2014) | Region VII | Bohol | 118220 | Caluasan ES | DAGOHOY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 070114S00207 | 14HC0013 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
5888 | NC 2014 | K10 (2014) | Region VII | Bohol | 118645 | Caluasan ES | SAN MIGUEL | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1
5889 | NC 2014 | K10 (2014) | Region VII | Bohol | 118645 | Caluasan ES | San Miguel | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
5890 | NC 2014 | K10 (2014) | Region VII | Bohol | 118070 | Cambus-oc ES | BUENAVISTA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1
5891 | NC 2014 | K10 (2014) | Region VII | Bohol | 118070 | Cambus-Oc ES | Buenavista | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
5892 | NC 2014 | K10 (2014) | Region VII | Bohol | 118593 | Campamanog ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00191 | 14HC0021 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-06 | 2014-12-10 | MAI CONSTRUCTION & SUPPLY
5893 | NC 2014 | K10 (2014) | Region VII | Bohol | 118326 | Campao ES | Getafe | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
5894 | NC 2014 | K10 (2014) | Region VII | Bohol | 118326 | Campao ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1
5895 | NC 2014 | K10 (2014) | Region VII | Bohol | 118636 | Candungao ES | SAN ISIDRO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092703.8954 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 070114S00228 | 14HC0061 | 2014-09-22 | 2014-10-04 | 2014-10-05 | 2014-10-09 | 2014-10-13 | WILTAN CONSTRUCTION
5896 | NC 2014 | K10 (2014) | Region VII | Bohol | 118328 | Cangmundo ES | Getafe | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-19 | 2015-10-19 | 070114S00247 | 15HC0015 | 2015-04-03 | 2015-04-15 | 2015-04-16 | 2015-04-20 | 2015-04-24 | BNYU ENTERPRISES & CONSTRUCTION
5897 | NC 2014 | K10 (2014) | Region VII | Bohol | 118594 | Canmangao ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00192 | 14HC0021 | 2014-11-21 | 2014-12-03 | 2014-12-04 | 2014-12-08 | 2014-12-10 | MAI CONSTRUCTION & SUPPLY
5898 | NC 2014 | K10 (2014) | Region VII | Bohol | 118610 | Canmano ES | SAGBAYAN (BORJA) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-18 | 070114S00431 | 15HC0014 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
5899 | NC 2014 | K10 (2014) | Region VII | Bohol | 118612 | Canmaya Diot ES | Sagbayan | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 070114S00243 | 15HC0013 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
5900 | NC 2014 | K10 (2014) | Region VII | Bohol | 118638 | Cansague Sur ES | SAN ISIDRO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1
5901 | NC 2014 | K10 (2014) | Region VII | Bohol | 118638 | Cansague Sur ES | San Isidro | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
5902 | NC 2014 | K10 (2014) | Region VII | Bohol | 118072 | Cantores PS | BUENAVISTA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-15 | 070114S00143 | 14HC0010 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | P.B. OBIAL CONSTRUCTION
5903 | NC 2014 | K10 (2014) | Region VII | Bohol | 118192 | Cantoyoc P/S | Clarin | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-12-31 | 070114S00271 | 15HC0001 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | PUREGOLD CONSTRUCTION & DEVT. CORP.
5904 | NC 2014 | K10 (2014) | Region VII | Bohol | 118073 | Cantuba ES | BUENAVISTA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070114S00144 | 14HC0036 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | WILTAN CONSTRUCTION
5905 | NC 2014 | K10 (2014) | Region VII | Bohol | 118648 | Capayas ES | SAN MIGUEL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00038 | 14HC0024 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | VIRLO CONSTRUCTION
5906 | NC 2014 | K10 (2014) | Region VII | Bohol | 118236 | Carbon PS | DANAO | 2 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 3 | 2003537.6289 |  |  | COMPLETED | 1 | 2015-11-18 | 2015-11-18 | 070114S00413 | 15HC0003 | 2015-04-02 | 2015-04-14 | 2015-04-15 | 2015-04-19 | 2015-04-23 | RAMONA CONSTRUCTION & ENTERPRISES
5907 | NC 2014 | K10 (2014) | Region VII | Bohol | 118813 | Casate ES | UBAY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2690828.124 |  |  | COMPLETED | 1 | 2015-12-23 | 2015-11-30 | 070114S00476 | 15HC0067 | 2015-08-05 | 2015-08-17 | 2015-08-18 | 2015-08-22 | 2015-08-26 | BNYU ENTERPRISES & CONSTRUCTION
5908 | NC 2014 | K10 (2014) | Region VII | Bohol | 500210 | Cataban Integrated School | TALIBON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-08-31 | 2015-08-31 | 070114S00060 | S-00060 | 2015-03-30 | 2015-04-11 | 2015-04-12 | 2015-04-16 | 2015-04-20 | By Administration
5909 | NC 2014 | K10 (2014) | Region VII | Bohol | 118074 | Catigbi-an ES | Buenavista | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-19 | 070114S00376 | 15HC0007 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | LEDA CONSTRUCTION INCORPORATED
5910 | NC 2014 | K10 (2014) | Region VII | Bohol | 118639 | Causwagan PS | San Isidro | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-08-31 | 070114S00252 | 15HC0005 | 2015-04-11 | 2015-04-23 | 2015-04-24 | 2015-04-28 | 2015-05-02 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5911 | NC 2014 | K10 (2014) | Region VII | Bohol | 118075 | Cawag ES | BUENAVISTA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070114S00145 | 14HC0010 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | P.B. OBIAL CONSTRUCTION
5912 | NC 2014 | K10 (2014) | Region VII | Bohol | 118193 | Clarin Central ES | CLARIN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2689245.2697 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-12-31 | 070114S00408 | 15HC0001 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | PUREGOLD CONSTRUCTION & DEVT. CORP.
5913 | NC 2014 | K10 (2014) | Region VII | Bohol | 118330 | Corte-Baud ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00210 | 14HC0016 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | EDANNA CONSTRUCTION
5914 | NC 2014 | K10 (2014) | Region VII | Bohol | 118372 | Cuaming ES | INABANGA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 070114S00174 | 14HC0041 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | DINAH JANE CONSTRUCTION SUPPLY
5915 | NC 2014 | K10 (2014) | Region VII | Bohol | 312337 | Dagnawan Integrated School | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-05-07 | 070114S00025 | 14HC0057 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | 3S BUILDERS
5916 | NC 2014 | K10 (2014) | Region VII | Bohol | 118238 | Dagohoy ES | DANAO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1
5917 | NC 2014 | K10 (2014) | Region VII | Bohol | 118373 | Dait Sur ES | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-30 | 2015-01-15 | 070114S00175 | 14HC0041 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | DINAH JANE CONSTRUCTION SUPPLY
5918 | NC 2014 | K10 (2014) | Region VII | Bohol | 118239 | Danao CES | DANAO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 070114S00290 | 15HC0003 | 2015-04-02 | 2015-04-14 | 2015-04-15 | 2015-04-19 | 2015-04-23 | RAMONA CONSTRUCTION & ENTERPRISES
5919 | NC 2014 | K10 (2014) | Region VII | Bohol | 118748 | Diis ES | TRINIDAD | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-03-02 | 070114S00052 | 14HC0052 | 2014-10-13 | 2014-10-25 | 2014-10-26 | 2014-10-30 | 2014-11-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5920 | NC 2014 | K10 (2014) | Region VII | Bohol | 302888 | Eugenio V. Amores NHS | Sagbayan | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1
5921 | NC 2014 | K10 (2014) | Region VII | Bohol | 118815 | Fatima ES | UBAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-20 | 070114S00011 | 14HC0032 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | PHILKONSTRACK DEVELOPMENT CORPORATION
5922 | NC 2014 | K10 (2014) | Region VII | Bohol | 118650 | Garcia ES | SAN MIGUEL | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-01-18 | 2015-01-18 | 070114S00046 | 14HC0025 | 2014-09-05 | 2014-09-17 | 2014-09-18 | 2014-09-22 | 2014-09-26 | VIRLO CONSTRUCTION
5923 | NC 2014 | K10 (2014) | Region VII | Bohol | 118595 | Gaus ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070114S00164 | 14HC0043 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | MAI CONSTRUCTION & SUPPLY
5924 | NC 2014 | K10 (2014) | Region VII | Bohol | 118817 | Gov. Boyles ES | UBAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2015-01-25 | 2015-01-20 | 070114S00010 | 14HC0055 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | PHILKONSTRACK DEVELOPMENT CORPORATION
5925 | NC 2014 | K10 (2014) | Region VII | Bohol | 118737 | Guindacpan ES | TALIBON | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2910174.43 |  |  | COMPLETED | 1 | 2015-08-31 | 2015-08-31 | 070114S00059 | S-00059 | 2015-04-14 | 2015-04-26 | 2015-04-27 | 2015-05-01 | 2015-05-05 | By Administration
5926 | NC 2014 | K10 (2014) | Region VII | Bohol | 118749 | Guinobatan ES | TRINIDAD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1177329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 070114S00051 | 14HC0028 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | BNYU ENTERPRISES & CONSTRUCTION
5927 | NC 2014 | K10 (2014) | Region VII | Bohol | 118818 | Guintaboan ES | UBAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-01-23 | 2015-01-23 | 070114S00009 | 14HC0029 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | DINAH JANE CONSTRUCTION SUPPLY
5928 | NC 2014 | K10 (2014) | Region VII | Bohol | 118651 | Hagbuyo PS | SAN MIGUEL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052703.8954 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 070114S00227 | 14HC0061 | 2014-10-21 | 2014-11-02 | 2014-11-03 | 2014-11-07 | 2014-11-11 | WILTAN CONSTRUCTION
5929 | NC 2014 | K10 (2014) | Region VII | Bohol | 118819 | Hambabauran ES | UBAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-15 | 070114S00001 | 14HC0030 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | DINAH JANE CONSTRUCTION SUPPLY
5930 | NC 2014 | K10 (2014) | Region VII | Bohol | 302828 | Handumon NHS | JETAFE | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2699295.2697 |  |  | COMPLETED | 1
5931 | NC 2014 | K10 (2014) | Region VII | Bohol | 118332 | Handumon ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-15 | 070114S00209 | 14HC0016 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | EDANNA CONSTRUCTION
5932 | NC 2014 | K10 (2014) | Region VII | Bohol | 302857 | Hingotanan NHS | BIEN UNIDO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2940174.43 |  |  | COMPLETED | 1
5933 | NC 2014 | K10 (2014) | Region VII | Bohol | 118820 | Humayhumay ES | UBAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00007 | 14HC0031 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
5934 | NC 2014 | K10 (2014) | Region VII | Bohol | 118377 | Ilaya P/S | Inabanga | 2 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 3 | 2003537.6289 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-12-31 | 070114S00280 | 15HC0044 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | LCG CONSTRUCTION
5935 | NC 2014 | K10 (2014) | Region VII | Bohol | 118821 | Ilihan ES | UBAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1092218.8144 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-19 | 070114S00422 | 15HC0016 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | MAI CONSTRUCTION & SUPPLY
5936 | NC 2014 | K10 (2014) | Region VII | Bohol | 118400 | Ilihan PS | INABANGA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1
5937 | NC 2014 | K10 (2014) | Region VII | Bohol | 118400 | Ilihan PS | Inabanga | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
5938 | NC 2014 | K10 (2014) | Region VII | Bohol | 500209 | Inabanga North Integrated School | INABANGA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1
5939 | NC 2014 | K10 (2014) | Region VII | Bohol | 312341 | Inabanga North Intrgrated School | Inabanga | 2 | 1 | 11 | 2UNITS 1STY3CL, 2UNITS 1STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 9775788.4937 |  |  | COMPLETED | 1
5940 | NC 2014 | K10 (2014) | Region VII | Bohol | 118378 | Inabanga North IS | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
5941 | NC 2014 | K10 (2014) | Region VII | Bohol | 118333 | Jagoliao ES | JETAFE | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-16 | 070114S00414 | 15HC0015 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | BNYU ENTERPRISES & CONSTRUCTION
5942 | NC 2014 | K10 (2014) | Region VII | Bohol | 118738 | Jao ES | TALIBON | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3830805.49 |  |  | COMPLETED | 1 | 2015-07-30 | 2015-06-30 | 070114S00058 | S-00058 | 2015-02-09 | 2015-02-21 | 2015-02-22 | 2015-02-26 | 2015-03-02 | By Administration
5943 | NC 2014 | K10 (2014) | Region VII | Bohol | 118823 | Juagdan ES | Ubay | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-15 | 070114S00256 | 15HC0016 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | MAI CONSTRUCTION & SUPPLY
5944 | NC 2014 | K10 (2014) | Region VII | Bohol | 118225 | Kagawitan ES | DAGOHOY | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3514886.575 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-15 | 070114S00477 | 15HC0057 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5945 | NC 2014 | K10 (2014) | Region VII | Bohol | 118615 | Katipunan ES | SAGBAYAN (BORJA) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2015-01-17 | 2015-01-17 | 070114S00043 | 14HC0022 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | SLP CONSTRUCTION
5946 | NC 2014 | K10 (2014) | Region VII | Bohol | 302862 | Kauswagan NHS | TRINIDAD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-03-02 | 070114S00018 | 14HC0052 | 2014-10-13 | 2014-10-25 | 2014-10-26 | 2014-10-30 | 2014-11-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5947 | NC 2014 | K10 (2014) | Region VII | Bohol | 118652 | La Esperanza ES | Dagohoy | 2 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 3576429.1398 |  |  | COMPLETED | 1
5948 | NC 2014 | K10 (2014) | Region VII | Bohol | 118754 | La Union ES | TRINIDAD | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-15 | 070114S00050 | 14HC0051 | 2014-10-02 | 2014-10-14 | 2014-10-15 | 2014-10-19 | 2014-10-23 | PHILKONSTRACK DEVELOPMENT CORPORATION
5949 | NC 2014 | K10 (2014) | Region VII | Bohol | 118381 | Liloan Sur ES | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-01-23 | 2015-01-23 | 070114S00182 | 14HC0019 | 2014-09-05 | 2014-09-17 | 2014-09-18 | 2014-09-22 | 2014-09-26 | YU CONSTRUCTION
5950 | NC 2014 | K10 (2014) | Region VII | Bohol | 118598 | Lipata ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-04 | 2015-02-04 | 070114S00085 | 14HC0020 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | MAI CONSTRUCTION & SUPPLY
5951 | NC 2014 | K10 (2014) | Region VII | Bohol | 118078 | Lubang ES | Buenavista | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-19 | 070114S00430 | 15HC0006 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | LEDA CONSTRUCTION INCORPORATED
5952 | NC 2014 | K10 (2014) | Region VII | Bohol | 302831 | Lubang NHS | BUENAVISTA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1097703.8954 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 070114S00222 | 14HC0059 | 2014-10-30 | 2014-11-10 | 2014-11-11 | 2014-11-15 | 2014-11-19 | L.C. CONSTRUCTION
5953 | NC 2014 | K10 (2014) | Region VII | Bohol | 118404 | Lutao ES | Inabanga | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-18 | 070114S00288 | 15HC0011 | 2015-04-01 | 2015-04-13 | 2015-04-14 | 2015-04-18 | 2015-04-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5954 | NC 2014 | K10 (2014) | Region VII | Bohol | 118405 | Luyo PS | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-01-23 | 2015-01-23 | 070114S00184 | 14HC0019 | 2014-09-05 | 2014-09-17 | 2014-09-18 | 2014-09-22 | 2014-09-26 | YU CONSTRUCTION
5955 | NC 2014 | K10 (2014) | Region VII | Bohol | 118827 | Luz ES | UBAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 070114S00014 | 14HC0030 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | DINAH JANE CONSTRUCTION SUPPLY
5956 | NC 2014 | K10 (2014) | Region VII | Bohol | 118406 | Mabuhay PS | Inabanga | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-18 | 070114S00278 | 15HC0011 | 2015-04-01 | 2015-04-13 | 2015-04-14 | 2015-04-18 | 2015-04-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5957 | NC 2014 | K10 (2014) | Region VII | Bohol | 118079 | Magkaya ES | BUENAVISTA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1
5958 | NC 2014 | K10 (2014) | Region VII | Bohol | 118079 | Magkaya ES | Buenavista | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
5959 | NC 2014 | K10 (2014) | Region VII | Bohol | 118242 | Magtangtang ES | DANAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-08-31 | 070114S00264 | 15HC0004 | 2015-04-01 | 2015-04-13 | 2015-04-14 | 2015-04-18 | 2015-04-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5960 | NC 2014 | K10 (2014) | Region VII | Bohol | 118120 | Mahangin ES | Candijay | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-12-31 | 070114S00255 | 15HC0073 | 2015-07-28 | 2015-08-09 | 2015-08-10 | 2015-08-14 | 2015-08-18 | AE BELLEZA BUILDERS
5961 | NC 2014 | K10 (2014) | Region VII | Bohol | 302873 | Mahayag NHS | SAN MIGUEL | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2035417.57 |  |  | COMPLETED | 1
5962 | NC 2014 | K10 (2014) | Region VII | Bohol | 118227 | Mahayag PS | DAGOHOY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00194 | 14HC0014 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | PHILKONSTRACK DEVELOPMENT CORPORATION
5963 | NC 2014 | K10 (2014) | Region VII | Bohol | 118032 | Malingin ES | BIEN UNIDO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-04-09 | 2015-04-09 | 070114S00125 | 14HC0044 | 2014-12-15 | 2014-12-27 | 2014-12-28 | 2015-01-01 | 2015-01-05 | YS CONSTRUCTION
5964 | NC 2014 | K10 (2014) | Region VII | Bohol | 118228 | Malitbog ES | DAGOHOY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 070114S00208 | 14HC0013 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
5965 | NC 2014 | K10 (2014) | Region VII | Bohol | 118383 | Nabuad ES | Inabanga | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-10-20 | 070114S00279 | 15HC0046 | 2015-06-10 | 2015-06-22 | 2015-06-23 | 2015-06-27 | 2015-07-01 | 3N CONSTRUCTION & SUPPLY
5966 | NC 2014 | K10 (2014) | Region VII | Bohol | 118197 | Nahawan ES | CLARIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1
5967 | NC 2014 | K10 (2014) | Region VII | Bohol | 118197 | Nahawan ES | Clarin | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3404228.7213 |  |  | COMPLETED | 1
5968 | NC 2014 | K10 (2014) | Region VII | Bohol | 118243 | Nahud ES | DANAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1858564.5699 |  |  | COMPLETED | 1 | 2015-11-17 | 2015-11-17 | 070114S00409 | 15HC0004 | 2015-04-01 | 2015-04-13 | 2015-04-14 | 2015-04-18 | 2015-04-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5969 | NC 2014 | K10 (2014) | Region VII | Bohol | 118337 | Nasingin ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-15 | 070114S00202 | 14HC0016 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | EDANNA CONSTRUCTION
5970 | NC 2014 | K10 (2014) | Region VII | Bohol | 118740 | Nocnocan ES | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-03-23 | 2015-03-23 | 070114S00057 | 14HC0044 | 2014-10-29 | 2014-11-10 | 2014-11-11 | 2014-11-15 | 2014-11-19 | BNYU ENTERPRISES & CONSTRUCTION
5971 | NC 2014 | K10 (2014) | Region VII | Bohol | 118036 | Nueva Estrella ES | BIEN UNIDO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-04-09 | 2015-04-09 | 070114S00137 | 14HC0044 | 2014-12-15 | 2014-12-27 | 2014-12-28 | 2015-01-01 | 2015-01-05 | YS CONSTRUCTION
5972 | NC 2014 | K10 (2014) | Region VII | Bohol | 118080 | Nueva Granada ES | BUENAVISTA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2015-06-30 | 2015-06-30 | 070114S00178 | 14HC0035 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | VIRLO CONSTRUCTION
5973 | NC 2014 | K10 (2014) | Region VII | Bohol | 118081 | Nueva Montana ES | Buenavista | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
5974 | NC 2014 | K10 (2014) | Region VII | Bohol | 118081 | Nueva Montaña ES | BUENAVISTA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
5975 | NC 2014 | K10 (2014) | Region VII | Bohol | 118082 | Overland ES | BUENAVISTA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
5976 | NC 2014 | K10 (2014) | Region VII | Bohol | 118082 | Overland ES | Buenavista | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
5977 | NC 2014 | K10 (2014) | Region VII | Bohol | 118083 | P. Tirol ES | Buenavista | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-19 | 070114S00267 | 15HC0007 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | LEDA CONSTRUCTION INCORPORATED
5978 | NC 2014 | K10 (2014) | Region VII | Bohol | 118732 | P/Lt. Eugenio B. Artiaga ES | TALIBON | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-03-23 | 2015-03-23 | 070114S00032 | 14HC0044 | 2014-10-29 | 2014-11-10 | 2014-11-11 | 2014-11-15 | 2014-11-19 | BNYU ENTERPRISES & CONSTRUCTION
5979 | NC 2014 | K10 (2014) | Region VII | Bohol | 118828 | Pag-asa ES | UBAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 070114S00006 | 14HC0056 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-11-01 | 2014-11-05 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
5980 | NC 2014 | K10 (2014) | Region VII | Bohol | 118338 | Pandanon ES | JETAFE | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1
5981 | NC 2014 | K10 (2014) | Region VII | Bohol | 312322 | Pandanon HS | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070114S00015 | 14HC0038 | 2014-10-14 | 2014-10-26 | 2014-10-27 | 2014-10-31 | 2014-11-04 | BANTAY CONSTRUCTION
5982 | NC 2014 | K10 (2014) | Region VII | Bohol | 118084 | Panghagban ES | BUENAVISTA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2740828.124 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-15 | 070114S00469 | 15HC0058 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | DINAH JANE CONSTRUCTION SUPPLY
5983 | NC 2014 | K10 (2014) | Region VII | Bohol | 118037 | Pinamgo ES | BIEN UNIDO | 2 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 2 | 4677514.4199 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070114S00219 | 14HC0044 | 2014-12-22 | 2015-01-03 | 2015-01-04 | 2015-01-08 | 2015-01-12 | YS CONSTRUCTION
5984 | NC 2014 | K10 (2014) | Region VII | Bohol | 118085 | Plateau PS | BUENAVISTA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1
5985 | NC 2014 | K10 (2014) | Region VII | Bohol | 312331 | Ponciana E. Leoligao HS | TALIBON | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1920466.749 |  |  | COMPLETED | 1
5986 | NC 2014 | K10 (2014) | Region VII | Bohol | 302895 | Pres. Carlos P. Garcia MHS | TALIBON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1
5987 | NC 2014 | K10 (2014) | Region VII | Bohol | 118086 | Putingbato ES | BUENAVISTA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1097703.8954 |  |  | COMPLETED | 1 | 2015-04-17 | 2015-04-17 | 070114S00220 | 14HC0059 | 2014-10-29 | 2014-11-10 | 2014-11-11 | 2014-11-15 | 2014-11-19 | L.C. CONSTRUCTION
5988 | NC 2014 | K10 (2014) | Region VII | Bohol | 118087 | Rufo Hill ES | BUENAVISTA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00201 | 14HC0011 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | PHILKONSTRACK DEVELOPMENT CORPORATION
5989 | NC 2014 | K10 (2014) | Region VII | Bohol | 118741 | Sag ES | TALIBON | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2975174.43 |  |  | COMPLETED | 1 | 2015-08-31 | 2015-08-31 | 070114S00056 | S-00056 | 2015-02-09 | 2015-02-21 | 2015-02-22 | 2015-02-26 | 2015-03-02 | By Administration
5990 | NC 2014 | K10 (2014) | Region VII | Bohol | 118039 | Sagasa ES | BIEN UNIDO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-06-30 | 2015-06-30 | 070114S00138 | S-00138 | 2015-02-09 | 2015-02-21 | 2015-02-22 | 2015-02-26 | 2015-03-02 | By Administration
5991 | NC 2014 | K10 (2014) | Region VII | Bohol | 118618 | Sagbayan Central ES | Sagbayan | 2 | 1 | 21 | 4UNITS 1STY3CL, 3UNITS 1STY2CL & 3UNITS 1STY1CL | 2014 K10 BATCH 3 | 18765131.2318 |  |  | COMPLETED | 1 | 2015-10-27 | 2015-09-30 | 070114S00248 | 15HC0012 | 2015-03-11 | 2015-03-23 | 2015-03-24 | 2015-03-28 | 2015-04-01 | YS CONSTRUCTION
5992 | NC 2014 | K10 (2014) | Region VII | Bohol | 118620 | San Agustin ES | Sagbayan | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-19 | 070114S00241 | 15HC0014 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
5993 | NC 2014 | K10 (2014) | Region VII | Bohol | 118723 | San Agustin ES | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00033 | 14HC0045 | 2014-10-16 | 2014-10-28 | 2014-10-29 | 2014-11-02 | 2014-11-06 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
5994 | NC 2014 | K10 (2014) | Region VII | Bohol | 118621 | San Antonio ES | Sagbayan | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 070114S00240 | 15HC0014 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
5995 | NC 2014 | K10 (2014) | Region VII | Bohol | 118742 | San Francisco ES | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00078 | 14HC0027 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | DINAH JANE CONSTRUCTION SUPPLY
5996 | NC 2014 | K10 (2014) | Region VII | Bohol | 118830 | San Francisco ES | UBAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00005 | 14HC0031 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
5997 | NC 2014 | K10 (2014) | Region VII | Bohol | 118641 | San Isidro Central ES | San Isidro | 2 | 1 | 5 | 2UNITS 1STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 4578197.9542 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-10-28 | 070114S00246 | 15HC0005 | 2015-04-11 | 2015-04-23 | 2015-04-24 | 2015-04-28 | 2015-05-02 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
5998 | NC 2014 | K10 (2014) | Region VII | Bohol | 118387 | San Isidro ES | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-15 | 070114S00179 | 14HC0018 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | MAI CONSTRUCTION & SUPPLY
5999 | NC 2014 | K10 (2014) | Region VII | Bohol | 118654 | San Isidro ES | SAN MIGUEL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00036 | 14HC0024 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | VIRLO CONSTRUCTION
6000 | NC 2014 | K10 (2014) | Region VII | Bohol | 118762 | San Isidro ES | TRINIDAD | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 070114S00049 | 14HC0028 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | BNYU ENTERPRISES & CONSTRUCTION
6001 | NC 2014 | K10 (2014) | Region VII | Bohol | 118831 | San Isidro ES | UBAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-23 | 2015-01-23 | 070114S00004 | 14HC0029 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | DINAH JANE CONSTRUCTION SUPPLY
6002 | NC 2014 | K10 (2014) | Region VII | Bohol | 312350 | San Isidro HS | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
6003 | NC 2014 | K10 (2014) | Region VII | Bohol | 500114 | San Isidro IS | Sagbayan | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3404228.7213 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-19 | 070114S00239 | 15HC0014 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
6004 | NC 2014 | K10 (2014) | Region VII | Bohol | 118388 | San Jose E/S | Inabanga | 2 | 1 | 7 | 1STY4CL & 1STY3CL | 2014 K10 BATCH 3 | 6003023.991 |  |  | COMPLETED | 1 | 2015-09-12 | 2015-08-31 | 070114S00282 | 15HC0008 | 2015-02-24 | 2015-03-08 | 2015-03-09 | 2015-03-13 | 2015-03-17 | YS CONSTRUCTION
6005 | NC 2014 | K10 (2014) | Region VII | Bohol | 118341 | San Jose ES | JETAFE | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-10-20 | 2015-09-18 | 070114S00415 | 15HC0015 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | BNYU ENTERPRISES & CONSTRUCTION
6006 | NC 2014 | K10 (2014) | Region VII | Bohol | 118604 | San Jose ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-02-04 | 2015-02-04 | 070114S00044 | 14HC0020 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | MAI CONSTRUCTION & SUPPLY
6007 | NC 2014 | K10 (2014) | Region VII | Bohol | 302891 | San Jose NHS | INABANGA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2797047.671 |  |  | COMPLETED | 1
6008 | NC 2014 | K10 (2014) | Region VII | Bohol | 302891 | San Jose NHS | Inabanga | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1
6009 | NC 2014 | K10 (2014) | Region VII | Bohol | 118247 | San Jose PS | DANAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-08-31 | 070114S00410 | 15HC0004 | 2015-04-01 | 2015-04-13 | 2015-04-14 | 2015-04-18 | 2015-04-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
6010 | NC 2014 | K10 (2014) | Region VII | Bohol | 118248 | San Miguel PS | DANAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1868614.5699 |  |  | COMPLETED | 1 | 2015-10-19 | 2015-08-31 | 070114S00411 | 15HC0003 | 2015-04-02 | 2015-04-14 | 2015-04-15 | 2015-04-19 | 2015-04-23 | RAMONA CONSTRUCTION & ENTERPRISES
6011 | NC 2014 | K10 (2014) | Region VII | Bohol | 302897 | San Miguel Technical Vocational School | SAN MIGUEL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1117703.8954 |  |  | COMPLETED | 1
6012 | NC 2014 | K10 (2014) | Region VII | Bohol | 118726 | San Roque ES | TALIBON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-10-10 | 2015-06-30 | 070114S00419 | 15HC0015 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | BNYU ENTERPRISES & CONSTRUCTION
6013 | NC 2014 | K10 (2014) | Region VII | Bohol | 118602 | San Vicente ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070114S00045 | 14HC0043 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | MAI CONSTRUCTION & SUPPLY
6014 | NC 2014 | K10 (2014) | Region VII | Bohol | 118763 | San Vicente ES | TRINIDAD | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-15 | 070114S00048 | 14HC0051 | 2014-10-02 | 2014-10-14 | 2014-10-15 | 2014-10-19 | 2014-10-23 | PHILKONSTRACK DEVELOPMENT CORPORATION
6015 | NC 2014 | K10 (2014) | Region VII | Bohol | 118833 | San Vicente ES | UBAY | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3860805.49 |  |  | COMPLETED | 1 | 2015-06-30 | 2015-06-30 | 070114S00003 | 14HC0053 | 2014-10-13 | 2014-10-25 | 2014-10-26 | 2014-10-30 | 2014-11-03 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6016 | NC 2014 | K10 (2014) | Region VII | Bohol | 118625 | San Vicente Norte PS | Sagbayan | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 070114S00238 | 15HC0013 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
6017 | NC 2014 | K10 (2014) | Region VII | Bohol | 118657 | San Vicente PS | SAN MIGUEL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00035 | 14HC0024 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | VIRLO CONSTRUCTION
6018 | NC 2014 | K10 (2014) | Region VII | Bohol | 118626 | San Vicente Sur PS | Sagbayan | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-18 | 070114S00237 | 15HC0013 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
6019 | NC 2014 | K10 (2014) | Region VII | Bohol | 118251 | Santo Niño PS | DANAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1858564.5699 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-08-31 | 070114S00412 | 15HC0004 | 2015-04-01 | 2015-04-13 | 2015-04-14 | 2015-04-18 | 2015-04-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
6020 | NC 2014 | K10 (2014) | Region VII | Bohol | 118834 | Sentinela ES | UBAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-24 | 070114S00002 | 14HC0055 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | PHILKONSTRACK DEVELOPMENT CORPORATION
6021 | NC 2014 | K10 (2014) | Region VII | Bohol | 118727 | Sikatuna ES | TALIBON | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1858564.5699 |  |  | COMPLETED | 1 | 2015-10-19 | 2015-08-31 | 070114S00418 | 15HC0015 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | BNYU ENTERPRISES & CONSTRUCTION
6022 | NC 2014 | K10 (2014) | Region VII | Bohol | 500216 | Soom Integrated School | TRINIDAD | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1137703.8954 |  |  | COMPLETED | 1 | 2015-04-04 | 2015-04-04 | 070114S00235 | 14HC0060 | 2014-10-16 | 2014-10-28 | 2014-10-29 | 2014-11-02 | 2014-11-06 | MAI CONSTRUCTION & SUPPLY
6023 | NC 2014 | K10 (2014) | Region VII | Bohol | 500216 | Soom IS | TRINIDAD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 070114S00055 | 14HC0028 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | BNYU ENTERPRISES & CONSTRUCTION
6024 | NC 2014 | K10 (2014) | Region VII | Bohol | 118401 | South Inabannga Central Sch | Inabanga | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
6025 | NC 2014 | K10 (2014) | Region VII | Bohol | 302859 | Southern Inabanga HS | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
6026 | NC 2014 | K10 (2014) | Region VII | Bohol | 118627 | Sta. Catalina ES | Sagbayan | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 070114S00245 | 15HC0013 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
6027 | NC 2014 | K10 (2014) | Region VII | Bohol | 118658 | Sto. Niño PS | SAN MIGUEL | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00016 | 14HC0014 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | PHILKONSTRACK DEVELOPMENT CORPORATION
6028 | NC 2014 | K10 (2014) | Region VII | Bohol | 118407 | Sto. Rosario ES | Inabanga | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-09-12 | 2015-08-31 | 070114S00244 | 15HC0008 | 2015-02-24 | 2015-03-08 | 2015-03-09 | 2015-03-13 | 2015-03-17 | YS CONSTRUCTION
6029 | NC 2014 | K10 (2014) | Region VII | Bohol | 302910 | Tagum Sur NHS | TRINIDAD | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1940466.749 |  |  | COMPLETED | 1
6030 | NC 2014 | K10 (2014) | Region VII | Bohol | 118743 | Talibon II Central ES | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 070114S00054 | 14HC0032 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | PHILKONSTRACK DEVELOPMENT CORPORATION
6031 | NC 2014 | K10 (2014) | Region VII | Bohol | 118408 | Tambooc P/S | Inabanga | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-05 | 2015-11-05 | 070114S00284 | 15HC0041 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | MAI CONSTRUCTION & SUPPLY
6032 | NC 2014 | K10 (2014) | Region VII | Bohol | 302844 | Taming NHS | DANAO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
6033 | NC 2014 | K10 (2014) | Region VII | Bohol | 118838 | Tintinan ES | UBAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070114S00008 | 14HC0054 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | WILTAN CONSTRUCTION
6034 | NC 2014 | K10 (2014) | Region VII | Bohol | 118659 | Tomoc ES | San Miguel | 2 | 1 | 4 | 1STY3CL & 1STY1CL | 2014 K10 BATCH 3 | 3600564.0842 |  |  | COMPLETED | 1 | 2015-11-19 | 2015-11-19 | 070114S00260 | 15HC0052 | 2015-07-02 | 2015-07-14 | 2015-07-15 | 2015-07-19 | 2015-07-23 | RAMONA CONSTRUCTION & ENTERPRISES
6035 | NC 2014 | K10 (2014) | Region VII | Bohol | 118128 | Tubod ES | Candijay | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-12-31 | 070114S00254 | 15HC0072 | 2015-07-28 | 2015-08-09 | 2015-08-10 | 2015-08-14 | 2015-08-18 | AE BELLEZA BUILDERS
6036 | NC 2014 | K10 (2014) | Region VII | Bohol |  | Tugas ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-20 | 070114S00171 | 14HC0015 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | MAI CONSTRUCTION & SUPPLY
6037 | NC 2014 | K10 (2014) | Region VII | Bohol | 118606 | Tugas ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4A | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-31 | 070114S00460 | 15HC0037 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-07-20 | 2015-07-24 | MAI CONSTRUCTION & SUPPLY
6038 | NC 2014 | K10 (2014) | Region VII | Bohol | 118345 | Tulang ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-02-04 | 2015-02-04 | 070114S00172 | 14HC0017 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | EDANNA CONSTRUCTION
6039 | NC 2014 | K10 (2014) | Region VII | Bohol | 302913 | Tulang NHS | JETAFE | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1
6040 | NC 2014 | K10 (2014) | Region VII | Bohol | 186506 | Tunaan-Daku ES | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-08-31 | 2015-08-31 | 070114S00023 | S-00023 | 2015-04-15 | 2015-04-27 | 2015-04-28 | 2015-05-02 | 2015-05-06 | By Administration
6041 | NC 2014 | K10 (2014) | Region VII | Bohol | 302915 | Ubay National Science HS | UBAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1
6042 | NC 2014 | K10 (2014) | Region VII | Bohol | 118629 | Ubojan ES | Sagbayan | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
6043 | NC 2014 | K10 (2014) | Region VII | Bohol | 118629 | Ubojan ES | SAGBAYAN (BORJA) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
6044 | NC 2014 | K10 (2014) | Region VII | Bohol | 118844 | Union ES | UBAY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2690828.124 |  |  | COMPLETED | 1 | 2016-01-22 |  | 070114S00475 | 15HC0068 | 2015-08-05 | 2015-08-17 | 2015-08-18 | 2015-08-22 | 2015-08-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
6045 | NC 2014 | K10 (2014) | Region VII | Bohol | 118410 | U-OG Ubuan ES | Inabanga | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
6046 | NC 2014 | K10 (2014) | Region VII | Bohol | 118410 | U-og Ubujan ES | INABANGA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1
6047 | NC 2014 | K10 (2014) | Region VII | Bohol | 186503 | Villaflor P/S | Clarin | 2 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 3 | 2003537.6289 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-12-31 | 070114S00272 | 15HC0002 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | PUREGOLD CONSTRUCTION & DEVT. CORP.
6048 | NC 2014 | K10 (2014) | Region VII | Bohol | 118510 | Abaca ES | MABINI | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 070114S00090 | 14HB0028 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6049 | NC 2014 | K10 (2014) | Region VII | Bohol | 118130 | Alegria ES | Carmen | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 070114S00336 | 14HB0064 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
6050 | NC 2014 | K10 (2014) | Region VII | Bohol | 118847 | Anas ES | Valencia | 3 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1 | 2015-07-10 | 2015-07-10 | 070114S00302 | 14HB0069 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6051 | NC 2014 | K10 (2014) | Region VII | Bohol | 118284 | Anibongan PS | DUERO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052703.8954 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070114S00232 | 14HB0032 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6052 | NC 2014 | K10 (2014) | Region VII | Bohol | 118848 | Anonang ES | Valencia | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 070114S00300 | 14HB0070 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6053 | NC 2014 | K10 (2014) | Region VII | Bohol | 118567 | Bagumbayan ES | PILAR | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1041968.8144 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00326 | 14HB0062 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6054 | NC 2014 | K10 (2014) | Region VII | Bohol | 118411 | Balili ES | Jagna | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070114S00307 | 14HB0073 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6055 | NC 2014 | K10 (2014) | Region VII | Bohol | 312356 | Bangwalog HS | DUERO | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1848514.5699 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 070114S00345 | 14HB0074 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
6056 | NC 2014 | K10 (2014) | Region VII | Bohol | 302815 | Batuan NHS | BATUAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1082168.8144 |  |  | COMPLETED | 1
6057 | NC 2014 | K10 (2014) | Region VII | Bohol | 118660 | Bayawahan ES | Sevilla | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070114S00330 | 14HB0067 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | A.S. OBQUIA CONSTRUCTION
6058 | NC 2014 | K10 (2014) | Region VII | Bohol | 118514 | Baybayon ES | MABINI | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 070114S00089 | 14HB0028 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6059 | NC 2014 | K10 (2014) | Region VII | Bohol | 118131 | Bicao ES | Carmen | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 070114S00337 | 14HB0064 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
6060 | NC 2014 | K10 (2014) | Region VII | Bohol | 118132 | Bohog ES | CARMEN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1
6061 | NC 2014 | K10 (2014) | Region VII | Bohol | 118132 | Bohog ES | Carmen | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
6062 | NC 2014 | K10 (2014) | Region VII | Bohol | 312329 | Bugsoc High School | SIERRA BULLONES | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070114S00073 | 14HB0029 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6063 | NC 2014 | K10 (2014) | Region VII | Bohol | 118350 | Bulawan ES | GUINDULMAN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00119 | 14HB0027 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6064 | NC 2014 | K10 (2014) | Region VII | Bohol | 118413 | Bunga Ilaya PS | JAGNA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1232329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00124 | 14HB0026 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6065 | NC 2014 | K10 (2014) | Region VII | Bohol | 118044 | Cabacnitan ES | Bilar | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
6066 | NC 2014 | K10 (2014) | Region VII | Bohol | 117937 | Cabatang ES | ALICIA | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1052018.8144 |  |  | COMPLETED | 1 | 2015-08-23 | 2015-08-23 | 070114S00261 | 14HB0060 | 2015-02-02 | 2015-02-04 | 2015-02-16 | 2015-02-25 | 2015-03-18 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6067 | NC 2014 | K10 (2014) | Region VII | Bohol | 118516 | Cabidian ES | MABINI | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 070114S00088 | 14HB0028 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6068 | NC 2014 | K10 (2014) | Region VII | Bohol | 500207 | Calatrava Integrated School | CARMEN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1
6069 | NC 2014 | K10 (2014) | Region VII | Bohol | 118662 | Calingaan PS | Sevilla | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070114S00292 | 14HB0067 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | A.S. OBQUIA CONSTRUCTION
6070 | NC 2014 | K10 (2014) | Region VII | Bohol | 118017 | Cambacay P/S | Batuan | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-05-14 | 2015-05-14 | 070114S00331 | 14HB0065 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6071 | NC 2014 | K10 (2014) | Region VII | Bohol | 118418 | Cambugason ES | JAGNA | 3 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3850805.49 |  |  | COMPLETED | 1 | 2015-04-14 | 2015-04-14 | 070114S00114 | 14HB0026 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6072 | NC 2014 | K10 (2014) | Region VII | Bohol | 118306 | Cambuyo ES | Garcia Hernandez | 3 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2015-08-09 | 2015-08-09 | 070114S00291 | 14HB0072 | 2014-12-02 | 2014-12-10 | 2014-12-23 | 2014-12-29 | 2015-01-12 | LTS BUILDERS AND CONSTRUCTION SUPPLY
6073 | NC 2014 | K10 (2014) | Region VII | Bohol | 312352 | Cambuyo HS | GARCIA HERNANDEZ | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1930466.749 |  |  | COMPLETED | 1
6074 | NC 2014 | K10 (2014) | Region VII | Bohol | 302865 | Candijay HS | CANDIJAY | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1
6075 | NC 2014 | K10 (2014) | Region VII | Bohol | 118852 | Canduao ES | Valencia | 3 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 3 | 4194992.4492 |  |  | COMPLETED | 1 | 2015-07-08 | 2015-07-08 | 070114S00299 | 14HB0069 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6076 | NC 2014 | K10 (2014) | Region VII | Bohol | 118420 | Canjulao ES | JAGNA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00063 | 14HB0026 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6077 | NC 2014 | K10 (2014) | Region VII | Bohol | 118677 | Canlangit ES | Sierra Bullones | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00297 | 14HB0063 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6078 | NC 2014 | K10 (2014) | Region VII | Bohol | 118865 | Cansibao ES | VALENCIA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-24 | 070114S00079 | 14HB0030 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6079 | NC 2014 | K10 (2014) | Region VII | Bohol | 118354 | Cansiwang ES | GUINDULMAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00118 | 14HB0027 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6080 | NC 2014 | K10 (2014) | Region VII | Bohol | 118571 | Cansungay ES | PILAR | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1041968.8144 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00327 | 14HB0062 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6081 | NC 2014 | K10 (2014) | Region VII | Bohol | 118678 | Canta-ub ES | Sierra Bullones | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00296 | 14HB0063 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6082 | NC 2014 | K10 (2014) | Region VII | Bohol | 118018 | Cantigdas ES | BATUAN | 3 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 4000835.14 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-01-09 | 070114S00095 | 14HB0021 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-28 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6083 | NC 2014 | K10 (2014) | Region VII | Bohol | 118154 | Carmen East Central ES | Carmen | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00341 | 14HB0065 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6084 | NC 2014 | K10 (2014) | Region VII | Bohol | 118355 | Casbu ES | GUINDULMAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00109 | 14HB0027 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6085 | NC 2014 | K10 (2014) | Region VII | Bohol | 118274 | Catugasan ES | DIMIAO | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1864740.174 |  |  | COMPLETED | 1 | 2016-02-13 |  | 070114S00471 | 15HB0032 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6086 | NC 2014 | K10 (2014) | Region VII | Bohol | 302834 | Catungawan NHS | Guindulman | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
6087 | NC 2014 | K10 (2014) | Region VII | Bohol | 118446 | Conception ES | Loay | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 070114S00305 | 14HB0070 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6088 | NC 2014 | K10 (2014) | Region VII | Bohol | 118048 | Dagohoy ES | Bilar | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 070114S00333 | 14HB0066 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | LTS BUILDERS AND CONSTRUCTION SUPPLY
6089 | NC 2014 | K10 (2014) | Region VII | Bohol | 118310 | Datag ES | Garcia Hernandez | 3 | 1 | 6 | 1STY3CL, 1STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 5388778.6541 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-12-15 | 070114S00304 | 15HB0029 | 2015-05-13 | 2015-05-15 | 2015-05-27 | 2015-06-04 | 2015-06-26 | LTS BUILDERS AND CONSTRUCTION SUPPLY
6090 | NC 2014 | K10 (2014) | Region VII | Bohol | 118518 | Del Mar ES | MABINI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1868614.5699 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00322 | 14HB0061 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6091 | NC 2014 | K10 (2014) | Region VII | Bohol | 118682 | Dusita ES | SIERRA BULLONES | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070114S00082 | 14HB0029 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6092 | NC 2014 | K10 (2014) | Region VII | Bohol | 302848 | Dusita NHS | Sierra Bullones | 3 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 3576429.1398 |  |  | COMPLETED | 1
6093 | NC 2014 | K10 (2014) | Region VII | Bohol | 118137 | El Progreso ES | Carmen | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00339 | 14HB0065 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6094 | NC 2014 | K10 (2014) | Region VII | Bohol | 118138 | El Salvador ES | Carmen | 3 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 3 | 2003537.6289 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00340 | 14HB0065 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6095 | NC 2014 | K10 (2014) | Region VII | Bohol | 118312 | Garcia Hernandez Central ES | Garcia Hernandez | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
6096 | NC 2014 | K10 (2014) | Region VII | Bohol | 118312 | Garcia-Hernandez Central ES | GARCIA HERNANDEZ | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
6097 | NC 2014 | K10 (2014) | Region VII | Bohol | 118139 | Guadalupe ES | CARMEN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00101 | 14HB0023 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | AL CHRIS CONSTRUCTION
6098 | NC 2014 | K10 (2014) | Region VII | Bohol | 302854 | Guinacot NHS | GUINDULMAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
6099 | NC 2014 | K10 (2014) | Region VII | Bohol | 302855 | Guinsularan High School | DUERO | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
6100 | NC 2014 | K10 (2014) | Region VII | Bohol | 118359 | Guio-ang ES | GUINDULMAN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00116 | 14HB0027 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6101 | NC 2014 | K10 (2014) | Region VII | Bohol | 302867 | Hinawanan NHS | LOAY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1
6102 | NC 2014 | K10 (2014) | Region VII | Bohol | 312358 | Jagna HS | JAGNA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
6103 | NC 2014 | K10 (2014) | Region VII | Bohol | 118436 | Jambawan ES | LILA | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052703.8954 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 070114S00233 | 14HB0032 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6104 | NC 2014 | K10 (2014) | Region VII | Bohol | 118020 | Janlud ES | BATUAN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-01-09 | 070114S00096 | 14HB0021 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-28 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6105 | NC 2014 | K10 (2014) | Region VII | Bohol | 117943 | Katipunan ES Annex | ALICIA | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2679195.2697 |  |  | COMPLETED | 1 | 2015-08-23 | 2015-08-23 | 070114S00262 | 14HB0060 | 2015-02-02 | 2015-02-04 | 2015-02-16 | 2015-02-25 | 2015-03-18 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6106 | NC 2014 | K10 (2014) | Region VII | Bohol | 118140 | Katipunan ES | CARMEN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2016-02-13 |  | 070114S00472 | 15HB0032 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6107 | NC 2014 | K10 (2014) | Region VII | Bohol | 312359 | Katipunan HS | ALICIA | 3 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3980835.14 |  |  | COMPLETED | 1
6108 | NC 2014 | K10 (2014) | Region VII | Bohol | 117944 | La Hacienda ES | ALICIA | 3 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3474578.7213 |  |  | COMPLETED | 1 | 2015-08-23 | 2015-08-23 | 070114S00265 | 14HB0060 | 2015-02-02 | 2015-02-04 | 2015-02-16 | 2015-02-26 | 2015-03-18 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6109 | NC 2014 | K10 (2014) | Region VII | Bohol | 302863 | La Hacienda NHS | ALICIA | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1875466.749 |  |  | COMPLETED | 1
6110 | NC 2014 | K10 (2014) | Region VII | Bohol | 118141 | La Libertad ES | CARMEN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2016-02-13 |  | 070114S00479 | 15HB0032 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6111 | NC 2014 | K10 (2014) | Region VII | Bohol | 118143 | La Salvacion ES | CARMEN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00102 | 14HB0023 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | AL CHRIS CONSTRUCTION
6112 | NC 2014 | K10 (2014) | Region VII | Bohol | 118117 | La Union Elementary School | Candijay | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-07-10 | 2015-07-10 | 070114S00314 | 14HB0075 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6113 | NC 2014 | K10 (2014) | Region VII | Bohol | 118683 | La Union ES | SIERRA BULLONES | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00328 | 14HB0062 | 2014-12-02 | 2014-12-10 |  | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6114 | NC 2014 | K10 (2014) | Region VII | Bohol | 118144 | La Victoria ES | CARMEN | 3 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3990835.14 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00103 | 14HB0022 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-28 | 2014-09-15 | AL CHRIS CONSTRUCTION
6115 | NC 2014 | K10 (2014) | Region VII | Bohol | 118855 | La Victoria ES | VALENCIA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-24 | 070114S00080 | 14HB0030 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6116 | NC 2014 | K10 (2014) | Region VII | Bohol | 186513 | Lapu-lapu ES | Carmen | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00343 | 14HB0065 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6117 | NC 2014 | K10 (2014) | Region VII | Bohol | 302868 | Lila NHS | LILA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1
6118 | NC 2014 | K10 (2014) | Region VII | Bohol | 118670 | Lobgob ES | Sevilla | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-06-17 | 2015-06-17 | 070114S00293 | 14HB0068 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6119 | NC 2014 | K10 (2014) | Region VII | Bohol | 118466 | Loboc CES | Loboc | 3 | 1 | 9 | 3UNITS 1STY3CL | 2014 K10 BATCH 3 | 7796385.8091 |  |  | COMPLETED | 1 | 2016-01-21 |  | 070114S00332 | 15HB0030 | 2015-05-13 | 2015-05-15 | 2015-05-27 | 2015-06-04 | 2015-06-26 | WYNN CONSTRUCTION
6120 | NC 2014 | K10 (2014) | Region VII | Bohol | 118295 | Lobogon ES | DUERO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1
6121 | NC 2014 | K10 (2014) | Region VII | Bohol | 118295 | Lobogon ES | Duero | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
6122 | NC 2014 | K10 (2014) | Region VII | Bohol | 118118 | Luan Elementary School | Candijay | 3 | 1 | 4 | 1STY3CL & 1STY1CL | 2014 K10 BATCH 3 | 3600564.0842 |  |  | COMPLETED | 1
6123 | NC 2014 | K10 (2014) | Region VII | Bohol | 312336 | Lungsodaan High School | MABINI | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 070114S00072 | 14HB0028 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6124 | NC 2014 | K10 (2014) | Region VII | Bohol | 118296 | Madua Norte PS | DUERO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1052018.8144 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 070114S00321 | 14HB0074 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
6125 | NC 2014 | K10 (2014) | Region VII | Bohol | 118671 | Magsaysay ES | SEVILLA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 070114S00083 | 14HB0025 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6126 | NC 2014 | K10 (2014) | Region VII | Bohol | 118685 | Magsaysay ES | Sierra Bullones | 3 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00312 | 14HB0062 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6127 | NC 2014 | K10 (2014) | Region VII | Bohol | 117945 | Mahayag ES | ALICIA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 070114S00053 | 14HB0019 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-28 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6128 | NC 2014 | K10 (2014) | Region VII | Bohol | 118521 | Mahayag ES | MABINI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070114S00323 | 14HB0061 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6129 | NC 2014 | K10 (2014) | Region VII | Bohol | 302878 | Mayuga NHS | GUINDULMAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1082703.8954 |  |  | COMPLETED | 1
6130 | NC 2014 | K10 (2014) | Region VII | Bohol | 118146 | Monte Hermoso ES | CARMEN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 070114S00104 | 14HB0024 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6131 | NC 2014 | K10 (2014) | Region VII | Bohol | 118148 | Monte Sunting ES | CARMEN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 070114S00105 | 14HB0024 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6132 | NC 2014 | K10 (2014) | Region VII | Bohol | 118149 | Montevideo ES | CARMEN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 070114S00106 | 14HB0024 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6133 | NC 2014 | K10 (2014) | Region VII | Bohol | 118153 | Nueva Vida Sur ES | CARMEN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1838464.5699 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 070114S00319 | 14HB0064 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
6134 | NC 2014 | K10 (2014) | Region VII | Bohol | 118279 | Oac ES | DIMIAO | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 070114S00094 | 14HB0025 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6135 | NC 2014 | K10 (2014) | Region VII | Bohol | 118431 | Odiong ES | Jagna | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-06-23 | 2015-06-23 | 070114S00308 | 14HB0073 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6136 | NC 2014 | K10 (2014) | Region VII | Bohol | 118524 | Paraiso ES | MABINI | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2669145.2697 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00324 | 14HB0061 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6137 | NC 2014 | K10 (2014) | Region VII | Bohol | 118581 | Pilar Central ES | PILAR | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070114S00087 | 14HB0029 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6138 | NC 2014 | K10 (2014) | Region VII | Bohol | 117963 | Porcenas PS | ANDA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 070114S00123 | 14HB0020 | 2014-09-08 | 2014-09-18 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6139 | NC 2014 | K10 (2014) | Region VII | Bohol | 118051 | Riverside PS | BILAR | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1
6140 | NC 2014 | K10 (2014) | Region VII | Bohol | 118051 | Riverside PS | Bilar | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
6141 | NC 2014 | K10 (2014) | Region VII | Bohol | 118317 | Sacaon ES | Garcia Hernandez | 3 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2015-06-23 | 2015-06-23 | 070114S00317 | 14HB0071 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6142 | NC 2014 | K10 (2014) | Region VII | Bohol | 118689 | San Agustin ES | Sierra Bullones | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00298 | 14HB0063 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6143 | NC 2014 | K10 (2014) | Region VII | Bohol | 118125 | San Isidro ES | CANDIJAY | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 070114S00099 | 14HB0020 | 2014-09-08 | 2014-09-18 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6144 | NC 2014 | K10 (2014) | Region VII | Bohol | 118300 | San Isidro ES | Duero | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 070114S00303 | 14HB0074 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
6145 | NC 2014 | K10 (2014) | Region VII | Bohol | 118584 | San Isidro ES | PILAR | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00093 | 14HB0023 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | AL CHRIS CONSTRUCTION
6146 | NC 2014 | K10 (2014) | Region VII | Bohol | 302889 | San Isidro Tech-Voc HS | PILAR | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1875466.749 |  |  | COMPLETED | 1
6147 | NC 2014 | K10 (2014) | Region VII | Bohol | 118692 | San Juan ES | SIERRA BULLONES | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3065174.43 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070114S00081 | 14HB0029 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6148 | NC 2014 | K10 (2014) | Region VII | Bohol | 118301 | San Pedro ES | DUERO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-02-16 | 070114S00121 | 14HB0031 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | AL CHRIS CONSTRUCTION
6149 | NC 2014 | K10 (2014) | Region VII | Bohol | 186505 | San Rafael PS | MABINI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1875466.749 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 070114S00216 | 14HB0033 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | WILTAN CONSTRUCTION
6150 | NC 2014 | K10 (2014) | Region VII | Bohol | 302903 | Sevilla NHS | Sevilla | 3 | 1 | 6 | 1STY4CL & 1STY2CL | 2014 K10 BATCH 3 | 5192443.2912 |  |  | COMPLETED | 1 | 2015-06-17 | 2015-06-17 | 070114S00294 | 14HB0068 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6151 | NC 2014 | K10 (2014) | Region VII | Bohol | 118693 | Sierra Bullones CES | Sierra Bullones | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00295 | 14HB0062 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6152 | NC 2014 | K10 (2014) | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1875466.749 |  |  | COMPLETED | 1
6153 | NC 2014 | K10 (2014) | Region VII | Bohol | 118860 | Simang ES | Valencia | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 070114S00301 | 14HB0070 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6154 | NC 2014 | K10 (2014) | Region VII | Bohol | 118054 | Subayon PS | BILAR | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 070114S00098 | 14HB0025 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6155 | NC 2014 | K10 (2014) | Region VII | Bohol | 302909 | Tabuan NHS | Garcia Hernandez | 3 | 1 | 3 | 2STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 5293668.4288 |  |  | COMPLETED | 1
6156 | NC 2014 | K10 (2014) | Region VII | Bohol | 118155 | Tagaonan ES | CARMEN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1
6157 | NC 2014 | K10 (2014) | Region VII | Bohol | 118155 | Tagaonan ES | Carmen | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
6158 | NC 2014 | K10 (2014) | Region VII | Bohol | 118529 | Tambo ES | MABINI | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2669145.2697 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00325 | 14HB0061 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6159 | NC 2014 | K10 (2014) | Region VII | Bohol | 500208 | Tubod Monte IS | JAGNA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00091 | 14HB0026 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6160 | NC 2014 | K10 (2014) | Region VII | Bohol | 118158 | Vallehermoso ES | CARMEN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00115 | 14HB0023 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | AL CHRIS CONSTRUCTION
6161 | NC 2014 | K10 (2014) | Region VII | Bohol | 312357 | Vallehermoso HS | CARMEN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00070 | 14HB0023 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | AL CHRIS CONSTRUCTION
6162 | NC 2014 | K10 (2014) | Region VII | Bohol | 118159 | Villaflor ES | CARMEN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00117 | 14HB0022 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-28 | 2014-09-15 | AL CHRIS CONSTRUCTION
6163 | NC 2014 | K10 (2014) | Region VII | Bohol | 118161 | Villarcayo ES | CARMEN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1858564.5699 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 070114S00320 | 14HB0064 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
6164 | NC 2014 | K10 (2014) | Region VII | Bohol | 117966 | Virgen ES | ANDA | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1858564.5699 |  |  | COMPLETED | 1 | 2015-07-10 | 2015-07-10 | 070114S00344 | 14HB0075 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6165 | NC 2014 | K10 (2014) | Region VII | Bohol | 118058 | Zamora ES | Bilar | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 070114S00335 | 14HB0066 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | LTS BUILDERS AND CONSTRUCTION SUPPLY
6166 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119154 | Buenavista ES | Carcar City | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-25 | 070214S00315 | 14-HE-0097 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | QUIRANTE CONSTRUCTION
6167 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119155 | Calidngan ES | Carcar City | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070214S00320 | 14-HE-0099 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | M.P. VILLEGAS CONSTRUCTION
6168 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119172 | Canal ES | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-10-17 | 2014-10-17 | 070214S00068 | 14-HE-0025 | 2014-05-27 | 2014-05-29 | 2014-06-10 | 2014-06-16 | 2014-06-20 | FIRST GRANDEUR BUILDERS
6169 | NC 2014 | K10 (2014) | Region VII | Carcar City | 302970 | Can-asujan NHS | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
6170 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119158 | Carcar Central ES | Carcar City | 1 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 3 | 4112918.6116 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00317 | 14-HE-0095 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | EL-JAKE BUILDERS
6171 | NC 2014 | K10 (2014) | Region VII | Carcar City | 303127 | Gelacio C. Babao, Sr. MNHS | CITY OF CARCAR | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10917293.5547 |  |  | COMPLETED | 1 | 2015-12-07 | 2015-12-07 | 070214S00309 | 14-HE-0122 | 2014-11-27 | 2014-12-15 | 2014-12-15 | 2014-12-18 | 2014-12-23 | QUIRANTE CONSTRUCTION
6172 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119173 | Guadalupe ES | Carcar City | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00319 | 14-HE-0096 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | EL-JAKE BUILDERS
6173 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119174 | Hunob Elementary School | CITY OF CARCAR | 1 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3980835.14 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 070214S00067 | 14-HE-0026 | 2014-05-27 | 2014-05-29 | 2014-06-10 | 2014-06-16 | 2014-06-20 | FIRST GRANDEUR BUILDERS
6174 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119175 | Kalangyawon ES | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 070214S00066 | 14-HE-0027 | 2014-06-24 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-18 | QUIRANTE CONSTRUCTION
6175 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119176 | Kamanggahan Elementary School | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
6176 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119176 | Kamanggahan ES | Carcar City | 1 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 3500545.7907 |  |  | COMPLETED | 1
6177 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119177 | Kayam Elementary School | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
6178 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119177 | Kayam ES | Carcar City | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1
6179 | NC 2014 | K10 (2014) | Region VII | Carcar City | 324901 | LIBURON NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-05-22 | 070214S00310 | 14-HE-0104 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | EL-JAKE BUILDERS
6180 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119179 | Maximina V. Barangan ES (Mercado) | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-12 | 070214S00072 | 14-HE-0029 | 2014-06-24 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-18 | QM BUILDERS
6181 | NC 2014 | K10 (2014) | Region VII | Carcar City | 303016 | Maximino Noel Memorial National High School | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6318764.7656 |  |  | COMPLETED | 1
6182 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119180 | Napo ES | Carcar City | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-25 | 070214S00302 | 14-HE-0100 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | M.P. VILLEGAS CONSTRUCTION
6183 | NC 2014 | K10 (2014) | Region VII | Carcar City | 356059 | Ocana National High School (Kalangyawon Extension) | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
6184 | NC 2014 | K10 (2014) | Region VII | Carcar City | 303066 | OCAÑA NHS | CITY OF CARCAR | 1 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 3 | 18979709.7656 |  |  | COMPLETED | 1
6185 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119161 | Perrelos ES | Carcar City | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00313 | 14-HE-0101 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | QUIRANTE CONSTRUCTION
6186 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119165 | Tagaytay ES | Carcar City | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1
6187 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119165 | Tagaytay Primary School | CITY OF CARCAR | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1
6188 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119184 | Upland ES | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6318764.7656 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-05 | 070214S00306 | 14-HE-0110 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QUIRANTE CONSTRUCTION
6189 | NC 2014 | K10 (2014) | Region VII | Carcar City | 303126 | Valencia Vocational NHS | Carcar City | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3335125.5846 |  |  | COMPLETED | 1
6190 | NC 2014 | K10 (2014) | Region VII | Carcar City | 119170 | Valladolid ES | Carcar City | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00324 | 14-HE-0096 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | EL-JAKE BUILDERS
6191 | NC 2014 | K10 (2014) | Region VII | Cebu | 312401 | Balud NHS | SAN FERNANDO | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4337124.6094 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-05-07 | 070214S00284 | 14-HE-0117 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QUIRANTE CONSTRUCTION
6192 | NC 2014 | K10 (2014) | Region VII | Cebu | 119618 | Balungag ES | SAN FERNANDO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1252712.2061 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 070214S00166 | 14-HE-0051 | 2014-06-25 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-18 | VIRLO CONSTRUCTION
6193 | NC 2014 | K10 (2014) | Region VII | Cebu | 312427 | Balungag NHS | SAN FERNANDO | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4563249.6094 |  |  | COMPLETED | 1
6194 | NC 2014 | K10 (2014) | Region VII | Cebu | 119481 | Calbasaan ES | MINGLANILLA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2161149.1921 |  |  | COMPLETED | 1
6195 | NC 2014 | K10 (2014) | Region VII | Cebu | 119481 | Calbasaan ES | Minglanilla | 1 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 2945000 |  |  | COMPLETED | 1
6196 | NC 2014 | K10 (2014) | Region VII | Cebu | 302969 | Camp 7 NHS | MINGLANILLA | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1
6197 | NC 2014 | K10 (2014) | Region VII | Cebu | 119710 | Candaguit ES | SIBONGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1102712.2061 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 070214S00165 | 14-HE-0051 | 2014-06-25 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-18 | VIRLO CONSTRUCTION
6198 | NC 2014 | K10 (2014) | Region VII | Cebu | 119713 | Lamacan ES | SIBONGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1182712.2061 |  |  | COMPLETED | 1 | 2014-10-15 | 2014-09-03 | 070214S00139 | 14-HE-0052 | 2014-06-25 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-18 | SB & T CONSTRUCTION
6199 | NC 2014 | K10 (2014) | Region VII | Cebu | 119485 | Lipata Central ES | MINGLANILLA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-14 |  | 070214S00434 | 15-HE-0096 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | SB & T CONSTRUCTION
6200 | NC 2014 | K10 (2014) | Region VII | Cebu | 119716 | Magcagong PS | Sibonga | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00301 | 14-HE-0102 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | QUIRANTE CONSTRUCTION
6201 | NC 2014 | K10 (2014) | Region VII | Cebu | 119717 | Manatad ES | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6600164.7656 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-06 | 070214S00312 | 14-HE-0106 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | MAP ALVIOLA CONSTRUCTION
6202 | NC 2014 | K10 (2014) | Region VII | Cebu | 312457 | Manatad NHS | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6529814.7656 |  |  | COMPLETED | 1
6203 | NC 2014 | K10 (2014) | Region VII | Cebu | 119486 | Manduang ES | MINGLANILLA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-02-27 | 070214S00291 | 14-HE-0094 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-12-28 | 2014-12-03 | RAMIJO CONSTRUCTION
6204 | NC 2014 | K10 (2014) | Region VII | Cebu | 119718 | Mangyan ES | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6709664.7656 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-05 | 070214S00281 | 14-HE-0108 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QM BUILDERS
6205 | NC 2014 | K10 (2014) | Region VII | Cebu | 119719 | Papan ES | Sibonga | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4294527.3578 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00288 | 14-HE-0102 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | QUIRANTE CONSTRUCTION
6206 | NC 2014 | K10 (2014) | Region VII | Cebu | 303102 | Simala NHS | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6499664.7656 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-05 | 070214S00283 | 14-HE-0109 | 2014-11-19 | 2014-12-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QM BUILDERS
6207 | NC 2014 | K10 (2014) | Region VII | Cebu | 119488 | Tungkil ES | MINGLANILLA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6358964.7656 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-05-22 | 070214S00314 | 14-HE-0116 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QM BUILDERS
6208 | NC 2014 | K10 (2014) | Region VII | Cebu | 312450 | Tungkil NHS | MINGLANILLA | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4442649.6094 |  |  | COMPLETED | 1
6209 | NC 2014 | K10 (2014) | Region VII | Cebu | 119480 | Vito ES | MINGLANILLA | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14456118.3984 |  |  | COMPLETED | 1 | 2016-01-06 |  | 070214S00322 | 14-HE-0128 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | GENETIAN BUILDERS
6210 | NC 2014 | K10 (2014) | Region VII | Cebu | 119489 | Agbalanga ES | Moalboal | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-15 | 070214S00293 | 14-HG-0129 (Cluster 2) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | GELA CONSTRUCTION
6211 | NC 2014 | K10 (2014) | Region VII | Cebu | 118939 | Alambijud ES | Argao | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-25 | 070214S00292 | 14-HG-0128 (Cluster 1) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
6212 | NC 2014 | K10 (2014) | Region VII | Cebu | 119291 | Amonsao Elem. School | DALAGUETE | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 2074740.174 |  |  | COMPLETED | 1 | 2015-09-05 | 2015-09-04 | 070214S00426 | 15HG0050 | 2015-06-05 | 2015-06-10 | 2015-06-22 | 2015-06-30 | 2015-07-01 | QUIRANTE CONSTRUCTION
6213 | NC 2014 | K10 (2014) | Region VII | CEBU | 119398 | Anao ES | GINATILAN | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 2 | 2903861.3982 |  |  | COMPLETED | 1 | 2015-01-10 | 2014-11-03 | 070214S00088 | 14-HG-0047 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-08-12 | 2014-08-13 | QUIRANTE CONSTRUCTION
6214 | NC 2014 | K10 (2014) | Region VII | Cebu | 302925 | Bala NHS | MOALBOAL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4A | 1750272.8953 |  |  | COMPLETED | 1 | 2015-04-26 | 2015-04-26 | 070214S00408 | 14HG0153 | 2014-12-16 | 2014-12-17 | 2014-12-22 | 2015-01-19 | 2015-01-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6215 | NC 2014 | K10 (2014) | Region VII | CEBU | 118942 | Balaas PS | ARGAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1861149.1921 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-12-22 | 070214S00087 | 14-HG-0056 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RIKDA CONSTRUCTION & DEVELOPMENT CORPORATION
6216 | NC 2014 | K10 (2014) | Region VII | Cebu | 119383 | Balaygtiki ES | DUMANJUG | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6459464.7656 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070214S00358 | 14-HG-0137 (Cluster 9) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
6217 | NC 2014 | K10 (2014) | Region VII | Cebu | 118918 | Balisong-Casay ES | ARGAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-25 | 070214S00295 | 14-HG-0128 (Cluster 1) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
6218 | NC 2014 | K10 (2014) | Region VII | Cebu | 118997 | Basangpangpang ES | BADIAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 070214S00296 | 14-HG-0130 (Cluster 3) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
6219 | NC 2014 | K10 (2014) | Region VII | Cebu | 119127 | Becerril ES | BOLJOON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1082712.2061 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 070214S00084 | 14-HG-0052 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-08-12 | 2014-08-13 | QUIRANTE CONSTRUCTION
6220 | NC 2014 | K10 (2014) | Region VII | Cebu | 119000 | Bugas ES | BADIAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 980365.9023 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 070214S00297 | 14-HG-0130 (Cluster 3) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
6221 | NC 2014 | K10 (2014) | Region VII | Cebu | 119494 | Bugho ES | Moalboal | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-15 | 070214S00254 | 14-HG-0129 (Cluster 2) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | GELA CONSTRUCTION
6222 | NC 2014 | K10 (2014) | Region VII | Cebu | 118873 | Bulalacao PS | ALCOY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-24 | 070214S00300 | 14-HG-0131 (Cluster 4) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6223 | NC 2014 | K10 (2014) | Region VII | Cebu | 118945 | Butong ES | ARGAO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2743213.9542 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-19 | 070214S00078 | 14-HG-0040 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | SERCHER DEVELOPMENT CORPORATION
6224 | NC 2014 | K10 (2014) | Region VII | Cebu | 187015 | Cabutongan ES | SANTANDER | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1112712.2061 |  |  | COMPLETED | 1 | 2014-10-22 | 2014-10-22 | 070214S00086 | 14-HG-0054 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-08-04 | 2014-08-05 | QUIRANTE CONSTRUCTION
6225 | NC 2014 | K10 (2014) | Region VII | Cebu | 119373 | Calaboon ES | DUMANJUG | 2 | 1 | 8 | 2UNITS 2STY4CL | 2014 K10 BATCH 3 | 12798329.5312 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-03-26 | 070214S00355 | 14-HG-0136 | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | DINAH JANE CONSTRUCTION SUPPLY
6226 | NC 2014 | K10 (2014) | Region VII | Cebu | 119374 | Camboang ES | DUMANJUG | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6369337.6381 |  |  | COMPLETED | 1 | 2015-10-05 | 2015-10-05 | 070214S00433 | 15HG0049 | 2015-06-05 | 2015-06-10 | 2015-06-22 | 2015-06-30 | 2015-07-01 | GELA CONSTRUCTION
6227 | NC 2014 | K10 (2014) | Region VII | Cebu | 119595 | Can-abujon ES | RONDA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2644754.4624 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-04-13 | 070214S00360 | 14-HG-0134 (Cluster 7) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | DINAH JANE CONSTRUCTION SUPPLY
6228 | NC 2014 | K10 (2014) | Region VII | Cebu | 118922 | Canbantug ES | ARGAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2161149.1921 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-11-15 | 070214S00075 | 14-HG-0044 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | QUIRANTE CONSTRUCTION
6229 | NC 2014 | K10 (2014) | Region VII | Cebu | 119002 | Candiis ES | BADIAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1911072.8953 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 070214S00298 | 14-HG-0130 (Cluster 3) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
6230 | NC 2014 | K10 (2014) | Region VII | Cebu | 302982 | Cerde¤a NHS | MALABUYOC | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1
6231 | NC 2014 | K10 (2014) | Region VII | Cebu | 119376 | Cotcoton ES | DUMANJUG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1810572.8953 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070214S00356 | 14-HG-0137 (Cluster 9) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
6232 | NC 2014 | K10 (2014) | Region VII | Cebu | 119298 | Dalaguete Central ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070214S00323 | 14-HG-0132 (Cluster 5) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
6233 | NC 2014 | K10 (2014) | Region VII | Cebu | 302997 | Dalaguete NHS | DALAGUETE | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4352199.6094 |  |  | COMPLETED | 1
6234 | NC 2014 | K10 (2014) | Region VII | Cebu | 119607 | Dalahikan ES | SAMBOAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-04-13 | 070214S00361 | 14-HG-0134 (Cluster 7) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | DINAH JANE CONSTRUCTION SUPPLY
6235 | NC 2014 | K10 (2014) | Region VII | Cebu | 118928 | Dalas-ag PS | ARGAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1102712.2061 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 070214S00076 | 14-HG-0049 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RAJLAURENTE CONSTRUCTION & DEVELOPMENT PHIL.
6236 | NC 2014 | K10 (2014) | Region VII | Cebu | 119299 | Dugyan ES | DALAGUETE | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-04-24 | 070214S00348 | 14-HG-0132 (Cluster 5) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
6237 | NC 2014 | K10 (2014) | Region VII | Cebu | 119131 | Granada ES | BOLJOON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-24 | 070214S00289 | 14-HG-0131 (Cluster 4) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6238 | NC 2014 | K10 (2014) | Region VII | Cebu | 118948 | Guiwanon ES | ARGAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1122712.2061 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 070214S00079 | 14-HG-0050 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RAJLAURENTE CONSTRUCTION & DEVELOPMENT PHIL.
6239 | NC 2014 | K10 (2014) | Region VII | Cebu | 187006 | Kanghalo PS | DUMANJUG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 990415.9023 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070214S00362 | 14-HG-0137 (Cluster 9) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
6240 | NC 2014 | K10 (2014) | Region VII | Cebu | 119301 | Karatagan ES | DALAGUETE | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2851238.7977 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070214S00349 | 14-HG-0132 (Cluster 5) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
6241 | NC 2014 | K10 (2014) | Region VII | Cebu | 119302 | Langkas ES | DALAGUETE | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1090915.9023 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070214S00350 | 14-HG-0133 (Cluster 6) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6242 | NC 2014 | K10 (2014) | Region VII | Cebu | 118891 | Legaspi Elementary School | ALEGRIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-09-30 | 070214S00080 | 14-HG-0045 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RUDPA CONSTRUCTION
6243 | NC 2014 | K10 (2014) | Region VII | Cebu | 119599 | Liboo ES | RONDA | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 2 | 2953861.3982 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-11-03 | 070214S00085 | 14-HG-0039 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RUDPA CONSTRUCTION
6244 | NC 2014 | K10 (2014) | Region VII | Cebu | 119321 | Lumbang ES | DALAGUETE | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-02-27 | 070214S00354 | 14-HG-0133 (Cluster 6) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6245 | NC 2014 | K10 (2014) | Region VII | CEBU | 302944 | Lunop NHS | BOLJOON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1
6246 | NC 2014 | K10 (2014) | Region VII | Cebu | 118955 | Malalag ES | ARGAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1252712.2061 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 070214S00090 | 14-HG-0051 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RAJLAURENTE CONSTRUCTION & DEVELOPMENT PHIL.
6247 | NC 2014 | K10 (2014) | Region VII | Cebu | 119305 | Mantalongon ES | DALAGUETE | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2896004.4624 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-05-29 | 070214S00351 | 14-HG-0132 (Cluster 5) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
6248 | NC 2014 | K10 (2014) | Region VII | Cebu | 303000 | Mantalongon NHS | DALAGUETE | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6499664.7656 |  |  | COMPLETED | 1
6249 | NC 2014 | K10 (2014) | Region VII | Cebu | 118896 | Mayana ES | ALEGRIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1192712.2061 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-15 | 070214S00074 | 14-HG-0046 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RUDPA CONSTRUCTION
6250 | NC 2014 | K10 (2014) | Region VII | Cebu | 118957 | Mompeller PS | ARGAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2051149.1921 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-11-03 | 070214S00081 | 14-HG-0042 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | QUIRANTE CONSTRUCTION
6251 | NC 2014 | K10 (2014) | Region VII | Cebu | 119499 | Omay PS | Moalboal | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-15 | 070214S00294 | 14-HG-0129 (Cluster 2) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | GELA CONSTRUCTION
6252 | NC 2014 | K10 (2014) | Region VII | Cebu | 312459 | Palanas Integrated School | GINATILAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1
6253 | NC 2014 | K10 (2014) | Region VII | CEBU | 303084 | Salamanca NHS | GINATILAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1
6254 | NC 2014 | K10 (2014) | Region VII | Cebu | 119449 | Salmeron ES | MALABUYOC | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2745254.4624 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-04-13 | 070214S00347 | 14-HG-0134 (Cluster 7) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | DINAH JANE CONSTRUCTION SUPPLY
6255 | NC 2014 | K10 (2014) | Region VII | Cebu | 119010 | Sanlagan ES | BADIAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 070214S00299 | 14-HG-0130 (Cluster 3) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
6256 | NC 2014 | K10 (2014) | Region VII | Cebu | 118960 | Sua ES | ARGAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1232712.2061 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 070214S00073 | 14-HG-0055 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RIKDA CONSTRUCTION & DEVELOPMENT CORPORATION
6257 | NC 2014 | K10 (2014) | Region VII | Cebu | 118961 | Sumaguan ES | ARGAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2011149.1921 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-11-23 | 070214S00083 | 14-HG-0041 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RUDPA CONSTRUCTION
6258 | NC 2014 | K10 (2014) | Region VII | Cebu | 118933 | Tabayag ES | ARGAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2261149.1921 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 070214S00077 | 14-HG-0043 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-08-12 | 2014-08-13 | QUIRANTE CONSTRUCTION
6259 | NC 2014 | K10 (2014) | Region VII | Cebu | 119309 | Tabon ES | DALAGUETE | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2896004.4624 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070214S00352 | 14-HG-0133 (Cluster 6) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6260 | NC 2014 | K10 (2014) | Region VII | Cebu | 312454 | Tan-awan NHS | OSLOB | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
6261 | NC 2014 | K10 (2014) | Region VII | Cebu | 119382 | Tapon ES | DUMANJUG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1810572.8953 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070214S00369 | 14-HG-0137 (Cluster 9) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
6262 | NC 2014 | K10 (2014) | Region VII | Cebu | 119014 | Taytay ES | BADIAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 070214S00334 | 14-HG-0130 (Cluster 3) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
6263 | NC 2014 | K10 (2014) | Region VII | Cebu | 119310 | Tubod ES | DALAGUETE | 2 | 1 | 3 | 3UNITS 1STY1CL | 2014 K10 BATCH 3 | 7884013.3872 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-02-27 | 070214S00353 | 14-HG-0133 (Cluster 6) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6264 | NC 2014 | K10 (2014) | Region VII | Cebu | 302923 | Tubod NHS | BADIAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
6265 | NC 2014 | K10 (2014) | Region VII | Cebu | 118963 | Tulang ES | Argao | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-25 | 070214S00280 | 14-HG-0128 (Cluster 1) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
6266 | NC 2014 | K10 (2014) | Region VII | Cebu | 118938 | Usmad ES | Argao | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-25 | 070214S00290 | 14-HG-0128 (Cluster 1) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
6267 | NC 2014 | K10 (2014) | Region VII | Cebu | 312455 | Willy B. Wenceslao NHS | SANTANDER | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
6268 | NC 2014 | K10 (2014) | Region VII | Cebu | 118901 | Angilan Elementary School | ALOGUINSAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-03-22 | 070214S00328 | 14HF0135 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
6269 | NC 2014 | K10 (2014) | Region VII | Cebu | 119552 | Anislag ES | PINAMUNGAHAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1112712.2061 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 070214S00178 | 14HF0042 | 2014-08-22 | 2014-09-02 | 2014-09-03 | 2014-09-10 | 2014-09-16 | DINAH JANE CONSTRUCTION SUPPLY
6270 | NC 2014 | K10 (2014) | Region VII | Cebu | 119826 | Antipolo ES | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-26 | 070214S00171 | 14HF0044 | 2014-08-27 | 2014-09-08 | 2014-09-09 | 2014-09-16 | 2014-09-22 | FIRST GRANDEUR BUILDERS
6271 | NC 2014 | K10 (2014) | Region VII | Cebu | 119806 | Bagasawe ES | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1082712.2061 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 070214S00174 | 14HF0043 | 2014-08-22 | 2014-09-02 | 2014-09-03 | 2014-09-10 | 2014-09-16 | MAP ALVIOLA CONSTRUCTION
6272 | NC 2014 | K10 (2014) | Region VII | Cebu | 119827 | Bakyawan ES | TUBURAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1971149.1921 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-10 | 070214S00170 | 14HF0078 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-10-31 | 2014-11-06 | By Administration
6273 | NC 2014 | K10 (2014) | Region VII | Cebu | 303069 | Bartolome & Manuela Pañares MNHS | BARILI | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1
6274 | NC 2014 | K10 (2014) | Region VII | Cebu | 119019 | Biasong ES | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-04-28 | 2015-04-28 | 070214S00333 | 14HF0121 | 2014-12-02 | 2014-12-03 | 2014-12-15 | 2014-12-18 | 2014-12-23 | LA PRUEBA CONSTRUCTION
6275 | NC 2014 | K10 (2014) | Region VII | Cebu | 119074 | Bolocboloc ES | BARILI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 070214S00343 | 14HF0090 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | FIRST GRANDEUR BUILDERS
6276 | NC 2014 | K10 (2014) | Region VII | Cebu | 118904 | Bonbon ES | ALOGUINSAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00329 | 14HF0127 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-05 | DINAH JANE CONSTRUCTION SUPPLY
6277 | NC 2014 | K10 (2014) | Region VII | Cebu | 302950 | BUANOY NHS-EVENING OPPORTUNITY CLASS | BALAMBAN | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1
6278 | NC 2014 | K10 (2014) | Region VII | Cebu | 119075 | Budbud ES | BARILI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-03-13 | 070214S00344 | 14HF0092 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | FIRST BUILDERS AND DEVELOPERS
6279 | NC 2014 | K10 (2014) | Region VII | Cebu | 187011 | Buhingtubig PS | PINAMUNGAHAN | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-04-21 | 070214S00229 | 14HF0118 | 2014-11-27 | 2014-12-08 | 2014-12-09 | 2014-12-12 | 2014-12-17 | GOLDFIN CONSTRUCTION
6280 | NC 2014 | K10 (2014) | Region VII | Cebu | 119555 | Busay ES | PINAMUNGAHAN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2644754.4624 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-03-13 | 070214S00218 | 14HF0091 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | BL PANGAN CONSTRUCTION
6281 | NC 2014 | K10 (2014) | Region VII | Cebu | 119020 | C. Pepito ES | BALAMBAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1020565.9023 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 070214S00346 | 14HF0132 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
6282 | NC 2014 | K10 (2014) | Region VII | Cebu | 303071 | Cagay NHS | BARILI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1
6283 | NC 2014 | K10 (2014) | Region VII | Cebu | 119036 | Cambagucbok ES | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 070214S00339 | 14HF0123 | 2014-12-02 | 2014-12-12 | 2014-12-15 | 2014-12-18 | 2014-12-23 | BL PANGAN CONSTRUCTION
6284 | NC 2014 | K10 (2014) | Region VII | Cebu | 119558 | Candiis ES | PINAMUNGAHAN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2644754.4624 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-26 | 070214S00222 | 14HF0123 | 2014-12-02 | 2014-12-12 | 2014-12-15 | 2014-12-18 | 2014-12-23 | BL PANGAN CONSTRUCTION
6285 | NC 2014 | K10 (2014) | Region VII | Cebu | 119038 | Cantibas PS | BALAMBAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1100965.9023 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-26 | 070214S00340 | 14HF0123 | 2014-12-02 | 2014-12-12 | 2014-12-15 | 2014-12-18 | 2014-12-23 | BL PANGAN CONSTRUCTION
6286 | NC 2014 | K10 (2014) | Region VII | Cebu | 119039 | Casili ES | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 070214S00341 | 14HF0114 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-05 | 2014-12-10 | LA PRUEBA CONSTRUCTION
6287 | NC 2014 | K10 (2014) | Region VII | Cebu | 302987 | Colonia NHS | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1
6288 | NC 2014 | K10 (2014) | Region VII | Cebu | 119040 | Cornelio C. Melgar Elementary School | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4A | 1750272.8953 |  |  | COMPLETED | 1 | 2015-04-28 | 2015-04-28 | 070214S00414 | 14HF0147 | 2014-12-23 | 2014-12-16 | 2014-12-23 | 2015-01-07 | 2015-01-22 | By Administration
6289 | NC 2014 | K10 (2014) | Region VII | Cebu | 303045 | Federico & Solidad MNHS | BARILI | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2813213.9542 |  |  | COMPLETED | 1
6290 | NC 2014 | K10 (2014) | Region VII | Cebu | 119082 | Federico & Solidad Villaflor ES (Luhod ES) | BARILI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-14 | 070214S00368 | 14HF0095 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | R.M. MONDARES CONSTRUCTION
6291 | NC 2014 | K10 (2014) | Region VII | Cebu | 119832 | Fortaliza PS | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 070214S00169 | 14HF0046 | 2014-08-27 | 2014-09-08 | 2014-09-09 | 2014-09-16 | 2014-09-22 | QUIRANTE CONSTRUCTION
6292 | NC 2014 | K10 (2014) | Region VII | Cebu | 119560 | Guimbawi-an ES | PINAMUNGAHAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1112712.2061 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 070214S00191 | 14HF0042 | 2014-08-22 | 2014-09-02 | 2014-09-03 | 2014-09-10 | 2014-09-16 | DINAH JANE CONSTRUCTION SUPPLY
6293 | NC 2014 | K10 (2014) | Region VII | Cebu | 119023 | Hingatmonan ES | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1901022.8953 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00335 | 14HF0126 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2014-12-26 | DINAH JANE CONSTRUCTION SUPPLY
6294 | NC 2014 | K10 (2014) | Region VII | Cebu | 312451 | Ireneo V. Diamante NHS | TUBURAN | 3 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 3701545.7907 |  |  | COMPLETED | 1
6295 | NC 2014 | K10 (2014) | Region VII | Cebu | 119836 | Kabangkalan ES | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1152712.2061 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-10 | 070214S00168 | 14HF0074 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-10-31 | 2014-11-06 | By Administration
6296 | NC 2014 | K10 (2014) | Region VII | Cebu | 312453 | Kalangahan NHS | TUBURAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
6297 | NC 2014 | K10 (2014) | Region VII | Cebu | 119839 | Kamansi ES | TUBURAN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 3103213.9542 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 070214S00167 | 14HF0045 | 2014-08-27 | 2014-09-08 | 2014-09-09 | 2014-09-16 | 2014-09-22 | MAP ALVIOLA CONSTRUCTION
6298 | NC 2014 | K10 (2014) | Region VII | Cebu | 119841 | Kansi ES | TUBURAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2011149.1921 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-09 | 070214S00096 | 14HF0075 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-10-31 | 2014-11-06 | By Administration
6299 | NC 2014 | K10 (2014) | Region VII | Cebu | 303029 | Lamac NHS | PINAMUNGAHAN | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8328953.2031 |  |  | COMPLETED | 1
6300 | NC 2014 | K10 (2014) | Region VII | Cebu | 119080 | Lamak ES | BARILI | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2644754.4624 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-03-14 | 070214S00345 | 14HF0105 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6301 | NC 2014 | K10 (2014) | Region VII | Cebu | 119025 | Lamesa ES | BALAMBAN | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8529953.2031 |  |  | COMPLETED | 1 | 2015-05-13 | 2015-05-13 | 070214S00325 | 14HF0121 | 2014-12-02 | 2014-12-03 | 2014-12-15 | 2014-12-18 | 2014-12-23 | LA PRUEBA CONSTRUCTION
6302 | NC 2014 | K10 (2014) | Region VII | Cebu | 118981 | Lunas Ii ES | ASTURIAS | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 070214S00330 | 14HF0091 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | BL PANGAN CONSTRUCTION
6303 | NC 2014 | K10 (2014) | Region VII | Cebu | 119814 | Lusong ES | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1132712.2061 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-09 | 070214S00164 | 14HF0077 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-10-31 | 2014-11-06 | By Administration
6304 | NC 2014 | K10 (2014) | Region VII | Cebu | 119562 | Lut-od ES | PINAMUNGAHAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1
6305 | NC 2014 | K10 (2014) | Region VII | Cebu | 119562 | Lut-od ES | Pinamungajan | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1
6306 | NC 2014 | K10 (2014) | Region VII | Cebu | 303078 | Lut-od NHS | PINAMUNGAHAN | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-04-21 | 070214S00200 | 14HF0118 | 2014-11-27 | 2014-12-08 | 2014-12-09 | 2014-12-12 | 2014-12-17 | GOLDFIN CONSTRUCTION
6307 | NC 2014 | K10 (2014) | Region VII | Cebu | 119845 | Mag-atubang PS | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1152712.2061 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-10 | 070214S00149 | 14HF0076 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-10-31 | 2014-11-06 | By Administration
6308 | NC 2014 | K10 (2014) | Region VII | Cebu | 119084 | Maghanoy ES | BARILI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 070214S00253 | 14HF0090 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | FIRST GRANDEUR BUILDERS
6309 | NC 2014 | K10 (2014) | Region VII | Cebu | 119847 | Mangga ES | TUBURAN | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6419264.7656 |  |  | COMPLETED | 1 | 2015-04-13 | 2015-04-13 | 070214S00228 | 14HF0107 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | FIRST GRANDEUR BUILDERS
6310 | NC 2014 | K10 (2014) | Region VII | Cebu | 312418 | Manguiao NHS | ASTURIAS | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
6311 | NC 2014 | K10 (2014) | Region VII | Cebu | 119098 | Mantalongon ES | BARILI | 3 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3395425.5846 |  |  | COMPLETED | 1 | 2015-04-13 | 2015-04-13 | 070214S00216 | 14HF0095 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | R.M. MONDARES CONSTRUCTION
6312 | NC 2014 | K10 (2014) | Region VII | Cebu | 119086 | Mantayupan ES | BARILI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-20 | 070214S00219 | 14HF0130 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
6313 | NC 2014 | K10 (2014) | Region VII | Cebu | 119817 | Matnog ES | TUBURAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1931149.1921 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 070214S00173 | 14HF0046 | 2014-08-27 | 2014-09-08 | 2014-09-09 | 2014-09-16 | 2014-09-22 | QUIRANTE CONSTRUCTION
6314 | NC 2014 | K10 (2014) | Region VII | Cebu | 119046 | Matun-og ES | BALAMBAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1070815.9023 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 070214S00342 | 14HF0132 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
6315 | NC 2014 | K10 (2014) | Region VII | Cebu | 119849 | Molobolo PS | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1152712.2061 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 070214S00150 | 14HF0045 | 2014-08-27 | 2014-09-08 | 2014-09-09 | 2014-09-16 | 2014-09-22 | MAP ALVIOLA CONSTRUCTION
6316 | NC 2014 | K10 (2014) | Region VII | Cebu | 119027 | Nangka ES | BALAMBAN | 3 | 1 | 10 | 2STY6CL & 2STY4CL | 2014 K10 BATCH 3 | 14778367.9688 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 070214S00337 | 14HF0128 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-05 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION
6317 | NC 2014 | K10 (2014) | Region VII | Cebu | 302949 | Nangka NHS | BALAMBAN | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7656 |  |  | COMPLETED | 1
6318 | NC 2014 | K10 (2014) | Region VII | Cebu | 119565 | Pandacan ES | PINAMUNGAHAN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070214S00223 | 14HF0137 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-05 | BL PANGAN CONSTRUCTION
6319 | NC 2014 | K10 (2014) | Region VII | Cebu | 119088 | Pangpang PS | BARILI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 070214S00217 | 14HF0130 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
6320 | NC 2014 | K10 (2014) | Region VII | Cebu | 303068 | Patupat NHS | BARILI | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2644754.4624 |  |  | COMPLETED | 1
6321 | NC 2014 | K10 (2014) | Region VII | Cebu | 119566 | Pinamungajan CES | Pinamungajan | 3 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 3 | 5088508.9248 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-04-21 | 070214S00357 | 14HF0116 | 2014-11-27 | 2014-12-08 | 2014-12-09 | 2014-12-12 | 2014-12-17 | BL PANGAN CONSTRUCTION
6322 | NC 2014 | K10 (2014) | Region VII | Cebu | 303075 | Pinamungajan NHS | PINAMUNGAHAN | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1
6323 | NC 2014 | K10 (2014) | Region VII | Cebu | 119567 | Punod ES | PINAMUNGAHAN | 3 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3385375.5846 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-04-21 | 070214S00236 | 14HF0118 | 2014-11-27 | 2014-12-08 | 2014-12-09 | 2014-12-12 | 2014-12-17 | GOLDFIN CONSTRUCTION
6324 | NC 2014 | K10 (2014) | Region VII | Cebu | 303083 | Rosario NHS | ALOGUINSAN | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8379203.2031 |  |  | COMPLETED | 1
6325 | NC 2014 | K10 (2014) | Region VII | Cebu | 119569 | Sacsac ES | PINAMUNGAHAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1780422.8953 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-03-22 | 070214S00225 | 14HF0131 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
6326 | NC 2014 | K10 (2014) | Region VII | Cebu | 118986 | San Isidro ES | ASTURIAS | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1870872.8953 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-11 | 070214S00331 | 14HF0093 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | BLIMEX CONSTRUCTION & SUPPLY
6327 | NC 2014 | K10 (2014) | Region VII | Cebu | 119571 | Sibago ES | PINAMUNGAHAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1000465.9023 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 070214S00215 | 14HF0131 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
6328 | NC 2014 | K10 (2014) | Region VII | Cebu | 119028 | Singsing PS | BALAMBAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-20 | 070214S00338 | 14HF0132 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
6329 | NC 2014 | K10 (2014) | Region VII | Cebu | 118989 | Sta. Rita ES | ASTURIAS | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-03-23 | 2015-03-23 | 070214S00332 | 14HF0117 | 2014-11-27 | 2014-12-08 | 2014-12-09 | 2014-12-12 | 2014-12-17 | BL PANGAN CONSTRUCTION
6330 | NC 2014 | K10 (2014) | Region VII | Cebu | 312414 | Sta. Rita NHS | ASTURIAS | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2853213.9542 |  |  | COMPLETED | 1
6331 | NC 2014 | K10 (2014) | Region VII | Cebu | 119572 | Tajao Central School | PINAMUNGAHAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-03-22 | 070214S00207 | 14HF0131 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
6332 | NC 2014 | K10 (2014) | Region VII | Cebu | 119573 | Tangub ES | PINAMUNGAHAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1000465.9023 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-03-22 | 070214S00227 | 14HF0131 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
6333 | NC 2014 | K10 (2014) | Region VII | Cebu | 119574 | Tanibag ES | PINAMUNGAHAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1830672.8953 |  |  | COMPLETED | 1 | 2015-03-23 | 2015-03-23 | 070214S00224 | 14HF0116 | 2014-11-27 | 2014-12-08 | 2014-12-09 | 2014-12-12 | 2014-12-17 | BL PANGAN CONSTRUCTION
6334 | NC 2014 | K10 (2014) | Region VII | Cebu | 118992 | Tubigagmanok ES | ASTURIAS | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-12-13 | 2015-12-07 | 070214S00432 | 15HF0078 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-02 | 2015-09-08 | J.A.R.C. CONSTRUCTION COMPANY
6335 | NC 2014 | K10 (2014) | Region VII | Cebu | 119824 | Tuburan Central ES | TUBURAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1911149.1921 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 070214S00182 | 14HF0043 | 2014-08-22 | 2014-09-02 | 2014-09-03 | 2014-09-10 | 2014-09-16 | MAP ALVIOLA CONSTRUCTION
6336 | NC 2014 | K10 (2014) | Region VII | Cebu | 303061 | Tuburan National High School | TUBURAN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1
6337 | NC 2014 | K10 (2014) | Region VII | Cebu | 119576 | Tutay ES | Pinamungajan | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 070214S00326 | 14HF0092 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | FIRST BUILDERS AND DEVELOPERS
6338 | NC 2014 | K10 (2014) | Region VII | Cebu | 500220 | Anapog Integrated School | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
6339 | NC 2014 | K10 (2014) | Region VII | Cebu | 500219 | Argawanon Integrated School | SAN REMIGIO | 4 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2644754.4624 |  |  | COMPLETED | 1
6340 | NC 2014 | K10 (2014) | Region VII | Cebu | 119059 | Atop-atop ES | Bantayan | 4 | 1 | 4 | 1STY3CL, 1STY1CL | 2014 K10 BATCH 2 | 4007000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00192 | 14HD0027 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
6341 | NC 2014 | K10 (2014) | Region VII | Cebu | 302924 | Bakhawan NHS | DAANBANTAYAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1
6342 | NC 2014 | K10 (2014) | Region VII | Cebu | 302938 | Bantayan NHS | BANTAYAN | 4 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11579484.375 |  |  | COMPLETED | 1
6343 | NC 2014 | K10 (2014) | Region VII | Cebu | 119062 | Baod ES | BANTAYAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1 | 2015-05-17 | 2015-05-17 | 070214S00196 | 15HD0017 | 2015-02-04 | 2015-02-16 | 2015-02-16 | 2015-02-23 | 2015-03-04 | ROVILLA CONSTRUCTION
6344 | NC 2014 | K10 (2014) | Region VII | Cebu | 119672 | Batad ES | San Remegio | 4 | 1 | 7 | 2U-1STY1CL, 1STY5CL | 2014 K10 BATCH 2 | 6579000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00147 | 14HD0022 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | FIRST BUILDERS AND DEVELOPERS
6345 | NC 2014 | K10 (2014) | Region VII | Cebu | 302939 | Bateria NHS | DAANBANTAYAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1
6346 | NC 2014 | K10 (2014) | Region VII | Cebu | 119264 | Bitoon ES | DAANBANTAYAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00153 | 14HD0025 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | FIRST BUILDERS AND DEVELOPERS
6347 | NC 2014 | K10 (2014) | Region VII | Cebu | 119265 | Calape ES | DAANBANTAYAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00163 | 14HD0024 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | BANTAY CONSTRUCTION
6348 | NC 2014 | K10 (2014) | Region VII | Cebu | 119749 | Canaocanao ES | Tabogon | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1063000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00154 | 14HD0019 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
6349 | NC 2014 | K10 (2014) | Region VII | Cebu | 119457 | Curva ES | Medellin | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1063000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00145 | 14HD0021 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
6350 | NC 2014 | K10 (2014) | Region VII | Cebu | 303026 | Curva NHS | MEDELLIN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1072712.2061 |  |  | COMPLETED | 1
6351 | NC 2014 | K10 (2014) | Region VII | Cebu | 119267 | Dalingding ES | DAANBANTAYAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00155 | 14HD0024 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | BANTAY CONSTRUCTION
6352 | NC 2014 | K10 (2014) | Region VII | Cebu | 119459 | Dalingding ES | Medellin | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1063000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00144 | 14HD0021 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
6353 | NC 2014 | K10 (2014) | Region VII | Cebu | 119461 | Don Virgilio ES | MEDELLIN | 4 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2733213.9542 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00157 | 14HD0021 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
6354 | NC 2014 | K10 (2014) | Region VII | Cebu | 303007 | Doong NHS | BANTAYAN | 4 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3536125.5846 |  |  | COMPLETED | 1
6355 | NC 2014 | K10 (2014) | Region VII | Cebu | 312458 | Gibitngil Integrated School | MEDELLIN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1986149.1921 |  |  | COMPLETED | 1
6356 | NC 2014 | K10 (2014) | Region VII | Cebu | 119268 | Guinsolungan ES | Daanbantayan | 4 | 1 | 6 | 1STY1CL, 1STY2CL, 1STY3CL | 2014 K10 BATCH 2 | 5679000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00184 | 14HD0025 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | FIRST BUILDERS AND DEVELOPERS
6357 | NC 2014 | K10 (2014) | Region VII | Cebu | 119687 | Hagdan ES | Sta. Fe | 4 | 1 | 17 | 2U-1STY3CL, 2U-1STY1CL, 1STY3CL, 1STY5CL, 1STY4CL | 2014 K10 BATCH 2 | 16500000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00135 | 14HD0028 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
6358 | NC 2014 | K10 (2014) | Region VII | Cebu | 119688 | Hilantagaan ES | SANTA FE | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4A | 1750272.8953 |  |  | COMPLETED | 1 | 2015-05-12 | 2015-05-12 | 070214S00405 | 15HD0022 | 2015-02-04 | 2015-02-16 | 2015-02-16 | 2015-02-23 | 2015-03-04 | ROVILLA CONSTRUCTION
6359 | NC 2014 | K10 (2014) | Region VII | Cebu | 312456 | Hilotongan Integrated School | BANTAYAN | 4 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3686875.5846 |  |  | COMPLETED | 1
6360 | NC 2014 | K10 (2014) | Region VII | Cebu | 303004 | Horacio Franco MNHS | TABOGON | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1921149.1921 |  |  | COMPLETED | 1
6361 | NC 2014 | K10 (2014) | Region VII | Cebu | 119752 | Jose Malazarte ES | TABOGON | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1981149.1921 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00158 | 14HD0019 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
6362 | NC 2014 | K10 (2014) | Region VII | Cebu | 119064 | Kabac ES | Bantayan | 4 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2246000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00190 | 14HD0027 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
6363 | NC 2014 | K10 (2014) | Region VII | Cebu | 303028 | Kinartacan NHS | SANTA FE | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 2001522.8953 |  |  | COMPLETED | 1
6364 | NC 2014 | K10 (2014) | Region VII | Cebu | 119281 | Lanao ES | DAANBANTAYAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-07-02 | 2015-07-02 | 070214S00303 | 15HD0016 | 2015-02-04 | 2015-02-16 | 2015-02-16 | 2015-02-23 | 2015-03-04 | FIRST BUILDERS AND DEVELOPERS
6365 | NC 2014 | K10 (2014) | Region VII | Cebu | 303041 | Libaong NHS | SAN REMIGIO | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1030615.9023 |  |  | COMPLETED | 1
6366 | NC 2014 | K10 (2014) | Region VII | Cebu | 119269 | Libertad Ps | Daanbantayan | 4 | 1 | 4 | 2U-1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 4008000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00194 | 14HD0026 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | BANTAY CONSTRUCTION
6367 | NC 2014 | K10 (2014) | Region VII | Cebu | 119052 | Lipayran ES | Bantayan | 4 | 1 | 8 | 2U-1STY2CL, 1STY1CL, 1STY3CL | 2014 K10 BATCH 2 | 7941000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00189 | 14HD0027 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
6368 | NC 2014 | K10 (2014) | Region VII | Cebu | 119282 | Logon ES | DAANBANTAYAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4A | 1750272.8953 |  |  | COMPLETED | 1 | 2015-09-18 | 2015-09-18 | 070214S00410 | 15HD0021 | 2015-05-18 | 2015-05-27 | 2015-05-27 | 2015-06-05 | 2015-06-24 | BANTAY CONSTRUCTION
6369 | NC 2014 | K10 (2014) | Region VII | Cebu | 119666 | Looc ES | SAN REMIGIO | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00206 | 14HD0084 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-10 | 2015-02-16 | GOLDFIN CONSTRUCTION
6370 | NC 2014 | K10 (2014) | Region VII | Cebu | 119679 | Luyang ES | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1810572.8953 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00209 | 14HD0084 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-10 | 2015-02-16 | GOLDFIN CONSTRUCTION
6371 | NC 2014 | K10 (2014) | Region VII | Cebu | 119428 | Maalat ES | MADRIDEJOS | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00199 | 14HD0088 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-06 | 2015-02-16 | ROVILLA CONSTRUCTION
6372 | NC 2014 | K10 (2014) | Region VII | Cebu | 119757 | Mabuli ES | TABOGON | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1961149.1921 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00159 | 14HD0019 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
6373 | NC 2014 | K10 (2014) | Region VII | Cebu | 119778 | Mabunao ES | Tabuelan | 4 | 1 | 7 | 5U-1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 7197000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00161 | 14HD0020 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | GONZALO CONSTRUCTION
6374 | NC 2014 | K10 (2014) | Region VII | Cebu | 119466 | Maharuhay ES | MEDELLIN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1890972.8953 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 070214S00214 | 15HD0015 | 2015-02-04 | 2015-02-16 | 2015-02-16 | 2015-02-23 | 2015-03-04 | BANTAY CONSTRUCTION
6375 | NC 2014 | K10 (2014) | Region VII | Cebu | 119053 | Mambacayao ES | Bantayan | 4 | 1 | 6 | 1STY3CL, 1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 6109000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00193 | 14HD0027 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
6376 | NC 2014 | K10 (2014) | Region VII | Cebu | 312445 | Marikaban Integrated School | SANTA FE | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
6377 | NC 2014 | K10 (2014) | Region VII | Cebu | 119759 | Muabog ES | Tabogon | 4 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2116000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00138 | 14HD0019 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
6378 | NC 2014 | K10 (2014) | Region VII | Cebu | 119692 | Okoy ES | SANTA FE | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1890972.8953 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00210 | 14HD0086 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-10 | 2015-02-16 | ROVILLA CONSTRUCTION
6379 | NC 2014 | K10 (2014) | Region VII | Cebu | 119693 | Pooc Elementary School | SANTA FE | 4 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2745254.4624 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00211 | 14HD0086 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-10 | 2015-02-16 | ROVILLA CONSTRUCTION
6380 | NC 2014 | K10 (2014) | Region VII | Cebu | 119668 | Punta ES | SAN REMIGIO | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00208 | 14HD0084 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-10 | 2015-02-16 | GOLDFIN CONSTRUCTION
6381 | NC 2014 | K10 (2014) | Region VII | Cebu | 119286 | Purgason PS | DAANBANTAYAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1921149.1921 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00148 | 14HD0026 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | BANTAY CONSTRUCTION
6382 | NC 2014 | K10 (2014) | Region VII | Cebu | 119763 | San Vicente ES | Tabogon | 4 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 2965000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00140 | 14HD0019 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
6383 | NC 2014 | K10 (2014) | Region VII | Cebu | 119069 | Sillon ES | Bantayan | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1123000 |  |  | COMPLETED | 1
6384 | NC 2014 | K10 (2014) | Region VII | Cebu | 119764 | Somosa ES | Tabogon | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1063000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00162 | 14HD0019 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
6385 | NC 2014 | K10 (2014) | Region VII | Cebu | 312420 | Sta. Fe. NHS-Hilantagaan Ext | Sta. Fe | 4 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 3105000 |  |  | COMPLETED | 1
6386 | NC 2014 | K10 (2014) | Region VII | Cebu | 119433 | tabagak Es | Madridejos | 4 | 1 | 4 | 2U-1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 4218000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00146 | 14HD0029 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
6387 | NC 2014 | K10 (2014) | Region VII | Cebu | 119288 | Talisay ES | DAANBANTAYAN | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-07-02 | 2015-07-02 | 070214S00202 | 15HD0016 | 2015-02-04 | 2015-02-16 | 2015-02-16 | 2015-02-23 | 2015-03-04 | FIRST BUILDERS AND DEVELOPERS
6388 | NC 2014 | K10 (2014) | Region VII | Cebu | 119289 | Tapilon CES | Daanbantayan | 4 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 2955000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00175 | 14HD0023 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | BANTAY CONSTRUCTION
6389 | NC 2014 | K10 (2014) | Region VII | Cebu | 302964 | Tapilon NHS | DAANBANTAYAN | 4 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2753213.9542 |  |  | COMPLETED | 1
6390 | NC 2014 | K10 (2014) | Region VII | Cebu | 119435 | Tarong ES | MADRIDEJOS | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1090915.9023 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00203 | 14HD0088 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-06 | 2015-02-16 | ROVILLA CONSTRUCTION
6391 | NC 2014 | K10 (2014) | Region VII | Cebu | 119290 | Tominjao ES | Daanbantayan | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1073000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00133 | 14HD0023 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | BANTAY CONSTRUCTION
6392 | NC 2014 | K10 (2014) | Region VII | Cebu | 302965 | Tominjao National High School | DAANBANTAYAN | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4352199.6094 |  |  | COMPLETED | 1
6393 | NC 2014 | K10 (2014) | Region VII | Cebu | 119436 | Tugas ES | MADRIDEJOS | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1090915.9023 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00204 | 14HD0088 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-10 | 2015-02-16 | ROVILLA CONSTRUCTION
6394 | NC 2014 | K10 (2014) | Region VII | Cebu | 119223 | Bagalnga ES | COMPOSTELA | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1072712.2061 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-25 | 070214S00118 | 14HI0032B | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | VEN RAY CONSTRUCTION CORPORATION
6395 | NC 2014 | K10 (2014) | Region VII | Cebu | 312448 | Bagalnga Integrated School | COMPOSTELA | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1072712.2061 |  |  | COMPLETED | 1
6396 | NC 2014 | K10 (2014) | Region VII | Cebu | 303105 | Bongdo NHS | BORBON | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1122712.2061 |  |  | COMPLETED | 1
6397 | NC 2014 | K10 (2014) | Region VII | Cebu | 302968 | Cabonga-an NHS | SAN FRANCISCO | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1830672.8953 |  |  | COMPLETED | 1
6398 | NC 2014 | K10 (2014) | Region VII | Cebu | 119639 | Cambat-an ES | San Francisco | 5 | 1 | 5 | 1STY4CL, 1STY1CL | 2014 K10 BATCH 2 | 4946000 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 070214S00142 | 14HI0030 | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6399 | NC 2014 | K10 (2014) | Region VII | Cebu | 302967 | Camotes NHS | SAN FRANCISCO | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2041149.1921 |  |  | COMPLETED | 1
6400 | NC 2014 | K10 (2014) | Region VII | Cebu | 119187 | Carmen Central ES | CARMEN | 5 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00266 | 14HI0093A | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
6401 | NC 2014 | K10 (2014) | Region VII | Cebu | 302973 | Carmen NHS-Day | CARMEN | 5 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4342149.6094 |  |  | COMPLETED | 1
6402 | NC 2014 | K10 (2014) | Region VII | Cebu | 119411 | Catarman ES | LILOAN | 5 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4362249.6094 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 070214S00268 | 15HI0004 | 2015-01-22 | 2015-02-03 | 2015-02-04 | 2015-02-08 | 2015-02-24 | NEOVENTURES CONSTRUCTION
6403 | NC 2014 | K10 (2014) | Region VII | Cebu | 312447 | Catmon Integrated School | CATMON | 5 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14456118.3984 |  |  | COMPLETED | 1
6404 | NC 2014 | K10 (2014) | Region VII | Cebu | 119226 | Compostela Central ES | COMPOSTELA | 5 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1 | 2016-04-20 |  | 070214S00431 | 15HI0076 | 2015-08-23 | 2015-09-04 | 2015-09-05 | 2015-09-09 | 2015-09-13 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6405 | NC 2014 | K10 (2014) | Region VII | Cebu | 119641 | Consuelo ES | SAN FRANCISCO | 5 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 3751795.7907 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070214S00274 | 14HI0096A | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | JOHN ARNE CONSTRUCTION
6406 | NC 2014 | K10 (2014) | Region VII | Cebu | 302994 | Consuelo NHS | San Francisco | 5 | 1 | 4 | 1STY3CL, 1STY1CL | 2014 K10 BATCH 2 | 3977000 |  |  | COMPLETED | 1
6407 | NC 2014 | K10 (2014) | Region VII | Cebu | 119642 | Daan Montealegre ES | SAN FRANCISCO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1030615.9023 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00275 | 14HI0094B | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6408 | NC 2014 | K10 (2014) | Region VII | Cebu | 119730 | Daat PS | Sogod | 5 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2126000 |  |  | COMPLETED | 1 | 2014-11-13 | 2014-11-13 | 070214S00177 | 14HI0037 | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6409 | NC 2014 | K10 (2014) | Region VII | Cebu | 119227 | Dapdap ES | COMPOSTELA | 5 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 2 | 3592562.5946 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-18 | 070214S00119 | 14HI0025 | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2015-01-19 | VEN RAY CONSTRUCTION CORPORATION
6410 | NC 2014 | K10 (2014) | Region VII | Cebu | 303074 | Don Filomeno Torres MNHS | PILAR | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1182712.2061 |  |  | COMPLETED | 1
6411 | NC 2014 | K10 (2014) | Region VII | Cebu | 119645 | Esperanza ES | SAN FRANCISCO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1030615.9023 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070214S00276 | 14HI0095B | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | JOHN ARNE CONSTRUCTION
6412 | NC 2014 | K10 (2014) | Region VII | Cebu | 119228 | Estaca ES | COMPOSTELA | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1861149.1921 |  |  | COMPLETED | 1 | 2014-11-28 | 2014-11-28 | 070214S00131 | 14HI0031A | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | NEOVENTURES CONSTRUCTION
6413 | NC 2014 | K10 (2014) | Region VII | Cebu | 119412 | Jubay ES | LILOAN | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15245522.3438 |  |  | COMPLETED | 1 | 2015-10-21 | 2015-10-21 | 070214S00258 | 15HI0001 | 2015-01-22 | 2015-02-03 | 2015-02-04 | 2015-02-08 | 2015-02-24 | VEN RAY CONSTRUCTION CORPORATION
6414 | NC 2014 | K10 (2014) | Region VII | Cebu | 119655 | Lucio O. Arquillano Memorial School | SAN FRANCISCO | 5 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4492899.6094 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 070214S00248 | 15HI0003 | 2015-01-22 | 2015-02-03 | 2015-02-04 | 2015-02-08 | 2015-02-24 | JOHN ARNE CONSTRUCTION
6415 | NC 2014 | K10 (2014) | Region VII | Cebu | 119229 | Lupa ES | COMPOSTELA | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1122712.2061 |  |  | COMPLETED | 1 | 2014-11-13 | 2014-11-13 | 070214S00111 | 14HI0033B | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | NEOVENTURES CONSTRUCTION
6416 | NC 2014 | K10 (2014) | Region VII | Cebu | 119231 | Mulao ES | COMPOSTELA | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1911149.1921 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-25 | 070214S00123 | 14HI0032A | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | VEN RAY CONSTRUCTION CORPORATION
6417 | NC 2014 | K10 (2014) | Region VII | Cebu | 119415 | Mulao ES | LILOAN | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1090915.9023 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00270 | 14HI0090A | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | JOHN ARNE CONSTRUCTION
6418 | NC 2014 | K10 (2014) | Region VII | Cebu | 119220 | Panalipan ES | CATMON | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1891149.1921 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 070214S00117 | 14HI0038A | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-11-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
6419 | NC 2014 | K10 (2014) | Region VII | Cebu | 119232 | Panangban ES | COMPOSTELA | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1881149.1921 |  |  | COMPLETED | 1 | 2014-11-28 | 2014-11-28 | 070214S00124 | 14HI0034A | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | JOHN ARNE CONSTRUCTION
6420 | NC 2014 | K10 (2014) | Region VII | Cebu | 119649 | Paypay ES | San Francisco | 5 | 1 | 6 | 1STY5CL, 1STY1CL | 2014 K10 BATCH 2 | 5846000 |  |  | COMPLETED | 1 | 2015-03-13 | 2015-03-13 | 070214S00141 | 14HI0026 | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6421 | NC 2014 | K10 (2014) | Region VII | Cebu | 303081 | Puertobello NHS - Pob. Ext. | TUDELA | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1830672.8953 |  |  | COMPLETED | 1
6422 | NC 2014 | K10 (2014) | Region VII | Cebu | 303080 | Puertobello NHS-Main | Tudela | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1
6423 | NC 2014 | K10 (2014) | Region VII | Cebu | 119590 | Rizal ES | PORO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 070214S00271 | 14HI0097C | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6424 | NC 2014 | K10 (2014) | Region VII | Cebu | 119651 | San Isidro ES | San Francisco | 5 | 1 | 5 | 1STY4CL, 1STY1CL | 2014 K10 BATCH 2 | 4876000 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-02-26 | 070214S00132 | 14HI0027 | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6425 | NC 2014 | K10 (2014) | Region VII | Cebu | 119152 | SAN JOSE ES | BORBON | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070214S00265 | 14HI0091B | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
6426 | NC 2014 | K10 (2014) | Region VII | Cebu | 119653 | Sonog ES | SAN FRANCISCO | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2745254.4624 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00277 | 14HI0094A | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6427 | NC 2014 | K10 (2014) | Region VII | Cebu | 119592 | Sta. Rita PS | PORO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 070214S00272 | 14HI0097B | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6428 | NC 2014 | K10 (2014) | Region VII | Cebu | 119233 | Tag-ubi ES | COMPOSTELA | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1122712.2061 |  |  | COMPLETED | 1 | 2014-11-28 | 2014-11-28 | 070214S00125 | 14HI0034B | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | JOHN ARNE CONSTRUCTION
6429 | NC 2014 | K10 (2014) | Region VII | Cebu | 119203 | Taguini ES | CARMEN | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2795504.4624 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00279 | 14HI0093B | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
6430 | NC 2014 | K10 (2014) | Region VII | Cebu | 187022 | Tamiao ES | COMPOSTELA | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1881149.1921 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 070214S00126 | 14HI0035A | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-11-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6431 | NC 2014 | K10 (2014) | Region VII | Cebu | 119746 | Tangke PS | Sogod | 5 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2126000 |  |  | COMPLETED | 1 | 2014-11-13 | 2014-11-13 | 070214S00136 | 14HI0036 | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | NEOVENTURES CONSTRUCTION
6432 | NC 2014 | K10 (2014) | Region VII | Cebu | 119421 | Tayud Elementary School | LILOAN | 5 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4B | 15121327.92 |  |  | COMPLETED | 1 | 2016-03-19 |  | 070214S00435 | 15HI0074 | 2015-08-11 | 2015-08-23 | 2015-08-24 | 2015-08-28 | 2015-09-01 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6433 | NC 2014 | K10 (2014) | Region VII | Cebu | 119593 | Teguis ES | PORO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 070214S00273 | 14HI0097A | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6434 | NC 2014 | K10 (2014) | Region VII | Cebu | 312449 | Tulang Integrated School | SAN FRANCISCO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1121065.9023 |  |  | COMPLETED | 1
6435 | NC 2014 | K10 (2014) | Region VII | Cebu | 303009 | Zosimo E. Fabroa MNHS | PORO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1
6436 | NC 2014 | K10 (2014) | Region VII | Cebu | 119234 | Bagong Lipunan Elementary School | CONSOLACION | 6 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1 | 2015-06-25 | 2015-06-25 | 070214S00220 | 15HN0007 | 2015-01-09 | 2015-01-12 | 2015-01-26 | 2015-02-05 | 2015-02-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6437 | NC 2014 | K10 (2014) | Region VII | Cebu | 119252 | Bangbang ES | CORDOBA | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4342149.6094 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-06 | 070214S00242 | 14HN0053 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | SERCHER DEVELOPMENT CORPORATION
6438 | NC 2014 | K10 (2014) | Region VII | Cebu | 187025 | Catarman Elementary School | CORDOBA | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070214S00257 | 14HN0057 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6439 | NC 2014 | K10 (2014) | Region VII | Cebu | 119238 | Consolacion Central ES | CONSOLACION | 6 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4B | 31252890.27 |  |  | COMPLETED | 1 | 2016-08-01 |  | 070214S00427 | 15HN0109 | 2015-09-02 | 2015-09-10 | 2015-09-22 | 2015-09-28 | 2015-10-07 | PLD CONSTRUCTION
6440 | NC 2014 | K10 (2014) | Region VII | Cebu | 119257 | Gabi ES | CORDOBA | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-04 | 070214S00243 | 14HN0054 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | NASH BUILDERS & SUPPLIES
6441 | NC 2014 | K10 (2014) | Region VII | Cebu | 119258 | Gilutongan ES | CORDOBA | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1142712.2061 |  |  | COMPLETED | 1 | 2014-12-21 | 2014-12-19 | 070214S00099 | 14HN0015 | 2014-08-13 | 2014-08-18 | 2014-09-01 | 2014-09-11 | 2014-09-22 | BANTAY CONSTRUCTION
6442 | NC 2014 | K10 (2014) | Region VII | Cebu | 119259 | Ibabao ES | CORDOBA | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4342149.6094 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-05 | 070214S00244 | 14HN0055 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | GELA CONSTRUCTION
6443 | NC 2014 | K10 (2014) | Region VII | Cebu | 119243 | Lanipga ES | CONSOLACION | 6 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2903213.9542 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-19 | 070214S00101 | 14HN0016 | 2014-08-13 | 2014-08-18 | 2014-09-01 | 2014-09-11 | 2014-09-22 | BANTAY CONSTRUCTION
6444 | NC 2014 | K10 (2014) | Region VII | Cebu | 119260 | Pilipog ES | CORDOBA | 6 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070214S00245 | 14HN0056 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-12 | PLD CONSTRUCTION
6445 | NC 2014 | K10 (2014) | Region VII | Cebu | 302991 | Pulpogan NHS | CONSOLACION | 6 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8328953.2031 |  |  | COMPLETED | 1 | 2015-05-21 | 2015-05-21 | 070214S00247 | 14HN0058 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-12 | GONZALODO ENTERPRISES
6446 | NC 2014 | K10 (2014) | Region VII | Cebu | 119250 | Tugbongan ES | CONSOLACION | 6 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10877093.5547 |  |  | COMPLETED | 1 | 2015-11-22 | 2015-11-20 | 070214S00241 | 15HN0016 | 2015-01-27 | 2015-01-29 | 2015-02-09 | 2015-02-17 | 2015-02-26 | GEETY REALTY AND DEVELOPMENT CORPORATION
6447 | NC 2014 | K10 (2014) | Region VII | Cebu City | 119929 | Budla-an ES | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7656 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-08-18 | 070214S00407 | 14HH0122 | 2014-12-19 | 2014-12-05 | 2014-12-19 | 2014-12-29 | 2015-02-13 | GOWIL BUILDERS
6448 | NC 2014 | K10 (2014) | Region VII | Cebu City | 303143 | Bulacao NHS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4322049.6094 |  |  | reverted | 0
6449 | NC 2014 | K10 (2014) | Region VII | Cebu City | 119906 | Dr. Emilio Osmena ES | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | reverted | 0
6450 | NC 2014 | K10 (2014) | Region VII | Cebu City | 119880 | Guadalupe ES | CEBU CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | reverted | 0
6451 | NC 2014 | K10 (2014) | Region VII | Cebu City | 119885 | Labangon Bliss ES | CEBU CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | reverted | 0
6452 | NC 2014 | K10 (2014) | Region VII | Cebu City | 119882 | Mambaling ES | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | reverted | 0
6453 | NC 2014 | K10 (2014) | Region VII | Cebu City | 119890 | Toong ES | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | reverted | 0
6454 | NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 325301 | Alpaco NHS | CITY OF NAGA | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1
6455 | NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 312433 | Lanas NHS | CITY OF NAGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1080865.9023 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00418 | 14-HE-0098 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | FIRST BUILDERS AND DEVELOPERS
6456 | NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 325307 | Lutac NHS | CITY OF NAGA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-13 | 2014-12-15 | 070214S00008 | 14-HE-0029 | 2014-06-24 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-18 | QM BUILDERS
6457 | NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 312435 | Mainit NHS | CITY OF NAGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1931172.8953 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-04-24 | 070214S00417 | 14-HE-0101 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | QUIRANTE CONSTRUCTION
6458 | NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 312436 | Mayana NHS | CITY OF NAGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00416 | 14-HE-0098 | 2014-11-11 | 2014-11-12 | 2014-12-25 | 2014-12-28 | 2014-12-03 | FIRST BUILDERS AND DEVELOPERS
6459 | NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 119508 | Naalad ES | CITY OF NAGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | reverted | 0
6460 | NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 119511 | Pangdan ES | CITY OF NAGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1901022.8953 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00419 | 14-HE-0098 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | FIRST BUILDERS AND DEVELOPERS
6461 | NC 2014 | K10 (2014) | Region VII | Danao City | 119351 | Bayabas ES | DANAO CITY | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-10-13 | 2014-10-13 | 070214S00019 | 14HI0015 | 2014-07-08 | 2014-07-20 | 2014-07-21 | 2014-07-30 | 2014-08-15 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
6462 | NC 2014 | K10 (2014) | Region VII | Danao City | 302957 | Beatriz D. Durano MNHS | DANAO CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | reverted | 0 |  |  | 070214S00011
6463 | NC 2014 | K10 (2014) | Region VII | Danao City | 500394 | Bibiana Mercado Integrated School | DANAO CITY | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2970174.43 |  |  | COMPLETED | 1 | 2014-11-12 | 2014-11-12 | 070214S00012 | 14HI0022 | 2014-07-08 | 2014-07-20 | 2014-07-21 | 2014-07-30 | 2014-08-15 | VEN RAY CONSTRUCTION CORPORATION
6464 | NC 2014 | K10 (2014) | Region VII | DANAO CITY | 119333 | Cabungahan ES | Danao | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1
6465 | NC 2014 | K10 (2014) | Region VII | DANAO CITY | 119335 | Cogon ES | Danao | 5 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 3 | 4112918.6116 |  |  | COMPLETED | 1
6466 | NC 2014 | K10 (2014) | Region VII | Danao City | 119347 | Dungga ES | DANAO CITY | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2880174.43 |  |  | COMPLETED | 1 | 2015-02-09 | 2015-02-09 | 070214S00009 | 14HI0047 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-11-01 | 2014-11-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
6467 | NC 2014 | K10 (2014) | Region VII | Danao City | 302959 | Elpidio H. Perez MNHS | DANAO CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 070214S00016 | 14HI0048 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-11-01 | 2014-11-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
6468 | NC 2014 | K10 (2014) | Region VII | DANAO CITY | 119361 | Eustaquio Capin ES | Danao | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070214S00255 | 14HI0091A | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
6469 | NC 2014 | K10 (2014) | Region VII | Danao City | 119363 | Gerardo Ypil ES | DANAO CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 070214S00010 | 14HI0016 | 2014-07-08 | 2014-07-20 | 2014-07-21 | 2014-07-30 | 2014-08-15 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
6470 | NC 2014 | K10 (2014) | Region VII | Danao City | 322002 | Guinsay National High School | DANAO CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 070214S00013 | 14HI0021 | 2014-07-08 | 2014-07-20 | 2014-07-21 | 2014-07-30 | 2014-08-15 | VEN RAY CONSTRUCTION CORPORATION
6471 | NC 2014 | K10 (2014) | Region VII | Danao City | 119365 | Langosig ES | DANAO CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 070214S00007 | 14HI0017 | 2014-07-08 | 2014-07-20 | 2014-07-21 | 2014-07-30 | 2014-08-15 | FIRST BUILDERS AND DEVELOPERS
6472 | NC 2014 | K10 (2014) | Region VII | DANAO CITY | 119338 | Lawaan ES | Danao | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1 | 2015-09-01 | 2015-09-01 | 070214S00251 | 14HI0092A | 2015-06-08 | 2015-06-20 | 2015-06-21 | 2015-06-25 | 2015-07-03 | VEN RAY CONSTRUCTION CORPORATION
6473 | NC 2014 | K10 (2014) | Region VII | DANAO CITY | 303036 | Lawaan NHS | Danao | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1
6474 | NC 2014 | K10 (2014) | Region VII | Danao City | 303036 | Lawaan NHS | DANAO CITY | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2910174.43 |  |  | COMPLETED | 1
6475 | NC 2014 | K10 (2014) | Region VII | Danao City | 303038 | Miguel C. Tiongko NHS | DANAO CITY | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1
6476 | NC 2014 | K10 (2014) | Region VII | Danao City | 302960 | Sandayong Sur NHS | DANAO CITY | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2890174.43 |  |  | COMPLETED | 1 | 2014-11-12 | 2014-11-12 | 070214S00017 | 14HI0018 | 2014-07-08 | 2014-07-20 | 2014-07-21 | 2014-07-30 | 2014-08-15 | VEN RAY CONSTRUCTION CORPORATION
6477 | NC 2014 | K10 (2014) | Region VII | Danao City | 303038 | Nicolas U. Tiongko MNHS | DANAO CITY | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1
6478 | NC 2014 | K10 (2014) | Region VII | Danao City | 119370 | Sibacan ES | DANAO CITY | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 070214S00094 | 14HI0035B | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-11-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
6479 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119979 | Marigondon Elementary School | LAPU-LAPU CITY (OPON) | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4A | 14045118.3984 |  |  | COMPLETED | 1 | 2015-09-08 | 2015-09-08 | 070214S00412 | 14HN0062 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-23 | 2015-01-12 | JJ &J CONSTRUCTION & GENERAL SUPPLY
6480 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119984 | Sudtonggan ES | LAPU-LAPU CITY (OPON) | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6094 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070214S00413 | 14HN0063 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-23 | 2015-01-12 | JJ &J CONSTRUCTION & GENERAL SUPPLY
6481 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119963 | Bankal ES | LAPU-LAPU CITY (OPON) | 1 | 1 | 15 | 3STY15CL | 2014 K10 BATCH 4B | 21383013.45 |  |  | COMPLETED | 1 | 2016-07-02 |  | 070214S00430 | 15HN0110 | 2015-09-02 | 2015-09-10 | 2015-09-22 | 2015-09-28 | 2015-10-07 | JJ &J CONSTRUCTION & GENERAL SUPPLY
6482 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119983 | Suba Masulog ES | LAPU-LAPU CITY (OPON) | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2016-04-02 |  | 070214S00429 | 15HN0078 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | GONZALODO ENTERPRISES
6483 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119985 | Babag l ES | Lapu-Lapu City | 6 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3335125.5846 |  |  | COMPLETED | 1 | 2015-04-26 | 2015-04-26 | 070214S00397 | 14HN0039 | 2014-11-27 | 2014-12-01 | 2014-12-12 | 2014-12-23 | 2015-01-07 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6484 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119986 | Babag ll ES | Lapu-Lapu City | 6 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 070214S00399 | 14HN0030 | 2014-11-27 | 2014-12-01 | 2014-12-12 | 2014-12-23 | 2015-01-07 | GELA CONSTRUCTION
6485 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 303173 | Babag NHS - Poblacion Night HS Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-06 | 070214S00394 | 14HN0052 |  | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | GELA CONSTRUCTION
6486 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 303174 | Bankal NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | reverted | 0
6487 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 303175 | Bankal NHS - Abuno HS Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | reverted | 0
6488 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119975 | Basak ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4342149.6094 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-05 | 070214S00393 | 14HN0051 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6489 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119964 | Buaya Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15245522.3438 |  |  | COMPLETED | 1 | 2015-09-03 | 2015-09-03 | 070214S00398 | 14HN0048 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | GONZALODO ENTERPRISES
6490 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119987 | Canjulao ES | Lapu-Lapu City | 6 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4294527.3578 |  |  | reverted | 0
6491 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119990 | Looc ES | Lapu-Lapu City | 6 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 3 | 5088508.9248 |  |  | reverted | 0
6492 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119966 | Mactan Air Base ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6348914.7656 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-06 | 070214S00396 | 14HN0049 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | GONZALODO ENTERPRISES
6493 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 303180 | Marigondon NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | reverted | 0
6494 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 303181 | Marigondon NHS - Basak Night HS Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | reverted | 0
6495 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119968 | Pajo ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-04-06 | 2015-04-06 | 070214S00392 | 14HN0050 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | GONZALODO ENTERPRISES
6496 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119956 | Poo ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1000465.9023 |  |  | COMPLETED | 1 | 2015-03-07 | 2015-03-06 | 070214S00304 | 14HN0032 | 2014-11-27 | 2014-12-01 | 2014-12-12 | 2014-12-23 | 2015-01-07 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6497 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119957 | Sabang ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4372299.6094 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-10 | 070214S00387 | 14HN0059 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6498 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 303189 | Sta. Rosa NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | reverted | 0
6499 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119982 | Subabasbas ES | Lapu-Lapu City | 6 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3335125.5846 |  |  | COMPLETED | 1 | 2015-05-26 | 2015-05-26 | 070214S00400 | 14HN0040 | 2014-11-27 | 2014-12-01 | 2014-12-12 | 2014-12-23 | 2015-01-07 | GELA CONSTRUCTION
6500 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119993 | Timpolok ES | Lapu-Lapu City | 6 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | reverted | 0
6501 | NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119962 | Tungasan ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-03-07 | 2015-03-06 | 070214S00391 | 14HN0031 | 2014-11-27 | 2014-12-01 | 2014-12-12 | 2014-12-23 | 2015-01-07 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
6502 | NC 2014 | K10 (2014) | Region VII | Mandaue City | 303195 | Canduman NHS | MANDAUE CITY | 6 | 1 | 6 | 3STY 6CL | 2014 K10 BATCH 1 | 8107000 |  |  | COMPLETED | 1
6503 | NC 2014 | K10 (2014) | Region VII | Mandaue City | 120013 | Maguikay ES | MANDAUE CITY | 6 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-03 | 2015-12-29 | 070214S00428 | 15HN0079 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | P.B. OBIAL CONSTRUCTION
6504 | NC 2014 | K10 (2014) | Region VII | Mandaue City | 303199 | Mandaue City Comprehensive NHS | MANDAUE CITY | 6 | 1 | 9 | 3STY 9CL | 2014 K10 BATCH 1 | 12159000 |  |  | COMPLETED | 1
6505 | NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 303065 | NAGA NATIONAL HIGH SCHOOL | NAGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1
6508 | NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 118704 | Cabawan ES | Tagbilaran City | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-09-30 | 070114S00377 | 15HA0008 | 2015-04-06 | 2015-03-23 | 2015-04-06 | 2015-05-27 | 2015-07-03 | HNR CONSTRUCTION & SUPPLY
6509 | NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 302846 | DCPNHS | Tagbilaran City | 1 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11277984.375 |  |  | COMPLETED | 1
6510 | NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 302875 | Mansasa National High School | TAGBILARAN CITY (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | [10 empty] | No Ceiling
6511 | NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 302875 | Mansasa NHS | Tagbilaran City | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
6512 | NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 118712 | San Isidro ES | Tagbilaran City | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-09-30 | 070114S00378 | 15HA0008 | 2015-04-06 | 2015-03-23 | 2015-04-06 | 2015-05-27 | 2015-07-03 | HNR CONSTRUCTION & SUPPLY
6513 | NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 322102 | SAN ISIDRO NATIONAL HIGH SCHOOL | TAGBILARAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00470 | 15HA0084 | 2015-08-11 | 2015-07-30 | 2015-08-11 | 2015-08-19 | 2015-09-21 | PUREGOLD CONSTRUCTION & DEVT. CORP.
6514 | NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 118713 | Tagbilaran City Central Elementary School | TAGBILARAN CITY (Capital) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2170417.57 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-06 | 070114S00064 | 14HA0022 | 2014-09-09 | 2014-08-28 | 2014-09-09 | 2014-09-13 | 2014-10-30 | JB ROCK CONSTRUCTION SUPPLY | No Painting, No Ceiling, No Toilet Fixtures
6515 | NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 118714 | Taloto ES | Tagbilaran City | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-09-30 | 070114S00379 | 15HA0008 | 2015-04-06 | 2015-03-23 | 2015-04-06 | 2015-05-27 | 2015-07-03 | HNR CONSTRUCTION & SUPPLY
6516 | NC 2014 | K10 (2014) | Region VII | Talisay City | 119785 | Borromeo Bros. ES | Talisay | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14045118.3984 |  |  | COMPLETED | 1 | 2016-01-06 |  | 070214S00373 | 14-HE-0125 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | GENETIAN BUILDERS
6517 | NC 2014 | K10 (2014) | Region VII | Talisay City | 119794 | Bulacao ES | Talisay | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14045118.3984 |  |  | COMPLETED | 1 | 2016-01-21 |  | 070214S00385 | 14-HE-0124 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | JEGMA CONSTRUCTION & DEVELOPMENT CORPORATION
6518 | NC 2014 | K10 (2014) | Region VII | Talisay City | 119797 | Candulawan ES | CITY OF TALISAY | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4317024.6094 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-05 | 070214S00371 | 14-HE-0105 | 2014-11-18 | 2014-12-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | GOLDFIN CONSTRUCTION
6519 | NC 2014 | K10 (2014) | Region VII | Talisay City | 302971 | Cansojong NHS | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6328814.7656 |  |  | COMPLETED | 1
6520 | NC 2014 | K10 (2014) | Region VII | Talisay City | 303019 | Jaclupan NHS | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6338864.7656 |  |  | COMPLETED | 1
6521 | NC 2014 | K10 (2014) | Region VII | Talisay City | 119800 | Lagtang ES | Talisay | 1 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11277984.375 |  |  | COMPLETED | 1 | 2015-09-04 | 2015-09-02 | 070214S00384 | 14-HE-0115 | 2014-11-18 | 2014-12-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QUIRANTE CONSTRUCTION
6522 | NC 2014 | K10 (2014) | Region VII | Talisay City | 322209 | Lawaan III National High School (Night) | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10917293.5547 |  |  | COMPLETED | 1 | 2015-12-17 | 2015-12-15 | 070214S00383 | 14-HE-0123 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | QUIRANTE CONSTRUCTION
6523 | NC 2014 | K10 (2014) | Region VII | Talisay City | 233501 | Linao ES | CITY OF TALISAY | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4306974.6094 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-05 | 070214S00372 | 14-HE-0110 | 2014-11-18 | 2014-12-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QUIRANTE CONSTRUCTION
6524 | NC 2014 | K10 (2014) | Region VII | Talisay City | 119788 | Maghaway ES | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6318764.7656 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-05-21 | 070214S00378 | 14-HE-0113 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | RAMIJO CONSTRUCTION
6525 | NC 2014 | K10 (2014) | Region VII | Talisay City | 322201 | Maghaway NHS | Talisay | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
6526 | NC 2014 | K10 (2014) | Region VII | Talisay City | 119790 | San Roque ES | Talisay | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14045118.3984 |  |  | COMPLETED | 1 | 2016-01-06 |  | 070214S00390 | 14-HE-0126 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | QUIRANTE CONSTRUCTION
6527 | NC 2014 | K10 (2014) | Region VII | Talisay City | 119803 | Tabunok CES | Talisay | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14045118.3984 |  |  | COMPLETED | 1 | 2016-01-06 |  | 070214S00375 | 14-HE-0127 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | GOLDFIN CONSTRUCTION
6528 | NC 2014 | K10 (2014) | Region VII | Talisay City | 119791 | Talisay City Central ES | CITY OF TALISAY | 1 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 4A | 18729509.7656 |  |  | COMPLETED | 1 | 2016-01-21 |  | 070214S00406 | 14-HE-0129 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | JEGMA CONSTRUCTION & DEVELOPMENT CORPORATION
6529 | NC 2014 | K10 (2014) | Region VII | Toledo City | 120713 | Biga ES | Toledo City | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | COMPLETED | 1 | 2015-12-06 | 2015-12-05 | 070214S00425 | 15HF0079 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-09-25 | 2015-10-01 | BLIMEX CONSTRUCTION & SUPPLY
6530 | NC 2014 | K10 (2014) | Region VII | Toledo City | 120743 | Bulongan ES | Toledo City | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4442649.6094 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070214S00376 | 14HF0126 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-05 | DINAH JANE CONSTRUCTION SUPPLY
6531 | NC 2014 | K10 (2014) | Region VII | Toledo City | 303317 | Bunga National High School | Toledo City | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1861149.1921 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 070214S00092 | 14HF0027 | 2014-07-16 | 2014-07-28 | 2014-07-29 | 2014-09-08 | 2014-09-12 | BLIMEX CONSTRUCTION & SUPPLY
6532 | NC 2014 | K10 (2014) | Region VII | Toledo City | 120726 | Canlumampao ES | Toledo City | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2453690.4049 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 070214S00381 | 14HF0134 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
6533 | NC 2014 | K10 (2014) | Region VII | Toledo City | 120727 | Captain Claudio ES | Toledo City | 3 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 3 | 5088508.9248 |  |  | reverted | 0
6534 | NC 2014 | K10 (2014) | Region VII | Toledo City | 120728 | Carmen ES | Toledo City | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-01-09 | 070214S00058 | 14HF0025 | 2014-07-10 | 2014-07-21 | 2014-07-22 | 2014-12-11 | 2014-12-16 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
6535 | NC 2014 | K10 (2014) | Region VII | Toledo City | 120732 | Mainggit ES | Toledo City | 3 | 1 | 4 | 2STY 4CL | 2014 K10 BATCH 1 | 5243164.26 |  |  | COMPLETED | 1
6536 | NC 2014 | K10 (2014) | Region VII | Toledo City | 120732 | Mainggit ES | Toledo City | 3 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3335125.5846 |  |  | COMPLETED | 1
6537 | NC 2014 | K10 (2014) | Region VII | Toledo City | 120734 | Matab-ang ES | Toledo City | 3 | 1 | 12 | 4UNITS 1STY3CL | 2014 K10 BATCH 3 | 7632763.3872 |  |  | Reverted | 0
6538 | NC 2014 | K10 (2014) | Region VII | Toledo City | 303313 | Matab-ang NHS | Toledo City | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7656 |  |  | COMPLETED | 1 | 2015-05-18 | 2015-05-18 | 070214S00411 | 14HF0140 | 2014-12-11 | 2014-12-12 | 2014-12-23 | 2015-01-07 | 2015-01-12 | DINAH JANE CONSTRUCTION SUPPLY
6539 | NC 2014 | K10 (2014) | Region VII | Toledo City | 120737 | Old Bucao ES | Toledo City | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2234658.24 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-03-14 | 070214S00420 | 14HF0025 | 2014-07-10 | 2014-07-21 | 2014-07-22 | 2014-12-11 | 2014-12-16 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
6540 | NC 2014 | K10 (2014) | Region VII | Toledo City | 120756 | Sam-ang ES | Toledo City | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-02-25 | 070214S00050 | 14HF0025 | 2014-07-10 | 2014-07-21 | 2014-07-22 | 2014-12-11 | 2014-12-16 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
6541 | NC 2014 | K10 (2014) | Region VII | Toledo City | 120740 | Talavera ES | Toledo City | 3 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 3 | 5088508.9248 |  |  | Reverted | 0
6542 | NC 2014 | K10 (2014) | Region VII | Toledo City | 190503 | Dumlog ES | Toledo City | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 070214S00093 | 14HF0027 | 2014-07-16 | 2014-07-28 | 2014-07-29 | 2014-09-08 | 2014-09-12 | BLIMEX CONSTRUCTION & SUPPLY
9925 | NC 2015 | K10 (2015) | Region VII | TANJAY CITY | 120410 | Calicanan ES | PAMPLONA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6289337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00190 | 0703-15-S-00190 | 2015-10-04 | 2015-10-16 | 2015-10-21 | 2015-11-04 | 2015-11-11 | SILLIMAN AVENUE CONST & SUPPLY (FORMERLY OVERDRIVE
12349 | NC 2015 | SHS (2015) | Region VII | BOGO CITY | 302930 | Banban National High School | CITY OF BOGO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
12350 | NC 2015 | SHS (2015) | Region VII | BOGO CITY | 302931 | Binabag NHS | CITY OF BOGO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00121 | 15HD0032 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-05 | 2015-08-12 | R.U. AQUINO CONSTRUCTION AND DEVELOPMENT CORP. (FO
12351 | NC 2015 | SHS (2015) | Region VII | BOGO CITY | 302932 | Cayang National High School | CITY OF BOGO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00122 | 15HD0033 | 2015-06-22 | 2015-07-02 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
12352 | NC 2015 | SHS (2015) | Region VII | Bogo City | 325001 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8504965.051 |  |  | COMPLETED | 1
12353 | NC 2015 | K10 (2015) | Region VII | Bogo City | 187009 | Don Celestino Martinez MNHS | CITY OF BOGO | 4 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | COMPLETED | 1 |  |  | 070215S00506 | 15HD0096 | 2015-10-14 | 2015-10-27 | 2015-10-27 | 2015-11-03 | 2015-11-10 | BANTAY CONSTRUCTION
12354 | NC 2015 | SHS (2015) | Region VII | BOGO CITY | 302933 | Don Potenciano Catarata MNHS | CITY OF BOGO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00100 | 15HD0033 | 2015-06-22 | 2015-07-02 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
12355 | NC 2015 | SHS (2015) | Region VII | Bogo City | 302934 | Jovencio N. Masong NHS | CITY OF BOGO | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8524965.051 |  |  | COMPLETED | 1 |  |  | 070215S00117 | 15HD0035 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
12356 | NC 2015 | SHS (2015) | Region VII | Bogo City | 302935 | La Paz NHS | CITY OF BOGO | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00115 | 15HD0036 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
12357 | NC 2015 | SHS (2015) | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1
12358 | NC 2015 | SHS (2015) | Region VII | BOGO CITY | 302937 | Odlot National High School | CITY OF BOGO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00093 | 15HD0033 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
12359 | NC 2015 | SHS (2015) | Region VII | Bohol | 302811 | Baclayon National High School | BACLAYON | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | Reverted | 0 |  |  | 070115S00149 | 15HA00-18 | 2015-09-30
12360 | NC 2015 | SHS (2015) | Region VII | Bohol | 302907 | Bantolinao National High School | ANTEQUERA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
12361 | NC 2015 | SHS (2015) | Region VII | Bohol | 302817 | Biking Tech-Voc HS | DAUIS | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
12362 | NC 2015 | K10 (2015) | Region VII | Bohol | 118494 | Bugho PS | LOON | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00215 | 15HA0148 | 2015-10-19 | 2015-10-07 | 2015-10-19 | 2015-10-23 | 2015-11-27 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12363 | NC 2015 | K10 (2015) | Region VII | Bohol | 118777 | Bunacan ES | TUBIGON | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00154 | 15HA0120 | 2015-09-11 | 2015-09-01 | 2015-09-11 | 2015-09-17 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12364 | NC 2015 | SHS (2015) | Region VII | Bohol | 302819 | Busao National High School | MARIBOJOC | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2690828.124 |  |  | COMPLETED | 1 |  |  | 070115S00063 | 15HA0088 | 2015-08-17 | 2015-08-05 | 2015-08-17 | 2015-08-21 | 2015-10-05 | PUREGOLD CONSTRUCTION & DEVT. CORP.
12365 | NC 2015 | SHS (2015) | Region VII | Bohol | 302820 | Cabilao NHS | LOON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6429337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00064 | 15HA0125 | 2015-10-02 | 2015-09-21 | 2015-10-02 | 2015-10-09 |  | DT&C CONSTRUCTION
12366 | NC 2015 | SHS (2015) | Region VII | Bohol | 302883 | Calape NHS | CALAPE | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00065 | 15HA0133 | 2015-10-09 | 2015-09-28 | 2015-10-09 | 2015-10-15 | 2015-11-09 | BNYU ENTERPRISES & CONSTRUCTION
12367 | NC 2015 | K10 (2015) | Region VII | Bohol | 118201 | Canapnapan PS | CORELLA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00214 | 15HA0123 | 2015-10-23 | 2015-10-12 | 2015-10-23 | 2015-10-29
12368 | NC 2015 | K10 (2015) | Region VII | Bohol | 312306 | Canlaas High School | ANTEQUERA | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00167 | 15HA0141 | 2015-10-16 | 2015-10-05 | 2015-10-16 | 2015-10-22 | 2015-11-18 | PUREGOLD CONSTRUCTION & DEVT. CORP.
12369 | NC 2015 | SHS (2015) | Region VII | Bohol | 302833 | Catigbian NHS | CATIGBIAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | COMPLETED | 1
12370 | NC 2015 | SHS (2015) | Region VII | Bohol | 302835 | Cawayanan NHS | TUBIGON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00075 | 15HA0093 | 2015-08-21 | 2015-08-10 | 2015-08-21 | 2015-08-28 | 2015-09-21 | DT&C CONSTRUCTION
12371 | NC 2015 | K10 (2015) | Region VII | Bohol | 118498 | Cogon Norte ES | LOON | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00153 | 15HA0144 | 2015-10-16 | 2015-10-05 | 2015-10-16 | 2015-10-22 | 2015-11-18 | PUREGOLD CONSTRUCTION & DEVT. CORP.
12372 | NC 2015 | SHS (2015) | Region VII | Bohol | 302838 | Cong. Pablo Malasarte NHS | BALILIHAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070115S00148 | 15HA0140 | 2015-10-12 | 2015-09-29 | 2015-10-12 | 2015-10-16 | 2015-11-03 | PUREGOLD CONSTRUCTION & DEVT. CORP.
12373 | NC 2015 | SHS (2015) | Region VII | Bohol | 302839 | Corella NHS | CORELLA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00067 | 15HA0097 | 2015-08-25 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-21 | PUREGOLD CONSTRUCTION & DEVT. CORP.
12374 | NC 2015 | K10 (2015) | Region VII | Bohol | 117975 | Danao PS | ANTEQUERA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00213 | 15HA0147 | 2015-10-19 | 2015-10-07 | 2015-10-19 | 2015-10-23 | 2015-11-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12375 | NC 2015 | SHS (2015) | Region VII | Bohol | 312304 | Dauis NHS | DAUIS | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00060 | 15HA0124 | 2015-10-02 | 2015-09-21 | 2015-10-02 | 2015-10-09 | 2015-11-26 | HNR CONSTRUCTION & SUPPLY
12376 | NC 2015 | K10 (2015) | Region VII | Bohol | 118539 | Dipatlong PS | MARIBOJOC | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00216 | 15HA0153 | 2015-10-23 | 2015-10-12 | 2015-10-23 | 2015-10-29 | 2015-12-03 | A.A. DE VERA CONSTRUCTION
12377 | NC 2015 | SHS (2015) | Region VII | Bohol | 302850 | Fatima NHS | CORTES | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2710828.124 |  |  | COMPLETED | 1 |  |  | 070115S00069 | 15HA0088 | 2015-08-17 | 2015-08-05 | 2015-08-17 | 2015-08-21 | 2015-10-05 | PUREGOLD CONSTRUCTION & DEVT. CORP.
12378 | NC 2015 | SHS (2015) | Region VII | Bohol | 302853 | Gov. Jacinto Borja National High School | LOON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00070 | 15HA0122 | 2015-10-02 | 2015-09-21 | 2015-10-02 | 2015-10-09 | 2015-11-09 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12379 | NC 2015 | K10 (2015) | Region VII | Bohol | 118540 | Guiwanon PS | MARIBOJOC | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00217 | 15HA0154 | 2015-10-23 | 2015-10-12 | 2015-10-23 | 2015-10-30 | 2015-12-18 | GCMG CONSTRUCTION
12380 | NC 2015 | SHS (2015) | Region VII | Bohol | 312320 | Haguilanan High School | CATIGBIAN | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2680828.124 |  |  | COMPLETED | 1
12381 | NC 2015 | SHS (2015) | Region VII | Bohol | 302856 | Hanopol NHS | BALILIHAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00072 | 15HA0089 | 2015-08-17 | 2015-08-05 | 2015-08-17 | 2015-08-21 | 2015-09-21 | PUREGOLD CONSTRUCTION & DEVT. CORP.
12382 | NC 2015 | SHS (2015) | Region VII | Bohol | 302871 | Loon South National HS | LOON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1
12383 | NC 2015 | SHS (2015) | Region VII | Bohol | 302872 | Lourdes NHS | PANGLAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
12384 | NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302872 | Lourdes NHS | PANGLAO | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2529549.27 |  |  | COMPLETED | 1
12385 | NC 2015 | SHS (2015) | Region VII | Bohol | 302877 | Mantacida NHS | CATIGBIAN | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2720828.124 |  |  | COMPLETED | 1 |  |  | 070115S00068 | 15HA0087 | 2015-08-17 | 2015-08-05 | 2015-08-17 | 2015-08-21 | 2015-09-21 | HNR CONSTRUCTION & SUPPLY
12386 | NC 2015 | SHS (2015) | Region VII | Bohol | 302824 | Mayor A. R. Tuazon Nat'l Sch. of Fisheries | CALAPE | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00066 | 15HA0094 | 2015-08-25 | 2015-08-14 | 2015-08-25 | 2015-09-02 | 2015-09-21 | GAIL CONSTRUCTION AND SUPPLY
12387 | NC 2015 | K10 (2015) | Region VII | Bohol | 118789 | Mocaboc PS | TUBIGON | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | Reverted | 0 |  |  | 070115S00218 | 15HA0127
12388 | NC 2015 | SHS (2015) | Region VII | Bohol | 302881 | Pagnito-an NHS | MARIBOJOC | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1
12389 | NC 2015 | SHS (2015) | Region VII | BOHOL | 312317 | Pamilacan HS | BACLAYON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00057 | 15HA0132 | 2015-10-09 | 2015-09-28 | 2015-10-09 | 2015-10-15 | 2015-11-03 | PUREGOLD CONSTRUCTION & DEVT. CORP.
12390 | NC 2015 | SHS (2015) | Region VII | Bohol | 302882 | Pangangan NHS Main | CALAPE | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6409337.6381 |  |  | Reverted | 0 |  |  | 070115S00056 | 15HA0095 | 2015-08-25 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-21 | GAIL CONSTRUCTION AND SUPPLY
12391 | NC 2015 | SHS (2015) | Region VII | Bohol | 302900 | San Roque NHS | ALBURQUERQUE | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
12392 | NC 2015 | SHS (2015) | Region VII | Bohol | 302902 | Sandingan National High School | LOON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8324965.051 |  |  | COMPLETED | 1
12393 | NC 2015 | SHS (2015) | Region VII | Bohol | 302906 | Sikatuna NHS | SIKATUNA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00054 | 15HA0091 | 2015-10-26 | 2015-10-13 | 2015-10-26
12394 | NC 2015 | SHS (2015) | Region VII | Bohol | 302908 | Tabalong NHS | DAUIS | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070115S00053 | 15HA0129 | 2015-10-26 | 2015-10-13 | 2015-10-26 |  |  | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12395 | NC 2015 | K10 (2015) | Region VII | Bohol | 118794 | Talenceras ES | TUBIGON | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00230 | 15HA0146 | 2015-10-19 | 2015-10-07 | 2015-10-19 | 2015-10-23 | 2015-11-18 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12396 | NC 2015 | K10 (2015) | Region VII | Bohol | 118563 | Tangnan ES | PANGLAO | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00161 | 15HA0143 | 2015-10-16 | 2015-10-05 | 2015-10-16 | 2015-10-22 | 2015-11-09 | PUREGOLD CONSTRUCTION & DEVT. CORP.
12397 | NC 2015 | K10 (2015) | Region VII | Bohol | 118265 | Tinago ES | DAUIS | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00171 | 15HA0092 | 2015-08-21 | 2015-08-10 | 2015-08-21 | 2015-08-28 | 2015-09-21 | JJF BUILDERS AND SUPPLY
12398 | NC 2015 | SHS (2015) | Region VII | Bohol | 312333 | Tubigon West Central HS | TUBIGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070115S00052 | 15HA0127 | 2015-10-05 | 2015-09-23 | 2015-10-05 | 2015-10-09 | 2015-11-09 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12399 | NC 2015 | SHS (2015) | Region VII | Bohol | 302822 | Tubigon West NHS | TUBIGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
12400 | NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302822 | Tubigon West NHS | TUBIGON | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
12401 | NC 2015 | K10 (2015) | Region VII | Bohol | 117980 | Tupas ES | ANTEQUERA | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00170 | 15HA0142 | 2015-10-16 | 2015-10-05 | 2015-10-16 | 2015-10-21 | 2015-11-18 | PUREGOLD CONSTRUCTION & DEVT. CORP.
12402 | NC 2015 | K10 (2015) | Region VII | Bohol | 118798 | Ubay PS | TUBIGON | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | Reverted | 0 |  |  | 070115S00220 | 15HA0129
12403 | NC 2015 | SHS (2015) | Region VII | Bohol | 302808 | Aguining National High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 070115S00050 | 15HC0126 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12404 | NC 2015 | K10 (2015) | Region VII | Bohol | 118218 | Babag ES | DAGOHOY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00164 | 15HC0083 | 2015-08-13 | 2015-08-25 | 2015-08-26 | 2015-08-30 | 2015-09-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12405 | NC 2015 | K10 (2015) | Region VII | Bohol | 118061 | Baluarte ES | BUENAVISTA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00221 | 15HC0161 | 2015-11-12
12406 | NC 2015 | K10 (2015) | Region VII | Bohol | 118393 | Banahao Elementary School | INABANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00193 | 15HC0169 | 2015-12-15
12407 | NC 2015 | K10 (2015) | Region VII | Bohol | 118367 | Baogo ES | INABANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 68012714.0187 |  |  | COMPLETED | 1 |  |  | 070115S00210 | 15HC0193 | 2015-12-01
12408 | NC 2015 | SHS (2015) | Region VII | BOHOL | 312335 | Basiao High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00049 | 15HC0069 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12409 | NC 2015 | SHS (2015) | Region VII | Bohol | 302816 | Biabas Trade High School | UBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00048 | 15HC0122 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12410 | NC 2015 | SHS (2015) | Region VII | Bohol | 312324 | Bonbonon HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
12411 | NC 2015 | K10 (2015) | Region VII | Bohol | 118064 | Bonotbonot ES | BUENAVISTA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00222 | 15HC0162 | 2015-11-12
12412 | NC 2015 | K10 (2015) | Region VII | Bohol | 118188 | Buacao PS | CLARIN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00223 | 15HC0163 | 2015-11-12
12413 | NC 2015 | K10 (2015) | Region VII | Bohol | 118643 | Bugang ES | SAN MIGUEL | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00188 | 15HC0171 | 2015-11-12
12414 | NC 2015 | SHS (2015) | Region VII | Bohol | 312334 | Bulilis High School | UBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00090 | 15HC0103 | 2015-08-31 | 2015-09-12 | 2015-09-13 | 2015-09-17 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12415 | NC 2015 | K10 (2015) | Region VII | Bohol | 118323 | Buyog ES | JETAFE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00226 | 15HC0165 | 2015-11-12
12416 | NC 2015 | SHS (2015) | Region VII | BOHOL | 500213 | Cabanugan Integrated School | SAN ISIDRO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00124 | 15HC0064 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
12417 | NC 2015 | SHS (2015) | Region VII | Bohol | 312351 | Cagting High School | UBAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00059 | 15HC0081 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12418 | NC 2015 | K10 (2015) | Region VII | Bohol | 302894 | Calituban HS | TALIBON | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00159 | 15HC0087 | 2015-08-17 | 2015-08-29 | 2015-08-30 | 2015-09-03 | 2015-09-07 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12419 | NC 2015 | SHS (2015) | Region VII | Bohol | 302825 | Camambugan NHS | UBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070115S00074 | 15HC0123 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12420 | NC 2015 | K10 (2015) | Region VII | Bohol | 118646 | Camanaga ES | SAN MIGUEL | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00160 | 15HC0089 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | RAMONA CONSTRUCTION & ENTERPRISES
12421 | NC 2015 | K10 (2015) | Region VII | Bohol | 118647 | Cambangay Norte ES | SAN MIGUEL | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00206 | 15HC0172 | 2015-11-12
12422 | NC 2015 | K10 (2015) | Region VII | Bohol | 118370 | Cambitoon ES | INABANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00228 | 15HC0167
12423 | NC 2015 | SHS (2015) | Region VII | BOHOL | 312353 | Campamanog HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00092 | 15HC0070 | 2015-09-03 | 2015-09-15 | 2015-09-16 | 2015-09-20 | 2015-09-24 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12424 | NC 2015 | SHS (2015) | Region VII | Bohol | 302827 | Campao Oriental NHS | JETAFE | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070115S00093 | 15HC0108 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12425 | NC 2015 | K10 (2015) | Region VII | Bohol | 118071 | Cangawa ES | BUENAVISTA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00172 | 15HC0082 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12426 | NC 2015 | SHS (2015) | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
12427 | NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
12428 | NC 2015 | SHS (2015) | Region VII | Bohol | 302842 | Cantubod NHS | DANAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00094 | 15HC0118 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12429 | NC 2015 | K10 (2015) | Region VII | Bohol | 118747 | Catoogan PS | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00183 | 15HC0174 | 2015-11-12
12430 | NC 2015 | K10 (2015) | Region VII | Bohol | 118397 | Cawayan ES | INABANGA | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00155 | 15HC0128 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | BNYU ENTERPRISES & CONSTRUCTION
12431 | NC 2015 | SHS (2015) | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070115S00095 | 15HC0117 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | FFJJ CONSTRUCTION
12432 | NC 2015 | K10 (2015) | Region VII | Bohol | 118649 | Corazon ES | SAN MIGUEL | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00184 | 15HC0173 | 2015-11-12
12433 | NC 2015 | SHS (2015) | Region VII | Bohol | 302840 | Dagohoy NHS | DAGOHOY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00096 | 15HC0120 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12434 | NC 2015 | SHS (2015) | Region VII | Bohol | 302841 | Danao NHS | DANAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00106 | 15HC0119 | 2015-09-04 | 2015-09-16 | 2015-09-17 | 2015-09-21 | 2015-09-25 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12435 | NC 2015 | K10 (2015) | Region VII | Bohol | 118374 | Datag ES | INABANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00227 | 15HC0168 | 2015-12-15
12436 | NC 2015 | K10 (2015) | Region VII | Bohol | 118224 | Estaca ES | DAGOHOY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00224 | 15HC0164 | 2015-11-12
12437 | NC 2015 | SHS (2015) | Region VII | Bohol | 302888 | Eugenio V. Amores MHS | SAGBAYAN (BORJA) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6409337.6381 |  |  | COMPLETED | 1
12438 | NC 2015 | SHS (2015) | Region VII | Bohol | 302843 | Francisco Dagohoy Mem. NHS | DANAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00091 | 15HC0078 | 2015-09-04 | 2015-09-16 | 2015-09-17 | 2015-09-21 | 2015-09-25 | RG FELISILDA CONSTRUCTION
12439 | NC 2015 | SHS (2015) | Region VII | BOHOL | 312325 | Gaus HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00100 | 15HC0071 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12440 | NC 2015 | K10 (2015) | Region VII | Bohol | 118376 | Hambongan ES | INABANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00207 | 15HC0192 | 2015-12-01
12441 | NC 2015 | SHS (2015) | Region VII | Bohol | 302828 | Handumon NHS | JETAFE | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1
12442 | NC 2015 | SHS (2015) | Region VII | Bohol | 302857 | Hingotanan NHS | BIEN UNIDO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1
12443 | NC 2015 | K10 (2015) | Region VII | Bohol | 118751 | Hinlayagan Ilaya ES | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00182 | 15HC0175 | 2015-11-12
12444 | NC 2015 | SHS (2015) | Region VII | Bohol | 302858 | Hinlayagan NHS | TRINIDAD | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00102 | 15HC0121 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12445 | NC 2015 | SHS (2015) | Region VII | Bohol | 302892 | Inabanga HS- Nabuad | INABANGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00103 | 15HC0096 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | MAI CONSTRUCTION & SUPPLY
12446 | NC 2015 | SHS (2015) | Region VII | Bohol | 312309 | JAPER Memorial High Shoool | SAGBAYAN (BORJA) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00104 | 15HC0104 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | SLP CONSTRUCTION
12447 | NC 2015 | K10 (2015) | Region VII | Bohol | 118824 | Katarungan ES | UBAY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00178 | 15HC0179 | 2015-11-12
12448 | NC 2015 | K10 (2015) | Region VII | Bohol | 118753 | Kinan-oan ES | TRINIDAD | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00158 | 15HC0086 | 2015-08-04 | 2015-08-16 | 2015-08-17 | 2015-08-21 | 2015-08-25 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12449 | NC 2015 | SHS (2015) | Region VII | Bohol | 312305 | Kinan-oan HS | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00076 | 15HC0076 | 2015-07-30 | 2015-08-11 | 2015-08-12 | 2015-08-16 | 2015-08-20 | B. VICENCIO CONSTRUCTION
12450 | NC 2015 | K10 (2015) | Region VII | Bohol | 118755 | La Victoria ES | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00211 | 15HC0160 | 2015-11-12
12451 | NC 2015 | K10 (2015) | Region VII | Bohol | 118756 | Loblob ES | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00181 | 15HC0176 | 2015-11-12
12452 | NC 2015 | K10 (2015) | Region VII | Bohol | 118825 | Lomangog ES | UBAY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00177 | 15HC0180 | 2015-11-12
12453 | NC 2015 | K10 (2015) | Region VII | Bohol | 118402 | Lomboy PS | INABANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00185 | 15HC0170 | 2015-11-12
12454 | NC 2015 | K10 (2015) | Region VII | Bohol | 118739 | Mahanay ES | TALIBON | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00229 | 15HC0191 | 2015-12-01
12455 | NC 2015 | K10 (2015) | Region VII | Bohol | 118653 | Mahayag ES | SAN MIGUEL | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00166 | 15HC0129 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | RAMONA CONSTRUCTION & ENTERPRISES
12456 | NC 2015 | SHS (2015) | Region VII | Bohol | 302873 | Mahayag NHS | SAN MIGUEL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
12457 | NC 2015 | K10 (2015) | Region VII | Bohol | 118757 | Manuel M. Roxas ES | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00180 | 15HC0177 | 2015-11-12
12458 | NC 2015 | SHS (2015) | Region VII | Bohol | 312313 | Mayor Catalino Casoyla MHS | TALIBON | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070115S00146 | 15HC0125 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12459 | NC 2015 | SHS (2015) | Region VII | Bohol | 312303 | Mayor Inocencio B. Mendez HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8429965.051 |  |  | COMPLETED | 1 |  |  | 070115S00046 | 15HC0116 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12460 | NC 2015 | K10 (2015) | Region VII | Bohol | 186515 | Merryland PS | BUENAVISTA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2281106.04 |  |  | COMPLETED | 1 |  |  | 070115S00212 | 15HC0184 | 2015-11-17
12461 | NC 2015 | SHS (2015) | Region VII | Bohol | 302879 | Nahawan NHS | CLARIN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 070115S00024 | 15HC0112 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12462 | NC 2015 | K10 (2015) | Region VII | Bohol | 118761 | Panaghi-usa ES | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00174 | 15HC0178 | 2015-11-12
12463 | NC 2015 | SHS (2015) | Region VII | Bohol | 312312 | Panghagban HS | BUENAVISTA | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3584886.575 |  |  | COMPLETED | 1 |  |  | 070115S00138 | 15HC0061 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-07-20 | 2015-07-24 | DINAH JANE CONSTRUCTION SUPPLY
12464 | NC 2015 | SHS (2015) | Region VII | Bohol | 312331 | Ponciana E. Leoligao HS | TALIBON | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1
12465 | NC 2015 | K10 (2015) | Region VII | Bohol | 312360 | Ponciano L. Padin National High School | BIEN UNIDO | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00168 | 15HC0127 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12466 | NC 2015 | SHS (2015) | Region VII | Bohol | 302886 | Pres. Carlos P. Garcia Technical Vocational School of Fisheries and Arts | BIEN UNIDO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 070115S00097 | 15HC0094 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12467 | NC 2015 | SHS (2015) | Region VII | Bohol | 302895 | President Carlos P. Garcia Memorial High School | TALIBON | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
12468 | NC 2015 | K10 (2015) | Region VII | Bohol | 118339 | Saguise ES | JETAFE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00219 | 15HC0166 | 2015-11-12
12469 | NC 2015 | SHS (2015) | Region VII | Bohol | 302887 | San Agustin NHS | SAGBAYAN (BORJA) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00088 | 15HC0106 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | SLP CONSTRUCTION
12470 | NC 2015 | SHS (2015) | Region VII | Bohol | 312350 | San Isidro HS | TALIBON | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
12471 | NC 2015 | SHS (2015) | Region VII | Bohol | 302890 | San Isidro NHS | SAN ISIDRO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00137 | 15HC0107 | 2015-08-31 | 2015-09-12 | 2015-09-13 | 2015-09-17 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12472 | NC 2015 | SHS (2015) | Region VII | Bohol | 302891 | San Jose NHS | INABANGA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10487131.51 |  |  | COMPLETED | 1
12473 | NC 2015 | SHS (2015) | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
12474 | NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
12475 | NC 2015 | K10 (2015) | Region VII | Bohol | 118229 | San Miguel ES | DAGOHOY | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 4447320.78 |  |  | COMPLETED | 1 |  |  | 070115S00225 | 15HC0196 | 2015-12-01
12476 | NC 2015 | SHS (2015) | Region VII | Bohol | 312321 | San Miguel Puertos HS | DAGOHOY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00084 | 15HC0079 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12477 | NC 2015 | SHS (2015) | Region VII | Bohol | 302897 | San Miguel Technical Vocational School | SAN MIGUEL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
12478 | NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302897 | San Miguel Technical Vocational School | SAN MIGUEL | 2 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
12479 | NC 2015 | SHS (2015) | Region VII | Bohol | 302899 | San Pascual National Agr'l HS | UBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00083 | 15HC0115 | 2015-09-04 | 2015-09-16 | 2015-09-17 | 2015-09-21 | 2015-09-25 | LTS BUILDERS AND CONSTRUCTION SUPPLY
12480 | NC 2015 | K10 (2015) | Region VII | Bohol | 118230 | San Vicente ES | DAGOHOY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00163 | 15HC0084 | 2015-08-04 | 2015-08-16 | 2015-08-17 | 2015-08-21 | 2015-08-25 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12481 | NC 2015 | SHS (2015) | Region VII | Bohol | 302896 | Sikatuna Nat'l Agricultural HS | TALIBON | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2820828.124 |  |  | COMPLETED | 1 |  |  | 070115S00082 | 15HC0066 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | B. VICENCIO CONSTRUCTION
12482 | NC 2015 | K10 (2015) | Region VII | Bohol | 118835 | Sinandigan ES | UBAY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00176 | 15HC0181 | 2015-11-12
12483 | NC 2015 | SHS (2015) | Region VII | Bohol | 302859 | Southern Inabanga HS | INABANGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
12484 | NC 2015 | K10 (2015) | Region VII | Bohol | 118389 | Sto. Niño PS | INABANGA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2142006.04 |  |  | COMPLETED | 1 |  |  | 070115S00205 | 15HC0195 | 2015-12-01
12485 | NC 2015 | K10 (2015) | Region VII | Bohol | 118603 | Sto. Rosario Elementary School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00191 | 15HC0194 | 2015-12-01
12486 | NC 2015 | SHS (2015) | Region VII | Bohol | 302910 | Tagum Sur NHS | TRINIDAD | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
12487 | NC 2015 | SHS (2015) | Region VII | Bohol | 302844 | Taming NHS | DANAO | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3584886.575 |  |  | COMPLETED | 1
12488 | NC 2015 | K10 (2015) | Region VII | Bohol | 118730 | Tanghaligue ES | TALIBON | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00208 | 15HC0158 | 2015-11-12
12489 | NC 2015 | SHS (2015) | Region VII | BOHOL | 500214 | Tapal Integrated School | UBAY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00078 | 15HC0065 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-07-20 | 2015-07-24 | MAI CONSTRUCTION & SUPPLY
12490 | NC 2015 | K10 (2015) | Region VII | Bohol | 118198 | Tontunan ES | CLARIN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00165 | 15HC0090 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | 2H2L CONSTRUCTION
12491 | NC 2015 | K10 (2015) | Region VII | Bohol | 118840 | Tres Reyes ES | UBAY | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 4001368.78 |  |  | COMPLETED | 1 |  |  | 070115S00175 | 15HC0183 | 2015-11-17
12492 | NC 2015 | SHS (2015) | Region VII | Bohol | 500215 | Tubog Integrated School | UBAY | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3574886.575 |  |  | COMPLETED | 1 |  |  | 070115S00077 | 15HC0063 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-07-18 | 2015-07-22 | MAI CONSTRUCTION & SUPPLY
12493 | NC 2015 | SHS (2015) | Region VII | Bohol | 302913 | Tulang NHS | JETAFE | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
12494 | NC 2015 | SHS (2015) | Region VII | Bohol | 302915 | Ubay National Science HS | UBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
12495 | NC 2015 | SHS (2015) | Region VII | Bohol | 302914 | Union NHS | UBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00016 | 15HC0114 | 2015-09-04 | 2015-09-16 | 2015-09-17 | 2015-09-21 | 2015-09-25 | MAI CONSTRUCTION & SUPPLY
12496 | NC 2015 | K10 (2015) | Region VII | Bohol | 118233 | Villa Aurora ES | DAGOHOY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00162 | 15HC0085 | 2015-08-04 | 2015-08-16 | 2015-08-17 | 2015-08-21 | 2015-08-25 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12497 | NC 2015 | K10 (2015) | Region VII | Bohol | 118731 | Zamora ES | TALIBON | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00209 | 15HC0159 | 2015-11-12
12498 | NC 2015 | SHS (2015) | Region VII | Bohol | 302814 | Zosimo A. Gulle Memorial National High Schhol | TALIBON | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070115S00015 | 15HC0110 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | BNYU ENTERPRISES & CONSTRUCTION
12499 | NC 2015 | K10 (2015) | Region VII | Bohol | 186507 | Alicia CES Annex | ALICIA | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00189 | 15HB0092 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
12500 | NC 2015 | SHS (2015) | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00135 | 15HB0071 | 2015-07-20 | 2015-07-21 | 2015-08-03 | 2015-08-12 | 2015-09-03 | ALGAMON CONSTRUCTION
12501 | NC 2015 | SHS (2015) | Region VII | Bohol | 302810 | Ambassador Pablo R. Suarez, Jr. NHS | CARMEN | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 |  |  | 070115S00014 | 15HB0064 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12502 | NC 2015 | SHS (2015) | Region VII | BOHOL | 302813 | Anda HS | ANDA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00134 | 15HB0057 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12503 | NC 2015 | SHS (2015) | Region VII | Bohol | 302912 | Anoling National High School | CANDIJAY | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3614886.575 |  |  | COMPLETED | 1 |  |  | 070115S00013 | 15HB0057 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12504 | NC 2015 | SHS (2015) | Region VII | Bohol | 302812 | Badiang NHS | ANDA | 3 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2830828.124 |  |  | COMPLETED | 1 |  |  | 070115S00133 | 15HB0057 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12505 | NC 2015 | K10 (2015) | Region VII | Bohol | 118346 | Basdio ES | GUINDULMAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 070115S00192 | 15HB0100 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
12506 | NC 2015 | SHS (2015) | Region VII | Bohol | 302815 | Batuan NHS | BATUAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
12507 | NC 2015 | SHS (2015) | Region VII | BOHOL | 312310 | Bayawahan National High School | SEVILLA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00005 | 15HB0062 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | RG FELISILDA CONSTRUCTION
12508 | NC 2015 | K10 (2015) | Region VII | Bohol | 118348 | Bayong ES | GUINDULMAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00203 | 15HB0089 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | ALGAMON CONSTRUCTION
12509 | NC 2015 | SHS (2015) | Region VII | Bohol | 302818 | Bilar NHS | BILAR | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070115S00012 | 15HB0034 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12510 | NC 2015 | K10 (2015) | Region VII | Bohol | 118515 | Bulawan ES | MABINI | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 070115S00187 | 15HB0100 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
12511 | NC 2015 | K10 (2015) | Region VII | Bohol | 118270 | Cadap-agan PS | DIMIAO | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00197 | 15HB0096 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | FIRST BUILDERS AND DEVELOPERS
12512 | NC 2015 | K10 (2015) | Region VII | Bohol | 118663 | Calinginan Norte Elementary | SEVILLA | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00201 | 15HB0095 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | FIRST BUILDERS AND DEVELOPERS
12513 | NC 2015 | SHS (2015) | Region VII | Bohol | 302826 | Camaya-an NHS | LOBOC | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
12514 | NC 2015 | SHS (2015) | Region VII | Bohol | 302826 | Camaya-an NHS | LOBOC | 3 | 1 | 4 | ADDITIONAL 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 6169337.64 |  |  | COMPLETED | 1
12515 | NC 2015 | SHS (2015) | Region VII | BOHOL | 302904 | Cambagui-Calinginan National Norte HS | SEVILLA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00010 | 15HB0062 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | RG FELISILDA CONSTRUCTION
12516 | NC 2015 | SHS (2015) | Region VII | Bohol | 312352 | Cambuyo HS | GARCIA HERNANDEZ | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1
12517 | NC 2015 | SHS (2015) | Region VII | Bohol | 302829 | Candabong National High School | ANDA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1
12518 | NC 2015 | SHS (2015) | Region VII | Bohol | 302829 | Candabong National High School | ANDA | 3 | 1 | 4 | ADDITIONAL 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 6169337.64 |  |  | COMPLETED | 1
12519 | NC 2015 | K10 (2015) | Region VII | Bohol | 118114 | Candijay Central ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 070115S00196 | 15HB0099 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
12520 | NC 2015 | SHS (2015) | Region VII | Bohol | 302865 | Candijay NHS | CANDIJAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8474965.051 |  |  | COMPLETED | 1
12521 | NC 2015 | SHS (2015) | Region VII | Bohol | 302832 | Canhayupon NHS | DIMIAO | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3574886.575 |  |  | COMPLETED | 1 |  |  | 070115S00004 | 15HB0060 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12522 | NC 2015 | SHS (2015) | Region VII | Bohol | 302834 | Catungawan NHS | GUINDULMAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1
12523 | NC 2015 | SHS (2015) | Region VII | BOHOL | 312316 | Cayacay HS | ALICIA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00131 | 15HB0059 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12524 | NC 2015 | K10 (2015) | Region VII | Bohol | 118116 | Cogtong ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 070115S00195 | 15HB0099 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
12525 | NC 2015 | SHS (2015) | Region VII | Bohol | 302866 | Cogtong NHS | CANDIJAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8474965.051 |  |  | COMPLETED | 1 |  |  | 070115S00007 | 15HB0037 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12526 | NC 2015 | SHS (2015) | Region VII | Bohol | 302837 | Concepcion NHS | MABINI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00140 | 15HB0059 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12527 | NC 2015 | K10 (2015) | Region VII | Bohol | 118681 | Danicop ES | SIERRA BULLONES | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00199 | 15HB0091 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | GELA CONSTRUCTION
12528 | NC 2015 | SHS (2015) | Region VII | Bohol | 302845 | Dimiao NHS | DIMIAO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 070115S00011 | 15HB0038 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12529 | NC 2015 | SHS (2015) | Region VII | Bohol | 302847 | Duero NHS | DUERO | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3514886.575 |  |  | COMPLETED | 1 |  |  | 070115S00032 | 15HB0058 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | LTS BUILDERS AND CONSTRUCTION SUPPLY
12530 | NC 2015 | SHS (2015) | Region VII | Bohol | 302848 | Dusita HS | SIERRA BULLONES | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1
12531 | NC 2015 | K10 (2015) | Region VII | Bohol | 118666 | Ewon Elementary School | SEVILLA | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00200 | 15HB0093 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | FIRST BUILDERS AND DEVELOPERS
12532 | NC 2015 | SHS (2015) | Region VII | Bohol | 302849 | Faraon NHS | JAGNA | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00042 | 15HB0060 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12533 | NC 2015 | SHS (2015) | Region VII | Bohol | 302861 | Francisco L. Adlaon HS | CARMEN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 070115S00041 | 15HB0040 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12534 | NC 2015 | SHS (2015) | Region VII | Bohol | 302852 | Garcia-Hernandez HS | GARCIA HERNANDEZ | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 070115S00040 | 15HB0041 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12535 | NC 2015 | SHS (2015) | Region VII | Bohol | 302854 | Guinacot NHS | GUINDULMAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8354965.051 |  |  | COMPLETED | 1
12536 | NC 2015 | SHS (2015) | Region VII | Bohol | 302855 | Guinsularan High School | DUERO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
12537 | NC 2015 | SHS (2015) | Region VII | Bohol | 302867 | Hinawanan NHS | LOAY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1
12538 | NC 2015 | SHS (2015) | Region VII | Bohol | 312358 | Jagna HS | JAGNA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1
12539 | NC 2015 | SHS (2015) | Region VII | Bohol | 312359 | Katipunan HS | ALICIA | 3 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2790828.124 |  |  | COMPLETED | 1
12540 | NC 2015 | SHS (2015) | Region VII | Bohol | 302860 | Katipunan NHS | CARMEN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070115S00036 | 15HB0044 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12541 | NC 2015 | SHS (2015) | Region VII | Bohol | 312318 | Katipunan NHS Annex | CARMEN | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 |  |  | 070115S00035 | 15HB0063 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12542 | NC 2015 | SHS (2015) | Region VII | Bohol | 302863 | La Hacienda NHS | ALICIA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
12543 | NC 2015 | K10 (2015) | Region VII | Bohol | 118577 | La Suerte ES | PILAR | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00156 | 15HB0079 | 2015-08-10 | 2015-08-12 | 2015-08-25 | 2015-09-03 | 2015-09-25 | ALGAMON CONSTRUCTION
12544 | NC 2015 | SHS (2015) | Region VII | Bohol | 302864 | La Union NHS | CANDIJAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00034 | 15HB0046 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12545 | NC 2015 | K10 (2015) | Region VII | Bohol | 118447 | Las Salinas ES | LOAY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00202 | 15HB0094 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
12546 | NC 2015 | SHS (2015) | Region VII | Bohol | 302868 | Lila NHS | LILA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
12547 | NC 2015 | SHS (2015) | Region VII | Bohol | 302869 | Loboc NHS | LOBOC | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3534886.575 |  |  | COMPLETED | 1 |  |  | 070115S00018 | 15HB0061 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | AL CHRIS CONSTRUCTION
12548 | NC 2015 | SHS (2015) | Region VII | Bohol | 302870 | Lonoy Heroes MHS | JAGNA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00031 | 15HB0048 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12549 | NC 2015 | K10 (2015) | Region VII | Bohol | 118118 | Luan ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
12550 | NC 2015 | K10 (2015) | Region VII | Bohol | 118119 | Lungsodaan ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 070115S00194 | 15HB0099 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
12551 | NC 2015 | K10 (2015) | Region VII | Bohol | 118519 | Lungsodaan ES | MABINI | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00157 | 15HB0077 | 2015-07-20 | 2015-07-21 | 2015-08-03 | 2015-08-12 | 2015-09-03 | FIRST BUILDERS AND DEVELOPERS
12552 | NC 2015 | K10 (2015) | Region VII | Bohol | 118021 | Lungsod-Daan ES | BATUAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00173 | 15HB0090 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | R.M. MONDARES CONSTRUCTION
12553 | NC 2015 | K10 (2015) | Region VII | Bohol | 117962 | Mahayahay PS | ANDA | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00179 | 15HB0088 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12554 | NC 2015 | SHS (2015) | Region VII | Bohol | 312311 | Mayor Pablo O. Lim MHS | VALENCIA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8424965.051 |  |  | COMPLETED | 1 |  |  | 070115S00145 | 15HB0082 | 2015-09-09 | 2015-09-11 | 2015-09-23 | 2015-09-30 | 2015-10-23 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
12555 | NC 2015 | SHS (2015) | Region VII | Bohol | 302878 | Mayuga NHS | GUINDULMAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1
12556 | NC 2015 | K10 (2015) | Region VII | Bohol | 117946 | Napo ES | ALICIA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 070115S00190 | 15HB0100 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
12557 | NC 2015 | SHS (2015) | Region VII | BOHOL | 302880 | Oy NHS | LOBOC | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00029 | 15HB0062 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | RG FELISILDA CONSTRUCTION
12558 | NC 2015 | K10 (2015) | Region VII | Bohol | 118122 | Panadtaran ES | CANDIJAY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00186 | 15HB0097 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
12559 | NC 2015 | SHS (2015) | Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
12560 | NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
12561 | NC 2015 | SHS (2015) | Region VII | Bohol | 302885 | Policronio S. Dano, Sr. HS | CARMEN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 070115S00038 | 15HB0051 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12562 | NC 2015 | SHS (2015) | Region VII | Bohol | 312339 | Ponciano F. Ramasola Sr. High School | CARMEN | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3564886.575 |  |  | COMPLETED | 1
12563 | NC 2015 | SHS (2015) | Region VII | BOHOL | 312314 | Quezon HS - Batuan NHS Annex | BATUAN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00127 | 15HB0062 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | RG FELISILDA CONSTRUCTION
12564 | NC 2015 | SHS (2015) | Region VII | BOHOL | 312315 | Rizal High Sschool | BATUAN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00126 | 15HB0063 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12565 | NC 2015 | SHS (2015) | Region VII | Bohol | 302889 | San Isidro Tech-Voc HS | PILAR | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1
12566 | NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302901 | San Roque National High School | MABINI | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
12567 | NC 2015 | SHS (2015) | Region VII | Bohol | 302901 | San Roque NHS | MABINI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1
12568 | NC 2015 | SHS (2015) | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8384965.051 |  |  | COMPLETED | 1
12569 | NC 2015 | K10 (2015) | Region VII | Bohol | 118694 | Sta. Cruz Elementary School | SIERRA BULLONES | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00198 | 15HB0098 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | GELA CONSTRUCTION
12570 | NC 2015 | SHS (2015) | Region VII | Bohol | 302909 | Tabuan NHS | GARCIA HERNANDEZ | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
12571 | NC 2015 | SHS (2015) | Region VII | Bohol | 302911 | Tambongan NHS | CANDIJAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 070115S00023 | 15HB0055 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12572 | NC 2015 | SHS (2015) | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1
12573 | NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA | 3 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7198647.81 |  |  | COMPLETED | 1
12574 | NC 2015 | K10 (2015) | Region VII | Carcar City | 119171 | Bolinawan ES | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00504 | 15-HE-0130 | 2015-09-21 | 2015-09-22 | 2015-10-05 | 2015-10-13 | 2015-10-19 | RCDG CONSTRUCTION CORPORATION
12575 | NC 2015 | K10 (2015) | Region VII | Carcar City | 119156 | Can-asujan ES | CITY OF CARCAR | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00402 | 15-HE-0090 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | LISA CONSTRUCTION
12576 | NC 2015 | SHS (2015) | Region VII | Carcar City | 302970 | Can-asujan NHS | CITY OF CARCAR | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
12577 | NC 2015 | SHS (2015) | Region VII | Carcar City | 302972 | Carcar Central National High School (Pob. Night) | CITY OF CARCAR | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 8 | 15371327.92 |  |  | COMPLETED | 1
12578 | NC 2015 | TECHVOC (2015) | Region VII | Carcar City | 302972 | Carcar Central National High School (Pob. Night) | CITY OF CARCAR | 1 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
12579 | NC 2015 | K10 (2015) | Region VII | Carcar City | 119160 | Lunas Elementary School | CITY OF CARCAR | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00403 | 15-HE-0091 | 2015-07-15 | 2015-07-16 | 2015-09-15 | 2015-09-21 | 2015-09-28 | A.T. DUMLAO CONSTRUCTION, INC. FORMERLYANDONI T. D
12580 | NC 2015 | SHS (2015) | Region VII | Carcar City | 303016 | Maximino Noel Memorial National High School | CITY OF CARCAR | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
12581 | NC 2015 | K10 (2015) | Region VII | Carcar City | 256001 | Moag ES | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00491 | 15-HE-0124 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12582 | NC 2015 | SHS (2015) | Region VII | CARCAR CITY | 356059 | Ocana National High School (Kalangyawon Extension) | CITY OF CARCAR | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
12583 | NC 2015 | SHS (2015) | Region VII | Carcar City | 303066 | OCAÑA NHS | CITY OF CARCAR | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
12584 | NC 2015 | K10 (2015) | Region VII | Carcar City | 324903 | Pit-os National High School | CITY OF CARCAR | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00405 | 15-HE-0093 | 2015-07-15 | 2015-07-16 | 2015-09-15 | 2015-09-21 | 2015-09-28 | A.T. DUMLAO CONSTRUCTION, INC. FORMERLYANDONI T. D
12585 | NC 2015 | SHS (2015) | Region VII | Carcar City | 303082 | ROBERTO E. SATO MEMORIAL NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00150 | 15-HE-0063 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-07-22 | QUIRANTE CONSTRUCTION
12586 | NC 2015 | K10 (2015) | Region VII | Carcar City | 119163 | Sa-ay Elementary School | CITY OF CARCAR | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00404 | 15-HE-0092 | 2015-07-15 | 2015-07-16 | 2015-09-15 | 2015-09-21 | 2015-09-28 | QUIRANTE CONSTRUCTION
12587 | NC 2015 | SHS (2015) | Region VII | Carcar City | 343971 | SHS in Carcar City | Carcar City | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 32102890 |  |  | COMPLETED | 1
12588 | NC 2015 | K10 (2015) | Region VII | Carcar City | 324905 | TAL-UT NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00387 | 15-HE-0094 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | MAP ALVIOLA CONSTRUCTION
12589 | NC 2015 | K10 (2015) | Region VII | Carcar City | 119167 | Tawog Elementary School | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | REVERTED | 0 |  |  | 070215S00505
12590 | NC 2015 | K10 (2015) | Region VII | Carcar City | 119168 | Tuyom ES | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00503 | 15-HE-0122 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | DINAH JANE CONSTRUCTION SUPPLY
12591 | NC 2015 | K10 (2015) | Region VII | Carcar City | 119169 | Valencia Elementary School | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00507 | 15-HE-0123 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | POWER MOVE BUILDERS & CONSTRUCTION SUPPLY
12592 | NC 2015 | SHS (2015) | Region VII | Carcar City | 303126 | Valencia VOCATIONAL NHS | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1
12593 | NC 2015 | SHS (2015) | Region VII | Cebu | 312427 | Balungag NHS | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2018606.04 |  |  | COMPLETED | 1
12594 | NC 2015 | K10 (2015) | Region VII | Cebu | 119619 | Basak ES | SAN FERNANDO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6279337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00519 | 15-HE-0120 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | PEDXING BUILDERS
12595 | NC 2015 | SHS (2015) | Region VII | Cebu | 302969 | Camp 7 NHS | MINGLANILLA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8409965.051 |  |  | COMPLETED | 1
12596 | NC 2015 | K10 (2015) | Region VII | Cebu | 119709 | Can-aga ES | SIBONGA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00401 | 15-HE-0095 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | MAP ALVIOLA CONSTRUCTION
12597 | NC 2015 | K10 (2015) | Region VII | Cebu | 119484 | Cuanos ES | MINGLANILLA | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 070215S00407 | 15-HE-0086 | 2015-12-14 | 2015-12-15 | 2015-12-28
12598 | NC 2015 | SHS (2015) | Region VII | Cebu | 303015 | Greenhills NHS | SAN FERNANDO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00281 | 15-HE-0055 | 2015-06-10 | 2015-06-11 | 2015-08-04 | 2015-08-12 | 2015-08-18 | BT CONSTRUCTION AND GENERAL SERVICES
12599 | NC 2015 | K10 (2015) | Region VII | Cebu | 119712 | Guimbangcoan PS | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00508 | 15-HE-0125 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | MAP ALVIOLA CONSTRUCTION
12600 | NC 2015 | K10 (2015) | Region VII | Cebu | 119475 | Guindarohan ES | MINGLANILLA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6299337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00495 | 15-HE-0115 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | MAP ALVIOLA CONSTRUCTION
12601 | NC 2015 | SHS (2015) | Region VII | Cebu | 303017 | Guindaruhan National High School | MINGLANILLA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10507131.51 |  |  | COMPLETED | 1 |  |  | 070215S00144 | 15-HE-0043 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-07-22 | PEDXING BUILDERS
12602 | NC 2015 | SHS (2015) | Region VII | Cebu | 303022 | Julian Enad MNHS | SIBONGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1978606.04 |  |  | COMPLETED | 1
12603 | NC 2015 | SHS (2015) | Region VII | Cebu | 303022 | Julian Enad MNHS | SIBONGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
12604 | NC 2015 | SHS (2015) | Region VII | Cebu | 312467 | Lantawan Integrated School | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00289 | 15-HE-0058 | 2015-06-10 | 2015-06-11 | 2015-08-04 | 2015-08-12 | 2015-08-18 | MAP ALVIOLA CONSTRUCTION
12605 | NC 2015 | SHS (2015) | Region VII | Cebu | 303042 | Lipata NHS | MINGLANILLA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 070215S00154 | 15-HE-0044 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | QUIRANTE CONSTRUCTION
12606 | NC 2015 | SHS (2015) | Region VII | Cebu | 303049 | Magsico NHS | SAN FERNANDO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070215S00279 | 15-HE-0056 | 2015-06-10 | 2015-06-11 | 2015-09-07 | 2015-09-14 | 2015-09-18 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12607 | NC 2015 | SHS (2015) | Region VII | Cebu | 312457 | Manatad NHS | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1
12608 | NC 2015 | SHS (2015) | Region VII | Cebu | 303051 | Mangyan NHS | SIBONGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2063606.04 |  |  | COMPLETED | 1 |  |  | 070215S00347 | 15-HE-0082 | 2015-07-15 | 2015-07-16 | 2015-10-05 | 2015-10-09 | 2015-10-14 | QUIRANTE CONSTRUCTION
12609 | NC 2015 | SHS (2015) | Region VII | Cebu | 303079 | PITALO NHS | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
12610 | NC 2015 | SHS (2015) | Region VII | Cebu | 303079 | PITALO NHS | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
12611 | NC 2015 | K10 (2015) | Region VII | Cebu | 119720 | Sabang ES | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00502 | 15-HE-0126 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | E.G. & I. CONSTRUCTION CORPORATION
12612 | NC 2015 | SHS (2015) | Region VII | Cebu | 312424 | San Fernando NHS | SAN FERNANDO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10617132 |  |  | REVERTED | 0 |  |  | 070215S00446 | 15-HE-0113 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | E.G. & I. CONSTRUCTION CORPORATION
12613 | NC 2015 | SHS (2015) | Region VII | Cebu | 303093 | Sangat NHS | SAN FERNANDO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10447131.51 |  |  | COMPLETED | 1 |  |  | 070215S00278 | 15-HE-0057 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-08-13 | PEDXING BUILDERS
12614 | NC 2015 | SHS (2015) | Region VII | Cebu | 303101 | Sibonga National High School | SIBONGA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10447131.51 |  |  | COMPLETED | 1 |  |  | 070215S00157 | 15-HE-0066 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-07-22 | GENETIAN BUILDERS
12615 | NC 2015 | SHS (2015) | Region VII | Cebu | 303067 | Teodoro dela Vega MNHS | SIBONGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 070215S00158 | 15-HE-0067 | 2015-06-10 | 2015-06-11 | 2015-10-05 | 2015-10-09 | 2015-10-14 | QUIRANTE CONSTRUCTION
12616 | NC 2015 | K10 (2015) | Region VII | Cebu | 119634 | Tinubdan ES | SAN FERNANDO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6299337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00518 | 15-HE-0129 | 2015-09-21 | 2015-09-22 | 2015-10-05 | 2015-10-13 | 2015-10-19 | MRRM TRADING & CONSTRUCTION
12617 | NC 2015 | K10 (2015) | Region VII | Cebu | 119635 | Tonggo ES | SAN FERNANDO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6209337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00517 | 15-HE-0121 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | PEDXING BUILDERS
12618 | NC 2015 | SHS (2015) | Region VII | Cebu | 303116 | Tubod National High School | MINGLANILLA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10542131.51 |  |  | COMPLETED | 1 |  |  | 070215S00159 | 15-HE-0045 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-07-22 | PEDXING BUILDERS
12619 | NC 2015 | SHS (2015) | Region VII | Cebu | 303117 | Tubod NHS (San Fernando) | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 070215S00342 | 15-HE-0079 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | MAP ALVIOLA CONSTRUCTION
12620 | NC 2015 | K10 (2015) | Region VII | Cebu | 303118 | Tulay MHS | MINGLANILLA | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 070215S00399 | 15-HE-0087 | 2015-07-15 | 2015-07-16 | 2015-10-22 | 2015-10-28 | 2015-11-03 | QUIRANTE CONSTRUCTION
12621 | NC 2015 | SHS (2015) | Region VII | Cebu | 312450 | Tungkil NHS | MINGLANILLA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0
12622 | NC 2015 | SHS (2015) | Region VII | Cebu | 303119 | Tungkop NHS | MINGLANILLA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10477131.51 |  |  | COMPLETED | 1 |  |  | 070215S00160 | 15-HE-0046 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-07-22 | FIRST BUILDERS AND DEVELOPERS
12623 | NC 2015 | SHS (2015) | Region VII | Cebu | 312419 | VITO NATIONAL HIGH SCHOOL | MINGLANILLA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10497131.51 |  |  | COMPLETED | 1 |  |  | 070215S00135 | 15-HE-0047 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | WORLDWIDE BUILDERS
12624 | NC 2015 | SHS (2015) | Region VII | Cebu | 302922 | Alcantara NHS | ALCANTARA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00288 | 15HG0082 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
12625 | NC 2015 | SHS (2015) | Region VII | Cebu | 302917 | Alcoy NHS | ALCOY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 070215S00151 | 15HG0091 | 2015-06-13 | 2015-06-11 | 2015-06-26 | 2015-08-14 | 2015-08-17 | E.G. & I. CONSTRUCTION CORPORATION
12626 | NC 2015 | K10 (2015) | Region VII | Cebu | 119526 | Alo ES | OSLOB | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6244337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00512 | 15HG0130 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | RUDPA CONSTRUCTION
12627 | NC 2015 | SHS (2015) | Region VII | Cebu | 302985 | Argao National High School | ARGAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070215S00128 | 15HG0072 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-07-20 | 2015-07-22 | DINAH JANE CONSTRUCTION SUPPLY
12628 | NC 2015 | K10 (2015) | Region VII | Cebu | 119437 | Armena ES | MALABUYOC | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6219337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00511 | 15HG0129 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-09 | 2015-11-10 | DINAH JANE CONSTRUCTION SUPPLY
12629 | NC 2015 | SHS (2015) | Region VII | Cebu | 302921 | Badian NHS | BADIAN | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10977342.5917 |  |  | COMPLETED | 1
12630 | NC 2015 | TECHVOC (2015) | Region VII | Cebu | 302921 | Badian NHS | BADIAN | 2 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7228647.81 |  |  | COMPLETED | 1
12631 | NC 2015 | K10 (2015) | Region VII | Cebu | 119491 | Balabagon ES | MOALBOAL | 2 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 070215S00301 | 15HG0113 | 2015-06-25 | 2015-06-25 | 2015-07-08 | 2015-08-14 | 2015-08-17 | DINAH JANE CONSTRUCTION SUPPLY
12632 | NC 2015 | K10 (2015) | Region VII | Cebu | 119313 | Banhigan ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6239337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00493 | 15HG0124 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-09 | 2015-11-10 | DINAH JANE CONSTRUCTION SUPPLY
12633 | NC 2015 | SHS (2015) | Region VII | Cebu | 302940 | Bitoon NVHS | DUMANJUG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00130 | 15HG0086 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-26 | 2015-08-27 | RUDPA CONSTRUCTION
12634 | NC 2015 | SHS (2015) | Region VII | Cebu | 302942 | Boljoon NHS | BOLJOON | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10457131.51 |  |  | COMPLETED | 1 |  |  | 070215S00131 | 15HG0092 | 2015-06-13 | 2015-06-11 | 2015-06-26 | 2015-08-14 | 2015-08-17 | QUIRANTE CONSTRUCTION
12635 | NC 2015 | SHS (2015) | Region VII | Cebu | 302951 | Bulak NHS | DUMANJUG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070215S00132 | 15HG0084 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
12636 | NC 2015 | SHS (2015) | Region VII | Cebu | 302953 | Bulasa NHS | ARGAO | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10507131.51 |  |  | COMPLETED | 1 |  |  | 070215S00143 | 15HG0093 | 2015-06-13 | 2015-06-11 | 2015-06-26 | 2015-08-14 | 2015-08-17 | DINAH JANE CONSTRUCTION SUPPLY
12637 | NC 2015 | K10 (2015) | Region VII | Cebu | 119372 | Bullogan ES | DUMANJUG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00299 | 15HG0111 | 2015-06-25 | 2015-06-25 | 2015-07-08 | 2015-08-26 | 2015-08-27 | DT&C CONSTRUCTION
12638 | NC 2015 | SHS (2015) | Region VII | Cebu | 302926 | Busay NHS | MOALBOAL | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00134 | 15HG0071 | 2015-06-10 | 2015-06-11 | 2015-06-24 | 2015-07-20 | 2015-07-22 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12639 | NC 2015 | K10 (2015) | Region VII | Cebu | 119293 | Caleriohan ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00494 | 15HG0123 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | RAJLAURENTE CONSTRUCTION & DEVELOPMENT PHIL.
12640 | NC 2015 | SHS (2015) | Region VII | Cebu | 312411 | Caleriohan National HIgh School | DALAGUETE | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1998606.04 |  |  | COMPLETED | 1
12641 | NC 2015 | SHS (2015) | Region VII | Cebu | 312411 | Caleriohan National HIgh School | DALAGUETE | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
12642 | NC 2015 | SHS (2015) | Region VII | Cebu | 302998 | Caliongan NHS | DALAGUETE | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2922592.44 |  |  | COMPLETED | 1
12643 | NC 2015 | SHS (2015) | Region VII | Cebu | 302998 | Caliongan NHS | DALAGUETE | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
12644 | NC 2015 | K10 (2015) | Region VII | Cebu | 187027 | Cambigong ES | SAMBOAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6239337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00501 | 15HG0133 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-09 | 2015-11-10 | DINAH JANE CONSTRUCTION SUPPLY
12645 | NC 2015 | K10 (2015) | Region VII | Cebu | 119529 | Canangcaan ES | OSLOB | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00513 | 15HG0131 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-09 | 2015-11-10 | DT&C CONSTRUCTION
12646 | NC 2015 | SHS (2015) | Region VII | Cebu | 312426 | Cañang-Marcelo Luna NHS | OSLOB | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2700828.124 |  |  | COMPLETED | 1 |  |  | 070215S00126 | 15HG0058 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | SERCHER DEVELOPMENT CORPORATION
12647 | NC 2015 | K10 (2015) | Region VII | Cebu | 119530 | Cansaloay Integrated School | OSLOB | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00524 | 15HG0132 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | RUDPA CONSTRUCTION
12648 | NC 2015 | SHS (2015) | Region VII | Cebu | 312469 | Cansaloay Integrated School | OSLOB | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00023 | 15HG0052 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | SERCHER DEVELOPMENT CORPORATION
12649 | NC 2015 | SHS (2015) | Region VII | Cebu | 303125 | Cansuje National High School - Usmad Ext. | ARGAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00136 | 15HG0063 | 2015-06-10 | 2015-06-11 | 2015-06-24 | 2015-07-20 | 2015-07-22 | BLIMEX CONSTRUCTION & SUPPLY
12650 | NC 2015 | SHS (2015) | Region VII | Cebu | 302977 | Casay NHS | DALAGUETE | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8299965.051 |  |  | COMPLETED | 1 |  |  | 070215S00137 | 15HG0075 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-07-20 | 2015-07-22 | DINAH JANE CONSTRUCTION SUPPLY
12651 | NC 2015 | K10 (2015) | Region VII | Cebu | 119295 | Catambisan ES | DALAGUETE | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00296 | 15HG0110 | 2015-06-25 | 2015-06-25 | 2015-07-08 | 2015-07-20 | 2015-07-22 | DT&C CONSTRUCTION
12652 | NC 2015 | K10 (2015) | Region VII | Cebu | 119296 | Catolohan ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6339337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00516 | 15HG0125 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | RAJLAURENTE CONSTRUCTION & DEVELOPMENT PHIL.
12653 | NC 2015 | SHS (2015) | Region VII | Cebu | 302981 | Cawayan NHS | DALAGUETE | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10537131.51 |  |  | COMPLETED | 1 |  |  | 070215S00138 | 15HG0090 | 2015-06-13 | 2015-06-11 | 2015-06-30 | 2015-08-14 | 2015-08-17 | SERCHER DEVELOPMENT CORPORATION
12654 | NC 2015 | K10 (2015) | Region VII | Cebu | 119440 | CerdeÑa ES | MALABUYOC | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00310 | 15HG0112 | 2015-06-25 | 2015-06-25 | 2015-07-08 | 2015-08-26 | 2015-08-27 | DT&C CONSTRUCTION
12655 | NC 2015 | SHS (2015) | Region VII | Cebu | 302982 | Cerdeña NHS | MALABUYOC | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2760828.124 |  |  | COMPLETED | 1
12656 | NC 2015 | SHS (2015) | Region VII | Cebu | 302983 | Cogon NHS | DUMANJUG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00140 | 15HG0085 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-07-20 | 2015-07-22 | DINAH JANE CONSTRUCTION SUPPLY
12657 | NC 2015 | SHS (2015) | Region VII | Cebu | 302984 | Colawin NHS | ARGAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00141 | 15HG0074 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-07-20 | 2015-07-22 | BLIMEX CONSTRUCTION & SUPPLY
12658 | NC 2015 | SHS (2015) | Region VII | Cebu | 302997 | Dalaguete NHS | DALAGUETE | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
12659 | NC 2015 | TECHVOC (2015) | Region VII | Cebu | 302997 | Dalaguete NHS | DALAGUETE | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
12660 | NC 2015 | K10 (2015) | Region VII | Cebu | 119319 | Dumalan ES | DALAGUETE | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 070215S00297 | 15HG0100 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-08-14 | 2015-08-17 | DINAH JANE CONSTRUCTION SUPPLY
12661 | NC 2015 | SHS (2015) | Region VII | Cebu | 302941 | Dumanjug NHS | DUMANJUG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00074 | 15HG0087 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | DINAH JANE CONSTRUCTION SUPPLY
12662 | NC 2015 | SHS (2015) | Region VII | Cebu | 302943 | El Pardo NHS | BOLJOON | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  | 070215S00027 | 15HG0059 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | DT&C CONSTRUCTION
12663 | NC 2015 | K10 (2015) | Region VII | Cebu | 118875 | Guiwang ES | ALCOY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00499 | 15HG0122 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | DT&C CONSTRUCTION
12664 | NC 2015 | SHS (2015) | Region VII | Cebu | 303018 | Guiwanon NHS | GINATILAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00098 | 15HG0079 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
12665 | NC 2015 | SHS (2015) | Region VII | Cebu | 312403 | Hipolito Boquecosa MNHS | DUMANJUG | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2720828.124 |  |  | COMPLETED | 1 |  |  | 070215S00039 | 15HG0061 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
12666 | NC 2015 | SHS (2015) | Region VII | Cebu | 312461 | Inghoy NHS | ALEGRIA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00024 | 15HG0056 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
12667 | NC 2015 | K10 (2015) | Region VII | Cebu | 119380 | Lawaan ES | DUMANJUG | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6219337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00514 | 15HG0127 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-09 | 2015-11-10 | DT&C CONSTRUCTION
12668 | NC 2015 | K10 (2015) | Region VII | Cebu | 119698 | Liloan ES | SANTANDER | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00303 | 15HG0102 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-08-14 | 2015-08-17 | WORLDWIDE BUILDERS
12669 | NC 2015 | SHS (2015) | Region VII | Cebu | 302944 | Lunop NHS | BOLJOON | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2058606.04 |  |  | COMPLETED | 1
12670 | NC 2015 | SHS (2015) | Region VII | Cebu | 303096 | Madridejos NHS (Alegria) | ALEGRIA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070215S00040 | 15HG0080 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
12671 | NC 2015 | SHS (2015) | Region VII | Cebu | 312462 | Mahanlud NHS | MALABUYOC | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00025 | 15HG055 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-08-26 | 2015-08-27 | DT&C CONSTRUCTION
12672 | NC 2015 | SHS (2015) | Region VII | Cebu | 302986 | Mandilikit NHS | ARGAO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00026 | 15HG0057 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | BLIMEX CONSTRUCTION & SUPPLY
12673 | NC 2015 | SHS (2015) | Region VII | Cebu | 302999 | Manlapay National High School | DALAGUETE | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2862592.44 |  |  | COMPLETED | 1
12674 | NC 2015 | SHS (2015) | Region VII | Cebu | 302999 | Manlapay National High School | DALAGUETE | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
12675 | NC 2015 | SHS (2015) | Region VII | Cebu | 303000 | Mantalongon NHS | DALAGUETE | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
12676 | NC 2015 | K10 (2015) | Region VII | Cebu | 119391 | Masa ES | DUMANJUG | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6249337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00510 | 15HG0128 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | GELA CONSTRUCTION
12677 | NC 2015 | SHS (2015) | Region VII | Cebu | 302927 | Moalboal NHS | MOALBOAL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 070215S00042 | 15HG0088 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-26 | 2015-08-27 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12678 | NC 2015 | SHS (2015) | Region VII | Cebu | 303057 | Monta¤eza NHS | MALABUYOC | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070215S00043 | 15HG0078 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-26 | 2015-08-27 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12679 | NC 2015 | SHS (2015) | Region VII | Cebu | 312460 | Montpeller NHS | ALEGRIA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00054 | 15HG0069 | 2015-06-10 | 2015-06-11 | 2015-06-24 | 2015-07-20 | 2015-07-22 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
12680 | NC 2015 | SHS (2015) | Region VII | Cebu | 302918 | Nug-as NHS | ALCOY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 070215S00309 | 15HG0097 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-20 | 2015-07-22 | QUIRANTE CONSTRUCTION
12681 | NC 2015 | SHS (2015) | Region VII | Cebu | 303099 | Oslob NHS | OSLOB | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00045 | 15HG0094 | 2015-06-13 | 2015-06-11 | 2015-06-26 | 2015-08-26 | 2015-08-27 | BLIMEX CONSTRUCTION & SUPPLY
12682 | NC 2015 | SHS (2015) | Region VII | Cebu | 312459 | Palanas Integrated School | GINATILAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
12683 | NC 2015 | K10 (2015) | Region VII | Cebu | 119328 | Panas ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6219337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00515 | 15HG0126 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | RAJLAURENTE CONSTRUCTION & DEVELOPMENT PHIL.
12684 | NC 2015 | SHS (2015) | Region VII | Cebu | 312466 | Pasol-Pugalo Integrated School | ALCOY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00028 | 15HG0053 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | DT&C CONSTRUCTION
12685 | NC 2015 | SHS (2015) | Region VII | Cebu | 312425 | Pedro B. Uy Calderon Memorial National High School | SAMBOAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00037 | 15HG0067 | 2015-06-10 | 2015-06-11 | 2015-06-24 | 2015-07-20 | 2015-07-22 | RUDPA CONSTRUCTION
12686 | NC 2015 | SHS (2015) | Region VII | Cebu | 312413 | Pungtod NHS | OSLOB | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00047 | 15HG0065 | 2015-06-10 | 2015-06-11 | 2015-06-24 | 2015-07-20 | 2015-07-22 | RUDPA CONSTRUCTION
12687 | NC 2015 | SHS (2015) | Region VII | Cebu | 303034 | Ronda NHS- Langin NHS Ext. | RONDA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00048 | 15HG0083 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
12688 | NC 2015 | SHS (2015) | Region VII | Cebu | 303084 | Salamanca NHS | GINATILAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1
12689 | NC 2015 | K10 (2015) | Region VII | Cebu | 119330 | Salug ES | DALAGUETE | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00298 | 15HG0101 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-08-26 | 2015-08-27 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
12690 | NC 2015 | SHS (2015) | Region VII | Cebu | 303090 | Samboan National High School | SAMBOAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00050 | 15HG0076 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-26 | 2015-08-27 | RUDPA CONSTRUCTION
12691 | NC 2015 | SHS (2015) | Region VII | Cebu | 303089 | San Sebastian NHS | SAMBOAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 070215S00051 | 15HG0077 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-26 | 2015-08-27 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12692 | NC 2015 | SHS (2015) | Region VII | Cebu | 303095 | Santa Filomena NHS | ALEGRIA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070215S00052 | 15HG0081 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
12693 | NC 2015 | K10 (2015) | Region VII | Cebu | 303098 | Santander NHS | SANTANDER | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00304 | 15HG0115 | 2015-06-25 | 2015-06-25 | 2015-07-08 | 2015-08-26 | 2015-08-27 | DT&C CONSTRUCTION
12694 | NC 2015 | SHS (2015) | Region VII | Cebu | 303058 | Sorsogon NHS | MALABUYOC | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00302 | 15HG0098 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-22 | 2015-07-23 | QUIRANTE CONSTRUCTION
12695 | NC 2015 | SHS (2015) | Region VII | Cebu | 303112 | Talaga NHS | ARGAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00029 | 15HG0073 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-07-20 | 2015-07-22 | DINAH JANE CONSTRUCTION SUPPLY
12696 | NC 2015 | SHS (2015) | Region VII | Cebu | 312454 | Tan-awan NHS | OSLOB | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6369337.6381 |  |  | COMPLETED | 1
12697 | NC 2015 | SHS (2015) | Region VII | Cebu | 302952 | Tubod Dugoan NHS | DUMANJUG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00046 | 15HG0070 | 2015-06-10 | 2015-06-11 | 2015-06-24 | 2015-07-20 | 2015-07-22 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
12698 | NC 2015 | SHS (2015) | Region VII | Cebu | 302923 | Tubod NHS | BADIAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1
12699 | NC 2015 | K10 (2015) | Region VII | Cebu | 119540 | Tumalog ES | OSLOB | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00292 | 15HG0114 | 2015-06-25 | 2015-06-25 | 2015-07-08 | 2015-07-20 | 2015-07-22 | DT&C CONSTRUCTION
12700 | NC 2015 | SHS (2015) | Region VII | Cebu | 303123 | Usmad NHS | ARGAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00021 | 15HG0062 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-08-26 | 2015-08-27 | GEMSTRONG CONSTRUCTION, INC.
12701 | NC 2015 | SHS (2015) | Region VII | Cebu | 312455 | Willy B. Wenceslao MNHS | SANTANDER | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1
12702 | NC 2015 | K10 (2015) | Region VII | Cebu | 119030 | Abucayan ES | BALAMBAN | 3 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22102343.62 |  |  | COMPLETED | 1 |  |  | 070215S00497 | 15HF0105 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | J.A.R.C. CONSTRUCTION COMPANY
12703 | NC 2015 | SHS (2015) | Region VII | Cebu | 302919 | Aloguinsan NHS | ALOGUINSAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10567131.51 |  |  | COMPLETED | 1 |  |  | 070215S00374 | 15HF0092 | 2015-07-28 | 2015-07-29 | 2015-08-10 | 2015-08-14 | 2015-08-20 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
12704 | NC 2015 | SHS (2015) | Region VII | Cebu | 302920 | Angilan NHS | ALOGUINSAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 070215S00376 | 15HF0081 | 2015-07-22 | 2015-07-23 | 2015-08-04 | 2015-08-10 | 2015-08-14 | DINAH JANE CONSTRUCTION SUPPLY
12705 | NC 2015 | SHS (2015) | Region VII | Cebu | 303077 | Anislag NHS | ` | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00020 | 15HF0050 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | FIRST BUILDERS AND DEVELOPERS
12706 | NC 2015 | SHS (2015) | Region VII | Cebu | 303076 | Anopog NHS | PINAMUNGAHAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 070215S00030 | 15HF0069 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | FIRST BUILDERS AND DEVELOPERS
12707 | NC 2015 | K10 (2015) | Region VII | Cebu | 118967 | Bago ES | ASTURIAS | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00492 | 15HF0108 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
12708 | NC 2015 | SHS (2015) | Region VII | Cebu | 302928 | Balao NHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070215S00031 | 15HF0053 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-03 | 2015-07-10 | HI-TRI DEVELOPMENT CORPORATION
12709 | NC 2015 | K10 (2015) | Region VII | Cebu | 119073 | Barili I Central ES | BARILI | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6189337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00498 | 15HF0111 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | FIRST BUILDERS AND DEVELOPERS
12710 | NC 2015 | SHS (2015) | Region VII | Cebu | 303069 | Bartolome & Manuela Pañares MNHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
12711 | NC 2015 | SHS (2015) | Region VII | Cebu | 302945 | Buanoy NHS | BALAMBAN | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14997518.84 |  |  | COMPLETED | 1
12712 | NC 2015 | TECHVOC (2015) | Region VII | Cebu | 302945 | Buanoy NHS | BALAMBAN | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
12713 | NC 2015 | SHS (2015) | Region VII | Cebu | 302950 | BUANOY NHS-EVENING OPPORTUNITY CLASS | BALAMBAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1
12714 | NC 2015 | SHS (2015) | Region VII | Cebu | 302946 | Cabagdalan National High School | BALAMBAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00034 | 15HF0064 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | LA PRUEBA CONSTRUCTION
12715 | NC 2015 | K10 (2015) | Region VII | Cebu | 187012 | Cabiangon PS | PINAMUNGAHAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 070215S00521 | 15HF0112 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | WERR CORPORATION INTERNATIONAL
12716 | NC 2015 | SHS (2015) | Region VII | Cebu | 303071 | Cagay NHS | BARILI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1
12717 | NC 2015 | SHS (2015) | Region VII | Cebu | 302987 | Colonia NHS | TUBURAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10567131.51 |  |  | COMPLETED | 1
12718 | NC 2015 | K10 (2015) | Region VII | Cebu | 118972 | Cubong Elementary School | ASTURIAS | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00466 | 15HF0106 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | J.A.R.C. CONSTRUCTION COMPANY
12719 | NC 2015 | K10 (2015) | Region VII | Cebu | 119559 | Duangan ES | PINAMUNGAHAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00509 | 15HF0110 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | BL PANGAN CONSTRUCTION
12720 | NC 2015 | SHS (2015) | Region VII | Cebu | 303045 | Federico & Soledad MNHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
12721 | NC 2015 | K10 (2015) | Region VII | Cebu | 119042 | Gaas Elementary School | BALAMBAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00391 | 15HF0080 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-09-25 | 2015-10-01 | J.A.R.C. CONSTRUCTION COMPANY
12722 | NC 2015 | K10 (2015) | Region VII | Cebu | 302947 | Gaas NHS | BALAMBAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00385 | 15HF0080 | [5 empty] | J.A.R.C. CONSTRUCTION COMPANY
12723 | NC 2015 | SHS (2015) | Region VII | Cebu | 303012 | Giloctog NHS | BARILI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6719337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00082 | 15HF0072 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-20 | 2015-07-24 | J.A.R.C. CONSTRUCTION COMPANY
12724 | NC 2015 | SHS (2015) | Region VII | Cebu | 312415 | Ginatilan NHS | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00080 | 15HF0047 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION
12725 | NC 2015 | SHS (2015) | Region VII | Cebu | 303070 | Guibuangan NHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00053 | 15HF0056 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-03 | 2015-07-10 | DUROS DEVELOPMENT CORP.
12726 | NC 2015 | K10 (2015) | Region VII | Cebu | 118974 | Guinabasan ES | ASTURIAS | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 070215S00523 | 15HF0102 | 2015-08-24 | 2015-08-25 | 2015-09-07 | 2015-10-20 | 2015-10-23 | MAP ALVIOLA CONSTRUCTION
12727 | NC 2015 | SHS (2015) | Region VII | Cebu | 312451 | Ireneo V. Diamante NHS | TUBURAN | 3 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2880828.124 |  |  | COMPLETED | 1
12728 | NC 2015 | K10 (2015) | Region VII | Cebu | 119094 | Japitan ES | BARILI | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00465 | 15HF0111 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | FIRST BUILDERS AND DEVELOPERS
12729 | NC 2015 | SHS (2015) | Region VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | BALAMBAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070215S00076 | 15HF0048 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | LA PRUEBA CONSTRUCTION
12730 | NC 2015 | SHS (2015) | Region VII | Cebu | 312453 | Kalangahan NHS | TUBURAN | 3 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2940828.124 |  |  | COMPLETED | 1
12731 | NC 2015 | K10 (2015) | Region VII | Cebu | 118908 | Kandingan Elementary | ALOGUINSAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6339337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00473 | 15HF0112 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | WERR CORPORATION INTERNATIONAL
12732 | NC 2015 | SHS (2015) | Region VII | Cebu | 312452 | Kansi NHS | TUBURAN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00057 | 15HF0043 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | QUIRANTE CONSTRUCTION
12733 | NC 2015 | SHS (2015) | Region VII | Cebu | 303029 | Lamac NHS | PINAMUNGAHAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1
12734 | NC 2015 | SHS (2015) | Region VII | Cebu | 312470 | Lamak National High School | BARILI | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2008606.04 |  |  | COMPLETED | 1
12735 | NC 2015 | SHS (2015) | Region VII | Cebu | 312470 | Lamak National High School | BARILI | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
12736 | NC 2015 | SHS (2015) | Region VII | Cebu | 302948 | Lamesa NHS | BALAMBAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 070215S00367 | 15HF0082 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-02 | 2015-09-08 | DINAH JANE CONSTRUCTION SUPPLY
12737 | NC 2015 | SHS (2015) | Region VII | Cebu | 312468 | Liki Integrated School | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00058 | 15HF0048 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | LA PRUEBA CONSTRUCTION
12738 | NC 2015 | SHS (2015) | Region VII | Cebu | 303044 | Looc Norte NHS | ASTURIAS | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070215S00079 | 15HF0044 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | QUIRANTE CONSTRUCTION
12739 | NC 2015 | K10 (2015) | Region VII | Cebu | 118980 | Lunas I ES | ASTURIAS | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 070215S00522 | 15HF0106 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | J.A.R.C. CONSTRUCTION COMPANY
12740 | NC 2015 | K10 (2015) | Region VII | Cebu | 119097 | Malolos ES | BARILI | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00388 | 15HF0087 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-02 | 2015-09-08 | DINAH JANE CONSTRUCTION SUPPLY
12741 | NC 2015 | SHS (2015) | Region VII | Cebu | 303050 | Malolos NHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00090 | 15HF0066 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | DINAH JANE CONSTRUCTION SUPPLY
12742 | NC 2015 | SHS (2015) | Region VII | Cebu | 312418 | Manguiao NHS | ASTURIAS | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1
12743 | NC 2015 | SHS (2015) | Region VII | Cebu | 303052 | Mantalongon NHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00073 | 15HF0067 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | DINAH JANE CONSTRUCTION SUPPLY
12744 | NC 2015 | K10 (2015) | Region VII | Cebu | 119848 | Marmol ES | TUBURAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00463 | 15HF0109 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | DINAH JANE CONSTRUCTION SUPPLY
12745 | NC 2015 | SHS (2015) | Region VII | Cebu | 312429 | Milan-Cantuod NHS | BALAMBAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00083 | 15HF0070 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-20 | 2015-07-24 | LA PRUEBA CONSTRUCTION
12746 | NC 2015 | SHS (2015) | Region VII | Cebu | 303059 | Montealegre NHS | TUBURAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6549337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00084 | 15HF0042 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | DINAH JANE CONSTRUCTION SUPPLY
12747 | NC 2015 | SHS (2015) | Region VII | Cebu | 302949 | Nangka NHS | BALAMBAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
12748 | NC 2015 | SHS (2015) | Region VII | Cebu | 303068 | Patupat NHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1
12749 | NC 2015 | SHS (2015) | Region VII | Cebu | 303075 | Pinamungajan NHS | PINAMUNGAHAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
12750 | NC 2015 | SHS (2015) | Region VII | Cebu | 303060 | Putat NHS | TUBURAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 3102592.44 |  |  | COMPLETED | 1 |  |  | 070215S00375 | 15HF0084 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-02 | 2015-09-08 | MAP ALVIOLA CONSTRUCTION
12751 | NC 2015 | K10 (2015) | Region VII | Cebu | 119568 | Rizal ES | PINAMUNGAHAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00464 | 15HF0110 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | BL PANGAN CONSTRUCTION
12752 | NC 2015 | SHS (2015) | Region VII | Cebu | 303083 | Rosario NHS | ALOGUINSAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1
12753 | NC 2015 | SHS (2015) | Region VII | Cebu | 303097 | Santa Lucia NHS | ASTURIAS | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 070215S00089 | 15HF0046 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | QUIRANTE CONSTRUCTION
12754 | NC 2015 | K10 (2015) | Region VII | Cebu | 119822 | Siotes PS | TUBURAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00457 | 15HF0109 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | DINAH JANE CONSTRUCTION SUPPLY
12755 | NC 2015 | K10 (2015) | Region VII | Cebu | 118988 | Sta. Lucia ES | ASTURIAS | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00468 | 15HF0107 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
12756 | NC 2015 | SHS (2015) | Region VII | Cebu | 312414 | Sta. Rita NHS | ASTURIAS | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8444965.051 |  |  | COMPLETED | 1
12757 | NC 2015 | SHS (2015) | Region VII | Cebu | 303013 | TEOTIMO A. ABELLANA SR. MEMORIAL NATIONAL HIGH SCHOOL | BARILI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00064 | 15HF0058 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-03 | 2015-07-10 | DUROS DEVELOPMENT CORP.
12758 | NC 2015 | SHS (2015) | Region VII | Cebu | 303061 | Tuburan National High School | TUBURAN | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10927342.5917 |  |  | COMPLETED | 1
12759 | NC 2015 | TECHVOC (2015) | Region VII | Cebu | 303061 | Tuburan National High School | TUBURAN | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4829098.54 |  |  | COMPLETED | 1
12760 | NC 2015 | K10 (2015) | Region VII | Cebu | 119029 | Vito ES | BALAMBAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00390 | 15HF0090 | 2015-07-28 | 2015-07-29 | 2015-08-10 | 2015-08-14 | 2015-08-20 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
12761 | NC 2015 | K10 (2015) | Region VII | Cebu | 303025 | Almacen-Torrevillas National High School | MEDELLIN | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00411 | 15HD0104 | 2015-11-11 | 2015-11-25 | 2015-11-26 | 2015-12-05 | 2015-12-17 | J.A.R.C. CONSTRUCTION COMPANY
12762 | NC 2015 | K10 (2015) | Region VII | Cebu | 119670 | Anapog ES | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00462 | 15HD0098 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-11-03 | 2015-11-10 | BANTAY CONSTRUCTION
12763 | NC 2015 | SHS (2015) | Region VII | Cebu | 500220 | Anapog Integrated School | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
12764 | NC 2015 | SHS (2015) | Region VII | Cebu | 500219 | Argawanon Integrated School | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6469337.6381 |  |  | COMPLETED | 1
12765 | NC 2015 | K10 (2015) | Region VII | Cebu | 119671 | Bagtik ES | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00461 | 15HD0099 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-11-03 | 2015-11-10 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
12766 | NC 2015 | SHS (2015) | Region VII | Cebu | 302924 | Bakhawan NHS | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8324965.051 |  |  | COMPLETED | 1
12767 | NC 2015 | K10 (2015) | Region VII | Cebu | 119660 | Bancasan ES | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00470 | 15HD0097 | 2015-10-14 | 2015-10-27 | 2015-10-27 | 2015-11-03 | 2015-11-10 | BANTAY CONSTRUCTION
12768 | NC 2015 | SHS (2015) | Region VII | Cebu | 302938 | Bantayan NHS | BANTAYAN | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15927518.84 |  |  | COMPLETED | 1
12769 | NC 2015 | SHS (2015) | Region VII | Cebu | 312421 | Bantayan Science High School | BANTAYAN | 4 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2920828.124 |  |  | COMPLETED | 1 |  |  | 070215S00061 | 15HD0063 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | ROVILLA CONSTRUCTION
12770 | NC 2015 | SHS (2015) | Region VII | Cebu | 302939 | Bateria NHS | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1
12771 | NC 2015 | SHS (2015) | Region VII | Cebu | 312464 | Bunakan Integrated School | MADRIDEJOS | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6839337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00364 | 15HD0086 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-10-22 | 2015-10-30 | GONZALODO ENTERPRISES
12772 | NC 2015 | SHS (2015) | Region VII | Cebu | 500221 | Busogon Integrated School | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00239 | 15HD0056 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
12773 | NC 2015 | SHS (2015) | Region VII | Cebu | 312442 | Calambua Integrated School | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00231 | 15HD0056 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
12774 | NC 2015 | SHS (2015) | Region VII | Cebu | 302961 | Calape NHS | DAANBANTAYAN | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10497131.51 |  |  | COMPLETED | 1 |  |  | 070215S00063 | 15HD0071 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-10-22 | 2015-10-30 | FIRST BUILDERS AND DEVELOPERS
12775 | NC 2015 | SHS (2015) | Region VII | Cebu | 302976 | Carnaza NHS | DAANBANTAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6839337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00055 | 15HD0054 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12776 | NC 2015 | SHS (2015) | Region VII | Cebu | 303026 | Curva NHS | MEDELLIN | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 8 | 15371327.92 |  |  | COMPLETED | 1
12777 | NC 2015 | SHS (2015) | Region VII | Cebu | 302995 | Daanbantayan NHS | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1
12778 | NC 2015 | TECHVOC (2015) | Region VII | Cebu | 302995 | Daanbantayan NHS | DAANBANTAYAN | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
12779 | NC 2015 | K10 (2015) | Region VII | Cebu | 119458 | Daanlungsod ES | MEDELLIN | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00384 | 15HD0074 | 2015-08-05 | 2015-08-17 | 2015-08-17 | 2015-08-22 | 2015-08-24 | ROVILLA CONSTRUCTION
12780 | NC 2015 | K10 (2015) | Region VII | Cebu | 119750 | Daantabogon ES | TABOGON | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00455 | 15HD0101 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-11-03 | 2015-11-10 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
12781 | NC 2015 | SHS (2015) | Region VII | Cebu | 312408 | Daantabogon NHS | TABOGON | 4 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2710828.124 |  |  | COMPLETED | 1 |  |  | 070215S00066 | 15HD0039 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-05 | 2015-08-12 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
12782 | NC 2015 | SHS (2015) | Region VII | Cebu | 303001 | Dapdap NHS, San Remigio | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00067 | 15HD0057 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | GONZALODO ENTERPRISES
12783 | NC 2015 | SHS (2015) | Region VII | Cebu | 303005 | Do¤a Liling Neis Negapatan MNHS | TABOGON | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00068 | 15HD0040 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | GONZALODO ENTERPRISES
12784 | NC 2015 | SHS (2015) | Region VII | Cebu | 303003 | Don Esteban Nolasco Memorial NHS | TABOGON | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00224 | 15HD0039 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-05 | 2015-08-12 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
12785 | NC 2015 | SHS (2015) | Region VII | Cebu | 303007 | Doong NHS | BANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9044965.051 |  |  | COMPLETED | 1
12786 | NC 2015 | SHS (2015) | Region VII | Cebu | 312458 | Gibitngil Integrated School | MEDELLIN | 4 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2870828.124 |  |  | COMPLETED | 1
12787 | NC 2015 | SHS (2015) | Region VII | Cebu | 312420 | Hilantagaan NHS Ext. | SANTA FE | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9074965.051 |  |  | COMPLETED | 1
12788 | NC 2015 | SHS (2015) | Region VII | Cebu | 312456 | Hilotongan Integrated School | BANTAYAN | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
12789 | NC 2015 | SHS (2015) | Region VII | Cebu | 303004 | Horacio Franco MNHS | TABOGON | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1
12790 | NC 2015 | K10 (2015) | Region VII | Cebu | 312465 | Ilihan Integrated School | TABOGON | 4 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1
12791 | NC 2015 | SHS (2015) | Region VII | Cebu | 312465 | Ilihan Integrated School | TABOGON | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15171328 |  |  | COMPLETED | 1
12792 | NC 2015 | SHS (2015) | Region VII | Cebu | 303021 | Jose R. Martinez | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00234 | 15HD0056 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
12793 | NC 2015 | SHS (2015) | Region VII | Cebu | 303103 | Juan Pamplona NHS | TABUELAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070215S00274 | 15HD0055 | 2015-08-17 | 2015-09-02 | 2015-09-02 | 2015-09-22 | 2015-09-30 | DINAH JANE CONSTRUCTION SUPPLY
12794 | NC 2015 | SHS (2015) | Region VII | Cebu | 303023 | Kal-anan NHS | TABOGON | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00275 | 15HD0041 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12795 | NC 2015 | SHS (2015) | Region VII | Cebu | 303024 | Kawit NHS | MEDELLIN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070215S00273 | 15HD0044 | 2015-07-14 | 2015-07-28 | 2015-07-28 | 2015-08-05 | 2015-08-12 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
12796 | NC 2015 | SHS (2015) | Region VII | Cebu | 303028 | Kinartacan NHS | SANTA FE | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9044965.051 |  |  | COMPLETED | 1
12797 | NC 2015 | SHS (2015) | Region VII | Cebu | 312443 | Kinawahan Integrated School | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00235 | 15HD0056 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
12798 | NC 2015 | SHS (2015) | Region VII | Cebu | 312463 | Kodia Integrated School | MADRIDEJOS | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00248 | 15HD0069 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | GONZALODO ENTERPRISES
12799 | NC 2015 | SHS (2015) | Region VII | Cebu | 303030 | Lambusan NHS | SAN REMIGIO | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 070215S00227 | 15HD0059 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-05 | 2015-08-12 | ZION CONSTRUCTION(FORMERLY MASTERPIECE CONST. & SU
12800 | NC 2015 | SHS (2015) | Region VII | Cebu | 303041 | Libaong NHS | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1
12801 | NC 2015 | SHS (2015) | Region VII | Cebu | 303043 | Logon NHS | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8734965.051 |  |  | COMPLETED | 1 |  |  | 070215S00246 | 15HD0050 | 2015-07-14 | 2015-07-28 | 2015-07-28 | 2015-08-05 | 2015-08-12 | BANTAY CONSTRUCTION
12802 | NC 2015 | K10 (2015) | Region VII | Cebu | 119756 | Loong Elementary School | TABOGON | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2538606.04 |  |  | COMPLETED | 1 |  |  | 070215S00520 | 15HD0103 | 2015-10-14 | 2015-10-27 | 2015-10-27 | 2015-11-03 | 2015-11-10 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
12803 | NC 2015 | SHS (2015) | Region VII | Cebu | 303006 | Loreto-Remedios Montebon NHS | TABOGON | 4 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2690828.124 |  |  | COMPLETED | 1 |  |  | 070215S00230 | 15HD0038 | 2015-07-14 | 2015-07-28 | 2015-07-28 | 2015-08-05 | 2015-08-12 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
12804 | NC 2015 | SHS (2015) | Region VII | Cebu | 303046 | Luyang NHS | SAN REMIGIO | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10717131.51 |  |  | COMPLETED | 1 |  |  | 070215S00368 | 15HD0092 | 2015-11-11 | 2015-11-25 | 2015-11-26 | 2015-12-07 | 2015-12-17 | R.U. AQUINO CONSTRUCTION AND DEVELOPMENT CORP. (FO
12805 | NC 2015 | SHS (2015) | Region VII | Cebu | 312422 | Mabunao NHS-Juan Pamplona Ext. | TABUELAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00361 | 15HD0088 | 2015-11-11 | 2015-11-25
12806 | NC 2015 | SHS (2015) | Region VII | Cebu | 303047 | Madridejos NHS | MADRIDEJOS | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 16171327.92 |  |  | COMPLETED | 1
12807 | NC 2015 | TECHVOC (2015) | Region VII | Cebu | 303047 | Madridejos NHS | MADRIDEJOS | 4 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
12808 | NC 2015 | SHS (2015) | Region VII | Cebu | 302962 | Malingin NHS | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 070215S00232 | 15HD0051 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | BANTAY CONSTRUCTION
12809 | NC 2015 | SHS (2015) | Region VII | Cebu | 312445 | Marikaban Integrated School | SANTA FE | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6839337.6381 |  |  | COMPLETED | 1
12810 | NC 2015 | SHS (2015) | Region VII | Cebu | 303053 | Maya NHS | DAANBANTAYAN | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 070215S00254 | 15HD0072 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-10-22 | 2015-10-30 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12811 | NC 2015 | SHS (2015) | Region VII | Cebu | 303054 | Medellin National High School | MEDELLIN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00252 | 15HD0045 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | GONZALODO ENTERPRISES
12812 | NC 2015 | SHS (2015) | Region VII | Cebu | 303027 | Medellin National Science and Technology School | MEDELLIN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00241 | 15HD0043 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | FIRST BUILDERS AND DEVELOPERS
12813 | NC 2015 | SHS (2015) | Region VII | Cebu | 312438 | Oboob Integrated School | BANTAYAN | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00236 | 15HD0063 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | ROVILLA CONSTRUCTION
12814 | NC 2015 | SHS (2015) | Region VII | Cebu | 312409 | Patao NHS | BANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8944965.051 |  |  | COMPLETED | 1 |  |  | 070215S00242 | 15HD0065 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | ROVILLA CONSTRUCTION
12815 | NC 2015 | SHS (2015) | Region VII | Cebu | 302963 | Paypay NHS | DAANBANTAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00243 | 15HD0046 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | R.U. AQUINO CONSTRUCTION AND DEVELOPMENT CORP. (FO
12816 | NC 2015 | SHS (2015) | Region VII | Cebu | 312430 | Salag NHS | TABOGON | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00237 | 15HD0038 | 2015-07-14 | 2015-07-28 | 2015-07-28 | 2015-08-05 | 2015-08-12 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
12817 | NC 2015 | SHS (2015) | Region VII | Cebu | 303048 | San Agustin NHS | MADRIDEJOS | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8964965.051 |  |  | COMPLETED | 1 |  |  | 070215S00244 | 15HD0068 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | GONZALODO ENTERPRISES
12818 | NC 2015 | K10 (2015) | Region VII | Cebu | 119762 | San Isidro Elementary School | TABOGON | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00451 | 15HD0101 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-11-03 | 2015-11-10 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
12819 | NC 2015 | SHS (2015) | Region VII | Cebu | 303086 | San Miguel NHS | SAN REMIGIO | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10767131.51 |  |  | COMPLETED | 1 |  |  | 070215S00355 | 15HD0094 | 2015-11-11 | 2015-11-25
12820 | NC 2015 | SHS (2015) | Region VII | Cebu | 303087 | San Remegio NHS | SAN REMIGIO | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00245 | 15HD0060 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | GONZALODO ENTERPRISES
12821 | NC 2015 | SHS (2015) | Region VII | Cebu | 303094 | Santa Fe NHS | SANTA FE | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 11337131.51 |  |  | COMPLETED | 1 |  |  | 070215S00255 | 15HD0073 | 2015-10-14 | 2015-10-27 | 2015-10-27 | 2015-11-03 | 2015-11-10 | ROVILLA CONSTRUCTION
12822 | NC 2015 | SHS (2015) | Region VII | Cebu | 119069 | Sillon ES | BANTAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6869337.6381 |  |  | COMPLETED | 1
12823 | NC 2015 | SHS (2015) | Region VII | Cebu | 302996 | SK Luis P. Canete NHS | DAANBANTAYAN | 4 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2690828.124 |  |  | COMPLETED | 1 |  |  | 070215S00240 | 15HD0046 | 2015-07-14 | 2015-07-28 | 2015-07-28 | 2015-08-05 | 2015-08-12 | R.U. AQUINO CONSTRUCTION AND DEVELOPMENT CORP. (FO
12824 | NC 2015 | SHS (2015) | Region VII | Cebu | 119057 | Sulangan ES | BANTAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6844337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00249 | 15HD0067 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | ROVILLA CONSTRUCTION
12825 | NC 2015 | K10 (2015) | Region VII | Cebu | 119766 | Tabogon Central ES | TABOGON | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00416 | 15HD0075 | 2015-08-05 | 2015-08-17 | 2015-08-17 | 2015-08-21 | 2015-08-24 | ROVILLA CONSTRUCTION
12826 | NC 2015 | SHS (2015) | Region VII | Cebu | 312444 | Tambongon Integrated School | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00337 | 15HD0089 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-10-22 | 2015-10-30 | GOLDFIN CONSTRUCTION
12827 | NC 2015 | K10 (2015) | Region VII | Cebu | 119070 | Tamiao ES | BANTAYAN | 4 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 070215S00386 | 15HD0091 | 2015-10-14 | 2015-10-27 | 2015-10-27 | 2015-11-03 | 2015-11-10 | ROVILLA CONSTRUCTION
12828 | NC 2015 | SHS (2015) | Region VII | Cebu | 302964 | Tapilon National High School | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
12829 | NC 2015 | SHS (2015) | Region VII | Cebu | 302965 | Tominjao National High School | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8324965.051 |  |  | COMPLETED | 1
12830 | NC 2015 | SHS (2015) | Region VII | Cebu | 312407 | Arcelo Memorial National Night High School | LILOAN | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00313 | 15HI0054 | 2015-07-09 | 2015-07-21 | 2015-07-22 | 2015-07-26 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12831 | NC 2015 | SHS (2015) | Region VII | Cebu | 312448 | Bagalnga Integrated School | COMPOSTELA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1
12832 | NC 2015 | SHS (2015) | Region VII | Cebu | 303105 | Bongdo NHS | BORBON | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1
12833 | NC 2015 | K10 (2015) | Region VII | Cebu | 119211 | Bongyas Elementary | CATMON | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00428 | 15HI0057 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-07-27 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12834 | NC 2015 | SHS (2015) | Region VII | Cebu | 303106 | Borbon NHS | BORBON | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00267 | 15HI0040 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | FIRST GRANDEUR BUILDERS
12835 | NC 2015 | K10 (2015) | Region VII | Cebu | 119225 | Cabadiangan ES | COMPOSTELA | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6244337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00454 | 15HI0077 | 2015-08-23 | 2015-09-04 | 2015-09-05 | 2015-09-09 | 2015-09-13 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12836 | NC 2015 | SHS (2015) | Region VII | Cebu | 302974 | Cabalawan NHS | SOGOD | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 070215S00276 | 15HI0035 | 2015-11-29
12837 | NC 2015 | SHS (2015) | Region VII | Cebu | 302968 | Cabonga-an NHS | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8964965.051 |  |  | COMPLETED | 1
12838 | NC 2015 | K10 (2015) | Region VII | Cebu | 119212 | Cabunga-an ES | CATMON | 5 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00429 | 15HI0056 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-07-27 | 2015-08-20 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
12839 | NC 2015 | K10 (2015) | Region VII | Cebu | 119410 | Calero ES | LILOAN | 5 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | COMPLETED | 1 |  |  | 070215S00496 | 15HI0075 | 2015-08-23 | 2015-09-04 | 2015-09-05 | 2015-09-09 | 2015-09-13 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12840 | NC 2015 | SHS (2015) | Region VII | Cebu |  | Calero IS | LILOAN | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6369338 |  |  | COMPLETED | 1
12841 | NC 2015 | K10 (2015) | Region VII | Cebu | 302966 | Calumboyan NHS | SOGOD | 5 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | Reverted | 0 |  |  | 070215S00426 | 15HI0058 | [5 empty] | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12842 | NC 2015 | SHS (2015) | Region VII | Cebu | 302967 | Camotes National High School | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8974965.051 |  |  | COMPLETED | 1
12843 | NC 2015 | SHS (2015) | Region VII | Cebu | 303107 | Campusong NHS | BORBON | 5 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00259 | 15HI0036 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | FIRST GRANDEUR BUILDERS
12844 | NC 2015 | SHS (2015) | Region VII | Cebu | 302975 | Cantumog NHS | CARMEN | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 070115S00020 | 15HI0089 | 2015-09-15 | 2015-09-27 | 2015-09-28 | 2015-10-02 | 2015-10-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12845 | NC 2015 | SHS (2015) | Region VII | Cebu | 312410 | Carmen National High School - Night | CARMEN | 5 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0 |  |  | 070115S00019 | 15HI0031
12846 | NC 2015 | SHS (2015) | Region VII | Cebu | 302973 | Carmen NHS-Day | CARMEN | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
12847 | NC 2015 | TECHVOC (2015) | Region VII | Cebu | 302973 | Carmen NHS-Day | CARMEN | 5 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
12848 | NC 2015 | SHS (2015) | Region VII | Cebu | 312447 | Catmon Integrated School | CATMON | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
12849 | NC 2015 | SHS (2015) | Region VII | Cebu | 312416 | Caurasan NHS | CARMEN | 5 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00021 | 15HI0030 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | YES CONSTRUCTION
12850 | NC 2015 | SHS (2015) | Region VII | Cebu | 302979 | Ceferino Sususco MNHS | CATMON | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6719337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00277 | 15HI0033 | 2015-11-29 | 2015-12-11 | 2015-12-12 | 2015-12-16 | 2015-12-20 | BANTAY CONSTRUCTION
12851 | NC 2015 | SHS (2015) | Region VII | Cebu | 303063 | Compostela National High School | COMPOSTELA | 5 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 070215S00271 | 15HI0095 | 2015-08-31 | 2015-09-12 | 2015-09-13 | 2015-09-17 | 2015-09-21 | VEN RAY CONSTRUCTION CORPORATION
12852 | NC 2015 | SHS (2015) | Region VII | Cebu | 312406 | Compostela Science & Technology High School | COMPOSTELA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00269 | 15HI0028 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | LA PRUEBA CONSTRUCTION
12853 | NC 2015 | SHS (2015) | Region VII | Cebu | 302994 | Consuelo NHS | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8914965.051 |  |  | COMPLETED | 1
12854 | NC 2015 | K10 (2015) | Region VII | Cebu | 119644 | Dapdap ES | SAN FRANCISCO | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00431 | 15HI0061 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-07-27 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12855 | NC 2015 | SHS (2015) | Region VII | Cebu | 303032 | Dapdap NHS | PILAR | 5 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00290 | 15HI0053 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | FIRST BUILDERS AND DEVELOPERS
12856 | NC 2015 | K10 (2015) | Region VII | Cebu | 119189 | Dawis Norte ES | CARMEN | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00452 | 15HI0079 | 2015-08-23 | 2015-09-04 | 2015-09-05 | 2015-09-09 | 2015-09-13 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12857 | NC 2015 | SHS (2015) | Region VII | Cebu | 303108 | Do¤a Milagros MNHS | BORBON | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070215S00268 | 15HI0041 | 2015-11-29
12858 | NC 2015 | SHS (2015) | Region VII | Cebu | 303074 | Don Filomeno M. Torres MNHS | PILAR | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6989337.6381 |  |  | COMPLETED | 1
12859 | NC 2015 | SHS (2015) | Region VII | Cebu | 303031 | Lanao NHS, Pilar | PILAR | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 7169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00315 | 15HI0063 | 2015-07-09 | 2015-07-21 | 2015-07-22 | 2015-07-26 | 2015-08-20 | FIRST BUILDERS AND DEVELOPERS
12860 | NC 2015 | SHS (2015) | Region VII | Cebu | 312428 | Lataban NHS | LILOAN | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00284 | 15HI0027 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
12861 | NC 2015 | SHS (2015) | Region VII | Cebu | 303092 | Liloan NHS | LILOAN | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
12862 | NC 2015 | TECHVOC (2015) | Region VII | Cebu | 303092 | Liloan NHS | LILOAN | 5 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | Reverted | 0
12863 | NC 2015 | SHS (2015) | Region VII | Cebu |  | Liloan NHS EXT Don Bosco | LILOAN | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
12864 | NC 2015 | SHS (2015) | Region VII | Cebu | 303122 | Lorenzo C. Tanza Memorial National High School | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8964965.051 |  |  | COMPLETED | 1 |  |  | 070215S00283 | 15HI0045 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12865 | NC 2015 | SHS (2015) | Region VII | Cebu | 303008 | Luciano B. Rama Sr. MNHS | PORO | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 7049337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00320 | 15HI0062 | 2015-07-09 | 2015-07-21 | 2015-07-22 | 2015-07-26 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12866 | NC 2015 | SHS (2015) | Region VII | Cebu | 312423 | Mar and Dorie Darunday NHS | BORBON | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6479337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00256 | 15HI0038 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
12867 | NC 2015 | K10 (2015) | Region VII | Cebu | 303110 | Mohon NHS | SOGOD | 5 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00436 | 15HI0059 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-07-27 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12868 | NC 2015 | SHS (2015) | Region VII | Cebu | 303062 | Mulao NHS | COMPOSTELA | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 070215S00266 | 15HI0086 | 2015-09-15 | 2015-09-27 | 2015-09-28 | 2015-10-02 | 2015-10-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12869 | NC 2015 | SHS (2015) | Region VII | Cebu | 303073 | Pilar NHS | PILAR | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9044965.051 |  |  | COMPLETED | 1 |  |  | 070215S00280 | 15HI0051 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | FIRST BUILDERS AND DEVELOPERS
12870 | NC 2015 | K10 (2015) | Region VII | Cebu | 119743 | Poblacion ES | SOGOD | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00434 | 15HI0060 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-07-27 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12871 | NC 2015 | SHS (2015) | Region VII | Cebu | 303080 | Puertobello NHS | TUDELA | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8994965.051 |  |  | COMPLETED | 1
12872 | NC 2015 | SHS (2015) | Region VII | Cebu | 303081 | Puertobello NHS - Pob. Ext. | TUDELA | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9024965.051 |  |  | COMPLETED | 1
12873 | NC 2015 | K10 (2015) | Region VII | Cebu | 119200 | Sac-on ES | CARMEN | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00453 | 15HI0098 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-10-31
12874 | NC 2015 | SHS (2015) | Region VII | Cebu | 303085 | San Jose NHS | PORO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8994965.051 |  |  | COMPLETED | 1 |  |  | 070215S00263 | 15HI0047 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12875 | NC 2015 | SHS (2015) | Region VII | Cebu | 303100 | Santiago National High School | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9064965.051 |  |  | COMPLETED | 1 |  |  | 070215S00282 | 15HI0050 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12876 | NC 2015 | SHS (2015) | Region VII | Cebu | 312417 | SAPAK HS | COMPOSTELA | 5 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0 |  |  | 070215S00257
12877 | NC 2015 | SHS (2015) | Region VII | Cebu | 303104 | Tabunan NHS | BORBON | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00261 | 15HI0039 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12878 | NC 2015 | SHS (2015) | Region VII | Cebu | 302980 | Tinabyonan NHS | CATMON | 5 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00253 | 15HI0032 | 2015-11-29
12879 | NC 2015 | K10 (2015) | Region VII | Cebu | 187023 | Tubigan ES | COMPOSTELA | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00430 | 15HI0055 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-07-27 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12880 | NC 2015 | K10 (2015) | Region VII | Cebu | 119658 | Union ES | SAN FRANCISCO | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00432 | 15HI0072 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12881 | NC 2015 | SHS (2015) | Region VII | Cebu | 303009 | Zosimo E. Fabroa MNHS | PORO | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6889337.6381 |  |  | COMPLETED | 1
12882 | NC 2015 | SHS (2015) | Region VII | Cebu | 302954 | Cabangahan NHS | CONSOLACION | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00163 | 15HN0092 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | YES CONSTRUCTION
12883 | NC 2015 | SHS (2015) | Region VII | Cebu | 302988 | Consolacion NHS - Day Class | CONSOLACION | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 070215S00178 | 15HN0093 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12884 | NC 2015 | SHS (2015) | Region VII | Cebu | 302989 | Consolacion NHS - Evening Class | CONSOLACION | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 070215S00179 | 15HN0094 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | GENETIAN BUILDERS
12885 | NC 2015 | SHS (2015) | Region VII | Cebu | 302955 | Cordova NHS | CORDOBA | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 070215S00180 | 15HN0099 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12886 | NC 2015 | K10 (2015) | Region VII | Cebu | 119240 | Garing ES | CONSOLACION | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6189337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00472 | 15HN0130 | 2015-09-22 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-29 | P.B. OBIAL CONSTRUCTION
12887 | NC 2015 | SHS (2015) | Region VII | Cebu | 303010 | Garing NHS | CONSOLACION | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 070215S00181 | 15HN0095 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | P.B. OBIAL CONSTRUCTION
12888 | NC 2015 | K10 (2015) | Region VII | Cebu | 119241 | Jugan ES | CONSOLACION | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00460 | 15HN0131 | 2015-09-22 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-29 | P.B. OBIAL CONSTRUCTION
12889 | NC 2015 | SHS (2015) | Region VII | Cebu | 302990 | Jugan NHS | CONSOLACION | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2008606.04 |  |  | Reverted | 0
12890 | NC 2015 | SHS (2015) | Region VII | Cebu | 302990 | Jugan NHS | CONSOLACION | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | Reverted | 0
12891 | NC 2015 | K10 (2015) | Region VII | Cebu | 119246 | Panoypoy ES | CONSOLACION | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6259337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00456 | 15HN0132 | 2015-09-22 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-29 | PLD CONSTRUCTION
12892 | NC 2015 | SHS (2015) | Region VII | Cebu | 303114 | Tayud NHS | CONSOLACION | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 070215S00182 | 15HN0096 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | GONZALODO ENTERPRISES
12893 | NC 2015 | SHS (2015) | Region VII | Cebu | 302992 | Tolotolo NHS | CONSOLACION | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2872592.44 |  |  | COMPLETED | 1 |  |  | 070215S00311 | 15HN0100 | 2015-08-26 | 2015-09-03 | 2015-09-15 | 2015-09-23 | 2015-10-02 | MANINGO ENTERPRISES
12894 | NC 2015 | SHS (2015) | Region VII | Cebu | 302993 | Tugbongan NHS | CONSOLACION | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00192 | 15HN0080 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | GONZALODO ENTERPRISES
12895 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303128 | Abellana NHS (Day & NIght) | CEBU CITY (Capital) | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 |  |  | 070215S00449 | 15HH0099 | 2015-09-22 | 2015-09-10 | 2015-09-22
12896 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303129 | Adlaon NHS | CEBU CITY (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10917131.51 |  |  | COMPLETED | 1 |  |  | 070215S00317 | 15HH0064 | 2015-07-29 | 2015-07-10 | 2015-07-29 | 2015-09-22 | 2015-10-10 | CHARLZ CONSTRUCTION
12897 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 303130 | Agsungot NHS . | CEBU CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00184 | 15HH0035 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-09-07 | 2015-09-18 | GOLDFIN CONSTRUCTION
12898 | NC 2015 | SHS (2015) | Region VII | Cebu City | 312503 | Banilad Night HS | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 070215S00177 | 15HH0071 | 2015-08-26 | 2015-08-14 | 2015-08-26 | 2015-09-16 | 2015-09-18 | CPR CONSTRUCTION AND SUPPLY
12899 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303152 | Barrio Luz NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 070215S00186 | 15HH0072 | 2015-08-26 | 2015-08-14 | 2015-08-26 | 2015-09-22 | 2015-10-26 | GONZALODO ENTERPRISES
12900 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 303131 | Binaliw NHS | CEBU CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00187 | 15HH0054 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-14 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
12901 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303134 | Bonbon NHS | CEBU CITY (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10767131.51 |  |  | COMPLETED | 1 |  |  | 070215S00356 | 15HH0065 | 2015-08-24 | 2015-08-12 | 2015-08-24 | 2015-09-07 | 2015-09-18 | GOWIL BUILDERS
12902 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303136 | Busay NHS | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6819337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00189 | 15HH0057 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-18 | RAMIJO CONSTRUCTION
12903 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303138 | Camp Lapu-Lapu NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15197518.84 |  |  | COMPLETED | 1
12904 | NC 2015 | TECHVOC (2015) | Region VII | Cebu City | 303138 | Camp Lapu-Lapu NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | Reverted | 0
12905 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303142 | Don Carlos Gothong Memorial NHS | CEBU CITY (Capital) | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31402890.27 |  |  | COMPLETED | 1 |  |  | 070215S00334 | 15HH0091 | 2015-09-14 | 2015-09-02 | 2015-09-14 | 2015-10-14 | 2015-10-29 | PLD CONSTRUCTION
12906 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. NHS (Basak NHS) | CEBU CITY (Capital) | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26902469.42 |  |  | COMPLETED | 1 |  |  | 070215S00340 | 15HH0090 | 2015-09-14 | 2015-09-02 | 2015-09-14 | 2015-10-14 | 2015-10-29 | GOLDFIN CONSTRUCTION
12907 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303157 | Guba NHS | CEBU CITY (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10717131.51 |  |  | COMPLETED | 1 |  |  | 070215S00190 | 15HH0069 | 2015-08-26 | 2015-08-14 | 2015-08-26 | 2015-09-16 | 2015-09-18 | CHARLZ CONSTRUCTION
12908 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303139 | Lahug NHS (Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 070215S00162 | 15HH0076 | 2015-08-26 | 2015-08-14 | 2015-08-26 | 2015-09-28 | 2015-10-26 | BLIMEX CONSTRUCTION & SUPPLY
12909 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303132 | Lusaran NHS | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00185 | 15HH0058 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-18 | BT CONSTRUCTION AND GENERAL SERVICES
12910 | NC 2015 | K10 (2015) | Region VII | Cebu City | 500044 | Mabini Integrated School | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00437 | 15HH0045 | 2015-07-29 | 2015-07-10 | 2015-07-29 | 2015-09-07 | 2015-10-26 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
12911 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 500044 | Mabini Integrated School | CEBU CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00183 | 15HH0036 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-09-07 | 2015-09-18 | GOLDFIN CONSTRUCTION
12912 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303151 | MABOLO NATIONAL HIGH SCHOOL | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15097518.84 |  |  | COMPLETED | 1 |  |  | 070215S00175 | 15HH0077 | 2015-08-26 | 2015-08-14 | 2015-08-26 | 2015-09-16 | 2015-10-02 | PLD CONSTRUCTION
12913 | NC 2015 | K10 (2015) | Region VII | Cebu City | 500230 | Malubog Integrated School | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | reverted | 0 |  |  | 070215S00459
12914 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303146 | Mambaling NHS (Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 070215S00339 | 15HH0086 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-09-07 | 2015-09-18 | GOLDFIN CONSTRUCTION
12915 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303159 | Pardo NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15147518.84 |  |  | COMPLETED | 1 |  |  | 070215S00344 | 15HH0087 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-09-28 | 2015-10-26 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
12916 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 303137 | Paril NHS | CEBU CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00174 | 15HH0037 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-09-07 | 2015-09-18 | GOLDFIN CONSTRUCTION
12917 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303160 | Pit-os NHS | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 070215S00316 | 15HH0074 | 2015-08-26 | 2015-08-14 | 2015-08-26 | 2015-09-24 | 2015-10-05 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
12918 | NC 2015 | SHS (2015) | Region VII | Cebu City | 312515 | Quiot High School | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15347518.84 |  |  | COMPLETED | 1
12919 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303161 | Ramon Duterte Memorial NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31402890.27 |  |  | COMPLETED | 1 |  |  | 070215S00327 | 15HH0092 | 2015-09-14 | 2015-09-02 | 2015-09-14 | 2015-10-14 | 2015-10-19 | GOLDFIN CONSTRUCTION
12920 | NC 2015 | K10 (2015) | Region VII | Cebu City | 119930 | Regino Mercado ES | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | reverted | 0 |  |  | 070215S00467
12921 | NC 2015 | SHS (2015) | Region VII | Cebu City |  | SHS within Agsungot ES | CEBU CITY (Capital) | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10877343 |  |  | COMPLETED | 1
12922 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 500222 | Sirao Integrated School | CEBU CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00173 | 15HH0055 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-11 | REBECCA NAJEEBA CONSTRUCTION & DEVELOPMENT
12923 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303140 | Talamban NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15197518.84 |  |  | Reverted | 0
12924 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303140 | Talamban NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 16 | 4STY16CL | 2015 ADDITIONAL FUND BATCH 9 | 11354950.58 |  |  | COMPLETED | 1
12925 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 500227 | Taptap IS | CEBU CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00171 | 15HH0056 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-11 | REBECCA NAJEEBA CONSTRUCTION & DEVELOPMENT
12926 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303155 | Tejero NHS (Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15097518.84 |  |  | Reverted | 0
12927 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303155 | Tejero NHS (Night) | CEBU CITY (Capital) | 1 | 1 | 20 | 4STY20CL | 2015 ADDITIONAL FUND BATCH 9 | 15855371.43 |  |  | COMPLETED | 1
12928 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303165 | Vicente Cosido NHS (Cambinocot NHS) | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00335 | 15HH0047 | 2015-07-29 | 2015-07-10 | 2015-07-29 | 2015-08-12 | 2015-09-14 | BT CONSTRUCTION AND GENERAL SERVICES
12929 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303156 | Zapatera NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11177342.5917 |  |  | COMPLETED | 1 |  |  | 070215S00312 | 15HH0049 | 2015-07-22 | 2015-07-10 | 2015-07-22 | 2015-08-12 | 2015-08-24 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
12930 | NC 2015 | SHS (2015) | Region VII | Cebu City | 312513 | ALASKA HS | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15097518.84 |  |  | COMPLETED | 1 |  |  | 070215S00170 | 15HH0079 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-09-07 | 2015-09-18 | GOLDFIN CONSTRUCTION
12931 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 312502 | Babag HS | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00251 | 15HH0051 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-18 | JJ & JM CONSTRUCTION & GENERAL SERVICES (FORMERLY
12932 | NC 2015 | K10 (2015) | Region VII | Cebu City | 119867 | Bitlang ES | CEBU CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00440 | 15HH0044 | 2015-07-29 | 2015-07-10 | 2015-07-29 | 2015-08-10 | 2015-08-26 | RIKDA CONSTRUCTION & DEVELOPMENT CORPORATION
12933 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 312509 | Bitlang National High School | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00168 | 15HH0038 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-07-20 | 2015-07-28 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
12934 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303143 | Bulacao Community HS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15147518.84 |  |  | COMPLETED | 1
12935 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 500229 | Cantipla IS | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00166 | 15HH0039 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-07-20 | 2015-07-28 | CEBU HAYDTER CONSTRUCTION
12936 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303141 | Cebu City National Science HS | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15097518.84 |  |  | COMPLETED | 1 |  |  | 070215S00165 | 15HH0081 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-09-07 | 2015-09-18 | SB & T CONSTRUCTION
12937 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303150 | Don Sergio Osme¤a, Sr. Memorial HS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15147518.84 |  |  | COMPLETED | 1
12938 | NC 2015 | TECHVOC (2015) | Region VII | Cebu City | 303150 | Don Sergio Osme¤a, Sr. Memorial HS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2679549.27 |  |  | COMPLETED | 1
12939 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 312504 | Dr. Emilio Osmena HS | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00207 | 15HH0052 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-04 | 2015-09-14 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
12940 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 303144 | First High School for the Hearing Impaired | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00176 | 15HH0040 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-07-20 | 2015-07-28 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
12941 | NC 2015 | K10 (2015) | Region VII | Cebu City | 119907 | Inayawan ES | CEBU CITY (Capital) | 2 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26552469.42 |  |  | COMPLETED | 1 |  |  | 070215S00481 | 15HH0100 | 2015-09-22 | 2015-09-10 | 2015-09-22 | 2015-10-22 |  | WTG CONSTRUCTION & DEVELOPMENT CORPORATION
12942 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303145 | Inayawan NHS (Night) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 070215S00191 | 15HH0083 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-09-28 | 2015-10-26 | GOWIL BUILDERS
12943 | NC 2015 | K10 (2015) | Region VII | Cebu City | 119881 | Kalunasan ES | CEBU CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 14971327.92 |  |  | COMPLETED | 1 |  |  | 070215S00458 | 15HH0097 | 2015-09-22 | 2015-09-10 | 2015-09-22 | 2015-10-22
12944 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303162 | OPRRA NHS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10867131.51 |  |  | COMPLETED | 1 |  |  | 070215S00209 | 15HH0067 | 2015-08-24 | 2015-08-12 | 2015-08-24 | 2015-09-04 | 2015-09-18 | SERCHER DEVELOPMENT CORPORATION
12945 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 312507 | Pamutan IS | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00210 | 15HH0041 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-07-20 | 2015-07-28 | JJ & JM CONSTRUCTION & GENERAL SERVICES (FORMERLY
12946 | NC 2015 | K10 (2015) | Region VII | Cebu City | 119914 | Pasil ES | CEBU CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00438 | 15HH0048 | 2015-07-29 | 2015-07-10 | 2015-07-29 | 2015-08-10 | 2015-08-20 | SB & T CONSTRUCTION
12947 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303147 | Pasil NHS (Night) | CEBU CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10667131.51 |  |  | Reverted | 0
12948 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303147 | Pasil NHS (Night) | CEBU CITY (Capital) | 2 | 1 | 12 | 3STY12CL | 2015 ADDITIONAL FUND BATCH 9 | 7405137.28 |  |  | COMPLETED | 1 | [10 empty] | Slow pacing of works
12949 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303148 | Punta Princesa NHS (Night) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15147518.84 |  |  | COMPLETED | 1 |  |  | 070215S00212 | 15HH0084 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-09-28 | 2015-10-26 | JJ & JM CONSTRUCTION & GENERAL SERVICES (FORMERLY
12950 | NC 2015 | K10 (2015) | Region VII | Cebu City | 187501 | Quiot ES | CEBU CITY (Capital) | 2 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | 070215S00489 | 15HH0098 | 2015-09-22 | 2015-09-10 | 2015-09-22 | 2015-10-22
12951 | NC 2015 | TECHVOC (2015) | Region VII | Cebu City | 312515 | Quiot High School | CEBU CITY (Capital) | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | reverted | 0
12952 | NC 2015 | SHS (2015) | Region VII | Cebu City | 344024 | SHS in Bonbon, Cebu City | CEBU CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1
12953 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 312516 | SIBUGAY HS | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00213 | 15HH0053 | 2015-07-30 | 2015-08-07 | 2015-08-12 | 2015-08-16 | 2015-08-20
12954 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 303163 | Sinsin NHS | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00223 | 15HH0042 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-07-20 | 2015-07-28 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
12955 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303164 | Sudlon NHS | CEBU CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10717131.51 |  |  | COMPLETED | 1 |  |  | 070215S00215 | 15HH0068 | 2015-08-24 | 2015-08-12 | 2015-08-24 | 2015-09-16 | 2015-09-18 | GOWIL BUILDERS
12956 | NC 2015 | SHS (2015) | Region VII | CEBU CITY | 500225 | Tabunan Integrated School | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
12957 | NC 2015 | TECHVOC (2015) | Region VII | Cebu City | 500225 | Tabunan Integrated School | CEBU CITY (Capital) | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
12958 | NC 2015 | SHS (2015) | Region VII | Cebu City | 312506 | Tisa HS (Day & Night) (Tisa Night HS) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15147518.84 |  |  | COMPLETED | 1 |  |  | 070215S00217 | 15HH0085 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-10-21 | 2015-10-26 | GOLDFIN CONSTRUCTION
12959 | NC 2015 | K10 (2015) | Region VII | Cebu City | 119871 | Tisa II ES | CEBU CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00439 | 15HH0046 | 2015-07-29 | 2015-07-10 | 2015-07-29 | 2015-08-12 | 2015-08-24 | BLIMEX CONSTRUCTION & SUPPLY
12960 | NC 2015 | SHS (2015) | Region VII | Cebu City | 303149 | Toong NHS (Day) | CEBU CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10767131.51 |  |  | COMPLETED | 1 |  |  | 070215S00194 | 15HH0066 | 2015-08-24 | 2015-08-12 | 2015-08-24 | 2015-09-04 | 2015-09-18 | SERCHER DEVELOPMENT CORPORATION
12961 | NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 325301 | Alpaco NHS | CITY OF NAGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1
12962 | NC 2015 | K10 (2015) | Region VII | City of Naga, Cebu | 119503 | Balirong ES | CITY OF NAGA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | reverted | 0 |  |  | 070215S00441 | 15-HE-0088 | 2015-07-15 | 2015-07-16
12963 | NC 2015 | K10 (2015) | Region VII | City of Naga, Cebu | 325309 | Cabuan National High School | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00442 | 15-HE-0089 | 2015-07-15 | 2015-07-16 | 2015-09-15 | 2015-09-21 | 2015-09-28 | MAP ALVIOLA CONSTRUCTION
12964 | NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 303002 | Don Emilio Canonigo Memorial NHS | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6349337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00196 | 15-HE-0050 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-07-10 | GENETIAN BUILDERS
12965 | NC 2015 | K10 (2015) | Region VII | City of Naga, Cebu | 119506 | Inayagan Elem. School | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00487 | 15-HE-0117 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | MPJR BUILDERS COMPANY
12966 | NC 2015 | K10 (2015) | Region VII | City of Naga, Cebu | 187030 | Inoburan ES | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00485 | 15-HE-0119 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | GENETIAN BUILDERS
12967 | NC 2015 | K10 (2015) | Region VII | City of Naga, Cebu | 119518 | Langtad ES | CITY OF NAGA | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 070215S00488 | 15-HE-0116 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | MPJR BUILDERS COMPANY
12968 | NC 2015 | K10 (2015) | Region VII | City of Naga, Cebu | 119519 | Lutac ES | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00486 | 15-HE-0118 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | GENETIAN BUILDERS
12969 | NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 303065 | Naga NHS | CITY OF NAGA | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15141327.92 |  |  | COMPLETED | 1
12970 | NC 2015 | TECHVOC (2015) | Region VII | City of Naga, Cebu | 303065 | Naga NHS | CITY OF NAGA | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
12971 | NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 312437 | Naga SPED Center- High School | CITY OF NAGA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00199 | 15-HE-0053 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-08-13 | QUIRANTE CONSTRUCTION
12972 | NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 325303 | Tinaan NHS | CITY OF NAGA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00200 | 15-HE-0054 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-07-10 | QUIRANTE CONSTRUCTION
12973 | NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 303120 | Tuyan NHS | CITY OF NAGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 070215S00197 | 15-HE-0051 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-07-10 | GENETIAN BUILDERS
12974 | NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 303121 | Uling NHS | CITY OF NAGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 070215S00198 | 15-HE-0052 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 |  | QUIRANTE CONSTRUCTION
12975 | NC 2015 | K10 (2015) | Region VII | Danao City | 322007 | Baliang National High School | DANAO CITY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00414 | 15HI0067 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12976 | NC 2015 | K10 (2015) | Region VII | Danao City | 119360 | Delfin Dawe ES | DANAO CITY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2118606.04 |  |  | COMPLETED | 1 |  |  | 070215S00483 | 15HI0090 | 2015-09-25 | 2015-10-07 | 2015-10-08 | 2015-10-12 | 2015-10-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12977 | NC 2015 | K10 (2015) | Region VII | Danao City | 500041 | Eduardo Gorre Memo. Integrated School | DANAO CITY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00433 | 15HI0068 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | VIRLO CONSTRUCTION
12978 | NC 2015 | SHS (2015) | Region VII | Danao City | 302956 | Estefa O. Monte MNHS (Cabungahan NHS) | DANAO CITY | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10657131.51 |  |  | COMPLETED | 1 |  |  | 070215S00201 | 15HI0078 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12979 | NC 2015 | K10 (2015) | Region VII | Danao City | 322008 | Guinacot Integrated School | DANAO CITY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 070215S00525 | 15HI0091 | 2015-09-23 | 2015-10-05 | 2015-10-06 | 2015-10-10 | 2015-10-14 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12980 | NC 2015 | K10 (2015) | Region VII | Danao City | 119340 | Leona Durano Zamora ES | DANAO CITY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00435 | 15HI0069 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12981 | NC 2015 | K10 (2015) | Region VII | Danao City | 119366 | Maslog Elementary School | DANAO CITY | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00484 | 15HI0088 | 2015-09-25 | 2015-10-07 | 2015-10-08 | 2015-10-12 | 2015-10-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12982 | NC 2015 | SHS (2015) | Region VII | Danao City | 303037 | Maslog National High School | DANAO CITY | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10687131.51 |  |  | COMPLETED | 1 |  |  | 070215S00202 | 15HI0087 | 2015-09-15 | 2015-09-27 | 2015-09-28 | 2015-10-02 | 2015-10-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12983 | NC 2015 | K10 (2015) | Region VII | Danao City | 119354 | Pili ES | DANAO CITY | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00410 | 15HI0080 | 2015-08-22 | 2015-09-03 | 2015-12-28
12984 | NC 2015 | K10 (2015) | Region VII | Danao City | 119341 | Quisol ES | DANAO CITY | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00418 | 15HI0066 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12985 | NC 2015 | SHS (2015) | Region VII | Danao City | 322003 | Ramon M. Durano Sr. Foundation - Science and Technology Education Center | DANAO CITY | 5 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22172343.62 |  |  | COMPLETED | 1 |  |  | 070215S00329 | 15HI0097 | 2015-10-26 | 2015-11-07 | 2015-11-08 | 2015-11-12 | 2015-11-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12986 | NC 2015 | SHS (2015) | Region VII | Danao City | 303039 | Ramon M. Durano Sr. MNHS | DANAO CITY | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10458131.51 |  |  | COMPLETED | 1 |  |  | 070215S00203
12987 | NC 2015 | K10 (2015) | Region VII | Danao City | 322010 | Raymunda B. Hermosilla Integrated School | DANAO CITY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00415 | 15HI0070 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12988 | NC 2015 | K10 (2015) | Region VII | Danao City | 322004 | Sabang NHS | DANAO CITY | 5 | 1 | 15 | 3STY15CL | 2015 K10 BATCH 3 | 21383013.45 |  |  | COMPLETED | 1 |  |  | 070215S00413 | 15HI0096 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-10-31 | 2015-11-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
12989 | NC 2015 | K10 (2015) | Region VII | Danao City | 322006 | Santican National High School | DANAO CITY | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00412 | 15HI0081 | 2015-08-22 | 2015-09-03 | 2015-12-28
12990 | NC 2015 | K10 (2015) | Region VII | Danao City | 322011 | Sta. Rosa Integrated School | DANAO CITY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00425 | 15HI0071 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | VIRLO CONSTRUCTION
12991 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 303176 | Bankal NHS - Maribago HS Ext. | LAPU-LAPU CITY (OPON) | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | reverted | 0
12992 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119972 | Abuno ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | COMPLETED | 1 |  |  | 070215S00480 | 15HN0135 | 2015-09-22 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-29 | EDANNA CONSTRUCTION
12993 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119973 | Agus ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 14971327.92 |  |  | COMPLETED | 1 |  |  | 070215S00477 | 15HN0139 | 2015-09-25 | 2015-10-06 | 2015-10-20 | 2015-10-22 | 2015-11-03 | JJ &J CONSTRUCTION & GENERAL SUPPLY
12994 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303172 | Babag National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
12995 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303172 | Babag National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
12996 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303172 | Babag National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1 | [10 empty] | Already Inspected but with some minor findings. On-going rectification
12997 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 312701 | Babag NHS - Babag Night HS | LAPU-LAPU CITY (OPON) | 6 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | reverted | 0
12998 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303174 | Bankal NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 27102469.42 |  |  | COMPLETED | 1
12999 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303174 | Bankal NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
13000 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119950 | Baring ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00409 | 15HN0117 | 2015-09-09 | 2015-09-16 | 2015-09-28 | 2015-10-05 | 2015-10-14 | JJ &J CONSTRUCTION & GENERAL SUPPLY
13001 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 303182 | Gun-ob Night High School | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | reverted | 0
13002 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119965 | Ibo Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00476 | 15HN0138 | 2015-09-25 | 2015-10-06 | 2015-10-20 | 2015-10-22 | 2015-11-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
13003 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303177 | Lo-ok National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 070215S00205 | 15HN0081 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | GONZALODO ENTERPRISES
13004 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303178 | Mactan NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 070215S00206 | 15HN0097 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | JJ &J CONSTRUCTION & GENERAL SUPPLY
13005 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 303179 | Mactan NHS - Punta Engano HS Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | reverted | 0
13006 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303180 | Marigondon NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 2 | 21783013.45 |  |  | COMPLETED | 1
13007 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303180 | Marigondon NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15121327.92 |  |  | COMPLETED | 1
13008 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303183 | Marigondon NHS - Science Tech. Educ. Center (STEC) Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3867968.78 |  |  | COMPLETED | 1
13009 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303183 | Marigondon NHS - Science Tech. Educ. Center (STEC) Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3667968.78 |  |  | COMPLETED | 1
13010 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303193 | Nemesio-Epifania Taneo MHS (Tingo HS (DE, January 15, 1995) | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 070215S00214 | 15HN0082 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | MANINGO ENTERPRISES
13011 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119980 | PAJAC ELEMENTARY SCHOOL | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 4STY4CL | 2015 K10 BATCH 6 | 6900000 |  |  | COMPLETED | 1 |  |  | 070215S00471 | 15HN0134 | 2015-09-22 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-29 | JJ &J CONSTRUCTION & GENERAL SUPPLY
13012 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303184 | Pajo NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1
13013 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303184 | Pajo NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 9 | 3STY9CL | 2015 ADDITIONAL FUND BATCH 9 | 4454196.41 |  |  | COMPLETED | 1
13014 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 303185 | Pajo NHS - Pajo (Night) HS | LAPU-LAPU CITY (OPON) | 6 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | reverted | 0
13015 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119955 | Pangan-an ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00475 | 15HN0137 | 2015-09-25 | 2015-11-05 | 2015-11-17 | 2015-11-19 | 2015-12-01 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
13016 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119991 | Poblacion PS | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 4STY4CL | 2015 K10 BATCH 6 | 6900000 |  |  | COMPLETED | 1 |  |  | 070215S00479 | 15HN0136 | 2015-09-25 | 2015-10-06 | 2015-10-20 | 2015-10-22 | 2015-11-03 | JJ &J CONSTRUCTION & GENERAL SUPPLY
13017 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119970 | Pusok Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 88509374.48 |  |  | COMPLETED | 1 |  |  | 070215S00474 | 15HN0159 | 2015-11-02 | 2015-11-24 | 2015-11-27 | 2015-12-01 | 2015-12-11 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
13018 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303187 | Pusok NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00193 | 15HN0084 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | EDANNA CONSTRUCTION
13019 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 303188 | Pusok NHS - Pusok (Night) HS | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00422 | 15HN0104 | 2015-08-26 | 2015-09-03 | 2015-09-15 | 2015-09-23 | 2015-10-02 | MANINGO ENTERPRISES
13020 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119971 | Soong ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26552469.42 |  |  | COMPLETED | 1 |  |  | 070215S00482 | 15HN0133 | 2015-09-22 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-29 | GONZALODO ENTERPRISES
13021 | NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303189 | Sta. Rosa NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 | [10 empty] | Inspection of Rectification on September 13,2019
13022 | NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119960 | Talima ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00419 | 15HN0118 | 2015-09-09 | 2015-09-16 | 2015-09-28 | 2015-10-05 | 2015-10-14 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
13023 | NC 2015 | K10 (2015) | Region VII | Mandaue City | 119998 | Basak ES | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 070215S00478 | 15HN0140 | 2015-09-25 | 2015-10-06 | 2015-10-20 | 2015-10-22 | 2015-11-03 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
13024 | NC 2015 | SHS (2015) | Region VII | Mandaue City | 303195 | Canduman NHS | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
13025 | NC 2015 | K10 (2015) | Region VII | Mandaue City | 119994 | Cesar M. Cabahug ES (Looc) | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 3 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00427 | 15HN0119 | 2015-10-13 | 2015-10-06 | 2015-10-28
13026 | NC 2015 | SHS (2015) | Region VII | Mandaue City | 303198 | Jagobiao NHS | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 070215S00219 | 15HN0086 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | PLD CONSTRUCTION
13027 | NC 2015 | SHS (2015) | Region VII | Mandaue City | 303200 | Mandaue City CNHS - Labogon NHS Ext. | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00218 | 15HN0087 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | PLD CONSTRUCTION
13028 | NC 2015 | SHS (2015) | Region VII | Mandaue City | 303199 | Mandaue City Comprehensive NHS | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
13029 | NC 2015 | SHS (2015) | Region VII | MANDAUE CITY | 312806 | Mandaue City School for the Arts | MANDAUE CITY | 6 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0
13030 | NC 2015 | SHS (2015) | Region VII | Mandaue City | 303202 | Subangdaku Tech-Voc HS (Mandaue City CNHS - Subangdaku NHS Ext.) | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10917132 |  |  | COMPLETED | 1 |  |  | 070215S00450 | 15HN0145 | 2015-10-27 | 2015-11-05 | 2015-11-17 | 2015-11-19 | 2015-12-01 | P.B. OBIAL CONSTRUCTION
13031 | NC 2015 | SHS (2015) | Region VII | Mandaue City | 312810 | Tingub High School | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10717131.51 |  |  | COMPLETED | 1 |  |  | 070215S00262 | 15HN0089 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | PLD CONSTRUCTION
13045 | NC 2015 | K10 (2015) | Region VII | Tagbilaran City | 312302 | Cogon HS Evening Class | TAGBILARAN CITY (Capital) | 1 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 3 | 18222268.79 |  |  | reverted | 0 |  |  | 070115S00169 | 15HA0121 | 2015-09-30
13046 | NC 2015 | SHS (2015) | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10437131.51 |  |  | COMPLETED | 1
13047 | NC 2015 | TECHVOC (2015) | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
13048 | NC 2015 | SHS (2015) | Region VII | Tagbilaran City | 302874 | Manga National High School | TAGBILARAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 070115S00115 | 15HA0136 | 2015-10-09 | 2015-09-28 | 2015-10-09 | 2015-10-16 | 2015-11-03 | LM CONSTRUCTION AND GENERAL MARKETING
13049 | NC 2015 | SHS (2015) | Region VII | Tagbilaran City | 302875 | Mansasa National High School | TAGBILARAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
13050 | NC 2015 | SHS (2015) | Region VII | Tagbilaran City | 302876 | Tagbilaran City Science High School | TAGBILARAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070115S00114 | 15HA0134 | 2015-10-09 | 2015-09-28 | 2015-10-09 | 2015-10-15 | 2015-11-09 | LM CONSTRUCTION AND GENERAL MARKETING
13051 | NC 2015 | SHS (2015) | Region VII | Talisay City | 322204 | Bulacao NHS | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00124 | 15-HE-0030 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | QUIRANTE CONSTRUCTION
13052 | NC 2015 | K10 (2015) | Region VII | Talisay City | 119795 | Camp 4 ES | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00393 | 15-HE-0083 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | MAP ALVIOLA CONSTRUCTION
13053 | NC 2015 | K10 (2015) | Region VII | Talisay City | 233505 | Campinsa ES | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Reverted | 0 |  |  | 070215S00469
13054 | NC 2015 | SHS (2015) | Region VII | Talisay City | 302971 | Cansojong NHS | CITY OF TALISAY | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15321327.92 |  |  | REVERTED | 0
13055 | NC 2015 | K10 (2015) | Region VII | Talisay City | 233504 | HAWANAY ES | CITY OF TALISAY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | Reverted | 0 |  |  | 070215S00400 | 15-HE-0084 | 2015-07-15 | 2015-07-16
13056 | NC 2015 | SHS (2015) | Region VII | Talisay City | 303019 | Jaclupan NHS | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1
13057 | NC 2015 | SHS (2015) | Region VII | Talisay City | 322206 | Lagtang Night HS | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00145 | 15-HE-0033 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-07-22 | QUIRANTE CONSTRUCTION
13058 | NC 2015 | SHS (2015) | Region VII | Talisay City | 303040 | Lawaan NHS, Talisay | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00106 | 15-HE-0034 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | QUIRANTE CONSTRUCTION
13059 | NC 2015 | SHS (2015) | Region VII | Talisay City | 322201 | Maghaway NHS | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1
13060 | NC 2015 | SHS (2015) | Region VII | Talisay City | 303056 | Mohon NHS (Mohon Divino Amore NHS) | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00105 | 15-HE-0036 | 2015-06-10 | 2015-06-11 | 2015-09-15 | 2015-09-21 | 2015-09-28 | QUIRANTE CONSTRUCTION
13061 | NC 2015 | SHS (2015) | Region VII | Talisay City | 303020 | Pooc NHS (Jaclupan NHS - Pooc Ext.) | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00104 | 15-HE-0037 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | QUIRANTE CONSTRUCTION
13062 | NC 2015 | SHS (2015) | Region VII | Talisay City | 303088 | San Roque NHS ( Laray NHS - Jaclupan NHS Ext.) | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00102 | 15-HE-0038 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | QUIRANTE CONSTRUCTION
13063 | NC 2015 | SHS (2015) | Region VII | Talisay City | 303111 | Tabunok Night HS | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00101 | 15-HE-0039 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | GOLDFIN CONSTRUCTION
13064 | NC 2015 | SHS (2015) | Region VII | Talisay City | 303113 | Talisay City National High School | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 070215S00091 | 15-HE-0040 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-07-22 | GENETIAN BUILDERS
13065 | NC 2015 | K10 (2015) | Region VII | Talisay City | 312402 | Tanke NHS | CITY OF TALISAY | 1 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 3 | 15121327.92 |  |  | Reverted | 0 |  |  | 070215S00408 | 15-HE-0085 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | ZION CONSTRUCTION(FORMERLY MASTERPIECE CONST. & SU
13066 | NC 2015 | SHS (2015) | Region VII | Talisay City | 322208 | Tapul NHS | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00099 | 15-HE-0041 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-09-15 | QUIRANTE CONSTRUCTION
13067 | NC 2015 | K10 (2015) | Region VII | Talisay City | 119793 | Vicenta A. Manreal ES (VAMES) | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Reverted | 0 |  |  | 070215S00490 | 15-HE-0114 | 2015-08-23 | 2015-08-24
13068 | NC 2015 | K10 (2015) | Region VII | Toledo City | 120741 | Awihao ES | TOLEDO CITY | 3 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 070215S00395 | 15HF0094 | 2015-07-31 | 2015-07-31 | 2015-08-12 | 2015-08-18 | 2015-08-26 | DINAH JANE CONSTRUCTION SUPPLY
13069 | NC 2015 | SHS (2015) | Region VII | Toledo City | 303308 | Bato NHS | TOLEDO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070215S00107 | 15HF0065 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | DINAH JANE CONSTRUCTION SUPPLY
13070 | NC 2015 | SHS (2015) | Region VII | Toledo City | 303310 | Don Andres Soriano NHS | TOLEDO CITY | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 070215S00097 | 15HF0062 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | DINAH JANE CONSTRUCTION SUPPLY
13071 | NC 2015 | SHS (2015) | Region VII | Toledo City | 303311 | General Climaco NHS | TOLEDO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070215S00096 | 15HF0061 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | DINAH JANE CONSTRUCTION SUPPLY
13072 | NC 2015 | K10 (2015) | Region VII | Toledo City | 120729 | Himatungan ES | TOLEDO CITY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | REVERTED | 0 |  |  | 070215S00396
13073 | NC 2015 | K10 (2015) | Region VII | Toledo City | 120719 | Lower Campo 8 ES | TOLEDO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | REVERTED | 0 |  |  | 070215S00398 | 15HF0089
13074 | NC 2015 | SHS (2015) | Region VII | Toledo City | 303318 | LURAY II NATIONAL HIGH SCHOOL (DAY & NIGHT)) | TOLEDO CITY | 3 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15321327.92 |  |  | COMPLETED | 1 |  |  | 070215S00095 | 15HF0071 | 2015-07-23 | 2015-07-23 | 2015-08-04 | 2015-08-10 | 2015-08-14 | HI-TRI DEVELOPMENT CORPORATION
13075 | NC 2015 | K10 (2015) | Region VII | Toledo City | 190501 | Makatol Elementary School | TOLEDO CITY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | REVERTED | 0 |  |  | 070215S00397 | 15HF0098 | [5 empty] | DINAH JANE CONSTRUCTION SUPPLY
13076 | NC 2015 | K10 (2015) | Region VII | Toledo City | 120755 | Poog ES | TOLEDO CITY | 3 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 14971327.92 |  |  | COMPLETED | 1 |  |  | 070215S00500 | 15HF0104 | 2015-08-22 | 2015-08-25 | 2015-09-07 | 2015-10-20 | 2015-10-23 | QUIRANTE CONSTRUCTION
13077 | NC 2015 | K10 (2015) | Region VII | Toledo City | 303315 | Toledo City Science High School | TOLEDO CITY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00394 | 15HF0097 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-26 | 2015-09-02 | DINAH JANE CONSTRUCTION SUPPLY
13078 | NC 2015 | SHS (2015) | Region VII | Toledo City | 303316 | Toledo National Vocational HS | TOLEDO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
13079 | NC 2015 | TECHVOC (2015) | Region VII | Toledo City | 303316 | Toledo National Vocational HS | TOLEDO CITY | 3 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7328647.81 |  |  | COMPLETED | 1
19647 | NC 2016 | K10 | Region VII | Bogo City | 119115 | Anonang Sur Es | City Of Bogo | 4 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1
19648 | NC 2016 | K10 | Region VII | Bogo City | 302933 | Don Potenciano | City Of Bogo | 4 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1
19649 | NC 2016 | K10 | Region VII | Bogo City | 302934 | Jovencio N. Masong Nhs | City Of Bogo | 4 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1
19650 | NC 2016 | SHS | Region VII | Bogo City | 302936 | Libertad Nhs | City Of Bogo | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1
19651 | NC 2016 | K10 | Region VII | Bohol | 302883 | Calape National High School | Calape | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9111461.555 |  |  | Completed | 1
19652 | NC 2016 | SHS | Region VII | Bohol | 302872 | Lourdes Nhs | Panglao | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1
19653 | NC 2016 | TECHVOC | Region VII | Bohol | 302830 | Cangawa Nhs | Buenavista | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
19654 | NC 2016 | SHS | Region VII | Bohol | 302830 | Cangawa Nhs | Buenavista | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
19655 | NC 2016 | TECHVOC | Region VII | Bohol | 302892 | Inabanga Hs- Nabuad | Inabanga | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
19656 | NC 2016 | K10 | Region VII | Bohol |  | Lonoy Ps | Inabanga | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
19657 | NC 2016 | TECHVOC | Region VII | Bohol | 302873 | Mahayag National High School | San Miguel | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
19658 | NC 2016 | TECHVOC | Region VII | Bohol | 302893 | San Jose Nhs | Talibon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
19659 | NC 2016 | SHS | Region VII | Bohol | 302893 | San Jose Nhs | Talibon | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
19660 | NC 2016 | SHS | Region VII | Bohol | 302897 | San Miguel Technical Vocational School | San Miguel | 2 | 1 | 12 | 2STY6CL | BATCH 13 CL | 18042923.11 |  |  | Completed | 1
19661 | NC 2016 | K10 | Region VII | Bohol | 118409 | Tungod Ps | Inabanga | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
19662 | NC 2016 | TECHVOC | Region VII | Bohol | 302809 | Alicia Technical-Voc'L Hs | Alicia | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
19663 | NC 2016 | SHS | Region VII | Bohol | 302884 | Pilar Technical-Vocational Hs | Pilar | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
19664 | NC 2016 | SHS | Region VII | Bohol | 302901 | San Roque National High School | Mabini | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
19665 | NC 2016 | TECHVOC | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | Sierra Bullones | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2656428.32 |  |  | Completed | 1
19666 | NC 2016 | SHS | Region VII | Bohol | 302916 | Valencia Tech-Voc Hs | Valencia | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
19667 | NC 2016 | SHS | Region VII | Carcar City | 302970 | Can-Asujan Nhs | City Of Carcar | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1
19668 | NC 2016 | K10 | Region VII | Carcar City | 119179 | Maximina V. Barangan Es (Mercado) | City Of Carcar | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
19669 | NC 2016 | SHS | Region VII | Cebu | 303093 | Sangat Nhs | San Fernando | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
19670 | NC 2016 | TECHVOC | Region VII | Cebu | 302985 | Argao National High School | Argao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
19671 | NC 2016 | SHS | Region VII | Cebu | 302985 | Argao National High School | Argao | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1
19672 | NC 2016 | SHS | Region VII | Cebu | 302921 | Badian Nhs | Badian | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1
19673 | NC 2016 | SHS | Region VII | Cebu | 302925 | Bala Nhs | Moalboal | 2 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10717131.51 |  |  | Completed | 1
19674 | NC 2016 | TECHVOC | Region VII | Cebu | 302940 | Bitoon Nvhs | Dumanjug | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
19675 | NC 2016 | SHS | Region VII | Cebu | 302940 | Bitoon Nvhs | Dumanjug | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1
19676 | NC 2016 | K10 | Region VII | Cebu | 303124 | Calagasan National High School | Argao | 2 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6520624.0402 |  |  | Completed | 1
19677 | NC 2016 | TECHVOC | Region VII | Cebu | 303124 | Calagasan National High School | Argao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2505000 |  |  | Completed | 1
19678 | NC 2016 | K10 | Region VII | Cebu | 118947 | Colawin Es | Argao | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6650000 |  |  | Completed | 1
19679 | NC 2016 | K10 | Region VII | Cebu | 302997 | Dalaguete National High School | Dalaguete | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1
19680 | NC 2016 | TECHVOC | Region VII | Cebu | 302941 | Dumanjug Nhs | Dumanjug | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
19681 | NC 2016 | TECHVOC | Region VII | Cebu | 303000 | Mantalongon Nhs | Dalaguete | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2445000 |  |  | Completed | 1
19682 | NC 2016 | K10 | Region VII | Cebu | 303000 | Mantalongon Nhs | Dalaguete | 2 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16172138.898 |  |  | Completed | 1
19683 | NC 2016 | K10 | Region VII | Cebu | 303000 | Mantalongon Nhs | Dalaguete | 2 |  | 10 | 2STY10CL | BATCH 13 CL | 12836310.09 |  |  | Completed | 1
19684 | NC 2016 | SHS | Region VII | Cebu | 303098 | Santander Nhs | Santander | 2 | 1 | 12 | 3STY12CL | BATCH 11 CL | 18559207.2002 |  |  | Completed | 1 | [10 empty] | Slow Progress
19685 | NC 2016 | SHS | Region VII | Cebu | 302919 | Aloguinsan Nhs | Aloguinsan | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1
19686 | NC 2016 | SHS | Region VII | Cebu | 302919 | Aloguinsan Nhs | Aloguinsan | 3 |  | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1
19687 | NC 2016 | SHS | Region VII | Cebu | 303069 | Bartolome & Manuela Pañares Mnhs | Barili | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.64 |  |  | Completed | 1
19688 | NC 2016 | SHS | Region VII | Cebu | 303069 | Bartolome & Manuela Pañares Mnhs | Barili | 3 |  | 18 | 3STY9CL | BATCH 9 CL | 30242655.84 |  |  | Completed | 1
19689 | NC 2016 | SHS | Region VII | Cebu | 303069 | Bartolome & Manuela Pañares Mnhs | Barili | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
19690 | NC 2016 | SHS | Region VII | Cebu | 302945 | Buanoy Nhs | Balamban | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31152890.27 |  |  | Completed | 1
19691 | NC 2016 | SHS | Region VII | Cebu | 302945 | Buanoy Nhs | Balamban | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 22182343.62 |  |  | Completed | 1
19692 | NC 2016 | SHS | Region VII | Cebu | 302947 | Gaas Nhs | Balamban | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10567131.51 |  |  | Completed | 1
19693 | NC 2016 | TECHVOC | Region VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | Balamban | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
19694 | NC 2016 | K10 | Region VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | Balamban | 3 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1
19695 | NC 2016 | TECHVOC | Region VII | Cebu | 312453 | Kalangahan Nhs | Tuburan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2758700 |  |  | Completed | 1
19696 | NC 2016 | TECHVOC | Region VII | Cebu | 303029 | Lamac Nhs | Pinamungahan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2808700 |  |  | Completed | 1
19697 | NC 2016 | TECHVOC | Region VII | Cebu | 303044 | Looc Norte Nhs | Asturias | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2470000 |  |  | Completed | 1
19698 | NC 2016 | SHS | Region VII | Cebu | 303078 | Lut-Od Nhs | Pinamungahan | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22352343.62 |  |  | Completed | 1
19699 | NC 2016 | K10 | Region VII | Cebu | 302949 | Nangka National High School | Balamban | 3 | 1 | 24 | 4STY12CL | BATCH 9 CL | 44304687.24 |  |  | Completed | 1
19700 | NC 2016 | SHS | Region VII | Cebu | 303075 | Pinamungajan Nhs | Pinamungahan | 3 | 1 | 36 | 4STY12CL | BATCH 9 CL | 67820975.64 |  |  | Completed | 1
19701 | NC 2016 | TECHVOC | Region VII | Cebu | 303075 | Pinamungajan Nhs | Pinamungahan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
19702 | NC 2016 | SHS | Region VII | Cebu | 312412 | Pinamungajan Nhs - Night | Pinamungahan | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1
19703 | NC 2016 | SHS | Region VII | Cebu | 303097 | Santa Lucia Nhs | Asturias | 3 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
19704 | NC 2016 | TECHVOC | Region VII | Cebu | 312414 | Sta. Rita Nhs | Asturias | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2530000 |  |  | Completed | 1
19705 | NC 2016 | SHS | Region VII | Cebu | 302938 | Bantayan Nhs | Bantayan | 4 | 1 | 20 | 4STY20CL | BATCH 9 CL | 32902890.27 |  |  | Completed | 1
19706 | NC 2016 | SHS | Region VII | Cebu | 302938 | Bantayan Nhs | Bantayan | 4 |  | 16 | 4STY16CL | BATCH 9 CL | 28202469.42 |  |  | Completed | 1
19707 | NC 2016 | SHS | Region VII | Cebu | 302938 | Bantayan Nhs | Bantayan | 4 |  | 8 | 4STY8CL | BATCH 9 CL | 15747518.84 |  |  | Completed | 1
19708 | NC 2016 | TECHVOC | Region VII | Cebu | 302938 | Bantayan Nhs | Bantayan | 4 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5084000 |  |  | Completed | 1
19709 | NC 2016 | K10 | Region VII | Cebu | 119265 | Calape Es | Calape Es | 4 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10650000 |  |  | Completed | 1
19710 | NC 2016 | SHS | Region VII | Cebu | 302995 | Daanbantayan Nhs | Daanbantayan | 4 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31102890.27 |  |  | Completed | 1
19711 | NC 2016 | SHS | Region VII | Cebu | 302995 | Daanbantayan Nhs | Daanbantayan | 4 |  | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1
19712 | NC 2016 | SHS | Region VII | Cebu | 303047 | Madridejos Nhs | Madridejos | 4 | 1 | 40 | 4STY20CL | BATCH 5 CL | 65905780.54 |  |  | Completed | 1
19713 | NC 2016 | SHS | Region VII | Cebu | 312409 | Patao Nhs | Bantayan | 4 | 1 | 20 | 4STY20CL | BATCH 5 CL | 32902890.27 |  |  | Completed | 1
19714 | NC 2016 | SHS | Region VII | Cebu | 312409 | Patao Nhs | Bantayan | 4 |  | 9 | 3STY9CL | BATCH 5 CL | 16011327.92 |  |  | Completed | 1
19715 | NC 2016 | TECHVOC | Region VII | Cebu | 312409 | Patao Nhs | Bantayan | 4 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 5110000 |  |  | Completed | 1
19716 | NC 2016 | K10 | Region VII | Cebu | 303087 | San Remigio Nhs | San Remigio | 4 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1
19717 | NC 2016 | K10 | Region VII | Cebu | 303087 | San Remigio Nhs | San Remigio | 4 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
19718 | NC 2016 | TECHVOC | Region VII | Cebu | 303087 | San Remigio Nhs | San Remigio | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1
19719 | NC 2016 | SHS | Region VII | Cebu | 303094 | Santa Fe Nhs | Santa Fe | 4 | 1 | 16 | 4STY8CL | BATCH 5 CL | 31495037.68 |  |  | Completed | 1
19720 | NC 2016 | TECHVOC | Region VII | Cebu | 303094 | Santa Fe Nhs | Santa Fe | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2550000 |  |  | Completed | 1
19721 | NC 2016 | SHS | Region VII | Cebu | 312476 | Sulangan Is | Bantayan | 4 | 1 | 8 | 4STY8CL | BATCH 5 CL | 15747518.84 |  |  | Completed | 1
19722 | NC 2016 | SHS | Region VII | Cebu | 303091 | Arcelo Mnhs | Liloan | 5 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62305780.54 |  |  | Completed | 1 |  |  |  | 16HI0038 | [5 empty] | ARN BUILDERS
19723 | NC 2016 | SHS | Region VII | Cebu | 303091 | Arcelo Mnhs | Liloan | 5 |  | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16HI0039 | [5 empty] | ARN BUILDERS
19724 | NC 2016 | SHS | Region VII | Cebu | 302968 | Cabonga-An Nhs | San Francisco | 5 | 1 | 16 | 4STY16CL | BATCH 11 CL | 28002469.42 |  |  | Completed | 1 |  |  |  | 16HI0052 | [5 empty] | AA MASONG CONSTRUCTION
19725 | NC 2016 | TECHVOC | Region VII | Cebu | 302968 | Cabonga-An Nhs | San Francisco | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  |  | 16HI0041 | [5 empty] | YES CONSTRUCTION
19726 | NC 2016 | SHS | Region VII | Cebu | 302967 | Camotes National High School | San Francisco | 5 | 1 | 20 | 4STY20CL | BATCH 11 CL | 32602890.27 |  |  | Completed | 1 |  |  |  | 16HI0051 | [5 empty] | ARN BUILDERS
19727 | NC 2016 | TECHVOC | Region VII | Cebu | 302967 | Camotes National High School | San Francisco | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  |  | 16HI0040 | [5 empty] | YES CONSTRUCTION
19728 | NC 2016 | SHS | Region VII | Cebu | 302967 | Camotes National High School | San Francisco | 5 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10417131.51 |  |  | Completed | 1 |  |  |  | 16HI0069 | [5 empty] | C. LARA CONSTRUCTION
19729 | NC 2016 | SHS | Region VII | Cebu | 119196 | Carmen Nhs-Day To Luyang Es | Carmen | 5 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62285780.54 |  |  | Completed | 1 |  |  |  | 17HI0043 | [5 empty] | PRAGMATIC DEV'T. CONST. CORP
19730 | NC 2016 | SHS | Region VII | Cebu | 302978 | Catmon Nhs | Catmon | 5 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8214965.05 |  |  | Completed | 1 |  |  |  | 16HI0070 | [5 empty] | YES CONSTRUCTION
19731 | NC 2016 | K10 | Region VII | Cebu | 119226 | Compostela National High School(Day Class) To Compostela Cs | Compostela | 5 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62205780.54 |  |  | Completed | 1 |  |  |  | 17HI0042 | [5 empty] | EDISON DEVELOPMENT CORP
19732 | NC 2016 | TECHVOC | Region VII | Cebu | 119226 | Compostela National High School(Day Class) To Compostela Cs | Compostela | 5 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4860000 |  |  | Completed | 1 |  |  |  | 17HI0053 | [5 empty] | BT CONSTRUCTION
19733 | NC 2016 | SHS | Region VII | Cebu | 303109 | Liki Nhs | Sogod | 5 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14977518.84 |  |  | Completed | 1 |  |  |  | 16HI0049 | [5 empty] | JO BUILDERS | Slow Progress
19734 | NC 2016 | TECHVOC | Region VII | Cebu | 303109 | Liki Nhs | Sogod | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2460000 |  |  | Completed | 1 |  |  |  | 16HI0031 | [5 empty] | FIRST GRANDUER BUILDERS
19735 | NC 2016 | SHS | Region VII | Cebu | 119419 | Liloan Nhs To Suba Es | Liloan | 5 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16HI0067 | [5 empty] | DUROS DEVELOPMENT CORP.
19736 | NC 2016 | SHS | Region VII | Cebu | 303009 | Zosimo E. Fabroa Mnhs | Poro | 5 | 1 | 8 | 2STY8CL | BATCH 11 CL | 11387342.59 |  |  | Completed | 1 |  |  |  | 16HI0053 | [5 empty] | BARR STEEL CONSTRUCTION
19737 | NC 2016 | SHS | Region VII | Cebu | 303114 | Tayud Nhs | Consolacion | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1 | [10 empty] | Slow Progress
19738 | NC 2016 | SHS | Region VII | Cebu | 302993 | Tugbongan Nhs | Consolacion | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15147518.84 |  |  | Completed | 1
19739 | NC 2016 | K10 | Region VII | Cebu City | 119926 | Agsungot Es | Cebu City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
19740 | NC 2016 | SHS | Region VII | Cebu City | 312502 | Babag Hs | Cebu City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [10 empty] | incomplete (DPWH request additional fund due to site development problem occurred during construction phase)
19741 | NC 2016 | SHS | Region VII | Cebu City | 303152 | Barrio Luz Nhs (Day & Night) | Cebu City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | COMPLETED | 1
19742 | NC 2016 | SHS | Region VII | Cebu City | 303134 | Bonbon Nhs | Cebu City (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9121461.5561 |  |  | Completed | 1
19743 | NC 2016 | TECHVOC | Region VII | Cebu City | 303134 | Bonbon Nhs | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
19744 | NC 2016 | TECHVOC | Region VII | Cebu City | 303143 | Bulacao Community Hs (Day & Night) | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
19745 | NC 2016 | K10 | Region VII | Cebu City | 303143 | Bulacao Community Hs(Day & Night) | Cebu City (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
19746 | NC 2016 | K10 | Region VII | Cebu City | 119891 | Busay Elementary School | Cebu City (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1 | [10 empty] | subject for termination (for re bid) due to MGB report of sinkholes
19747 | NC 2016 | K10 | Region VII | Cebu City | 303138 | Camp Lapu-Lapu Nhs(Day & Night) | Cebu City (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
19748 | NC 2016 | K10 | Region VII | Cebu City | 303153 | City Central Nhs(Day & Night) | Cebu City (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 | [10 empty] | Works has been resume by DPWH started on June 3, 2019
19749 | NC 2016 | K10 | Region VII | Cebu City | 303153 | City Central Nhs(Day & Night) | Cebu City (Capital) | 1 |  | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [10 empty] | Schedule for turnover after rectification works be completed
19750 | NC 2016 | K10 | Region VII | Cebu City | 303142 | Don Carlos A. Gothong Memorial Nhs | Cebu City (Capital) | 2 | 1 | 24 | 4STY12CL | BATCH 9 CL | 45900000 |  |  | Completed | 1
19751 | NC 2016 | TECHVOC | Region VII | Cebu City | 303142 | Don Carlos A. Gothong Memorial Nhs | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
19752 | NC 2016 | SHS | Region VII | Cebu City | 303150 | Don Sergio Osme¤A, Sr. Memorial Hs (Day & Night) | Cebu City (Capital) | 2 | 1 | 32 | 4STY16CL | BATCH 9 CL | 58715432.724 |  |  | Completed | 1
19753 | NC 2016 | TECHVOC | Region VII | Cebu City | 303150 | Don Sergio Osme¤A, Sr. Memorial Hs (Day & Night) | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
19754 | NC 2016 | TECHVOC | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. Nhs (Basak Nhs) | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [10 empty] | Incomplete (only complete based on POW)
19755 | NC 2016 | K10 | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. Nhs(Basak Nhs) | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 29357716.362 |  |  | Completed | 1 | [10 empty] | DPWH follow up/pressure the contractor and gave the contractor an ultimatum or face legal action
19756 | NC 2016 | K10 | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. Nhs(Basak Nhs) | Cebu City (Capital) | 2 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [10 empty] | DPWH follow up/pressure the contractor and gave the contractor an ultimatum or face legal action
19757 | NC 2016 | K10 | Region VII | Cebu City | 119886 | Labangon Elementary School | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [10 empty] | Schedule for turnover after rectification works be completed
19758 | NC 2016 | K10 | Region VII | Cebu City | 303139 | Lahug Nhs(Night) | Cebu City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1
19759 | NC 2016 | SHS | Region VII | Cebu City | 303132 | Lusaran Nhs | Cebu City (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10350000 |  |  | Completed | 1
19760 | NC 2016 | SHS | Region VII | Cebu City | 303158 | Mabini Integrated School | Cebu City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
19761 | NC 2016 | SHS | Region VII | Cebu City | 303151 | Mabolo National High School | Cebu City (Capital) | 1 | 1 | 32 | 4STY16CL | BATCH 9 CL | 58715432.724 |  |  | Completed | 1
19762 | NC 2016 | TECHVOC | Region VII | Cebu City | 303151 | Mabolo National High School | Cebu City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
19763 | NC 2016 | K10 | Region VII | Cebu City | 303162 | Oprra Nhs(Day & Night) | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
19764 | NC 2016 | K10 | Region VII | Cebu City | 312507 | Pamutan Integrated School | Cebu City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [10 empty] | incomplete (DPWH request additional fund due to site development problem occurred during construction phase)
19765 | NC 2016 | K10 | Region VII | Cebu City | 119910 | Pardo Extension Elementary School | Cebu City (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22950000 |  |  | Completed | 1
19766 | NC 2016 | TECHVOC | Region VII | Cebu City | 303159 | Pardo Nhs (Day & Night) | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | REVERTED | 0
19767 | NC 2016 | SHS | Region VII | Cebu City | 303159 | Pardo Nhs (Day & Night) | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 27350000 |  |  | Completed | 1
19768 | NC 2016 | SHS | Region VII | Cebu City | 303137 | Paril Nhs | Cebu City (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
19769 | NC 2016 | K10 | Region VII | Cebu City | 303160 | Pit-Os National High School | Cebu City (Capital) | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1
19770 | NC 2016 | TECHVOC | Region VII | Cebu City | 303160 | Pit-Os National High School | Cebu City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
19771 | NC 2016 | K10 | Region VII | Cebu City |  | Shs In Bonbon, Cebu City | Cebu City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11593844.661 |  |  | Completed | 1
19772 | NC 2016 | SHS | Region VII | Cebu City | 303163 | Sinsin Nhs | Cebu City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
19773 | NC 2016 | TECHVOC | Region VII | Cebu City | 303163 | Sinsin Nhs | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2517000 |  |  | REVERTED | 0 | [10 empty] | Subject for reversion
19774 | NC 2016 | SHS | Region VII | Cebu City | 312501 | Sirao Integrated School | Cebu City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
19775 | NC 2016 | TECHVOC | Region VII | Cebu City | 303164 | Sudlon Nhs | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [10 empty] | Incomplete works despite buffer fund has been downloaded last Dec. 2017
19776 | NC 2016 | SHS | Region VII | Cebu City | 312505 | Tabunan Integrated School | Cebu City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11443844.661 |  |  | Completed | 1
19777 | NC 2016 | SHS | Region VII | Cebu City | 303140 | Talamban Nhs (Day & Night) | Cebu City (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 20550000 |  |  | Completed | 1
19778 | NC 2016 | TECHVOC | Region VII | Cebu City | 303140 | Talamban Nhs (Day & Night) | Cebu City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
19779 | NC 2016 | SHS | Region VII | Cebu City | 500227 | Taptap Is | Cebu City (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11443844.661 |  |  | Completed | 1 | [10 empty] | Incomplete works despite buffer fund has been downloaded last Dec. 2017
19780 | NC 2016 | K10 | Region VII | Cebu City | 303155 | Tejero Nhs(Day & Night) | Cebu City (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1 | [10 empty] | Works has been resume by DPWH started on June 3, 2019
19781 | NC 2016 | K10 | Region VII | Cebu City | 312506 | Tisa High School ( Day & Night) | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
19782 | NC 2016 | K10 | Region VII | Cebu City | 312506 | Tisa High School ( Day & Night) | Cebu City (Capital) | 2 |  | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
19783 | NC 2016 | K10 | Region VII | Danao City | 302956 | Estefa O. Monte Memorial National High School | Danao | 5 | 1 | 6 | 3STY6CL | BATCH 3 CL | 10437131.51 |  |  | Completed | 1 |  |  |  | 16HI0050 | [5 empty] | JO BUILDERS
19784 | NC 2016 | SHS | Region VII | Danao City | 303037 | Maslog National High School |  | 5 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1 |  |  |  | 16HI0047 | [5 empty] | JO BUILDERS
19785 | NC 2016 | K10 | Region VII | Danao City | 322003 | Ramon M. Durano Sr. Foundation - Science & Technology Center | Danao | 5 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28007601.243 |  |  | Completed | 1 |  |  |  | 16HI0030 | [5 empty] | SAN NARCISO BUILDERS
19786 | NC 2016 | K10 | Region VII | Danao City | 303039 | Ramon M. Durano Sr. Memorial National High School | Danao | 5 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15237982.3363 |  |  | Completed | 1 |  |  |  | 16HI0048 | [5 empty] | JO BUILDERS
19787 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 119985 | Babag I Es | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1
19788 | NC 2016 | SHS | Region VII | Lapu-Lapu City | 303172 | Babag National High School | Lapu-Lapu City (Opon) | 6 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1
19789 | NC 2016 | SHS | Region VII | Lapu-Lapu City | 303172 | Babag National High School | Lapu-Lapu City (Opon) | 6 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
19790 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 119974 | Bagong Silang Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
19791 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 119963 | Bankal Es | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | COMPLETED | 1 | [10 empty] | PUNCHLIST HAVE NOT YET BEEN COMPLIED
19792 | NC 2016 | SHS | Region VII | Lapu-Lapu City | 303174 | Bankal National High School | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1
19793 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 119975 | Basak Es | Lapu-Lapu City (Opon) | 6 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1
19794 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 119964 | Buaya Elementary School | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1
19795 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 119987 | Canjulao Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
19796 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 119977 | Gun-Ob Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
19797 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 303177 | Lo-Ok National High School | Lapu-Lapu City (Opon) | 6 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1
19798 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 119966 | Mactan Air Base Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Reverted | 0
19799 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 303178 | Mactan Nhs | Lapu-Lapu City (Opon) | 6 | 1 | 24 | 4STY12CL | BATCH 9 CL | 39904218.516 |  |  | Completed | 1
19800 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 303178 | Mactan Nhs | Lapu-Lapu City (Opon) | 6 |  | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
19801 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 119979 | Marigondon Elementary School | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28007601.243 |  |  | Completed | 1
19802 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 303180 | Marigondon Nhs | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1
19803 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 303181 | Marigondon Nhs - Basak Night Hs Ext. | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
19804 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 303193 | Nemesio-Epifania Taneo Mhs (Tingo Hs (De, January 15, 1995) | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 20352109.258 |  |  | Completed | 1
19805 | NC 2016 | SHS | Region VII | Lapu-Lapu City | 303184 | Pajo National High School | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1
19806 | NC 2016 | SHS | Region VII | Lapu-Lapu City | 303184 | Pajo National High School | Lapu-Lapu City (Opon) | 6 |  | 16 | 4STY8CL | BATCH 9 CL | 26845533.912 |  |  | Completed | 1
19807 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 119969 | Punta Engano Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
19808 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 303187 | Pusok Nhs | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28007601.243 |  |  | Completed | 1
19809 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 303189 | Sta. Rosa Nhs | Lapu-Lapu City (Opon) | 6 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10817131.51 |  |  | Completed | 1
19810 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 119984 | Sudtonggan Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
19811 | NC 2016 | K10 | Region VII | Lapu-Lapu City | 119962 | Tungasan Es | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22552343.62 |  |  | Completed | 1
19812 | NC 2016 | K10 | Region VII | Mandaue City | 312811 | Banilad Nhs (Cabancalan Nhs Ext.) | Mandaue City | 6 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10882042.74 |  |  | Completed | 1
19813 | NC 2016 | K10 | Region VII | Mandaue City | 120005 | Cabancalan Ii Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1
19814 | NC 2016 | K10 | Region VII | Mandaue City | 303194 | Cabancalan Nhs | Mandaue City | 6 | 1 | 16 | 4STY8CL | BATCH 9 CL | 29795037.68 |  |  | Completed | 1
19815 | NC 2016 | K10 | Region VII | Mandaue City | 120010 | Canduman Es | Mandaue City | 6 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1
19816 | NC 2016 | SHS | Region VII | Mandaue City | 303195 | Canduman Nhs | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15395522.34 |  |  | Completed | 1
19817 | NC 2016 | K10 | Region VII | Mandaue City | 120011 | Casili Night Hs To Casili Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16328864.74 |  |  | Completed | 1 |  |  | P00075842VS | 17HN0075 | [5 empty] | SERCHER DEV'T. CORP.
19818 | NC 2016 | SHS | Region VII | Mandaue City | 303198 | Jagobiao Nhs | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
19819 | NC 2016 | K10 | Region VII | Mandaue City | 312807 | Maguikay Nhs | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
19820 | NC 2016 | SHS | Region VII | Mandaue City | 303200 | Mandaue City Cnhs - Labogon Nhs Ext. | Mandaue City | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23012343.62 |  |  | Completed | 1
19821 | NC 2016 | SHS | Region VII | Mandaue City | 303199 | Mandaue City Comprehensive Nhs | Mandaue City | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 32212890.87 |  |  | Completed | 1
19822 | NC 2016 | K10 | Region VII | Mandaue City | 119997 | Mandaue City Cs | Mandaue City | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
19823 | NC 2016 | K10 | Region VII | Mandaue City | 119997 | Mandaue City Cs | Mandaue City | 6 |  | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
19824 | NC 2016 | K10 | Region VII | Mandaue City | 189001 | Mandaue City Cs Sped Center | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15395522.34 |  |  | Completed | 1
19825 | NC 2016 | SHS | Region VII | Mandaue City | 312809 | Mandaue Sped Center Hs | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15905522.34 |  |  | Completed | 1
19826 | NC 2016 | K10 | Region VII | Mandaue City | 120006 | Subangdaku Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
19827 | NC 2016 | SHS | Region VII | Mandaue City | 303202 | Subangdaku Tech-Voc Hs (Mandaue City Cnhs - Subangdaku Nhs Ext.) | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15905522.34 |  |  | Completed | 1
19828 | NC 2016 | K10 | Region VII | Mandaue City | 120017 | Tabok Es Ii | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
19829 | NC 2016 | K10 | Region VII | Mandaue City | 120007 | Tipolo Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
19830 | NC 2016 | K10 | Region VII | Mandaue City | 120003 | Umapad Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
19854 | NC 2016 | K10 | Region VII | Talisay City | 233503 | Biasong Elementary School | City Of Talisay | 1 | 1 | 6 | 3STY6CL | BATCH 13 CL | 11443844.661 |  |  | Completed | 1
19855 | NC 2016 | K10 | Region VII | Talisay City | 119785 | Borromeo Bros. Elementary School | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15221327.92 |  |  | Completed | 1
19856 | NC 2016 | K10 | Region VII | Talisay City | 322204 | Bulacao National High School | City Of Talisay | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15097518 |  |  | Completed | 1
19857 | NC 2016 | K10 | Region VII | Talisay City | 302971 | Cansojong National High School | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15221327 |  |  | Completed | 1
19858 | NC 2016 | K10 | Region VII | Talisay City | 303019 | Jaclupan National High School | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15421327.92 |  |  | Completed | 1
19859 | NC 2016 | K10 | Region VII | Talisay City | 119800 | Lagtang Elementary School | City Of Talisay | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518 |  |  | Completed | 1
19860 | NC 2016 | K10 | Region VII | Talisay City | 322206 | Lagtang Night High School | City Of Talisay | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10417131 |  |  | Completed | 1
19861 | NC 2016 | K10 | Region VII | Talisay City | 303040 | Lawaan National High School | City Of Talisay | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518 |  |  | Completed | 1
19862 | NC 2016 | K10 | Region VII | Talisay City | 322201 | Maghaway National High School | City Of Talisay | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10517131 |  |  | Completed | 1
19863 | NC 2016 | K10 | Region VII | Talisay City | 322201 | Maghaway National High School | City Of Talisay | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6452000 |  |  | Completed | 1
19864 | NC 2016 | SHS | Region VII | Talisay City | 303056 | Mohon Nhs (Mohon Divino Amore Nhs) | City Of Talisay | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518 |  |  | Completed | 1
19865 | NC 2016 | K10 | Region VII | Talisay City | 119790 | San Roque Elementary School | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327 |  |  | Completed | 1
19866 | NC 2016 | K10 | Region VII | Talisay City | 303088 | San Roque Nhs (Laray Nhs - Jaclupan Nhs Ext.) | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15221327 |  |  | Completed | 1
19867 | NC 2016 | SHS | Region VII | Talisay City | 303113 | Talisay City National High School | City Of Talisay | 1 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26996317.0922 |  |  | Completed | 1
19868 | NC 2016 | SHS | Region VII | Talisay City | 303113 | Talisay City National High School | City Of Talisay | 1 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518 |  |  | Completed | 1
19869 | NC 2016 | SHS | Region VII | Toledo City | 303308 | Bato National High School | Toledo City | 3 | 1 | 24 | 4STY8CL | BATCH 9 CL | 40268300.868 |  |  | Completed | 1
19870 | NC 2016 | K10 | Region VII | Toledo City | 120715 | Cantabaco Elementary School | Toledo City | 3 | 1 | 12 | 2STY12CL | BATCH 13 CL | 14579217.18 |  |  | Completed | 1
19871 | NC 2016 | K10 | Region VII | Toledo City | 303318 | Don Sndres Soriano Nat. High School | Toledo City | 3 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31202890.27 |  |  | Completed | 1
19872 | NC 2016 | K10 | Region VII | Toledo City | 303311 | General Climaco National High School | Toledo City | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1
19873 | NC 2016 | K10 | Region VII | Toledo City | 303311 | General Climaco National High School | Toledo City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13622766.956 |  |  | Completed | 1
19874 | NC 2016 | K10 | Region VII | Toledo City | 303310 | Luray Ii National High School (Day & Night) | Toledo City | 3 |  | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
19875 | NC 2016 | K10 | Region VII | Toledo City | 303310 | Luray Ii National High School (Day & Night) | Toledo City | 3 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
19876 | NC 2016 | K10 | Region VII | Toledo City | 120756 | Sam-Ang Elementary School | Toledo City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5802403.8743 |  |  | Completed | 1
19877 | NC 2016 | SHS | Region VII | Toledo City | 303316 | Toledo National Vocational School | Toledo City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
19878 | NC 2016 | SHS | Region VII | Toledo City | 303316 | Toledo National Vocational School | Toledo City | 3 |  | 28 | 4STY28CL | BATCH 9 CL | 36076151.526 |  |  | Completed | 1
29108 | NC 2017 | SHS | Region VII | Cebu | 302917 | Alcoy National High School | ALCOY | 2 | 1 | 8 | 4STY8CL | BATCH 8 | 17179570.67 |  |  | Completed | 1
29109 | NC 2017 | TVL | Region VII | Cebu | 302917 | Alcoy National High School | ALCOY | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
29110 | NC 2017 | TVL | Region VII | Cebu | 302917 | Alcoy National High School | ALCOY | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
29111 | NC 2017 | TVL | Region VII | Cebu | 302917 | Alcoy National High School | ALCOY | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
29112 | NC 2017 | SHS | Region VII | Cebu | 303025 | Almacen-Torrevillas National High School | MEDELLIN | 4 | 1 | 4 | 2STY4CL | BATCH 8 | 9007915.89 |  |  | Completed | 1
29113 | NC 2017 | TVL | Region VII | Cebu | 303025 | Almacen-Torrevillas National High School | MEDELLIN | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
29114 | NC 2017 | K10 | Region VII | Cebu | 118966 | Asturias Central ES | ASTURIAS | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3817546.25 |  |  | Completed | 1
29115 | NC 2017 | TVL | Region VII | Cebu | 302921 | Badian NHS | BADIAN | 7 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2700000 |  |  | Completed | 1
29131 | NC 2017 | TVL | Region VII | Bohol | 302811 | Baclayon National High School | BACLAYON | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 6778750 |  |  | Completed | 1
29132 | NC 2017 | TVL | Region VII | Bohol | 302811 | Baclayon National High School | BACLAYON | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 6733610 |  |  | Completed | 1
29133 | NC 2017 | TVL | Region VII | Bohol | 302811 | Baclayon National High School | BACLAYON | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 5169500 |  |  | Completed | 1
29134 | NC 2017 | SHS | Region VII | Bohol | 302824 | Mayor A. R. Tuazon Nat'l Sch. of Fisheries | CALAPE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2844149.2 |  |  | Completed | 1
29135 | NC 2017 | TVL | Region VII | Bohol | 302833 | Catigbian NHS | CATIGBIAN | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 5241360 |  |  | Completed | 1
29136 | NC 2017 | K10 | Region VII | Bohol | 118307 | Canayaon ES | GARCIA HERNANDEZ | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 4957321.29 |  |  | Completed | 1
29137 | NC 2017 | K10 | Region VII | Cebu | 119137 | Bagacay Elementary School | BORBON | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0063 | [5 empty] | JO BUILDERS
29138 | NC 2017 | SHS | Region VII | Cebu | 302924 | Bakhawan National High School | DAANBANTAYAN | 4 | 1 | 6 | 3STY6CL | BATCH 14 | 13989515.1 |  |  | Completed | 1 |  |  | P00184497VS-CW1 | 17HD0096 | 2017-08-30 |  | 2017-12-19 |  | 2017-12-27 | P.B OBIAL CONST.
29139 | NC 2017 | SHS | Region VII | Cebu | 302924 | Bakhawan National High School | DAANBANTAYAN | 4 |  | 4 | 2STY4CL | BATCH 14 | 9195901.76 |  |  | Completed | 1
29140 | NC 2017 | K10 | Region VII | Cebu | 119292 | Balud ES | DALAGUETE | 2 | 1 | 6 | 2STY6CL | BATCH 8 | 11716168.02 |  |  | Completed | 1
29141 | NC 2017 | SHS | Region VII | Cebu | 302938 | Bantayan Senior High School | BANTAYAN | 4 | 1 | 12 | 3STY12CL | BATCH 14 | 30827230.61 |  |  | Completed | 1
29142 | NC 2017 | SHS | Region VII | Cebu | 302938 | Bantayan Senior High School | BANTAYAN | 4 |  | 16 | 4STY16CL | BATCH 14 | 38756274.86 |  |  | Completed | 1
29143 | NC 2017 | K10 | Region VII | Cebu | 118943 | Binlod ES | ARGAO | 2 | 1 | 6 | 2STY6CL | BATCH 8 | 11706168.02 |  |  | Completed | 1
29144 | NC 2017 | K10 | Region VII | Cebu | 119210 | Binongkalan ES | CATMON | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0061 | [5 empty] | COCOS TIERRA DEV'T. CORPORATION
29145 | NC 2017 | TVL | Region VII | Cebu | 302940 | Bitoon NVHS | DUMANJUG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
29146 | NC 2017 | K10 | Region VII | Cebu | 118920 | Bogo ES | ARGAO | 2 | 1 | 6 | 3STY6CL | BATCH 8 | 13794515.1 |  |  | Completed | 1
29147 | NC 2017 | K10 | Region VII | Cebu | 118920 | Bogo ES | ARGAO | 2 |  | 6 | 3STY6CL | BATCH 8 | 13794515.1 |  |  | Completed | 1
29148 | NC 2017 | K10 | Region VII | Cebu | 119767 | Bongon ES | TABUELAN | 4 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
29149 | NC 2017 | TVL | Region VII | Cebu | 302945 | Buanoy National High School | BALAMBAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2830352.68 |  |  | Completed | 1
29150 | NC 2017 | TVL | Region VII | Cebu | 302953 | Bulasa NHS | ARGAO | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
29151 | NC 2017 | K10 | Region VII | Cebu | 119696 | Bunlan ES | SANTANDER | 2 | 1 | 6 | 2STY6CL | BATCH 8 | 11711168.02 |  |  | Completed | 1
29152 | NC 2017 | K10 | Region VII | Cebu | 119696 | Bunlan ES | SANTANDER | 2 |  | 6 | 2STY6CL | BATCH 8 | 11711168.02 |  |  | Completed | 1
29153 | NC 2017 | K10 | Region VII | Cebu | 119090 | Cabcaban ES | BARILI | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3876111.86 |  |  | Completed | 1
29154 | NC 2017 | K10 | Region VII | Cebu | 119090 | Cabcaban ES | BARILI | 3 |  | 2 | 1STY2CL | BATCH 4 | 2957536.55 |  |  | Completed | 1
29155 | NC 2017 | K10 | Region VII | Cebu | 119747 | Caduawan ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
29156 | NC 2017 | K10 | Region VII | Cebu | 119265 | Calape ES | DAANBANTAYAN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2919729.9 |  |  | Completed | 1
29157 | NC 2017 | SHS | Region VII | Cebu | 302961 | Calape NHS | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | BATCH 8 | 17159570.67 |  |  | Completed | 1 |  |  | P00177997VS-CW1 | 17HD0077 | 2017-08-30 |  | 2017-11-24 |  | 2017-12-14 | JO BUILDERS
29158 | NC 2017 | SHS | Region VII | Cebu | 302961 | Calape NHS | DAANBANTAYAN | 4 |  | 4 | 2STY4CL | BATCH 8 | 8945901.76 |  |  | Completed | 1
29159 | NC 2017 | K10 | Region VII | Cebu | 119748 | Camoboan ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
29160 | NC 2017 | K10 | Region VII | Cebu | 119749 | Canaocanao ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
29161 | NC 2017 | K10 | Region VII | City of Naga, Cebu | 119524 | Uling ES | CITY OF NAGA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00173477VS-CWI | 17-HE-0131 | 2017-08-07 | 2017-08-14 | 2017-08-29 | 2017-10-18 | 2017-10-24 | A.T. Dumlao Construction
29211 | NC 2017 | TVL | Region VII | Toledo City | 303316 | Toledo National Vocational School | TOLEDO CITY | 3 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 5337013.21 |  |  | Completed | 1
29215 | NC 2017 | SHS | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29216 | NC 2017 | TVL | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 12587337.5 |  |  | Completed | 1
29217 | NC 2017 | SHS | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3099218.54 |  |  | Completed | 1
29218 | NC 2017 | SHS | Region VII | Bohol | 312359 | Katipunan High School | ALICIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29219 | NC 2017 | SHS | Region VII | Bohol | 302813 | Anda HS | ANDA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2863745.92 |  |  | Completed | 1
29220 | NC 2017 | K10 | Region VII | Bohol | 117957 | Candabong ES | ANDA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29221 | NC 2017 | K10 | Region VII | Bohol | 117958 | Casica PS | ANDA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29222 | NC 2017 | K10 | Region VII | Bohol | 117961 | Londag ES | ANDA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29223 | NC 2017 | K10 | Region VII | Bohol | 118013 | Batuan Central ES - Annex | BATUAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29224 | NC 2017 | SHS | Region VII | Bohol | 302815 | Batuan NHS | BATUAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29225 | NC 2017 | TVL | Region VII | Bohol | 302815 | Batuan NHS | BATUAN | 3 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 9176100 |  |  | Completed | 1
29226 | NC 2017 | K10 | Region VII | Bohol | 118015 | Bonifacio ES | BATUAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29227 | NC 2017 | SHS | Region VII | Bohol | 302818 | Bilar NHS | BILAR | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29228 | NC 2017 | K10 | Region VII | Bohol | 118046 | Campagao ES | BILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3159218.54 |  |  | Completed | 1
29229 | NC 2017 | K10 | Region VII | Bohol | 118053 | Roxas PS | BILAR | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29230 | NC 2017 | K10 | Region VII | Bohol | 118054 | Subayon PS | BILAR | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29231 | NC 2017 | K10 | Region VII | Bohol | 118058 | Zamora ES | BILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29232 | NC 2017 | TVL | Region VII | Bohol | 302912 | Anoling National High School | CANDIJAY | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
29233 | NC 2017 | K10 | Region VII | Bohol | 118114 | Candijay Central ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3239218.54 |  |  | Completed | 1
29234 | NC 2017 | SHS | Region VII | Bohol | 302865 | Candijay National High School | CANDIJAY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29235 | NC 2017 | K10 | Region VII | Bohol | 118116 | Cogtong ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3074218.54 |  |  | Completed | 1
29236 | NC 2017 | TVL | Region VII | Bohol | 302866 | Cogtong NHS | CANDIJAY | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
29237 | NC 2017 | K10 | Region VII | Bohol | 118117 | La Union ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3089218.54 |  |  | Completed | 1
29238 | NC 2017 | TVL | Region VII | Bohol | 302864 | La Union NHS | CANDIJAY | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 6117400 |  |  | Completed | 1
29239 | NC 2017 | K10 | Region VII | Bohol | 118118 | Luan ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29240 | NC 2017 | TVL | Region VII | Bohol | 302911 | Tambongan NHS | CANDIJAY | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
29241 | NC 2017 | K10 | Region VII | Bohol | 118138 | El Salvador ES | CARMEN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3029218.54 |  |  | Completed | 1
29242 | NC 2017 | TVL | Region VII | Bohol | 302861 | Francisco L. Adlaon HS | CARMEN | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 6117400 |  |  | Completed | 1
29243 | NC 2017 | K10 | Region VII | Bohol | 118139 | Guadalupe ES | CARMEN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29244 | NC 2017 | K10 | Region VII | Bohol | 118140 | Katipunan ES | CARMEN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3099218.54 |  |  | Completed | 1
29245 | NC 2017 | TVL | Region VII | Bohol | 302860 | Katipunan NHS | CARMEN | 3 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 9632581.68 |  |  | Completed | 1
29246 | NC 2017 | K10 | Region VII | Bohol | 118158 | Vallehermoso ES | CARMEN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29247 | NC 2017 | TVL | Region VII | Bohol | 302832 | Canhayupon NHS | DIMIAO | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
29248 | NC 2017 | TVL | Region VII | Bohol | 302845 | Dimiao NHS | DIMIAO | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3168346.56 |  |  | Completed | 1
29249 | NC 2017 | K10 | Region VII | Bohol | 118277 | Lapsaon ES | DIMIAO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29250 | NC 2017 | SHS | Region VII | Bohol | 312356 | Bangwalog HS | DUERO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29251 | NC 2017 | K10 | Region VII | Bohol | 118302 | Taytay Elementary School | DUERO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29252 | NC 2017 | K10 | Region VII | Bohol | 118310 | Datag ES | GARCIA HERNANDEZ | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29253 | NC 2017 | SHS | Region VII | Bohol | 302852 | Garcia-Hernandez HS | GARCIA HERNANDEZ | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29254 | NC 2017 | TVL | Region VII | Bohol | 302852 | Garcia-Hernandez HS | GARCIA HERNANDEZ | 3 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 9176100 |  |  | COMPLETED | 1
29255 | NC 2017 | K10 | Region VII | Bohol | 118314 | Malinao ES | GARCIA HERNANDEZ | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29256 | NC 2017 | K10 | Region VII | Bohol | 118319 | Tabuan ES | GARCIA HERNANDEZ | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29257 | NC 2017 | K10 | Region VII | Bohol | 118346 | Basdio ES | GUINDULMAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29258 | NC 2017 | K10 | Region VII | Bohol | 118354 | Cansiwang ES | GUINDULMAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29259 | NC 2017 | K10 | Region VII | Bohol | 118355 | Casbu ES | GUINDULMAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29260 | NC 2017 | TVL | Region VII | Bohol | 302834 | Catungawan National High School | GUINDULMAN | 3 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 9932581.68 |  |  | Completed | 1
29261 | NC 2017 | K10 | Region VII | Bohol | 118357 | Guinacot ES | GUINDULMAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29262 | NC 2017 | TVL | Region VII | Bohol | 302878 | Mayuga NHS | GUINDULMAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3058700 |  |  | Completed | 1
29263 | NC 2017 | K10 | Region VII | Bohol | 186516 | Pansul PS | GUINDULMAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29264 | NC 2017 | K10 | Region VII | Bohol | 118363 | Tambis ES | GUINDULMAN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4231623.39 |  |  | Completed | 1
29265 | NC 2017 | K10 | Region VII | Bohol | 118420 | Canjulao ES | JAGNA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29266 | NC 2017 | TVL | Region VII | Bohol | 302849 | Faraon NHS | JAGNA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3360860.56 |  |  | Completed | 1
29267 | NC 2017 | K10 | Region VII | Bohol | 118426 | Larapan ES | JAGNA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29268 | NC 2017 | TVL | Region VII | Bohol | 302870 | Lonoy Heroes MHS | JAGNA | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 6117400 |  |  | Completed | 1
29269 | NC 2017 | TVL | Region VII | Bohol | 302868 | Lila NHS | LILA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3058700 |  |  | Completed | 1
29270 | NC 2017 | K10 | Region VII | Bohol | 118439 | Malinao ES | LILA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29271 | NC 2017 | SHS | Region VII | Bohol | 302867 | Hinawanan NHS | LOAY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2863745.92 |  |  | Completed | 1
29272 | NC 2017 | TVL | Region VII | Bohol | 302867 | Hinawanan NHS | LOAY | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 6421721.12 |  |  | Completed | 1
29273 | NC 2017 | K10 | Region VII | Bohol | 118452 | Tayong ES | LOAY | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29274 | NC 2017 | TVL | Region VII | Bohol | 302826 | Camaya-an NHS | LOBOC | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
29275 | NC 2017 | K10 | Region VII | Bohol | 118502 | Napo Elementary School | LOON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2891384 |  |  | Completed | 1
29276 | NC 2017 | K10 | Region VII | Bohol | 118527 | San Roque ES | MABINI | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3099218.54 |  |  | Completed | 1
29277 | NC 2017 | SHS | Region VII | Bohol | 302901 | San Roque National High School | MABINI | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2863745.92 |  |  | Completed | 1
29278 | NC 2017 | K10 | Region VII | Bohol | 118569 | Buenasuerte ES | PILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3159218.54 |  |  | Completed | 1
29279 | NC 2017 | K10 | Region VII | Bohol | 118574 | Estaca ES | PILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3159218.54 |  |  | Completed | 1
29280 | NC 2017 | K10 | Region VII | Bohol | 118581 | Pilar Central ES | PILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29281 | NC 2017 | SHS | Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29282 | NC 2017 | SHS | Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29283 | NC 2017 | TVL | Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3058700 |  |  | Completed | 1
29284 | NC 2017 | K10 | Region VII | Bohol | 118582 | Rizal ES | PILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29285 | NC 2017 | K10 | Region VII | Bohol | 118584 | San Isidro ES | PILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29286 | NC 2017 | TVL | Region VII | Bohol | 302889 | San Isidro Tech-Voc HS | PILAR | 3 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 12234800 |  |  | Completed | 1
29287 | NC 2017 | K10 | Region VII | Bohol | 118660 | Bayawahan ES | SEVILLA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3099218.54 |  |  | Completed | 1
29288 | NC 2017 | K10 | Region VII | Bohol | 118665 | Cambagui ES | SEVILLA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29289 | NC 2017 | SHS | Region VII | Bohol | 302904 | Cambagui-Calinginan Norte National HS | SEVILLA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29290 | NC 2017 | TVL | Region VII | Bohol | 302904 | Cambagui-Calinginan Norte National HS | SEVILLA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
29291 | NC 2017 | K10 | Region VII | Bohol | 118672 | Sevilla Central ES | SEVILLA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29292 | NC 2017 | K10 | Region VII | Bohol | 118673 | Abachanan ES | SIERRA BULLONES | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29293 | NC 2017 | TVL | Region VII | Bohol | 302848 | Dusita High School | SIERRA BULLONES | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 6521721.12 |  |  | Completed | 1
29294 | NC 2017 | K10 | Region VII | Bohol | 118691 | San Jose Elementary School | SIERRA BULLONES | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29295 | NC 2017 | SHS | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
29296 | NC 2017 | TVL | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3260860.56 |  |  | Completed | 1
29297 | NC 2017 | K10 | Region VII | Bohol | 118848 | Anonang ES | VALENCIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29298 | NC 2017 | K10 | Region VII | Bohol | 118852 | Canduao ES | VALENCIA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
29299 | NC 2017 | K10 | Region VII | Bohol | 118856 | Lantang ES | VALENCIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29300 | NC 2017 | K10 | Region VII | Bohol | 118857 | Limokon ES | VALENCIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29301 | NC 2017 | TVL | Region VII | Bohol | 312311 | Mayor Pablo O. Lim MHS | VALENCIA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
29302 | NC 2017 | K10 | Region VII | Bohol | 186508 | Taculing ES | VALENCIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
29303 | NC 2017 | TVL | Region VII | Carcar City | 303016 | Maximino Noel Memorial National High School | CITY OF CARCAR | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3386180 |  |  | Completed | 1
29304 | NC 2017 | TVL | Region VII | Carcar City | 303082 | ROBERTO E. SATO MEMORIAL NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3478800 |  |  | Completed | 1
29305 | NC 2017 | TVL | Region VII | Carcar City | 343971 | Tuyom Senior High School | CITY OF CARCAR | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3386180 |  |  | Completed | 1
29306 | NC 2017 | TVL | Region VII | Carcar City | 303126 | Valencia National Vocational HS | CITY OF CARCAR | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3386180 |  |  | Completed | 1
29307 | NC 2017 | TVL | Region VII | Cebu | 312469 | Cansaloay Integrated School | OSLOB | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
29319 | NC 2017 | TVL | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
29320 | NC 2017 | TVL | Region VII | Bohol | 312312 | Panghagban HS | BUENAVISTA | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
29321 | NC 2017 | TVL | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
29322 | NC 2017 | TVL | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
29323 | NC 2017 | TVL | Region VII | Bohol | 302879 | Nahawan NHS | CLARIN | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
29324 | NC 2017 | TVL | Region VII | Bohol | 302879 | Nahawan NHS | CLARIN | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
29325 | NC 2017 | TVL | Region VII | Bohol | 302840 | Dagohoy NHS / Integrated SHS | DAGOHOY | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
29326 | NC 2017 | TVL | Region VII | Bohol | 312321 | San Miguel-Puertos HS | DAGOHOY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
29327 | NC 2017 | TVL | Region VII | Bohol | 312321 | San Miguel-Puertos HS | DAGOHOY | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
29328 | NC 2017 | TVL | Region VII | Bohol | 302842 | Cantubod NHS | DANAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
29329 | NC 2017 | TVL | Region VII | Bohol | 302842 | Cantubod NHS | DANAO | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
29330 | NC 2017 | TVL | Region VII | Bohol | 302841 | Danao NHS | DANAO | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
29331 | NC 2017 | TVL | Region VII | Bohol | 302844 | Taming NHS | DANAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
29332 | NC 2017 | TVL | Region VII | Bohol | 302844 | Taming NHS | DANAO | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
29333 | NC 2017 | TVL | Region VII | Bohol | 302892 | Inabanga HS- Nabuad | INABANGA | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
29334 | NC 2017 | TVL | Region VII | Bohol | 302891 | San Jose National High School | INABANGA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
29335 | NC 2017 | TVL | Region VII | Bohol | 302891 | San Jose National High School | INABANGA | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
29336 | NC 2017 | TVL | Region VII | Bohol | 302827 | Campao Oriental High School | JETAFE | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
29337 | NC 2017 | TVL | Region VII | Bohol | 302828 | Handumon NHS | JETAFE | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
29338 | NC 2017 | TVL | Region VII | Bohol | 302808 | Aguining National High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
29339 | NC 2017 | TVL | Region VII | Bohol | 312335 | Basiao High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
29340 | NC 2017 | TVL | Region VII | Bohol | 312324 | Bonbonon High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
29341 | NC 2017 | TVL | Region VII | Bohol | 312324 | Bonbonon High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
29342 | NC 2017 | TVL | Region VII | Bohol | 312353 | Campamanog HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
29343 | NC 2017 | TVL | Region VII | Bohol | 312353 | Campamanog HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
29344 | NC 2017 | TVL | Region VII | Bohol | 312325 | Gaus High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
29345 | NC 2017 | TVL | Region VII | Bohol | 312303 | Mayor Inocencio B. Mendez HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
29346 | NC 2017 | TVL | Region VII | Bohol | 302888 | Eugenio V. Amores MHS | SAGBAYAN (BORJA) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
29347 | NC 2017 | TVL | Region VII | Bohol | 312309 | JAPeR Memorial High School | SAGBAYAN (BORJA) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
29348 | NC 2017 | TVL | Region VII | Bohol | 302873 | Mahayag National High School | SAN MIGUEL | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
29349 | NC 2017 | TVL | Region VII | Bohol | 312313 | Mayor Catalino Y. Casoyla MHS | TALIBON | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
29350 | NC 2017 | TVL | Region VII | Bohol | 302895 | President Carlos P. Garcia Memorial High School | TALIBON | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
29351 | NC 2017 | TVL | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 14780000 |  |  | Completed | 1
29352 | NC 2017 | TVL | Region VII | Bohol | 302896 | Sikatuna Nat'l Agricultural HS | TALIBON | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
29353 | NC 2017 | TVL | Region VII | Bohol | 302858 | Hinlayagan NHS | TRINIDAD | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
29354 | NC 2017 | K10 | Region VII | Cebu | 118925 | Cansuje ES | ARGAO | 2 | 1 | 8 | 2STY8CL | BATCH 8 | 17064790.26 |  |  | Completed | 1
29355 | NC 2017 | TVL | Region VII | Cebu | 302975 | Cantumog NHS | CARMEN | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0144 | [5 empty] | YES CONSTRUCTION
29356 | NC 2017 | TVL | Region VII | Cebu | 302975 | Cantumog NHS | CARMEN | 5 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1 |  |  |  | 17HI0143 | [5 empty] | JOHN ARNE CONSTRUCTION
29357 | NC 2017 | TVL | Region VII | Cebu | 302984 | Colawin NHS | ARGAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
29358 | NC 2017 | SHS | Region VII | Cebu | 302984 | Colawin NHS | ARGAO | 2 |  | 6 | 2STY6CL | BATCH 8 | 11716168.02 |  |  | Completed | 1
29359 | NC 2017 | K10 | Region VII | Cebu | 119831 | Colonia Central ES | TUBURAN | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2885356.85 |  |  | Completed | 1
29360 | NC 2017 | TVL | Region VII | Cebu | 302987 | Colonia NHS | TUBURAN | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 5493092.36 |  |  | Completed | 1
29361 | NC 2017 | TVL | Region VII | Cebu | 302955 | Cordova NHS | CORDOBA | 6 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2613745.92 |  |  | Completed | 1
29362 | NC 2017 | K10 | Region VII | Cebu | 119040 | Cornelio C. Melgar Elementary School | BALAMBAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2775955.98 |  |  | Completed | 1
29363 | NC 2017 | SHS | Region VII | Cebu | 302995 | Daanbantayan National High School | DAANBANTAYAN | 4 | 1 | 3 | 1STY3CL | BATCH 8 | 3768435.02 |  |  | Completed | 1
29364 | NC 2017 | K10 | Region VII | Cebu | 119298 | Dalaguete Central ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | BATCH 8 | 8985901.76 |  |  | Completed | 1
29365 | NC 2017 | SHS | Region VII | Cebu | 302997 | Dalaguete National High School | DALAGUETE | 2 | 1 | 6 | 3STY6CL | BATCH 8 | 13739515.1 |  |  | Completed | 1
29366 | NC 2017 | SHS | Region VII | Cebu | 302997 | Dalaguete NHS | DALAGUETE | 2 | 1 | 16 | 4STY16CL | BATCH 8 | 37070737.96 |  |  | Completed | 1
29367 | NC 2017 | K10 | Region VII | Cebu | 119459 | Dalingding Sur ES | MEDELLIN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
29368 | NC 2017 | TVL | Region VII | Cebu | 303005 | Doña Liling Neis Negapatan NHS | TABOGON | 4 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 5400000 |  |  | Completed | 1
29369 | NC 2017 | K10 | Region VII | Cebu | 119299 | Dugyan ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | BATCH 8 | 8975901.76 |  |  | Completed | 1
29370 | NC 2017 | SHS | Region VII | Cebu | 302941 | Dumanjug NHS | DUMANJUG | 2 | 1 | 8 | 4STY8CL | BATCH 8 | 17159570.67 |  |  | Completed | 1
29371 | NC 2017 | TVL | Region VII | Cebu | 302941 | Dumanjug NHS | DUMANJUG | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
29372 | NC 2017 | K10 | Region VII | Cebu | 119091 | Giloctog ES | BARILI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2995221.99 |  |  | Completed | 1
29373 | NC 2017 | K10 | Region VII | Cebu | 119218 | Ginabukan ES | CATMON | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0060 | [5 empty] | COCOS TIERRA DEV'T. CORP
29374 | NC 2017 | TVL | Region VII | Cebu | 303070 | Guibuangan NHS | BARILI | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2904389.71 |  |  | Completed | 1
29375 | NC 2017 | TVL | Region VII | Cebu | 303018 | Guiwanon NHS | GINATILAN | 7 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2607211.55 |  |  | Completed | 1
29376 | NC 2017 | K10 | Region VII | Cebu | 119623 | Ilaya ES | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2673745.92 |  |  | Completed | 1
29377 | NC 2017 | K10 | Region VII | Cebu | 119751 | Ilihan IS | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
29378 | NC 2017 | K10 | Region VII | Cebu | 119751 | Ilihan IS | TABOGON | 4 |  | 6 | 2STY6CL | BATCH 8 | 11686168.02 |  |  | Completed | 1
29379 | NC 2017 | K10 | Region VII | Cebu | 119751 | Ilihan IS | TABOGON | 4 |  | 4 | 2STY4CL | BATCH 8 | 9055901.75 |  |  | Completed | 1
29380 | NC 2017 | TVL | Region VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | BALAMBAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2830352.68 |  |  | Completed | 1
29381 | NC 2017 | SHS | Region VII | Cebu | 303103 | Juan Pamplona NHS | TABUELAN | 4 | 1 | 6 | 3STY6CL | BATCH 8 | 14452527.13 |  |  | Completed | 1 |  |  | P00178018VS-CW1 | 17HD0082 | 2017-08-30 |  | 2017-11-24 |  | 2017-12-12 | PAGAY CONST.
29382 | NC 2017 | TVL | Region VII | Cebu | 303022 | Julian Enad MNHS | SIBONGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2730000 |  |  | Completed | 1 |  |  | P00181947VS-CW1 | 17-HE-0171 | 2017-11-18 | 2017-11-23 | 2017-12-05 | 2017-12-11 | 2017-12-22 | V.O. Chupuico Construction
29383 | NC 2017 | K10 | Region VII | Cebu | 119769 | Kabalawan ES | TABUELAN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
29384 | NC 2017 | K10 | Region VII | Cebu | 119753 | Kal-anan ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
29385 | NC 2017 | TVL | Region VII | Cebu | 312453 | Kalangahan NHS | TUBURAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2960364.26 |  |  | Completed | 1
29386 | NC 2017 | TVL | Region VII | Cebu | 303024 | Kawit NHS | MEDELLIN | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
29387 | NC 2017 | TVL | Region VII | Cebu | 303028 | Kinatarcan NHS | SANTA FE | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2800000 |  |  | Completed | 1
29388 | NC 2017 | K10 | Region VII | Cebu | 119754 | Labangon ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
29389 | NC 2017 | TVL | Region VII | Cebu | 303029 | Lamac National High School | PINAMUNGAHAN | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2882474.81 |  |  | Completed | 1
29390 | NC 2017 | TVL | Region VII | Cebu | 303031 | Lanao NHS, Pilar | PILAR | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0154 | [5 empty] | JOHN ARNE CONSTRUCTION
29391 | NC 2017 | TVL | Region VII | Cebu | 303031 | Lanao NHS, Pilar | PILAR | 5 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1 |  |  |  | 17HI0153 | [5 empty] | JOHN ARNE CONSTRUCTION
29392 | NC 2017 | K10 | Region VII | Cebu | 118930 | Langtad ES | ARGAO | 2 | 1 | 4 | 2STY4CL | BATCH 8 | 8975901.76 |  |  | Completed | 1
29393 | NC 2017 | K10 | Region VII | Cebu | 119678 | Libaong ES | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
29394 | NC 2017 | K10 | Region VII | Cebu | 119755 | Libjo ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
29395 | NC 2017 | K10 | Region VII | Cebu | 119282 | Logon ES | DAANBANTAYAN | 4 | 1 | 6 | 3STY6CL | BATCH 8 | 14426490.85 |  |  | Completed | 1 |  |  | P00177995VS-CW1 | 17HD0076 | 2017-08-30 |  | 2017-11-24 |  | 2017-12-14 | JO BUILDERS
29396 | NC 2017 | TVL | Region VII | Cebu | 119283 | Looc PS | DAANBANTAYAN | 4 | 1 | 2 | 2STY2CL | BATCH 8 | 6290008.53 |  |  | Completed | 1
29397 | NC 2017 | TVL | Region VII | Cebu | 303122 | Lorenzo C. Tanza Memorial National High School | SAN FRANCISCO | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0148 | [5 empty] | BL PANGAN CONSTRUCTION
29398 | NC 2017 | K10 | Region VII | Cebu | 119736 | Lubo ES | SOGOD | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0062 | [5 empty] | JO BUILDERS
29399 | NC 2017 | TVL | Region VII | Cebu | 303008 | Luciano B. Rama Sr. MNHS | PORO | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0149 | [5 empty] | FIRST BUILDERS AND DEVELOPERS
29400 | NC 2017 | K10 | Region VII | Cebu | 119132 | Lunop ES | BOLJOON | 2 | 1 | 4 | 2STY4CL | BATCH 8 | 8975901.76 |  |  | Completed | 1
29401 | NC 2017 | TVL | Region VII | Cebu | 303049 | Magsico NHS | SAN FERNANDO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2838000 |  |  | Completed | 1 |  |  | P00181948VS-CW1 | 17-HE-0172 | 2017-11-18 | 2017-11-23 | 2017-12-05 | 2017-12-11 | 2017-12-22 | DT&C Construction
29402 | NC 2017 | K10 | Region VII | Cebu | 118955 | Malalag ES | ARGAO | 2 | 1 | 4 | 2STY4CL | BATCH 8 | 8975901.76 |  |  | Completed | 1
29403 | NC 2017 | K10 | Region VII | Cebu | 119270 | Malbago Elementary School | DAANBANTAYAN | 4 | 1 | 6 | 3STY6CL | BATCH 8 | 13899515.1 |  |  | Completed | 1 |  |  | P00177994VS-CW1 | 17HD0186 | 2017-08-30 |  | 2017-11-27 |  | 2017-12-15 | BANTAY CONST.
29404 | NC 2017 | SHS | Region VII | Cebu | 302962 | Malingin NHS | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1 |  |  | P00184501VS-CW1 | 17HD0140 | 2017-08-30 |  | 2017-12-19 |  | 2017-12-27 | BANTAY CONST.
29405 | NC 2017 | TVL | Region VII | Cebu | 312457 | Manatad National High School | SIBONGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2781000 |  |  | Completed | 1 |  |  | P00181950VS-CW1 | 17-HE-0174 | 2017-11-18 | 2017-11-23 | 2017-12-05 | 2017-12-11 | 2017-12-22 | Square One Builders
29406 | NC 2017 | TVL | Region VII | Cebu | 312457 | Manatad National High School | SIBONGA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2781000 |  |  | Completed | 1 |  |  | P00181951VS-CW1 | 17-HE-0175 | 2017-11-18 | 2017-11-23 | 2017-12-05 | 2017-12-11 | 2017-12-22 | Celjem Const. & Dev't. Corp.
29407 | NC 2017 | K10 | Region VII | Cebu | 118956 | Mandilikit ES | ARGAO | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
29408 | NC 2017 | TVL | Region VII | Cebu | 302986 | Mandilikit NHS | ARGAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
29409 | NC 2017 | TVL | Region VII | Cebu | 302986 | Mandilikit NHS | ARGAO | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
29410 | NC 2017 | K10 | Region VII | Cebu | 119486 | Manduang ES | MINGLANILLA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2673745.92 |  |  | Completed | 1
29411 | NC 2017 | K10 | Region VII | Cebu | 119758 | Manlagtang ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
29412 | NC 2017 | K10 | Region VII | Cebu | 119305 | Mantalongon ES | DALAGUETE | 2 | 1 | 9 | 3STY9CL | BATCH 8 | 24558047.73 |  |  | Completed | 1
29413 | NC 2017 | K10 | Region VII | Cebu | 119305 | Mantalongon ES | DALAGUETE | 2 |  | 4 | 2STY4CL | BATCH 8 | 8985901.76 |  |  | Completed | 1
29414 | NC 2017 | K10 | Region VII | Cebu | 119611 | Manuel L. Quezon ES | SAMBOAN | 2 | 1 | 9 | 3STY9CL | BATCH 8 | 24558047.73 |  |  | Completed | 1
29415 | NC 2017 | SHS | Region VII | Cebu | 303054 | Medellin National High School | MEDELLIN | 4 | 1 | 8 | 4STY8CL | BATCH 8 | 17159570.67 |  |  | Completed | 1
29416 | NC 2017 | TVL | Region VII | Cebu | 303057 | Montañeza NHS | MALABUYOC | 7 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2700000 |  |  | Completed | 1
29417 | NC 2017 | TVL | Region VII | Cebu | 303059 | Montealegre NHS | TUBURAN | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3075390.12 |  |  | Completed | 1
29418 | NC 2017 | TVL | Region VII | Cebu | 312460 | Montpeller NHS | ALEGRIA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
29419 | NC 2017 | K10 | Region VII | Cebu | 119759 | Muabog ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
29420 | NC 2017 | TVL | Region VII | Cebu | 302949 | Nangka National High School | BALAMBAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2904389.71 |  |  | Completed | 1
29421 | NC 2017 | K10 | Region VII | Cebu | 119537 | Nueva Caceres ES | OSLOB | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
29422 | NC 2017 | K10 | Region VII | Cebu | 118877 | Nug-as ES | ALCOY | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
29423 | NC 2017 | TVL | Region VII | Cebu | 302918 | Nug-as NHS | ALCOY | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
29424 | NC 2017 | TVL | Region VII | Cebu | 302918 | Nug-as NHS | ALCOY | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
29425 | NC 2017 | K10 | Region VII | Cebu | 119780 | Olivo ES | TABUELAN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
29426 | NC 2017 | TVL | Region VII | Cebu | 303081 | Puertobello NHS - Pob. Ext. | TUDELA | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0152 | [5 empty] | FIRST BUILDERS AND DEVELOPERS
29427 | NC 2017 | TVL | Region VII | Cebu | 303081 | Puertobello NHS - Pob. Ext. | TUDELA | 5 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1
29428 | NC 2017 | TVL | Region VII | Cebu | 303060 | Putat NHS | TUBURAN | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 5643846.13 |  |  | Completed | 1
29429 | NC 2017 | TVL | Region VII | Cebu | 303085 | San Jose National High School | PORO | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0150 | [5 empty] | FIRST BUILDERS AND DEVELOPERS
29446 | NC 2017 | TVL | Region VII | Bohol | 302811 | Baclayon National High School | BACLAYON | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 5169000 |  |  | Completed | 1
29447 | NC 2017 | TVL | Region VII | Bohol | 302833 | Catigbian NHS | CATIGBIAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 5241000 |  |  | Completed | 1
29448 | NC 2017 | SHS | Region VII | Bohol | 302873 | Mahayag National High School | SAN MIGUEL | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4156545.02 |  |  | Completed | 1
29449 | NC 2017 | K10 | Region VII | Cebu | 118987 | San Roque ES | ASTURIAS | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3817546.25 |  |  | Completed | 1
29450 | NC 2017 | TVL | Region VII | Cebu | 303089 | San Sebastian NHS | SAMBOAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
29451 | NC 2017 | TVL | Region VII | Cebu | 303094 | Santa Fe National High School | SANTA FE | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
29452 | NC 2017 | K10 | Region VII | Cebu | 119201 | Santikan Elementary School | CARMEN | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0059 | [5 empty] | COCOS TIERRA DEV'T. CORP
29453 | NC 2017 | TVL | Region VII | Cebu | 303101 | Sibonga National High School | SIBONGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2754000 |  |  | reverted | 0
29454 | NC 2017 | SHS | Region VII | Cebu | 302996 | Sir Knight Luis P. Cañete Sr. NHS | DAANBANTAYAN | 4 | 1 | 6 | 3STY6CL | BATCH 14 | 13739515.1 |  |  | Completed | 1 |  |  | P00184502VS-CW1 | 17HD0196 | 2017-11-16 |  | 2017-12-11 |  | 2017-12-22 | J.A.R.C CONST.
29455 | NC 2017 | SHS | Region VII | Cebu | 302996 | Sir Knight Luis P. Cañete Sr. NHS | DAANBANTAYAN | 4 |  | 6 | 3STY6CL | BATCH 14 | 13739515.1 |  |  | Completed | 1 |  |  | P00184503VS-CW1 | 17HD0197 | 2017-11-16 |  | 2017-12-11 |  | 2017-12-22 | J.A.R.C CONST.
29456 | NC 2017 | K10 | Region VII | Cebu | 119764 | Somosa ES | TABOGON | 4 | 1 | 3 | 1STY3CL | BATCH 2 | 3768435.02 |  |  | Completed | 1
29457 | NC 2017 | K10 | Region VII | Cebu | 119766 | Tabogon Central ES | TABOGON | 4 | 1 | 12 | 3STY12CL | BATCH 8 | 29469267.25 |  |  | Completed | 1
29458 | NC 2017 | TVL | Region VII | Cebu | 303104 | Tabunan NHS | BORBON | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0147 | [5 empty] | JO BUILDERS
29459 | NC 2017 | K10 | Region VII | Cebu | 118934 | Talaga ES | ARGAO | 2 | 1 | 6 | 2STY6CL | BATCH 8 | 11716168.02 |  |  | Completed | 1
29460 | NC 2017 | K10 | Region VII | Cebu | 118934 | Talaga ES | ARGAO | 2 |  | 6 | 2STY6CL | BATCH 8 | 11716168.02 |  |  | Completed | 1
29461 | NC 2017 | TVL | Region VII | Cebu | 303112 | Talaga NHS | ARGAO | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
29462 | NC 2017 | K10 | Region VII | Cebu | 118935 | Talaytay Elementary School | ARGAO | 2 | 1 | 4 | 2STY4CL | BATCH 8 | 8985901.76 |  |  | Completed | 1
29463 | NC 2017 | K10 | Region VII | Cebu | 118962 | Taloot Central Elementary School | ARGAO | 2 | 1 | 6 | 2STY6CL | BATCH 8 | 11706168.02 |  |  | Completed | 1
29464 | NC 2017 | K10 | Region VII | Cebu | 118962 | Taloot Central Elementary School | ARGAO | 2 |  | 6 | 2STY6CL | BATCH 8 | 11706168.02 |  |  | Completed | 1
29472 | NC 2017 | SHS | Region VII | Bohol | 302907 | Bantolinao National High School | ANTEQUERA | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2891384 |  |  | Completed | 1
29473 | NC 2017 | SHS | Region VII | Bohol | 302832 | Canhayupon NHS | DIMIAO | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1
29474 | NC 2017 | K10 | Region VII | Bohol | 118502 | Napo Elementary School | LOON | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2891384 |  |  | Completed | 1
29475 | NC 2017 | SHS | Region VII | Bohol | 302819 | Busao National High School | MARIBOJOC | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2891384 |  |  | Completed | 1
29476 | NC 2017 | K10 | Region VII | Cebu | 118962 | Taloot Central Elementary School | ARGAO | 2 |  | 6 | 2STY6CL | BATCH 8 | 11706168.02 |  |  | Completed | 1
29477 | NC 2017 | K10 | Region VII | Cebu | 119539 | Tan-awan ES | OSLOB | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
29478 | NC 2017 | TVL | Region VII | Cebu | 302980 | Tinabyonan NHS | CATMON | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0146 | [5 empty] | JOHN ARNE CONSTRUCTION
29479 | NC 2017 | TVL | Region VII | Cebu | 302980 | Tinabyonan NHS | CATMON | 5 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1 |  |  |  | 17HI0145 | [5 empty] | JOHN ARNE CONSTRUCTION
29480 | NC 2017 | K10 | Region VII | Cebu | 119471 | Tindog ES | MEDELLIN | 4 | 1 | 3 | 1STY3CL | BATCH 2 | 3768435.02 |  |  | Completed | 1
29481 | NC 2017 | K10 | Region VII | Cebu City | 303129 | Adlaon NHS | CEBU CITY (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 12 | 16046618.12 |  |  | Completed | 1
29482 | NC 2017 | K10 | Region VII | Cebu City | 119928 | Binaliw ES | CEBU CITY (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 12 | 25561526.15 |  |  | Completed | 1
29483 | NC 2017 | SHS | Region VII | Cebu City | 303131 | BINALIW NATIONAL HIGH SCHOOL | CEBU CITY (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 12 | 32056227.4 |  |  | Completed | 1
29484 | NC 2017 | K10 | Region VII | Cebu City | 119909 | Pardo Elementary School | CEBU CITY (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 12 | 37501520.885 |  |  | Completed | 1
29485 | NC 2017 | K10 | Region VII | Cebu City | 119914 | Pasil Elementary School | CEBU CITY (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 12 | 37851920.18 |  |  | Completed | 1
29486 | NC 2017 | K10 | Region VII | Cebu City | 119890 | Toong ES | CEBU CITY (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 12 | 24508829.56 |  |  | Completed | 1
29487 | NC 2017 | SHS | Region VII | Danao City | 302956 | Estefa O. Monte Memo. National High School | DANAO CITY | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0155 | [5 empty] | BL PANGAN CONSTRUCTION
29488 | NC 2017 | SHS | Region VII | Danao City | 303037 | Maslog National High School | DANAO CITY | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0156 | [5 empty] | FIRST BUILDERS AND DEVELOPERS
29492 | NC 2017 | K10 | Region VII | Mandaue City | 119998 | Basak ES | MANDAUE CITY | 6 | 1 | 12 | 4STY12CL | BATCH 12 | 32201289.72 |  |  | Completed | 1
29493 | NC 2017 | SHS | Region VII | Mandaue City | 303198 | Jagobiao NHS | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL | BATCH 12 | 17637320.67 |  |  | Completed | 1
29494 | NC 2017 | K10 | Region VII | Mandaue City | 312807 | Maguikay HS | MANDAUE CITY | 6 | 1 | 16 | 4STY16CL | BATCH 12 | 37449237.96 |  |  | Completed | 1
29495 | NC 2017 | SHS | Region VII | Mandaue City | 303199 | Mandaue City Comprehensive NHS | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL | BATCH 12 | 17478820.67 |  |  | Completed | 1
29496 | NC 2017 | K10 | Region VII | Mandaue City | 119997 | Mandaue City CS | MANDAUE CITY | 6 | 1 | 16 | 4STY16CL | BATCH 12 | 37379237.96 |  |  | Completed | 1
29497 | NC 2017 | K10 | Region VII | Mandaue City | 120006 | Subangdaku ES | MANDAUE CITY | 6 | 1 | 20 | 4STY20CL | BATCH 12 | 42119659.74 |  |  | Completed | 1
29498 | NC 2017 | K10 | Region VII | Mandaue City | 120007 | Tipolo ES | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL | BATCH 12 | 17418820.67 |  |  | Completed | 1
29505 | NC 2017 | K10 | Region VII | Bogo City | 119125 | Polambato ES | CITY OF BOGO | 4 | 1 | 6 | 2STY6CL | BATCH 14 | 11696168.02 |  |  | Completed | 1 |  |  | P00184485VS | 17HD0074 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | Dinah Jane Const.
29506 | NC 2017 | SHS | Region VII | Bogo City | 302934 | Jovencio N. Masong NHS | CITY OF BOGO | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 18049155.23 |  |  | Completed | 1 |  |  | P00184486VS | 17HD0107 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | B.L. Pangan
29507 | NC 2017 | SHS | Region VII | Bogo City | 302935 | La Paz NHS | CITY OF BOGO | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 18049155.23 |  |  | Completed | 1 |  |  | P00184487VS | 17HD0108 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | P.B. Obial
29508 | NC 2017 | SHS | Region VII | Bogo City | 302935 | La Paz NHS | CITY OF BOGO | 4 |  | 6 | 3STY6CL | BATCH 14 | 14452527.73 |  |  | Completed | 1 |  |  | P00184488VS | 17HD0093 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | Dinah Jane Const.
29509 | NC 2017 | SHS | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 18249155.23 |  |  | Completed | 1 |  |  | P00184489VS | 17HD0109 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | Dinah Jane Const. | Slow paced progress
29510 | NC 2017 | SHS | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 |  | 6 | 3STY6CL | BATCH 14 | 14552527.73 |  |  | Completed | 1 |  |  | P00184490VS | 17HD0D94 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | P.B. Obial
29511 | NC 2017 | SHS | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 |  | 4 | 2STY4CL | BATCH 14 | 9273175.995 |  |  | Completed | 1 |  |  | P00184491VS | 17HD0192 | 2017-11-16 | 2017-11-28 | 2017-12-11 | 2017-12-18 | 2017-12-22 | Gonzalodo Enterp.
29512 | NC 2017 | SHS | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 |  | 4 | 2STY4CL | BATCH 14 | 9273175.995 |  |  | Completed | 1 |  |  | P00184492VS | 17HD0193 | 2017-11-16 | 2017-11-28 | 2017-12-11 | 2017-12-16 | 2017-12-22 | Gonzalodo Enterp.
29513 | NC 2017 | SHS | Region VII | Bogo City | 302937 | Odlot NHS | CITY OF BOGO | 4 | 1 | 6 | 3STY6CL | BATCH 14 | 14452527.73 |  |  | Completed | 1 |  |  | P00184493VS | 17HD0075 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | Dinah Jane Const.
29514 | NC 2017 | SHS | Region VII | Bogo City | 500407 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1 |  |  | P00184494VS | 17HD0194 | 2017-11-16 | 2017-09-28 | 2017-12-11 | 2017-12-18 | 2017-12-22 | Dinah Jane Const.
29515 | NC 2017 | SHS | Region VII | Bogo City | 500407 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 |  | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1 |  |  | P00184495VS | 17HD0195 | 2017-11-16 | 2017-09-28 | 2017-12-11 | 2017-12-18 | 2017-12-22 | Dinah Jane Const.
29516 | NC 2017 | K10 | Region VII | Cebu | 119471 | Tindog ES | MEDELLIN | 4 | 1 | 6 | 2STY6CL | BATCH 8 | 11676168.02 |  |  | Completed | 1
29517 | NC 2017 | TVL | Region VII | Cebu | 302965 | Tominjao National High School | DAANBANTAYAN | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
29518 | NC 2017 | K10 | Region VII | Cebu | 118937 | Tulic ES | ARGAO | 2 | 1 | 6 | 3STY6CL | BATCH 8 | 13799515.1 |  |  | Completed | 1
29519 | NC 2017 | K10 | Region VII | Cebu | 118915 | Tuyokon Elementary School | ALOGUINSAN | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3886162.11 |  |  | Completed | 1
29520 | NC 2017 | K10 | Region VII | Cebu | 119658 | Union ES | SAN FRANCISCO | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0064 | [5 empty] | YES CONSTRUCTION
29521 | NC 2017 | K10 | Region VII | Cebu | 119104 | Vito ES | BARILI | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3815668.69 |  |  | Completed | 1
29522 | NC 2017 | K10 | Region VII | Cebu | 119104 | Vito ES | BARILI | 3 |  | 3 | 1STY3CL | BATCH 4 | 3815668.69 |  |  | Completed | 1
29523 | NC 2017 | SHS | Region VII | City of Naga, Cebu | 303121 | Uling National High School | CITY OF NAGA | 1 | 1 | 12 | 3STY12CL | BATCH 14 | 29359267.25 |  |  | Completed | 1 |  |  | P00184504VS-CWI | 17-HE-0166 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-14 | 2017-12-22 | Quirante Construction
29524 | NC 2017 | SHS | Region VII | City of Naga, Cebu | 325303 | Tinaan National High School | CITY OF NAGA | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Reverted | 0
29525 | NC 2017 | K10 | Region VII | Lapu-Lapu City | 119960 | Talima ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 8 | 4STY8CL | BATCH 14 | 18088049.2 |  |  | Completed | 1 | [10 empty] | for final inspection, DPWH transferred the location of the fire escape infront of the building façade
29526 | NC 2017 | K10 | Region VII | Lapu-Lapu City | 119968 | Pajo ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 8 | 4STY8CL | BATCH 14 | 17242570.67 |  |  | Completed | 1
29527 | NC 2017 | K10 | Region VII | Lapu-Lapu City | 119971 | Soong ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 8 | 4STY8CL | BATCH 14 | 17234570.67 |  |  | Completed | 1
29528 | NC 2017 | K10 | Region VII | Lapu-Lapu City | 119976 | Buyong Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | BATCH 14 | 31732289.72 |  |  | Completed | 1
29529 | NC 2017 | K10 | Region VII | Lapu-Lapu City | 119989 | Lapu-Lapu City CES | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | BATCH 14 | 31857289.72 |  |  | Completed | 1
29530 | NC 2017 | K10 | Region VII | Lapu-Lapu City | 119990 | Look ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | BATCH 14 | 31744789.72 |  |  | Completed | 1 | [10 empty] | Contractor have not yet completed the works in the punchlist
29543 | NC 2017 | SHS | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 37511535 |  |  | Completed | 1 | [9 empty] | Gail Construction & Supply
29544 | NC 2017 | SHS | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 |  | 20 | 4STY20CL | BATCH 14 | 48094000 |  |  | Completed | 1 | [9 empty] | Rudhil Construction & Enterprises, Inc.
29545 | NC 2017 | K10 | Region VII | Talisay City | 119787 | Lawaan ES | CITY OF TALISAY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 31649789.72 |  |  | Completed | 1
29546 | NC 2017 | K10 | Region VII | Talisay City | 119800 | Lagtang Elementary School | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1
29547 | NC 2017 | SHS | Region VII | Talisay City | 303019 | Jaclupan National High School | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1
29548 | NC 2017 | SHS | Region VII | Talisay City | 303020 | Pooc NHS (Jaclupan NHS - Pooc Ext.) | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1
29549 | NC 2017 | SHS | Region VII | Talisay City | 303040 | Lawaan NHS, Talisay | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1
29550 | NC 2017 | SHS | Region VII | Talisay City | 322204 | Bulacao National High School | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1
29551 | NC 2017 | SHS | Region VII | Talisay City | 322206 | Lagtang Night HS | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1
29552 | NC 2017 | SHS | Region VII | Talisay City | 322208 | Tapul National High School | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 8128972.94 |  |  | Completed | 1
37755 | NC 2018 | K10 | Region VII | Bohol | 118291 | Duero Central ES | DUERO | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13898951.6 |  |  | Completed | 1
37756 | NC 2018 | SHS | Region VII | Bohol | 302813 | Anda HS | ANDA | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 17112546.66 |  |  | Completed | 1
37757 | NC 2018 | SHS | Region VII | Bohol | 302813 | Anda HS | ANDA | 3 |  | 4 | 2STY4CL | BATCH 1 | 9014779.96 |  |  | Completed | 1
37758 | NC 2018 | SHS | Region VII | Bohol | 302813 | Anda HS | ANDA | 3 |  | 4 | 2STY4CL | BATCH 1 | 9014779.96 |  |  | Completed | 1
37759 | NC 2018 | SHS | Region VII | Bohol | 302815 | Batuan NHS | BATUAN | 3 | 1 | 12 | 3STY12CL | BATCH 1 | 29359267.25 |  |  | Completed | 1
37760 | NC 2018 | SHS | Region VII | Bohol | 302832 | Canhayupon NHS | DIMIAO | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 16974790.26 |  |  | Completed | 1
37761 | NC 2018 | SHS | Region VII | Bohol | 302847 | Duero NHS | DUERO | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 17134226.26 |  |  | Completed | 1
37762 | NC 2018 | SHS | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13739515.1 |  |  | Completed | 1
37763 | NC 2018 | SHS | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 |  | 8 | 2STY8CL | BATCH 1 | 16974790.26 |  |  | Completed | 1
37764 | NC 2018 | SHS | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA | 3 | 1 | 12 | 3STY12CL | BATCH 1 | 29359267.25 |  |  | Completed | 1
37765 | NC 2018 | SHS | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA | 3 |  | 8 | 2STY8CL | BATCH 1 | 16974790.26 |  |  | Completed | 1
37766 | NC 2018 | SHS | Region VII | Bohol | 312315 | Rizal High Sschool | BATUAN | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 16974790.26 |  |  | Completed | 1
37767 | NC 2018 | SHS | Region VII | Bohol | 312352 | Cambuyo HS | GARCIA HERNANDEZ | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13739515.1 |  |  | Completed | 1
37768 | NC 2018 | SHS | Region VII | Bohol | 312352 | Cambuyo HS | GARCIA HERNANDEZ | 3 |  | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
37769 | NC 2018 | TVL | Region VII | Bohol | 302822 | Tubigon West NHS | TUBIGON | 1 | 1 | 4 | 1 unit 4STY 4 lab | Batch 3 | 18988498 |  |  | Completed | 1
37770 | NC 2018 | TVL | Region VII | Bohol | 302824 | Mayor A. R. Tuazon Nat'l Sch. of Fisheries | CALAPE | 1 | 1 | 4 | 1 unit 4STY 4 lab | Batch 3 | 18882766 |  |  | Completed | 1
37771 | NC 2018 | TVL | Region VII | Bohol | 302835 | Cawayanan NHS | TUBIGON | 1 | 1 | 8 | 1 unit 4STY 8 lab | Batch 3 | 40423613 |  |  | Completed | 1
37772 | NC 2018 | TVL | Region VII | Bohol | 302839 | Corella National High School | CORELLA | 1 | 1 | 4 | 4STY 4 lab | Batch 6 Realignment | 18617613 |  |  | Completed | 1
37773 | NC 2018 | TVL | Region VII | Bohol | 302877 | Mantacida National High School | CATIGBIAN | 1 | 1 | 2 | 1 unit 2STY 2 lab | Batch 3 | 10600582 |  |  | Completed | 1
37774 | NC 2018 | TVL | Region VII | Bohol | 302881 | Pagnitoan National High School | MARIBOJOC | 1 | 1 | 8 | 1 unit 4STY 8 lab | Batch 3 | 38610442 |  |  | Completed | 1
37775 | NC 2018 | TVL | Region VII | Bohol | 302883 | Calape National High School | CALAPE | 1 | 1 | 3 | 2 unit 3STY 3 lab | Batch 3 | 31322047 |  |  | Completed | 1
37776 | NC 2018 | SHS | Region VII | Bohol | 302900 | San Roque National High School | ALBURQUERQUE | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11529530 |  |  | Completed | 1
37777 | NC 2018 | TVL | Region VII | Bohol | 302908 | Tabalong NHS | DAUIS | 1 | 1 | 4 | 4STY 4 lab | Batch 6 Realignment | 18911891 |  |  | Completed | 1
37778 | NC 2018 | SHS | Region VII | Bohol | 312333 | Tubigon West Central HS | TUBIGON | 1 | 1 | 9 | 3STY9CL | Batch 3 | 27074015 |  |  | Completed | 1
37779 | NC 2018 | TVL | Region VII | Bohol | 302808 | Aguining National High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1
37780 | NC 2018 | TVL | Region VII | Bohol | 302808 | Aguining National High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 |  | 6 | 2STY6CL (Regular workshop) | Batch 3 | 14159039.49 |  |  | Completed | 1 | [9 empty] | JECK CONSTRUCTION
37781 | NC 2018 | TVL | Region VII | Bohol | 302814 | Zosimo A. Gulle Memorial National High School | TALIBON | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10962735.9 |  |  | Completed | 1 | [9 empty] | ALGAMON CONSTRUCTION
37782 | NC 2018 | TVL | Region VII | Bohol | 302827 | Campao Oriental High School | JETAFE | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11062735.9 |  |  | Completed | 1 | [9 empty] | WILTAN CONSTRUCTION
37783 | NC 2018 | TVL | Region VII | Bohol | 302828 | Handumon NHS | JETAFE | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1
37784 | NC 2018 | TVL | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1 | [9 empty] | GMT BUILDERS & SUPPLY
37785 | NC 2018 | TVL | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 |  | 12 | 3STY12CL (Regular workshop) | Batch 3 | 32300000 |  |  | Completed | 1
37786 | NC 2018 | TVL | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
37787 | NC 2018 | TVL | Region VII | Bohol | 302841 | Danao NHS | DANAO | 2 |  | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1 | [9 empty] | AMAZING FIND BUILDERS CORPORATION
37788 | NC 2018 | TVL | Region VII | Bohol | 302843 | Francisco Dagohoy Memorial High School | DANAO | 2 | 1 | 4 | 2STY4CL (Regular workshop) | Batch 3 | 10962735.9 |  |  | Completed | 1
37789 | NC 2018 | TVL | Region VII | Bohol | 302858 | Hinlayagan NHS | TRINIDAD | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11000000 |  |  | Completed | 1 | [9 empty] | Rudhil Costruction
37790 | NC 2018 | TVL | Region VII | Bohol | 302859 | Southern Inabanga HS | INABANGA | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
37791 | NC 2018 | TVL | Region VII | Bohol | 302879 | Nahawan NHS | CLARIN | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
37792 | NC 2018 | TVL | Region VII | Bohol | 302886 | Pres. Carlos P. Garcia Technical Vocational School of Fisheries and Arts | BIEN UNIDO | 2 | 1 | 4 | 2STY4CL (Regular workshop) | Batch 3 | 10762735.9 |  |  | completed | 1 | [9 empty] | RUDHIL CONSTRUCTION & ENTERPRISES
37793 | NC 2018 | TVL | Region VII | Bohol | 302886 | Pres. Carlos P. Garcia Technical Vocational School of Fisheries and Arts | BIEN UNIDO | 2 |  | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
37794 | NC 2018 | TVL | Region VII | Bohol | 302886 | Pres. Carlos P. Garcia Technical Vocational School of Fisheries and Arts | BIEN UNIDO | 2 |  | 6 | 2STY6CL (Regular workshop) | Batch 3 | 13786108.5 |  |  | Completed | 1 | [9 empty] | RUDHIL CONSTRUCTION & ENTERPRISES
37795 | NC 2018 | TVL | Region VII | Bohol | 302887 | San Agustin NHS | SAGBAYAN (BORJA) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
37796 | NC 2018 | TVL | Region VII | Bohol | 302887 | San Agustin NHS | SAGBAYAN (BORJA) | 2 |  | 4 | 2STY4CL (Regular workshop) | Batch 3 | 10762735.9 |  |  | Completed | 1
37797 | NC 2018 | TVL | Region VII | Bohol | 302887 | San Agustin NHS | SAGBAYAN (BORJA) | 2 |  | 10 | 2STY10CL (Regular workshop) | Batch 3 | 21815765.83 |  |  | Completed | 1
37798 | NC 2018 | TVL | Region VII | Bohol | 302888 | Eugenio V. Amores MHS | SAGBAYAN (BORJA) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
37799 | NC 2018 | TVL | Region VII | Bohol | 302891 | San Jose National High School | INABANGA | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1 | [9 empty] | GERSON CONST. & HARDWARE SUPPLY
37800 | NC 2018 | TVL | Region VII | Bohol | 302892 | Inabanga HS- Nabuad | INABANGA | 2 | 1 | 4 | 2STY4CL (Regular workshop) | Batch 3 | 10762735.9 |  |  | Completed | 1
37801 | NC 2018 | TVL | Region VII | Bohol | 302892 | Inabanga HS- Nabuad | INABANGA | 2 |  | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
37802 | NC 2018 | TVL | Region VII | Bohol | 302892 | Inabanga HS- Nabuad | INABANGA | 2 |  | 6 | 2STY6CL (Regular workshop) | Batch 3 | 13786108.5 |  |  | Completed | 1
37803 | NC 2018 | TVL | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
37804 | NC 2018 | TVL | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 |  | 9 | 3STY9CL (Regular workshop) | Batch 3 | 27000000 |  |  | Completed | 1
37805 | NC 2018 | TVL | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 |  | 12 | 3STY12CL (Regular workshop) | Batch 3 | 32100000 |  |  | Completed | 1
37806 | NC 2018 | TVL | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 |  | 4 | 2STY4CL (Regular workshop) | Batch 3 | 10762735.9 |  |  | Completed | 1 | [9 empty] | RUDHIL CONSTRUCTION & ENTERPRISES
37807 | NC 2018 | TVL | Region VII | Bohol | 302895 | President Carlos P. Garcia Memorial High School | TALIBON | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10962735.9 |  |  | Completed | 1
37808 | NC 2018 | TVL | Region VII | Bohol | 302896 | Sikatuna Nat'l Agricultural HS | TALIBON | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10962735.9 |  |  | Completed | 1
37809 | NC 2018 | TVL | Region VII | Bohol | 302913 | Tulang NHS | JETAFE | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10962735.9 |  |  | Completed | 1
37810 | NC 2018 | TVL | Region VII | Bohol | 312303 | Mayor Inocencio B. Mendez HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 6 | 2STY6CL (Regular workshop) | Batch 3 | 14159039.49 |  |  | Completed | 1
37811 | NC 2018 | TVL | Region VII | Bohol | 312303 | Mayor Inocencio B. Mendez HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 |  | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1 | [9 empty] | RUDHIL CONSTRUCTION & ENTERPRISES
37812 | NC 2018 | TVL | Region VII | Bohol | 312309 | JAPeR Memorial High School | SAGBAYAN (BORJA) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
37813 | NC 2018 | TVL | Region VII | Bohol | 312312 | Panghagban HS | BUENAVISTA | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
37814 | NC 2018 | TVL | Region VII | Bohol | 312313 | Mayor Catalino Y. Casoyla MHS | TALIBON | 2 | 1 | 4 | 2STY4CL (Regular workshop) | Batch 3 | 11055280.22 |  |  | Completed | 1
37815 | NC 2018 | TVL | Region VII | Bohol | 312324 | Bonbonon High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1
37816 | NC 2018 | TVL | Region VII | Bohol | 312325 | Gaus High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1 | [9 empty] | MAI CONSTRUCTION & SUPPLY
37817 | NC 2018 | TVL | Region VII | Bohol | 312331 | Ponciana E. Leoligao HS | TALIBON | 2 | 1 | 6 | 2STY6CL (Regular workshop) | Batch 3 | 13786108.5 |  |  | Completed | 1
37818 | NC 2018 | TVL | Region VII | Bohol | 312335 | Basiao High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1
37819 | NC 2018 | TVL | Region VII | Bohol | 312350 | San Isidro High School | TALIBON | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
37820 | NC 2018 | TVL | Region VII | Bohol | 312353 | Campamanog HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1
37821 | NC 2018 | TVL | Region VII | Bohol | 312360 | Ponciano L. Padin National High School | BIEN UNIDO | 2 | 1 | 8 | 2STY8CL (Regular workshop) | Batch 3 | 19120864.64 |  |  | Completed | 1
37822 | NC 2018 | SHS | Region VII | Bohol | 302870 | Lonoy Heroes MHS | JAGNA | 3 | 1 | 12 | 3STY12CL | Batch 3 | 29359267.25 |  |  | Completed | 1
37823 | NC 2018 | SHS | Region VII | Bohol | 302880 | Oy NHS | LOBOC | 3 | 1 | 8 | 2STY8CL | Batch 3 | 17440775.18 |  |  | Completed | 1
37824 | NC 2018 | SHS | Region VII | Bohol | 312311 | Mayor Pablo O. Lim MHS | VALENCIA | 3 | 1 | 12 | 3STY12CL | Batch 3 | 29359267.25 |  |  | Completed | 1
37825 | NC 2018 | SHS | Region VII | Bohol | 312358 | Jagna HS | JAGNA | 3 | 1 | 12 | 3STY12CL | Batch 3 | 29359267.25 |  |  | Completed | 1
37826 | NC 2018 | SHS | Region VII | Bohol | 312359 | Katipunan High School | ALICIA | 3 | 1 | 8 | 2STY8CL | Batch 3 | 17440775.18 |  |  | Completed | 1
37827 | NC 2018 | K10 | Region VII | Bohol | 118745 | Banlasan ES | TRINIDAD | 2 | 1 | 2 | 1STY2CL | Batch 5 | 3394342 |  |  | Completed | 1
37828 | NC 2018 | K10 | Region VII | Bohol | 118752 | Kauswagan ES | TRINIDAD | 2 | 1 | 2 | 1STY2CL | Batch 5 | 3394342 |  |  | Completed | 1
37829 | NC 2018 | K10 | Region VII | Bohol | 500216 | Soom IS | TRINIDAD | 2 | 1 | 6 | 2STY6CL | Batch 5 | 13589942.7 |  |  | Completed | 1
37830 | NC 2018 | K10 | Region VII | Carcar City | 119158 | Carcar Central ES | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 | [9 empty] | Quirante Construction
37831 | NC 2018 | K10 | Region VII | Carcar City | 119171 | Bolinawan ES | CITY OF CARCAR | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 13739515.1 |  |  | Completed | 1 | [9 empty] | Solidcore Construction
37832 | NC 2018 | SHS | Region VII | Carcar City | 303066 | OCAÑA NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 | 1 | 16 | 4STY16CL | BATCH 1 | 36910737.96 |  |  | Completed | 1 | [9 empty] | Quirante Construction
37833 | NC 2018 | SHS | Region VII | Carcar City | 303066 | OCAÑA NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 |  | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 | [9 empty] | Quirante Construction
37834 | NC 2018 | SHS | Region VII | Carcar City | 303066 | OCAÑA NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 |  | 8 | 4STY8CL | BATCH 1 | 17159570.67 |  |  | Completed | 1 | [9 empty] | Quirante Construction
37835 | NC 2018 | K10 | Region VII | Carcar City | 119158 | Carcar Central ES | CITY OF CARCAR | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22671910.24 |  |  | Completed | 1 | [10 empty] | Building Permit issue
37836 | NC 2018 | SHS | Region VII | Cebu | 303025 | Almacen-Torrevillas National High School | MEDELLIN | 4 | 1 | 6 | 3STY6CL | Batch 3 | 13839515.1 |  |  | Completed | 1
37837 | NC 2018 | K10 | Region VII | Cebu | 119617 | Balud Elementary | SAN FERNANDO | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14047305.4 |  |  | Completed | 1 |  |  | POO272296VS-CW1 | 18-HE-0099 | 2018-03-28 | 2018-04-04 | 2018-05-10 | 2018-06-05 | 2018-06-08 | BT Construction & Gen. Services
37838 | NC 2018 | SHS | Region VII | Cebu | 312421 | Bantayan Science High School | BANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 18938739.78 |  |  | Completed | 1
37839 | NC 2018 | K10 | Region VII | Cebu | 119073 | Barili I Central ES | BARILI | 3 | 1 | 16 | 4STY16CL | BATCH 1 | 38940294.6 |  |  | Completed | 1 |  |  | P00272306VS | 18HF0129 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | GENETIAN BUILDERS
37840 | NC 2018 | SHS | Region VII | Cebu | 302939 | Bateria NHS | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17159570.67 |  |  | completed | 1
37841 | NC 2018 | K10 | Region VII | Cebu | 119453 | Bomedco ES | MEDELLIN | 4 | 1 | 9 | 3STY9CL | Batch 3 | 24468047.73 |  |  | Completed | 1 |  |  | P00274558VS-CW1 | 18HD0209 | [5 empty] | DINAH JANE CONSTRUCTION AND SUPPLY
37842 | NC 2018 | K10 | Region VII | Cebu | 118904 | Bonbon ES | ALOGUINSAN | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13814525.45 |  |  | completed | 1 |  |  | P00272304VS | 18HF0127 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | DINAH JANE CONST.& SUPPLY
37843 | NC 2018 | K10 | Region VII | Cebu | 119033 | Buanoy Central ES | BALAMBAN | 3 | 1 | 16 | 4STY16CL | BATCH 1 | 38940294.6 |  |  | Completed | 1 |  |  | P00272305VS | 18HF0128 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | JARC CONST.& MARINE SERVICES CORP.
37844 | NC 2018 | K10 | Region VII | Cebu | 119620 | Bugho ES | SAN FERNANDO | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14104305.4 |  |  | Completed | 1 |  |  | POO272299VS-CW1 | 18-HE-0102 | 2018-03-28 | 2018-04-04 | 2018-05-10 | 2018-06-05 | 2018-06-08 | DT&C Construction
37845 | NC 2018 | SHS | Region VII | Cebu | 500221 | Busogon Integrated School | SAN REMIGIO | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17259570.67 |  |  | Completed | 1
37846 | NC 2018 | TVL | Region VII | Cebu | 302961 | Calape NHS | DAANBANTAYAN | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 2700000 |  |  | Completed | 1 |  |  | P00272318VS-CW1 | 18HD0145 | 2018-05-30 | 2018-06-08 | 2018-06-25 |  | 2018-07-06 | DINAH JANE CONSTRUCTION SUPPLY
37847 | NC 2018 | SHS | Region VII | Cebu | 302961 | Calape NHS | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17359570.67 |  |  | Completed | 1 |  |  |  | 18HD0165 | [5 empty] | SAN NARCISO BUILDERS CORPORATION
37848 | NC 2018 | K10 | Region VII | Cebu | 119410 | Calero ES | LILOAN | 5 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | completed | 1 |  |  |  | 18HI0058 | [5 empty] | CHUPUICO CONST.
37849 | NC 2018 | K10 | Region VII | Cebu | 119855 | CALMANTE ELEMENTARY SCHOOL | TUDELA | 5 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  |  | 18HI0067 | [5 empty] | GENETIAN BUILDERS
37850 | NC 2018 | SHS | Region VII | Cebu | 302967 | Camotes National High School | SAN FRANCISCO | 5 | 1 | 8 | 2STY8CL | Batch 3 | 17654337.16 |  |  | Completed | 1 |  |  |  | 18HI0059 | [5 empty] | GENETIAN BUILDERS
37851 | NC 2018 | K10 | Region VII | Cebu | 119597 | Cansayahon ES | RONDA | 7 | 1 | 6 | 2STY6CL | BATCH 1 | 11716168.02 |  |  | Completed | 1 |  |  | P00272338VS-CW1 | 18HG0136 | 2018-04-11 | 2018-04-18 | 2018-04-30 | 2018-05-29 | 2018-06-06 | APRIL ROSE ENT. & BUILDERS
37852 | NC 2018 | SHS | Region VII | Cebu | 302984 | Colawin NHS | ARGAO | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 36910737.96 |  |  | Completed | 1 |  |  | P00272301VS-CW1 | 18HG0132 | 2018-04-11 | 2018-04-18 | 2018-04-30 | 2018-05-29 | 2018-06-06 | DINAH JANE CONST. SUPPLY
37853 | NC 2018 | K10 | Region VII | Cebu | 119831 | Colonia Central ES | TUBURAN | 3 | 1 | 9 | 3STY9CL | BATCH 1 | 26420056.92 |  |  | Completed | 1 |  |  | P00272310VS | 18HF0133 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | RUDHIL CONST. & ENTERPRISES
37854 | NC 2018 | K10 | Region VII | Cebu | 119856 | Daan Secante ES | TUDELA | 5 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  |  | 18HI0066 | [5 empty] | GENETIAN BUILDERS
37855 | NC 2018 | SHS | Region VII | Cebu | 302995 | Daanbantayan National High School | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17159570.67 |  |  | Completed | 1
37856 | NC 2018 | SHS | Region VII | Cebu | 303001 | Dapdap NHS, San Remigio | SAN REMIGIO | 4 | 1 | 8 | 4STY8CL | Batch 3 | 18049155.23 |  |  | Completed | 1
37857 | NC 2018 | K10 | Region VII | Cebu | 119377 | Dumanjug Central ES | DUMANJUG | 7 | 1 | 9 | 3STY9CL | Batch 3 | 24558047.73 |  |  | Completed | 1
37858 | NC 2018 | K10 | Region VII | Cebu | 119645 | Esperanza ES | SAN FRANCISCO | 5 | 1 | 9 | 3STY9CL | BATCH 1 | 24468047.73 |  |  | Completed | 1 |  |  |  | 18HI0061 | [5 empty] | VIRLO CONST.
37859 | NC 2018 | K10 | Region VII | Cebu | 119228 | Estaca ES | COMPOSTELA | 5 | 1 | 12 | 4STY12CL | BATCH 1 | 31649789.72 |  |  | Completed | 1 |  |  |  | 18HI0071 | [5 empty] | ASCENTIA CONST.
37860 | NC 2018 | K10 | Region VII | Cebu | 119094 | Japitan ES | BARILI | 3 | 1 | 8 | 4STY8CL | BATCH 1 | 17420383.73 |  |  | Completed | 1 |  |  | P00272307VS | 18HF0130 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | FIRST BUILDERS & DEVELOPERS
37861 | NC 2018 | SHS | Region VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | BALAMBAN | 3 | 1 | 12 | 4STY12CL | BATCH 1 | 31539789.72 |  |  | Completed | 1 |  |  | P00272314VS | 18HF0137 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | JEGMA CONST. & DEVT. CORP.
37862 | NC 2018 | SHS | Region VII | Cebu | 303103 | Juan Pamplona NHS | TABUELAN | 4 | 1 | 12 | 3STY12CL | Batch 3 | 31151517.79 |  |  | Completed | 1
37863 | NC 2018 | K10 | Region VII | Cebu | 119241 | Jugan ES | CONSOLACION | 6 | 1 | 12 | 4STY12CL | BATCH 1 | 31649789.72 |  |  | Completed | 1
37864 | NC 2018 | K10 | Region VII | Cebu | 119753 | Kal-anan ES | TABOGON | 4 | 1 | 9 | 3STY9CL | BATCH 1 | 24498047.73 |  |  | Completed | 1 |  |  | P00272317VS-CW1 | 18HD0147 | 2018-05-30 | 2018-06-08 | 2018-07-05 |  | 2018-07-20 | A.C. RIVERO DEVELOPMENT CORPORATION
37865 | NC 2018 | SHS | Region VII | Cebu | 303024 | Kawit NHS | MEDELLIN | 4 | 1 | 6 | 3STY6CL | Batch 3 | 13964515.1 |  |  | Completed | 1
37866 | NC 2018 | SHS | Region VII | Cebu | 303011 | Lanipga NHS | CONSOLACION | 6 | 1 | 6 | 3STY6CL | BATCH 1 | 13739515.1 |  |  | Completed | 1
37867 | NC 2018 | SHS | Region VII | Cebu | 303011 | Lanipga NHS | CONSOLACION | 6 |  | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
37868 | NC 2018 | K10 | Region VII | Cebu | 119414 | Liloan Central ES | LILOAN | 5 | 1 | 16 | 4STY16CL | BATCH 1 | 36910737.96 |  |  | Completed | 1 |  |  |  | 18HI0068 | [5 empty] | EDISON DEV'T. & CONST.
37869 | NC 2018 | K10 | Region VII | Cebu | 119485 | Lipata Central ES | MINGLANILLA | 1 | 1 | 16 | 4STY16CL | BATCH 1 | 37668952.72 |  |  | Completed | 1 |  |  | POO272295VS-CW1 | 18-HE-0098 | 2018-03-28 | 2018-04-04 | 2018-05-10 | 2018-06-05 | 2018-06-08 | ARQ Builders
37870 | NC 2018 | SHS | Region VII | Cebu | 303042 | Lipata NHS | MINGLANILLA | 1 | 1 | 16 | 4STY16CL | BATCH 1 | 37708952.72 |  |  | Completed | 1 |  |  | POO272297VS-CW1 | 18-HE-0100 | 2018-03-28 | 2018-04-04 | 2018-05-10 | 2018-06-05 | 2018-06-08 | Quirante Construction
37871 | NC 2018 | SHS | Region VII | Cebu | 303042 | Lipata NHS | MINGLANILLA | 1 | 1 | 8 | 4STY8CL | Batch 3 | 18678345.15 |  |  | Completed | 1
37872 | NC 2018 | SHS | Region VII | Cebu | 303044 | Looc Norte NHS | ASTURIAS | 3 | 1 | 16 | 4STY16CL | BATCH 1 | 38422952.32 |  |  | Completed | 1 |  |  | P00272310VS | 18HF0134 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | JARC CONST.& MARINE SERVICES CORP.
37873 | NC 2018 | SHS | Region VII | Cebu | 303008 | Luciano B. Rama Sr. MNHS | PORO | 5 | 1 | 16 | 4STY16CL | Batch 3 | 37988576.19 |  |  | Completed | 1 |  |  |  | 18HI0067 | [5 empty] | GENETIAN BUILDERS
37874 | NC 2018 | SHS | Region VII | Cebu | 303047 | Madridejos NHS | MADRIDEJOS | 4 | 1 | 16 | 4STY16CL | Batch 3 | 38872189.63 |  |  | Completed | 1
37875 | NC 2018 | K10 | Region VII | Cebu | 119098 | Mantalongon ES | BARILI | 3 | 1 | 16 | 4STY16CL | BATCH 1 | 37318080.24 |  |  | Completed | 1 |  |  | P00272308VS | 18HF0131 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | JARC CONST & MARINE SERVICES CORP.
37876 | NC 2018 | SHS | Region VII | Cebu | 303052 | Mantalongon NHS | BARILI | 3 | 1 | 16 | 4STY16CL | BATCH 1 | 36800737.72 |  |  | Completed | 1 |  |  | P00272312VS | 18HF0135 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | JARC CONST & MARINE SERVICES CORP.
37877 | NC 2018 | K10 | Region VII | Cebu | 119100 | Paril ES | BARILI | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13889545.21 |  |  | Completed | 1 |  |  | P00272300VS-CW1 | 18HF0126 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | SOLIDCORE CONSTRUCTION
37878 | NC 2018 | SHS | Region VII | Cebu | 312409 | Patao NHS | BANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 18049155.23 |  |  | Completed | 1
37879 | NC 2018 | SHS | Region VII | Cebu | 303060 | Putat NHS | TUBURAN | 3 | 1 | 12 | 4STY12CL | BATCH 1 | 33272004.08 |  |  | Completed | 1 |  |  | P00272313VS | 18HF0136 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | DINAH JANE CONSTRUCTION & SUPPLY
37880 | NC 2018 | K10 | Region VII | Cebu | 119601 | Ronda Central ES | RONDA | 7 | 1 | 9 | 3STY9CL | Batch 3 | 24558047.73 |  |  | Completed | 1
37881 | NC 2018 | K10 | Region VII | Cebu | 119648 | Rosalia N Lucernas ES | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  |  | 18HI0063 | [5 empty] | GENETIAN BUILDERS
37882 | NC 2018 | K10 | Region VII | Cebu | 119467 | Rosalino L. Arreglado ES | MEDELLIN | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9005901.75 |  |  | Completed | 1 |  |  | P00272315VS-CW1 | 18HD0144 | 2018-05-30 | 2018-06-08 | 2018-06-25 |  | 2018-07-06 | GONZALODO ENT.
37883 | NC 2018 | SHS | Region VII | Cebu | 303090 | Samboan National High School | SAMBOAN | 2 | 1 | 12 | 4STY12CL | BATCH 1 | 31669789.72 |  |  | Completed | 1 |  |  | P00272303VS-CW1 | 18HG0134 | 2018-04-11 | 2018-04-18 | 2018-04-30 | 2018-05-29 | 2018-06-06 | ORANI BUILDERS
37884 | NC 2018 | K10 | Region VII | Cebu | 119650 | San Francisco Central ES | SAN FRANCISCO | 5 | 1 | 20 | 4STY20CL | BATCH 1 | 41408409.74 |  |  | Completed | 1 |  |  |  | 18HI0072 | [5 empty] | PLD CONST.
37885 | NC 2018 | SHS | Region VII | Cebu | 303087 | San Remegio NHS | SAN REMIGIO | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17284570.67 |  |  | Completed | 1
37886 | NC 2018 | SHS | Region VII | Cebu | 303089 | San Sebastian NHS | SAMBOAN | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 36910737.96 |  |  | Completed | 1 |  |  | P00272302VS-CW1 | 18HG0133 | 2018-04-11 | 2018-04-18 | 2018-04-30 | 2018-05-29 | 2018-06-06 | ORANI BUILDERS
37887 | NC 2018 | SHS | Region VII | Cebu | 303102 | Simala National High School | SIBONGA | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 17229570.67 |  |  | Completed | 1 |  |  | POO272298VS-CW1 | 18-HE-0101 | 2018-03-28 | 2018-04-04 | 2018-05-10 | 2018-06-05 | 2018-06-08 | RCDG Const Corp./AT Dumlao
37888 | NC 2018 | SHS | Region VII | Cebu | 303102 | Simala National High School | SIBONGA | 1 | 1 | 8 | 4STY8CL | Batch 3 | 18299570.98 |  |  | Completed | 1
37889 | NC 2018 | K10 | Region VII | Cebu | 119653 | Sonog ES | SAN FRANCISCO | 5 | 1 | 9 | 3STY9CL | BATCH 1 | 24468047.73 |  |  | Completed | 1 |  |  |  | 18HI0062 | [5 empty] | ASCENTIA CONST.
37890 | NC 2018 | K10 | Region VII | Cebu | 119572 | Tajao Central School | PINAMUNGAHAN | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 14437360.69 |  |  | completed | 1 |  |  | P00272309VS | 18HF0132 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | CELGEM CONST. & DEVT. CORP.
37891 | NC 2018 | SHS | Region VII | Cebu | 119683 | Tambongon Integrated School | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8965901.76 |  |  | completed | 1 |  |  | P00272316VS-CW1 | 18HD0146 | 2018-05-30 | 2018-06-08 | 2018-06-25 |  | 2018-07-06 | GOLDFIN CONSTRUCTION & DEVELOPMENT CORP.
37892 | NC 2018 | SHS | Region VII | Cebu | 302964 | Tapilon National High School | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17159570.67 |  |  | Completed | 1
37893 | NC 2018 | K10 | Region VII | Cebu | 119382 | Tapon ES | DUMANJUG | 7 | 1 | 10 | 2STY10CL | BATCH 1 | 19708155.67 |  |  | Completed | 1 |  |  | P00272337VS-CW1 | 18HG0135 | 2018-04-11 | 2018-04-18 | 2018-04-30 | 2018-05-29 | 2018-06-06 | QM BUILDERS JV (APRIL ROSE)
37894 | NC 2018 | K10 | Region VII | Cebu | 119248 | Tayud ES | CONSOLACION | 6 | 1 | 20 | 4STY20CL | BATCH 1 | 41408409.74 |  |  | completed | 1
37895 | NC 2018 | K10 | Region VII | Cebu | 119248 | Tayud ES | CONSOLACION | 6 |  | 16 | 4STY16CL | BATCH 1 | 36910737.96 |  |  | completed | 1
37896 | NC 2018 | SHS | Region VII | Cebu | 302965 | Tominjao National High School | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 18299155.23 |  |  | Completed | 1 |  |  |  | 18HD0176 | [5 empty] | BANTAY CONSTRUCTION
37897 | NC 2018 | K10 | Region VII | Cebu | 119863 | Tudela Central ES | TUDELA | 5 | 1 | 9 | 3STY9CL | BATCH 1 | 24468047.73 |  |  | Completed | 1 |  |  |  | 18HI0065 | [5 empty] | GENETIAN BUILDERS
37898 | NC 2018 | K10 | Region VII | Cebu | 119657 | Unidos ES | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  |  | 18HI0064 | [5 empty] | ASCENTIA CONST.
37899 | NC 2018 | K10 | Region VII | Cebu | 119423 | Yati Elementary School | LILOAN | 5 | 1 | 20 | 4STY20CL | BATCH 1 | 41460909.74 |  |  | Completed | 1 |  |  |  | 18HI0069 | [5 empty] | EDISON DEV'T. & CONST.
37900 | NC 2018 | K10 | Region VII | Cebu | 119423 | Yati Elementary School | LILOAN | 5 |  | 20 | 4STY20CL | BATCH 1 | 41460909.74 |  |  | Completed | 1 |  |  |  | 18HI0070 | [5 empty] | DUROS DEV'T. CORP.
37901 | NC 2018 | K10 | Region VII | Cebu City | 119901 | Mabolo ES | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 20809475.06 |  |  | Completed | 1
37902 | NC 2018 | K10 | Region VII | Cebu City | 119904 | Talamban Elementary School | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 20534567.08 |  |  | Completed | 1
37903 | NC 2018 | K10 | Region VII | Cebu City | 119931 | Zapatera ES (Night/Sped) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 20823220.52 |  |  | Completed | 1
37904 | NC 2018 | SHS | Region VII | Cebu City | 303140 | Talamban NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 20511935.95 |  |  | Completed | 1
37905 | NC 2018 | SHS | Region VII | Cebu City | 303165 | Vicente Cosido NHS (Cambinocot NHS) | CEBU CITY (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 17048243.55 |  |  | Completed | 1
37906 | NC 2018 | K10 | Region VII | Cebu City | 119879 | Banawa ES | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 20534567.08 |  |  | Completed | 1
37907 | NC 2018 | K10 | Region VII | Cebu City | 119880 | Guadalupe ES | CEBU CITY (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 37851920.18 |  |  | Completed | 1
37908 | NC 2018 | K10 | Region VII | Cebu City | 119885 | Labangon Bliss ES | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 20532370.66 |  |  | Completed | 1
37909 | NC 2018 | K10 | Region VII | Cebu City | 119916 | Sawang Calero ES | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 20615557.73 |  |  | Completed | 1
37910 | NC 2018 | SHS | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. NHS (Basak NHS) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 20461813.92 |  |  | Completed | 1
37911 | NC 2018 | SHS | Region VII | Cebu City | 303150 | Don Sergio Osme¤a, Sr. Memorial HS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 20567649.03 |  |  | Completed | 1
37912 | NC 2018 | SHS | Region VII | Cebu City | 312506 | Tisa National High School ( Day & Night) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 21062380.75 |  |  | Completed | 1
37913 | NC 2018 | SHS | Region VII | Cebu City | 312513 | ALASKA HS | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 20604599.6 |  |  | Completed | 1
37914 | NC 2018 | K10 | Region VII | Cebu City | 119900 | Guba Elementary School | CEBU CITY (Capital) | 1 | 1 | 6 | 3STY6CL | Batch 3 | 18697242.47 |  |  | Completed | 1
37915 | NC 2018 | SHS | Region VII | Cebu City | 312503 | Banilad Night HS | CEBU CITY (Capital) | 1 | 1 | 12 | 4STY12CL | Batch 3 | 34937939.03 |  |  | Completed | 1
37916 | NC 2018 | K10 | Region VII | Cebu City | 119886 | Labangon Elementary School | CEBU CITY (Capital) | 2 | 1 | 12 | 4STY12CL | Batch 3 | 34883165.92 |  |  | Completed | 1
37917 | NC 2018 | K10 | Region VII | City of Naga, Cebu | 119504 | Cantao-an Elementary School | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10109687.41 |  |  | Reverted | 0
37918 | NC 2018 | K10 | Region VII | City of Naga, Cebu | 119508 | Naalad Elementary School | CITY OF NAGA | 1 | 1 | 6 | 3STY6CL | Batch 3 | 14870654.72 |  |  | Completed | 1 |  |  | P00274581VS-CW1 | 18-HE-0136 | 2018-10-26 | 2018-11-06 | 2018-11-19 | 2018-11-28 | 2018-12-05 | January Builders
37919 | NC 2018 | K10 | Region VII | City of Naga, Cebu | 119509 | Naga Central ES | CITY OF NAGA | 1 | 1 | 8 | 4STY8CL | Batch 3 | 18215680.56 |  |  | Completed | 1 |  |  | P00274582VS-CW1 | 18-HE-0141 | 2018-10-26 | 2018-11-06 | 2018-11-19 | 2018-11-28 | 2018-12-05 | Quirante Construction
37920 | NC 2018 | K10 | Region VII | City of Naga, Cebu | 119510 | NPC-Colon Elementary School | CITY OF NAGA | 1 | 1 | 6 | 2STY6CL | Batch 3 | 12787968.58 |  |  | completed | 1 |  |  | P00274583VS-CW1 | 18-HE-0134 | 2018-10-26 | 2018-11-06 | 2018-11-19 | 2018-12-03 | 2018-12-06 | E.G. & I. Construction Corporation
37921 | NC 2018 | K10 | Region VII | City of Naga, Cebu | 119512 | Tuyan Central Elementary School | CITY OF NAGA | 1 | 1 | 9 | 3STY9CL | Batch 3 | 25595570.32 |  |  | Completed | 1 |  |  | P00274584VS-CW1 | 18-HE-0145 | 2018-10-26 | 2018-11-06 | 2018-11-19 | 2018-11-26 | 2018-12-05 | Quirante Construction
37922 | NC 2018 | K10 | Region VII | City of Naga, Cebu | 119518 | Langtad ES | CITY OF NAGA | 1 | 1 | 9 | 3STY9CL | Batch 3 | 25608910.5 |  |  | Completed | 1 |  |  | P00274585VS-CW1 | 18-HE-0146 | 2018-10-26 | 2018-11-06 | 2018-11-19 | 2018-11-26 | 2018-12-05 | Celjem Construction & Development Corp.
37923 | NC 2018 | SHS | Region VII | Danao City | 303037 | Maslog National High School | DANAO CITY | 5 | 1 | 6 | 3STY6CL | BATCH 1 | 13739515.1 |  |  | Completed | 1
37924 | NC 2018 | SHS | Region VII | Danao City | 322003 | Ramon M. Durano Sr. Foundation - Science and Technology Education Center | DANAO CITY | 5 | 1 | 12 | 3STY12CL | BATCH 1 | 29359267.25 |  |  | Completed | 1 |  |  |  | 18HI0060 | [5 empty] | DUROS DEV'T. CORP.
37925 | NC 2018 | K10 | Region VII | Danao City | 119355 | Portland ES | DANAO CITY | 5 | 1 | 4 | 2STY4CL | Batch 3 | 8945901.76 |  |  | Completed | 1 |  |  |  | 18HI0060 | [5 empty] | LLABAN CONST. SUPPLY
37926 | NC 2018 | K10 | Region VII | Danao City | 119366 | Maslog Elementary School | DANAO CITY | 5 | 1 | 4 | 2STY4CL | Batch 3 | 8945901.76 |  |  | Completed | 1 |  |  |  | 18HI0056 | [5 empty] | DINAH JANE CONSTRUCTION SUPPLY
37942 | NC 2018 | K10 | Region VII | Lapu-Lapu City | 119967 | Mactan ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 20 | 4STY20CL | BATCH 1 | 41665909.74 |  |  | Completed | 1 |  |  | P0022354VS-CW1 | 18HN0065 | 2018-05-30 | 2018-06-08 | 2018-06-20 | 2018-06-22 | 2018-07-05 | QM Builders/ Docast Const. (JV)
37943 | NC 2018 | K10 | Region VII | Lapu-Lapu City | 119978 | Maribago Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | Batch 3 | 31766289.72 |  |  | Completed | 1 |  |  | P00274600VS-CW1 | 18HN0078 | 2018-10-15 | 2018-10-26 | 2018-11-07 | 2018-11-22 | 2018-12-05 | Gonzalodo Enterprises
37944 | NC 2018 | K10 | Region VII | Mandaue City | 119994 | Cesar M. Cabahug ES (Looc) | MANDAUE CITY | 6 | 1 | 12 | 4STY12CL | Batch 3 | 31743013.78 |  |  | Completed | 1 |  |  | P00274601VS-C1 | 18HN0079 | 2018-10-15 | 2018-10-26 | 2018-11-07 |  | 2018-11-29 | PLD CONST. &DEV'T. CORP
37945 | NC 2018 | K10 | Region VII | Mandaue City | 119995 | Mayor A.S. Fortuna Memorial ES | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL | Batch 3 | 18043793.49 |  |  | Completed | 1 |  |  | P00274602VS-C2 | 18HN0080 | 2018-10-15 | 2018-10-26 | 2018-11-07 |  | 2018-11-29 | BANTAY CONSTRUCTION
37946 | NC 2018 | K10 | Region VII | Mandaue City | 119998 | Basak ES | MANDAUE CITY | 6 | 1 | 12 | 4STY12CL | Batch 3 | 30797968.8 |  |  | Completed | 1 |  |  | P00274602VS-C3 | 18HN0081 | 2018-10-15 | 2018-10-26 | 2018-11-07 |  | 2018-11-29 | P.B. OBIAL CONSTRUCTION
37947 | NC 2018 | K10 | Region VII | Mandaue City | 120000 | Leonard Wood ES | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL | Batch 3 | 18094736.83 |  |  | Completed | 1 |  |  | P00274602VS-C4 | 18HN0082 | 2018-10-15 | 2018-10-26 | 2018-11-07 |  | 2018-11-29 | PLD CONST. &DEV'T. CORP
37948 | NC 2018 | K10 | Region VII | Mandaue City | 120001 | Opao ES | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL | Batch 3 | 18100260.76 |  |  | Completed | 1 |  |  | P00274602VS-C5 | 18HN0083 | 2018-10-15 | 2018-10-26 | 2018-11-07 |  | 2018-11-29 | BANTAY CONSTRUCTION
38003 | NC 2018 | TVL | Region VII | Tagbilaran City | 302874 | Manga National High School | TAGBILARAN CITY (Capital) | 1 | 1 | 2 | 2UNITS 1STY TVL BLDG. | Batch 5 | 10943463 |  |  | Completed | 1
38004 | NC 2018 | K10 | Region VII | Talisay City | 119788 | Maghaway ES | CITY OF TALISAY | 1 | 1 | 9 | 3STY9CL | Batch 3 | 28343650.67 |  |  | completed | 1
38005 | NC 2018 | SHS | Region VII | Talisay City | 303056 | Mohon (Divino Amore) National High School | CITY OF TALISAY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 32798595.44 |  |  | completed | 1
38006 | NC 2018 | SHS | Region VII | Talisay City | 303088 | San Roque NHS | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 23021167.14 |  |  | completed | 1
38007 | NC 2018 | SHS | Region VII | Talisay City | 303113 | Talisay City National High School | CITY OF TALISAY | 1 |  | 8 | 4STY8CL | Batch 3 | 22721533.51 |  |  | completed | 1
38008 | NC 2018 | SHS | Region VII | Talisay City | 303113 | Talisay City National High School | CITY OF TALISAY | 1 |  | 8 | 4STY8CL | Batch 3 | 22810602.9 |  |  | completed | 1
38009 | NC 2018 | SHS | Region VII | Talisay City | 322201 | Maghaway National High School | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | Batch 3 | 15089654.21 |  |  | completed | 1
38026 | NC 2018 | K10 | Region VII | Toledo City | 120711 | Apid ES | TOLEDO CITY | 3 | 1 | 8 | 4STY8CL | BATCH 1 | 17470383.73 |  |  | Completed | 1 |  |  | P00272383VS | 18HF0138 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | Edison Devt., & Construction
38027 | NC 2018 | K10 | Region VII | Toledo City | 120757 | South City Central ES | TOLEDO CITY | 3 | 1 | 20 | 4STY20CL | BATCH 1 | 43322493.84 |  |  | Completed | 1 |  |  | P0027384VS | 18HF0139 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | BL Pangan Construction
39732 | NC 2019 | SHS | Region VII | Bogo City | 500408 | Don Celestino Martinez Sr. Taytayan IS | CITY OF BOGO | 4 | 1 | 4 | 2STY4CL |  | 9791535.6045 |  | COMPLETED | 1 | [11 empty] | 0
39733 | NC 2019 | K10 | Region VII | Bohol | 118696 | Abucay ES | SIKATUNA | 1 | 1 | 3 | 1STY3CL |  | 7200957.5 |  | COMPLETED | 1 | [11 empty] | 0
39734 | NC 2019 | K10 | Region VII | Bohol | 118555 | Bolod ES | PANGLAO | 1 | 1 | 3 | 1STY3CL |  | 7164667 |  | COMPLETED | 1 | [11 empty] | 0
39735 | NC 2019 | K10 | Region VII | Bohol | 118277 | Lapsaon ES | DIMIAO | 3 | 1 | 2 | 1STY2CL |  | 4272098.9634 |  | COMPLETED | 1 | [11 empty] | 0
39736 | NC 2019 | K10 | Region VII | Bohol | 118560 | Lourdes ES | PANGLAO | 1 | 1 | 3 | 1STY3CL |  | 7118351.5 |  | COMPLETED | 1 | [11 empty] | 0
39737 | NC 2019 | K10 | Region VII | Bohol | 118858 | Omjon ES | VALENCIA | 3 | 1 | 2 | 1STY2CL |  | 4390167.0976 |  | COMPLETED | 1 | [11 empty] | 0
39738 | NC 2019 | K10 | Region VII | Bohol | 186501 | Pagahat ES | ALICIA | 3 | 1 | 2 | 1STY2CL |  | 4096105.3566 |  | COMPLETED | 1 | [11 empty] | 0
39739 | NC 2019 | K10 | Region VII | Bohol | 118562 | Panglao Central ES | PANGLAO | 1 | 1 | 4 | 2STY4CL |  | 10454982.275 |  | COMPLETED | 1 | [11 empty] | 0
39740 | NC 2019 | K10 | Region VII | Bohol | 118023 | Quirino PS | BATUAN | 3 | 1 | 2 | 1STY2CL |  | 4390167.0976 |  | COMPLETED | 1 | [11 empty] | 0
39741 | NC 2019 | K10 | Region VII | Bohol | 118039 | Sagasa ES | BIEN UNIDO | 2 | 1 | 2 | 1STY2CL |  | 2988873.4698 |  | COMPLETED | 1 | [11 empty] | 0
39742 | NC 2019 | K10 | Region VII | Bohol | 118723 | San Agustin Elementary School | TALIBON | 2 | 1 | 2 | 1STY2CL |  | 2817025 |  | COMPLETED | 1 | [11 empty] | 0
39743 | NC 2019 | K10 | Region VII | Bohol | 118723 | San Agustin Elementary School | TALIBON | 2 |  | 2 | 1STY2CL |  | 3402827.855 |  | COMPLETED | 1 | [11 empty] | 0
39744 | NC 2019 | K10 | Region VII | Bohol | 117964 | Talisay PS | ANDA | 3 | 1 | 4 | 1STY4CL |  | 7422886.8899 |  | COMPLETED | 1 | [11 empty] | 0
39745 | NC 2019 | K10 | Region VII | Bohol | 118564 | Tawala ES | PANGLAO | 1 | 1 | 2 | 1STY2CL |  | 5112810.15 |  | COMPLETED | 1 | [11 empty] | 0
39746 | NC 2019 | K10 | Region VII | Carcar City | 500726 | Puesto Integrated School | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL |  | 12899852.9694 |  | completed | 1 | [11 empty] | 0
39747 | NC 2019 | K10 | Region VII | Cebu | 118917 | Argao I Central ES | ARGAO | 2 | 1 | 8 | 2STY8CL |  | 22343418.2475 |  | completed | 1 | [11 empty] | 0
39748 | NC 2019 | K10 | Region VII | Cebu | 119472 | Bacay ES | MINGLANILLA | 1 | 1 | 12 | 4STY12CL |  | 42401040.6961 |  | completed | 1 | [11 empty] | 0
39749 | NC 2019 | K10 | Region VII | Cebu | 118998 | Basiao PS | BADIAN | 7 | 1 | 2 | 1STY2CL |  | 4106081.3043 |  | completed | 1 | [11 empty] | 0
39750 | NC 2019 | K10 | Region VII | Cebu | 118998 | Basiao PS | BADIAN | 7 |  | 2 | 1STY2CL |  | 4106081.3043 |  | completed | 1 | [11 empty] | 0
39751 | NC 2019 | K10 | Region VII | Cebu | 119316 | Casay ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL |  | 13627365.455 |  | completed | 1 | [11 empty] | 0
39752 | NC 2019 | K10 | Region VII | Cebu | 119409 | Ernesto V. Veloso ES (Cabadiangan ES) | LILOAN | 5 | 1 | 4 | 2STY4CL |  | 9552777.9489 |  | completed | 1 | [11 empty] | 0
39753 | NC 2019 | K10 | Region VII | Cebu | 119561 | Lamac ES | PINAMUNGAHAN | 3 | 1 | 12 | 4STY12CL |  | 39448812.1602 |  | completed | 1 | [11 empty] | 0
39754 | NC 2019 | K10 | Region VII | Cebu | 119303 | Libo PS | DALAGUETE | 2 | 1 | 4 | 2STY4CL |  | 12542361.5095 |  | completed | 1 | [11 empty] | 0
39755 | NC 2019 | K10 | Region VII | Cebu | 119322 | Malones Elementary School | DALAGUETE | 2 | 1 | 4 | 2STY4CL |  | 12391986.5095 |  | completed | 1 | [11 empty] | 0
39756 | NC 2019 | SHS | Region VII | Cebu | 302963 | Paypay NHS | DAANBANTAYAN | 4 | 1 | 10 | 3STY10CL |  | 30567091.6612 |  | completed | 1 | [11 empty] | 0
39757 | NC 2019 | K10 | Region VII | Cebu | 119247 | Polog ES | CONSOLACION | 6 | 1 | 2 | 1STY2CL |  | 4178445.8144 |  | completed | 1 | [11 empty] | 0
39758 | NC 2019 | K10 | Region VII | Cebu | 119862 | Secante Bag-o PS | TUDELA | 5 | 1 | 6 | 2STY6CL |  | 12238899.9274 |  | completed | 1 | [11 empty] | 0
39759 | NC 2019 | K10 | Region VII | Cebu | 119422 | Tiltilon ES | LILOAN | 5 | 1 | 12 | 4STY12CL |  | 33384584.508 |  | completed | 1 | [11 empty] | 0
39760 | NC 2019 | K10 | Region VII | Cebu City | 119872 | Cambinocot ES | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL |  | 24130195.2605 |  | COMPLETED | 1 | [11 empty] | 0
39761 | NC 2019 | K10 | Region VII | Cebu City | 119869 | Sinsin ES | CEBU CITY (Capital) | 2 | 1 | 6 | 3STY6CL |  | 20265495.2246 |  | completed | 1 | [11 empty] | 0
39762 | NC 2019 | K10 | Region VII | City of Naga, Cebu | 302929 | Balirong National High School | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL |  | 13311193.1654 |  | COMPLETED | 1 |  |  |  | 19-HE-0103 |  | 2019-08-02 | 2019-08-14 |  |  |  |  | 0
39763 | NC 2019 | SHS | Region VII | Danao City | 322001 | Ubaldo Iway Memo. NHS | DANAO CITY | 5 | 1 | 6 | 2STY6CL |  | 11656095.169 |  | COMPLETED | 1 | [11 empty] | 0
39767 | NC 2019 | SHS | Region VII | Mandaue City | 303194 | Cabancalan NHS | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL |  | 18426169.347 |  | COMPLETED | 1 | [11 empty] | 0
39785 | NC 2019 | SHS | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL |  | 4535390.6511 |  | Completed | 1 | [11 empty] | 0
39786 | NC 2019 | K10 | Region VII | Toledo City | 120745 | Ibo Elementary School | TOLEDO CITY | 3 | 1 | 9 | 3STY9CL |  | 28260329.3067 |  | COMPLETED | 1 | [11 empty] | 0
40449 | NC 2020 | SHS | Region VII | Bohol | 302819 | Busao National High School | MARIBOJOC | 1 | 1 | 6 | 1unit 4STY4 lab |  | 28390800 |  |  | completed | 1
40450 | NC 2020 | K10 | Region VII | Bohol | 118029 | Bilangbilangan East PS | BIEN UNIDO | 2 | 1 | 2 | 1STY2CL |  | 4852018.28 |  |  | completed | 1
40451 | NC 2020 | K10 | Region VII | Bohol | 118034 | Maomawan ES | BIEN UNIDO | 2 | 1 | 2 | 1STY2CL |  | 4852018.28 |  |  | completed | 1
40452 | NC 2020 | K10 | Region VII | Bohol | 118070 | Cambus-oc ES | BUENAVISTA | 2 | 1 | 2 | 1STY2CL |  | 4341232.88 |  |  | completed | 1
40453 | NC 2020 | K10 | Region VII | Bohol | 118072 | Cantores PS | BUENAVISTA | 2 | 1 | 2 | 1STY2CL |  | 4341232.88 |  |  | completed | 1
40454 | NC 2020 | K10 | Region VII | Bohol | 118082 | Overland ES | BUENAVISTA | 2 | 1 | 2 | 1STY2CL |  | 4341232.88 |  |  | completed | 1
40455 | NC 2020 | K10 | Region VII | Bohol | 118186 | Bonbon Elementary School | CLARIN | 2 | 1 | 2 | 1STY2CL |  | 4497620.36 |  |  | completed | 1
40456 | NC 2020 | K10 | Region VII | Bohol | 118192 | Cantoyoc PS | CLARIN | 2 | 1 | 2 | 1STY2CL |  | 4341232.88 |  |  | completed | 1
40457 | NC 2020 | TVL | Region VII | Bohol | 118749 | Guinobatan ES | TRINIDAD | 2 | 1 | 6 | 2 Sty, 6 CL Regular Workshop |  | 16424189.23 |  |  | completed | 1
40458 | NC 2020 | TVL | Region VII | Bohol | 118759 | Mahagbu ES | TRINIDAD | 2 | 1 | 4 | 2 Sty 4 CL (Regular Workshop) |  | 13676945.58 |  |  | completed | 1
40459 | NC 2020 | K10 | Region VII | Bohol | 118768 | Trinidad Central Elementary School | TRINIDAD | 2 | 1 | 8 | Modified Standard 2 STY, 8CL |  | 22690056.01 |  |  | completed | 1
40460 | NC 2020 | K10 | Region VII | Bohol | 118424 | Jagna Central ES | JAGNA | 3 | 1 | 2 | 1STY2CL |  | 5513750 |  |  | completed | 1
40461 | NC 2020 | SHS | Region VII | Bohol | 302860 | Katipunan NHS | CARMEN | 3 | 1 | 8 | 2STY8CL |  | 24702058.04 |  |  | completed | 1
40462 | NC 2020 | K10 | Region VII | Cebu | 119477 | Minglanilla Central ES | MINGLANILLA | 1 | 1 | 8 | 4STY8CL |  | 26004445.5 |  |  | completed | 1
40463 | NC 2020 | K10 | Region VII | Cebu | 312472 | Badian NHS - Sanlagan Ext. | BADIAN | 2 | 1 | 6 | 2STY6CL |  | 17543750 |  |  | COMPLETED | 1
40464 | NC 2020 | K10 | Region VII | Cebu | 500487 | Minolos IS | BARILI | 3 | 1 | 12 | 4STY12CL |  | 39021945.87 |  |  | completed | 1
40465 | NC 2020 | K10 | Region VII | Cebu | 119266 | Daanbantayan Central ES | DAANBANTAYAN | 4 | 1 | 12 | 4STY12CL |  | 35406257.75 |  |  | COMPLETED | 1
40466 | NC 2020 | SHS | Region VII | Cebu | 500655 | Bagalnga Integrated School | COMPOSTELA | 5 | 1 | 12 | 4STY12CL |  | 36420261.13 |  |  | completed | 1
40467 | NC 2020 | K10 | Region VII | Cebu | 119257 | Gabi ES | CORDOBA | 6 | 1 | 6 | 3STY6CL |  | 18259500.34 |  |  | completed | 1
40468 | NC 2020 | K10 | Region VII | Cebu | 500894 | Ginatilan Integrated School | GINATILAN | 7 | 1 | 8 | 4STY8CL |  | 24710864.2 |  |  | completed | 1
40485 | NC 2020 | K10 | Region VII | Tagbilaran City | 118713 | Tagbilaran City Central Elementary School | TAGBILARAN CITY (Capital) | 1 | 1 | 24 | 4STY24CL |  | 57228955.6 |  |  | COMPLETED | 1
40486 | NC 2020 | SHS | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 | 1 | 12 | 4STY12CL |  | 37503994.17 |  |  | completed | 1
40487 | NC 2020 | SHS | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 |  | 20 | 4STY20CL |  | 52701826 |  |  | completed | 1
40488 | NC 2020 | SHS | Region VII | Tagbilaran City | 302876 | Tagbilaran City Science High School | TAGBILARAN CITY (Capital) | 1 | 1 | 4 | 4 Sty, 4 Lab |  | 29704469.99 |  |  | Completed | 1
40489 | NC 2020 | K10 | Region VII | Talisay City | 119803 | Tabunoc Central Elem. School | CITY OF TALISAY | 1 | 1 | 16 | 4STY16CL |  | 41637101.72 |  |  | completed | 1
41265 | NC 2021 | K10 | Region VII | Bohol | 117930 | Bahi PS | ALBURQUERQUE | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 751574.25 | 749700 | 744700 | Completed | 1 | 2021-11-28 | 2021-11-19 | P00575142VS | 21HA0192 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-12 | 2021-09-28 | C. JANSEN CONSTRUCTION AND GENEREAL MERCHANDISE
41266 | NC 2021 | K10 | Region VII | Bohol | 117967 | Angilan ES | Antequera | 1 | 1 | 3 | Construction/Completion (1STY3CL) |  | 408188.9275 | 407171 | 404976.36 | Completed | 1 | 2021-11-28 | 2021-10-25 | P00575143VS | 21HA0193 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-12 | 2021-09-30 | GAIL CONSTRUCTION & SUPPLY
41267 | NC 2021 | K10 | Region VII | Bohol | 117985 | Tanday ES | BACLAYON | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 426944.7 | 425880 | 420880 | Completed | 1 | 2021-11-26 | 2021-11-19 | P00575144VS | 21HA0188 | 2021-07-07 | 2021-07-14 | 2021-07-26 | 2021-08-10 | 2021-09-28 | C. JANSEN CONSTRUCTION AND GENEREAL MERCHANDISE
41268 | NC 2021 | K10 | Region VII | Bohol | 118213 | New Lourdes ES | CORTES | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 399634.595 | 398638 | 397660.11 | Completed | 1 | 2021-11-28 | 2021-11-08 | P00575145VS | 21HA0194 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-12 | 2021-09-30 | 3N CONSTRUCTION & SUPPLY
41269 | NC 2021 | K10 | Region VII | Bohol | 118481 | Cantaongon ES | Loon North | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 381314.91 | 380364 | 375337 | Completed | 1 | 2021-11-28 | 2021-10-25 | P00575146VS | 21HA0195 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-12 | 2021-09-30 | 3N CONSTRUCTION & SUPPLY
41270 | NC 2021 | K10 | Region VII | Bohol | 118564 | Tawala ES | PANGLAO | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 435786.75 | 434700 | 429700 | Completed | 1 | 2021-11-26 | 2021-11-19 | P00575147VS | 21HA0189 | 2021-07-07 | 2021-07-14 | 2021-07-26 | 2021-08-10 | 2021-09-28 | C. JANSEN CONSTRUCTION AND GENEREAL MERCHANDISE
41271 | NC 2021 | SHS | Region VII | Bohol | 305543 | Felix E. Bompat High School | PANGLAO | 1 | 1 | 4 | Construction/Completion (4CL) |  | 38095000 | 38000000 | 37429645.88 | COMPLETED | 1 | 2022-04-24 |  | P00575144VS | 21HA0187 | 2021-07-07 | 2021-07-14 | 2021-07-26 | 2021-08-10 | 2021-09-27 | BNYU DEVELOPMENT CORP. | Delivery of materials may cause delay due to unpassable road, muddy when rain falls
41272 | NC 2021 | SHS | Region VII | Bohol | 500211 | San Roque Integrated School | BALILIHAN | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 19248000 | 19200000 | 18831184.62 | Completed | 1 | 2022-02-28 |  | P00575144VS | 21HA0191 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-12 | 2021-09-27 | LAWRENCE BUILDERS & SUPPLY | Building Permit on process
41273 | NC 2021 | K10 | Region VII | Bohol | 118039 | Sagasa ES | BIEN UNIDO | 2 | 1 | 2 | Construction/Completion (1STY2CL) |  | 1047888.3178 | 1045275.13 |  | Completed | 1 |  | 2021-11-15
41274 | NC 2021 | K10 | Region VII | Bohol | 118723 | San Agustin Elementary School | TALIBON | 2 | 1 | 2 | Construction/Completion (1STY2CL) |  | 460620.9507 | 459472.27 |  | Completed | 1
41275 | NC 2021 | K10 | Region VII | Bohol | 118723 | San Agustin Elementary School | TALIBON | 2 |  | 2 | Construction/Completion (1STY2CL) |  | 1100664.79 | 1097919.99 |  | Completed | 1
41276 | NC 2021 | K10 | Region VII | Bohol | 117964 | Talisay PS | ANDA | 3 | 1 | 4 | Construction/Completion (1STY4CL) |  | 1561182.1423 | 1557288.92 |  | Completed | 1
41277 | NC 2021 | K10 | Region VII | Bohol | 118277 | Lapsaon ES | DIMIAO | 3 | 1 | 2 | Construction/Completion (1STY2CL) |  | 803470.5071 | 801466.84 |  | Completed | 1
41278 | NC 2021 | K10 | Region VII | Bohol | 186501 | Pagahat ES | ALICIA | 3 | 1 | 2 | Construction/Completion (1STY2CL) |  | 859370.9497 | 857227.88 |  | Completed | 1
41279 | NC 2021 | SHS | Region VII | Carcar City | 500726 | Puesto Integrated School | CITY OF CARCAR | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 6494267.591 | 6478072.41 |  | COMPLETED | 1
41280 | NC 2021 | K10 | Region VII | Cebu | 119305 | Mantalongon ES | DALAGUETE | 2 | 1 | 9 | Construction of Slope Protection |  | 721634.5975 | 719835.01 |  | COMPLETED | 1
41281 | NC 2021 | SHS | Region VII | Cebu | 303089 | San Sebastian NHS | SAMBOAN | 2 | 1 | 16 | Construction/Completion (4STY16CL) |  | 941800.6099 | 939451.98 |  | COMPLETED | 1
41282 | NC 2021 | K10 | Region VII | Cebu | 119420 | Tabla ES | LILOAN | 5 | 1 | 4 | Construction (1 UNIT 1STY2CL) |  | 4210500 | 4200000 |  | COMPLETED | 1
41283 | NC 2021 | SHS | Region VII | Cebu | 303011 | Lanipga NHS | CONSOLACION | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 6484523.3612 | 6468352.48 |  | COMPLETED | 1
41284 | NC 2021 | K10 | Region VII | Cebu | 119382 | Tapon ES | DUMANJUG | 7 | 1 | 10 | Construction/Completion (2STY10CL) |  | 293122.6492 | 292391.67 |  | COMPLETED | 1
41285 | NC 2021 | SHS | Region VII | Cebu City | 303131 | Binaliw NHS | CEBU CITY (Capital) | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 2040433.4728 | 2035345.11 |  | COMPLETED | 1
41286 | NC 2021 | SHS | Region VII | Cebu City | 303132 | Lusaran NHS | CEBU CITY (Capital) | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 348504.3983 | 347635.31 |  | COMPLETED | 1
41287 | NC 2021 | SHS | Region VII | Cebu City | 303155 | TEJERO NHS(DAY & NIGHT) | CEBU CITY (CAPITAL) | 1 | 1 | 12 | Construction/Completion (4STY12CL) |  | 813869.6201 | 811840.02 |  | COMPLETED | 1
41288 | NC 2021 | SHS | Region VII | Cebu City | 500227 | TAPTAP IS | CEBU CITY (CAPITAL) | 1 | 1 | 6 | Construction/Completion (3STY6CL) |  | 1160622.5706 | 1157728.25 |  | COMPLETED | 1
41289 | NC 2021 | TVL | Region VII | Cebu City | 303133 | DON VICENTE RAMA MEM. NHS (BASAK NHS) | CEBU CITY (CAPITAL) | 2 | 1 | 1 | Construction/Completion (SHS UNIQUE WORKSHOP) |  | 368298.5502 | 367380.1 |  | COMPLETED | 1
41290 | NC 2021 | TVL | Region VII | Cebu City | 303164 | SUDLON NHS | CEBU CITY (CAPITAL) | 2 | 1 | 1 | Construction/Completion (SHS UNIQUE WORKSHOP) |  | 289807.2213 | 289084.51 |  | COMPLETED | 1
41291 | NC 2021 | SHS | Region VII | Cebu City | 312502 | BABAG HS | CEBU CITY (CAPITAL) | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1935394.8711 | 1930568.45 |  | COMPLETED | 1
41292 | NC 2021 | SHS | Region VII | Cebu City | 312507 | PAMUTAN INTEGRATED SCHOOL | CEBU CITY (CAPITAL) | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1999454.0798 | 1994467.91 |  | COMPLETED | 1
41293 | NC 2021 | K10 | Region VII | Cebu City | 312515 | Quiot High School | CEBU CITY (CAPITAL) | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 2671353.6699 | 2664691.94 |  | COMPLETED | 1
41294 | NC 2021 | TVL | Region VII | Cebu City | 500225 | Tabunan Integrated School | CEBU CITY (Capital) | 2 | 1 | 1 | Construction/Completion (1 unit Standard Technical and Vocational Building) |  | 1023904.3374 | 1021350.96 |  | COMPLETED | 1
41299 | NC 2021 | K10 | Region VII | Mandaue City | 119995 | Mayor A.S. Fortuna Memorial ES | MANDAUE CITY | 6 | 1 | 8 | Construction/Completion (4STY8CL) |  | 2122608.7887 | 2117315.5 |  | COMPLETED | 1
41323 | NC 2021 | K10 | Region VII | Tagbilaran City | 118712 | San Isidro ES | Tagbilaran City | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 717469.2 | 715680 |  | Completed | 1
41324 | NC 2021 | K10 | Region VII | Tagbilaran City | 118714 | Taloto ES | Tagbilaran City | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 701048.25 | 699300 |  | Completed | 1 | [9 empty] | C. Jansen Construction and General Merchandise
41701 | NC 2022 | K10 | Region VII | Bohol | 117934 | Tagbuane Elementary School | ALBURQUERQUE | 1 | 1 | 2 | 1STY2CL | 2 |  | 7352335 | 7334000 | Completed | 1 | 2023-04-29 | 2023-06-25 | P00675014VS | 22HA0182 | 2022-04-11 | 2022-11-15 | 2022-11-28 | 2022-11-29 | 2022-12-12 | GERSON Construction and Hardware Supply | The project was issued with Monthly Time Suspension due to unfavorable weather condition. PCMA update is on process due to revised construction shcedule and will be updated once approved by the BOC.
41702 | NC 2022 | K10 | Region VII | Bohol | 186510 | Pandol Primary School | CORELLA | 1 | 1 | 2 | 1STY2CL | 2 |  | 7300205 | 7281995.1 | Completed | 1 | 2023-05-27 | 2023-03-29 | P00675015VS | 22HA0183 | 2022-04-11 | 2022-11-15 | 2022-11-28 | 2022-12-28 | 2023-09-01 | LAWRENCE Builders & Supply | The project is already completed at site. PCMA Data Correction is for approval due to approved Variation Order. Project status will be updated once approved by the BOC.
41703 | NC 2022 | K10 | Region VII | Bohol | 305722 | De La Paz High School | CORTES | 1 | 1 | 2 | 1STY2CL | 2 |  | 7300205 | 7139785.54 | Completed | 1 | 2023-05-27 | 2023-06-26 | P00675016VS | 22HA0184 | 2022-04-11 | 2022-11-15 | 2022-11-28 | 2022-12-28 | 2023-09-01 | SLP Construction | The project was issued with Monthly Time Suspension due to unfavorable weather condition. PCMA update is on process due to revised construction shcedule and will be updated once approved by the BOC.
41704 | NC 2022 | K10 | Region VII | Bohol | 118227 | Mahayag Elementary School | DAGOHOY | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4979901.4 | Completed | 1 | 2023-05-17 | 2023-03-07 | P00675018VS | 22HC0119 | 2022-11-29 | 2022-11-28 | 2022-12-19 | 2022-12-21 | 2023-04-01 | RAMYER CONST. & SUPPLY | Issued Monthly Time Suspension
41705 | NC 2022 | K10 | Region VII | Bohol | 117954 | Bacong ES | ANDA | 3 | 1 | 2 | 1STY2CL | 2 |  | 6107077.7202 | 6091553.91 | Completed | 1 | 2023-03-05 | 2023-03-05 | P00675021VS-CW1 | 22HB0158 | 2022-11-28 | 2022-07-12 | 2022-12-20 | 2022-12-27 | 2023-04-01 | WBV CONSTRUCTION | With approved Contract Time Extension of 30 CD.
41706 | NC 2022 | K10 | Region VII | Bohol | 118019 | Garcia ES | BATUAN | 3 | 1 | 2 | 1STY2CL | 2 |  | 6107077.7202 | 6027541.75 | Completed | 1 | 2023-03-04 | 2023-04-21 | P00675022VS-CW1 | 22HB0157 | 2022-11-28 | 2022-07-12 | 2022-12-20 | 2022-12-27 | 2023-04-01 | ALAY BALAY DEVELOPMENT CORP | Awaiting for the aprroval of Contract Time Extension for 18 CD
41707 | NC 2022 | K10 | Region VII | Bohol | 118671 | Magsaysay ES | SEVILLA | 3 | 1 | 2 | 1STY2CL | 2 |  | 6107077.7202 | 5973898.36 | Completed | 1 | 2023-03-04 | 2023-02-06 | P00675023VS-CW1 | 22HB0156 | 2022-11-28 | 2022-07-12 | 2022-12-20 | 2022-12-27 | 2023-04-01 | WILTAN CONSTRUCTION | Variation Order & Request for Contract Time Extension on process.
41708 | NC 2022 | K10 | Region VII | Cebu | 119266 | Daanbantayan Central ES | DAANBANTAYAN | 4 | 1 | 12 | 4STY12CL | 2 |  | 32186354.2225 | 32075000 | Completed | 1 | 2023-06-05 | 2023-11-21 | P00675024VS-CW1 | 22HD0068 | 2022-07-06 | 2022-07-13 | 2022-07-25 | 2022-11-14 | 2022-11-23 | TRIUNE MACRO BUILDERS JV WITH ANGAS CONSTRUCTION
41709 | NC 2022 | K10 | Region VII | Cebu | 501669 | Hagnaya IS | SAN REMIGIO | 4 | 1 | 12 | 3STY12CL | 2 |  | 32186354.2225 | 32076089 | Ongoing | 0.95 | 2023-05-31 |  | P00675025VS-CW1 | 22HD0069 | 2022-07-06 | 2022-07-13 | 2022-07-25 | 2022-11-14 | 2022-11-23 | SAN NARCISO BUILDERS CORPORATION
41827 | NC 2022 | SHS | Region VII | Bohol | 500217 | Danahaw IS | CLARIN | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4950000 | Completed | 1 | 2023-05-17 | 2023-08-08 | P00675017VS | 22HC0118 | 2022-11-29 | 2022-11-28 | 2022-12-19 | 2022-12-21 | 2023-04-01 | MAI CONST & SUPPLY | Issued Monthly Time Suspension
41828 | NC 2022 | SHS | Region VII | Bohol | 312327 | Candungao High School | SAN ISIDRO | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4999998.53 | Completed | 1 | 2023-05-17 | 2023-07-08 | P00675019VS | 22HC0120 | 2022-11-29 | 2022-11-28 | 2022-12-19 | 2022-12-21 | 2023-04-01 | MAI CONST & SUPPLY | Issued Monthly Time Suspension
41829 | NC 2022 | SHS | Region VII | Bohol | 303130 | Erico B. Aumentado High School | UBAY | 2 | 1 | 12 | 4STY12CL | 2 |  | 38190237.5 | 38029995.58 | Ongoing | 0.8 | 2024-09-05 |  | P00655020VS | 22HC0121 | 2023-09-06 | 2023-10-06 | 2023-06-29 | 2023-08-14 | 2023-08-05 | DINA RBS & SUPPLY INC. | Issued Notice To Proceed dated May 9, 2023
41830 | NC 2022 | SHS | Region VII | Cebu | 303032 | Dapdap NHS | PILAR | 5 | 1 | 12 | 2UNITS 3STY6CL | 2 |  | 33384584.508 | 33266500 | Ongoing | 0.95 | 2023-11-05 |  | P00675026VS-CW1 | 22HI0077 | 2022-11-19 | 2022-11-28 | 2022-12-12 | 2022-12-23 | 2023-01-10 | MPJR BUILDERS COMPANY
41831 | NC 2022 | SHS | Region VII | Cebu | 303080 | Puertobello NHS | TUDELA | 5 | 1 | 6 | 3STY6CL | 2 |  | 17544375.56 | 17470514 | Ongoing | 0.95 | 2023-07-08 |  | P00675027VS-CW1 | 22HI0078 | 2022-11-19 | 2022-11-28 | 2022-12-12 | 2022-12-23 | 2023-01-10 | CYJE FIRST BUILDERS CONSTRUCTION CORP | FOR PUNCHLIST COMPLIANCE
42578 | NC 2023 | K10 | Region VII | Bohol | 118004 | Dorol ES | BALILIHAN |  | 1 | 5 |  | Batch 1 | 14556262.5 | 14430000 | 14361419.81 | Completed | 1 | 2024-05-24 | 2023-12-15 | P00775086VS | 23HA0108 | 2023-07-06 | 2023-07-14 | 2023-07-26 | 2023-07-28 | 2023-08-08 | 3N Construction & Supply
42579 | NC 2023 | K10 | Region VII | Bohol | 500211 | San Roque Integrated School | BALILIHAN |  | 1 | 6 |  | Batch 1 | 18422474.39 | 18262675.97 | 18242123.89 | Completed | 1 | 2024-02-15 | 2024-02-15 | P00775087VS | 23HA0116 | 2023-08-08 | 2023-08-15 | 2023-08-29 | 2023-08-31 | 2023-09-11 | 3N Construction & Supply
42580 | NC 2023 | K10 | Region VII | Bohol | 305722 | De La Paz High School | CORTES |  | 1 | 2 |  | Batch 1 | 6556875 | 6500000 | 6440000 | Completed | 1 | 2023-12-26 | 2023-06-26 | P00775088VS | 23HA0109 | 2023-07-06 | 2023-07-14 | 2023-07-26 | 2023-07-28 | 2023-08-08 | 3N Construction & Supply
42581 | NC 2023 | K10 | Region VII | Bohol | 118063 | Bato Elementary School | BUENAVISTA |  | 1 | 0 |  | Batch 1 | 5043750 | 5000000 | 4321958.33 | Completed | 1 | 2024-03-22 | 2023-06-27 | P00775089VS | 23HC0124 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-09-20 | 2023-10-04 | 3N CONST. & SUPPLY
42582 | NC 2023 | SHS | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN |  | 1 | 4 |  | Batch 1 | 11065987.5 | 10970000 | 9648940.65 | Completed | 1 | 2024-04-29 | 2023-06-27 | P00775090VS | 23HC0129 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-08-30 | 2023-10-04 | WYNN CONST.
42583 | NC 2023 | SHS | Region VII | Bohol | 302840 | Dagohoy NHS | DAGOHOY |  | 1 | 8 |  | Batch 1 | 26731875 | 26500000 | 22125830 | Ongoing | 1 | 2024-06-05 | 2024-06-05 | P00775093VS | 23HC0133 | 2023-08-29 | 2023-08-18 | 2023-09-11 | 2023-09-23 | 2023-10-04 | MAI CONST. & SUPPLY
42584 | NC 2023 | K10 | Region VII | Bohol | 118227 | Mahayag Elementary School | DAGOHOY |  | 1 | 2 |  | Batch 1 | 5548125 | 5500000 | 5498000 | Completed | 1 | 2024-01-08 | 2024-01-08 | P00775091VS | 23HC0126 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-08-08 | 2024-01-08 | C. JANSEN CONST & GEN. MDSE
42585 | NC 2023 | K10 | Region VII | Bohol | 118231 | Sta. Cruz ES | DAGOHOY |  | 1 | 2 |  | Batch 1 | 5548125 | 5500000 | 4,365.554.94 | Completed | 1 | 2024-02-23 | 2023-06-27 | P00775092VS | 23HC0125 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-08-30 | 2023-09-13 | SOMBRIO CONST. & SUPPLY
42586 | NC 2023 | K10 | Region VII | Bohol | 305721 | Canmaya Diot High School | SAGBAYAN (BORJA) |  | 1 | 6 |  | Batch 1 | 20175000 | 20000000 | 19887935.92 | Completed | 1 | 2024-04-25 | 2023-07-26 | P00775094VS | 23HC0130 | 2023-07-26 | 2023-08-04 | 2023-08-16 | 2023-08-28 | 2023-09-08 | CLAVITE CONST. & SUPPLY
42587 | NC 2023 | K10 | Region VII | Bohol | 118635 | Cambansag Elementary | SAN ISIDRO |  | 1 | 2 |  | Batch 1 | 5548125 | 5500000 | 5069409.47 | Completed | 1 | 2024-03-15 | 2024-03-15 | P00775095VS | 23HC0127 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-09-10 | 2023-09-22 | ROSEJEL CONST.
42588 | NC 2023 | K10 | Region VII | Bohol | 118640 | Masonoy PS | SAN ISIDRO |  | 1 | 2 |  | Batch 1 | 5749875 | 5700000 | 5688983.2 | Completed | 1 | 2024-04-10 | 2023-06-27 | P00775096VS | 23HC0128 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-08-17 | 2023-08-22 | MAI CONST. & SUPPLY
42589 | NC 2023 | K10 | Region VII | Bohol | 118801 | Achila Elementary School | UBAY |  | 1 | 0 |  | Batch 1 | 5043750 | 5000000 | 4990000 | Completed | 1 | 2024-02-14 | 2024-02-14 | P00775097 | 23HC0123 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-09-21 | 2024-02-14 | MAI CONST. & SUPPLY
42590 | NC 2023 | SHS | Region VII | Bohol | 302809 | Alicia Technical Vocational HS | ALICIA |  | 1 | 1 |  | Batch 1 | 3362499.67 | 3333333 | 3306436.48 | Completed | 1 | 2023-10-09 | 2023-10-09 | P00775098VS-CW1 | 23HB0154 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-04 | REBER ENTERPRISES AND CONSTRUCTION
42591 | NC 2023 | SHS | Region VII | Bohol | 302829 | Candabong National High School | ANDA |  | 1 | 1 |  | Batch 1 | 3362499.67 | 3333333 | 3306794.91 | Completed | 1 | 2023-10-16 | 2023-10-16 | P00775099VS-CW1 | 23hb0150 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-14 | WBV CONSTRUCTION
42592 | NC 2023 | SHS | Region VII | Bohol | 312314 | Quezon HS | BATUAN |  | 1 | 6 |  | Batch 1 | 18745937.17 | 15250000 | 15383437.5 | Completed | 1 | 2024-02-06 |  | P00775100VS-CW1 | 23HB0159 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-04 | ALAY BALAY DEVELOPMENT CORP.
42593 | NC 2023 | K10 | Region VII | Bohol | 118308 | Candulao ES | GARCIA HERNANDEZ |  | 1 | 1 |  | Batch 1 | 3362499.67 | 3333333 | 3333333 | Completed | 1 | 2023-10-16 | 2023-10-16 | P00775102VS-CW1 | 23HB0156 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-14 | JEGSTONE CONSTRUCTION
42594 | NC 2023 | K10 | Region VII | Bohol | 118466 | Loboc Central Elementary School | LOBOC |  | 1 | 1 |  | Batch 1 | 3362499.67 | 3333333 | 3303051.59 | Completed | 1 | 2023-12-14 |  | P00775103VS-CW1 | 23hb0151 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-11 | RONNYL CONSTRUCTION
42595 | NC 2023 | SHS | Region VII | Bohol | 302837 | Concepcion NHS | MABINI |  | 1 | 1 |  | Batch 1 | 3362499.67 | 3333333 | 3306809.94 | Completed | 1 | 2023-10-16 | 2023-11-20 | P00775104VS-CW1 | 23HB0155 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 373870 | WBV CONSTRUCTION
42596 | NC 2023 | SHS | Region VII | Bohol | 302903 | Sevilla National High School | SEVILLA |  | 1 | 1 |  | Batch 1 | 3362499.67 | 3333333 | 3306507.15 | Completed | 1 | 2023-10-09 | 2023-10-09 | P00775105VS-CW1 | 23HB0157 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-04 | VNCO CONSTRUCTION
42597 | NC 2023 | SHS | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES |  | 1 | 1 |  | Batch 1 | 3362499.67 | 3333333 | 3307340.7 | Completed | 1 | 2023-10-16 | 2023-10-16 | P00775106VS-CW1 | 23HB0153 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-14 | VNCO CONSTRUCTION
42598 | NC 2023 | SHS | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA |  | 1 | 1 |  | Batch 1 | 3362499.67 | 3333333 | 3306542.84 | Completed | 1 | 2023-10-15 | 2023-10-15 | P00775107VS-CW1 | 23HB0152 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-11 | JEGSTONE CONSTRUCTION
42600 | NC 2023 | K10 | Region VII | Cebu | 118917 | Argao I Central ES | ARGAO |  | 1 | 4 |  | Batch 1 | 11451808.45 | 11352474.3 | 11322441 | Completed | 1 | 2024-01-16 | 2025-02-07 | 23HG0066 | P00775109VS | 2023-08-24 | 2023-08-31 | 2023-09-12 | 2023-10-02 | 2023-10-13 | BT CONSTRUCTION AND GENERAL SERVICES
42601 | NC 2023 | K10 | Region VII | Cebu | 118947 | Colawin ES | ARGAO |  | 1 | 4 |  | Batch 1 | 8687799.44 | 8612440.58 | 8571728.27 | Completed | 1 | 2024-01-27 | 2024-06-21 | 23HG0087 | P00775110VS | 2023-11-15 | 2023-11-22 | 2023-12-15 | 2023-12-13 | 2024-01-01 | SERCHER DEVELOPMENT CORPORATION
42602 | NC 2023 | SHS | Region VII | Cebu | 302944 | LUNOP NATIONAL HIGH SCHOOL | BOLJOON |  | 1 | 9 |  | Batch 1 | 34041184.9 | 33745908.2 | 33694237.58 | Ongoing | 0.95 | 2025-04-30 |  | 23HG0067 | P00775111VS | 2023-08-24 | 2023-08-31 | 2023-09-12 | 2023-10-02 | 2023-10-13 | BT CONSTRUCTION AND GENERAL SERVICES
42603 | NC 2023 | SHS | Region VII | Cebu | 303164 | Dumalan NHS | DALAGUETE |  | 1 | 4 |  | Batch 1 | 11451808.45 | 11352474.3 | 11302474.3 | Ongoing | 0.7 | 2024-01-16 |  | 23HG0068 | P00775112VS | 2023-08-24 | 2023-08-31 | 2023-09-12 | 2023-10-02 | 2023-10-13 | 647 CONSTRUCTION AND DEVELOPMENT CORP. | DUE TO RROW ACCESS
42604 | NC 2023 | K10 | Region VII | Cebu | 119040 | Cornelio C. Melgar Elementary School | BALAMBAN |  | 1 | 6 |  | Batch 1 | 10087500 | 10000000 | 9900000 | Completed | 1 | 2023-11-23 | 2024-04-24 | 23HF0084 | P00775113VS-CW1 | 2023-07-01 | 2023-07-07 | 2023-07-19 | 2023-07-25 | 2023-07-28 | FIRST GRANDEUR BUILDERS
42605 | NC 2023 | SHS | Region VII | Cebu | 302928 | Balao NHS | BARILI |  | 1 | 6 |  | Batch 1 | 20175000 | 20000000 | 19997841.38 | Completed | 1 | 2024-02-15 | 2024-12-19 | 23HF0085 | P00721824VS-CW1 | 2023-08-03 | 2023-08-09 | 2023-08-29 | 2023-09-14 | 2023-09-19 | FDC CONSTRUCTION AND SUPPLIES CO.
42606 | NC 2023 | SHS | Region VII | Cebu | 303068 | Patupat NHS | BARILI |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4722534.5 | Completed | 1 | 2024-01-26 | 2024-03-21 | 23HF0086 | P00775115VS-CW1 | 2023-08-03 | 2023-08-09 | 2023-08-22 | 2023-08-25 | 2023-08-30 | JUGA BUILDERS & CONSTRUCTION SUPPLY
42607 | NC 2023 | K10 | Region VII | Cebu | 305595 | Lusong National High School | TUBURAN |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4725934.5 | Completed | 1 | 2023-12-02 | 2024-06-18 | 23HF0087 | P00775116VS-CW1 | 2023-08-03 | 2023-08-09 | 2023-08-22 | 2023-08-25 | 2023-08-30 | JUGA BUILDERS AND CONSTRUCTION SUPPLY
42608 | NC 2023 | K10 | Region VII | Cebu | 500660 | Gibitngil Integrated School | MEDELLIN |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9933761.62 | Ongoing | 0.95 | 2023-12-02 |  | 23HD0079 | P00775117VS-CW1 | 2023-07-25 | 2023-08-01 | 2023-08-14 | 2023-08-25 | 2023-09-04 | Z & G CONSTRUCTION SERVICES
42609 | NC 2023 | K10 | Region VII | Cebu | 500666 | Calambua Integrated School | SAN REMIGIO |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4735027.84 | Ongoing | 0.95 | 2023-12-02 |  | 23HD0080 | P00775118VS-CW1 | 2023-07-25 | 2023-08-01 | 2023-08-14 | 2023-08-25 | 2023-09-04 | DINAH RBS CONSTRUCTION AND SUPPLY INCORPORATION
42610 | NC 2023 | SHS | Region VII | Cebu | 303041 | Libaong National High School | SAN REMIGIO |  | 1 | 4 |  | Batch 1 | 10087501.01 | 10000001 | 9987996.88 | Ongoing | 0.95 | 2023-11-02 |  | 23HD0081 | P00775119VS-CW1 | 2023-07-25 | 2023-08-01 | 2023-08-14 | 2023-08-25 | 2023-09-04 | DINAH RBS CONSTRUCTION AND SUPPLY INCORPORATION
42611 | NC 2023 | K10 | Region VII | Cebu | 119771 | Kanlim-ao ES | TABUELAN |  | 1 | 4 |  | Batch 1 | 10087502.02 | 10000002 | 9987997.58 | Ongoing | 0.7 | 2023-12-02 |  | 23HD0082 | P00775120VS-CW1 | 2023-07-25 | 2023-08-01 | 2023-08-14 | 2023-08-25 | 2023-09-04 | DINAH RBS CONSTRUCTION AND SUPPLY INCORPORATION
42612 | NC 2023 | SHS | Region VII | Cebu | 303106 | Borbon NHS | BORBON |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4744762.06 | Ongoing | 0.95 | 2023-12-26 |  | 23HI0125 | P00775121VS-CW1 | 2023-07-07 | 2023-07-14 | 2023-07-28 | 2023-08-15 | 2023-08-29 | NOGNOG ENTERPRISES
42613 | NC 2023 | K10 | Region VII | Cebu | 119216 | Catmondaan ES | CATMON |  | 1 | 3 |  | Batch 1 | 10087500 | 10000000 | 9979567.83 | Completed | 1 | 2024-01-27 | 2024-04-05 | 23HI0127 | P00775122VS-CW1 | 2023-07-28 | 2023-08-05 | 2023-08-17 | 2023-08-22 | 2023-08-24 | NEOVENTURES CONSTRUCTION
42614 | NC 2023 | K10 | Region VII | Cebu | 502211 | Basak Integrated School | COMPOSTELA |  | 1 | 3 |  | Batch 1 | 10087500 | 10000000 | 9985380.57 | Ongoing | 0.95 | 2024-01-27 |  | 23HI0126 | P00775123VS-CW1 | 2023-07-28 | 2023-08-05 | 2023-08-17 | 2023-08-22 | 2023-08-31 | WQC DESIGN AND CONSTRUCTION
42615 | NC 2023 | K10 | Region VII | Cebu | 501916 | Catarman Integrated School | LILOAN |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9980000 | Ongoing | 0.95 | 2024-04-25 |  | 23HI0122 | P00775126VS-CW1 | 2023-07-07 | 2023-07-14 | 2023-07-28 | 2023-08-17 | 2023-08-30 | POWER MOVE BUILDERS & CONSTRUCTION SUPPLY | 4STY12CL
42616 | NC 2023 | K10 | Region VII | Cebu | 119413 | Lataban ES | LILOAN |  | 1 | 8 |  | Batch 1 | 10087500 | 10000000 | 9971486.74 | Ongoing | 0.15 | 2024-07-29 |  | 23HI0136 | P00775124VS-CW1 | 2023-11-22 | 2023-11-29 | 2023-12-12 | 2023-12-29 | 2024-01-11 | VSP STRUCTURE VENTURES CORPORATION
42617 | NC 2023 | K10 | Region VII | Cebu | 119417 | Simeon Ayuda ES | LILOAN |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9980000 | Ongoing | 0.95 | 2024-04-25 |  | 23HI0123 | P00775125VS-CW1 | 2023-07-07 | 2023-07-14 | 2023-07-28 | 2023-08-17 | 2023-08-30 | POWER MOVE BUILDERS & CONSTRUCTION SUPPLY
42618 | NC 2023 | K10 | Region VII | Cebu | 502121 | Campo Integrated School | SAN FRANCISCO |  | 1 | 3 |  | Batch 1 | 10087500 | 10000000 | 9989101.61 | Completed | 1 | 2024-01-27 | 2024-01-27 | 23HI0128 | P00775127VS-CW1 | 2023-07-28 | 2023-08-05 | 2023-08-17 | 2023-08-22 | 2023-08-31 | BARR STEEL CONSTRUCTION
42619 | NC 2023 | K10 | Region VII | Cebu | 500498 | Pansoy Integrated School | SOGOD |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4745000 | Completed | 1 | 2023-12-26 | 2024-05-29 | 23HI0124 | P00775128VS-CW1 | 2023-07-07 | 2023-07-14 | 2023-07-28 | 2023-08-15 | 2023-08-29 | DT & C CONSTRUCTION
42620 | NC 2023 | K10 | Region VII | Cebu | 137084 | Pitogo Primary School | CONSOLACION |  | 1 | 12 |  | Batch 1 | 10087500 | 10000000 | 9969817.19 | Ongoing | 0.95 | 2024-02-23 |  | 23HN0149 | P00775130VS-CW1 | 2023-07-06 | 2023-07-13 | 2023-07-25 | 2023-07-27 | 2023-08-04 | GTM Builders & Supply
42621 | NC 2023 | K10 | Region VII | Cebu | 136962 | Tilhaong Primary School | CONSOLACION |  | 1 | 12 |  | Batch 1 | 10087500 | 10000000 | 9893822.42 | Ongoing | 0.95 | 2024-02-16 |  | 23HN0152 | P00775129VS-CW1 | 2023-07-06 | 2023-07-13 | 2023-07-25 | 2023-08-02 | 2023-08-11 | Rudhil Const. & Enterprises, Inc.
42622 | NC 2023 | K10 | Region VII | Cebu | 187025 | Catarman Elementary School | CORDOVA |  | 1 | 6 |  | Batch 1 | 10087500 | 10000000 | 9985000 | Ongoing | 0.95 | 2024-03-19 |  | 23HN0173 | P00775131VS-CW1 | 2023-10-24 | 2023-10-31 | 2023-11-16 | 2023-11-28 | 2023-12-07 | Powermove builders and construction supply
42623 | NC 2023 | K10 | Region VII | Cebu | 118869 | Lawaan ES | ALCANTARA |  | 1 | 12 |  | Batch 1 | 59511206.25 | 58995000 | 58108000 | Ongoing | 0.7 | 2024-03-27 |  | 23HO0234 | P00775132VS-CW1 | 2023-06-15 | 2023-06-10 | 2023-07-04 | 2023-07-11 | 2023-07-24 | QM BUILDERS
42624 | NC 2023 | K10 | Region VII | Cebu | 119008 | Matutinao ES | BADIAN |  | 1 | 5 |  | Batch 1 | 10732989.77 | 10639890.72 | 10628150.72 | Ongoing | 0.95 | 2024-07-18 |  | 23HO0320 | P00775133VS-CW1 | 2023-10-18 | 2023-10-25 | 2023-11-14 | 2024-02-27 | 2024-03-12 | CELJEM CONSTRUCTION & DEVELOPMENT CORP.
42625 | NC 2023 | K10 | Region VII | Cebu | 119405 | Kagsing ES | GINATILAN |  | 1 | 12 |  | Batch 1 | 59511206.25 | 58995000 | 2600000 | Ongoing | 0.9 | 2024-01-18 |  | 23HO0322 | P00775279NP | 2023-10-18 | 2023-10-25 | 2023-11-14 | 2023-11-22 | 2023-12-05 | FIRST GRANDEUR BUILDERS
42626 | NC 2023 | K10 | Region VII | Cebu | 119447 | Montañeza ES | MALABUYOC |  | 1 | 15 |  | Batch 1 | 71154703.13 | 70537500 | 70435888 | Ongoing | 0.9 | 2024-04-11 |  | 23H00233 | P00775135VS-CW1 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-24 | QUIRANTE CONSTRUCTION CORPORATION
42627 | NC 2023 | K10 | Region VII | Cebu | 119596 | Cansalonoy ES | RONDA |  | 1 | 8 |  | Batch 1 | 39674137.5 | 39330000 | 39328142.38 | Ongoing | 0.75 | 2024-04-09 |  | 23H00235 | P00775136VS-CW1 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-24 | ZLREJ TRADING AND CONSTRUCTION CORP./DINAH RBS CONSTRUCTION AND SUPPLY INC (JV)
42628 | NC 2023 | SHS | Region VII | Cebu | 303033 | Langin NHS | RONDA |  | 1 | 6 |  | Batch 1 | 18422474.39 | 18262675.97 | 18260485.96 | Ongoing | 0.95 | 2024-08-08 |  | 23HO0319 | P00775137VS-CW1 | 2023-10-18 | 2023-10-25 | 2023-11-14 | 2024-02-27 | 2024-03-12 | FIRST GRANDEUR BUILDERS
42629 | NC 2023 | K10 | Region VII | Cebu City | 500044 | Mabini Integrated School | CEBU CITY (Capital) |  | 1 | 8 |  | Batch 1 | 15131250 | 15000000 | 14983888.88 | Ongoing | 0.85 | 2024-05-06 |  | P00775139VS-CW1 | 23HH0149 |  | 2023-10-06 | 2023-10-18 | 2023-10-23 | 2023-11-03 | Powerframe Construction | Delayed
42630 | NC 2023 | K10 | Region VII | Cebu City | 119901 | Mabolo ES | CEBU CITY (Capital) |  | 1 | 8 |  | Batch 1 | 15131250 | 15000000 | 14980000 | Ongoing | 0.87 | 2024-05-06 |  | P00775138VS-CW1 | 23HH0148 |  | 2023-10-06 | 2023-10-18 | 2023-10-23 | 2023-11-03 | Planac Construction | Delayed
42631 | NC 2023 | SHS | Region VII | Cebu City | 303141 | Cebu City National Science HS | CEBU CITY (Capital) |  | 1 | 0 |  | Batch 1 | 30262500 | 30000000 | 26356000 | Ongoing | 0.95 | 2024-06-12 |  | P00775140VS-CW1 | 23HH0158 |  | 2023-10-12 | 2023-10-24 | 2023-10-25 | 2023-11-16 | La PruebaConstruction/WTG | Delayed
42636 | NC 2023 | K10 | Region VII | Lapu-Lapu City | 119957 | Sabang Elementary School | LAPU-LAPU CITY (OPON) |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29950003.84 | Completed | 1 | 2024-05-12 | 2024-06-11 | P00775145VS-CW1 | 23HN0151 | 2023-07-06 | 2023-07-13 | 2023-07-25 | 2023-08-02 | 2023-08-11 | Vanguard Builders Inc. | Phase I Only
42637 | NC 2023 | K10 | Region VII | Mandaue City | 120013 | Maguikay ES | MANDAUE CITY |  | 1 | 12 |  | Batch 1 | 30262500 | 30000000 | 29900000 | Ongoing | 0.57 | 2024-04-12 | 2024-10-09 | P00775146VS-CW1 | 23HNO147 | 2023-07-06 | 2023-07-13 | 2023-07-25 | 2023-08-02 | 2023-08-11 | ZLREJ Const. Corp./Dinah RBS Const. & Supply Inc. (JV)
42638 | NC 2023 | K10 | Region VII | Mandaue City | 303196 | Pagsabungan NHS | MANDAUE CITY |  | 1 | 4 |  | Batch 1 | 8687799.44 | 8612440.58 | 8601899.66 | Completed | 1 | 2023-12-13 | 2024-05-19 | P00775147VS-CW1 | 23HNO153 | 2023-07-06 | 2023-07-13 | 2023-08-15 | 2023-08-22 | 2023-08-31 | LRTY Construction & Supply | Completed Phase 1 only
42653 | NC 2023 | K10 | Region VII | Talisay City | 119802 | San Isidro Elementary School | CITY OF TALISAY |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29970000 | Completed | 1 | 2024-04-11 | 2024-04-11 | P00775162VS-CW1 | 23HE0166 | 2023-07-14 | 2023-07-21 | 2023-08-02 | 2023-08-15 | 2023-08-23 | Celjem Construction & Development Corp.
44217 | NC 2024 |  | Region VII | Bogo City | 119107 | Bogo Central School 111 | CITY OF BOGO |  | 1 | 12 | 4STY12CL | BATCH 1 | 42180000 |  | P 41,959,100.00 | Ongoing | 0.9 | 2024-10-12 |  | P00875669VS-CW1 | 24HD0080 | 2024-04-27 | 2024-07-05 | 2024-05-21 | 2024-05-27 | 2024-05-29 | JARC CONSTRUCTION AND MARINE SERVICES CORPORATION
44218 | NC 2024 |  | Region VII | Bohol | 117998 | Boyog ES | BALILIHAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4965000 | Completed | 1 | 2024-09-11 | 2024-10-13 | P00875403VS | 24HA0105 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | GERSON CONSTRUCTION AND HARDWARE SUPPLY | Issued Work Suspension Order due to Unworkable site condition (i.e. unfavorable weather condition at the project site, access to project site not passable)
44219 | NC 2024 |  | Region VII | Bohol | 305719 | Modesto G. Autida High School | BIEN UNIDO |  | 1 | 2 | 2 Classrooms | GAA 17B | 5000000 |  | 4973000 | Completed | 1 | 2024-12-19 |  | P00875413VS | 24HC0096 | 2024-05-20 | 2024-05-27 | 2024-10-06 | 2024-06-28 | 2024-09-07 | C. Jansen Const. & Gen. Mdse. | Completed
44220 | NC 2024 |  | Region VII | Bohol | 118088 | Banlasan ES | CALAPE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967000 | Completed | 1 | 2024-10-11 | 2024-10-11 | P00875409VS | 24HA0113 |  | 2024-04-26 | 2024-05-08 | 2024-05-21 | 2024-06-10 | NENIAL CONSTRUCTION
44221 | NC 2024 |  | Region VII | Bohol | 312319 | Hagbuaya High School | CATIGBIAN |  | 1 | 6 | 2STY6CL | GAA 17B | 10000000 |  | 9928825 | Ongoing | 0.45 | 2025-05-07 |  | P00875412VS | 24HA0154 |  | 2024-09-04 | 2024-09-17 | 2024-10-25 | 2024-12-04 | JA ACHACOSO Enterprises and General Services | Modified to 1STY 3CL
44222 | NC 2024 |  | Region VII | Bohol | 312320 | Haguilanan High School | CATIGBIAN |  | 1 | 6 | 2STY6CL | GAA 17B | 10000000 |  | 9933518.69 | Ongoing | 0.45 | 2025-05-07 |  | P00875411VS | 24HA0155 |  | 2024-09-04 | 2024-09-17 | 2024-10-25 | 2024-12-04 | JA ACHACOSO Enterprises and General Services | Modified to 1STY 3CL
44223 | NC 2024 |  | Region VII | Bohol | 118176 | Liboron ES | CATIGBIAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4951140 | Completed | 1 | 2024-10-11 | 2024-10-11 | P00875410VS | 24HA0114 |  | 2024-04-26 | 2024-05-08 | 2024-05-21 | 2024-06-10 | JJF BUILDERS AND SUPPLY
44224 | NC 2024 |  | Region VII | Bohol | 500212 | Canangcaan Integrated School | CORELLA |  | 1 | 6 | 2STY6CL | BATCH 1 | 19500000 |  | 19372172.54 | Ongoing | 0.6 | 2025-04-05 |  | P00875674VS | 24HA0153 |  | 2024-08-30 | 2024-09-11 | 2024-09-24 | 2024-10-04 | CEMPRON CONSTRUCTION & DEVELOPMENT
44225 | NC 2024 |  | Region VII | Bohol | 118202 | Cancatac ES | CORELLA |  | 1 | 3 | 1STY3CL | BATCH 1 | 8700000 |  | 8636080.4 | Completed | 1 | 2024-11-10 | 2024-11-10 | P00875670VS | 24HA0118 |  | 2024-05-02 | 2024-05-21 | 2024-05-31 | 2024-06-10 | FSB CONSTRUCTION AND SUPPLY
44226 | NC 2024 |  | Region VII | Bohol | 302839 | Corella National High School | CORELLA |  | 1 | 3 | 1STY3CL | BATCH 1 | 8700000 |  | 8651618.47 | Completed | 1 | 2024-11-10 | 2024-11-10 | P00875673VS | 24HA0121 |  | 2024-05-02 | 2024-05-21 | 2024-05-28 | 2024-06-10 | INABANGA DRILLING, CONSTRUCTION, STEEL FABRICATION, AND GEN. MDSE.
44227 | NC 2024 |  | Region VII | Bohol | 118204 | Sambog ES | CORELLA |  | 1 | 3 | 1STY3CL | BATCH 1 | 8700000 |  | 8651851.11 | Ongoing | 0.9 | 2025-03-08 |  | P00875671VS | 24HA0119 |  | 2024-06-13 | 2024-06-25 | 2024-06-28 | 2024-07-09 | 3N CONSTRUCTION & SUPPLY | Demolition or other clearing related issues (except utilities)
44228 | NC 2024 |  | Region VII | Bohol | 118205 | Tanday ES | CORELLA |  | 1 | 3 | 1STY3CL | BATCH 1 | 8700000 |  | 8641500 | Completed | 1 | 2024-11-10 | 2024-11-10 | P00875672VS | 24HA0120 |  | 2024-05-02 | 2024-05-21 | 2024-05-28 | 2024-06-10 | EC SOLICON BUILDERS & SUPPLY, INC.
44229 | NC 2024 |  | Region VII | Bohol | 305722 | De La Paz High School | CORTES |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5964932.49 | Completed | 1 | 2024-09-26 | 2024-09-26 | P00875431VS | 24HA0107 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | 3N CONSTRUCTION & SUPPLY
44230 | NC 2024 |  | Region VII | Bohol | 302817 | Biking Tech-Voc HS | DAUIS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969792.86 | Completed | 1 | 2024-09-11 | 2024-09-11 | P00875406VS | 24HA0104 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | 3N CONSTRUCTION & SUPPLY
44231 | NC 2024 |  | Region VII | Bohol | 302820 | Cabilao NHS | LOON |  | 1 | 4 | 1STY4CL | GAA 17B | 14000000 |  | 13900000 | Ongoing | 0.6 | 2025-06-06 |  | P00875429VS | 24HA0156 |  | 2024-09-04 | 2024-09-17 | 2024-10-25 | 2024-12-04 | ONE ORCHARD Construction Corporation | Modified to 1STY 3CL
44232 | NC 2024 |  | Region VII | Bohol | 306050 | Loon North High School | LOON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4968169.21 | Completed | 1 | 2024-10-11 | 2024-10-11 | P00875404VS | 24HA0115 |  | 2024-04-26 | 2024-05-08 | 2024-05-21 | 2024-06-10 | DOLCI CONSTRUCTION & GENERAL MERCHANDISE
44233 | NC 2024 |  | Region VII | Bohol | 305957 | Lopez-Dano-Simbajon High School | LOON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967000 | Completed | 1 | 2024-12-12 | 2024-12-12 | P00875405VS | 24HA0142 |  | 2024-07-12 | 2024-07-24 | 2024-04-30 | 2024-08-12 | NENIAL CONSTRUCTION
44234 | NC 2024 |  | Region VII | Bohol | 118545 | Pagnitoan ES | MARIBOJOC |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5966199.53 | Completed | 1 | 2024-10-26 | 2024-10-26 | P00875432VS | 24HA0116 |  | 2024-04-26 | 2024-05-08 | 2024-05-21 | 2024-06-10 | K & J CONSTRUCTION
44235 | NC 2024 |  | Region VII | Bohol | 118549 | San Vicente Elementary School | MARIBOJOC |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5940000 | Completed | 1 | 2024-09-26 | 2024-09-26 | P00875430VS | 24HA0109 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | A.A. DE VERA CONSTRUCTION
44236 | NC 2024 |  | Region VII | Bohol | 118558 | Libaong ES | PANGLAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4973741.35 | Completed | 1 | 2024-09-11 | 2024-09-11 | P00875408VS | 24HA0108 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | EFB CONSTRUCTION SERVICES
44237 | NC 2024 |  | Region VII | Bohol | 312332 | Bagongbanwa High School | TUBIGON |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7954812.16 | Completed | 1 | 2025-01-24 | 2025-01-24 | P00875428VS | 24HA0103 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | GREYSTONE CONSTRUCTION
44238 | NC 2024 |  | Region VII | Bohol | 118776 | Buenos Aires ES | TUBIGON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970713.87 | Completed | 1 | 2024-09-11 | 2024-09-11 | P00875407VS | 24HA0106 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | GREYSTONE CONSTRUCTION
44239 | NC 2024 |  | Region VII | Bohol | 306191 | BUENAVISTA HIGH SCHOOL | BUENAVISTA |  | 1 | 8 | 2STY8CL CONSTRUCTION OF CLASSROOMS | BATCH 2 | 29600000 |  |  | Ongoing | 0.25
44240 | NC 2024 |  | Region VII | Bohol | 302831 | Lubang National High School | BUENAVISTA |  | 1 | 6 | Construction of 6CL | GAA 17B | 15000000 |  | 14892798.79 | Ongoing | 0.55 | 2025-10-04 |  | P00875433VS | 24HC0121 | 2024-07-19 | 2024-07-26 | 2024-07-08 | 2024-08-14 | 2024-08-14 | RL Earth Hauling & Equiptment Services, Inc. | Ongoing
44241 | NC 2024 |  | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN |  | 1 | 4 | 1STY4CL | BATCH 2 | 11500000 |  | 9648940.65 | Ongoing | 0.47
44242 | NC 2024 |  | Region VII | Bohol | 312326 | Cuaming HS | INABANGA |  | 1 | 3 | Construction of 3CL | GAA 17B | 7500000 |  | 7452500 | Ongoing | 0.93 | 2025-01-17 |  | P00875436VS | 24HC0115 | 2024-01-07 | 2024-08-07 | 2024-07-23 | 2024-07-30 | 2024-07-30 | Greystone Construction | Ongoing
44243 | NC 2024 |  | Region VII | Bohol | 500209 | Inabanga North Central Integrated School | INABANGA |  | 1 | 1 | Construction of 1CL | GAA 17B | 2500000 |  | 2388000 | Ongoing | 0.94 | 2024-11-30 |  | P00875437VS | 24HC0105 | 2024-07-06 | 2024-06-14 | 2024-06-26 | 2024-06-27 | 2024-07-15 | A.A de vera Construction | Ongoing
44244 | NC 2024 |  | Region VII | Bohol | 501143 | San Jose Integrated School (Secondary) | PRES. CARLOS P. GARCIA (PITOGO) |  | 1 | 2 | Construction of 2CL | GAA 17B | 5000000 |  | 4970000 | Completed | 1 | 2024-08-11 |  | P00875414VS | 24HC0094 | 2024-05-20 | 2024-05-27 | 2024-10-06 | 2024-06-20 | 2024-06-28 | J.F Estapia Construction | Completed
44245 | NC 2024 |  | Region VII | Bohol | 118614 | Kagawasan ES | SAGBAYAN (BORJA) |  | 1 | 1 | Construction of 1CL | GAA 17B | 2500000 |  | 2486654 | Completed | 1 | 2024-11-15 |  | P00875419VS | 24HC0104 | 2024-07-06 | 2024-06-14 | 2024-06-26 | 2024-06-27 | 2024-11-07 | Brightstone Construction | Completed
44246 | NC 2024 |  | Region VII | Bohol | 118616 | Langtad ES | SAGBAYAN (BORJA) |  | 1 | 2 | Construction of 2CL | GAA 17B | 7500000 |  | 7460500 | Ongoing | 0.96 | 2025-02-02 |  | P00875418VS | 24HC0119 | 2024-07-16 | 2024-07-23 | 2024-05-08 | 2024-08-14 | 2024-08-23 | Mai Const. & Supply | Ongoing
44247 | NC 2024 |  | Region VII | Bohol | 118623 | San Ramon Elementary School | SAGBAYAN (BORJA) |  | 1 | 3 | Construction of 3CL | GAA 17B | 7500000 |  | 7432155.19 | Completed | 1 | 2025-12-01 |  | P00875416VS | 24HC0114 | 2024-01-07 | 2024-08-07 | 2024-07-23 | 2024-07-26 | 2024-02-08 | ZMS Construction | Completed
44248 | NC 2024 |  | Region VII | Bohol | 118625 | San Vicente Norte ES | SAGBAYAN (BORJA) |  | 1 | 3 | Construction of 3CL | GAA 17B | 7500000 |  | 7460500 | Completed | 1 | 2025-01-19 |  | P00875417VS | 24HC0116 | 2024-10-07 | 2024-07-17 | 2024-07-29 | 2024-07-31 | 2024-09-08 | Mai Construction and Suplly | Completed
44249 | NC 2024 |  | Region VII | Bohol | 500213 | Cabanugan Integrated School | SAN ISIDRO |  | 1 | 2 | Construction of 2CL | GAA 17B | 5000000 |  | 4964297.82 | Ongoing | 0.98 | 2024-07-12 |  | P00875435VS | 24HC0110 | 2024-06-21 | 2024-06-28 | 2024-01-07 | 2024-07-26 | 2024-02-08 | 4K Vermark Civil Eng'g. Const. | Ongoing
44250 | NC 2024 |  | Region VII | Bohol | 118644 | Cabangahan ES | SAN MIGUEL |  | 1 | 2 | 1STY2CL | BATCH 1 | 5549101.8 |  |  | Completed | 1
44251 | NC 2024 |  | Region VII | Bohol | 500210 | Cataban Integrated School (Secondary) | TALIBON |  | 1 | 2 | Construction of 2CL | GAA 17B | 5000000 |  | 4965000 | Completed | 1 | 2024-11-13 |  | P00875415VS | 24HC0093 | 2024-05-20 | 2024-05-27 | 2024-10-06 | -604299 | 2024-03-07 | Three K Const. & Ent., Inc. | Completed
44252 | NC 2024 |  | Region VII | Bohol | 312334 | Bulilis High School | UBAY |  | 1 | 2 | Construction of 2CL | GAA 17B | 5000000 |  | 4965000 | Completed | 1 | 2024-11-19 |  | P00875438VS | 24HC0092 | 2024-05-20 | 2024-07-27 | 2024-10-06 | 2024-06-28 | 2024-09-07 | BMG Const. & Supply | Completed
44253 | NC 2024 |  | Region VII | Bohol | 500214 | Tapal IS | UBAY |  | 1 | 2 | Construction of 2CL | GAA 17B | 5000000 |  | 4970000 | Completed | 1 | 2024-11-19 |  | P00875434VS | 24HC0091 | 2024-05-20 | 2024-07-27 | 2024-10-06 | 2024-06-28 | 2024-09-07 | A & D Const. & Supply | Completed
44254 | NC 2024 |  | Region VII | Bohol | 118804 | Ubay II Central ES (Biabas CES ) | UBAY |  | 1 | 2 | Construction of School Building with Facilities and Site Improvement | GAA 17B | 13600000 |  | 13522000 | Completed | 0.75 | 2025-02-04 |  | P00875441VS | 24HC0117 | 2024-07-15 | 2024-07-23 | 2024-05-08 | 2024-08-14 | 2024-08-23 | Three K Const. & Ent., Inc. | Completed
44255 | NC 2024 |  | Region VII | Bohol | 118012 | Batuan Central ES | BATUAN |  | 1 | 4 | 2STY4CL | BATCH 1 | 14800000 |  |  | Ongoing | 0.4
44256 | NC 2024 |  | Region VII | Bohol | 302885 | Policronio S. Dano, Sr. HS | CARMEN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4940168 | Completed | 1 | 2024-07-29 | 2024-08-09 | P00875425VS-CW1 | 24HB0118 | 2024-03-25 | 2024-03-04 | 2024-04-15 | 2024-04-23 | 2024-04-29 | CLAIRE CONSTRUCTION AND SUPPLY CORPORATION
44257 | NC 2024 |  | Region VII | Bohol | 305581 | Valeriano Ganas High School | CARMEN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4944966.86 | Ongoing | 0.25 |  |  | P00875424VS-CW1 | 24HB0119 | 2024-03-25 | 2024-03-04 | 2024-04-15 | 2024-04-23 | 2024-04-29 | ALOJA BUILDERS AND REALTY | Suspended due to location under protected area, for compliance of ECC
44258 | NC 2024 |  | Region VII | Bohol | 118300 | San Isidro ES | DUERO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4945596 | Completed | 1 | 2024-07-29 | 2024-10-25 | P00875426VS-CW1 | 24HB0117 | 2024-03-25 | 2024-03-04 | 2024-04-15 | 2024-04-22 | 2024-04-29 | JEGSTONE CONSTRUCTION
44259 | NC 2024 |  | Region VII | Bohol | 306194 | ABIJILAN HIGH SCHOOL | GARCIA HERNANDEZ |  | 1 | 4 | 2STY4CL | BATCH 2 | 12800000 |  |  | Ongoing | 0.39
44260 | NC 2024 |  | Region VII | Bohol | 118308 | Candulao ES | GARCIA HERNANDEZ |  | 1 | 4 | 2STY4CL | BATCH 1 | 12800000 |  |  | Ongoing | 0.55
44261 | NC 2024 |  | Region VII | Bohol | 306193 | CAYAM HIGH SCHOOL | GARCIA HERNANDEZ |  | 1 | 4 | 2STY4CL | BATCH 2 | 12800000 |  |  | Ongoing | 0.6
44262 | NC 2024 |  | Region VII | Bohol |  | Catungawan Norte Elementary School | GUINDULMAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
44263 | NC 2024 |  | Region VII | Bohol | 118424 | Jagna Central ES | JAGNA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964830.84 | Completed | 1 | 2024-07-26 |  | P00875420VS-CW1 | 24HB0121 | 2024-03-25 | 2024-04-13 | 2024-04-15 | 2024-04-22 | 2024-04-29 | G.U. AUDITOR CONSTRUCTION & SUPPLY | On-going process of Contract Time Extension due to unworkable weather condition
44264 | NC 2024 |  | Region VII | Bohol | 118434 | Calvario Elementary School | LILA |  | 1 | 2 | 1STY2CL | BATCH 1 | 6500000 |  | 6447671.61 | Completed | 1 | 2024-09-30 |  | P00875678VS-CW1 | 24HB0160 | 2024-05-14 | 2024-05-23 | 2024-04-06 | 2024-06-26 | 2024-04-07 | ALOJA BUILDERS & REALTY | On-going process of Contract Time Extension due to unworkable weather condition
44265 | NC 2024 |  | Region VII | Bohol | 118435 | Cogon ES | LILA |  | 1 | 2 | 1STY2CL | BATCH 1 | 6500000 |  | 6456668.77 | Completed | 1 | 2024-09-30 |  | P00875679VS-CW1 | 24HB0161 | 2024-05-14 | 2024-05-23 | 2024-04-06 | 2024-06-26 | 2024-04-07 | ALOJA BUILDERS & REALTY | On-going process of Contract Time Extension due to unworkable weather condition
44266 | NC 2024 |  | Region VII | Bohol | 118436 | Jambawan ES | LILA |  | 1 | 2 | 1STY2CL | BATCH 1 | 6500000 |  | 6464344.86 | Ongoing | 0.89 | 2024-04-10 |  | P00875680VS-CW1 | 24HB0157 | 2024-05-14 | 2024-05-23 | 2024-04-06 | 2024-06-28 | 2024-09-07 | RAMYER CONSTRUCTION &TRADING | On-going process of Contract Time Extension due to unworkable weather condition
44267 | NC 2024 |  | Region VII | Bohol | 118437 | Lila Central ES | LILA |  | 1 | 2 | 1STY2CL | BATCH 1 | 6500000 |  | 5741145.59 | Completed | 1 | 2024-09-27 |  | P00875681VS-CW1 | 24HB0158 | 2024-05-14 | 2024-05-23 | 2024-04-06 | 2024-06-21 | 2024-03-07 | KEPRISHYLIE CIVIL ENGINEERING CONSTRUCTION | On-going process of Contract Time Extension due to unworkable weather condition
44268 | NC 2024 |  | Region VII | Bohol | 302868 | Lila NHS | LILA |  | 1 | 6 | 3STY6CL | BATCH 1 | 19500000 |  | 19206207.71 | Ongoing | 0.5 | 2025-06-02 |  | P00875684VS-CW1 | 24HB0170 | 2024-08-07 | 2024-07-17 | 2024-07-29 | 2024-08-27 | 2024-05-09 | A&D CONSTRUCTION AND SUPPLY
44269 | NC 2024 |  | Region VII | Bohol | 118438 | Macalingan P/S | LILA |  | 1 | 2 | 1STY2CL | BATCH 1 | 6500000 |  | 6451768.91 | Completed | 1 | 2024-11-10 |  | P00875682VS-CW1 | 24HB0162 | 2024-05-14 | 2024-05-23 | 2024-04-06 | 2024-06-28 | 2024-07-15 | ALOJA BUILDERS & REALTY | On-going process of Contract Time Extension due to unworkable weather condition
44270 | NC 2024 |  | Region VII | Bohol | 118440 | Nagsulay Elem. School | LILA |  | 1 | 3 | 1STY3CL | BATCH 1 | 8700000 |  | 7602053.43 | Completed | 1 | 2024-10-21 |  | P00875683VS-CW1 | 24HB0159 | 2024-05-14 | 2024-05-23 | 2024-04-06 | 2024-06-27 | 2024-07-15 | KEPRISHYLIE CIVIL ENGINEERING CONSTRUCTION | On-going process of Contract Time Extension due to unworkable weather condition
44271 | NC 2024 |  | Region VII | Bohol | 306192 | LOAY NHS | LOAY |  | 1 | 2 | 1STY2CL | BATCH 2 | 6500000 |  |  | Ongoing | 0.8
44272 | NC 2024 |  | Region VII | Bohol |  | San Jose National High Scool | MABINI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
44273 | NC 2024 |  | Region VII | Bohol | 302901 | San Roque National High School | MABINI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964859.94 | Completed | 1 | 2024-07-29 |  | P00875427VS-CW1 | 24HB0116 | 2024-03-25 | 2024-04-13 | 2024-04-15 | 2024-04-19 | 2024-04-29 | G.U. AUDITOR CONSTRUCTION & SUPPLY
44274 | NC 2024 |  | Region VII | Bohol | 118847 | Anas ES | VALENCIA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4962602.96 | Completed | 1 | 2024-07-29 |  | P00875422VS-CW1 | 24HB0120 | 2024-03-25 | 2024-04-13 | 2024-04-15 | 2024-04-22 | 2024-04-29 | LTS BUILDERS AND CONSTRUCTION SUPPLY | On-going process of Contract Time Extension due to unworkable weather condition
44275 | NC 2024 |  | Region VII | Bohol | 306239 | ANAS HIGH SCHOOL | VALENCIA |  | 1 | 3 | 1STY3CL | BATCH 2 | 9600000 |  |  | Ongoing | 0.46
44277 | NC 2024 |  | Region VII | Carcar City | 119159 | Liburon Elementary School | CITY OF CARCAR |  | 1 | 12 | Construction of 12CL | GAA 17B | 40000000 |  |  | Ongoing | 0.8 | [9 empty] | Quirante Construction
44278 | NC 2024 |  | Region VII | Cebu | 302985 | Argao National High School | ARGAO |  | 1 | 9 | 3STY9CL | GAA 17B | 40000000 |  | 39747299.83 | Ongoing | 0.25 | 2025-03-25 |  | P00875443VS | 24HG0078 | 2024-03-14 | 2024-03-21 | 2024-04-02 | 2024-05-06 | 2024-05-24 | BT CONSTRUCTION AND GENERAL SERVICES
44279 | NC 2024 |  | Region VII | Cebu | 303071 | Cagay NHS | BARILI |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19847000 | Ongoing | 0.25 | 2025-05-01 |  | P00875445VS-CW1 | 24HF0102 | 2024-05-08 | 2024-05-14 | 2024-05-27 | 2024-05-31 | 2024-06-05 | FDC CONSTRUCTION AND SUPPLIES CO.
44280 | NC 2024 |  | Region VII | Cebu | 119101 | Patupat ES | BARILI |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19887754.26 | Ongoing | 0.3 | 2025-05-01 |  | P00875444VS-CW1 | 24HF0101 | 2024-05-08 | 2024-05-14 | 2024-05-27 | 2024-05-31 | 2024-06-05 | FDC CONSTRUCTION AND SUPPLIES CO.
44281 | NC 2024 |  | Region VII | Cebu | 500652 | Hilotongan Integrated School | BANTAYAN |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9926615.74 | Ongoing | 0.5 | 2024-12-19 |  | P00875454VS | 24HD0120 | 2024-07-19 | 2024-07-26 | 2024-08-07 | 2024-08-15 | 2024-08-22 | XLA CONSTRUCTION
44282 | NC 2024 |  | Region VII | Cebu | 119456 | Caputatan Sur ES | MEDELLIN |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9928258.61 | Ongoing | 0.9 | 2024-11-19 |  | P00875457VS | 24HD0118 | 2024-07-19 | 2024-07-26 | 2024-08-07 | 2024-08-15 | 2024-08-22 | Z & G CONSTRUCTION SERVICES
44283 | NC 2024 |  | Region VII | Cebu | 119692 | Okoy ELEMENTARY SCHOOL | SANTA FE |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9926690.16 | Ongoing | 0.85 | 2024-11-29 |  | P00875455VS | 24HD0121 | 2024-07-19 | 2024-07-26 | 2024-08-07 | 2024-08-15 | 2024-08-22 | XLA CONSTRUCTION
44284 | NC 2024 |  | Region VII | Cebu | 312408 | Daantabogon NHS | TABOGON |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9925961.51 | Ongoing | 0.7 | 2024-11-19 |  | P00875456VS | 24HD0119 | 2024-07-19 | 2024-07-26 | 2024-08-07 | 2024-08-15 | 2024-08-22 | SAN NARCISO BUILDERS CORPORATION
44285 | NC 2024 |  | Region VII | Cebu | 119147 | Doña Milagros Osmeña ES | BORBON |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.1 | 2025-02-23 |  | P00875476VS-CW1 | 24HI0146 | 2024-08-29 | 2024-09-05 | 2024-09-18 | 2024-09-24 | 2024-09-27 | WQC DESIGN & CONSTRUCTION | Rebid
44286 | NC 2024 |  | Region VII | Cebu | 119150 | Managase ES | BORBON |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.7 | 2024-10-19 |  | P00875477VS-CW1 | 24HI0108 | 2024-04-04 | 2024-04-11 | 2024-04-23 | 2024-05-08 | 2024-05-23 | WQC DESIGN & CONSTRUCTION | -
44287 | NC 2024 |  | Region VII | Cebu | 119186 | Cantumog ES | CARMEN |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.95 | 2024-11-09 |  | P00875448VS-CW1 | 24HI0086 | 2024-05-01 | 2024-05-08 | 2024-05-21 | 2024-05-28 | 2024-06-13 | WQC DESIGN & CONSTRUCTION | Rebid
44288 | NC 2024 |  | Region VII | Cebu | 500042 | Catmon Integrated School | CATMON |  | 1 | 21 | 4STY20CL & Regular TVL | BATCH 1 | 59000000 |  | 58677631.09 | Ongoing | 0.4 | 2025-05-24 |  | P00875685VS | 24HI0147 | 2024-08-29 | 2024-09-05 | 2024-09-18 | 2024-09-24 | 2024-09-27 | NEOVENTURES CONST./ DINAH RBS CONST. & SUPPLY INC., JV. | DEMOLITION WORKS
44289 | NC 2024 |  | Region VII | Cebu | 119216 | Catmondaan ES | CATMON |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9934720.45 | Ongoing | 0.01 | 2025-09-02 |  | P00875449VS-CW1 | 24HI0152 | 2025-02-21 | 2025-02-28 | 2025-05-06 | 2025-05-14 | 2025-05-21 | WQC DESIGN & CONSTRUCTION | MODIFIED DUE TO LAST BUILDABLE SPACE. RECOMMENDED TO CONSTRUCT 4STY8CL.
44290 | NC 2024 |  | Region VII | Cebu | 500991 | Cabadiangan Integrated School | COMPOSTELA |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.25 | 2024-11-16 |  | P00875447VS-CW1 | 24HI0129 | 2024-05-09 | 2024-05-16 | 2024-05-29 | 2024-06-05 | 2024-06-20 | WQC DESIGN & CONSTRUCTION
44291 | NC 2024 |  | Region VII | Cebu | 187019 | Canamucan ES | COMPOSTELA |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.75 | 2024-11-09 |  | P00875446VS-CW1 | 24HI0115 | 2024-05-01 | 2024-05-08 | 2024-05-21 | 2024-05-28 | 2024-06-13 | WQC DESIGN & CONSTRUCTION
44292 | NC 2024 |  | Region VII | Cebu | 501349 | Dapdap Integrated School | COMPOSTELA |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.95 | 2024-10-19 |  | P00875472VS-CW1 | 24HI0107 | 2024-04-04 | 2024-04-11 | 2024-04-23 | 2024-05-08 | 2024-05-23 | WQC DESIGN & CONSTRUCTION
44293 | NC 2024 |  | Region VII | Cebu | 500423 | Calero IS | LILOAN |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.25 | 2024-11-16 |  | P00875453VS-CW1 | 24HI0128 | 2024-05-09 | 2024-05-16 | 2024-05-29 | 2024-06-05 | 2024-06-20 | WQC DESIGN & CONSTRUCTION
44294 | NC 2024 |  | Region VII | Cebu | 119549 | Pilar Central School | PILAR |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9939619.02 | Ongoing | 0.85 | 2024-11-01 |  | P00875475VS-CW1 | 24HI0110 | 2024-04-04 | 2024-04-11 | 2024-04-23 | 2024-04-30 | 2024-05-16 | M.C. BUYSER CONSTRUCTION & SUPPLY
44295 | NC 2024 |  | Region VII | Cebu | 119582 | Esperanza ES | PORO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.95 | 2024-10-05 |  | P00875452VS-CW1 | 24HI0087 | 2024-03-06 | 2024-03-14 | 2024-03-27 | 2024-04-15 | 2024-04-29 | WQC DESIGN & CONSTRUCTION
44296 | NC 2024 |  | Region VII | Cebu | 303085 | San Jose National High School | PORO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.9 | 2024-10-05 |  | P00875474VS-CW1 | 24HI0088 | 2024-03-06 | 2024-03-14 | 2024-03-27 | 2024-04-15 | 2024-04-29 | WQC DESIGN & CONSTRUCTION
44297 | NC 2024 |  | Region VII | Cebu | 501353 | Sta. Rita Integrated School | PORO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.95 | 2024-10-05 |  | P00875473VS-CW1 | 24HI0089 | 2024-03-06 | 2024-03-14 | 2024-03-27 | 2024-04-15 | 2024-04-29 | WQC DESIGN & CONSTRUCTION
44298 | NC 2024 |  | Region VII | Cebu | 502121 | Campo IS | SAN FRANCISCO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.4 | 2024-11-23 |  | P00875451VS-CW1 | 24HI0124 | 2024-05-03 | 2024-05-10 | 2024-05-22 | 2024-05-30 | 2024-06-17 | WQC DESIGN & CONSTRUCTION
44299 | NC 2024 |  | Region VII | Cebu | 187036 | Dumalerio Elementary School | SAN FRANCISCO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.91 | 2025-06-21 |  | P0087540VS-CW1 | 24HI0127 | 2024-05-09 | 2024-03-16 | 2024-05-29 | 2024-12-27 | 2025-01-13 | WQC DESIGN & CONSTRUCTION
44300 | NC 2024 |  | Region VII | Cebu | 119732 | Inocoyan ES | SOGOD |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9933715.08 | Ongoing | 0.38 | 2025-08-10 |  | P00875479VS-CW1 | 24HI0133 | 2024-11-16 | 2024-11-27 | 2024-12-10 | 2024-12-27 | 2025-01-13 | WQC DESIGN & CONSTRUCTION | Not yet mobilized
44301 | NC 2024 |  | Region VII | Cebu | 119746 | Tangke Elementary School | SOGOD |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.4 | 2025-02-23 |  | P00875476VS-CW1 | 24HI0109 | 2024-04-04 | 2024-04-11 | 2024-04-23 | 2024-05-08 | 2024-05-23 | WQC DESIGN & CONSTRUCTION
44302 | NC 2024 |  | Region VII | Cebu | 119234 | Bagong Lipunan Elementary School | CONSOLACION |  | 1 | 8 | 4STY8CL (Phase 1) | GAA 17B | 15000000 |  | 14904512.79 | Ongoing | 0.3 | 2025-02-03 |  | P00875460VS-CW1 | 24HN0167 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-06-10 | 2024-06-18 | XLA CONSTRUCTION
44303 | NC 2024 |  | Region VII | Cebu | 137084 | Pitogo Primary School | CONSOLACION |  | 1 | 12 | 4STY12CL | GAA 17B | 25000000 |  | 24782396.29 | Ongoing | 0.4 | 2024-11-07 |  | P00875458VS-CW1 | 24HN0156 | 2024-04-15 | 2024-04-23 | 2024-05-07 | 2024-05-09 | 2024-05-15 | GTM BUILDERS AND SUPPLY
44304 | NC 2024 |  | Region VII | Cebu | 187025 | Catarman Elementary School | CORDOVA |  | 1 | 12 | 4STY12CL | GAA 17B | 15000000 |  | 14910000 | Ongoing | 0.05 | 2025-01-11 |  | P00875459VS-CW1 | 24HN0166 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-06-10 | 2024-06-18 | POWER MOVE BUILDERS AND CONSTRUCTION SUPPLY
44305 | NC 2024 |  | Region VII | Cebu | 305874 | Pilipog Night High School | CORDOVA |  | 1 | 20 | 4STY20CL (Phase 1) | GAA 17B | 20000000 |  | 19891365.13 | Ongoing | 0.15 | 2025-03-16 |  | P00875461VS-CW1 | 24HN0173 | 2024-06-07 | 2024-06-14 | 2024-07-31 | 2024-08-08 | 2024-08-14 | BANTAY CONSTRUCTION
44306 | NC 2024 |  | Region VII | Cebu | 119008 | Matutinao ES | BADIAN |  | 1 | 6 | 2STY6CL (Phase 2) | GAA 17B | 24000000 |  | 23585000 | Ongoing | 0.5 | 2024-09-23 |  | P00875462VS-CW1 | 24HO0132 | 2024-02-28 | 2024-03-06 | 2024-03-19 | 2024-03-26 | 2024-04-08 | CELJEM CONSTRUCTION & DEVELOPMENT CORP.
44307 | NC 2024 |  | Region VII | Cebu | 303033 | Langin NHS | RONDA |  | 1 | 6 | 2STY6CL (Phase 2) | GAA 17B | 16000000 |  | 15820000 | Ongoing | 0.9 | 2024-09-27 |  | P00875463VS-CW1 | 24HO0143 | 2024-03-06 | 2024-03-13 | 2024-04-02 | 2024-04-08 | 2024-04-16 | FIRST GRANDEUR BUILDERS
44308 | NC 2024 |  | Region VII | Cebu City | 119899 | Banilad ES | CEBU CITY (Capital) |  | 1 | 12 | 4STY12CL | GAA 17B | 25000000 |  | 24855000 | Ongoing | 0.35 | 2024-12-14 |  | P00875464VS-CW1 | 24HH0101 | 2024-03-20 | 2024-04-05 | 2024-04-17 | 2024-04-24 | 2024-05-20 | MBD General Construction | On-going
44309 | NC 2024 |  | Region VII | Cebu City | 119901 | Mabolo ES | CEBU CITY (Capital) |  | 1 | 8 | 4STY8CL | GAA 17B | 15000000 |  | 14915000 | Ongoing | 0.85 | 2024-10-10 |  | P00875465VS-CW1 | 24HH0100 | 2024-03-20 | 2024-04-05 | 2024-04-17 | 2024-04-25 | 2024-05-08 | Planac Construction | On-going
44310 | NC 2024 |  | Region VII | Cebu City | 303160 | Pit-os National High School | CEBU CITY (Capital) |  | 1 | 8 | 4STY8CL | BATCH 1 | 39334722.35 |  | 39113048.74 | Ongoing | 0.23 | 2024-04-16 |  | P00875686VS-CW1 | 24HH0129 | 2024-07-03 | 2024-07-12 | 2024-07-24 | 2024-07-29 | 2024-08-20 | W & J Construction & General Supply | On-going
44311 | NC 2024 |  | Region VII | Cebu City | 303162 | OPRRA NHS (Day & Night) | CEBU CITY (Capital) |  | 1 | 16 | 4STY16CL | BATCH 1 | 64000000 |  | 63550000 | Ongoing | 0.08 | 2024-07-15 |  | P00800480VS-CW1 | 24HH0132 | 2024-07-31 | 2024-08-09 | 2024-08-22 | 2024-08-29 | 2024-09-19 | E.U. Caballero/ARQ Builders(J.V.) | On-going
44312 | NC 2024 |  | Region VII | Cebu City | 187501 | Quiot ES | CEBU CITY (Capital) |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39759647 | Ongoing | 0.55 | 2025-01-17 |  | P00875466VS-CW1 | 24HH0102 | 2024-04-04 | 2024-04-12 | 2024-04-25 | 2024-04-29 | 2024-05-17 | La Prueba Construction/WTG Const. & Devlopment Corp.(J.V.) | On-going
44317 | NC 2024 |  | Region VII | Lapu-Lapu City | 119985 | Babag I Elementary School | LAPU-LAPU CITY (OPON) |  | 1 | 8 | 4STY8CL | BATCH 1 | 40062069.4 |  | 39830555.51 | Ongoing | 0.65 | 2025-04-13 |  | P00875690VS-CW1 | 24HN0155 | 2024-04-15 | 2024-04-23 | 2024-08-09 | 2024-08-19 | 2024-08-27 | SBD BUILDERS
44318 | NC 2024 |  | Region VII | Lapu-Lapu City | 119953 | Cawhagan Elementary School | LAPU-LAPU CITY (OPON) |  | 1 | 8 | 4STY8CL | GAA 17B | 20000000 |  | 14915000.38 | Ongoing | 0.7 | 2025-02-13 |  | P00875467VS-CW1 | 24HN0165 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-06-10 | 2024-06-18 | SBD BUILDERS | Phase 1 Only
44319 | NC 2024 |  | Region VII | Lapu-Lapu City | 119982 | Suba Basbas Elementary School | LAPU-LAPU CITY (OPON) |  | 1 | 8 | 4STY8CL | GAA 17B | 20000000 |  | 14915006.06 | Completed | 1 | 2025-03-02 | 2025-04-15 | P00875468VS-CW1 | 24HN0168 | 2024-05-16 | 2024-05-23 | 2024-05-16 | 2024-06-10 | 2024-06-18 | SBD BUILDERS | Phase 1 Only
44320 | NC 2024 |  | Region VII | Mandaue City | 120013 | Maguikay ES | MANDAUE CITY |  | 1 | 12 | 4STY12CL | GAA 17B | 20000000 |  | 19850000 | Ongoing | 0.85 | 2025-01-29 |  | POO875470VS-CW1 | 24HN0148 | 2024-03-27 | 2024-04-04 | 2024-04-16 | 2024-09-05 | 2014-05-15 | ZLREJ TRADING AND CONST. CORP.
44321 | NC 2024 |  | Region VII | Mandaue City | 119995 | Mayor A.S. Fortuna Memorial ES | MANDAUE CITY |  | 1 | 4 | 4STY4CL | GAA 17B | 20000000 |  | 19869996.83 | Ongoing | 0.65 | 2025-02-27 |  | POO875471VS-CW1 | 24HN0172 | 2024-07-06 | 2024-06-14 | 2024-06-26 | 2024-07-01 | 2024-10-07 | GOLDFIN CONSTRUCTION AND DEV'T. CORP.
44330 | NC 2024 |  | Region VII | Tagbilaran City | 118705 | City East Elementary School | TAGBILARAN CITY (Capital) |  | 1 | 8 | Construction of 8CL | GAA 17B | 20000000 |  | 18298800 | Ongoing | 0.15 | 2025-07-14 |  | 24HA0158 | 24HA0158 | 2024-08-28 | 2024-09-04 | 2024-09-17 | 2024-11-26 | 2024-12-09 | HANZGRACE CONSTRUCTION AND TRADING CORPORATION | Approved for Modification
44331 | NC 2024 |  | Region VII | Tagbilaran City | 322102 | San Isidro National High School | TAGBILARAN CITY (Capital) |  | 1 | 8 | Construction of 8CL | GAA 17B | 20000000 |  | 19870000 | Ongoing | 0.09 | 2025-07-14 |  | 24HA0157 | 24HA0157 | 2024-08-28 | 2024-09-04 | 2024-09-17 | 2024-11-26 | 2024-12-09 | One Orchard Construction Corporation | Approved for Modification
44332 | NC 2024 |  | Region VII | Tagbilaran City | 118714 | Taloto Elementary School | TAGBILARAN CITY (Capital) |  | 1 | 11 | 1STY2CL & 3STY9CL | BATCH 1 | 38682075.08 |  | 38455812.43 | Ongoing | 0.17 | 2025-07-17 |  | 24HA0149 | 24HA0149 | 2024-08-02 | 2024-08-09 | 2024-08-22 | 2024-08-30 | 2024-09-13 | CEMPRON CONSTRUCTION AND DEVELOPMENT
44333 | NC 2024 |  | Region VII | Talisay City | 119789 | Mohon Elementary School | CITY OF TALISAY |  | 1 | 16 | 4STY16CL | BATCH 1 | 69821643 |  | 69440000 | Ongoing | 0.95 | 2025-03-23 | 2025-03-23 | P00875693VS-CW1 | 24HE0198 | 2024-10-05 | 2024-05-29 | 2024-05-29 | 2024-06-18 | 2024-06-28 | January Builders | On going
44334 | NC 2024 |  | Region VII | Toledo City | 120734 | Matab-ang ES | TOLEDO CITY |  | 1 | 12 | 4STY12CL | BATCH 1 | 35894925.92 |  | 35615000 | Ongoing | 0.85 | 2025-01-03 |  | P00875694VS-CW1 | 24HF0100 | 2024-05-05 | 2024-10-05 | 2024-05-22 | 2024-05-28 | 2024-03-06 | QM Builders | DPWH IMPLEMENTED

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.