## Sheet1
INDEX (DO NOT MODIFY) | PROGRAM-YEAR | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | BATCH | TOTAL PROJECT ALLOCATION | TOTAL PROJECT COST | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
7344 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126620 | Awol ES | MANOLO FORTICH | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00166 | 14KC0034 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | LYD CONSTRUCTION
7345 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126794 | Balaon ES | TALAKAG | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2916174.43 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-11-24 | 100314S00160 | 14KC0024 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7346 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126795 | Basak ES | TALAKAG | 1 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 4A | 3459016.9194 |  |  | COMPLETED | 1 | 2015-06-25 | 2015-06-15 | 100314S00191 | 14KC0061 | 2014-11-02 | 2014-11-03 | 2014-12-04 | 2014-12-09 | 2014-12-18 | R. SEMILLA CONSTRUCTION & MARKETING
7347 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126264 | Buenavista ES | BAUNGON | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-12-06 | 2014-12-06 | 100314S00131 | 14KC0030 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7348 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126798 | Colawingon ES | TALAKAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2028417.57 |  |  | COMPLETED | 1 | 2014-11-26 | 2014-11-26 | 100314S00159 | 14KC0027 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7349 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126799 | Cosina ES | TALAKAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2028417.57 |  |  | COMPLETED | 1 | 2014-11-26 | 2014-11-25 | 100314S00158 | 14KC0025 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7350 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126624 | Dahilayan ES | MANOLO FORTICH | 1 | 1 | 4 | 1STY3CL & 1STY1CL | 2014 K10 BATCH 4A | 3481339.0447 |  |  | COMPLETED | 1 | 2015-06-25 | 2015-06-15 | 100314S00190 | 14KC0061 | 2014-11-02 | 2014-11-03 | 2014-12-04 | 2014-12-09 | 2014-12-18 | R. SEMILLA CONSTRUCTION & MARKETING
7351 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126625 | Dalirig ES | MANOLO FORTICH | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00170 | 14KC0033 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7352 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126520 | Gango ES | LIBONA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00164 | 14KC0029 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7353 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126640 | Guilang-Guilang ES | MANOLO FORTICH | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00152 | 14KC0033 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7354 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126601 | Kiabo ES | MALITBOG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00187 | 14KC0035 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7355 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126631 | Kitam-Is ES | MANOLO FORTICH | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00169 | 14KC0034 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | LYD CONSTRUCTION
7356 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126807 | Lapok ES | TALAKAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-11-26 | 2014-11-25 | 100314S00157 | 14KC0027 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7357 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126271 | Liboran ES | BAUNGON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00140 | 14KC0029 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7358 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126808 | Liguron PS | TALAKAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2028417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-11-28 | 100314S00156 | 14KC0024 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7359 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126811 | Lourdes Village ES | TALAKAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2028417.57 |  |  | COMPLETED | 1 | 2014-11-26 | 2014-11-26 | 100314S00155 | 14KC0026 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7360 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126812 | Lugsayan ES | TALAKAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-11-26 | 100314S00154 | 14KC0024 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7361 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126634 | Lunucan ES | MANOLO FORTICH | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00168 | 14KC0034 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | LYD CONSTRUCTION
7362 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126786 | Lupiagan ES | SUMILAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 100314S00162 | 14KC0031 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | DOMUGAN CONSTRUCTION & SUPPLY
7363 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126525 | Maambong ES | LIBONA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-06 | 2014-10-20 | 100314S00172 | 14KC0028 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7364 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126274 | Mabunga ES | BAUNGON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00130 | 14KC0029 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7365 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126635 | Maluko ES | MANOLO FORTICH | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00167 | 14KC0033 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7366 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126636 | Mambatangan ES | MANOLO FORTICH | 1 | 1 | 3 | 1STY2CL & 1STY1CL | 2014 K10 BATCH 4A | 2692811.1604 |  |  | COMPLETED | 1 | 2015-06-25 | 2015-06-15 | 100314S00197 | 14KC0061 | 2014-11-02 | 2014-11-03 | 2014-12-04 | 2014-12-09 | 2014-12-18 | R. SEMILLA CONSTRUCTION & MARKETING
7367 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126637 | Mampayag ES | MANOLO FORTICH | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 100314S00171 | 14KC0032 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7368 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126639 | Mantibugao ES | MANOLO FORTICH | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 100314S00165 | 14KC0032 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7369 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126814 | Masimag ES | TALAKAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2018417.57 |  |  | COMPLETED | 1 | 2014-11-26 | 2014-11-24 | 100314S00153 | 14KC0025 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7370 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126817 | Migpait ES | TALAKAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-11-26 | 2014-11-24 | 100314S00150 | 14KC0027 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7371 | NC 2014 | K10 (2014) | Region X | Bukidnon | 199525 | New Nebo PS | TALAKAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-11-26 | 2014-11-26 | 100314S00044 | 14KC0025 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7372 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126609 | Patpat ES | MALITBOG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00186 | 14KC0034 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | LYD CONSTRUCTION
7373 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126277 | Pualas ES | BAUNGON | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2014-12-06 | 2014-12-06 | 100314S00129 | 14KC0030 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7374 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126819 | Salucot ES | TALAKAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1 | 2014-11-26 | 2014-11-25 | 100314S00081 | 14KC0026 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7375 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126529 | Salvacion ES | LIBONA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-06 | 2014-12-06 | 100314S00175 | 14KC0030 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7376 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126610 | Sampiano ES | MALITBOG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00185 | 14KC0035 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7377 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126790 | San Roque ES | SUMILAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 100314S00161 | 14KC0031 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | DOMUGAN CONSTRUCTION & SUPPLY
7378 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126280 | San Vicente ES | BAUNGON | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00138 | 14KC0029 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7379 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126645 | Santiago ES | MANOLO FORTICH | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00163 | 14KC0033 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7380 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126532 | Sil-Ipon ES | LIBONA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-06 | 2014-10-20 | 100314S00174 | 14KC0028 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7381 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126613 | Siloo ES | MALITBOG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00184 | 14KC0035 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7382 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126614 | Sta Ines ES | MALITBOG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00183 | 14KC0035 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7383 | NC 2014 | K10 (2014) | Region X | Bukidnon | 314903 | Sumilao NHS - Kisolon Annex | SUMILAO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 |  | 2014-12-20 | 100314S00043 | 14KC0031 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | DOMUGAN CONSTRUCTION & SUPPLY
7384 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126647 | Ticala ES | MANOLO FORTICH | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 100314S00173 | 14KC0032 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7385 | NC 2014 | K10 (2014) | Region X | Bukidnon | 199507 | Tigbao ES | LIBONA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-06 | 2014-10-20 | 100314S00045 | 14KC0028 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7386 | NC 2014 | K10 (2014) | Region X | Bukidnon | 314919 | Tikalaan NHS | TALAKAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 |  | 2014-11-26 | 100314S00042 | 14KC0026 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7387 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126617 | Umagling ES | MALITBOG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 100314S00182 | 14KC0035 | 2014-05-27 | 2014-05-26 | 2014-06-17 | 2014-06-23 | 2014-07-10 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7388 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126496 | Alanib ES | LANTAPAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-07-08 | 100314S00039 | 14KA0026 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | A.R. & MARK BUILDERS
7389 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126497 | Babahagon PS | LANTAPAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-05-14 | 100314S00061 | 14KA0027 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | PAGADIAN AGGREGATES & MARKETING
7390 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126500 | Bantuanon ES | LANTAPAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-04-06 | 100314S00060 | 14KA0027 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | PAGADIAN AGGREGATES & MARKETING
7391 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126369 | Bontongon ES | IMPASUG-ONG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2015-04-28 | 100314S00046 | 14KA0018 | 2014-06-30 | 2014-07-01 | 2014-07-31 | 2014-08-29 | 2014-09-08 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7392 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126370 | Bulonay ES | IMPASUG-ONG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-12-23 | 2014-12-23 | 100314S00036 | 14KA0024 | 2014-08-21 | 2014-08-22 | 2014-09-04 | 2014-09-17 | 2014-09-25 | L & L CONSTRUCTION
7393 | NC 2014 | K10 (2014) | Region X | Bukidnon | 314908 | Cabulohan-Paradise NHS - Townsite Annex | CABANGLASAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 |  | 2014-11-09 | 100314S00051 | 14KA0025 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | BRILLANTES CONSTRUCTION
7394 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126372 | Capitan Bayong ES | IMPASUG-ONG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1988417.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2015-01-22 | 100314S00035 | 14KA0018 | 2014-06-30 | 2014-07-01 | 2014-07-31 | 2014-08-29 | 2014-09-08 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7395 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126504 | Cawayan ES | LANTAPAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-04-06 | 100314S00059 | 14KA0027 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | PAGADIAN AGGREGATES & MARKETING
7396 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126750 | Cayaga ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-24 | 2015-06-05 | 100314S00176 | 14KA0033 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7397 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126286 | Crossing Mandaing | CABANGLASAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-05-04 | 100314S00041 | 14KA0025 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | BRILLANTES CONSTRUCTION
7398 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126373 | Dumalaguing ES | IMPASUG-ONG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-12-22 | 100314S00034 | 14KA0019 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ZI 9 BUILDERS AND SUPPLIES
7399 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126754 | Iglugsad ES | SAN FERNANDO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2015-05-18 | 100314S00180 | 14KA0033 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7400 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126290 | Imbatug ES | CABANGLASAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-05-04 | 100314S00040 | 14KA0025 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | BRILLANTES CONSTRUCTION
7401 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126377 | Impalutao ES | IMPASUG-ONG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2015-01-20 | 100314S00033 | 14KA0019 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ZI 9 BUILDERS AND SUPPLIES
7402 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126378 | Impasug-Ong CES | IMPASUG-ONG | 2 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 4A | 4247544.864 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-05-16 | 100314S00198 | 14KA0082 | 2014-12-09 | 2014-12-17 | 2014-12-23 | 2014-12-29 | 2015-01-12 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7403 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126779 | Intavas ES | IMPASUG-ONG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2015-01-12 | 100314S00037 | 14KA0018 | 2014-06-30 | 2014-07-01 | 2014-07-31 | 2014-08-29 | 2014-09-08 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7404 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126505 | Kaatuan ES | LANTAPAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-07-28 | 100314S00058 | 14KA0026 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | A.R. & MARK BUILDERS
7405 | NC 2014 | K10 (2014) | Region X | Bukidnon | 303957 | Kalabugao NHS | IMPASUG-ONG | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 |  | 2014-11-14 | 100314S00052 | 14KA0019 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ZI 9 BUILDERS AND SUPPLIES
7406 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126758 | Kawayan ES | SAN FERNANDO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2015-05-11 | 100314S00181 | 14KA0033 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7407 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126383 | Kibuwa ES | IMPASUG-ONG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-06 | 2014-12-06 | 100314S00032 | 14KA0020 | 2014-06-30 | 2014-07-01 | 2014-07-31 | 2014-08-29 | 2014-09-08 | J.T. GAMOLO CONSTRUCTION
7408 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126385 | Kubayan ES | IMPASUG-ONG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-26 | 2015-01-12 | 100314S00054 | 14KA0018 | 2014-06-30 | 2014-07-01 | 2014-07-31 | 2014-08-29 | 2014-09-08 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7409 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126760 | Little Baguio ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-24 | 2015-05-19 | 100314S00179 | 14KA0033 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7410 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126389 | New Imbatug ES | IMPASUG-ONG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-26 | 2015-04-28 | 100314S00056 | 14KA0018 | 2014-06-30 | 2014-07-01 | 2014-07-31 | 2014-08-29 | 2014-09-08 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7411 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126771 | Palacpacan ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-24 | 2015-06-05 | 100314S00178 | 14KA0033 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7412 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126301 | Paradise ES | CABANGLASAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-05-04 | 100314S00031 | 14KA0025 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | BRILLANTES CONSTRUCTION
7413 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126773 | San Jose ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-24 | 2015-06-05 | 100314S00177 | 14KA0033 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7414 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126789 | San Juan ES | IMPASUG-ONG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-15 | 100314S00053 | 14KA0019 | 2014-06-08 | 2014-06-10 | 2014-06-26 | 2014-07-16 | 2014-07-28 | ZI 9 BUILDERS AND SUPPLIES
7415 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126510 | Sobsob ES | LANTAPAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-04-06 | 100314S00057 | 14KA0027 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | PAGADIAN AGGREGATES & MARKETING
7416 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126511 | Songco ES | LANTAPAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-07-08 | 100314S00023 | 14KA0026 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | A.R. & MARK BUILDERS
7417 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126304 | Tagiptip ES | CABANGLASAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-23 | 2014-12-23 | 100314S00038 | 14KA0024 | 2014-08-21 | 2014-08-22 | 2014-09-04 | 2014-09-17 | 2014-09-25 | L & L CONSTRUCTION
7418 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126512 | Valbueco ES | LANTAPAN | 2 | 1 | 7 | 1STY3CL & 2STY4CL | 2014 K10 BATCH 3 | 8816701.1096 |  |  | COMPLETED | 1 | 2015-04-14 | 2015-06-10 | 100314S00189 | 14KA0069 | 2014-11-13 | 2014-11-14 | 2014-11-27 | 2014-12-08 | 2014-12-16 | KEZ ENTERPRISES
7419 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126513 | Victory ES | LANTAPAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-07-28 | 100314S00055 | 14KA0026 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | A.R. & MARK BUILDERS
7420 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126648 | Ali-al PS | MARAMAG | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2016-01-20 |  | 100314S00201 | 15KB0010 | 2015-07-23 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-17 | FFJJ CONSTRUCTION
7421 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126308 | Anggaan ES | DAMULOG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-16 | 2015-08-26 | 100314S00050 | 14KB00003 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7422 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126705 | Apyao ES | QUEZON | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-12-19 | 100314S00103 | 14KB00012 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7423 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126433 | Balintawak ES | KIBAWE | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-05-15 | 100314S00017 | 14KB00007 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7424 | NC 2014 | K10 (2014) | Region X | Bukidnon | 199524 | Balud PS | DAMULOG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-12-16 | 2015-08-27 | 100314S00098 | 14KB00003 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7425 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126651 | Bantayan PS | MARAMAG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-08-27 | 100314S00063 | 14KB00010 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7426 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126325 | Barongcot ES | DANGCAGAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-12-01 | 100314S00022 | 14KB00004 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | MAFIL BUILDERS, INC.
7427 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126652 | Base Camp ES | MARAMAG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-08-25 | 100314S00120 | 14KB00011 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7428 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126463 | Bobong ES | KITAOTAO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2015-06-01 | 100314S00021 | 14KB00008 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7429 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126466 | Calapaton ES | KITAOTAO | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-08-27 | 100314S00019 | 14KB00009 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7430 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126653 | Camp I ES | MARAMAG | 3 | 1 | 9 | 2UNIT 1STY3CL & 1STY3CL | 2014 K10 BATCH 4A | 7554109.032 |  |  | COMPLETED | 1 | 2015-09-03 | 2015-09-30 | 100314S00193 | 14KB00045 | 2014-12-08 | 2014-12-12 | 2014-12-23 | 2015-01-05 | 2015-01-12 | Z & L CONSTRUCTION & SUPPLIES
7431 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126725 | Cawayan ES | QUEZON | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2015-07-31 | 100314S00100 | 14KB00013 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7432 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126654 | Colambugon ES | MARAMAG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-08-25 | 100314S00110 | 14KB00010 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7433 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126656 | Danggawan ES | MARAMAG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-08-25 | 100314S00109 | 14KB00010 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7434 | NC 2014 | K10 (2014) | Region X | Bukidnon | 314921 | Dologon NHS - Kiharong Annex | MARAMAG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 |  | 2014-12-01 | 100314S00126 | 14KB00011 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7435 | NC 2014 | K10 (2014) | Region X | Bukidnon | 314928 | Dologon NHS (San Roque Annex) | MARAMAG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 |  | 2014-12-01 | 100314S00124 | 14KB00011 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7436 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126328 | Dolorosa ES | DANGCAGAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1998417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-12-01 | 100314S00014 | 14KB00004 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | MAFIL BUILDERS, INC.
7437 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126344 | Don Carlos CES | DON CARLOS | 3 | 1 | 7 | 2STY4CL & 1STY3CL | 2014 K10 BATCH 4A | 8816701.1096 |  |  | COMPLETED | 1 | 2015-09-18 | 2015-10-31 | 100314S00192 | 14KB00044 | 2014-12-08 | 2014-12-12 | 2014-12-23 | 2015-01-05 | 2015-01-12 | Z & L CONSTRUCTION & SUPPLIES
7438 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126708 | Dumalama ES | QUEZON | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2002417.57 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-12-19 | 100314S00047 | 14KB00012 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7439 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126397 | Husayan ES | KADINGILAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2015-08-27 | 100314S00007 | 14KB00006 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7440 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126347 | Kalubihon ES | DON CARLOS | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-07-31 | 100314S00011 | 14KB00005 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7441 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126348 | Kasigkot ES | DON CARLOS | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-07-31 | 100314S00015 | 14KB00005 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7442 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126472 | Kauyonan ES | KITAOTAO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2014-12-31 | 100314S00024 | 14KB00009 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7443 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126709 | Kibacania ES | QUEZON | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2007417.57 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 100314S00111 | 14KB00013 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7444 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126401 | Kibalagon ES | KADINGILAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2015-08-27 | 100314S00006 | 14KB00006 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7445 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126402 | Kibogtok ES | KADINGILAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2015-08-27 | 100314S00005 | 14KB00006 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7446 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126439 | Kikipot ES | KIBAWE | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 100314S00202 | 15KB0009 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-17 | RRN CONSTRUCTION
7447 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126474 | Kipilas ES | KITAOTAO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2015-08-27 | 100314S00025 | 14KB00008 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7448 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126662 | Kuya ES | MARAMAG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-07-31 | 100314S00108 | 14KB00010 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7449 | NC 2014 | K10 (2014) | Region X | Bukidnon | 303965 | Kuya NHS | MARAMAG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 |  | 2014-12-01 | 100314S00118 | 14KB00010 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7450 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126443 | Labuagon ES | KIBAWE | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-05-15 | 100314S00018 | 14KB00007 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7451 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126711 | Libertad ES | QUEZON | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1987417.57 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 100314S00101 | 14KB00013 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7452 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126404 | Mabuhay ES | KADINGILAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2015-08-27 | 100314S00004 | 14KB00006 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7453 | NC 2014 | K10 (2014) | Region X | Bukidnon | 314929 | Macapari NHS | DAMULOG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 |  | 2014-12-16 | 100314S00123 | 14KB00003 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7454 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126444 | Magsaysay ES | KIBAWE | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-01-29 |  | 100314S00030 | 14KB00007 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7455 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126665 | Mahawan ES | MARAMAG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-08-25 | 100314S00107 | 14KB00010 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7456 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126316 | Maican ES | DAMULOG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2014-12-16 | 2015-08-26 | 100314S00049 | 14KB00003 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7457 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126334 | Migcuya ES | DANGCAGAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1998417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-12-01 | 100314S00013 | 14KB00004 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | MAFIL BUILDERS, INC.
7458 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126356 | Minsalagan ES | DON CARLOS | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-08-07 | 100314S00009 | 14KB00005 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7459 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126318 | New Compostela ES | DAMULOG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-16 | 2015-08-26 | 100314S00048 | 14KB00003 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7460 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126480 | North Dalurong ES | KITAOTAO | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2015-08-27 | 100314S00026 | 14KB00008 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7461 | NC 2014 | K10 (2014) | Region X | Bukidnon | 303976 | Old Damulog NHS | DAMULOG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 |  | 2014-12-01 | 100314S00102 | 14KB00003 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7462 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126481 | Pagan ES | KITAOTAO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-08-27 | 100314S00027 | 14KB00009 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7463 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126669 | Panadtalan ES | MARAMAG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-07-31 | 100314S00106 | 14KB00011 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7464 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126670 | Panalsalan ES | MARAMAG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-07-31 | 100314S00105 | 14KB00010 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7465 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126408 | Pinamangguan ES | KADINGILAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2015-08-27 | 100314S00010 | 14KB00006 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7466 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126450 | Pinamula ES | KIBAWE | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-07-31 | 100314S00020 | 14KB00007 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7467 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126739 | Pinilayan ES | QUEZON | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-12-19 | 100314S00099 | 14KB00012 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7468 | NC 2014 | K10 (2014) | Region X | Bukidnon | 314912 | Quezon NHS | QUEZON | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 |  | 2014-12-31 | 100314S00104 | 14KB00013 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
7469 | NC 2014 | K10 (2014) | Region X | Bukidnon | 314930 | Quezon NHS - Apyao Annex | QUEZON | 3 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3775805.49 |  |  | COMPLETED | 1 |  | 2014-12-19 | 100314S00122 | 14KB00012 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7470 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126484 | Sagasaan ES | KITAOTAO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-07-31 | 100314S00028 | 14KB00009 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7471 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126337 | Sagbayan ES | DANGCAGAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-12-01 | 100314S00012 | 14KB00004 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | MAFIL BUILDERS, INC.
7472 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126322 | Sampagar ES | DAMULOG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 100314S00062 | 14KB00003 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7473 | NC 2014 | K10 (2014) | Region X | Bukidnon | 314926 | San Andres NHS - Cabadiangan Annex | KADINGILAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 |  | 2014-12-15 | 100314S00125 | 14KB00006 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7474 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126672 | San Carlos ES | MARAMAG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-07-31 | 100314S00096 | 14KB00010 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | A.R. & MARK BUILDERS
7475 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126673 | San Miguel CES | MARAMAG | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4B | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 100314S00199 | 15KB0008 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-08-05 | 2015-08-17 | J.T. GAMOLO CONSTRUCTION
7476 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126365 | San Nicolas ES | DON CARLOS | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-08-07 | 100314S00008 | 14KB00005 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7477 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126366 | San Roque ES | DON CARLOS | 3 | 1 | 3 | 1STY2CL & 1STY1CL | 2014 K10 BATCH 4A | 2692811.1604 |  |  | COMPLETED | 1 | 2015-05-16 | 2015-07-15 | 100314S00194 | 14KB00046 | 2014-12-08 | 2014-12-12 | 2014-12-23 | 2015-01-05 | 2015-01-12 | Z & L CONSTRUCTION & SUPPLIES
7478 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126338 | San Vicente ES | DANGCAGAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-12-01 | 100314S00003 | 14KB00004 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | MAFIL BUILDERS, INC.
7479 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126410 | Sibonga ES | KADINGILAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2015-05-15 | 100314S00016 | 14KB00006 | 2014-07-22 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7480 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126367 | Sinangguyan ES | DON CARLOS | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-20 | 2015-12-20 | 100314S00200 | 15KB0011 | 2015-07-10 | 2015-07-10 | 2015-08-20 | 2015-09-07 | 2015-09-17 | XY BUILDERS
7481 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126489 | Sinaysayan ES | KITAOTAO | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2015-08-27 | 100314S00029 | 14KB00008 | 2014-07-02 | 2014-06-13 | 2014-07-22 | 2014-07-30 | 2014-08-29 | LEGACY CONSTRUCTION
7482 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126675 | Tubigon ES | MARAMAG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2015-08-27 | 100314S00078 | 14KB00011 | 2014-06-26 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-30 | LLM CONCRETE PRODUCTS
7483 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126676 | Adtuyon ES | PANGANTUCAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-06 | 100314S00116 | 14KC0042 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | BRILLANTES CONSTRUCTION
7484 | NC 2014 | K10 (2014) | Region X | Bukidnon | 199516 | Agaton ES | KALILANGAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-22 | 100314S00073 | 14KC0040 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7485 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126680 | Bangahan ES | PANGANTUCAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-04 | 100314S00115 | 14KC0043 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7486 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126413 | Bangbang ES | KALILANGAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-19 | 100314S00121 | 14KC0040 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7487 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126418 | Forchacu III ES | KALILANGAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-23 | 100314S00112 | 14KC0040 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7488 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126419 | Forchacu IV ES | KALILANGAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-22 | 100314S00119 | 14KC0040 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7489 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126683 | Jarque ES | PANGANTUCAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-08 | 100314S00114 | 14KC0042 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | BRILLANTES CONSTRUCTION
7490 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126422 | Kibaning ES | KALILANGAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-19 | 100314S00127 | 14KC0041 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7491 | NC 2014 | K10 (2014) | Region X | Bukidnon | 199520 | Kidansalan ES | KALILANGAN | 4 | 1 | 3 | 1STY2CL & 1STY1CL | 2014 K10 BATCH 4A | 2692811.1604 |  |  | COMPLETED | 1 | 2015-06-25 | 2015-06-15 | 100314S00195 | 14KC0061 | 2014-11-02 | 2014-11-03 | 2014-12-04 | 2014-12-09 | 2014-12-18 | R. SEMILLA CONSTRUCTION & MARKETING
7492 | NC 2014 | K10 (2014) | Region X | Bukidnon | 303962 | Kimanait NHS | PANGANTUCAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 |  | 2014-12-11 | 100314S00071 | 14KC0044 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7493 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126686 | Kipaducan ES | PANGANTUCAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-10-07 | 100314S00113 | 14KC0044 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7494 | NC 2014 | K10 (2014) | Region X | Bukidnon | 314902 | Langcataon NHS | PANGANTUCAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 |  | 2014-12-11 | 100314S00079 | 14KC0045 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7495 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126688 | Lantay ES | PANGANTUCAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-10-08 | 100314S00088 | 14KC0045 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7496 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126689 | Madaya ES | PANGANTUCAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-08 | 100314S00065 | 14KC0043 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7497 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126430 | Maulawe ES | KALILANGAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-23 | 100314S00117 | 14KC0041 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7498 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126691 | Mendiz ES | PANGANTUCAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-10 | 100314S00097 | 14KC0043 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7499 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126694 | New Eden ES | PANGANTUCAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-09-15 | 100314S00077 | 14KC0044 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7500 | NC 2014 | K10 (2014) | Region X | Bukidnon | 199508 | Pamotolon ES | KALILANGAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-23 | 100314S00074 | 14KC0041 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7501 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126698 | Portulin ES | PANGANTUCAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-03 | 100314S00076 | 14KC0045 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7502 | NC 2014 | K10 (2014) | Region X | Bukidnon | 199533 | Pud-ong PS | KALILANGAN | 4 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2900174.43 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-22 | 100314S00064 | 14KC0041 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | LLM CONCRETE PRODUCTS
7503 | NC 2014 | K10 (2014) | Region X | Bukidnon | 126702 | San Miguel ES | PANGANTUCAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-11-29 | 100314S00075 | 14KC0042 | 2014-06-26 | 2014-06-30 | 2014-07-11 | 2014-07-13 | 2014-07-25 | BRILLANTES CONSTRUCTION
7504 | NC 2014 | K10 (2014) | Region X | Cagayan de Oro City | 127973 | Besigan ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-13 | 100814S00005 | 14KH0017 | 2014-07-31 | 2014-08-12 | 2014-08-13 | 2014-09-10 | 2014-09-16 | KVC CONSTRUCTION
7505 | NC 2014 | K10 (2014) | Region X | Cagayan de Oro City | 315411 | Kauswagan NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7656 |  |  | COMPLETED | 1 |  | 2015-05-21 | 100814S00016 | 14KH0056 | 2014-12-08 | 2014-12-11 | 2014-12-23 | 2015-01-05 | 2015-01-15 | RED CONSTRUCTION TECHNIK
7506 | NC 2014 | K10 (2014) | Region X | Cagayan de Oro City | 304119 | Lumbia NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4A | 8228453.2031 |  |  | COMPLETED | 1 |  | 2015-06-20 | 100814S00015 | 14KH0055 | 2014-12-08 | 2014-12-11 | 2014-12-23 | 2015-01-05 | 2015-01-15 | BADSBRO CONSTRUCTION AND GENERAL MERCHANDISE
7507 | NC 2014 | K10 (2014) | Region X | Cagayan de Oro City | 304110 | Pedro "Oloy" N. Roa, Sr. HS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8298453.2031 |  |  | COMPLETED | 1 | 2015-06-03 | 2015-06-03 | 100814S00014 | 14KH0053 | 2014-12-02 | 2014-12-02 | 2014-12-12 | 2014-12-19 | 2014-12-29 | FOOTPRINTS CONSTRUCTION
7508 | NC 2014 | K10 (2014) | Region X | Cagayan de Oro City | 127993 | Sacred Heart Village ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-04-04 | 2015-04-04 | 100814S00010 | 14KH0052 | 2014-12-02 | 2014-12-02 | 2014-12-12 | 2014-12-22 | 2014-12-29 | L & L CONSTRUCTION
7509 | NC 2014 | K10 (2014) | Region X | Cagayan de Oro City | 127964 | Camaman-An ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14115118.3984 |  |  | COMPLETED | 1 | 2015-07-05 | 2015-07-05 | 100814S00008 | 14KD0029 | 2014-11-18 | 2014-11-19 | 2014-12-11 | 2014-12-26 | 2014-12-31 | L.C. CONSTRUCTION
7510 | NC 2014 | K10 (2014) | Region X | Cagayan de Oro City | 127940 | City CS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 27 | 3UNIT 3STY9CL | 2014 K10 BATCH 3 | 42345355.1953 |  |  | COMPLETED | 1 | 2015-09-03 | 2015-10-25 | 100814S00013 | 14KD0031 | 2014-11-20 | 2014-11-20 | 2014-12-11 | 2014-12-16 | 2014-12-31 | THREE W BUILDERS, INC.
7511 | NC 2014 | K10 (2014) | Region X | Cagayan de Oro City | 127955 | Corrales ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1 | 2015-06-20 | 2015-06-20 | 100814S00007 | 14KD0026 | 2014-11-17 | 2014-11-19 | 2014-12-11 | 2014-12-16 | 2014-12-31 | L.C. CONSTRUCTION
7512 | NC 2014 | K10 (2014) | Region X | Cagayan de Oro City | 127941 | Cugman ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-06 | 100814S00012 | 14KD0027 | 2014-11-18 | 2014-11-19 | 2014-12-01 | 2014-12-09 | 2014-12-31 | CDH BUILDERS, INC. (FORMERLY: CDH BUILDERS AND FAB
7513 | NC 2014 | K10 (2014) | Region X | Cagayan de Oro City | 127965 | Indahag ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8298453.2031 |  |  | COMPLETED | 1 | 2015-06-04 | 2015-07-24 | 100814S00006 | 14KD0025 | 2014-11-04 | 2014-11-16 | 2014-11-19 | 2014-11-28 | 2014-12-15 | DL ENTERPRISES
7514 | NC 2014 | K10 (2014) | Region X | Cagayan de Oro City | 304118 | Lapasan NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14045118.3984 |  |  | COMPLETED | 1 | 2015-07-05 | 2015-09-16 | 100814S00011 | 14KD0030 | 2014-11-18 | 2014-11-19 | 2014-12-11 | 2014-12-16 | 2014-12-31 | A.R. & MARK BUILDERS
7515 | NC 2014 | K10 (2014) | Region X | Cagayan de Oro City | 127954 | Tablon ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14045118.3984 |  |  | COMPLETED | 1 | 2015-07-05 | 2015-07-05 | 100814S00009 | 14KD0028 | 2014-11-18 | 2014-11-19 | 2014-12-11 | 2014-12-16 | 2014-12-31 | JARGON CONSTRUCTION & SUPPLY
7516 | NC 2014 | K10 (2014) | Region X | Camiguin | 303991 | Guinsiliban NHS | GUINSILIBAN | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4362249.6094 |  |  | COMPLETED | 1 |  | 2015-06-27 | 100414S00001 | 14KE0056 | 2015-01-03 | 2015-01-08 | 2015-01-09 | 2015-01-17 | 2015-01-27 | JAPUZ-JANSOL ENTERPRISES
7517 | NC 2014 | K10 (2014) | Region X | El Salvador | 127670 | Cogon ES | CITY OF EL SALVADOR | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-25 | 2014-09-25 | 100614S00025 | 14KL0048 | 2014-07-19 | 2014-07-22 | 2014-07-25 | 2014-08-06 | 2014-08-26 | R. DE MESA CONSTRUCTION
7518 | NC 2014 | K10 (2014) | Region X | El Salvador | 315318 | Hinigdaan NHS | CITY OF EL SALVADOR | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1993417.57 |  |  | COMPLETED | 1 |  | 2014-09-16 | 100614S00024 | 14KL0025 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | PAGADIAN AGGREGATES & MARKETING
7519 | NC 2014 | K10 (2014) | Region X | Gingoog City | 128031 | Kamanikan ES | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6419264.7656 |  |  | COMPLETED | 1 | 2015-05-14 | 2015-05-14 | 100614S00128 | 14KK0097 | 2014-11-11 | 2014-11-23 | 2014-11-24 | 2014-11-28 | 2014-12-09 | WDM CONSTRUCTION AND SUPPLIES
7520 | NC 2014 | K10 (2014) | Region X | Gingoog City | 128037 | Maribucao ES | GINGOOG CITY | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2875174.43 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-10-25 | 100614S00073 | 14KK0021- Cluster LK | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7521 | NC 2014 | K10 (2014) | Region X | Gingoog City | 128040 | Pangasihan ES | GINGOOG CITY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-10-25 | 100614S00072 | 14KK0021- Cluster LK | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7522 | NC 2014 | K10 (2014) | Region X | Gingoog City | 128075 | Pigsalohan ES | GINGOOG CITY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 100614S00070 | 14KK0021- Cluster LK | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7523 | NC 2014 | K10 (2014) | Region X | Gingoog City | 128077 | Sulpicio Lugod ES | GINGOOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-10-25 | 100614S00042 | 14KK0021- Cluster LK | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7524 | NC 2014 | K10 (2014) | Region X | Iligan City | 315605 | Del Carmen Integrated School | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 100114S00020 | 14KF0015 | 2014-06-16 | 2014-06-29 | 2014-06-30 | 2014-07-09 | 2014-07-22 | AL-FAHDEL CONSTRUCTION & ENGINEERING
7525 | NC 2014 | K10 (2014) | Region X | Iligan City | 128084 | Dorotheo Lloren MES | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2046737.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 100114S00021 | 14KF0015 | 2014-06-16 | 2014-06-29 | 2014-06-30 | 2014-07-09 | 2014-07-22 | AL-FAHDEL CONSTRUCTION & ENGINEERING
7526 | NC 2014 | K10 (2014) | Region X | Iligan City | 128121 | Kabangahan I ES | ILIGAN CITY | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2962278.43 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-11-18 | 100114S00014 | 14KF0016 | 2014-06-17 | 2014-06-27 | 2014-06-30 | 2014-07-09 | 2014-07-22 | AL-FAHDEL CONSTRUCTION & ENGINEERING
7527 | NC 2014 | K10 (2014) | Region X | Iligan City | 128123 | Kalamalamahan ES | ILIGAN CITY | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3018922.43 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-11-18 | 100114S00017 | 14KF0016 | 2014-06-17 | 2014-06-29 | 2014-06-30 | 2014-07-09 | 2014-07-22 | AL-FAHDEL CONSTRUCTION & ENGINEERING
7528 | NC 2014 | K10 (2014) | Region X | Iligan City | 128141 | Lumbatin ES | ILIGAN CITY | 0 | 1 | 4 | 2UNIT 2STY2CL |  | 9144096.98 |  |  | COMPLETED | 1
7529 | NC 2014 | K10 (2014) | Region X | Iligan City | 128159 | Maria Cristina Falls ES | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2018577.57 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-10-20 | 100114S00016 | 14KF0015 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-09 | 2014-07-22 | AL-FAHDEL CONSTRUCTION & ENGINEERING
7530 | NC 2014 | K10 (2014) | Region X | Iligan City | 128087 | Servillano Reuyan MES | ILIGAN CITY | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2929910.43 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 100114S00019 | 14KF0015 | 2014-06-17 | 2014-06-27 | 2014-06-30 | 2014-07-09 | 2014-07-22 | AL-FAHDEL CONSTRUCTION & ENGINEERING
7531 | NC 2014 | K10 (2014) | Region X | Iligan City | 315607 | Sultan Mamarinta Panandigan Integrated School | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2021137.57 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-11-18 | 100114S00012 | 14KF0016 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-09 | 2014-07-22 | AL-FAHDEL CONSTRUCTION & ENGINEERING
7532 | NC 2014 | K10 (2014) | Region X | Iligan City | 304159 | Tubaran NHS | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2006257.57 |  |  | COMPLETED | 1 |  | 2014-11-18 | 100114S00015 | 14KF0016 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-09 | 2014-07-22 | AL-FAHDEL CONSTRUCTION & ENGINEERING
7533 | NC 2014 | K10 (2014) | Region X | Iligan City | 315606 | Tubaran NHS (Lanipao Annex) | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2029297.57 |  |  | COMPLETED | 1 |  | 2015-02-01 | 100114S00013 | 14KF0041 | 2014-07-04 | 2014-07-16 | 2014-10-03 | 2014-10-18 | 2014-11-04 | AHMADI BUILDERS
7534 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 126949 | Abaga ES | BALOI | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 100114S00005 | 14KG0033 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | LANAO BUILDER AND ENTERPRISES
7535 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127211 | Cabasaran PS | TAGOLOAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 100114S00049 | 14KG0035 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | TESAR BUILDERS
7536 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 126952 | Cadayonan ES | BALOI | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-07 | 2015-11-07 | 100114S00060 | 15KG0010 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-31 | 2015-08-07 | LANAO GENESIS CONSTRUCTION SUPPLY
7537 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 200510 | Demarao PS | BACOLOD | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-11 | 2015-12-11 | 100114S00058 | 15KF0066 | 2015-07-17 | 2015-07-29 | 2015-07-30 | 2015-08-04 | 2015-08-28 | MARKBUILT ENTERPRISES
7538 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127212 | Dimayon PS | TAGOLOAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 100114S00041 | 14KG0035 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | TESAR BUILDERS
7539 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 304001 | Diosdado Yap Memo. NHS | BAROY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 |  | 2014-10-19 | 100114S00009 | 14KF0018 | 2014-06-16 | 2014-06-29 | 2014-06-30 | 2014-07-09 | 2014-07-22 | RARMAN CONSTRUCTION & TRADING
7540 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 126943 | Kahayag ES | BACOLOD | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-19 | 2014-10-19 | 100114S00008 | 14KF0018 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-09 | 2014-07-22 | RARMAN CONSTRUCTION & TRADING
7541 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 304011 | Marcela T. Mabanta Memo. NHS | KAUSWAGAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 |  | 2014-10-19 | 100114S00010 | 14KF0018 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-09 | 2014-07-22 | RARMAN CONSTRUCTION & TRADING
7542 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 126970 | Matampay PS | BALOI | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 100114S00006 | 14KG0033 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | LANAO BUILDER AND ENTERPRISES
7543 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 126971 | Momungan ES | BALOI | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-07 | 2015-11-07 | 100114S00050 | 15KG0009 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-31 | 2015-08-07 | JAMCON BUILDERS
7544 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 126972 | Olango ES | BALOI | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-10-13 | 2014-10-13 | 100114S00007 | 14KG0027 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | LANAO BUILDER AND ENTERPRISES
7545 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127229 | Palao Elementary School | TUBOD (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-11 | 2015-11-11 | 100114S00059 | 15KF0065 | 2015-07-17 | 2015-07-28 | 2015-07-30 | 2015-08-04 | 2015-08-28 | LANAO BUILDER AND ENTERPRISES
7546 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127142 | Pendulonan PS | MATUNGAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-07 | 2015-11-07 | 100114S00055 | 15KG0008 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-31 | 2015-08-07 | TESAR BUILDERS
7547 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 126947 | Rufino Santos Sr Mem ES | BACOLOD | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-19 | 2014-10-19 | 100114S00004 | 14KF0018 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-09 | 2014-07-22 | RARMAN CONSTRUCTION & TRADING
7548 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127099 | Samburon ES | LINAMON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-19 | 2014-10-19 | 100114S00011 | 14KF0018 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-09 | 2014-07-22 | RARMAN CONSTRUCTION & TRADING
7549 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 126960 | Sigayan PS | BALOI | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-07 | 2015-11-07 | 100114S00056 | 15KG0005 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-31 | 2015-08-07 | TESAR BUILDERS
7550 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127062 | Sucodan ES | KOLAMBUGAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-11 | 2015-12-11 | 100114S00057 | 15KF0067 | 2015-07-17 | 2015-07-29 | 2015-07-30 | 2015-08-04 | 2015-08-28 | LANAO BUILDER AND ENTERPRISES
7551 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127218 | Tagoloan ES | TAGOLOAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 100114S00042 | 14KG0035 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | TESAR BUILDERS
7552 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 200521 | Balintad PS | MUNAI | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 100114S00031 | 14KG0032 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | JAMCON BUILDERS
7553 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 126988 | Bel-is ES | KAPATAGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-15 | 2014-10-15 | 100114S00043 | 14KG0022 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | UNAYAN BUILDERS & CONSTRUCTION SUPPLY
7554 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 200518 | Cadayonan PS | MUNAI | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 100114S00032 | 14KG0032 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | JAMCON BUILDERS
7555 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127067 | Camalan PS | LALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 100114S00037 | 14KG0018 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | LANAO BUILDER AND ENTERPRISES
7556 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127019 | Campo Islam PS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 100114S00018 | 14KG0031 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | UNAYAN BUILDERS & CONSTRUCTION SUPPLY
7557 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 500249 | Carusa ES | KAPATAGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-15 | 2014-10-15 | 100114S00045 | 14KG0023 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | UNAYAN BUILDERS & CONSTRUCTION SUPPLY
7558 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127069 | Donggoan ES | LALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 100114S00039 | 14KG0019 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | LANAO BUILDER AND ENTERPRISES
7559 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127194 | Inudaran ES | SAPAD | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 100114S00033 | 14KG0028 | 2014-06-26 | 2014-06-27 | 2014-07-09 | 2014-07-14 | 2014-07-21 | JAMCON BUILDERS
7560 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127008 | La Libertad ES | KAPATAGAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 100114S00046 | 14KG0025 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | LANAO BUILDER AND ENTERPRISES
7561 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 315108 | Lala Proper IS | LALA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2015-11-07 | 2015-11-07 | 100114S00053 | 15KG0006 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-31 | 2015-08-07 | D.C.M. CONSTRUCTION
7562 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 |  | 2014-09-28 | 100114S00038 | 14KG0034 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | UNAYAN BUILDERS & CONSTRUCTION SUPPLY
7563 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127140 | Pantaon PS | POONA PIAGAPO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 100114S00035 | 14KG0030 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | TESAR BUILDERS
7564 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127088 | Pendulonan ES | LALA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 100114S00040 | 14KG0020 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | LANAO BUILDER AND ENTERPRISES
7565 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 304006 | Placida Mequiabas Mem. NHS (Lapinig NHS) | KAPATAGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 |  | 2014-10-15 | 100114S00048 | 14KG0021 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | UNAYAN BUILDERS & CONSTRUCTION SUPPLY
7566 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 315104 | Poonapiagapo NHS(Annex Matungao NHS) | POONA PIAGAPO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 |  | 2014-09-28 | 100114S00030 | 14KG0030 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | TESAR BUILDERS
7567 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127157 | Pualas Primary School | PANTAO RAGAT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 100114S00034 | 14KG0034 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | UNAYAN BUILDERS & CONSTRUCTION SUPPLY
7568 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 126998 | San Vicente PS | KAPATAGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-10-03 | 100114S00044 | 14KG0024 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | UNAYAN BUILDERS & CONSTRUCTION SUPPLY
7569 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127106 | Shiek Omar ES (Lumbac ES) | MAGSAYSAY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-20 | 2014-10-20 | 100114S00036 | 14KG0029 | 2014-07-20 | 2014-07-21 | 2014-08-01 | 2014-08-11 | 2014-08-15 | AMMAR CONSTRUCTION AND ENTERPRISES
7570 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127034 | Sultan Naga Dimaporo CS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-25 | 100114S00024 | 14KG0031 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | UNAYAN BUILDERS & CONSTRUCTION SUPPLY
7571 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 315107 | Sultan Naga Dimaporo Mem. IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-12-15 | 100114S00054 | 15KG0007 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-31 | 2015-08-07 | D.C.M. CONSTRUCTION
7572 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 200544 | Tamparan Primary School | MUNAI | 2 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 4B | 3629480.3479 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-11-02 | 100114S00052 | 15KG0020 | 2015-07-21 | 2015-07-22 | 2015-08-03 | 2015-08-07 | 2015-08-17 | AMMAR CONSTRUCTION AND ENTERPRISES
7573 | NC 2014 | K10 (2014) | Region X | Lanao del Norte | 127013 | Tipolo ES | KAPATAGAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 100114S00047 | 14KG0026 | 2014-06-03 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-09 | LANAO BUILDER AND ENTERPRISES
7574 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126557 | Aglayan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 2UNIT 1STY1CL | 2014 K10 BATCH 1 | 2194658.24 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-30 | 100314S00066 | 14KA0022 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7575 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126534 | Bagong Silang ES | CITY MALAYBALAY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-30 | 100314S00069 | 14KA0022 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7576 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126560 | Binalbagan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-15 | 100314S00086 | 14KA0023 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | MAFIL BUILDERS, INC.
7577 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 314904 | Bukidnon NHS - Aglayan Annex | CITY MALAYBALAY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 |  | 2014-11-09 | 100314S00095 | 14KA0022 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7578 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 314916 | Bukidnon NHS - San Jose Annex | CITY MALAYBALAY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 |  | 2014-11-09 | 100314S00085 | 14KA0021 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | J.T. GAMOLO CONSTRUCTION
7579 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 500409 | Busdi IS | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 |  | 2014-12-23 | 100314S00083 | 14KA0024 | 2014-08-21 | 2014-08-22 | 2014-09-04 | 2014-09-17 | 2014-09-25 | L & L CONSTRUCTION
7580 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 500245 | Canayan IS | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 |  | 2014-12-06 | 100314S00084 | 14KA0020 | 2014-06-30 | 2014-07-01 | 2014-07-31 | 2014-08-29 | 2014-09-08 | J.T. GAMOLO CONSTRUCTION
7581 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126580 | Dalwangan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-06 | 2014-12-06 | 100314S00093 | 14KA0020 | 2014-06-30 | 2014-07-01 | 2014-07-31 | 2014-08-29 | 2014-09-08 | J.T. GAMOLO CONSTRUCTION
7582 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126563 | Dapulan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-30 | 100314S00070 | 14KA0023 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | MAFIL BUILDERS, INC.
7583 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126581 | Imbayao ES | CITY MALAYBALAY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 100314S00092 | 14KA0021 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | J.T. GAMOLO CONSTRUCTION
7584 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126582 | Kalasungay CES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-15 | 100314S00091 | 14KA0022 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7585 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126564 | Laguitas ES | CITY MALAYBALAY (Capital) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 100314S00072 | 14KA0021 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | J.T. GAMOLO CONSTRUCTION
7586 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126547 | Managok ES | CITY MALAYBALAY (Capital) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2900174.43 |  |  | COMPLETED | 1 | 2014-12-23 | 2014-12-23 | 100314S00068 | 14KA0024 | 2014-08-21 | 2014-08-22 | 2014-09-04 | 2014-09-17 | 2014-09-25 | L & L CONSTRUCTION
7587 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126550 | Miglamin ES | CITY MALAYBALAY (Capital) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-15 | 100314S00067 | 14KA0025 | 2014-06-24 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | BRILLANTES CONSTRUCTION
7588 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126570 | Padernal ES | CITY MALAYBALAY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-15 | 100314S00094 | 14KA0023 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | MAFIL BUILDERS, INC.
7589 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126590 | Patpat ES | CITY MALAYBALAY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-06 | 2014-12-06 | 100314S00090 | 14KA0020 | 2014-06-30 | 2014-07-01 | 2014-07-31 | 2014-08-29 | 2014-09-08 | J.T. GAMOLO CONSTRUCTION
7590 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126591 | San Jose ES | CITY MALAYBALAY (Capital) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 100314S00089 | 14KA0021 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | J.T. GAMOLO CONSTRUCTION
7591 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 303982 | San Martin Agro-Industrial NHS | CITY MALAYBALAY (Capital) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 |  | 2014-11-09 | 100314S00087 | 14KA0023 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | MAFIL BUILDERS, INC.
7592 | NC 2014 | K10 (2014) | Region X | Malaybalay City | 126595 | Tintinaan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-30 | 100314S00080 | 14KA0022 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7593 | NC 2014 | K10 (2014) | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1 | 1 | 14 | COMPLETION OF 2STY10CL & COMPLETION OF 2STY4CL (WORKSHOP BLDG. SOTA-TECHVOC) | 2014 K10 BATCH 4A | 3210869.475 |  |  | COMPLETED | 1 |  | 2015-04-27 | 100514S00022 | 14KI0037 | 2014-11-05 | 2014-11-06 | 2014-12-11 | 2014-12-15 | 2014-12-22 | EDMOND RAY CONSTRUCTION & SUPPLY
7594 | NC 2014 | K10 (2014) | Region X | Misamis Occidental | 127409 | Biasong ES | LOPEZ JAENA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-25 | 2014-10-25 | 100514S00019 | 14ki0007 | 2014-06-09 | 2014-06-11 | 2014-06-24 | 2014-07-15 | 2014-07-21 | JDRC CONSTRUCTION & SUPPLIES
7595 | NC 2014 | K10 (2014) | Region X | Misamis Occidental | 304043 | Macalibre Alto NHS | LOPEZ JAENA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 |  | 2014-10-25 | 100514S00015 | 14ki0007 | 2014-06-09 | 2014-06-11 | 2014-06-24 | 2014-07-15 | 2014-07-21 | JDRC CONSTRUCTION & SUPPLIES
7596 | NC 2014 | K10 (2014) | Region X | Misamis Occidental | 304035 | Don Victoriano NHS | DON VICTORIANO CHIONGBIAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 |  | 2014-10-23 | 100514S00001 | 14KJ00025G | 2014-06-30 | 2014-07-14 | 2014-07-29 | 2014-08-06 | 2014-08-18 | By Administration
7597 | NC 2014 | K10 (2014) | Region X | Misamis Occidental | 127569 | Gumbil ES | TUDELA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 100514S00020 | 14KJ0022 | 2014-06-30 | 2014-07-18 | 2014-07-31 | 2014-08-08 | 2014-08-13 | L.C. CONSTRUCTION
7598 | NC 2014 | K10 (2014) | Region X | Misamis Occidental | 127545 | Katipunan ES | SINACABAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-16 | 2014-09-30 | 100514S00005 | 14KJ0024 | 2014-06-30 | 2014-07-08 | 2014-07-15 | 2014-08-08 | 2014-08-11 | C. DY BUILDERS AND GENERAL MERCHANDISE (FORMERLY CD
7599 | NC 2014 | K10 (2014) | Region X | Misamis Occidental | 127301 | Lodiong ES | BONIFACIO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-16 | 2014-09-30 | 100514S00014 | 14KJ0021 | 2014-06-30 | 2014-07-08 | 2014-07-11 | 2014-08-04 | 2014-08-11 | PUREGOLD CONSTRUCTION & DEVT. CORP.
7600 | NC 2014 | K10 (2014) | Region X | Misamis Occidental | 127305 | Lumapas ES | BONIFACIO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 100514S00010 | 14KJ0020 | 2014-06-30 | 2014-07-18 | 2014-07-31 | 2014-08-06 | 2014-08-13 | C. DY BUILDERS AND GENERAL MERCHANDISE (FORMERLY CD
7601 | NC 2014 | K10 (2014) | Region X | Misamis Occidental | 127307 | Migsale ES | BONIFACIO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-10-23 | 100514S00012 | 14KJ0018G | 2014-06-30 | 2014-07-14 | 2014-07-29 | 2014-08-06 | 2014-08-18 | By Administration
7602 | NC 2014 | K10 (2014) | Region X | Misamis Occidental | 127310 | Quezon ES | BONIFACIO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 100514S00018 | 14KJ0019 | 2014-06-30 | 2014-07-18 | 2014-07-31 | 2014-08-06 | 2014-08-13 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
7603 | NC 2014 | K10 (2014) | Region X | Misamis Occidental | 304055 | Sinonoc NHS | SINACABAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 |  | 2014-10-16 | 100514S00002 | 14KJ0023 | 2014-06-30 | 2014-07-08 | 2014-07-14 | 2014-08-08 | 2014-08-11 | C. DY BUILDERS AND GENERAL MERCHANDISE (FORMERLY CD
7604 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127714 | Alicomohan ES | SUGBONGCOGON | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-10-15 | 100614S00021 | 14KK0021-Cluster LH | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7605 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 500250 | Alipuaton IS | SALAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-25 | 2014-09-25 | 100614S00017 | 14KK0020-Cluster LG | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7606 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127771 | Artadi ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 7 | 1STY1CL & 2STY6CL | 2014 K10 BATCH 3 | 9196519.8953 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-06-24 | 100614S00114 | 14KK0088 | 2014-11-28 | 2014-12-10 | 2014-12-11 | 2014-12-15 | 2014-12-19 | WDM CONSTRUCTION AND SUPPLIES
7607 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127600 | Bagaay ES | BALINGASAG | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8290763.2031 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-07-03 | 100614S00127 | 14KK0096 | 2014-11-28 | 2014-12-10 | 2014-12-11 | 2014-12-15 | 2014-12-19 | PUREGOLD CONSTRUCTION & DEVT. CORP.
7608 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127601 | Balagnan ES | BALINGASAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102629.12 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-05 | 100614S00023 | 14KK0018-Cluster LE | 2014-06-10 | 2014-06-22 | 2014-06-23 | 2014-06-27 | 2014-07-01 | THREE W BUILDERS, INC.
7609 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127603 | Baliwagan CS | BALINGASAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-05 | 100614S00026 | 14KK0018-Cluster LE | 2014-06-10 | 2014-06-22 | 2014-06-23 | 2014-06-27 | 2014-07-01 | THREE W BUILDERS, INC.
7610 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127718 | Bolisong ES | KINOGUITAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-05 | 100614S00035 | 14KK0022 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | EDISON DEVELOPMENT CONSTRUCTION
7611 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127772 | Bonifacio Aquino ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 100614S00022 | 14KK0025- Cluster LL | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | DL ENTERPRISES
7612 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127607 | Calawag ES | BALINGASAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2015-03-03 | 2015-03-03 | 100614S00027 | 14KK0018-Cluster LE | 2014-06-10 | 2014-06-22 | 2014-06-23 | 2014-06-26 | 2014-07-01 | THREE W BUILDERS, INC.
7613 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127609 | Cogon ES | BALINGASAG | 1 | 1 | 5 | 1STY1CL & 2STY4CL | 2014 K10 BATCH 3 | 7266731.4578 |  |  | COMPLETED | 1 | 2015-06-13 | 2015-06-13 | 100614S00121 | 14KK0091 | 2014-11-18 | 2014-11-30 | 2014-12-01 | 2014-12-05 | 2014-12-09 | RBT CONSTRUCTION
7614 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127777 | Consuelo ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 100614S00034 | 14KK0025- Cluster LL | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | DL ENTERPRISES
7615 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127778 | Damayohan ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-06-13 | 2015-06-13 | 100614S00111 | 14KK0085 | 2014-11-11 | 2014-11-23 | 2014-11-24 | 2014-11-28 | 2014-12-09 | FOOTPRINTS CONSTRUCTION
7616 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127722 | Dampias ES | BINUANGAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-10-15 | 100614S00036 | 14KK0021-Cluster LH | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7617 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127610 | Dansuli ES | BALINGASAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-05 | 100614S00028 | 14KK0018-Cluster LE | 2014-06-10 | 2014-06-22 | 2014-06-23 | 2014-06-27 | 2014-07-01 | THREE W BUILDERS, INC.
7618 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127743 | Gaston ES | LAGONGLONG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-10-25 | 100614S00040 | 14KK0019- Cluster LF | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7619 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127853 | Guinalaban ES | SALAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-25 | 2014-09-25 | 100614S00009 | 14KK0020-Cluster LG | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7620 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 315313 | Gumabon NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105219.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 100614S00019 | 14KK0026 | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7621 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127613 | Hermano ES | BALINGASAG | 1 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 3 | 3474015.1776 |  |  | COMPLETED | 1 | 2015-03-25 | 2015-03-25 | 100614S00123 | 14KK0092 | 2014-11-11 | 2014-11-23 | 2014-11-24 | 2014-11-28 | 2014-12-09 | FOOTPRINTS CONSTRUCTION
7622 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127854 | Ili-Ilihon ES | SALAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-10-15 | 100614S00020 | 14KK0020-Cluster LG | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7623 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 315312 | Inobulan (Hunga Gue) NHS | SALAY | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-10-25 | 100614S00018 | 14KK0021-Cluster LH | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7624 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127855 | Inobulan ES | SALAY | 1 | 1 | 7 | 1STY1CL & 2STY6CL | 2014 K10 BATCH 3 | 9196519.8953 |  |  | COMPLETED | 1 | 2015-07-23 | 2015-07-23 | 100614S00113 | 14KK0087 | 2014-11-28 | 2014-12-10 | 2014-12-11 | 2014-12-15 | 2014-12-19 | WDM CONSTRUCTION AND SUPPLIES
7625 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127780 | Kandiis ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 100614S00032 | 14KK0025- Cluster LL | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | DL ENTERPRISES
7626 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127781 | Katipunan ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 100614S00006 | 14KK0026 | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7627 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127746 | Kauswagan ES | LAGONGLONG | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 100614S00041 | 14KK0019- Cluster LF | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7628 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127615 | Kibanban ES | BALINGASAG | 1 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2756530.281 |  |  | COMPLETED | 1 | 2015-06-13 | 2015-06-13 | 100614S00124 | 14KK0093 | 2014-11-11 | 2014-11-23 | 2014-11-24 | 2014-11-28 | 2014-12-02 | By Administration
7629 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127819 | Kibugahan ES | MEDINA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 100614S00002 | 14KK0023- Cluster LJ | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | ALXM CONSTRUCTION
7630 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127783 | Kibungsod CS | MAGSAYSAY (LINUGOS) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 100614S00008 | 14KK0025- Cluster LL | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | DL ENTERPRISES
7631 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 304076 | Kibungsod NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 |  | 2014-11-30 | 100614S00016 | 14KK0025- Cluster LL | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | DL ENTERPRISES
7632 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127619 | Linabu ES | BALINGASAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-05 | 100614S00029 | 14KK0018-Cluster LE | 2014-06-10 | 2014-06-22 | 2014-06-23 | 2014-06-27 | 2014-07-01 | THREE W BUILDERS, INC.
7633 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127730 | Mabini ES | BINUANGAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-10-15 | 100614S00037 | 14KK0021-Cluster LH | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7634 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127883 | Macopa ES | TALISAYAN | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-06-13 | 2015-06-13 | 100614S00112 | 14KK0086 | 2014-11-11 | 2014-11-22 | 2014-11-24 | 2014-11-28 | 2014-12-09 | L & L CONSTRUCTION
7635 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127786 | Mahayahay ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 100614S00004 | 14KK0026 | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7636 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127620 | Mambayaan ES | BALINGASAG | 1 | 1 | 12 | 2UNIT 2STY6CL | 2014 K10 BATCH 3 | 16456906.4062 |  |  | COMPLETED | 1 | 2015-07-23 |  | 100614S00129 | 14kk0098 | 2014-11-28 | 2014-12-10 | 2014-12-11 | 2014-12-15 | 2014-12-19 | EDISON DEVELOPMENT CONSTRUCTION
7637 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127885 | Mandahilag ES | TALISAYAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 100614S00011 | 14KK0023- Cluster LJ | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | ALXM CONSTRUCTION
7638 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127621 | Mandangoa ES | BALINGASAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-05 | 100614S00030 | 14KK0018-Cluster LE | 2014-06-10 | 2014-06-22 | 2014-06-23 | 2014-06-27 | 2014-07-01 | THREE W BUILDERS, INC.
7639 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127886 | Mantangale ES | BALINGOAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-05 | 2014-12-30 | 100614S00012 | 14KK0022 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | EDISON DEVELOPMENT CONSTRUCTION
7640 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127888 | Mintabon ES | TALISAYAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 100614S00013 | 14KK0023- Cluster LJ | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | ALXM CONSTRUCTION
7641 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127622 | Napaliran ES | BALINGASAG | 1 | 1 | 10 | 2STY4CL & 2STY6CL | 2014 K10 BATCH 3 | 14527117.9688 |  |  | COMPLETED | 1 | 2015-07-23 |  | 100614S00125 | 14KK0094 | 2014-11-28 | 2014-12-10 | 2014-12-11 | 2014-12-15 | 2014-12-19 | EDISON DEVELOPMENT CONSTRUCTION
7642 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127735 | Panabol ES | KINOGUITAN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 100614S00038 | 14KK0022 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | EDISON DEVELOPMENT CONSTRUCTION
7643 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127890 | Pook ES | TALISAYAN | 1 | 1 | 5 | 1STY1CL & 2STY4CL | 2014 K10 BATCH 3 | 7266731.4578 |  |  | COMPLETED | 1 | 2015-05-14 | 2015-05-14 | 100614S00107 | 14KK0082 | 2014-10-30 | 2014-11-11 | 2014-11-12 | 2014-11-16 | 2014-11-20 | WDM CONSTRUCTION AND SUPPLIES
7644 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127826 | Portulin ES | MEDINA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-11-15 | 100614S00001 | 14KK0023- Cluster LJ | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | ALXM CONSTRUCTION
7645 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127891 | Punta Santiago ES | TALISAYAN | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-05-14 | 2015-05-14 | 100614S00108 | 14KK0083 | 2014-11-11 | 2014-11-23 | 2014-11-24 | 2014-12-05 | 2014-12-09 | L & L CONSTRUCTION
7646 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127892 | Puting Balas ES | TALISAYAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 100614S00014 | 14KK0023- Cluster LJ | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | ALXM CONSTRUCTION
7647 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127623 | Quezon ES | BALINGASAG | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6362984.7656 |  |  | COMPLETED | 1
7648 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127624 | Rosario ES | BALINGASAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-05 | 100614S00031 | 14KK0018-Cluster LE | 2014-06-10 | 2014-06-22 | 2014-06-23 | 2014-06-26 | 2014-07-01 | THREE W BUILDERS, INC.
7649 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127626 | San Francisco ES | BALINGASAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-05 | 100614S00045 | 14KK0018-Cluster LE | 2014-06-10 | 2014-06-22 | 2014-06-23 | 2014-06-27 | 2014-07-01 | THREE W BUILDERS, INC.
7650 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127627 | San Isidro ES | BALINGASAG | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1 | 2015-06-23 | 2015-06-23 | 100614S00126 | 14KK0095 | 2014-11-28 | 2014-12-10 | 2014-12-11 | 2014-12-15 | 2014-12-19 | RYM CONSTRUCTION
7651 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127827 | San Jose ES | MEDINA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-26 | 2015-11-02 | 100614S00138 | 15kk0049 | 2015-07-31 | 2015-08-12 | 2015-08-13 | 2015-08-17 | 2015-08-21 | L & L CONSTRUCTION
7652 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127862 | Saray ES | SALAY | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2903574.43 |  |  | COMPLETED | 1 | 2014-09-25 | 2014-09-25 | 100614S00010 | 14KK0020-Cluster LG | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7653 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127894 | Sibantang ES | TALISAYAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 100614S00015 | 14KK0023- Cluster LJ | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | ALXM CONSTRUCTION
7654 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127830 | Sidlakan ES | MEDINA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 100614S00005 | 14KK0023- Cluster LJ | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | ALXM CONSTRUCTION
7655 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127737 | Suarez ES | KINOGUITAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-15 | 2015-03-15 | 100614S00039 | 14KK0022 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | EDISON DEVELOPMENT CONSTRUCTION
7656 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127629 | Sulo ES | BALINGASAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-05 | 100614S00033 | 14KK0018-Cluster LE | 2014-06-10 | 2014-06-22 | 2014-06-23 | 2014-06-27 | 2014-07-01 | THREE W BUILDERS, INC.
7657 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127750 | Tabok ES | LAGONGLONG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 100614S00071 | 14KK0019- Cluster LF | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7658 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127898 | Talisayan CS | TALISAYAN | 1 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11277984.375 |  |  | COMPLETED | 1 | 2015-06-23 | 2015-08-02 | 100614S00109 | 14KK0084 | 2014-10-29 | 2014-11-10 | 2014-11-11 | 2014-11-15 | 2014-11-19 | PUREGOLD CONSTRUCTION & DEVT. CORP.
7659 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127630 | Talusan ES | BALINGASAG | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-06-24 | 100614S00116 | 14KK0089 | 2014-11-28 | 2014-12-10 | 2014-12-11 | 2014-12-15 | 2014-12-19 | WDM CONSTRUCTION AND SUPPLIES
7660 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127792 | Tama ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2903574.43 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 100614S00003 | 14KK0026 | 2014-05-19 | 2014-06-07 | 2014-06-14 | 2014-06-18 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7661 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127863 | Tinagaan ES | SALAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-25 | 2014-09-25 | 100614S00007 | 14KK0020-Cluster LG | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7662 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127751 | Umagos ES | LAGONGLONG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 100614S00043 | 14KK0019- Cluster LF | 2014-06-06 | 2014-06-18 | 2014-06-19 | 2014-06-23 | 2014-06-27 | WDM CONSTRUCTION AND SUPPLIES
7663 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127584 | Alubijid CS | ALUBIJID | 2 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 3 | 18799509.7656 |  |  | COMPLETED | 1 | 2015-09-15 | 2015-10-15 | 100614S00119 | 14KL0113 | 2014-12-05 | 2014-12-15 | 2014-12-16 | 2014-12-22 | 2015-01-19 | N.B. SALBO CONSTRUCTION
7664 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 304059 | Alubijid NCHS | ALUBIJID | 2 | 1 | 10 | 2STY6CL & 2STY4CL | 2014 K10 BATCH 3 | 14527117.9688 |  |  | COMPLETED | 1 |  | 2015-07-17 | 100614S00118 | 14KL0100 | 2014-12-05 | 2014-12-11 | 2014-12-13 | 2014-12-17 | 2015-01-19 | FOOTPRINTS CONSTRUCTION
7665 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127635 | Aposkahoy II ES | CLAVERIA | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3799205.49 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-12-02 | 100614S00085 | 14KL0018 | 2014-06-04 | 2014-06-07 | 2014-06-11 | 2014-07-23 | 2014-08-04 | AMMAR CONSTRUCTION AND ENTERPRISES
7666 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127910 | Aromahon ES | LAGUINDINGAN | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3799205.49 |  |  | COMPLETED | 1 | 2014-10-02 | 2014-10-02 | 100614S00053 | 14KL0019 | 2014-07-19 | 2014-07-24 | 2014-07-26 | 2014-07-30 | 2014-08-04 | AMMAR CONSTRUCTION AND ENTERPRISES
7667 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127921 | Aya-Aya ES | LUGAIT | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00055 | 14KL0030 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | JDRC CONSTRUCTION & SUPPLIES
7668 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127834 | Bagocboc ES | OPOL | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2903574.43 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00047 | 14KL0025 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | PAGADIAN AGGREGATES & MARKETING
7669 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127865 | Baluarte ES | TAGOLOAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1983217.57 |  |  | COMPLETED | 1
7670 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127585 | Baybay ES | ALUBIJID | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00044 | 14KL0039 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | PAGADIAN AGGREGATES & MARKETING
7671 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127836 | Bayugbayogan ES | OPOL | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2903574.43 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00048 | 14KL0039 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | PAGADIAN AGGREGATES & MARKETING
7672 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127586 | Benigwayan ES | ALUBIJID | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117929.12 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00069 | 14KL0035 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | KVC CONSTRUCTION
7673 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127922 | Biga ES | LUGAIT | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1983217.57 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00056 | 14KL0030 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | JDRC CONSTRUCTION & SUPPLIES
7674 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127700 | Bobontugan ES | JASAAN | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-05-18 | 2015-04-18 | 100614S00115 | 14KL0103 | 2014-12-05 | 2014-12-11 | 2014-12-15 | 2014-12-18 | 2015-01-19 | L & L CONSTRUCTION
7675 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127637 | Bulahan ES | CLAVERIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117929.12 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00095 | 14KL0024 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7676 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127638 | Cabacungan ES | CLAVERIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117929.12 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00086 | 14KL0021 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | PAGADIAN AGGREGATES & MARKETING
7677 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127587 | Calatcat ES | ALUBIJID | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2903574.43 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00094 | 14KL0035 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | KVC CONSTRUCTION
7678 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127838 | Cauyonan ES | OPOL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117929.12 |  |  | COMPLETED | 1 | 2014-10-25 | 2014-10-25 | 100614S00049 | 14KL0048 | 2014-07-12 | 2014-07-16 | 2014-07-28 | 2014-08-18 | 2014-08-26 | R. DE MESA CONSTRUCTION
7679 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127701 | Corrales ES | JASAAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00103 | 14KL0031 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | A.P. JACOB CONSTRUCTION
7680 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127901 | Don F. Jacinto ES | VILLANUEVA | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8267045.2031 |  |  | COMPLETED | 1 | 2015-06-17 | 2015-05-18 | 100614S00117 | 14KL0102 | 2014-12-01 | 2014-12-06 | 2014-12-09 | 2014-12-16 | 2015-01-19 | L & L CONSTRUCTION
7681 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127928 | Don Pedro ES | NAAWAN | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3773605.49 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00058 | 14KL0022 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | TESAR BUILDERS
7682 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127758 | Gitagum CS | GITAGUM | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00098 | 14KL0036 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | MIKKIL CONSTRUCTION
7683 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127686 | Initao CS | INITAO | 2 | 1 | 16 | 2UNIT 2STY8CL | 2014 K10 BATCH 4A | 22555968.75 |  |  | COMPLETED | 1 | 2015-11-14 | 2015-11-14 | 100614S00130 | 14KL0098 | 2014-12-05 | 2014-12-13 | 2014-12-15 | 2014-12-18 | 2015-01-19 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7684 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127704 | Jampason ES | JASAAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00102 | 14KL0040 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
7685 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 315317 | Kalacapan NHS | INITAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1983217.57 |  |  | COMPLETED | 1 |  | 2014-09-21 | 100614S00074 | 14KL0034 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | SCF DAUGHSONS CONSTRUCTION CORPORATION
7686 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127689 | Kamelon ES | INITAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1983217.57 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00078 | 14KL0041 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | PAGADIAN AGGREGATES & MARKETING
7687 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127645 | Kanangkaan ES | CLAVERIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117929.12 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00083 | 14KL0020 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | MIKKIL CONSTRUCTION
7688 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127690 | Kanitoan ES | INITAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00077 | 14KL0029 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | SCF DAUGHSONS CONSTRUCTION CORPORATION
7689 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 304075 | Kibaghot NHS | LAGUINDINGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00088 | 14KL0036 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | MIKKIL CONSTRUCTION
7690 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127589 | Lanao ES | ALUBIJID | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2903574.43 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 100614S00093 | 14KL0038 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
7691 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127914 | Lapad ES | LAGUINDINGAN | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3799205.49 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00054 | 14KL0037 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | R. DE MESA CONSTRUCTION
7692 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127905 | Looc ES | VILLANUEVA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00051 | 14KL0031 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | A.P. JACOB CONSTRUCTION
7693 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127930 | Lubilan ES | NAAWAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-10-15 | 2014-12-16 | 100614S00075 | 14KL0015 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
7694 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127761 | Lubluban ES | LIBERTAD | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2877974.43 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00099 | 14KL0034 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | SCF DAUGHSONS CONSTRUCTION CORPORATION
7695 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127926 | Lugait CS | LUGAIT | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00057 | 14KL0033 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | A.P. JACOB CONSTRUCTION
7696 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127592 | Lumbo ES | ALUBIJID | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 100614S00092 | 14KL0038 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
7697 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127842 | Luyong Bonbon ES | OPOL | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7656 |  |  | COMPLETED | 1 | 2015-05-18 | 2015-05-18 | 100614S00131 | 14KL0101 | 2014-12-03 | 2014-12-10 | 2014-12-13 | 2014-12-22 | 2015-01-19 | LIGHT CONSTRUCTION & SUPPLY
7698 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127650 | Madaguing ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2008817.57 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-11-22 | 100614S00082 | 14KL0043 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
7699 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127803 | Mahayahay ES | MANTICAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117929.12 |  |  | COMPLETED | 1 | 2014-10-02 | 2014-10-02 | 100614S00100 | 14KL0014 | 2014-07-02 | 2014-07-05 | 2014-07-11 | 2014-07-23 | 2014-08-04 | LANAO BUILDER AND ENTERPRISES
7700 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 304083 | Malagana NHS | CLAVERIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117929.12 |  |  | COMPLETED | 1 |  | 2014-09-16 | 100614S00065 | 14KL0024 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7701 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 315307 | Manticao NHS | MANTICAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 |  | 2014-10-03 | 100614S00066 | 14KL0033 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | A.P. JACOB CONSTRUCTION
7702 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127932 | Mapulog ES | NAAWAN | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3773605.49 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00060 | 14KL0023 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | LYD CONSTRUCTION
7703 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127933 | Maputi ES | NAAWAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00046 | 14KL0015 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
7704 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127655 | Mat-i CS | CLAVERIA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2903574.43 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00081 | 14KL0021 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | PAGADIAN AGGREGATES & MARKETING
7705 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127934 | Mat-I ES | NAAWAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1983217.57 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00062 | 14KL0013 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | R. DE MESA CONSTRUCTION
7706 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127657 | Minsacuba ES | CLAVERIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117929.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-11-22 | 100614S00080 | 14KL0043 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
7707 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 201511 | Molocboloc PS | ALUBIJID | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1983217.57 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00064 | 14KL0028 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | MIKKIL CONSTRUCTION
7708 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127845 | Nangcaon ES | OPOL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2008817.57 |  |  | COMPLETED | 1 | 2014-10-25 | 2014-10-25 | 100614S00050 | 14KL0048 | 2014-07-19 | 2014-07-22 | 2014-07-25 | 2014-08-12 | 2014-08-26 | R. DE MESA CONSTRUCTION
7709 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127709 | Natubo ES | JASAAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117929.12 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00101 | 14KL0040 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
7710 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127691 | Oguis ES | INITAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-10-17 | 2014-10-17 | 100614S00084 | 14KL0016 | 2014-07-15 | 2014-07-17 | 2014-07-18 | 2014-07-21 | 2014-08-04 | LANAO BUILDER AND ENTERPRISES
7711 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127692 | Pagahan ES | INITAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-02 | 2014-10-02 | 100614S00097 | 14KL0016 | 2014-07-18 | 2014-07-19 | 2014-07-19 | 2014-07-21 | 2014-08-04 | LANAO BUILDER AND ENTERPRISES
7712 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127808 | Patag ES | MANTICAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00087 | 14KL0013 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | R. DE MESA CONSTRUCTION
7713 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127937 | Patag ES | NAAWAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00063 | 14KL0041 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | PAGADIAN AGGREGATES & MARKETING
7714 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 315314 | Patrocinio NHS | CLAVERIA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2877974.43 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00067 | 14KL0020 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | MIKKIL CONSTRUCTION
7715 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127809 | Punta Silum ES | MANTICAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 100614S00059 | 14KL0014 | 2014-07-02 | 2014-07-05 | 2014-07-11 | 2014-07-16 | 2014-08-04 | LANAO BUILDER AND ENTERPRISES
7716 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127593 | Sampatulog ES | ALUBIJID | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00091 | 14KL0032 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7717 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127908 | San Martin ES | VILLANUEVA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00052 | 14KL0031 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | A.P. JACOB CONSTRUCTION
7718 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127712 | San Nicolas ES | JASAAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117929.12 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00096 | 14KL0040 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
7719 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127713 | Solana ES | JASAAN | 2 | 1 | 7 | 1STY1CL & 2STY6CL | 2014 K10 BATCH 3 | 9196519.8953 |  |  | COMPLETED | 1 | 2015-07-17 | 2015-08-17 | 100614S00110 | 14KL0099 | 2014-12-05 | 2014-12-13 | 2014-12-15 | 2014-12-18 | 2015-01-19 | GENETIAN BUILDERS
7720 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127595 | Sungay ES | ALUBIJID | 2 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 3 | 4124403.42 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 100614S00122 | 14KL0105 | 2014-12-01 | 2014-12-05 | 2014-12-06 | 2014-12-13 | 2015-01-19 | LIGHT CONSTRUCTION & SUPPLY
7721 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127938 | Tagbalogo ES | NAAWAN | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3799205.49 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00061 | 14KL0017 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | TESAR BUILDERS
7722 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127696 | Tagpaco ES | INITAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-10-17 | 2014-10-17 | 100614S00105 | 14KL0016 | 2014-07-18 | 2014-07-21 | 2014-07-21 | 2014-07-21 | 2014-08-04 | LANAO BUILDER AND ENTERPRISES
7723 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127596 | Talaba ES | ALUBIJID | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00090 | 14KL0032 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7724 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 315315 | Tambobong-Balacanas NHS | VILLANUEVA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1983217.57 |  |  | COMPLETED | 1 |  | 2014-09-21 | 100614S00068 | 14KL0042 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | A.P. JACOB CONSTRUCTION
7725 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127597 | Taparak ES | ALUBIJID | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3786405.49 |  |  | COMPLETED | 1 | 2014-11-08 | 2014-10-29 | 100614S00089 | 14KL0027 | 2014-07-05 | 2014-07-09 | 2014-07-10 | 2014-07-12 | 2014-07-31 | CRIZEL CONSTRUCTION & CONCRETE PRODUCTS
7726 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127666 | Tipolohon ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-09-16 | 2014-09-16 | 100614S00079 | 14KL0024 | 2014-06-27 | 2014-07-09 | 2014-07-10 | 2014-07-14 | 2014-07-18 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE.
7727 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127698 | Tubigan ES | INITAO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00104 | 14KL0029 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | SCF DAUGHSONS CONSTRUCTION CORPORATION
7728 | NC 2014 | K10 (2014) | Region X | Misamis Oriental | 127599 | Tula ES | ALUBIJID | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-21 | 100614S00076 | 14KL0028 | 2014-06-30 | 2014-07-11 | 2014-07-12 | 2014-07-17 | 2014-07-23 | MIKKIL CONSTRUCTION
7729 | NC 2014 | K10 (2014) | Region X | Oroquieta City | 500402 | Dullan IS | OROQUIETA CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-25 | 2014-10-25 | 100514S00004 | 14KI0006 | 2014-06-09 | 2014-06-11 | 2014-06-24 | 2014-07-15 | 2014-07-21 | JDRC CONSTRUCTION & SUPPLIES
7730 | NC 2014 | K10 (2014) | Region X | Oroquieta City | 304045 | Misamis Occidental NHS | OROQUIETA CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 |  | 2014-10-25 | 100514S00003 | 14KI0006 | 2014-06-09 | 2014-06-11 | 2014-06-24 | 2014-07-15 | 2014-07-21 | JDRC CONSTRUCTION & SUPPLIES
7731 | NC 2014 | K10 (2014) | Region X | Ozamis City | 128192 | Cavinte ES | OZAMIS CITY | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3800805.49 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-10-23 | 100514S00016 | 14KJ0010 | 2014-06-30 | 2014-07-14 | 2014-07-29 | 2014-08-04 | 2014-08-18 | A.R. & MARK BUILDERS
7732 | NC 2014 | K10 (2014) | Region X | Ozamis City | 315703 | Cogon IS | OZAMIS CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-10-23 | 100514S00011 | 14KJ0013 | 2014-06-30 | 2014-07-14 | 2014-07-29 | 2014-08-06 | 2014-08-18 | A.R. & MARK BUILDERS
7733 | NC 2014 | K10 (2014) | Region X | Ozamis City | 315701 | Kinuman Norte National High School | OZAMIS CITY | 2 |  | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3790805.49 |  |  | COMPLETED | 1 |  | 2014-10-23 | 100514S00017 | 14KJ0011 | 2014-06-30 | 2014-07-14 | 2014-07-29 | 2014-08-11 | 2014-08-18 | A.R. & MARK BUILDERS
7734 | NC 2014 | K10 (2014) | Region X | Ozamis City | 315704 | Misamis Annex IS | OZAMIS CITY | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4542899.6094 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 100514S00021 | 14KJ0059 | 2014-11-20 | 2014-12-04 | 2014-12-04 | 2014-12-15 | 2014-12-19 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7735 | NC 2014 | K10 (2014) | Region X | Ozamis City | 304169 | Pulot NHS | OZAMIS CITY | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 |  | 2016-01-01 | 100514S00024 | 15KJ0076 | 2015-07-16 | 2015-07-29 | 2015-07-31 | 2015-08-14 | 2015-08-25 | HSO CONSTRUCTION CORPORATION (FOREMERLY : HENRY S.
7736 | NC 2014 | K10 (2014) | Region X | Ozamis City | 128188 | Trigos ES | OZAMIS CITY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-10-23 | 100514S00013 | 14KJ0012 | 2014-06-30 | 2014-07-14 | 2014-07-29 | 2014-08-06 | 2014-08-18 | A.R. & MARK BUILDERS
7737 | NC 2014 | K10 (2014) | Region X | Tangub City | 128224 | Hoyohoy ES | TANGUB CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 100514S00009 | 14KJ0016 | 2014-06-30 | 2014-07-14 | 2014-07-29 | 2014-08-06 | 2014-08-13 | C. DY BUILDERS AND GENERAL MERCHANDISE (FORMERLY CD
7738 | NC 2014 | K10 (2014) | Region X | Tangub City | 128246 | Lorenzo Tan Memorial CS | TANGUB CITY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-09-30 | 100514S00007 | 14KJ0014 | 2014-06-30 | 2014-07-14 | 2014-07-29 | 2014-08-06 | 2014-08-11 | PUREGOLD CONSTRUCTION & DEVT. CORP.
7739 | NC 2014 | K10 (2014) | Region X | Tangub City | 128231 | Salimpuno ES | TANGUB CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-09-30 | 100514S00006 | 14KJ0017 | 2014-06-30 | 2014-07-14 | 2014-07-21 | 2014-08-08 | 2014-08-11 | C. DY BUILDERS AND GENERAL MERCHANDISE (FORMERLY CD
7740 | NC 2014 | K10 (2014) | Region X | Tangub City | 304171 | Tangub City NHS | TANGUB CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 |  | 2014-10-18 | 100514S00008 | 14KJ0015 | 2014-06-30 | 2014-07-14 | 2014-07-29 | 2014-08-06 | 2014-08-13 | PUREGOLD CONSTRUCTION & DEVT. CORP.
7741 | NC 2014 | K10 (2014) | Region X | Valencia City | 126864 | Araneta ES | CITY OF VALENCIA | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 100314S00142 | 14KA0030 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | KEZ ENTERPRISES
7742 | NC 2014 | K10 (2014) | Region X | Valencia City | 126831 | Bagontaas CES | CITY OF VALENCIA | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 100314S00082 | 14KA0028 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | RRN CONSTRUCTION
7743 | NC 2014 | K10 (2014) | Region X | Valencia City | 323807 | Banlag IS | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 |  | 2014-11-09 | 100314S00133 | 14KA0032 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ZI 9 BUILDERS AND SUPPLIES
7744 | NC 2014 | K10 (2014) | Region X | Valencia City | 199513 | Bantal ES | CITY OF VALENCIA | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 100314S00151 | 14KA0032 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ZI 9 BUILDERS AND SUPPLIES
7745 | NC 2014 | K10 (2014) | Region X | Valencia City | 126868 | Buyog ES | CITY OF VALENCIA | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 100314S00141 | 14KA0032 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ZI 9 BUILDERS AND SUPPLIES
7746 | NC 2014 | K10 (2014) | Region X | Valencia City | 126869 | Cabayugan ES | CITY OF VALENCIA | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 100314S00128 | 14KA0028 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | RRN CONSTRUCTION
7747 | NC 2014 | K10 (2014) | Region X | Valencia City | 126839 | Dabongdabong ES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 100314S00149 | 14KA0028 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | RRN CONSTRUCTION
7748 | NC 2014 | K10 (2014) | Region X | Valencia City | 323808 | Dagatkidavao IS | CITY MALAYBALAY (Capital) | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 |  | 2014-11-09 | 100314S00132 | 14KA0030 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | KEZ ENTERPRISES
7749 | NC 2014 | K10 (2014) | Region X | Valencia City | 250501 | Logdeck PS | CITY OF VALENCIA | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 100314S00137 | 14KA0032 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | ZI 9 BUILDERS AND SUPPLIES
7750 | NC 2014 | K10 (2014) | Region X | Valencia City | 323805 | Lourdes IS | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 |  | 2014-12-09 | 100314S00134 | 14KA0031 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | WDM CONSTRUCTION AND SUPPLIES
7751 | NC 2014 | K10 (2014) | Region X | Valencia City | 126846 | Lumbo ES | CITY OF VALENCIA | 4 | 1 | 7 | 1STY3CL & 2 UNIT 1STY2CL | 2014 K10 BATCH 1 | 6881009.57 |  |  | COMPLETED | 1 | 2014-12-09 | 2014-12-05 | 100314S00148 | 14KA0031 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | WDM CONSTRUCTION AND SUPPLIES
7752 | NC 2014 | K10 (2014) | Region X | Valencia City | 126847 | Lurugan Elementary School | CITY OF VALENCIA | 4 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3775805.49 |  |  | COMPLETED | 1 |  | 2014-12-24 | 100314S00147 | 14KA0029 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | A.R. & MARK BUILDERS
7753 | NC 2014 | K10 (2014) | Region X | Valencia City | 303970 | Lurugan NHS | CITY OF VALENCIA | 4 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3780805.49 |  |  | COMPLETED | 1 |  | 2014-12-24 | 100314S00136 | 14KA0029 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | A.R. & MARK BUILDERS
7754 | NC 2014 | K10 (2014) | Region X | Valencia City | 126853 | New Visayas ES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-12-24 | 2015-07-08 | 100314S00146 | 14KA0029 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | A.R. & MARK BUILDERS
7755 | NC 2014 | K10 (2014) | Region X | Valencia City | 126878 | Sinabuagan ES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 100314S00139 | 14KA0030 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | KEZ ENTERPRISES
7756 | NC 2014 | K10 (2014) | Region X | Valencia City | 126857 | Sinalayan ES | CITY OF VALENCIA | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1141329.12 |  |  | COMPLETED | 1 | 2014-12-09 | 2014-12-05 | 100314S00145 | 14KA0031 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | WDM CONSTRUCTION AND SUPPLIES
7757 | NC 2014 | K10 (2014) | Region X | Valencia City | 126859 | Tagalawa ES | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2014-12-24 |  | 100314S00144 | 14KA0029 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | A.R. & MARK BUILDERS
7758 | NC 2014 | K10 (2014) | Region X | Valencia City | 126862 | Ulaligan ES | CITY OF VALENCIA | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2015-07-08 | 100314S00143 | 14KA0029 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | A.R. & MARK BUILDERS
7759 | NC 2014 | K10 (2014) | Region X | Valencia City | 126863 | Valencia CES | CITY OF VALENCIA | 4 | 1 | 15 | 3STY15CL | 2014 K10 BATCH 4A | 22475411.7188 |  |  | COMPLETED | 1 | 2015-10-03 | 2015-12-13 | 100314S00196 | 14KA0077 | 2014-11-30 | 2014-12-04 | 2014-12-23 | 2014-12-29 | 2015-01-12 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
7760 | NC 2014 | K10 (2014) | Region X | Valencia City | 303988 | Valencia NHS | CITY OF VALENCIA | 4 | 1 | 12 | 1STY2CL & 2STY4CL & 2STY6CL | 2014 K10 BATCH 3 | 16256626.4284 |  |  | COMPLETED | 1 |  | 2015-05-14 | 100314S00188 | 14KA0070 | 2014-11-13 | 2014-11-14 | 2014-11-27 | 2014-12-08 | 2014-12-16 | J.T. GAMOLO CONSTRUCTION
7761 | NC 2014 | K10 (2014) | Region X | Valencia City | 323803 | Valencia NHS - Concepcion Annex | CITY OF VALENCIA | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 |  | 2014-11-09 | 100314S00135 | 14KA0028 | 2014-06-08 | 2014-06-10 | 2014-06-24 | 2014-07-16 | 2014-07-28 | RRN CONSTRUCTION
13907 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126619 | Alae CES | MANOLO FORTICH | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00210 | 15KC0066 | 2015-08-24 | 2015-08-31 | 2015-09-03 | 2015-09-28 | 2015-09-30 | FFJJ CONSTRUCTION
13908 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303944 | Alae NHS | MANOLO FORTICH | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00046 | 15KC0048 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-08-03 | 2015-08-17 | FFJJ CONSTRUCTION
13909 | NC 2015 | TECHVOC (2015) | Region X | Bukidnon | 303944 | Alae NHS | MANOLO FORTICH | 1 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  | 100315S00216 | 15KC0082 | 2015-09-28 | 2015-10-05 | 2015-10-08 | 2015-10-20 | 2015-11-10 | L & L CONSTRUCTION
13910 | NC 2015 | K10 (2015) | Region X | Bukidnon | 199539 | Bagong Silang Primary School | MALITBOG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00203 | 15KC0072 | 2015-08-24 | 2015-08-31 | 2015-09-03 | 2015-09-28 | 2015-09-30 | FFJJ CONSTRUCTION
13911 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303947 | Baungon NHS | BAUNGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 100315S00021 | 15KC0035 | 2015-05-18 | 2015-05-24 | 2015-06-04 | 2015-06-15 | 2015-07-15 | DICON BUILDERS CORP.
13912 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314925 | Baungon NHS - Danatag Annex | BAUNGON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00047 | 15KC0041 | 2015-08-03 | 2015-08-04 | 2015-08-04 | 2015-08-07 | 2015-08-17 | LLM ENTERPRISES
13913 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314925 | Baungon NHS - Danatag Annex | BAUNGON | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00048 | 15KC0041 | 2015-08-03 | 2015-08-04 | 2015-08-04 | 2015-08-06 | 2015-08-17 | LLM ENTERPRISES
13914 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126801 | DAGUMBAAN ELEMENTARY SCHOOL | TALAKAG | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00205 | 15KC0068 | 2015-08-24 | 2015-08-31 | 2015-09-03 | 2015-09-28 | 2015-09-30 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
13915 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314901 | Dalirig NHS | MANOLO FORTICH | 1 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3494886.575 |  |  | COMPLETED | 1 |  |  | 100315S00022 | 15KC0032 | 2015-05-18 | 2015-05-24 | 2015-06-04 | 2015-06-15 | 2015-07-15 | TWINA BUILDERS AND SUPPLY
13916 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314901 | Dalirig NHS | MANOLO FORTICH | 1 |  | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1844740.174 |  |  | COMPLETED | 1 |  |  | 100315S00023 | 15KC0032 | 2015-05-18 | 2015-05-24 | 2015-06-04 | 2015-06-15 | 2015-07-15 | TWINA BUILDERS AND SUPPLY
13917 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303969 | Kinawe NHS | LIBONA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00049 | 15KC0049 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-08-03 | 2015-08-17 | E AND R ENTERPRISES AND CONSTRUCTION
13918 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126784 | Laruk ES | SUMILAO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00209 | 15KC0067 | 2015-08-24 | 2015-08-31 | 2015-09-03 | 2015-09-28 | 2015-09-30 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
13919 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303968 | Libona NHS | LIBONA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 100315S00024 | 15KC0037 | 2015-05-18 | 2015-05-24 | 2015-06-04 | 2015-06-15 | 2015-07-15 | LLM CONCRETE PRODUCTS
13920 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126633 | Lingion ES | MANOLO FORTICH | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 100315S00118 | 15KC0058 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-07-31 | 2015-08-17 | LLM CONCRETE PRODUCTS
13921 | NC 2015 | K10 (2015) | Region X | Bukidnon | 199532 | Logdeck PS | MALITBOG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00167 | 15KC0072 | 2015-08-24 | 2015-08-31 | 2015-09-03 | 2015-09-28 | 2015-09-30 | FFJJ CONSTRUCTION
13922 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303972 | Malitbog Nat. Agr'I. HS | MALITBOG | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2720828.124 |  |  | COMPLETED | 1 |  |  | 100315S00044 | 15KC0061 | 2015-07-07 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-17 | TKS BUILDERS & SUPPLIES
13923 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303972 | Malitbog Nat. Agr'I. HS | MALITBOG | 1 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2670828.124 |  |  | COMPLETED | 1 |  |  | 100315S00043 | 15KC0061 | 2015-07-07 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-17 | TKS BUILDERS & SUPPLIES
13924 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303974 | Manolo Fortich NHS | MANOLO FORTICH | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100315S00050 | 15KC0055 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-08-03 | 2015-08-17 | FFJJ CONSTRUCTION
13925 | NC 2015 | TECHVOC (2015) | Region X | Bukidnon | 303974 | Manolo Fortich NHS | MANOLO FORTICH | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1 |  |  | 100315S00217 | 15KC0082 | 2015-09-28 | 2015-10-05 | 2015-10-08 | 2015-10-20 | 2015-11-10 | L & L CONSTRUCTION
13926 | NC 2015 | K10 (2015) | Region X | Bukidnon | 199538 | Mantaboo Sil-ipon PS | LIBONA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00116 | 15KC0056 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-07-31 | 2015-08-17 | FFJJ CONSTRUCTION
13927 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126816 | Miarayon ES | TALAKAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00177 | 15KC0073 | 2015-08-24 | 2015-08-31 | 2015-09-03 | 2015-09-28 | 2015-09-30 | LLM CONCRETE PRODUCTS
13928 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126527 | Palabucan ES | LIBONA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00212 | 15KC0071 | 2015-08-24 | 2015-08-31 | 2015-09-03 | 2015-09-28 | 2015-09-30 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
13929 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126276 | Patpat ES | BAUNGON | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 6 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 100315S00207 | 15KC0070 | 2015-08-24 | 2015-09-02 | 2015-10-29 | 2015-11-05 | 2015-12-01 | LLM CONCRETE PRODUCTS
13930 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126788 | Puntian ES | SUMILAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00208 | 15KC0071 | 2015-08-24 | 2015-08-31 | 2015-09-03 | 2015-09-28 | 2015-09-30 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
13931 | NC 2015 | K10 (2015) | Region X | Bukidnon | 199534 | Sabangan PS | MANOLO FORTICH | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00115 | 15KC0056 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-07-31 | 2015-08-17 | FFJJ CONSTRUCTION
13932 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126821 | San Isidro ES | TALAKAG | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00166 | 15KC0069 | 2015-08-24 | 2015-08-26 | 2015-09-03 | 2015-09-28 | 2015-09-30 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
13933 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303981 | San Luis NHS | MALITBOG | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2897592.44 |  |  | COMPLETED | 1 |  |  | 100315S00052 | 15KC0042 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-07-31 | 2015-08-17 | FFJJ CONSTRUCTION
13934 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303981 | San Luis NHS | MALITBOG | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 100315S00051 | 15KC0042 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-07-31 | 2015-08-17 | FFJJ CONSTRUCTION
13935 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126791 | San Vicente ES | SUMILAO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00121 | 15KC0057 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-07-31 | 2015-08-17 | FFJJ CONSTRUCTION
13936 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126824 | Sanggaya ES | TALAKAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00179 | 15KC0073 | 2015-08-24 | 2015-08-31 | 2015-09-03 | 2015-09-28 | 2015-09-30 | LLM CONCRETE PRODUCTS
13937 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303983 | Sankanan NHS | MANOLO FORTICH | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2862592.44 |  |  | COMPLETED | 1 |  |  | 100315S00054 | 15KC0043 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-08-03 | 2015-08-17 | FFJJ CONSTRUCTION
13938 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303983 | Sankanan NHS | MANOLO FORTICH | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 100315S00053 | 15KC0043 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-07-31 | 2015-08-17 | FFJJ CONSTRUCTION
13939 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303986 | Sumilao NHS | SUMILAO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00056 | 15KC0044 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-08-01 | 2015-08-17 | FFJJ CONSTRUCTION
13940 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303986 | Sumilao NHS | SUMILAO | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00099 | 15KC0044 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-08-03 | 2015-08-17 | FFJJ CONSTRUCTION
13941 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314903 | Sumilao NHS - Kisolon Annex | SUMILAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100315S00045 | 15KC0054 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-08-03 | 2015-08-17 | PETRINA CONSTRUCTION & GENERAL MERCHANDISING
13942 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314924 | Sumilao NHS - Vista Villa Annex | SUMILAO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00025 | 15KC0038 | 2015-05-18 | 2015-05-24 | 2015-06-04 | 2015-06-15 | 2015-07-15 | FOOTPRINTS CONSTRUCTION
13943 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303987 | Talakag NHS | TALAKAG | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00086 | 15KC0050 | 2015-08-03 | 2015-08-04 | 2015-08-04 | 2015-08-07 | 2015-08-17 | C ZARLES CONSTRUCTION & SUPPLY
13944 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314919 | Tikalaan NHS | TALAKAG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 100315S00087 | 15KC0053 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-08-03 | 2015-08-17 | FFJJ CONSTRUCTION
13945 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126281 | Anlugan ES | CABANGLASAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00168 | 15KA0074 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-11-19 | 2015-11-24 | FIVE MASSIVE INFRA & SUPPLY CORP.
13946 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126498 | Baclayon ES | LANTAPAN | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 100315S00120 | 15KA0046 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-11-20 | J.T. GAMOLO CONSTRUCTION
13947 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126747 | Bonacao ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00171 | 15KA0077 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-05 | 2015-10-20 | XY BUILDERS
13948 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303949 | Bugcaon NHS | LANTAPAN | 2 | 1 | 8 | 2STY4CL | 2015 SHS BATCH 1 | 6819337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00026 | 15KA0057 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | PETRINA CONSTRUCTION & GENERAL MERCHANDISING
13949 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303949 | Bugcaon NHS | LANTAPAN | 2 |  | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6329337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00027 | 15KA0058 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | KEZ ENTERPRISES
13950 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303952 | Cabulohan-Paradise NHS | CABANGLASAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 100315S00088 | 15KA0055 | 2015-10-29 | 2015-10-30 | 2015-11-12 | 2015-11-27 | 2015-12-10 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
13951 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314908 | Cabulohan-Paradise NHS - Townsite Annex | CABANGLASAN | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2760828.124 |  |  | COMPLETED | 1 |  |  | 100315S00028 | 15KA0014 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-24 | 2015-07-27 | J.T. GAMOLO CONSTRUCTION
13952 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314908 | Cabulohan-Paradise NHS - Townsite Annex | CABANGLASAN | 2 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2760828.124 |  |  | COMPLETED | 1 |  |  | 100315S00013 | 15KA0014 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-24 | 2015-07-27 | J.T. GAMOLO CONSTRUCTION
13953 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126777 | Cawayan ES | IMPASUG-ONG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00122 | 15KA0044 | 2015-08-31 | 2015-09-03 | 2015-09-15 | 2015-09-30 | 2015-10-04 | MAMAWAG CONSTRUCTION
13954 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126777 | Cawayan ES | IMPASUG-ONG | 2 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00123 | 15KA0044 | 2015-08-31 | 2015-09-03 | 2015-09-15 | 2015-09-30 | 2015-10-04 | MAMAWAG CONSTRUCTION
13955 | NC 2015 | K10 (2015) | Region X | Bukidnon | 199526 | Dao ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00175 | 15KA0081 | 2015-12-03 | 2015-12-04 | 2015-12-17
13956 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126375 | Hagpa ES | IMPASUG-ONG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00124 | 15KA0045 | 2015-08-31 | 2015-09-03 | 2015-09-15 | 2015-09-30 | 2015-10-04 | MAMAWAG CONSTRUCTION
13957 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126375 | Hagpa ES | IMPASUG-ONG | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 100315S00125 | 15KA0045 | 2015-08-31 | 2015-09-03 | 2015-09-15 | 2015-09-30 | 2015-10-04 | MAMAWAG CONSTRUCTION
13958 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126753 | Halapitan CES | SAN FERNANDO | 2 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 100315S00142 | 15KA0050 | 2015-08-31 | 2015-09-03 | 2015-09-15 | 2015-09-30 | 2015-10-04 | L & L CONSTRUCTION
13959 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303955 | Halapitan NHS | SAN FERNANDO | 2 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 2 | 13071310.093 |  |  | COMPLETED | 1 |  |  | 100315S00089 | 15KA0056 | 2015-08-30 | 2015-09-03 | 2015-09-15 | 2015-09-30 | 2015-10-05 | L & L CONSTRUCTION
13960 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303955 | Halapitan NHS | SAN FERNANDO | 2 |  | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00090 | 15KA0022 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | MAMAWAG CONSTRUCTION
13961 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314907 | Halapitan NHS - Little Baguio Annex | SAN FERNANDO | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3534886.575 |  |  | COMPLETED | 1 |  |  | 100315S00041 | 15KA0015 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-24 | 2015-07-27 | MAMAWAG CONSTRUCTION
13962 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314907 | Halapitan NHS - Little Baguio Annex | SAN FERNANDO | 2 |  | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1844740.174 |  |  | COMPLETED | 1 |  |  | 100315S00040 | 15KA0015 | 2015-06-10 | 2015-06-18 | 2015-06-30 | 2015-07-24 | 2015-07-27 | MAMAWAG CONSTRUCTION
13963 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303956 | Impasug-Ong NHS | IMPASUG-ONG | 2 | 1 | 8 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00091 | 15KA0023 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | Z & L CONSTRUCTION & SUPPLIES
13964 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303956 | Impasug-Ong NHS | IMPASUG-ONG | 2 |  | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00092 | 15kA0024 | 2015-08-31 | 2015-09-03 | 2015-09-15 | 2015-09-30 | 2015-10-04 | MAMAWAG CONSTRUCTION
13965 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314923 | Impasugong NHS-Kapitan Bayong Annex | IMPASUG-ONG | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2715828.124 |  |  | COMPLETED | 1 |  |  | 100315S00032 | 15KA0016 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-24 | 2015-07-27 | MAFIL ENTERPRISES
13966 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314923 | Impasugong NHS-Kapitan Bayong Annex | IMPASUG-ONG | 2 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2715828.124 |  |  | COMPLETED | 1 |  |  | 100315S00030 | 15KA0016 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-24 | 2015-07-27 | MAFIL ENTERPRISES
13967 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303957 | Kalabugao NHS | IMPASUG-ONG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 100315S00093 | 15KA0025 | 2015-08-31 | 2015-09-03 | 2015-09-15 | 2015-09-25 | 2015-10-04 | MAMAWAG CONSTRUCTION
13968 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303957 | Kalabugao NHS | IMPASUG-ONG | 2 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2892592.44 |  |  | COMPLETED | 1 |  |  | 100315S00094 | 15KA0025 | 2015-08-31 | 2015-09-03 | 2015-09-15 | 2015-09-25 | 2015-10-04 | MAMAWAG CONSTRUCTION
13969 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126506 | Kibanggay ES | LANTAPAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00134 | 15KA0047 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | PUREGOLD CONSTRUCTION & DEVT. CORP.
13970 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126506 | Kibanggay ES | LANTAPAN | 2 |  | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00114 | 15KA0048 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | PUREGOLD CONSTRUCTION & DEVT. CORP.
13971 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126759 | Kibongkog ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00172 | 15KA0078 | 2015-11-30 | 2015-12-04 | 2015-12-29
13972 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126293 | Lambagan ES | CABANGLASAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00119 | 15KA0043 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | J.T. GAMOLO CONSTRUCTION
13973 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303967 | Lantapan NHS | LANTAPAN | 2 | 1 | 8 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00095 | 15KA0026 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | ZI 9 BUILDERS AND SUPPLIES
13974 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303967 | Lantapan NHS | LANTAPAN | 2 |  | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00096 | 15KA0027 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | PUREGOLD CONSTRUCTION & DEVT. CORP.
13975 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126763 | Magkalungay ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00173 | 15KA0079 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-13 | XY BUILDERS
13976 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126295 | Mainaga ES | CABANGLASAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00169 | 15KA0075 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-11-19 | 2015-11-24 | FIVE MASSIVE INFRA & SUPPLY CORP.
13977 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126765 | Malambago ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00174 | 15KA0080 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | XY BUILDERS
13978 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126299 | Miaray ES | CABANGLASAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00170 | 15KA0076 | 2015-12-03 | 2015-12-04 | 2015-12-29
13979 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126770 | Namnam ES | SAN FERNANDO | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100315S00141 | 15KA0051 | 2015-08-31 | 2015-09-03 | 2015-09-15 | 2015-09-30 | 2015-10-04 | L & L CONSTRUCTION
13980 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126509 | Old Kibanggay ES | LANTAPAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00143 | 15KA0049 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | PUREGOLD CONSTRUCTION & DEVT. CORP.
13981 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126461 | Balocbocan ES | KITAOTAO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00191 | 15KB0060 | 2015-09-10 | 2015-08-28 | 2015-09-10 | 2015-09-28 | 2015-10-26 | FFJJ CONSTRUCTION
13982 | NC 2015 | K10 (2015) | Region X | Bukidnon | 199537 | Basag PS | DAMULOG | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00182 | 15KB0062
13983 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303948 | Bocboc NHS | DON CARLOS | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100315S00112 | 15KB0016 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | J.T. GAMOLO CONSTRUCTION
13984 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314927 | Bocboc NHS (Kiara Annex) | DON CARLOS | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00098 | 15KB0017 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | RRN CONSTRUCTION
13985 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126326 | Bugwak ES | DANGCAGAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00140 | 15KB0013 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | FFJJ CONSTRUCTION
13986 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126326 | Bugwak ES | DANGCAGAN | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 100315S00139 | 15KB0013 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | FFJJ CONSTRUCTION
13987 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303951 | Bukidnon NSHI | MARAMAG | 3 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 100315S00031 | 15KB0049 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | J.T. GAMOLO CONSTRUCTION
13988 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314911 | Bukidnon NSHI - San Miguel Annex | MARAMAG | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00084 | 15KB0028 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | RRN CONSTRUCTION
13989 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303953 | Dangcagan NHS | DANGCAGAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 100315S00039 | 15KB0042 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | DAVAO CONCRETE PRODUCTS
13990 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314910 | Dangcagan NHS - Miaray Annex | DANGCAGAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 100315S00033 | 15KB0043 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | DAVAO CONCRETE PRODUCTS
13991 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303954 | Dologon NHS | MARAMAG | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 100315S00100 | 15KB0029 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | DAVAO CONCRETE PRODUCTS
13992 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314921 | Dologon NHS - Kiharong Annex | MARAMAG | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00101 | 15KB0030 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | J.T. GAMOLO CONSTRUCTION
13993 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314928 | Dologon NHS (San Roque Annex) | MARAMAG | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2018606 |  |  | COMPLETED | 1 |  |  | 100315S00158 | 15KB0055 | 2015-09-10 | 2015-08-28 | 2015-09-10 | 2015-10-26 | 2015-10-30 | LTB BUILDERS & CONSTRUCTION
13994 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314913 | Don Carlos NHS | DON CARLOS | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00102 | 15KB0018 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | FFJJ CONSTRUCTION
13995 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314913 | Don Carlos NHS | DON CARLOS | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00103 | 15KB0018 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | FFJJ CONSTRUCTION
13996 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126329 | Kapalaran ES | DANGCAGAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00138 | 15KB0014 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | FFJJ CONSTRUCTION
13997 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126329 | Kapalaran ES | DANGCAGAN | 3 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00137 | 15KB0014 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | FFJJ CONSTRUCTION
13998 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303959 | Kibatang NHS | DON CARLOS | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 100315S00159 | 15KB0054 | 2015-09-10 | 2015-08-28 | 2015-09-10 | 2015-10-26 | 2015-10-30 | TWINA BUILDERS AND SUPPLY
13999 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303960 | Kibawe NHS | KIBAWE | 3 | 1 | 8 | 2STY4CL | 2015 SHS BATCH 1 | 6449337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00019 | 15KB0046 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | RRN CONSTRUCTION
14000 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303960 | Kibawe NHS | KIBAWE | 3 |  | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6449337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00020 | 15KB0047 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | RRN CONSTRUCTION
14001 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303961 | Kiburiao National High School | QUEZON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8444965.051 |  |  | COMPLETED | 1 |  |  | 100315S00104 | 15KB0035 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | DAVAO CONCRETE PRODUCTS
14002 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126660 | Kiharong ES | MARAMAG | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00178 | 15KB0056 | 2015-09-10 | 2015-08-28 | 2015-09-10 | 2015-09-28 | 2015-10-23 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
14003 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126729 | Kipolot ES | QUEZON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00180 | 15KB0059 | 2015-09-10 | 2015-08-28 | 2015-09-10 | 2015-09-28 | 2015-10-23 | TWINA BUILDERS AND SUPPLY
14004 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314931 | Kitaotao National High School - Digongan Annex | KITAOTAO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 3052592.44 |  |  | COMPLETED | 1 |  |  | 100315S00105 | 15KB0023 | 2015-08-20 | 2015-08-07 | 2015-08-20 | 2015-09-07 | 2015-09-17 | XY BUILDERS
14005 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303963 | Kitaotao NHS | KITAOTAO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8259965.051 |  |  | COMPLETED | 1 |  |  | 100315S00106 | 15KB0024 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | FFJJ CONSTRUCTION
14006 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303964 | Kitubo NHS | KITAOTAO | 3 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2890828.124 |  |  | COMPLETED | 1 |  |  | 100315S00015 | 15KB0048 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | FFJJ CONSTRUCTION
14007 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303964 | Kitubo NHS | KITAOTAO | 3 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2740828.124 |  |  | COMPLETED | 1 |  |  | 100315S00014 | 15KB0048 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | FFJJ CONSTRUCTION
14008 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303965 | Kuya NHS | MARAMAG | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00107 | 15KB0031 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | RRN CONSTRUCTION
14009 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314918 | Kuya NHS - La Roxas Annex | MARAMAG | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 15KB0032 | 42192 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 |  | 42368
14010 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314918 | Kuya NHS - La Roxas Annex | MARAMAG | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 15KB0032 | 42192 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 |  | 42368
14011 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126730 | Lagislis ES | QUEZON | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00127 | 15KB0038 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | FFJJ CONSTRUCTION
14012 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126731 | Linabo ES | QUEZON | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00136 | 15KB0039 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | DAVAO CONCRETE PRODUCTS
14013 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126732 | Lipa ES | QUEZON | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00149 | 15KB0040 | 2015-08-20 | 2015-08-07 | 2015-08-20 | 2015-09-07 | 2015-09-28 | FFJJ CONSTRUCTION
14014 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314929 | Macapari NHS | DAMULOG | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00016 | 15KB0041 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | GOLDEN VIDO BUILDERS & SUPPLY
14015 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126664 | Magsaysay ES | MARAMAG | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100315S00129 | 15KB0034 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | J.T. GAMOLO CONSTRUCTION
14016 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126446 | Mascarinas ES | KIBAWE | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00164 | 15KB0061
14017 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126333 | Miaray Elementary School | DANGCAGAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00126 | 15KB0015 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | DAVAO CONCRETE PRODUCTS
14018 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126667 | Musuan ES | MARAMAG | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00130 | 15KB0033 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | DAVAO CONCRETE PRODUCTS
14019 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126447 | Natulongan ES | KIBAWE | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00135 | 15KB0022 | 2015-08-20 | 2015-08-07 | 2015-08-20 | 2015-09-07 | 2015-09-28 | FFJJ CONSTRUCTION
14020 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303975 | New Nongnongan NHS | DON CARLOS | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8344965.051 |  |  | COMPLETED | 1 |  |  | 100315S00018 | 15KB0044 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | J.T. GAMOLO CONSTRUCTION
14021 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314922 | New Nongnongan NHS - San Nicolas Annex | DON CARLOS | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8259965.051 |  |  | COMPLETED | 1 |  |  | 100315S00110 | 15KB0019 | 2015-08-20 | 2015-08-07 | 2015-08-20 | 2015-09-07 | 2015-09-28 | FFJJ CONSTRUCTION
14022 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126335 | New Visayas ES | DANGCAGAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00176 | 15KB0057 | 2015-09-10 | 2015-08-28 | 2015-09-10 | 2015-09-28 | 2015-10-23 | TWINA BUILDERS AND SUPPLY
14023 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303976 | Old Damulog NHS | DAMULOG | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8259965.051 |  |  | COMPLETED | 1 |  |  | 100315S00111 | 15KB0012 | 2015-08-20 | 2015-08-07 | 2015-08-20 | 2015-09-07 | 2015-09-28 | FFJJ CONSTRUCTION
14024 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303977 | Old Nongnongan NHS | DON CARLOS | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00070 | 15KB0020 | 2015-08-20 | 2015-08-07 | 2015-08-20 | 2015-09-07 | 2015-09-28 | FFJJ CONSTRUCTION
14025 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126718 | Paitan ES | QUEZON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00165 | 15KB0058 | 2015-09-20 | 2015-09-25 | 2015-10-08 | 2015-10-13 | 2015-11-02 | DAVAO CONCRETE PRODUCTS
14026 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314912 | Quezon NHS | QUEZON | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10997342.5917 |  |  | COMPLETED | 1 |  |  | 100315S00068 | 15KB0036 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | DAVAO CONCRETE PRODUCTS
14027 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314930 | Quezon NHS - Apyao Annex | QUEZON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 100315S00042 | 15KB0050 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | DAVAO CONCRETE PRODUCTS
14028 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126485 | Sagundanon ES | KITAOTAO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00183 | 15KB0063
14029 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303979 | Salawagan NHS | QUEZON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 100315S00097 | 15KB0037 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | FFJJ CONSTRUCTION
14030 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303980 | San Andres NHS | KADINGILAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 100315S00017 | 15KB0045 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
14031 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314926 | San Andres NHS - Cabadiangan Annex | KADINGILAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00057 | 15KB0021 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | RRN CONSTRUCTION
14032 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303985 | Sinuda NHS | KITAOTAO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 100315S00058 | 15KB0025 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | ALGON ENGINEERING CONSTRUCTION CORPORATION
14033 | NC 2015 | K10 (2015) | Region X | Bukidnon | 199535 | Sita ES | KITAOTAO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00131 | 15KB0027 | 2015-11-12 | 2015-11-16 | 2015-11-27 | 2015-12-14 | 2015-12-22 | R. SEMILLA CONSTRUCTION & MARKETING
14034 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126456 | Talahiron Elementary School | KIBAWE | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00144 | 15KB0022 | 2015-08-20 | 2015-08-07 | 2015-08-20 | 2015-09-07 | 2015-09-28 | FFJJ CONSTRUCTION
14035 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126494 | Tawas ES | KITAOTAO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00133 | 15KB0026 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | ALGON ENGINEERING CONSTRUCTION CORPORATION
14036 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126494 | Tawas ES | KITAOTAO | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 100315S00132 | 15KB0026 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | ALGON ENGINEERING CONSTRUCTION CORPORATION
14037 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126723 | Zubiri Village ES | QUEZON | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00148 | 15KB0038 | 2015-07-07 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-24 | FFJJ CONSTRUCTION
14038 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303945 | Bacusanon National High School | PANGANTUCAN | 4 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2685828.124 |  |  | COMPLETED | 1 |  |  | 100315S00036 | 15KC0034 | 2015-05-18 | 2015-05-24 | 2015-06-04 | 2015-06-15 | 2015-07-15 | MIKZKAR BUILDERS
14039 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303945 | Bacusanon National High School | PANGANTUCAN | 4 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2685828.124 |  |  | COMPLETED | 1 |  |  | 100315S00037 | 15KC0034 | 2015-05-18 | 2015-05-24 | 2015-06-04 | 2015-06-15 | 2015-07-15 | MIKZKAR BUILDERS
14040 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303958 | Kalilangan NHS | KALILANGAN | 4 | 1 | 10 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 100315S00035 | 15KC0036 | 2015-05-18 | 2015-05-24 | 2015-06-04 | 2015-06-15 | 2015-07-15 | KEZ ENTERPRISES
14041 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126424 | Kimagting ES | KALILANGAN | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00145 | 15KC0059 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-07-31 | 2015-08-17 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
14042 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303962 | Kimanait NHS | PANGANTUCAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 100315S00061 | 15KC0045 | 2015-07-02 | 2015-07-14 | 2015-07-15 | 2015-08-03 | 2015-08-17 | L & L CONSTRUCTION
14043 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303962 | Kimanait NHS | PANGANTUCAN | 4 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00060 | 15KC0045 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-08-03 | 2015-08-17 | L & L CONSTRUCTION
14044 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303962 | Kimanait NHS | PANGANTUCAN | 4 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00059 | 15KC0045 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-08-03 | 2015-08-17 | L & L CONSTRUCTION
14045 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303966 | Lampanusan NHS | KALILANGAN | 4 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3727968.78 |  |  | COMPLETED | 1 |  |  | 100315S00062 | 15KC0052 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-08-03 | 2015-08-17 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
14046 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314902 | Langcataon NHS | PANGANTUCAN | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2862592.44 |  |  | COMPLETED | 1 |  |  | 100315S00063 | 15KC0046 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-08-03 | 2015-08-17 | LLM CONCRETE PRODUCTS
14047 | NC 2015 | SHS (2015) | Region X | Bukidnon | 314902 | Langcataon NHS | PANGANTUCAN | 4 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00064 | 15KC0046 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-08-03 | 2015-08-17 | LLM CONCRETE PRODUCTS
14048 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303971 | Malinao NHS | KALILANGAN | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2892592.44 |  |  | COMPLETED | 1 |  |  | 100315S00065 | 15KC0047 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-08-03 | 2015-08-17 | LLM CONCRETE PRODUCTS
14049 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303971 | Malinao NHS | KALILANGAN | 4 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 100315S00066 | 15KC0047 | 2015-07-02 | 2015-07-13 | 2015-07-14 | 2015-08-03 | 2015-08-17 | LLM CONCRETE PRODUCTS
14050 | NC 2015 | SHS (2015) | Region X | Bukidnon | 303978 | Pangantucan NHS | PANGANTUCAN | 4 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 100315S00067 | 15KC0051 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-08-03 | 2015-08-17 | LLM CONCRETE PRODUCTS
14051 | NC 2015 | K10 (2015) | Region X | Bukidnon | 126699 | Quarry ES | PANGANTUCAN | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00146 | 15KC0060 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-07-31 | 2015-08-17 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
14052 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304106 | Bayabas NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100815S00029
14053 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 315412 | Bonbon NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 100815S00039
14054 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127997 | Bulao ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100815S00051 | 15KH0054 | 2015-10-09 | 2015-10-09 | 2015-10-21 | 2015-11-09 | 2015-11-16 | JDE CONSTRUCTION
14055 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127998 | Bulua CS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 31102890.27 |  |  | COMPLETED | 1 |  |  | 100815S00052 | 15KH0055 | 2015-10-09 | 2015-10-09 | 2015-10-21 | 2015-11-09 | 2015-11-16 | FFJJ CONSTRUCTION
14056 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304108 | Bulua NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 100815S00025 | 15KH0026 | 2015-08-06 | 2015-08-07 | 2015-08-19 | 2015-09-04 | 2015-09-11 | JAMARI CONSTRUCTION (FORMERLY FRAE CONSTRUCTION)
14057 | NC 2015 | TECHVOC (2015) | Region X | Cagayan de Oro City | 304108 | Bulua NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  | 100815S00060 | 15KH0059 | 2015-11-18 | 2015-11-18 | 2015-12-01 | 2015-12-31
14058 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 315403 | Cagayan de Oro NHS - Balulang Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100815S00024 | 15KH0038 | 2015-08-06 | 2015-08-07 | 2015-08-19 | 2015-09-04 | 2015-09-11 | FOOTPRINTS CONSTRUCTION
14059 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304109 | Canitoan NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 100815S00023 | 15KH0027 | 2015-08-06 | 2015-08-07 | 2015-08-19 | 2015-09-04 | 2015-09-11 | FOOTPRINTS CONSTRUCTION
14060 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304112 | Carmen NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 100815S00022 | 15KH0028 | 2015-08-06 | 2015-08-07 | 2015-08-19 | 2015-09-04 | 2015-09-11 | FOOTPRINTS CONSTRUCTION
14061 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127991 | Fr. William F. Masterson, SJ., ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 3 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 100815S00035 | 15KH0040 | 2015-09-10 | 2015-09-10 | 2015-09-22 | 2015-10-12 | 2015-10-19 | BRIMA CONSTRUCTION AND ENTERPRISES
14062 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 128002 | G. L. Reyes-Anhawon ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 100815S00053
14063 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 128003 | Iponan ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 100815S00044 | 15KH0056 | 2015-10-13 | 2015-10-13 | 2015-10-26 | 2015-11-17 | 2015-11-23 | A.R. & MARK BUILDERS
14064 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304117 | Iponan NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100815S00018 | 15KH0029 | 2015-08-06 | 2015-08-07 | 2015-08-19 | 2015-09-04 | 2015-09-11 | JDE CONSTRUCTION
14065 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 315409 | Iponan NHS - San Simon Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100815S00020 | 15KH0030 | 2015-08-06 | 2015-08-07 | 2015-08-19 | 2015-09-04 | 2015-09-11 | CDH BUILDERS, INC. (FORMERLY: CDH BUILDERS AND FAB
14066 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127963 | Kauswagan CS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 100815S00046 | 15KH0050 | 2015-10-09 | 2015-10-09 | 2015-10-21 | 2015-11-09 | 2015-11-16 | L & L CONSTRUCTION
14067 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 315411 | Kauswagan NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100815S00021 | 15KH0037 | 2015-08-06 | 2015-08-07 | 2015-08-19 | 2015-09-04 | 2015-09-11 | JAMARI CONSTRUCTION (FORMERLY FRAE CONSTRUCTION)
14068 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304119 | Lumbia NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 100815S00026 | 15KH0031 | 2015-08-06 | 2015-08-07 | 2015-08-19 | 2015-09-04 | 2015-09-11 | L & L CONSTRUCTION
14069 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127992 | Macanhan ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 100815S00058 | 15KH0058 | 2015-10-13 | 2015-10-13 | 2015-10-26 | 2015-11-17 | 2015-11-23 | A.R. & MARK BUILDERS
14070 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127979 | Mambuaya ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100815S00047 | 15KH0051 | 2015-10-09 | 2015-10-09 | 2015-10-21 | 2015-11-09 | 2015-11-16 | ZI 9 BUILDERS AND SUPPLIES
14071 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304121 | Mambuaya NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100815S00030 | 15KH0039 | 2015-08-06 | 2015-08-07 | 2015-08-19 | 2015-09-04 | 2015-09-11 | JAMARI CONSTRUCTION (FORMERLY FRAE CONSTRUCTION)
14072 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304122 | Mambuaya NHS-Bayanga Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 100815S00037 | 15KH0082 | 2015-11-18 | 2015-11-19 | 2015-12-01 | 2015-12-31
14073 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 128004 | Pagatpat ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 100815S00054 | 15KH0057 | 2015-10-13 | 2015-10-13 | 2015-10-26 | 2015-11-13 | 2015-11-23 | JDE CONSTRUCTION
14074 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304125 | Taglimao NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100815S00028 | 15KH0032 | 2015-09-10 | 2015-09-10 | 2015-09-22 | 2015-09-30 | 2015-10-19 | JAMARI CONSTRUCTION (FORMERLY FRAE CONSTRUCTION)
14075 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304126 | Taglimao NHS-Besigan Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100815S00019 | 15KH0033 | 2015-08-06 | 2015-08-07 | 2015-08-19 | 2015-09-04 | 2015-09-11 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
14076 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 315406 | Taglimao NHS-Tumpagon Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100815S00027 | 15KH0034 | 2015-09-10 | 2015-09-10 | 2015-09-22 | 2015-09-30 | 2015-10-19 | BRIMA CONSTRUCTION AND ENTERPRISES
14077 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127985 | Tagpangi ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100815S00048 | 15KH0052 | 2015-10-09 | 2015-10-09 | 2015-10-21 | 2015-11-09 | 2015-11-16 | FOOTPRINTS CONSTRUCTION
14078 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304127 | Tagpangi NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100815S00031 | 15KH0035 | 2015-09-10 | 2015-09-10 | 2015-09-22 | 2015-09-30 | 2015-10-19 | BRIMA CONSTRUCTION AND ENTERPRISES
14079 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304128 | Tagpangi NHS-Tuburan Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3697969 |  |  | COMPLETED | 1 |  |  | 100815S00038 | 15KH0074 | 2015-12-01 | 2015-12-01 | 2015-12-14 | 2015-12-31
14080 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304123 | Tignapoloan NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6529337.6381 |  |  | COMPLETED | 1 |  |  | 100815S00013 | 15KH0041 | 2015-08-14 | 2015-08-14 | 2015-08-26 | 2015-09-11 | 2015-09-18 | GENETIAN BUILDERS
14081 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127995 | West City CS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 31102890.27 |  |  | COMPLETED | 1 |  |  | 100815S00050 | 15KH0049 | 2015-10-09 | 2015-10-09 | 2015-10-21 | 2015-11-09 | 2015-11-16 | FOOTPRINTS CONSTRUCTION
14082 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127995 | West City CS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 100815S00045 | 15KH0053 | 2015-10-09 | 2015-10-09 | 2015-10-21 | 2015-11-09 | 2015-11-16 | FOOTPRINTS CONSTRUCTION
14083 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127947 | Agusan ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 29795037.68 |  |  | COMPLETED | 1 |  |  | 100815S00057 | 15KD0042 | 2015-10-07 | 2015-10-01 | 2015-10-07 | 2015-11-05 | 2015-11-13 | FFJJ CONSTRUCTION
14084 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304104 | Agusan National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100815S00033 | 15KD0020 | 2015-07-19 | 2015-07-21 | 2015-08-13 | 2015-08-19 | 2015-08-26 | JDE CONSTRUCTION
14085 | NC 2015 | TECHVOC (2015) | Region X | Cagayan de Oro City | 304104 | Agusan National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1 |  |  | 100815S00062 | 15KD0045 | 2015-10-09 | 2015-10-16 | 2015-10-27 | 2015-12-04 | 2015-12-15 | A.R. & MARK BUILDERS
14086 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304113 | Angeles Sisters NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15321327.92 |  |  | COMPLETED | 1 |  |  | 100815S00005 | 15KD0030 | 2015-08-23 | 2015-08-12 | 2015-08-26 | 2015-09-29 | 2015-10-06 | FFJJ CONSTRUCTION
14087 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 315401 | Balubal NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1 |  |  | 100815S00015 | 15KD0024 | 2015-07-20 | 2015-07-21 | 2015-08-13 | 2015-08-19 | 2015-08-26 | LAJ TRUCKING AND BUILDERS
14088 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 304107 | Bugo NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | COMPLETED | 1 |  |  | 100815S00036 | 15KD0028 | 2015-08-23 | 2015-08-12 | 2015-08-26 | 2015-09-20 | 2015-09-29 | BRIMA CONSTRUCTION AND ENTERPRISES
14089 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 304107 | Bugo NHS | CAGAYAN DE ORO CITY (Capital) | 2 |  | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 100815S00034 | 15KD0027 | 2015-08-23 | 2015-08-12 | 2015-09-10 | 2015-10-16 | 2015-10-27 | JARGON CONSTRUCTION & SUPPLY
14090 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304107 | Bugo NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1
14091 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304111 | Cagayan de Oro National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 100815S00006 | 15KD0031 | 2015-08-23 | 2015-08-12 | 2015-08-26 | 2015-09-25 | 2015-10-06 | L.N. SALVADOR CONSTRUCTION
14092 | NC 2015 | TECHVOC (2015) | Region X | Cagayan de Oro City | 304111 | Cagayan de Oro National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | REVERTED | 0 |  |  | 100815S00061 | 15KD0044 | 2015-10-27 | 2015-10-16 | 2015-10-27 | 2015-12-04 | 2015-12-15 | EDMOND RAY CONSTRUCTION & SUPPLY
14093 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 315404 | Camaman-an NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100815S00007 | 15KD0021 | 2015-07-19 | 2015-07-21 | 2015-08-13 | 2015-08-19 | 2015-08-26 | JDE CONSTRUCTION
14094 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127944 | Gusa ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 28 | 4STY28CL | 2015 K10 BATCH 6 | 40067946.14 |  |  | COMPLETED | 1 |  |  | 100815S00049 | 15KD0040 | 2015-10-01 | 2015-10-01 | 2015-10-07 | 2015-11-05 | 2015-11-13 | LEGACY CONSTRUCTION
14095 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 315408 | Gusa NHS - FS Catanico Annex | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100815S00008 | 15KD0026 | 2015-07-17 | 2015-07-23 | 2015-08-13 | 2015-08-20 | 2015-08-26 | DCD BUILDERS & ENTERPISES
14096 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304115 | Gusa NHS-Cugman Annex | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 100815S00009 | 15KD0033 | 2015-08-23 | 2015-08-12 | 2015-09-15 | 2015-10-18 | 2015-10-27 | A.R. & MARK BUILDERS
14097 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304114 | Gusa Regional Science High School-X | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 100815S00010 | 15KD0032 | 2015-08-23 | 2015-08-12 | 2015-08-26 | 2015-09-11 | 2015-10-12 | L.C. CONSTRUCTION
14098 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304116 | Indahag National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 100815S00011 | 15KD0039 | 2015-10-07 | 2015-10-16 | 2015-10-20 | 2015-11-12 | 2015-11-20 | DICON BUILDERS CORP.
14099 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 315407 | Lapasan NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1 |  |  | 100815S00043 | 125KD0038 | 2015-10-07 | 2015-09-18 | 2015-10-07 | 2015-11-09 | 2015-11-17 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
14100 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 315407 | Lapasan NHS-Gusa Annex | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100815S00012 | 15KD0022 | 2015-07-19 | 2015-07-21 | 2015-08-13 | 2015-08-20 | 2015-08-26 | BRIMA CONSTRUCTION AND ENTERPRISES
14101 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304120 | Macabalan NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 |  |  | 100815S00042 | 15KD0008 | 2015-10-08 | 2015-09-25 | 2015-10-08 | 2015-11-05 | 2015-11-13 | LAJ TRUCKING AND BUILDERS
14102 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 315410 | Macasandig NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100815S00017 | 15KD0023 | 2015-07-19 | 2015-07-21 | 2015-08-13 | 2015-08-21 | 2015-08-26 | BRIMA CONSTRUCTION AND ENTERPRISES
14103 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127952 | Puerto ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100815S00055 | 15KD0047 | 2015-11-05 | 2015-10-27 | 2015-11-05 | 2015-11-27 | 2015-12-10 | D2J BUILDERS VENTURE
14104 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 315402 | Puerto NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 7 | 22152344 |  |  | REVERTED | 0 |  |  | 100815S00059
14105 | NC 2015 | K10 (2015) | Region X | Cagayan de Oro City | 127967 | South City CS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100815S00056 | 15KD0041 | 2015-10-07 | 2015-10-01 | 2015-10-07 | 2015-11-07 | 2015-11-17 | DCD BUILDERS & ENTERPISES
14106 | NC 2015 | SHS (2015) | Region X | Cagayan de Oro City | 304105 | Tablon NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 100815S00014 | 15KD0025 | 2015-07-20 | 2015-07-23 | 2015-08-06 | 2015-08-28 | 2015-09-08 | FFJJ CONSTRUCTION
14107 | NC 2015 | K10 (2015) | Region X | Camiguin | 126905 | Agoho Elementary School | MAMBAJAO (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100415S00011 | 15KE0040 | 2015-08-17 | 2015-09-07 | 2015-09-11 | 2015-09-15 | 2015-09-28 | SHEEN-SHEEN CONSTRUCTION
14108 | NC 2015 | K10 (2015) | Region X | Camiguin | 315002 | Alangilan Integrated School | SAGAY | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2188606 |  |  | COMPLETED | 1 |  |  | 100415S00019 | 15KE0054 | 2015-08-29 | 2015-09-07 | 2015-09-11 | 2015-10-02 | 2015-10-31 | SHEEN-SHEEN CONSTRUCTION
14109 | NC 2015 | K10 (2015) | Region X | Camiguin | 315002 | Alangilan Integrated School | SAGAY | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2038606 |  |  | COMPLETED | 1 |  |  | 100415S00018 | 15KE0055 | 2015-08-29 | 2015-09-07 | 2015-09-11 | 2015-10-02 | 2015-10-31 | SHEEN-SHEEN CONSTRUCTION
14110 | NC 2015 | SHS (2015) | Region X | Camiguin | 303989 | Bonbon NHS | CATARMAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 100415S00009 | 15KE0036 | 2015-08-17 | 2015-09-04 | 2015-09-11 | 2015-09-14 | 2015-09-21 | GCMG CONSTRUCTION
14111 | NC 2015 | K10 (2015) | Region X | Camiguin | 315004 | Bugang Integrated School | SAGAY | 0 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 100415S00012 | 15KE0043 | 2015-07-24 | 2015-08-19 | 2015-08-20 | 2015-09-07 | 2015-09-28 | SHEEN-SHEEN CONSTRUCTION
14112 | NC 2015 | SHS (2015) | Region X | Camiguin | 303990 | Camiguin NHS | CATARMAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 100415S00008 | 15KE0057 | 2015-08-17 | 2015-09-08 | 2015-09-11 | 2015-09-14 | 2015-09-21 | GCMG CONSTRUCTION
14113 | NC 2015 | SHS (2015) | Region X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | SAGAY | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100415S00007 | 15KE0029 | 2015-08-17 | 2015-09-05 | 2015-09-11 | 2015-09-14 | 2015-09-28 | JAPUZ-JANSOL ENTERPRISES
14114 | NC 2015 | SHS (2015) | Region X | Camiguin | 303991 | Guinsiliban National High School | GUINSILIBAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8219965.051 |  |  | COMPLETED | 1 |  |  | 100415S00006 | 15KE0030 | 2015-08-26 | 2015-09-09 | 2015-09-11 | 2015-09-15 | 2015-09-28 | JAPUZ-JANSOL ENTERPRISES
14115 | NC 2015 | SHS (2015) | Region X | Camiguin | 303992 | Lawigan-Bura National High School | CATARMAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 100415S00010 | 15KE0037 | 2015-08-17 | 2015-09-02 | 2015-09-11 | 2015-09-15 | 2015-09-28 | GCMG CONSTRUCTION
14116 | NC 2015 | K10 (2015) | Region X | Camiguin | 126933 | Maac ES | GUINSILIBAN | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100415S00013 | 15KE0041 | 2015-08-17 | 2015-09-07 | 2015-09-11 | 2015-09-14 | 2015-09-28 | JAPUZ-JANSOL ENTERPRISES
14117 | NC 2015 | SHS (2015) | Region X | Camiguin | 315001 | Maac NHS | GUINSILIBAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100415S00005 | 15KE0031 | 2015-08-21 | 2015-09-04 | 2015-09-11 | 2015-09-14 | 2015-09-28 | JAPUZ-JANSOL ENTERPRISES
14118 | NC 2015 | K10 (2015) | Region X | Camiguin | 315003 | Mahinog National High School II | MAHINOG | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100415S00016 | 15KE0042 | 2015-08-17 | 2015-09-03 | 2015-09-11 | 2015-09-14 | 2015-09-28 | SHEEN-SHEEN CONSTRUCTION
14119 | NC 2015 | SHS (2015) | Region X | Camiguin | 303993 | Mahinog NHS | MAHINOG | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10422131.51 |  |  | COMPLETED | 1 |  |  | 100415S00004 | 15KE0032 | 2015-08-17 | 2015-09-04 | 2015-09-11 | 2015-09-15 | 2015-09-28 | GCMG CONSTRUCTION
14120 | NC 2015 | SHS (2015) | Region X | Camiguin | 303994 | Mambajao NHS | MAMBAJAO (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100415S00003 | 15KE0033 | 2015-08-17 | 2015-09-07 | 2015-09-11 | 2015-09-14 | 2015-09-28 | SHEEN-SHEEN CONSTRUCTION
14121 | NC 2015 | K10 (2015) | Region X | Camiguin | 126903 | Tacangon ES | MAHINOG | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100415S00015 | 2865.2689999999998 |  | 2015-07-23 | 2015-08-19 | 2015-08-20 | 2015-09-11 | 42275
14122 | NC 2015 | K10 (2015) | Region X | Camiguin | 126903 | Tacangon ES | MAHINOG | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 100415S00014 | 2020.8326999999999 |  | 2015-07-24 | 2015-08-19 | 2015-08-20 | 2015-09-07 | 42275
14123 | NC 2015 | SHS (2015) | Region X | Camiguin | 303996 | Tupsan NHS | MAMBAJAO (Capital) | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 100415S00002 | 15KE0032 | 2015-08-17 | 2015-09-02 | 2015-09-11 | 2015-09-14 | 2015-09-28 | GCMG CONSTRUCTION
14124 | NC 2015 | K10 (2015) | Region X | Camiguin | 126922 | Volcan ES | MAMBAJAO (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1948606.04 |  |  | COMPLETED | 1 |  |  | 100415S00017 | 15KE0056 | 2015-08-20 | 2015-09-07 | 2015-09-11 | 2015-09-15 | 2015-09-28 | JAPUZ-JANSOL ENTERPRISES
14125 | NC 2015 | SHS (2015) | Region X | Camiguin | 303997 | Yumbing National High School | MAMBAJAO (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8216965.051 |  |  | COMPLETED | 1 |  |  | 100415S00001 | 15KE0035 | 2015-08-17 | 2015-09-08 | 2015-09-11 | 2015-09-14 | 2015-09-28 | SHEEN-SHEEN CONSTRUCTION
14126 | NC 2015 | SHS (2015) | Region X | El Salvador | 304065 | Cogon NHS | CITY OF EL SALVADOR | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8279965.051 |  |  | COMPLETED | 1 |  |  | 100615S00008 | 15KL0036 | 2015-07-06 | 2015-07-18 | 2015-07-21 | 2015-07-25 | 2015-07-31 | JDE CONSTRUCTION
14127 | NC 2015 | K10 (2015) | Region X | El Salvador | 127672 | Himaya ES | CITY OF EL SALVADOR | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 100615S00050 | 15KL0044 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-08-07 | 2015-08-13 | FOOTPRINTS CONSTRUCTION
14128 | NC 2015 | K10 (2015) | Region X | El Salvador | 127673 | Hinigdaan ES | CITY OF EL SALVADOR | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100615S00049 | 15KL0043 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-08-07 | 2015-08-13 | C ZARLES CONSTRUCTION & SUPPLY
14129 | NC 2015 | SHS (2015) | Region X | El Salvador | 315318 | Hinigdaan NHS | CITY OF EL SALVADOR | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6484337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00007 | 15KL0037 | 2015-07-06 | 2015-07-18 | 2015-07-21 | 2015-07-25 | 2015-07-31 | RAMONA CONSTRUCTION & ENTERPRISES
14130 | NC 2015 | SHS (2015) | Region X | El Salvador | 315305 | Molugan NHS | CITY OF EL SALVADOR | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1 |  |  | 100615S00009 | 15KL0035 | 2015-07-06 | 2015-07-18 | 2015-07-21 | 2015-07-25 | 2015-07-31 | JDE CONSTRUCTION
14131 | NC 2015 | K10 (2015) | Region X | El Salvador | 127669 | San Francisco de Asis ES (Calongonan ES) | CITY OF EL SALVADOR | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 100615S00075 | 15KL0093 | 2015-08-25 | 2015-08-26 | 2015-09-07 | 2015-09-16 | 2015-09-25 | FFJJ CONSTRUCTION
14132 | NC 2015 | SHS (2015) | Region X | Gingoog City | 304131 | BACKKISMI NHS | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6449337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00010 | 15KK0043 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-10 | 2015-08-14 | WDM CONSTRUCTION AND SUPPLIES
14133 | NC 2015 | SHS (2015) | Region X | Gingoog City | 304129 | Bal-ason NHS | GINGOOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 100615S00011 | 15KK0034 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | WDM CONSTRUCTION AND SUPPLIES
14134 | NC 2015 | K10 (2015) | Region X | Gingoog City | 128062 | Bantaawan Elementary School | GINGOOG CITY | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 100615S00095
14135 | NC 2015 | K10 (2015) | Region X | Gingoog City | 128065 | Dona J. Pelaez Reyes ES | GINGOOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 100615S00096 | 15KK0095 | 2015-11-20 | 2015-12-02 | 2015-12-03 | 2015-12-07 | 2015-12-11 | R. DE MESA CONSTRUCTION
14136 | NC 2015 | K10 (2015) | Region X | Gingoog City | 128025 | Dukdokaan ES | GINGOOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 100615S00073
14137 | NC 2015 | SHS (2015) | Region X | Gingoog City | 500254 | EUREKA NATIONAL HIGH SCHOOL | GINGOOG CITY | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2805828.124 |  |  | COMPLETED | 1 |  |  | 100615S00012 | 15KK0044 | 2015-08-14 | 2015-08-26 | 2015-08-27 | 2015-08-31
14138 | NC 2015 | SHS (2015) | Region X | Gingoog City | 304130 | Gingoog City CNHS | GINGOOG CITY | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14962518.84 |  |  | COMPLETED | 1 |  |  | 100615S00013 | 15KK0068 | 2015-08-25 | 2015-09-06 | 2015-09-07 | 2015-09-11 | 2015-09-15 | RYM CONSTRUCTION
14139 | NC 2015 | SHS (2015) | Region X | Gingoog City | 304130 | Gingoog City CNHS | GINGOOG CITY | 1 |  | 20 | 4STY20CL | 2015 SHS BATCH 1 | 31102890.27 |  |  | COMPLETED | 1 |  |  | 100615S00024 | 15KK0067 | 2015-08-25 | 2015-09-06 | 2015-09-07 | 2015-09-11 | 2015-09-15 | DICON BUILDERS CORP.
14140 | NC 2015 | SHS (2015) | Region X | Gingoog City | 315505 | Gingoog City CNHS - Anakan NHS Annex | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6384337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00015 | 15KK0042 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-10 | 2015-08-14 | ALEBON GENUINE MERCHANDISING INCORPORATED
14141 | NC 2015 | SHS (2015) | Region X | Gingoog City | 315503 | Gingoog City CNHS - LURISA NHS Annex | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6449337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00006 | 15KK0046 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-10 | 2015-08-14 | ALEBON GENUINE MERCHANDISING INCORPORATED
14142 | NC 2015 | SHS (2015) | Region X | Gingoog City | 315504 | Gingoog City CNHS - PUNDASAN NHS Annex | GINGOOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8289965.051 |  |  | COMPLETED | 1 |  |  | 100615S00017 | 15KK0039 | 2015-07-21 | 2015-08-02 | 2015-08-03 | 2015-08-07 | 2015-08-11 | RYM CONSTRUCTION
14143 | NC 2015 | K10 (2015) | Region X | Gingoog City | 128029 | IMPALUHOD ELEMENTARY SCH | GINGOOG CITY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100615S00053 | 15KK0054
14144 | NC 2015 | K10 (2015) | Region X | Gingoog City | 128029 | IMPALUHOD ELEMENTARY SCH | GINGOOG CITY | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 100615S00054 | 15KK0053
14145 | NC 2015 | SHS (2015) | Region X | Gingoog City | 304132 | Kalipay NHS | GINGOOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8359965.051 |  |  | COMPLETED | 1 |  |  | 100615S00018 | 15KK0035 | 2015-11-13 | 2015-11-25 | 2015-11-26 | 2015-11-30 | 2015-12-04 | LEGACY CONSTRUCTION
14146 | NC 2015 | SHS (2015) | Region X | Gingoog City | 315506 | Kisande NHS | GINGOOG CITY | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100615S00019 | 15KK0045 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-10 | 2015-08-14 | BRYTON BUILDERS AND DEVELOPMENT CORP.
14147 | NC 2015 | K10 (2015) | Region X | Gingoog City | 128014 | Libon ES | GINGOOG CITY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100615S00052 | 15KK0058 | 2015-11-20 | 2015-12-02 | 2015-12-03 | 2015-12-07 | 2015-12-11 | A.C. SY CONSTRUCTION
14148 | NC 2015 | K10 (2015) | Region X | Gingoog City | 128014 | Libon ES | GINGOOG CITY | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 100615S00043 | 15KK0059 | 2015-11-20 | 2015-12-02 | 2015-12-03 | 2015-12-07 | 2015-12-11 | A.C. SY CONSTRUCTION
14149 | NC 2015 | SHS (2015) | Region X | Gingoog City | 315507 | Lunao NHS | GINGOOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8279965.051 |  |  | COMPLETED | 1 |  |  | 100615S00005 | 15KK0036 | 2015-07-26 | 2015-08-05 | 2015-07-26 | 2015-07-30 | 2015-08-03 | R.C. TAGALA CONSTRUCTION
14150 | NC 2015 | SHS (2015) | Region X | Gingoog City | 304133 | Malibud NHS | GINGOOG CITY | 1 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 1 | 12916310.093 |  |  | COMPLETED | 1 |  |  | 100615S00020 | 15KK0069 | 2015-11-25 | 2015-12-07 | 2015-12-08 | 2015-12-12 | 2015-12-16 | LEGACY CONSTRUCTION
14151 | NC 2015 | SHS (2015) | Region X | Gingoog City | 304134 | Malinao NHS | GINGOOG CITY | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2800828.124 |  |  | COMPLETED | 1 |  |  | 100615S00014 | 15KK0047 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-10 | 2015-08-14 | BRYTON BUILDERS AND DEVELOPMENT CORP.
14152 | NC 2015 | K10 (2015) | Region X | Gingoog City | 128055 | Manuel Lugod CS | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00094 | 15KK0093 | 2015-09-24 | 2015-10-06 | 2015-10-07 | 2015-10-11 | 2015-10-15 | BRIMA CONSTRUCTION AND ENTERPRISES
14153 | NC 2015 | SHS (2015) | Region X | Gingoog City | 304135 | Mimbunga NHS | GINGOOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8329965.051 |  |  | COMPLETED | 1 |  |  | 100615S00021 | 15KK0037 | 2015-07-21 | 2015-08-02 | 2015-08-03 | 2015-08-07 | 2015-08-11 | WDM CONSTRUCTION AND SUPPLIES
14154 | NC 2015 | SHS (2015) | Region X | Gingoog City | 304136 | Odiongan NHS | GINGOOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 100615S00022 | 15KK0038 | 2015-07-21 | 2015-08-02 | 2015-08-03 | 2015-08-07 | 2015-08-11 | AMMAR CONSTRUCTION AND ENTERPRISES
14155 | NC 2015 | SHS (2015) | Region X | Gingoog City | 315502 | Odiongan NHS - Talisay NHS Annex | GINGOOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8279965.051 |  |  | COMPLETED | 1 |  |  | 100615S00023 | 15KK0041 | 2015-07-21 | 2015-08-02 | 2015-08-03 | 2015-08-07 | 2015-08-11 | AMMAR CONSTRUCTION AND ENTERPRISES
14156 | NC 2015 | K10 (2015) | Region X | Gingoog City | 128020 | Punong Elementary School | GINGOOG CITY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100615S00048 | 15KK0060 | 2015-09-08 | 2015-09-20 | 2015-09-21 | 2015-09-25 | 2015-09-29 | Z & L CONSTRUCTION & SUPPLIES
14157 | NC 2015 | K10 (2015) | Region X | Gingoog City | 128020 | Punong Elementary School | GINGOOG CITY | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 100615S00051 | 15KK0061 | 2015-09-08 | 2015-09-20 | 2015-09-21 | 2015-09-25 | 2015-09-29 | Z & L CONSTRUCTION & SUPPLIES
14158 | NC 2015 | SHS (2015) | Region X | Gingoog City | 304137 | San Luis NHS | GINGOOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8279965.051 |  |  | COMPLETED | 1 |  |  | 100615S00016 | 15KK0040 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | LEGACY CONSTRUCTION
14159 | NC 2015 | K10 (2015) | Region X | Gingoog City | 128043 | Sioan ES | GINGOOG CITY | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 100615S00101 | 15KK0092 | 2015-11-20 | 2015-12-02 | 2015-12-03 | 2015-12-07 | 2015-12-11 | A.C. SY CONSTRUCTION
14160 | NC 2015 | K10 (2015) | Region X | Gingoog City | 128021 | Sta. Rita ES | GINGOOG CITY | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 6 | 10957342.5917 |  |  | COMPLETED | 1 |  |  | 100615S00076 | 15KK0090 | 2015-11-20 | 2015-12-02 | 2015-12-03 | 2015-12-07 | 2015-12-11 | RYM CONSTRUCTION
14161 | NC 2015 | SHS (2015) | Region X | Iligan City | 304139 | Acelo C. Badelles, Sr. MNHS - Abuno HS Annex | ILIGAN CITY | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00017 | 15KF0027 | 2015-07-22 | 2015-08-03 | 2015-08-04 | 2015-08-08 | 2015-09-04 | D.C.M. CONSTRUCTION
14162 | NC 2015 | SHS (2015) | Region X | Iligan City | 304138 | Acelo C. Badelles, Sr. MNHS (Tipanoy NHS) | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | COMPLETED | 1 |  |  | 100115S00069 | 15KF0093 | 2015-09-03 | 2015-09-15 | 2015-09-16 |  |  | TESAR BUILDERS
14163 | NC 2015 | K10 (2015) | Region X | Iligan City | 203002 | BACUITANA ES | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00073 | 15KF0089 | 2015-08-27 | 2015-09-08 | 2015-09-09 | 2015-09-13 | 2015-10-02 | AHMADI BUILDERS
14164 | NC 2015 | SHS (2015) | Region X | Iligan City | 304140 | Bunawan Agri. HS | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100115S00007 | 15KF0037 | 2015-07-21 | 2015-08-02 | 2015-08-03 | 2015-08-07 | 2015-09-04 | AHMADI BUILDERS
14165 | NC 2015 | SHS (2015) | Region X | Iligan City | 304143 | Dalipuga NHS | ILIGAN CITY | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 100115S00011 | 15KF0052 | 2015-07-15 | 2015-07-28 | 2015-07-28 | 2015-08-01 | 2015-08-26 | AHMADI BUILDERS
14166 | NC 2015 | SHS (2015) | Region X | Iligan City | 304144 | Dalipuga NHS - Hindang NHS Annex | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100115S00016 | 15KF0034 | 2015-07-18 | 2015-07-30 | 2015-07-31 | 2015-08-04 | 2015-09-03 | AHMADI BUILDERS
14167 | NC 2015 | SHS (2015) | Region X | Iligan City | 315609 | Dalipuga NHS - Kalubihon Annex | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100115S00038 | 15KF0035 | 2015-07-18 | 2015-07-30 | 2015-07-31 | 2015-08-04 | 2015-09-03 | AHMADI BUILDERS
14168 | NC 2015 | K10 (2015) | Region X | Iligan City | 128148 | Dona Josefa F. Celdran MS | ILIGAN CITY | 0 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 100115S00067 | 15KF0072 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-12 | 2015-09-07 | DICON BUILDERS CORP.
14169 | NC 2015 | SHS (2015) | Region X | Iligan City | 304154 | Esperidion F. Encabo I MHS (Pugaan NHS) | ILIGAN CITY | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00002 | 15KF0025 | 2015-07-22 | 2015-08-03 | 2015-08-04 | 2015-08-08 | 2015-09-04 | AHMADI BUILDERS
14170 | NC 2015 | SHS (2015) | Region X | Iligan City | 315608 | Francisco Laya Memorial Integrated School | ILIGAN CITY | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00008 | 15KF0026 | 2015-07-22 | 2015-08-03 | 2015-08-04 | 2015-08-08 | 2015-09-04 | AL-FAHDEL CONSTRUCTION & ENGINEERING
14171 | NC 2015 | K10 (2015) | Region X | Iligan City | 128091 | Iligan City Central School | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00088 | 15KF0088 | 2015-08-27 | 2015-09-08 | 2015-09-09 | 2015-09-13 | 2015-10-02 | TESAR BUILDERS
14172 | NC 2015 | SHS (2015) | Region X | Iligan City | 304149 | Iligan City East HS - Hinaplanon Annex | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00013 | 15KF0058 | 2015-07-16 | 2015-07-28 | 2015-07-29 | 2015-08-02 | 2015-08-26 | MARKBUILT ENTERPRISES
14173 | NC 2015 | SHS (2015) | Region X | Iligan City | 304147 | Iligan City East HS - Kiwalan Annex | ILIGAN CITY | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  | 100115S00010 | 15KF0030 | 2015-06-26 | 2015-07-08 | 2015-07-09 | 2015-07-13 | 2015-08-03 | AL-FAHDEL CONSTRUCTION & ENGINEERING
14174 | NC 2015 | SHS (2015) | Region X | Iligan City | 304148 | Iligan City East HS - Santiago HS Annex | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100115S00037 | 15KF0036 | 2015-07-18 | 2015-07-30 | 2015-07-31 | 2015-08-04 | 2015-09-03 | BRIMA CONSTRUCTION AND ENTERPRISES
14175 | NC 2015 | SHS (2015) | Region X | Iligan City | 304146 | Iligan City East HS (Sta. Filomena) | ILIGAN CITY | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 100115S00019 | 15KF0053 | 2015-07-15 | 2015-07-27 | 2015-07-28 | 2015-08-01 | 2015-08-26 | BRIMA CONSTRUCTION AND ENTERPRISES
14176 | NC 2015 | SHS (2015) | Region X | Iligan City | 304145 | Iligan City NHS | ILIGAN CITY | 0 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 1 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 100115S00009 | 15KF0060 | 2015-07-15 | 2015-07-27 | 2015-07-28 | 2015-08-01 | 2015-08-26 | DICON BUILDERS CORP.
14177 | NC 2015 | SHS (2015) | Region X | Iligan City | 304145 | Iligan City NHS | ILIGAN CITY | 0 |  | 16 | 4STY16CL | 2015 SHS BATCH 1 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 100115S00006 | 15KF0061 | 2015-07-16 | 2015-07-28 | 2015-07-29 | 2015-08-02 | 2015-08-26 | D.C.M. CONSTRUCTION
14178 | NC 2015 | TECHVOC (2015) | Region X | Iligan City | 304145 | Iligan City NHS | ILIGAN CITY | 0 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1 |  |  | 100115S00100 | 15KF0094 | 2015-09-03 | 2015-09-15 | 2015-09-16 | 2015-09-20 | 2015-10-16 | MARKBUILT ENTERPRISES
14179 | NC 2015 | SHS (2015) | Region X | Iligan City | 315603 | Iligan City NHS - Tambacan HS Annex | ILIGAN CITY | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00005 | 15KF0054 | 2015-07-15 | 2015-07-27 | 2015-07-28 | 2015-08-01 | 2015-08-26 | D.C.M. CONSTRUCTION
14180 | NC 2015 | SHS (2015) | Region X | Iligan City | 304150 | Iligan City NSOF | ILIGAN CITY | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 100115S00004 | 15KF0055 | 2015-07-15 | 2015-07-27 | 2015-07-28 | 2015-08-01 | 2015-08-26 | D.C.M. CONSTRUCTION
14181 | NC 2015 | K10 (2015) | Region X | Iligan City | 128109 | Kabacsanan ES | ILIGAN CITY | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 3152592.44 |  |  | COMPLETED | 1 |  |  | 100115S00059 | 15KF0075 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-10 | 2015-09-07 | AL-FAHDEL CONSTRUCTION & ENGINEERING
14182 | NC 2015 | K10 (2015) | Region X | Iligan City | 128109 | Kabacsanan ES | ILIGAN CITY | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 100115S00060 | 15KF0074 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-10 | 2015-09-07 | AL-FAHDEL CONSTRUCTION & ENGINEERING
14183 | NC 2015 | SHS (2015) | Region X | Iligan City | 304142 | Kabacsanan National High School | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100115S00036 | 15KF0039 | 2015-07-21 | 2015-08-02 | 2015-08-03 | 2015-08-07 | 2015-09-04 | AHMADI BUILDERS
14184 | NC 2015 | K10 (2015) | Region X | Iligan City | 128101 | Kalilangan ES | ILIGAN CITY | 0 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 100115S00056 | 15KF0098 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-21 | DCD BUILDERS & ENTERPISES
14185 | NC 2015 | K10 (2015) | Region X | Iligan City | 128102 | Lanipao ES | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00080 | 15KF0091 | 2015-08-27 | 2015-09-08 | 2015-09-09 | 2015-09-13 | 2015-10-02 | DCD BUILDERS & ENTERPISES
14186 | NC 2015 | SHS (2015) | Region X | Iligan City | 304151 | Mainit High School | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100115S00035 | 15KF0038 | 2015-07-21 | 2015-08-02 | 2015-08-03 | 2015-08-07 | 2015-09-04 | DCD BUILDERS & ENTERPISES
14187 | NC 2015 | SHS (2015) | Region X | Iligan City | 304153 | Maria Cristina HS - Ditucalan HS Annex | ILIGAN CITY | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2790828.124 |  |  | COMPLETED | 1 |  |  | 100115S00003 | 15KF0028 | 2015-06-26 | 2015-07-08 | 2015-07-09 | 2015-07-13 | 2015-08-03 | D.C.M. CONSTRUCTION
14188 | NC 2015 | SHS (2015) | Region X | Iligan City | 304152 | Maria Cristina NHS | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1844740.174 |  |  | COMPLETED | 1 |  |  | 100115S00018 | 15KF0032 | 2015-07-18 | 2015-07-30 | 2015-07-31 | 2015-08-04 | 2015-09-03 | D.O.T. CONSTRUCTION
14189 | NC 2015 | SHS (2015) | Region X | Iligan City | 304152 | Maria Cristina NHS | ILIGAN CITY | 0 |  | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1844740.174 |  |  | COMPLETED | 1 |  |  | 100115S00022 | 15KF0033 | 2015-07-18 | 2015-07-30 | 2015-07-31 | 2015-08-04 | 2015-09-03 | BRIMA CONSTRUCTION AND ENTERPRISES
14190 | NC 2015 | K10 (2015) | Region X | Iligan City | 128132 | Pudog ES | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00072 | 15KF0090 | 2015-08-27 | 2015-09-08 | 2015-09-09 | 2015-09-13 | 2015-10-02 | AL-FAHDEL CONSTRUCTION & ENGINEERING
14191 | NC 2015 | K10 (2015) | Region X | Iligan City | 128133 | Rebucon ES | ILIGAN CITY | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100115S00061 | 15KF0099 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-21 | MARKBUILT ENTERPRISES
14192 | NC 2015 | SHS (2015) | Region X | Iligan City | 304155 | Rogongon Agricultural High School | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100115S00034 | 15KF0040 | 2015-08-23 | 2015-09-04 | 2015-09-05 | 2015-09-09 | 2015-10-02 | MARKBUILT ENTERPRISES
14193 | NC 2015 | SHS (2015) | Region X | Iligan City | 304156 | Suarez NHS | ILIGAN CITY | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00012 | 15KF0056 | 2015-07-16 | 2015-07-28 | 2015-07-29 | 2015-08-02 | 2015-08-26 | AMMAR CONSTRUCTION AND ENTERPRISES
14194 | NC 2015 | SHS (2015) | Region X | Iligan City | 304157 | Tomas Cabili NHS | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | COMPLETED | 1 |  |  | 100115S00068 | 15KF0152 | 2015-11-04 | 2015-11-16 | 2015-11-17 | 2015-11-21 |  | TESAR BUILDERS
14195 | NC 2015 | SHS (2015) | Region X | Iligan City | 304159 | Tubaran NHS | ILIGAN CITY | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2740828.124 |  |  | COMPLETED | 1 |  |  | 100115S00028 | 15KF0029 | 2015-06-26 | 2015-07-08 | 2015-07-09 | 2015-07-13 | 2015-08-03 | AL-FAHDEL CONSTRUCTION & ENGINEERING
14196 | NC 2015 | SHS (2015) | Region X | Iligan City | 304160 | Tubaran NHS - Digkilaan HS Annex | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6429337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00052 | 15KF0059 | 2015-07-16 | 2015-07-28 | 2015-07-29 | 2015-08-02 | 2015-08-26 | AHMADI BUILDERS
14197 | NC 2015 | SHS (2015) | Region X | Iligan City | 315606 | Tubaran NHS (Lanipao Annex) | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2188606 |  |  | COMPLETED | 1 |  |  | 100115S00070 | 15KF0095 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-21 | DCD BUILDERS & ENTERPISES
14198 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304002 | Arsenio A. Quibranza NHS (LNNAIHS) | TUBOD (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00033 | 15KF0048 | 2015-07-14 | 2015-07-26 | 2015-07-27 | 2015-07-31 | 2015-08-26 | R. DE MESA CONSTRUCTION
14199 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 126950 | Bago Ingud PS | BALOI | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100115S00074 | 15KG0033 | 2015-08-05 | 2015-08-05 | 2015-09-03 | 2015-09-09 | 2015-09-17 | DCD BUILDERS & ENTERPISES
14200 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 126961 | Baloi Central ES | BALOI | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 100115S00055 | 15KG0021 | 2015-08-02 | 2015-08-13 | 2015-08-24 | 2015-09-11 | 2015-09-17 | D.C.M. CONSTRUCTION
14201 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 303998 | Baloi NHS | BALOI | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00032 | 15KG0032 | 2015-08-02 | 2015-08-03 | 2015-08-14 | 2015-08-24 | 2015-09-01 | RCM CONSTRUCTION & SUPPLIES
14202 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304000 | Binuni-Demologan NHS | BACOLOD | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 100115S00031 | 15KF0044 | 2015-07-11 | 2015-07-23 | 2015-07-24 | 2015-07-28 | 2015-08-19 | AMMAR CONSTRUCTION AND ENTERPRISES
14203 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 315109 | Dalama Integrated School Co Integrated with School ID 127012 | TUBOD (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00062 | 15KF0077 | 2015-07-28 | 2015-08-09 | 2015-08-10 | 2015-08-14 | 2015-09-14 | D.C.M. CONSTRUCTION
14204 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 200536 | Darimbang PS | TAGOLOAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00098 | 15KG0053 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-05 | AL-MODHEL CONSTRUCTION AND ENGINEERING SERVICES
14205 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 315106 | Delabayan NHS (Annex Marcela Mabanta NHS) | KAUSWAGAN | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  | 100115S00020 | 15KF0031 | 2015-06-26 | 2015-07-08 | 2015-07-09 | 2015-07-13 | 2015-08-03 | TESAR BUILDERS
14206 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304013 | Diego H. Patigayon NHS (Mukas NHS) | KOLAMBUGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 100115S00029 | 15KF0043 | 2015-07-11 | 2015-07-23 | 2015-07-24 | 2015-07-28 | 2015-08-19 | LANAO BUILDER AND ENTERPRISES
14207 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304001 | Diosdado Yap Memo. NHS | BAROY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 100115S00039 | 15KF0092 | 2015-09-03 | 2015-09-15 | 2015-09-16 | 2015-09-20 | 2015-10-16 | GRAND BUILDERS
14208 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304020 | Geronima Cabrera NHS (Riverside NHS) | KOLAMBUGAN | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10457131.51 |  |  | COMPLETED | 1 |  |  | 100115S00027 | 15KF0062 | 2015-07-16 | 2015-07-28 | 2015-07-29 | 2015-08-02 | 2015-08-26 | LANAO BUILDER AND ENTERPRISES
14209 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304005 | Lanao del Norte NCHS | BAROY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00026 | 15KF0050 | 2015-07-14 | 2015-07-26 | 2015-07-27 | 2015-07-31 | 2015-08-26 | D.C.M. CONSTRUCTION
14210 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 315102 | Lanao del Norte Provincial Science and Technology HS (former Malingao NHS (Annex New Pualas NHS) | TUBOD (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00025 | 15KF0049 | 2015-07-14 | 2015-07-26 | 2015-07-27 | 2015-07-31 | 2015-08-26 | LANAO BUILDER AND ENTERPRISES
14211 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304007 | Liangan NHS | BACOLOD | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 100115S00024 | 15KF0045 | 2015-07-11 | 2015-07-23 | 2015-07-24 | 2015-07-28 | 2015-08-19 | AMMAR CONSTRUCTION AND ENTERPRISES
14212 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127046 | Libertad ES | KAUSWAGAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00057 | 15KF0078 | 2015-07-28 | 2015-08-08 | 2015-08-10 | 2015-08-14 | 2015-09-14 | AHMADI BUILDERS
14213 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127227 | Licapao PS | TUBOD (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1948606.04 |  |  | COMPLETED | 1 |  |  | 100115S00076 | 15KF0097 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-21 | LANAO BUILDER AND ENTERPRISES
14214 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304008 | Linamon NHS | LINAMON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8219965.051 |  |  | COMPLETED | 1 |  |  | 100115S00023 | 15KF0047 | 2015-07-14 | 2015-07-26 | 2015-07-27 | 2015-07-31 | 2015-08-26 | LANAO BUILDER AND ENTERPRISES
14215 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304010 | Maigo NHS | MAIGO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10437131.51 |  |  | COMPLETED | 1 |  |  | 100115S00021 | 15KF0063 | 2015-07-16 | 2015-07-28 | 2015-07-29 | 2015-08-02 | 2015-08-26 | D.C.M. CONSTRUCTION
14216 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304011 | Marcela T. Mabanta Memo. NHS | KAUSWAGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00030 | 15KF0046 | 2015-07-14 | 2015-07-27 | 2015-07-27 | 2015-07-31 | 2015-08-26 | AHMADI BUILDERS
14217 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304012 | Matungao NHS | MATUNGAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 |  |  | 100115S00051 | 15KG0027 | 2015-08-02 | 2015-08-03 | 2015-08-14 | 2015-08-24 | 2015-09-01 | RCM CONSTRUCTION & SUPPLIES
14218 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304019 | Pantar NHS | PANTAR | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00050 | 15KG0028 | 2015-08-02 | 2015-08-03 | 2015-08-14 | 2015-08-24 | 2015-09-01 | AL-BADR CONSTRUCTION
14219 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304021 | Tagoloan NHS | TAGOLOAN | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100115S00102 | 15KG0015 | 2015-07-21 | 2015-07-22 | 2015-08-03 | 2015-08-07 | 2015-08-17 | TESAR BUILDERS
14220 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127172 | Tambo-Cadayonan PS | PANTAR | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 100115S00075
14221 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304015 | Teofila C. Quibranza NHS (New Pualas NHS) | TUBOD (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8229965.051 |  |  | COMPLETED | 1 |  |  | 100115S00049 | 15KF0041 | 2015-07-11 | 2015-07-23 | 2015-07-24 | 2015-07-28 | 2015-08-19 | AMMAR CONSTRUCTION AND ENTERPRISES
14222 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127234 | Teofilo Morales Sr. MES | TUBOD (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100115S00079 | 15KF0096 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-21 | LANAO BUILDER AND ENTERPRISES
14223 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304022 | Andres Bersales, Sr. Nat'l. HS (Pandanan NHS) | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 100115S00048 | 15KG0023 | 2015-08-02 | 2015-08-03 | 2015-08-14 | 2015-08-24 | 2015-09-01 | D.C.M. CONSTRUCTION
14224 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127014 | Bangaan Primary School | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100115S00077 | 15KG0038 | 2015-08-05 | 2015-08-05 | 2015-09-03 | 2015-09-09 | 2015-09-17 | AL-MODHEL CONSTRUCTION AND ENGINEERING SERVICES
14225 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127051 | Banisilon Elementary School | TANGCAL | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00093 | 15KG0049 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-05 | DCD BUILDERS & ENTERPISES
14226 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 303999 | Bansarvil NHS | KAPATAGAN | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 100115S00103 | 15KG0056 | 2015-10-19 | 2015-10-19 | 2015-10-30 | 2015-11-05 | 2015-11-16 | LANAO BUILDER AND ENTERPRISES
14227 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127020 | Dableston ES | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100115S00096 | 15KG0039 | 2015-08-05 | 2015-08-05 | 2015-09-03 | 2015-09-09 | 2015-09-17 | AL-MODHEL CONSTRUCTION AND ENGINEERING SERVICES
14228 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127193 | Dansalan PS | SAPAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00085 | 15KG0043 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-05 | D.C.M. CONSTRUCTION
14229 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127083 | Deogracias Urbano Tenazas Memo. School | LALA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100115S00092 | 15KG0036 | 2015-08-05 | 2015-08-05 | 2015-09-03 | 2015-09-09 | 2015-09-17 | D.C.M. CONSTRUCTION
14230 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127150 | Dimayon ES | PANTAO RAGAT | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00078 | 15KG0046 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-05 | MARKBUILT ENTERPRISES
14231 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127084 | El Salvador ES | LALA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100115S00058 | 15KG0018 | 2015-07-21 | 2015-07-22 | 2015-08-03 | 2015-08-07 | 2015-08-17 | TESAR BUILDERS
14232 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127022 | Ilian ES | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100115S00065 | 15KG0016 | 2015-07-21 | 2015-07-22 | 2015-08-03 | 2015-08-07 | 2015-08-17 | DCD BUILDERS & ENTERPISES
14233 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127022 | Ilian ES | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100115S00066 | 15KG0019 | 2015-07-21 | 2015-07-22 | 2015-08-03 | 2015-08-07 | 2015-08-17 | DCD BUILDERS & ENTERPISES
14234 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304003 | Kapatagan NHS | KAPATAGAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00105 | 15KG0024 | 2015-08-02 | 2015-08-03 | 2015-08-14 | 2015-08-24 | 2015-09-01 | LANAO BUILDER AND ENTERPRISES
14235 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127024 | Koreo Primary School | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00095 | 15KG0052 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-05 | AL-FAHDEL CONSTRUCTION & ENGINEERING
14236 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10927342.5917 |  |  | COMPLETED | 1 |  |  | 100115S00040 | 15KG0042 | 2015-08-12 | 2015-08-13 | 2015-08-24 | 2015-08-28 | 2015-09-07 | LANAO BUILDER AND ENTERPRISES
14237 | NC 2015 | TECHVOC (2015) | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2479549.27 |  |  | COMPLETED | 1 |  |  | 100115S00101 | 15KG0063 | 2015-10-27 | 2015-10-28 | 2015-11-09 | 2015-11-13 | 2015-11-23 | RARMAN CONSTRUCTION & TRADING
14238 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127151 | Lomidong ES | PANTAO RAGAT | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00087 | 15KG0045 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-05 | DCD BUILDERS & ENTERPISES
14239 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127103 | Magsaysay CS | MAGSAYSAY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00063 | 15KG0025 | 2015-08-02 | 2015-08-03 | 2015-08-14 | 2015-08-24 | 2015-09-01 | AMMAR CONSTRUCTION AND ENTERPRISES
14240 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 100115S00054 | 15KG0026 | 2015-08-02 | 2015-08-03 | 2015-08-14 | 2015-08-24 | 2015-09-01 | AMMAR CONSTRUCTION AND ENTERPRISES
14241 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127026 | Maguindanao ES | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00086 | 15KG0051 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-05 | TESAR BUILDERS
14242 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127203 | Masibay PS | NUNUNGAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | REVERTED | 0 |  |  | 100115S00084
14243 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304014 | Munai NHS | MUNAI | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100115S00046 | 15KG0012 | 2015-08-04 | 2015-08-05 | 2015-08-17 | 2015-08-24 | 2015-09-01 | AL-FAHDEL CONSTRUCTION & ENGINEERING
14244 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127137 | Nunang PS | POONA PIAGAPO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100115S00089 | 15KG0041 | 2015-08-05 | 2015-08-05 | 2015-09-03 | 2015-09-09 | 2015-09-17 | DCD BUILDERS & ENTERPISES
14245 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304016 | Nunungan NHS | NUNUNGAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | REVERTED | 0 |  |  | 100115S00053
14246 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127186 | Padianan ES | SALVADOR | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00097 | 15KG0044 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-05 | DCD BUILDERS & ENTERPISES
14247 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304017 | Panoloon NHS | SAPAD | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5286910.09 |  |  | COMPLETED | 1 |  |  | 100115S00047 | 15KG0014 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-31 | 2015-08-07 | D.C.M. CONSTRUCTION
14248 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 100115S00042 | 15KG0030 | 2015-08-02 | 2015-08-03 | 2015-08-14 | 2015-08-24 | 2015-09-01 | RCM CONSTRUCTION & SUPPLIES
14249 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127121 | Pendolonan ES | MUNAI | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00091 | 15KG0048 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-05 | AMMAR CONSTRUCTION AND ENTERPRISES
14250 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127031 | Pikalawag ES | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100115S00094 | 15KG0040 | 2015-08-05 | 2015-08-05 | 2015-09-03 | 2015-09-09 | 2015-09-17 | D.C.M. CONSTRUCTION
14251 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304006 | Placida Mequiabas Mem. NHS (Lapinig NHS) | KAPATAGAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100115S00104 | 15KG0029 | 2015-08-02 | 2015-08-03 | 2015-08-14 | 2015-08-24 | 2015-09-01 | LANAO BUILDER AND ENTERPRISES
14252 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 315104 | Poonapiagapo NHS(Annex Matungao NHS) | POONA PIAGAPO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100115S00041 | 15KG0011 | 2015-08-04 | 2015-08-05 | 2015-08-17 | 2015-08-24 | 2015-09-01 | TESAR BUILDERS
14253 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127033 | Ramain ES | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00071 | 15KG0050 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-05 | D.C.M. CONSTRUCTION
14254 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 127122 | Ramain ES | MUNAI | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00090 | 15KG0047 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-05 | AMMAR CONSTRUCTION AND ENTERPRISES
14255 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 304023 | Salvador NHS (Salvador Trade HS) | SALVADOR | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 100115S00045 | 15KG0031 | 2015-08-02 | 2015-08-03 | 2015-08-14 | 2015-08-24 | 2015-09-01 | AL-FAHDEL CONSTRUCTION & ENGINEERING
14256 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 315110 | SERGIO P. CERUJALES, JR. NHS | MAGSAYSAY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1 |  |  | 100115S00099 | 15KG0064 | 2015-10-29 | 2015-10-29 | 2015-11-09 | 2015-11-13 | 2015-11-23 | RARMAN CONSTRUCTION & TRADING
14257 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 200530 | Sugod Primary School | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100115S00083 | 15KG0054 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-05 | AL-FAHDEL CONSTRUCTION & ENGINEERING
14258 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 315101 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 100115S00043 | 15KG0022 | 2015-08-02 | 2015-08-03 | 2015-08-14 | 2015-08-24 | 2015-09-01 | D.C.M. CONSTRUCTION
14259 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 200516 | Talambo PS | MAGSAYSAY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100115S00064 | 15KG0017 | 2015-07-21 | 2015-07-22 | 2015-08-03 | 2015-08-07 | 2015-08-17 | AMMAR CONSTRUCTION AND ENTERPRISES
14260 | NC 2015 | SHS (2015) | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2830828.124 |  |  | COMPLETED | 1 |  |  | 100115S00044 | 15KG0013 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-31 | 2015-08-07 | JAMCON BUILDERS
14261 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 200545 | Taporog Primary School | MUNAI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 100115S00081
14262 | NC 2015 | K10 (2015) | Region X | Lanao del Norte | 200539 | TOPOCON PRIMARY SCHOOL | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 100115S00082
14263 | NC 2015 | K10 (2015) | Region X | Malaybalay City | 126574 | Airport Village ES | CITY MALAYBALAY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8289965.051 |  |  | COMPLETED | 1 |  |  | 100315S00189 | 15KA0083 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | Z & L CONSTRUCTION & SUPPLIES
14264 | NC 2015 | K10 (2015) | Region X | Malaybalay City | 325505 | Apo Macote NHS | CITY MALAYBALAY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 100315S00117 | 15KA0054 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | FFJJ CONSTRUCTION
14265 | NC 2015 | K10 (2015) | Region X | Malaybalay City | 126575 | Baganao ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 100315S00188 | 15KA0084 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | FIVE MASSIVE INFRA & SUPPLY CORP.
14266 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 303946 | Bangcud NHS | CITY MALAYBALAY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00083 | 15KA0035 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | J.T. GAMOLO CONSTRUCTION
14267 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 303946 | Bangcud NHS | CITY MALAYBALAY (Capital) | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00069 | 15KA0035 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | J.T. GAMOLO CONSTRUCTION
14268 | NC 2015 | TECHVOC (2015) | Region X | Malaybalay City | 303946 | Bangcud NHS | CITY MALAYBALAY (Capital) | 2 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  | 100315S00215 | 15KA0105 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | J.T. GAMOLO CONSTRUCTION
14269 | NC 2015 | K10 (2015) | Region X | Malaybalay City | 199510 | Barangay 9 ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 6015818.12 |  |  | REVERTED | 0 |  |  | 100315S00185 | 15KA0087 | 2015-11-12 | 2015-11-13 | 2015-11-26 |  |  | J.T. GAMOLO CONSTRUCTION
14270 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 303950 | Bukidnon NHS | CITY MALAYBALAY (Capital) | 2 | 1 | 32 | 3STY9CL | 2015 SHS BATCH 2 | 15246327.92 |  |  | COMPLETED | 1 |  |  | 100315S00055 | 15KA0036 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-10-21 | 2015-11-05 | FFJJ CONSTRUCTION
14271 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 303950 | Bukidnon NHS | CITY MALAYBALAY (Capital) | 2 |  | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 100315S00071 | 15KA0037 | 2015-09-03 | 2015-09-03 | 2015-09-22 | 2015-10-21 | 2015-11-05 | JORVIVS CONSTRUCTION
14272 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 303950 | Bukidnon NHS | CITY MALAYBALAY (Capital) | 2 |  | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 100315S00072 | 15KA0038 | 2015-08-31 | 2015-09-03 | 2015-09-22 | 2015-10-21 | 2015-11-05 | PETRINA CONSTRUCTION & GENERAL MERCHANDISING
14273 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 303950 | Bukidnon NHS | CITY MALAYBALAY (Capital) | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00073 | 15KA0039 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | J.T. GAMOLO CONSTRUCTION
14274 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 303950 | Bukidnon NHS | CITY MALAYBALAY (Capital) | 2 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 100315S00074 | 15KA0039 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | J.T. GAMOLO CONSTRUCTION
14275 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 314904 | Bukidnon NHS - Annex Aglayan | CITY MALAYBALAY (Capital) | 2 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 12886310 |  |  | COMPLETED | 1 |  |  | 100315S00150 | 15KA0140 | 2015-10-29 | 2015-10-30 | 2015-11-12 | 2015-11-27 | 2015-12-10 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
14276 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 314914 | Bukidnon NHS - Annex Casisang | CITY MALAYBALAY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6409338 |  |  | COMPLETED | 1 |  |  | 100315S00156 | 15Ka0065 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-21 | 2015-11-05 | MAMAWAG CONSTRUCTION
14277 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 325504 | Bukidnon NHS - Annex Dalwangan | CITY MALAYBALAY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8259965 |  |  | COMPLETED | 1 |  |  | 100315S00160 | 15KA0073 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-13 | A.R. & MARK BUILDERS
14278 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 325503 | Bukidnon NHS - Annex Imbayao | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2008606 |  |  | COMPLETED | 1 |  |  | 100315S00151 | 15KA0072 | 2015-11-12 | 2015-11-13 | 2015-11-26 | 2015-12-21 | 2015-12-23 | FIVE MASSIVE INFRA & SUPPLY CORP.
14279 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 314916 | Bukidnon NHS - Annex San Jose | CITY MALAYBALAY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8259965 |  |  | COMPLETED | 1 |  |  | 100315S00155 | 15KA0067 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-21 | 2015-11-05 | L & L CONSTRUCTION
14280 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 314915 | Bukidnon NHS - Extension Kalasungay | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1973606 |  |  | COMPLETED | 1 |  |  | 100315S00163 | 15KA0066 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-21 | 2015-11-05 | MAFIL BUILDERS, INC.
14281 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 500409 | Busdi IS | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2018606 |  |  | COMPLETED | 1 |  |  | 100315S00152 | 15KA0071 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-21 | 2015-11-05 | MAMAWAG CONSTRUCTION
14282 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 500245 | Can-ayan IS | CITY MALAYBALAY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6359338 |  |  | COMPLETED | 1 |  |  | 100315S00161 | 15KA0068 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-21 | 2015-11-05 | MAMAWAG CONSTRUCTION
14283 | NC 2015 | K10 (2015) | Region X | Malaybalay City | 126579 | Casisang CS | CITY MALAYBALAY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00187 | 15KA0085 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | MAFIL BUILDERS, INC.
14284 | NC 2015 | K10 (2015) | Region X | Malaybalay City | 126583 | Kapt. Angel ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 100315S00186 | 15KA0086 | 2015-11-12 | 2015-11-13 | 2015-11-26 | 2015-12-21 | 2015-12-23 | FIVE MASSIVE INFRA & SUPPLY CORP.
14285 | NC 2015 | K10 (2015) | Region X | Malaybalay City | 199518 | Kibalabag ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 100315S00184 | 15KA0088 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | FIVE MASSIVE INFRA & SUPPLY CORP.
14286 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 303973 | Managok National High School | CITY MALAYBALAY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 100315S00075 | 15KA0040 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | FFJJ CONSTRUCTION
14287 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 325501 | Managok NHS - Lalawan Annex | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1978606 |  |  | COMPLETED | 1 |  |  | 100315S00153 | 15KA0070 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-21 | 2015-11-05 | MAFIL BUILDERS, INC.
14288 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 314920 | Managok NHS - Miglamin Annex | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1978606 |  |  | COMPLETED | 1 |  |  | 100315S00154 | 15KA0069 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-21 | 2015-11-05 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
14289 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 303982 | San Martin Agro-Industrial NHS | CITY MALAYBALAY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 100315S00076 | 15KA0041 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | MAFIL BUILDERS, INC.
14290 | NC 2015 | SHS (2015) | Region X | Malaybalay City |  | SHS within Casisang CS | CITY MALAYBALAY (Capital) | 2 | 1 | 18 | 3STY9CL | 2015 SHS BATCH 5 | 35891596 |  |  | COMPLETED | 1 |  |  | 100315S00157 | 15KA0139 | 2015-11-22 | 2015-11-24 | 2015-12-08 | 2015-12-22 | 2015-12-29 | JORVIVS CONSTRUCTION
14291 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 303984 | Silae NHS | CITY MALAYBALAY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 100315S00077 | 15KA0042 | 2015-12-24
14292 | NC 2015 | SHS (2015) | Region X | Malaybalay City | 314905 | Silae NHS - Annex St. Peter | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2008606 |  |  | COMPLETED | 1 |  |  | 100315S00162 | 15KA0064 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-21 | 2015-11-05 | FIVE MASSIVE INFRA & SUPPLY CORP.
14293 | NC 2015 | K10 (2015) | Region X | Malaybalay City | 126556 | Zamboanguita CS | CITY MALAYBALAY (Capital) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2832592.44 |  |  | COMPLETED | 1 |  |  | 100315S00190 | 15KA0082 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | FIVE MASSIVE INFRA & SUPPLY CORP.
14294 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 100515S00028 | 15KI0021 | 2015-07-13 | 2015-07-16 | 2015-08-11 | 2015-09-07 | 2015-09-18 | GENETIAN BUILDERS
14295 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 315208 | Aquino IS | PLARIDEL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 100515S00050 | 15KI0050 | 2015-08-10 | 2015-08-13 | 2015-08-25 | 2015-11-09 | 2015-11-23 | DDS BUILDERS
14296 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304025 | Baliangao SOF | BALIANGAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 100515S00019 | 15KI0022 | 2015-07-13 | 2015-07-16 | 2015-08-11 | 2015-09-07 | 2015-09-18 | GENETIAN BUILDERS
14297 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304030 | Calamba CNHS | CALAMBA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10447131.51 |  |  | COMPLETED | 1 |  |  | 100515S00018 | 15KI0023 | 2015-07-13 | 2015-07-16 | 2015-10-08 | 2015-11-11 | 2015-11-23 | RIVER CONCRETE CONST. & DEVT. CORP.
14298 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 315203 | Carmen IS | JIMENEZ | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2028606.04 |  |  | COMPLETED | 1 |  |  | 100515S00040 | 15KI0036 | 2015-07-13 | 2015-07-16 | 2015-07-28 | 2015-08-14 | 2015-08-20 | EDMOND RAY CONSTRUCTION & SUPPLY
14299 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304033 | Concepcion NHS | CONCEPCION | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100515S00033 | 15KI0024 | 2015-07-13 | 2015-07-16 | 2015-08-25 | 2015-09-09 | 2015-09-21 | L.C. CONSTRUCTION
14300 | NC 2015 | K10 (2015) | Region X | Misamis Occidental | 304036 | Guinabut NHS | SAPANG DALAGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100515S00044 | 15KI0040 | 2015-07-13 | 2015-07-16 | 2015-08-11 | 2015-09-09 | 2015-09-21 | RAMONA CONSTRUCTION & ENTERPRISES
14301 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304037 | Jimenez NCHS | JIMENEZ | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100515S00017 | 15KI0025 | 2015-07-13 | 2015-07-16 | 2015-08-11 | 2015-09-07 | 2015-09-18 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
14302 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304040 | Looc NHS | PLARIDEL | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10437131.51 |  |  | COMPLETED | 1 |  |  | 100515S00032 | 15KI0026 | 2015-07-13 | 2015-07-16 | 2015-10-08 | 2015-11-11 | 2015-11-23 | RIVER CONCRETE CONST. & DEVT. CORP.
14303 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304043 | Macalibre Alto NHS | LOPEZ JAENA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 100515S00039 | 15KI0037 | 2015-07-13 | 2015-07-16 | 2015-07-28 | 2015-08-14 | 2015-08-20 | RRJ BUILDERS CONSTRUCTION AND GENERAL MERCHANDISE
14304 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304043 | Macalibre Alto NHS | LOPEZ JAENA | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 100515S00041 | 15KI0038 | 2015-07-12 | 2015-07-24 | 2015-07-25 | 2015-07-29 | 2015-08-02 | RRJ BUILDERS CONSTRUCTION AND GENERAL MERCHANDISE
14305 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304048 | Panaon NHS | PANAON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6349337.6381 |  |  | COMPLETED | 1 |  |  | 100515S00003 | 15KI0027 | 2015-07-13 | 2015-07-16 | 2015-08-11 | 2015-09-09 | 2015-09-21 | ANIMAS BROS CONSTRUCTION
14306 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304042 | Roque L. SU MNHS (Mabini NHS) | BALIANGAO | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3717968.78 |  |  | COMPLETED | 1 |  |  | 100515S00038 | 15KI0039 | 2015-07-13 | 2015-07-16 | 2015-07-28 | 2015-08-14 | 2015-08-20 | RIVER CONCRETE CONST. & DEVT. CORP.
14307 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304051 | Sapang Dalaga NHS | SAPANG DALAGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100515S00016 | 15KI0028 | 2015-07-13 | 2015-07-16 | 2015-08-11 | 2015-09-09 | 2015-09-21 | RAMONA CONSTRUCTION & ENTERPRISES
14308 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 315207 | Sibugon IS | LOPEZ JAENA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100515S00029 | 15KI0029 | 2015-07-13 | 2015-07-16 | 2015-08-11 | 2015-09-07 | 2015-09-18 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
14309 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 315210 | Tabo-o IS | JIMENEZ | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100515S00014 | 15KI0030 | 2015-07-13 | 2015-07-16 | 2015-07-28 | 2015-08-14 | 2015-08-20 | EDMOND RAY CONSTRUCTION & SUPPLY
14310 | NC 2015 | K10 (2015) | Region X | Misamis Occidental | 315206 | Tagwanao IS | ALORAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2183406 |  |  | COMPLETED | 1 |  |  | 100515S00068 | 15KI0049 | 2015-08-17 | 2015-09-24 | 2015-11-24
14311 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304028 | Bonifacio NHS | BONIFACIO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 100515S00013 | 15KJ0059 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | GENETIAN BUILDERS
14312 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304031 | Clarin NHS | CLARIN | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15151327.92 |  |  | COMPLETED | 1 |  |  | 100515S00031 | 15KJ0051 | 2015-07-10 | 2015-07-31 | 2015-09-15 | 2015-09-28 | 2015-10-09 | GENETIAN BUILDERS
14313 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304039 | Colambutan Bajo NHS | TUDELA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 100515S00037 | 15KJ0071 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | HSO CONSTRUCTION CORPORATION (FOREMERLY : HENRY S.
14314 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304039 | Colambutan Bajo NHS | TUDELA | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 100515S00042 | 15KJ0072 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | HSO CONSTRUCTION CORPORATION (FOREMERLY : HENRY S.
14315 | NC 2015 | K10 (2015) | Region X | Misamis Occidental | 127541 | Colupan Alto ES | SINACABAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 100515S00067 | 15KJ0084 | 2015-10-09 | 2015-10-26 | 2015-10-28 | 2015-11-06 | 2015-11-19 | VICTORIANO C. LIM CONSTRUCTION
14316 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304034 | Diwat NHS | BONIFACIO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9014965.051 |  |  | COMPLETED | 1 |  |  | 100515S00012 | 15KJ0055 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | GENETIAN BUILDERS
14317 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304035 | Don Victoriano NHS | DON VICTORIANO CHIONGBIAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8494965.051 |  |  | COMPLETED | 1 |  |  | 100515S00011 | 15KJ0056 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | GENETIAN BUILDERS
14318 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 315204 | Ignacio Tan MIS | BONIFACIO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 7106838 |  |  | COMPLETED | 1 |  |  | 100515S00051 | 15KJ0146 | 2015-11-27
14319 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304038 | Katipunan NHS | SINACABAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6609337.6381 |  |  | COMPLETED | 1 |  |  | 100515S00034 | 15KJ0067 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | L.C. CONSTRUCTION
14320 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304038 | Katipunan NHS | SINACABAN | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100515S00036 | 15KJ0070 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-20 | 2015-08-25 | L.C. CONSTRUCTION
14321 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304046 | Nueva Vista National High School | DON VICTORIANO CHIONGBIAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2358606.04 |  |  | COMPLETED | 1 |  |  | 100515S00043 | 15KJ0069 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | GENETIAN BUILDERS
14322 | NC 2015 | K10 (2015) | Region X | Misamis Occidental | 127311 | Remedios ES | BONIFACIO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100515S00045 | 15KJ0074 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | GENETIAN BUILDERS
14323 | NC 2015 | K10 (2015) | Region X | Misamis Occidental | 127577 | Sebac PS | TUDELA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100515S00061 | 15KJ0086 | 2015-10-09 | 2015-10-26 | 2015-10-28 | 2015-11-16 | 2015-11-19 | EDMOND RAY CONSTRUCTION & SUPPLY
14324 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304055 | Sinonoc NHS | SINACABAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100515S00010 | 15KJ0063 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | L.C. CONSTRUCTION
14325 | NC 2015 | SHS (2015) | Region X | Misamis Occidental | 304058 | Tudela National Comprehensive High School | TUDELA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10597131.51 |  |  | COMPLETED | 1 |  |  | 100515S00030 | 15KJ0053 | 2015-07-10 | 2015-07-31 | 2015-09-15 | 2015-09-28 | 2015-10-09 | GENETIAN BUILDERS
14326 | NC 2015 | K10 (2015) | Region X | Misamis Occidental | 127314 | Upper Montol ES | BONIFACIO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 100515S00046 | 15KJ0075 | 2015-07-10 | 2015-07-31 | 2015-08-04 | 2015-08-14 | 2015-08-25 | C. DY BUILDERS AND GENERAL MERCHANDISE (FORMERLY CD
14327 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127715 | Ampianga ES | SUGBONGCOGON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1950606.04 |  |  | COMPLETED | 1 |  |  | 100615S00074 | 15kk0081 | 2015-11-11 | 2015-11-23 | 2015-11-24 | 2015-11-29 | 2015-12-03 | CAGALAWAN ENTERPRISES
14328 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304061 | Baliwagan NHS | BALINGASAG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8384965.051 |  |  | COMPLETED | 1 |  |  | 100615S00028 | 15KK0029 | 2015-06-16 | 2015-06-28 | 2015-06-29 | 2015-07-03 | 2015-07-07 | C. DY BUILDERS AND GENERAL MERCHANDISE (FORMERLY CD
14329 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127716 | Binuangan CS | BINUANGAN | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100615S00047 | 15kk0050 | 2015-07-31 | 2015-08-12 | 2015-08-13 | 2015-08-17 | 2015-08-21 | AMMAR CONSTRUCTION AND ENTERPRISES
14330 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304062 | Binuangan NHS | BINUANGAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6468087.6381 |  |  | COMPLETED | 1 |  |  | 100615S00041 | 15kk0048 | 2015-07-31 | 2015-08-12 | 2015-08-13 | 2015-08-17 | 2015-08-21 | AMMAR CONSTRUCTION AND ENTERPRISES
14331 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127876 | Bugdang ES | TALISAYAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100615S00106
14332 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127741 | C. Gadrinab ES | LAGONGLONG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 100615S00102 | 15KK0085 | 2015-09-15 | 2015-09-27 | 2015-09-28 | 2015-10-02 | 2015-10-06 | C & R CONSTRUCTION AND SUPPLY
14333 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 500253 | Calubo IS | KINOGUITAN | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8239965 |  |  | COMPLETED | 1 |  |  | 100615S00116 | 15KK0101 | 2015-09-22 | 2015-10-04 | 2015-10-05 | 2015-10-09 | 2015-10-13 | D.O.T. CONSTRUCTION
14334 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 500253 | Calubo IS | KINOGUITAN | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 100615S00109 | 15KK0102 | 2015-09-22 | 2015-10-04 | 2015-10-05 | 2015-10-09 | 2015-10-13 | D.O.T. CONSTRUCTION
14335 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127721 | Campo ES | KINOGUITAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2958842.44 |  |  | COMPLETED | 1 |  |  | 100615S00107 | 15KK0087 | 2015-09-15 | 2015-09-27 | 2015-09-28 | 2015-10-02 | 2015-10-06 | R.C. TAGALA CONSTRUCTION
14336 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127877 | Carmen ES | TALISAYAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1959606.04 |  |  | COMPLETED | 1 |  |  | 100615S00085
14337 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304066 | Consuelo NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8226965 |  |  | COMPLETED | 1 |  |  | 100615S00064 | 15KK0075 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-28 | 2015-10-02 | WDM CONSTRUCTION AND SUPPLIES
14338 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304070 | Esperanza NHS | KINOGUITAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8289965.051 |  |  | COMPLETED | 1 |  |  | 100615S00025 | 15KK0030 | 2015-06-16 | 2015-06-28 | 2015-06-29 | 2015-07-03 | 2015-07-07 | L & L CONSTRUCTION
14339 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304076 | Kibungsod NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 2 | 5377651.88 |  |  | COMPLETED | 1 |  |  | 100615S00037 | 15KK0055 | 2015-08-21 | 2015-09-02 | 2015-09-03 | 2015-09-07 | 2015-09-11 | WDM CONSTRUCTION AND SUPPLIES
14340 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304076 | Kibungsod NHS | MAGSAYSAY (LINUGOS) | 1 |  | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 2 | 5322651.88 |  |  | COMPLETED | 1 |  |  | 100615S00040 | 15KK0056 | 2015-08-21 | 2015-09-02 | 2015-09-03 | 2015-09-07 | 2015-09-11 | WDM CONSTRUCTION AND SUPPLIES
14341 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127725 | Kidampas IS | SUGBONGCOGON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 100615S00100 | 15KK0082 | 2015-09-15 | 2015-09-27 | 2015-09-28 | 2015-10-02 | 2015-10-06 | R.C. TAGALA CONSTRUCTION
14342 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 315321 | Kidampas IS | SUGBONGCOGON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1963606 |  |  | COMPLETED | 1 |  |  | 100615S00110 | 15KK0099 | 2015-11-25 | 2015-12-07 | 2015-12-08 | 2015-12-12 | 2015-12-16 | CAGALAWAN ENTERPRISES
14343 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 315321 | Kidampas IS | SUGBONGCOGON | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 100615S00111 | 15KK0100 | 2015-11-25 | 2015-12-07 | 2015-12-08 | 2015-12-12 | 2015-12-16 | CAGALAWAN ENTERPRISES
14344 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304077 | Kinoguitan Nat. Agr'l. HS | KINOGUITAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2001606.04 |  |  | COMPLETED | 1 |  |  | 100615S00042 | 15KK0057 | 2015-09-08 | 2015-09-20 | 2015-09-21 | 2015-09-25 | 2015-09-29 | ALEBON GENUINE MERCHANDISING INCORPORATED
14345 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127820 | Labas-Pagsama ES | MEDINA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2213606.04 |  |  | COMPLETED | 1 |  |  | 100615S00104 | 15KK0086 | 2015-12-01 | 2015-12-13 | 2015-12-14 | 2015-12-18 | 2015-12-22 | L & L CONSTRUCTION
14346 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127617 | Lantad ES | BALINGASAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 100615S00097
14347 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304080 | Looc NHS | SALAY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2723606 |  |  | COMPLETED | 1 |  |  | 100615S00069 | 15KK0071 | 2015-11-20 | 2015-12-02 | 2015-12-03 | 2015-12-07 | 2015-12-11 | L & L CONSTRUCTION
14348 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 315304 | Lumbo NHS | LAGONGLONG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8234965 |  |  | COMPLETED | 1 |  |  | 100615S00062 | 15KK0074 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-28 | 2015-10-02 | D.O.T. CONSTRUCTION
14349 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127749 | Manaol ES | LAGONGLONG | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00103 | 15KK0096 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | CAGALAWAN ENTERPRISES
14350 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8456215.051 |  |  | COMPLETED | 1 |  |  | 100615S00033 | 15KK0031 | 2015-06-16 | 2015-06-28 | 2015-06-29 | 2015-07-03 | 2015-07-07 | L & L CONSTRUCTION
14351 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127858 | Mimbuli ES | SALAY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100615S00105 | 15KK0088 | 2015-09-15 | 2015-09-27 | 2015-09-28 | 2015-10-02 | 2015-10-06 | R.C. TAGALA CONSTRUCTION
14352 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127734 | Nabataan PS | BINUANGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100615S00093 | 15kk0089 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | CAGALAWAN ENTERPRISES
14353 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304095 | Portulin NHS | MEDINA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00123 | 15KK0109 | 2015-10-30 | 2015-11-11 | 2015-11-12 | 2015-11-16 | 2015-11-20 | CAGALAWAN ENTERPRISES
14354 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 315306 | Rosario NHS | BALINGASAG | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6605963 |  |  | COMPLETED | 1 |  |  | 100615S00061 | 15KK0072 | 2015-10-21 | 2015-11-02 | 2015-11-03 | 2015-11-07 | 2015-11-11 | ALEBON GENUINE MERCHANDISING INCORPORATED
14355 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304096 | Salay NHS | SALAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 100615S00032 | 15KK0032 | 2015-06-16 | 2015-06-28 | 2015-06-29 | 2015-07-03 | 2015-07-07 | RYM CONSTRUCTION
14356 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127625 | Samay ES | BALINGASAG | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00078 | 15kk0097 | 2015-11-20 | 2015-12-02 | 2015-12-03 | 2015-12-07 | 2015-12-11 | LEGACY CONSTRUCTION
14357 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304097 | San Isidro NHS | BALINGASAG | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6911338 |  |  | COMPLETED | 1 |  |  | 100615S00063 | 15KK0073 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-10-31 | 2015-11-04 | ALEBON GENUINE MERCHANDISING INCORPORATED
14358 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304098 | San Juan NHS | BALINGASAG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100615S00031 | 15KK0033 | 2015-07-21 | 2015-08-02 | 2015-08-03 | 2015-08-07 | 2015-08-11 | R.C. TAGALA CONSTRUCTION
14359 | NC 2015 | SHS (2015) | Region X | Misamis Oriental |  | SHS within Kinoguitian CES | KINOGUITAN | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 100615S00119 | 15KK0105 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | R. DE MESA CONSTRUCTION
14360 | NC 2015 | SHS (2015) | Region X | Misamis Oriental |  | SHS within Lagonglong CS | LAGONGLONG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100615S00118 | 15KK0106 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | JIMWEN CONSTRUCTION & GENERAL MERCHANDISE
14361 | NC 2015 | SHS (2015) | Region X | Misamis Oriental |  | SHS within Mambayaag ES | BALINGASAG | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00124 | 15KK0107 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | GRAND BUILDERS
14362 | NC 2015 | SHS (2015) | Region X | Misamis Oriental |  | SHS within Mantangale ES | BALINGOAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00121 | 15KK0108 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | BRIMA CONSTRUCTION AND ENTERPRISES
14363 | NC 2015 | SHS (2015) | Region X | Misamis Oriental |  | SHS within Sta. Ines ES | TALISAYAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00122 | 15KK0110 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-18 | 2015-10-23 | CAGALAWAN ENTERPRISES
14364 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127895 | Sindangan ES | TALISAYAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2068606.04 |  |  | COMPLETED | 1 |  |  | 100615S00083
14365 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304101 | Sugbongcogon NHS | SUGBONGCOGON | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10507132 |  |  | COMPLETED | 1 |  |  | 100615S00058 | 15KK0118 | 2015-10-30 | 2015-11-11 | 2015-11-12 | 2015-11-16 | 2015-11-20 | PUREGOLD CONSTRUCTION & DEVT. CORP.
14366 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304093 | Talisayan NHS | TALISAYAN | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 100615S00125 | 15KK0119 | 2015-10-30 | 2015-11-11 | 2015-11-12 | 2015-11-16 | 2015-11-20 | DICON BUILDERS CORP.
14367 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127632 | Waterfall ES | BALINGASAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1985606.04 |  |  | COMPLETED | 1 |  |  | 100615S00098 | 15KK0084 | 2015-11-25 | 2015-12-07 | 2015-12-08 | 2015-12-12 | 2015-12-16 | L & L CONSTRUCTION
14368 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304059 | Alubijid NCHS | ALUBIJID | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 100615S00067 | 15KL0071 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-14 | 2015-10-28 | C. DY BUILDERS AND GENERAL MERCHANDISE (FORMERLY CD
14369 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127699 | Aplaya ES | JASAAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00045 | 15KL0041 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-08-07 | 2015-08-13 | LAJ TRUCKING AND BUILDERS
14370 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 315309 | Aposkahoy NHS | CLAVERIA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2032356 |  |  | COMPLETED | 1 |  |  | 100615S00070 | 15KL0073 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-14 | 2015-10-28 | DCD BUILDERS & ENTERPISES
14371 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 315301 | Bagocboc NHS | OPOL | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2032356 |  |  | COMPLETED | 1 |  |  | 100615S00072 | 15KL0075 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-14 | 2015-10-28 | LAJ TRUCKING AND BUILDERS
14372 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127835 | Barra ES | OPOL | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100615S00086 | 15KL0085 | 2015-08-11 | 2015-08-22 | 2015-08-25 | 2015-09-01 | 2015-09-16 | ALEBON GENUINE MERCHANDISING INCORPORATED
14373 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 304063 | Bobuntugan NHS | JASAAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 100615S00112 | 15KL0087 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-21 | 2015-11-06 | LAJ TRUCKING AND BUILDERS
14374 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304064 | Cabalantian NHS | MANTICAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 100615S00060 | 15KL0072 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-14 | 2015-10-28 | LANAO BUILDER AND ENTERPRISES
14375 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127684 | Casilihon ES | INITAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100615S00082 | 15KL0083 | 2015-08-18 | 2015-08-12 | 2015-08-24 | 2015-12-30 |  | By Administration
14376 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 315310 | Casinglot NHS | TAGOLOAN | 2 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 7 | 13183810 |  |  | COMPLETED | 1 |  |  | 100615S00114 | 15KL0061 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-21 | 2015-11-06 | GENETIAN BUILDERS
14377 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127702 | Danao ES | JASAAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100615S00092 | 15KL0086 | 2015-08-11 | 2015-08-22 | 2015-08-25 | 2015-09-01 | 2015-09-16 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
14378 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 315302 | Danao NHS | JASAAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6469338 |  |  | COMPLETED | 1 |  |  | 100615S00066 | 15KL0065 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-14 | 2015-10-28 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
14379 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304069 | Dr. Gerardo Sabal Memorial NHS | CLAVERIA | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5293160.09 |  |  | COMPLETED | 1 |  |  | 100615S00035 | 15KL0038 | 2015-07-06 | 2015-07-18 | 2015-07-21 | 2015-07-25 | 2015-07-31 | ALEBON GENUINE MERCHANDISING INCORPORATED
14380 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127867 | Gracia ES | TAGOLOAN | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4572048.49 |  |  | COMPLETED | 1 |  |  | 100615S00087 | 15KL0076 | 2015-08-11 | 2015-08-22 | 2015-08-25 | 2015-09-01 | 2015-09-16 | ALEBON GENUINE MERCHANDISING INCORPORATED
14381 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304071 | Hinaplanan NHS | CLAVERIA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 100615S00059 | 15KL0067 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-14 | 2015-10-28 | FFJJ CONSTRUCTION
14382 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127643 | Impadiding ES | CLAVERIA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | REVERTED | 0 |  |  | 100615S00099 | 15KL0068
14383 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304072 | Initao NCHS | INITAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 100615S00030 | 15KL0032 | 2015-06-22 | 2015-07-04 | 2015-07-06 | 2015-07-10 | 2015-07-14 | FOOTPRINTS CONSTRUCTION
14384 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304073 | Jasaan NHS | JASAAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | COMPLETED | 1 |  |  | 100615S00055 | 15KL0064 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-14 | 2015-10-28 | FFJJ CONSTRUCTION
14385 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 315317 | Kalacapan NHS | INITAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 100615S00071 | 15KL0084 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-14 | 2015-10-28 | JDE CONSTRUCTION
14386 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304074 | Kalingagan NHS | VILLANUEVA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8335590.051 |  |  | COMPLETED | 1 |  |  | 100615S00029 | 15KL0028 | 2015-06-22 | 2015-07-04 | 2015-07-06 | 2015-07-10 | 2015-07-14 | L & L CONSTRUCTION
14387 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304078 | Laguindingan NHS | LAGUINDINGAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 100615S00034 | 15KL0029 | 2015-06-22 | 2015-07-04 | 2015-07-06 | 2015-07-10 | 2015-07-14 | FOOTPRINTS CONSTRUCTION
14388 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 500251 | Lantad IS | ALUBIJID | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 100615S00108
14389 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304079 | Libertad NHS | LIBERTAD | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100615S00036 | 15KL0031 | 2015-06-22 | 2015-07-04 | 2015-07-06 | 2015-07-10 | 2015-07-14 | JDE CONSTRUCTION
14390 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127648 | Linandang ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100615S00079 | 15KL0081 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-09-23 | 2015-10-12 | DCD BUILDERS & ENTERPISES
14391 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 201503 | Lonsi ES | ALUBIJID | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1973606.04 |  |  | COMPLETED | 1 |  |  | 100615S00091 | 15KL0082 | 2015-08-11 | 2015-08-22 | 2015-08-25 | 2015-09-01 | 2015-09-16 | ALEBON GENUINE MERCHANDISING INCORPORATED
14392 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304081 | Lourdes Alubijid NHS | ALUBIJID | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 100615S00057 | 15KL0070 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-14 | 2015-10-28 | JDE CONSTRUCTION
14393 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127802 | Magpait ES | MANTICAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100615S00077 | 15KL0090 | 2015-08-11 | 2015-08-22 | 2015-08-25 | 2015-09-01 | 2015-09-16 | BRIMA CONSTRUCTION AND ENTERPRISES
14394 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304083 | Malagana NHS | CLAVERIA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6413088 |  |  | COMPLETED | 1 |  |  | 100615S00068 | 15KL0063 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-14 | 2015-10-28 | DCD BUILDERS & ENTERPISES
14395 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 315307 | Manticao NHS | MANTICAO | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5166910.09 |  |  | COMPLETED | 1 |  |  | 100615S00026 | 15KL0033 | 2015-06-22 | 2015-07-04 | 2015-07-06 | 2015-07-10 | 2015-07-14 | ALEBON GENUINE MERCHANDISING INCORPORATED
14396 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304086 | Matangad NHS | GITAGUM | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 100615S00027 | 15KL0030 | 2015-06-22 | 2015-07-04 | 2015-07-06 | 2015-07-10 | 2015-07-14 | DICON BUILDERS CORP.
14397 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304087 | Mat-I NHS (Claveria) | CLAVERIA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 100615S00039 | 15KL0040 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-08-07 | 2015-08-13 | FFJJ CONSTRUCTION
14398 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304088 | Mat-I NHS (Naawan) | NAAWAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 100615S00056 | 15KL0089 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-14 | 2015-10-28 | ALEBON GENUINE MERCHANDISING INCORPORATED
14399 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304091 | Mis. Or. Gen. CHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | REVERTED | 0 |  |  | 100815S00016 | 15KD0013 | [5 empty] | JEJORs CONSTRUCTION CORPORATION
14400 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 315303 | Naawan NHS | NAAWAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2933842 |  |  | COMPLETED | 1 |  |  | 100615S00113 | 15KL0078 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-21 | 2015-11-06 | ALEBON GENUINE MERCHANDISING INCORPORATED
14401 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127869 | Natumolan ES | TAGOLOAN | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4572048.49 |  |  | COMPLETED | 1 |  |  | 100615S00088 | 15KL0077 | 2015-08-11 | 2015-08-22 | 2015-08-25 | 2015-09-01 | 2015-09-16 | AL-FAHDEL CONSTRUCTION & ENGINEERING
14402 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304094 | Opol NSTS | OPOL | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 100615S00038 | 15KL0039 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-08-07 | 2015-08-13 | L & L CONSTRUCTION
14403 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127936 | Pasagdihon ES | NAAWAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100615S00090 | 15KL0088 | 2015-08-11 | 2015-08-22 | 2015-08-25 | 2015-09-01 | 2015-09-16 | BRIMA CONSTRUCTION AND ENTERPRISES
14404 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127660 | Patrocinio ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100615S00080 | 15KL0080 | 2015-08-11 | 2015-08-22 | 2015-08-25 | 2015-09-01 | 2015-09-16 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
14405 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127661 | Plaridel ES | CLAVERIA | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100615S00046 | 15KL0045 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-08-07 | 2015-08-13 | DICON BUILDERS CORP.
14406 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 500252 | Sampatulog IS | ALUBIJID | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2088606 |  |  | COMPLETED | 1 |  |  | 100615S00115 | 15KL0074 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-21 | 2015-11-06 | RAMONA CONSTRUCTION & ENTERPRISES
14407 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127710 | San Antonio ES | JASAAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00044 | 15KL0042 | 2015-07-10 | 2015-07-22 | 2015-08-19 | 2015-09-03 | 2015-09-14 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
14408 | NC 2015 | SHS (2015) | Region X | Misamis Oriental |  | SHS within Maputi ES | NAAWAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100615S00120 | 15KL0091 | 2015-08-19 | 2015-08-14 | 2015-08-26 | 2015-09-22 | 2015-10-12 | C ZARLES CONSTRUCTION & SUPPLY
14409 | NC 2015 | SHS (2015) | Region X | Misamis Oriental |  | SHS within Tagoloan CS | TAGOLOAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00117 | 15KL0092 | 2015-08-19 | 2015-08-14 | 2015-08-27 | 2015-11-20 | 2015-11-27 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
14410 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 304099 | Sta Ana NHS | TAGOLOAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8519965.051 |  |  | COMPLETED | 1 |  |  | 109715S00024 | 15KL0027 | 2015-06-22 | 2015-07-04 | 2015-07-06 | 2015-07-10 | 2015-08-24 | L & L CONSTRUCTION
14411 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127873 | Tagoloan CS | TAGOLOAN | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 6 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 100615S00089 | 15KL0062 | 2015-08-11 | 2015-08-22 | 2015-09-14 | 2015-09-23 | 2015-09-30 | C. DY BUILDERS AND GENERAL MERCHANDISE (FORMERLY CD
14412 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127665 | Tamboboan ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100615S00081 | 15KL0079 | 2015-08-11 | 2015-08-22 | 2015-08-25 | 2015-09-01 | 2015-09-16 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
14413 | NC 2015 | SHS (2015) | Region X | Misamis Oriental | 315315 | Tambobong-Balacanas NHS | VILLANUEVA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6399338 |  |  | COMPLETED | 1 |  |  | 100615S00065 | 15KL0066 | 2015-08-17 | 2015-08-12 | 2015-08-24 | 2015-10-14 | 2015-10-28 | HMG PRIME BUILDERS DEVELOPMENT CORPORATION
14414 | NC 2015 | K10 (2015) | Region X | Misamis Oriental | 127768 | Taytayan ES | LIBERTAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100615S00084 | 15KL0069 | 2015-08-11 | 2015-08-22 | 2015-08-25 | 2015-09-01 | 2015-09-16 | RAMONA CONSTRUCTION & ENTERPRISES
14415 | NC 2015 | SHS (2015) | Region X | Oroquieta City | 304029 | Bunga NHS | OROQUIETA CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | COMPLETED | 1 |  |  | 100515S00052 | 15KI0048 | 2015-08-10 | 2015-08-13 | 2015-08-25 | 2015-11-09 | 2015-11-23 | GENETIAN BUILDERS
14416 | NC 2015 | K10 (2015) | Region X | Oroquieta City | 127454 | Ciriaco Pastrano Memorial ES | OROQUIETA CITY (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100515S00049 | 15KI0041 | 2015-07-13 | 2015-07-16 | 2015-07-28 | 2015-08-14 | 2015-08-20 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE
14417 | NC 2015 | SHS (2015) | Region X | Oroquieta City | 304044 | Mis. Occ Sci. & Tech HS (Pines NHS) | OROQUIETA CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 100515S00009 | 15KI0031 | 2015-07-13 | 2015-07-16 | 2015-08-11 | 2015-09-07 | 2015-09-18 | GENETIAN BUILDERS
14418 | NC 2015 | SHS (2015) | Region X | Oroquieta City | 304045 | Misamis Occidental NHS | OROQUIETA CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15107518.84 |  |  | COMPLETED | 1 |  |  | 100515S00007 | 15KI0032 | 2015-07-13 | 2015-07-16 | 2015-10-08 | 2015-11-11 | 2015-11-23 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
14419 | NC 2015 | SHS (2015) | Region X | Oroquieta City | 500401 | Mobod IS | OROQUIETA CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8439965.051 |  |  | COMPLETED | 1 |  |  | 100515S00005 | 15KI0033 | 2015-07-13 | 2015-08-20 | 2015-09-03 | 2015-09-09 | 2015-09-21 | GENETIAN BUILDERS
14420 | NC 2015 | K10 (2015) | Region X | Oroquieta City | 323204 | Sebucal Integrated School | OROQUIETA CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | REVERTED | 0 |  |  | 100515S00069 | 15KI0047
14421 | NC 2015 | SHS (2015) | Region X | Oroquieta City | 304052 | Senote NHS | OROQUIETA CITY (Capital) | 1 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3724886.575 |  |  | COMPLETED | 1 |  |  | 100515S00004 | 15KI0034 | 2015-07-13 | 2015-07-16 | 2015-07-28 | 2015-08-24 | 2015-09-04 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE
14422 | NC 2015 | SHS (2015) | Region X | Oroquieta City | 304057 | Talairon NHS | OROQUIETA CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 |  |  | 100515S00015 | 15KI0035 | 2015-07-13 | 2015-07-16 | 2015-08-11 | 2015-09-07 | 2015-09-18 | GENETIAN BUILDERS
14423 | NC 2015 | K10 (2015) | Region X | Oroquieta City | 127459 | Tuyabang Alto ES | OROQUIETA CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2041606.04 |  |  | COMPLETED | 1 |  |  | 100515S00062 | 15KI0051 | 2015-08-10 | 2015-08-13 | 2015-09-24 | 2015-10-14 | 2015-11-11 | 3Rs BUILDERS AND RESOURCES
14424 | NC 2015 | K10 (2015) | Region X | Oroquieta City | 127460 | Tuyabang Bajo ES | OROQUIETA CITY (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100515S00048 | 15KI0042 | 2015-07-13 | 2015-07-16 | 2015-07-28 | 2015-08-14 | 2015-08-20 | DDS BUILDERS
14425 | NC 2015 | K10 (2015) | Region X | Oroquieta City | 127462 | Upper Lamac ES | OROQUIETA CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100515S00063 | 15KI0052 | 2015-08-10 | 2015-08-13 | 2015-08-25 | 2015-09-15 | 2015-09-28 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE
14426 | NC 2015 | K10 (2015) | Region X | Ozamis City | 128173 | Antero D. Hinagdanan ES | OZAMIS CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100515S00064 | 15KJ0085 | 2015-10-09 | 2015-10-26 | 2015-10-28 | 2015-11-06 | 2015-11-19 | 3Rs BUILDERS AND RESOURCES
14427 | NC 2015 | K10 (2015) | Region X | Ozamis City | 128196 | Gregorio A. Saquin ES | OZAMIS CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1 |  |  | 100515S00066 | 15KJ0083 | 2015-10-09 | 2015-10-26 | 2015-10-28 | 2015-11-06 | 2015-11-19 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
14428 | NC 2015 | SHS (2015) | Region X | Ozamis City | 315701 | Kinuman Norte National High School | OZAMIS CITY | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2740828.124 |  |  | COMPLETED | 1 |  |  | 100515S00020 | 15KJ0065 | 2015-07-10 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-08-25 | GENETIAN BUILDERS
14429 | NC 2015 | SHS (2015) | Region X | Ozamis City | 304161 | Labinay NHS | OZAMIS CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6469338 |  |  | COMPLETED | 1 |  |  | 100515S00053 | 15KJ0138 | 2015-11-27
14430 | NC 2015 | SHS (2015) | Region X | Ozamis City | 304163 | Labo NHS | OZAMIS CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 100515S00021 | 15KJ0061 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | HSO CONSTRUCTION CORPORATION (FOREMERLY : HENRY S.
14431 | NC 2015 | SHS (2015) | Region X | Ozamis City | 304166 | Montol NHS | OZAMIS CITY | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 4364886.575 |  |  | COMPLETED | 1 |  |  | 100515S00022 | 15KJ0064 | 2015-07-10 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-08-25 | C. DY BUILDERS AND GENERAL MERCHANDISE (FORMERLY CD
14432 | NC 2015 | SHS (2015) | Region X | Ozamis City | 304167 | Ozamiz City NHS | OZAMIS CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 100515S00023 | 15KJ0054 | 2015-07-10 | 2015-08-14 | 2015-09-15 | 2015-09-28 | 2015-10-09 | L.C. CONSTRUCTION
14433 | NC 2015 | SHS (2015) | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8384965.051 |  |  | COMPLETED | 1 |  |  | 100515S00024 | 15KJ0058 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | RAMONA CONSTRUCTION & ENTERPRISES
14434 | NC 2015 | TECHVOC (2015) | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2599549.27 |  |  | COMPLETED | 1 |  |  | 100515S00070 | 15KJ0087 | 2015-10-09 | 2015-10-26 | 2015-10-28 | 2015-11-06 | 2015-11-26 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
14435 | NC 2015 | SHS (2015) | Region X | Ozamis City | 304169 | Pulot NHS | OZAMIS CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100515S00035 | 15KJ0068 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | HSO CONSTRUCTION CORPORATION (FOREMERLY : HENRY S.
14436 | NC 2015 | K10 (2015) | Region X | Ozamis City | 128175 | San Antonio ES | OZAMIS CITY | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4672048.49 |  |  | COMPLETED | 1 |  |  | 100515S00065 | 15KJ0082 | 2015-10-09 | 2015-10-26 | 2015-10-28 | 2015-11-06 | 2015-11-19 | ANGEL & SAM CONSTRUCTION & GEN. MDSE.
14437 | NC 2015 | SHS (2015) | Region X | Ozamis City | 304165 | San Antonio NHS | OZAMIS CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6619338 |  |  | COMPLETED | 1 |  |  | 100515S00054 | 15KJ0139 | 2015-11-27
14438 | NC 2015 | SHS (2015) | Region X | Ozamis City | 304162 | Tabid NHS | OZAMIS CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 100515S00025 | 15KJ0060 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | RAMONA CONSTRUCTION & ENTERPRISES
14439 | NC 2015 | SHS (2015) | Region X | Tangub City | 304026 | Banglay NHS | TANGUB CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6324338 |  |  | COMPLETED | 1 |  |  | 100515S00055 | 15KJ0142 | 2015-11-27
14440 | NC 2015 | SHS (2015) | Region X | Tangub City | 304027 | Bongabong NHS | TANGUB CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2023606 |  |  | COMPLETED | 1 |  |  | 100515S00056 | 15KJ0145 | 2015-11-27
14441 | NC 2015 | SHS (2015) | Region X | Tangub City | 304054 | Caniangan NHS | TANGUB CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1947606 |  |  | COMPLETED | 1 |  |  | 100515S00058 | 15KJ0144 | 2015-11-27
14442 | NC 2015 | SHS (2015) | Region X | Tangub City | 304041 | Lorenzo Tan NHS | TANGUB CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100515S00026 | 15KJ0062 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | L.C. CONSTRUCTION
14443 | NC 2015 | K10 (2015) | Region X | Tangub City | 323303 | Maquilao Integrated School | TANGUB CITY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100515S00047 | 15KJ0073 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-20 | 2015-08-25 | GENETIAN BUILDERS
14444 | NC 2015 | SHS (2015) | Region X | Tangub City | 323303 | Maquilao Integrated School | TANGUB CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6414338 |  |  | COMPLETED | 1 |  |  | 100515S00060 | 15KJ0140 | 2015-11-27
14445 | NC 2015 | SHS (2015) | Region X | Tangub City | 304050 | Santa Maria NHS | TANGUB CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10597131.51 |  |  | COMPLETED | 1 |  |  | 100515S00027 | 15KJ0052 | 2015-07-10 | 2015-07-31 | 2015-09-15 | 2015-09-28 | 2015-10-09 | HSO CONSTRUCTION CORPORATION (FOREMERLY : HENRY S.
14446 | NC 2015 | SHS (2015) | Region X | Tangub City | 304053 | Silangit NHS | TANGUB CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6324338 |  |  | COMPLETED | 1 |  |  | 100515S00057 | 15KJ0143 | 2015-11-27
14447 | NC 2015 | SHS (2015) | Region X | Tangub City | 323302 | Simasay NHS | TANGUB CITY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100515S00008 | 15KJ0066 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | L.C. CONSTRUCTION
14448 | NC 2015 | SHS (2015) | Region X | Tangub City | 304056 | Sumirap NHS | TANGUB CITY | 2 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 5 | 5402652 |  |  | COMPLETED | 1 |  |  | 100515S00059 | 15KJ0141 | 2015-11-27
14449 | NC 2015 | SHS (2015) | Region X | Tangub City | 304171 | Tangub City NHS | TANGUB CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1 |  |  | 100515S00006 | 15KJ0057 | 2015-07-10 | 2015-07-31 | 2015-08-07 | 2015-08-14 | 2015-08-25 | GENETIAN BUILDERS
14450 | NC 2015 | SHS (2015) | Region X | Valencia City | 323807 | Banlag IS | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100315S00029 | 15KA0017 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-24 | 2015-07-27 | KEZ ENTERPRISES
14451 | NC 2015 | K10 (2015) | Region X | Valencia City | 126832 | Barobo ES | CITY OF VALENCIA | 4 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100315S00214 | 15KA0089 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | KEZ ENTERPRISES
14452 | NC 2015 | K10 (2015) | Region X | Valencia City | 126833 | Batangan CES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 100315S00213 | 15KA0090 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | XY BUILDERS
14453 | NC 2015 | K10 (2015) | Region X | Valencia City | 126833 | Batangan CES | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 100315S00206 | 15KA0091 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | XY BUILDERS
14454 | NC 2015 | K10 (2015) | Region X | Valencia City | 126833 | Batangan CES | CITY OF VALENCIA | 4 |  | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  | 100315S00192 | 15KA0092 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | XY BUILDERS
14455 | NC 2015 | K10 (2015) | Region X | Valencia City | 126866 | Buco-Sinait ES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 100315S00196 | 15KA0101 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-13 | KOUZBARY BUILDERS
14456 | NC 2015 | K10 (2015) | Region X | Valencia City | 126835 | Cabanuangan ES | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00204 | 15KA0093 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
14457 | NC 2015 | K10 (2015) | Region X | Valencia City | 126837 | Catumbalon ES | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00211 | 15KA0094 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | BRILLANTES CONSTRUCTION
14458 | NC 2015 | SHS (2015) | Region X | Valencia City | 323803 | Concepcion National High School | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2852592.44 |  |  | COMPLETED | 1 |  |  | 100315S00085 | 15KA0028 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | MAFIL BUILDERS, INC.
14459 | NC 2015 | SHS (2015) | Region X | Valencia City | 323808 | Dagatkidavao Integrated School | CITY MALAYBALAY (Capital) | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100315S00038 | 15KA0018 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-24 | 2015-07-27 | KEZ ENTERPRISES
14460 | NC 2015 | SHS (2015) | Region X | Valencia City | 314909 | Guinuyoran National High School | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6449337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00078 | 15KA0029 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | XY BUILDERS
14461 | NC 2015 | K10 (2015) | Region X | Valencia City | 126841 | Kahaponan ES | CITY OF VALENCIA | 4 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100315S00202 | 15KA0095 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | KEZ ENTERPRISES
14462 | NC 2015 | K10 (2015) | Region X | Valencia City | 126843 | Lilingayon ES | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00201 | 15KA0096 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | BRILLANTES CONSTRUCTION
14463 | NC 2015 | SHS (2015) | Region X | Valencia City | 314906 | Lilingayon NHS | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2897592.44 |  |  | COMPLETED | 1 |  |  | 100315S00113 | 15KA0030 | 2015-08-31 | 2015-09-03 | 2015-09-15 | 2015-09-30 | 2015-10-04 | BRILLANTES CONSTRUCTION
14464 | NC 2015 | K10 (2015) | Region X | Valencia City | 126844 | Liloan ES | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00200 | 15KA0097 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-13 | XY BUILDERS
14465 | NC 2015 | SHS (2015) | Region X | Valencia City | 323805 | Lourdes IS | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 100315S00034 | 15KA0019 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-24 | 2015-07-27 | J.T. GAMOLO CONSTRUCTION
14466 | NC 2015 | K10 (2015) | Region X | Valencia City | 126847 | Lurugan Elementary School | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 100315S00181 | 15KA0109 | 2015-09-17 | 2015-09-17 | 2015-10-01 | 2015-10-23 | 2015-10-27 | XY BUILDERS
14467 | NC 2015 | SHS (2015) | Region X | Valencia City | 303970 | Lurugan NHS | CITY OF VALENCIA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 100315S00079 | 15KA0031 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | KEZ ENTERPRISES
14468 | NC 2015 | K10 (2015) | Region X | Valencia City | 250502 | Migtulod Elementary School | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 100315S00147 | 15KA0052 | 2015-08-31 | 2015-09-03 | 2015-09-15 | 2015-09-30 | 2015-10-04 | BRILLANTES CONSTRUCTION
14469 | NC 2015 | K10 (2015) | Region X | Valencia City | 126851 | Mt. Nebo ES | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00199 | 15KA0098 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
14470 | NC 2015 | K10 (2015) | Region X | Valencia City | 199515 | Pantaron ES | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00193 | 15KA0104 | 2015-11-30 | 2015-12-04 | 2015-12-29
14471 | NC 2015 | K10 (2015) | Region X | Valencia City | 126855 | San Carlos ES | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00198 | 15KA0099 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
14472 | NC 2015 | K10 (2015) | Region X | Valencia City | 126856 | San Isidro ES | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00128 | 15KA0053 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | ZI 9 BUILDERS AND SUPPLIES
14473 | NC 2015 | K10 (2015) | Region X | Valencia City | 126877 | San Vicente ES | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00195 | 15KA0102 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | ZI 9 BUILDERS AND SUPPLIES
14474 | NC 2015 | K10 (2015) | Region X | Valencia City | 126879 | SINAYAWAN CS | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 100315S00194 | 15KA0103 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | XY BUILDERS
14475 | NC 2015 | K10 (2015) | Region X | Valencia City | 126858 | SUGOD ES | CITY OF VALENCIA | 4 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 100315S00197 | 15KA0100 | 2015-09-02 | 2015-09-03 | 2015-09-22 | 2015-10-15 | 2015-10-20 | MAFIL BUILDERS, INC.
14476 | NC 2015 | SHS (2015) | Region X | Valencia City | 323801 | Tongantongan National High School | CITY OF VALENCIA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8344965.051 |  |  | COMPLETED | 1 |  |  | 100315S00080 | 15KA0032 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | KEZ ENTERPRISES
14477 | NC 2015 | SHS (2015) | Region X | Valencia City | 303988 | Valencia NHS | CITY OF VALENCIA | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15201327.92 |  |  | COMPLETED | 1 |  |  | 100315S00081 | 15KA0033 | 2015-08-31 | 2015-09-03 | 2015-10-22 | 2015-11-23 | 2015-11-25 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
14478 | NC 2015 | SHS (2015) | Region X | Valencia City | 323802 | Valencia NHS - Catumbalon Annex | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2867592.44 |  |  | COMPLETED | 1 |  |  | 100315S00082 | 15KA0034 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-09-15 | MAFIL BUILDERS, INC.
20341 | NC 2016 | SHS | Region X | Bukidnon | 303944 | Alae Nhs | Manolo Fortich | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1
20342 | NC 2016 | SHS | Region X | Bukidnon | 303944 | Alae Nhs | Manolo Fortich | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 6369337.64 |  |  | Completed | 1
20343 | NC 2016 | K10 | Region X | Bukidnon | 303947 | Baungon National High School | Baungon | 1 | 1 | 20 | 2STY10CL | BATCH 1 CL | 25642620.1861 |  |  | Completed | 1 |  |  | P00070137MN | 16KC0010 |  |  | 2016-06-30 | 2016-07-20 | 2016-08-09 | LLM Concrete Products
20344 | NC 2016 | TECHVOC | Region X | Bukidnon | 314901 | Dalirig Nhs | Manolo Fortich | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2550000 |  |  | Completed | 1 | [6 empty] | 2016-08-04
20345 | NC 2016 | SHS | Region X | Bukidnon | 303958 | Kalilangan Nhs | Kalilangan | 1 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6389337.6381 |  |  | Completed | 1 |  |  | P00070144MN | 16KC0017 |  |  | 2016-06-30 | 2016-07-20 | -618499 | KEZ Enterprises
20346 | NC 2016 | SHS | Region X | Bukidnon | 303958 | Kalilangan Nhs | Kalilangan | 1 |  | 18 | 3STY18CL | BATCH 1 CL | 25777559.98 |  |  | Completed | 1 |  |  | P00070143MN | 16KC0015 |  |  | 2016-06-30 | 2016-07-20 | -618499 | LLM Concrete Products
20347 | NC 2016 | SHS | Region X | Bukidnon | 303958 | Kalilangan Nhs | Kalilangan | 1 |  | 4 | 2STY4CL | BATCH 1 CL | 6389337.6381 |  |  | Completed | 1 |  |  | P00070142MN | 16KC0016 |  |  | 2016-06-30 | 2016-07-20 | -618499 | KEZ Enterprises
20348 | NC 2016 | TECHVOC | Region X | Bukidnon | 303969 | Kinawe National High School | Libona | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2550000 |  |  | Completed | 1 | [6 empty] | 2016-08-04
20349 | NC 2016 | TECHVOC | Region X | Bukidnon | 303966 | Lampanusan Nhs | Kalilangan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2560000 |  |  | Completed | 1 | [6 empty] | 2016-08-04
20350 | NC 2016 | TECHVOC | Region X | Bukidnon | 303968 | Libona Nhs | Libona | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2552472.0728 |  |  | Completed | 1 | [6 empty] | 2016-08-04
20351 | NC 2016 | SHS | Region X | Bukidnon | 303968 | Libona Nhs | Libona | 1 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18272268.79 |  |  | Completed | 1
20352 | NC 2016 | TECHVOC | Region X | Bukidnon | 303972 | Malitbog Nat. Agr'I. Hs | Malitbog | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2700000 |  |  | Completed | 1 | [6 empty] | 2016-08-04
20353 | NC 2016 | SHS | Region X | Bukidnon | 303974 | Manolo Fortich Nhs | Manolo Fortich | 1 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8925121.051 |  |  | Completed | 1 |  |  | P00070141MN | 16KC0014 |  |  | 2016-06-30 | 2016-07-20 | 2016-08-09 | Footprints Construction
20354 | NC 2016 | SHS | Region X | Bukidnon | 303974 | Manolo Fortich Nhs | Manolo Fortich | 1 |  | 20 | 4STY20CL | BATCH 1 CL | 31152890.27 |  |  | Completed | 1 |  |  | P00070139MN | 16KC0011 |  |  | 2016-06-30 | 2016-07-20 | 2016-08-09 | Legacy Construction
20355 | NC 2016 | SHS | Region X | Bukidnon | 303974 | Manolo Fortich Nhs | Manolo Fortich | 1 |  | 6 | 2STY6CL | BATCH 1 CL | 8264965.051 |  |  | Completed | 1 |  |  | P00070140MN | 16KC0013 |  |  | 2016-06-30 | 2016-07-20 | 2016-08-09 | RR Seismundo Construction & Supply
20356 | NC 2016 | SHS | Region X | Bukidnon | 303974 | Manolo Fortich Nhs | Manolo Fortich | 1 |  | 6 | 2STY6CL | BATCH 1 CL | 8264965.051 |  |  | Completed | 1 |  |  | P00070138MN | 16KC0012 |  |  | 2016-06-30 | 2016-07-20 | 2016-08-09 | Footprints Construction
20357 | NC 2016 | SHS | Region X | Bukidnon | 303978 | Pangantucan Nhs | Pangantucan | 1 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15191327.92 |  |  | Completed | 1
20358 | NC 2016 | TECHVOC | Region X | Bukidnon | 303978 | Pangantucan Nhs | Pangantucan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2570000 |  |  | Completed | 1 | [6 empty] | 2016-08-04
20359 | NC 2016 | TECHVOC | Region X | Bukidnon | 303983 | Sankanan Nhs | Manolo Fortich | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2560000 |  |  | Completed | 1 | [6 empty] | 2016-08-04
20360 | NC 2016 | TECHVOC | Region X | Bukidnon | 303986 | Sumilao Nhs | Sumilao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2560000 |  |  | Completed | 1 | [6 empty] | 2016-08-04
20361 | NC 2016 | SHS | Region X | Bukidnon | 314924 | Sumilao Nhs - Vista Villa Annex | Sumilao | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8294965.051 |  |  | Completed | 1
20362 | NC 2016 | SHS | Region X | Bukidnon | 303987 | Talakag Nhs | Talakag | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12821310.09 |  |  | Completed | 1
20363 | NC 2016 | TECHVOC | Region X | Bukidnon | 314919 | Tikalaan Nhs | Talakag | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2600000 |  |  | Completed | 1 | [6 empty] | 2016-08-04
20364 | NC 2016 | TECHVOC | Region X | Bukidnon | 303952 | Cabulohan-Paradise Nhs | Cabanglasan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2597333.12 |  |  | Completed | 1 |  |  |  | 16KA0032 |  |  | 2016-08-09
20365 | NC 2016 | SHS | Region X | Bukidnon | 314908 | Cabulohan-Paradise Nhs - Townsite Annex | Cabanglasan | 2 | 1 | 16 | 2STY8CL | BATCH 1 CL | 22194685.1834 |  |  | Completed | 1 |  |  |  | 16KA0004 | [5 empty] | J.T. Gamolo Construction
20366 | NC 2016 | TECHVOC | Region X | Bukidnon | 314908 | Cabulohan-Paradise Nhs - Townsite Annex | Cabanglasan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2549549.27 |  |  | Completed | 1 |  |  |  | 16KA0005 |  |  | 2016-05-24 |  |  | Angel & Sam Construction
20367 | NC 2016 | TECHVOC | Region X | Bukidnon | 314907 | Halapitan Nhs - Little Baguio Annex | San Fernando | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2607333.12 |  |  | Completed | 1 |  |  |  | 16KA0033 |  |  | 2016-08-09
20368 | NC 2016 | TECHVOC | Region X | Bukidnon | 303956 | Impasugong Nhs | Impasug-Ong | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  |  | 16KA0031 |  |  | 2016-08-09
20369 | NC 2016 | K10 | Region X | Bukidnon | 303956 | Impasugong Nhs | Impasug-Ong | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8464965.05 |  |  | Completed | 1
20370 | NC 2016 | SHS | Region X | Bukidnon | 303957 | Kalabugao Nhs | Impasug-Ong | 2 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1173449.69 |  |  | Completed | 1
20371 | NC 2016 | SHS | Region X | Bukidnon | 303957 | Kalabugao Nhs | Impasug-Ong | 2 |  | 8 | 2STY8CL | BATCH 13 CL | 12175076.849 |  |  | Completed | 1
20372 | NC 2016 | K10 | Region X | Bukidnon | 303967 | Lantapan National High School | Lantapan | 2 | 1 | 30 | 3STY15CL | BATCH 7 CL | 47450000 |  |  | Completed | 1 |  |  |  | 16KA0013 |  |  | 2016-05-24 |  |  | Legacy Construction
20373 | NC 2016 | K10 | Region X | Bukidnon | 303967 | Lantapan National High School | Lantapan | 2 |  | 4 | 2STY4CL | BATCH 7 CL | 6551031.01 |  |  | Completed | 1 |  |  |  | 16KA0012 |  |  | 2016-05-24 |  |  | Mafil Builders Inc.
20374 | NC 2016 | TECHVOC | Region X | Bukidnon | 303967 | Lantapan National High School | Lantapan | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5285000 |  |  | Completed | 1 |  |  |  | 16KA0014 |  |  | 2016-05-24 |  |  | Mafil Builders
20375 | NC 2016 | TECHVOC | Region X | Bukidnon | 303948 | Bocboc Nhs | Don Carlos | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2806435.56 |  |  | Completed | 1 |  |  |  | 16KB0030 |  | 2016-08-19 | 2016-08-30
20376 | NC 2016 | SHS | Region X | Bukidnon | 303951 | Bukidnon Nshi | Maramag | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34086221.03 |  |  | Completed | 1
20377 | NC 2016 | SHS | Region X | Bukidnon | 303951 | Bukidnon Nshi | Maramag | 3 |  | 18 | 3STY9CL | BATCH 9 CL | 30218711.82 |  |  | Completed | 1 |  |  |  | 16KB0026 |  | 2016-07-22 | 2016-08-02
20378 | NC 2016 | SHS | Region X | Bukidnon | 303951 | Bukidnon Nshi | Maramag | 3 |  | 2 | 1STY2CL | BATCH 9 CL | 2046214.1914 |  |  | Completed | 1 |  |  |  | 16KB0018 |  |  | 2016-08-02
20379 | NC 2016 | TECHVOC | Region X | Bukidnon | 303951 | Bukidnon Nshi | Maramag | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2550000 |  |  | Completed | 1 |  |  |  | 16KB0024 |  | 2016-08-19 | 2016-08-30
20380 | NC 2016 | SHS | Region X | Bukidnon | 303953 | Dangcagan Nhs | Dangcagan | 3 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11284616.02 |  |  | Completed | 1 |  |  | P00070146MN | 16KB0001 |  |  | 2016-03-10 |  | 2016-06-24 | Davao Concrete Products
20381 | NC 2016 | SHS | Region X | Bukidnon | 303953 | Dangcagan Nhs | Dangcagan | 3 |  | 6 | 2STY6CL | BATCH 1 CL | 8645614.7 |  |  | Completed | 1 |  |  | P00070147MN | 16KB0002 |  |  | 2016-03-10 |  | 2016-06-24 | Davao Concrete Products
20382 | NC 2016 | SHS | Region X | Bukidnon | 303953 | Dangcagan Nhs | Dangcagan | 3 |  | 6 | 2STY6CL | BATCH 1 CL | 8495614.7 |  |  | Completed | 1 |  |  | P00070148MN | 16KB0003 |  |  | 2016-03-10 |  | 2016-06-24 | Davao Concrete Products
20383 | NC 2016 | K10 | Region X | Bukidnon | 303960 | Kibawe National High School | Kibawe | 3 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20992991.13 |  |  | Completed | 1
20384 | NC 2016 | TECHVOC | Region X | Bukidnon | 303961 | Kiburiao National High School | Quezon | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2650000 |  |  | Completed | 1 |  |  |  | 16KB0027 |  | 2016-08-19 | 2016-08-30
20385 | NC 2016 | TECHVOC | Region X | Bukidnon | 303965 | Kuya Nhs | Maramag | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2739283.03 |  |  | Completed | 1 |  |  |  | 16KB0031 |  | 2016-08-19 | 2016-08-30
20386 | NC 2016 | TECHVOC | Region X | Bukidnon | 314929 | Macapari Nhs | Damulog | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2833296.57 |  |  | Completed | 1 |  |  |  | 16KB0029 |  | 2016-08-19 | 2016-08-30
20387 | NC 2016 | SHS | Region X | Bukidnon | 303976 | Old Damulog Nhs | Damulog | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6571031.01 |  |  | Completed | 1 |  |  | P00072492MN | 16KB0019 |  | 2016-06-10 | 2016-06-21 | 2016-07-04 | 2016-08-03 | Cartesian Builders
20388 | NC 2016 | SHS | Region X | Bukidnon | 303976 | Old Damulog Nhs | Damulog | 3 |  | 12 | 2STY12CL | BATCH 7 CL | 15163509.35 |  |  | Completed | 1
20389 | NC 2016 | SHS | Region X | Bukidnon | 303976 | Old Damulog Nhs | Damulog | 3 |  | 6 | 2STY6CL | BATCH 7 CL | 8545614.7 |  |  | Completed | 1 |  |  | P00072499MN | 16KB0021 |  | 2016-06-10 | 2016-06-21 | 2016-07-04 | 2016-08-03 | RR Seismundo Construction & Supply
20390 | NC 2016 | TECHVOC | Region X | Bukidnon | 314912 | Quezon Nhs | Quezon | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2575000 |  |  | Completed | 1 |  |  |  | 16KB0028 |  | 2016-08-19 | 2016-08-30
20391 | NC 2016 | SHS | Region X | Bukidnon | 314912 | Quezon Nhs | Quezon | 3 | 1 | 45 | 3STY15CL | BATCH 13 CL | 70918944.385 |  |  | Completed | 1
20392 | NC 2016 | SHS | Region X | Bukidnon | 303979 | Salawagan Nhs | Quezon | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6571031.01 |  |  | Completed | 1 |  |  | P00074125MN | 16KB0020 |  | 2016-06-10 | 2016-06-21 | 2016-07-04 | 2016-08-03 | Mafil Builders, Inc.
20393 | NC 2016 | SHS | Region X | Bukidnon | 303979 | Salawagan Nhs | Quezon | 3 |  | 12 | 2STY12CL | BATCH 9 CL | 15163509.35 |  |  | Completed | 1
20394 | NC 2016 | TECHVOC | Region X | Bukidnon | 303979 | Salawagan Nhs | Quezon | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2575000 |  |  | Completed | 1
20395 | NC 2016 | SHS | Region X | Bukidnon | 303980 | San Andres Nhs | Kadingilan | 3 | 1 | 12 | 3STY12CL | BATCH 13 CL | 21390000.48 |  |  | Completed | 1
20396 | NC 2016 | K10 | Region X | Cagayan De Oro City | 127959 | Bayabas Elementary School | Cagayan De Oro City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6904740.0014 |  |  | Completed | 1 |  |  | P00074127MN | 16KH0046 | 2016-07-28 | 2016-08-16 | 2016-08-16
20397 | NC 2016 | SHS | Region X | Cagayan De Oro City | 304108 | Bulua National High School | Cagayan De Oro City (Capital) | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31914205.49 |  |  | Completed | 1
20398 | NC 2016 | SHS | Region X | Cagayan De Oro City | 304109 | Canitoan National High School | Cagayan De Oro City (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1
20399 | NC 2016 | SHS | Region X | Cagayan De Oro City | 315409 | Iponan Nhs - San Simon Annex | Cagayan De Oro City (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8775713.3 |  |  | Completed | 1 |  |  | P00070595MN | 16KH0038 | 2016-07-06 | 2016-07-13 | 2016-07-25
20400 | NC 2016 | SHS | Region X | Cagayan De Oro City | 315409 | Iponan Nhs - San Simon Annex | Cagayan De Oro City (Capital) | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6785304.52 |  |  | Completed | 1 |  |  | P00070596MN | 16KH0037 | 2016-07-06 | 2016-07-13 | 2016-07-25
20401 | NC 2016 | SHS | Region X | Cagayan De Oro City | 304121 | Mambuaya National High School | Cagayan De Oro City (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10766122.08 |  |  | Completed | 1 |  |  | P00070593MN | 16KH0014 | 2016-04-15 | 2016-04-15 | 2016-04-27 |  | 2016-05-23 | L & L Construction
20402 | NC 2016 | SHS | Region X | Cagayan De Oro City | 304121 | Mambuaya National High School | Cagayan De Oro City (Capital) | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8775713.3 |  |  | Completed | 1 |  |  | P00070594MN | 16KH0015 | 2016-04-15 | 2016-04-15 | 2016-04-27 |  | 2016-05-23 | L & L Construction
20403 | NC 2016 | SHS | Region X | Cagayan De Oro City | 304122 | Mambuaya Nhs-Bayanga Annex | Cagayan De Oro City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1 |  |  | P00074128MN | 16KH0044 | 2016-07-13 | 2016-07-20 | 2016-08-01
20404 | NC 2016 | K10 | Region X | Cagayan De Oro City | 127999 | Pedro "Oloy" N. Roa, Sr. Elementary School | Cagayan De Oro City (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10949545.4331 |  |  | Completed | 1 |  |  | P00074129MN | 16KH0043 | 2016-07-13 | 2016-07-20 | 2016-08-01
20405 | NC 2016 | K10 | Region X | Cagayan De Oro City | 127993 | Sacred Heart Vill Es Elementary School | Cagayan De Oro City (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
20406 | NC 2016 | SHS | Region X | Cagayan De Oro City | 304125 | Taglimao National High School | Cagayan De Oro City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6904740 |  |  | Completed | 1 |  |  | P00070597MN | 16KH0036 | 2016-07-06 | 2016-07-13 | 2016-07-25
20407 | NC 2016 | TECHVOC | Region X | Cagayan De Oro City | 315401 | Balubal, National High School | Cagayan De Oro City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2599609.1386 |  |  | Reverted | 0 |  |  |  | 16KD00013 | 2016-02-18 | 2016-03-04 | 2016-03-22 | 2016-06-23 | 2016-06-29 | FFJJ Construction
20408 | NC 2016 | SHS | Region X | Cagayan De Oro City | 304111 | Cagayan De Oro National High School | Cagayan De Oro City (Capital) | 2 | 1 | 40 | 4STY20CL | BATCH 5 CL | 63508449.18 |  |  | Completed | 1
20409 | NC 2016 | TECHVOC | Region X | Cagayan De Oro City | 315404 | Camaman-An,National High School | Cagayan De Oro City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Reverted | 0
20410 | NC 2016 | K10 | Region X | Cagayan De Oro City | 127955 | Corrales Elementary School | Cagayan De Oro City (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 23311859.63 |  |  | Completed | 1
20411 | NC 2016 | K10 | Region X | Cagayan De Oro City | 127965 | Indahag Elementary School | Cagayan De Oro City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
20412 | NC 2016 | K10 | Region X | Cagayan De Oro City | 127954 | Tablon Elementary School | Cagayan De Oro City (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 23311859.63 |  |  | Completed | 1
20413 | NC 2016 | K10 | Region X | Camiguin | 126925 | Bacnit Es | Sagay | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6532755 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074144 MN | 16KE0036 | 2016-05-27 | 2016-06-07 | 2016-07-27
20414 | NC 2016 | SHS | Region X | Camiguin | 303989 | Bonbon Nhs | Catarman | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058584.1914 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074130 MN | 16KE0044 | 2016-07-15 | 2016-07-25 | 2016-08-09
20415 | NC 2016 | SHS | Region X | Camiguin | 303990 | Camiguin Nhs | Catarman | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8424000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074131 MN | 16KE0029 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-03 | 2016-07-23 | GCMG CONST.
20416 | NC 2016 | SHS | Region X | Camiguin | 303990 | Camiguin Nhs | Catarman | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 8424000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074132 MN | 16KE0028 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-03 | 2016-07-23 | GCMG CONST.
20417 | NC 2016 | SHS | Region X | Camiguin | 303990 | Camiguin Nhs | Catarman | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 15909000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074133 MN | 16KE0033 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-07 |  | JAPUZ-JANSOL ENT.
20418 | NC 2016 | SHS | Region X | Camiguin | 303990 | Camiguin Nhs | Catarman | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 15909000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074134 MN | 16KE0034 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-07 |  | JAPUZ-JANSOL ENT.
20419 | NC 2016 | K10 | Region X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | Sagay | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6555338 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00070590 MN | 16KE0005 | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-04 | 2016-07-23 | JAPUZ-JANSOL ENT.
20420 | NC 2016 | K10 | Region X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | Sagay | 0 |  | 4 | 2STY4CL | BATCH 3 CL | 6555338 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00070591 MN | 16KE0006 | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-04 | 2016-07-23 | JAPUZ-JANSOL ENT.
20421 | NC 2016 | SHS | Region X | Camiguin | 303991 | Guinsiliban National High School | Guinsiliban | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6532755 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074137 MN | 16KE0038 | 2016-05-27 | 2016-06-07 | 2016-07-27
20422 | NC 2016 | K10 | Region X | Camiguin | 315005 | Kuguita Integrated School | Mambajao (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6607000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00070592 MN | 16KE0007 | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-04 | 2016-07-23 | JAPUZ-JANSOL ENT.
20423 | NC 2016 | SHS | Region X | Camiguin | 303992 | Lawigan-Bura National High School | Catarman | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058584.1914 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074135 MN | 16KE00043 | 2016-07-15 | 2016-07-25 | 2016-08-09
20424 | NC 2016 | K10 | Region X | Camiguin | 315001 | Maac National High School | Guinsiliban | 0 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8516440 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00072471 MN | 16KE0032 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-03 | 2016-07-23 | GCMG CONST.
20425 | NC 2016 | TECHVOC | Region X | Camiguin | 315001 | Maac National High School | Guinsiliban | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2636400 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00072643 MN | 16KE0042 | 2016-07-15 | 2016-07-25 | 2016-08-09
20426 | NC 2016 | SHS | Region X | Camiguin | 303993 | Mahinog Nhs | Mahinog | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11564000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074139 MN | 16KE0037 | 2016-07-15 | 2016-07-25 | 2016-08-09
20427 | NC 2016 | SHS | Region X | Camiguin | 303993 | Mahinog Nhs | Mahinog | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6510000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074138 MN | 16KE0045 | 2016-05-27 | 2016-06-07 | 2016-06-29 | 2016-07-04 | 2016-07-23 | GCMG CONST.
20428 | NC 2016 | SHS | Region X | Camiguin | 303994 | Mambajao Nhs | Mambajao (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 1 CL | 15999000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00070130 MN | 16KE0008 | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-04 |  | JAPUZ-JANSOL ENT.
20429 | NC 2016 | SHS | Region X | Camiguin | 303994 | Mambajao Nhs | Mambajao (Capital) | 0 |  | 12 | 3STY12CL | BATCH 1 CL | 19245000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00070131 MN | 16KE0009 | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-04 |  | JAPUZ-JANSOL ENT.
20430 | NC 2016 | SHS | Region X | Camiguin | 303994 | Mambajao Nhs | Mambajao (Capital) | 0 |  | 12 | 3STY12CL | BATCH 1 CL | 19245000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00070132 MN | 16KE0010 | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-04 |  | JAPUZ-JANSOL ENT.
20431 | NC 2016 | K10 | Region X | Camiguin | 126892 | Sto. Nino Es | Catarman | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8516440 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074136 MN | 16KE0031 | 2016-05-27 | 2016-06-07 | 2016-07-27
20432 | NC 2016 | SHS | Region X | Camiguin | 303996 | Tupsan Nhs | Mambajao (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6530000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00072472 MN | 16KE0025 | 2016-05-18 | 2016-05-27 | 2016-06-10 | 2016-07-04 | 2016-07-23 | SHEEN-SHEEN CONST.
20433 | NC 2016 | SHS | Region X | Camiguin | 303997 | Yumbing National High School | Mambajao (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11485000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074140 MN | 16KE0046 | 2016-07-15 | 2016-07-25 | 2016-08-09
20434 | NC 2016 | SHS | Region X | Camiguin | 303997 | Yumbing National High School | Mambajao (Capital) | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 8424000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074141 MN | 16KE0030 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-03 | 2016-07-23 | SHEEN-SHEEN CONST.
20435 | NC 2016 | SHS | Region X | Camiguin | 303997 | Yumbing National High School | Mambajao (Capital) | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6465000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074142 MN | 16KE0035 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-03 | 2016-07-23 | SHEEN-SHEEN CONST.
20436 | NC 2016 | SHS | Region X | Camiguin | 303997 | Yumbing National High School | Mambajao (Capital) | 0 |  | 1 | 1STY1CL | BATCH 9 CL | 1113254.6197 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074143 MN | 16KE0041 | 2016-07-15 | 2016-07-25 | 2016-08-09
20437 | NC 2016 | SHS | Region X | El Salvador | 304065 | Cogon Nhs | City Of El Salvador | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22350000 |  |  | Completed | 1
20438 | NC 2016 | TECHVOC | Region X | El Salvador | 304065 | Cogon Nhs | City Of El Salvador | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1
20439 | NC 2016 | K10 | Region X | El Salvador | 315318 | Hinigdaan Nhs | City Of El Salvador | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15350000 |  |  | Completed | 1
20440 | NC 2016 | K10 | Region X | El Salvador | 315305 | Molugan Nhs | City Of El Salvador | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26950000 |  |  | Completed | 1
20441 | NC 2016 | TECHVOC | Region X | Gingoog City | 304129 | Bal-Ason Nhs | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
20442 | NC 2016 | TECHVOC | Region X | Gingoog City | 304130 | Gingoog City Cnhs | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2662953.92 |  |  | Completed | 1
20443 | NC 2016 | SHS | Region X | Gingoog City | 304130 | Gingoog City Cnhs | Gingoog City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24401857.982 |  |  | Completed | 1
20444 | NC 2016 | TECHVOC | Region X | Gingoog City | 315504 | Gingoog City Cnhs - Pundasan Nhs Annex | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
20445 | NC 2016 | TECHVOC | Region X | Gingoog City | 304132 | Kalipay Nhs | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
20446 | NC 2016 | TECHVOC | Region X | Gingoog City | 304133 | Malibud National High School | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2575000 |  |  | Completed | 1
20447 | NC 2016 | TECHVOC | Region X | Gingoog City | 304135 | Mimbunga Nhs | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
20448 | NC 2016 | TECHVOC | Region X | Gingoog City | 304136 | Odiongan Nhs | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
20449 | NC 2016 | TECHVOC | Region X | Gingoog City | 315502 | Odiongan Nhs - Talisay Nhs Annex | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
20450 | NC 2016 | SHS | Region X | Iligan City | 304138 | Acelo C. Badelles, Sr. Mnhs (Tipanoy Nhs) | Iligan City | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15518925.24 |  |  | Completed | 1 |  |  | P00074147MN | 16KF0044 | [5 empty] | LANAO BUILDER AND ENTERPRISES
20451 | NC 2016 | K10 | Region X | Iligan City | 128153 | Bernardo E. Ramos Memorial School | Iligan City | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1990417.57 |  |  | Completed | 1 |  |  | P00074148MN | 16KF0019 | [5 empty] | AMSCON BUILDERS ENTERPRISES
20452 | NC 2016 | K10 | Region X | Iligan City | 203003 | Binasan Es | Iligan City | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3015174.43 |  |  | Completed | 1 |  |  | P00074149MN | 16KF0023 | [5 empty] | D.O.T CONSTRUCTION
20453 | NC 2016 | SHS | Region X | Iligan City | 304140 | Bunawan Agri. Hs | Iligan City | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11691139.03 |  |  | Completed | 1 |  |  | P00074150MN | 16KF0026 | [5 empty] | AHMADI BUILDERS
20454 | NC 2016 | K10 | Region X | Iligan City | 128119 | Caribao Es | Iligan City | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2167459.327 |  |  | Completed | 1 |  |  | P00074151MN | 16KF0030 | [5 empty] | D.O.T CONSTRUCTION
20455 | NC 2016 | K10 | Region X | Iligan City | 128098 | Dalamas Es | Iligan City | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6521031.01 |  |  | Completed | 1 |  |  | P00074152MN | 16KF0031 | [5 empty] | D.O.T CONSTRUCTION
20456 | NC 2016 | K10 | Region X | Iligan City | 304143 | Dalipuga National High School | Iligan City | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11371139.03 |  |  | Completed | 1 |  |  | P00074153MN | 16KF0040 | [5 empty] | AHMADI BUILDERS
20457 | NC 2016 | TECHVOC | Region X | Iligan City | 304143 | Dalipuga National High School | Iligan City | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5040000 |  |  | Completed | 1 |  |  | P00074598MN | 16KF0033 | [5 empty] | AHM BUILDERS
20458 | NC 2016 | SHS | Region X | Iligan City | 304144 | Dalipuga Nhs - Hindang Nhs Annex | Iligan City | 0 | 1 | 4 | 1STY2CL | BATCH 9 CL | 4020835.14 |  |  | Completed | 1 |  |  | P00074154MN | 16KF0028 | [5 empty] | MARKBUILT ENTERPRISES
20459 | NC 2016 | TECHVOC | Region X | Iligan City | 304144 | Dalipuga Nhs - Hindang Nhs Annex | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2520000 |  |  | Completed | 1 |  |  | P00074597MN | 16KF0037 | [5 empty] | MARKBUILT ENTERPRISES
20460 | NC 2016 | SHS | Region X | Iligan City | 304154 | Esperidion F. Encabo I Mhs (Pugaan Nhs) | Iligan City | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15518925.24 |  |  | Completed | 1 |  |  | P00074155MN | 16KF0046 | [5 empty] | D.C.M CONSTRUCTION
20461 | NC 2016 | SHS | Region X | Iligan City | 315608 | Francisco Laya Memorial Integrated School | Iligan City | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8375614.7 |  |  | Completed | 1 |  |  | P00074156MN | 16KF0016 | [5 empty] | DCM ENTERPRISES
20462 | NC 2016 | TECHVOC | Region X | Iligan City | 315608 | Francisco Laya Memorial Integrated School | Iligan City | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5040000 |  |  | Completed | 1 |  |  | P00074599MN | 16KF0034 | [5 empty] | SALMAN CONSTRUCTION DEVELOPMENT
20463 | NC 2016 | K10 | Region X | Iligan City | 304149 | Iligan City East High School - Hinaplanon Annex | Iligan City | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15498925.24 |  |  | Completed | 1 |  |  | P00074157MN | 16KF0045 | [5 empty] | AL-FAHDEL CONST. AND ENGINEERING
20464 | NC 2016 | TECHVOC | Region X | Iligan City | 304149 | Iligan City East High School - Hinaplanon Annex | Iligan City | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5040000 |  |  | Completed | 1 |  |  | P00074600MN | 16KF0032 | [5 empty] | MARKBUILT ENTERPRISES
20465 | NC 2016 | SHS | Region X | Iligan City | 304147 | Iligan City East Hs - Kiwalan Annex | Iligan City | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15508925.24 |  |  | Completed | 1 |  |  | P00074158MN | 16KF0043 | [5 empty] | AL-FAHDEL CONST. AND ENGINEERING
20466 | NC 2016 | TECHVOC | Region X | Iligan City | 304147 | Iligan City East Hs - Kiwalan Annex | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2520000 |  |  | Completed | 1 |  |  | P00074601MN | 16KF0042 | [5 empty] | NDP CONSTRUCTION DEVELOPMENT
20467 | NC 2016 | TECHVOC | Region X | Iligan City | 304148 | Iligan City East Hs - Santiago Hs Annex | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  | P00075262MN | 16KF0059 | [5 empty] | GLOBAL TECH DESIGN BUILDERS INC.
20468 | NC 2016 | SHS | Region X | Iligan City | 304148 | Iligan City East Hs - Santiago Hs Annex | Iligan City | 0 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6451031.01 |  |  | Reverted | 0
20469 | NC 2016 | K10 | Region X | Iligan City | 304146 | Iligan City East National Hs (Sta. Filomena) | Iligan City | 0 | 1 | 20 | 4STY20CL | BATCH 1 CL | 34337130.83 |  |  | Completed | 1 |  |  | P00070129MN | 16KF0006 | [5 empty] | D.C.M CONSTRUCTION
20470 | NC 2016 | TECHVOC | Region X | Iligan City | 304146 | Iligan City East National Hs (Sta. Filomena) | Iligan City | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 10085080.61 |  |  | Completed | 1 |  |  | P00070123MN | 16KF0014 | [5 empty] | AHMADI BUILDERS
20471 | NC 2016 | K10 | Region X | Iligan City | 304142 | Kabacsanan National High School | Iligan City | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11991139.03 |  |  | Completed | 1 |  |  | P00074159MN | 16KF0035 | [5 empty] | D.C.M CONSTRUCTION
20472 | NC 2016 | K10 | Region X | Iligan City | 128121 | Kabangahan I Es | Iligan City | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6521031.01 |  |  | Completed | 1 |  |  | P00074160MN | 16KF0027 | [5 empty] | DCD BUILDERS AND ENTERPRISES
20473 | NC 2016 | K10 | Region X | Iligan City | 315609 | Kalubihon High School | Iligan City | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11791139.03 |  |  | Completed | 1 |  |  | P00074161MN | 16KF0036 | [5 empty] | AHMADI BUILDERS
20474 | NC 2016 | K10 | Region X | Iligan City | 128141 | Lumbatin Elementary School | Iligan City | 0 | 1 | 4 | 1STY2CL | BATCH 9 CL | 3990835.14 |  |  | Completed | 1 |  |  | P00074162MN | 16KF0029 | [5 empty] | NDP CONSTRUCTION DEVELOPMENT
20475 | NC 2016 | TECHVOC | Region X | Iligan City | 304151 | Mainit High School | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2600000 |  |  | Completed | 1 |  |  | P00075263MN | 16KF0058 | [5 empty] | DCD BUILDERS AND ENTERPRISES
20476 | NC 2016 | K10 | Region X | Iligan City | 304153 | Maria Cristina Hs - Ditucalan Annex | Iligan City | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8395614.7 |  |  | Completed | 1 |  |  | P00074163MN | 16KF0022 | [5 empty] | DCM CONTRUCTION
20477 | NC 2016 | K10 | Region X | Iligan City | 304153 | Maria Cristina Hs - Ditucalan Annex | Iligan City | 0 |  | 3 | 1STY3CL | BATCH 9 CL | 2915174.43 |  |  | Completed | 1 |  |  | P00074164MN | 16KF0025 | [5 empty] | MARKBUILT ENTERPRISES
20478 | NC 2016 | K10 | Region X | Iligan City | 304152 | Maria Cristina National High School | Iligan City | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11371397.03 |  |  | Completed | 1 |  |  | P00074165MN | 16KF0039 | [5 empty] | AHMADI BUILDERS
20479 | NC 2016 | TECHVOC | Region X | Iligan City | 304152 | Maria Cristina National High School | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2520000 |  |  | Completed | 1 |  |  | P00074601MN | 16KF0038 | [5 empty] | NDP CONSTRUCTION DEVELOPMET
20480 | NC 2016 | SHS | Region X | Iligan City | 304155 | Rogongon Agricultural High School | Iligan City | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8795614.7 |  |  | Completed | 1 |  |  | P00074166MN | 16KF0021 | [5 empty] | LANAO BUILDER AND ENTERPRISES
20481 | NC 2016 | K10 | Region X | Iligan City | 128087 | Servillano G. Reuyan Memorial Elementary School | Iligan City | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1995417.57 |  |  | Completed | 1 |  |  | P0074167MN | 16KF0020 | [5 empty] | AL QAOD CONSTRUCTION AND SUPPLY
20482 | NC 2016 | SHS | Region X | Iligan City | 304157 | Tomas Cabili Nhs | Iligan City | 0 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6421031.01 |  |  | Completed | 1 |  |  | P00075963MN | 16KF0065
20483 | NC 2016 | SHS | Region X | Iligan City | 304158 | Tomas Cabili Nhs - Annex | Iligan City | 0 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8625324.52 |  |  | Completed | 1 |  |  | P00070128MN | 16KF0003 | [5 empty] | AL-FAHDEL CONTS. AND ENGINEERING
20484 | NC 2016 | TECHVOC | Region X | Iligan City | 304158 | Tomas Cabili Nhs - Annex | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 4800013.39 |  |  | Completed | 1 |  |  | P00070212MN | 16KF0007 | [5 empty] | N.D.P. CONSTRUCTION
20485 | NC 2016 | SHS | Region X | Iligan City | 304159 | Tubaran Nhs | Iligan City | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2020417.57 |  |  | Completed | 1 |  |  | P00074168MN | 16KF0017 | [5 empty] | GREEN BUILDERS AND ENTERPRISES
20486 | NC 2016 | SHS | Region X | Iligan City | 304159 | Tubaran Nhs | Iligan City | 0 |  | 3 | 1STY3CL | BATCH 9 CL | 2925174.43 |  |  | Completed | 1 |  |  | P00074169MN | 16KF0024 | [5 empty] | SDM VENTURES
20487 | NC 2016 | SHS | Region X | Iligan City | 304160 | Tubaran Nhs - Digkilaan Hs Annex | Iligan City | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2020417.57 |  |  | Completed | 1 |  |  | P0074170MN | 16KF0018 | [5 empty] | MARKBUILT ENTERPRISES
20488 | NC 2016 | TECHVOC | Region X | Iligan City | 304160 | Tubaran Nhs - Digkilaan Hs Annex | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2550000 |  |  | Completed | 1 |  |  | P00074603MN | 16KF0042 | [5 empty] | GLOBAL TECH DESIGN BUILDERS INC.
20489 | NC 2016 | TECHVOC | Region X | Lanao Del Norte | 304002 | Arsenio A. Quibranza Nhs (Lnnaihs) | Tubod (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1 |  |  | P00075303MN | 16KF0054 | [5 empty] | MARKBUILT ENTERPRISES
20490 | NC 2016 | TECHVOC | Region X | Lanao Del Norte |  | Binuni-Demologan Nhs | Bacolod | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2587125.29 |  |  | Completed | 1 |  |  | P00075299MN | 16KF0056 | [5 empty] | TESAR BUILDERS
20491 | NC 2016 | TECHVOC | Region X | Lanao Del Norte | 304013 | Diego H. Patigayon Nhs (Mukas Nhs) | Kolambugan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2668449.38 |  |  | Reverted | 0
20492 | NC 2016 | TECHVOC | Region X | Lanao Del Norte | 304005 | Lanao Del Norte Nchs | Baroy | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2860276.42 |  |  | Completed | 1 |  |  | P00075296MN | 16KF0055 | [5 empty] | MJALONTO BUILDER AND ENTERPRISES
20493 | NC 2016 | SHS | Region X | Lanao Del Norte | 304005 | Lanao Del Norte Nchs | Baroy | 1 | 1 | 18 | 3STY9CL | BATCH 13 CL | 32086060.84 |  |  | Completed | 1 |  |  | P00075964MN | 16KF0061
20494 | NC 2016 | SHS | Region X | Lanao Del Norte | 315102 | Lanao Del Norte Provincial Science And Technology Hs (Former Malingao Nhs (Annex New Pualas Nhs) | Tubod (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 7266271.404 |  |  | Completed | 1 |  |  | P00074924MN | 16KF0051 | [5 empty] | MJALONTO BUILDER AND ENTERPRISES
20495 | NC 2016 | TECHVOC | Region X | Lanao Del Norte | 315102 | Lanao Del Norte Provincial Science And Technology Hs (Former Malingao Nhs (Annex New Pualas Nhs) | Tubod (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1 |  |  | P00075304MN | 16KF0053 | [5 empty] | MARKBUILT ENTERPRISES
20496 | NC 2016 | TECHVOC | Region X | Lanao Del Norte | 304008 | Linamon Nhs | Linamon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2589808.27 |  |  | Completed | 1 |  |  | P00075302MN | 16KF0052 | [5 empty] | AMSCON BUILDERS AND ENTERPRISES
20497 | NC 2016 | TECHVOC | Region X | Lanao Del Norte |  | Marcela T. Mabanta Nhs | Kauswagan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2620710.36 |  |  | Completed | 1 |  |  | P00075300MN | 16KF0057 | [5 empty] | TESAR BUILDERS
20498 | NC 2016 | TECHVOC | Region X | Lanao Del Norte | 304003 | Kapatagan Nhs | Kapatagan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1
20499 | NC 2016 | SHS | Region X | Lanao Del Norte | 304003 | Kapatagan Nhs | Kapatagan | 2 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16022138.898 |  |  | Completed | 1
20500 | NC 2016 | SHS | Region X | Lanao Del Norte | 304004 | Lala Nhs | Lala | 2 | 1 | 24 | 4STY24CL | BATCH 13 CL | 43039971.1394 |  |  | Completed | 1
20501 | NC 2016 | SHS | Region X | Lanao Del Norte | 304004 | Lala Nhs | Lala | 2 |  | 12 | 4STY12CL | BATCH 13 CL | 22919343.62 |  |  | Completed | 1
20502 | NC 2016 | TECHVOC | Region X | Lanao Del Norte | 315101 | Sultan Ali Dimaporo Memorial Is | Sultan Naga Dimaporo (Karomatan) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2765539.15 |  |  | Completed | 1
20503 | NC 2016 | SHS | Region X | Malaybalay City | 303946 | Bangcud Nhs | City Malaybalay (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12020076.849 |  |  | Completed | 1
20504 | NC 2016 | SHS | Region X | Malaybalay City | 303950 | Bukidnon Nhs | City Malaybalay (Capital) | 2 | 1 | 15 | 3STY15CL | BATCH 11 CL | 23506314.795 |  |  | Completed | 1 |  |  | Construction of School Building @ BNHS (1unit of 3S 15CL) | 16KA0028 |  | 2016-07-21 | 2016-08-02
20505 | NC 2016 | K10 | Region X | Malaybalay City |  | Casisang Cs | City Malaybalay (Capital) | 2 | 1 | 15 | 3STY15CL | BATCH 11 CL | 21583013.45 |  |  | Completed | 1 |  |  | Construction of School Building @ Casisang CS- SHS (1unit of 3S 15CL) | 16KA0029 |  | 2016-07-21
20506 | NC 2016 | K10 | Region X | Malaybalay City |  | Casisang Cs | City Malaybalay (Capital) | 2 |  | 12 | 3STY12CL | BATCH 11 CL | 18422268.79 |  |  | Completed | 1 |  |  | Construction of School Building @ Casisang CS- SHS (1unit of 3S 12CL) | 16KA0030 |  | 2016-07-21
20507 | NC 2016 | K10 | Region X | Malaybalay City | 314904 | Malaybalay City National Science Hs | City Malaybalay (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20089495.669 |  |  | Completed | 1
20508 | NC 2016 | SHS | Region X | Misamis Occidental | 304024 | Aloran Trade Hs | Aloran | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 23506314.795 |  |  | Completed | 1 |  |  | P00275970MN-CW1 | 16KI0042 | [5 empty] | DICON BUILDERS CORP.
20509 | NC 2016 | TECHVOC | Region X | Misamis Occidental | 304024 | Aloran Trade Hs | Aloran | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  | 16KJ10028 |  |  | 2016-07-28
20510 | NC 2016 | TECHVOC | Region X | Misamis Occidental | 304025 | Baliangao Sof | Baliangao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  | 16KJ10029 |  |  | 2016-07-28
20511 | NC 2016 | SHS | Region X | Misamis Occidental | 304040 | Looc Nhs | Plaridel | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1 |  |  | P00275975MN-CW1 | 16KI0043 | [5 empty] | RUDHIL CONST. & ENTERPRISES, INC
20512 | NC 2016 | TECHVOC | Region X | Misamis Occidental | 315207 | Sibugon Is | Lopez Jaena | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  | 16KJ10030 |  |  | 2016-07-28
20513 | NC 2016 | TECHVOC | Region X | Misamis Occidental | 304028 | Bonifacio Nhs | Bonifacio | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
20514 | NC 2016 | SHS | Region X | Misamis Occidental | 304031 | Clarin Nhs | Clarin | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1
20515 | NC 2016 | SHS | Region X | Misamis Occidental | 304031 | Clarin Nhs | Clarin | 2 |  | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
20516 | NC 2016 | TECHVOC | Region X | Misamis Occidental | 304034 | Diwat National High School | Bonifacio | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2666968.4882 |  |  | Completed | 1
20517 | NC 2016 | SHS | Region X | Misamis Occidental | 304035 | Don Victoriano Nhs | Don Victoriano Chiongbian | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 7071751.654 |  |  | Completed | 1
20518 | NC 2016 | SHS | Region X | Misamis Occidental | 304046 | Nueva Vista National High School | Don Victoriano Chiongbian | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9008016.57 |  |  | Completed | 1
20519 | NC 2016 | SHS | Region X | Misamis Oriental | 304061 | Baliwagan Nhs | Balingasag | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31964205.49 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20520 | NC 2016 | SHS | Region X | Misamis Oriental | 304062 | Binuangan Nhs | Binuangan | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6835304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20521 | NC 2016 | K10 | Region X | Misamis Oriental | 127718 | Bolisong Es | Kinoguitan | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1924740.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20522 | NC 2016 | SHS | Region X | Misamis Oriental | 304066 | Consuelo Nhs | Magsaysay (Linugos) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6845304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20523 | NC 2016 | K10 | Region X | Misamis Oriental | 304077 | Kinoguitan National Agricultural Hs | Kinoguitan | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11027342.59 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20524 | NC 2016 | SHS | Region X | Misamis Oriental | 304080 | Looc Nhs | Salay | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6845304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20525 | NC 2016 | SHS | Region X | Misamis Oriental | 315304 | Lumbo Nhs | Lagonglong | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6845304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20526 | NC 2016 | TECHVOC | Region X | Misamis Oriental | 315304 | Lumbo Nhs | Lagonglong | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5260000 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20527 | NC 2016 | K10 | Region X | Misamis Oriental | 127730 | Mabini Es | Binuangan | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6795304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20528 | NC 2016 | K10 | Region X | Misamis Oriental | 127620 | Mambayaan Es | Balingasag | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6835304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20529 | NC 2016 | K10 | Region X | Misamis Oriental | 127886 | Mantangale Es | Balingoan | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8825713.3 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20530 | NC 2016 | K10 | Region X | Misamis Oriental | 127890 | Pook Es | Talisayan | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1964740.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20531 | NC 2016 | SHS | Region X | Misamis Oriental | 315306 | Rosario Nhs | Balingasag | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6835304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20532 | NC 2016 | SHS | Region X | Misamis Oriental | 304096 | Salay Nhs | Salay | 1 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11107342.5917 |  |  | Completed | 1 |  |  |  |  | 2016-02-12 | 2016-02-17 | 2016-03-10
20533 | NC 2016 | SHS | Region X | Misamis Oriental | 304096 | Salay Nhs | Salay | 1 |  | 10 | 2STY10CL | BATCH 1 CL | 12821310.093 |  |  | Completed | 1 |  |  |  |  | 2016-02-12 | 2016-02-17 | 2016-03-10
20534 | NC 2016 | SHS | Region X | Misamis Oriental | 304097 | San Isidro Nhs | Balingasag | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6835304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20535 | NC 2016 | SHS | Region X | Misamis Oriental | 304098 | San Juan Nhs | Balingasag | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1964740.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20536 | NC 2016 | K10 | Region X | Misamis Oriental | 127896 | Sta. Ines Es | Talisayan | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15669491.95 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20537 | NC 2016 | SHS | Region X | Misamis Oriental | 304101 | Sugbongcogon Nhs | Sugbongcogon | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11037342.59 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20538 | NC 2016 | SHS | Region X | Misamis Oriental | 304093 | Talisayan Nhs | Talisayan | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11037342.59 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20539 | NC 2016 | TECHVOC | Region X | Misamis Oriental | 304093 | Talisayan Nhs | Talisayan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2660000 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30
20540 | NC 2016 | SHS | Region X | Misamis Oriental | 304059 | Alubijid Nchs | Alubijid | 2 | 1 | 20 | 4STY20CL | BATCH 1 CL | 31302890.27 |  |  | Completed | 1
20541 | NC 2016 | SHS | Region X | Misamis Oriental | 304059 | Alubijid Nchs | Alubijid | 2 |  | 4 | 2STY4CL | BATCH 1 CL | 6359337.6381 |  |  | Completed | 1
20542 | NC 2016 | TECHVOC | Region X | Misamis Oriental | 304059 | Alubijid Nchs | Alubijid | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2429549.27 |  |  | Completed | 1
20543 | NC 2016 | K10 | Region X | Misamis Oriental | 127635 | Aposkahoy Ii Es | Claveria | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2690829 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20544 | NC 2016 | SHS | Region X | Misamis Oriental | 315309 | Aposkahoy Nhs | Claveria | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10977342.59 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20545 | NC 2016 | K10 | Region X | Misamis Oriental | 127865 | Baluarte Es | Tagoloan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20546 | NC 2016 | K10 | Region X | Misamis Oriental | 127922 | Biga Es | Lugait | 2 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13550000 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20547 | NC 2016 | SHS | Region X | Misamis Oriental | 304064 | Cabalantian Nhs | Manticao | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10977342.59 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20548 | NC 2016 | K10 | Region X | Misamis Oriental | 127866 | Casinglot Es | Tagoloan | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8775713.3 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20549 | NC 2016 | K10 | Region X | Misamis Oriental | 127901 | Don F. Jacinto Es | Villanueva | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6785304.52 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-14 | 2016-04-26
20550 | NC 2016 | K10 | Region X | Misamis Oriental | 304069 | Dr. Gerardo Sabal Mnhs | Claveria | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10977342.59 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20551 | NC 2016 | SHS | Region X | Misamis Oriental | 304071 | Hinaplanan Nhs | Claveria | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6785304.52 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20552 | NC 2016 | K10 | Region X | Misamis Oriental | 127703 | Ignacio S. Cruz Es | Jasaan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20553 | NC 2016 | SHS | Region X | Misamis Oriental | 304072 | Initao Nchs | Initao | 2 | 1 | 16 | 2STY8CL | BATCH 7 CL | 21954685.18 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20554 | NC 2016 | SHS | Region X | Misamis Oriental | 315317 | Kalacapan Nhs | Initao | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8775713.3 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20555 | NC 2016 | TECHVOC | Region X | Misamis Oriental | 315317 | Kalacapan Nhs | Initao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2600000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20556 | NC 2016 | K10 | Region X | Misamis Oriental | 304074 | Kalingagan National High School | Villanueva | 2 | 1 | 12 | 3STY12CL | BATCH 7 CL | 19350000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20557 | NC 2016 | TECHVOC | Region X | Misamis Oriental | 304074 | Kalingagan National High School | Villanueva | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2600000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20558 | NC 2016 | SHS | Region X | Misamis Oriental | 304078 | Laguindingan Nhs | Laguindingan | 2 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31914205.49 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20559 | NC 2016 | TECHVOC | Region X | Misamis Oriental | 304078 | Laguindingan Nhs | Laguindingan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2600000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20560 | NC 2016 | K10 | Region X | Misamis Oriental | 127589 | Lanao Es | Alubijid | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20561 | NC 2016 | SHS | Region X | Misamis Oriental | 304079 | Libertad Nhs | Libertad | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13550000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20562 | NC 2016 | TECHVOC | Region X | Misamis Oriental | 304079 | Libertad Nhs | Libertad | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2600000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20563 | NC 2016 | SHS | Region X | Misamis Oriental | 304081 | Lourdes Alubijid Nhs | Alubijid | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13550000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20564 | NC 2016 | K10 | Region X | Misamis Oriental | 127930 | Lubilan Es | Naawan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20565 | NC 2016 | K10 | Region X | Misamis Oriental | 127842 | Luyong Bonbon Es | Opol | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6785304.52 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20566 | NC 2016 | SHS | Region X | Misamis Oriental | 304083 | Malagana Nhs | Claveria | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6785304.52 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20567 | NC 2016 | K10 | Region X | Misamis Oriental | 127933 | Maputi Es | Naawan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6785304.52 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20568 | NC 2016 | K10 | Region X | Misamis Oriental | 127868 | Maribojoc Es | Tagoloan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1
20569 | NC 2016 | SHS | Region X | Misamis Oriental | 304086 | Matangad Nhs | Gitagum | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10977342.59 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20570 | NC 2016 | K10 | Region X | Misamis Oriental | 304088 | Mat-I (Naawan) Nhs | Naawan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6785304.52 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20571 | NC 2016 | K10 | Region X | Misamis Oriental | 127655 | Mat-I Cs | Claveria | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10977342.59 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20572 | NC 2016 | K10 | Region X | Misamis Oriental | 127709 | Natubo Es | Jasaan | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8775713.3 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20573 | NC 2016 | TECHVOC | Region X | Misamis Oriental | 304094 | Opol Nsts | Opol | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
20574 | NC 2016 | SHS | Region X | Misamis Oriental | 304094 | Opol Nsts | Opol | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1
20575 | NC 2016 | K10 | Region X | Misamis Oriental | 127658 | Panampawan Es | Claveria | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2690829 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20576 | NC 2016 | K10 | Region X | Misamis Oriental | 127908 | San Martin Es | Villanueva | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 22650000 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-14 | 2016-04-26
20577 | NC 2016 | K10 | Region X | Misamis Oriental |  | Shs In Lugait, Misamis Oriental | Lugait | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 16125000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20578 | NC 2016 | SHS | Region X | Misamis Oriental | 304099 | Sta Ana Nhs | Tagoloan | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8775713.3 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20579 | NC 2016 | TECHVOC | Region X | Misamis Oriental | 304099 | Sta Ana Nhs | Tagoloan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2600000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20580 | NC 2016 | K10 | Region X | Misamis Oriental | 127873 | Tagoloan Cs | Tagoloan | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8775713.3 |  |  | Completed | 1 | [5 empty] | 2016-04-13 | 2016-04-25
20581 | NC 2016 | K10 | Region X | Misamis Oriental | 127696 | Tagpaco Es | Initao | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20582 | NC 2016 | SHS | Region X | Misamis Oriental | 315315 | Tambobong-Balacanas Nhs | Villanueva | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8775713.3 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18
20583 | NC 2016 | K10 | Region X | Misamis Oriental | 127767 | Tangkub Es | Libertad | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6785304.52 |  |  | Completed | 1 | [5 empty] | 2016-04-13 | 2016-04-25
20584 | NC 2016 | K10 | Region X | Misamis Oriental | 127597 | Taparak Es | Alubijid | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20585 | NC 2016 | K10 | Region X | Misamis Oriental | 127666 | Tipolohon Es | Claveria | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27
20586 | NC 2016 | TECHVOC | Region X | Oroquieta City | 304045 | Misamis Occidental Nhs | Oroquieta City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2661358.7 |  |  | Completed | 1
20587 | NC 2016 | SHS | Region X | Oroquieta City | 304045 | Misamis Occidental Nhs | Oroquieta City (Capital) | 1 | 1 | 32 | 4STY32CL | BATCH 13 CL | 48980442.044 |  |  | Completed | 1 |  |  | P002759789MN-CW1 | 16KI0040 | [5 empty] | GENETIAN BUILDERS
20588 | NC 2016 | SHS | Region X | Oroquieta City | 304045 | Misamis Occidental Nhs | Oroquieta City (Capital) | 1 |  | 20 | 4STY20CL | BATCH 13 CL | 34208179.297 |  |  | Completed | 1 |  |  | P00275978MN-CW1 | 16KI0040 | [5 empty] | RUDHIL CONST. & ENTERPRISES, INC
20589 | NC 2016 | SHS | Region X | Oroquieta City | 304045 | Misamis Occidental Nhs | Oroquieta City (Capital) | 1 |  | 8 | 4STY8CL | BATCH 13 CL | 16377270.724 |  |  | Completed | 1
20590 | NC 2016 | TECHVOC | Region X | Oroquieta City | 304057 | Talairon Nhs | Oroquieta City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2663131.1667 |  |  | Completed | 1
20591 | NC 2016 | K10 | Region X | Ozamis City | 304164 | Calabayan National High School | Ozamis City | 2 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8416000 |  |  | Completed | 1
20592 | NC 2016 | K10 | Region X | Ozamis City | 304164 | Calabayan National High School | Ozamis City | 2 |  | 4 | 2STY4CL | BATCH 1 CL | 6472000 |  |  | Completed | 1
20593 | NC 2016 | TECHVOC | Region X | Ozamis City | 304164 | Calabayan National High School | Ozamis City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2800000 |  |  | Completed | 1
20594 | NC 2016 | K10 | Region X | Ozamis City | 203506 | Capucao C Es | Ozamis City | 2 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1160000 |  |  | Completed | 1
20595 | NC 2016 | K10 | Region X | Ozamis City | 315701 | Kinuman Norte National High School | Ozamis City | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8396000 |  |  | Completed | 1
20596 | NC 2016 | K10 | Region X | Ozamis City | 315701 | Kinuman Norte National High School | Ozamis City | 2 |  | 3 | 1STY3CL | BATCH 3 CL | 2881000 |  |  | Completed | 1
20597 | NC 2016 | TECHVOC | Region X | Ozamis City | 315701 | Kinuman Norte National High School | Ozamis City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2650000 |  |  | Completed | 1
20598 | NC 2016 | K10 | Region X | Ozamis City | 304161 | Labinay National High School | Ozamis City | 2 | 1 | 6 | 1STY3CL | BATCH 9 CL | 5662000 |  |  | Completed | 1
20599 | NC 2016 | SHS | Region X | Ozamis City | 304163 | Labo Nhs | Ozamis City | 2 | 1 | 12 | 3STY12CL | BATCH 3 CL | 18223000 |  |  | Completed | 1
20600 | NC 2016 | SHS | Region X | Ozamis City | 304166 | Montol Nhs | Ozamis City | 2 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13048000 |  |  | Completed | 1
20601 | NC 2016 | SHS | Region X | Ozamis City | 304166 | Montol Nhs | Ozamis City | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6462000 |  |  | Completed | 1
20602 | NC 2016 | TECHVOC | Region X | Ozamis City | 304166 | Montol Nhs | Ozamis City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2650000 |  |  | Completed | 1
20603 | NC 2016 | K10 | Region X | Ozamis City | 304167 | Ozamiz City National High School | Ozamis City | 2 | 1 | 40 | 4STY20CL | BATCH 9 CL | 68396358.594 |  |  | Completed | 1
20604 | NC 2016 | K10 | Region X | Ozamis City | 304167 | Ozamiz City National High School | Ozamis City | 2 |  | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1
20605 | NC 2016 | TECHVOC | Region X | Ozamis City | 304168 | Ozamiz City School Of Arts And Trades | Ozamis City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
20606 | NC 2016 | SHS | Region X | Ozamis City | 304168 | Ozamiz City School Of Arts And Trades | Ozamis City | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1
20607 | NC 2016 | SHS | Region X | Ozamis City | 304169 | Pulot Nhs | Ozamis City | 2 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12898000 |  |  | Completed | 1
20608 | NC 2016 | TECHVOC | Region X | Ozamis City | 304169 | Pulot Nhs | Ozamis City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2600000 |  |  | Completed | 1
20609 | NC 2016 | SHS | Region X | Ozamis City | 304165 | San Antonio Nhs | Ozamis City | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
20610 | NC 2016 | SHS | Region X | Ozamis City | 304165 | San Antonio Nhs | Ozamis City | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
20611 | NC 2016 | SHS | Region X | Ozamis City | 304162 | Tabid Nhs | Ozamis City | 2 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10985000 |  |  | Completed | 1
20612 | NC 2016 | SHS | Region X | Ozamis City | 304162 | Tabid Nhs | Ozamis City | 2 |  | 4 | 2STY4CL | BATCH 3 CL | 6382000 |  |  | Completed | 1
20613 | NC 2016 | TECHVOC | Region X | Ozamis City | 304162 | Tabid Nhs | Ozamis City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2600000 |  |  | Completed | 1
20614 | NC 2016 | SHS | Region X | Tangub City | 304054 | Caniangan Nhs | Tangub City | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8753897.86 |  |  | Completed | 1
20615 | NC 2016 | TECHVOC | Region X | Tangub City | 304041 | Lorenzo Tan Nhs | Tangub City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
20616 | NC 2016 | TECHVOC | Region X | Tangub City | 304053 | Silangit Nhs | Tangub City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
20617 | NC 2016 | SHS | Region X | Tangub City | 323302 | Simasay Nhs | Tangub City | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9031363.81 |  |  | Completed | 1
20618 | NC 2016 | TECHVOC | Region X | Tangub City | 304056 | Sumirap Nhs | Tangub City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2667882.5863 |  |  | Completed | 1
20619 | NC 2016 | SHS | Region X | Tangub City | 304171 | Tangub City Nhs | Tangub City | 2 | 1 | 18 | 2STY6CL | BATCH 13 CL | 27100098.835 |  |  | Completed | 1
20620 | NC 2016 | SHS | Region X | Tangub City | 304171 | Tangub City Nhs | Tangub City | 2 |  | 4 | 2STY4CL | BATCH 13 CL | 6950951.864 |  |  | Completed | 1
20621 | NC 2016 | K10 | Region X | Valencia City | 126846 | Lumbo Es | City Of Valencia | 4 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15271327.92 |  |  | Completed | 1
20622 | NC 2016 | SHS | Region X | Valencia City | 303988 | Valencia Nhs | City Of Valencia | 4 | 1 | 20 | 2STY10CL | BATCH 13 CL | 26442620.18 |  |  | Completed | 1
20623 | NC 2016 | K10 | Region X | Misamis Occidental | 127336 | Canibungan Daku Es | Clarin | 2 | 1 | 6 | 1STY3CL w/ toilet attached | BATCH 14 CL | 5685184.88 |  |  | Completed | 1
20624 | NC 2016 | K10 | Region X | Misamis Occidental | 127346 | Segatic Sur Es To Segatic Norte Ps | Clarin | 2 | 1 | 2 | 1STY2CL w/ toilet attached | BATCH 14 CL | 1938606.04 |  |  | Completed | 1
30336 | NC 2017 | TVL | Region X | Bukidnon | 314925 | Baungon NHS - Danatag Annex | BAUNGON | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3083000 |  |  | Completed | 1
30337 | NC 2017 | K10 | Region X | Bukidnon | 126266 | Imbatug CES | BAUNGON | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4286533.3 |  |  | Completed | 1
30338 | NC 2017 | K10 | Region X | Bukidnon | 126266 | Imbatug CES | BAUNGON | 1 |  | 5 | 1STY5CL W/ TOILET | BATCH 4 | 6122487.45 |  |  | Completed | 1
30339 | NC 2017 | K10 | Region X | Bukidnon | 126272 | Lingating ES | BAUNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2820000 |  |  | Completed | 1
30340 | NC 2017 | K10 | Region X | Bukidnon | 126305 | Cabanglasan ES | CABANGLASAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3250000 |  |  | Completed | 1
30341 | NC 2017 | K10 | Region X | Bukidnon | 126295 | Mainaga ES | CABANGLASAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3328000 |  |  | Completed | 1
30342 | NC 2017 | K10 | Region X | Bukidnon | 126349 | Kawilihan ES | DON CARLOS | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2875119.92 |  |  | Completed | 1
30343 | NC 2017 | K10 | Region X | Bukidnon | 126351 | Kibatang Elementary School | DON CARLOS | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2972297.68 |  |  | Completed | 1
30344 | NC 2017 | K10 | Region X | Bukidnon | 126357 | New Nongnongan ES | DON CARLOS | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2972297.68 |  |  | Completed | 1
30345 | NC 2017 | K10 | Region X | Bukidnon | 126360 | Pinamaloy ES | DON CARLOS | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3048295.76 |  |  | Completed | 1
30346 | NC 2017 | K10 | Region X | Bukidnon | 126360 | Pinamaloy ES | DON CARLOS | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2998295.76 |  |  | Completed | 1
30347 | NC 2017 | K10 | Region X | Bukidnon | 126367 | Sinangguyan ES | DON CARLOS | 3 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 4 | 6522650.72 |  |  | Completed | 1
30348 | NC 2017 | TVL | Region X | Bukidnon | 303966 | Lampanusan NHS | KALILANGAN | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2792000 |  |  | Completed | 1
30349 | NC 2017 | K10 | Region X | Bukidnon | 126449 | Old Kibawe ES | KIBAWE | 3 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5670704.69 |  |  | Completed | 1
30350 | NC 2017 | K10 | Region X | Bukidnon | 126494 | Tawas ES | KITAOTAO | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2875119.92 |  |  | Completed | 1
30351 | NC 2017 | K10 | Region X | Bukidnon | 126497 | Babahagon ES | LANTAPAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2880000 |  |  | Completed | 1
30352 | NC 2017 | K10 | Region X | Bukidnon | 126501 | Basac ES | LANTAPAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3000000 |  |  | Completed | 1
30353 | NC 2017 | K10 | Region X | Bukidnon | 126501 | Basac ES | LANTAPAN | 2 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3000000 |  |  | Completed | 1
30354 | NC 2017 | K10 | Region X | Bukidnon | 126502 | Bugcaon ES | LANTAPAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2946000 |  |  | Completed | 1
30355 | NC 2017 | K10 | Region X | Bukidnon | 126505 | Kaatuan ES | LANTAPAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3484000 |  |  | Completed | 1
30356 | NC 2017 | K10 | Region X | Bukidnon | 126506 | Kibanggay ES | LANTAPAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3285000 |  |  | Completed | 1
30357 | NC 2017 | K10 | Region X | Bukidnon | 126511 | Songco ES | LANTAPAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3255000 |  |  | Completed | 1
30358 | NC 2017 | K10 | Region X | Bukidnon | 126514 | Camp 14 ES | LIBONA | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3802600 |  |  | REVERTED | 0
30359 | NC 2017 | K10 | Region X | Bukidnon | 126517 | Crossing ES | LIBONA | 1 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5005000 |  |  | Completed | 1
30360 | NC 2017 | K10 | Region X | Bukidnon | 126519 | Dona P1Lar ES | LIBONA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2884000 |  |  | Completed | 1
30361 | NC 2017 | TVL | Region X | Bukidnon | 303969 | Kinawe National High School | LIBONA | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2661000 |  |  | Completed | 1
30362 | NC 2017 | K10 | Region X | Bukidnon | 126523 | Laturan ES | LIBONA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2965000 |  |  | Completed | 1
30363 | NC 2017 | TVL | Region X | Bukidnon | 303968 | Libona NHS | LIBONA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2888000 |  |  | Completed | 1
30364 | NC 2017 | K10 | Region X | Bukidnon | 126600 | Kalingking ES | MALITBOG | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2797000 |  |  | Completed | 1
30365 | NC 2017 | K10 | Region X | Bukidnon | 126604 | Mabuhay ES | MALITBOG | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3850000 |  |  | Completed | 1
30366 | NC 2017 | K10 | Region X | Bukidnon | 126605 | Malitbog CES | MALITBOG | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2808000 |  |  | Completed | 1
30367 | NC 2017 | K10 | Region X | Bukidnon | 126605 | Malitbog CES | MALITBOG | 1 |  | 2 | 1STY2CL | BATCH 4 | 2808000 |  |  | Completed | 1
30368 | NC 2017 | TVL | Region X | Bukidnon | 303972 | Malitbog Nat. Agr'I. HS | MALITBOG | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2805000 |  |  | Completed | 1
30369 | NC 2017 | K10 | Region X | Bukidnon | 126619 | Alae CES | MANOLO FORTICH | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3277063.5 |  |  | Completed | 1
30370 | NC 2017 | K10 | Region X | Bukidnon | 126619 | Alae CES | MANOLO FORTICH | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4255616.62 |  |  | Completed | 1
30371 | NC 2017 | K10 | Region X | Bukidnon | 126621 | Bagalangit Elementary School | MANOLO FORTICH | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2829000 |  |  | Completed | 1
30372 | NC 2017 | SHS | Region X | Bukidnon | 314901 | Dalirig NHS | MANOLO FORTICH | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2775000 |  |  | Completed | 1
30373 | NC 2017 | TVL | Region X | Bukidnon | 314901 | Dalirig NHS | MANOLO FORTICH | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2635000 |  |  | Completed | 1
30374 | NC 2017 | K10 | Region X | Bukidnon | 126629 | Impakibel ES | MANOLO FORTICH | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2825000 |  |  | Completed | 1
30375 | NC 2017 | K10 | Region X | Bukidnon | 126634 | Lunucan ES | MANOLO FORTICH | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2746000 |  |  | Completed | 1
30376 | NC 2017 | TVL | Region X | Bukidnon | 303974 | Manolo Fortich NHS | MANOLO FORTICH | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3020000 |  |  | Completed | 1
30377 | NC 2017 | K10 | Region X | Bukidnon | 126643 | San Miguel ES | MANOLO FORTICH | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2805000 |  |  | Completed | 1
30378 | NC 2017 | TVL | Region X | Bukidnon | 303983 | Sankanan NHS | MANOLO FORTICH | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2635000 |  |  | Completed | 1
30379 | NC 2017 | K10 | Region X | Bukidnon | 126649 | Anahawon ES | MARAMAG | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2849745.92 |  |  | Completed | 1
30380 | NC 2017 | K10 | Region X | Bukidnon | 126656 | Danggawan Elementary School | MARAMAG | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2977753.63 |  |  | Completed | 1
30381 | NC 2017 | K10 | Region X | Bukidnon | 126659 | Francisco Villa ES | MARAMAG | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2793745.92 |  |  | Completed | 1
30382 | NC 2017 | K10 | Region X | Bukidnon | 126675 | Tubigon ES | MARAMAG | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3009320.67 |  |  | Completed | 1
30383 | NC 2017 | K10 | Region X | Bukidnon | 126675 | Tubigon ES | MARAMAG | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3009320.67 |  |  | Completed | 1
30384 | NC 2017 | TVL | Region X | Bukidnon | 303962 | Kimanait NHS | PANGANTUCAN | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2790000 |  |  | Completed | 1
30385 | NC 2017 | TVL | Region X | Bukidnon | 303962 | Kimanait NHS | PANGANTUCAN | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3864000 |  |  | Completed | 1
30386 | NC 2017 | K10 | Region X | Bukidnon | 126688 | Lantay Elementary School | PANGANTUCAN | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2860000 |  |  | Completed | 1
30387 | NC 2017 | K10 | Region X | Bukidnon | 126689 | MADAYA ELEMENTARY SCHOOL | PANGANTUCAN | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5005000 |  |  | Completed | 1
30388 | NC 2017 | K10 | Region X | Bukidnon | 126690 | Malipayon ES | PANGANTUCAN | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2860000 |  |  | Completed | 1
30389 | NC 2017 | K10 | Region X | Bukidnon | 126690 | Malipayon ES | PANGANTUCAN | 4 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2860000 |  |  | Completed | 1
30390 | NC 2017 | TVL | Region X | Bukidnon | 303978 | Pangantucan NHS | PANGANTUCAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3008000 |  |  | Completed | 1
30391 | NC 2017 | K10 | Region X | Bukidnon | 126701 | San Isidro Elementary School | PANGANTUCAN | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5000000 |  |  | Completed | 1
30392 | NC 2017 | K10 | Region X | Bukidnon | 126705 | Apyao ES | QUEZON | 3 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 4 | 7016975.54 |  |  | Completed | 1
30393 | NC 2017 | K10 | Region X | Bukidnon | 126705 | Apyao ES | QUEZON | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2977385.79 |  |  | Completed | 1
30394 | NC 2017 | K10 | Region X | Bukidnon | 126712 | Lumintao ES | QUEZON | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3035933.7 |  |  | Completed | 1
30395 | NC 2017 | K10 | Region X | Bukidnon | 126712 | Lumintao ES | QUEZON | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3035933.7 |  |  | Completed | 1
30396 | NC 2017 | K10 | Region X | Bukidnon | 126734 | Menongan ES | QUEZON | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3037606.5 |  |  | Completed | 1
30397 | NC 2017 | K10 | Region X | Bukidnon | 126715 | Merangeran ES | QUEZON | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2875119.92 |  |  | Completed | 1
30398 | NC 2017 | K10 | Region X | Bukidnon | 126740 | Puntian ES | QUEZON | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4145278 |  |  | Completed | 1
30399 | NC 2017 | K10 | Region X | Bukidnon | 126752 | Durian ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3359000 |  |  | Completed | 1
30400 | NC 2017 | K10 | Region X | Bukidnon | 126757 | Kauswagan Elementary School | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3200000 |  |  | Completed | 1
30401 | NC 2017 | K10 | Region X | Bukidnon | 126760 | Little Baguio ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2900000 |  |  | Completed | 1
30402 | NC 2017 | K10 | Region X | Bukidnon | 126763 | Magkalungay ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3323000 |  |  | Completed | 1
30403 | NC 2017 | K10 | Region X | Bukidnon | 126770 | Namnam ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3238000 |  |  | Completed | 1
30404 | NC 2017 | K10 | Region X | Bukidnon | 126787 | OCASION ELEMENTARY SCHOOL | SUMILAO | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3850000 |  |  | Completed | 1
30405 | NC 2017 | TVL | Region X | Bukidnon | 314924 | Sumilao NHS - Vista Villa Annex | SUMILAO | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2640000 |  |  | Completed | 1
30406 | NC 2017 | TVL | Region X | Bukidnon | 314924 | Sumilao NHS - Vista Villa Annex | SUMILAO | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2897000 |  |  | Completed | 1
30407 | NC 2017 | K10 | Region X | Bukidnon | 126797 | Cacaon Elementary School | TALAKAG | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2885000 |  |  | Completed | 1
30408 | NC 2017 | K10 | Region X | Bukidnon | 126799 | Cosina ES | TALAKAG | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2910000 |  |  | Completed | 1
30409 | NC 2017 | K10 | Region X | Bukidnon | 126809 | Lingion ES | TALAKAG | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2860000 |  |  | Completed | 1
30410 | NC 2017 | K10 | Region X | Bukidnon | 199525 | New Nebo ES | TALAKAG | 1 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5113000 |  |  | Completed | 1
30411 | NC 2017 | K10 | Region X | Bukidnon | 126826 | Talakag CES | TALAKAG | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2854000 |  |  | Completed | 1
30412 | NC 2017 | TVL | Region X | Bukidnon | 303987 | Talakag NHS | TALAKAG | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2903000 |  |  | Completed | 1
30413 | NC 2017 | K10 | Region X | Bukidnon | 126827 | Tankulan ES | TALAKAG | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2840000 |  |  | Completed | 1
30414 | NC 2017 | K10 | Region X | Bukidnon | 126829 | Tikalaan Cental Elementary School | TALAKAG | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2895000 |  |  | Completed | 1
30415 | NC 2017 | TVL | Region X | Bukidnon | 314919 | Tikalaan National High School | TALAKAG | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2805000 |  |  | Completed | 1
30416 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315401 | Balubal National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00173808MN-CW1 | 17KD0058 |  |  |  |  | 2018-11-16 | JIMWEN CONST. & GEN. MDSE.
30417 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304116 | Indahag National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P0017806MN-CW1 | 17KD0057 |  |  |  |  | 2017-11-21 | RUDHIL CONST. 7 GEN. MDSE
30418 | NC 2017 | TVL | Region X | Cagayan de Oro City | 304120 | Macabalan NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 11000000 |  |  | Completed | 1 |  |  | P00173807MN-CW1 | 17KD0056 |  |  |  |  | 2017-11-16 | H & N BUILDERS AND ENTERPRISE
30419 | NC 2017 | TVL | Region X | El Salvador | 304065 | Cogon NHS | CITY OF EL SALVADOR | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 5227491.84 |  |  | Completed | 1 |  |  |  | 17KL0128
30420 | NC 2017 | K10 | Region X | El Salvador | 325701 | SAN FRANCISCO DE ASIS NATIONAL HIGH SCHOOL | CITY OF EL SALVADOR | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0112
30421 | NC 2017 | K10 | Region X | Iligan City | 128140 | Dona Juana A. Lluch MCS | ILIGAN CITY | 0 | 1 | 8 | 2STY8CL | BATCH 4 | 17024790.26 |  |  | Completed | 1 |  |  | P00173811MN | 17KF0145 | [5 empty] | AL FAHDEL CONT. & ENG'G.
30422 | NC 2017 | K10 | Region X | Iligan City | 128161 | Sgt. Miguel Canoy MCS | ILIGAN CITY | 0 | 1 | 6 | 2STY6CL | BATCH 4 | 12462753.8 |  |  | Completed | 1 |  |  | P00173812MN | 17KF0122 | [5 empty] | ALFAHAD BUILDERS AND ENTERPRISES
30423 | NC 2017 | K10 | Region X | Lanao del Norte | 126956 | Maria Cristina CS | BALOI | 1 | 1 | 4 | 1STY4CL | BATCH 4 | 4930851.15 |  |  | Completed | 1
30424 | NC 2017 | K10 | Region X | Lanao del Norte | 127011 | SAN ISIDRO ELEMENTARY SCHOOL | KAPATAGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2708745.92 |  |  | Completed | 1
30425 | NC 2017 | K10 | Region X | Lanao del Norte | 127081 | Tunaan PS | LALA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2687745.92 |  |  | Completed | 1
30426 | NC 2017 | K10 | Region X | Lanao del Norte | 127108 | Tambacon ES | MAGSAYSAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2649745.92 |  |  | Completed | 1
30427 | NC 2017 | SHS | Region X | Lanao del Norte | 304016 | Nunungan NHS | NUNUNGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3284745.92 |  |  | Completed | 1
30428 | NC 2017 | K10 | Region X | Lanao del Norte | 127179 | Curva Miagao ES | SALVADOR | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2676745.92 |  |  | Completed | 1
30429 | NC 2017 | K10 | Region X | Lanao del Norte | 127201 | MALA SALUG ELEMENTARY SCHOOL | SAPAD | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2709745.92 |  |  | Completed | 1
30430 | NC 2017 | K10 | Region X | Lanao del Norte | 127022 | Ilian ES | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3785809.68 |  |  | Completed | 1
30431 | NC 2017 | K10 | Region X | Lanao del Norte | 127022 | Ilian ES | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 |  | 3 | 1STY3CL | BATCH 4 | 3785809.68 |  |  | Completed | 1
30432 | NC 2017 | K10 | Region X | Lanao del Norte | 127034 | Sultan Naga Dimaporo Central Elementary School | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 5 | 1STY5CL | BATCH 4 | 6164650.72 |  |  | Completed | 1
30433 | NC 2017 | K10 | Region X | Lanao del Norte | 127224 | Dalama Integrated School | TUBOD (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3118745.92 |  |  | Completed | 1 |  |  | P00173812MN | 17KF0094 | [5 empty] | LANAO BUILDER AND ENTERPRISES
30434 | NC 2017 | K10 | Region X | Lanao del Norte | 315109 | Dalama Integrated School Co Integrated with School ID 127012 | TUBOD (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3118745.92 |  |  | Completed | 1 |  |  | P00173816MN | 17KF0095 | [5 empty] | MJ ALONTO BUILDER AND ENTERPRISES
30435 | NC 2017 | SHS | Region X | Lanao del Norte | 315102 | Lanao del Norte Provincial Science and Technology HS (former Malingao NHS (Annex New Pualas NHS) | TUBOD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2806359.67 |  |  | Completed | 1 |  |  | P00173815MN | 17KF0096 | [5 empty] | NDP CONSTRUCTION DEV'T.
30436 | NC 2017 | K10 | Region X | Malaybalay City | 126574 | Airport Village ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2762949.04 |  |  | Completed | 1
30437 | NC 2017 | K10 | Region X | Malaybalay City | 126579 | Casisang CS | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2762949.04 |  |  | Completed | 1
30438 | NC 2017 | K10 | Region X | Malaybalay City | 126580 | Dalwangan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2789373.65 |  |  | Completed | 1
30439 | NC 2017 | K10 | Region X | Malaybalay City | 126540 | Indalasa ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2886313.86 |  |  | Completed | 1
30440 | NC 2017 | K10 | Region X | Malaybalay City | 126582 | Kalasungay CS | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2795461.73 |  |  | Completed | 1
30441 | NC 2017 | SHS | Region X | Malaybalay City | 314915 | Kalasungay NHS | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2757687.26 |  |  | Completed | 1
30442 | NC 2017 | K10 | Region X | Malaybalay City | 126583 | Kapitan Angel ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2809345.57 |  |  | Completed | 1
30443 | NC 2017 | K10 | Region X | Malaybalay City | 126588 | Natid-asan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2789774.65 |  |  | Completed | 1
30444 | NC 2017 | K10 | Region X | Malaybalay City | 126589 | New Ilocos ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2817314.02 |  |  | Completed | 1
30445 | NC 2017 | TVL | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1 | 1 | 1 | WORKSHOP BLDG. (7X18) | BATCH 4 | 3041746.96 |  |  | Completed | 1 |  |  |  | 17KI0121 | 2017-09-14 | 2017-09-21 | 2017-10-05 | 2017-10-30 | 2017-11-16 | VICTORIANO C. LIM CONSTRUCTION
30446 | NC 2017 | TVL | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1 |  | 1 | WORKSHOP BLDG. (7X18) | BATCH 4 | 3052800.45 |  |  | Completed | 1 |  |  |  | 17KI0119 | 2017-09-14 | 2017-09-21 | 2017-10-05 | 2017-11-17 | 2017-12-04 | VICTORIANO C. LIM CONSTRUCTION
30447 | NC 2017 | TVL | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1 |  | 1 | WORKSHOP BLDG. (7X18) | BATCH 4 | 3041746.96 |  |  | Completed | 1 |  |  |  | 17KI0122 | 2017-09-14 | 2017-09-21 | 2017-10-05 | 2017-11-06 | 2017-11-23 | SGM CONSTRUCTION
30448 | NC 2017 | K10 | Region X | Misamis Occidental | 127253 | Lumbayao Elementary School | ALORAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2697533 |  |  | Completed | 1 |  |  | POO173835MN-CW1 | 17KI0100 | 2017-08-16 | 2017-08-24 | 2017-09-06 | 2017-10-30 | 2017-11-16 | DICON BUILDERS
30449 | NC 2017 | K10 | Region X | Misamis Occidental | 127260 | Monterico ES | ALORAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2697533 |  |  | Completed | 1 |  |  | POO173836MN-CW1 | 17KI0115 | 2017-09-14 | 2017-09-21 | 2017-10-05 | 2017-11-06 | 2017-11-23 | R.T. LIM CONSTRUCTION & SUPPLY
30450 | NC 2017 | K10 | Region X | Misamis Occidental | 127262 | Ozamiz ES | ALORAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2697533 |  |  | Completed | 1 |  |  | POO173837MN-CW1 | 17KI0114 | 2017-09-14 | 2017-09-21 | 2017-10-05 | 2017-10-30 | 2017-11-16 | R.T. LIM CONSTRUCTION & SUPPLY
30451 | NC 2017 | K10 | Region X | Misamis Occidental | 127263 | Pelong ES | ALORAN | 1 | 1 | 5 | 1STY5CL | BATCH 4 | 5915634 |  |  | Completed | 1 |  |  | POO173838MN-CW1 | 17KI0091 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-11-06 | 2017-11-16 | SGM CONSTRUCTION
30452 | NC 2017 | K10 | Region X | Misamis Occidental | 127269 | Tuburan ES | ALORAN | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3872998 |  |  | Completed | 1 |  |  | P00173839MN-CW1 | 17KI0102 | 2017-08-16 | 2017-08-24 | 2017-09-06 | 2017-10-30 | 2017-11-16 | SGM CONSTRUCTION
30453 | NC 2017 | K10 | Region X | Misamis Occidental | 127286 | Bagong Anonang Diut ES | BONIFACIO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2801154 |  |  | Completed | 1
30454 | NC 2017 | TVL | Region X | Misamis Occidental | 304034 | Diwat National High School | BONIFACIO | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3575650 |  |  | Completed | 1
30455 | NC 2017 | K10 | Region X | Misamis Occidental | 201018 | Sibuyon Elementary School | BONIFACIO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2798828 |  |  | Completed | 1
30456 | NC 2017 | K10 | Region X | Misamis Occidental | 127316 | Bonifacio ES | CALAMBA | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3859448 |  |  | Completed | 1 |  |  | P00173843MN-CW1 | 17KI0093 | 2017-08-01 | 2017-08-15 | 2017-09-29 | 2017-10-30 | 2017-11-16 | RDT CONSTRUCTION & GEN. MDSE.
30457 | NC 2017 | K10 | Region X | Misamis Occidental | 127328 | San Isidro ES | CALAMBA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2715456 |  |  | Completed | 1 |  |  | P00173844MN-CW1 | 17KI0092 | 2017-08-01 | 2017-08-15 | 2017-09-29 | 2017-10-30 | 2017-11-16 | RDT CONSTRUCTION & GEN. MDSE.
30458 | NC 2017 | TVL | Region X | Misamis Occidental | 304031 | Clarin NHS | CLARIN | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3866771 |  |  | Completed | 1
30459 | NC 2017 | TVL | Region X | Misamis Occidental | 304031 | Clarin NHS | CLARIN | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3823909 |  |  | Completed | 1
30460 | NC 2017 | K10 | Region X | Misamis Occidental | 304032 | Congressman Hilarion J. Ramiro Jr. Memorial National High School | CLARIN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2772585 |  |  | Completed | 1
30461 | NC 2017 | K10 | Region X | Misamis Occidental | 127341 | Dalingap ES (Francisco Adaza ES) | CLARIN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2787544 |  |  | Completed | 1
30462 | NC 2017 | K10 | Region X | Misamis Occidental | 127352 | Kinangay Sur ES | CLARIN | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4156227 |  |  | Completed | 1
30463 | NC 2017 | K10 | Region X | Misamis Occidental | 127354 | Malibangcao ES | CLARIN | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4153754.28 |  |  | Completed | 1
30464 | NC 2017 | K10 | Region X | Misamis Occidental | 127361 | Concepcion CS | CONCEPCION | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2697533 |  |  | Completed | 1 |  |  | PO0173835MN-CW1 | 17KI0098 | 2017-08-01 | 2017-08-15 | 2017-09-29 | 2017-10-30 | 2017-11-16 | SGM CONSTRUCTION
30465 | NC 2017 | K10 | Region X | Misamis Occidental | 127363 | Guiban ES | CONCEPCION | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2720252 |  |  | Completed | 1 |  |  | PO0173846MN-CW1 | 17KI0098 | 2017-11-15 | 2017-11-21 | 2017-12-05 | 2017-12-29 | 2018-01-15 | LONG ISLAND BUILDERS AND CONSTRUCTION
30466 | NC 2017 | SHS | Region X | Misamis Occidental | 315211 | Lampasan Integrated School | DON VICTORIANO CHIONGBIAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2784748 |  |  | Completed | 1
30467 | NC 2017 | TVL | Region X | Misamis Occidental | 304046 | Nueva Vista National High School | DON VICTORIANO CHIONGBIAN | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3474335 |  |  | Completed | 1
30468 | NC 2017 | K10 | Region X | Misamis Occidental | 127393 | Jimenez Central School | JIMENEZ | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3875345 |  |  | Completed | 1 |  |  | PO0173847MN-CW1 | 17KI0108 | 2017-08-16 | 2017-08-24 | 2017-09-06 | 2017-12-29 | 2018-01-15 | CDY BUILDERS
30469 | NC 2017 | K10 | Region X | Misamis Occidental | 127418 | Katipa ES | LOPEZ JAENA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2727444 |  |  | Completed | 1 |  |  | PO0173848MN-CW1 | 17KI0105 | 2017-08-16 | 2017-08-24 | 2017-09-06 | 2017-10-30 | 2017-11-16 | AFG ZILLION CONST. CORP.
30470 | NC 2017 | K10 | Region X | Misamis Occidental | 127422 | Macalibre Alto ES | LOPEZ JAENA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2697533 |  |  | Completed | 1 |  |  | PO0173849MN-CW1 | 17KI0104 | 2017-08-16 | 2017-08-24 | 2017-09-06 | 2017-10-30 | 2017-11-16 | DDS BUILDERS
30471 | NC 2017 | K10 | Region X | Misamis Occidental | 127425 | Manguehan ES | LOPEZ JAENA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2697533 |  |  | Completed | 1 |  |  | PO0173850MN-CW1 | 17KI0104 | 2017-08-16 | 2017-08-24 | 2017-09-06 | 2017-10-30 | 2017-11-16 | RDT CONSTRUCTION & GEN. MDSE.
30472 | NC 2017 | K10 | Region X | Misamis Occidental | 127478 | Camanucan PS | PANAON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2697533 |  |  | Completed | 1 |  |  | PO0173851MN-CW1 | 17KI110 | 2017-08-16 | 2017-08-24 | 2017-09-06 | 2017-10-30 | 2017-11-16 | R.T. LIM CONSTRUCTION & SUPPLY
30473 | NC 2017 | K10 | Region X | Misamis Occidental | 127481 | Map-An PS | PANAON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2697533 |  |  | Completed | 1 |  |  | PO0173852MN-CW1 | 17KI0109 | 2017-08-16 | 2017-08-24 | 2017-09-06 | 2017-10-30 | 2017-11-16 | R.T. LIM CONSTRUCTION & SUPPLY
30474 | NC 2017 | TVL | Region X | Misamis Occidental | 304048 | Panaon NHS | PANAON | 1 | 1 | 1 | WORKSHOP BLDG. (7X18) | BATCH 4 | 3030693.47 |  |  | Completed | 1 |  |  |  | 17KI0120 | 2017-09-14 | 2017-09-21 | 2017-10-05 | 2017-10-30 | 2017-11-16 | R.T. LIM CONSTRUCTION & SUPPLY
30475 | NC 2017 | K10 | Region X | Misamis Occidental | 127484 | Punta PS | PANAON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2720252 |  |  | Completed | 1 |  |  | PO0173853MN-CW1 | 17KI112 | 2017-08-16 | 2017-08-24 | 2017-09-06 | 2017-10-30 | 2017-11-16 | R.T. LIM CONSTRUCTION & SUPPLY
30476 | NC 2017 | K10 | Region X | Misamis Occidental | 127485 | Salimpono ES | PANAON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2697533 |  |  | Completed | 1 |  |  | PO0173854MN-CW1 | 17KI111 | 2017-08-16 | 2017-08-24 | 2017-09-06 | 2017-10-30 | 2017-11-16 | R.T. LIM CONSTRUCTION & SUPPLY
30477 | NC 2017 | K10 | Region X | Misamis Occidental | 127488 | Sumasap ES | PANAON | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3884986 |  |  | Completed | 1 |  |  | PO0173855MN-CW1 | 17KI113 | 2017-10-03 | 2017-10-12 | 2017-10-24 | 2017-11-17 | 2017-12-04 | R.T. LIM CONSTRUCTION & SUPPLY
30478 | NC 2017 | TVL | Region X | Misamis Occidental | 304040 | LOOC NATIONAL HIGH SCHOOL | PLARIDEL | 1 | 1 | 1 | WORKSHOP BLDG. (7X18) | BATCH 4 | 3052800.45 |  |  | Completed | 1 |  |  |  | 17KI0118 | 2017-10-11 | 2017-10-24 | 2017-11-07 | 2017-11-17 | 2017-12-04 | DDS BUILDERS
30479 | NC 2017 | K10 | Region X | Misamis Occidental | 127503 | Plaridel CS | PLARIDEL | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3884986 |  |  | Completed | 1 |  |  | P00173857MN-CW1 | 17KI0107 | 2017-08-16 | 2017-08-24 | 2017-09-06 | 2017-10-30 | 2017-11-16 | DDS BUILDERS
30480 | NC 2017 | K10 | Region X | Misamis Occidental | 315209 | Bitibut IS | SAPANG DALAGA | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3884986 |  |  | Completed | 1 |  |  | P00173859MN-CW1 | 17KI0097 | 2017-08-01 | 2017-08-15 | 2017-09-29 | 2017-10-30 | 2017-11-16 | SGM CONSTRUCTION
30481 | NC 2017 | K10 | Region X | Misamis Occidental | 315209 | Bitibut IS | SAPANG DALAGA | 1 |  | 2 | 1STY2CL | BATCH 4 | 2697533 |  |  | Completed | 1 |  |  | P00173860MN-CW1 | 17KI0094 | 2017-08-01 | 2017-08-15 | 2017-09-29 | 2017-10-30 | 2017-11-16 | SGM CONSTRUCTION
30482 | NC 2017 | K10 | Region X | Misamis Occidental | 127555 | Fulgencio Baloria-Sinonoc ES | SINACABAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2795193 |  |  | Completed | 1
30483 | NC 2017 | K10 | Region X | Misamis Occidental | 127576 | San Nicolas ES | TUDELA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2835968 |  |  | Completed | 1
30484 | NC 2017 | K10 | Region X | Misamis Oriental | 127589 | LANAO ELEMENTARY SCHOOL | ALUBIJID | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3865905.02 |  |  | Completed | 1 |  |  |  | 17KL0097
30485 | NC 2017 | K10 | Region X | Misamis Oriental | 127591 | Lourdes ES | ALUBIJID | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0098
30486 | NC 2017 | K10 | Region X | Misamis Oriental | 127593 | Sampatulog IS | ALUBIJID | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2682145.92 |  |  | Completed | 1 |  |  |  | 17KL0095
30487 | NC 2017 | K10 | Region X | Misamis Oriental | 315319 | Sampatulog IS | ALUBIJID | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2682145.92 |  |  | Completed | 1 |  |  |  | 17KL0096
30488 | NC 2017 | K10 | Region X | Misamis Oriental | 127634 | Aposkahoy I ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0122
30489 | NC 2017 | K10 | Region X | Misamis Oriental | 127636 | Bangonbangon ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0121
30490 | NC 2017 | K10 | Region X | Misamis Oriental | 127639 | Claveria CS | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2750545.92 |  |  | Completed | 1 |  |  |  | 17KL0120
30491 | NC 2017 | K10 | Region X | Misamis Oriental | 127642 | Hinaplanan ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0123
30492 | NC 2017 | K10 | Region X | Misamis Oriental | 127688 | Kalacapan ES | INITAO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2682145.92 |  |  | Completed | 1 |  |  |  | 17KL0105
30493 | NC 2017 | K10 | Region X | Misamis Oriental | 127697 | Tawantawan ES | INITAO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0104
30494 | NC 2017 | K10 | Region X | Misamis Oriental | 127709 | Natubo ES | JASAAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17kl0118
30495 | NC 2017 | K10 | Region X | Misamis Oriental | 127710 | San Antonio ES | JASAAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2676294.72 |  |  | Completed | 1 |  |  |  | 17KL0117
30496 | NC 2017 | K10 | Region X | Misamis Oriental | 127911 | Gasi ES | LAGUINDINGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2646235.92 |  |  | Completed | 1 |  |  |  | 17KL0099
30497 | NC 2017 | K10 | Region X | Misamis Oriental | 127918 | Sambulawan ES | LAGUINDINGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0100
30498 | NC 2017 | K10 | Region X | Misamis Oriental | 127757 | Gimaylan ES | LIBERTAD | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2682145.92 |  |  | Completed | 1 |  |  |  | 17KL0103
30499 | NC 2017 | K10 | Region X | Misamis Oriental | 127760 | Libertad CS | LIBERTAD | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2750545.92 |  |  | Completed | 1 |  |  |  | 17KL0102
30500 | NC 2017 | K10 | Region X | Misamis Oriental | 127767 | Tangkub ES | LIBERTAD | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2706085.92 |  |  | Completed | 1 |  |  |  | 17KL0101
30501 | NC 2017 | K10 | Region X | Misamis Oriental | 127924 | Kalangahan ES | LUGAIT | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2646235.92 |  |  | Completed | 1 |  |  |  | 17KL0111
30502 | NC 2017 | K10 | Region X | Misamis Oriental | 127925 | Kaluknayan ES | LUGAIT | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0110
30503 | NC 2017 | K10 | Region X | Misamis Oriental | 127805 | Manticao CS | MANTICAO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2750545.92 |  |  | Completed | 1 |  |  |  | 17KL0107
30504 | NC 2017 | K10 | Region X | Misamis Oriental | 127809 | Punta Silum ES | MANTICAO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2682145.92 |  |  | Completed | 1 |  |  |  | 17KL0106
30505 | NC 2017 | K10 | Region X | Misamis Oriental | 127935 | Naawan CS | NAAWAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0109
30506 | NC 2017 | K10 | Region X | Misamis Oriental | 127939 | Tuboran ES | NAAWAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0108
30507 | NC 2017 | K10 | Region X | Misamis Oriental | 127839 | Igpit ES | OPOL | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3973535.02 |  |  | Completed | 1 |  |  |  | 17KL0113
30508 | NC 2017 | TVL | Region X | Misamis Oriental | 304094 | Opol NSTS | OPOL | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0127
30509 | NC 2017 | SHS | Region X | Misamis Oriental | 304094 | Opol NSTS | OPOL | 2 |  | 2 | 1STY2CL | BATCH 4 | 2682145.92 |  |  | Completed | 1 |  |  |  | 17KL0116
30510 | NC 2017 | K10 | Region X | Misamis Oriental | 127847 | Patag ES | OPOL | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0114
30511 | NC 2017 | K10 | Region X | Misamis Oriental | 127849 | Tingalan ES | OPOL | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0115
30512 | NC 2017 | K10 | Region X | Misamis Oriental | 127867 | Gracia ES | TAGOLOAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0119
30513 | NC 2017 | K10 | Region X | Oroquieta City | 127442 | Apil ES | OROQUIETA CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2715456 |  |  | Completed | 1
30514 | NC 2017 | K10 | Region X | Oroquieta City | 127439 | Dulapo Elementary School | OROQUIETA CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2727444 |  |  | Completed | 1
30515 | NC 2017 | K10 | Region X | Oroquieta City | 127447 | Dullan IS | OROQUIETA CITY (Capital) | 1 | 1 | 4 | 1STY4CL | BATCH 4 | 5038986 |  |  | Completed | 1
30516 | NC 2017 | K10 | Region X | Oroquieta City | 127455 | Langcangan CES | OROQUIETA CITY (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3865459 |  |  | Completed | 1
30517 | NC 2017 | K10 | Region X | Oroquieta City | 127456 | Layawan ES | OROQUIETA CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2755381 |  |  | Completed | 1
30518 | NC 2017 | SHS | Region X | Oroquieta City | 304044 | Misamis Occidental Science & Tech. HS | OROQUIETA CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2697533 |  |  | Completed | 1
30519 | NC 2017 | K10 | Region X | Oroquieta City | 127440 | Senote ES | OROQUIETA CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2727444 |  |  | Completed | 1
30520 | NC 2017 | K10 | Region X | Ozamis City | 128179 | Capucao ES | OZAMIS CITY | 2 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 4 | 6626198 |  |  | Completed | 1
30521 | NC 2017 | K10 | Region X | Ozamis City | 128182 | Guimad Elementary School | OZAMIS CITY | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4222406 |  |  | Completed | 1
30522 | NC 2017 | K10 | Region X | Ozamis City | 128183 | Guingona Elementary School | OZAMIS CITY | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4222406 |  |  | Completed | 1
30523 | NC 2017 | TVL | Region X | Ozamis City | 304163 | Labo National High School | OZAMIS CITY | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3795136 |  |  | Completed | 1
30524 | NC 2017 | TVL | Region X | Ozamis City | 304163 | Labo National High School | OZAMIS CITY | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3715067 |  |  | Completed | 1
30525 | NC 2017 | TVL | Region X | Ozamis City | 304167 | Ozamiz City National High School | OZAMIS CITY | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3780933 |  |  | Completed | 1
30526 | NC 2017 | TVL | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4390766.31 |  |  | Completed | 1
30527 | NC 2017 | TVL | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4414601.53 |  |  | Completed | 1
30528 | NC 2017 | TVL | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4390766.31 |  |  | Completed | 1
30529 | NC 2017 | TVL | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4490383 |  |  | Completed | 1
30530 | NC 2017 | TVL | Region X | Ozamis City | 304169 | Pulot National High School | OZAMIS CITY | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4115524 |  |  | Completed | 1
30531 | NC 2017 | TVL | Region X | Ozamis City | 304169 | Pulot National High School | OZAMIS CITY | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4051962 |  |  | Completed | 1
30532 | NC 2017 | TVL | Region X | Ozamis City | 304169 | Pulot National High School | OZAMIS CITY | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4021579 |  |  | Completed | 1
30533 | NC 2017 | TVL | Region X | Ozamis City | 304162 | Tabid National High School | OZAMIS CITY | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4306388 |  |  | Completed | 1
30534 | NC 2017 | K10 | Region X | Ozamis City | 203505 | Tipan Elementary School | OZAMIS CITY | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4517916 |  |  | Completed | 1
30535 | NC 2017 | K10 | Region X | Tangub City | 128208 | Kauswagan ES | TANGUB CITY | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4376710 |  |  | Completed | 1
30536 | NC 2017 | TVL | Region X | Tangub City | 304041 | Lorenzo Tan NHS | TANGUB CITY | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3775570 |  |  | Completed | 1
30537 | NC 2017 | TVL | Region X | Tangub City | 323303 | Maquilao Integrated School | TANGUB CITY | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4464285 |  |  | Completed | 1
30538 | NC 2017 | TVL | Region X | Tangub City | 323303 | Maquilao Integrated School | TANGUB CITY | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4464285 |  |  | Completed | 1
30539 | NC 2017 | K10 | Region X | Tangub City | 128256 | Simasay ES | TANGUB CITY | 2 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 4 | 6410564 |  |  | Completed | 1
30540 | NC 2017 | TVL | Region X | Tangub City | 323302 | Simasay NHS | TANGUB CITY | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3819570 |  |  | Completed | 1
30541 | NC 2017 | TVL | Region X | Tangub City | 304171 | Tangub City NHS | TANGUB CITY | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4221678.69 |  |  | Completed | 1
30542 | NC 2017 | K10 | Region X | Valencia City | 126833 | Batangan CES | CITY OF VALENCIA | 4 | 1 | 4 | 1STY4CL | BATCH 4 | 5865000 |  |  | Completed | 1
30543 | NC 2017 | K10 | Region X | Valencia City | 126866 | Buco-Sinait Elementary School | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 4218000 |  |  | Completed | 1
30544 | NC 2017 | K10 | Region X | Valencia City | 126868 | Buyog ES | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 4071000 |  |  | Completed | 1
30545 | NC 2017 | K10 | Region X | Valencia City | 126834 | Cabanbanagan ES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
30546 | NC 2017 | K10 | Region X | Valencia City | 126837 | Catumbalon ES | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4160000 |  |  | Completed | 1
30547 | NC 2017 | SHS | Region X | Valencia City | 323802 | Catumbalon National High School | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 4335000 |  |  | Completed | 1
30548 | NC 2017 | SHS | Region X | Valencia City | 314909 | Guinuyoran National High School | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
30549 | NC 2017 | K10 | Region X | Valencia City | 126841 | Kahaponan ES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
30550 | NC 2017 | K10 | Region X | Valencia City | 126844 | Liloan ES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
30551 | NC 2017 | K10 | Region X | Valencia City | 126845 | Lourdes ES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
30552 | NC 2017 | K10 | Region X | Valencia City | 126845 | Lourdes ES | CITY OF VALENCIA | 4 |  | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
30553 | NC 2017 | K10 | Region X | Valencia City | 323805 | Lourdes IS | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
30554 | NC 2017 | K10 | Region X | Valencia City | 126874 | Lumbayao ES | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4218000 |  |  | Completed | 1
30555 | NC 2017 | K10 | Region X | Valencia City | 126848 | Maapag ES | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 4100000 |  |  | Completed | 1
30556 | NC 2017 | K10 | Region X | Valencia City | 126851 | Mt. Nebo ES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
30557 | NC 2017 | K10 | Region X | Valencia City | 126856 | San Isidro ES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
30558 | NC 2017 | K10 | Region X | Valencia City | 126878 | Sinabuagan ES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2788257.28 |  |  | Completed | 1
30559 | NC 2017 | SHS | Region X | Valencia City | 323801 | Tongantongan National High School | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
30560 | NC 2017 | K10 | Region X | Valencia City | 126861 | Tugaya ES | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL | BATCH 4 | 4110000 |  |  | Completed | 1
30561 | NC 2017 | K10 | Region X | Bukidnon | 126753 | Halapitan CES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 5 | 3548000 |  |  | Completed | 1
30562 | NC 2017 | K10 | Region X | Bukidnon | 126755 | Ilian ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 5 | 3300000 |  |  | Completed | 1
30563 | NC 2017 | K10 | Region X | Bukidnon | 126756 | Kalagangan Central School | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 5 | 3095000 |  |  | Completed | 1
30564 | NC 2017 | K10 | Region X | Valencia City | 126867 | Bulacao ES | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL | BATCH 5 | 4210000 |  |  | Completed | 1
30565 | NC 2017 | K10 | Region X | Valencia City | 126836 | Cambangon ES | CITY OF VALENCIA | 4 |  | 2 | 1STY2CL | BATCH 5 | 2613745.92 |  |  | Completed | 1
30566 | NC 2017 | SHS | Region X | Valencia City | 323803 | Concepcion National High School | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 5 | 2613745.92 |  |  | Completed | 1
30567 | NC 2017 | K10 | Region X | Bukidnon | 199537 | Basag PS | DAMULOG | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3290785.14 |  |  | Completed | 1
30568 | NC 2017 | K10 | Region X | Bukidnon | 199529 | Kidama ES | DAMULOG | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3299671.77 |  |  | Completed | 1
30569 | NC 2017 | K10 | Region X | Bukidnon | 126320 | Omonay ES | DAMULOG | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3163962.31 |  |  | Completed | 1
30570 | NC 2017 | K10 | Region X | Bukidnon | 126325 | Barongcot ES | DANGCAGAN | 3 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5332351.15 |  |  | Completed | 1
30571 | NC 2017 | K10 | Region X | Bukidnon | 126325 | Barongcot ES | DANGCAGAN | 3 |  | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5332351.15 |  |  | Completed | 1
30572 | NC 2017 | K10 | Region X | Bukidnon | 126328 | Dolorosa ES | DANGCAGAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3129255.77 |  |  | Completed | 1
30573 | NC 2017 | K10 | Region X | Bukidnon | 126337 | Sagbayan Elementary School | DANGCAGAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3124441.78 |  |  | Completed | 1
30574 | NC 2017 | SHS | Region X | Bukidnon | 314913 | Don Carlos NHS | DON CARLOS | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2803745.92 |  |  | Completed | 1
30575 | NC 2017 | K10 | Region X | Bukidnon | 126392 | Bacbacon ES | KADINGILAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3202516.32 |  |  | Completed | 1
30576 | NC 2017 | K10 | Region X | Bukidnon | 126392 | Bacbacon ES | KADINGILAN | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3202516.32 |  |  | Completed | 1
30577 | NC 2017 | K10 | Region X | Bukidnon | 199512 | Bahucanon E/S | KADINGILAN | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4614957.04 |  |  | Completed | 1
30578 | NC 2017 | K10 | Region X | Bukidnon | 126408 | Pinamangguan ES | KADINGILAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3188863.7 |  |  | Completed | 1
30579 | NC 2017 | SHS | Region X | Bukidnon | 303966 | Lampanusan NHS | KALILANGAN | 1 | 1 | 4 | 2STY4CL | BATCH 7 | 9615308.86 |  |  | Completed | 1
30580 | NC 2017 | K10 | Region X | Bukidnon | 126446 | Mascarinas ES | KIBAWE | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3291430.09 |  |  | Completed | 1
30581 | NC 2017 | K10 | Region X | Bukidnon | 199542 | Bacayan Primary School | KITAOTAO | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3321055.45 |  |  | Completed | 1
30582 | NC 2017 | K10 | Region X | Bukidnon | 199542 | Bacayan Primary School | KITAOTAO | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3321055.45 |  |  | Completed | 1
30583 | NC 2017 | K10 | Region X | Bukidnon | 126465 | Cabalantian ES | KITAOTAO | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3203080.04 |  |  | Completed | 1
30584 | NC 2017 | K10 | Region X | Bukidnon | 126467 | Digongan Elementary School | KITAOTAO | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4530786.69 |  |  | Completed | 1
30585 | NC 2017 | K10 | Region X | Bukidnon | 126467 | Digongan Elementary School | KITAOTAO | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3175561.23 |  |  | Completed | 1
30586 | NC 2017 | K10 | Region X | Bukidnon | 126469 | Kabalansihan ES | KITAOTAO | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4575005.73 |  |  | Completed | 1
30587 | NC 2017 | K10 | Region X | Bukidnon | 126474 | Kipilas ES | KITAOTAO | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3269522.83 |  |  | Completed | 1
30588 | NC 2017 | SHS | Region X | Bukidnon | 314931 | Kitaotao National High School - Digongan Annex | KITAOTAO | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3175561.23 |  |  | Completed | 1
30589 | NC 2017 | K10 | Region X | Bukidnon | 126478 | Lorega ES | KITAOTAO | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3273440.46 |  |  | Completed | 1
30590 | NC 2017 | K10 | Region X | Bukidnon | 126482 | Panganan ES | KITAOTAO | 3 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5950498.44 |  |  | Reverted | 0
30591 | NC 2017 | K10 | Region X | Bukidnon | 126485 | Sagundanon ES | KITAOTAO | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3794288.83 |  |  | Completed | 1
30592 | NC 2017 | K10 | Region X | Bukidnon | 126490 | Sinuda CES | KITAOTAO | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4513565.78 |  |  | Completed | 1
30593 | NC 2017 | K10 | Region X | Bukidnon | 126490 | Sinuda CES | KITAOTAO | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3152215.79 |  |  | Completed | 1
30594 | NC 2017 | K10 | Region X | Bukidnon | 314937 | South Dalurong Integrated School | KITAOTAO | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3240498.12 |  |  | Completed | 1
30595 | NC 2017 | K10 | Region X | Bukidnon | 314937 | South Dalurong Integrated School | KITAOTAO | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3240498.12 |  |  | Completed | 1
30596 | NC 2017 | K10 | Region X | Bukidnon | 314937 | South Dalurong Integrated School | KITAOTAO | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3240498.12 |  |  | Completed | 1
30597 | NC 2017 | K10 | Region X | Bukidnon | 314938 | White Kulaman Integrated School | KITAOTAO | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4774107.7 |  |  | Completed | 1
30598 | NC 2017 | K10 | Region X | Bukidnon | 314938 | White Kulaman Integrated School | KITAOTAO | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3428991.25 |  |  | Completed | 1
30599 | NC 2017 | SHS | Region X | Bukidnon | 303968 | Libona NHS | LIBONA | 1 | 1 | 4 | 2STY4CL | BATCH 7 | 9511988.26 |  |  | Completed | 1
30600 | NC 2017 | SHS | Region X | Bukidnon | 303944 | Alae NHS | MANOLO FORTICH | 1 | 1 | 4 | 2STY4CL | BATCH 7 | 9393846.62 |  |  | Completed | 1
30601 | NC 2017 | K10 | Region X | Bukidnon | 126652 | Base Camp Elementary school | MARAMAG | 3 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5298351.15 |  |  | Completed | 1
30602 | NC 2017 | K10 | Region X | Bukidnon | 126652 | Base Camp Elementary school | MARAMAG | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2843745.92 |  |  | Completed | 1
30603 | NC 2017 | K10 | Region X | Bukidnon | 126653 | Camp I ES | MARAMAG | 3 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5304351.15 |  |  | Completed | 1
30604 | NC 2017 | K10 | Region X | Bukidnon | 126653 | Camp I ES | MARAMAG | 3 |  | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4094435.02 |  |  | Completed | 1
30605 | NC 2017 | K10 | Region X | Bukidnon | 126695 | PANGANTUCAN CENTRAL ELEMENTAYR SCHOOL | PANGANTUCAN | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 9650640.55 |  |  | Completed | 1
30606 | NC 2017 | SHS | Region X | Bukidnon | 303978 | Pangantucan NHS | PANGANTUCAN | 1 | 1 | 4 | 2STY4CL | BATCH 7 | 9480653.79 |  |  | Completed | 1
30607 | NC 2017 | K10 | Region X | Bukidnon | 126753 | Halapitan CES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3548000 |  |  | Completed | 1
30608 | NC 2017 | K10 | Region X | Bukidnon | 126755 | Ilian ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3300000 |  |  | Completed | 1
30609 | NC 2017 | K10 | Region X | Bukidnon | 126756 | Kalagangan Central School | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3095000 |  |  | Completed | 1
30610 | NC 2017 | K10 | Region X | Bukidnon | 126791 | San Vicente ES | SUMILAO | 1 | 1 | 4 | 2STY4CL | BATCH 7 | 9271704.7 |  |  | Completed | 1
30611 | NC 2017 | SHS | Region X | Bukidnon | 314924 | Sumilao NHS - Vista Villa Annex | SUMILAO | 1 | 1 | 4 | 2STY4CL | BATCH 7 | 9230526.29 |  |  | Completed | 1
30612 | NC 2017 | K10 | Region X | Bukidnon | 314932 | Dagumbaan Integrated School | TALAKAG | 1 | 1 | 4 | 2STY4CL | BATCH 7 | 9264503.5 |  |  | Completed | 1
30613 | NC 2017 | SHS | Region X | Bukidnon | 303987 | Talakag NHS | TALAKAG | 1 | 1 | 8 | 2STY8CL | BATCH 7 | 16955280 |  |  | Completed | 1
30614 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304116 | Indahag National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Reverted | 0
30615 | NC 2017 | K10 | Region X | Camiguin | 126888 | Lawigan ES | CATARMAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2831126.09 |  |  | Completed | 1 | [9 empty] | GCMC CONST.
30616 | NC 2017 | K10 | Region X | Camiguin | 126890 | Manduao ES | CATARMAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2872000 |  |  | Completed | 1 | [9 empty] | JUNJING CONST. & GEN MERCHANDISE
30617 | NC 2017 | K10 | Region X | Camiguin | 126928 | Butay ES | GUINSILIBAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2816700 |  |  | Completed | 1 | [9 empty] | SHEEN-SHEEN CONST.
30618 | NC 2017 | K10 | Region X | Camiguin | 126930 | Cantaan Elementary School | GUINSILIBAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2800600 |  |  | Completed | 1 | [9 empty] | SHEEN-SHEEN CONST.
30619 | NC 2017 | K10 | Region X | Camiguin | 126896 | Hubangon ES | MAHINOG | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2768923.15 |  |  | Completed | 1 | [9 empty] | SHEEN-SHEEN CONST.
30620 | NC 2017 | K10 | Region X | Camiguin | 126906 | Anito ES | MAMBAJAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2858000 |  |  | Completed | 1
30621 | NC 2017 | K10 | Region X | Camiguin | 126907 | Balbagon Elem. School | MAMBAJAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2825000 |  |  | Completed | 1
30622 | NC 2017 | TVL | Region X | Camiguin | 303994 | Mambajao NHS | MAMBAJAO (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2956000 |  |  | Completed | 1 | [9 empty] | JAPUZ-JANSOL ENTERPRISES
30623 | NC 2017 | TVL | Region X | Camiguin | 303997 | Yumbing National High School | MAMBAJAO (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3528661 |  |  | Completed | 1
30624 | NC 2017 | TVL | Region X | Camiguin | 303997 | Yumbing National High School | MAMBAJAO (Capital) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3408175 |  |  | Completed | 1 | [9 empty] | SHEEN-SHEEN CONST.
30625 | NC 2017 | K10 | Region X | Camiguin | 126936 | Subocan ES | SAGAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2845376 |  |  | Completed | 1 | [9 empty] | SHEEN-SHEEN CONST.
30626 | NC 2017 | K10 | Region X | Iligan City | 128113 | DALIPUGA CENTRAL SCHOOL | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | BATCH 7 | 9075901.76 |  |  | Completed | 1 |  |  | P00176929MN | 17KF0116 | [5 empty] | RED CONSTRUCTIOM TECHNIK
30627 | NC 2017 | TVL | Region X | Iligan City | 304153 | Ditucalan National High School | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 9045901.76 |  |  | Completed | 1 |  |  | P00176938MN | 17KF0124 | [5 empty] | MJ ALONTO BUILDER & ENTERPRISES
30628 | NC 2017 | K10 | Region X | Iligan City | 128099 | Dulag ES | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2783745.92 |  |  | Reverted | 0
30629 | NC 2017 | TVL | Region X | Iligan City | 304154 | Esperidion F. Encabo I MHS (Pugaan NHS) | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 9075901.76 |  |  | Completed | 1 |  |  | P00176939MN | 17KF0125 | [5 empty] | MJ ALONTO BUILDER & ENTERPRISES
30630 | NC 2017 | TVL | Region X | Iligan City | 315608 | Francisco Laya Memorial Integrated School | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 9025901.76 |  |  | Completed | 1 |  |  | P00176947MN | 17KF0130 | [5 empty] | AL FAHDEL CONST. & ENG'G.
30631 | NC 2017 | K10 | Region X | Iligan City | 128100 | Hinaplanon Elementary School | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2738745.92 |  |  | Completed | 1 |  |  | P00176928MN | 17KF0100 | [5 empty] | AMMAR CONTRUCTION & ENTERPRISES
30632 | NC 2017 | K10 | Region X | Iligan City | 128091 | Iligan City Central School | ILIGAN CITY | 0 | 1 | 12 | 3STY12CL | BATCH 7 | 29459267.25 |  |  | Completed | 1 |  |  | P00176925MN | 17KF0133 | [5 empty] | RUDHIL CONSTRUCTION AND ENTERPRISES, INC.
30633 | NC 2017 | TVL | Region X | Iligan City | 304145 | Iligan City NHS | ILIGAN CITY | 0 | 1 | 3 | 3STY WORKSHOP BLDG (7X18) | BATCH 7 | 13889515.1 |  |  | Completed | 1 |  |  | P00176936MN | 17KF0132 | [5 empty] | D.O.T CONSTRUCTION
30634 | NC 2017 | TVL | Region X | Iligan City | 304150 | Iligan City NSOF | ILIGAN CITY | 0 | 1 | 4 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 9105901.76 |  |  | Completed | 1 |  |  | P00176937MN | 17KF0123 | [5 empty] | SDM VENTURES
30635 | NC 2017 | K10 | Region X | Iligan City | 128123 | Kalamalamahan ES | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2783745.92 |  |  | Completed | 1 |  |  | P00176930MN | 17KF0101 | [5 empty] | ALFAHAD BUILDERS & ENTERPRISES
30636 | NC 2017 | TVL | Region X | Iligan City | 315609 | Kalubihon High School | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 9075901.76 |  |  | Completed | 1 |  |  | P00176948MN | 17KF0131 | [5 empty] | ALQAOD CONSTRUCTION AND SUPPLY
30637 | NC 2017 | K10 | Region X | Iligan City | 203001 | Limunsudan Bayug Falls ES | ILIGAN CITY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2783745.92 |  |  | Completed | 1 |  |  | P00176935MN | 17KF0098 | [5 empty] | ALFAHAD BUILDERS & ENTERPRISES
30638 | NC 2017 | K10 | Region X | Iligan City | 128159 | Maria Cristina Falls ES | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | BATCH 7 | 9025901.76 |  |  | Completed | 1 |  |  | P00176934MN | 17KF0118 | [5 empty] | SDM VENTURES
30639 | NC 2017 | K10 | Region X | Iligan City | 128138 | North I CES | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | BATCH 7 | 9015901.76 |  |  | Completed | 1 |  |  | P00176932MN | 17KF0117 | [5 empty] | DCD BUILDERS AND ENTERPRISES
30640 | NC 2017 | K10 | Region X | Iligan City | 128130 | Northeast II-B CS | ILIGAN CITY | 0 | 1 | 3 | 1STY3CL | BATCH 7 | 3903435.02 |  |  | Completed | 1 |  |  | P00176931MN | 17KF0113 | [5 empty] | AHMADI BUILDERS
30641 | NC 2017 | K10 | Region X | Iligan City | 128142 | Pugaan Elementary School | ILIGAN CITY | 0 | 1 | 3 | 1STY3CL | BATCH 7 | 3898435.02 |  |  | Completed | 1 |  |  | P00176933MN | 17KF0114 | [5 empty] | RHIO CONSTRUCTION AND ENTERPRISES
30642 | NC 2017 | TVL | Region X | Iligan City | 304155 | Rogongon Agricultural High School | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 9195901.76 |  |  | Completed | 1 |  |  | P00176940MN | 17KF0126 | [5 empty] | MJ ALONTO BUILDER & ENTERPRISES
30643 | NC 2017 | TVL | Region X | Iligan City | 304155 | Rogongon Agricultural High School | ILIGAN CITY | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3200000 |  |  | Completed | 1 |  |  | P00176941MN | 17KF0134 | [5 empty] | H & N ENTERPRISES
30644 | NC 2017 | K10 | Region X | Iligan City | 128095 | Sta. Filomena Central School | ILIGAN CITY | 0 | 1 | 6 | 2STY6CL | BATCH 7 | 12410852.94 |  |  | Completed | 1 |  |  | P00176926MN | 17KF0120 | [5 empty] | ALFAHAD BUILDERS AND ENTERPRISES
30645 | NC 2017 | TVL | Region X | Iligan City | 304156 | Suarez National High School | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 9025901.76 |  |  | Completed | 1 |  |  | P00176942MN | 17KF0127 | [5 empty] | AHM BUILDERS
30646 | NC 2017 | TVL | Region X | Iligan City | 304156 | Suarez National High School | ILIGAN CITY | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3070000 |  |  | Completed | 1 |  |  | P00176943MN | 17KF0136 | [5 empty] | JRS BUILDERS
30647 | NC 2017 | K10 | Region X | Iligan City | 128081 | Tambo Central School | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | BATCH 7 | 9065901 |  |  | Completed | 1 |  |  | P00176923MN | 17KF0115 | [5 empty] | SDM VENTURES
30648 | NC 2017 | TVL | Region X | Iligan City | 304159 | Tubaran NHS | ILIGAN CITY | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3086250 |  |  | Completed | 1 |  |  | P00176944MN | 17KF0136 | [5 empty] | ALFAHAD BUILDERS AND ENTERPRISES
30649 | NC 2017 | TVL | Region X | Iligan City | 304160 | Tubaran NHS - Digkilaan HS Annex | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 9105901.76 |  |  | Completed | 1 |  |  | P00176945MN | 17KF0128 | [5 empty] | DCD BUILDERS AND ENTERPRISES
30650 | NC 2017 | TVL | Region X | Iligan City | 315606 | Tubaran NHS (Lanipao Annex) | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 9095901.76 |  |  | Completed | 1 |  |  | P00176946MN | 17KF0130 | [5 empty] | SORAINIE CONSTRUCTION INC.
30651 | NC 2017 | K10 | Region X | Iligan City | 128088 | Ubaldo D. Laya Memorial Central Sch. | ILIGAN CITY | 0 | 1 | 6 | 2STY6CL | BATCH 7 | 12410852.94 |  |  | Completed | 1 |  |  | P00176924MN | 17KF0119 | [5 empty] | RED CONSTRUCTION TECHNIK
30652 | NC 2017 | K10 | Region X | Lanao del Norte | 126937 | Alegria ES | BACOLOD | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2851359.67 |  |  | Completed | 1 |  |  | P00176949MN | 17KF0103 | [5 empty] | NDP CONST. DEV'T.
30653 | NC 2017 | TVL | Region X | Lanao del Norte | 304000 | Binuni-Demologan NHS | BACOLOD | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3112900 |  |  | Completed | 1 |  |  | P00176951MN | 17KF0143 | [5 empty] | NDP CONST. DEV'T.
30654 | NC 2017 | TVL | Region X | Lanao del Norte | 304000 | Binuni-Demologan NHS | BACOLOD | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3112900 |  |  | Completed | 1 |  |  | P00176952MN | 17KF0141 | [5 empty] | NDP CONST. DEV'T.
30655 | NC 2017 | K10 | Region X | Lanao del Norte | 126941 | Esperanza ES | BACOLOD | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2716359.67 |  |  | Completed | 1 |  |  | P00176950MN | 17KF0105 | [5 empty] | NDP CONST. DEV'T.
30656 | NC 2017 | K10 | Region X | Lanao del Norte | 126961 | Baloi Central ES | BALOI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
30657 | NC 2017 | K10 | Region X | Lanao del Norte | 126961 | Baloi Central ES | BALOI | 1 |  | 3 | 1STY3CL | BATCH 7 | 3692809.68 |  |  | Completed | 1
30658 | NC 2017 | K10 | Region X | Lanao del Norte | 126961 | Baloi Central ES | BALOI | 1 |  | 2 | 1STY2CL | BATCH 7 | 2636745.92 |  |  | Completed | 1
30659 | NC 2017 | TVL | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2880000 |  |  | Completed | 1
30660 | NC 2017 | K10 | Region X | Lanao del Norte | 126967 | Dadoan ES | BALOI | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3692809.68 |  |  | Completed | 1
30661 | NC 2017 | K10 | Region X | Lanao del Norte | 126973 | Pacalundo ES | BALOI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
30662 | NC 2017 | K10 | Region X | Lanao del Norte | 126973 | Pacalundo ES | BALOI | 1 |  | 3 | 1STY3CL | BATCH 7 | 3692809.68 |  |  | Completed | 1
30663 | NC 2017 | K10 | Region X | Lanao del Norte | 126977 | Dalama ES | BAROY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2826359.67 |  |  | Completed | 1 |  |  | P00176960MN | 17KF0102 | [5 empty] | NDP CONST. DEV'T.
30664 | NC 2017 | TVL | Region X | Lanao del Norte | 304001 | Diosdado Yap Sr. National High School | BAROY | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3107900 |  |  | Completed | 1 |  |  | P00176961MN | 17KF0142 | [5 empty] | NDP CONST. DEV'T.
30665 | NC 2017 | TVL | Region X | Lanao del Norte | 304005 | Lanao del Norte NCHS | BAROY | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3062900 |  |  | Completed | 1 |  |  | P00176962MN | 17KF0144 | [5 empty] | RUDHIL CONSTRUCTION AND ENTERPRISES, INC
30666 | NC 2017 | SHS | Region X | Lanao del Norte | 304005 | Lanao del Norte NCHS | BAROY | 1 |  | 6 | 2STY6CL | BATCH 7 | 12449024.13 |  |  | Completed | 1 |  |  | P00176963MN | 17KF0137 | [5 empty] | NDP CONSTRUCTION DEVELOPMENT
30667 | NC 2017 | K10 | Region X | Lanao del Norte | 200504 | Anacorita Apat Tongco-Rubillar PS | KAPATAGAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2696745.92 |  |  | Completed | 1
30668 | NC 2017 | K10 | Region X | Lanao del Norte | 127001 | BAGONG BADIAN ELEMENTARY SCHOOL | KAPATAGAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2712745.92 |  |  | Completed | 1
30669 | NC 2017 | K10 | Region X | Lanao del Norte | 127002 | Balili Central ES | KAPATAGAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2688745.92 |  |  | Completed | 1
30670 | NC 2017 | K10 | Region X | Lanao del Norte | 127003 | Bansarvil ES | KAPATAGAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3763809.68 |  |  | Completed | 1
30671 | NC 2017 | SHS | Region X | Lanao del Norte | 303999 | Bansarvil NHS | KAPATAGAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3735309.68 |  |  | Completed | 1
30672 | NC 2017 | TVL | Region X | Lanao del Norte | 303999 | Bansarvil NHS | KAPATAGAN | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2975500 |  |  | Completed | 1
30673 | NC 2017 | TVL | Region X | Lanao del Norte | 303999 | Bansarvil NHS | KAPATAGAN | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2975500 |  |  | Completed | 1
30674 | NC 2017 | K10 | Region X | Lanao del Norte | 127007 | KAHAYAGAN ES | KAPATAGAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2782745.92 |  |  | Completed | 1
30675 | NC 2017 | TVL | Region X | Lanao del Norte | 304003 | Kapatagan NHS | KAPATAGAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2975500 |  |  | Completed | 1
30676 | NC 2017 | TVL | Region X | Lanao del Norte | 304003 | Kapatagan NHS | KAPATAGAN | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2975500 |  |  | Completed | 1
30677 | NC 2017 | TVL | Region X | Lanao del Norte | 304003 | Kapatagan NHS | KAPATAGAN | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2981000 |  |  | Completed | 1
30678 | NC 2017 | K10 | Region X | Lanao del Norte | 126995 | Mahayahay ES | KAPATAGAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3763809.68 |  |  | Completed | 1
30679 | NC 2017 | K10 | Region X | Lanao del Norte | 127012 | Taguitic Integrated School | KAPATAGAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2716745.92 |  |  | Completed | 1
30680 | NC 2017 | K10 | Region X | Lanao del Norte | 127063 | Guillermo A. Gimeno ES (Titunod ES) | KOLAMBUGAN | 1 | 1 | 4 | 2STY4CL | BATCH 7 | 9125901.76 |  |  | Completed | 1 |  |  | P00176965MN | 17KF0121 | [5 empty] | TESAR BUILDERS
30681 | NC 2017 | K10 | Region X | Lanao del Norte | 127057 | Manga ES | KOLAMBUGAN | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3023745.92 |  |  | Completed | 1 |  |  | P00176964MN | 17KF0110 | [5 empty] | TESAR BUILDERS
30682 | NC 2017 | K10 | Region X | Lanao del Norte | 127084 | El Salvador ES | LALA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2645745.92 |  |  | Completed | 1
30683 | NC 2017 | K10 | Region X | Lanao del Norte | 127071 | F. M. Posadas ES | LALA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2672745.92 |  |  | Completed | 1
30684 | NC 2017 | K10 | Region X | Lanao del Norte | 127085 | F. Ylaya Mem ES | LALA | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 4996351.15 |  |  | Completed | 1
30685 | NC 2017 | K10 | Region X | Lanao del Norte | 127072 | Gumagamot ES | LALA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3866809.68 |  |  | Completed | 1
30686 | NC 2017 | TVL | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2899000 |  |  | Completed | 1
30687 | NC 2017 | TVL | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2899000 |  |  | Completed | 1
30688 | NC 2017 | K10 | Region X | Lanao del Norte | 127076 | Matampay Ilaya ES | LALA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2645745.92 |  |  | Completed | 1
30689 | NC 2017 | K10 | Region X | Lanao del Norte | 127091 | San Manuel ES | LALA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2672745.92 |  |  | Completed | 1
30690 | NC 2017 | K10 | Region X | Lanao del Norte | 127100 | Datu Bebit Dalug ES (Baguiguicon ES) | MAGSAYSAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2645745.92 |  |  | Completed | 1
30691 | NC 2017 | K10 | Region X | Lanao del Norte | 127100 | Datu Bebit Dalug ES (Baguiguicon ES) | MAGSAYSAY | 2 |  | 2 | 1STY2CL | BATCH 7 | 2645745.92 |  |  | Completed | 1
30692 | NC 2017 | TVL | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2919000 |  |  | Completed | 1
30693 | NC 2017 | TVL | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2919000 |  |  | Completed | 1
30694 | NC 2017 | TVL | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2960000 |  |  | Completed | 1
30695 | NC 2017 | K10 | Region X | Lanao del Norte | 127110 | Atanacia Logronio ES (Segapod ES) | MAIGO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2786359.67 |  |  | Completed | 1 |  |  | P00176966MN | 17KF0105 | [5 empty] | NDP CONST. DEV'T.
30696 | NC 2017 | K10 | Region X | Lanao del Norte | 200512 | Baybay Kulasihan PS | MAIGO | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2998745.92 |  |  | Completed | 1 |  |  | P00176970MN | 17KF0111 | [5 empty] | NDP CONST. DEV'T.
30697 | NC 2017 | K10 | Region X | Lanao del Norte | 127112 | Camp I PS | MAIGO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2776484.17 |  |  | Completed | 1 |  |  | P00176967MN | 17KF0106 | [5 empty] | NDP CONST. DEV'T.
30698 | NC 2017 | K10 | Region X | Lanao del Norte | 127113 | Claro M. Recto ES | MAIGO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2746359.67 |  |  | Completed | 1 |  |  | P00176968MN | 17KF0107 | [5 empty] | ALQAOD CONTS. AND SUPPLY
30699 | NC 2017 | K10 | Region X | Lanao del Norte | 127117 | Maigo CES | MAIGO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2746359.67 |  |  | Completed | 1 |  |  | P00176969MN | 17KF0108 | [5 empty] | ALFAHAD BUILDERS & ENTERPRISES
30700 | NC 2017 | SHS | Region X | Lanao del Norte | 304010 | Maigo NHS | MAIGO | 1 | 1 | 6 | 2STY6CL | BATCH 7 | 12445346.84 |  |  | Completed | 1 |  |  | P00176971MN | 17KF0138 | [5 empty] | NDP CONST. DEV'T.
30701 | NC 2017 | K10 | Region X | Lanao del Norte | 127125 | Bangco ES | MATUNGAO | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3717809.68 |  |  | Completed | 1
30702 | NC 2017 | K10 | Region X | Lanao del Norte | 127127 | Batangan ES | MATUNGAO | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6171650.72 |  |  | Completed | 1
30703 | NC 2017 | K10 | Region X | Lanao del Norte | 127127 | Batangan ES | MATUNGAO | 1 |  | 3 | 1STY3CL | BATCH 7 | 3653809.68 |  |  | Completed | 1
30704 | NC 2017 | K10 | Region X | Lanao del Norte | 127142 | Pendulonan ES | MATUNGAO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2615745.92 |  |  | Completed | 1
30705 | NC 2017 | SHS | Region X | Lanao del Norte | 304014 | Munai NHS | MUNAI | 2 | 1 | 5 | 1STY5CL | BATCH 7 | 6120150.72 |  |  | Completed | 1
30706 | NC 2017 | K10 | Region X | Lanao del Norte | 127146 | Banday ES | PANTAO RAGAT | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2615745.92 |  |  | Completed | 1
30707 | NC 2017 | K10 | Region X | Lanao del Norte | 127148 | Cabasagan ES | PANTAO RAGAT | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2666745.92 |  |  | Completed | 1
30708 | NC 2017 | K10 | Region X | Lanao del Norte | 127150 | Dimayon Elementary School | PANTAO RAGAT | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2615745.92 |  |  | Completed | 1
30709 | NC 2017 | K10 | Region X | Lanao del Norte | 127151 | Lomidong ES | PANTAO RAGAT | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2616745.92 |  |  | Completed | 1
30710 | NC 2017 | K10 | Region X | Lanao del Norte | 127151 | Lomidong ES | PANTAO RAGAT | 2 |  | 2 | 1STY2CL | BATCH 7 | 2616745.92 |  |  | Completed | 1
30711 | NC 2017 | K10 | Region X | Lanao del Norte | 127153 | Matampay PS | PANTAO RAGAT | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2615745.92 |  |  | Completed | 1
30712 | NC 2017 | SHS | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 5008351.15 |  |  | Completed | 1
30713 | NC 2017 | SHS | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 |  | 3 | 1STY3CL | BATCH 7 | 3659809.68 |  |  | Completed | 1
30714 | NC 2017 | TVL | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2840000 |  |  | Completed | 1
30715 | NC 2017 | TVL | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2904000 |  |  | Completed | 1
30716 | NC 2017 | K10 | Region X | Lanao del Norte | 127156 | Pantao Ragat Central School | PANTAO RAGAT | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3659809.68 |  |  | Completed | 1
30717 | NC 2017 | K10 | Region X | Lanao del Norte | 127161 | Cabasaran ES | PANTAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2644745.92 |  |  | Completed | 1
30718 | NC 2017 | K10 | Region X | Lanao del Norte | 127163 | Kalanganan Elementary School | PANTAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
30719 | NC 2017 | K10 | Region X | Lanao del Norte | 127170 | Punod ES | PANTAR | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2628745.92 |  |  | Completed | 1
30720 | NC 2017 | K10 | Region X | Lanao del Norte | 127170 | Punod ES | PANTAR | 1 |  | 2 | 1STY2CL | BATCH 7 | 2628745.92 |  |  | Completed | 1
30721 | NC 2017 | K10 | Region X | Lanao del Norte | 127170 | Punod ES | PANTAR | 1 |  | 2 | 1STY2CL | BATCH 7 | 2628745.92 |  |  | Completed | 1
30722 | NC 2017 | K10 | Region X | Lanao del Norte | 127129 | Cormatan PS | POONA PIAGAPO | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3749809.68 |  |  | Completed | 1
30723 | NC 2017 | SHS | Region X | Lanao del Norte | 315104 | Poonapiagapo NHS(Annex Matungao NHS) | POONA PIAGAPO | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3689809.68 |  |  | Completed | 1
30724 | NC 2017 | K10 | Region X | Lanao del Norte | 200515 | Sultan Domaub PS | POONA PIAGAPO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2631745.92 |  |  | Completed | 1
30725 | NC 2017 | K10 | Region X | Lanao del Norte | 127176 | Buntong ES | SALVADOR | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2679745.92 |  |  | Completed | 1
30726 | NC 2017 | SHS | Region X | Lanao del Norte | 304023 | Salvador NHS (Salvador Trade HS) | SALVADOR | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2647745.92 |  |  | Completed | 1
30727 | NC 2017 | TVL | Region X | Lanao del Norte | 304023 | Salvador NHS (Salvador Trade HS) | SALVADOR | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2942000 |  |  | Completed | 1
30728 | NC 2017 | K10 | Region X | Lanao del Norte | 127204 | Miguel E. Esmade Memorial Elementary School | SAPAD | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2672745.92 |  |  | Completed | 1
30729 | NC 2017 | K10 | Region X | Lanao del Norte | 127206 | Panoloon ES | SAPAD | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2688745.92 |  |  | Completed | 1
30730 | NC 2017 | TVL | Region X | Lanao del Norte | 304022 | Andres Bersales, Sr. Nat'l. HS (Pandanan NHS) | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3007000 |  |  | Completed | 1
30731 | NC 2017 | TVL | Region X | Lanao del Norte | 304022 | Andres Bersales, Sr. Nat'l. HS (Pandanan NHS) | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2994000 |  |  | Completed | 1
30732 | NC 2017 | K10 | Region X | Lanao del Norte | 127023 | KIRAPAN ELEMENTARY SCHOOL | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669745.92 |  |  | Completed | 1
30733 | NC 2017 | K10 | Region X | Lanao del Norte | 127030 | Payong Elem. School | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2665745.92 |  |  | Completed | 1
30734 | NC 2017 | K10 | Region X | Lanao del Norte | 127030 | Payong Elem. School | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 |  | 2 | 1STY2CL | BATCH 7 | 2665745.92 |  |  | Completed | 1
30735 | NC 2017 | K10 | Region X | Lanao del Norte | 127032 | PIRAKA ES | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2671745.92 |  |  | Completed | 1
30736 | NC 2017 | K10 | Region X | Lanao del Norte | 315101 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3759809.68 |  |  | Completed | 1
30737 | NC 2017 | TVL | Region X | Lanao del Norte | 315101 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3007000 |  |  | Completed | 1
30738 | NC 2017 | TVL | Region X | Lanao del Norte | 315101 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2994000 |  |  | Completed | 1
30739 | NC 2017 | K10 | Region X | Lanao del Norte | 315107 | Sultan Naga Dimaporo Memorial Integrated School | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3759809.68 |  |  | Completed | 1
30740 | NC 2017 | K10 | Region X | Lanao del Norte | 127215 | Lininding ES | TAGOLOAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2614745.92 |  |  | Completed | 1
30741 | NC 2017 | K10 | Region X | Lanao del Norte | 200534 | Tangkal Proper IPS | TANGCAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2711745.92 |  |  | Completed | 1
30742 | NC 2017 | K10 | Region X | Lanao del Norte | 127228 | Malingao CS | TUBOD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2826359.67 |  |  | Completed | 1 |  |  | p00176982mn | 17kf0109 | [5 empty] | LANAO BUILDERS & ENTERPRISES
30743 | NC 2017 | K10 | Region X | Lanao del Norte | 127229 | Palao Elementary School | TUBOD (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3118745.92 |  |  | Completed | 1 |  |  | P00176983MN | 17KF0112 | [5 empty] | ALQAOD CONSTRUCTION SUPPLY
30744 | NC 2017 | K10 | Region X | Lanao del Norte | 127241 | San Antonio ES | TUBOD (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 7 | 12460792.62 |  |  | Completed | 1 |  |  | P00176984MN | 17KF0139 | [5 empty] | ALQAOD CONSTRUCTION SUPPLY
30745 | NC 2017 | K10 | Region X | Lanao del Norte | 127243 | Tubod Central ES | TUBOD (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 7 | 12460792.62 |  |  | Completed | 1 |  |  | P00176985MN | 17KF0140 | [5 empty] | SDM VENTURES
30746 | NC 2017 | K10 | Region X | Malaybalay City | 126575 | Baganao ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2802217.08 |  |  | Completed | 1
30747 | NC 2017 | K10 | Region X | Malaybalay City | 126558 | Bangcud CES | CITY MALAYBALAY (Capital) | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4025136.53 |  |  | Completed | 1
30748 | NC 2017 | K10 | Region X | Malaybalay City | 126577 | Can-ayan IS | CITY MALAYBALAY (Capital) | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4067021.66 |  |  | Completed | 1
30749 | NC 2017 | K10 | Region X | Malaybalay City | 126578 | Candiisan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 7 | 6319336.13 |  |  | Completed | 1
30750 | NC 2017 | K10 | Region X | Malaybalay City | 126584 | Kibalabag ES | CITY MALAYBALAY (Capital) | 2 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 7 | 6258438.11 |  |  | Completed | 1
30751 | NC 2017 | K10 | Region X | Malaybalay City | 126545 | Lunokan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2824691.01 |  |  | Completed | 1
30752 | NC 2017 | K10 | Region X | Malaybalay City | 126547 | Managok ES | CITY MALAYBALAY (Capital) | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5130686.86 |  |  | Completed | 1
30753 | NC 2017 | K10 | Region X | Malaybalay City | 126587 | Manalog ES | CITY MALAYBALAY (Capital) | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4107370.79 |  |  | Completed | 1 | [10 empty] | weather and access road concern. LGU road construction spillway and box culverts
30754 | NC 2017 | K10 | Region X | Misamis Occidental | 127349 | Clarin CS | CLARIN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2752732 |  |  | Completed | 1
30755 | NC 2017 | K10 | Region X | Misamis Occidental | 127505 | Sta Cruz ES | PLARIDEL | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3884986 |  |  | Completed | 1 |  |  | P00177051MN-CW1 | 17KI0125 | 2017-10-03 | 2017-10-12 | 2017-10-24 | 2017-11-06 | 2017-11-23 | CDY BUILDERS
30756 | NC 2017 | TVL | Region X | Misamis Oriental | 304081 | Lourdes Alubijid NHS | ALUBIJID | 2 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0147
30757 | NC 2017 | K10 | Region X | Misamis Oriental | 127603 | Baliwagan CS | BALINGASAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2965612.32 |  |  | Completed | 1
30758 | NC 2017 | K10 | Region X | Misamis Oriental | 127622 | Napaliran ES | BALINGASAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2987306.3 |  |  | Completed | 1
30759 | NC 2017 | SHS | Region X | Misamis Oriental | 341227 | SHS within Mambayaan ES | BALINGASAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2924247.41 |  |  | Completed | 1
30760 | NC 2017 | TVL | Region X | Misamis Oriental | 341227 | SHS within Mambayaan ES | BALINGASAG | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2734338.22 |  |  | Completed | 1
30761 | NC 2017 | K10 | Region X | Misamis Oriental | 127875 | Balingoan CS | BALINGOAN | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4180835.5 |  |  | Completed | 1
30762 | NC 2017 | TVL | Region X | Misamis Oriental | 304062 | Binuangan NHS | BINUANGAN | 1 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 7 | 6044914.69 |  |  | Completed | 1
30763 | NC 2017 | K10 | Region X | Misamis Oriental | 127740 | Valdeconcha ES | BINUANGAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2988958.27 |  |  | Completed | 1
30764 | NC 2017 | K10 | Region X | Misamis Oriental | 127644 | Kalawitan ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0133
30765 | NC 2017 | K10 | Region X | Misamis Oriental | 127651 | Malagana ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2662480.92 |  |  | Completed | 1 |  |  |  | 17KL0132
30766 | NC 2017 | K10 | Region X | Misamis Oriental | 127654 | Man-ibay ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0142
30767 | NC 2017 | TVL | Region X | Misamis Oriental | 304072 | Initao NCHS | INITAO | 2 | 1 | 2 | 2UNITS 1STY UNIQUE WORKSHOP | BATCH 7 | 6825600 |  |  | Completed | 1 |  |  |  | 17KL0146
30768 | NC 2017 | K10 | Region X | Misamis Oriental | 127699 | Aplaya ES | JASAAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0141
30769 | NC 2017 | TVL | Region X | Misamis Oriental | 304073 | Jasaan NHS | JASAAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3447000 |  |  | Completed | 1 |  |  |  | 17KL0148
30770 | NC 2017 | K10 | Region X | Misamis Oriental | 127719 | Buko ES | KINOGUITAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3686974.41 |  |  | Completed | 1
30771 | NC 2017 | K10 | Region X | Misamis Oriental | 127726 | Kinoguitan CS | KINOGUITAN | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5521978.22 |  |  | Completed | 1
30772 | NC 2017 | TVL | Region X | Misamis Oriental | 304077 | Kinoguitan Nat'l Agricultural HS | KINOGUITAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3125387.8 |  |  | Completed | 1
30773 | NC 2017 | K10 | Region X | Misamis Oriental | 127750 | Tabok ES | LAGONGLONG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2985499.8 |  |  | Completed | 1
30774 | NC 2017 | TVL | Region X | Misamis Oriental | 360847 | Lugait SHS (within TESDA site) | LUGAIT | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3276000 |  |  | Completed | 1 |  |  |  | 17KL0151
30775 | NC 2017 | TVL | Region X | Misamis Oriental | 304066 | Consuelo NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3110881.39 |  |  | Completed | 1
30776 | NC 2017 | K10 | Region X | Misamis Oriental | 127783 | Kibungsod CS | MAGSAYSAY (LINUGOS) | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4331709.09 |  |  | Completed | 1
30777 | NC 2017 | TVL | Region X | Misamis Oriental | 304076 | Kibungsod NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3526586.26 |  |  | Completed | 1
30778 | NC 2017 | TVL | Region X | Misamis Oriental | 315307 | Manticao NHS | MANTICAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3276000 |  |  | Completed | 1 |  |  |  | 17KL0145
30779 | NC 2017 | TVL | Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 7 | 6110151.72 |  |  | Completed | 1
30780 | NC 2017 | TVL | Region X | Misamis Oriental | 304095 | Portulin NHS | MEDINA | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2745997.51 |  |  | Completed | 1
30781 | NC 2017 | K10 | Region X | Misamis Oriental | 127828 | San Roque ES | MEDINA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3234332.9 |  |  | Completed | 1
30782 | NC 2017 | K10 | Region X | Misamis Oriental | 127931 | Macabagla ES | NAAWAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0140
30783 | NC 2017 | K10 | Region X | Misamis Oriental | 127841 | Limunda ES | OPOL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2633745.92 |  |  | Completed | 1 |  |  |  | 17KL0143
30784 | NC 2017 | K10 | Region X | Misamis Oriental | 127841 | Limunda ES | OPOL | 2 |  | 2 | 1STY2CL | BATCH 7 | 2633745.92 |  |  | Completed | 1 |  |  |  | 17KL0144
30785 | NC 2017 | K10 | Region X | Misamis Oriental | 127845 | Nangcaon ES | OPOL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0139
30786 | NC 2017 | K10 | Region X | Misamis Oriental | 127848 | Salawaga ES | OPOL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
30787 | NC 2017 | K10 | Region X | Misamis Oriental | 127856 | Looc ES | SALAY | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4126143.09 |  |  | Completed | 1
30788 | NC 2017 | TVL | Region X | Misamis Oriental | 304096 | Salay NHS | SALAY | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2909260.37 |  |  | Completed | 1
30789 | NC 2017 | K10 | Region X | Misamis Oriental | 127866 | Casinglot ES | TAGOLOAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2682145.92 |  |  | Completed | 1 |  |  |  | 17KL0137
30790 | NC 2017 | K10 | Region X | Misamis Oriental | 315310 | Casinglot NHS | TAGOLOAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2646235.92 |  |  | Completed | 1 |  |  |  | 17KL0136
30791 | NC 2017 | SHS | Region X | Misamis Oriental | 341231 | SHS within Tagoloan CS | TAGOLOAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0135
30792 | NC 2017 | TVL | Region X | Misamis Oriental | 341231 | SHS within Tagoloan CS | TAGOLOAN | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3276000 |  |  | Completed | 1
30793 | NC 2017 | K10 | Region X | Misamis Oriental | 127874 | Babanlagan ES | TALISAYAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3129913.45 |  |  | Completed | 1
30794 | NC 2017 | TVL | Region X | Misamis Oriental | 304093 | Talisayan NHS | TALISAYAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2971662.47 |  |  | Completed | 1
30795 | NC 2017 | SHS | Region X | Misamis Oriental | 341232 | SHS within San Martin ES | VILLANUEVA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17KL0134
30796 | NC 2017 | TVL | Region X | Misamis Oriental | 341232 | SHS within San Martin ES | VILLANUEVA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3276000 |  |  | Completed | 1 |  |  |  | 17KL0149
30797 | NC 2017 | K10 | Region X | Valencia City | 126833 | Batangan CES | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 4405000 |  |  | Completed | 1
30798 | NC 2017 | K10 | Region X | Valencia City | 126867 | Bulacao ES | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4132148.24 |  |  | Completed | 1
30799 | NC 2017 | K10 | Region X | Valencia City | 126836 | Cambangon ES | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
30800 | NC 2017 | SHS | Region X | Valencia City | 323802 | Catumbalon National High School | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 12000000 |  |  | Completed | 1
30801 | NC 2017 | SHS | Region X | Valencia City | 323803 | Concepcion National High School | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
30802 | NC 2017 | K10 | Region X | Valencia City | 250502 | Migtulod Elementary School | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2613745.92 |  |  | Completed | 1
30803 | NC 2017 | K10 | Region X | Valencia City | 126859 | Tagalawa ES | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4961901.28 |  |  | Completed | 1
30804 | NC 2017 | K10 | Region X | Bukidnon | 314939 | San Luis NHS - Sabangaan Annex | MALITBOG | 1 | 1 | 6 | 2STY6CL | BATCH 8 | 11120020.11 |  |  | Completed | 1
30805 | NC 2017 | K10 | Region X | Bukidnon | 126636 | Mambatangan ES | MANOLO FORTICH | 1 | 1 | 6 | 2STY6CL | BATCH 8 | 11129230.15 |  |  | Completed | 1
30806 | NC 2017 | K10 | Region X | Bukidnon | 126638 | Manolo Fortich CES | MANOLO FORTICH | 1 | 1 | 6 | 2STY6CL | BATCH 8 | 11223865.58 |  |  | Completed | 1
30807 | NC 2017 | K10 | Region X | Bukidnon | 126642 | Plantation ES | MANOLO FORTICH | 1 | 1 | 10 | 2STY10CL | BATCH 8 | 19205170 |  |  | Completed | 1
30808 | NC 2017 | K10 | Region X | Bukidnon | 126647 | Ticala ES | MANOLO FORTICH | 1 | 1 | 6 | 2STY6CL | BATCH 8 | 11458095.17 |  |  | Completed | 1
30809 | NC 2017 | SHS | Region X | Bukidnon | 303945 | Bacusanon National High School | PANGANTUCAN | 1 | 1 | 6 | 2STY6CL | BATCH 8 | 11465154.71 |  |  | Completed | 1
30810 | NC 2017 | K10 | Region X | Bukidnon | 126782 | Kisolon Central ES | SUMILAO | 1 | 1 | 6 | 2STY6CL | BATCH 8 | 11362268.72 |  |  | Completed | 1
30811 | NC 2017 | K10 | Region X | Bukidnon | 314932 | Dagumbaan Integrated School | TALAKAG | 1 | 1 | 6 | 2STY6CL | BATCH 8 | 11235514.41 |  |  | Completed | 1
30812 | NC 2017 | SHS | Region X | Bukidnon | 314919 | Tikalaan National High School | TALAKAG | 1 | 1 | 6 | 2STY6CL | BATCH 8 | 11499996.25 |  |  | Completed | 1
30813 | NC 2017 | SHS | Region X | Misamis Occidental | 304039 | Colambutan Bajo NHS | TUDELA | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 2772317 |  |  | Completed | 1
30814 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304104 | Agusan National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 32900000 |  |  | Completed | 1 |  |  | P00180246MN-CW1 | 17KD0063 | [5 empty] | AC RIVERO DEVT. CORP
30815 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304104 | Agusan National High School | CAGAYAN DE ORO CITY (Capital) | 2 |  | 24 | 4STY24CL | BATCH 10 | 59100000 |  |  | Completed | 1 |  |  | P00180247MN-CW1 | 17KD0070 | [5 empty] | DCM CONS.
30816 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127996 | Baikingon ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 10 | 17125005.47 |  |  | Completed | 1 |  |  | P00180186MN-CW1 | 17KH0111 | 2017-12-02 |  |  | 2017-12-26 | 2018-01-17 | RT LIM CONSTRUCTION & SUPPLY
30817 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127948 | Balubal ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9500000 |  |  | Completed | 1 |  |  | P00180241MN-CW1 | 17KD0073 | [5 empty] | LANCE CONS.
30818 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127948 | Balubal ES | CAGAYAN DE ORO CITY (Capital) | 2 |  | 4 | 2STY4CL | BATCH 10 | 9500000 |  |  | Completed | 1 |  |  | P00180240MN-CW1 | 17KD0074 | [5 empty] | MMA CHIEVER
30819 | NC 2017 | TVL | Region X | Cagayan de Oro City | 315401 | Balubal National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 10 | 4500000 |  |  | Completed | 1 |  |  | P00180253MN-CW1 | 17KD0066 | [5 empty] | GREEN BUILDERS & ENT.
30820 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315401 | Balubal National High School | CAGAYAN DE ORO CITY (Capital) | 2 |  | 12 | 3STY12CL | BATCH 10 | 32900000 |  |  | Completed | 1 |  |  | P00180254MN-CW1 | 17KD0079 | [5 empty] | BRIMA CONS. & ENT.
30821 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127971 | Batinay Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180170MN-CW1 | 17KH0046 | 2017-08-23 |  | 2017-09-13 | 2017-09-13 | 2018-01-03 | AT BUILDERS & GEN. MERCHANDISE
30822 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127959 | Bayabas ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 29648117.03 |  |  | Completed | 1 |  |  | P00180168MN-CW1 | 17KH0080 | 2017-11-27 |  |  | 2017-12-19 | 2018-01-15 | LC CONSTRUCTION
30823 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304106 | Bayabas NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 37033627.5 |  |  | Completed | 1 |  |  | P00180197MN-CW1 | 17KH0094 | 2017-11-29 |  |  | 2017-12-20 | 2018-01-16 | L & L CONST.
30824 | NC 2017 | TVL | Region X | Cagayan de Oro City | 304106 | Bayabas NHS | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | 1UNIT TVL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00180198MN-CW1 | 17KH0121 | 2017-12-02 |  |  | 2017-09-26 | 2018-01-17 | AT BUILDERS & GEN. MERCHANDISE
30825 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315412 | Bonbon National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 29482156.79 |  |  | Completed | 1 |  |  | P00180235MN-CW1 | 17KH0083 | 2017-11-27 |  |  | 2017-12-19 | 2018-01-15 | L & L CONST.
30826 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127949 | Bugo Central School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9690000 |  |  | Completed | 1 |  |  | P00180242MN-CW1 | 17KD0060 | [5 empty] | LEXAND CONS DEVT.
30827 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127949 | Bugo Central School | CAGAYAN DE ORO CITY (Capital) | 2 |  | 10 | 2STY10CL | BATCH 10 | 23118400 |  |  | Completed | 1 |  |  | P00180243MN-CW1 | 17KD0061 | [5 empty] | L & L CONST.
30828 | NC 2017 | TVL | Region X | Cagayan de Oro City | 304107 | Bugo National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 10 | 4500000 |  |  | Completed | 1 |  |  | P00180248MN-CW1 | 17KD0065 | [5 empty] | LEXAND CONS DEVT.
30829 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304107 | Bugo National High School | CAGAYAN DE ORO CITY (Capital) | 2 |  | 20 | 4STY20CL | BATCH 10 | 52800000 |  |  | Completed | 1 |  |  | P00180249MN-CW1 | 17KD0083 | [5 empty] | ESR CONST. & DEV. CORP.
30830 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127998 | Bulua CS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 29482156.79 |  |  | Completed | 1 |  |  | P00180187MN-CW1 | 17KH0078 | 2017-11-27 |  |  | 2017-12-19 | 2018-01-15 | LEGACY CONSTRUCTION
30831 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304108 | Bulua National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 37033627.5 |  |  | Completed | 1 |  |  | P00180199MN-CW1 | 17KH0093 | 2017-11-29 |  |  | 2017-12-20 | 2018-01-16 | LAJ TRUCKING AND BUILDERS INC
30832 | NC 2017 | K10 | Region X | Cagayan de Oro City | 202003 | Cadayonan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180196MN-CW1 | 17KH0047 | 2017-08-24 |  | 2017-09-14 | 2017-09-14 | 2018-01-03 | DCS BUILDERS AND ENTERPRISES
30833 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304111 | CAGAYAN DE ORO NATIONAL HIGH SCHOOL | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 28 | 4STY28CL | BATCH 10 | 65400000 |  |  | Completed | 1 |  |  | P00180251MN-CW1 | 17KD0084 | [5 empty] | LEGACY CONS. CORP.
30834 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304111 | CAGAYAN DE ORO NATIONAL HIGH SCHOOL | CAGAYAN DE ORO CITY (Capital) | 2 |  | 28 | 4STY28CL | BATCH 10 | 65400000 |  |  | Completed | 1 |  |  | P00180250MN-CW1 | 17KD0085 | [5 empty] | DCM CONS.
30835 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315403 | Cagayan de Oro NHS - Balulang Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 29482156.79 |  |  | Completed | 1 |  |  | P00180226MN-CW1 | 17KH0081 | 2017-11-27 |  |  | 2017-12-19 | 2018-01-15 | JDE CONSTRUCTION
30836 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315403 | Cagayan de Oro NHS - Balulang Annex | CAGAYAN DE ORO CITY (Capital) | 1 |  | 6 | 3STY6CL | BATCH 10 | 13862404.64 |  |  | Completed | 1 |  |  | P00180227MN-CW1 | 17KH0101 | 2017-12-01 |  |  | 2017-12-22 | 2018-01-16 | JDE CONSTRUCTION
30837 | NC 2017 | TVL | Region X | Cagayan de Oro City | 315403 | Cagayan de Oro NHS - Balulang Annex | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | 1UNIT TVL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00180228MN-CW1 | 17KH0067 | 2017-11-24 |  |  | 2017-09-14 | 2018-01-15 | JDE CONSTRUCTION
30838 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127964 | Camaman-an Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 52980427.05 |  |  | Completed | 1 |  |  | P00180244MN-CW1 | 17KD0062 | [5 empty] | ST. TIMOTHY CONS. CORP.
30839 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315404 | CAMAMAN-AN NATIONAL HIGH SCHOOL | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 10 | 29400000 |  |  | Completed | 1 |  |  | P00180255MN-CW1 | 17KD0080 | [5 empty] | L.C. CONS. CORP.
30840 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315404 | CAMAMAN-AN NATIONAL HIGH SCHOOL | CAGAYAN DE ORO CITY (Capital) | 2 |  | 4 | 2STY4CL | BATCH 10 | 9753800 |  |  | Completed | 1 |  |  | P00180256MN-CW1 | 17KD0068 | [5 empty] | ANGEL AND SAM CONS. & GEN. MDSE
30841 | NC 2017 | K10 | Region X | Cagayan de Oro City | 128000 | Camp Evangelista ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180189MN-CW1 | 17KH0042 | 2017-08-23 |  | 2017-09-13 | 2017-09-13 | 2018-01-03 | JTA BUILDERS
30842 | NC 2017 | K10 | Region X | Cagayan de Oro City | 128001 | Canito-an Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 1STY4CL | BATCH 10 | 4888835.15 |  |  | Completed | 1 |  |  | P00180190MN-CW1 | 17KH0060 |  |  |  | 2017-09-27 | 2018-01-03 | JTA BUILDERS
30843 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304109 | Canitoan National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 37033627.5 |  |  | Completed | 1 |  |  | p00180200mn-cw1 | 17HK0086 | 2017-11-27 |  |  | 2017-12-19 | 2018-01-15 | JTA BUILDERS
30844 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304112 | Carmen National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 29482156.79 |  |  | Completed | 1 |  |  | P00180203MN-CW1 | 17KH0082 | 2017-11-27 |  |  | 2017-12-19 | 2018-01-15 | JTA BUILDERS
30845 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304112 | Carmen National High School | CAGAYAN DE ORO CITY (Capital) | 1 |  | 6 | 3STY6CL | BATCH 10 | 13862404.64 |  |  | Completed | 1 |  |  | P00180204MN-CW1 | 17KH0100 | 2017-12-01 |  |  | 2017-12-22 | 2018-01-16 | ZI-9 BUILDERS & SUPPLIES
30846 | NC 2017 | TVL | Region X | Cagayan de Oro City | 304112 | Carmen National High School | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | 1UNIT TVL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00180205MN-CW1 | 17KH0066 | 2017-11-24 |  |  | 2017-12-14 | 2018-01-15 | H & N BUILDERS & ENTERPRISES
30847 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127941 | Cugman ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9634000 |  |  | Completed | 1 |  |  | P00180236MN-CW1 | 17KD0067 | [5 empty] | MJ ALONTO BUILDERS & ENT.
30848 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127941 | Cugman ES | CAGAYAN DE ORO CITY (Capital) | 2 |  | 9 | 3STY9CL | BATCH 10 | 29400000 |  |  | Completed | 1 |  |  | P00180237MN-CW1 | 17KD0077 | [5 empty] | L.C. CONS. CORP.
30849 | NC 2017 | K10 | Region X | Cagayan de Oro City | 202001 | Dunggoan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180195MN-CW1 | 17KH0043 | 2017-08-23 |  |  | 2017-09-13 | 2018-01-03 | DCD BUILDERS & ENTERPRISES
30850 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127991 | Fr. William F. Masterson, SJ., ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 31895471.3 |  |  | Completed | 1 |  |  | P00180181MN-CW1 | 17KH0089 | 2017-11-29 |  |  | 2017-12-20 | 2018-01-16 | LAJ TRUCKING AND BUILDERS INC
30851 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127944 | Gusa ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 41983330.11 |  |  | Completed | 1 |  |  | P00180238MN-CW1 | 17KD0076 | [5 empty] | ALPHA & OMEGA GEN. CONTRACTOR AND DEV. CORP.
30852 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127944 | Gusa ES | CAGAYAN DE ORO CITY (Capital) | 2 |  | 16 | 4STY16CL | BATCH 10 | 47002970.94 |  |  | Completed | 1 |  |  | P00180239MN-CW1 | 17KD0078 | [5 empty] | LEGACY CONS. CORP.
30853 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315408 | Gusa NHS - FS Catanico Annex | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 32900000 |  |  | Completed | 1 |  |  | P00180257MN-CW1 | 17KD0081 | [5 empty] | ESR CONST. & DEV. CORP.
30854 | NC 2017 | K10 | Region X | Cagayan de Oro City | 128003 | IPONAN ELEMENTARY SCHOOL | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9089256.64 |  |  | Completed | 1 |  |  | P00180191MN-CW1 | 17KH0074 | 2017-11-25 |  |  | 2017-12-18 | 2018-01-15 | H & N BUILDERS & ENTERPRISES
30855 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304117 | Iponan National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 37033627.5 |  |  | Completed | 1 |  |  | P00180206MN-CW1 | 17HK0092 | 2017-11-29 |  |  | 2017-12-20 | 2018-01-16 | JAMARI CONSTRUCTION
30856 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315409 | Iponan NHS - San Simon Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 8950901.76 |  |  | Completed | 1 |  |  | P00180234MN-CW1 | 17KH0072 | 2017-11-25 |  |  | 2017-12-18 | 2018-01-15 | TRENCH ENGINEERING
30857 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127963 | Kauswagan CS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 10 | 24673897.39 |  |  | Completed | 1 |  |  | P00180169MN-CW1 | 17KH0087 | 2017-11-29 |  |  | 2017-12-20 | 2018-01-16 | L & L CONST.
30858 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127976 | Kiam-Is ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9013136.85 |  |  | Completed | 1 |  |  | P00180171MN-CW1 | 17HK0077 | 2017-11-25 |  |  | 2017-12-18 | 2018-01-15 | H & N BUILDERS & ENTERPRISES
30859 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127977 | Lumbia Central School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9013136.84 |  |  | Completed | 1 |  |  | P00180172MN-CW1 | 17KH0075 | 2017-11-25 |  |  | 2017-12-18 | 2018-01-15 | RBT VENTURES
30860 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127977 | Lumbia Central School | CAGAYAN DE ORO CITY (Capital) | 1 |  | 4 | 1STY4CL | BATCH 10 | 4888835.15 |  |  | Completed | 1 |  |  | P00180173MN-CW1 | 17KH0059 | 2017-09-08 |  |  | 2017-09-27 | 2018-01-03 | KS AGAD CONSTRUCTION
30861 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304119 | LUMBIA NATIONAL HIGH SCHOOL | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180207MN-CW1 | 17KH0045 | 2017-08-23 |  | 2017-09-13 | 2017-09-13 | 2018-01-03 | L & L CONST.
30862 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304119 | LUMBIA NATIONAL HIGH SCHOOL | CAGAYAN DE ORO CITY (Capital) | 1 |  | 8 | 4STY8CL | BATCH 10 | 17282460.21 |  |  | Completed | 1 |  |  | P00180208MN-CW1 | 17KH0104 | 2017-12-01 |  |  | 2017-12-22 | 2018-01-16 | JDE CONSTRUCTION
30863 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304119 | LUMBIA NATIONAL HIGH SCHOOL | CAGAYAN DE ORO CITY (Capital) | 1 |  | 6 | 3STY6CL | BATCH 10 | 13862404.64 |  |  | Completed | 1 |  |  | P00180209MN-CW1 | 17KH0102 | 2017-12-01 |  |  | 2017-12-22 | 2018-01-16 | CAGALAWAN ENTERPRISES
30864 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304119 | LUMBIA NATIONAL HIGH SCHOOL | CAGAYAN DE ORO CITY (Capital) | 1 |  | 12 | 3STY12CL | BATCH 10 | 29482156.79 |  |  | Completed | 1 |  |  | P00180210MN-CW1 | 17KH0084 | 2017-11-27 |  |  | 2017-12-19 | 2018-01-15 | L & L CONST.
30865 | NC 2017 | TVL | Region X | Cagayan de Oro City | 304119 | LUMBIA NATIONAL HIGH SCHOOL | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | 1UNIT TVL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00180211MN-CW1 | 17KH0120 | 2017-12-02 |  |  | 2017-12-26 | 2018-01-17 | CAGALAWAN ENTERPRISES
30866 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304120 | Macabalan NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 52827083.39 |  |  | Completed | 1 |  |  | P00180250MN-CW1 | 17KD0082 | [5 empty] | RCDG CONS. CORP./MEGAKONSTRUK DEV. CORP.
30867 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315410 | Macasandig National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 46883000 |  |  | Completed | 1 |  |  | P00180258MN-CW1 | 17KD0069 | [5 empty] | LEGACY CONST. CORP.
30868 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127978 | Magayad ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180174MN-CW1 | 17KH0049 | 2017-08-24 |  |  | 2017-09-14 | 2018-01-03 | DCD BUILDERS & ENTERPRISES
30869 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304121 | Mambuaya National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11705265.98 |  |  | Completed | 1 |  |  | P00180212MN-CW1 | 17KH0113 | 2017-12-02 |  |  | 2017-12-26 | 2018-01-17 | CAGALAWAN ENTERPRISES
30870 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304121 | Mambuaya National High School | CAGAYAN DE ORO CITY (Capital) | 1 |  | 4 | 2STY4CL | BATCH 10 | 8994999.72 |  |  | Completed | 1 |  |  | P00180213MN-CW1 | 17KH0107 | 2017-12-01 |  |  | 2017-12-22 | 2018-01-16 | L & L CONST.
30871 | NC 2017 | TVL | Region X | Cagayan de Oro City | 304121 | Mambuaya National High School | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | 1UNIT TVL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00180214MN-CW1 | 17KH0068 | 2017-08-24 |  |  | 2017-09-14 | 2018-01-15 | FOUR L BUILDERS & CONST. SUPPLY
30872 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304122 | Mambuaya NHS-Bayanga Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 10 | 16979790.26 |  |  | Completed | 1 |  |  | P00180215MN-CW1 | 17KH0114 | 2017-12-02 |  |  | 2017-12-26 | 2018-01-17 | L & L CONST.
30873 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315405 | Mambuaya NHS-Dansolihon Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180229MN-CW1 | 17KH0044 | 2017-08-23 |  | 2017-09-13 | 2017-09-14 | 2018-01-03 | FOUR L BUILDERS & CONST. SUPPLY
30874 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315405 | Mambuaya NHS-Dansolihon Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180230MN-CW1 | 17KH0048 | 2017-08-24 |  |  | 2017-09-14 | 2018-01-03 | FOUR L BUILDERS & CONST. SUPPLY
30875 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315405 | Mambuaya NHS-Dansolihon Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9100387.99 |  |  | Completed | 1 |  |  | P00180231MN-CW1 | 17KH0105 | 2017-12-01 |  |  | 2017-12-22 | 2018-01-16 | JTA BUILDERS
30876 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315405 | Mambuaya NHS-Dansolihon Annex | CAGAYAN DE ORO CITY (Capital) | 1 |  | 4 | 2STY4CL | BATCH 10 | 9100387.99 |  |  | Completed | 1 |  |  | P00180232MN-CW1 | 17KH0106 | 2017-12-01 |  |  | 2017-12-22 | 2018-01-16 | JTA BUILDERS
30877 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127980 | Man-Ai ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180175MN-CW1 | 17KH0050 | 2017-08-24 |  |  | 2017-09-14 | 2018-01-03 | H & N BUILDERS & ENTERPRISES
30878 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127981 | Midkiwan ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 8950901.76 |  |  | Completed | 1 |  |  | P00180176MN-CW1 | 17KH0070 | 2017-11-25 |  |  | 2017-12-18 | 2018-01-15 | Genetian Builders
30879 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127981 | Midkiwan ES | CAGAYAN DE ORO CITY (Capital) | 1 |  | 4 | 2STY4CL | BATCH 10 | 8950901.76 |  |  | Completed | 1 |  |  | P00180177MN-CW1 | 17KH0071 | 2017-11-25 |  |  | 2017-12-18 | 2018-01-15 | Genetian Builders
30880 | NC 2017 | K10 | Region X | Cagayan de Oro City | 128004 | Pagatpat ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 29604948.83 |  |  | Completed | 1 |  |  | P00180192MN-CW1 | 17HK0079 | 2017-11-27 |  |  | 2017-12-19 | 2018-01-15 | JIMWEN CONSTRUCTION & GEN. MSDE
30881 | NC 2017 | K10 | Region X | Cagayan de Oro City | 128005 | Pamalihi ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 8992391.82 |  |  | Completed | 1 |  |  | P00180193MN-CW1 | 17HK0076 | 2017-11-25 |  |  | 2017-12-18 | 2018-01-15 | D2J BUILDERS
30882 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127999 | Pedro "Oloy" N. Roa, Sr. ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 11840463.58 |  |  | Completed | 1 |  |  | P00180188MN-CW1 | 17KH0112 | 2017-12-02 |  |  | 2017-12-26 | 2018-01-17 | RT LIM CONSTRUCTION & SUPPLY
30883 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304110 | Pedro "Oloy" N. Roa, Sr. HS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 11779057.56 |  |  | Completed | 1 |  |  | P00180201MN-CW1 | 17KH0099 | 2017-12-01 |  |  | 2017-12-22 | 2018-01-16 | PAGADIAN AGGREGATES & MARKETING
30884 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304110 | Pedro "Oloy" N. Roa, Sr. HS | CAGAYAN DE ORO CITY (Capital) | 1 |  | 16 | 4STY16CL | BATCH 10 | 37033627.5 |  |  | Completed | 1 |  |  | P00180202MN-CW1 | 17KH0085 | 2017-11-27 |  |  | 2017-12-19 | 2018-01-15 | JTA BUILDERS
30885 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127993 | Sacred Heart Vill ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 17364321.56 |  |  | Completed | 1 |  |  | P00180182MN-CW1 | 17KH0110 | 2017-12-01 |  |  | 2017-12-22 | 2018-01-16 | LEGACY CONSTRUCTION
30886 | NC 2017 | K10 | Region X | Cagayan de Oro City | 128006 | San Simon ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11764893.17 |  |  | Completed | 1 |  |  | P00180194MN-CW1 | 17KH0109 | 2017-12-01 |  |  | 2017-12-22 | 2018-01-16 | TRENCH ENGINEERING
30887 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127967 | South City CS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 52895849.8 |  |  | Completed | 1 |  |  | P00180245MN-CW1 | 17KD0064 | [5 empty] | SCP/EDMOND RAY CONS. & SUPPLY (JV)
30888 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304125 | Taglimao National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11823155.52 |  |  | Completed | 1 |  |  | P00180219MN-CW1 | 17KH0117 | 2017-12-02 |  |  | 2017-12-26 | 2018-01-17 | PAGADIAN AGGREGATES & MARKETING
30889 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304125 | Taglimao National High School | CAGAYAN DE ORO CITY (Capital) | 1 |  | 4 | 2STY4CL | BATCH 10 | 9112889.26 |  |  | Completed | 1 |  |  | P00180220MN-CW1 | 17HK0108 | 2017-12-01 |  |  | 2017-12-22 | 2018-01-16 | DCD BUILDERS & ENTERPRISES
30890 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304126 | Taglimao NHS-Besigan Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180221MN-CW1 | 17KH0051 | 2017-08-24 |  |  | 2017-09-14 | 2018-01-03 | DCD BUILDERS & ENTERPRISES
30891 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304126 | Taglimao NHS-Besigan Annex | CAGAYAN DE ORO CITY (Capital) | 1 |  | 4 | 2STY4CL | BATCH 10 | 9131984.69 |  |  | Completed | 1 |  |  | P00180222MN-CW1 | 17HK0118 | 2017-12-02 |  |  | 2017-12-26 | 2018-01-17 | DCD BUILDERS & ENTERPRISES
30892 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315406 | Taglimao NHS-Tumpagon Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 10 | 17141777.76 |  |  | Completed | 1 |  |  | P00180233MN-CW1 | 17KH0166 | 2017-12-02 |  |  | 2017-12-26 | 2018-01-17 | BRIMA CONSTRUCTION AND ENTERPRISES
30893 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127985 | Tagpangi ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180178MN-CW1 | 17KH0042 | 2017-08-23 |  | 2017-09-13 | 2017-09-13 | 2018-01-03 | AT BUILDERS & GEN. MERCHANDISE
30894 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304127 | Tagpangi NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 17364321.56 |  |  | Completed | 1 |  |  | P00180223MN-CW1 | 17KH0103 | 2017-12-01 |  |  | 2017-12-22 | 2018-01-16 | JTA BUILDERS
30895 | NC 2017 | TVL | Region X | Cagayan de Oro City | 304127 | Tagpangi NHS | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | 1UNIT TVL | BATCH 10 | 3768436.02 |  |  | Completed | 1 |  |  | P00180224MN-CW1 | 17KH0124 | 2017-12-02 |  |  | 2017-12-26 | 2018-01-17 | KS AGAD CONSTRUCTION
30896 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304128 | Tagpangi NHS-Tuburan Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9131984.69 |  |  | Completed | 1 |  |  | P00180225MN-CW1 | 17KH0119 | 2017-12-02 |  |  | 2017-12-26 | 2018-01-17 | DCD BUILDERS & ENTERPRISES
30897 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127986 | Tignapolo-an ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 8950901.76 |  |  | Completed | 1 |  |  | P00180179MN-CW1 | 17KH0073 | 2017-11-25 |  |  | 2017-12-18 | 2018-01-15 | H & N BUILDERS & ENTERPRISES
30898 | NC 2017 | SHS | Region X | Cagayan de Oro City | 304123 | Tignapoloan NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 10 | 17141777.76 |  |  | Completed | 1 |  |  | P00180216MN-CW1 | 17KH0115 | 2017-12-02 |  |  | 2017-12-26 | 2018-01-17 | JDE CONSTRUCTION
30899 | NC 2017 | TVL | Region X | Cagayan de Oro City | 304123 | Tignapoloan NHS | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | 1UNIT TVL | BATCH 10 | 3768436.02 |  |  | Completed | 1 |  |  | P00180217MN-CW1 | 17KH0122 | 2017-12-02 |  |  | 2017-09-26 | 2018-01-17 | VISTA CONSTRUCTION
30900 | NC 2017 | TVL | Region X | Cagayan de Oro City | 304123 | Tignapoloan NHS | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | 1UNIT TVL | BATCH 10 | 3768436.02 |  |  | Completed | 1 |  |  | P00180218MN-CW1 | 17KH0123 | 2017-12-02 |  |  | 2017-09-26 | 2018-01-17 | VISTA CONSTRUCTION
30901 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127989 | Tumpagon ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180180MN-CW1 | 17KH0058 | 2017-09-08 |  |  | 2017-09-27 | 2018-01-03 | KS AGAD CONSTRUCTION
30902 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127994 | Upper Carmen ES | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00180183MN-CW1 | 17KH0052 | 2017-08-24 |  |  | 2017-09-14 | 2018-01-03 | ANGEL AND SAM CONS. & GEN. MDSE
30903 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127995 | West City Central School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 41655959.5 |  |  | Completed | 1 |  |  | P00180184MN-CW1 | 17KH0069 | 2017-11-25 |  |  | 2017-12-18 | 2018-01-15 | JTA BUILDERS
30904 | NC 2017 | K10 | Region X | Cagayan de Oro City | 127995 | West City Central School | CAGAYAN DE ORO CITY (Capital) | 1 |  | 12 | 4STY12CL | BATCH 10 | 31897339.48 |  |  | Completed | 1 |  |  | P00180185MN-CW1 | 17KH0090 | 2017-11-29 |  |  | 2017-12-20 | 2018-01-16 | JTA BUILDERS
30905 | NC 2017 | SHS | Region X | Camiguin | 315001 | Maac National High School | GUINSILIBAN | 0 | 1 | 8 | 2STY8CL | BATCH 10 | 17511571 |  |  | Completed | 1 | [9 empty] | JUNJING CONSTRUCTION AND GENERAL MERCHANDISE
30906 | NC 2017 | TVL | Region X | Camiguin | 315001 | Maac National High School | GUINSILIBAN | 0 |  | 2 | WORKSHOP BLDG. 7X18) | BATCH 10 | 5238720 |  |  | Completed | 1 | [9 empty] | JAPUZ-JANSOL ENTERPRISES
30907 | NC 2017 | K10 | Region X | Camiguin | 126895 | Catohugan ES | MAHINOG | 0 | 1 | 4 | 1STY4CL | BATCH 10 | 5054181.56 |  |  | Completed | 1 | [9 empty] | SHEEN-SHEEN CONST.
30908 | NC 2017 | K10 | Region X | Camiguin | 126900 | Owakan Elementary School | MAHINOG | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 4136390.14 |  |  | Completed | 1 | [9 empty] | SHEEN-SHEEN CONST.
30909 | NC 2017 | SHS | Region X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | SAGAY | 0 | 1 | 4 | 2STY4CL | BATCH 10 | 9244997.11 |  |  | Completed | 1 |  |  | P00180261MN-CW1 | 17KE0089 | [5 empty] | JAPUZ-JANSOL ENTERPRISES
30910 | NC 2017 | SHS | Region X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | SAGAY | 0 |  | 4 | 2STY4CL | BATCH 10 | 9244997.11 |  |  | Completed | 1 |  |  | P00180262MN-CW1 | 17KE0090 | [5 empty] | JAPUZ-JANSOL ENTERPRISES
30911 | NC 2017 | SHS | Region X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | SAGAY | 0 |  | 4 | 2STY4CL | BATCH 10 | 9189079.88 |  |  | Completed | 1 | [9 empty] | CAGALAWAN ENTERPRISES
30912 | NC 2017 | TVL | Region X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | SAGAY | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3512385 |  |  | Completed | 1 | [9 empty] | FOUR L BUILDERS & CONST. SUPPLY
30913 | NC 2017 | TVL | Region X | Iligan City | 304138 | Acelo C. Badelles, Sr. MHS (Tipanoy NHS) | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 9095901.76 |  |  | Completed | 1 |  |  | P00180267MN | 17KF0154 | [5 empty] | AL FAHDEL CONSTRUCTION AND ENGINEERING
30914 | NC 2017 | TVL | Region X | Iligan City | 304139 | Acelo C. Badelles, Sr. MNHS - Abuno HS Annex | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 9065901.76 |  |  | Completed | 1 |  |  | P00180268MN | 17KF0155 | [5 empty] | D.O.T. CONSTRUCTION
30915 | NC 2017 | TVL | Region X | Iligan City | 304143 | Dalipuga National High School | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 9065901.76 |  |  | Completed | 1 |  |  | P00180269MN | 17KF0156 | [5 empty] | RED CONSTRUCTION TECHNIK
30916 | NC 2017 | TVL | Region X | Iligan City | 304144 | Dalipuga NHS - Hindang NHS Annex | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 9065901.76 |  |  | Completed | 1 |  |  | P00180270MN | 17KF0157 | [5 empty] | AHMADI BUILDERS
30917 | NC 2017 | TVL | Region X | Iligan City | 304146 | Iligan City East National HS (Sta. Filomena) | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 9115901.76 |  |  | Completed | 1 |  |  | P00180271MN | 17KF0158 | [5 empty] | INMAR BUILDER AND ENTERPRISES
30918 | NC 2017 | SHS | Region X | Iligan City | 315603 | Iligan City NHS - Tambacan HS Annex | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | BATCH 10 | 9045901.76 |  |  | Completed | 1 |  |  | P00180276MN | 17KF0153 | [5 empty] | MJ ALONTO BUILDERS & ENTERPRISES
30919 | NC 2017 | TVL | Region X | Iligan City | 304147 | KIWALAN NATIONAL HIGH SCHOOL | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 9045901.76 |  |  | Completed | 1 |  |  | P00180272MN | 17KF0159 | [5 empty] | ALFAHAD BUILDERS AND ENTERPRISES
30920 | NC 2017 | TVL | Region X | Iligan City | 304152 | Maria Cristina National High School | ILIGAN CITY | 0 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 9045901.76 |  |  | Completed | 1 |  |  | P00180273MN | 17KF0160 | [5 empty] | AMMAR CONSTRUCTION AND ENTERPRISES
30921 | NC 2017 | SHS | Region X | Iligan City | 304156 | Suarez National High School | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | BATCH 10 | 9115901.76 |  |  | Completed | 1 |  |  | P00180274MN | 17KF0152 | [5 empty] | SDM VENTURES
30922 | NC 2017 | TVL | Region X | Iligan City | 304160 | Tubaran NHS - Digkilaan HS Annex | ILIGAN CITY | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3083750 |  |  | Completed | 1 |  |  | P00180275MN | 17KF0161 | [5 empty] | AHMADI BUILDERS
30923 | NC 2017 | SHS | Region X | Lanao del Norte | 304000 | Binuni-Demologan NHS | BACOLOD | 1 | 1 | 8 | 2STY8CL | BATCH 10 | 17174790.26 |  |  | Completed | 1 |  |  | P00180278MN | 17KF0171 | [5 empty] | TOMAHAWK BUILDERS AND GENERAL SERVICE
30924 | NC 2017 | TVL | Region X | Lanao del Norte | 304007 | Liangan NHS | BACOLOD | 1 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 10976394.94 |  |  | Completed | 1 |  |  | P00180284MN | 17KF0177 | [5 empty] | ALQAOD CONSTRUCTION AND SUPPLY
30925 | NC 2017 | TVL | Region X | Lanao del Norte | 304007 | Liangan NHS | BACOLOD | 1 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 10976394.94 |  |  | Completed | 1 |  |  | P00180285MN | 17KF0178 | [5 empty] | ALQAOD CONSTRUCTION AND SUPPLY
30926 | NC 2017 | TVL | Region X | Lanao del Norte | 304007 | Liangan NHS | BACOLOD | 1 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 11111394.94 |  |  | Completed | 1 |  |  | P00180286MN | 17KF0181 | [5 empty] | ALFAHAD BUILDERS AND ENTERPRISES
30927 | NC 2017 | SHS | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
30928 | NC 2017 | TVL | Region X | Lanao del Norte | 304001 | Diosdado Yap Sr. National High School | BAROY | 1 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 10991394.94 |  |  | Completed | 1 |  |  | P00180279MN | 17KF0175 | [5 empty] | MARKBUILT ENTERPRISES
30929 | NC 2017 | TVL | Region X | Lanao del Norte | 304001 | Diosdado Yap Sr. National High School | BAROY | 1 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 10991394.94 |  |  | Completed | 1 |  |  | P00180280MN | 17KF0176 | [5 empty] | ALFAHAD BUILDERS AND ENTERPRISES
30930 | NC 2017 | TVL | Region X | Lanao del Norte | 304005 | Lanao del Norte NCHS | BAROY | 1 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 10966394.94 |  |  | Completed | 1 |  |  | P00180281MN | 17KF0172 | [5 empty] | RUDHIL CONSTRUCTION AND ENTERPRISES, INC
30931 | NC 2017 | TVL | Region X | Lanao del Norte | 304005 | Lanao del Norte NCHS | BAROY | 1 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 10966394.94 |  |  | Completed | 1 |  |  | P00180282MN | 17KF0173 | [5 empty] | RUDHIL CONSTRUCTION AND ENTERPRISES, INC
30932 | NC 2017 | TVL | Region X | Lanao del Norte | 304005 | Lanao del Norte NCHS | BAROY | 1 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 10966394.94 |  |  | Completed | 1 |  |  | P00180283MN | 17KF0174 | [5 empty] | RUDHIL CONSTRUCTION AND ENTERPRISES, INC
30933 | NC 2017 | K10 | Region X | Lanao del Norte | 126990 | Cathedral Falls ES | KAPATAGAN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3763809.68 |  |  | Completed | 1
30934 | NC 2017 | K10 | Region X | Lanao del Norte | 126990 | Cathedral Falls ES | KAPATAGAN | 2 |  | 3 | 1STY3CL | BATCH 10 | 3763809.68 |  |  | Completed | 1
30935 | NC 2017 | K10 | Region X | Lanao del Norte | 127010 | Margos ES | KAPATAGAN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3763809.68 |  |  | Completed | 1
30936 | NC 2017 | K10 | Region X | Lanao del Norte | 127010 | Margos ES | KAPATAGAN | 2 |  | 3 | 1STY3CL | BATCH 10 | 3763809.68 |  |  | Completed | 1
30937 | NC 2017 | K10 | Region X | Lanao del Norte | 127009 | Sixto Maghanoy Sr. MES (Formerly Lapinig ES) | KAPATAGAN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3766809.68 |  |  | Completed | 1
30938 | NC 2017 | K10 | Region X | Lanao del Norte | 127009 | Sixto Maghanoy Sr. MES (Formerly Lapinig ES) | KAPATAGAN | 2 |  | 3 | 1STY3CL | BATCH 10 | 3766809.68 |  |  | Completed | 1
30939 | NC 2017 | K10 | Region X | Lanao del Norte | 127009 | Sixto Maghanoy Sr. MES (Formerly Lapinig ES) | KAPATAGAN | 2 |  | 3 | 1STY3CL | BATCH 10 | 3766809.68 |  |  | Completed | 1
30940 | NC 2017 | SHS | Region X | Lanao del Norte | 304011 | Marcela T. Mabanta NHS | KAUSWAGAN | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9075901.76 |  |  | Completed | 1 |  |  | P00180291MN | 17KF0170 | [5 empty] | BRIMA CONSTRUCTION AND ENTERPRISES
30941 | NC 2017 | SHS | Region X | Lanao del Norte | 304020 | Geronima Cabrera NHS (Riverside NHS) | KOLAMBUGAN | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 13939515.1 |  |  | Completed | 1 |  |  | P00180293MN | 17KF0182 | [5 empty] | SDM VENTURES
30942 | NC 2017 | TVL | Region X | Lanao del Norte | 304020 | Geronima Cabrera NHS (Riverside NHS) | KOLAMBUGAN | 1 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 11001394.94 |  |  | Completed | 1 |  |  | P00180294MN | 17KF0179 | [5 empty] | NDP CONSTRUCTION DEVELOPMENT
30943 | NC 2017 | TVL | Region X | Lanao del Norte | 304020 | Geronima Cabrera NHS (Riverside NHS) | KOLAMBUGAN | 1 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 11001394.94 |  |  | Completed | 1 |  |  | P00180295MN | 17KF0180 | [5 empty] | TESAR BUILDERS
30944 | NC 2017 | K10 | Region X | Lanao del Norte | 127071 | F. M. Posadas ES | LALA | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3766809.68 |  |  | Completed | 1
30945 | NC 2017 | K10 | Region X | Lanao del Norte | 127072 | Gumagamot ES | LALA | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3866809.68 |  |  | Completed | 1
30946 | NC 2017 | K10 | Region X | Lanao del Norte | 127073 | Lala Proper ES | LALA | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3766809.68 |  |  | Completed | 1
30947 | NC 2017 | K10 | Region X | Lanao del Norte | 127073 | Lala Proper ES | LALA | 2 |  | 3 | 1STY3CL | BATCH 10 | 3766809.68 |  |  | Completed | 1
30948 | NC 2017 | K10 | Region X | Lanao del Norte | 127073 | Lala Proper ES | LALA | 2 |  | 3 | 1STY3CL | BATCH 10 | 3766809.68 |  |  | Completed | 1
30949 | NC 2017 | K10 | Region X | Lanao del Norte | 127091 | San Manuel ES | LALA | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3766809.68 |  |  | Completed | 1
30950 | NC 2017 | SHS | Region X | Lanao del Norte | 304010 | Maigo NHS | MAIGO | 1 | 1 | 9 | 3STY9CL | BATCH 10 | 24666047.73 |  |  | Completed | 1 |  |  | P00180287MN | 17KF0162 | [5 empty] | JUNJING CONSTRUCTION AND GENERAL MERCHANDISE
30951 | NC 2017 | TVL | Region X | Lanao del Norte | 304010 | Maigo NHS | MAIGO | 1 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 11041394.94 |  |  | Completed | 1 |  |  | P00180288MN | 17KF0163 | [5 empty] | GRAND BUILDERS
30952 | NC 2017 | TVL | Region X | Lanao del Norte | 304010 | Maigo NHS | MAIGO | 1 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 11091394.94 |  |  | Completed | 1 |  |  | P00180289MN | 17KF0164 | [5 empty] | NDP CONST. DEV'T.
30953 | NC 2017 | TVL | Region X | Lanao del Norte | 304010 | Maigo NHS | MAIGO | 1 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 11091394.94 |  |  | Completed | 1 |  |  | P00180290MN | 17KF0165 | [5 empty] | NDP CONST. DEV'T.
30954 | NC 2017 | SHS | Region X | Lanao del Norte | 304019 | Pantar NHS | PANTAR | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
30955 | NC 2017 | TVL | Region X | Lanao del Norte | 315102 | Lanao del Norte Provincial Science and Technology HS (former Malingao NHS (Annex New Pualas NHS) | TUBOD (Capital) | 1 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 11021394.94 |  |  | Completed | 1 |  |  | P00180296MN | 17KF0166 | [5 empty] | MJ ALONTO BUILDERS AND ENTERPRISES
30956 | NC 2017 | TVL | Region X | Lanao del Norte | 315102 | Lanao del Norte Provincial Science and Technology HS (former Malingao NHS (Annex New Pualas NHS) | TUBOD (Capital) | 1 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 11021394.94 |  |  | Completed | 1 |  |  | P00180297MN | 17KF0167 | [5 empty] | ALFAHAD BUILDERS AND ENTERPRISES
30957 | NC 2017 | TVL | Region X | Lanao del Norte | 315102 | Lanao del Norte Provincial Science and Technology HS (former Malingao NHS (Annex New Pualas NHS) | TUBOD (Capital) | 1 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 11021394.94 |  |  | Completed | 1 |  |  | P00180298MN | 17KF0168 | [5 empty] | LANAO BUILDERS AND ENTERPRISES
30958 | NC 2017 | K10 | Region X | Misamis Oriental | 127598 | Tugasnon ES | ALUBIJID | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2682145.92 |  |  | Completed | 1 |  |  |  | 17KL0221
30959 | NC 2017 | K10 | Region X | Misamis Oriental | 127600 | Bagaay ES | BALINGASAG | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4124689.48 |  |  | Completed | 1
30960 | NC 2017 | K10 | Region X | Misamis Oriental | 127607 | Calawag ES | BALINGASAG | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3005724.83 |  |  | Completed | 1
30961 | NC 2017 | K10 | Region X | Misamis Oriental | 127610 | Dansuli ES | BALINGASAG | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3457249.96 |  |  | Completed | 1
30962 | NC 2017 | K10 | Region X | Misamis Oriental | 127612 | Gumpot ES | BALINGASAG | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3049756.77 |  |  | Completed | 1
30963 | NC 2017 | K10 | Region X | Misamis Oriental | 127881 | Kauswagan ES | BALINGOAN | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4197982.9 |  |  | Completed | 1
30964 | NC 2017 | K10 | Region X | Misamis Oriental | 127887 | Mapua ES | BALINGOAN | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4117405.88 |  |  | Completed | 1
30965 | NC 2017 | K10 | Region X | Misamis Oriental | 127740 | Valdeconcha ES | BINUANGAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2988958.27 |  |  | Completed | 1
30966 | NC 2017 | K10 | Region X | Misamis Oriental | 127640 | Don Gregorio Pelaez ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2722145.92 |  |  | Completed | 1 |  |  |  | 17KL0220
30967 | NC 2017 | K10 | Region X | Misamis Oriental | 127647 | Lanise ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2790545.92 |  |  | Completed | 1 |  |  |  | 17KL0219
30968 | NC 2017 | K10 | Region X | Misamis Oriental | 127651 | Malagana ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2727145.92 |  |  | Completed | 1 |  |  |  | 17KL0218
30969 | NC 2017 | K10 | Region X | Misamis Oriental | 127758 | Gitagum CS | GITAGUM | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2750545.92 |  |  | Completed | 1 |  |  |  | 17KL0217
30970 | NC 2017 | K10 | Region X | Misamis Oriental | 127685 | Gimangpang ES | INITAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2750545.92 |  |  | Completed | 1 |  |  |  | 17KL0216
30971 | NC 2017 | TVL | Region X | Misamis Oriental | 304072 | Initao NCHS | INITAO | 2 | 1 | 8 | 4STY8CL (4 REGULAR WORKSHOP) | BATCH 10 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0238
30972 | NC 2017 | TVL | Region X | Misamis Oriental | 304072 | Initao NCHS | INITAO | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 10 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0237
30973 | NC 2017 | SHS | Region X | Misamis Oriental | 304072 | Initao NCHS | INITAO | 2 |  | 2 | 1STY2CL | BATCH 10 | 2682145.92 |  |  | Completed | 1 |  |  |  | 17KL0214
30974 | NC 2017 | K10 | Region X | Misamis Oriental | 127690 | Kanitoan ES | INITAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2682145.92 |  |  | Completed | 1 |  |  |  | 17KL0215
30975 | NC 2017 | K10 | Region X | Misamis Oriental | 127707 | Kimaya ES | JASAAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2682145.92 |  |  | Completed | 1 |  |  |  | 17KL0213
30976 | NC 2017 | K10 | Region X | Misamis Oriental | 127717 | Biray ES | KINOGUITAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3319351 |  |  | Completed | 1
30977 | NC 2017 | K10 | Region X | Misamis Oriental | 127721 | Campo ES | KINOGUITAN | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4159648.02 |  |  | Completed | 1
30978 | NC 2017 | K10 | Region X | Misamis Oriental | 127912 | Kibaghot ES | LAGUINDINGAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2750545.92 |  |  | Completed | 1 |  |  |  | 17KL0212
30979 | NC 2017 | SHS | Region X | Misamis Oriental | 304078 | Laguindingan NHS | LAGUINDINGAN | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 12643213.02 |  |  | Completed | 1 |  |  |  | 17KL0239
30980 | NC 2017 | TVL | Region X | Misamis Oriental | 304078 | Laguindingan NHS | LAGUINDINGAN | 2 |  | 16 | 4STY16CL (4 REGULAR WORKSHOP, 2 SCIENCE LAB, 2 ICT LAB) | BATCH 10 | 42656087.96 |  |  | Completed | 1 |  |  |  | 17KL0236
30981 | NC 2017 | SHS | Region X | Misamis Oriental | 304078 | Laguindingan NHS | LAGUINDINGAN | 2 |  | 2 | 1STY2CL | BATCH 10 | 2682145.92 |  |  | Completed | 1 |  |  |  | 17KL0211
30982 | NC 2017 | K10 | Region X | Misamis Oriental | 127775 | Cabubuhan ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3149279.9 |  |  | Completed | 1
30983 | NC 2017 | K10 | Region X | Misamis Oriental | 127788 | Pag-Asa ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3791468.78 |  |  | Completed | 1
30984 | NC 2017 | K10 | Region X | Misamis Oriental | 127864 | Yungod ES | SALAY | 1 | 1 | 4 | 1STY4CL | BATCH 10 | 5385143.89 |  |  | Completed | 1
30985 | NC 2017 | K10 | Region X | Misamis Oriental | 127714 | Alicomohan ES | SUGBONGCOGON | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4137055.17 |  |  | Completed | 1
30986 | NC 2017 | K10 | Region X | Misamis Oriental | 127865 | Baluarte ES | TAGOLOAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2750545.92 |  |  | Completed | 1 |  |  |  | 17KL0210
30987 | NC 2017 | K10 | Region X | Misamis Oriental | 127880 | Kalamkam ES | TALISAYAN | 1 | 1 | 4 | 1STY4CL | BATCH 10 | 5643839.95 |  |  | Completed | 1
30988 | NC 2017 | K10 | Region X | Misamis Oriental | 127884 | Magkarila ES | TALISAYAN | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4262152.06 |  |  | Completed | 1
30989 | NC 2017 | K10 | Region X | Misamis Oriental | 127895 | Sindangan ES | TALISAYAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3423590.19 |  |  | Completed | 1
30990 | NC 2017 | K10 | Region X | Misamis Oriental | 127908 | San Martin ES | VILLANUEVA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2750545.92 |  |  | Completed | 1 |  |  |  | 17KL0209
30991 | NC 2017 | TVL | Region X | Tangub City | 304026 | Banglay NHS | TANGUB CITY | 2 | 1 | 4 | FOUR (4) REGULAR WORKSHOP (2STY8CL) | BATCH 10 | 18672000 |  |  | Completed | 1
30992 | NC 2017 | TVL | Region X | Tangub City | 304027 | Bongabong NHS | TANGUB CITY | 2 | 1 | 2 | TWO (2) REGULAR WORKSHOP (2STY4CL) | BATCH 10 | 10073000 |  |  | Completed | 1
30993 | NC 2017 | TVL | Region X | Tangub City | 304027 | Bongabong NHS | TANGUB CITY | 2 |  | 2 | TWO (2) REGULAR WORKSHOP (2STY4CL) | BATCH 10 | 11314000 |  |  | Completed | 1
30994 | NC 2017 | TVL | Region X | Tangub City | 304054 | Caniangan NHS | TANGUB CITY | 2 | 1 | 2 | TWO (2) REGULAR WORKSHOP (2STY4CL) | BATCH 10 | 10033000 |  |  | Completed | 1
30995 | NC 2017 | TVL | Region X | Tangub City | 304054 | Caniangan NHS | TANGUB CITY | 2 |  | 2 | TWO (2) REGULAR WORKSHOP (2STY4CL) | BATCH 10 | 10140000 |  |  | Completed | 1
30996 | NC 2017 | K10 | Region X | Tangub City | 128246 | Lorenzo Tan Memorial CS | TANGUB CITY | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 13751000 |  |  | Completed | 1
30997 | NC 2017 | K10 | Region X | Tangub City | 128227 | Maloro ES | TANGUB CITY | 2 | 1 | 9 | 3STY9CL | BATCH 10 | 27762000 |  |  | Completed | 1
30998 | NC 2017 | K10 | Region X | Tangub City | 128227 | Maloro ES | TANGUB CITY | 2 |  | 4 | 2STY4CL | BATCH 10 | 11014000 |  |  | Completed | 1
30999 | NC 2017 | K10 | Region X | Tangub City | 128211 | Maquilao Integrated School | TANGUB CITY | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 14520000 |  |  | Completed | 1
31000 | NC 2017 | TVL | Region X | Tangub City | 323303 | Maquilao Integrated School | TANGUB CITY | 2 | 1 | 6 | SIX (6) REGULAR WORKSHOP (3STY12CL) | BATCH 10 | 31321000 |  |  | Completed | 1 |  |  | P00180371MN-CW1 | 17KJ0111 | [5 empty] | RUDHIL CONSTRUCTION & ENTERPRISES INC.
31001 | NC 2017 | K10 | Region X | Tangub City | 128252 | Pangabuan Elementary School | TANGUB CITY | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 13580000 |  |  | Completed | 1
31002 | NC 2017 | K10 | Region X | Tangub City | 128252 | Pangabuan Elementary School | TANGUB CITY | 2 |  | 6 | 2STY6CL | BATCH 10 | 13580000 |  |  | Completed | 1
31003 | NC 2017 | TVL | Region X | Tangub City | 304050 | Santa Maria NHS | TANGUB CITY | 2 | 1 | 8 | EIGHT (8) REGULAR WORKSHOP (4STY16CL) | BATCH 10 | 36750000 |  |  | Completed | 1 |  |  | P00180358MN-CW1 | 17KJ0112 | [5 empty] | GENETIAN BUILDERS
31004 | NC 2017 | TVL | Region X | Tangub City | 304053 | Silangit NHS | TANGUB CITY | 2 | 1 | 2 | TWO (2) REGULAR WORKSHOP (2STY4CL) | BATCH 10 | 10573000 |  |  | Completed | 1
31005 | NC 2017 | TVL | Region X | Tangub City | 304053 | Silangit NHS | TANGUB CITY | 2 |  | 3 | THREE (3) REGULAR WORKSHOP (3STY6CL) | BATCH 10 | 17356000 |  |  | Completed | 1
31006 | NC 2017 | TVL | Region X | Tangub City | 323302 | Simasay NHS | TANGUB CITY | 2 | 1 | 6 | SIX (6) REGULAR WORKSHOP (3STY12CL) | BATCH 10 | 30419000 |  |  | Completed | 1 |  |  | P00180370MN-CW1 | 17KJ0115 | [5 empty] | R.T LIM CONST. & SUPPLY/ RSMA BLDRS & GEN. MDSE
31007 | NC 2017 | SHS | Region X | Tangub City | 304056 | Sumirap NHS | TANGUB CITY | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 18592000 |  |  | Completed | 1
31008 | NC 2017 | TVL | Region X | Tangub City | 304056 | Sumirap NHS | TANGUB CITY | 2 |  | 6 | SIX (6) REGULAR WORKSHOP (2STY12CL) | BATCH 10 | 23945000 |  |  | Completed | 1
31009 | NC 2017 | K10 | Region X | Tangub City | 128217 | Tangub City CS | TANGUB CITY | 2 | 1 | 12 | 2STY12CL | BATCH 10 | 24834000 |  |  | Completed | 1
31010 | NC 2017 | K10 | Region X | Tangub City | 128217 | Tangub City CS | TANGUB CITY | 2 |  | 12 | 2STY12CL | BATCH 10 | 24844000 |  |  | Completed | 1
31011 | NC 2017 | K10 | Region X | Tangub City | 128217 | Tangub City CS | TANGUB CITY | 2 |  | 6 | 2STY6CL | BATCH 10 | 13847000 |  |  | Completed | 1
31012 | NC 2017 | K10 | Region X | Tangub City | 128217 | Tangub City CS | TANGUB CITY | 2 |  | 4 | 2STY4CL | BATCH 10 | 10569000 |  |  | Completed | 1
31013 | NC 2017 | TVL | Region X | Tangub City | 304171 | Tangub City NHS | TANGUB CITY | 2 | 1 | 8 | EIGHT (8) REGULAR WORKSHOP (4STY16CL) | BATCH 10 | 37254000 |  |  | Completed | 1
31014 | NC 2017 | SHS | Region X | Tangub City | 304171 | Tangub City NHS | TANGUB CITY | 2 |  | 9 | 3STY9CL | BATCH 10 | 26466000 |  |  | Completed | 1
31015 | NC 2017 | SHS | Region X | Tangub City | 304171 | Tangub City NHS | TANGUB CITY | 2 |  | 12 | 4STY12CL | BATCH 10 | 29736000 |  |  | Completed | 1
31016 | NC 2017 | SHS | Region X | Tangub City | 304171 | Tangub City NHS | TANGUB CITY | 2 |  | 12 | 4STY12CL | BATCH 10 | 29736000 |  |  | Completed | 1
31017 | NC 2017 | SHS | Region X | Tangub City | 304171 | Tangub City NHS | TANGUB CITY | 2 |  | 16 | 4STY16CL | BATCH 10 | 37256000 |  |  | Completed | 1
31018 | NC 2017 | K10 | Region X | Bukidnon | 126309 | Damulog CES | DAMULOG | 3 | 1 | 4 | 2STY4CL W/ TOILET | BATCH 12 | 9449979.35 |  |  | Completed | 1
31019 | NC 2017 | SHS | Region X | Bukidnon | 314929 | Macapari NHS | DAMULOG | 3 | 1 | 4 | 2STY4CL | BATCH 12 | 9725843.37 |  |  | Completed | 1
31020 | NC 2017 | SHS | Region X | Bukidnon | 314929 | Macapari NHS | DAMULOG | 3 |  | 4 | 2STY4CL | BATCH 12 | 9725843.37 |  |  | Completed | 1
31021 | NC 2017 | SHS | Region X | Bukidnon | 314929 | Macapari NHS | DAMULOG | 3 |  | 6 | 3STY6CL | BATCH 12 | 14961281.53 |  |  | Completed | 1
31022 | NC 2017 | K10 | Region X | Bukidnon | 126325 | Barongcot ES | DANGCAGAN | 3 | 1 | 4 | 2STY4CL W/ TOILET | BATCH 12 | 9825734.81 |  |  | Completed | 1
31023 | NC 2017 | SHS | Region X | Bukidnon | 303953 | Dangcagan NHS | DANGCAGAN | 3 | 1 | 6 | 2STY6CL W/ TOILET | BATCH 12 | 11751135.92 |  |  | Completed | 1
31024 | NC 2017 | SHS | Region X | Bukidnon | 303948 | Bocboc NHS | DON CARLOS | 3 | 1 | 9 | 3STY9CL | BATCH 12 | 24924478.13 |  |  | Completed | 1
31025 | NC 2017 | SHS | Region X | Bukidnon | 303948 | Bocboc NHS | DON CARLOS | 3 |  | 6 | 3STY6CL | BATCH 12 | 14593844.57 |  |  | Completed | 1
31026 | NC 2017 | SHS | Region X | Bukidnon | 314927 | Bocboc NHS (Kiara Annex) | DON CARLOS | 3 | 1 | 6 | 3STY6CL | BATCH 12 | 14746309.51 |  |  | Completed | 1
31027 | NC 2017 | SHS | Region X | Bukidnon | 314927 | Bocboc NHS (Kiara Annex) | DON CARLOS | 3 |  | 4 | 2STY4CL | BATCH 12 | 9291142 |  |  | Completed | 1
31028 | NC 2017 | SHS | Region X | Bukidnon | 303975 | New Nongnongan ES to New Nongnongan NHS | DON CARLOS | 3 | 1 | 6 | 2STY6CL | BATCH 12 | 12324461.81 |  |  | Completed | 1
31029 | NC 2017 | SHS | Region X | Bukidnon | 314922 | New Nongnongan NHS - San Nicolas Annex | DON CARLOS | 3 | 1 | 6 | 3STY6CL | BATCH 12 | 15028213.8 |  |  | Completed | 1
31030 | NC 2017 | SHS | Region X | Bukidnon | 314922 | New Nongnongan NHS - San Nicolas Annex | DON CARLOS | 3 |  | 4 | 2STY4CL | BATCH 12 | 9754169.11 |  |  | Completed | 1
31031 | NC 2017 | SHS | Region X | Bukidnon | 303977 | Old Nongnongan NHS | DON CARLOS | 3 | 1 | 6 | 3STY6CL | BATCH 12 | 15068204.66 |  |  | Completed | 1
31032 | NC 2017 | SHS | Region X | Bukidnon | 303977 | Old Nongnongan NHS | DON CARLOS | 3 |  | 4 | 2STY4CL W/ TOILET | BATCH 12 | 9725157.02 |  |  | Completed | 1
31033 | NC 2017 | SHS | Region X | Cagayan de Oro City | 315411 | Kauswagan National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 12 | 36910737.96 |  |  | Completed | 1 |  |  | P00182208MN-CW1 | 17KH0091 | 2017-11-29 |  |  | 2017-12-20 | 2018-01-16 | L & L CONSTRUCTION
31034 | NC 2017 | K10 | Region X | El Salvador | 127676 | Molugan Central School | CITY OF EL SALVADOR | 2 | 1 | 4 | 2STY4CL | BATCH 12 | 9527701.76 |  |  | Completed | 1 |  |  |  | 17KL0227
31035 | NC 2017 | K10 | Region X | El Salvador | 127676 | Molugan Central School | CITY OF EL SALVADOR | 2 |  | 12 | 2UNITS 2STY6CL | BATCH 12 | 24897736.04 |  |  | Completed | 1 |  |  |  | 17KL0226
31036 | NC 2017 | K10 | Region X | Gingoog City | 128059 | Agay-ayan Elementary School | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | BATCH 12 | 10019925.82 |  |  | Completed | 1
31037 | NC 2017 | K10 | Region X | Gingoog City | 128062 | Bantaawan Elementary School | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | BATCH 12 | 10101823.65 |  |  | Completed | 1
31038 | NC 2017 | K10 | Region X | Gingoog City | 128049 | Civoleg Elementary School | GINGOOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2895794.2102 |  |  | Completed | 1
31039 | NC 2017 | K10 | Region X | Gingoog City | 128025 | Dukdokaan Elementary School | GINGOOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2971655.8282 |  |  | Completed | 1
31040 | NC 2017 | TVL | Region X | Gingoog City | 304130 | Gingoog City CNHS | GINGOOG CITY | 1 | 1 | 3 | Provision of 3 unit Techvoc Workshop Bldgs./Laboratories | BATCH 12 | 11151083.6062 |  |  | Completed | 1
31041 | NC 2017 | TVL | Region X | Gingoog City | 315505 | Gingoog City CNHS - Anakan NHS Annex | GINGOOG CITY | 1 | 1 | 1 | Provision of 1 unit Techvoc Workshop Bldgs./Laboratories | BATCH 12 | 3733383.6044 |  |  | Completed | 1
31042 | NC 2017 | TVL | Region X | Gingoog City | 304131 | Gingoog City CNHS - BACKKISMI NHS Annex | GINGOOG CITY | 1 | 1 | 4 | 2STY 4 LABORATORIES | BATCH 12 | 20122090.49 |  |  | Completed | 1
31043 | NC 2017 | K10 | Region X | Gingoog City | 128011 | Hindangon Elementary School | GINGOOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2968952.2727 |  |  | Completed | 1
31044 | NC 2017 | SHS | Region X | Gingoog City | 304132 | Kalipay National High School | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | BATCH 12 | 10030344.91 |  |  | Completed | 1
31045 | NC 2017 | TVL | Region X | Gingoog City | 304132 | Kalipay National High School | GINGOOG CITY | 1 |  | 1 | Provision of 1 unit Techvoc Workshop Bldgs./Laboratories | BATCH 12 | 3838832.0213 |  |  | Completed | 1
31046 | NC 2017 | K10 | Region X | Gingoog City | 128033 | Kidahon Elementary School | GINGOOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2870795.6536 |  |  | Completed | 1
31047 | NC 2017 | K10 | Region X | Gingoog City | 128014 | Libon Elementary School | GINGOOG CITY | 1 | 1 | 3 | 1STY3CL | BATCH 12 | 4242166.3054 |  |  | Completed | 1
31048 | NC 2017 | K10 | Region X | Gingoog City | 128055 | Manuel Lugod CS | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | BATCH 12 | 9993381.59 |  |  | Completed | 1
31049 | NC 2017 | K10 | Region X | Misamis Occidental | 127244 | Aloran Central School | ALORAN | 1 | 1 | 6 | 2STY6CL | BATCH 12 | 12424536 |  |  | Completed | 1 |  |  | P00182224MN-CW1 | 17KI0141 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | VICTORIANO C. LIM CONSTRUCTION
31050 | NC 2017 | TVL | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1 | 1 | 6 | 3STY12CL SCIENCE LAB, ICT LAB, REGULAR WORKSHOP | BATCH 12 | 29356661 |  |  | Completed | 1 |  |  | P00182226MN-CW1 | 17KI0142 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | GENETIAN BUILDERS
31051 | NC 2017 | SHS | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1 |  | 6 | 2STY6CL | BATCH 12 | 12424536 |  |  | Completed | 1 |  |  | P0018222MN-CW1 | 17KI0143 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | CMA BUILDERS
31052 | NC 2017 | SHS | Region X | Misamis Occidental | 304025 | Baliangao SOF | BALIANGAO | 1 | 1 | 8 | 2STY8CL | BATCH 12 | 17900448 |  |  | Completed | 1 |  |  | P00182228MN-CW1 | 17KI0144 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | GENETIAN BUILDERS
31053 | NC 2017 | SHS | Region X | Misamis Occidental | 315204 | Ignacio Tan MIS | BONIFACIO | 2 | 1 | 4 | 2STY4CL | BATCH 12 | 10626000 |  |  | Completed | 1
31054 | NC 2017 | K10 | Region X | Misamis Occidental | 127296 | Kabulihan ES | BONIFACIO | 2 | 1 | 4 | 2STY4CL | BATCH 12 | 10103000 |  |  | Completed | 1
31055 | NC 2017 | SHS | Region X | Misamis Occidental | 315201 | Upper Usugan National Comprehensive High School | BONIFACIO | 2 | 1 | 6 | 2STY6CL | BATCH 12 | 12981000 |  |  | Completed | 1
31056 | NC 2017 | TVL | Region X | Misamis Occidental | 304043 | Macalibre Alto NHS | LOPEZ JAENA | 1 | 1 | 2 | 2STY4CL SCIENCE LAB, ICT LAB | BATCH 12 | 9529624 |  |  | Completed | 1 |  |  | P00182229MN-CW1 | 17KI0145 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | VICTORIANO C. LIM CONSTRUCTION
31057 | NC 2017 | SHS | Region X | Misamis Occidental | 304058 | Tudela National Comprehensive High School | TUDELA | 2 | 1 | 9 | 3STY9CL | BATCH 12 | 25697000 |  |  | Completed | 1
31058 | NC 2017 | TVL | Region X | Misamis Oriental | 304061 | Baliwagan NHS | BALINGASAG | 1 | 1 | 2 | 2UNITS 1STY UNIQUE WORKSHOP | BATCH 12 | 7290147.18 |  |  | Completed | 1
31059 | NC 2017 | K10 | Region X | Misamis Oriental | 127604 | Binitinan ES | BALINGASAG | 1 | 1 | 4 | 2STY4CL | BATCH 12 | 10340266.21 |  |  | Completed | 1
31060 | NC 2017 | TVL | Region X | Misamis Oriental | 341227 | SHS within Mambayaan ES | BALINGASAG | 1 | 1 | 1 | 1UNIT UNIQUE WORKSHOP (7X22.5) | BATCH 12 | 868801.35 |  |  | Completed | 1
31061 | NC 2017 | TVL | Region X | Misamis Oriental | 341227 | SHS within Mambayaan ES | BALINGASAG | 1 |  | 4 | 2STY 4 LABORATORIES | BATCH 12 | 18630668.08 |  |  | Completed | 1
31062 | NC 2017 | TVL | Region X | Misamis Oriental | 304077 | Kinoguitan Nat'l Agricultural HS | KINOGUITAN | 1 | 1 | 1 | 1UNIT UNIQUE WORKSHOP (7X22.5) | BATCH 12 | 810938.73 |  |  | Completed | 1
31063 | NC 2017 | TVL | Region X | Misamis Oriental | 304066 | Consuelo NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | 1 | 1UNIT UNIQUE WORKSHOP (7X22.5) | BATCH 12 | 730977.4 |  |  | Completed | 1
31064 | NC 2017 | TVL | Region X | Misamis Oriental | 304076 | Kibungsod NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | 1 | 1UNIT UNIQUE WORKSHOP (7X22.5) | BATCH 12 | 534793.05 |  |  | Completed | 1
31065 | NC 2017 | TVL | Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1 | 1 | 1 | 2UNITS UNIQUE WORKSHOP (7X22.5) | BATCH 12 | 1178458.99 |  |  | Completed | 1
31066 | NC 2017 | TVL | Region X | Misamis Oriental | 304095 | Portulin NHS | MEDINA | 1 | 1 | 1 | 1UNIT UNIQUE WORKSHOP (7X22.5) | BATCH 12 | 855500.07 |  |  | Reverted | 0
31067 | NC 2017 | TVL | Region X | Misamis Oriental | 304096 | Salay NHS | SALAY | 1 | 1 | 1 | 1UNIT UNIQUE WORKSHOP (7X22.5) | BATCH 12 | 821874.01 |  |  | Completed | 1
31068 | NC 2017 | TVL | Region X | Misamis Oriental | 304093 | Talisayan NHS | TALISAYAN | 1 | 1 | 1 | 1UNIT UNIQUE WORKSHOP (7X22.5) | BATCH 12 | 795304.59 |  |  | Completed | 1
31069 | NC 2017 | TVL | Region X | Ozamis City | 304161 | Labinay National High School | OZAMIS CITY | 2 | 1 | 4 | FOUR (4) REGULAR WORKSHOP (4STY8CL) | BATCH 12 | 19741684 |  |  | Completed | 1
31070 | NC 2017 | TVL | Region X | Ozamis City | 304161 | Labinay National High School | OZAMIS CITY | 2 |  | 4 | FOUR (4) REGULAR WORKSHOP (4STY8CL) | BATCH 12 | 20161607 |  |  | Completed | 1
31071 | NC 2017 | K10 | Region X | Ozamis City | 128178 | Maximino S. Laurete, Sr. Elementary School | OZAMIS CITY | 2 | 1 | 6 | 2STY6CL | BATCH 12 | 13471000 |  |  | Completed | 1
31072 | NC 2017 | SHS | Region X | Bukidnon | 314913 | Don Carlos NHS | DON CARLOS | 3 | 1 | 4 | 2STY4CL | BATCH 13 | 9321459.42 |  |  | Completed | 1
31073 | NC 2017 | SHS | Region X | Bukidnon | 314913 | Don Carlos NHS | DON CARLOS | 3 |  | 8 | 2STY8CL W/ TOILET | BATCH 13 | 17234837.21 |  |  | Completed | 1
31074 | NC 2017 | K10 | Region X | Bukidnon | 126357 | New Nongnongan ES | DON CARLOS | 3 | 1 | 6 | 3STY6CL | BATCH 13 | 14689194.79 |  |  | Completed | 1
31075 | NC 2017 | SHS | Region X | Bukidnon | 303977 | Old Nongnongan NHS | DON CARLOS | 3 |  | 6 | 3STY6CL | BATCH 13 | 15068204.66 |  |  | Completed | 1
31076 | NC 2017 | SHS | Region X | Bukidnon | 303980 | San Andres National High School | KADINGILAN | 3 | 1 | 8 | 2UNITS 2STY4CL | BATCH 13 | 19485527.29 |  |  | Completed | 1
31077 | NC 2017 | SHS | Region X | Bukidnon | 314926 | San Andres NHS - Cabadiangan Annex | KADINGILAN | 3 | 1 | 6 | 3STY6CL | BATCH 13 | 15102602.62 |  |  | Completed | 1
31078 | NC 2017 | SHS | Region X | Bukidnon | 303960 | KIBAWE NATIONAL HIGH SCHOOL | KIBAWE | 3 | 1 | 4 | 2STY4CL | BATCH 13 | 9681349.28 |  |  | Completed | 1
31079 | NC 2017 | SHS | Region X | Bukidnon | 303960 | KIBAWE NATIONAL HIGH SCHOOL | KIBAWE | 3 |  | 6 | 3STY6CL | BATCH 13 | 14910060.99 |  |  | Completed | 1
31080 | NC 2017 | K10 | Region X | Bukidnon | 126475 | Kitaotao CES | KITAOTAO | 3 | 1 | 8 | 2STY8CL | BATCH 13 | 17364699.09 |  |  | Completed | 1
31081 | NC 2017 | K10 | Region X | Bukidnon | 126475 | Kitaotao CES | KITAOTAO | 3 |  | 4 | 2STY4CL W/ TOILET | BATCH 13 | 9102876.83 |  |  | Completed | 1
31082 | NC 2017 | SHS | Region X | Bukidnon | 303963 | Kitaotao NHS | KITAOTAO | 3 | 1 | 8 | 2STY8CL W/ TOILET | BATCH 13 | 17296806.81 |  |  | Completed | 1
31083 | NC 2017 | SHS | Region X | Bukidnon | 303963 | Kitaotao NHS | KITAOTAO | 3 |  | 4 | 2STY4CL W/ TOILET | BATCH 13 | 9116729.2 |  |  | Completed | 1
31084 | NC 2017 | SHS | Region X | Bukidnon | 303964 | Kitubo National High School | KITAOTAO | 3 | 1 | 6 | 2STY6CL | BATCH 13 | 12589651.72 |  |  | Completed | 1
31085 | NC 2017 | SHS | Region X | Bukidnon | 303964 | Kitubo National High School | KITAOTAO | 3 |  | 6 | 3STY6CL | BATCH 13 | 14821528.63 |  |  | Completed | 1
31086 | NC 2017 | K10 | Region X | Bukidnon | 126490 | Sinuda CES | KITAOTAO | 3 | 1 | 6 | 2STY6CL W/ TOILET | BATCH 13 | 12641729.52 |  |  | Completed | 1
31087 | NC 2017 | SHS | Region X | Bukidnon | 303985 | Sinuda National High School | KITAOTAO | 3 | 1 | 6 | 2STY6CL | BATCH 13 | 12179279.18 |  |  | Completed | 1
31088 | NC 2017 | SHS | Region X | Bukidnon | 303985 | Sinuda National High School | KITAOTAO | 3 |  | 6 | 3STY6CL | BATCH 13 | 14760191.19 |  |  | Completed | 1
31089 | NC 2017 | K10 | Region X | Bukidnon | 126652 | Base Camp Elementary school | MARAMAG | 3 | 1 | 4 | 2STY4CL | BATCH 13 | 9213514.34 |  |  | Completed | 1
31090 | NC 2017 | K10 | Region X | Bukidnon | 126652 | Base Camp Elementary school | MARAMAG | 3 |  | 4 | 2STY4CL | BATCH 13 | 9213514.34 |  |  | Completed | 1
31091 | NC 2017 | SHS | Region X | Bukidnon | 303951 | Bukidnon NSHI | MARAMAG | 3 | 1 | 4 | 2STY4CL | BATCH 13 | 8945901.76 |  |  | Completed | 1
31092 | NC 2017 | SHS | Region X | Bukidnon | 303951 | Bukidnon NSHI | MARAMAG | 3 |  | 6 | 3STY6CL | BATCH 13 | 13799040.04 |  |  | Completed | 1
31093 | NC 2017 | SHS | Region X | Bukidnon | 314911 | Bukidnon NSHI - San Miguel Annex | MARAMAG | 3 | 1 | 4 | 2STY4CL W/ TOILET | BATCH 13 | 9204860.74 |  |  | Completed | 1
31094 | NC 2017 | SHS | Region X | Bukidnon | 303954 | Dologon NHS | MARAMAG | 3 | 1 | 4 | 2STY4CL | BATCH 13 | 9058908.48 |  |  | Completed | 1
31095 | NC 2017 | SHS | Region X | Bukidnon | 303954 | Dologon NHS | MARAMAG | 3 |  | 6 | 2STY6CL | BATCH 13 | 11678174.74 |  |  | Completed | 1
31096 | NC 2017 | SHS | Region X | Bukidnon | 303954 | Dologon NHS | MARAMAG | 3 |  | 8 | 2UNITS 2STY4CL | BATCH 13 | 18004810.24 |  |  | Completed | 1
31097 | NC 2017 | SHS | Region X | Bukidnon | 314921 | Dologon NHS - Kiharong Annex | MARAMAG | 3 | 1 | 4 | 2STY4CL | BATCH 13 | 9176061.92 |  |  | Completed | 1
31098 | NC 2017 | SHS | Region X | Bukidnon | 314921 | Dologon NHS - Kiharong Annex | MARAMAG | 3 |  | 6 | 3STY6CL | BATCH 13 | 14091246.69 |  |  | Completed | 1
31099 | NC 2017 | SHS | Region X | Bukidnon | 314928 | Dologon NHS (San Roque Annex) | MARAMAG | 3 | 1 | 4 | 2STY4CL | BATCH 13 | 9295211.62 |  |  | Completed | 1
31100 | NC 2017 | SHS | Region X | Bukidnon | 303965 | KUYA NATIONAL HIGH SCHOOL | MARAMAG | 3 | 1 | 4 | 2STY4CL | BATCH 13 | 9613703.8 |  |  | Completed | 1
31101 | NC 2017 | SHS | Region X | Bukidnon | 303965 | KUYA NATIONAL HIGH SCHOOL | MARAMAG | 3 |  | 6 | 3STY6CL | BATCH 13 | 14275861.23 |  |  | Completed | 1
31102 | NC 2017 | SHS | Region X | Bukidnon | 314918 | KUYA NHS ANNEX- LA ROXAS | MARAMAG | 3 | 1 | 6 | 3STY6CL | BATCH 13 | 14654447.79 |  |  | Completed | 1
31103 | NC 2017 | SHS | Region X | Bukidnon | 314918 | KUYA NHS ANNEX- LA ROXAS | MARAMAG | 3 |  | 4 | 2STY4CL | BATCH 13 | 9553964.94 |  |  | Completed | 1
31104 | NC 2017 | K10 | Region X | Bukidnon | 126727 | Dilapa Elem School | QUEZON | 3 | 1 | 4 | 2STY4CL | BATCH 13 | 9095791.73 |  |  | Completed | 1
31105 | NC 2017 | SHS | Region X | Bukidnon | 303961 | Kiburiao National High School | QUEZON | 3 | 1 | 8 | 2UNITS 2STY4CL | BATCH 13 | 19395047.15 |  |  | Completed | 1
31106 | NC 2017 | SHS | Region X | Bukidnon | 303961 | Kiburiao National High School | QUEZON | 3 |  | 6 | 2STY6CL | BATCH 13 | 12038563.02 |  |  | Completed | 1
31107 | NC 2017 | SHS | Region X | Bukidnon | 303961 | Kiburiao National High School | QUEZON | 3 |  | 10 | 2STY10CL | BATCH 13 | 20498298.81 |  |  | Completed | 1
31108 | NC 2017 | SHS | Region X | Bukidnon | 314912 | Quezon National High School | QUEZON | 3 | 1 | 8 | 2UNITS 2STY4CL | BATCH 13 | 18031481.48 |  |  | Completed | 1
31109 | NC 2017 | SHS | Region X | Bukidnon | 314912 | Quezon National High School | QUEZON | 3 |  | 12 | 3STY12CL | BATCH 13 | 29359267.25 |  |  | Completed | 1
31110 | NC 2017 | SHS | Region X | Bukidnon | 303979 | Salawagan NHS | QUEZON | 3 | 1 | 4 | 2UNITS 2STY4CL | BATCH 13 | 18900052.4 |  |  | Completed | 1
31111 | NC 2017 | K10 | Region X | Cagayan de Oro City |  | Pagalungan NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 11728578.02 |  |  | Completed | 1 |  |  | P00183142MN-CW1 | 17KH0095 | 2017-11-29 |  |  | 2017-12-20 | 2018-01-16 | JTA BUILDERS
31112 | NC 2017 | K10 | Region X | Cagayan de Oro City |  | Pagalungan NHS | CAGAYAN DE ORO CITY (Capital) | 1 |  | 6 | 2STY6CL | BATCH 13 | 11728578.02 |  |  | Completed | 1 |  |  | P00183143MN-CW1 | 17KH0096 | 2017-11-29 |  |  | 2017-12-20 | 2018-01-16 | JTA BUILDERS
31113 | NC 2017 | K10 | Region X | Cagayan de Oro City |  | Patag NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 13 | 29482156.79 |  |  | Reverted | 0 |  |  | P00183141MN-CW1 | 17KH0088 | 2017-11-29 |  |  | 2017-12-20 | 2018-01-16 | JDE CONSTRUCTION
31114 | NC 2017 | SHS | Region X | Camiguin | 303989 | Bonbon NHS | CATARMAN | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 9223459.5 |  |  | Completed | 1
31115 | NC 2017 | SHS | Region X | Camiguin | 303989 | Bonbon NHS | CATARMAN | 0 |  | 4 | 2STY4CL | BATCH 13 | 9161839.88 |  |  | Completed | 1 | [9 empty] | JUNJING CONST. & GEN. MERCHANDISE
31116 | NC 2017 | SHS | Region X | Camiguin | 303990 | Camiguin NHS | CATARMAN | 0 | 1 | 8 | 2STY8CL | BATCH 13 | 17359820 |  |  | Completed | 1 | [9 empty] | JAPUZ-JANSOL ENTERPRISES
31117 | NC 2017 | SHS | Region X | Camiguin | 303990 | Camiguin NHS | CATARMAN | 0 |  | 16 | 2STY16CL | BATCH 13 | 30982127.37 |  |  | Completed | 1 |  |  | P00183154MN-CW1 | 17KE0093 | [5 empty] | JAPUZ-JANSOL ENTERPRISES
31118 | NC 2017 | K10 | Region X | Camiguin | 126885 | Catarman CS | CATARMAN | 0 | 1 | 6 | 2STY6CL | BATCH 13 | 12362239.16 |  |  | Completed | 1 | [9 empty] | ARN BUILDERS INC.
31119 | NC 2017 | SHS | Region X | Camiguin | 303992 | Lawigan-Bura National High School | CATARMAN | 0 | 1 | 10 | 2STY10CL | BATCH 13 | 20850479.31 |  |  | Completed | 1 | [9 empty] | ARN BUILDERS INC.
31120 | NC 2017 | K10 | Region X | Camiguin | 315006 | Sto. Niño Integrated School | CATARMAN | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 9181584.2 |  |  | Completed | 1 | [9 empty] | ARN BUILDERS INC.
31121 | NC 2017 | K10 | Region X | Camiguin | 126931 | Guinsiliban CS | GUINSILIBAN | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 9300840.41 |  |  | Completed | 1 | [9 empty] | FOUR L BUILDERS & CONST. SUPPLY
31122 | NC 2017 | SHS | Region X | Camiguin | 303991 | Guinsiliban National High School | GUINSILIBAN | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 9276875.62 |  |  | Completed | 1 | [9 empty] | FOUR L BUILDERS & CONST. SUPPLY
31123 | NC 2017 | SHS | Region X | Camiguin | 315003 | Mahinog National High School II | MAHINOG | 0 | 1 | 6 | 2STY6CL | BATCH 13 | 12342823.95 |  |  | Completed | 1 | [9 empty] | AHM BUILDERS
31124 | NC 2017 | K10 | Region X | Camiguin | 126909 | Benhaan ES | MAMBAJAO (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 9181584.2 |  |  | Completed | 1 | [9 empty] | JUNJING CONST. & GEN. MERCHANDISE
31125 | NC 2017 | K10 | Region X | Camiguin | 126911 | Bug-ong ES | MAMBAJAO (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 13 | 12165274.91 |  |  | Completed | 1 | [9 empty] | JUNJING CONST. & GEN. MERCHANDISE
31126 | NC 2017 | SHS | Region X | Camiguin | 303994 | Mambajao NHS | MAMBAJAO (Capital) | 0 |  | 16 | 2STY16CL | BATCH 13 | 30902244.68 |  |  | Completed | 1 |  |  | P00181357MN-CW1` | 17KE0087 | [5 empty] | JAPUZ-JANSOL ENTERPRISES
31127 | NC 2017 | SHS | Region X | Camiguin | 303996 | Tupsan NHS | MAMBAJAO (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 13 | 17466411.7 |  |  | Completed | 1 | [9 empty] | JUNJING CONST. & GEN. MERCHANDISE
31128 | NC 2017 | SHS | Region X | Camiguin | 303996 | Tupsan NHS | MAMBAJAO (Capital) | 0 |  | 4 | 2STY4CL | BATCH 13 | 9181584.2 |  |  | Completed | 1 | [9 empty] | CALAWAGAN ENTERPRISES
31129 | NC 2017 | K10 | Region X | Camiguin | 126923 | Yumbing ES | MAMBAJAO (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 9211764.78 |  |  | Completed | 1 | [9 empty] | ARN BUILDERS INC.
31130 | NC 2017 | SHS | Region X | Camiguin | 303997 | Yumbing National High School | MAMBAJAO (Capital) | 0 | 1 | 10 | 2STY10CL | BATCH 13 | 20850479.11 |  |  | Completed | 1 | [9 empty] | ARN BUILDERS INC.
31131 | NC 2017 | SHS | Region X | Camiguin | 303997 | Yumbing National High School | MAMBAJAO (Capital) | 0 |  | 8 | 2STY8CL | BATCH 13 | 17374144 |  |  | Completed | 1 | [9 empty] | JAPUZ-JANSOL ENTERPRISES
31132 | NC 2017 | K10 | Region X | Camiguin | 315002 | Alangilan Integrated School | SAGAY | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 9267377.81 |  |  | Completed | 1 | [9 empty] | ARN BUILDERS INC.
31133 | NC 2017 | K10 | Region X | Camiguin | 126927 | Bugang IS | SAGAY | 0 | 1 | 6 | 2STY6CL | BATCH 13 | 12347138.7 |  |  | Completed | 1 | [9 empty] | ANGEL & SAM CONST. & GEN. MERCHANDISE
31134 | NC 2017 | K10 | Region X | Camiguin | 126934 | Manuyog ES | SAGAY | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 9722073.6 |  |  | Completed | 1 | [9 empty] | ARN BUILDERS INC.
31135 | NC 2017 | TVL | Region X | El Salvador | 304065 | Cogon NHS | CITY OF EL SALVADOR | 2 | 1 | 16 | 4STY16CL (4 REGULAR WORKSHOP, 2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 42356837.96 |  |  | Completed | 1 |  |  |  | 17KL0235
31136 | NC 2017 | K10 | Region X | El Salvador | 127671 | El Salvador City CS | CITY OF EL SALVADOR | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9527701.76 |  |  | Completed | 1 |  |  |  | 17KL0229
31137 | NC 2017 | K10 | Region X | El Salvador | 127671 | El Salvador City CS | CITY OF EL SALVADOR | 2 |  | 4 | 2STY4CL | BATCH 13 | 9390901.76 |  |  | Completed | 1 |  |  |  | 17KL0230
31138 | NC 2017 | K10 | Region X | El Salvador | 127673 | Hinigdaan ES | CITY OF EL SALVADOR | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9527701.76 |  |  | Completed | 1 |  |  |  | 17KL0234
31139 | NC 2017 | TVL | Region X | El Salvador | 315318 | Hinigdaan NHS | CITY OF EL SALVADOR | 2 | 1 | 6 | 3STY6CL (3 REGULAR WORKSHOP) | BATCH 13 | 15189515.1 |  |  | Completed | 1 |  |  |  | 17KL0225
31140 | NC 2017 | TVL | Region X | El Salvador | 315318 | Hinigdaan NHS | CITY OF EL SALVADOR | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19199120.67 |  |  | Completed | 1 |  |  |  | 17KL0224
31141 | NC 2017 | TVL | Region X | El Salvador | 315305 | MOLUGAN NATIONAL HIGH SCHOOL | CITY OF EL SALVADOR | 2 | 1 | 4 | 2STY4CL (2 REGULAR WORKSHOP) | BATCH 13 | 9390901.76 |  |  | Completed | 1 |  |  |  | 17KL0232
31142 | NC 2017 | TVL | Region X | El Salvador | 315305 | MOLUGAN NATIONAL HIGH SCHOOL | CITY OF EL SALVADOR | 2 |  | 4 | 2STY4CL (1 SCIENCE LAB, 1 ICT LAB) | BATCH 13 | 9390901.76 |  |  | Completed | 1 |  |  |  | 17KL0233
31143 | NC 2017 | K10 | Region X | El Salvador | 127669 | San Francisco de Asis ES (Calongonan ES) | CITY OF EL SALVADOR | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9527701.76 |  |  | Completed | 1 |  |  |  | 17KL0228
31144 | NC 2017 | K10 | Region X | El Salvador | 127680 | Taytay ES | CITY OF EL SALVADOR | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9390901.76 |  |  | Completed | 1 |  |  |  | 17KL0231
31145 | NC 2017 | TVL | Region X | Gingoog City | 304129 | Bal-ason NHS | GINGOOG CITY | 1 | 1 | 6 | 2STY 6 LABORATORIES | BATCH 13 | 24383209.55 |  |  | Completed | 1
31146 | NC 2017 | K10 | Region X | Gingoog City | 128063 | Baybay ES | GINGOOG CITY | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 18781474.14 |  |  | Completed | 1
31147 | NC 2017 | K10 | Region X | Gingoog City | 128010 | Daan Lungsod ES | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10056778.87 |  |  | Completed | 1
31148 | NC 2017 | TVL | Region X | Gingoog City | 304130 | Gingoog City CNHS | GINGOOG CITY | 1 | 1 | 8 | 4STY 8 LABORATORIES | BATCH 13 | 38508135.08 |  |  | Completed | 1
31149 | NC 2017 | TVL | Region X | Gingoog City | 304130 | Gingoog City CNHS | GINGOOG CITY | 1 |  | 8 | 4STY 8 LABORATORIES | BATCH 13 | 38766239.78 |  |  | Completed | 1
31150 | NC 2017 | TVL | Region X | Gingoog City | 315505 | Gingoog City CNHS - Anakan NHS Annex | GINGOOG CITY | 1 |  | 8 | 4STY 8 LABORATORIES | BATCH 13 | 38538265.85 |  |  | Completed | 1
31151 | NC 2017 | TVL | Region X | Gingoog City | 315503 | Gingoog City CNHS - LURISA NHS Annex | GINGOOG CITY | 1 | 1 | 4 | 2STY 4 LABORATORIES | BATCH 13 | 21530100.81 |  |  | Completed | 1
31152 | NC 2017 | TVL | Region X | Gingoog City | 315503 | Gingoog City CNHS - LURISA NHS Annex | GINGOOG CITY | 1 |  | 4 | 2STY 4 LABORATORIES | BATCH 13 | 21530100.81 |  |  | Completed | 1
31153 | NC 2017 | K10 | Region X | Gingoog City | 128013 | Lawit Elementary school | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10021028.42 |  |  | Completed | 1
31154 | NC 2017 | K10 | Region X | Gingoog City | 128054 | Magallanes PS | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10013220.8 |  |  | Completed | 1
31155 | NC 2017 | K10 | Region X | Gingoog City | 128035 | Malinao ES | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10279774.38 |  |  | Completed | 1
31156 | NC 2017 | K10 | Region X | Gingoog City | 128020 | Punong Elementary School | GINGOOG CITY | 1 | 1 | 3 | 1STY3CL | BATCH 13 | 4104165.6815 |  |  | Completed | 1
31157 | NC 2017 | K10 | Region X | Gingoog City | 128041 | San Jose ES | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10116032.65 |  |  | Completed | 1
31158 | NC 2017 | TVL | Region X | Gingoog City | 304137 | San Luis NHS | GINGOOG CITY | 1 | 1 | 4 | 2STY 4 LABORATORIES | BATCH 13 | 18180661.54 |  |  | Completed | 1
31159 | NC 2017 | K10 | Region X | Gingoog City | 128047 | Topside ES | GINGOOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 2866398.3413 |  |  | Completed | 1
31160 | NC 2017 | K10 | Region X | Misamis Occidental | 127273 | Baliangao CS | BALIANGAO | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9551240 |  |  | Completed | 1 |  |  | P00183190MN-CW1 | 17KIO129 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | RRJ BUILDERS & GEN. MDSE. | for Punchlist, without Occupancy Permit
31161 | NC 2017 | TVL | Region X | Misamis Occidental | 304030 | Calamba CNHS | CALAMBA | 1 | 1 | 6 | 3STY12CL SCIENCE LAB, ICT LAB, REGULAR WORKSHOP | BATCH 13 | 28356581 |  |  | Completed | 1 |  |  | P00183192MN-CW1 | 17KI0131 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | RUDHIL CONSTRUCTION | for Punchlist, without Occupancy Permit
31162 | NC 2017 | TVL | Region X | Misamis Occidental | 304031 | Clarin NHS | CLARIN | 2 | 1 | 12 | TWELVE (12) REGULAR WORKSHOP (4STY24CL) | BATCH 13 | 47564386 |  |  | Completed | 1
31163 | NC 2017 | K10 | Region X | Misamis Occidental | 127353 | Lapasan ES | CLARIN | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 13782000 |  |  | Completed | 1
31164 | NC 2017 | K10 | Region X | Misamis Occidental | 127343 | Mialen Central School | CLARIN | 2 | 1 | 8 | 2STY8CL | BATCH 13 | 18605000 |  |  | Completed | 1
31165 | NC 2017 | SHS | Region X | Misamis Occidental | 304033 | Concepcion NHS | CONCEPCION | 1 | 1 | 4 | 2STY6CL SCIENCE LAB, ICT LAB, REGULAR CLASSROOMS | BATCH 13 | 12514200 |  |  | Completed | 1 |  |  |  | 17KI0132 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | VICTORIANO C. LIM CONSTRUCTION | for Punchlist, without Occupancy Permit
31166 | NC 2017 | SHS | Region X | Misamis Occidental | 315203 | Carmen IS | JIMENEZ | 1 | 1 | 4 | 2STY6CL SCIENCE LAB, ICT LAB, REGULAR CLASSROOMS | BATCH 13 | 12424536 |  |  | Completed | 1 |  |  | P00183197MN-CW1 | 17KI0136 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | CMA CONSTRUCTION
31167 | NC 2017 | TVL | Region X | Misamis Occidental | 304037 | Jimenez NCHS | JIMENEZ | 1 | 1 | 4 | 4STY8CL SCIENCE LAB, ICT LAB, REGULAR WORKSHOP | BATCH 13 | 18355790 |  |  | Completed | 1 |  |  | P00183194MN-CW1 | 17KI0133 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | VICTORIANO C. LIM CONSTRUCTION
31168 | NC 2017 | K10 | Region X | Misamis Occidental | 127399 | Palilan ES | JIMENEZ | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9551240 |  |  | Completed | 1 |  |  |  | 17KI0130 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | RUDHIL CONSTRUCTION
31169 | NC 2017 | SHS | Region X | Misamis Occidental | 315210 | Tabo-o Integrated School | JIMENEZ | 1 | 1 | 4 | 2STY6CL SCIENCE LAB, ICT LAB, REGULAR CLASSROOMS | BATCH 13 | 12523315 |  |  | Completed | 1 |  |  | P183201MN-CW1 | 17KI1040 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | VICTORIANO C. LIM CONSTRUCTION
31170 | NC 2017 | SHS | Region X | Misamis Occidental | 315207 | Sibugon IS | LOPEZ JAENA | 1 | 1 | 6 | 3STY9CL SCIENCE LAB, ICT LAB, REGULAR CLASSROOMS | BATCH 13 | 23630396 |  |  | Completed | 1 |  |  | p00183198mn-cw1 | 17KI0137 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | AFG ZILLION CONST. CORP.
31171 | NC 2017 | SHS | Region X | Misamis Occidental | 315207 | Sibugon IS | LOPEZ JAENA | 1 |  | 6 | 2STY6CL | BATCH 13 | 12424536 |  |  | Completed | 1 |  |  | P00183199MN-CW1 | 17KI0138 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | AFG ZILLION CONST. CORP. | for Punchlist, without Occupancy Permit
31172 | NC 2017 | SHS | Region X | Misamis Occidental | 304048 | Panaon NHS | PANAON | 1 | 1 | 4 | 2STY6CL SCIENCE LAB, ICT LAB, REGULAR CLASSROOMS | BATCH 13 | 12434300 |  |  | Completed | 1 |  |  | P00183195MN-CW1 | 17KI0134 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | VICTORIANO C. LIM CONSTRUCTION
31173 | NC 2017 | SHS | Region X | Misamis Occidental | 315208 | Aquino IS | PLARIDEL | 1 | 1 | 6 | 2STY8CL SCIENCE LAB, ICT LAB, REGULAR CLASSROOMS | BATCH 13 | 17872327 |  |  | Completed | 1 |  |  | P00183200MN-CW1 | 17KI0139 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | VICTORIANO C. LIM CONSTRUCTION | for Punchlist, without Occupancy Permit
31174 | NC 2017 | SHS | Region X | Misamis Occidental | 304051 | Sapang Dalaga National High School | SAPANG DALAGA | 1 | 1 | 4 | 3STY6CL SCIENCE LAB, ICT LAB, REGULAR CLASSROOMS | BATCH 13 | 14790188 |  |  | Completed | 1 |  |  | P00183196MN-CW1 | 17KI0135 | 2017-12-06 | 2017-12-14 | 2017-12-27 | 2017-12-29 | 2018-01-15 | VICTORIANO C. LIM CONSTRUCTION
31175 | NC 2017 | TVL | Region X | Misamis Occidental | 304038 | Katipunan NHS | SINACABAN | 2 | 1 | 4 | FOUR (4) REGULAR WORKSHOP (2STY8CL) | BATCH 13 | 18854015 |  |  | Completed | 1
31176 | NC 2017 | TVL | Region X | Misamis Occidental | 304055 | Sinonoc NHS | SINACABAN | 2 | 1 | 6 | SIX (6) REGULAR WORKSHOP (3STY12CL) | BATCH 13 | 30610380 |  |  | Completed | 1
31177 | NC 2017 | K10 | Region X | Misamis Occidental | 127582 | Tudela Central School | TUDELA | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 10589000 |  |  | Completed | 1
31178 | NC 2017 | TVL | Region X | Misamis Occidental | 304058 | Tudela National Comprehensive High School | TUDELA | 2 | 1 | 6 | SIX (6) REGULAR WORKSHOP (3STY12CL) | BATCH 13 | 31442785 |  |  | Completed | 1
31179 | NC 2017 | TVL | Region X | Misamis Oriental | 304059 | Alubijid NCHS | ALUBIJID | 2 | 1 | 16 | 4STY16CL (8 REGULAR WORKSHOP) | BATCH 13 | 42356837.96 |  |  | Completed | 1 |  |  |  | 17KL0176
31180 | NC 2017 | TVL | Region X | Misamis Oriental | 304059 | Alubijid NCHS | ALUBIJID | 2 |  | 8 | 2STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 17770890.26 |  |  | Completed | 1 |  |  |  | 17KL0194
31181 | NC 2017 | SHS | Region X | Misamis Oriental | 304059 | Alubijid NCHS | ALUBIJID | 2 |  | 8 | 2STY8CL | BATCH 13 | 17805090.26 |  |  | Completed | 1 |  |  |  | 17KL0195
31182 | NC 2017 | TVL | Region X | Misamis Oriental | 304081 | Lourdes Alubijid NHS | ALUBIJID | 2 | 1 | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0196
31183 | NC 2017 | K10 | Region X | Misamis Oriental | 127596 | Talaba ES | ALUBIJID | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9390901.76 |  |  | Completed | 1 |  |  |  | 17KL0152
31184 | NC 2017 | K10 | Region X | Misamis Oriental | 304092 | Misamis Oriental NHS | BALINGASAG | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10315856.91 |  |  | Completed | 1
31185 | NC 2017 | SHS | Region X | Misamis Oriental | 341228 | SHS within Mantangale ES | BALINGOAN | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 15101038.71 |  |  | Completed | 1
31186 | NC 2017 | K10 | Region X | Misamis Oriental | 304067 | Dampias NHS | BINUANGAN | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10480422.59 |  |  | Completed | 1
31187 | NC 2017 | SHS | Region X | Misamis Oriental | 304091 | Mis. Or. Gen. CHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 13 | 47182909.74 |  |  | Completed | 1 |  |  |  | 17KL0167
31188 | NC 2017 | TVL | Region X | Misamis Oriental | 315309 | Aposkahoy NHS | CLAVERIA | 2 | 1 | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0170
31189 | NC 2017 | K10 | Region X | Misamis Oriental | 127639 | Claveria CS | CLAVERIA | 2 | 1 | 16 | 4STY16CL | BATCH 13 | 42288437.96 |  |  | Completed | 1 |  |  |  | 17KL0174
31190 | NC 2017 | K10 | Region X | Misamis Oriental | 127639 | Claveria CS | CLAVERIA | 2 |  | 16 | 4STY16CL | BATCH 13 | 42356837.96 |  |  | Completed | 1 |  |  |  | 17KL0175
31191 | NC 2017 | TVL | Region X | Misamis Oriental | 304069 | Dr. Gerardo Sabal MNHS | CLAVERIA | 2 | 1 | 8 | 4STY8CL (4 REGULAR WORKSHOP) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0173
31192 | NC 2017 | TVL | Region X | Misamis Oriental | 304069 | Dr. Gerardo Sabal MNHS | CLAVERIA | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0178
31193 | NC 2017 | TVL | Region X | Misamis Oriental | 304071 | Hinaplanan NHS | CLAVERIA | 2 | 1 | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0171
31194 | NC 2017 | TVL | Region X | Misamis Oriental | 304083 | Malagana NHS | CLAVERIA | 2 | 1 | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0192
31195 | NC 2017 | SHS | Region X | Misamis Oriental | 304087 | Mat-i (Claveria) NHS | CLAVERIA | 2 | 1 | 8 | 2UNITS 2STY4CL | BATCH 13 | 18781803.52 |  |  | Completed | 1 |  |  |  | 17KL0193
31196 | NC 2017 | K10 | Region X | Misamis Oriental | 315314 | Patrocinio NHS | CLAVERIA | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 12315443.02 |  |  | Completed | 1 |  |  |  | 17KL0165
31197 | NC 2017 | TVL | Region X | Misamis Oriental | 304086 | Matangad NHS | GITAGUM | 2 | 1 | 4 | 2STY 4CL (2 REGULAR WORKSHOP) | BATCH 13 | 9390901.76 |  |  | Completed | 1 |  |  |  | 17KL0154
31198 | NC 2017 | TVL | Region X | Misamis Oriental | 304086 | Matangad NHS | GITAGUM | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0197
31199 | NC 2017 | K10 | Region X | Misamis Oriental | 127686 | Initao CS | INITAO | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 12381368.02 |  |  | Completed | 1 |  |  |  | 17KL0155
31200 | NC 2017 | TVL | Region X | Misamis Oriental | 315317 | Kalacapan NHS | INITAO | 2 | 1 | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0205
31201 | NC 2017 | TVL | Region X | Misamis Oriental | 315302 | Danao NHS | JASAAN | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0172
31202 | NC 2017 | SHS | Region X | Misamis Oriental | 304073 | Jasaan NHS | JASAAN | 2 | 1 | 8 | 4STY8CL | BATCH 13 | 19216220.67 |  |  | Completed | 1 |  |  |  | 17KL0190
31203 | NC 2017 | SHS | Region X | Misamis Oriental | 304073 | Jasaan NHS | JASAAN | 2 |  | 4 | 2STY4CL | BATCH 13 | 9527701.76 |  |  | Completed | 1 |  |  |  | 17KL0161
31204 | NC 2017 | TVL | Region X | Misamis Oriental | 304073 | Jasaan NHS | JASAAN | 2 |  | 8 | 2UNITS 4STY8CL (8 REGULAR WORKSHOP) | BATCH 13 | 38312741.34 |  |  | Completed | 1 |  |  |  | 17KL0191
31205 | NC 2017 | TVL | Region X | Misamis Oriental | 304073 | Jasaan NHS | JASAAN | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19216220.67 |  |  | Completed | 1 |  |  |  | 17KL0189
31206 | NC 2017 | SHS | Region X | Misamis Oriental | 360848 | SHS within Esperanza ES | KINOGUITAN | 1 | 1 | 6 | 3STY6CL | BATCH 13 | 18519214.54 |  |  | Completed | 1
31207 | NC 2017 | K10 | Region X | Misamis Oriental | 127751 | Umagos ES | LAGONGLONG | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 18630668.08 |  |  | Completed | 1
31208 | NC 2017 | K10 | Region X | Misamis Oriental | 127918 | Sambulawan ES | LAGUINDINGAN | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9390901.76 |  |  | Completed | 1 |  |  |  | 17KL0153
31209 | NC 2017 | TVL | Region X | Misamis Oriental | 304079 | Libertad NHS | LIBERTAD | 2 | 1 | 8 | 4STY8CL (4 REGULAR WORKSHOP) | BATCH 13 | 19156370.67 |  |  | Completed | 1 |  |  |  | 17KL0199
31210 | NC 2017 | TVL | Region X | Misamis Oriental | 304079 | Libertad NHS | LIBERTAD | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19156370.67 |  |  | Completed | 1 |  |  |  | 17KL0198
31211 | NC 2017 | SHS | Region X | Misamis Oriental | 360847 | Lugait SHS (within TESDA site) | LUGAIT | 2 | 1 | 12 | 4STY12CL | BATCH 13 | 36424289.72 |  |  | Completed | 1 |  |  |  | 17KL0179
31212 | NC 2017 | TVL | Region X | Misamis Oriental | 360847 | Lugait SHS (within TESDA site) | LUGAIT | 2 |  | 8 | 4STY8CL (2 REGULAR WORKSHOP, 1 SCIENCE LAB, 1 ICT LAB) | BATCH 13 | 19307570.67 |  |  | Completed | 1 |  |  |  | 17KL0206
31213 | NC 2017 | K10 | Region X | Misamis Oriental | 127777 | Consuelo ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10028288.76 |  |  | Completed | 1
31214 | NC 2017 | K10 | Region X | Misamis Oriental | 127790 | San Vicente ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10152731.74 |  |  | Completed | 1
31215 | NC 2017 | K10 | Region X | Misamis Oriental | 127793 | Tibon-Tibon ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10238423.05 |  |  | Completed | 1
31216 | NC 2017 | K10 | Region X | Misamis Oriental | 127795 | Villa Felipa ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10176502.37 |  |  | Completed | 1
31217 | NC 2017 | TVL | Region X | Misamis Oriental | 304064 | Cabalantian NHS | MANTICAO | 2 | 1 | 4 | 2STY4CL (2 REGULAR WORKSHOP) | BATCH 13 | 9390901.76 |  |  | Completed | 1 |  |  |  | 17KL0156
31218 | NC 2017 | TVL | Region X | Misamis Oriental | 304064 | Cabalantian NHS | MANTICAO | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0177
31219 | NC 2017 | TVL | Region X | Misamis Oriental | 315307 | Manticao NHS | MANTICAO | 2 | 1 | 4 | 2STY4CL (2 REGULAR WORKSHOP) | BATCH 13 | 9390901.76 |  |  | Completed | 1 |  |  |  | 17KL0157
31220 | NC 2017 | TVL | Region X | Misamis Oriental | 315307 | Manticao NHS | MANTICAO | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0201
31221 | NC 2017 | K10 | Region X | Misamis Oriental | 127817 | Gov. Pelaez ES | MEDINA | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10220100.77 |  |  | Completed | 1
31222 | NC 2017 | K10 | Region X | Misamis Oriental | 127831 | Tambagan ES (Tambagan Mananum Daan ES) | MEDINA | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10206901.69 |  |  | Completed | 1
31223 | NC 2017 | TVL | Region X | Misamis Oriental | 304088 | Mat-i (Naawan) NHS | NAAWAN | 2 | 1 | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0202
31224 | NC 2017 | K10 | Region X | Misamis Oriental | 127935 | Naawan CS | NAAWAN | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9527701.76 |  |  | Completed | 1 |  |  |  | 17KL0158
31225 | NC 2017 | SHS | Region X | Misamis Oriental | 341230 | SHS within Maputi ES | NAAWAN | 2 | 1 | 9 | 3STY9CL | BATCH 13 | 29958047.73 |  |  | Completed | 1 |  |  |  | 17KL0205
31226 | NC 2017 | TVL | Region X | Misamis Oriental | 341230 | SHS within Maputi ES | NAAWAN | 2 |  | 8 | 4STY8CL (4 REGULAR WORKSHOP) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0204
31227 | NC 2017 | TVL | Region X | Misamis Oriental | 341230 | SHS within Maputi ES | NAAWAN | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0203
31228 | NC 2017 | TVL | Region X | Misamis Oriental | 304094 | Opol NSTS | OPOL | 2 | 1 | 16 | 4STY16CL (8 REGULAR WORKSHOP) | BATCH 13 | 42232862.96 |  |  | Completed | 1 |  |  |  | 17KL0208
31229 | NC 2017 | TVL | Region X | Misamis Oriental | 304094 | Opol NSTS | OPOL | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19464170.67 |  |  | Completed | 1 |  |  | P00183262MN-CW1 | 17KL0222 | [5 empty] | L&L CONSTRUCTION
31230 | NC 2017 | K10 | Region X | Misamis Oriental | 315311 | Alipuaton IS | SALAY | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 18630668.08 |  |  | reverted | 0
31231 | NC 2017 | K10 | Region X | Misamis Oriental | 127860 | Salay CS | SALAY | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10155862.88 |  |  | Completed | 1
31232 | NC 2017 | SHS | Region X | Misamis Oriental | 304096 | Salay NHS | SALAY | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10255804.96 |  |  | Completed | 1
31233 | NC 2017 | TVL | Region X | Misamis Oriental | 341231 | SHS within Tagoloan CS | TAGOLOAN | 2 | 1 | 12 | 3STY12CL (6 REGULAR WORKSHOP) | BATCH 13 | 34880367.25 |  |  | Completed | 1 |  |  |  | 17KL0207
31234 | NC 2017 | TVL | Region X | Misamis Oriental | 341231 | SHS within Tagoloan CS | TAGOLOAN | 2 |  | 4 | 2STY4CL (2 SCIENCE LAB) | BATCH 13 | 9527701.76 |  |  | Completed | 1 |  |  |  | 17KL0159
31235 | NC 2017 | TVL | Region X | Misamis Oriental | 341231 | SHS within Tagoloan CS | TAGOLOAN | 2 |  | 4 | 2STY4CL (2 ICT LAB) | BATCH 13 | 9527701.76 |  |  | Completed | 1 |  |  |  | 17KL0160
31236 | NC 2017 | TVL | Region X | Misamis Oriental | 304099 | Sta. Ana NHS | TAGOLOAN | 2 | 1 | 6 | 3STY6CL (3 REGULAR WORKSHOP) | BATCH 13 | 15189515.1 |  |  | Completed | 1 |  |  |  | 17KL0180
31237 | NC 2017 | TVL | Region X | Misamis Oriental | 304099 | Sta. Ana NHS | TAGOLOAN | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0182
31238 | NC 2017 | K10 | Region X | Misamis Oriental | 127873 | Tagoloan CS | TAGOLOAN | 2 | 1 | 8 | 2STY8CL | BATCH 13 | 17805090.26 |  |  | Completed | 1 |  |  |  | 17KL0183
31239 | NC 2017 | K10 | Region X | Misamis Oriental | 304102 | Tagoloan NHS | TAGOLOAN | 2 | 1 | 12 | 4STY12CL | BATCH 13 | 36287489.72 |  |  | Completed | 1 |  |  |  | 17KL0168
31240 | NC 2017 | K10 | Region X | Misamis Oriental | 304102 | Tagoloan NHS | TAGOLOAN | 2 |  | 16 | 2UNITS 4STY8CL | BATCH 13 | 38312741.34 |  |  | Completed | 1 |  |  |  | 17KL0181
31241 | NC 2017 | K10 | Region X | Misamis Oriental | 127888 | Mintabon ES | TALISAYAN | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10078021.27 |  |  | Completed | 1
31242 | NC 2017 | SHS | Region X | Misamis Oriental | 341235 | SHS within Sta. Ines ES | TALISAYAN | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10006208.66 |  |  | Completed | 1
31243 | NC 2017 | K10 | Region X | Misamis Oriental | 127900 | Dayawan ES | VILLANUEVA | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 12381368.02 |  |  | Completed | 1 |  |  |  | 17KL0162
31244 | NC 2017 | TVL | Region X | Misamis Oriental | 304074 | Kalingagan NHS | VILLANUEVA | 2 | 1 | 6 | 3STY6CL (3 REGULAR WORKSHOP) | BATCH 13 | 15189515.1 |  |  | Completed | 1 |  |  |  | 17KL0187
31245 | NC 2017 | TVL | Region X | Misamis Oriental | 304074 | Kalingagan NHS | VILLANUEVA | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0185
31246 | NC 2017 | K10 | Region X | Misamis Oriental | 127904 | Kirahon ES | VILLANUEVA | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 12449768.02 |  |  | Completed | 1 |  |  |  | 17KL0164
31247 | NC 2017 | K10 | Region X | Misamis Oriental | 127906 | Lukong ES | VILLANUEVA | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 12176168.02 |  |  | Completed | 1 |  |  |  | 17KL0163
31248 | NC 2017 | K10 | Region X | Misamis Oriental | 127907 | Nangka ES | VILLANUEVA | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 12544193.02 |  |  | Completed | 1 |  |  |  | 17KL0166
31249 | NC 2017 | TVL | Region X | Misamis Oriental | 341232 | SHS within San Martin ES | VILLANUEVA | 2 |  | 8 | 4STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 19019570.67 |  |  | Completed | 1 |  |  |  | 17KL0186
31250 | NC 2017 | TVL | Region X | Misamis Oriental | 315315 | Tambobong-Balacanas NHS | VILLANUEVA | 2 |  | 8 | 2STY8CL (2 SCIENCE LAB, 2 ICT LAB) | BATCH 13 | 17497290.26 |  |  | Completed | 1 |  |  |  | 17KL0184
31251 | NC 2017 | K10 | Region X | Misamis Oriental | 127909 | Vn Chavez MCS | VILLANUEVA | 2 | 1 | 20 | 4STY20CL | BATCH 13 | 47182909.74 |  |  | Completed | 1 |  |  |  | 17KL0169
31252 | NC 2017 | K10 | Region X | Misamis Oriental | 127909 | Vn Chavez MCS | VILLANUEVA | 2 |  | 12 | 3STY12CL | BATCH 13 | 34880367.25 |  |  | Completed | 1 |  |  |  | 17KL0188
31253 | NC 2017 | K10 | Region X | Ozamis City | 128187 | Antero U. Roa ES (Stimson Abordo ES) | OZAMIS CITY | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 14977000 |  |  | Completed | 1
31254 | NC 2017 | K10 | Region X | Ozamis City | 128162 | Baybay ES | OZAMIS CITY | 2 | 1 | 9 | 3STY9CL | BATCH 13 | 24906000 |  |  | Completed | 1
31255 | NC 2017 | K10 | Region X | Ozamis City | 128191 | Bongbong ES | OZAMIS CITY | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9972000 |  |  | Completed | 1
31256 | NC 2017 | K10 | Region X | Ozamis City | 128194 | Dimaluna ES | OZAMIS CITY | 2 | 1 | 8 | 2STY8CL | BATCH 13 | 19013000 |  |  | Completed | 1
31257 | NC 2017 | K10 | Region X | Ozamis City | 128168 | Dona Consuelo ES | OZAMIS CITY | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 13505000 |  |  | Completed | 1
31258 | NC 2017 | K10 | Region X | Ozamis City | 128169 | Embargo ES | OZAMIS CITY | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 10971000 |  |  | Completed | 1
31259 | NC 2017 | K10 | Region X | Ozamis City | 128181 | Felipe Carreon MS | OZAMIS CITY | 2 | 1 | 12 | 3STY12CL | BATCH 13 | 30038000 |  |  | Completed | 1
31260 | NC 2017 | K10 | Region X | Ozamis City | 128171 | Gotocan ES | OZAMIS CITY | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 11277000 |  |  | Completed | 1
31261 | NC 2017 | K10 | Region X | Ozamis City | 128172 | Labo CS | OZAMIS CITY | 2 | 1 | 12 | 3STY12CL | BATCH 13 | 30323000 |  |  | Completed | 1
31262 | NC 2017 | TVL | Region X | Ozamis City | 304163 | Labo National High School | OZAMIS CITY | 2 | 1 | 14 | TWELVE (12) REGULAR WORKSHOP (4STY24CL) | BATCH 13 | 47534325 |  |  | Completed | 1
31263 | NC 2017 | K10 | Region X | Ozamis City | 128199 | Litapan ES | OZAMIS CITY | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 14839000 |  |  | Completed | 1
31264 | NC 2017 | K10 | Region X | Ozamis City | 128199 | Litapan ES | OZAMIS CITY | 2 |  | 4 | 2STY4CL | BATCH 13 | 11056000 |  |  | Completed | 1
31265 | NC 2017 | K10 | Region X | Ozamis City | 128185 | Malaubang Integrated School | OZAMIS CITY | 2 | 1 | 6 | 3STY6CL | BATCH 13 | 16563000 |  |  | Completed | 1
31266 | NC 2017 | K10 | Region X | Ozamis City | 128174 | Maningcol Central School | OZAMIS CITY | 2 | 1 | 12 | 3STY12CL | BATCH 13 | 30244000 |  |  | Completed | 1
31267 | NC 2017 | TVL | Region X | Ozamis City | 304166 | Montol National High School | OZAMIS CITY | 2 | 1 | 6 | SIX (6) REGULAR WORKSHOP (3STY12CL) | BATCH 13 | 30364847 |  |  | Completed | 1
31268 | NC 2017 | K10 | Region X | Ozamis City | 128203 | Narciso B. Ledesma CS | OZAMIS CITY | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 13006000 |  |  | Completed | 1
31269 | NC 2017 | K10 | Region X | Ozamis City | 128164 | Ozamiz City CS | OZAMIS CITY | 2 | 1 | 18 | 3STY18CL | BATCH 13 | 40204000 |  |  | Completed | 1
31270 | NC 2017 | K10 | Region X | Ozamis City | 128164 | Ozamiz City CS | OZAMIS CITY | 2 |  | 18 | 3STY18CL | BATCH 13 | 40209000 |  |  | Completed | 1
31271 | NC 2017 | TVL | Region X | Ozamis City | 304167 | Ozamiz City National High School | OZAMIS CITY | 2 | 1 | 14 | TWELVE (12) REGULAR WORKSHOP (4STY24CL) | BATCH 13 | 47459005 |  |  | Completed | 1
31272 | NC 2017 | SHS | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 | 1 | 16 | 4STY16CL | BATCH 13 | 37257000 |  |  | Completed | 1
31273 | NC 2017 | TVL | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 |  | 12 | TWELVE (12) REGULAR WORKSHOP (4STY24CL) | BATCH 13 | 48694258 |  |  | Completed | 1
31274 | NC 2017 | SHS | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 |  | 24 | 4STY24CL | BATCH 13 | 48946000 |  |  | Completed | 1
31275 | NC 2017 | K10 | Region X | Ozamis City | 128201 | Pulot ES | OZAMIS CITY | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 15124000 |  |  | Completed | 1
31276 | NC 2017 | TVL | Region X | Ozamis City | 304169 | Pulot National High School | OZAMIS CITY | 2 | 1 | 12 | TWELVE (12) REGULAR WORKSHOP (4STY24CL) | BATCH 13 | 44945987 |  |  | Completed | 1
31277 | NC 2017 | K10 | Region X | Ozamis City | 128186 | Roman Mabanag, Sr. ES | OZAMIS CITY | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 11326000 |  |  | Completed | 1
31278 | NC 2017 | TVL | Region X | Ozamis City | 304165 | San Antonio National High School | OZAMIS CITY | 2 | 1 | 9 | EIGHT (8) REGULAR WORKSHOP (4STY16CL) | BATCH 13 | 35824092 |  |  | Completed | 1
31279 | NC 2017 | K10 | Region X | Ozamis City | 128189 | Sancho Capa ES | OZAMIS CITY | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 13463000 |  |  | Completed | 1
31280 | NC 2017 | K10 | Region X | Ozamis City | 128202 | Sinusa ES | OZAMIS CITY | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 10046000 |  |  | Completed | 1
31281 | NC 2017 | TVL | Region X | Ozamis City | 304162 | Tabid National High School | OZAMIS CITY | 2 | 1 | 8 | EIGHT (8) REGULAR WORKSHOP (4STY16CL) | BATCH 13 | 37142921 |  |  | Completed | 1
31282 | NC 2017 | TVL | Region X | Ozamis City | 304162 | Tabid National High School | OZAMIS CITY | 2 |  | 2 | EIGHT (8) REGULAR WORKSHOP (2STY4CL) | BATCH 13 | 11978000 |  |  | Completed | 1
31283 | NC 2017 | TVL | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 14 | 367000 |  |  | Completed | 1
31284 | NC 2017 | TVL | Region X | Lanao del Norte | 303999 | Bansarvil NHS | KAPATAGAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 807000 |  |  | Completed | 1
31285 | NC 2017 | TVL | Region X | Lanao del Norte | 303999 | Bansarvil NHS | KAPATAGAN | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 807000 |  |  | Completed | 1
31286 | NC 2017 | TVL | Region X | Lanao del Norte | 304003 | Kapatagan NHS | KAPATAGAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 807000 |  |  | Completed | 1
31287 | NC 2017 | TVL | Region X | Lanao del Norte | 304003 | Kapatagan NHS | KAPATAGAN | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 807000 |  |  | Completed | 1
31288 | NC 2017 | TVL | Region X | Lanao del Norte | 304003 | Kapatagan NHS | KAPATAGAN | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 14 | 395900 |  |  | Completed | 1
31289 | NC 2017 | TVL | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 849000 |  |  | Completed | 1
31290 | NC 2017 | TVL | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 849000 |  |  | Completed | 1
31291 | NC 2017 | TVL | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 849000 |  |  | Completed | 1
31292 | NC 2017 | TVL | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 849000 |  |  | Completed | 1
31293 | NC 2017 | TVL | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 14 | 309900 |  |  | Completed | 1
31294 | NC 2017 | TVL | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 849000 |  |  | Completed | 1
31295 | NC 2017 | TVL | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 14 | 368900 |  |  | Completed | 1
31296 | NC 2017 | TVL | Region X | Lanao del Norte | 304022 | Andres Bersales, Sr. Nat'l. HS (Pandanan NHS) | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 867000 |  |  | Completed | 1
31297 | NC 2017 | TVL | Region X | Lanao del Norte | 304022 | Andres Bersales, Sr. Nat'l. HS (Pandanan NHS) | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 14 | 408900 |  |  | Completed | 1
31298 | NC 2017 | TVL | Region X | Lanao del Norte | 304023 | Salvador NHS (Salvador Trade HS) | SALVADOR | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 849000 |  |  | Completed | 1
31299 | NC 2017 | TVL | Region X | Lanao del Norte | 315101 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 867000 |  |  | Completed | 1
31300 | NC 2017 | TVL | Region X | Lanao del Norte | 315101 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 14 | 408900 |  |  | Completed | 1
38486 | NC 2018 | K10 | Region X | Bukidnon | 126319 | Old Damulog ES | DAMULOG | 3 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | BATCH 1 | 3081597.4 |  |  | Completed | 1
38487 | NC 2018 | K10 | Region X | Bukidnon | 126473 | Kimolong ES | KITAOTAO | 3 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | BATCH 1 | 4387675.4 |  |  | Completed | 1
38488 | NC 2018 | K10 | Region X | Bukidnon | 126473 | Kimolong ES | KITAOTAO | 3 |  | 3 | 1STY3CL W/ TOILET ATTACHED | BATCH 1 | 4387675.4 |  |  | Completed | 1
38489 | NC 2018 | K10 | Region X | Bukidnon | 126263 | Balintad ES | BAUNGON | 1 | 1 | 4 | 1STY4CL W/ TOILET ATTACHED | Batch 3 | 10758797 |  |  | Completed | 1 |  |  | PP00275000MN-CW1 | 18KC0137 | [5 empty] | AHM BUILDERS
38490 | NC 2018 | K10 | Region X | Bukidnon | 126269 | Lacolac ES | BAUNGON | 1 | 1 | 4 | 2STY4CL W/ TOILET ATTACHED | Batch 3 | 12142720.6 |  |  | Completed | 1 |  |  | P00275001MN-CW1 | 18KC0138 | [5 empty] | ZI9BUILDERS AND SUPPLIES
38491 | NC 2018 | K10 | Region X | Bukidnon | 126270 | Langaon ES | BAUNGON | 1 | 1 | 6 | 2STY6CL W/ TOILET ATTACHED | Batch 3 | 17801465.32 |  |  | Completed | 1 |  |  | P00275002MN-CW1 | 18KC0139 | [5 empty] | D2J BUILDERS VENTURE
38492 | NC 2018 | K10 | Region X | Bukidnon | 126271 | Liboran ES | BAUNGON | 1 | 1 | 10 | 2STY10CL W/ TOILET ATTACHED | Batch 3 | 26921855.74 |  |  | Completed | 1 |  |  | P00275003MN-CW1 | 18KC0140 | [5 empty] | LBL TRAFFIC CONTROL AND
38493 | NC 2018 | K10 | Region X | Bukidnon | 126274 | Mabunga Elementary School | BAUNGON | 1 | 1 | 6 | 2STY6CL W/ TOILET ATTACHED | Batch 3 | 16860021.79 |  |  | Completed | 1 |  |  | P00275004MN-CW1 | 18KC0141 | [5 empty] | TRENCH ENGINEERING AND
38494 | NC 2018 | K10 | Region X | Bukidnon | 126625 | Dalirig ES | MANOLO FORTICH | 1 | 1 | 6 | 2STY6CL W/ TOILET ATTACHED | Batch 3 | 16864759.52 |  |  | Completed | 1 |  |  | P00275005MN-CW1 | 18KC0142 | [5 empty] | PETRINA CONSTRUCTION &
38495 | NC 2018 | K10 | Region X | Bukidnon | 126635 | Maluko ES | MANOLO FORTICH | 1 | 1 | 10 | 2STY10CL W/ TOILET ATTACHED | Batch 3 | 26890907.11 |  |  | Completed | 1 |  |  | P00275006MN-CW1 | 18KC0143 | [5 empty] | R.R SEIESMUNDO CONSTRUCTION
38496 | NC 2018 | K10 | Region X | Bukidnon | 126638 | Manolo Fortich Central Elementary School | MANOLO FORTICH | 1 | 1 | 6 | 2STY6CL W/ TOILET ATTACHED | Batch 3 | 16914258.56 |  |  | Completed | 1 |  |  | P00275007MN-CW1 | 18KC0144 | [5 empty] | R.R SEIESMUNDO CONSTRUCTION
38497 | NC 2018 | K10 | Region X | Bukidnon | 126638 | Manolo Fortich Central Elementary School | MANOLO FORTICH | 1 |  | 4 | 2STY4CL W/ TOILET ATTACHED | Batch 3 | 11901811.51 |  |  | Completed | 1 |  |  | P002705008MN-CW1 | 18KC0145 | [5 empty] | FOOTPRINTS CONSTRUCTION
38498 | NC 2018 | K10 | Region X | Bukidnon | 126820 | San Antonio Elementary School | TALAKAG | 1 | 1 | 8 | 2STY8CL W/ TOILET ATTACHED | Batch 3 | 23322596.92 |  |  | Completed | 1 |  |  | P00275009MN-CW1 | 18KC0146 | [5 empty] | KOUZBARY BUILDERS
38499 | NC 2018 | K10 | Region X | Bukidnon | 126826 | Talakag CES | TALAKAG | 1 | 1 | 10 | 2STY10CL W/ TOILET ATTACHED | Batch 3 | 27003999.1 |  |  | Completed | 1 |  |  | P00275010MN-CW1 | 18KC0147 | [5 empty] | E & h CONSTRUCTION
38500 | NC 2018 | K10 | Region X | Bukidnon | 126378 | Impasug-Ong CES | IMPASUG-ONG | 2 | 1 | 12 | 3STY12CL | Batch 3 | 27600000 |  |  | Completed | 1 |  |  | P00275011MN-CW1 | 18KA0091 | [5 empty] | BARKADAHAN YOUNG BUILDERS, INC
38501 | NC 2018 | K10 | Region X | Bukidnon | 126507 | KIBUDA ELEMENTARY SCHOOL | LANTAPAN | 2 | 1 | 5 | 1STY5CL | Batch 3 | 7500000 |  |  | Completed | 1 |  |  | P00275012MN-CW1 | 18KA0092 | [5 empty] | ZI9 BUILDERS AND SUPPLIES
38502 | NC 2018 | K10 | Region X | Bukidnon | 126773 | San Jose ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3180000 |  |  | Completed | 1
38503 | NC 2018 | K10 | Region X | Bukidnon | 126773 | San Jose ES | SAN FERNANDO | 2 |  | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3143000 |  |  | Completed | 1
38504 | NC 2018 | SHS | Region X | Bukidnon | 303955 | Halapitan National High School | SAN FERNANDO | 2 | 1 | 8 | 2STY8CL | Batch 3 | 17600000 |  |  | Completed | 1 |  |  | P00275015MN-CW1 | 18KA0082 | [5 empty] | KIOKONG CONSTRUCTION AND DEV'T. CORPORATION
38505 | NC 2018 | K10 | Region X | Bukidnon | 500246 | Impalutao Integrated School | IMPASUG-ONG | 2 | 1 | 8 | 2STY8CL | Batch 3 | 17100000 |  |  | Completed | 1 |  |  | P00275016MN-CW1 | 18KA0083 | [5 empty] | J.T. GAMOLO CONSTRUCTION
38506 | NC 2018 | K10 | Region X | Bukidnon | 500679 | Kibenton IS | IMPASUG-ONG | 2 | 1 | 8 | 2STY8CL | Batch 3 | 17300000 |  |  | Completed | 1 |  |  | P00275017MN-CW1 | 18KA0084 | [5 empty] | MAMAWAG CONSTRUCTION
38507 | NC 2018 | K10 | Region X | Bukidnon | 500890 | Iba Integrated School | CABANGLASAN | 2 | 1 | 8 | 2STY8CL | Batch 3 | 17200000 |  |  | Completed | 1 |  |  | P00275018MN-CW1 | 18KA0085 | [5 empty] | MCA CONSTRUCTION AND SUPPLIES
38508 | NC 2018 | K10 | Region X | Bukidnon | 126315 | Macapari Elementary School | DAMULOG | 3 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3771798.08 |  |  | Completed | 1
38509 | NC 2018 | K10 | Region X | Bukidnon | 126315 | Macapari Elementary School | DAMULOG | 3 |  | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 2997749.08 |  |  | Completed | 1
38510 | NC 2018 | K10 | Region X | Bukidnon | 126319 | Old Damulog ES | DAMULOG | 3 | 1 | 4 | 1STY4CL W/ TOILET ATTACHED | Batch 3 | 5600850.51 |  |  | Completed | 1 |  |  | P00275021MN-CW1 | 18KB0146 | [5 empty] | KIOKONG CONST. & DEV'T. CORP
38511 | NC 2018 | K10 | Region X | Bukidnon | 126322 | Sampagar ES | DAMULOG | 3 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 4294228.48 |  |  | Completed | 1 |  |  | P00275022MN-CW1 | 18KB0139 | [5 empty] | JIZAN BUILDERS
38512 | NC 2018 | K10 | Region X | Bukidnon | 126322 | Sampagar ES | DAMULOG | 3 |  | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 5052040.48 |  |  | Completed | 1 |  |  | P00275023MN-CW1 | 18KB0140 | [5 empty] | MARK ANTHONY CONST. AND SUPPLY
38513 | NC 2018 | K10 | Region X | Bukidnon | 126356 | Minsalagan ES | DON CARLOS | 3 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 4180361.02 |  |  | Completed | 1
38514 | NC 2018 | K10 | Region X | Bukidnon | 126356 | Minsalagan ES | DON CARLOS | 3 |  | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 2850351.07 |  |  | Completed | 1
38515 | NC 2018 | K10 | Region X | Bukidnon | 126362 | San Antonio East ES | DON CARLOS | 3 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 4180172.26 |  |  | Completed | 1 |  |  | P00275026MN-CW1 | 18KB0134 | [5 empty] | ANGEL & SAM CONST. & GEN. MDSE.
38516 | NC 2018 | K10 | Region X | Bukidnon | 126439 | Kikipot ES | KIBAWE | 3 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3118369.04 |  |  | Completed | 1
38517 | NC 2018 | K10 | Region X | Bukidnon | 126439 | Kikipot ES | KIBAWE | 3 |  | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3308530.1 |  |  | Completed | 1
38518 | NC 2018 | K10 | Region X | Bukidnon | 126451 | Romagook ES | KIBAWE | 3 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3097815.78 |  |  | Completed | 1
38519 | NC 2018 | K10 | Region X | Bukidnon | 126472 | Kauyonan ES | KITAOTAO | 3 | 1 | 6 | 2UNITS 1STY3CL W/ TOILET ATTACHED | Batch 3 | 8400259.51 |  |  | Completed | 1 |  |  | P00275030MN-CW1 | 18KB0149 | [5 empty] | EP MANANTAN CONST. & DEV. CORP
38520 | NC 2018 | K10 | Region X | Bukidnon | 126479 | Metebagao ES | KITAOTAO | 3 | 1 | 4 | 1STY4CL W/ TOILET ATTACHED | Batch 3 | 5509960.29 |  |  | Completed | 1 |  |  | P00275031MN-CW1 | 18KB0147 | [5 empty] | MEGAKONSTRUK DEV. CORP
38521 | NC 2018 | K10 | Region X | Bukidnon | 126487 | San Lorenzo ES | KITAOTAO | 3 | 1 | 4 | 1STY4CL W/ TOILET ATTACHED | Batch 3 | 5494586.91 |  |  | Completed | 1 |  |  | P00275032MN-CW1 | 18KB0148 | [5 empty] | DOMUGAN CONSTRUCTION & SUPPLY
38522 | NC 2018 | K10 | Region X | Bukidnon | 126493 | Tandong ES | KITAOTAO | 3 | 1 | 4 | 2UNITS 1STY2CL W/ TOILET ATTACHED | Batch 3 | 5697723 |  |  | Completed | 1 |  |  | P00275033MN-CW1 | 18KB0145 | [5 empty] | ELC CONST. & TRADING
38523 | NC 2018 | K10 | Region X | Bukidnon | 126655 | Dagumbaan ES | MARAMAG | 3 | 1 | 4 | 1STY4CL W/ TOILET ATTACHED | Batch 3 | 5566886.51 |  |  | Completed | 1 |  |  | P00275034MN-CW1 | 18KB0129 | [5 empty] | KIOKONG CONST. AND DEV'T. CORP
38524 | NC 2018 | K10 | Region X | Bukidnon | 126655 | Dagumbaan ES | MARAMAG | 3 |  | 4 | 1STY4CL W/ TOILET ATTACHED | Batch 3 | 5630536.31 |  |  | Completed | 1 |  |  | P00275035MN-CW1 | 18KB0130 | [5 empty] | MAFIL BUILDERS
38525 | NC 2018 | K10 | Region X | Bukidnon | 126657 | DOLOGON CENTRAL ELEMENTARY SCHOOL | MARAMAG | 3 | 1 | 8 | 2STY8CL W/ TOILET ATTACHED | Batch 3 | 19411471.93 |  |  | Completed | 1 |  |  | P00275036MN-CW1 | 18KB0161 | [5 empty] | ER SALAC BUILDERS CORP
38526 | NC 2018 | K10 | Region X | Bukidnon | 126657 | DOLOGON CENTRAL ELEMENTARY SCHOOL | MARAMAG | 3 |  | 8 | 2STY8CL W/ TOILET ATTACHED | Batch 3 | 19401471.93 |  |  | Completed | 1 |  |  | P00275037MN-CW1 | 18KB0162 | [5 empty] | ER SALAC BUILDERS CORP
38527 | NC 2018 | K10 | Region X | Bukidnon | 126660 | Kiharong ES | MARAMAG | 3 | 1 | 4 | 2STY4CL W/ TOILET ATTACHED | Batch 3 | 10302885.41 |  |  | Completed | 1 |  |  | P00275038MN-CW1 | 18KB0163 | [5 empty] | WOLAND CONST. & DEV'T Corp
38528 | NC 2018 | K10 | Region X | Bukidnon | 126660 | Kiharong ES | MARAMAG | 3 |  | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 2863924.17 |  |  | Completed | 1
38529 | NC 2018 | K10 | Region X | Bukidnon | 126661 | Kisanday ES | MARAMAG | 3 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 4142342.28 |  |  | Completed | 1 |  |  | P00275040MN-CW1 | 18KB0131 | [5 empty] | AMSCON BUILDERS & ENTERPRISES
38530 | NC 2018 | K10 | Region X | Bukidnon | 126661 | Kisanday ES | MARAMAG | 3 |  | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 4142342.28 |  |  | Completed | 1
38531 | NC 2018 | K10 | Region X | Bukidnon | 126666 | Maramag Central Elementary School | MARAMAG | 3 | 1 | 10 | 2STY10CL W/ TOILET ATTACHED | Batch 3 | 22618959.4 |  |  | Completed | 1 |  |  | P00275042MN-CW1 | 18KB0158 | [5 empty] | AVECS CORP.
38532 | NC 2018 | K10 | Region X | Bukidnon | 126666 | Maramag Central Elementary School | MARAMAG | 3 |  | 10 | 2STY10CL W/ TOILET ATTACHED | Batch 3 | 22708959.4 |  |  | Completed | 1 |  |  | P00275043MN-CW1 | 18KB0159 | [5 empty] | LTB BUILDERS INC
38533 | NC 2018 | K10 | Region X | Bukidnon | 126666 | Maramag Central Elementary School | MARAMAG | 3 |  | 10 | 2STY10CL W/ TOILET ATTACHED | Batch 3 | 22708959.4 |  |  | Completed | 1 |  |  | P00275044MN-CW1 | 18KB0160 | [5 empty] | LLM UNIFIED BUILDERS
38534 | NC 2018 | K10 | Region X | Bukidnon | 126713 | Mahayag Elementary School | QUEZON | 3 | 1 | 4 | 1STY4CL W/ TOILET ATTACHED | Batch 3 | 5715526.37 |  |  | Completed | 1 |  |  | P00275045MN-CW1 | 18KB0143 | [5 empty] | KIOKONG CONST. & DEV'T. CORP
38535 | NC 2018 | SHS | Region X | Bukidnon | 314913 | Don Carlos NHS | DON CARLOS | 3 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 2890351.05 |  |  | Completed | 1
38536 | NC 2018 | K10 | Region X | Bukidnon | 500680 | San Jose Integrated School | QUEZON | 3 | 1 | 6 | 2STY8CL W/ TOILET ATTACHED | Batch 3 | 19441409.41 |  |  | Completed | 1 |  |  | P00275047MN-CW1 | 18KB0164 | [5 empty] | R.R. SEISMUNDO CONST. & SUPPLY
38537 | NC 2018 | K10 | Region X | Bukidnon |  | San Jose ES | QUEZON | 3 | 1 | 6 | 2STY6CL W/ TOILET ATTACHED | Batch 3 | 13508635.11 |  |  | Completed | 1 |  |  | P00275048MN-CW1 | 18KB0165 | [5 empty] | ER SALAC BUILDERS CORP.
38538 | NC 2018 | K10 | Region X | Bukidnon | 126687 | Langcataon Central Elementary School | PANGANTUCAN | 4 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 4614932.71 |  |  | Completed | 1 |  |  | P00275049MN-CW1 | 18KC0148 | [5 empty] | XY BUILDERS
38539 | NC 2018 | K10 | Region X | Bukidnon | 126687 | Langcataon Central Elementary School | PANGANTUCAN | 4 |  | 4 | 1STY4CL W/ TOILET ATTACHED | Batch 3 | 5638714.42 |  |  | Completed | 1 |  |  | P00275050MN-CW1 | 18KC0149 | [5 empty] | XY BUILDERS
38540 | NC 2018 | K10 | Region X | Cagayan de Oro City | 127960 | Bonbon Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | 3STY6CL | Batch 3 | 25173825.89 |  |  | Completed | 1 |  |  | P00275051MN-CW1 | 18KH0067 | 2018-12-04 |  | 2018-12-24 |  | 2019-01-11 | DL ENTERPRISES
38541 | NC 2018 | K10 | Region X | Cagayan de Oro City | 127961 | Bongbongon Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 12 | 3STY12CL | Batch 3 | 42520267.01 |  |  | Completed | 1 |  |  | P00275052MN-CW1 | 18KH0066 | 2018-12-04 |  | 2018-12-24 |  | 2019-01-11
38542 | NC 2018 | K10 | Region X | Cagayan de Oro City | 127969 | Balongkot Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL | Batch 3 | 6182112.41 |  |  | Completed | 1 |  |  | P00275053MN-CW1 | 18KH0070 | 2018-12-04 |  | 2018-12-24 |  | 2019-01-11 | KS AGAD CONSTRUCTION
38543 | NC 2018 | K10 | Region X | Cagayan de Oro City | 127972 | Bayanga Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 8 | 2STY8CL | Batch 3 | 23940958.27 |  |  | Completed | 1 |  |  | P00275054MN-CW1 | 18KH0068 | 2018-12-04 |  | 2018-12-24 |  | 2019-01-11 | DL ENTERPRISES
38544 | NC 2018 | K10 | Region X | Cagayan de Oro City | 128003 | Iponan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL | Batch 3 | 14038389.43 |  |  | completed | 1 |  |  | P00275055MN-CW1 | 18KH0069 | 2018-12-04 |  | 2018-12-24 |  | 2019-01-11 | JDE CONSTRUCTION
38545 | NC 2018 | K10 | Region X | Cagayan de Oro City | 127943 | FS Catanico ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 13000000 |  |  | completed | 1 |  |  | P00275056MN-CW1 | [6 empty] | AT BUILDERS & GEN. MDSE
38546 | NC 2018 | K10 | Region X | Cagayan de Oro City | 127946 | Malasag ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12500000 |  |  | Completed | 1 |  |  | P00275057MN-CW1 | [6 empty] | LANCE CONS. & SUPPLY
38547 | NC 2018 | K10 | Region X | Cagayan de Oro City | 127950 | Linangohan ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12500000 |  |  | completed | 1 |  |  | P00275058MN-CW1 | [6 empty] | LANCE CONS. & SUPPLY
38548 | NC 2018 | K10 | Region X | Cagayan de Oro City | 127956 | Macabalan ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 15 | 3STY15CL | Batch 3 | 53462500 |  |  | Completed | 1 |  |  | P00275059MN-CW1 | [6 empty] | BRIMA CONSTRUCTION
38549 | NC 2018 | K10 | Region X | Cagayan de Oro City | 127962 | Consolacion ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 6 | 3STY6CL | Batch 3 | 25480000 |  |  | Completed | 1 |  |  | P00275060MN-CW1 | [6 empty] | ESR CONSTRUCTION
38550 | NC 2018 | K10 | Region X | Cagayan de Oro City | 127968 | Taguanao ES | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 6 | 3STY6CL | Batch 3 | 25480000 |  |  | Completed | 1 |  |  | P00275061MN-CW1 | [6 empty] | VISTA CORPORATION
38551 | NC 2018 | SHS | Region X | Cagayan de Oro City | 304106 | Tablon NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | Batch 3 | 17000000 |  |  | Completed | 1 |  |  | P00275062MN-CW1 | [6 empty] | MJ ALONTO BUILDERS AND ENTERPRISES
38552 | NC 2018 | SHS | Region X | Cagayan de Oro City | 304115 | Gusa NHS-Cugman Annex | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 12 | 3STY12CL | Batch 3 | 42770000 |  |  | Completed | 1 |  |  | P002750603MN-CW1 | [6 empty] | MEGAKONSTRUK DEV. CORP.
38553 | NC 2018 | K10 | Region X | Camiguin | 126897 | Mahinog Central School | MAHINOG | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4300915 |  |  | Completed | 1 |  |  | P00275064MN-CW1 | 18KE0061 | [5 empty] | SHEEN-SHEEN CONSTRUCTION
38554 | NC 2018 | K10 | Region X | Camiguin | 126914 | Mambajao CS | MAMBAJAO (Capital) | 0 | 1 | 6 | 2STY6CL | Batch 3 | 16562503 |  |  | Completed | 1 |  |  | P00275065MN-CW1 | 18KE0062 | [5 empty] | SHEEN-SHEEN CONSTRUCTION
38555 | NC 2018 | K10 | Region X | Camiguin | 126917 | Pandan ES | MAMBAJAO (Capital) | 0 | 1 | 3 | 1STY3CL | Batch 3 | 6421000 |  |  | Completed | 1 |  |  | P00275066MN-CW1 | 18KE0063 | [5 empty] | SHEEN-SHEEN CONSTRUCTION
38556 | NC 2018 | SHS | Region X | Camiguin | 303993 | Sixto A. Abao NHS | MAHINOG | 0 | 1 | 4 | 1STY4CL | Batch 3 | 7580600 |  |  | Completed | 1 |  |  | P00275067MN-CW1 | 18KE0064 | [5 empty] | GCMG CONSTRUCTION
38557 | NC 2018 | SHS | Region X | Camiguin | 303993 | Sixto A. Abao NHS | MAHINOG | 0 |  | 4 | 1STY4CL | Batch 3 | 7580600 |  |  | Completed | 1 |  |  | P00275068MN-CW1 | 18KE0065 | [5 empty] | GCMG CONSTRUCTION
38558 | NC 2018 | SHS | Region X | Camiguin | 303993 | Sixto A. Abao NHS | MAHINOG | 0 |  | 4 | 1STY4CL | Batch 3 | 7580600 |  |  | Completed | 1 |  |  | P00275069MN-CW1 | 18KE0066 | [5 empty] | GCMG CONSTRUCTION
38559 | NC 2018 | K10 | Region X | El Salvador | 127678 | Sambulawan Elementary School | CITY OF EL SALVADOR | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11167669.01 |  |  | Completed | 1 |  |  | P00275070MN-CW1 | 18KL0134 | [5 empty] | ALEBON GENUINE MERCH. INC.
38560 | NC 2018 | K10 | Region X | El Salvador | 127679 | Sinaloc Elementary School | CITY OF EL SALVADOR | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12037941.14 |  |  | Completed | 1 |  |  | P00275071MN-CW1 | 18KL0133 | [5 empty] | CAGALAWAN ENTERPRISES
38561 | NC 2018 | K10 | Region X | Gingoog City | 128050 | Don Restituto Baol Central School | GINGOOG CITY | 1 | 1 | 20 | 4STY20CL | BATCH 1 | 42402633.53 |  |  | Completed | 1 |  |  | P00272488MN | 18KK0143 | [5 empty] | DICON BUILDERS CORP./LT POWER BUILDUERS
38562 | NC 2018 | K10 | Region X | Gingoog City | 128060 | Alagatan Elementary School | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11784999.32 |  |  | Completed | 1
38563 | NC 2018 | K10 | Region X | Gingoog City | 128066 | Kalagonoy Elementary School | GINGOOG CITY | 1 | 1 | 6 | 2STY6CL | Batch 3 | 16150962.02 |  |  | Completed | 1
38564 | NC 2018 | TVL | Region X | Gingoog City | 304132 | Kalipay National High School | GINGOOG CITY | 1 | 1 | 12 | 2STY6 LABORATORIES | Batch 3 | 24686911.75 |  |  | Completed | 1
38565 | NC 2018 | TVL | Region X | Gingoog City | 315501 | EUREKA NATIONAL HIGH SCHOOL | GINGOOG CITY | 1 | 1 | 12 | 2STY6 LABORATORIES | Batch 3 | 25232936 |  |  | Completed | 1
38566 | NC 2018 | K10 | Region X | Iligan City | 128083 | Abuno ES | ILIGAN CITY | 0 | 1 | 10 | 2 UNITS 1STY5CL | Batch 3 | 15905919.84 |  |  | Completed | 1 |  |  | P00275076MN | 18KF0128 | [5 empty] | TESAR BUILDERS
38567 | NC 2018 | K10 | Region X | Iligan City | 128094 | Kiwalan ES | ILIGAN CITY | 0 | 1 | 20 | 4STY20CL | Batch 3 | 52392891.69 |  |  | Completed | 1 |  |  | P00275077MN | 18KF0131 | [5 empty] | RUDHIL CONSTRUCTION AND ENTERPRISES INC.
38568 | NC 2018 | K10 | Region X | Iligan City | 128145 | Iligan City South I-A Central School | ILIGAN CITY | 0 | 1 | 12 | 3STY12CL | Batch 3 | 40791527.89 |  |  | Completed | 1 |  |  | P00275078MN | 18KF0130 | [5 empty] | DCM CONST/ REC CONST AND ENT. (jv)
38569 | NC 2018 | K10 | Region X | Iligan City | 128150 | Tomas Cabili Central School | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL | Batch 3 | 12551746.25 |  |  | Completed | 1 |  |  | P00275079MN | 18KF0129 | [5 empty] | R. DE MESA CONSTRUCTION
38570 | NC 2018 | K10 | Region X | Iligan City | 128151 | Victor G. Guevara MS | ILIGAN CITY | 0 | 1 | 6 | 2STY6CL | Batch 3 | 16317676.51 |  |  | Completed | 1 |  |  | P00275080MN | 18KF0126 | [5 empty] | ALQAOD CONST. AND SUPPLY
38571 | NC 2018 | TVL | Region X | Iligan City | 304140 | Don Jose F. Yañez MHS (Bunawan NHS) | ILIGAN CITY | 0 | 1 | 2 | 2STY LABORATORY WORKSHOP BLDG. | Batch 3 | 12770189.75 |  |  | Completed | 1 |  |  | P00275081MN | 18KF0133 | [5 empty] | D.O.T. CONSTRUCTION
38572 | NC 2018 | TVL | Region X | Iligan City | 304150 | Iligan City NSOF | ILIGAN CITY | 0 | 1 | 4 | 2STY 2 LABORATORY WORKSHOP BLDG. | Batch 3 | 12664189.75 |  |  | Completed | 1 |  |  | P00275082MN | 18KF0134 | [5 empty] | ASMAC BUILDERS
38573 | NC 2018 | TVL | Region X | Iligan City | 304152 | Maria Cristina National High School | ILIGAN CITY | 0 | 1 | 4 | 2STY 2 LABORATORY WORKSHOP BLDG. | Batch 3 | 12640189.75 |  |  | Completed | 1 |  |  | P00275083MN | 18KF0135 | [5 empty] | AL FAHDEL CONST. AND ENG'G
38574 | NC 2018 | TVL | Region X | Iligan City | 304160 | Tubaran NHS - Digkilaan Annex | ILIGAN CITY | 0 | 1 | 2 | 2STY 2 LABORATORY WORKSHOP BLDG. | Batch 3 | 12700189.75 |  |  | Completed | 1 |  |  | P00275084MN | 18KF0136 | [5 empty] | ALFAHAD BUILDERS AND ENTERPRISES
38575 | NC 2018 | K10 | Region X | Lanao del Norte | 127166 | Pantar CES | PANTAR | 1 | 1 | 12 | 3UNITS 1STY4CL | BATCH 1 | 15384800 |  |  | Completed | 1 |  |  | P00272489MN-CW1 | 18KG0108 | [5 empty] | MARKBUILT ENTERPRISES
38576 | NC 2018 | TVL | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1 | 1 | 2 | 2STY 2 REGULAR WORKSHOP | BATCH 1 | 9861236.96 |  |  | Completed | 1 |  |  | P00272490MN-CW1 | 18KG0087 | [5 empty] | MMG CONSTRUCTION
38577 | NC 2018 | TVL | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1 |  | 2 | 2STY 2 SCIENCE LAB. | BATCH 1 | 10015305.25 |  |  | Completed | 1 |  |  | P00272491MN-CW1 | 18KG0068 | [5 empty] | JIZAN BUILDERS
38578 | NC 2018 | TVL | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1 |  | 2 | 2STY 2 ICT | BATCH 1 | 9782136.29 |  |  | Completed | 1 |  |  | P00272492MN-CW1 | 18KG0081 | [5 empty] | AMSCON BUILDERS & ENTERPRISES
38579 | NC 2018 | TVL | Region X | Lanao del Norte | 304012 | MATUNGAO NATIONAL HIGH SCHOOL | MATUNGAO | 1 | 1 | 2 | 2STY 2 SCIENCE LAB. | BATCH 1 | 9987580.57 |  |  | Completed | 1 |  |  | P00272493MN-CW1 | 18KG0089 | [5 empty] | JIZAN BUILDERS
38580 | NC 2018 | TVL | Region X | Lanao del Norte | 304012 | MATUNGAO NATIONAL HIGH SCHOOL | MATUNGAO | 1 | 1 | 2 | 2STY 2 ICT | BATCH 1 | 9755064.3 |  |  | Completed | 1 |  |  | P00272494MN-CW1 | 18KG0082 | [5 empty] | AL-QAOD CONST. & SUPPLY
38581 | NC 2018 | SHS | Region X | Lanao del Norte | 304019 | Pantar NHS | PANTAR | 1 | 1 | 12 | 3STY12CL | BATCH 1 | 32700370 |  |  | Completed | 1 |  |  | P00272495MN-CW1 | 18KG0109 | [5 empty] | N.B. SALBO CONSTRUCTION
38582 | NC 2018 | TVL | Region X | Lanao del Norte | 304019 | Pantar NHS | PANTAR | 1 |  | 4 | 2STY 4 REGULAR WORKSHOP | BATCH 1 | 19072728.98 |  |  | Completed | 1 |  |  | P00272496MN-CW1 | 18KG0102 | [5 empty] | NASCON BUILDERS
38583 | NC 2018 | TVL | Region X | Lanao del Norte | 304019 | Pantar NHS | PANTAR | 1 |  | 2 | 2STY 2 SCIENCE LAB. | BATCH 1 | 10069700.21 |  |  | Completed | 1 |  |  | P00272497MN-CW1 | 18KG0072 | [5 empty] | LANAO GENESIS CONST.
38584 | NC 2018 | TVL | Region X | Lanao del Norte | 304019 | Pantar NHS | PANTAR | 1 |  | 2 | 2STY 2 ICT | BATCH 1 | 9835571.47 |  |  | Completed | 1 |  |  | P00272498MN-CW1 | 18KG0086 | [5 empty] | SPMANGORSI CONST.
38585 | NC 2018 | TVL | Region X | Lanao del Norte | 304021 | Tagoloan NHS | TAGOLOAN | 1 | 1 | 2 | 2STY 2 SCIENCE LAB. | BATCH 1 | 10334250.69 |  |  | Completed | 1 |  |  | P00272499MN-CW1 | 18KG0070 | [5 empty] | GREEN BUILDERS & Ent
38586 | NC 2018 | TVL | Region X | Lanao del Norte | 304021 | Tagoloan NHS | TAGOLOAN | 1 |  | 2 | 2STY 2 ICT | BATCH 1 | 10118595.11 |  |  | Completed | 1 |  |  | P00272500MN-CW1 | 18KG0076 | [5 empty] | TESAR BUILDERS
38587 | NC 2018 | K10 | Region X | Lanao del Norte | 126993 | Kapatagan East CS | KAPATAGAN | 2 | 1 | 16 | 2UNITS 2STY8CL | BATCH 1 | 39024000 |  |  | Completed | 1 |  |  | P00272501MN-CW1 | 18KG0106 | [5 empty] | JIMWEN CONST. & GEN. MERCHANDISE/LECAR BLDRS
38588 | NC 2018 | K10 | Region X | Lanao del Norte | 127203 | Masibay ES | NUNUNGAN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 10427000 |  |  | Completed | 1 |  |  | P00272501MN-CW1 | 18KG0104 | [5 empty] | SAFENUR CONST. &
38589 | NC 2018 | TVL | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2 | 1 | 8 | 4STY 8 REGULAR WORKSHOP | BATCH 1 | 42222630.71 |  |  | Completed | 1 |  |  | P00272503MN-CW1 | 18KG0110 | [5 empty] | RUHDIL CONST. & ENTERPRISES
38590 | NC 2018 | TVL | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2 |  | 2 | 2STY 2 REGULAR WORKSHOP | BATCH 1 | 10082274.41 |  |  | Completed | 1 |  |  | P00272504MN-CW1 | 18KG0077 | [5 empty] | LANCE CONSTRUCTION
38591 | NC 2018 | TVL | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2 |  | 2 | 2STY 2 SCIENCE LAB. | BATCH 1 | 10225040.29 |  |  | Completed | 1 |  |  | P00272505MN-CW1 | 18KG0091 | [5 empty] | AJD CONSTRUCTION
38592 | NC 2018 | TVL | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2 |  | 2 | 2STY 2 ICT | BATCH 1 | 9987393.97 |  |  | Completed | 1 |  |  | P00272506MN-CW1 | 18KG0084 | [5 empty] | MAMSHAR CONSTRUCTION
38593 | NC 2018 | TVL | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2 | 1 | 2 | 2STY 2 SCIENCE LAB. | BATCH 1 | 10276649.44 |  |  | Completed | 1 |  |  | P00272507MN-CW1 | 18KG0090 | [5 empty] | AHM BUILDERS
38594 | NC 2018 | TVL | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2 |  | 2 | 2STY 2 ICT | BATCH 1 | 10037789.08 |  |  | Completed | 1 |  |  | P00272508MN-CW1 | 18KG0080 | [5 empty] | RUSH STEEL ESTATE BUILDERS
38595 | NC 2018 | TVL | Region X | Lanao del Norte | 304014 | Munai NHS | MUNAI | 2 | 1 | 2 | 2STY 2 SCIENCE LAB. | BATCH 1 | 10167942.52 |  |  | Completed | 1 |  |  | P00272509MN-CW1 | 18KG0088 | [5 empty] | AMMAR CONST. & Ent.
38596 | NC 2018 | TVL | Region X | Lanao del Norte | 304014 | Munai NHS | MUNAI | 2 |  | 2 | 2STY 2 ICT | BATCH 1 | 9931601.54 |  |  | Completed | 1 |  |  | P00272510MN-CW1 | 18KG0085 | [5 empty] | AHM BUILDERS
38597 | NC 2018 | TVL | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 | 1 | 2 | 2STY 2 SCIENCE LAB. | BATCH 1 | 10214489.75 |  |  | Completed | 1 |  |  | P00272511MN-CW1 | 18KG0069 | [5 empty] | GREEN BUILDERS & ENTERPRISES
38598 | NC 2018 | TVL | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 | 1 | 2 | 2STY 2 ICT | BATCH 1 | 9977062.06 |  |  | Completed | 1 |  |  | P00272512MN-CW1 | 18KG0083 | [5 empty] | AL-AMEN BUILDERS
38599 | NC 2018 | TVL | Region X | Lanao del Norte | 304022 | Andres Bersales, Sr. Nat'l. HS (Pandanan NHS) | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 2 | 2STY 2 SCIENCE LAB. | BATCH 1 | 10520820.01 |  |  | Completed | 1 |  |  | P00272513MN-CW1 | 18KG0094 | [5 empty] | NOREEN CONSTRUCTION
38600 | NC 2018 | TVL | Region X | Lanao del Norte | 304022 | Andres Bersales, Sr. Nat'l. HS (Pandanan NHS) | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 |  | 2 | 2STY 2 ICT | BATCH 1 | 10276702.25 |  |  | Completed | 1 |  |  | P00272514MN-CW1 | 18KG0079 | [5 empty] | ANSAR CONST. SERVICES
38601 | NC 2018 | TVL | Region X | Lanao del Norte | 304023 | Salvador NHS (Salvador Trade HS) | SALVADOR | 2 | 1 | 4 | 2STY 4 REGULAR WORKSHOP | BATCH 1 | 19185000 |  |  | Completed | 1 |  |  | P00272515MN-CW1 | 18KH0101 | [5 empty] | SDM VENTURES
38602 | NC 2018 | TVL | Region X | Lanao del Norte | 304023 | Salvador NHS (Salvador Trade HS) | SALVADOR | 2 |  | 2 | 2STY 2 SCIENCE LAB. | BATCH 1 | 10250915.53 |  |  | Completed | 1 |  |  | P00272516MN-CW1 | 18KG0092 | [5 empty] | DCD BUILDERS & ENT.
38603 | NC 2018 | TVL | Region X | Lanao del Norte | 304023 | Salvador NHS (Salvador Trade HS) | SALVADOR | 2 |  | 2 | 2STY 2 ICT | BATCH 1 | 10012654.52 |  |  | Completed | 1 |  |  | P00272517MN-CW1 | 18KG0074 | [5 empty] | SDM VENTURES
38604 | NC 2018 | TVL | Region X | Lanao del Norte | 315104 | Poonapiagapo NHS(Annex Matungao NHS) | POONA PIAGAPO | 2 | 1 | 2 | 2STY 2 SCIENCE LAB. | BATCH 1 | 10250670.02 |  |  | Completed | 1 |  |  | P00272518MN-CW1 | 18KG0093 | [5 empty] | NDP CONST.
38605 | NC 2018 | TVL | Region X | Lanao del Norte | 315104 | Poonapiagapo NHS(Annex Matungao NHS) | POONA PIAGAPO | 2 |  | 2 | 2STY 2 ICT | BATCH 1 | 10014494.29 |  |  | Completed | 1 |  |  | p00272519MN-CW! | 18KG0075 | [5 empty] | AL-AMEN BUILDERS
38606 | NC 2018 | TVL | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 4 | 2STY 4 REGULAR WORKSHOP | BATCH 1 | 19223000 |  |  | Completed | 1 |  |  | P00272520MN-CW1 | 18KG0103 | [5 empty] | NDP CONST. SERVICE
38607 | NC 2018 | TVL | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 |  | 2 | 2STY 2 SCIENCE LAB. | BATCH 1 | 10520820.01 |  |  | Completed | 1 |  |  | P00272521MN0CW1 | 18KG0071 | [5 empty] | AL-AMEN BUILDERS
38608 | NC 2018 | TVL | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 |  | 2 | 2STY 2 ICT | BATCH 1 | 10276702.25 |  |  | Completed | 1 |  |  | P00272521MN-CW1 | 18KG0073 | [5 empty] | SAFENUR CONST. &
38609 | NC 2018 | SHS | Region X | Lanao del Norte | 304002 | Arsenio A. Quibranza NHS (LNNAIHS) | TUBOD (Capital) | 1 | 1 | 4 | 2STY4CL | Batch 3 | 12153746.25 |  |  | Completed | 1 |  |  | P00275085MN | 18KF0124 | [5 empty] | NDP CONST. AND DEV'T.
38610 | NC 2018 | SHS | Region X | Lanao del Norte | 304015 | Teofila C. Quibranza NHS (New Pualas NHS) | TUBOD (Capital) | 1 | 1 | 6 | 2STY6CL | Batch 3 | 16175676.51 |  |  | Completed | 1 |  |  | P00275086MN | 18KF0125 | [5 empty] | TESAR BUILDERS
38611 | NC 2018 | K10 | Region X | Lanao del Norte | 500430 | Rufo Dela Cruz Integrated School | TUBOD (Capital) | 1 | 1 | 8 | 2STY8CL | Batch 3 | 20611420.58 |  |  | Completed | 1 |  |  | P00275087MN | 18KF0132 | [5 empty] | NDP CONST. AND DEV'T.
38612 | NC 2018 | K10 | Region X | Lanao del Norte | 500687 | Dalama Integrated School | TUBOD (Capital) | 1 | 1 | 6 | 2STY6CL | Batch 3 | 16507676.51 |  |  | Completed | 1 |  |  | P00275088MN | 18KF0127 | [5 empty] | TESAR BUILDERS
38613 | NC 2018 | K10 | Region X | Malaybalay City | 126566 | Macote Elementary School | CITY MALAYBALAY (Capital) | 2 | 1 | 10 | 2STY10CL | Batch 3 | 26066034.6 |  |  | Completed | 1 |  |  | P00275089MN-CW1 | 18KA0093 | [5 empty] | KEZ ENTERPRISES
38614 | NC 2018 | K10 | Region X | Malaybalay City | 126571 | San Martin ES | CITY MALAYBALAY (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 10744490.19 |  |  | Completed | 1 |  |  | P00275090MN-CW1 | 18KA0094 | [5 empty] | AL-NAJIM CONSTRUCTION CORPORATION
38615 | NC 2018 | K10 | Region X | Malaybalay City | 126586 | Malaybalay City Central School | CITY MALAYBALAY (Capital) | 2 | 1 | 12 | 3STY12CL | Batch 3 | 33460413.6 |  |  | Completed | 1 |  |  | P00275091MN-CW1 | 18KA0095 | [5 empty] | LEGACY CONSTRUCTION CORPORATION
38616 | NC 2018 | K10 | Region X | Malaybalay City | 126586 | Malaybalay City Central School | CITY MALAYBALAY (Capital) | 2 |  | 12 | 3STY12CL | Batch 3 | 33898416.52 |  |  | Completed | 1 |  |  | P00275092MN-CW1 | 18KA0096 | [5 empty] | ANGEL & SAM CONSTRUCTION & GE. MDSE.
38617 | NC 2018 | K10 | Region X | Malaybalay City | 126593 | Sumpong Central School | CITY MALAYBALAY (Capital) | 2 | 1 | 15 | 3STY15CL | Batch 3 | 37113038.08 |  |  | Completed | 1 |  |  | P00275093MN-CW1 | 18KA0097 | [5 empty] | JORVIVS CONSTRUCTION CORP./ PETRINA CONSTRUCTION & GEN. MDSE
38618 | NC 2018 | SHS | Region X | Malaybalay City | 303982 | San Martin Agro-Industrial NHS | CITY MALAYBALAY (Capital) | 2 | 1 | 9 | 3STY9CL | Batch 3 | 28084290.05 |  |  | Completed | 1 |  |  | P00275094MN-CW1 | 18KA0098 | [5 empty] | ZI9 BUILDERS AND SUPLLIES
38619 | NC 2018 | K10 | Region X | Misamis Occidental | 127268 | Toril ES | ALORAN | 1 | 1 | 3 | 1STY3CL | Batch 3 | 4401691.86 |  |  | Completed | 1 |  |  | P00275095MN-CW1 | 18KI0118 | [5 empty] | DDS BUILDERS
38620 | NC 2018 | K10 | Region X | Misamis Occidental | 127278 | Timoteo SU ES (Lupagan ES) | BALIANGAO | 1 | 1 | 6 | 2STY6CL | Batch 3 | 14727925.3 |  |  | Completed | 1 |  |  | P00275096MN-CW1 | 18KI0120
38621 | NC 2018 | K10 | Region X | Misamis Occidental | 127386 | Adorable Elementary School | JIMENEZ | 1 | 1 | 3 | 1STY3CL | Batch 3 | 4521561.26 |  |  | Completed | 1 |  |  | P00275097MN-CW1 | 18KI0121 | [5 empty] | GOODLIFE CONSTRUCTION
38622 | NC 2018 | K10 | Region X | Misamis Occidental | 127509 | Bautista ES | SAPANG DALAGA | 1 | 1 | 2 | 1STY2CL | Batch 3 | 3358948.54 |  |  | Completed | 1 |  |  | P00275098MN-CW1 | 18KI0119 | [5 empty] | DDS BUILDERS
38623 | NC 2018 | SHS | Region X | Misamis Occidental | 304030 | Calamba CNHS | CALAMBA | 1 | 1 | 16 | 4STY16CL | Batch 3 | 44258625.23 |  |  | Completed | 1 |  |  | P00275099MN-CW1 | 18KI0116
38624 | NC 2018 | SHS | Region X | Misamis Occidental | 304040 | LOOC NATIONAL HIGH SCHOOL | PLARIDEL | 1 | 1 | 20 | 4STY20CL | Batch 3 | 55164773.44 |  |  | Completed | 1 |  |  | P00275100MN-CW1 | 18KI0117 | [5 empty] | GSMAXX CONSTRUCTION
38625 | NC 2018 | K10 | Region X | Misamis Occidental | 127299 | Liloan CS | BONIFACIO | 2 | 1 | 10 | 2STY10CL | Batch 3 | 28103852.82 |  |  | Completed | 1
38626 | NC 2018 | K10 | Region X | Misamis Occidental | 127303 | Tiaman ES | BONIFACIO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 15152056.54 |  |  | completed | 1
38627 | NC 2018 | K10 | Region X | Misamis Occidental | 127340 | Dolores ES | CLARIN | 2 | 1 | 8 | 2STY8CL | Batch 3 | 23682632.55 |  |  | Completed | 1
38628 | NC 2018 | K10 | Region X | Misamis Occidental | 127349 | Clarin CS | CLARIN | 2 | 1 | 6 | 2STY6CL | Batch 3 | 17937610.08 |  |  | completed | 1
38629 | NC 2018 | K10 | Region X | Misamis Occidental | 127543 | Dinas Elementary School | SINACABAN | 2 | 1 | 2 | 1STY2CL | Batch 3 | 4890261.69 |  |  | completed | 1
38630 | NC 2018 | K10 | Region X | Misamis Occidental | 127581 | Tonggo Elementary School | TUDELA | 2 | 1 | 2 | 1STY2CL | Batch 3 | 4866777.19 |  |  | completed | 1
38631 | NC 2018 | K10 | Region X | Misamis Occidental | 201008 | Pan-ay Diot ES | TUDELA | 2 | 1 | 3 | 1STY3CL | Batch 3 | 5739751.37 |  |  | completed | 1
38632 | NC 2018 | K10 | Region X | Misamis Occidental |  | Pisaan NHS | BONIFACIO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 20644914.47 |  |  | completed | 1
38633 | NC 2018 | K10 | Region X | Misamis Occidental |  | Pan-ay Daku NHS | CLARIN | 2 | 1 | 9 | 3STY9CL | Batch 3 | 35074005.59 |  |  | Completed | 1
38634 | NC 2018 | K10 | Region X | Misamis Occidental | 127344 | Pan-ay ES | CLARIN | 2 | 1 | 6 | 2STY6CL | Batch 5 | 17663112.92 |  |  | Completed | 1
38635 | NC 2018 | K10 | Region X | Misamis Occidental | 127582 | Tudela Central School | TUDELA | 2 | 1 | 6 | 2STY6CL | Batch 5 | 18029080.17 |  |  | completed | 1
38636 | NC 2018 | K10 | Region X | Misamis Oriental | 127602 | Balingasag CS | BALINGASAG | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 14339528.03 |  |  | Completed | 1 |  |  | P00272523MN | 18KK0144 | [5 empty] | DICON BUILDERS CORPORATION
38637 | NC 2018 | K10 | Region X | Misamis Oriental | 127609 | Cogon ES | BALINGASAG | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 14405194.19 |  |  | Completed | 1 |  |  | P00272524MN | 18KK0145 | [5 empty] | DICON BUILDERS CORPORATION
38638 | NC 2018 | K10 | Region X | Misamis Oriental | 127728 | Kitamban ES | BINUANGAN | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3560452.19 |  |  | Completed | 1 |  |  | P00272525MN | 18KK0126 | [5 empty] | A.C SY CONSTRUCTION
38639 | NC 2018 | K10 | Region X | Misamis Oriental | 127733 | Mosangot ES | BINUANGAN | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 14667398.94 |  |  | Completed | 1 |  |  | P00272526MN | 18KK0147 | [5 empty] | WDM CONST. & SUPPLIES
38640 | NC 2018 | K10 | Region X | Misamis Oriental | 127791 | Sta. Cruz ES | MAGSAYSAY (LINUGOS) | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 14962666.19 |  |  | Completed | 1 |  |  | P00272527MN | 18KK0148 | [5 empty] | WDM CONST. & SUPPLIES
38641 | NC 2018 | K10 | Region X | Misamis Oriental | 127861 | Salay River ES | SALAY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 14541400.34 |  |  | Completed | 1 |  |  | P00272528MN | 18KK0149 | [5 empty] | PYRAMID CONSOLIDATED BUILDERS &
38642 | NC 2018 | K10 | Region X | Misamis Oriental | 127885 | Mandahilag ES | TALISAYAN | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 14429795.36 |  |  | Completed | 1 |  |  | P00272529MN | 18KK0151 | [5 empty] | DCM CONSTRUCTION
38643 | NC 2018 | K10 | Region X | Misamis Oriental | 127893 | San Alonzo ES | BALINGOAN | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 14512928.1 |  |  | Completed | 1 |  |  | P00272530MN | 18KK0146 | [5 empty] | R. DE MESA CONSTRUCTION
38644 | NC 2018 | TVL | Region X | Misamis Oriental | 304061 | Baliwagan NHS | BALINGASAG | 1 | 1 | 20 | 4STY 10 LAB | BATCH 1 | 41942098.5775 |  |  | Completed | 1 |  |  | P00272531MN | 18KK0164 | [5 empty] | DICON BUILDERS CORPORATION
38645 | NC 2018 | TVL | Region X | Misamis Oriental | 304062 | Binuangan NHS | BINUANGAN | 1 | 1 | 9 | 3STY 3 LAB & 3 LEC | BATCH 1 | 33035612.32 |  |  | Completed | 1 |  |  | P00272532MN | 18KK0156 | [5 empty] | NURBEN ENGINEERING AND BUILDING
38646 | NC 2018 | TVL | Region X | Misamis Oriental | 304066 | Consuelo NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | 6 | 3STY 3 LAB | BATCH 1 | 18913726.67 |  |  | Completed | 1 |  |  | P00272533MN | 18KK0163 | [5 empty] | BRIMA CONST. & ENTERPRISES
38647 | NC 2018 | TVL | Region X | Misamis Oriental | 304076 | Kibungsod NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | 20 | 4STY 6 LAB, 2CL for SHS & 5CL | BATCH 1 | 42662095.52 |  |  | Completed | 1 |  |  | P00272534MN | 18KK0157 | [5 empty] | FOOTPRINTS CONSTRUCTION
38648 | NC 2018 | TVL | Region X | Misamis Oriental | 304077 | Kinoguitan Nat'l Agricultural HS | KINOGUITAN | 1 | 1 | 12 | 3STY 6 LAB | BATCH 1 | 38104139.17 |  |  | Completed | 1 |  |  | P00272535MN | 18KK0167 | [5 empty] | DICON BUILDERS CORPORATION
38649 | NC 2018 | TVL | Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1 | 1 | 20 | 4STY 10 LAB | BATCH 1 | 43067985.06 |  |  | Completed | 1 |  |  | P00272536MN | 18KK0166 | [5 empty] | BRIMA CONST. & ENTERPRISES
38650 | NC 2018 | TVL | Region X | Misamis Oriental | 304095 | Portulin NHS | MEDINA | 1 | 1 | 12 | 3STY 6 LAB | BATCH 1 | 38075290.71 |  |  | Completed | 1 |  |  | P00272537MN | 18KK0165 | [5 empty] | BRIMA CONST. & ENTERPRISES
38651 | NC 2018 | TVL | Region X | Misamis Oriental | 304096 | Salay NHS | SALAY | 1 | 1 | 20 | 4STY 10 LAB | BATCH 1 | 43618988.29 |  |  | Completed | 1 |  |  | P00272538MN | 18KK0162 | [5 empty] | D.O.T. CONSTRUCTION/C.B GABAY PHIL
38652 | NC 2018 | TVL | Region X | Misamis Oriental | 304098 | San Juan NHS | BALINGASAG | 1 | 1 | 8 | 2STY 4 LAB | BATCH 1 | 18110904.97 |  |  | Completed | 1 |  |  | P00272539MN | 18KK0155 | [5 empty] | HEXAMINDZ CORPORATION
38653 | NC 2018 | TVL | Region X | Misamis Oriental | 315304 | Lumbo NHS | LAGONGLONG | 1 | 1 | 9 | 3STY 3 LAB & 3CL | BATCH 1 | 32810042.9 |  |  | Completed | 1 |  |  | P00272540MN | 18KK0158 | [5 empty] | FOOTPRINTS CONSTRUCTION
38654 | NC 2018 | TVL | Region X | Misamis Oriental | 315306 | Rosario NHS | BALINGASAG | 1 | 1 | 12 | 3STY 6 LAB | BATCH 1 | 38474449.24 |  |  | Completed | 1 |  |  | P00272541MN | 18KK0159 | [5 empty] | CAGALAWAN ENTERPRISES/ FOOTPRINTS CONSTRUCTION
38655 | NC 2018 | SHS | Region X | Misamis Oriental | 341228 | SHS within Mantangale ES | BALINGOAN | 1 | 1 | 9 | 3 STY 3 LAB & 3CL | BATCH 1 | 32622488.55 |  |  | Completed | 1 |  |  | P00272542MN | 18KK0154 | [5 empty] | BRIMA CONST. & ENTERPRISES
38656 | NC 2018 | SHS | Region X | Misamis Oriental | 341235 | SHS within Sta. Ines ES | TALISAYAN | 1 | 1 | 6 | 3STY 3 LAB | BATCH 1 | 19088985.54 |  |  | Completed | 1 |  |  | P00272543MN | 18KK0161 | [5 empty] | JTA BUILDERS
38657 | NC 2018 | SHS | Region X | Misamis Oriental | 360848 | SHS within Esperanza ES | KINOGUITAN | 1 | 1 | 12 | 3STY 6 LAB | BATCH 1 | 37849882.65 |  |  | Completed | 1 |  |  | P00272544MN | 18KK0160 | [5 empty] | DCM CONSTRUCTION
38658 | NC 2018 | K10 | Region X | Misamis Oriental | 500692 | Kidampas IS | SUGBONGCOGON | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 14632800.08 |  |  | Completed | 1 |  |  | P00272545MN | 18KK0150 | [5 empty] | RYM CONSTRUCTION
38659 | NC 2018 | SHS | Region X | Misamis Oriental | 304101 | Sugbongcogon NHS | SUGBONGCOGON | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11641007.46 |  |  | Completed | 1
38660 | NC 2018 | K10 | Region X | Misamis Oriental | 127591 | Lourdes ES | ALUBIJID | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11199329.67 |  |  | Completed | 1 |  |  | P00275111MN-CW1 | 18KL0135 | [5 empty] | ALEBON GENUINE MERCH. INC.
38661 | NC 2018 | K10 | Region X | Misamis Oriental | 127687 | Jampason ES | INITAO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11157131.22 |  |  | Completed | 1 |  |  | P00275112MN-CW1 | 18KL0137 | [5 empty] | CAGALWAN ENTERPRISES
38662 | NC 2018 | K10 | Region X | Misamis Oriental | 127755 | Dulong ES | LIBERTAD | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11264840.97 |  |  | Completed | 1 |  |  | P00275112MN-CW1 | 18KL0136 | [5 empty] | FOOTPRINTS CONSTRYUCTION/ CAGALAWAN ENTERPRISES
38663 | NC 2018 | K10 | Region X | Misamis Oriental | 127805 | Manticao CS | MANTICAO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 13626083.59 |  |  | Completed | 1 |  |  | P00275114MN-CW1 | 18KL0139 | [5 empty] | CAGALAWAN ENTERPRISES
38664 | NC 2018 | K10 | Region X | Misamis Oriental | 127847 | Patag ES | OPOL | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11153631.54 |  |  | Completed | 1 |  |  | P00275115MN-CW1 | 18KL0141 | [5 empty] | CAGALAWAN ENTERPRISES
38665 | NC 2018 | K10 | Region X | Misamis Oriental | 127871 | Sta. Ana ES | TAGOLOAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11098881.11 |  |  | Completed | 1 |  |  | P00275116MN-CW1 | 18KL0142 | [5 empty] | FOUR BUILDERS & CONST. SUPPLY
38666 | NC 2018 | K10 | Region X | Misamis Oriental | 127902 | Kalingagan ES | VILLANUEVA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11106816.14 |  |  | Completed | 1 |  |  | P00275117MN-CW1 | 18KL0144 | [5 empty] | CAGALAWAN ENTERPRISES
38667 | NC 2018 | K10 | Region X | Misamis Oriental | 127909 | VN Chavez MCS | VILLANUEVA | 2 | 1 | 12 | 3STY12CL | Batch 3 | 28752595.9 |  |  | Completed | 1 |  |  | P00275118MN-CW1 | 18KL0132 | [5 empty] | CAGALAWAN ENTERPRISES
38668 | NC 2018 | K10 | Region X | Misamis Oriental | 127909 | VN Chavez MCS | VILLANUEVA | 2 |  | 20 | 4STY20CL | Batch 3 | 42567563.06 |  |  | Completed | 1 |  |  | P00275119MN-CW1 | 18KL0131 | [5 empty] | FOOTPRINTS CONSTRUCTION/CAGALAWAN ENTERPRISES
38669 | NC 2018 | K10 | Region X | Misamis Oriental | 304060 | Aplaya NHS | JASAAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11297161.28 |  |  | Completed | 1 |  |  | P00275120MN-CW1 | 18KL0145 | [5 empty] | E & R ENTERPRISES & CONSTRUCTION
38670 | NC 2018 | K10 | Region X | Misamis Oriental | 330528 | Rosario NHS of Tagoloan | TAGOLOAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11177427.12 |  |  | Completed | 1 |  |  | P00275121MN-CW1 | 18KL0143 | [5 empty] | JIMWEN CONST. & GENERAL MERCHANDISE
38671 | NC 2018 | K10 | Region X | Misamis Oriental | 500519 | Andales ES | INITAO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11301321.54 |  |  | Completed | 1 |  |  | P00275122MN-CW1 | 18KL0138 | [5 empty] | AJ CONSTRUCTION & SUPPLY
38672 | NC 2018 | K10 | Region X | Misamis Oriental | 500523 | Mahayahay IS | MANTICAO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11133046.56 |  |  | Completed | 1 |  |  | P00275123MN-CW1 | 18KL0140 | [5 empty] | ALEBON GENUINE MERCH. INC.
38673 | NC 2018 | K10 | Region X | Misamis Oriental | 500524 | Minalwang IS | CLAVERIA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11945421.1 |  |  | Completed | 1 |  |  | P00275124MN-CW1 | 18KL0146 | [5 empty] | ALEBON GENUINE MERCH. INC.
38674 | NC 2018 | K10 | Region X | Oroquieta City | 127455 | Langcangan CES | OROQUIETA CITY (Capital) | 1 | 1 | 6 | 2STY6CL | Batch 3 | 12849000 |  |  | Completed | 1 |  |  | P00275125MN-CW1 | 18KI0102 | [5 empty] | AFG ZILLION CONST. CORP
38675 | NC 2018 | K10 | Region X | Oroquieta City | 127472 | Talic ES | OROQUIETA CITY (Capital) | 1 | 1 | 6 | 2STY6CL | Batch 3 | 12827867.27 |  |  | Completed | 1 |  |  | P00275126MN-CW1 | 18KI0104 | [5 empty] | DDS BUILDERS
38676 | NC 2018 | TVL | Region X | Oroquieta City | 304044 | Misamis Occidental Science & Tech. HS | OROQUIETA CITY (Capital) | 1 | 1 | 6 | 4STY8CL (SCIENCE LAB, ICT LAB &REGULAR CLASSROOMS) | Batch 3 | 21058658.07 |  |  | Completed | 1 |  |  | P00275127MN-CW1 | 18KI0110 | [5 empty] | TRIMLUV BUILDERS & SUPPLY
38677 | NC 2018 | TVL | Region X | Oroquieta City | 304057 | Talairon NHS | OROQUIETA CITY (Capital) | 1 | 1 | 6 | 3STY9CL (SCIENCE LAB, ICT LAB & REGULAR WORKSHOP & REGULAR CLASSROOMS) | Batch 3 | 29415992.07 |  |  | Completed | 1 |  |  | P00275128MN-CW1 | 18KI0111 | [5 empty] | SGM CONSTRUCTION
38678 | NC 2018 | TVL | Region X | Oroquieta City | 500401 | Mobod IS | OROQUIETA CITY (Capital) | 1 | 1 | 2 | 2STY4CL (SCIENCE LAB, ICT LAB) | Batch 3 | 11220104.61 |  |  | Completed | 1 |  |  | P00275129MN-CW1 | 18KI0101 | [5 empty] | DDS BUILDERS
38679 | NC 2018 | K10 | Region X | Ozamis City | 128176 | Sangay Elementary School | OZAMIS CITY | 2 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | BATCH 1 | 4693000 |  |  | Completed | 1
38680 | NC 2018 | K10 | Region X | Ozamis City | 128176 | Sangay Elementary School | OZAMIS CITY | 2 |  | 3 | 1STY3CL W/ TOILET ATTACHED | BATCH 1 | 4693000 |  |  | Completed | 1
38681 | NC 2018 | K10 | Region X | Ozamis City | 128200 | Jacinto Nemeno Elementary School | OZAMIS CITY | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 14098000 |  |  | Completed | 1
38682 | NC 2018 | K10 | Region X | Ozamis City | 128164 | Ozamiz City Central School | OZAMIS CITY | 2 | 1 | 15 | 3STY15CL | Batch 3 | 48099796.06 |  |  | completed | 1
38683 | NC 2018 | K10 | Region X | Ozamis City | 128192 | Cruz Lanzado Saligan Elementary School | OZAMIS CITY | 2 | 1 | 4 | 2STY4CL | Batch 5 | 15411303.21 |  |  | Completed | 1
38684 | NC 2018 | K10 | Region X | Tangub City | 128221 | Bongabong ES | TANGUB CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 14508888.99 |  |  | Completed | 1
38685 | NC 2018 | K10 | Region X | Tangub City | 128230 | Polao IS | TANGUB CITY | 2 | 1 | 8 | 2STY8CL | Batch 3 | 23399284.69 |  |  | completed | 1
38686 | NC 2018 | SHS | Region X | Tangub City | 323301 | Mayor Alfonso Tan High School | TANGUB CITY | 2 | 1 | 8 | 2STY8CL | Batch 3 | 24591689.14 |  |  | Completed | 1
38687 | NC 2018 | K10 | Region X | Valencia City | 126831 | Bagontaas CES | CITY OF VALENCIA | 4 | 1 | 6 | 2STY6CL | Batch 3 | 13200000 |  |  | Completed | 1 |  |  | P00275134MN-CW1 | 18KA0099 |  |  |  |  | 2018-12-26 | AL-NAJIM CONSTRUCTION
38688 | NC 2018 | K10 | Region X | Valencia City | 126858 | SUGOD ES | CITY OF VALENCIA | 4 | 1 | 5 | 1STY5CL W/ TOILET ATTACHED | Batch 3 | 6200000 |  |  | Completed | 1 |  |  | P00275135MN-CW1 | 18KA0086 |  |  |  |  | 2018-12-26 | MAFIL BUILDERS INC.
38689 | NC 2018 | K10 | Region X | Valencia City | 126863 | Valencia City Central School | CITY OF VALENCIA | 4 | 1 | 4 | 2STY4CL | Batch 3 | 10600000 |  |  | Completed | 1 |  |  | P00275136MN-CW1 | 18KA0100 |  |  |  |  | 2018-12-26 | M. DESIGN & CONSTRUCTION
38690 | NC 2018 | K10 | Region X | Valencia City | 126863 | Valencia City Central School | CITY OF VALENCIA | 4 |  | 12 | 3STY12CL | Batch 3 | 33500000 |  |  | Completed | 1 |  |  | P00275137MN-CW1 | 18KA0101 |  |  |  |  | 2018-12-26 | FOOTPRINTS CONSTRUCTION
38691 | NC 2018 | K10 | Region X | Valencia City | 126881 | Vintar ELEMENTARY SCHOOL | CITY OF VALENCIA | 4 | 1 | 5 | 1STY5CL W/ TOILET ATTACHED | Batch 3 | 6300000 |  |  | Completed | 1 |  |  | P00275138MN-CW1 | 18KA0087 |  |  |  |  | 2018-12-26 | M. DESIGN & CONSTRUCTION
38692 | NC 2018 | SHS | Region X | Valencia City | 303970 | Lurugan National High School | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 4200000 |  |  | Completed | 1 |  |  | P00275139MN-CW1 | 18KA0088 |  |  |  |  | 2018-12-26 | BRILLANTES CONSTRUCTION
38693 | NC 2018 | SHS | Region X | Valencia City | 314906 | Lilingayon Nationla High School | CITY OF VALENCIA | 4 | 1 | 6 | 2STY6CL | Batch 3 | 13500000 |  |  | Completed | 1 |  |  | P00275140MN-CW1 | 18KA0089 |  |  |  |  | 2018-12-26 | BARKADAHAN YOUNG BUILDERS INC.
38694 | NC 2018 | SHS | Region X | Valencia City | 323803 | Concepcion National High School | CITY OF VALENCIA | 4 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3000000 |  |  | Completed | 1 |  |  | P00275141MN-CW1 | 18KA0090 |  |  |  |  | 2018-12-26 | FOOTPRINTS CONSTRUCTION
39851 | NC 2019 | K10 | Region X | Bukidnon | 126810 | Lirongan ES | TALAKAG | 1 | 1 | 4 | 1STY4CL |  | 10825793.9925 |  | completed | 1 |  |  |  | 19KC0098 |  |  | 2019-06-11 |  |  |  |  | 0
39852 | NC 2019 | K10 | Region X | Bukidnon | 501153 | Capt. Juan IS | ANTAPAN | 2 | 1 | 2 | 1STY2CL |  | 4986594.207 |  | completed | 1 | [11 empty] | 0
39853 | NC 2019 | SHS | Region X | Bukidnon |  | Impasug-Ong Stand Alone SHS | IMPASUG-ONG | 2 | 1 | 4 | 2STY4CL |  | 12076243.7711 |  | COMPLETED | 1 | [11 empty] | 0
39854 | NC 2019 | K10 | Region X | Bukidnon | 126768 | Nakabuklad ES | SAN FERNANDO | 2 | 1 | 2 | 1STY2CL |  | 5146012.8397 |  | completed | 1 | [11 empty] | 0
39855 | NC 2019 | K10 | Region X | Bukidnon | 126776 | Tigua ES | SAN FERNANDO | 2 | 1 | 3 | 1STY3CL |  | 7064432.8094 |  | completed | 1 | [11 empty] | 0
39856 | NC 2019 | K10 | Region X | Bukidnon | 126710 | Kipaypayon ES | QUEZON | 3 | 1 | 6 | 2UNITS 1STY3CL |  | 18476720.9809 |  | completed | 1 | [11 empty] | 0
39857 | NC 2019 | K10 | Region X | Bukidnon | 126712 | Lumintao ES | QUEZON | 3 | 1 | 5 | 1STY5CL |  | 13468044.5961 |  | completed | 1 | [11 empty] | 0
39858 | NC 2019 | K10 | Region X | Bukidnon | 126719 | Quezon CES | QUEZON | 3 | 1 | 9 | 3STY9CL |  | 31814538 |  | completed | 1 | [11 empty] | 0
39859 | NC 2019 | K10 | Region X | Bukidnon | 126720 | Salaysay ES | QUEZON | 3 | 1 | 4 | 1STY4CL |  | 10612291.6878 |  | completed | 1 | [11 empty] | 0
39860 | NC 2019 | K10 | Region X | Bukidnon | 126685 | Kimanait ES | PANGANTUCAN | 4 | 1 | 4 | 1STY4CL |  | 10785693.9925 |  | completed | 1 |  |  |  | 19KC0099 |  |  | 2019-06-11 |  |  |  |  | 0
39861 | NC 2019 | K10 | Region X | Cagayan de Oro City | 127979 | Mambuaya Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 2 | 1STY2CL |  | 5588066.117 |  | completed | 1 | [11 empty] | 0
39862 | NC 2019 | K10 | Region X | Cagayan de Oro City | 127948 | Balubal Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 2 | 1STY2CL |  | 6516250 |  | completed | 1 | [11 empty] | 0
39863 | NC 2019 | K10 | Region X | Camiguin | 126932 | Liong ES | Guinsiliban | 0 | 1 | 4 | 2STY4CL |  | 14003117.9737 |  | COMPLETED | 1 | [11 empty] | 0
39864 | NC 2019 | K10 | Region X | El Salvador | 127674 | Kalabaylabay ES | CITY OF EL SALVADOR | 2 | 1 | 9 | 3STY9CL |  | 25973630.8969 |  | completed | 1 | [11 empty] | 0
39865 | NC 2019 | K10 | Region X | Gingoog City | 128051 | Esik Campilan Elementary School | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL |  | 12151927.4405 |  | completed | 1 | [11 empty] | 0
39866 | NC 2019 | K10 | Region X | Gingoog City | 128058 | Roy Vizcara Elementary School | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL |  | 12299615.0467 |  | completed | 1 | [11 empty] | 0
39867 | NC 2019 | K10 | Region X | Iligan City | 128154 | Estenzo Comendador MES (Upper Tominobo ES) | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL |  | 12903925.6156 |  | completed | 1 | [11 empty] | 0
39868 | NC 2019 | SHS | Region X | Lanao del Norte | 304000 | Binuni-Demologan NHS | BACOLOD | 1 | 1 | 4 | 2STY4CL |  | 12647285.6156 |  | completed | 1 | [11 empty] | 0
39869 | NC 2019 | SHS | Region X | Lanao del Norte | 304013 | Diego H. Patigayon NHS (Mukas NHS) | KOLAMBUGAN | 1 | 1 | 4 | 2STY4CL |  | 14316448.1156 |  | completed | 1 | [11 empty] | 0
39870 | NC 2019 | K10 | Region X | Lanao del Norte | 127186 | Padianan ES | SALVADOR | 2 | 1 | 6 | 2STY6CL |  | 16667013.625 |  | completed | 1 | [11 empty] | 0
39871 | NC 2019 | K10 | Region X | Malaybalay City | 103629 | Pighalugan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 5 | 1STY5CL |  | 10844681.2529 |  | completed | 1 | [11 empty] | 0
39872 | NC 2019 | K10 | Region X | Misamis Occidental | 127500 | Mangidkid Elementary School | PLARIDEL | 1 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED |  | 6949731.9724 |  | completed | 1 | [11 empty] | 0
39873 | NC 2019 | K10 | Region X | Misamis Occidental | 127370 | San Francisco ES | CONCEPCION | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED |  | 7441920.9965 |  | completed | 1 | [11 empty] | 0
39874 | NC 2019 | K10 | Region X | Misamis Occidental | 127270 | Tugaya ES | ALORAN | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED |  | 5099053.6946 |  | completed | 1 | [11 empty] | 0
39875 | NC 2019 | K10 | Region X | Misamis Occidental | 127384 | Petianan ES | DON VICTORIANO CHIONGBIAN | 2 | 1 | 6 | 2STY6CL |  | 22179300.6968 |  | completed | 1 | [11 empty] | 0
39876 | NC 2019 | K10 | Region X | Misamis Occidental | 127359 | Tinaclaan ES | CLARIN | 2 | 1 | 4 | 2STY4CL |  | 19582366.2511 |  | completed | 1 | [11 empty] | 0
39877 | NC 2019 | K10 | Region X | Misamis Oriental | 500250 | Alipuaton IS | SALAY | 1 | 1 | 4 | 2STY4CL |  | 12969790.9784 |  | completed | 1 | [11 empty] | 0
39878 | NC 2019 | K10 | Region X | Misamis Oriental | 500250 | Alipuaton IS | SALAY | 1 |  | 6 | 2STY6CL |  | 16976587.7603 |  | completed | 1 | [11 empty] | 0
39879 | NC 2019 | K10 | Region X | Misamis Oriental | 127927 | Talacogon ES | LUGAIT | 2 | 1 | 10 | 2STY10CL |  | 25173868.8679 |  | completed | 1 | [11 empty] | 0
39880 | NC 2019 | K10 | Region X | Oroquieta City | 127468 | Sarancial Mialen ES | OROQUIETA CITY (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED |  | 5023607.1386 |  | completed | 1 | [11 empty] | 0
39881 | NC 2019 | K10 | Region X | Ozamis City | 128165 | Bacolod Elementary School | OZAMIS CITY | 2 | 1 | 6 | 2STY6CL |  | 17114579.8703 |  | completed | 1 | [11 empty] | 0
39882 | NC 2019 | K10 | Region X | Ozamis City | 128162 | Baybay Central School | OZAMIS CITY | 2 | 1 | 6 | 3STY6CL |  | 28992806.1522 |  | completed | 1 | [11 empty] | 0
39883 | NC 2019 | K10 | Region X | Ozamis City | 128170 | Gango Elementary School | OZAMIS CITY | 2 | 1 | 9 | 3STY9CL |  | 34647658.1575 |  | completed | 1 | [11 empty] | 0
39884 | NC 2019 | K10 | Region X | Ozamis City | 500701 | Misamis Annex Integrated School | OZAMIS CITY | 2 | 1 | 6 | 3STY6CL |  | 25076720.2219 |  | completed | 1 | [11 empty] | 0
39885 | NC 2019 | K10 | Region X | Tangub City | 128237 | Villaba ES | TANGUB CITY | 2 | 1 | 4 | 2STY4CL |  | 13251768.2235 |  | completed | 1 | [11 empty] | 0
39886 | NC 2019 | K10 | Region X | Valencia City | 126873 | Laligan Central School | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL |  | 7017500 |  | completed | 1 | [11 empty] | 0
40540 | NC 2020 | K10 | Region X | Bukidnon | 126531 | SAN JOSE ES | LIBONA | 1 | 1 | 2 | 1STY2CL |  | 5486579.23 |  |  | Completed | 1
40541 | NC 2020 | K10 | Region X | Bukidnon | 126603 | LARAPAN ES | MALITBOG | 1 | 1 | 2 | 1STY2CL |  | 5501616.73 |  |  | Completed | 1
40542 | NC 2020 | K10 | Region X | Bukidnon | 126631 | KITAM-IS ES | MANOLO FORTICH | 1 | 1 | 2 | 1STY2CL |  | 5486579.23 |  |  | Completed | 1
40543 | NC 2020 | K10 | Region X | Bukidnon | 126781 | KILABONG ES | SUMILAO | 1 | 1 | 2 | 1STY2CL |  | 5486579.23 |  |  | Completed | 1
40544 | NC 2020 | K10 | Region X | Bukidnon | 126814 | MASIMAG ES | TALAKAG | 1 | 1 | 2 | 1STY2CL |  | 5506629.23 |  |  | Completed | 1
40545 | NC 2020 | K10 | Region X | Bukidnon | 126817 | MIGPAIT ES | TALAKAG | 1 | 1 | 2 | 1STY2CL |  | 5506629.23 |  |  | Completed | 1
40546 | NC 2020 | SHS | Region X | Bukidnon | 314923 | Impasugong NHS-Kapitan Bayong Annex | IMPASUG-ONG | 2 | 1 | 4 | 2STY4CL (SHS W/ COMPUTER ROOM - OPTION 3 PLAN) |  | 11278125 |  |  | Completed | 1
40547 | NC 2020 | K10 | Region X | Bukidnon | 500890 | Iba Integrated School | CABANGLASAN | 2 | 1 | 4 | 2STY4CL |  | 11278125 |  |  | Completed | 1
40548 | NC 2020 | K10 | Region X | Bukidnon | 126405 | Malinao ES | KADINGILAN | 3 | 1 | 5 | 1STY5CL |  | 14267662.81 |  |  | Completed | 1
40549 | NC 2020 | K10 | Region X | Bukidnon | 126706 | Busco ES | QUEZON | 3 | 1 | 4 | 2UNITS 1STY2CL |  | 11328517.39 |  |  | Completed | 1
40550 | NC 2020 | K10 | Region X | Bukidnon | 126716 | Miluya ES | QUEZON | 3 | 1 | 2 | 1STY2CL |  | 5406845.19 |  |  | Completed | 1
40551 | NC 2020 | K10 | Region X | Bukidnon | 126717 | Minsalirac ES | QUEZON | 3 | 1 | 3 | 1STY3CL |  | 7917315.26 |  |  | Completed | 1
40552 | NC 2020 | K10 | Region X | Bukidnon | 500677 | Dilapa Integrated School | QUEZON | 3 | 1 | 3 | 1STY3CL (JUNIOR HIGHSCHOOL) |  | 7928572.1 |  |  | Completed | 1
40553 | NC 2020 | K10 | Region X | Bukidnon | 126418 | FORCHACU III ES | KALILANGAN | 4 | 1 | 3 | 1STY3CL |  | 8229868.85 |  |  | Completed | 1
40554 | NC 2020 | SHS | Region X | Cagayan de Oro City | 304117 | Iponan National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 4 | 2STY4CL |  | 12531250 |  |  | Completed | 1
40555 | NC 2020 | K10 | Region X | Cagayan de Oro City | 127942 | East City Central School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 2STY4CL |  | 15037500 |  |  | Completed | 1
40556 | NC 2020 | K10 | Region X | Camiguin | 126935 | Sagay Central School | SAGAY | 0 | 1 | 4 | 1STY4CL |  | 10025000 |  |  | Completed | 1
40557 | NC 2020 | TVL | Region X | Camiguin | 315003 | Mahinog National High School II | MAHINOG | 0 | 1 | 1 | UNIQE WORKSHOP |  | 5012500 |  |  | Completed | 1
40558 | NC 2020 | K10 | Region X | El Salvador | 304787 | El Salvador City National High School | CITY OF EL SALVADOR | 2 | 1 | 4 | 2STY4CL |  | 12180375 |  |  | Completed | 1
40559 | NC 2020 | K10 | Region X | Gingoog City | 128045 | Talisay Elementary School | GINGOOG CITY | 1 | 1 | 4 | 2STY4CL |  | 12835269.84 |  |  | Completed | 1
40560 | NC 2020 | K10 | Region X | Gingoog City | 501024 | Sangalan Integrated School | Ginggoog City | 1 | 1 | 6 | 2STY6CL |  | 20911448.25 |  |  | Completed | 1
40561 | NC 2020 | K10 | Region X | Iligan City | 128093 | Echavez ES | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL |  | 12792902.5 |  |  | Completed | 1
40562 | NC 2020 | K10 | Region X | Iligan City | 128156 | SUAREZ CENTRAL SCHOOL | ILIGAN CITY | 0 | 1 | 8 | 2STY8CL |  | 20399238.92 |  |  | Completed | 1
40563 | NC 2020 | SHS | Region X | Iligan City | 500698 | Del Carmen Integrated School | ILIGAN CITY | 0 | 1 | 4 | 2STY4CL |  | 12983377.5 |  |  | Completed | 1
40564 | NC 2020 | K10 | Region X | Lanao del Norte | 127239 | Pigcarangan Integrated School | TUBOD (Capital) | 1 | 1 | 6 | 2STY6CL |  | 17543750 |  |  | Completed | 1 | 2021-04-16 | [8 empty] | MATROSON Builders & Engineering Services
40565 | NC 2020 | SHS | Region X | Lanao del Norte | 304013 | Diego H. Patigayon NHS (Mukas NHS) | KOLAMBUGAN | 1 | 1 | 6 | 2STY6CL |  | 17744250 |  |  | Completed | 1 | [9 empty] | MATROSON Builders & Engineering Services
40566 | NC 2020 | SHS | Region X | Lanao del Norte | 500249 | Carusa Integrated School | KAPATAGAN | 2 | 1 | 6 | 3STY6CL |  | 19595321.8 |  |  | Completed | 1 | 2021-02-05 | [7 empty] | 2020-09-09 | AJD Construction & Supply
40567 | NC 2020 | K10 | Region X | Lanao del Norte | 501240 | Calube Integrated School | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 4 | 1STY4CL |  | 11380341.34 |  |  | Completed | 1 | 2020-12-07 | [7 empty] | 2020-08-25 | Al-Modhel Construction & Engineering | Punch listed
40568 | NC 2020 | K10 | Region X | Malaybalay City | 126591 | San Jose ES | CITY MALAYBALAY (Capital) | 2 | 1 | 6 | 3STY6CL |  | 16842000 |  |  | Completed | 1 | 2022-09-30 |  | 20KA0095 | [6 empty] | ZDA Construction
40569 | NC 2020 | TVL | Region X | Malaybalay City | 314916 | Malaybalay City NHS | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL (SCIENCE ROOM) |  | 5162875 |  |  | Completed | 1 | 2020-11-21 |  | 20KA0096 | [6 empty] | MMG Builders
40570 | NC 2020 | SHS | Region X | Malaybalay City | 325505 | Apo Macote NHS | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | 1STY2CL |  | 5563875 |  |  | Completed | 1 | 2020-11-21 |  | 20KA0097 | [6 empty] | Mafil Builders
40571 | NC 2020 | K10 | Region X | Misamis Occidental | 127426 | Mansabay Alto ES | LOPEZ JAENA | 1 | 1 | 4 | 1STY4CL WITH TOILET ATTACHED |  | 9542546.05 |  |  | Completed | 1
40572 | NC 2020 | K10 | Region X | Misamis Occidental | 127290 | Bonifacio CS | BONIFACIO | 2 | 1 | 10 | 2STY10CL |  | 37079769.12 |  |  | Completed | 1
40573 | NC 2020 | K10 | Region X | Misamis Occidental | 127342 | Lupagan Elementary School | CLARIN | 2 | 1 | 4 | 2STY4CL |  | 19628822.16 |  |  | Completed | 1
40574 | NC 2020 | K10 | Region X | Misamis Occidental | 127355 | Ozamiz ES | CLARIN | 2 | 1 | 2 | 1STY2CL |  | 6969649.33 |  |  | Completed | 1
40575 | NC 2020 | K10 | Region X | Misamis Occidental | 127562 | Camating ES | TUDELA | 2 | 1 | 3 | 1STY3CL |  | 10025000 |  |  | Completed | 1
40576 | NC 2020 | K10 | Region X | Misamis Oriental | 127604 | Binitinan ES | BALINGASAG | 1 | 1 | 12 | 3STY12CL |  | 42074925 |  |  | Completed | 1
40577 | NC 2020 | K10 | Region X | Misamis Oriental | 315322 | Damayuhan NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | 2 | 1STY2CL |  | 6395950 |  |  | Completed | 1
40578 | NC 2020 | SHS | Region X | Misamis Oriental | 500251 | Lantad IS | BALINGASAG | 1 | 1 | 4 | 2UNITS 1STY2CL |  | 11829500 |  |  | Completed | 1
40579 | NC 2020 | K10 | Region X | Misamis Oriental | 501038 | Maribojoc Integrated School | TAGOLOAN | 2 | 1 | 4 | 2STY4CL |  | 12180375 |  |  | Completed | 1
40580 | NC 2020 | K10 | Region X | Misamis Oriental | 501158 | Tuod Integrated School | MANTICAO | 2 | 1 | 4 | 2STY4CL |  | 12180375 |  |  | Completed | 1
40581 | NC 2020 | K10 | Region X | Misamis Oriental | 501161 | Luna Integrated School | CLAVERIA | 2 | 1 | 4 | 2STY4CL |  | 12180375 |  |  | Completed | 1
40582 | NC 2020 | K10 | Region X | Oroquieta City | 127458 | Poblacion 2 ES | OROQUIETA CITY (Capital) | 1 | 1 | 6 | 2STY6CL |  | 17708476.97 |  |  | Completed | 1 | 2021-02-20 |  | 20KI0092 | NO DATA GIVEN | [5 empty] | LEXAND CONST. AND DEV | DPWH (DELAY PROJECTS WORKS HIGHWAY)
40583 | NC 2020 | K10 | Region X | Ozamis City | 500701 | Misamis Annex Integrated School | OZAMIS CITY | 2 | 1 | 9 | 3STY9CL |  | 41922736.17 |  |  | Completed | 1
40584 | NC 2020 | K10 | Region X | Valencia City | 126875 | Mabuhay Elementary School | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL |  | 7518750 |  |  | Completed | 1 | 2020-12-06 |  | 20KA0092 | 20KA0092 | [5 empty] | XY Builders
40585 | NC 2020 | SHS | Region X | Valencia City | 500703 | Dagat-Kidavao IS | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL |  | 7518750 |  |  | Completed | 1 | 2020-12-06 |  | 20KA0098 | 20KA0098 | [5 empty] | Mafil Builders
40586 | NC 2020 | SHS | Region X | Valencia City | 500705 | Mt. Nebo ES | CITY OF VALENCIA | 4 | 1 | 3 | 1STY3CL |  | 7518750 |  |  | Completed | 1 | 2020-12-06 |  | 20KA0099 | 20KA0099 | [5 empty] | KEZ Enterprises
41518 | NC 2021 | K10 | Region X | Cagayan de Oro City | 127963 | Kauswagan Central School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 9 | Construction/Completion (3STY9CL) |  | 1566599.6423 | 1562692.91 |  | COMPLETED | 1
41519 | NC 2021 | K10 | Region X | Cagayan de Oro City | 315411 | Kauswagan National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 141715.1744 | 141361.77 |  | COMPLETED | 1
41520 | NC 2021 | TVL | Region X | Gingoog City | 304130 | Gingoog City CNHS | GINGOOG CITY | 1 | 1 | 8 | Construction/Completion (4STY 8 LABORATORIES) |  | 5011139.6977 | 4998643.09 |  | COMPLETED | 1
41521 | NC 2021 | TVL | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2 | 1 | 8 | Construction/Completion (4STY 8 REGULAR WORKSHOP) |  | 2957375 | 2950000 |  | COMPLETED | 1
41522 | NC 2021 | K10 | Region X | Malaybalay City | 300507 | Luyungan High School | CITY MALAYBALAY (Capital) | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 16464955.1585 | 16423895.42 |  | COMPLETED | 1 | 2022-09-30 | [9 empty] | punchlist works ongoing
41523 | NC 2021 | TVL | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1 | 1 | 12 | Construction/Completion (3STY12CL (Science Lab, ICT Lab, Regular Workshop)) |  | 751875 | 750000 |  | COMPLETED | 1
41524 | NC 2021 | TVL | Region X | Misamis Occidental | 304030 | Calamba CNHS | CALAMBA | 1 | 1 | 12 | Construction/Completion (3STY12CL (Science Lab, ICT Lab, Regular Workshop)) |  | 751875 | 750000 |  | COMPLETED | 1
41525 | NC 2021 | K10 | Region X | Misamis Occidental | 304030 | Calamba CNHS | CALAMBA | 1 |  | 16 | Construction/Completion (4STY616CL) |  | 751875 | 750000 |  | COMPLETED | 1
41526 | NC 2021 | TVL | Region X | Misamis Occidental | 304033 | Concepcion NHS | CONCEPCION | 1 | 1 | 6 | Construction/Completion (2STY6CL (Science Lab, ICT Lab, Regular Classrooms)) |  | 751875 | 750000 |  | COMPLETED | 1
41527 | NC 2021 | K10 | Region X | Ozamis City | 128165 | Bacolod Elementary School | OZAMIS CITY | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 5633106.1663 | 5619058.52 |  | COMPLETED | 1
41528 | NC 2021 | K10 | Region X | Tangub City | 128227 | Maloro ES | TANGUB CITY | 2 | 1 | 9 | Construction/Completion (3STY9CL) |  | 1089557.6514 | 1086840.55 |  | COMPLETED | 1 | 2022-09-30 | [9 empty] | on-going rectification of punchlist
41529 | NC 2021 | K10 | Region X | Tangub City | 128227 | Maloro ES | TANGUB CITY | 2 |  | 4 | Construction/Completion (2STY4CL) |  | 1128410.3008 | 1125596.31 |  | COMPLETED | 1 | 2022-09-30 | [9 empty] | on-going rectification of punchlist
41530 | NC 2021 | K10 | Region X | Tangub City | 128237 | Villaba ES | TANGUB CITY | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 4133108.9048 | 4122801.9 |  | COMPLETED | 1 | 2022-09-30 | [9 empty] | on-going rectification of punchlist
41531 | NC 2021 | K10 | Region X | Tangub City | 128256 | Simasay ES | TANGUB CITY | 2 | 1 | 5 | Construction/Completion (1STY5CL W/ TOILET) |  | 551793.9748 | 550417.93 |  | COMPLETED | 1 | 2022-09-30 | [9 empty] | on-going rectification of punchlist
41532 | NC 2021 | SHS | Region X | Tangub City | 304053 | Silangit NHS | TANGUB CITY | 2 | 1 | 2 | Construction/Completion (TWO (2) REGULAR WORKSHOP (2STY4CL)) |  | 771956.6088 | 770031.53 |  | COMPLETED | 1 | 2022-09-30 | [9 empty] | on-going rectification of punchlist
41533 | NC 2021 | SHS | Region X | Tangub City | 304056 | Sumirap NHS | TANGUB CITY | 2 | 1 | 6 | Construction/Completion (SIX (6) REGULAR WORKSHOP (2STY12CL)) |  | 9020737.6551 | 8998242.05 |  | COMPLETED | 1
41763 | NC 2022 | K10 | Region X | Bukidnon | 126280 | San Vicente ES | BAUNGON | 1 | 1 | 3 | 1STY3CL | 2 |  | 8521250 |  | Completed | 1
41764 | NC 2022 | K10 | Region X | Camiguin | 126884 | Bura Elementary School | CATARMAN | 0 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | 2023-10-27
41765 | NC 2022 | K10 | Region X | Camiguin | 126929 | Cabuan es | GUINSILIBAN | 0 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | [10 empty] | Completed as per contract and for Final Inspection
41766 | NC 2022 | K10 | Region X | Camiguin | 126901 | Pontod Elementary School | MAHINOG | 0 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | [10 empty] | Still ongoing
41767 | NC 2022 | K10 | Region X | Camiguin | 126935 | Sagay Central School | SAGAY | 0 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | [10 empty] | Waiting for compliance of punchlisted items
41768 | NC 2022 | K10 | Region X | Lanao del Norte | 127095 | Linamon Central School | LINAMON | 1 | 1 | 6 | 2STY6CL | 2 |  | 17804400 | 17218117.6 | Completed | 1 | 2023-12-18 |  | P00675014MN-CW1 | 22KF0113 | 2022-12-14 | 2023-01-03 | 2023-01-03 | 2023-04-03 | 2023-04-14 | AL-AMEN BUILDERS
41769 | NC 2022 | K10 | Region X | Lanao del Norte | 127136 | Sultan Macalpang Permites CS (Matungao CES) | MATUNGAO | 1 | 1 | 4 | 2STY4CL | 2 |  | 12664755.4713 |  | Completed | 1 | [10 empty] | Punchlist works
41770 | NC 2022 | K10 | Region X | Misamis Occidental | 127527 | Masubong Primary School | SAPANG DALAGA | 1 | 1 | 2 | 1STY2CL WITH TOILET ATTACHED | 2 |  | 6077278.0769 |  | Completed | 1 | [10 empty] | Completed
41771 | NC 2022 | K10 | Region X | Misamis Occidental | 501875 | Libertad Bajo Integrated School | SINACABAN | 2 | 1 | 3 | 1STY3CL WITH TOILET ATTACHED | 2 |  | 9110651.6395 |  | Completed | 1 | [10 empty] | Completed
41772 | NC 2022 | K10 | Region X | Misamis Occidental | 501875 | Libertad Bajo Integrated School | SINACABAN | 2 |  | 3 | 1STY3CL WITH TOILET ATTACHED | 2 |  | 9922936.0163 |  | Completed | 1 | [10 empty] | Completed
41773 | NC 2022 | K10 | Region X | Misamis Oriental | 127875 | Balingoan CS | BALINGOAN | 1 | 1 | 4 | 2STY4CL | 2 |  | 11528750 |  | Completed | 1 | 2023-09-15 | [9 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
41774 | NC 2022 | K10 | Region X | Misamis Oriental | 127744 | Kabulawan ES | LAGONGLONG | 1 | 1 | 4 | 2STY4CL | 2 |  | 11528750 |  | Completed | 1 | 2023-09-15
41775 | NC 2022 | K10 | Region X | Misamis Oriental | 127738 | Sugbongcogon CS | SUGBONGCOGON | 1 | 1 | 4 | 2STY4CL | 2 |  | 11528750 |  | Completed | 1 | 2023-09-15
41776 | NC 2022 | K10 | Region X | Misamis Oriental | 127760 | Libertad CS | LIBERTAD | 2 | 1 | 4 | 2STY4CL | 2 |  | 11528750 |  | Completed | 1 | 2023-09-15
41834 | NC 2022 | SHS | Region X | El Salvador | 304787 | El Salvador City National High School | CITY OF EL SALVADOR | 2 | 1 | 4 | 2STY4CL | 2 |  | 10025000 |  | Completed | 1 | 2023-05-22
41835 | NC 2022 | SHS | Region X | Lanao del Norte | 315110 | SERGIO P. CERUJALES, JR. NHS | MAGSAYSAY | 2 | 1 | 4 | 2STY4CL | 2 |  | 12918814.6253 |  | Completed | 1 | [10 empty] | Punchlist works
41836 | NC 2022 | SHS | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL | 2 | 1 | 4 | 2STY4CL | 2 |  | 12755376.92 |  | Completed | 1 | [10 empty] | Still ongoing
42841 | NC 2023 | K10 | Region X | Bukidnon | 126279 | San Miguel ELEMENTARY SCHOOL | BAUNGON |  | 1 | 2 |  | Batch 1 | 6254250 | 6200000 | 6071195.32 | Completed | 1 | 2023-11-03 | 2023-11-03 | P00775465 | 23KC0132 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-26 | 2023-08-10 | 4G and P Construction | Completed
42842 | NC 2023 | K10 | Region X | Bukidnon | 126622 | Camp 1 ES | MANOLO FORTICH |  | 1 | 6 |  | Batch 1 | 17350500 | 17200000 | 16851921.76 | Completed | 1 | 2024-02-08 | 2024-02-08 | P00775466 | 23KC0133 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-08-18 | 2023-09-22 | Pyramid Consolidated | Completed
42843 | NC 2023 | K10 | Region X | Bukidnon | 126815 | Megbadiang ES | TALAKAG |  | 1 | 2 |  | Batch 1 | 6657750 | 6600000 | 6504443.75 | Ongoing | 0.95 | 2024-02-08 |  | P00775467 | 23KC0134 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-26 | 2023-08-10 | 4G and P Construction | For Final Inspection
42844 | NC 2023 | K10 | Region X | Bukidnon | 126336 | Osmena Elementary School | DANGCAGAN |  | 1 | 3 |  | Batch 1 | 9583125 | 9500000 | 9396962.03 | Completed | 1 | 2023-11-24 | 2023-11-24 |  | 23KB0161 | 2023-06-09 | 2023-06-16 | 2023-07-11 | 2023-07-24 | 2023-08-18 | Mafil Builders, Inc. | Completed
42845 | NC 2023 | K10 | Region X | Bukidnon | 126447 | Natulongan CS | KIBAWE |  | 1 | 2 |  | Batch 1 | 6758625 | 6700000 | 6661009.18 | Completed | 1 | 2023-08-24 | 2023-08-24 |  | 23KB0162 | 2023-06-09 | 2023-06-16 | 2023-07-11 | 2023-07-24 | 2023-08-18 | Petrina Construction and General Merchandising | Completed
42846 | NC 2023 | K10 | Region X | Bukidnon | 126662 | Kuya ES | MARAMAG |  | 1 | 2 |  | Batch 1 | 6960375 | 6900000 | 6753621.77 | Completed | 1 | 2023-11-17 | 2023-11-17 |  | 23KB0160 | 2023-06-09 | 2023-07-11 | 2023-07-27 | 2023-08-01 | 2023-08-24 | Sta. Ana Raycon Corporation | Completed
42847 | NC 2023 | K10 | Region X | Bukidnon | 126675 | Tubigon ES | MARAMAG |  | 1 | 2 |  | Batch 1 | 6960375 | 6900000 | 6868074.89 | Completed | 1 | 2023-08-30 | 2023-08-30 |  | 23KB0163 | 2023-06-29 | 2023-07-11 | 2023-07-27 | 2023-08-01 | 2023-08-24 | Cagalawan Enterprises | Completed
42848 | NC 2023 | K10 | Region X | Cagayan de Oro City | 128001 | Canitoan Elementary School | CAGAYAN DE ORO CITY (Capital) |  | 1 | 6 |  | Batch 1 | 16346916.47 | 16205121.65 | 16205121.65 | Completed | 1 | 2023-11-18 | 2024-04-16 | P00775472MN-CW1 | 23KH0067 | 2023-06-21 | 2023-07-29 | 2023-07-18 | 2023-07-27 | 2023-07-27 | Cagalawan Enterprises
42849 | NC 2023 | SHS | Region X | Cagayan de Oro City | 304117 | Iponan National High School | CAGAYAN DE ORO CITY (Capital) |  | 1 | 8 |  | Batch 1 | 20956065.73 | 20774290.69 | 20774290.69 | Completed | 1 | 2023-12-18 | 2024-06-13 | P00775473MN-CW1 | 23KH0068 | 2023-06-21 | 2023-07-29 | 2023-07-18 | 2023-07-27 | 2023-07-27 | Cagalawan Enterprises
42850 | NC 2023 | SHS | Region X | Cagayan de Oro City | 304119 | Lumbia National High School | CAGAYAN DE ORO CITY (Capital) |  | 1 | 12 |  | Batch 3 | 42000000 | 40530000 | 39878320 | Ongoing | 0.3 | 2025-10-10 |  | P00772768MN-CW1 | 24540100 | 2024-06-06 | 2024-06-13 | 2024-06-25 | 2024-07-11 | 2024-07-22 | Cagalawan Enterprises | Preparing for pouring of concrete at 2nd flr. level
42851 | NC 2023 | SHS | Region X | Cagayan de Oro City | 304114 | Gusa Regional Science High School-X | CAGAYAN DE ORO CITY (Capital) |  | 1 | 6 |  | Batch 1 | 18422474.39 | 18262675.97 | 18422474.32 | Ongoing | 0.96 | 2024-01-07 |  | P00775475MN-CW1 | 23KD0058 | 2023-07-05 | 2023-07-19 | 2023-08-07 | 2023-08-14 | 2023-08-14 | 5S Development Corporation
42852 | NC 2023 | K10 | Region X | Cagayan de Oro City | 127967 | South City Central School | CAGAYAN DE ORO CITY (Capital) |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 | 11451808.4 | Ongoing | 0.98 | 2023-12-04 |  | P00775474MN-CW1 | 23KD0057 | 2023-07-05 | 2023-07-19 | 2023-08-07 | 2023-08-14 | 2023-08-14 | Four L Builders and Construction Supply
42853 | NC 2023 | K10 | Region X | Camiguin | 126889 | Mainit ES | CATARMAN |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9834730.35 | Completed | 1 |  |  | 23KE0069 | No data available | 2023-06-16 |  | 2023-07-18 | 2023-08-07 |  | Sheen-Sheen Construction Corporation | Incomplete Building. Completed as per contract. Needs addditional funds.
42854 | NC 2023 | K10 | Region X | Camiguin | 126890 | Manduao ES | CATARMAN |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4946883.03 | Completed | 1 |  |  | 23KE0070 | No data available | 2023-06-16 |  | 2023-07-18 | 2023-08-07 | 2023-08-17 | Janrhyll Construction | Incomplete Building. Completed as per contract. Needs addditional funds.
42855 | NC 2023 | K10 | Region X | Camiguin | 126897 | Mahinog Central School | MAHINOG |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4899688.61 | Completed | 1 |  |  | 23KE0071 | No data available | 2023-06-16 |  | 2023-07-18 | 2023-08-07 | 2023-08-14 | CLC Construction Services and Supplu | Incomplete Building. Completed as per contract. Needs addditional funds.
42856 | NC 2023 | SHS | Region X | Camiguin | 303993 | Sixto A. Abao NHS | MAHINOG |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4948900.04 | Completed | 1 |  |  | 23KE0072 | No data available | 2023-06-16 |  | 2023-07-18 | 2023-08-07 | 2023-08-17 | Janrhyll Construction | Incomplete Building. Completed as per contract. Needs addditional funds.
42857 | NC 2023 | K10 | Region X | Camiguin | 126916 | Naasag ES | MAMBAJAO (Capital) |  | 1 | 5 |  | Batch 1 | 14122500 | 14000000 | 13855872.14 | Completed | 1 |  |  | 23KE0073 | No data available | 2023-06-16 |  | 2023-07-18 | 2023-08-07 | 2023-08-17 | Janrhyll Construction | Complete Building.
42858 | NC 2023 | K10 | Region X | Camiguin | 126918 | Quiboro ES | MAMBAJAO (Capital) |  | 1 | 3 |  | Batch 1 | 11096250 | 11000000 | 10874759.39 | Completed | 1 |  |  | 23KE0074 | No data available | 2023-06-16 |  | 2023-07-18 | 2023-08-07 |  | Ss Construction and Supply | Complete Building.
42859 | NC 2023 | K10 | Region X | Camiguin | 500683 | Alangilan Integrated School | SAGAY |  | 1 | 8 |  | Batch 1 | 20175000 | 20000000 | 19601281.98 | Completed | 1 |  |  | 23KE0075 | No data available | 2023-06-16 |  | 2023-07-18 | 2023-08-07 | 2023-08-14 | CLC Construction Services and Supplu | Incomplete Building. Completed as per contract. Needs addditional funds.
42860 | NC 2023 | K10 | Region X | Gingoog City | 500811 | Pedro Maligmat Integrated School - Elem | GINGOOG CITY |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 |  | Completed | 1
42861 | NC 2023 | K10 | Region X | Iligan City | 128086 | Miguel Obach MES | ILIGAN CITY |  | 1 | 4 |  | Batch 1 | 12942262.5 | 12830000 | 12830000 | Completed | 1 |  |  | 23KM0058 | 23KM0058 | 2023-05-27 | 2023-06-05 | 2023-06-21 |  | 2023-07-17 | Silver Construction
42862 | NC 2023 | K10 | Region X | Iligan City | 128146 | Tipanoy ES | ILIGAN CITY |  | 1 | 4 |  | Batch 1 | 12942262.5 | 12830000 | 12830000 | Completed | 1 |  |  | 23KM0057 | 23KM0057 | 2023-05-27 | 2023-06-05 | 2023-06-19 |  | 2023-07-17 | Silver Construction
42863 | NC 2023 | K10 | Region X | Lanao del Norte | 501369 | Bacolod Central Integrated School | BACOLOD |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 | 29100006.87 | Completed | 1 | 2024-04-17 | 2024-04-17 | P00775486MN-CW1 | 23KG0072 | 2023-06-20 | 2023-07-24 | 2023-07-24 | 2023-08-22 | 2023-08-29 | MATROSON BUILDERS & ENGINEERING SERVICES | Completed
42864 | NC 2023 | K10 | Region X | Lanao del Norte | 127039 | Cayontor PS | KAUSWAGAN |  | 1 | 2 |  | Batch 1 | 7160515.37 | 7098404.33 | 6844699.42 | Completed | 1 | 2024-01-04 | 2024-01-04 | P00775487MN-CW1 | 23KG0064 | 2023-06-17 | 2023-07-17 | 2023-07-17 | 2023-08-22 | 2023-08-29 | MOYA CONSTRUCTION | Completed
42865 | NC 2023 | K10 | Region X | Lanao del Norte | 502082 | Sultan Dimasangcay Mananggolo Integrated School | KAUSWAGAN |  | 1 | 28 |  | Batch 1 | 119628791.69 | 41073947.31 | 16529975.05 | Completed | 1 | 2024-02-26 | 2024-02-26 | P00775492MN-CW1 | 23KG0068 | 2023-06-17 | 2023-07-17 | 2023-07-17 | 2023-08-22 | 2023-08-29 | DUE EAST CONSTRUCTION AND EQUIPMENTS INC., LANAO BUILDERS AND ENTERPRISES, AND NDP CONSTRUCTION & DEVELOPMENT | Completed
42866 | NC 2023 | K10 | Region X | Lanao del Norte | 127049 | Tingintingin PS | KAUSWAGAN |  | 1 | 2 |  | Batch 1 | 7122642.69 | 7060860.16 | 6842930.86 | Completed | 1 |  |  | P00775488MN-CW1 | 23KG0059 | 2023-06-17 | 2023-07-17 | 2023-07-17 | 2023-08-22 | 2023-08-29 | TESAR BUILDERS
42867 | NC 2023 | K10 | Region X | Lanao del Norte | 200529 | Upper Tugar PS | KAUSWAGAN |  | 1 | 2 |  | Batch 1 | 7139963.09 | 7078030.32 | 6826484.15 | Completed | 1 | 2024-01-09 | 2024-01-09 | P00775489MN-CW1 | 23KG0061 | 2023-06-17 | 2023-07-17 | 2023-07-17 | 2023-08-22 | 2023-08-29 | NDP CONSTRUCTION DEVELOPMENT
42868 | NC 2023 | K10 | Region X | Lanao del Norte | 127093 | Bosque Elementary School | LINAMON |  | 1 | 6 |  | Batch 1 | 27621203.29 | 27381614.16 | 26523350.4 | Completed | 1 | 2024-03-31 | 2024-03-31 | P00775493MN-CW1 | 23KG0069 | 2023-06-20 | 2023-07-24 | 2023-07-24 | 2023-08-22 | 2023-08-29 | NDP CONSTRUCTION DEVELOPMENT
42869 | NC 2023 | K10 | Region X | Lanao del Norte | 127126 | Batal ES | MATUNGAO |  | 1 | 2 |  | Batch 1 | 7215505.68 | 7152917.65 | 7009077.8 | Completed | 1 | 2024-01-09 | 2024-01-09 | P00775494MN-CW1 | 23KG0060 | 2023-06-17 | 2023-07-17 | 2023-07-17 | 2023-08-22 | 2023-08-29 | MEGALINE BUILDERS AND SUPPLY
42870 | NC 2023 | K10 | Region X | Lanao del Norte | 200508 | Bubong Radapan P S | MATUNGAO |  | 1 | 2 |  | Batch 1 | 7293606.77 | 7230341.28 | 7085582.56 | Completed | 1 | 2024-01-26 | 2024-01-26 | P00775495MN-CW1 | 23KG0063 | 2023-06-17 | 2023-07-17 | 2023-07-17 | 2023-09-04 |  | MEGALINE BUILDERS AND SUPPLY
42871 | NC 2023 | K10 | Region X | Lanao del Norte | 127136 | Sultan Macalpang Permites CS (Matungao CES) | MATUNGAO |  | 1 | 4 |  | Batch 2 | 2475397.64 | 2391688.54 |  | Completed | 1
42872 | NC 2023 | K10 | Region X | Lanao del Norte | 127159 | Bowi PS | PANTAR |  | 1 | 3 |  | Batch 1 | 10683443.66 | 10590774.38 | 10532794.51 | Completed | 1 | 2024-01-14 | 2024-01-14 | P00775496MN-CW1 | 23KG0065 | 2023-06-17 | 2023-07-17 | 2023-07-17 | 2023-08-22 | 2023-08-29 | AL-NOORWAY CORPORATION
42873 | NC 2023 | K10 | Region X | Lanao del Norte | 127161 | Cabasaran ES | PANTAR |  | 1 | 4 |  | Batch 1 | 17260904.79 | 17111181.95 | 16250802.76 | Completed | 1 | 2024-03-14 | 2024-03-14 | P00775497MN-CW1 | 23KG0075 | 2023-06-20 | 2023-07-24 | 2023-07-24 | 2023-09-05 |  | AL-NOORWAY CORPORATION
42874 | NC 2023 | K10 | Region X | Lanao del Norte | 127172 | Tambo-Cadayonan ES | PANTAR |  | 1 | 6 |  | Batch 1 | 28034628.03 | 27791452.82 | 26389377.55 | Completed | 1 | 2024-04-22 | 2024-04-22 | P00775498MN-CW1 | 23KG0074 | 2023-06-20 | 2023-07-24 | 2023-07-24 | 2023-09-04 |  | AL-NOORWAY CORPORATION
42875 | NC 2023 | K10 | Region X | Lanao del Norte | 127211 | CABASARAN PS | TAGOLOAN |  | 1 | 4 |  | Batch 1 | 17206357.69 | 17057107.99 | 16530893.34 | Completed | 1 | 2024-02-21 | 2024-02-21 | P00775499MN-CW1 | 23KG0076 | 2023-06-20 | 2023-07-24 | 2023-07-24 | 2023-08-22 | 2023-08-29 | NDP CONSTRUCTION DEVELOPMENT
42876 | NC 2023 | K10 | Region X | Lanao del Norte | 127213 | Gadongan PS | TAGOLOAN |  | 1 | 2 |  | Batch 1 | 7106830.05 | 7045184.68 | 6829290.95 | Completed | 1 | 2024-01-04 | 2024-01-04 | P00775500MN-CW1 | 23KG0062 | 2023-06-17 | 2023-07-17 | 2023-07-17 | 2023-08-22 | 2023-08-29 | TESAR BUILDERS
42877 | NC 2023 | K10 | Region X | Lanao del Norte | 501395 | Kiasar Integrated School | TAGOLOAN |  | 1 | 6 |  | Batch 1 | 27529464.6 | 27290671.23 | 26468884.54 | Completed | 1 | 2024-03-21 | 2024-03-21 | P00775503MN-CW1 | 23KG0070 | 2023-06-20 | 2023-07-17 | 2023-07-17 | 2023-08-22 | 2023-08-29 | AJJ STRUCTURE BUILDERS INC
42878 | NC 2023 | K10 | Region X | Lanao del Norte | 501394 | Tagoloan Integrated School | TAGOLOAN |  | 1 | 12 |  | Batch 1 | 54982018.12 | 27252549.25 | 26198362.84 | Completed | 1 | 2024-03-21 | 2024-03-21 | P00775501MN-CW1 | 23KG0071 | 2023-06-20 | 2023-07-24 | 2023-07-24 | 2023-08-22 | 2023-08-29 | AL-NOORWAY CORPORATION
42879 | NC 2023 | K10 | Region X | Lanao del Norte | 501433 | Tumple Integrated School | TAGOLOAN |  | 1 | 6 |  | Batch 1 | 21135398.91 | 10469274.91 | 20465815.86 | Completed | 1 | 2024-01-11 | 2024-01-11 | P00775504MN-CW1 & P00775505MN-CW1 | 23KG0066 & 23KG0067 | 2023-06-17 | 2023-07-17 | 2023-07-17 | 2023-08-22 | 2023-08-29 | AL-NOORWAY CORPORATION, AND NJS CONSTRUCTION & SERVICES
42880 | NC 2023 | K10 | Region X | Lanao del Norte | 500689 | Lala Proper ES | LALA |  | 1 | 4 |  | Batch 1 | 17663249.9 | 17510037.07 | 16886095.19 | Completed | 1 | 2024-01-16 | 2024-01-16 | P00775506MN-CW1 | 23KF0133 | 2023-07-05 | 2023-07-04 | 2023-07-24 | 2023-08-29 |  | MATROSON BUILDERS & ENGINEERING SERVICES
42881 | NC 2023 | K10 | Region X | Lanao del Norte | 127104 | Abucay -Cancamo ES (Olango ES) | MAGSAYSAY |  | 1 | 2 |  | Batch 1 | 7565625 | 7500000 | 7194052.9 | Completed | 1 |  |  | P00775508MN-CW1 | 23KF0131 | 2023-08-03 | 2023-07-04 | 2023-08-22 | 2023-09-07 |  | H & W CONSTRUCTION SERVICES
42882 | NC 2023 | K10 | Region X | Lanao del Norte | 127101 | Durianon Primary School | MAGSAYSAY |  | 1 | 2 |  | Batch 1 | 7565625 | 7500000 | 7197565.93 | Completed | 1 |  |  | P00775507MN-CW1 | 23KF0130 | 2023-07-05 | 2023-07-04 | 2023-07-24 | 2023-08-22 |  | AHM BUILDERS
42883 | NC 2023 | K10 | Region X | Lanao del Norte | 315110 | SERGIO P. CERUJALES, JR. NHS | MAGSAYSAY |  | 1 | 4 |  | Batch 2 | 3740357.9 | 3613872.37 |  | Completed | 1
42884 | NC 2023 | K10 | Region X | Lanao del Norte | 501378 | Shiek Omar Integrated School | MAGSAYSAY |  | 1 | 4 |  | Batch 1 | 17774175 | 17620000 | 16999513.15 | Completed | 1 | 2024-01-12 | 2024-01-12 | P00775510MN-CW1 | 23KF0134 | 2023-07-05 | 2023-07-04 | 2023-07-24 | 2023-08-22 |  | AHM BUILDERS
42885 | NC 2023 | K10 | Region X | Lanao del Norte | 500431 | Tambacon Integrated School | MAGSAYSAY |  | 1 | 4 |  | Batch 1 | 17552250 | 17400000 | 17098871.24 | Completed | 1 | 2024-02-07 | 2024-02-07 | P00775509MN-CW1 | 23KF0129 | 2023-07-05 | 2023-07-04 | 2023-07-24 |  | 2023-10-05 | LANAO BUILDERS AND ENTERPRISES
42886 | NC 2023 | K10 | Region X | Lanao del Norte | 127174 | Barandia PS | SALVADOR |  | 1 | 2 |  | Batch 1 | 7565625 | 7500000 | 7163387.58 | Completed | 1 | 2024-01-08 | 2024-01-08 | P00775511MN-CW1 | 23KF0145 | 2023-07-18 | 2023-07-12 | 2023-08-07 |  | 2023-10-05 | AL-NOORWAY CORPORATION
42887 | NC 2023 | K10 | Region X | Lanao del Norte | 127175 | Bulacon PS | SALVADOR |  | 1 | 2 |  | Batch 1 | 7565625 | 7500000 | 7178620.98 | Completed | 1 |  |  | P00775512MN-CW1 | 23KF0146 | 2023-07-18 | 2023-07-12 | 2023-08-07 | 2023-08-30 |  | AL-NOORWAY CORPORATION
42888 | NC 2023 | K10 | Region X | Lanao del Norte | 137089 | Pangantapan Primary School | SALVADOR |  | 1 | 2 |  | Batch 1 | 7565625 | 7500000 | 7163985.84 | Completed | 1 |  |  | P00775514MN-CW1 | 23KF0138 | 2023-07-11 | 2023-07-07 | 2023-07-31 | 2023-08-30 |  | AL-NOORWAY CORPORATION
42889 | NC 2023 | K10 | Region X | Lanao del Norte | 200505 | Pansur PS | SALVADOR |  | 1 | 2 |  | Batch 1 | 7616062.5 | 7550000 | 7234993.02 | Completed | 1 |  |  | P00775515MN-CW1 | 23KF0137 | 2023-07-11 | 2023-07-07 | 2023-07-31 | 2023-08-30 |  | AL-NOORWAY CORPORATION
42890 | NC 2023 | K10 | Region X | Lanao del Norte | 127188 | Sudlon ES | SALVADOR |  | 1 | 6 |  | Batch 1 | 28345875 | 28100000 | 27185254.94 | Completed | 1 | 2024-02-19 | 2024-02-19 | P00775513MN-CW1 | 23KF0139 | 2023-07-05 | 2023-07-04 | 2023-07-24 |  | 2023-10-04 | AL FAHDEL CONSTRUCTION & ENGINEERING
42891 | NC 2023 | K10 | Region X | Lanao del Norte | 127190 | Baning Elem. School | SAPAD |  | 1 | 2 |  | Batch 1 | 7616062.5 | 7550000 | 7239136.52 | Completed | 1 |  |  | P00775516MN-CW1 | 23KF0143 | 2023-07-18 | 2023-07-12 | 2023-08-07 | 2023-08-24 |  | S & J BUILDERS
42892 | NC 2023 | SHS | Region X | Lanao del Norte | 304017 | Panoloon NHS | SAPAD |  | 1 | 2 |  | Batch 1 | 8170875 | 8100000 | 7704042.36 | Completed | 1 |  |  | P00775518MN-CW1 | 23KF0140 | 2023-07-11 | 2023-07-07 | 2023-07-31 | 2023-08-23 |  | SBM BUILDERS
42893 | NC 2023 | K10 | Region X | Lanao del Norte | 127210 | SAPAD ELEMENTARY SCHOOL | SAPAD |  | 1 | 2 |  | Batch 1 | 7565625 | 7500000 | 6453119.54 | Completed | 1 |  |  | P00775517MN-CW1 | 23KF0144 | 2023-07-18 | 2023-07-12 | 2023-08-07 | 2023-08-30 |  | AL-MAN CONSTRUCTION
42894 | NC 2023 | K10 | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) |  | 1 | 3 |  | Batch 1 | 11451291.1 | 11351961.44 | 10929100.53 | Completed | 1 |  |  | P00775519MN-CW1 | 23KF0132 | 2023-07-05 | 2023-07-04 | 2023-07-24 | 2023-08-22 |  | MOYA CONSTRUCTION
42895 | NC 2023 | K10 | Region X | Lanao del Norte | 136950 | BAYABAO PRIMARY SCHOOL | TANGCAL |  | 1 | 2 |  | Batch 1 | 7565625 | 7500000 | 7136532.66 | Completed | 1 |  |  | P00775521MN-CW1 | 23KF0142 | 2023-07-11 | 2023-07-07 | 2023-07-31 | 2023-08-22 |  | JIZAN BUILDERS
42896 | NC 2023 | K10 | Region X | Lanao del Norte | 501599 | Big Banisilon Integrated School | TANGCAL |  | 1 | 6 |  | Batch 1 | 28245000 | 28000000 | 26949069.14 | Completed | 1 | 2024-05-21 | 2024-05-21 | P00775522MN-CW1 | 23KF0153 |  | 2023-07-04 |  |  | 2024-01-04 | AL-HAYAT CONSTRUCTION
42897 | NC 2023 | K10 | Region X | Lanao del Norte | 501602 | Pelingkingan Integrated School | TANGCAL |  | 1 | 4 |  | Batch 1 | 17562337.5 | 17410000 | 16698847.01 | Completed | 1 | 2024-01-15 | 2025-05-25 | P00775523MN-CW1 | 23KF0136 | 2023-07-11 | 2023-07-07 | 2023-07-31 | 2023-08-22 |  | JIZAN BUILDERS
42898 | NC 2023 | K10 | Region X | Lanao del Norte | 136949 | SULTAN LINDONGAN PRIMARY SCHOOL | TANGCAL |  | 1 | 4 |  | Batch 1 | 17740886.25 | 17587000 | 16981216.85 | Completed | 1 | 2024-01-12 | 2024-01-12 | P00775520MN-CW1 | 23KF0135 | 2023-07-05 | 2023-07-04 | 2023-07-24 | 2023-08-22 |  | TESAR BUILDERS
42899 | NC 2023 | K10 | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL |  | 1 | 4 |  | Batch 2 | 4045444.55 | 3908642.08 |  | Completed | 1 | [10 empty] | for n/a, DPWH will provide the data ASAP
42900 | NC 2023 | K10 | Region X | Malaybalay City | 501195 | Candiisan Integrated School | CITY MALAYBALAY (Capital) |  | 1 | 2 |  | Batch 1 | 10087500 | 10000000 | 9893099.76 | Completed | 1 | 2023-12-11 |  | 23KA0176 | 23KA0176 |  |  |  |  | 2023-06-23 | Mafil Builders, Inc. | Ongoing variantion works and punchlist works with time extension
42901 | NC 2023 | K10 | Region X | Malaybalay City | 126590 | Patpat Elementary School | CITY MALAYBALAY (Capital) |  | 1 | 6 |  | Batch 1 | 20175000 | 20000000 | 19805764.79 | Completed | 1 | 2024-02-27 |  | 23KA0177 | 23KA0177 |  |  |  |  | 2023-06-23 | JT Gamolo Construction | Ongoing variantion works and punchlist works with time extension
42902 | NC 2023 | K10 | Region X | Misamis Occidental | 127395 | Malibacsan ELementary School | JIMENEZ |  | 1 | 2 |  | Batch 1 | 7061250 | 7000000 | No data available | Completed | 1 |  |  | No data available | No data available | [5 empty] | No data available | Completed, No data submitted
42903 | NC 2023 | K10 | Region X | Misamis Occidental | 501871 | Panalsalan Integrated School | PLARIDEL |  | 1 | 2 |  | Batch 1 | 7061250 | 7000000 | No data available | Completed | 1 |  |  | No data available | No data available | [5 empty] | No data available | Completed, No data submitted
42904 | NC 2023 | K10 | Region X | Misamis Occidental | 501874 | Manla Integrated School | SAPANG DALAGA |  | 1 | 6 |  | Batch 1 | 21969983 | 21779413.13 | No data available | Ongoing | 0.95 |  |  | No data available | No data available | [5 empty] | No data available | Completed, No data submitted
42905 | NC 2023 | K10 | Region X | Misamis Occidental | 127533 | Sapang Dalaga Central Elementary School | SAPANG DALAGA |  | 1 | 3 |  | Batch 1 | 9078750 | 9000000 | No data available | Completed | 1 |  |  | No data available | No data available | [5 empty] | No data available | Completed, No data submitted
42906 | NC 2023 | K10 | Region X | Misamis Occidental | 127339 | Dela Paz Elementary School | CLARIN |  | 1 | 2 |  | Batch 1 | 6818141.25 | 6759000 | 6556229.35 | Completed | 1 | 2023-12-25 | 2024-03-27 | P00775530MN-CW1 | 23KJ0092 |  | 2023-06-23 | 2023-07-05 | 2023-07-27 | 2023-08-07 | Abib Builders Enterprise | Completed
42907 | NC 2023 | K10 | Region X | Misamis Occidental | 127541 | Colupan Alto ES | SINACABAN |  | 1 | 4 |  | Batch 1 | 13275150 | 13160000 | 12765199.62 | Completed | 1 | 2024-01-29 | 2024-03-22 | P00775531MN-CW1 | 23KJ0099 |  | 2023-07-06 | 2023-07-18 | 2023-08-11 | 2023-08-22 | Abib Builders Enterprise | Completed
42908 | NC 2023 | K10 | Region X | Misamis Occidental | 127550 | San Isidro Bajo Primary School | SINACABAN |  | 1 | 3 |  | Batch 1 | 10169208.75 | 10081000 | 9778569.29 | Completed | 1 | 2024-01-09 | 2024-05-06 | P00775532MN-CW1 | 23KJ0094 |  | 2023-06-23 | 2023-07-05 | 2023-07-27 | 2023-08-07 | Abib Builders Enterprise | Completed
42909 | NC 2023 | K10 | Region X | Misamis Oriental | 500522 | Kabulakan IS | BALINGOAN |  | 1 | 6 |  | Batch 1 | 21321695.56 | 21136749 |  | Completed | 1 | 2024-01-28 | 2024-01-19 | P00775534MN-CW1 | 23KK0172 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42910 | NC 2023 | K10 | Region X | Misamis Oriental | 304085 | Mantangale NHS | BALINGOAN |  | 1 | 4 |  | Batch 1 | 16143719.63 | 16003687.36 |  | Completed | 1 | 2024-01-22 | 2024-01-18 | P00775533MN-CW1 | 23KK0174 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42911 | NC 2023 | SHS | Region X | Misamis Oriental | 304062 | Binuangan NHS | BINUANGAN |  | 1 | 2 |  | Batch 1 | 6130819.35 | 6077640 |  | Completed | 1 | 2023-12-08 | 2023-11-29 | P00775537MN-CW1 | 23KK0177 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42912 | NC 2023 | K10 | Region X | Misamis Oriental | 127722 | Dampias E.A. Rañises ES | BINUANGAN |  | 1 | 4 |  | Batch 1 | 16550364.04 | 16406804.5 |  | Completed | 1 | 2024-01-22 | 2024-01-15 | P00775545MN-CW1 | 23KK0173 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42913 | NC 2023 | K10 | Region X | Misamis Oriental | 127733 | Mosangot ES | BINUANGAN |  | 1 | 2 |  | Batch 1 | 6230396.09 | 6176353 |  | Completed | 1 | 2024-01-07 | 2024-07-01 | P00775536MN-CW1 | 23KK0180 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42914 | NC 2023 | K10 | Region X | Misamis Oriental | 500253 | Calubo IS | KINOGUITAN |  | 1 | 3 |  | Batch 1 | 11105305.04 | 11008976.49 |  | Completed | 1 | 2023-12-23 | 2023-12-18 | P00775541MN-CW1 | 23KK0191 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42915 | NC 2023 | K10 | Region X | Misamis Oriental | 304070 | Esperanza NHS | KINOGUITAN |  | 1 | 6 |  | Batch 1 | 21389629.36 | 21204093.54 |  | Completed | 1 | 2023-12-11 | 2023-07-12 | P00775540MN-CW1 | 23KK0175 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42916 | NC 2023 | K10 | Region X | Misamis Oriental | 127735 | Panabol ES | KINOGUITAN |  | 1 | 2 |  | Batch 1 | 6000813.67 | 5948762 |  | Completed | 1 | 2023-12-08 | 2023-11-28 | P00775538MN-CW1 | 23KK0181 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42917 | NC 2023 | K10 | Region X | Misamis Oriental | 127737 | Suarez ES | KINOGUITAN |  | 1 | 2 |  | Batch 1 | 6092446.5 | 6039600 |  | Completed | 1 | 2023-11-08 | 2023-08-11 | P00775539MN-CW1 | 23KK0182 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42918 | NC 2023 | K10 | Region X | Misamis Oriental | 127741 | C.Gadrinab ES | LAGONGLONG |  | 1 | 2 |  | Batch 1 | 6058134.88 | 6005586 |  | Completed | 1 | 2023-11-08 | 2023-08-11 | P00775542MN-CW1 | 23KK0178 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42919 | NC 2023 | K10 | Region X | Misamis Oriental | 304068 | Dampil NHS | LAGONGLONG |  | 1 | 8 |  | Batch 1 | 29549988.84 | 29293669.23 |  | Completed | 1 | 2024-01-22 | 2024-01-15 | P00775545MN-CW1 | 23KK0173 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42920 | NC 2023 | K10 | Region X | Misamis Oriental | 127743 | Gaston ES | LAGONGLONG |  | 1 | 3 |  | Batch 1 | 11013891.24 | 10918355.63 |  | Completed | 1 | 2023-12-18 | 2023-12-18 | P00775543MN-CW1 | 23KK0192 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42921 | NC 2023 | K10 | Region X | Misamis Oriental | 127750 | Tabok ES | LAGONGLONG |  | 1 | 4 |  | Batch 1 | 5845286.61 | 5794584 |  | Completed | 1 | 2023-12-23 | 2023-12-19 | P00775544MN-CW1 | 23KK0193 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42922 | NC 2023 | K10 | Region X | Misamis Oriental | 127715 | Ampianga ES | SUGBONGCOGON |  | 1 | 2 |  | Batch 1 | 6197196.11 | 6143441 |  | Completed | 1 | 2023-12-16 | 2023-12-16 | P00775546MN-CW1 | 23KK0176 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42923 | NC 2023 | K10 | Region X | Misamis Oriental | 127724 | Kaulayanan ES | SUGBONGCOGON |  | 1 | 2 |  | Batch 1 | 6112377.38 | 6059358 |  | Completed | 1 | 2023-12-14 | 2023-12-14 | P00775547MN-CW1 | 23KK0179 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42924 | NC 2023 | K10 | Region X | Misamis Oriental | 127731 | Mangga ES | SUGBONGCOGON |  | 1 | 4 |  | Batch 1 | 16224527.35 | 16083794.15 |  | Completed | 1 | 2023-12-01 | 2023-11-27 | P00775548MN-CW1 | 23KK0184 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42925 | NC 2023 | K10 | Region X | Misamis Oriental | 127712 | San Nicolas ES | JASAAN |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 | 11182545.26 | Completed | 1 |  |  |  | 23KL0101 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42926 | NC 2023 | K10 | Region X | Misamis Oriental | 127926 | Lugait CS | LUGAIT |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 | 11010900.02 | Completed | 1 |  |  |  | 23KL0100 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42927 | NC 2023 | K10 | Region X | Misamis Oriental | 127872 | Sta. Cruz ES | TAGOLOAN |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 | 11265538.47 | Completed | 1 |  |  |  | 23KL0099 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
42928 | NC 2023 | K10 | Region X | Oroquieta City | 500402 | Dullan IS | OROQUIETA CITY (Capital) |  | 1 | 2 |  | Batch 1 | 7061250 | 7000000 |  | Completed | 1
42929 | NC 2023 | K10 | Region X | Valencia City | 501120 | Batangan Integrated School | CITY OF VALENCIA |  | 1 | 6 |  | Batch 1 | 18661875 | 18500000 | 18311084.73 | Completed | 1 | 2024-03-04 |  | 23K00341 | 23K00341 | 2023-09-04 | 2023-09-05 | 2023-09-25 | 2023-10-03 | 2023-10-13 | MAFIL BUILDERS, INC.
42930 | NC 2023 | K10 | Region X | Valencia City | 126839 | Dabongdabong ES | CITY OF VALENCIA |  | 1 | 3 |  | Batch 1 | 9078750 | 9000000 | 8942345.76 | Completed | 1 | 2024-02-19 |  | 23K00340 | 23K00340 | 2023-09-04 | 2023-09-05 | 2023-09-25 | 2023-11-03 | 2023-11-13 | JRTP CONSTRUCTION
44466 | NC 2024 |  | Region X | Bukidnon | 126266 | Imbatug CES | BAUNGON |  | 1 | 8 | 2STY8CL (PHASE I) | GAA 17B | 10000000 |  | 9944923.23 | Ongoing | 0.6 | 2024-06-12 |  | P00875068MN-CW1 | 24KC0118 | 2024-06-13 | 2024-06-21 | 2024-04-07 | 2024-02-08 | 2024-08-14 | ABAYCER Construction Supplies and Gen. Merchandise | Ongoing - UPDATED 5-2025
44467 | NC 2024 |  | Region X | Bukidnon | 303969 | Kinawe National High School | LIBONA |  | 1 | 10 | 2STY10CL (PHASE I) | GAA 17B | 10000000 |  | 9944885.37 | Ongoing | 1 | 2024-06-12 |  | P00875069MN-CW1 | 24KC0116 | 2024-06-13 | 2024-06-21 | 2024-04-07 | 2024-02-08 | 2024-08-14 | Y Construction and Supply | Completed - UPDATED 5-2025
44468 | NC 2024 |  | Region X | Bukidnon | 303972 | Malitbog Agricultural HS | MALITBOG |  | 1 | 10 | 2STY10CL | GAA 17B | 10000000 |  | 9897252.52 | Ongoing | 0.35 | 2025-03-31 |  | P00875070MN-CW1 | 24KC0122 | 2024-10-30 |  | 2024-11-19 | 2024-12-17 | 2024-12-27 | Buildzone Construction and Supply | Ongoing - UPDATED 5-2025
44469 | NC 2024 |  | Region X | Bukidnon | 501647 | Cosina Integrated School | TALAKAG |  | 1 | 10 | 2UNITS 1STY5CL | BATCH 1 | 31750000 |  | 30727713.46 | Ongoing | 0.55 | 2024-12-16 |  | P00875410MN-CW1 | 24KC0105 | 2024-07-03 | 2024-03-14 | 2024-03-26 | 2024-05-06 | 2024-05-06 | EBCON 52 Ventures Inc. | Ongoing - UPDATED 5-2025
44470 | NC 2024 |  | Region X | Bukidnon | 126821 | San Isidro ES | TALAKAG |  | 1 | 10 | 2STY10CL | GAA 17B | 10000000 |  | 9653682.18 | Ongoing | 0.15 | 2024-06-12 |  | P00875071MN-CW1 | 24KC0117 | 2024-06-13 | 2024-06-21 | 2024-04-07 |  | 2024-08-14 | EBCON 52 Ventures Inc. | Ongoing - UPDATED 5-2025
44471 | NC 2024 |  | Region X | Bukidnon | 126288 | Freedom Elementary School | CABANGLASAN |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9948982.12 | Ongoing | 0.98 | 2024-01-09 |  | P00875074MN-CW1 | 24KA0157 | 2024-02-17 | 2024-02-23 | 2024-11-03 | 2024-03-15 | 2024-03-21 | H & N Builders and Enterprises | Ongoing - UPDATED 2-2025
44472 | NC 2024 |  | Region X | Bukidnon | 113761 | Basbasanan To Diraya To Tigwa | SAN FERNANDO |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9944800.94 | Completed | 1 | 2024-06-09 | 2024-06-09 | P00875075MN-CW1 | 24KA0158 | 2024-02-17 | 2024-02-23 | 2024-11-03 | 2024-03-15 | 2024-03-21 | Jorvivs Construction Corporation | Completed - UPDATED 2-2025
44473 | NC 2024 |  | Region X | Bukidnon | 126760 | Little Baguio ES | SAN FERNANDO |  | 1 | 8 | 2STY8CL | BATCH 1 | 26000000 |  | 25084394.21 | Ongoing | 0.65 | 2025-02-02 |  | P0087541MN-CW1 | 24KA0084 | 2023-11-16 | 2023-11-23 | 2024-05-12 | 2024-04-22 | 2024-04-24 | H & N Builders and Enterprises | Ongoing - UPDATED 2-2025
44474 | NC 2024 |  | Region X | Bukidnon | 199524 | Balud ES | DAMULOG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969662.75 | Completed | 1 | 2024-08-13 |  | P00875079MN-CW1 | 24KB0072 | 2024-01-17 | 2024-01-24 | 2024-05-03 | 2024-03-22 | 2024-04-25 | Revilo Construction | Completed - UPDATED 2-2025
44475 | NC 2024 |  | Region X | Bukidnon | 126352 | Mahayahay ES | DON CARLOS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4971480.98 | Completed | 1 | 2024-08-13 |  | P00875081MN-CW1 | 24KB0074 | 2024-01-17 | 2024-01-24 | 2024-05-03 | 2024-03-22 | 2024-04-25 | Maryam Construction | Completed - UPDATED 2-2025
44476 | NC 2024 |  | Region X | Bukidnon |  | Kadingilan NHS | KADINGILAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4971480.98 | Completed | 1 | 2024-08-13 |  | P00875080MN-CW1 | 24KB0073 | 2024-01-17 | 2024-01-24 | 2024-05-03 | 2024-03-22 | 2024-04-25 | Maryam Construction | Completed - UPDATED 2-2025
44477 | NC 2024 |  | Region X | Bukidnon | 126438 | Kibawe CS | KIBAWE |  | 1 | 10 | 2STY10CL | BATCH 1 | 34898574.09 |  | 34673695.1 | Ongoing | 0.9 | 2025-02-22 |  | P00875412MN-CW1 | 24KB0195 | 2024-05-21 | 2024-08-05 | 2024-11-06 | 2024-06-18 | 2024-06-27 | Kiokong Construction and Development Corporation | Ongoing - UPDATED 5-2025
44478 | NC 2024 |  | Region X | Bukidnon | 126465 | Cabalantian ES | KITAOTAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4933263.6 | Completed | 1 | 2024-08-13 |  | P00875078MN-CW1 | 24KB0071 | 2024-01-17 | 2024-01-24 | 2024-12-03 | 2024-03-25 | 2024-04-25 | Mikkil Construction | Completed - UPDATED 2-2025
44479 | NC 2024 |  | Region X | Bukidnon | 126477 | Kiulom Elementary School | KITAOTAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4932919.12 | Ongoing | 0.9 | 2024-08-13 |  | P00875077 | 24KB0070 | 2024-01-17 | 2024-01-24 | 2024-12-03 | 2024-03-25 | 2024-04-25 | Mikkil Construction | Ongoing
44480 | NC 2024 |  | Region X | Bukidnon | 501673 | Sagundanon Integrated School | KITAOTAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4954038.19 | Completed | 1 | 2024-08-13 | 2024-08-13 | P00875076 | 24KB0069 | 2024-01-17 | 2024-01-24 | 2024-05-03 | 2024-03-22 | 2024-04-25 | Caresystem Technology Solution Co., Inc. | Completed
44481 | NC 2024 |  | Region X | Bukidnon | 314930 | Apyao National High School | QUEZON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4974000 | Completed | 1 | 2024-08-13 | 2024-08-13 | P00875082MN-CW1 | 24KB0075 | 2024-01-17 | 2024-01-24 | 2024-05-03 | 2024-03-22 | 2024-04-25 | Maryam Construction | Completed
44482 | NC 2024 |  | Region X | Bukidnon | 303961 | Kiburiao National High School | QUEZON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4973971.56 | Completed | 1 | 2024-08-13 | 2024-08-13 | P00875083MN-CW1 | 24KB0076 | 2024-01-17 | 2024-01-24 | 2024-05-03 | 2024-03-22 | 2024-04-25 | Maryam Construction | Completed
44483 | NC 2024 |  | Region X | Cagayan de Oro City | 127963 | Kauswagan Central School | CAGAYAN DE ORO CITY (Capital) |  | 1 | 8 | 4STY8CL | BATCH 1 | 45802997.34 |  | 45552990.83 | Ongoing | 0.3 | 2025-04-27 |  |  | 24KH0088 |  | 2024-06-13 | 2024-06-25 | 2024-11-07 | 2024-07-22 | CAGALAWAN ENTERPRISES
44484 | NC 2024 |  | Region X | Cagayan de Oro City | 127994 | Upper Carmen Elementary School | CAGAYAN DE ORO CITY (Capital) |  | 1 | 8 | 2STY8CL | GAA 17B | 40000000 |  | 39772731.79 | Ongoing | 0.8 | 2025-01-14 |  | P00875124MN-CW1 | 24KH0075 | [5 empty] | CAGALAWAN ENTERPRISES
44485 | NC 2024 |  | Region X | Cagayan de Oro City | 127956 | Macabalan Elementary School | CAGAYAN DE ORO CITY (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 15000000 |  | 14903222.68 | Ongoing | 0.5 | 2024-10-19 |  | P00875125MN-CW1 | 24KD0051 | [5 empty] | HOLONHAUS CONTN. AND DEVT.
44486 | NC 2024 |  | Region X | Cagayan de Oro City | 304105 | Tablon National High School | CAGAYAN DE ORO CITY (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 15000000 |  | 14626500.04 | Ongoing | 0.4 | 2024-10-10 |  | P00875126MN-CW1 | 24KD0052 |  |  |  |  | 2024-08-05 | ANGEL & SAM CONSTRUCTION
44487 | NC 2024 |  | Region X | Cagayan de Oro City | 127968 | Taguanao Elementary School | CAGAYAN DE ORO CITY (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9904536.88 | Ongoing | 0.65 | 2024-02-12 |  | P00875127MN-CW1 | 24KD0050 |  |  |  |  | 2024-04-06 | STA. ANA RAYCON CORP.
44488 | NC 2024 |  | Region X | Camiguin | 126891 | Panghiawan Elementary School | CATARMAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4973593.84 | Ongoing | 0.95 | 2024-06-10 |  | P00875090MN | 24KE0096 | 2024-10-05 | 2024-05-20 | 2024-06-14 | 2024-06-26 | 2024-09-07 | JANRHYLL CONSTRUCTION | Punchlsit not yet complied
44489 | NC 2024 |  | Region X | Camiguin | 126893 | Tangaro ES | CATARMAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4973646.99 | Ongoing | 0.9 | 2024-06-10 |  | P00875089MN | 24KE0100 | 2024-10-05 | 2024-05-20 | 2024-06-14 | 2024-06-26 | 2024-09-07 | JANRHYLL CONSTRUCTION | Ongoing
44490 | NC 2024 |  | Region X | Camiguin | 126929 | Cabuan ES | GUINSILIBAN |  | 1 | 3 | 1STY3CL | GAA 17B | 7500000 |  | 7460408.25 | Completed | 1 | 2024-10-17 |  | P00875092MN | 24KE0101 | 2024-10-05 | 2024-05-20 | 2024-06-14 | 2024-06-26 | 2024-09-07 | F. P. ALONTO CONSTRUCTION SERVICES | Ongoing
44491 | NC 2024 |  | Region X | Camiguin | 126895 | Catohugan ES | MAHINOG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972882.94 | Completed | 1 | 2024-06-10 |  | P00875087MN | 24KE0102 | 2024-10-05 | 2024-05-20 | 2024-06-14 | 2024-06-26 | 2024-09-07 | F. P. ALONTO CONSTRUCTION SERVICES | Ongoing
44492 | NC 2024 |  | Region X | Camiguin | 315003 | Mahinog National High School II | MAHINOG |  | 1 | 6 | 2STY6CL | BATCH 1 | 21805027.8 |  | 21342854.01 | Ongoing | 0.55 |  |  | P00875414MN | 24KE0111 | 2024-07-21 | 2024-07-26 | 2024-12-08 | 2024-08-25 | 2024-03-10 | SHEEN-SHEEN CORPORATION | Ongoing
44493 | NC 2024 |  | Region X | Camiguin | 126900 | Owakan Elementary School | MAHINOG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4874893.99 | Ongoing | 0.95 | 2024-08-10 |  | P00875088MN | 24KE0098 | 2024-10-05 | 2024-05-20 | 2024-06-14 | 2024-06-26 | 2024-11-07 | SICARIO BUILDERS | Punchlsit not yet complied
44494 | NC 2024 |  | Region X | Camiguin | 126911 | Bug-ong ES | MAMBAJAO (Capital) |  | 1 | 3 | 1STY3CL | GAA 17B | 7500000 |  | 7459328.46 | Ongoing | 1 | 2024-10-27 |  | P00875086MN | 24KE0097 | 2024-10-05 | 2024-05-20 | 2024-06-14 | 2024-06-26 | 2024-07-19 | FNTC CONSTRUCTION | completed
44495 | NC 2024 |  | Region X | Camiguin | 126934 | Manuyog ES | SAGAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4874865.98 | Ongoing | 1 | 2024-08-10 |  | P00875091MN | 24KE0098 | 2024-10-05 | 2024-05-20 | 2024-06-14 | 2024-06-26 | 2024-11-07 | SICARIO BUILDERS | completed
44496 | NC 2024 |  | Region X | Iligan City | 128117 | Ampucao ES | ILIGAN CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4808644.23 | Ongoing | 0.95 | 2024-11-12 |  | 24KM0075 | 24KM0075 |  |  | 2024-05-13 |  | 2024-07-26 | A & R BUILDER | Ongoing
44497 | NC 2024 |  | Region X | Iligan City | 128158 | Francesca Paradela-Legaspi (Taytay ES) | ILIGAN CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4814384.06 | Ongoing | 0.95 | 2024-11-12 |  | 24KM0076 | 24KM0076 |  |  | 2024-05-13 |  | 2024-07-26 | ALFAHAD BUILDERS & ENTERPRISES | Done joint final inspection
44498 | NC 2024 |  | Region X | Iligan City | 128094 | Kiwalan Elementary School | ILIGAN CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4810384.4 | Ongoing | 0.95 | 2024-11-18 |  | 24KM0077 | 24KM0077 |  |  | 2024-05-13 |  | 2024-03-07 | NDP CONSTRUCTION DEVELOPMENT | Done joint final inspection
44499 | NC 2024 |  | Region X | Iligan City | 128126 | Laranjo Elementary School | ILIGAN CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4797672.53 | Ongoing | 0.95 | 2024-11-18 |  | 24KM0078 | 24KM0078 |  |  | 2024-05-13 |  | 2024-03-07 | THE HUANG BUILDERS, INC. | Done joint final inspection
44500 | NC 2024 |  | Region X | Iligan City | 128129 | Mainit ES | ILIGAN CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4803661.62 | Ongoing | 0.95 | 2024-11-12 |  | 24KM0079 | 24KM0079 |  |  | 2024-05-13 |  | 2024-07-26 | A & R BUILDERS | Ongoing
44501 | NC 2024 |  | Region X | Iligan City | 128114 | Primitivo Quimpo MES | ILIGAN CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4808916.2 | Ongoing | 0.95 | 2024-11-12 |  | 24KM0080 | 24KM0080 |  |  | 2024-05-13 |  | 2024-07-26 | SILVER CONSTRUCTION | Ongoing
44502 | NC 2024 |  | Region X | Iligan City | 128134 | Sardab Elementary School | ILIGAN CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4797627.18 | Ongoing | 0.95 | 2024-11-12 |  | 24KM0081 | 24KM0081 |  |  | 2024-05-13 |  | 2024-07-26 | THE HUANG BUILDERS, INC. | Done joint final inspection
44503 | NC 2024 |  | Region X | Iligan City | 500697 | Sultan Mamarinta Panandigan Integrated School | ILIGAN CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4797621.65 | Ongoing | 0.95 | 2024-11-18 |  | 24KM0082 | 24KM0082 |  |  | 2024-05-13 |  | 2024-03-07 | THE HUANG BUILDERS, INC. | Done joint final inspection
44504 | NC 2024 |  | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9832952.33 | Ongoing | 0.8 | 2025-04-25 |  | P00875102MN-CW1 | 24KG0050 | 2024-10-29 | 2024-11-05 | 2024-11-18 | 2024-12-02 | 2024-12-10 | Al-Noorway Corporation | The project is suspended due to DENR Permit
44505 | NC 2024 |  | Region X | Lanao del Norte | 127043 | Kauswagan CES | KAUSWAGAN |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9950000 | Completed | 1 | 2024-08-26 | 2024-08-26 | P00875104MN-CW1 | 24KG0042 | 2024-02-27 | 2024-05-03 | 2024-03-18 | 2024-02-04 | 2024-12-04 | NDP Construction Development | The project is completed.
44506 | NC 2024 |  | Region X | Lanao del Norte | 501030 | Samburon Integrated School | LINAMON |  | 1 | 12 | 3STY12CL | BATCH 1 | 50426912.86 |  | 49248176.08 | Ongoing | 0.9 | 2025-12-01 |  | P00875415MN-CW1 | 24KG0046 | 2024-05-04 | 2024-04-15 | 2024-04-25 | 2024-05-22 | 2024-05-24 | Alfahad Builders and Enterprises | the project is suspended due to force majeure. There is a proposed Contract Time Extension
44507 | NC 2024 |  | Region X | Lanao del Norte | 304012 | MATUNGAO NATIONAL HIGH SCHOOL | MATUNGAO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9836945.41 | Ongoing | 0.8 | 2025-04-25 |  | P00875103MN-CW1 | 24KG0049 | 2024-10-29 | 2024-11-05 | 2024-11-18 | 2024-12-02 | 2024-12-10 | Al-Noorway Corporation | The project is suspended due to LGU Permits.
44508 | NC 2024 |  | Region X | Lanao del Norte | 200543 | Malimbato Primary School | TAGOLOAN |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9849535.02 | Completed | 1 | 2024-08-26 | 2024-08-19 | P00875101MN-CW1 | 24KG0041 | 2024-02-27 | 2024-05-03 | 2024-03-18 | 2024-02-04 | 2024-12-04 | SBM Builder | The project is completed.
44509 | NC 2024 |  | Region X | Lanao del Norte | 127242 | Sergio Mata ES (Tubaran ES) | TUBOD (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4922111.74 | Ongoing | 1 | 2025-03-26 |  | P00875109MN-CW1 | 24KG0051 | 2024-11-14 | 2024-11-18 | 2024-11-28 | 2024-12-10 | 2024-12-17 | Al-Noorway Corporation | The project is ongoing and is ahead of its schedule.
44510 | NC 2024 |  | Region X | Lanao del Norte | 304023 | Salvador NHS (Salvador Trade HS) | SALVADOR |  | 1 | 3 | 1STY3CL | GAA 17B | 10700000 |  | 10211475.88 | Completed | 1 |  |  | P00875105MN-CW1 | 24KF0065 | 2024-01-03 | 2024-08-03 | 2024-03-20 | 2024-04-15 | 2024-06-05 | Al-Noorway Corporation | for n/a, DPWH will provide the data ASAP
44511 | NC 2024 |  | Region X | Lanao del Norte | 304017 | Panoloon NHS | SAPAD |  | 1 | 2 | 1STY2CL | GAA 17B | 7650000 |  | 7201919.38 | Completed | 1 |  |  | P00875106MN-CW1 | 24KF0064 | 2024-01-03 | 2024-08-03 | 2024-03-20 | 2024-04-22 | 2024-05-13 | U.M.D. Construction | for n/a, DPWH will provide the data ASAP
44512 | NC 2024 |  | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) |  | 1 | 2 | 1STY2CL | GAA 17B | 7750000 |  | 7296214.53 | Completed | 1 |  |  | P00875107MN-CW1 | 24KF0063 | 2024-01-03 | 2024-08-03 | 2024-03-20 | 2024-04-15 | 2024-06-05 | MOYA Construction | for n/a, DPWH will provide the data ASAP
44513 | NC 2024 |  | Region X | Lanao del Norte | 500691 | Sultan Naga Dimaporo Memorial Integrated School | SULTAN NAGA DIMAPORO (KAROMATAN) |  | 1 | 2 | 1STY2CL | GAA 17B | 13900000 |  | 10285071.63 | Completed | 1 |  |  | P00875108MN-CW1 | 24KF0072 | 2024-07-18 | 2024-07-25 | 2024-06-08 | 2024-08-21 | 2024-09-09 | MOYA Construction | for n/a, DPWH will provide the data ASAP
44514 | NC 2024 |  | Region X | Malaybalay City | 126582 | Kalasungay Central School | CITY MALAYBALAY (Capital) |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9935908.87 | Ongoing | 0.6 | 2024-06-09 |  | P00875073MN-CW1 | 24KA 0160 | 2024-02-17 | 2024-02-23 | 2024-07-03 | 2024-03-14 | 2024-03-21 | Ohms Construction | delayed onsite, ongoing roofing
44515 | NC 2024 |  | Region X | Malaybalay City | 501581 | Tuburan Integrated School | CITY MALAYBALAY (Capital) |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9845410 | Ongoing | 0.95 | 2024-01-09 |  | P00875072MN-CW1 | 24KA 0159 | 2024-02-17 | 2024-02-23 | 2024-07-03 | 2024-03-19 | 2024-03-21 | Red Construction Technik | Waiting on the delivery of furniture (Infra-Conts. package)
44516 | NC 2024 |  | Region X | Misamis Occidental | 501866 | Adorable Integrated School | JIMENEZ |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  |  | Ongoing | 1 | 2024-10-26 |  | P00875110MN-CW1 | 24KI0086 | [5 empty] | HSO PDCC | No report submitted
44517 | NC 2024 |  | Region X | Misamis Occidental | 127399 | Palilan ES | JIMENEZ |  | 1 | 2 | 1STY2CL | GAA 17B | 7000000 |  |  | Ongoing | 1 | 2024-10-17 |  | P00875111MN-CW1 | 24KI0073 | [5 empty] | SGM Construction | No report submitted
44518 | NC 2024 |  | Region X | Misamis Occidental | 501868 | Alegria Inegrated School | LOPEZ JAENA |  | 1 | 2 | 1STY2CL | GAA 17B | 7000000 |  |  | Ongoing | 1 | 2024-10-17 |  | P00875115MN-CW1 | 24KI0074 | [5 empty] | SBU BUilders and Gen MDse | No report submitted
44519 | NC 2024 |  | Region X | Misamis Occidental | 501869 | BURGOS INTEGRATED SCHOOL | LOPEZ JAENA |  | 1 | 2 | 1STY2CL | GAA 17B | 7000000 |  |  | Ongoing | 0.85 | 2024-10-17 |  | P00875112MN-CW1 | 24KI0075 | [5 empty] | 3Rs BUilders and Resources | No report submitted
44520 | NC 2024 |  | Region X | Misamis Occidental | 501870 | Sta Cruz Integrated School | PLARIDEL |  | 1 | 2 | 1STY2CL | GAA 17B | 7000000 |  |  | Ongoing | 1 | 2024-10-17 |  | P00875113MN-CW1 | 24KI0071 | [5 empty] | MDS COnstruction and Enterprises | No report submitted
44521 | NC 2024 |  | Region X | Misamis Occidental | 501876 | Maikay Integrated School | TUDELA |  | 1 | 8 | 2STY8CL | BATCH 1 | 31060000 |  |  | Ongoing | 0.85 |  |  | P00875416MN | 24KJ0121 | [5 empty] | Abib Builders Enterprise | On-going Construction
44522 | NC 2024 |  | Region X | Misamis Oriental | 127621 | Mandangoa ES | BALINGASAG |  | 1 | 8 | 2STY8CL | BATCH 1 | 32419613.16 |  | 32223327.09 | Ongoing | 0.2 |  |  | 24kk108 |  | 2024-03-25 | 2024-01-04 | 2024-04-15 | 2024-04-26 | 2024-04-30 | L&L Construction | Project On going
44523 | NC 2024 |  | Region X | Misamis Oriental | 127747 | Lagonglong CS | LAGONGLONG |  | 1 | 6 | 2STY6CL | GAA 17B | 22700000 |  | 22565635.92 | Ongoing | 0.2 |  |  | 24kk103 |  | 2024-04-26 | 2024-06-05 | 2024-05-20 | 2024-05-28 | 2024-05-30 | FJQ Construction | Project On going
44524 | NC 2024 |  | Region X | Misamis Oriental | 501045 | Kandiis IS | MAGSAYSAY (LINUGOS) |  | 1 | 4 | 2STY4CL | GAA 17B | 17300000 |  | 17162931.04 | Ongoing | 0.2 |  |  | 24kk104 |  | 2024-06-03 | 2024-03-14 | 2024-03-26 | 2024-12-04 | 2024-04-19 | Sta. Ana Raycon | Project On going
44525 | NC 2024 |  | Region X | Misamis Oriental | 304079 | Libertad NHS | LIBERTAD |  | 1 | 15 | 3STY15CL | GAA 17B | 20000000 |  |  | Ongoing | 0.02 | [9 empty] | LIGHT CONSTRUCTION & SUPPLY | Project On going
44526 | NC 2024 |  | Region X | Misamis Oriental | 127926 | Lugait CS | LUGAIT |  | 1 | 8 | 2STY8CL | GAA 17B | 20000000 |  | 19900000 | Ongoing | 0.02 |  |  | 24kl0121 |  |  | 2024-07-19 | 2024-07-31 |  | 2024-09-15 | Ramzie Builders and Ent. | Project On going
44527 | NC 2024 |  | Region X | Oroquieta City | 501974 | Taboc Integrated School | OROQUIETA CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 7000000 |  | 6738649.64 | Ongoing | 0.9 | 2024-10-17 |  | P00875114MN-CW1 | 24KI0072 | [5 empty] | NLMC COnstruction Services | Project On going
44528 | NC 2024 |  | Region X | Oroquieta City | 127452 | Victor Enerio MES | OROQUIETA CITY (Capital) |  | 1 | 6 | 2STY6CL | BATCH 1 | 21969983 |  | 21182468.96 | Ongoing | 0.45 | [9 empty] | no available data | Project On going
44529 | NC 2024 |  | Region X | Ozamis City | 501205 | Cruz Lanzado Saligan Integrated School | OZAMIS CITY |  | 1 |  | Construction of School Building | GAA 17B | 5000000 |  |  | Completed | 1 |  |  | P00875119MN | [6 empty] | Weisenwork Construction | Project Completed
44530 | NC 2024 |  | Region X | Ozamis City | 128195 | Gala Elementary School | OZAMIS CITY |  | 1 |  | Construction of School Building | GAA 17B | 12000000 |  | 11581799.75 | Ongoing | 0.7 |  |  | P00875116MN | [6 empty] | Weisenwork Construction | Project On going
44531 | NC 2024 |  | Region X | Ozamis City | 502051 | Sancho Capa Integrated School | OZAMIS CITY |  | 1 |  | Construction of School Building (PHASE I) | GAA 17B | 11000000 |  |  | Ongoing | 0.15 |  |  | P00875117MN | [6 empty] | Victoriano C. Lim Construction Corporation | Project On going
44532 | NC 2024 |  | Region X | Ozamis City | 502053 | Sinusa Integrated School | OZAMIS CITY |  | 1 |  | Construction of School Building | GAA 17B | 12000000 |  |  | Ongoing | 0.6 |  |  | P00875118MN | [6 empty] | Weisenwork Construction | Project On going
44533 | NC 2024 |  | Region X | Valencia City | 314909 | Guinuyoran National High School | CITY OF VALENCIA |  | 1 | 12 | 3STY12CL | GAA 17B | 33000000 |  |  | Ongoing | 0.55 | 2025-04-20 |  | P00875084MN-CW1 | 24k00371 |  |  |  |  | 2024-07-25 | JT GAMOLO | ONGOING
44534 | NC 2024 |  | Region X | Valencia City | 126847 | Lurugan Elementary School | CITY OF VALENCIA |  | 1 | 6 | 2STY6CL | BATCH 1 | 13196678.39 |  |  | Not Yet Started | 0 | [10 empty] | reverted
44535 | NC 2024 |  | Region X | Valencia City | 501125 | Vintar Integrated School | CITY OF VALENCIA |  | 1 | 3 | 1STY3CL | GAA 17B | 7000000 |  |  | Completed | 1 | 2024-05-08 |  | P00875085MN-CW1 | 24K00130 |  |  |  |  | 2024-03-05 | JRTT CONSTRUCTION AND SUPPLIES | completed

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.