## Sheet1
INDEX (DO NOT MODIFY) | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
2285 | QRF 2021 | Region X | Camiguin | 303994 | Mambajao NHS | MAMBAJAO (Capital) | 0 | 1 | 5 | DAMAGED CLASSROOMS DUE TO TREES TOPPLED OVER IT (STRONG WINDS) | 1473234.1441 | 1 | 1462809.68 | COMPLETED | 1 | 2022-02-05 | 2021-12-18 | QRF 2021 - R X - Camiguin - 003 | Infra-01-02-2021 | 2021-06-01 | 2022-06-09 | 2021-06-21 | 2021-07-27 | 2021-08-09 | JAPUZ JANSOL ENTERPRISES
2286 | QRF 2021 | Region X | Camiguin | 126921 | Tupsan ES | MAMBAJAO (Capital) | 0 | 1 | 4 | FIRE INCIDENT | 1971512.2694 | 1 | 1960536.73 | COMPLETED | 1 | 2022-03-24 | 2022-06-04 | QRF 2021 - R X - Camiguin - 002 | Infra-01-03-2021 | 2021-06-01 | 2022-06-09 | 2021-06-21 | 2021-07-27 | 2021-08-09 | JAPUZ JANSOL ENTERPRISES
2287 | QRF 2021 | Region X | Camiguin | 126921 | Tupsan ES | MAMBAJAO (Capital) | 0 |  | 2 | DAMAGED CLASSROOMS DUE TO TREES TOPPLED OVER IT (STRONG WINDS) | 4758089.7892 | 1 | 1960536.73 | COMPLETED | 1 | 2022-02-05 | 2021-12-18 | QRF 2021 - R X - Camiguin - 004 | Infra-01-02-2021 | 2021-06-01 | 2022-06-09 | 2021-06-21 | 2021-07-27 | 2021-08-09 | Minkonstrak Eng'g. & Gen. Srvcs.
2288 | QRF 2021 | Region X | Camiguin | 126936 | Subocan ES | SAGAY | 0 | 1 | 2 | DAMAGED CLASSROOMS DUE TO TREES TOPPLED OVER IT (STRONG WINDS) | 4849009.2892 | 1 | 4838031.27 | Completed | 1 | 2022-01-21 | 2022-02-26 | QRF 2021 - R X - Camiguin - 001 | Infra-01-04-2021 | 2021-06-01 | 2022-06-09 | 2021-06-21 | 2021-07-27 | 2021-08-09 | Minkonstrak Eng'g. & Gen. Srvcs.
2558 | QRF 2022 | Region X | Camiguin | 126885 | Catarman CS | CATARMAN | 0 |  | 10 | NEW CONSTRUCTION | 19869482.89 | 1 | 19866688.44 | completed | 1 | 2023-08-30 | 2023-08-18 | QRF 2022 - R X - Camiguin - 004 | QRF 2022 - R X - Camiguin - LOT 2 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | VINLABZ CONSTRUCTION
2559 | QRF 2022 | Region X | Camiguin | 126885 | Catarman CS | CATARMAN | 0 | 1 | 1 | REPAIR/ REHABILITATION | 150000 | 1 | 149472.02 | completed | 1 | 2023-08-30 | 2023-08-18 | QRF 2022 - R X - Camiguin - 043 | QRF 2022 - R X - Camiguin - LOT 2 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | VINLABZ CONSTRUCTION
2560 | QRF 2022 | Region X | Camiguin | 126928 | BUTAY ES | GUINSILIBAN | 0 | 1 | 2 | REPAIR/ REHABILITATION | 300000 | 1 | 296463.41 | Completed | 1 | 2023-06-01 | 2023-08-05 | QRF 2022 - R X - Camiguin - 033 | QRF 2022 - R X - Camiguin - LOT 3 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | MINKONSTRAK ENG'G. & GEN. SRVCS.
2561 | QRF 2022 | Region X | Camiguin | 126931 | Guinsiliban CS | GUINSILIBAN | 0 | 1 | 2 | REPAIR/ REHABILITATION | 800000 | 1 | 798629.57 | completed | 1 | 2023-06-01 | 2023-08-05 | QRF 2022 - R X - Camiguin - 031 | QRF 2022 - R X - Camiguin - LOT 3 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | MINKONSTRAK ENG'G. & GEN. SRVCS.
2562 | QRF 2022 | Region X | Camiguin | 126933 | Maac Elementary School | GUINSILIBAN | 0 | 1 | 6 | NEW CONSTRUCTION | 12667615.79 | 1 | 12662340.68 | completed | 1 | 2023-06-01 | 2023-08-05 | QRF 2022 - R X - Camiguin - 005 | QRF 2022 - R X - Camiguin - LOT 3 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | MINKONSTRAK ENG'G. & GEN. SRVCS.
2563 | QRF 2022 | Region X | Camiguin | 126914 | Mambajao CS | MAMBAJAO (Capital) | 0 |  | 11 | NEW CONSTRUCTION | 22536171.13 | 1 | 22525933.1 | completed | 1 | 2023-09-29 | 2023-10-27 | QRF 2022 - R X - Camiguin - 003 | QRF 2022 - R X - Camiguin - LOT 1 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | VINLABZ CONSTRUCTION
2564 | QRF 2022 | Region X | Camiguin | 126914 | Mambajao CS | MAMBAJAO (Capital) | 0 | 1 | 4 | REPAIR/ REHABILITATION | 650981.29 | 1 | 644855.12 | completed | 1 | 2023-09-29 | 2023-10-27 | QRF 2022 - R X - Camiguin - 021 | QRF 2022 - R X - Camiguin - LOT 1 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | VINLABZ CONSTRUCTION
2565 | QRF 2022 | Region X | Camiguin | 126935 | Sagay Central School | SAGAY | 0 | 1 | 3 | REPAIR/ REHABILITATION | 1866506.75 | 1 | 1860652.7 | completed | 1 | 2023-09-29 |  | QRF 2022 - R X - Camiguin - 015 | QRF 2022 - R X - Camiguin - LOT 4 | 2022-07-04 | 2022-07-13 | 2021-06-25 | 2022-08-08 | 2022-09-19 | MINKONSTRAK ENG'G. & GEN. SRVCS.
2566 | QRF 2022 | Region X | Camiguin | 126935 | Sagay Central School | SAGAY | 0 |  | 12 | NEW CONSTRUCTION | 24369730.96 | 1 | 24363319.78 | completed | 1 | 2023-09-29 |  | QRF 2022 - R X - Camiguin - 002 | QRF 2022 - R X - Camiguin - LOT 4 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | MINKONSTRAK ENG'G. & GEN. SRVCS.
2567 | QRF 2022 | Region X | El Salvador | 127670 | Cogon ES | CITY OF EL SALVADOR | 2 | 1 | 2 | NEW CONSTRUCTION | 5858817.72 | 1 | 4624522.96 | Completed | 1 | 2023-07-16 | 2023-06-26 | 2022-04-0066 |  | 2022-04-29 | 2022-05-11 | 2022-05-23 | 2022-09-25 | 2023-09-29 | Tri FB Construction & Gen Mdse
2568 | QRF 2022 | Region X | El Salvador | 127677 | Pedro Sa. Baculio ES (Bolobolo) | CITY OF EL SALVADOR | 2 | 1 | 2 | REPAIR/ REHABILITATION | 1301701.99 | 1 | 1105506.66 | completed | 1 | 2023-03-18 | 2023-04-25 | 2022-04-0067 |  | 2022-04-29 | 2022-05-11 | 2022-05-23 | 2022-09-25 | 2023-09-29 | AbrahamBM Construction
2569 | QRF 2022 | Region X | El Salvador | 127677 | Pedro Sa. Baculio ES (Bolobolo) | CITY OF EL SALVADOR | 2 |  | 2 | NEW CONSTRUCTION | 6509328.44 | 1 | 5313487.54 | completed | 1 | 2023-07-16 | 2023-02-03 | 2022-04-0069 |  | 2022-04-29 | 2022-05-11 | 2022-05-23 | 2022-09-25 | 2023-09-29 | AbrahamBM Construction
2570 | QRF 2022 | Region X | El Salvador | 127678 | Sambulawan Elementary School | CITY OF EL SALVADOR | 2 | 1 | 2 | NEW CONSTRUCTION | 6836370.06 | 1 | 6270286.1 | Completed | 1 | 2023-03-18 | 2023-06-26 | 2022-04-0068 |  | 2022-04-29 | 2022-05-11 | 2022-05-23 | 2022-09-25 | 2023-09-29 | AbrahamBM Construction
2571 | QRF 2022 | Region X | Gingoog City | 501023 | Civoleg Integrated School - Elem | GINGOOG CITY | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1500000 | 1 |  | Completed | 1 | 2022-12-29 |  | QRF 2022 - R X - Camiguin - 004 | QRF 2022 - R X - Camiguin - LOT 2 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | VINLABZ CONSTRUCTION
2572 | QRF 2022 | Region X | Gingoog City | 128065 | Dona J. Pelaez Reyes CS | GINGOOG CITY | 1 | 1 | 1 | REPAIR/ REHABILITATION | 1000000 | 1 |  | Completed | 1 | 2022-12-29 |  | QRF 2022 - R X - Camiguin - 043 | QRF 2022 - R X - Camiguin - LOT 2 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | VINLABZ CONSTRUCTION
2759 | QRF 2022 REPLENISHMENT | Region X | Camiguin | 126897 | Mahinog Central School | MAHINOG | Lone | 1 | 3 | Replacement | 6333807.9 | 1 | 6316664.91 | COMPLETED | 1 | 2023-10-09 |  | QRF 2022 - R X - Camiguin - 010 | QRF 2022 BATCH 2 | 2023-03-14 | 2023-03-22 | 2023-03-06 | 2023-03-27 | 2023-05-08 | VINLABZ CONSTRUCTION
3053 | QRF 2023 | Region X | Misamis Occidental | 127244 | Aloran Central School | ALORAN | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 1181156.34 | 1 | 1169675.6 | Completed | 1 | 2024-01-14 | 2024-01-31 | QRF 2023 | 010-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing
3054 | QRF 2023 | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1st | 1 | 14 | REPAIR OF CLASSROOMS | 2631921.7 | 1 | 2605810.49 | Completed | 1 | 2024-04-20 | 2024-01-31 | QRF 2023 | 010-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing - With Variation Order
3055 | QRF 2023 | Region X | Misamis Occidental | 127252 | Lobogon ES | ALORAN | 1st | 1 | 12 | 2UNITS 2STY6CL | 49200000 | 1 | 48462000 | completed | 1 | 2024-01-14 |  | QRF 2023 | 011-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-17 | HSO | Ongoing
3056 | QRF 2023 | Region X | Misamis Occidental | 201016 | Palayan PS | ALORAN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 550000 | 1 | 544594.41 | Completed | 1 | 2024-01-14 | 2024-01-31 | QRF 2023 | 010-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing
3057 | QRF 2023 | Region X | Misamis Occidental | 127507 | Usocan Elementary School | PLARIDEL | 1st | 1 | 7 | REPAIR OF CLASSROOMS | 3415705.95 | 1 | 3392720.89 | Completed | 1 | 2024-03-18 | 2024-03-29 | QRF 2023 | 021-2023 | 2023-09-09 | 2023-08-10 | 2023-08-25 | 2023-10-12 | 2023-12-13 | RJLG Construction and Supplies | Ongoing - with issued Site Instruction
3058 | QRF 2023 | Region X | Misamis Occidental | 127334 | Bitoon Elementary School | CLARIN | 2nd | 1 | 4 | 1STY4CL | 10094200 | 1 | 9791374 | Ongoing | 0.8 | 2024-04-01 |  | QRF 2023 | 013-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-17 | SGM | Ongoing - with liquidated damages
3059 | QRF 2023 | Region X | Misamis Occidental | 127538 | Cagay-Anon ES | SINACABAN | 2nd | 1 | 4 | 2STY4CL | 16800000 | 1 | 16346376.58 | Ongoing | 0.85 | 2024-03-24 |  | QRF 2023 | 014-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing-With Suspension Order due to change in foundation to suit actual field condition - Resumption on April 1, 2024
3060 | QRF 2023 | Region X | Misamis Occidental | 127552 | San Vicente ES | SINACABAN | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1786838.15 | 1 | 1773076.95 | Completed | 1 | 2024-03-18 | 2024-03-26 | QRF 2023 | 022-2023 | 2023-09-09 | 2023-08-10 | 2023-08-25 | 2023-10-12 | October 27, 2027 | RJLG Construction and Supplies | Ongoing
3061 | QRF 2023 | Region X | Misamis Occidental | 127575 | Ozamiz Elementary School | TUDELA | 2nd | 1 | 6 | 2STY6CL | 24600000 | 1 | 23861999.87 | Ongoing | 0.83 | 2024-04-21 |  | QRF 2023 | 015-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-17 | Mindanao Rock | Ongoing
3062 | QRF 2023 | Region X | Misamis Occidental | 127582 | Tudela Central School | TUDELA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 766473.74 | 1 | 758014.3 | Completed | 1 | 2024-01-14 | 2024-01-31 | QRF 2023 | 018-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing
3063 | QRF 2023 | Region X | Misamis Occidental | 304058 | Tudela National Comprehensive High School | TUDELA | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2173436.49 | 1 | 2151115.2 | Completed | 1 | 2024-01-14 | 2024-01-31 | QRF 2023 | 018-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing
3064 | QRF 2023 | Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1st | 1 | 15 | 3STY15CL | 45000000 | 1 | 39598320.79 | Completed | 1 | September 30, 2024 |  | QRF 2023 | PB Const2023-002 | June 3,2023 | June 13,2023 | June 27,2023 | July 27,2023 | October 27, 2023 | Junjing Construction and Gen Mer. | Ongoing
3065 | QRF 2023 | Region X | Misamis Oriental | 304081 | Lourdes Alubijid NHS | ALUBIJID | 2nd | 1 | 0 | Structural Assessment & Repair of 1CL TVL Bldg. | 1000000 | 1 | 835775.02 | Completed | 1 | March 1,2024 | February 25, 2024 | QRF 2023 | G2PB Repair 2023-001 | October 10,2023 | Oct 23,2023 | Nov 6,2023 | Nov 22, 2023 | Dec.19, 2023 | Tri - FB | Completed
3066 | QRF 2023 | Region X | Oroquieta City | 127437 | Oroquieta City CES | OROQUIETA CITY (Capital) | 1st | 1 | 8 | 2STY8CL | 24871003.7 | 1 | 21907012.66 | completed | 1 | 17‎ ‎July‎ ‎2024 |  | INFRA-2023-DEPEDOROQ-1 |  | 2023-04-27 | 2023-05-10 | 2023-05-22 | 2023-07-10 | 2023-07-14 | G-Baron Construction | variance is subject for utilization
3067 | QRF 2023 | Region X | Oroquieta City | 304049 | Rizal NHS | OROQUIETA CITY (Capital) | 1st | 1 | 6 | 2STY6CL | 18906773.84 | 1 | 16036677.23 | Completed | 1 | ‎29‎ ‎December‎ ‎2023 |  | INFRA-2023-DEPEDOROQ-3 |  | 2023-04-27 | 2023-05-10 | 2023-05-23 | 2023-06-26 | 2023-07-17 | RJLG Construction | Completed - Subject for turn-over
3068 | QRF 2023 | Region X | Oroquieta City | 127474 | Vicente Flores MES | OROQUIETA CITY (Capital) | 1st | 1 | 6 | 2STY6CL | 21824913.64 | 1 | 18973207.53 | Completed | 1 | ‎13‎ ‎January‎ ‎2024 |  | INFRA-2023-DEPEDOROQ-2 |  | 2023-04-27 | 2023-05-10 | 2023-05-22 | 2023-06-26 | 2023-07-17 | RJLG Construction | variance is subject for utilization
3069 | QRF 2023 | Region X | Oroquieta City | 127474 | Vicente Flores MES | OROQUIETA CITY (Capital) | 1st |  | 3 | REPAIR OF CLASSROOMS | 4793783.14 | 1 | 3817916.63 | Completed | 1 | ‎14‎ ‎December‎ ‎2023 |  | INFRA-2023-DEPEDOROQ-4 |  | 2023-04-27 | 2023-05-10 | 2023-05-23 | 2023-06-26 | 2023-07-17 | RJLG Construction | variance is subject for utilization
3244 | QRF 2024 | Region X | Bukidnon | 126484 | Sagasaan ES | KITAOTAO | 3rd | 1 | 2 | 1STY2CL | 6599650.8 | 1- NC |  | Ongoing | 0.5

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%