## Sheet1
INDEX (DO NOT MODIFY) | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
2184 | REPAIR 2020 | Region X | Bukidnon | 126818 | Sagaran ES | TALAKAG | 1 | 1 | 4 | Repair of Classrooms | 1006621 | 1 |  | COMPLETED | 1 |  |  | PB-02-01-2020-0003 |  | January 23, 2020 | January 31, 2020 | February 12, 2020 |  |  |  | Rebid
2185 | REPAIR 2020 | Region X | Bukidnon | 126779 | Intavas Elementary School | IMPASUG-ONG | 2 | 1 | 6 | Repair of Classrooms | 1725348 | 1 |  | COMPLETED | 1 |  |  | PB-02-01-2020-0003 |  | January 23, 2020 | January 31, 2020 | February 12, 2020 |  |  |  | Rebid
2186 | REPAIR 2020 | Region X | Bukidnon | 126497 | Babahagon ES | LANTAPAN | 2 | 1 | 5 | Repair of Classrooms | 2035461 | 1 |  | COMPLETED | 1 |  |  | PB-02-01-2020-0003 |  | January 23, 2020 | January 31, 2020 | February 12, 2020 |  |  |  | Rebid
2187 | REPAIR 2020 | Region X | Bukidnon | 126354 | Maraymaray ES | DON CARLOS | 3 | 1 | 11 | Repair of Classrooms | 4066050 | 1 | 4066049.62 | COMPLETED | 1 |  |  | PB-02-01-2020-0003 |  | January 23, 2020 | January 31, 2020 | February 12, 2020 |  |  |  | AWAITING FOR SUB-ARO
2188 | REPAIR 2020 | Region X | Bukidnon | 126365 | San Nicolas ES | DON CARLOS | 3 | 1 | 19 | Repair of Classrooms | 5090229 | 1 | 5090228.1 | COMPLETED | 1 |  |  | PB-02-01-2020-0003 |  | January 23, 2020 | January 31, 2020 | February 12, 2020 |  |  |  | AWAITING FOR SUB-ARO
2189 | REPAIR 2020 | Region X | Bukidnon | 126395 | Balaoro ES | KADINGILAN | 3 | 1 | 2 | Repair of Classrooms | 913873 | 1 | 913872.63 | COMPLETED | 1 |  |  | PB-02-01-2020-0003 |  | January 23, 2020 | January 31, 2020 | February 12, 2020 |  |  |  | AWAITING FOR SUB-ARO
2190 | REPAIR 2020 | Region X | Bukidnon | 126414 | Barorawon Elementary School | KALILANGAN | 4 | 1 | 7 | Repair of Classrooms | 2222638 | 1 |  | COMPLETED | 1
2191 | REPAIR 2020 | Region X | Bukidnon | 126423 | Kibaritan ES | KALILANGAN | 4 | 1 | 2 | Repair of Classrooms | 935495.65 | 1 |  | COMPLETED | 1
2192 | REPAIR 2020 | Region X | Bukidnon | 126678 | BALMAR ELEMENTARY SCHOOL | PANGANTUCAN | 4 | 1 | 5 | Repair of Classrooms | 1690252.98 | 1 |  | COMPLETED | 1
2193 | REPAIR 2020 | Region X | Bukidnon | 126685 | Kimanait ES | PANGANTUCAN | 4 | 1 | 2 | Repair of Classrooms | 1071961.79 | 1 |  | COMPLETED | 1
2194 | REPAIR 2020 | Region X | Bukidnon | 126693 | New Iloilo ES | PANGANTUCAN | 4 | 1 | 4 | Repair of Classrooms | 1900000 | 1 |  | COMPLETED | 1
2195 | REPAIR 2020 | Region X | Cagayan de Oro City | 127957 | North City Central School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 8 | Repair of Classrooms | 1708745 | 1 | 1708744.56 | COMPLETED | 1 |  |  |  |  | 2020-01-13 | 2020-01-20 | 2020-02-03 |  |  | Brima Const. | Waiting for Sub-ARO
2196 | REPAIR 2020 | Region X | Cagayan de Oro City | 304124 | Puntod National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 16 | Repair of Classrooms | 2744803 | 1 | 2744802.27 | COMPLETED | 1 |  |  |  |  | 2020-01-13 | 2020-01-20 | 2020-02-03 |  |  | JARM Const. | Waiting for Sub-ARO
2197 | REPAIR 2020 | Region X | Cagayan de Oro City | 127958 | St. John Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 5 | Repair of Classrooms | 1025981 | 1 | 1025980.57 | COMPLETED | 1 |  |  |  |  | 2020-01-13 | 2020-01-20 | 2020-02-03 |  |  | Brima Const. | Waiting for Sub-ARO
2198 | REPAIR 2020 | Region X | Camiguin | 126887 | Compol ES | CATARMAN | 0 | 1 | 5 | Repair of Classrooms | 2555182 | 1 | 2555181.99 | COMPLETED | 1 | [10 empty] | Waiting for Sub-ARO
2199 | REPAIR 2020 | Region X | Camiguin | 126922 | Volcan ES | MAMBAJAO (Capital) | 0 | 1 | 3 | Repair of Classrooms | 1356240 | 1 | 1356239.24 | COMPLETED | 1 | [10 empty] | Waiting for Sub-ARO
2200 | REPAIR 2020 | Region X | Camiguin | 126934 | MANUYOG ES | SAGAY | 0 | 1 | 1 | Repair of Classroom | 610453 | 1 | 610452.81 | COMPLETED | 1 | [10 empty] | Waiting for Sub-ARO
2201 | REPAIR 2020 | Region X | El Salvador | 127679 | Sinaloc Elementary School | CITY OF EL SALVADOR | 2 | 1 | 11 | Repair of Classrooms | 5475269 | 1 |  | COMPLETED | 1 | [10 empty] | Under-procurement
2202 | REPAIR 2020 | Region X | Gingoog City | 128007 | Anakan Central School | GINGOOG CITY | 1 | 1 | 2 | Repair of Classrooms | 1848904 | 1 |  | COMPLETED | 1
2203 | REPAIR 2020 | Region X | Gingoog City | 128016 | Elpidio Galarion Ampatin PS (Mangilit PS) | GINGOOG CITY | 1 | 1 | 2 | Repair of Classrooms | 1838607 | 1 |  | COMPLETED | 1 | [10 empty] | with issue on peace and order
2204 | REPAIR 2020 | Region X | Gingoog City | 128044 | Tagdaging Elementary School | GINGOOG CITY | 1 | 1 | 2 | Repair of Classrooms | 1839227 | 1 |  | COMPLETED | 1
2205 | REPAIR 2020 | Region X | Iligan City | 128153 | Bernardo E. Ramos Memorial School | ILIGAN CITY | 0 | 1 | 3 | Repair of Classrooms | 553054 | 1 |  | COMPLETED | 1 | [10 empty] | for award
2206 | REPAIR 2020 | Region X | Iligan City | 128090 | Iligan City SPED Center | ILIGAN CITY | 0 | 1 | 18 | Repair of Classrooms | 2171114 | 1 |  | COMPLETED | 1 | [10 empty] | WITH LD
2207 | REPAIR 2020 | Region X | Iligan City | 128103 | Mandulog ES | ILIGAN CITY | 0 | 1 | 10 | Repair of Classrooms | 1469000 | 1 |  | COMPLETED | 1 | [10 empty] | for award
2208 | REPAIR 2020 | Region X | Iligan City | 128087 | Servillano G. Reuyan Memorial Elementary School | ILIGAN CITY | 0 | 1 | 4 | Repair of Classrooms | 721717 | 1 |  | COMPLETED | 1 | [10 empty] | for award
2209 | REPAIR 2020 | Region X | Iligan City | 128144 | Villaverde ES | ILIGAN CITY | 0 | 1 | 12 | Repair of Classrooms | 1601250 | 1 |  | COMPLETED | 1 | [10 empty] | WITH LD
2210 | REPAIR 2020 | Region X | Lanao del Norte | 126945 | Minaulon Elementary School | BACOLOD | 1 | 1 | 4 | Repair of Classrooms | 1126939 | 1 | 1126938.04 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Yamar Construction
2211 | REPAIR 2020 | Region X | Lanao del Norte | 126947 | Rufino Santos Sr MES | BACOLOD | 1 | 1 | 5 | Repair of Classrooms | 1662788 | 1 | 1662787.66 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Yamar Construction
2212 | REPAIR 2020 | Region X | Lanao del Norte | 126948 | Rupagan ES | BACOLOD | 1 | 1 | 7 | Repair of Classrooms | 1695571 | 1 | 1695570.93 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Lanao Genesis Construction Supply
2213 | REPAIR 2020 | Region X | Lanao del Norte | 126983 | Pendulonan PS | BAROY | 1 | 1 | 2 | Repair of Classrooms | 788032 | 1 | 788031.04 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Lanao Genesis Construction Supply
2214 | REPAIR 2020 | Region X | Lanao del Norte | 127056 | Libertad ES | KOLAMBUGAN | 1 | 1 | 2 | Repair of Classrooms | 740972 | 1 | 740971.71 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Lanao Genesis Construction Supply
2215 | REPAIR 2020 | Region X | Lanao del Norte | 127110 | Atanacia Logronio ES (Segapod ES) | MAIGO | 1 | 1 | 6 | Repair of Classrooms | 1804270 | 1 | 1804269.16 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Lanao Genesis Construction Supply
2216 | REPAIR 2020 | Region X | Lanao del Norte | 127115 | Liangan West ES | MAIGO | 1 | 1 | 5 | Repair of Classrooms | 1399695 | 1 | 1399694.96 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Lanao Genesis Construction Supply
2217 | REPAIR 2020 | Region X | Lanao del Norte | 127237 | Kakai-Renabor ES | TUBOD (Capital) | 1 | 1 | 5 | Repair of Classrooms | 1416436 | 1 | 1416435.36 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Millenium Builders & Construction
2218 | REPAIR 2020 | Region X | Lanao del Norte | 315102 | Lanao del Norte Provincial Science and Technology HS (former Malingao NHS (Annex New Pualas NHS) | TUBOD (Capital) | 1 | 1 | 14 | Repair of Classrooms | 3759554 | 1 |  | COMPLETED | 1
2219 | REPAIR 2020 | Region X | Lanao del Norte | 127228 | Malingao Central School | TUBOD (Capital) | 1 | 1 | 10 | Repair of Classrooms | 2771299 | 1 | 2771298.55 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Millenium Builders & Construction
2220 | REPAIR 2020 | Region X | Lanao del Norte | 127086 | Maranding CES | LALA | 2 | 1 | 1 | Repair of Multi-Purpose Bldg. | 2655805 | 1 | 2655804.75 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Inmar Builders
2221 | REPAIR 2020 | Region X | Malaybalay City | 126550 | Miglamin ES | CITY MALAYBALAY (Capital) | 2 | 1 | 15 | Repair of Classrooms | 4054554 | 1 | 4054553.38 | COMPLETED | 1 |  |  | 002-INFRA -2020-001 | 002-INFRA -2020-001 | 2020-01-30 | 2020-02-07 | 2020-02-19 |  |  |  | Under-procurement
2222 | REPAIR 2020 | Region X | Misamis Occidental | 127326 | Pestanas ES | CALAMBA | 1 | 1 | 3 | Repair of Classrooms | 1006093 | 1 | 1006092.03 | COMPLETED | 1 | [10 empty] | for award
2223 | REPAIR 2020 | Region X | Misamis Occidental | 127419 | Lopez Jaena CS | LOPEZ JAENA | 1 | 1 | 22 | Repair of Classrooms | 7286935 | 1 | 7286934.67 | COMPLETED | 1
2224 | REPAIR 2020 | Region X | Misamis Occidental | 127483 | Panaon CES | PANAON | 1 | 1 | 23 | Repair of Classrooms | 6066929 | 1 | 6066928.88 | COMPLETED | 1
2225 | REPAIR 2020 | Region X | Misamis Occidental | 127286 | Bagong Anonang Diut ES | BONIFACIO | 2 | 1 | 1 | Repair of Classroom | 404547 | 1 | 404546.21 | COMPLETED | 1 | [10 empty] | for award
2226 | REPAIR 2020 | Region X | Misamis Occidental | 127342 | Lupagan Elementary School | CLARIN | 2 | 1 | 3 | Repair of Classrooms | 924746 | 1 | 924745.55 | COMPLETED | 1 | [10 empty] | for award
2227 | REPAIR 2020 | Region X | Misamis Occidental | 127357 | Sebasi ES | CLARIN | 2 | 1 | 1 | Repair of Classroom | 370302 | 1 | 370301.95 | COMPLETED | 1 | [10 empty] | for award
2228 | REPAIR 2020 | Region X | Misamis Occidental | 127545 | Katipunan ES | SINACABAN | 2 | 1 | 7 | Repair of Classrooms | 2430598 | 1 | 1797255.26 | COMPLETED | 1 | [10 empty] | for award
2229 | REPAIR 2020 | Region X | Misamis Oriental | 127826 | Portulin ES | MEDINA | 1 | 1 | 3 | Repair of Classrooms | 1149685 | 1 |  | COMPLETED | 1 | [10 empty] | For RTA
2230 | REPAIR 2020 | Region X | Misamis Oriental | 127585 | Baybay ES | ALUBIJID | 2 | 1 | 4 | Repair of Classrooms | 1573035 | 1 |  | COMPLETED | 1 | [10 empty] | For RTA
2231 | REPAIR 2020 | Region X | Misamis Oriental | 127588 | Lagtang ES | ALUBIJID | 2 | 1 | 3 | Repair of Classrooms | 1176407 | 1 |  | COMPLETED | 1 | [10 empty] | For RTA
2232 | REPAIR 2020 | Region X | Misamis Oriental | 127695 | Sinalac ES | INITAO | 2 | 1 | 3 | Repair of Classrooms | 1480061 | 1 |  | COMPLETED | 1 | [10 empty] | For RTA
2233 | REPAIR 2020 | Region X | Misamis Oriental | 127920 | Tubajon ES | LAGUINDINGAN | 2 | 1 | 6 | Repair of Classrooms | 2233191 | 1 |  | COMPLETED | 1 | [10 empty] | For RTA
2234 | REPAIR 2020 | Region X | Misamis Oriental | 501158 | Tuod ES | MANTICAO | 2 | 1 | 9 | Repair of Classrooms | 3256655 | 1 |  | COMPLETED | 1 | [10 empty] | For RTA
2235 | REPAIR 2020 | Region X | Oroquieta City | 127448 | Malindang ES | OROQUIETA CITY (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2377623 | 1 | 2377622.68 | COMPLETED | 1 | [10 empty] | for award
2236 | REPAIR 2020 | Region X | Oroquieta City | 127467 | Rizal ES | OROQUIETA CITY (Capital) | 1 | 1 | 10 | Repair of Classrooms | 3496604 | 1 | 3496603.59 | COMPLETED | 1 | [10 empty] | for award
2237 | REPAIR 2020 | Region X | Oroquieta City | 127461 | Tuyabang Proper ES | OROQUIETA CITY (Capital) | 1 | 1 | 3 | Repair of Classrooms | 689469 | 1 | 689468.57 | COMPLETED | 1 | [10 empty] | for award
2238 | REPAIR 2020 | Region X | Ozamis City | 128173 | Antero D. Hinagdanan Elementary School | OZAMIS CITY | 2 | 1 | 4 | Repair of Classrooms | 1426384 | 1 | 1426383.73 | COMPLETED | 1 | [10 empty] | for award
2239 | REPAIR 2020 | Region X | Ozamis City | 304163 | Labo National High School | OZAMIS CITY | 2 | 1 | 7 | Repair of Classrooms | 2804615 | 1 | 2804614.34 | COMPLETED | 1 | [10 empty] | for award
2240 | REPAIR 2020 | Region X | Ozamis City | 500701 | Misamis Annex Integrated School | OZAMIS CITY | 2 | 1 | 10 | Repair of Classrooms | 3046802 | 1 | 3046801.1 | COMPLETED | 1 | [10 empty] | for award
2241 | REPAIR 2020 | Region X | Tangub City | 128247 | Matugnao ES | TANGUB CITY | 2 | 1 | 3 | Repair of Classrooms | 930033 | 1 |  | COMPLETED | 1 |  |  | Repair2020-RX-Tangub City-004 |  | 2020-01-14 | 2020-01-24 | 2020-02-05 |  |  |  | for contract signing
2242 | REPAIR 2020 | Region X | Tangub City | 128250 | Panalsalan ES | TANGUB CITY | 2 | 1 | 6 | Repair of Classrooms | 1786304 | 1 |  | COMPLETED | 1 |  |  | Repair2020-RX-Tangub City-011 |  | 2020-01-14 | 2020-01-24 | 2020-02-05 |  |  |  | for contract signing
2243 | REPAIR 2020 | Region X | Tangub City | 128214 | San Apolinario ES | TANGUB CITY | 2 | 1 | 6 | Repair of Classrooms | 1786304 | 1 |  | COMPLETED | 1 |  |  | Repair2020-RX-Tangub City-008 |  | 2020-01-14 | 2020-01-24 | 2020-02-05 |  |  |  | for contract signing
2244 | REPAIR 2020 | Region X | Tangub City | 128235 | Tituron ES | TANGUB CITY | 2 | 1 | 6 | Repair of Classrooms | 1781946 | 1 |  | COMPLETED | 1 |  |  | Repair2020-RX-Tangub City-002 |  | 2020-01-14 | 2020-01-24 | 2020-02-05 |  |  |  | for contract signing
2245 | REPAIR 2020 | Region X | Valencia City | 126844 | Liloan ES | CITY OF VALENCIA | 4 | 1 | 4 | Repair of Classrooms | 1298766 | 1 |  | COMPLETED | 1 | [10 empty] | for award
3629 | REPAIR 2021 | Region X | Bukidnon | 126278 | Salimbalan ES | BAUNGON | 1 | 1 | 3 | Repair of Classrooms | 2253180.23 | 1 |  | COMPLETED | 1
3630 | REPAIR 2021 | Region X | Bukidnon | 126385 | Kubayan ES | IMPASUG-ONG | 2 | 1 | 4 | Repair of Classrooms | 2371397.18 | 1 |  | COMPLETED | 1
3631 | REPAIR 2021 | Region X | Bukidnon | 126404 | Mabuhay ES | KADINGILAN | 3 | 1 | 3 | Repair of Classrooms | 1806904.73 | 1 |  | COMPLETED | 1
3632 | REPAIR 2021 | Region X | Cagayan de Oro City | 128003 | Iponan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 1904895.89 | 1 |  | COMPLETED | 1 | 2021-12-12 |  | REPAIR 2021 - RX - CAGAYAN DE ORO CITY - 001 | 2021-005 | 2021-06-28 | 2021-07-05 | 2021-08-20 | 2021-09-06 | September 13,2021 | JARM Construction Services and Supply
3633 | REPAIR 2021 | Region X | Cagayan de Oro City | 127982 | Pagalungan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 1017217.93 | 1 |  | COMPLETED | 1 | 2021-12-12 |  | REPAIR 2021 - RX - CAGAYAN DE ORO CITY - 003 | 2021-005 | 2021-06-28 | 2021-07-05 | 2021-08-20 | 2021-09-06 | September 13,2021 | JARM Construction Services and Supply
3634 | REPAIR 2021 | Region X | Cagayan de Oro City | 315408 | Gusa National High School - FS Catanico Annex | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 8 | Repair of Classrooms | 2684852.97 | 1 |  | COMPLETED | 1 | 2022-01-11 |  | REPAIR 2021 - RX - CAGAYAN DE ORO CITY - 002 | 2021-006 | 2021-06-28 | 2021-07-05 | 2021-08-20 | 2021-09-06 | September 13,2021 | JARM Construction Services and Supply
3635 | REPAIR 2021 | Region X | Camiguin | 126929 | Cabuan ES | GUINSILIBAN | 0 | 1 | 7 | Repair of Classrooms | 2579270.93 | 1 |  | COMPLETED | 1 | 2022-02-05 | [7 empty] | 2021-08-09 | VINLABZ CONSTRUCTION
3636 | REPAIR 2021 | Region X | Camiguin | 126934 | Manuyog ES | SAGAY | 0 | 1 | 1 | Rehabilitation of H.E. Bldg. | 420729.07 | 1 | 610452.81 | COMPLETED | 1 | 2022-02-05 | [7 empty] | 2021-08-09 | VINLABZ CONSTRUCTION | Waiting for Sub-ARO
3637 | REPAIR 2021 | Region X | El Salvador | 127675 | Kibonbon ES | CITY OF EL SALVADOR | 2 | 1 | 4 | Repair of Classrooms | 3003709.82 | 1 |  | COMPLETED | 1
3638 | REPAIR 2021 | Region X | Gingoog City | 501379 | Alfonso Ang Militante Integrated School - Elem | GINGOOG CITY | 1 | 1 | 2 | Repair of Classrooms | 934544.54 | 1 |  | COMPLETED | 1 | [10 empty] | for issuance of NTP
3639 | REPAIR 2021 | Region X | Gingoog City | 128026 | DULAG ELEMENTARY SCHOOL | GINGOOG CITY | 1 | 1 | 4 | Repair of Classrooms | 2075040.34 | 1 |  | COMPLETED | 1 | [10 empty] | for issuance of NTP
3640 | REPAIR 2021 | Region X | Iligan City | 128106 | Bulalang Elementary School | ILIGAN CITY | 0 | 1 | 4 | Repair of Classrooms | 1095118.2 | 1 |  | COMPLETED | 1 | [10 empty] | for award
3641 | REPAIR 2021 | Region X | Iligan City | 128140 | Doña Juana A. Lluch MCS | ILIGAN CITY | 0 | 1 | 2 | Repair of Classrooms | 756841.2 | 1 |  | COMPLETED | 1 | [10 empty] | for award
3642 | REPAIR 2021 | Region X | Iligan City | 128102 | Lanipao ES | ILIGAN CITY | 0 | 1 | 7 | Repair of Classrooms | 3188086.04 | 1 |  | COMPLETED | 1 | [10 empty] | for award
3643 | REPAIR 2021 | Region X | Lanao del Norte | 126978 | Fausto Alvia MES | BAROY | 1 | 1 | 10 | Repair of Classrooms | 4552901.44 | 1 |  | COMPLETED | 1 |  |  | 2021-02- INFRA- Lot No. 1 |  |  |  | 2021-08-05 |  |  | AMMAR Construcrion & Enterprises
3644 | REPAIR 2021 | Region X | Lanao del Norte | 200511 | San Juan PS | BAROY | 1 | 1 | 1 | Repair of Classroom | 574294.78 | 1 |  | COMPLETED | 1 | 2022-01-26 |  | 2021-02- INFRA-Lot No. 2 |  |  |  | 2021-08-05 |  | 2021-10-20 | INMAR Builder & Enterprises
3645 | REPAIR 2021 | Region X | Lanao del Norte | 127005 | CONCEPCION ELEMENTARY SCHOOL | KAPATAGAN | 2 | 1 | 2 | Repair of Classrooms | 942043.8 | 1 |  | COMPLETED | 1 | 2022-01-26 |  | 2021-02- INFRA-Lot No. 2 |  |  |  | 2021-08-05 |  | 2021-10-20 | INMAR Builder & Enterprises
3646 | REPAIR 2021 | Region X | Lanao del Norte | 501240 | Calube Integrated School | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 2 | Repair of Classrooms | 1601151 | 1 |  | COMPLETED | 1 | 2022-01-26 |  | 2021-02- INFRA-Lot No. 3 |  |  |  | 2021-08-05 |  | 2021-10-20 | Lanao Genesis Construction Supply
3647 | REPAIR 2021 | Region X | Malaybalay City | 126575 | Baganao ES | CITY MALAYBALAY (Capital) | 2 | 1 | 4 | Repair of Classrooms | 1279959.15 | 1 |  | COMPLETED | 1 | 2022-09-30 |  | 002-INFRA-2021 | 002-INFRA-2021 | 2021-06-10 | 2021-06-19 | 2021-06-30 | 2021-07-26 | 2021-08-30 | X & C Building Construction | For Punchlist Inspection
3648 | REPAIR 2021 | Region X | Malaybalay City | 126535 | Balangbang ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | Repair of Classrooms | 827616.47 | 1 |  | COMPLETED | 1 | 2022-09-30 |  | 002-INFRA-2021 | 002-INFRA-2021 | 2021-06-10 | 2021-06-18 | 2021-06-30 | 2021-07-26 | 2021-08-30 | X & C Building Construction | Issued Punchlist Inspection Report for Final Inspection
3649 | REPAIR 2021 | Region X | Malaybalay City | 126588 | Natid-asan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 3 | Repair of Classrooms | 892424.38 | 1 |  | COMPLETED | 1 | 2022-09-30 |  | 002-INFRA-2021 | 002-INFRA-2021 | 2021-06-10 | 2021-06-20 | 2021-06-30 | 2021-07-26 | 2021-08-30 | X & C Building Construction | Issued Punchlist Inspection Report for Final Inspection
3650 | REPAIR 2021 | Region X | Misamis Occidental | 127392 | Guintomoyan ES | JIMENEZ | 1 | 1 | 2 | Repair of Classrooms | 1164418.06 | 1 |  | COMPLETED | 1 |  |  | REPAIR 2021-RX-Misamis Occidental-001 |  | July 1, 2021 | July 9, 2021 | July 21, 2021 | August 13, 2021 |  | KAYRO CONSTRUCTION & SUPPLY
3651 | REPAIR 2021 | Region X | Misamis Occidental | 127356 | San Roque ES | CLARIN | 2 | 1 | 9 | Repair of Classrooms | 4449102.42 | 1 |  | COMPLETED | 1 |  |  | REPAIR 2021-RX-Misamis Occidental-002 |  | July 1, 2021 | July 9, 2021 | July 21, 2021 | August 13, 2021 |  | ESL MILESTONE BUILDERS & SUPPLY, INC
3652 | REPAIR 2021 | Region X | Misamis Occidental | 304046 | Nueva Vista National High School | DON VICTORIANO CHIONGBIAN | 2 | 1 | 4 | Repair of Classrooms | 2282577.48 | 1 |  | COMPLETED | 1 |  |  | REPAIR 2021-RX-Misamis Occidental-003 |  | July 1, 2021 | July 9, 2021 | July 21, 2021 | August 13, 2021 |  | ESL MILESTONE BUILDERS & SUPPLY, INC
3653 | REPAIR 2021 | Region X | Misamis Oriental | 127764 | Quezon ES | GITAGUM | 2 | 1 | 3 | Repair of Classrooms | 1875615.35 | 1 |  | COMPLETED | 1 | [5 empty] | Aug 19,2021 | Aug 31,2021 | Sept 6,2021 | Sept 8,2021 | TriFB
3654 | REPAIR 2021 | Region X | Misamis Oriental | 127711 | San Isidro ES | JASAAN | 2 | 1 | 4 | Repair of Classrooms | 2253427.64 | 1 |  | COMPLETED | 1 | [5 empty] | Aug 19,2021 | Aug 31,2021 | Sept 6,2021 | Sept 8,2021 | TriFB
3655 | REPAIR 2021 | Region X | Oroquieta City | 127444 | Cosme Cagas Memorial School | OROQUIETA CITY (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1873870.36 | 1 |  | COMPLETED | 1 | 2021-11-07 |  |  |  | 2021-05-27 | June 16,2021 | 2021-06-28 | 2021-07-12 | 2021-08-09 | Kayro Construction & Supply | Variance is subject for Variation order & Additional Works
3656 | REPAIR 2021 | Region X | Oroquieta City | 304052 | Senote NHS | OROQUIETA CITY (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1200968.32 | 1 |  | COMPLETED | 1 | 2021-11-07 |  |  |  | 2021-05-27 | June 16,2021 | 2021-06-28 | 2021-07-12 | 2021-08-09 | Kayro Construction & Supply | Variance is subject for Variation order & Additional Works
3657 | REPAIR 2021 | Region X | Ozamis City | 128197 | Juan A. Acapulco Elementary School | OZAMIS CITY | 2 | 1 | 7 | Repair of Classrooms | 3380610.6 | 1 |  | COMPLETED | 1 | 2021-11-27 |  | REPAIR2021-RX-OZAMIZCITY-001 | 092-INFRA2021-002 | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-23 | 2021-08-18 | JJFY Construction Services
3658 | REPAIR 2021 | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 | 1 | 1 | Rehabilitation of Library Hub Bldg. | 2616798.77 | 1 |  | COMPLETED | 1 | 2021-11-17 |  | REPAIR2021-RX-OZAMIZCITY-002 | 092-INFRA2021-003 | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-23 | 2021-08-18 | JJFY Construction Services
3659 | REPAIR 2021 | Region X | Tangub City | 128231 | Salimpuno Elementary School | TANGUB CITY | 2 | 1 | 5 | Repair of Classrooms | 2542915.98 | 1 |  | COMPLETED | 1 | 2021-11-02 |  | REPAIR2021-RX-TANGUB CITY-001 |  | 2021-06-02 | 2021-06-10 | 2021-06-22 | 2021-07-04 | 2021-07-12 | ESL MILESTONE BUILDERS & SUPPLY, INC
3660 | REPAIR 2021 | Region X | Tangub City | 128257 | Sumirap Central School | TANGUB CITY | 2 | 1 | 5 | Repair of Classrooms | 2536138.58 | 1 |  | COMPLETED | 1 | 2021-11-02 |  | REPAIR2021-RX-TANGUB CITY-002 |  | 2021-06-02 | 2021-06-10 | 2021-06-22 | 2021-07-04 | 2021-07-12 | ESL MILESTONE BUILDERS & SUPPLY, INC
3661 | REPAIR 2021 | Region X | Valencia City | 126850 | MAILAG CENTRAL SCHOOL | CITY OF VALENCIA | 4 | 1 | 8 | Repair of Classrooms | 5203482.82 | 1 |  | COMPLETED | 1 | 2021-11-25 |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-21 | 2021-06-23 | 2021-06-28 | White Beard Construction
4122 | REPAIR 2022 | Region X | Camiguin | 126893 | Tangaro ES | CATARMAN | 0 | 1 | 6 | Repair of Classrooms | 3077889.81 | 1 | 2807412.83 | COMPLETED | 1 | 2022-12-03 |  | INFRA-01-02-2022 | INFRA-01-02-2022 | 2022-02-15 | 2022-02-23 | 2022-03-07 | 2022-04-11 | 2022-06-06 | MINKONSTRAK ENGINEERING & GEN. SRVC. | Completed
4123 | REPAIR 2022 | Region X | Camiguin | 500962 | Bacnit Integrated School | SAGAY | 0 | 1 | 5 | Repair of Classrooms | 2836875.5 | 1 | 3046248.33 | COMPLETED | 1 | 2022-12-03 |  | INFRA-01-01-2022 | INFRA-01-01-2022 | 2022-02-15 | 2022-02-23 | 2022-03-07 | 2022-04-11 | 2022-06-06 | MINKONSTRAK ENGINEERING & GEN. SRVC. | Completed
4124 | REPAIR 2022 | Region X | El Salvador | 127671 | El Salvador City CS | CITY OF EL SALVADOR | 2 | 1 | 2 | Repair of Classrooms | 1100000 | 1 | 1098020.25 | COMPLETED | 1 | 2022-09-09 | 2022-09-22 | 2022-02-0014 | 2022-07-0151 | 2022-02-22 | 2022-03-09 | 2022-03-21 | 2022-06-14 | 2022-07-13 | 3L and JES Construction | Completed
4125 | REPAIR 2022 | Region X | El Salvador | 315318 | Hinigdaan NHS | CITY OF EL SALVADOR | 2 | 1 | 4 | Repair of Classrooms | 572224 | 1 | 371364.47 | COMPLETED | 1 | 2022-09-09 | 2022-09-22 | 2022-02-0015 | 2022-07-0152 | 2022-02-22 | 2022-03-09 | 2022-03-21 | 2022-06-14 | 2022-07-13 | 3L and JES Construction | Completed
4126 | REPAIR 2022 | Region X | Lanao del Norte | 127043 | Kauswagan CES | KAUSWAGAN | 1 | 1 | 12 | Repair of Classrooms | 5629079.84 | 1 | 4499745.95 | COMPLETED | 1 | 2022-11-10 |  |  | Lot-4 | 2022-02-15 | 2022-02-23 | 2022-03-08 | 2022-05-16 | 2022-07-07 | MOH'D Construction
4127 | REPAIR 2022 | Region X | Lanao del Norte | 127097 | Purakan Elementary School | LINAMON | 1 | 1 | 7 | Repair of Classrooms | 2802226.63 | 1 | 2296283.81 | COMPLETED | 1 | 2022-10-11 | 2022-10-25 |  | Lot-2 | 2022-02-15 | 2022-02-23 | 2022-03-08 | 2022-04-18 | 2022-06-20 | ABRAHAM-BM Construction
4128 | REPAIR 2022 | Region X | Lanao del Norte | 127136 | Sultan Macalpang Permites CS (Matungao CES) | MATUNGAO | 1 | 1 | 15 | Repair of Classrooms | 6201512.58 | 1 | 4767687.39 | COMPLETED | 1 | 2022-11-09 |  |  | Lot-5 | 2022-02-15 | 2022-02-23 | 2022-03-08 | 2022-04-18 | 2022-06-20 | RAMZIE Builders & Enterprises | Punchlist
4129 | REPAIR 2022 | Region X | Lanao del Norte | 127165 | Lower Kalanganan PS | PANTAR | 1 | 1 | 3 | Repair of Classrooms | 1524953.52 | 1 | 1325129.24 | COMPLETED | 1 | 2022-10-11 | 2022-11-29 |  | Lot-1 | 2022-02-15 | 2022-02-23 | 2022-03-08 | 2022-04-18 | 2022-06-20 | SBM Builder
4130 | REPAIR 2022 | Region X | Lanao del Norte | 127211 | CABASARAN PS | TAGOLOAN | 1 | 1 | 2 | Repair of Classrooms | 743312.94 | 1 | 646706.7 | COMPLETED | 1 | 2022-10-11 | 2022-11-29 |  |  | 2022-02-15 | 2022-02-23 | 2022-03-08 | 2022-04-18 | 2022-06-20 | SBM Builder
4131 | REPAIR 2022 | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL | 2 | 1 | 3 | Repair of Classrooms | 1467550.2 | 1 | 1452276.7 | COMPLETED | 1 | 2022-10-11 |  |  | Lot-3 | 2022-02-15 | 2022-02-23 | 2022-03-08 | 2022-04-18 | 2022-06-20 | MOH'D Construction | Substantially Completed
4132 | REPAIR 2022 | Region X | Misamis Occidental | 501880 | Sapang Ama Integrated School | SAPANG DALAGA | 1 | 1 | 3 | Repair of Classrooms | 2009565.97 | 1 |  | COMPLETED | 1 | 2022-10-17 | 2022-11-11 | 010-2022 | 010-2022 | 2022-02-23 | 2022-03-02 | 2022-03-14 | 2022-05-10 | 2022-07-26 | KAYRO Construction and Supply | subject for final inspection
4133 | REPAIR 2022 | Region X | Misamis Occidental | 304055 | Sinonoc NHS | SINACABAN | 2 | 1 | 17 | Repair of Classrooms | 10675365.03 | 1 |  | COMPLETED | 1 | 2022-12-01 |  | 009-2022 | 009-2022 | 2022-02-23 | 2022-03-02 | 2022-03-14 | 2022-05-10 | 2022-07-26 | JJFY Construction and Services | on-going
4134 | REPAIR 2022 | Region X | Misamis Oriental | 201505 | Bauk-Bauk ES | BALINGOAN | 1 | 1 | 1 | Repair of Classroom with Embankment & Riprap | 747250 | 1 | 582206.44 | COMPLETED | 1 | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-17 | GREEN BUILDER AND ENTERPRISE | for punchlisting
4135 | REPAIR 2022 | Region X | Misamis Oriental | 127878 | Kabangasan ES | BALINGOAN | 1 | 1 | 1 | Repair of Classroom | 473640.36 | 1 | 432034.86 | COMPLETED | 1 | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-17 | GREEN BUILDER AND ENTERPRISE
4136 | REPAIR 2022 | Region X | Misamis Oriental | 127887 | Mapua ES | BALINGOAN | 1 | 1 | 2 | Repair of Classrooms | 1104388.18 | 1 | 937124.44 | COMPLETED | 1 | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-17 | GREEN BUILDER AND ENTERPRISE
4137 | REPAIR 2022 | Region X | Misamis Oriental | 127740 | Valdeconcha ES | BINUANGAN | 1 | 1 | 4 | Repair of Classrooms | 1659691.73 | 1 | 1445658.19 | COMPLETED | 1 | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-17 | GREEN BUILDER AND ENTERPRISE | Substancially Completed
4138 | REPAIR 2022 | Region X | Misamis Oriental | 127737 | Suarez ES | KINOGUITAN | 1 | 1 | 2 | Repair of Classrooms | 1110727.03 | 1 | 919693.99 | COMPLETED | 1 | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-24 | ALEBON GENUINE MERCHANDIZING INC.
4139 | REPAIR 2022 | Region X | Misamis Oriental | 127747 | Lagonglong CS | LAGONGLONG | 1 | 1 | 4 | Repair of Classrooms | 1976088.08 | 1 | 1571802.16 | COMPLETED | 1 | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-24 | ALEBON GENUINE MERCHANDIZING INC. | on-going
4140 | REPAIR 2022 | Region X | Misamis Oriental | 127731 | Mangga ES | SUGBONGCOGON | 1 | 1 | 2 | Repair of Classrooms | 1138119.97 | 1 | 930454.79 | COMPLETED | 1 | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-24 | ALEBON GENUINE MERCHANDIZING INC.
4141 | REPAIR 2022 | Region X | Misamis Oriental | 127753 | C.P. Garcia ES | GITAGUM | 2 | 1 | 4 | Repair of Classrooms | 1770692.18 | 1 | 1389931.3 | COMPLETED | 1 | 2022-12-09 | 2022-11-25 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-17 | JDE CONSTRUCTION
4142 | REPAIR 2022 | Region X | Misamis Oriental | 127759 | Natalio L. Bongcas Sr. Memorial ES | GITAGUM | 2 | 1 | 2 | Repair of Classrooms | 1107389.8 | 1 | 872625.55 | COMPLETED | 1 | 2022-12-09 | 2022-11-04 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-17 | JDE CONSTRUCTION
5174 | REPAIR 2023 | Region X | Camiguin | 126909 | Benhaan ES | MAMBAJAO (Capital) | Lone | 1 | 4 | Repair of Classrooms | 528720.48 | DEPED (Batch 1) | 496580.82 | COMPLETED | 1 | 2024-02-02 | 2024-02-29 | REPAIR 2023 - R X - CAMIGUIN - 001 | OSEC-10-23-4914 | 2023-10-13 |  | 2023-12-01 | 2023-12-06 | 2024-01-03 | MINKONSTRAK ENG'G. & GEN. SRVCS.
5175 | REPAIR 2023 | Region X | Camiguin | 126919 | Sorosoro ES | MAMBAJAO (Capital) | Lone | 1 | 4 | Repair of Classrooms | 2624639.98 | DPWH (Batch 1) |  | COMPLETED | 1
5176 | REPAIR 2023 | Region X | Camiguin | 126920 | Tagdo ES | MAMBAJAO (Capital) | Lone | 1 | 4 | Repair of Classrooms | 2415853.39 | DPWH (Batch 1) |  | COMPLETED | 1
5177 | REPAIR 2023 | Region X | Camiguin | 126923 | Yumbing ES | MAMBAJAO (Capital) | Lone | 1 | 6 | Repair of Classrooms | 1924624.92 | DPWH (Batch 1) |  | COMPLETED | 1
5178 | REPAIR 2023 | Region X | El Salvador | 127670 | Cogon ES | CITY OF EL SALVADOR | 2nd | 1 | 4 | Repair of Classrooms | 2705200 | DPWH (Batch 1) | 2532178.52 | COMPLETED | 1 | 2023-10-21 | 2023-10-21 | P00775406NP | 23KL0096 | 2023-05-17 | 2023-05-24 | 2023-06-15 | 2023-08-17 | 2023-08-22 | KS AGAD Construction | Based on report submitted by DPWH
5179 | REPAIR 2023 | Region X | El Salvador | 127676 | Molugan Central School | CITY OF EL SALVADOR | 2nd | 1 | 4 | Repair of Classrooms | 2755500 | DPWH (Batch 1) | 2634468.65 | COMPLETED | 1 | 2023-10-21 | 2023-10-21 | P00775407NP | 23KL0097 | 2023-05-17 | 2023-05-24 | 2023-06-15 | 2023-08-17 | 2023-08-22 | XYTEX Construction | Based on report submitted by DPWH
5180 | REPAIR 2023 | Region X | El Salvador | 127680 | Taytay ES | CITY OF EL SALVADOR | 2nd | 1 | 4 | Repair of Classrooms | 2650800 | DPWH (Batch 1) | 2531810.63 | COMPLETED | 1 | 2023-10-21 | 2023-10-21 | P00775408NP | 23KL0095 | 2023-05-17 | 2023-05-24 | 2023-06-15 | 2023-08-17 | 2023-08-22 | M & L Construction and Enterprises | Based on report submitted by DPWH
5181 | REPAIR 2023 | Region X | Lanao del Norte | 500453 | Kawit Oriental Integrated School | KAUSWAGAN | 1st | 1 | 5 | Repair of Classrooms | 2651306.27 | DPWH (Batch 1) |  | COMPLETED | 1
5182 | REPAIR 2023 | Region X | Lanao del Norte | 127095 | Linamon Central School | LINAMON | 1st | 1 | 5 | Repair of Classrooms | 2671255.51 | DPWH (Batch 1) |  | COMPLETED | 1
5183 | REPAIR 2023 | Region X | Lanao del Norte | 501030 | Samburon Integrated School | LINAMON | 1st | 1 | 5 | Repair of Classrooms | 3232784.29 | DPWH (Batch 1) |  | COMPLETED | 1
5184 | REPAIR 2023 | Region X | Lanao del Norte | 501557 | Matampay Integrated School | MATUNGAO | 1st | 1 | 7 | Repair of Classrooms | 4427006.66 | DPWH (Batch 1) |  | COMPLETED | 1
5185 | REPAIR 2023 | Region X | Lanao del Norte | 304012 | MATUNGAO NATIONAL HIGH SCHOOL | MATUNGAO | 1st | 1 | 9 | Repair of Classrooms | 4924284.54 | DPWH (Batch 1) |  | COMPLETED | 1
5186 | REPAIR 2023 | Region X | Lanao del Norte | 127212 | DIMAYON PS | TAGOLOAN | 1st | 1 | 4 | Repair of Classrooms | 2267977.31 | DPWH (Batch 1) |  | COMPLETED | 1
5187 | REPAIR 2023 | Region X | Lanao del Norte | 127210 | SAPAD ELEMENTARY SCHOOL | SAPAD | 2nd | 1 | 4 | Repair of Classrooms | 2695218.99 | DPWH (Batch 1) |  | COMPLETED | 1
5188 | REPAIR 2023 | Region X | Lanao del Norte | 501667 | Sapad Integrated School | SAPAD | 2nd | 1 | 3 | Repair of Classrooms | 1916237.29 | DPWH (Batch 1) |  | COMPLETED | 1
5189 | REPAIR 2023 | Region X | Misamis Occidental | 127542 | COLUPAN BAJO ES | SINACABAN | 2nd | 1 | 5 | Repair of Classrooms | 4200000 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | With rectification works
5190 | REPAIR 2023 | Region X | Misamis Occidental | 127544 | ESTRELLA ES | SINACABAN | 2nd | 1 | 5 | Repair of Classrooms | 4419000 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | With rectification works
5191 | REPAIR 2023 | Region X | Misamis Occidental | 304038 | KATIPUNAN NHS | SINACABAN | 2nd | 1 | 16 | Repair of Classrooms | 10930000 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | With rectification works
5192 | REPAIR 2023 | Region X | Misamis Occidental | 127554 | Sinacaban CS | SINACABAN | 2nd | 1 | 9 | Repair of Classrooms | 6485000 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | Completed
5193 | REPAIR 2023 | Region X | Misamis Oriental | 127893 | San Alonzo ES | BALINGOAN | 1st | 1 | 3 | Repair of Classrooms | 1875000 | DPWH (Batch 1) | 1875000 | COMPLETED | 1 | 19/11/2023 | 2023-12-11 | P00775421NP | 23KK0187
5194 | REPAIR 2023 | Region X | Misamis Oriental | 304067 | Dampias A.O. Rañises NHS | BINUANGAN | 1st | 1 | 2 | Repair of Classrooms | 1336750.68 | DPWH (Batch 1) | 1336750.68 | COMPLETED | 1 | 2023-04-12 | 21/11/2023 | P00775422NP | 23KK0188
5195 | REPAIR 2023 | Region X | Misamis Oriental | 127718 | Bolisong ES | KINOGUITAN | 1st | 1 | 2 | Repair of Classrooms | 1349621.8 | DPWH (Batch 1) | 1349621.8 | COMPLETED | 1 | 2023-01-12 | 27/11/2023 | P00775423NP | 23KK0184
5196 | REPAIR 2023 | Region X | Misamis Oriental | 127748 | Lumbo ES | LAGONGLONG | 1st | 1 | 4 | Repair of Classrooms | 2395243.76 | DPWH (Batch 1) | 2395243.76 | COMPLETED | 1 | 19/11/2023 | 15/11/2023 | P00775424NP | 23KK0185 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
5197 | REPAIR 2023 | Region X | Misamis Oriental | 127749 | Manaol ES | LAGONGLONG | 1st | 1 | 2 | Repair of Classrooms | 1345592.02 | DPWH (Batch 1) | 1345592.02 | COMPLETED | 1 | 2023-04-12 | 20/11/2023 | P00775425NP | 23KK0195 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
5198 | REPAIR 2023 | Region X | Misamis Oriental | 127750 | Tabok ES | LAGONGLONG | 1st | 1 | 3 | Repair of Classrooms | 2115052.94 | DPWH (Batch 1) | 2115052.94 | COMPLETED | 1 | 2023-04-12 | 2023-08-11 | P00775426NP | 23KK0189 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental
5199 | REPAIR 2023 | Region X | Misamis Oriental | 127736 | Silad ES | SUGBONGCOGON | 1st | 1 | 1 | Repair of Classroom | 625000 | DEPED (Batch 1) |  | COMPLETED | 1 | 2024-03-16 | 2024-03-18 | G2PB Repair 2023-01 |  |  |  | 2024-02-12 |  | 2024-02-16 | RI Construction Services
5200 | REPAIR 2023 | Region X | Misamis Oriental | 304101 | Sugbongcogon NHS | SUGBONGCOGON | 1st | 1 | 4 | Repair of Classrooms | 2545875.39 | DPWH (Batch 1) | 2544704.45 | COMPLETED | 1 | 2023-04-12 | 29/11/2023 | P00775427NP | 23KK0196
5201 | REPAIR 2023 | Region X | Misamis Oriental | 127758 | Gitagum CS | GITAGUM | 2nd | 1 | 3 | Repair of Classrooms | 1875000 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | Based on report submitted by DPWH and was checked on January 31, 2024.
5202 | REPAIR 2023 | Region X | Misamis Oriental | 304086 | Matangad NHS | GITAGUM | 2nd | 1 | 4 | Repair of Classrooms | 2500000 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | Based on report submitted by DPWH and was checked on January 31, 2024.
5203 | REPAIR 2023 | Region X | Misamis Oriental | 127760 | Libertad CS | LIBERTAD | 2nd | 1 | 4 | Repair of Classrooms | 2500000 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | Previous accomplishment was based on the report submitted by DPWH. It was corrected during the joint inspection conducted on January 31, 2024.
5563 | REPAIR 2024 | Region X | Bukidnon | 126264 | Buenavista ES | BAUNGON | 1st | 1 | 2 | Repair of Classrooms | 1262626.26 | 1 | 1129319.63 | COMPLETED | 1 | 2025-01-09 | 2025-02-08 | PB-02-06-2024-0010 | 046-2024 | 2024-06-29 | 2024-07-05 | 2024-07-18 | 2024-09-04 | 2024-10-18 | TRI FB Construction & General Merchandise | Updated 2-2025. CTE-1 APPROVED. Revised Expiry on February 8, 2025. Awaiting doc reqs for official completion & turnover.
5564 | REPAIR 2024 | Region X | Bukidnon | 126267 | Kalanganan Elementary School | BAUNGON | 1st | 1 | 2 | Repair of Classrooms | 1378787.88 | 1 | 1264091.35 | COMPLETED | 1 | 2025-01-09 | 2025-02-28 | PB-02-06-2024-0010 | 047-2024 | 2024-06-29 | 2024-07-05 | 2024-07-18 | 2024-09-04 | 2024-10-18 | TRI FB Construction & General Merchandise | Updated 2-2025. CTE-2 APPROVED. Revised Expiry on February 28, 2025. Awaiting doc. reqs for official completion & turnonver.
5565 | REPAIR 2024 | Region X | Bukidnon | 126751 | Colon ES | SAN FERNANDO | 2nd | 1 | 5 | Repair of Classrooms | 3282828.28 | 1 | 3250000 | COMPLETED | 1 | 2025-04-08 | 2025-04-02 | PB-02-06-2024-0010 | 048-2024 | 2024-06-29 | 2024-07-05 | 2024-07-18 | 2024-07-29 | 2024-11-11 | Vibranium Builders Corporation | Completed
5566 | REPAIR 2024 | Region X | Bukidnon | 126359 | Old Nongnongan ES | DON CARLOS | 3rd | 1 | 4 | Repair of Classrooms | 2626262.63 | 1 | 2555805.04 | COMPLETED | 1 | 2025-03-21 | 2024-12-20 | PB-02-06-2024-0010 | 049-2024 | 2024-06-29 | 2024-07-05 | 2024-07-18 | 2024-07-29 | 2024-10-17 | Vibranium Builders Corporation | Completed
5567 | REPAIR 2024 | Region X | Cagayan de Oro City | 502015 | Cadayonan Integrated School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 4 | Repair of Classrooms | 3728406.67 | 1 | 2962474.57 | COMPLETED | 1 | 2025-03-04 | Ongoing | REPAIR 2024-X-CAGAYAN DE ORO-002 | 2024-018 | 2024-06-28 | 2024-07-15 | 2024-07-29 | 2024-08-16 | 2024-11-04 | Parbros Construction & Supply | On-going
5568 | REPAIR 2024 | Region X | Cagayan de Oro City | 304107 | Bugo National High School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 5 | Repair of Classrooms | 4986459.21 | 1 | 3813512.21 | COMPLETED | 1 | 2025-03-04 | 2025-03-04 | REPAIR 2024-X-CAGAYAN DE ORO-001 | 2024-019 | 2024-06-28 | 2024-07-15 | 2024-07-29 | 2024-08-16 | 2024-11-04 | HERA1 Strength Construction | Substantially completed
5569 | REPAIR 2024 | Region X | Camiguin | 315001 | Maac National High School | GUINSILIBAN | Lone | 1 | 12 | Repair of Classrooms | 2424242.42 | 1 |  | COMPLETED | 1 |  |  | Infra-01-05-2024 |  | 2024-09-23 | 2024-10-01 | 2024-10-14 |  |  | MINKONSTRAK ENGINEERING & GENERAL SERVICES | On-going
5570 | REPAIR 2024 | Region X | Camiguin | 126902 | San Isidro ES | MAHINOG | Lone | 1 | 4 | Repair of Classrooms | 2591596.08 | 1 |  | COMPLETED | 1 |  |  | Infra-01-06-2024 |  | 2024-09-23 | 2024-10-01 | 2024-10-14 |  |  | VINLABZ CONSTRUCTION | On-going
5571 | REPAIR 2024 | Region X | Camiguin | 126903 | Tacangon ES | MAHINOG | Lone | 1 | 2 | Repair of Classrooms | 1616161.62 | 1 |  | COMPLETED | 1 |  |  | Infra-01-07-2024 |  | 2024-09-23 | 2024-10-01 | 2024-10-14 |  |  | MINKONSTRAK ENGINEERING & GENERAL SERVICES | On-going
5572 | REPAIR 2024 | Region X | El Salvador | 315305 | MOLUGAN NATIONAL HIGH SCHOOL | CITY OF EL SALVADOR | 2nd | 1 | 8 | Repair of Classrooms | 3880688.05 | 1 | 2940701.84 | COMPLETED | 1 | 2024-02-07 | 2024-12-27 | 2024-08-0026 | 2024-09-0011 | 2024-08-08 | 2024-08-27 | 2024-09-09 | 2024-09-16 | 2024-10-07 | JDE Construction | Subject for Final Inspection
5573 | REPAIR 2024 | Region X | Gingoog City | 501400 | Talon Integrated School | GINGOOG CITY | 1st | 1 | 3 | Repair of Classrooms | 2949448.84 | 1 |  | COMPLETED | 1 | [10 empty] | On-going
5574 | REPAIR 2024 | Region X | Gingoog City | 128022 | Tinabalan Elementary School | GINGOOG CITY | 1st | 1 | 2 | Repair of Classrooms | 1915480.8 | 1 |  | COMPLETED | 1 | [10 empty] | Subject for Final Inspection
5575 | REPAIR 2024 | Region X | Iligan City | 128129 | Mainit ES | ILIGAN CITY | Lone | 1 | 7 | Repair of Classrooms | 6363636.36 | 1 | 5179347.77 | COMPLETED | 1 | 2025-04-10 | 2025-04-07 | INFRA24-08-02 | INFRA24-08-02 | 2024-08-13 | 2024-08-27 | 2024-09-09 | Octobe 15, 2024 | 2024-11-04 | Abraham BM Construction | Ongoing
5576 | REPAIR 2024 | Region X | Lanao del Norte | 126976 | Baroy CS | BAROY | 1st |  |  | Repair of Classrooms | 2451970.88 | 1 |  | Realigned (see other remarks) | 1 | [10 empty] | allocation was Re-align to Geronima
5577 | REPAIR 2024 | Region X | Lanao del Norte | 304020 | Geronima Cabrera NHS (Riverside NHS) | KOLAMBUGAN | 1st | 1 | 11 | Repair of Classrooms | 5657828.4838 | 1 | 4743199.28 | COMPLETED | 1 | 2025-04-11 |  | 2024-18(Infra) | 2024-18(Infra) | 2024-08-15 | 2024-08-30 | 2024-09-12 | 2024-11-11 | 2024-12-12 | Haffy Construction Services | Completed
5578 | REPAIR 2024 | Region X | Lanao del Norte | 127141 | Pasayanon Elementary School | MATUNGAO | 1st |  |  | Repair of Classrooms | 943065.72 | 1 |  | Realigned (see other remarks) | 1 | [10 empty] | allocation was Re-align to Geronima
5579 | REPAIR 2024 | Region X | Lanao del Norte | 127222 | Juan Ardon-Camp 5 ES | TUBOD (Capital) | 1st |  |  | Repair of Classrooms | 471532.86 | 1 |  | Realigned (see other remarks) | 1 | [10 empty] | allocation was Re-align to Geronima
5580 | REPAIR 2024 | Region X | Lanao del Norte | 127077 | Panadtaran ES | LALA | 2nd | 1 | 5 | Repair of Classrooms | 2357428.5467 | 1 |  | COMPLETED | 1 | 2025-03-26 | 2025-07-24 | 2025-01(Infra)Negotiated Procurement | 2025-01(Infra)) | 2025-01-16 | 2025-01-22 | 2025-02-05 | 2025-03-14 | 2025-03-20 | S & J BUILDERS | Ongoing
5581 | REPAIR 2024 | Region X | Lanao del Norte | 501397 | Poonapiagapo Central Integrated School | POONA PIAGAPO | 2nd |  |  | Repair of Classrooms | 565839.43 | 1 |  | Realigned (see other remarks) | 1 | [10 empty] | allocation was Re-align to Geronima
5582 | REPAIR 2024 | Region X | Lanao del Norte | 127187 | Salvador CES | SALVADOR | 2nd |  |  | Repair of Classrooms | 1414598.59 | 1 |  | Realigned (see other remarks) | 1 | [10 empty] | allocation was Re-align to Panadtaran
5583 | REPAIR 2024 | Region X | Malaybalay City | 500245 | Can-ayan IS | CITY MALAYBALAY (Capital) | 2nd | 1 | 3 | Repair of Classrooms | 1886131.44 | 1 | 1565974.23 | COMPLETED | 1 | 2025-01-27 |  | 002-INFRA-2024 | 002-INFRA-2024 | 2024-08-12 | 2024-08-20 | 2024-09-03 |  | 2024-11-13 | JDE CONSTRUCTION | Completed
5584 | REPAIR 2024 | Region X | Malaybalay City | 126564 | Laguitas Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 1037372.29 | 1 | 858895.96 | COMPLETED | 1 | 2025-01-03 |  | 002-INFRA-2024 | 002-INFRA-2024 | 2024-08-12 | 2024-08-20 | 2024-09-03 |  | 2024-10-29 | WEGE Konstruck Civil Engineering Estimates.Construction | Completed
5585 | REPAIR 2024 | Region X | Malaybalay City | 314904 | Malaybalay City National Science HS | CITY MALAYBALAY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 1131678.87 | 1 | 998067.06 | COMPLETED | 1 | 2025-01-11 |  | 002-INFRA-2024 | 002-INFRA-2024 | 2024-08-12 | 2024-08-20 | 2024-09-03 |  | 2024-10-29 | WEGE Konstruck Civil Engineering Estimates.Construction | Completed
5586 | REPAIR 2024 | Region X | Misamis Occidental | 127278 | Timoteo SU ES (Lupagan ES) | BALIANGAO | 1st | 1 | 1 | Repair of Classrooms | 1297167.68 | 1 | 1282667.76 | COMPLETED | 1 | 2025-01-11 |  | BEFF 2024 REPAIR/REHABILITATION OF CLASSROOMS BATCH 1 - REGION X - MISAMIS OCCIDENTAL - 001 | 022-2024 | 2024-07-29 | 2024-08-06 | 2024-08-19 | 2024-09-16 | 2024-10-30 | ESL MILESTONE BUILDERS AND SUPPLY, INC. | For rectification of issued Punchlist of Corrective Works
5587 | REPAIR 2024 | Region X | Misamis Occidental | 127415 | Don Andres Soriano PS | LOPEZ JAENA | 1st | 1 | 1 | Repair of Classrooms | 1297167.68 | 1 | 1279611.3 | COMPLETED | 1 | 2025-03-12 |  | BEFF 2024 REPAIR/REHABILITATION OF CLASSROOMS BATCH 1 - REGION X - MISAMIS OCCIDENTAL - 002 | 023-2024 | 2024-07-29 | 2024-08-06 | 2024-08-19 | 2024-09-16 | 2024-10-30 | ESL MILESTONE BUILDERS AND SUPPLY, INC. | For rectification of issued Punchlist of Corrective Works
5588 | REPAIR 2024 | Region X | Misamis Occidental | 127499 | Mamanga ES | PLARIDEL | 1st | 1 | 3 | Repair of Classrooms | 3891502.02 | 1 | 3834248.18 | COMPLETED | 1 | 2025-02-10 |  | BEFF 2024 REPAIR/REHABILITATION OF CLASSROOMS BATCH 1 - REGION X - MISAMIS OCCIDENTAL - 003 | 024-2024 | 2024-07-29 | 2024-08-06 | 2024-08-19 | 2024-09-16 | 2024-10-30 | ESL MILESTONE BUILDERS AND SUPPLY, INC. | On-going
5589 | REPAIR 2024 | Region X | Misamis Occidental | 127339 | Dela Paz Elementary School | CLARIN | 2nd | 1 | 2 | Repair of Classrooms | 1717171.72 | 1 | 1691541.52 | COMPLETED | 1 | 2025-02-10 |  | BEFF 2024 REPAIR/REHABILITATION OF CLASSROOMS BATCH 1 - REGION X - MISAMIS OCCIDENTAL - 004 | 025-2024 | 2024-07-29 | 2024-08-06 | 2024-08-19 | 2024-09-16 | 2024-10-30 | ESL MILESTONE BUILDERS AND SUPPLY, INC. | On-going
5590 | REPAIR 2024 | Region X | Misamis Occidental | 127340 | Dolores ES | CLARIN | 2nd | 1 | 2 | Repair of Classrooms | 1717171.72 | 1 | 1690830.59 | COMPLETED | 1 |  |  | BEFF 2024 REPAIR/REHABILITATION OF CLASSROOMS BATCH 1 - REGION X - MISAMIS OCCIDENTAL - 005 | 026-2024 | 2024-07-29 | 2024-08-06 | 2024-08-19 | 2024-09-16 | 2024-10-30 | ESL MILESTONE BUILDERS AND SUPPLY, INC. | On-going
5591 | REPAIR 2024 | Region X | Misamis Oriental | 304077 | Kinoguitan Nat'l Agricultural HS | KINOGUITAN | 1st | 1 | 6 | Repair of Classrooms | 3787878.79 | 1 | 3260255.31 | COMPLETED | 1 | 2025-05-04 |  | PB-BAC1-Repair-2024-002 | 5230097 | 2024-07-29 | 2024-08-07 | 2024-08-20 | 2024-09-10 | 2024-11-27 | I M & M CONSTRUCTION | On-going
5592 | REPAIR 2024 | Region X | Misamis Oriental | 127785 | Magsaysay CS | MAGSAYSAY (LINUGOS) | 1st | 1 | 4 | Repair of Classrooms | 2525252.53 | 1 | 2137413.94 | COMPLETED | 1 | 2025-04-04 |  | PB-BAC1-Repair-2024-002 | 5230172 | 2024-07-29 | 2024-08-07 | 2024-08-20 | 2024-09-10 | 2024-11-27 | MINKONSTRAK ENGINEERING & GEN. SERVICES | On-going
5593 | REPAIR 2024 | Region X | Misamis Oriental | 304101 | Sugbongcogon NHS | SUGBONGCOGON | 1st | 1 | 2 | Repair of Classrooms | 1262626.26 | 1 | 1062509.1 | COMPLETED | 1 | 2025-02-27 |  | PB-BAC1-Repair-2024-003 | 5235571 | 2024-09-30 | 2024-10-08 | 2024-10-21 | 2024-11-07 | 2024-12-20 | TRI FB | On-going
5594 | REPAIR 2024 | Region X | Misamis Oriental | 127599 | Tula ES | ALUBIJID | 2nd | 1 | 2 | Repair of Classrooms | 1262626.26 | 1 | 991302.16 | COMPLETED | 1 |  | 2025-02-07 | PB-BAC1-Repair-2024-003 | 5267990 | 2024-09-30 | 2024-10-08 | 2024-10-21 | 2024-11-07 | 2024-12-20 | JDE CONSTRUCTION
5595 | REPAIR 2024 | Region X | Misamis Oriental | 501253 | Natubo IS | JASAAN | 2nd | 1 | 2 | Repair of Classrooms | 1262626.26 | 1 | 1160573.89 | COMPLETED | 1 |  | 2025-02-01 | PB-BAC1-Repair-2024-002 | 5235571 | 2024-07-29 | 2024-08-07 | 2024-08-20 | 2024-10-07 | 2024-11-26 | CY SQUARED
5596 | REPAIR 2024 | Region X | Oroquieta City | 501972 | Apil Integrated School | OROQUIETA CITY (Capital) | 1st | 1 | 4 | Repair of Classrooms | 4040404.04 | 1 | 3235513.33 | COMPLETED | 1 | 2‎ ‎April‎ ‎2025 |  | INFRA-2024-DEPEDOROQ-03 |  | 2024-06-27 | 2024-07-05 | 2024-07-17 | 2024-09-20 | 2024-10-04 | ESL builders | Ongoing
5597 | REPAIR 2024 | Region X | Ozamis City | 128196 | Gregorio A. Saquin Elementary School | OZAMIS CITY | 2nd | 1 | 3 | Repair of Classrooms | 4545454.55 | 1 | 4456644.33 | COMPLETED | 1 | 2025-03-29 |  | 092-CIVIL-2024-001 | 092-CIVIL-2024-001 | 2024-08-08 | 2024-08-15 | 2024-08-27 | 2024-09-30 | 2024-10-30 | MITZ AND NICK BUILDERS | on-going implementation
5598 | REPAIR 2024 | Region X | Tangub City | 128213 | San Antonio ES | TANGUB CITY | 2nd | 1 | 4 | Repair of Classrooms | 3547407.4 | 1 | 2835886.17 | COMPLETED | 1 |  |  |  |  | 2024-07-08 | 2024-07-16 | 2024-07-29 | 2024-08-05 |  | ESL Milestone Builders Inc | On-going
5599 | REPAIR 2024 | Region X | Valencia City | 126837 | Catumbalon ES | CITY OF VALENCIA | 4th | 1 | 7 | Repair of Classrooms | 5656565.66 | 1 |  | Under procurement | 0 | [10 empty] | rebid; Failure of 1st bidding

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%