## Sheet1
INDEX (DO NOT MODIFY) | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
126 | GABALDON 2020 | Region XII | General Santos City | 131273 | Lagao Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 10140232.79 | 1 |  | Completed | 1
127 | GABALDON 2020 | Region XII | North Cotabato | 129994 | Ugalingan ES | Carmen | 3 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 6000000 | 1 |  | Completed | 1
128 | GABALDON 2020 | Region XII | Sarangani | 500795 | Glan Central Integrated SPED Center | Glan | 0 | 1 | 16 | 1 | Rehabilitation of Gabaldon Building | 6801120.53 | 1 |  | Completed | 1
169 | GABALDON 2021 | Region XII | General Santos city | 131290 | Jose Divinagracia ES | General Santos city | 1 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 9254653 | 1 |  | COMPLETED | 1
206 | GABALDON 2023 | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | 13 | 1 | Restoration & Conservation of Gabaldon Building | 25735852.11 | 1 | 21312201.38 | Ongoing | 0.985 | 2024-12-09 | ongoing | 2023-09-001 | 2023-12-006 | 2023-09-26 | 2023-10-04 | 2023-10-16 | 2023-11-05 | 2023-12-14 | JANMARIE CONSTRUCTION SERVICE AND SUPPLY | No Submission for March update
289 | GABALDON 2024 | Region XII | South Cotabato | 130708 | Norala Central Elementary School | NORALA | 2nd | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 17337379.73 | 1 |  | Ongoing | 0.0433

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%