## Sheet1
Region | Division | School ID | School Name | Municipality | Leg District | No. of Sites | Scope of Work | Total Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 4, 2025
CARAGA | Agusan del Norte | 131508 | Buenavista CES | BUENAVISTA | 2nd | 1 | CONSTRUCTION OF TWO (2) STOREY ALTERNATIVE LEARNING SYSTEM - COMMUNITY LEARNING CENTER WITH ROOF DECK- (18.00m x 9.50m), WITH RAINWATER COLLECTOR, PERIMETER FENCE AND FURNITURE | 14141414.14 | 14070707.07 | completed | 1 | April 26, 2025 | May 15, 2025 | ALS-CLC 2024 - CARAGA - AGUSAN DEL NORTE - 001 | ALS-CLC 2024 - CARAGA - AGUSAN DEL NORTE - 001 | June 5, 2024 | June 28, 2024 | July 11, 2024 | August 5, 2024 | August 15, 2024 | JD-RG Const. & Supplies | WITH VARIATION ORDER AND TIME EXTENSION

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%