## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | WITH TRANSFOPMER (Y/N) | CATEGORY 2 | Status as of July 4, 2025
ELECTRIFICATION 2017 | CARAGA | Agusan del Norte | 211503 | Cabayugan ES | BUENAVISTA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 294804.52 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Norte | 131415 | A.P. Quiamjot ES | CARMEN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220633.82 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131710 | Makalindang PS | ESPERANZA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 264557.49 | 168059.72 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131897 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131777 | La Fortuna Eementary School | PROSPERIDAD (Capital) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 400034.38 | 263642.28 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131710 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212051 | Jose T. Cuyos, Sr. I PS | ROSARIO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 163465.08 | 162809.72 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 212051 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131943 | Datu Bandahan ES | SAN LUIS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 211004.38 | 236243.74 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131854 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212074 | DOP BINATUNAN IP SCHOOL (IPA) | SAN LUIS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 332058.21 | 457504.63 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 212032 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131954 | Mahagsay ES | SAN LUIS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 366700.99 | 652599.78 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131864 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212026 | Balonbon Elementary School | SIBAGAT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 395070.28 | 365367.45 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131954 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131864 | Banag-banag ES | SIBAGAT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 653936.23 | 223062.4 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131758 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131874 | Magkalape ES | SIBAGAT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 354088.04 | 353050.87 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131874 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131988 | New Davao ES | TALACOGON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 209911.75 | 250997.12 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131901 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212060 | San Roque PS | TALACOGON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 200138.25 | 487312.68 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 212029 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131662 | Sta. Monica ES | BUNAWAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 522735.74 | 353050.87 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131874 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131748 | Angeles PS | LA PAZ | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 210638.25 | 162809.72 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 212051 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131758 | Log Pond 3 PS | LA PAZ | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 223243.06 | 521986.02 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131662 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131854 | Manangahon ES | SAN FRANCISCO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 236554.34 | 210405.87 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131748 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212032 | Dao Elementary School | SANTA JOSEFA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 459079.18 | 456711.45 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 132014 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212057 | DATU MADAGNAS PS | SANTA JOSEFA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 263830.99 | 393689.97 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 212026 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 132014 | San Marcos ES | TRENTO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 458082.2 | 209813.14 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131943 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212029 | Singapore Elementary School | TRENTO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 488330.22 | 208220.63 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131988 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131897 | Basilica PS | VERUELA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 168715.08 | 168059.72 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131897 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131901 | Candiis ES | VERUELA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 251685.26 | 398862.85 | COMPLETED | 1 | 2018-03-09 |  | BEFF 2017 | 131777 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Bayugan City | 212012 | Datu Hugmakan ES | CITY OF BAYUGAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 406181.81 | 404000 | COMPLETED | 1 | April 23, 2018 |  |  | 2018-002 | November 24, 2017 |  | December 1, 2017 | December 18, 2017 | January 15, 2018 | Vinnex Enterprises |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Bayugan City | 131642 | Sto Nino ES | CITY OF BAYUGAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 373719.04 | 370000 | COMPLETED | 1 | April 23, 2018 |  |  | 2018-001 | November 24, 2017 |  | December 1, 2017 | December 18, 2017 | January 15, 2018 | Vinnex Enterprises |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Bislig City | 322507 | Danipas NHS Labisma Annex | CITY OF BISLIG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 100690.38 | 100368.97 | COMPLETED | 1 | 2018-04-10 | 2018-04-10 | 2017BEFF-Electrification | 2017BEFF-Electrification | 2017-11-17 | 2017-11-29 | 2017-12-11 | 2017-12-18 | 2018-01-03 | RMF Const. & Supply |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Bislig City | 235003 | New Bongga PS | CITY OF BISLIG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 170998.68 | 170467.83 | COMPLETED | 1 | 2018-04-10 | 2018-04-10 | 2017BEFF-Electrification | 2017BEFF-Electrification | 2017-11-17 | 2017-11-29 | 2017-12-11 | 2017-12-18 | 2018-01-03 | RMF Const. & Supply |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Butuan City | 132095 | Mabuhay ES | BUTUAN CITY (Capital) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 294804.52 | 287803.06 | COMPLETED | 1 | April 16, 2018 | April 5, 2018 | 015 S’2017 | 015 S’2017 | Oct. 20, 2017 | Nov. 24, 2017 | Dec.08, 2017 | 2017-12-18 | 2018-01-17 | ADSE ENTERPRISE |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Butuan City | 132078 | Masago PS | BUTUAN CITY (Capital) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 294804.52 | 287803.06 | COMPLETED | 1 | April 16, 2018 | April 5, 2018 | 015 S’2017 | 015 S’2017 | Oct. 20, 2017 | Nov. 24, 2017 | Dec.08, 2017 | 2017-12-18 | 2018-01-17 | ADSE ENTERPRISE |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Butuan City | 212504 | Tud-ol ES | BUTUAN CITY (Capital) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220633.82 | 215393.88 | COMPLETED | 1 | April 16, 2018 | April 5, 2018 | 015 S’2017 | 015 S’2017 | Oct. 20, 2017 | Nov. 24, 2017 | Dec.08, 2017 | 2017-12-18 | 2018-01-17 | ADSE ENTERPRISE |  |  | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Cabadbaran City | 281003 | Dagnasay ES | CABADBARAN CITY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 177560.6 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Cabadbaran City | 131523 | Lusong ES | CITY OF CABADBARAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 177560.6 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132273 | Alang-alang ES | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220203.36 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132274 | Alegria ES | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 405084.95 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Surigao City | 304793 | Alegria NHS | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 477182.44 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132277 | Bay-bay ES | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 180524.3 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132278 | Bilabid PS | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 92522.05 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132279 | Buenavista ES | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 406380.7 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132280 | Catadman ES | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 108642.54 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132285 | Tomas Florya Eder Memorial Elementary School | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 270646.47 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | CARAGA | Surigao del Norte | 132438 | Meliton Morales PS | MAINIT | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 222400 | 221000 | COMPLETED | 1 | 2018-02-19 | 2018-02-19 |  | 010-2018 | 2017-12-10 |  |  | 2017-12-13 | 2018-01-05 | RJB Construction and Supply |  |  | ENERGIZATION
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304680 | Casiklan NHS- Durian NHS Annex | LAS NIEVES | 1 | 1 | UPGRADING | 2 | 908776.8783 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304679 | Durian NHS | LAS NIEVES | 1 | 1 | UPGRADING | 2 | 1001800.817 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304689 | Las Nieves NHS | LAS NIEVES | 1 | 1 | UPGRADING | 2 | 1995482.4464 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304694 | Marcos Calo NHS | LAS NIEVES | 1 | 1 | UPGRADING | 2 | 1000395.19 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304674 | Buenavista NHS | BUENAVISTA | 2 | 1 | UPGRADING | 2 | 1375813.6202 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304682 | Guinabsan NHS | BUENAVISTA | 2 | 1 | UPGRADING | 2 | 890124.6 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 500049 | Manapa II Integrated School | BUENAVISTA | 2 | 1 | UPGRADING | 2 | 1485353.95 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 317304 | Cahayagan NHS (Carmen NHS Annex) | CARMEN | 2 | 1 | UPGRADING | 2 | 722664.43 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304685 | Jabonga NHS | JABONGA | 2 | 1 | UPGRADING | 2 | 1264534.97 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304688 | Kitcharao NHS | KITCHARAO | 2 | 1 | UPGRADING | 2 | 1511842.0007 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304691 | Magallanes National High School | MAGALLANES | 2 | 1 | UPGRADING | 2 | 1352554.6445 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304696 | Nasipit National Vocational School | NASIPIT | 2 | 1 | UPGRADING | 2 | 1598975.7697 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 317302 | Nasipit NHS | NASIPIT | 2 | 1 | UPGRADING | 2 | 781156.32 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304673 | Agay National High School | REMEDIOS T. ROMUALDEZ | 2 | 1 | UPGRADING | 2 | 1461966.2225 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304686 | Jagupit NHS | SANTIAGO | 2 | 1 | UPGRADING | 2 | 1422466.5055 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304698 | Santiago NHS | SANTIAGO | 2 | 1 | UPGRADING | 2 | 1381089.87 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 317309 | Dona Rosario NHS - Tubay NHS Annex | TUBAY | 2 | 1 | UPGRADING | 2 | 1058491.7855 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304701 | Tubay NHS | TUBAY | 2 | 1 | UPGRADING | 2 | 1063694.0519 |  | COMPLETED | 1 |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 304730 | Patin-ay National High School | PROSPERIDAD (Capital) | 1 | 1 | UPGRADING | 2 | 3637477.62 |  | COMPLETED | 1 |  |  |  | 2018-09-012 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | RJB CONSTRUCTION & SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 304731 | Prosperidad NHS | PROSPERIDAD (Capital) | 1 | 1 | UPGRADING | 2 | 4255007.78 |  | COMPLETED | 1 |  |  |  | 2018-09-015 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | A-MARTINA CONSTRUCTION & SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 304749 | Sta. Irene National High School | PROSPERIDAD (Capital) | 1 | 1 | UPGRADING | 2 | 5421042.52 |  | COMPLETED | 1 |  |  |  | 2018-09-014 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | A-MARTINA CONSTRUCTION & SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 317428 | West Prosperidad Nhs | PROSPERIDAD (Capital) | 1 | 1 | UPGRADING | 2 | 2904296.75 |  | COMPLETED | 1 |  |  |  | 2018-09-013 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | A-MARTINA CONSTRUCTION & SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 304709 | Bunawan National High School | BUNAWAN | 2 | 1 | UPGRADING | 2 | 4335897.39 |  | COMPLETED | 1 |  |  |  | 2018-09-016 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | ARCLER BUILDERS & CONST. SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 304745 | Bayugan III NHS | ROSARIO | 2 | 1 | UPGRADING | 2 | 3924975.51 |  | COMPLETED | 1 |  |  |  | 2018-09-018 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | ARCLER BUILDERS & CONST. SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 304744 | Sta. Cruz NHS | ROSARIO | 2 | 1 | UPGRADING | 2 | 3571779.59 |  | COMPLETED | 1 |  |  |  | 2018-09-017 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | ARCLER BUILDERS & CONST. SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 317402 | Bayugan II National High School | SAN FRANCISCO | 2 | 1 | UPGRADING | 2 | 2315300.82 |  | COMPLETED | 1 |  |  |  | 2018-09-019 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | ARCLER BUILDERS & CONST. SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Bayugan City | 304723 | Marcelina NHS | CITY OF BAYUGAN | 1 | 1 | UPGRADING | 2 | 1247694.45 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Bayugan City | 304728 | Noli National High School | CITY OF BAYUGAN | 1 | 1 | UPGRADING | 2 | 1313237.32 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Bayugan City | 340297 | STAND ALONE SHS | CITY OF BAYUGAN | 1 | 1 | UPGRADING | 2 | 2716825.75 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Bislig City | 304865 | Bislig City NHS | CITY OF BISLIG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 2 | 2627484.1 | 2596626.53 | COMPLETED | 1 | Sept. 26, 2018 |  | 2018BEFF-Electrification-C1 | 2018BEFF-Electrification-C1 | 2018-03-23 | 2018-04-05 | 2018-04-17 | 2018-04-25 | May 23, 2018 | MAG Corporation |  | Y | ENERGIZATION
ELECTRIFICATION 2018 | CARAGA | Bislig City | 304919 | Mangagoy NHS | CITY OF BISLIG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 2 | 1519924.76 | 1502002.64 | COMPLETED | 1 | Aug. 27, 2018 |  | 2018BEFF-Electrification-C2 | 2018BEFF-Electrification-C2 | 2018-03-23 | 2018-04-05 | 2018-04-17 | 2018-04-25 | May 23, 2018 | MAG Corporation |  | Y | ENERGIZATION
ELECTRIFICATION 2018 | CARAGA | Bislig City | 304869 | Sikahoy NHS | CITY OF BISLIG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 2 | 1144311.01 | 1130069.36 | COMPLETED | 1 | Aug. 27, 2018 |  | 2018BEFF-Electrification-C2 | 2018BEFF-Electrification-C2 | 2018-03-23 | 2018-04-05 | 2018-04-17 | 2018-04-25 | May 23, 2018 | MAG Corporation |  | Y | ENERGIZATION
ELECTRIFICATION 2018 | CARAGA | Bislig City | 340306 | Stand Alone SHS | CITY OF BISLIG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 2 | 1438901.82 | 1422202.03 | COMPLETED | 1 | Sept. 26, 2018 |  | 2018BEFF-Electrification-C1 | 2018BEFF-Electrification-C1 | 2018-03-23 | 2018-04-05 | 2018-04-17 | 2018-04-25 | May 23, 2018 | MAG Corporation |  | Y | ENERGIZATION
ELECTRIFICATION 2018 | CARAGA | Butuan City | 304756 | Agusan National High School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2221583.24 | 1949719.39 | COMPLETED | 1 | December 15, 2018 |  | RRC-2018-006 | RRC-2018-006 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | july, 23, 2018 | ETP Builders |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Butuan City | 304757 | Agusan Pequeno NHS | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1663800.35 | 1414442.2064 | COMPLETED | 1 | December 15, 2018 |  | RRC-2018-007 | RRC-2018-007 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | July 6, 2018 | Two J.E. Construction & Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Butuan City | 304762 | Butuan City Sch. of Arts & Trades | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2205770.32 | 1877249.5724 | COMPLETED | 1 | December 15, 2018 |  | RRC-2018-007 | RRC-2018-007 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | July 6, 2018 | Two J.E. Construction & Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Butuan City | 340337 | Butuan City Senior High School Stand Alone | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2762431.87 | 1818553.25 | COMPLETED | 1 | December 15, 2018 |  | RRC-2018-006 | RRC-2018-006 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | july, 23, 2018 | ETP Builders |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Butuan City | 304763 | Libertad Integrated Senior High School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1663800.35 | 1414442.2064 | COMPLETED | 1 | December 15, 2018 |  | RRC-2018-007 | RRC-2018-007 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | July 6, 2018 | Two J.E. Construction & Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Butuan City | 304769 | San Vicente National High School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1663800.35 | 1414442.2064 | COMPLETED | 1 | December 15, 2018 |  | RRC-2018-007 | RRC-2018-007 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | July 6, 2018 | Two J.E. Construction & Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Butuan City | 304771 | Taligaman NHS | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1663800.35 | 1652389.55 | COMPLETED | 1 | December 15, 2018 |  | RRC-2018-006 | RRC-2018-006 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | july, 23, 2018 | ETP Builders |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Cabadbaran City | 304676 | Calamba NHS | CITY OF CABADBARAN | 2 | 1 | UPGRADING | 2 | 1117389.43 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Cabadbaran City | 340341 | La Union SHS (Stand Alone) | CITY OF CABADBARAN | 2 | 1 | UPGRADING | 2 | 1006220.12 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Dinagat Island | 304815 | Cagdianao NHS | CAGDIANAO | 0 | 1 | UPGRADING | 1 | 2138817.1 |  | COMPLETED | 1 | NOV. 17, 2018 |  |  | INFRA18-002-02 |  |  |  |  | JULY 11, 2018 |  |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 | 1 | UPGRADING | 1 | 2371554.25 |  | COMPLETED | 1 | NOV. 17, 2018 |  |  | INFRA18-002-04 |  |  |  |  | JULY 11, 2018 |  |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | DINAGAT | 0 | 1 | UPGRADING | 1 | 2001578.36 |  | COMPLETED | 1 | NOV. 17, 2018 |  |  | INFRA18-002-05 |  |  |  |  | JULY 11, 2018 |  |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Dinagat Island | 304808 | Albor NHS | LIBJO (ALBOR) | 0 | 1 | UPGRADING | 1 | 2335700.05 |  | COMPLETED | 1 | NOV. 17, 2018 |  |  | INFRA18-002-01 |  |  |  |  | JULY 11, 2018 |  |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | 1 | 2337098.19 |  | COMPLETED | 1 | NOV. 17, 2018 |  |  | INFRA18-002-03 |  |  |  |  | JULY 11, 2018 |  |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Dinagat Island | 304854 | Tubajon NHS | TUBAJON | 0 | 1 | UPGRADING | 1 | 2390442.95 |  | COMPLETED | 1 | NOV. 17, 2018 |  |  | INFRA18-002-06 |  |  |  |  | JULY 11, 2018 |  |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Siargao | 304774 | Dapa NHS | DAPA | 1 | 1 | UPGRADING | 1 | 2929746.09 | 2905000 | COMPLETED | 1 |  |  |  | BEFF-INFRA2018-008 | February 8 ,2018 | February 19, 2018 | March 5, 2018 | May 3, 2018 | May 16, 2018 | Vic B. Borja Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Siargao | 304783 | Del Carmen NHS | DEL CARMEN | 1 | 1 | UPGRADING | 1 | 2271995.06 | 2250000 | COMPLETED | 1 |  |  |  | BEFF-INFRA2018-009 | February 8 ,2018 | February 19, 2018 | March 5, 2018 | May 3, 2018 | May 16, 2018 | Vic B. Borja Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Siargao | 304777 | Gen Luna NHS | GENERAL LUNA | 1 | 1 | UPGRADING | 1 | 2775183.35 | 2750000 | COMPLETED | 1 |  |  |  | BEFF-INFRA2018-010 | February 8 ,2018 | February 19, 2018 | March 5, 2018 | May 3, 2018 | May 16, 2018 | Vic B. Borja Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Siargao | 304784 | Roxas National High School | SAN ISIDRO | 1 | 1 | UPGRADING | 2 | 2109106.54 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Siargao | 304782 | San Isidro National High School | SAN ISIDRO | 1 | 1 | UPGRADING | 3 | 3050000 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Siargao | 304785 | Sapao National High School | SANTA MONICA (SAPAO) | 1 | 1 | UPGRADING | 3 | 3050000 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Siargao | 304790 | Pamosaingan National High School | SOCORRO | 1 | 1 | UPGRADING | 3 | 3050000 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Siargao | 132224 | Socorro Central Elementary School and SPED Center | SOCORRO | 1 | 1 | UPGRADING | 3 | 3000000 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Siargao | 304788 | SOCORRO NATIONAL HIGH SCHOOL | SOCORRO | 1 | 1 | UPGRADING | 3 | 3700000 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao City | 304800 | Anomar NHS | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 2 | 568659.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao City | 340383 | Cabrera-Altres National High School | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 2 | 565967.91 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao City | 304794 | Caraga Regional Science HS | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 2 | 567310.44 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao City | 304795 | Ipil NHS | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 3 | 1348769.53 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao City | 317704 | Lipata National High School | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 3 | 953359.27 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao City | 304799 | mat-i national high school | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 2 | 1356411.85 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao City | 304801 | Surigao City NHS | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 2 | 2488304.96 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao City | 317701 | Taft NHS | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 3 | 987826.51 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 340416 | Alegria Stand Alone Senior High School | ALEGRIA | 2 | 1 | UPGRADING | 3 | 1657085.43 |  | COMPLETED | 1 | 2019-02-20 |  |  | 025-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304813 | Bacuag Nat'L Agro-Indust'L Sch. | BACUAG | 2 | 1 | UPGRADING | 1 | 1168482.85 | 1162181.16 | COMPLETED | 1 | 2018-08-05 |  |  | 017-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-04 | RJB Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304817 | Campo NHS | BACUAG | 2 | 1 | UPGRADING | 1 | 1178282.61 | 1171932.16 | COMPLETED | 1 | 2018-08-05 |  |  | 017-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-04 | RJB Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 317806 | Payapag NHS | BACUAG | 2 | 1 | UPGRADING | 1 | 1129680.82 | 1123572.18 | COMPLETED | 1 | 2018-08-05 |  |  | 017-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-04 | RJB Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 | 1 | UPGRADING | 1 | 1915898.59 | 1901116.76 | COMPLETED | 1 | 2018-07-11 |  |  | 018-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-04 | RJB Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304835 | Hacienda NHS | MAINIT | 2 | 1 | UPGRADING | 1 | 1271122.29 | 1263572.957 | COMPLETED | 1 | 2018-08-29 |  |  | 023-2018 | 2018-04-04 | 2018-05-04 | 2018-05-22 | 2018-05-24 | 2018-06-15 | Maxter Resources, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 317803 | Magpayang NHS | MAINIT | 2 | 1 | UPGRADING | 1 | 1129680.82 | 1121180.273 | COMPLETED | 1 | 2018-07-19 |  |  | 020-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304829 | Mainit NHS | MAINIT | 2 | 1 | UPGRADING | 1 | 1336228.12 | 1326699.973 | COMPLETED | 1 | 2018-07-19 |  |  | 020-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304834 | Matin-ao National High School | MAINIT | 2 | 1 | UPGRADING | 1 | 1284562.4 | 1276946.207 | COMPLETED | 1 | 2018-08-29 |  |  | 023-2018 | 2018-04-04 | 2018-05-04 | 2018-05-22 | 2018-05-24 | 2018-06-15 | Maxter Resources, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 132460 | Malimono Central Elementary School | MALIMONO | 2 | 1 | UPGRADING | 3 | 1593266.33 |  | COMPLETED | 1 | 2019-02-20 |  |  | 026-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304833 | Malimono NHS | MALIMONO | 2 | 1 | UPGRADING | 3 | 1943819.1 |  | COMPLETED | 1 | 2019-02-20 |  |  | 027-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304845 | Amando A. Fabio MNHS | PLACER | 2 | 1 | UPGRADING | 1 | 1178282.61 | 1171195.167 | COMPLETED | 1 | 2018-08-05 |  |  | 019-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Digos Constrak Corporation |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 132478 | Placer Central Elementary School | PLACER | 2 | 1 | UPGRADING | 3 | 1493969.85 |  | COMPLETED | 1 | 2019-02-20 |  |  | 028-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304837 | Placer NHS | PLACER | 2 | 1 | UPGRADING | 1 | 1284443.5 | 1276827.897 | COMPLETED | 1 | 2018-08-05 |  |  | 019-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Digos Constrak Corporation |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 132479 | Placer West CES | PLACER | 2 | 1 | UPGRADING | 3 | 1405226.13 |  | COMPLETED | 1 | 2019-03-29 |  |  | 031-2018 | 2018-11-30 | 2018-12-07 | 2018-12-21 | 2018-12-27 | 2018-12-29 | RCDG Construction |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 132482 | Sta Cruz ES | PLACER | 2 | 1 | UPGRADING | 3 | 1627085.43 |  | COMPLETED | 1 | 2019-02-20 |  |  | 029-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 132331 | Anao-aon CES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | UPGRADING | 3 | 1582814.07 |  | COMPLETED | 1 | 2019-02-20 |  |  | 030-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304814 | Balite NHS | SAN FRANCISCO (ANAO-AON) | 2 | 1 | UPGRADING | 1 | 1163382.98 | 1150077.79 | COMPLETED | 1 | 2018-08-03 |  |  | 016-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304843 | San Francisco NHS | SAN FRANCISCO (ANAO-AON) | 2 | 1 | UPGRADING | 1 | 1129680.82 | 1116543.31 | COMPLETED | 1 | 2018-08-03 |  |  | 016-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 317808 | Dakung Patag NHS - Annex (TS PSMHS) | SISON | 2 | 1 | UPGRADING | 1 | 1129680.82 | 1120606.347 | COMPLETED | 1 | 2018-07-19 |  |  | 021-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304850 | Mayag National High School | SISON | 2 | 1 | UPGRADING | 3 | 1858090.45 |  | COMPLETED | 1 | 2019-03-29 |  |  | 032-2018 | 2018-11-30 | 2018-12-07 | 2018-11-07 | 2018-12-27 | 2018-12-29 | RJB Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304849 | T.S Pantilo, Sr. MNHS | SISON | 2 | 1 | UPGRADING | 1 | 1141983.51 | 1132847.827 | COMPLETED | 1 | 2018-07-19 |  |  | 021-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304847 | Surigao Del Norte NHS | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 1 | 1900350.59 | 1883378.9 | COMPLETED | 1 | 2018-08-03 |  |  | 016-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304812 | Tagana-an NHS (ASA NHS) | TAGANA-AN | 2 | 1 | UPGRADING | 1 | 1280970.03 | 1273371.717 | COMPLETED | 1 | 2018-08-05 |  |  | 019-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Digos Constrak Corporation |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304853 | Timamana National High School | TUBOD | 2 | 1 | UPGRADING | 1 | 1129680.82 | 1118994.447 | COMPLETED | 1 | 2018-08-29 |  |  | 024-2018 | 2018-04-04 | 2018-05-04 | 2018-05-22 | 2018-05-24 | 2018-06-15 | Maxter Resources, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304855 | Tubod NHS | TUBOD | 2 | 1 | UPGRADING | 1 | 1129680.82 | 1118994.447 | COMPLETED | 1 | 2018-08-29 |  |  | 024-2018 | 2018-04-04 | 2018-05-04 | 2018-05-22 | 2018-05-24 | 2018-06-15 | Maxter Resources, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304861 | Barobo National High School | BAROBO | 1 | 1 | UPGRADING | 2 | 1215833.39 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304888 | Gamut National School (Barobo) | BAROBO | 1 | 1 | UPGRADING | 2 | 1132934.81 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304895 | Lingig National High School | LINGIG | 1 | 1 | UPGRADING | 2 | 2040849.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304862 | Cabacungan National High School | BAROBO | 2 | 1 | UPGRADING | 2 | 826611.18 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 317941 | Rizal National High School | BAROBO | 2 | 1 | UPGRADING | 2 | 989901.63 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304864 | Tambis National High School | BAROBO | 2 | 1 | UPGRADING | 2 | 1165346.88 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500577 | Baculin Integrated School | HINATUAN | 2 | 1 | UPGRADING | 2 | 1230229.49 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304891 | Dugmanon National High School | HINATUAN | 2 | 1 | UPGRADING | 2 | 1285902.31 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304890 | Hinatuan National Comprehensive High School | HINATUAN | 2 | 1 | UPGRADING | 2 | 1958192.28 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 317940 | Hinatuan NCHS - Cambatong NHS Annex | HINATUAN | 2 | 1 | UPGRADING | 2 | 2157380.51 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 317939 | Hinatuan NCHS - Roxas NHS Annex | HINATUAN | 2 | 1 | UPGRADING | 2 | 1076759.56 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304920 | Tagasaka National High School | HINATUAN | 2 | 1 | UPGRADING | 2 | 1018059.73 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304921 | Tagasaka NHS - Bigaan NHS Annex | HINATUAN | 2 | 1 | UPGRADING | 2 | 699350.11 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 317910 | Tagasaka NHS - Loyola NHS Annex | HINATUAN | 2 | 1 | UPGRADING | 2 | 1686150.22 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500579 | Tarusan Integrated School | HINATUAN | 2 | 1 | UPGRADING | 2 | 980049.41 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304923 | Tidman National High School | HINATUAN | 2 | 1 | UPGRADING | 2 | 1039113.16 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500581 | Anibongan Integrated School | LINGIG | 2 | 1 | UPGRADING | 2 | 634932.93 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304860 | BARCELONA NATIONAL HIGH SCHOOL | LINGIG | 2 | 1 | UPGRADING | 2 | 1692675.85 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304896 | M.K.Yusingco National High School | LINGIG | 2 | 1 | UPGRADING | 2 | 1370222.68 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500327 | Rajah Cabungsuan Integrated School | LINGIG | 2 | 1 | UPGRADING | 2 | 886819.09 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500326 | Carpenito Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1162180.11 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304879 | Dante Luib Osano Maputi National High School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1426254.45 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500586 | Jobar Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1034475.45 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304880 | Kahayagan National High School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1167541.05 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500324 | Maglambing Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1136011.53 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304881 | Maglatab National High School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1117283.12 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500582 | Malixi Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1210039.51 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500585 | Manambia Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1130028.26 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500580 | Osmeña Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1356777.94 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500325 | Quary I Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 829362.43 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500583 | Quezon Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1275561.55 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304883 | Sta. Juana National High School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1162498.57 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500584 | Sta. Maria Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1295078.32 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317310 | E. G. Montilla NHS (Mat-I NHS Annex) | LAS NIEVES | 1 | 1 | UPGRADING | Batch 3 | 704990.36 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 500048 | Lawan-Lawan IS (Secondary Level) | LAS NIEVES | 1 | 1 | UPGRADING | Batch 3 | 843620.35 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304690 | LINGAYAO NATIONAL HIGH SCHOOL | LAS NIEVES | 1 | 1 | UPGRADING |  | 940467.19 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304693 | Maningalao NHS | LAS NIEVES | 1 | 1 | UPGRADING | Batch 3 | 747559.24 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304695 | Mat-i NHS | LAS NIEVES | 1 | 1 | UPGRADING |  | 995143.82 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317314 | Abilan NHS (Buenavista NHS Annex) | BUENAVISTA | 2 | 1 | UPGRADING | Batch 3 | 862491.02 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317315 | Agong-ong NHS (Buenavista NHS Annex | BUENAVISTA | 2 | 1 | UPGRADING |  | 1052871.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 500047 | Buenavista SPED IS (Secondary Level) | BUENAVISTA | 2 | 1 | UPGRADING |  | 785900.08 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317305 | Lekda NHS (Guinabsan NHS Annex) | BUENAVISTA | 2 | 1 | UPGRADING | Batch 3 | 1118711.25 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317317 | Rizal NHS (Guinabsan NHS Annex) | BUENAVISTA | 2 | 1 | UPGRADING |  | 1641299.4 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317301 | Sangay National High School | BUENAVISTA | 2 | 1 | UPGRADING |  | 826272.58 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304683 | Simbalan NHS - Guinabsan NHS Annex | BUENAVISTA | 2 | 1 | UPGRADING |  | 1045919.94 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 500311 | Manoligao IS (Secondary Level) | CARMEN | 2 | 1 | UPGRADING | Batch 3 | 777700.13 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 340204 | SHS in Carmen, Agusan Del Norte | CARMEN | 2 | 1 | UPGRADING |  | 1169355.11 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304702 | Vinapor NHS | CARMEN | 2 | 1 | UPGRADING | Batch 3 | 888563.93 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317319 | Bangonay NHS | JABONGA | 2 | 1 | UPGRADING | Batch 3 | 848076.13 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304678 | Cuyago NHS | JABONGA | 2 | 1 | UPGRADING |  | 737006.48 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304692 | Magdagooc NHS | JABONGA | 2 | 1 | UPGRADING |  | 752717.45 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317303 | San Vicente NHS | JABONGA | 2 | 1 | UPGRADING |  | 657461.09 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304687 | Jaliobong NHS | KITCHARAO | 2 | 1 | UPGRADING |  | 814349.32 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317308 | Culit National High School (Nasipit National Vocational School Annex) | NASIPIT | 2 | 1 | UPGRADING | Batch 3 | 888356.26 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 500314 | Hinandayan IS (Secondary Level) | NASIPIT | 2 | 1 | UPGRADING | Batch 3 | 864725.88 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | NOT-IN-NSBI | Nasipit NHS EXT. | NASIPIT | 2 | 1 | UPGRADING | Batch 3 | 760940.19 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317311 | Balangbalang NHS (Agay NHS Annex) | REMEDIOS T. ROMUALDEZ | 2 | 1 | UPGRADING |  | 696535.15 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304700 | Tinigbasan NHS | TUBAY | 2 | 1 | UPGRADING | Batch 3 | 944933.87 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Sur | 304747 | Datu Lipus Makapandong National High School | ROSARIO | 2 | 1 | UPGRADING |  | 5368286.81 |  | COMPLETED | 1 |  |  | 6311080 | 2019-02-001 | JULY 11, 2019 | JULY 17, 2019 | AUGUST 07, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Sur | 304703 | Agusan del Sur National High School | SAN FRANCISCO | 2 | 1 | UPGRADING |  | 6924016.46 |  | COMPLETED | 1 |  |  | 6311080 | 2019-02-002 | JULY 11, 2019 | JULY 17, 2019 | AUGUST 07, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Sur | 304717 | Lapinigan National High School | SAN FRANCISCO | 2 | 1 | UPGRADING |  | 4151839.06 |  | COMPLETED | 1 |  |  | 6311080 | 2019-02-003 | JULY 11, 2019 | JULY 17, 2019 | AUGUST 07, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Sur | 304750 | Sta. Josefa National High School | SANTA JOSEFA | 2 | 1 | UPGRADING | Batch 3 | 7402004.11 |  | COMPLETED | 1 |  |  | 6311080 | 2019-02-004 | JULY 11, 2019 | JULY 17, 2019 | AUGUST 07, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Sur | 304753 | Trento NHS | TRENTO | 2 | 1 | UPGRADING |  | 4918248.24 |  | COMPLETED | 1 |  |  | 6311080 | 2019-02-005 | JULY 11, 2019 | JULY 17, 2019 | AUGUST 07, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Agusan del Sur | 317445 | Veruela NHS Annex - Nueva Era HS | VERUELA | 2 | 1 | UPGRADING | Batch 3 | 3020197.72 |  | COMPLETED | 1 |  |  | 6311080 | 2019-02-006 | JULY 11, 2019 | JULY 17, 2019 | AUGUST 07, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bayugan City | 304707 | Bayugan NCHS | CITY OF BAYUGAN | 1 | 1 | UPGRADING |  | 3628416.64 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bayugan City | 304732 | Salvacion National High School | CITY OF BAYUGAN | 1 | 1 | UPGRADING | Batch 3 | 1669797.12 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bayugan City | 304735 | SAN JUAN NATIONAL HIGH SCHOOL | CITY OF BAYUGAN | 1 | 1 | UPGRADING | Batch 3 | 1457873.37 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bislig City | 132609 | Bislig Central Elementary School | CITY OF BISLIG | 2 | 1 | UPGRADING | Batch 3 | 1521189.69 | 1049912.04 | COMPLETED | 1 | 2020-01-02 |  | Electrification-Cluster 1 | 2019E-005 | June 28, 2019 | July 8, 2019 | July 22, 2019 | Aug. 16, 2019 | Aug. 28, 2019 | MAG Corporation |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bislig City | 322503 | Bucto NHS | CITY OF BISLIG | 2 | 1 | UPGRADING |  | 1645959.26 | 1474578 | COMPLETED | 1 | December 14, 2019 |  | Electrification-Cluster 2 | 2019E-004 | Oct. 26, 2018 | Nov. 6, 2018 | Nov. 19, 2018 | Aug. 02, 2019 | Aug. 09, 2019 | MAG Corporation |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bislig City | 132838 | Caramcam Central ES | CITY OF BISLIG | 2 | 1 | UPGRADING | Batch 3 | 892769.64 | 620890.22 | COMPLETED | 1 | December 3, 2019 |  | Electrification-Cluster 2 | 2019E-006 | June 28, 2019 | July 8, 2019 | July 22, 2019 | Aug. 16, 2019 | Aug. 28, 2019 | MAG Corporation |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bislig City | 304894 | Lawigan NHS | CITY OF BISLIG | 2 | 1 | UPGRADING |  | 1042710.07 | 1140961.06 | COMPLETED | 1 | December 14, 2019 |  | Electrification-Cluster 1 | 2019E-003 | Oct. 26, 2018 | Nov. 6, 2018 | Nov. 19, 2018 | Aug. 02, 2019 | Aug. 09, 2019 | MAG Corporation |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bislig City | 322505 | Mabog National High School | CITY OF BISLIG | 2 | 1 | UPGRADING |  | 1391390.96 | 1246108 | COMPLETED | 1 | December 14, 2019 |  | Electrification-Cluster 2 | 2019E-004 | Oct. 26, 2018 | Nov. 6, 2018 | Nov. 19, 2018 | Aug. 02, 2019 | Aug. 09, 2019 | MAG Corporation |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bislig City | 304866 | Maharlika NHS | CITY OF BISLIG | 2 | 1 | UPGRADING |  | 1648913.07 | 936981.59 | COMPLETED | 1 | December 14, 2019 |  | Electrification-Cluster 1 | 2019E-003 | Oct. 26, 2018 | Nov. 6, 2018 | Nov. 19, 2018 | Aug. 02, 2019 | Aug. 09, 2019 | MAG Corporation |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bislig City | 132833 | Mangagoy CES | CITY OF BISLIG | 2 | 1 | UPGRADING | Batch 3 | 978905.45 | 676985.52 | COMPLETED | 1 | December 3, 2019 |  | Electrification-Cluster 2 | 2019E-006 | June 28, 2019 | July 8, 2019 | July 22, 2019 | Aug. 16, 2019 | Aug. 28, 2019 | MAG Corporation |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bislig City | 132843 | Plaza CES | CITY OF BISLIG | 2 | 1 | UPGRADING |  | 803582.41 | 719848.67 | COMPLETED | 1 | December 14, 2019 |  | Electrification-Cluster 1 | 2019E-003 | Oct. 26, 2018 | Nov. 6, 2018 | Nov. 19, 2018 | Aug. 02, 2019 | Aug. 09, 2019 | MAG Corporation |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bislig City | 132635 | San Roque Central Elementary School | CITY OF BISLIG | 2 | 1 | UPGRADING | Batch 3 | 1350800.29 | 932482.36 | COMPLETED | 1 | 2020-01-02 |  | Electrification-Cluster 1 | 2019E-005 | June 28, 2019 | July 8, 2019 | July 22, 2019 | Aug. 16, 2019 | Aug. 28, 2019 | MAG Corporation |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Bislig City | 304917 | Tabon M. Estrella National High School | CITY OF BISLIG | 2 | 1 | UPGRADING |  | 1270572.67 | 1479959.16 | COMPLETED | 1 | December 14, 2019 |  | Electrification-Cluster 2 | 2019E-004 | Oct. 26, 2018 | Nov. 6, 2018 | Nov. 19, 2018 | Aug. 02, 2019 | Aug. 09, 2019 | MAG Corporation |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Butuan City | 304759 | Banza NHS | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1663800.35 | 1654361.99 | COMPLETED | 1 |  |  | ESHS-2019-001 |  | 2019-06-03 | 2019-07-05 | 2019-07-08 | 2019-09-06 |  | Arcler Builder and Construction Supply |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Butuan City | 132023 | Butuan Central Elementary School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1684905.35 | 1147508.93 | COMPLETED | 1 | 2020-01-03 |  | ESHS-2018-001 | ESHS-2018-001 | 2018-12-06 | 2018-12-14 | 2018-12-27 | 2019-01-11 | 2019-09-05 | Maxter Resources Incorporated |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Butuan City | 304761 | Butuan City Comprehensive HS | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1663800.35 | 1654361.99 | COMPLETED | 1 |  |  | ESHS-2019-001 |  | 2019-06-03 | 2019-07-05 | 2019-07-08 | 2019-09-06 |  | Arcler Builder and Construction Supply |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Butuan City | 317507 | Consuelo National High School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1663800.35 | 1147508.93 | COMPLETED | 1 | 2020-01-03 |  | ESHS-2018-002 | ESHS-2018-002 | 2018-12-06 | 2018-12-14 | 2018-12-27 | 2019-01-11 | 2019-09-05 | Maxter Resources Incorporated |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Butuan City | 317510 | Kinamlutan National High School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1663800.35 | 1654361.99 | COMPLETED | 1 |  |  | ESHS-2019-001 |  | 2019-06-03 | 2019-07-05 | 2019-07-08 | 2019-09-06 |  | Arcler Builder and Construction Supply |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Butuan City | 304764 | Los Angeles National High School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1663800.35 | 1147508.93 | COMPLETED | 1 | 2020-01-03 |  | ESHS-2018-002 | ESHS-2018-002 | 2018-12-06 | 2018-12-14 | 2018-12-27 | 2019-01-11 | 2019-09-05 | Maxter Resources Incorporated |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Butuan City | 304767 | Maguinda NHS | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1663800.35 | 1147508.93 | COMPLETED | 1 | 2020-01-03 |  | ESHS-2018-001 | ESHS-2018-001 | 2018-12-06 | 2018-12-14 | 2018-12-27 | 2019-01-11 | 2019-09-05 | Maxter Resources Incorporated |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Butuan City | 304772 | Tungao NHS | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1684905.35 | 1146894.68 | COMPLETED | 1 | 2020-01-03 |  | ESHS-2018-002 | ESHS-2018-002 | 2018-12-06 | 2018-12-14 | 2018-12-27 | 2019-01-11 | 2019-09-05 | Maxter Resources Incorporated |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Cabadbaran City | 304699 | Cabadbaran City National High School | CITY OF CABADBARAN | 2 | 1 | UPGRADING |  | 2424321.83 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Cabadbaran City | 317307 | Del Pilar NHS | CITY OF CABADBARAN | 2 | 1 | UPGRADING | Batch 3 | 1819429.64 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 304851 | Tag-abaca NHS | BASILISA (RIZAL) | 0 | 1 | UPGRADING | Batch 2 | 2963774.48 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 304840 | R. E. Ecleo Sr. NHS | CAGDIANAO | 0 | 1 | UPGRADING | Batch 2 | 2442378.72 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 317802 | Valencia National High School | CAGDIANAO | 0 | 1 | UPGRADING | Batch 2 | 2671625.71 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 324401 | Llamera NHS | LIBJO (ALBOR) | 0 | 1 | UPGRADING | Batch 2 | 2643133.25 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 317801 | Rosita National High School | LIBJO (ALBOR) | 0 | 1 | UPGRADING | Batch 2 | 2442378.72 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 304810 | San Jose National High School | LIBJO (ALBOR) | 0 | 1 | UPGRADING | Batch 2 | 2641134.86 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 304828 | Loreto National high school | LORETO | 0 | 1 | UPGRADING | Batch 2 | 2682178.47 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 2 | 2454098.93 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 317805 | Trinidad Mapa-Gupana NHS | TUBAJON | 0 | 1 | UPGRADING | Batch 2 | 2661072.95 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Siargao | 132139 | Dapa Central Elementary School & SPED Center | DAPA | 1 | 1 | UPGRADING | Batch 3 | 3000000 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Siargao | 304779 | Pilar National High School | PILAR | 1 | 1 | UPGRADING |  | 3050000 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500574 | Cabangahan Integrated School | CANTILAN | 1 | 1 | UPGRADING | Batch 3 | 1127964.11 |  | COMPLETED | 1 |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304873 | Cantilan National High School | CANTILAN | 1 | 1 | UPGRADING | Batch 1 | 1653184.94 | 1152745 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-018 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 317928 | Cantilan National High School - Consuelo Annex | CANTILAN | 1 | 1 | UPGRADING | Batch 1 | 1255260.45 | 874592.77 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-018 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500575 | Isla General Integrated School | CANTILAN | 1 | 1 | UPGRADING | Batch 3 | 1005489.5 |  | COMPLETED | 1 |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500570 | Palasao Integrated School | CANTILAN | 1 | 1 | UPGRADING | Batch 3 | 1466804.64 |  | COMPLETED | 1 |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304901 | Parang National High School | CANTILAN | 1 | 1 | UPGRADING | Batch 1 | 1314111.13 | 915662.23 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-018 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304875 | Carmen National Agricultural High School | CARMEN | 1 | 1 | UPGRADING | Batch 1 | 1221860.92 | 850951.6 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-016 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | NOT-IN-NSBI | Esperanza ISS (Carmen Nat'l. Agr'l. HS - Esperanza NHS Annex) | CARMEN | 1 | 1 | UPGRADING | Batch 3 | 1212892.15 |  | COMPLETED | 1 |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304857 | Adlay National High School | CARRASCAL | 1 | 1 | UPGRADING | Batch 1 | 1928978.57 | 1344126.05 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-019 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304877 | Carrascal National High School | CARRASCAL | 1 | 1 | UPGRADING | Batch 1 | 2851263.4 | 1985873.95 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-019 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304900 | Panikian National High School | CARRASCAL | 1 | 1 | UPGRADING | Batch 3 | 1375891.89 |  | COMPLETED | 1 |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304872 | Burgos National High School | CORTES | 1 | 1 | UPGRADING | Batch 1 | 1500271.3 | 1045028.28 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-016 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304886 | Felisberto Verano National high school | CORTES | 1 | 1 | UPGRADING | Batch 1 | 1538865.71 | 1073020.11 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-016 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500321 | Matho IS | CORTES | 1 | 1 | UPGRADING | Batch 3 | 1621790.35 |  | COMPLETED | 1 |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304887 | Tigao National High School | CORTES | 1 | 1 | UPGRADING | Batch 3 | 1750041.35 |  | COMPLETED | 1 |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500578 | Agsam Integrated School | LANUZA | 1 | 1 | UPGRADING | Batch 3 | 1785447.51 |  | COMPLETED | 1 |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304885 | Florita Herrera-Irizari National High School | LANUZA | 1 | 1 | UPGRADING | Batch 3 | 1294402.28 |  | COMPLETED | 1 |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500320 | Nurcia Integrated School | LANUZA | 1 | 1 | UPGRADING | Batch 3 | 1716311.05 |  | COMPLETED | 1 |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304897 | Madrid National High School | MADRID | 1 | 1 | UPGRADING | Batch 1 | 2374996.94 | 1655268.67 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-017 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 317904 | Madrid NHS - Union NHS Annex | MADRID | 1 | 1 | UPGRADING | Batch 1 | 1137072.29 | 791731.33 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-017 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304863 | Javier National High School | BAROBO | 2 | 1 | UPGRADING | Batch 1 | 1129903.06 | 786377.82 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-015 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 317921 | Wakat National High School | BAROBO | 2 | 1 | UPGRADING | Batch 1 | 640212.7 | 445893.95 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-015 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500572 | Bingcongan Integrated School | HINATUAN | 2 | 1 | UPGRADING | Batch 1 | 1435055.36 | 998411.64 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-014 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304902 | Portlamon Pastor Uy National High School | HINATUAN | 2 | 1 | UPGRADING | Batch 1 | 1186757.78 | 828588.36 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-014 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304878 | Doña Carmen National High School | TAGBINA | 2 | 1 | UPGRADING | Batch 3 | 1051052.86 |  | COMPLETED | 1 |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304882 | San Vicente II National High School | TAGBINA | 2 | 1 | UPGRADING | Batch 3 | 1109868.75 |  | COMPLETED | 1 |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304884 | Tagbina National High School | TAGBINA | 2 | 1 | UPGRADING | Batch 1 | 1260411.86 | 878728.24 | COMPLETED | 1 | 2019-12-19 |  |  | 2019-015 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Tandag City | 304871 | Buenavista National High School | CITY OF TANDAG (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1468612.62 |  | COMPLETED | 1 |  |  |  |  | July 29, 2019 | August 13, 2019 | August 29 2019 |  |  | MAG Constuction |  | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Tandag City | 304871 | Buenavista National High School | CITY OF TANDAG (Capital) | 1 | 1 | UPGRADING |  | 1548603.82 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | CARAGA | Tandag City | 304922 | Tandag National Science High School | CITY OF TANDAG (Capital) | 1 | 1 | UPGRADING | Batch 2 | 1646127.05 |  | COMPLETED | 1 |  |  |  |  | July 29, 2019 | August 13, 2019 | August 29 2019 |  |  | MAG Constuction |  | Y | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131508 | Buenavista CES | BUENAVISTA | 2 | 1 |  |  | 1618651.77 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-Agusan Del Norte -002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 304677 | Carmen NHS | CARMEN | 2 | 1 |  |  | 1243610.78 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-Agusan Del Norte -003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131433 | Jabonga Central Elementary School | JABONGA | 2 | 1 |  |  | 1641775.98 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-Agusan Del Norte -015 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131450 | Kitcharao CES | KITCHARAO | 2 | 1 |  |  | 1464358.77 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-Agusan Del Norte -004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131485 | Magallanes CES | MAGALLANES | 2 | 1 |  |  | 1462870.78 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-Agusan Del Norte -005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 317320 | Pupotsan NHS (Magallanes NHS Annex) | MAGALLANES | 2 | 1 |  |  | 1459645.15 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-Agusan Del Norte -022 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131500 | Nasipit CES | NASIPIT | 2 | 1 |  |  | 1560825.23 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-Agusan Del Norte -009 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131534 | RT Romualdez CES | REMEDIOS T. ROMUALDEZ | 2 | 1 |  |  | 1526790.1 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-Agusan Del Norte -011 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131546 | Santiago CES | SANTIAGO | 2 | 1 |  |  | 1745805.59 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-Agusan Del Norte -018 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Sur | 304722 | Lucena NHS | PROSPERIDAD | 1 | 1 |  |  | 3012416.33 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-AGUSAN DEL SUR-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Sur | 317442 | Afga Nhs | SIBAGAT | 1 | 1 |  |  | 2615202.1 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-AGUSAN DEL SUR-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Sur | 304740 | SIBAGAT NATIONAL HIGH SCHOOL OF HOME INDUSTRIES | SIBAGAT | 1 | 1 |  |  | 5205167.22 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-AGUSAN DEL SUR-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Sur | 304752 | Talacogon NHS | TALACOGON | 1 | 1 |  |  | 3860458.02 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-AGUSAN DEL SUR-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Sur | 304718 | Libertad NHS | BUNAWAN | 2 | 1 |  |  | 3759806.31 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-AGUSAN DEL SUR-011 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Agusan del Sur | 304716 | La Paz NHS | LA PAZ | 2 | 1 |  |  | 3998159.77 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-AGUSAN DEL SUR-007 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Bayugan City | 131615 | Agusan del Sur Pilot Laboratory School | CITY OF BAYUGAN | 1 | 1 |  |  | 1424202.62 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BAYUGAN CITY-006 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Bayugan City | 131616 | Bayugan Central Elem. School SPED Center | CITY OF BAYUGAN | 1 | 1 |  |  | 1400511.95 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BAYUGAN CITY-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Bayugan City | 304729 | Calaitan NHS | CITY OF BAYUGAN | 1 | 1 |  |  | 1428228.4 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BAYUGAN CITY-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Bayugan City | 131596 | East Bayugan CES | CITY OF BAYUGAN | 1 | 1 |  |  | 1320371.2 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BAYUGAN CITY-007 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Bayugan City | 317420 | Magkiangkang National High School | CITY OF BAYUGAN | 1 | 1 |  |  | 1441439.83 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BAYUGAN CITY-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Bayugan City | 304724 | Mt. Olive National High School | CITY OF BAYUGAN | 1 | 1 |  |  | 1400511.95 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BAYUGAN CITY-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Bislig City | 132834 | Mangagoy East ES | CITY OF BISLIG | 2 | 1 |  |  | 1127986.47 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BISLIG CITY-007 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Bislig City | 132837 | Mangagoy South ES | CITY OF BISLIG | 2 | 1 |  |  | 1442285.01 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BISLIG CITY-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Bislig City | 322501 | San Jose NHS | CITY OF BISLIG | 2 | 1 |  |  | 1310336.46 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BISLIG CITY-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Bislig City | 132636 | San Vicente ES | CITY OF BISLIG | 2 | 1 |  |  | 1270630.11 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BISLIG CITY-010 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Bislig City | 304868 | San Vicente NHS | CITY OF BISLIG | 2 | 1 |  |  | 1311681.51 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BISLIG CITY-006 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Butuan City | 317517 | Alviola ISS | BUTUAN CITY (Capital) | 1 | 1 |  |  | 1443590.17 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BUTUAN CITY-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Butuan City | 304758 | Amparo NHS | BUTUAN CITY (Capital) | 1 | 1 |  |  | 1995868.08 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BUTUAN CITY-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Butuan City | 132027 | Ampayon CES | BUTUAN CITY (Capital) | 1 | 1 |  |  | 1547996.57 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BUTUAN CITY-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Butuan City | 317511 | Ampayon National High School | BUTUAN CITY (Capital) | 1 | 1 |  |  | 2021533.04 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BUTUAN CITY-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Butuan City | 317506 | La Trinidad Integrated Secondary School | BUTUAN CITY (Capital) | 1 | 1 |  |  | 1968534.69 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BUTUAN CITY-009 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Butuan City | 317521 | Pigdaulan National High School | BUTUAN CITY (Capital) | 1 | 1 |  |  | 1980367.49 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-BUTUAN CITY-011 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Cabadbaran City | 304699 | Cabadbaran City National High School | CITY OF CABADBARAN | 2 | 1 |  |  | 1635417.68 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-CABADBARAN CITY-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Cabadbaran City | 500312 | North Cabadbaran CES | CITY OF CABADBARAN | 2 | 1 |  |  | 1695411.85 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-CABADBARAN CITY-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Cabadbaran City | 330101 | Puting Bato National High School | CITY OF CABADBARAN | 2 | 1 |  |  | 1660594.07 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-CABADBARAN CITY-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Dinagat Island | 132360 | Cagdianao Central Elementary School | CAGDIANAO | 0 | 1 |  |  | 2845996.85 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-DINAGAT ISLANDS-003 | [9 empty] | ENERGIZATION
ELECTRIFICATION 2020 | CARAGA | Dinagat Island | 132305 | Albor CES | LIBJO (ALBOR) | 0 | 1 |  |  | 2465085.22 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-DINAGAT ISLANDS-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Dinagat Island | 132559 | TUBAJON CENTRAL ELEMENTARY SCHOOL | TUBAJON | 0 | 1 |  |  | 2410255.07 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-DINAGAT ISLANDS-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Siargao | 132217 | Burgos Central Elementary School | BURGOS | 1 | 1 |  |  | 1356517.38 |  | COMPLETED | 1 |  |  | Elec2020-CARAGA-SIARGAO-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1 | 1 |  |  | 1339658.53 |  | COMPLETED | 1 |  |  | Elec2020-CARAGA-SIARGAO-014 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Siargao | 132129 | Don Enrique Navarro Memorial School | DAPA | 1 | 1 |  |  | 1405433.03 |  | COMPLETED | 1 |  |  | Elec2020-CARAGA-SIARGAO-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Siargao | 304791 | Union National High School | DAPA | 1 | 1 |  |  | 1223271.85 |  | COMPLETED | 1 |  |  | Elec2020-CARAGA-SIARGAO-016 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Siargao | 132179 | Sayak Elementary School | DEL CARMEN | 1 | 1 |  |  | 1095063.55 |  | COMPLETED | 1 |  |  | Elec2020-CARAGA-SIARGAO-012 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 1 | 1 |  |  | 1379086.87 |  | COMPLETED | 1 |  |  | Elec2020-CARAGA-SIARGAO-015 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Siargao | 132234 | Nueva Estrella Central Elementary School | SOCORRO | 1 | 1 |  |  | 1092485.34 |  | COMPLETED | 1 |  |  | Elec2020-CARAGA-SIARGAO-006 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao City | 304793 | Alegria NHS | SURIGAO CITY (Capital) | 2 | 1 |  |  | 1171837.37 |  | COMPLETED | 1 |  |  | ELEC-2020-CARAGA-SURIGAO CITY-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao City | 304806 | Zaragoza National High School | SURIGAO CITY (Capital) | 2 | 1 |  |  | 1095649.99 |  | COMPLETED | 1 |  |  | ELEC-2020-CARAGA-SURIGAO CITY-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Norte | 304811 | Alegria NHS | ALEGRIA | 2 | 1 | UPGRADING |  | 1869023.38 |  | COMPLETED | 1 |  |  | ELEC-2020-CARAGA-SURIGAO DEL NORTE-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Norte | 304832 | Bunyasan NHS | MALIMONO | 2 | 1 | UPGRADING |  | 1866251.64 |  | COMPLETED | 1 |  |  | ELEC-2020-CARAGA-SURIGAO DEL NORTE-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Norte | 317807 | Pananay-an NHS - Annex (Placer NHS) | PLACER | 2 | 1 | UPGRADING |  | 1071080.82 |  | COMPLETED | 1 |  |  | ELEC-2020-CARAGA-SURIGAO DEL NORTE-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Norte | 132534 | Sison CES | SISON | 2 | 1 | UPGRADING |  | 1247830.26 |  | COMPLETED | 1 |  |  | ELEC-2020-CARAGA-SURIGAO DEL NORTE-006 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304909 | Solomon P. Lozada National High School | BAYABAS | 1 | 1 |  |  | 1453178.46 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-010 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132661 | CANTILAN PILOT ELEMENTARY SCHOOL | CANTILAN | 1 | 1 |  |  | 1241487.93 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-040 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132695 | CARRASCAL CENTRAL ELEMTARY SCHOOL | CARRASCAL | 1 | 1 |  |  | 1276863.39 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-036 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304858 | Anibongan National High School | LIANGA | 1 | 1 |  |  | 1552815.65 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304859 | Lianga National Comprehensive National High School | LIANGA | 1 | 1 |  |  | 1487789.52 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-010 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 317906 | Cresencio S. Lago National High School | MARIHATAG | 1 | 1 |  |  | 1609273.47 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304898 | Marihatag National Agricultural High School | MARIHATAG | 1 | 1 |  |  | 1489951.03 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-015 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304904 | Salvacion National High School | SAN AGUSTIN | 1 | 1 |  |  | 1588834.02 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-014 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304906 | Bolhoon National High School | SAN MIGUEL | 1 | 1 |  |  | 1458950.67 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132887 | SAN MIGUEL CENTRAL ELEMENTARY SCHOOL | SAN MIGUEL | 1 | 1 |  |  | 1242738.86 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-034 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304905 | San Miguel National Comprehensive High School | SAN MIGUEL | 1 | 1 |  |  | 1483216.35 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-013 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304907 | San Miguel National Comprehensive High School - Sagbayan Annex | SAN MIGUEL | 1 | 1 |  |  | 1544768.82 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-016 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304908 | San Miguel National High School | SAN MIGUEL | 1 | 1 |  |  | 1552193.49 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-027 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132890 | TINA CENTRAL ELEMENTARY SCHOOL | SAN MIGUEL | 1 | 1 |  |  | 1206157.31 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-032 | [9 empty] | ENERGIZATION
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304889 | Gamut National High School (Tago) | TAGO | 1 | 1 |  |  | 1587621.61 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-007 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132572 | BAROBO CENTRAL ELEMENTARY SCHOOL | BAROBO | 2 | 1 |  |  | 1634468.1 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-041 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132597 | TAMBIS CENTRAL ELEMENTARY SCHOOL | BAROBO | 2 | 1 |  |  | 1207366.06 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-031 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132924 | TAGBINA CENTRAL ELEMENTARY SCHOOL | TAGBINA | 2 | 1 |  |  | 1206112.47 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-042 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Tandag City | 132960 | Bongtud Elementary School | CITY OF TANDAG (Capital) | 1 | 1 |  |  | 1095896.21 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-TANDAG CITY-008 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Tandag City | 304892 | Jacinto P. Elpa National High School | CITY OF TANDAG (Capital) | 1 | 1 |  |  | 1657965.1 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-TANDAG CITY-010 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Tandag City | 132978 | Tandag Central Elementary School | CITY OF TANDAG (Capital) | 1 | 1 |  |  | 1893947 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-TANDAG CITY-001 | [9 empty] | ENERGIZATION
ELECTRIFICATION 2020 | CARAGA | Tandag City | 132979 | Tandag Pilot Elementary School | CITY OF TANDAG (Capital) | 1 | 1 |  |  | 1343682.33 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-TANDAG CITY-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | CARAGA | Tandag City | 304893 | Vicente L. Pimentel Sr. National High School | CITY OF TANDAG (Capital) | 1 | 1 |  |  | 1165750.43 |  | COMPLETED | 1 |  |  | ELEC2020-CARAGA-TANDAG CITY-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Dinagat Island | 132394 | Cab-ilan Elementary School | DINAGAT | Lone | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1433633.85 | 1103616.34 | COMPLETED | 1 | 2023-10-20 | 2022-10-20 | INFRA23-003-02 |  | 2023-07-07 | 2023-07-17 | 2023-07-27 | 2023-08-07 | SEPT 8, 2023 | RJB CONSTRUCTION AND SUPPLY |  |  | SOLAR
ELECTRIFICATION 2023 | CARAGA | Dinagat Island | 132396 | Dinagat Central Elementary School | DINAGAT | Lone | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1566338.6089 | 1076466.49 | COMPLETED | 1 | 2023-10-20 | 2022-10-20 | INFRA23-003-01 |  | 2023-07-07 | 2023-07-17 | 2023-07-27 | 2023-08-07 | SEPT 8, 2023 | RJB CONSTRUCTION AND SUPPLY |  |  | SOLAR
ELECTRIFICATION 2023 | CARAGA | Siargao | 304776 | Mariano Matugas Memorial National High School | DEL CARMEN | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1281098.66 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Siargao | 132176 | Numancia Central Elementary School | DEL CARMEN | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1328462.22 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | SOLAR
ELECTRIFICATION 2023 | CARAGA | Siargao | 132145 | Anajawan Elementary School | GENERAL LUNA | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1471012.92 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | SOLAR
ELECTRIFICATION 2023 | CARAGA | Siargao | 132152 | General Luna CES | GENERAL LUNA | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1328154.13 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Siargao | 304777 | General Luna NHS | GENERAL LUNA | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3034314.86 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Siargao | 132153 | La Januza ES | GENERAL LUNA | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1447674.25 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | SOLAR
ELECTRIFICATION 2023 | CARAGA | Siargao | 132156 | Malinao Elementary Schol | GENERAL LUNA | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1269995.33 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Siargao | 132157 | Mam-on PS | GENERAL LUNA | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1263766.73 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | SOLAR
ELECTRIFICATION 2023 | CARAGA | Siargao | 304778 | Sta. Fe National High School | GENERAL LUNA | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1308743.46 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Siargao | 132160 | Suyangan ES | GENERAL LUNA | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1644323.14 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | SOLAR
ELECTRIFICATION 2023 | CARAGA | Siargao | 317601 | Suyangan National High School | GENERAL LUNA | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1771044.48 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | SOLAR
ELECTRIFICATION 2023 | CARAGA | Siargao | 132190 | Pilar Central Elementary School | PILAR | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1329571.32 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Siargao | 132230 | San Benito Central Elementary School | SAN BENITO | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1271107.91 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Siargao | 132199 | San Isidro Central Elementary School | SAN ISIDRO | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1330680.43 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Siargao | 317607 | Alegria National High School | SANTA MONICA (SAPAO) | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1308743.46 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Siargao | 132213 | Sapao Central Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1301948.31 |  | COMPLETED | 1 | 2023-12-20 | 2023-11-29 | [10 empty] | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 304813 | Bacuag National Agro-Industrial School | BACUAG | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -50 KVA Transformer | 1 | 1197266.56 | 1189766.47 | COMPLETED | 1 | 2023-01-21 | 2023-01-23 | 001-ELECTRIFICATION 2023-Caraga | 025-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | A N ESCALANTE CONSTRUCTION, INC. |  |  | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 304833 | Malimono National High School | MALIMONO | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -50 KVA Transformer | 1 | 1112775.27 | 1107766.21 | COMPLETED | 1 | 2023-01-18 | 2023-01-20 | 002-ELECTRIFICATION 2023-Caraga | 026-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | RJB CONSTRUCTION AND SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 304831 | Masgad National High School | MALIMONO | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -50 KVA Transformer | 1 | 1164972.94 | 1159944.78 | COMPLETED | 1 | 2023-01-18 | 2023-01-20 | 003-ELECTRIFICATION 2023-Caraga | 027-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | RJB CONSTRUCTION AND SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 304819 | Pili National High School | MALIMONO | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -50 KVA Transformer | 1 | 1196841.18 | 1191824.36 | COMPLETED | 1 | 2023-01-18 | 2023-01-20 | 004-ELECTRIFICATION 2023-Caraga | 028-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | RJB CONSTRUCTION AND SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 317808 | Dakung Patag National High School | SISON | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -50 KVA Transformer | 1 | 1098526.93 | 1090371.12 | COMPLETED | 1 | 2023-01-21 | 2023-01-23 | 005-ELECTRIFICATION 2023-Caraga | 029-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | A N ESCALANTE CONSTRUCTION, INC. |  |  | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 304812 | Tagana-an National High School (ASA NHS) | TAGANA-AN | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -50 KVA Transformer | 1 | 1129402.34 | 1128350.96 | COMPLETED | 1 | 2023-01-18 | 2023-01-20 | 006-ELECTRIFICATION 2023-Caraga | 030-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | RJB CONSTRUCTION AND SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 132568 | Tubod CES | TUBOD | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -37.5 KVA Transformer | 1 | 1096269.78 | 1128350.96 | COMPLETED | 1 | 2023-01-18 | 2023-01-20 | 007-ELECTRIFICATION 2023-Caraga | 031-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | RJB CONSTRUCTION AND SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Surigao del Sur | 132601 | Bayabas Central Elementary School | BAYABAS | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1637648.75 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2023 | CARAGA | Surigao del Sur | 132602 | Cabugo Elementary School | BAYABAS | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1450037.55 |  | COMPLETED | 1 | [12 empty] | SOLAR
ELECTRIFICATION 2023 | CARAGA | Surigao del Sur | 132685 | Gacub Elementary School | CARMEN | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1265305.49 |  | COMPLETED | 1 | [12 empty] | SOLAR
ELECTRIFICATION 2024 | CARAGA | Agusan del Norte | 131506 | Abilan ES | BUENAVISTA | 2nd | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3880778.58 |  | ONGOING | 0.05 | [10 empty] | realigned from Mateo B. Abao CES realigned to Abilan ES |  | SOLAR
ELECTRIFICATION 2024 | CARAGA | Bayugan City | 131632 | Maygatasan Elementary School | CITY OF BAYUGAN | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1645288.94 |  | ONGOING | 0.95 | [10 empty] | Realigned from Noli CES to Maygatasan ES |  | UPGRADING
ELECTRIFICATION 2024 | CARAGA | Bislig City | 304867 | Mone National High School | CITY OF BISLIG | 2nd | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3867121.91 |  | COMPLETED | 1 | [12 empty] | SOLAR
ELECTRIFICATION 2024 | CARAGA | Cabadbaran City | 131529 | Antonio C Dagani Central Elementary School | CITY OF CABADBARAN | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2439348.64 | 2157571.43 | COMPLETED | 1 | 2024-09-06 |  | 10312261 | 10312261 | 2023-11-13 | 2023-11-09 | 2023-12-06 | 2024-05-24 | 2024-06-06 | MCLA CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2024 | CARAGA | Dinagat Island | 132501 | Omay Edradan Elementary School | Basilisa | Lone | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2494859.88 | 1904114.72 | COMPLETED | 1 | 2024-08-08 | 2024-07-31 | 2023-006-1 |  | 2023-12-05 | 2023-12-11 | 2024-01-03 | 2024-01-11 | 2024-06-10 | MCLA CONSTRUCTION |  |  | SOLAR
ELECTRIFICATION 2024 | CARAGA | Dinagat Island | 132492 | F. S. Matugas Elementary School | BASILISA (RIZAL) | Lone | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2504295.38 | 1924729.44 | COMPLETED | 1 | 2024-08-09 | 2024-07-31 | 2023-006-2 |  | 2023-12-05 | 2023-12-11 | 2024-01-03 | 2024-01-11 | 2024-06-11 | MCLA CONSTRUCTION |  |  | SOLAR
ELECTRIFICATION 2024 | CARAGA | Siargao | 132129 | Don E.Navarro MS | Dapa | 1st | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2511786.84 | 2496984.68 | COMPLETED | 1 | [12 empty] | SOLAR
ELECTRIFICATION 2024 | CARAGA | Siargao | 132236 | Pamosaingan ES | Socorro | 1st | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2515687.73 | 2509599.6 | COMPLETED | 1 | [12 empty] | SOLAR
ELECTRIFICATION 2024 | CARAGA | Surigao City | 304806 | Zaragoza National High School | SURIGAO CITY (Capital) | 2nd | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2593727.4 | 1894155.62 | COMPLETED | 1 | Septemebr 28, 2024 |  | 2023-11-574 | FY-2023-INFRA-012 | 2023-12-12 | 2023-12-18 | 2024-01-05 | 2024-07-26 | 2024-08-09 | MLCA CONSTRUCTION |  |  | SOLAR
ELECTRIFICATION 2024 | CARAGA | Surigao del Norte | 501680 | Hinatuan Integrated School | GIGAQUIT | 2nd | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3890654.59 | 3887576.96 | COMPLETED | 1 | 2024-07-12 |  | 2024-(001)- ELECTRIFICATION-CARAGA | INFRA004-2024 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2024-05-09 | 2024-05-13 | RJB CONSTRUCTION AND SUPPLY | With Time Extension |  | SOLAR
ELECTRIFICATION 2024 | CARAGA | Surigao del Sur | 132647 | Cempron Elementary School | CAGWAIT | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2580764.37 |  | COMPLETED | 1 | [10 empty] | for award |  | ENERGIZATION
ELECTRIFICATION 2024 | CARAGA | Surigao del Sur | 132734 | Hinatuan North Central Elementary School | HINATUAN | 2nd | 1 | Upgrading of Electrical System | 1 | 2633549.54 |  | COMPLETED | 1 | [10 empty] | for award |  | UPGRADING
ELECTRIFICATION 2024 | CARAGA | Tandag City | 136972 | Pag-asa Tribal Community Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3850173.23 | 3049107.82 | COMPLETED | 1 | 2024-09-10 |  | 2023-11-202 |  | 2023-11-29 | 2023-12-07 | 2023-12-27 | 2024-01-10 | 2024-07-11 | HPS Electrical Engineering Services |  |  | SOLAR

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%