## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | Status as of July 4, 2025
REPAIR 2020 | Caraga | Bayugan City | 131600 | Katipunan ES | Bayugan City | 1 | 1 | 7 | Repair of Classrooms | 3279775 | 1 |  | COMPLETED | 1 |  |  | 2020-001 | 2020-001 | [5 empty] | ALCT Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Caraga | Bayugan City | 131601 | Kiawan ES | Bayugan City | 1 | 1 | 3 | Repair of Classrooms | 1533187 | 1 |  | COMPLETED | 1 |  |  | 2020-002 | 2020-002 | [5 empty] | ALCT Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Caraga | Bayugan City | 131636 | New Leyte ES | Bayugan City | 1 | 1 | 5 | Repair of Classrooms | 2208541 | 1 |  | COMPLETED | 1 |  |  | 2020-004 | 2020-004 | [5 empty] | MAIR Construction General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Caraga | Bayugan City | 131611 | San Isidro ES | Bayugan City | 1 | 1 | 6 | Repair of Classrooms | 3082265 | 1 |  | COMPLETED | 1 |  |  | 2020-003 | 2020-003 | [5 empty] | ETP Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%