## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Program-Year | Status as of July 4, 2025
K10 (2014) | NCR | Caloocan City | 305384 | Baesa HS | Caloocan City | 1 | 1 | 8 | 4STY 8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-09-23 | NC0214S00072 | 14OD0076 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-25 | 2015-02-27 | ORANI BUILDERS & SUPPLY |  | NC 2014
K10 (2014) | NCR | Caloocan City | 136651 | Bagumbong ES | Caloocan City | 1 | 1 | 18 | 3STY 18CL | 2014 K10 BATCH 3 | 27120494.0625 |  |  | COMPLETED | 1 |  |  | NC0214S00061 | [8 empty] | NC 2014
K10 (2014) | NCR | Caloocan City | 223501 | Caloocan North ES | Caloocan City | 1 | 1 | 48 | 4STY28CL & 4STY20CL | 2014 K10 BATCH 4B | 71170836.41 |  |  | COMPLETED | 1 |  |  | NC0214S00114 | [8 empty] | NC 2014
K10 (2014) | NCR | Caloocan City | 136641 | Kalayaan ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Caloocan City | 305379 | Manuel L. Quezon HS | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-09-23 | NC0214S00059 | 14OD0073 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-25 | 2015-02-27 | ORANI BUILDERS & SUPPLY |  | NC 2014
K10 (2014) | NCR | Caloocan City | 136640 | Sto. Nino ES | Caloocan City | 1 | 1 | 8 | 4STY 8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-10-24 | 2015-10-23 | NC0214S00060 | 14OD0074 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-25 | 2015-02-27 | ST. GERRARD CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Caloocan City | 305388 | Caloocan HS | Caloocan City | 2 | 1 | 36 | 4STY20CL & 4STY16CL | 2014 K10 BATCH 4B | 57805359.69 |  |  | COMPLETED | 1 |  |  | NC0214S00113 | [8 empty] | NC 2014
K10 (2014) | NCR | Caloocan City | 136606 | Grace Park ES (Main) | Caloocan City | 2 | 1 | 8 | 4STY/8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-07-25 | NC0214S00065 | 14OD0075 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-16 | 2015-02-27 | ORANI BUILDERS & SUPPLY |  | NC 2014
K10 (2014) | NCR | Caloocan City | 136608 | Kasarinlan ES | Caloocan City | 2 | 1 | 9 | 3STY/9CL and installation of remaining bored piles | 2014 K10 BATCH 4B | 16565073.8707 |  |  | COMPLETED | 1 |  |  | NC0214S00097 | 15OD0070 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-14 | 2015-09-04 | J. SIMEON CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Caloocan City | 136609 | Kaunlaran ES | Caloocan City | 2 | 1 | 6 | 4STY6CL (Open Ground) | 2014 K10 BATCH 4A | 15035522.3438 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Caloocan City | 136609 | Kaunlaran ES | Caloocan City | 2 | 1 | 12 | Completion of 4STY/12CL(remaining 4CL), 4STY/8CL and installation of remaining bored piles | 2014 K10 BATCH 4B | 30789912.22 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | Caloocan City | 2 | 1 | 40 | 2 UNITS 4STY20CL | 2014 K10 BATCH 3 | 64101168.75 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | Caloocan City | 2 | 1 | 9 | 3STY/9CL and installation of remaining bored piles | 2014 K10 BATCH 4B | 16565073.8707 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Caloocan City | 136613 | Maypajo ES | Caloocan City | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0214S00108 | [7 empty] | termination of contract on process | NC 2014
K10 (2014) | NCR | Caloocan City | 136614 | Sampalukan ES | Caloocan City | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10817093.5547 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Caloocan City | 500330 | Tandang Sora IS | Caloocan City | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1 | [10 empty] | ongoing; rebidded | NC 2014
K10 (2014) | NCR | Las Piñas City | 136773 | CAA ES | CITY OF LAS PIÑAS | 0 | 1 | 32 | 2 Units 4STY 16CL | 2014 K10 BATCH 3 | 55078781.25 |  |  | COMPLETED | 1 | 2016-08-10 |  | NC0214S00066 | 15OI0047 | 2015-04-13 | 2015-04-15 | 2015-05-04 | 2015-06-03 | 2015-06-18 | PRECIOUS CONSTRUCTION |  | NC 2014
SHS (2014) | NCR | Las Piñas City | 305432 | Golden Acres NHS | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0214S00123 |  | 2015-07-17 |  | 2015-08-05 |  | 2015-09-02 | RGDG CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Las Piñas City | 136788 | Pamplona ES I | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0214S00100 | 15OI0140 | 2015-07-23 | 2015-07-24 | 2015-11-23 |  |  | DAVHEZ TRADING & CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Malabon City | 136840 | Amang Rodriguez ES | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 19220118.3984 |  |  | COMPLETED | 1 | [8 empty] | 2015-10-30 |  |  | NC 2014
K10 (2014) | NCR | Malabon City | 500337 | Catmon IS | CITY OF MALABON | 0 | 1 | 24 | 3STY15CL (1CL open) & 3STY9CL | 2014 K10 BATCH 4B | 36184341.37 |  |  | COMPLETED | 1 |  |  | NC0214S00101 | 016OA0017 | 2015-12-09 | 2015-12-17 | 2015-12-29 |  | 2016-02-03 |  |  | NC 2014
K10 (2014) | NCR | Malabon City | 136828 | Dampalit ES | CITY OF MALABON | 0 | 1 | 2 | Completion of 2STY/4CL(construction of remaining 2CL) | 2014 K10 BATCH 4B | 5078460.2437 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Malabon City | 136854 | Epifanio de los Santos ES | CITY OF MALABON | 0 | 1 | 15 | 3STY15CL | 2014 K10 BATCH 4B | 21383013.45 |  |  | COMPLETED | 1 |  |  | NC0214S00102 | 016OA0019 | 2015-12-09 | 2015-12-17 | 2015-12-29 |  | 2016-02-03 |  |  | NC 2014
K10 (2014) | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 19220118.3984 |  |  | COMPLETED | 1 | [8 empty] | 2015-10-30 |  |  | NC 2014
K10 (2014) | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | 0 | 1 | 7 | Completion of 2STY/10CL(construction of remaining 7CL) | 2014 K10 BATCH 4B | 7383047.4188 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Malabon City | 305447 | Malabon NHS | Malabon City | 0 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Malabon City | 136844 | Muzon ES | CITY OF MALABON | 0 | 1 | 5 | Completion of 2STY/6CL(construction of remaining 5CL) | 2014 K10 BATCH 4B | 8023252.8469 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Malabon City | 136831 | Panghulo ES | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 19220118.3984 |  |  | COMPLETED | 1 | [8 empty] | 2015-10-30 |  |  | NC 2014
K10 (2014) | NCR | Malabon City | 136832 | Panghulo ES I | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 23904509.7656 |  |  | COMPLETED | 1 | 2016-05-05 |  | NC0214S00069 | 015OA0079 | 2015-07-29 | 2015-08-07 | 2015-08-19 | 2015-08-27 | 2015-09-09 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY |  | NC 2014
K10 (2014) | NCR | Malabon City | 305450 | Panghulo NHS | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 19220118.3984 |  |  | COMPLETED | 1 | [8 empty] | 2015-10-30 |  |  | NC 2014
SHS (2014) | NCR | Malabon City | 305449 | Potrero NHS | Malabon City | 0 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 |  |  | NC0214S00136 | 016OA0016 | 2015-12-09 | 2015-12-17 | 2015-12-29 |  | 2016-02-03 |  |  | NC 2014
K10 (2014) | NCR | Malabon City | 136850 | Tinajeros ES | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4B | 15121327.92 |  |  | COMPLETED | 1 | 2016-06-29 |  | NC0214S00103 | 015OA0095 | 2015-10-22 | 2015-11-11 | 2015-11-11 | 2015-11-23 | 2015-12-03 | R.D. TALENS CONSTRUCTION AND TRADING |  | NC 2014
K10 (2014) | NCR | Malabon City | 320504 | Tinajeros NHS - Acacia Annex | CITY OF MALABON | 0 | 1 | 0 | Completion of 3STY/9CL | 2014 K10 BATCH 4B | 1505105.4375 |  |  | COMPLETED | 1 | 2015-09-21 | 2015-09-21 | NC0214S00105 | 015OA0062 | 2015-06-10 | 2015-06-18 | 2015-06-29 | 2015-07-08 | 2015-07-24 | DREAMWORX BUILDER & TRADING, INC. |  | NC 2014
K10 (2014) | NCR | Malabon City | 136839 | Tonsuya ES | CITY OF MALABON | 0 | 1 | 3 | 3STY3CL | 2014 K10 BATCH 3 | 7323603.6303 |  |  | COMPLETED | 1 | [8 empty] | 2015-09-09 |  |  | NC 2014
K10 (2014) | NCR | Malabon City | 136839 | Tonsuya ES | CITY OF MALABON | 0 | 1 | 3 | Completion of 3STY/9CL(construction of remaining 3CL) | 2014 K10 BATCH 4B | 3995299.9594 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Mandaluyong City | 319803 | Eulogio Rodriguez Integ. Sch. | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-03-01 |  | NC0214S00135 | 0150B0159 | 2015-06-30 | 2015-08-17 | 2015-08-27 | 2015-09-18 | 2015-09-30 | TRACSOM BUILDERS, INC. |  | NC 2014
K10 (2014) | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1 | 1 | 20 | 4STY20CL w/ provision for micropiles @ 250mm, 15m depth (Replacement of Burned Bldg.) | 2014 K10 BATCH 3 | 46161534.375 |  |  | COMPLETED | 1 | [9 empty] | ORANI BUILDERS |  | NC 2014
K10 (2014) | NCR | Manila | 305296 | Pres. Sergio Osmena, Sr. High School | TONDO | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | [9 empty] | M.V CALDO CONST. ENGINEERING & SUPPLY |  | NC 2014
SHS (2014) | NCR | Manila | 305296 | Pres. Sergio Osmena, Sr. High School | Manila | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | [9 empty] | SUPREME ABF CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 28544390.625 |  |  | COMPLETED | 1 | [9 empty] | PRECIOUS CONSTRUCTION |  | NC 2014
SHS (2014) | NCR | Manila | 305299 | Dona Teodora Alonzo HS | Manila | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0114S00027 | 15-OE0091 | 2015-07-02 | 2015-07-02 | 2015-07-14 |  |  | HEXAMINDZ CORPORATION |  | NC 2014
SHS (2014) | NCR | Manila | 305303 | Raja Soliman Science and Technology High School | Manila | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | reverted | 0 |  |  | NC0114S00021 | [8 empty] | NC 2014
SHS (2014) | NCR | Manila | 305307 | Claro M. Recto High School | Manila | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0114S00026 | 15-OE0090 | 2015-07-02 | 2015-07-02 | 2015-07-14 |  |  | SUPREME ABF CONSTRUCTION |  | NC 2014
SHS (2014) | NCR | Manila | 305312 | Manila Science High School | Manila | 5 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | reverted | 0 |  |  | NC0114S00030 | [8 empty] | NC 2014
K10 (2014) | NCR | Manila | 305318 | Manuel A. Roxas High School | PACO | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | [9 empty] | TRIPLE 8 CONST. & SUPPLY |  | NC 2014
K10 (2014) | NCR | Manila | 305314 | Gen. Emilio Aguinaldo IS- Annex | Manila | 6 | 1 | 16 | 4STY 16CL(proposed for SHS) | 2014 K10 BATCH 3 | 27539390.625 |  |  | reverted | 0 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 136671 | Barangka ES | Marikina City | 1 | 1 | 10 | 3STY 30CL (phase 2) | 2014 K10 BATCH 4A | 12864000 |  |  | COMPLETED | 1 | 2015-07-05 | 2015-07-03 | NC0214S00090 | 0140B0258 | 2014-12-10 | 2014-12-11 | 2014-12-23 | 2015-01-06 | 2015-01-07 | NVF CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Marikina City | 136672 | Industrial Valley ES | Marikina City | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14195118.3984 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 319907 | Jesus dela Pena NHS | Marikina City | 1 | 1 | 16 | 4STY 16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | COMPLETED | 1 | 2016-01-06 |  | NC0214S00084 | 0150B0290 | 2014-12-10 | 2014-12-11 | 2015-03-30 | 2015-04-28 | 2015-05-12 | FIRMABUILT CONSTRUCTION |  | NC 2014
SHS (2014) | NCR | Marikina City | 319904 | Kalumpang National High School | Marikina City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 319904 | Kalumpang National High School | Marikina City | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 32050584.375 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 319904 | Kalumpang National High School | Marikina City | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4A | 31900584.375 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 136675 | Malanday ES | Marikina City | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4A | 19861783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Marikina City | 305402 | Malanday NHS | Marikina City | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-07-01 |  | NC0214S00133 | 0150B0295 | 2015-10-01 | 2015-10-02 | 2015-10-15 | 2015-10-21 | 2015-11-04 | R.D. TALENS CONSTRUCTION AND TRADING |  | NC 2014
K10 (2014) | NCR | Marikina City | 136676 | Marikina ES | Marikina City | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 136676 | Marikina ES | Marikina City | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4A | 19861783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City |  | San Roque National High School | Marikina City | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 32050584.375 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 136687 | Sto. Nino ES | Marikina City | 1 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | COMPLETED | 1 | 2016-02-05 |  | NC0214S00082 | 0140B0238 | 2014-12-04 | 2014-12-11 | 2015-03-30 | 2015-04-30 | 2015-05-08 | JEMN BUILDERS |  | NC 2014
SHS (2014) | NCR | Marikina City | 319906 | Sto. Nino National High School | Marikina City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 319906 | Sto. Nino National High School | Marikina City | 1 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 136679 | Concepcion Integrated School | Marikina City | 2 | 1 | 3 | Completion of 4STY12CL (Construction of remaining 3CL) | 2014 K10 BATCH 4B | 5625000 |  |  | COMPLETED | 1 | 2015-12-11 | 2015-12-04 | NC0214S00219 | 0150B0127 | 2015-05-13 | 2015-05-15 | 2015-05-26 | 2015-06-16 | 2015-08-14 | LTDL BUILDERS |  | NC 2014
K10 (2014) | NCR | Marikina City | 136682 | H. Bautista ES | Marikina City | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 305398 | Marikina HS | Marikina City | 2 | 1 | 32 | 2 UNITS 4STY12CL & 4STY8CL | 2014 K10 BATCH 3 | 55209089.5312 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 136677 | Nangka ES | Marikina City | 2 | 1 | 12 | 4STY 12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 136677 | Nangka ES | Marikina City | 2 | 1 | 0 | Construction of remaining 1 bay of stairs for both buildings (4STY20CL & 3STY9CL) and connecting bridge | 2014 K10 BATCH 4B | 4968750 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 305404 | Parang HS | Marikina City | 2 | 1 | 24 | 2UNITS 4STY12CL | 2014 K10 BATCH 3 | 40023567.1875 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 136685 | SSS Village ES | Marikina City | 2 | 1 | 24 | 2 units of 4STY/12CL | 2014 K10 BATCH 3 | 40023567.1875 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Marikina City | 136686 | St. Mary ES | Marikina City | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Muntinlupa City | 136910 | Bayanan Elementary School Unit I | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Muntinlupa City | 136900 | F. de Mesa ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15205622.3438 |  |  | COMPLETED | 1 | 2015-10-30 | 2015-10-30 | NC0214S00086 | 150I0005 | 2015-01-26 | 2015-01-26 | 2015-02-09 | 2015-02-20 | 2015-03-05 | MRRM TRADING & CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Muntinlupa City | 136901 | Itaas Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4B | 31102890.27 |  |  | COMPLETED | 1 |  |  | NC0214S00145 | 15OI0161 | 2015-12-14 | 2015-12-16 | 2015-12-28 | 2016-12-29 | 2016-01-15 | CHIARA CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Muntinlupa City | 136902 | Lakeview ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15205622.3438 |  |  | COMPLETED | 1 | 2015-09-30 |  | NC0214S00077 | 15OI0004 | 2015-01-26 | 2015-01-28 | 2015-02-09 | 2014-02-16 | 2015-03-05 | VICVERA BUILDERS,INC. |  | NC 2014
K10 (2014) | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 | 1 | 60 | 3 UNITS 4STY20CL | 2014 K10 BATCH 3 | 96181903.125 |  |  | COMPLETED | 1 |  |  | NC0214S00142 | [8 empty] | NC 2014
SHS (2014) | NCR | Muntinlupa City | 305469 | Muntinlupa Science High School | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22692343.62 |  |  | COMPLETED | 1 | 2016-06-18 |  | NC0214S00131 | 15OI0107 | 2015-08-25 | 2015-08-19 | 2015-09-07 | 2015-09-15 | 2015-10-21 | ORANI BUILDERS & SUPPLY |  | NC 2014
K10 (2014) | NCR | Muntinlupa City | 136914 | Sucat Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-09-08 | 2015-09-08 | NC0214S00051 | 140I0099 | 2015-01-04 | 2015-01-07 | 2015-01-20 | 2015-02-06 | 2015-02-26 | REDCAR TRADING & CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Muntinlupa City | 136906 | Tunasan ES | CITY OF MUNTINLUPA | 0 | 1 | 16 | 2UNITS 4STY8CL | 2014 K10 BATCH 4B | 29795037.68 |  |  | reverted | 0 |  |  | NC0214S00144 | 15OI0164 | 2015-12-14 | 2015-12-16 | 2015-12-28 | 2016-12-29 | 2016-01-15 | ORANI BUILDERS & SUPPLY |  | NC 2014
K10 (2014) | NCR | Navotas |  | Bangkulasi NHS | CITY OF NAVOTAS | 0 | 1 | 12 | 3STY 12CL | 2014 K10 BATCH 3 | 28929509.7656 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Navotas | 136858 | Dagat-dagatan Elementary School | CITY OF NAVOTAS | 0 | 1 | 6 | Micropiles | 2014 K10 BATCH 4A | 7543437.8817 |  |  | COMPLETED | 1 | 2015-05-08 | 2015-05-08 | NC0214S00095 | 014OA0051 | 2014-12-04 | 2014-12-05 | 2014-12-09 | 2014-12-24 | 2015-01-09 | STRUKTURA TEKNIKA SERVICES CO. |  | NC 2014
K10 (2014) | NCR | Navotas | 136859 | Kapitbahayan Elementary School | CITY OF NAVOTAS | 0 | 1 | 6 | Micropiles | 2014 K10 BATCH 4A | 7543437.8817 |  |  | COMPLETED | 1 | 2015-05-08 | 2015-05-08 | NC0214S00092 | 014OA0047 | 2014-12-04 | 2014-12-05 | 2014-12-09 | 2014-12-24 | 2015-01-09 | STRUKTURA TEKNIKA SERVICES CO. |  | NC 2014
K10 (2014) | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | 0 | 1 | 4 | cement grouting at 10 meter depth | 2014 K10 BATCH 4A | 1593230.51 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | 0 | 1 |  | 3STY12CL | 2014 K10 BATCH 3 | 28929509.7656 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | 0 | 1 | 0 | cement grouting at 13.5 meter depth | 2014 K10 BATCH 4A | 1433787.4509 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-07 | NC0214S00096 | 014OA0050 | 2014-12-04 | 2014-12-05 | 2014-12-09 | 2014-12-24 | 2015-01-09 | FEL-GENE CONSTRUCTION |  | NC 2014
SHS (2014) | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 22937518.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | 0 | 1 |  | 3STY12CL | 2014 K10 BATCH 3 | 23904509.7656 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 3 | 28929509.7656 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Navotas | 305457 | Tangos National High School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 27397518.84 |  |  | COMPLETED | 1 | 2016-04-23 |  | NC0214S00129 | 015OA0093 | 2015-09-18 | 2015-09-28 | 2015-10-08 | 2015-10-15 | 2015-10-27 | J. SIMEON CONSTRUCTION |  | NC 2014
SHS (2014) | NCR | Navotas | 305455 | Tanza National High School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 19897518.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Navotas | 305455 | Tanza National High School | CITY OF NAVOTAS | 0 | 1 | 3 | cement grouting | 2014 K10 BATCH 4A | 3242509.8498 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Parañaque City | 136754 | La Huerta ES | CITY OF PARAÑAQUE | 1 | 1 | 32 | 4STY32CL | 2014 K10 BATCH 3 | 51340935 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Parañaque City | 136757 | Paranaque Elementary School Unit II | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Parañaque City | 136756 | Paranaque ES Central | CITY OF PARAÑAQUE | 1 | 1 | 36 | 4STY24CL & 4STY/12CL | 2014 K10 BATCH 3 | 58442484.8438 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Parañaque City | 305426 | Paranaque National High School - Baclaran | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 19205522.3438 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Parañaque City | 136765 | Sto. Niño ES | CITY OF PARAÑAQUE | 1 | 1 | 12 | 4STY12CL only since a 3STY3CL bldg was already constructed at the proposed site | 2014 K10 BATCH 4B | 22152343.62 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Parañaque City |  | Don Bosco ES (El Dorado) | CITY OF PARAÑAQUE | 2 | 1 | 24 | 4STY24CL | 2014 K10 BATCH 3 | 38430701.25 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Parañaque City |  | Marcelo Green HS | CITY OF PARAÑAQUE | 2 | 1 | 16 | 4STY16CL(open 4CL @ GF) | 2014 K10 BATCH 3 | 20768199.0547 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Parañaque City | 136758 | Sampaloc Site II ES | CITY OF PARAÑAQUE | 2 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4B | 31102890.27 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Pasay City | 305367 | Pasay City East HS | Pasay City | 0 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-04-01 |  | NC0114S00023 | 15OH0074 | 2015-07-15 | 2015-07-27 | 2015-08-27 | 2015-08-30 | 2015-09-10 | HERBANA BUILDERS AND SUPPLY |  | NC 2014
SHS (2014) | NCR | Pasay City | 319602 | Philippine National School for the Blind | Pasay City | 0 |  |  | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Pasay City | 136595 | Rivera Village ES | Pasay City | 0 | 1 | 9 | 4STY9CL (using 4STY12CL open GF) | 2014 K10 BATCH 3 | 19107283.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Pasay City | 136601 | Timoteo Paez ES | Pasay City | 0 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 32050584.375 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | CITY OF PASIG | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-23 |  | NC0214S00119 | 0150B0167 | 2015-07-01 | 2015-07-03 | 2015-07-14 | 2015-08-04 | 2015-08-27 | L.P.O. ENTERPRISES |  | NC 2014
K10 (2014) | NCR | Quezon City | 136490 | Balingasa Elementary School | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-10-06 | 2015-10-06 | NC0314S00021 | 14OF0130 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | AYLAN CONSTRUCTION & TRADING |  | NC 2014
K10 (2014) | NCR | Quezon City | 136500 | Bungad ES | QUEZON CITY | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-10-07 | 2015-10-07 | NC0314S00022 | 14OF0131 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | AYLAN CONSTRUCTION & TRADING |  | NC 2014
SHS (2014) | NCR | Quezon City | 305322 | Eulogio Rodriguez, Jr. HS | Quezon City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-23 |  | NC0314S00061 | 15OF0111 | 2015-07-15 | 2015-07-24 | 2015-08-05 | 2015-08-24 | 2015-08-25 | AYLAN CONSTRUCTION & TRADING |  | NC 2014
SHS (2014) | NCR | Quezon City | 305321 | Judge Juan Luna HS | Quezon City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0314S00067 | 15OF0123 | 2015-08-12 | 2015-08-13 | 2015-08-25 |  |  | TAPNIO AND TAN CONSTRUCTION AND DEVT. CORPORATION |  | NC 2014
K10 (2014) | NCR | Quezon City | 136509 | Project 6 ES | QUEZON CITY | 1 | 1 | 0 | Completion of 4STY/8CL(Ramp, plumbing, sanitary & tile works(incl masonry for toilet cubicles), security grilles, railings) | 2014 K10 BATCH 4B | 364687.5 |  |  | COMPLETED | 1 | 2015-10-25 | 2015-10-25 | NC0314S00046 | 15OF0120 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-21 | AYLAN CONSTRUCTION & TRADING |  | NC 2014
SHS (2014) | NCR | Quezon City | 305329 | Quezon City Science HS | Quezon City | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-05-23 |  | NC0314S00065 | 15OF0112 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | JYBL CONSTRUCTION & TRADING |  | NC 2014
K10 (2014) | NCR | Quezon City | 136505 | San Antonio ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Quezon City | 136498 | San Francisco ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1 | 2016-05-23 |  | NC0314S00044 | 15OF0103 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | AYLAN CONSTRUCTION & TRADING |  | NC 2014
SHS (2014) | NCR | Quezon City | 305327 | San Francisco HS | Quezon City | 1 | 1 | 16 | 4STY16CL | 2014 SHS BATCH 1 | 26702469.42 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Quezon City | 305327 | San Francisco HS | Quezon City | 1 | 1 | 16 | 4STY16CL | 2014 SHS BATCH 1 | 26702469.42 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Quezon City | 305324 | Sergio Osmena, Sr. HS to BALINGASA HS | Quezon City | 1 | 1 |  | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-10-12 |  | NC0314S00052 | 15OF0136 | 2015-08-18 | 2015-09-04 | 2015-09-29 | 2015-10-09 | 2015-10-13 | AYLAN CONSTRUCTION & TRADING |  | NC 2014
K10 (2014) | NCR | Quezon City | 136506 | Toro Hills ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Quezon City | 136506 | Toro Hills ES | QUEZON CITY | 1 | 1 | 0 | Completion of 4STY/12CL(Plumbing, sanitary & tile works, blackboards) | 2014 K10 BATCH 4B | 279375 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Quezon City | 136539 | Bagong Silangan ES | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Quezon City | 136539 | Bagong Silangan ES | QUEZON CITY | 2 | 1 | 0 | Completion of 4STY/8CL(Plumbing (incl. septic tank), sanitary & tile works, security grilles) | 2014 K10 BATCH 4B | 414375 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Quezon City | 305331 | Commonwealth HS | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15105522.3438 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Quezon City | 305331 | Commonwealth HS | Quezon City | 2 | 1 | 20 | 4STY20CL | 2014 SHS BATCH 1 | 31102890.27 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Quezon City | 136542 | Dona Juana ES | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-11-30 | NC0314S00026 | 14OF0133 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-12 | JAMARI CONSTRUCTION (FORMERLY FRAE CONSTRUCTION) |  | NC 2014
K10 (2014) | NCR | Quezon City | 319505 | Judge Feliciano Belmonte, Sr. HS | QUEZON CITY | 2 | 1 | 24 | 4STY16CL & 4STY8CL | 2014 K10 BATCH 3 | 42564912.9688 |  |  | COMPLETED | 1 | 2016-08-01 |  | NC0314S00034 | 15OF0062 | 2014-12-04 | 2015-03-13 | 2015-06-03 | 2015-06-11 | 2015-06-25 | TAPNIO AND TAN CONSTRUCTION AND DEVT. CORPORATION |  | NC 2014
K10 (2014) | NCR | Quezon City |  | New Holy Spirit HS (Annex) | Quezon City | 2 | 1 | 40 | 2 UNITS OF 4STY 20CL | 2014 K10 BATCH 3 | 64101168.75 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Quezon City | 136548 | Payatas B ES | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-11-08 | 2015-10-07 | NC0314S00024 | 14OF0127 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | HONEYVILLE CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Quezon City | 136540 | Pres. Corazon C. Aquino ES (Batasan Hills ES) | QUEZON CITY | 2 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | COMPLETED | 1 | 2016-03-06 |  | NC0314S00020 | 14OF0126 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | AYLAN CONSTRUCTION & TRADING |  | NC 2014
K10 (2014) | NCR | Quezon City | 305347 | Carlos P. Garcia HS | QUEZON CITY | 3 | 1 | 8 | 4STY/8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Quezon City | 305347 | Carlos P. Garcia HS | Quezon City | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Quezon City | 136557 | Cubao ES | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4B | 26702469.42 |  |  | COMPLETED | 1 | 2016-05-13 |  | NC0314S00048 | 15OG0088 | 2015-08-05 | 2015-08-20 | 2015-08-24 | 2015-09-01 | 2015-09-17 | RCDG CONSTRUCTION CORPORATION |  | NC 2014
SHS (2014) | NCR | Quezon City | 305352 | Juan Sumulong HS | Quezon City | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-02-17 |  | NC0314S00060 | 15OG0093 | 2015-08-05 | 2015-08-15 | 2015-08-24 | 2015-09-10 | 2015-09-21 | GREENWALL CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Quezon City | 136565 | Teodora Alonzo ES | QUEZON CITY | 3 | 1 | 4 | 4STY4CL | 2014 K10 BATCH 3 | 10205307.6562 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | NC0314S00019 | 14og00088 | 2014-11-07 | 2014-11-20 | 2014-11-25 | 2014-12-16 | 2014-12-19 | METRICS CONSTRUCTION & TRADING |  | NC 2014
SHS (2014) | NCR | Quezon City | 305355 | Carlos L. Albert HS | Quezon City | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Quezon City | 305362 | Dr. Josefa Jara Martinez HS | Quezon City | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-04-24 |  | NC0314S00058 | 15OG0100 | 2015-08-20 | 2015-09-01 | 2015-09-07 | 2015-09-22 | 2015-09-28 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS |  | NC 2014
SHS (2014) | NCR | Quezon City | 305361 | Manuel Roxas HS | Quezon City | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-06-06 |  | NC0314S00057 | 15-OG084 | 2015-07-28 | 2015-08-07 | 2015-10-20 | 2015-11-02 | 2015-11-06 | ST. GERRARD CONSTRUCTION |  | NC 2014
SHS (2014) | NCR | Quezon City | 305356 | Ponciano Bernardo HS | Quezon City | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-03-19 |  | NC0314S00056 | 15-OG083 | 2015-07-27 | 2015-08-10 | 2015-08-10 | 2015-08-29 | 2015-09-01 | GRAIA CONSTRUCTION CORPORATION |  | NC 2014
SHS (2014) | NCR | Quezon City | 305359 | Quezon City HS | Quezon City | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-03-02 |  | NC0314S00053 | 15OG-0085 | 2015-07-22 | 2015-08-08 | 2015-08-10 | 2015-09-01 | 2015-09-04 | E.A. RAMIREZ CONSTRUCTION, INC. |  | NC 2014
K10 (2014) | NCR | Quezon City | 136527 | Dona Rosario Elementary School | Quezon City | 5 | 1 | 0 | Completion of 4STY/8CL(2 units toilets, catch basins, electric fans, security grilles) | 2014 K10 BATCH 4B | 398437.5 |  |  | COMPLETED | 1 | 2015-10-25 | 2015-10-25 | NC0314S00039 | 15OF0120 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-21 | AYLAN CONSTRUCTION & TRADING |  | NC 2014
K10 (2014) | NCR | Quezon City | 319504 | Dona Rosario HS | Quezon City | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-10-08 | 2015-10-08 | NC0314S00032 | 14OF0125 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | JYBL CONSTRUCTION & TRADING |  | NC 2014
K10 (2014) | NCR | Quezon City | 136534 | Lagro ES | Quezon City | 5 | 1 | 3 | Completion of 3STY 9CL: 3CL at 3rd Floor (masongry, carpentry. Electrical, painting), roofing and steel works, plumbing and sanitary works. Security grilles for the whole building | 2014 K10 BATCH 4A | 3718500 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-05-11 | NC0314S00035 | 14OF0047 | 2014-11-28 | 2014-11-29 | 2014-12-04 | 2014-12-28 | 2015-01-06 | AYLAN CONSTRUCTION & TRADING |  | NC 2014
K10 (2014) | NCR | Quezon City | 305336 | Lagro HS | Quezon City | 5 | 1 | 0 | Completion of 4STY/16CL (Finishing work, plumbing, sanitary, tile works, cubicles, septic tank, security grills) | 2014 K10 BATCH 4B | 564375 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Quezon City | 136535 | Maligaya ES | Quezon City | 5 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4B | 26702469.42 |  |  | COMPLETED | 1 | 2016-06-28 |  | NC0314S00040 | 15OF0106 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | R.D. MANDANAS CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Quezon City | 305338 | Maligaya HS | Quezon City | 5 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Quezon City | 136537 | North Fairview ES | Quezon City | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 | 2016-05-17 |  | NC0314S00049 | 15OF0108 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | E.A. RAMIREZ CONSTRUCTION, INC. |  | NC 2014
K10 (2014) | NCR | Quezon City | 136523 | Odelco ES | Quezon City | 5 | 1 | 4 | 4STY4CL | 2014 K10 BATCH 3 | 10205307.6562 |  |  | COMPLETED | 1 | 2015-07-10 | 2015-09-07 | NC0314S00030 | 14OF0123 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | TAPNIO AND TAN CONSTRUCTION AND DEVT. CORPORATION |  | NC 2014
K10 (2014) | NCR | Quezon City | 136528 | Rosa L. Susano - Novaliches ES | Quezon City | 5 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4B | 31102890.27 |  |  | COMPLETED | 1 | 2016-08-27 |  | NC0314S00047 | 15OF0107 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | MPJR BUILDERS COMPANY |  | NC 2014
K10 (2014) | NCR | Quezon City | 136538 | San Agustin ES | Quezon City | 5 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | 2015-11-07 | 2015-11-05 | NC0314S00031 | 14OF0124 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | PRISMODIAL CONSTRUCTION CORPORATION (FOR. PRISMODI |  | NC 2014
K10 (2014) | NCR | Quezon City | 136529 | San Gabriel ES | Quezon City | 5 | 1 | 0 | Completion of 4STY/12CL(Plumbing, sanitary & tile works (incl masonry for cubicles), septic tank, security grilles) | 2014 K10 BATCH 4B | 564375 |  |  | COMPLETED | 1 | 2015-10-25 | 2015-10-25 | NC0314S00041 | 15OF0120 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-21 | AYLAN CONSTRUCTION & TRADING |  | NC 2014
SHS (2014) | NCR | Quezon City | 305342 | Sta. Lucia HS | Quezon City | 5 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-10-22 |  | NC0314S00055 | 15OF0143 | 2015-08-18 | 2015-09-04 | 2015-09-29 | 2015-10-06 | 2015-10-22 | JYBL CONSTRUCTION & TRADING |  | NC 2014
K10 (2014) | NCR | Quezon City | 222501 | West Fairview Elementary School | Quezon City | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-29 |  | NC0314S00042 | 15OF0109 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | MPJR BUILDERS COMPANY |  | NC 2014
SHS (2014) | NCR | Quezon City | 305335 | Ismael Mathay, Sr. HS | Quezon City | 6 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-30 |  | NC0314S00054 | 15OF0114 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | M O M ENTERPRISES |  | NC 2014
K10 (2014) | NCR | Quezon City | 136522 | Leopoldo B. Santos ES | Quezon City | 6 | 1 | 8 | 4STY/8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-10-08 | 2015-10-08 | NC0314S00033 | 14OF0122 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | HONEYVILLE CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Quezon City | 136524 | Placido del Mundo ES | Quezon City | 6 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-30 |  | NC0314S00037 | 15OF0110 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-28 | MPJR BUILDERS COMPANY |  | NC 2014
SHS (2014) | NCR | Taguig City & Pateros | 320607 | Agripino Manalo National HS | Taguig City & Pateros | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Reverted | 0 |  |  | NC0214S00120 | [8 empty] | NC 2014
K10 (2014) | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Taguig City & Pateros | 136894 | Capt. H. Francisco ES Annex | Pateros | 1 | 1 | 12 | 4STY 12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Taguig City & Pateros | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Taguig City & Pateros | 136883 | Cipriano P. Sta. Teresa Elementary School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Taguig City & Pateros | 136871 | Ciriaco P. Tiñga Elementary School | TAGUIG CITY | 1 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Taguig City & Pateros | 305467 | Maria Concepcion Cruz HS | Taguig City & Pateros | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Reverted | 0 |  |  | NC0214S00121 | 0150B0164 | 2015-07-05 | 2015-07-06 | 2015-07-16 | 2015-07-31 |  | ORANI BUILDERS & SUPPLY |  | NC 2014
K10 (2014) | NCR | Taguig City & Pateros | 136874 | Napindan Elementary School | TAGUIG CITY | 1 | 1 | 24 | 4STY24CL | 2014 K10 BATCH 3 | 38430701.25 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | PATEROS | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Taguig City & Pateros | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-09-12 |  | NC0214S00048 | 0140B0253 | 2014-12-10 | 2014-12-11 | 2014-12-23 | 2015-01-16 | 2015-02-14 | E.R. VENZON CONSTRUCTION |  | NC 2014
SHS (2014) | NCR | Taguig City & Pateros | 305460 | Taguig National High School | Taguig City & Pateros | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-06-05 |  | NC0214S00122 | 0150B0271 | 2015-08-13 | 2015-08-17 | 2015-08-27 | 2015-09-18 | 2015-10-07 | R.T. MORABE CONSTRUCTION |  | NC 2014
SHS (2014) | NCR | Taguig City & Pateros | 305464 | Tipas National High School | Taguig City & Pateros | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-06-13 |  | NC0214S00124 | 0150B0303 | 2015-10-08 | 2015-10-09 | 2015-10-22 | 2015-11-10 | 2015-11-16 | R.S. MESA CONSTRUCTION CORPORATION |  | NC 2014
K10 (2014) | NCR | Taguig City & Pateros |  | DepED Property | Taguig- Pateros | 2 | 1 | 24 | 2 Units 4STY 12CL(elevated @ 1.5m) | 2014 K10 BATCH 3 | 44137296.8717 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Taguig City & Pateros | 320602 | Maria Asuncion Rodriguez Tiñga High School | Taguig City & Pateros | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Reverted | 0 | 2016-03-05 |  | NC0214S00125 | 015B0164 | 2015-07-01 | 2015-07-03 | 2015-07-14 | 2015-08-04 | 2015-09-07 |  |  | NC 2014
K10 (2014) | NCR | Taguig City & Pateros | 305463 | Signal Village NHS | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Taguig City & Pateros | 305465 | Western Bicutan NHS | TAGUIG CITY | 2 | 1 | 7 | 4STY7CL (with 1 stair open below 1cl) | 2014 K10 BATCH 3 | 15064922.3438 |  |  | COMPLETED | 1 | 2016-03-12 |  | NC0214S00034 | 0140B0254 | 2014-12-10 | 2014-12-11 | 2014-12-23 | 2015-01-06 | 2015-01-07 | HONY TRADING & CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Valenzuela City | 320404 | Bignay NHS | CITY OF VALENZUELA | 1 | 1 | 0 | Completion of 4STY8CL | 2014 K10 BATCH 4B | 1363279.6969 |  |  | COMPLETED | 1 | 2015-10-18 |  |  |  | 2015-07-22 |  | 2015-08-18 |  |  | C.B. Tampengco Const. & Supply |  | NC 2014
SHS (2014) | NCR | Valenzuela City | 320404 | Bignay NHS | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14907518.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Valenzuela City | 136802 | Coloong ES | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Valenzuela City | 305440 | Lawang Bato NHS | CITY OF VALENZUELA | 1 | 1 | 3 | 3STY3CL | 2014 K10 BATCH 3 | 7323603.6328 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-09-10 | NC0214S00040 | 14OD0077 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-25 | 2015-02-27 | R.D. TALENS CONSTRUCTION AND TRADING |  | NC 2014
K10 (2014) | NCR | Valenzuela City | 136797 | Malinta ES | CITY OF VALENZUELA | 1 | 1 | 8 | Completion of 3STY12CL (incl. finishing works, toilets, roofing, carpentry) | 2014 K10 BATCH 4B | 4523437.5 |  |  | COMPLETED | 1 | 2015-12-02 |  | NC0214S00111 | 15OD0065 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-18 | 2015-09-04 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP. |  | NC 2014
SHS (2014) | NCR | Valenzuela City | 305438 | Malinta NHS | Valenzuela City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14907518.84 |  |  | COMPLETED | 1 |  |  | NC0214S00138 | 15OD0101 | 2015-10-07 | 2015-10-19 | 2015-10-20 | 2015-10-26 | 2015-11-17 | CARDRIAN BUILDERS CO. |  | NC 2014
K10 (2014) | NCR | Valenzuela City | 136806 | Pasolo ES | CITY OF VALENZUELA | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14195118.4009 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
K10 (2014) | NCR | Valenzuela City | 136807 | Pio Valenzuela ES | CITY OF VALENZUELA | 1 | 1 | 8 | Completion of 3STY12CL(construction of remaining 8CL) | 2014 K10 BATCH 4B | 5533060.275 |  |  | COMPLETED | 1 | 2016-01-01 |  | NC0214S00110 | 15OD0071 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-18 | 2015-09-04 | LARSEN-DUTCHER CONSTRACTOR |  | NC 2014
K10 (2014) | NCR | Valenzuela City | 136812 | Roberta de Jesus ES | CITY OF VALENZUELA | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2016-02-17 |  | NC0214S00116 | 15OD0074 | 2015-08-14 | 2015-08-26 | 2015-08-27 | 2015-09-04 | 2015-09-21 | CARDRIAN BUILDERS CO. |  | NC 2014
K10 (2014) | NCR | Valenzuela City | 320402 | Vicente Trinidad NHS (Punturin NHS) | CITY OF VALENZUELA | 1 | 1 | 0 | Completion of 4STY8CL | 2014 K10 BATCH 4B | 1382887.575 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-16 | NC0214S00118 | 15OD0067 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-16 | 2015-09-04 | J. SIMEON CONSTRUCTION |  | NC 2014
K10 (2014) | NCR | Valenzuela City | 136811 | WawangPulo ES | CITY OF VALENZUELA | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10817093.5547 |  |  | COMPLETED | 1 | [11 empty] | NC 2014
SHS (2014) | NCR | Valenzuela City | 320407 | Wawangpulo National High School | Valenzuela City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14907518.84 |  |  | COMPLETED | 1 |  |  | NC0214S00127 | [8 empty] | NC 2014
K10 (2014) | NCR | Valenzuela City | 136822 | Caruhatan West ES | CITY OF VALENZUELA | 2 | 1 | 2 | Completion of 3STY/6CL | 2014 K10 BATCH 4B | 2863237.8662 |  |  | COMPLETED | 1 | 2015-11-17 |  | NC0214S00115 | 15OD0064 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-18 | 2015-11-05 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY |  | NC 2014
K10 (2014) | NCR | Valenzuela City | 136825 | Marulas Central ES | CITY OF VALENZUELA | 2 | 1 | 0 | Completion of 4STY/8CL & 3STY/9CL | 2014 K10 BATCH 4B | 1274735.0159 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-11-02 | NC0214S00109 | 15OD0066 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-17 | 2015-09-04 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY |  | NC 2014
K10 (2015) | NCR | Caloocan City | 136650 | Bagbaguin ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00138 | 15OD0094 | 2015-09-18 | 2015-10-30 | 2015-10-01 | 2015-10-06 | 2015-11-05 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP. |  | NC 2015
K10 (2015) | NCR | Caloocan City | 136641 | Kalayaan ES | Caloocan City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Caloocan City | 319705 | Maypajo HS | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 7 | 22152344 |  |  | COMPLETED | 1 |  |  | NC0215S00154 | [6 empty] | PRISMOIDIAL CONST. CORP. |  | NC 2015
K10 (2015) | NCR | Caloocan City | 136629 | Morning Breeze ES | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 3 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00092 | 15OD0089 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-29 | 2015-10-23 | TM ABAD CONSTRUCTION |  | NC 2015
K10 (2015) | NCR | Caloocan City | 136646 | NHC ES | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00140 | 15OD0102 | 2015-10-07 | 2015-10-16 | 2015-10-20 | 2015-10-26 | 2015-11-17 | CARDRIAN BUILDERS CO. |  | NC 2015
SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 1 (Caloocan City Business High School) | Caloocan City | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 |  |  |  |  | 2015-11-26 |  |  |  |  | ORIENTECH CONSTRUCTION & DEVELOPMENT CORP. |  | NC 2015
SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 11 (Caloocan National Science & Technology High School) | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-04 | 2015-09-22 | 2015-09-24 | 2015-09-29 | 2015-11-05 | H.T.L. CONS'T |  | NC 2015
SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 2 (Cielito Zamora High School) | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-04 | 2015-09-22 | 2015-09-24 | 2015-09-29 | 2015-11-05 | T.M. ABAD CONS'T |  | NC 2015
SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 4 (NHC HS) | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-11 | 2015-09-29 | 2015-10-01 | 2015-10-05 | 2015-11-05 | CARDRIAN BUILDERS CO. |  | NC 2015
SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 6 (Bagong Barrio NHS - Annex) | Caloocan City | 1 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | COMPLETED | 1 |  |  |  |  | 2015-11-26 |  |  |  |  | SUPREME ABF CONST. & CONST. SUPPLY CO. INC. |  | NC 2015
SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 7 (AHS-Horacio Dela Costa Annex) | Caloocan City | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 |  |  |  |  | 2015-11-26 |  |  |  |  | GENETIAN BUILDERS |  | NC 2015
SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 9 (Bagumbong High School) | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-11 | 2015-09-29 | 2015-10-01 | 2015-10-05 | 2015-11-05 | VICTORIA DEV'T & CONS'T CORP. |  | NC 2015
K10 (2015) | NCR | Caloocan City | 136649 | Tala ES | Caloocan City | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 30952890.27 |  |  | COMPLETED | 1 |  |  | NC0215S00143 | [8 empty] | NC 2015
K10 (2015) | NCR | Caloocan City | 136631 | Talipapa ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00082 | 15OD0095 | 2015-09-18 | 2015-09-30 | 2015-10-01 | 2015-10-06 | 2015-11-05 | CARDRIAN BUILDERS CO. |  | NC 2015
K10 (2015) | NCR | Caloocan City | 305371 | Talipapa HS | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 7 | 22152344 |  |  | COMPLETED | 1 |  |  | NC0215S00150 |  | 2015-09-18 | 2015-09-30 | 2015-10-01 | 2015-10-09 | 2015-11-05 |  |  | NC 2015
K10 (2015) | NCR | Caloocan City | 136638 | Urduja ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Caloocan City | 136638 | Urduja ES | Caloocan City | 1 |  | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26552469.42 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Caloocan City | 136618 | Gregoria de Jesus ES | Caloocan City | 2 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00137 | 15OD0096 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-10-01 | 2015-10-23 | CARDRIAN BUILDERS CO. |  | NC 2015
K10 (2015) | NCR | Caloocan City | 136609 | Kaunlaran ES | Caloocan City | 2 | 1 |  | Completion of 4STY6CL (Open Ground) | 2015 COMPLETION BATCH 4 | 843004.5563 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | Caloocan City | 2 | 1 |  | Completion of 2 UNITSof 4STY20CL | 2015 COMPLETION BATCH 4 | 4993346.46 |  |  |  | 0 | [11 empty] | NC 2015
K10 (2015) | NCR | Caloocan City | 305390 | Maria Clara HS | Caloocan City | 2 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 3 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0215S00083 | 15OD0092 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-30 | 2015-10-23 | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM |  | NC 2015
SHS (2015) | NCR | Caloocan City | 305392 | Proposed Stand Alone 3 (M. B. Asistio Sr. HS Unit 1) | Caloocan City | 2 | 1 | 32 | 4STY16CL | 2015 SHS BATCH 8 | 53404938.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Caloocan City | 500330 | Proposed Stand Alone 5 (Tandang Sora IS) | Caloocan City | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 |  |  |  |  | 2015-11-05 |  |  |  |  | EDISON DEV'T CONST. | ongoing; rebidded | NC 2015
SHS (2015) | NCR | Caloocan City | 500330 | Proposed Stand Alone 5 (Tandang Sora IS) | Caloocan City | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | COMPLETED | 1 | [9 empty] | C.B. TAMPENGCO CONST. & SUPPLY |  | NC 2015
K10 (2015) | NCR | Caloocan City | 136614 | Sampalukan ES | Caloocan City | 2 | 1 |  | Completion of 3STY6CL | 2015 COMPLETION BATCH 4 | 2088779.1753 |  |  |  | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Caloocan City | 500330 | Tandang Sora IS | Caloocan City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 3780074.83 |  |  |  | 0 |  |  | NC0215S00165 | 15OD0088 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-30 | 2015-10-23 | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM | Contract Terminated | NC 2015
SHS (2015) | NCR | City of San Juan |  | Proposed Stand Alone SHS 1 (Tech-Voc) (Pinaglabanan ES) | City of San Juan | 0 | 1 | 9 | 4STY12CL (open 3 cl @ ground) | 2015 SHS BATCH 5 | 21192344 |  |  | reverted | 0 | [11 empty] | NC 2015
SHS (2015) | NCR | City of San Juan | 305423 | San Juan National HS (Academic) | City of San Juan | 0 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | reverted | 0 |  |  | NC0215S00128 | [8 empty] | NC 2015
SHS (2015) | NCR | Las Piñas City | 320304 | Las Pinas City National Science High School | CITY OF LAS PIÑAS | 0 | 1 |  | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Las Piñas City | 320304 | Las Pinas City National Science High School | CITY OF LAS PIÑAS | 0 | 1 | 16 | 2UNITS 4STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 21280072.63 |  |  | COMPLETED | 1 |  |  | NC0215S00075 |  | 2015-08-17 |  | 2015-09-07 |  | 2016-03-01 | DAVHEZ TRADING & CONSTRUCTION |  | NC 2015
SHS (2015) | NCR | Las Piñas City | 305430 | Las Piñas National HIgh School | CITY OF LAS PIÑAS | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | COMPLETED | 1 |  |  | NC0215S00068 |  | 2015-12-17 |  | 2016-01-05 |  | 2016-03-23 | ORANI BUILDERS AND SUPPLY |  | NC 2015
SHS (2015) | NCR | Las Piñas City | 305430 | Las Piñas National HIgh School | CITY OF LAS PIÑAS | 0 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0215S00069 |  | 2015-12-17 |  | 2016-01-05 |  | 2016-03-23 | ORANI BUILDERS AND SUPPLY |  | NC 2015
K10 (2015) | NCR | Las Piñas City | 136778 | Manuyo Elementary School | CITY OF LAS PIÑAS | 0 | 1 | 3 | 3STY3CL | 2015 K10 BATCH 6 | 6653472.88 |  |  | COMPLETED | 1 |  |  | NC0215S00136 | 15OI0154 | 2015-12-03 |  | 2015-12-22 |  | 2016-01-15 | MRJR CONSTRUCTION & TRADING |  | NC 2015
SHS (2015) | NCR | Las Piñas City |  | Proposed Stand Alone SHS 1 (Las Pinas CES) | CITY OF LAS PIÑAS | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  |  |  | 2015-10-28 |  | 2015-11-23 |  | 2015-12-22 | ORANI BUILDERS AND SUPPLY |  | NC 2015
K10 (2015) | NCR | Malabon City | 136840 | Amang Rodriguez ES | CITY OF MALABON | 0 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 1718800.4616 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | 0 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 1718800.4616 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | 15 | 3sty15cl | 2015 ADDITIONAL FUND BATCH 9 | 6111685.53 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Malabon City | 320502 | Malabon NHS - Concepcion Voc-Tech Annex | CITY OF MALABON | 0 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 7 | 10417132 |  |  | COMPLETED | 1 |  |  | NC0215S00153 | [5 empty] | 2016-03-18 |  |  | NC 2015
K10 (2015) | NCR | Malabon City | 136831 | Panghulo ES | CITY OF MALABON | 0 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 1718800.4616 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Malabon City | 305450 | Panghulo NHS | CITY OF MALABON | 0 | 1 |  | Completion of Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 1718800.4616 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Malabon City |  | Proposed Stand Alone SHS 1 (TNHS-Acacia Annex) | CITY OF MALABON | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1 | [8 empty] | 2016-01-11 |  |  | NC 2015
SHS (2015) | NCR | Malabon City |  | Proposed Stand Alone SHS 2 (Dampalit ES) | CITY OF MALABON | 0 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 5 | 18222269 |  |  | COMPLETED | 1 | [8 empty] | 2016-07-19 |  |  | NC 2015
SHS (2015) | NCR | Malabon City |  | Proposed Stand Alone SHS 4 (Imelda ES) | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15121328 |  |  | COMPLETED | 1 | [8 empty] | 2016-06-07 |  |  | NC 2015
SHS (2015) | NCR | Malabon City |  | Proposed Stand Alone SHS 4 (Imelda ES) | CITY OF MALABON | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1 | [8 empty] | 2016-01-25 |  |  | NC 2015
SHS (2015) | NCR | Malabon City |  | Proposed Stand Alone SHS 6 (Santiago Syjuco Memorial School) | CITY OF MALABON | 0 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 5 | 21383013 |  |  | COMPLETED | 1 | [8 empty] | 2016-04-11 |  |  | NC 2015
K10 (2015) | NCR | Malabon City | 500339 | Tanong IS | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 7 | 15121328 |  |  | COMPLETED | 1 |  |  | NC0215S00152 | [5 empty] | 2016-03-18 |  |  | NC 2015
K10 (2015) | NCR | Malabon City | 136839 | Tonsuya ES | CITY OF MALABON | 0 | 1 |  | Completion of 3STY3CL | 2015 COMPLETION BATCH 4 | 612128.4262 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Mandaluyong City | 319802 | Highway Hills Integrated School | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 30152344 |  |  | COMPLETED | 1 |  |  | NC0215S00116 | 0150B0301 | 2015-10-08 | 2015-10-09 | 2015-10-22 | 2015-11-04 | 2015-11-16 | TRACSOM BUILDERS, INC. |  | NC 2015
SHS (2015) | NCR | Mandaluyong City | 500331 | Isaac Lopez Integrated School | CITY OF MANDALUYONG | 0 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00070 | [8 empty] | NC 2015
SHS (2015) | NCR | Mandaluyong City | 319804 | Jose Fabella Memorial School | CITY OF MANDALUYONG | 0 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 2 | 35596257.14 |  |  | reverted | 0 |  |  | NC0215S00073 | 0150B300 | 2015-10-08 | 2015-10-09 | 2015-10-22 | 2015-11-12 |  | TRACSOM BUILDERS, INC. |  | NC 2015
SHS (2015) | NCR | Mandaluyong City | 305393 | Mandaluyong High School | CITY OF MANDALUYONG | 0 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 37202469.42 |  |  | COMPLETED | 1 |  |  | NC0215S00067 | 0150B0299 | 2015-10-09 | 2015-10-09 | 2015-10-22 | 2015-10-30 | 2015-11-05 | TRACSOM BUILDERS, INC. |  | NC 2015
SHS (2015) | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 38002890 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 26252344 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0115S00021 | 15-OE0159 | 2015-11-20 | 2015-11-20 | 2015-12-03 |  |  | R.D. TALENS CONSTRUCTION AND TRADING |  | NC 2015
K10 (2015) | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1 | 1 |  | Completion of 4STY20CL | 2015 COMPLETION BATCH 4 | 142465.625 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Manila | 305291 | Tondo High School | TONDO | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0115S00016 | [8 empty] | NC 2015
K10 (2015) | NCR | Manila | 305296 | Pres. Sergio Osmena, Sr. High School | TONDO | 2 | 1 |  | Completion of 4STY8CL | 2015 COMPLETION BATCH 4 | 7694435.2484 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3 | 1 |  | Completion of 4STY16CL | 2015 COMPLETION BATCH 4 | 10909209.6668 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Manila | 305302 | Jose Abad Santos High School | SANTA CRUZ | 3 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | reverted | 0 |  |  | NC0115S00015 | [8 empty] | NC 2015
K10 (2015) | NCR | Manila | 136464 | Moises Salvador Elementary School | Manila | 4 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1 |  |  | NC0115S00017 | 15-OE0158 | 2015-11-20 | 2015-11-20 | 2015-12-03 |  |  | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | NC 2015
SHS (2015) | NCR | Manila | 305308 | Valeriano E. Fugoso Memorial High School | MANILA | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  | NC0115S00020 | [8 empty] | NC 2015
SHS (2015) | NCR | Manila | 305309 | M.Araullo High School | ERMITA | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0115S00014 | 15OH0097 | 2015-10-11 | 2015-10-26 | 2015-10-27 |  |  | WERR CONSTRUCTION INTERNATIONAL |  | NC 2015
K10 (2015) | NCR | Manila | 305318 | Manuel A. Roxas High School | PACO | 5 | 1 |  | Completion of 4STY8CL | 2015 COMPLETION BATCH 4 | 5577284.5063 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Manila | 305314 | Gen. Emilio Aguinaldo IS- Annex | Manila | 6 | 1 |  | Completion of 4STY16CL | 2015 COMPLETION BATCH 4 | 9983526.165 |  |  |  | 0 | [11 empty] | NC 2015
SHS (2015) | NCR | Manila |  | Proposed Stand Alone SHS 6 (Bacood ES) | SAMPALOC | 6 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | COMPLETED | 1 | [9 empty] | HEXAMINDZ CORPORATION |  | NC 2015
K10 (2015) | NCR | Marikina City | 136672 | Industrial Valley ES | Marikina City | 1 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 5999172.5916 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Marikina City | 136675 | Malanday ES | Marikina City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 2239374.87 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Marikina City | 136676 | Marikina ES | Marikina City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 7213523.0963 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Marikina City | 136676 | Marikina ES | Marikina City | 1 |  |  | Completion of 4STY12CL (Batch 4A) | 2015 COMPLETION BATCH 4 | 7462337.94 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Marikina City | 319905 | San Roque National High School | Marikina City | 1 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 3 | 26702469.42 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Marikina City | 319905 | San Roque National High School | Marikina City | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Marikina City | 136680 | Concepcion ES | Marikina City | 2 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | COMPLETED | 1 |  |  | NC0215S00085 | 0150B0293 | 2015-09-23 | 2015-10-05 | 2015-10-06 | 2015-10-29 | 2015-11-06 | ORANI BUILDERS & SUPPLY |  | NC 2015
SHS (2015) | NCR | Marikina City | 305403 | Concepcion Integrated School | Marikina City | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  | NC0215S00115 | 0150B0292 | 2015-09-23 | 2015-09-25 | 2015-10-06 | 2015-10-27 | 2015-11-23 | C.B. GARAY PHILWIDE BUILDERS |  | NC 2015
K10 (2015) | NCR | Marikina City | 136682 | H. Bautista ES | Marikina City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 7213523.0963 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Marikina City | 305398 | Marikina HS | Marikina City | 2 | 1 |  | Completion of 2 Units 4STY12CL & Completion of 4STY8CL | 2015 COMPLETION BATCH 4 | 15730030.3788 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Marikina City | 136677 | Nangka ES | Marikina City | 2 | 1 |  | Completion 4STY12CL | 2015 COMPLETION BATCH 4 | 7213523.0963 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Marikina City | 136684 | Parang ES | Marikina City | 2 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | COMPLETED | 1 |  |  | NC0215S00086 | 0150B0285 | 2015-09-23 | 2015-09-25 | 2015-10-06 | 2015-10-22 | 2015-12-01 | ORANI BUILDERS & SUPPLY |  | NC 2015
K10 (2015) | NCR | Marikina City | 305404 | Parang HS | Marikina City | 2 | 1 |  | Completion of 2 Units 4STY12CL | 2015 COMPLETION BATCH 4 | 13266387.7325 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Marikina City | 305404 | Parang HS | Marikina City | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Marikina City | 136685 | SSS Village ES | Marikina City | 2 | 1 |  | Completion of 2 units of 4STY/12CL | 2015 COMPLETION BATCH 4 | 13266387.7325 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Marikina City | 136686 | St. Mary ES | Marikina City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00087 | 15OI0109 | 2015-08-31 | 2015-09-02 | 2015-09-14 | 2015-09-25 | 2015-10-20 | PRECIOUS CONSTRUCTION |  | NC 2015
K10 (2015) | NCR | Muntinlupa City | 320702 | Muntinlupa Business High School - Sucat Annex | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 3 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00088 | 15OI0159 | 2015-12-14 | 2015-12-16 | 2015-12-28 | 2016-12-29 | 2016-01-19 | LMG CONSTRUCTION |  | NC 2015
SHS (2015) | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 |  | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Muntinlupa City |  | Proposed Stand Alone SHS 1 (Muntinlupa NHS) | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Muntinlupa City |  | Proposed Stand Alone SHS 2 (Cupang SHS) | CITY OF MUNTINLUPA | 0 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Muntinlupa City | 136904 | Putatan ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00139 | 15OI0143 | 2015-11-12 | 2015-11-13 | 2015-11-25 | 2015-12-11 | 2015-12-23 | ORANI BUILDERS & SUPPLY |  | NC 2015
K10 (2015) | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | 0 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 14971327.92 |  |  | COMPLETED | 1 |  |  | NC0215S00145 | [8 empty] | NC 2015
K10 (2015) | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | 0 | 1 | 20 | Completion of 3STY12CL. (Upgrading of 3STY12CL to 4STY20CL INCLUDING COST for soil improvement and additional 1m elevation | 2015 COMPLETION BATCH 4 | 13422977.41 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Navotas | 340628 | Lisan SHS Stand Alone | CITY OF NAVOTAS | 0 | 1 | 17 | 2 units 3STY9CL(1 unit with 1 cl open at the ground floor; 1.5m addl elevation) | 2015 SHS BATCH 5 | 31836524 |  |  | reverted | 0 | [11 empty] | NC 2015
K10 (2015) | NCR | Navotas | 136860 | Navotas Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00144 | [8 empty] | NC 2015
SHS (2015) | NCR | Navotas | 305454 | San Rafael Technological High School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 19897518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00080 | 015OA0091 | 2015-09-18 | 2015-09-28 | 2015-10-08 | 2015-10-16 | 2015-10-27 | VRV CONSTRUCTION AND TRADING |  | NC 2015
K10 (2015) | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00089 | 015OA0097 | 2015-11-02 | 2015-11-19 | 2015-11-27 |  |  | STRUKTURA TEKNIKA SERVICES CO. |  | NC 2015
K10 (2015) | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | 0 | 1 | 12 | Completion of 3STY12CL. (Upgrading of 3STY12CL to 4STY12CL INCLUDING COST for soil improvement and additional 1m elevation | 2015 COMPLETION BATCH 4 | 4379706.6847 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Parañaque City | 136768 | Baclaran ES Unit I | CITY OF PARAÑAQUE | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 30952890.27 |  |  | COMPLETED | 1 |  |  | NC0215S00146 | 15OC0075 | 2015-08-20 | 2015-08-21 | 2015-09-03 | 2015-09-07 | 2015-09-18 | PRECIOUS CONSTRUCTION |  | NC 2015
K10 (2015) | NCR | Parañaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00141 | 15OC0069 | 2015-08-17 | 2015-08-20 | 2015-09-01 | 2015-09-08 | 2015-09-18 | MPJR BUILDERS COMPANY |  | NC 2015
K10 (2015) | NCR | Parañaque City | 136762 | Don Galo ES | CITY OF PARAÑAQUE | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 30952890.27 |  |  | COMPLETED | 1 |  |  | NC0215S00149 | 15OC0076 | 2015-08-20 | 2015-08-21 | 2015-09-03 | 2015-09-07 | 2015-09-18 | PRECIOUS CONSTRUCTION |  | NC 2015
K10 (2015) | NCR | Parañaque City | 136754 | La Huerta ES | CITY OF PARAÑAQUE | 1 | 1 |  | Completion of 4STY32CL | 2015 COMPLETION BATCH 4 | 5228199.416 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Parañaque City | 136756 | Paranaque ES Central | CITY OF PARAÑAQUE | 1 | 1 |  | Completion of 4STY24CL & 4STY/12CL | 2015 COMPLETION BATCH 4 | 14094676.5723 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Parañaque City | 305426 | Paranaque National High School - Baclaran | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Parañaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 18 | 4STY20CL (2cl open at ground floor) | 2015 SHS BATCH 5 | 29822890 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Parañaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Parañaque City |  | Proposed Stand Alone SHS 3 (PNHS-Sto. Nino) | CITY OF PARAÑAQUE | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Parañaque City |  | Proposed Stand Alone SHS 4 (PNHS-Don Bosco) | CITY OF PARAÑAQUE | 2 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Pasay City | 319601 | Kalayaan NHS | PASAY CITY | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Pasay City | 319601 | Kalayaan NHS | PASAY CITY | 0 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Pasay City | 319602 | Philippine HS for the Blind | PASAY CITY | 0 | 1 | 4 | 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 4354597.47 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Pasay City | 136595 | Rivera Village ES | Pasay City | 0 | 1 |  | 4STY9CL (Completion of 4STY12CL open GF) | 2015 COMPLETION BATCH 4 | 3192828.2063 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Pasay City | 136601 | Timoteo Paez ES | Pasay City | 0 | 1 |  | Completion of 4STY20CL | 2015 COMPLETION BATCH 4 | 6454915.895 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Pasig City |  | Porposed Stand Alone SHS 2 (Ugong Pasig City National) | CITY OF PASIG | 0 | 1 | 12 | 4STY12CL (L-Shape) | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Pasig City |  | Proposed Stand Alone SHS 3 (RHS) | CITY OF PASIG | 0 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Quezon City | 305320 | Balingasa HS | QUEZON CITY | 1 | 1 | 24 | 4STY24CL | 2015 ADDITIONAL FUND BATCH 9 | 13293913.52 |  |  | COMPLETED | 1 |  |  | NC0315S00043 | 15OF0127 | 2015-08-12 | 2015-08-13 | 2015-12-15 | 2015-12-22 |  | AYLAN CONSTRUCTION & TRADING |  | NC 2015
SHS (2015) | NCR | Quezon City | 136500 | Bungad ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 4330387.33 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Quezon City | 319506 | National Orthopedic Hospital School for Crippled Children | QUEZON CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | NC0315S00033 | 15OF0102 | 2015-07-23 | 2015-07-10 | 2015-08-05 | 2015-08-06 | 2015-08-28 | SUMMIT MERIDIEN CONSTRUCTION GROUP INC. |  | NC 2015
SHS (2015) | NCR | Quezon City |  | Proposed Stand Alone SHS 1 (Balingasa HS; from Masambong HS & San Jose HS) | QUEZON CITY | 1 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Quezon City |  | Proposed Stand Alone SHS 4 (Toro Hills; from Pugad Lawin & E Rod HS) | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Quezon City |  | Proposed Stand Alone SHS 5 (E. Abada; from SFHS) | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Quezon City |  | Proposed Stand Alone SHS 6 (Bagong Pag-asa ES) | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Quezon City | 136505 | San Antonio ES | Quezon City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 3780074.83 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Quezon City | 136498 | San Francisco ES | Quezon City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 3780074.83 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Quezon City | 305330 | Batasan Hills National HS | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1 |  |  | NC0315S00032 | 15OF0122 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-23 | RCDG CONSTRUCTION CORPORATION |  | NC 2015
SHS (2015) | NCR | Quezon City | 305345 | Balara HS | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0315S00031 | 15OG0099 | 2015-08-20 | 2015-09-04 | 2015-09-07 | 2015-09-22 | 2015-09-30 | MPJR BUILDERS COMPANY |  | NC 2015
SHS (2015) | NCR | Quezon City | 305346 | Camp Gen. E. Aguinaldo HS | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0315S00030 | 15OG0090 | 2015-08-11 | 2015-08-22 | 2015-08-24 | 2015-08-28 | 2015-09-01 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | NC 2015
K10 (2015) | NCR | Quezon City | 136558 | Eulogio Rodriguez, Sr. ES | QUEZON CITY | 3 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0315S00044 | 15OG0103 | 2015-10-02 | 2015-10-18 | 2015-10-20 | 2015-11-04 | 2015-11-05 | R.E. ORLINA CONSTRUCTION CORPORATION |  | NC 2015
K10 (2015) | NCR | Quezon City | 136559 | Quirino ES | QUEZON CITY | 3 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0315S00045 | 15OG-0104 | 2015-10-01 | 2015-10-15 | 2015-10-20 | 2015-11-04 | 2015-11-05 | METRICS CONSTRUCTION & TRADING |  | NC 2015
SHS (2015) | NCR | Quezon City | 305350 | Quirino HS | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Quezon City | 305350 | Quirino HS | QUEZON CITY | 3 |  | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Quezon City | 305355 | Carlos L. Albert HS | QUEZON CITY | 4 | 1 | 16 | additional 2 units 4STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 29795037.68 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Quezon City | 305360 | Don Alejandro Roces, Sr. Sci. & Tech. HS | QUEZON CITY | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0315S00026 | 15OG0089 | 2015-08-11 | 2015-08-22 | 2015-08-24 | 2015-08-28 | 2015-09-01 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS |  | NC 2015
K10 (2015) | NCR | Quezon City | 136576 | Pedro Tuason ES | QUEZON CITY | 4 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0315S00046 | 15OG-0111 | 2015-10-16 | 2015-10-27 | 2015-11-04 | 2015-11-20 | 2015-11-23 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS |  | NC 2015
SHS (2015) | NCR | Quezon City | 136580 | Proposed Stand Alone SHS10 (Kamuning A&D ES; for Media Arts students from all over QC) | QUEZON CITY | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Quezon City | 136581 | Proposed Stand AloneSHS 9 (MH del Pilar; from R Magsaysay) | QUEZON CITY | 4 | 1 | 16 | 4STY8CL | 2015 SHS BATCH 5 | 29795038 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Quezon City | 136533 | Kaligayahan ES | Quezon City | 5 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1 |  |  | NC0315S00035 | 15OF0130 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-23 | LMG CONSTRUCTION |  | NC 2015
SHS (2015) | NCR | Quezon City | 305336 | Lagro HS | QUEZON CITY | 5 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 2 | 35596257.14 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Quezon City | 305338 | Maligaya HS | Quezon City | 5 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 3780074.83 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Quezon City | 136530 | Villa Verde Elementary School | QUEZON CITY | 5 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26552469.42 |  |  | COMPLETED | 1 |  |  | NC0315S00047 | 15OF0132 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-08 | 2015-09-23 | PRISMODIAL CONSTRUCTION CORPORATION (FOR. PRISMODI |  | NC 2015
SHS (2015) | NCR | Quezon City | 305333 | Culiat HS | Quezon City | 6 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | COMPLETED | 1 |  |  | NC0315S00034 | 15OF0133 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-14 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J |  | NC 2015
K10 (2015) | NCR | Quezon City | 136519 | Lucas R. Pascual ES | Quezon City | 6 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | COMPLETED | 1 |  |  | NC0315S00036 | 15OF0134 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-14 | MPJR BUILDERS COMPANY |  | NC 2015
SHS (2015) | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | Taguig City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Taguig City & Pateros | 136894 | Capt. H. Francisco ES Annex | Taguig City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 5222963.07 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Taguig City & Pateros | 136893 | Capt. Hipolito Francisco Elementary School - Main | Taguig City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Taguig City & Pateros | 136883 | Cipriano P. Sta. Teresa Elementary School | Taguig City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 5222963.07 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Taguig City & Pateros | 136871 | Ciriaco P. Tiñga Elementary School | Taguig City | 1 | 1 |  | Completion of 4STY16CL | 2015 COMPLETION BATCH 4 | 6383621.53 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Taguig City & Pateros | 136874 | Napindan Elementary School | Taguig City | 1 | 1 |  | Completion of 4STY24CL | 2015 COMPLETION BATCH 4 | 9285267.68 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | Taguig City | 1 | 1 |  | Completion of 4STY8CL | 2015 COMPLETION BATCH 4 | 3481975.38 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Taguig City & Pateros |  | Proposed Stand Alone SHS 2 (Taguig ES) | TAGUIG CITY | 1 | 1 | 24 | 4STY12CL | 2015 SHS BATCH 5 | 44304687 |  |  | COMPLETED | 1 | [10 empty] | CONTRACT TO BE TERMINATED | NC 2015
SHS (2015) | NCR | Taguig City & Pateros |  | Proposed Stand Alone SHS 3 (DANES) | TAGUIG CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Taguig City & Pateros |  | Proposed Stand Alone SHS 4 (Brgy. Fort Bonifacio SHS) | TAGUIG CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Taguig City & Pateros | 136876 | Taguig Elementary School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00147 | 0150B0352 | 2015-11-19 | 2015-11-23 | 2015-12-03 | 2015-12-23 |  | VERZONTAL BUILDERS, INC. (FORMERLY VERZONTAL BUILD |  | NC 2015
SHS (2015) | NCR | Taguig City & Pateros | 320601 | Taguig Science High School | TAGUIG CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 |  |  | NC0215S00107 | [8 empty] | NC 2015
K10 (2015) | NCR | Taguig City & Pateros |  | DepED Property | Taguig City | 2 | 1 |  | Completion of 2 units 4STY12CL(elevated @ 1.5m) | 2015 COMPLETION BATCH 4 | 602647.6184 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | Taguig City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Taguig City & Pateros | 320606 | Pres. Diosdado Macapagal HS - Signal VNHS Annex | TAGUIG CITY | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Reverted | 0 |  |  | NC0215S00081 | [8 empty] | NC 2015
K10 (2015) | NCR | Taguig City & Pateros | 305463 | Signal Village NHS | Taguig City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
SHS (2015) | NCR | Taguig City & Pateros | 305463 | Signal Village NHS | TAGUIG CITY | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Valenzuela City | 136800 | A. Deato ES | Valenzuela City | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 3 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00090 | [8 empty] | NC 2015
K10 (2015) | NCR | Valenzuela City | 136802 | Coloong ES | CITY OF VALENZUELA | 1 | 1 |  | Completion 4STY8CL | 2015 COMPLETION BATCH 4 | 3043971.8762 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Valenzuela City | 136806 | Pasolo ES | CITY OF VALENZUELA | 1 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 776209.5191 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Valenzuela City | 136811 | WawangPulo ES | CITY OF VALENZUELA | 1 | 1 |  | Completion of 3STY6CL | 2015 COMPLETION BATCH 4 | 2932013.3353 |  |  | COMPLETED | 1 | [11 empty] | NC 2015
K10 (2015) | NCR | Valenzuela City | 305445 | Caruhatan NHS | CITY OF VALENZUELA | 2 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 7 | 22152344 |  |  | COMPLETED | 1 |  |  | NC0215S00151 | [8 empty] | NC 2015
K10 (2015) | NCR | Valenzuela City | 320408 | DALANDANAN NHS- Bagbaguin Annex | Valenzuela City | 2 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 3 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0215S00091 | 15OD0104 | 2015-10-07 | 2015-10-16 | 2015-10-19 | 2015-10-22 | 2015-11-17 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | NC 2015
K10 (2015) | NCR | Valenzuela City | 136817 | Paso de Blas ES | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00148 | 15OD0099 | 2015-09-18 | 2015-09-30 | 2015-10-01 | 2015-10-15 | 2015-11-05 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY |  | NC 2015
SHS (2015) | NCR | Valenzuela City | 305446 | Sitero Francisco Mem. NHS | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15082518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00071 | 15OD0103 | 2015-10-07 | 2015-10-19 | 2015-10-20 | 2015-10-26 | 2015-11-17 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS |  | NC 2015
K10 | NCR | Caloocan City | 305376 | Amparo High School | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22153000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Caloocan City | 305376 | Amparo High School | Caloocan City | 1 |  | 2 | 1STY2CL | BATCH 13 CL | 2132466.644 |  |  | Reverted | 0 | [11 empty] | NC 2016
K10 | NCR | Caloocan City | 136639 | Bagong Silang Es | Caloocan City | 1 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10567131.51 |  |  | Completed | 1 |  |  | P00074635LZ | 16OD0069 |  |  | 2016-09-06 |  |  | J. Simeon Construction |  | NC 2016
K10 | NCR | Caloocan City | 136639 | Bagong Silang Es | Caloocan City | 1 | 1 | 2 | Completion of 4STY8CL | BATCH 11 CL | 2000000 |  |  | Completed | 1 |  |  | P00074644LZ P00171687LZ | 17OD0121 |  |  | 2017-07-20 |  |  | Aylan Const. & Trading |  | NC 2016
SHS | NCR | Caloocan City | 319707 | Caloocan City Business High School | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 |  |  | P00074645LZ | 16OD0072 |  |  | 2016-09-13 |  |  | Prismodial Const. Corp. |  | NC 2016
K10 | NCR | Caloocan City | 340539 | Caloocan North Shs | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074639LZ P00181048LZ | 16OD0117 |  |  | 2017-09-04 |  |  | C.B. Tampengco Const. and Supply |  | NC 2016
K10 | NCR | Caloocan City | 305374 | Camarin Hs | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074642LZ | 16OD0073 |  |  | 2016-09-15 |  |  | Victoria Dev't. & Const. Supply Corp. |  | NC 2016
K10 | NCR | Caloocan City | 305374 | Camarin Hs | Caloocan City | 1 |  | 16 | 4STY8CL | BATCH 11 CL | 29795037.68 |  |  | Completed | 1 |  |  | P00074643LZ | 16OD0074 |  |  | 2016-09-15 |  |  | Aylan Const. & Trading |  | NC 2016
K10 | NCR | Caloocan City |  | Camarin Shs (Brixton) | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Caloocan City | 136652 | Caybiga Es | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Caloocan City | 319701 | Cielito Zamora High School (Bonifacio Campus) | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Caloocan City | 136636 | Congress Es | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14898000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Caloocan City | 305387 | Llano Hs | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00074647LZ | 16OD0078 |  |  | 2016-09-27 |  |  | Prismodial Const. Corp. |  | NC 2016
K10 | NCR | Caloocan City |  | Samalla Tala Shs | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074650LZ | 16OD0076 |  |  | 2016-09-22 |  |  | St. Gerrard Construction |  | NC 2016
K10 | NCR | Caloocan City |  | Sampaguita Shs | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074649LZ | 16OD0075 |  |  | 2016-09-22 |  |  | Prismodial Const. Corp. | TO VERIFY APPROPRIATION FROM DPWH REPORT: 14,897,518.84 | NC 2016
K10 | NCR | Caloocan City | 305380 | Tala Hs | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 |  |  | P00074648LZ | 16OD0083 |  |  | 2016-10-25 |  |  | Aylan Const. & Trading |  | NC 2016
K10 | NCR | Caloocan City | 136615 | Andres Bonifacio Es | Caloocan City | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31103000 |  |  | Completed | 1 |  |  | P00072840LZ | 16OD0059 |  |  | 2016-08-02 |  |  | St. Gerrard Construction |  | NC 2016
K10 | NCR | Caloocan City | 136615 | Andres Bonifacio Es | Caloocan City | 2 |  | 16 | 4STY16CL | BATCH 9 CL | 26703000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Caloocan City | 136606 | Grace Park Es (Main) | Caloocan City | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Caloocan City | 319706 | Kasarinlan Hs | Caloocan City | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 |  |  | P00074638LZ | 17OD0119 |  |  | 2017-07-20 |  |  | St. Timothy Const. Corp. |  | NC 2016
K10 | NCR | Caloocan City | 305391 | M. B. Asistio Sr. Hs (Main) | Caloocan City | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 |  |  | P00074636LZ P00171689LZ | 17OD0120 |  |  | 2017-07-20 |  |  | Omicron Const. |  | NC 2016
SHS | NCR | Caloocan City | 305391 | M. B. Asistio Sr. Hs Unit 1 To M. B. Asistio, Sr. Hs | Caloocan City | 2 |  | 32 | 4STY32CL | BATCH 13 CL | 44532220.04 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Las Piñas City | 136773 | Caa Elementary School Main | City Of Las Piñas | 0 | 1 | 40 | 4STY20CL | BATCH 13 CL | 62205780.54 |  |  | Completed | 1 |  |  | P00075393LZ | 17OI0077 | 2017-06-13 | 2017-06-21 | 2017-07-04 | 2017-07-19 | 2017-10-16 | REDCAR TRADING AND CONSTRUCTION |  | NC 2016
K10 | NCR | Las Piñas City | 136790 | Daniel Fajardo Es To Talon Es | City Of Las Piñas | 0 | 1 | 12 | 4STY12CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 17OI0123 | 2017-11-02 | 2017-11-10 | 2017-11-23 | 2017-11-29 | 2017-12-15 | DAVHEZ CONSTRUCTION |  | NC 2016
K10 | NCR | Las Piñas City | 136784 | Dona Manuela Es | City Of Las Piñas | 0 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00075394LZ | 17OI0051 | 2017-03-17 | 2017-03-24 | 2017-04-05 | 2017-04-24 | 2017-10-16 | DAVHEZ CONSTRUCTION |  | NC 2016
K10 | NCR | Las Piñas City | 136775 | Gatchalian Es | City Of Las Piñas | 0 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 |  |  | P0007031LZ | 16OI0027 | 2017-02-23 | 2017-03-02 | 2017-03-14 | 2017-03-21 | 2017-06-06 | MRRM Trading and Construction |  | NC 2016
K10 | NCR | Las Piñas City |  | Moonwalk Es To Realign To Repsci Las Pinas | City Of Las Piñas | 0 | 1 | 16 | 4STY16CL | BATCH 3 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00070312LZ | 16OI0095 | 2017-09-29 | 2017-10-06 | 2017-10-13 | 2017-10-28 | 2017-11-22 | DAVHEZ CONSTRUCTION |  | NC 2016
K10 | NCR | Las Piñas City |  | Shs In Martinville, Las Piñas City/ Realign To Golden Acres Las Pinas | Las Piñas City | 0 | 1 | 32 | 4STY32CL | BATCH 3 CL | 44532220.04 |  |  | Completed | 1 |  |  | P00070310LZ | 17OI0098 | 2017-09-06 | 2017-09-14 | 2017-09-26 | 2017-10-06 | 2017-12-15 | DAVHEZ CONSTRUCTION |  | NC 2016
K10 | NCR | Las Piñas City | 136791 | Zapote Es | City Of Las Piñas | 0 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00075395LZ | 17OI0052 | 2017-03-17 | 2017-03-24 | 2017-04-05 | 2017-12-24 | 2017-12-15 | LMG CONSTRUCTION |  | NC 2016
K10 | NCR | Malabon City | 136834 | Imelda Es | City Of Malabon | 0 | 1 | 24 | 4STY24CL | BATCH 7 CL | 35596257.14 |  |  | Completed | 1 | [8 empty] | 2016-10-27 | edison devt & const |  | NC 2016
K10 | NCR | Malabon City |  | Ninoy Aquino Es | City Of Malabon | 0 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [8 empty] | 2017-08-08 | hexamindz corp |  | NC 2016
K10 | NCR | Malabon City | 136846 | Santiago Syjuco Memorial School | City Of Malabon | 0 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [8 empty] | 2016-05-12 | LTM builders |  | NC 2016
K10 | NCR | Malabon City | 136838 | Tañong Es I | City Of Malabon | 0 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [8 empty] | 2016-11-15 | victoria devt |  | NC 2016
K10 | NCR | Malabon City | 136850 | Tinajeros Es | City Of Malabon | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18222268.79 |  |  | Completed | 1 | [8 empty] | 2017-10-16 | alpha & omega general contractor |  | NC 2016
K10 | NCR | Malabon City | 320504 | Tinajeros Nhs - Acacia Annex | City Of Malabon | 0 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1 | [8 empty] | 2016-10-12 | framecon builders |  | NC 2016
K10 | NCR | Mandaluyong City | 500051 | Andres Bonifacio Is | Mandaluyong City | 0 | 1 | 16 | 4STY16CL | BATCH 11 CL | 33300000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Mandaluyong City | 136657 | Filemon Javier Es | Mandaluyong City | 0 | 1 | 12 | 4STY12CL (INCL. SITE DEV & DEMOLITION) WITH COVERED HIGH COLUMN SUPPORT FOR MULTI-PURPOSE HALL/ROOF DECK | BATCH 11 CL | 35300000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Mandaluyong City | 136831 | Hulo Integrated School | Mandaluyong City | 0 | 1 | 24 | 4STY24CL | BATCH 11 CL | 52300000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Mandaluyong City | 500335 | Ilaya Barangka Is | Mandaluyong City | 0 | 1 | 12 | 4STY12CL | BATCH 11 CL | 35450000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Mandaluyong City | 319804 | Jose Fabella Memorial School | City Of Mandaluyong | 0 | 1 | 16 | 4STY16CL | BATCH 3 CL | 32150000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Mandaluyong City | 305394 | Mataas Na Paaralang Neptali A. Gonzales | City Of Mandaluyong | 0 | 1 | 48 | 4STY48CL | BATCH 13 CL | 100950000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Manila | 136488 | Gen. Emilio Aguinaldo Is | Manila | 6 | 1 | 12 | 4STY12CL | BATCH 11 CL | 24352577.982 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Marikina City | 136681 | Fortune Es | Marikina City | 2 | 1 | 4 | Completion of 3STY9CL | BATCH 11 CL | 5959577.43 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Marikina City | 136685 | Sss Village Es | City Of Marikina | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Marikina City | 136685 | Sss Village Es | City Of Marikina | 2 |  | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Muntinlupa City | 136908 | Alabang Es (Main) | City Of Muntinlupa | 0 | 1 | 32 | 4STY16CL | BATCH 7 CL | 53404938.84 |  |  | Completed | 1 |  |  |  | 16OI0049 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-07 | MRRM Trading & Const. |  | NC 2016
K10 | NCR | Muntinlupa City | 136908 | Alabang Es (Main) | City Of Muntinlupa | 0 |  | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16OI0043 | 2016-02-29 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-07 | RV Rieta Trading & Gen Const. |  | NC 2016
K10 | NCR | Muntinlupa City | 136910 | Bayanan Elementary School Unit I | City Of Muntinlupa | 0 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16OI0050 | 2016-03-02 | 2016-03-09 | 2016-03-21 |  |  | R. V. Rieta Trading & Gen. Const. |  | NC 2016
K10 | NCR | Muntinlupa City | 136912 | Cupang Es | City Of Muntinlupa | 0 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16OI0042 | 2016-02-29 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-13 | Redcar Trading & Const. |  | NC 2016
K10 | NCR | Muntinlupa City | 136900 | F. De Mesa Es | City Of Muntinlupa | 0 | 1 | 16 | 4STY8CL | BATCH 7 CL | 29795837.68 |  |  | Completed | 1 |  |  |  | 16OI0053 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-07 | MRRM Trading & Const. |  | NC 2016
K10 | NCR | Muntinlupa City | 136901 | Itaas Elementary School | City Of Muntinlupa | 0 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16OI0054 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-07 | MRRM Trading & Const. |  | NC 2016
K10 | NCR | Muntinlupa City | 136903 | Muntinlupa Es | City Of Muntinlupa | 0 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16OI0051 | 2016-03-02 | 2016-03-09 | 2016-03-21 |  |  |  |  | NC 2016
K10 | NCR | Muntinlupa City | 136903 | Muntinlupa Es | City Of Muntinlupa | 0 |  | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16OI0057 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-13 | Orani Builders Supply |  | NC 2016
K10 | NCR | Muntinlupa City | 305468 | Muntinlupa Nhs | City Of Muntinlupa | 0 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897918.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Muntinlupa City | 305468 | Muntinlupa Nhs | City Of Muntinlupa | 0 |  | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Muntinlupa City | 305468 | Muntinlupa Nhs | City Of Muntinlupa | 0 |  | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Muntinlupa City | 305470 | Pedro E. Diaz High School | City Of Muntinlupa | 0 | 1 | 24 | 4STY12CL | BATCH 7 CL | 44304687.24 |  |  | Completed | 1 |  |  |  | 16OI0055 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-13 | Orani Builders Supply |  | NC 2016
K10 | NCR | Muntinlupa City | 305470 | Pedro E. Diaz High School | City Of Muntinlupa | 0 |  | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16OI0052 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-13 | Precious Const. |  | NC 2016
K10 | NCR | Muntinlupa City | 136905 | Soldiers' Hills Es | City Of Muntinlupa | 0 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Muntinlupa City | 136914 | Sucat Elementary School | City Of Muntinlupa | 0 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16OI0056 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-07 | E. M. Paule Const. & Trading |  | NC 2016
K10 | NCR | Muntinlupa City | 136914 | Sucat Elementary School | City Of Muntinlupa | 0 |  | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16OI0068 | 2016-04-22 | 2016-03-09 | 2016-05-11 | 2016-05-19 | 2016-07-03 | Orani Builders Supply |  | NC 2016
K10 | NCR | Navotas City | 136858 | Dagat-Dagatan Elementary School | City Of Navotas | 0 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Navotas City | 305454 | San Rafael Technological High School | City Of Navotas | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Navotas City | 136867 | Tangos Elementary School | City Of Navotas | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Navotas City | 305457 | Tangos National High School | City Of Navotas | 0 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Navotas City | 305453 | Navotas National High School | Navotas City | 0 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26852469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Navotas City |  | Navotas Science High School | Navotas City | 0 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Navotas City | 136863 | North Bay Boulevard North Elementary School | City Of Navotas | 0 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Navotas City | 340628 | Shs In Lisan, Navotas City | City Of Navotas | 0 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Paranaque City | 305424 | Paranaque National High School Main | City Of Parañaque | 0 |  | 56 | 4STY28CL | BATCH 11 CL | 80135892.28 |  |  | Completed | 1 | [9 empty] | Flordes Construction & Trading |  | NC 2016
K10 | NCR | Paranaque City | 136754 | La Huerta Elementary School | City Of Parañaque | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [9 empty] | Triple 8 Construction & Supply Inc. |  | NC 2016
K10 | NCR | Paranaque City | 136754 | La Huerta Elementary School | City Of Parañaque | 1 |  | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Reverted | 0 | [9 empty] | Flordes Construction & Trading | Mutual termination; cancelled effective December 23, 2021 | NC 2016
K10 | NCR | Paranaque City | 136757 | Paranaque Elementary School Unit Ii | City Of Parañaque | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [9 empty] | Flordes Construction & Trading |  | NC 2016
K10 | NCR | Paranaque City | 136756 | Paranaque Es Central | City Of Parañaque | 1 | 1 | 16 | 4STY8CL | BATCH 13 CL | 29795037.68 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Paranaque City |  | Paranaque Es Central | City Of Parañaque | 1 | 1 | 16 | 4STY8CL | BATCH 11 CL | 29795037.68 |  |  | Completed | 1 | [9 empty] | Redcar Trading and Construction |  | NC 2016
SHS | NCR | Paranaque City | 305426 | Paranaque National High School - Baclaran | City Of Parañaque | 1 | 1 | 28 | 4STY28CL | BATCH 3 CL | 40067946.14 |  |  | Completed | 1 | [9 empty] | MRRM Trading and Construction |  | NC 2016
SHS | NCR | Paranaque City | 305426 | Paranaque National High School - Baclaran | City Of Parañaque | 1 |  | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 | [9 empty] | R.E. Orlina Construction Corp |  | NC 2016
SHS | NCR | Paranaque City | 305426 | Paranaque National High School - Baclaran | City Of Parañaque | 1 |  | 16 | 4STY16CL | BATCH 3 CL | 26702469.42 |  |  | Completed | 1 | [9 empty] | R.E. Orlina Construction Corp |  | NC 2016
SHS | NCR | Paranaque City | 305424 | Paranaque National High School Main | City Of Parañaque | 1 | 1 | 24 | 4STY12CL | BATCH 11 CL | 44304687.24 |  |  | Completed | 1 | [9 empty] | Hexamindz Corporation |  | NC 2016
K10 | NCR | Paranaque City | 305427 | Paranaque Nhs - Don Galo Annex | City Of Parañaque | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [9 empty] | Omicron Construction |  | NC 2016
K10 | NCR | Paranaque City | 305427 | Paranaque Nhs - Don Galo Annex | City Of Parañaque | 1 |  | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 | [9 empty] | Henscha Philippines Inc. |  | NC 2016
K10 | NCR | Paranaque City |  | Sto. Nino Es | City Of Parañaque | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [9 empty] | R.E. Orlina Construction Corp |  | NC 2016
K10 | NCR | Paranaque City | 136765 | Sto. Nino Es | City Of Parañaque | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Paranaque City | 136766 | Tambo Es | City Of Parañaque | 1 | 1 | 32 | 4STY32CL | BATCH 7 CL | 44532220.04 |  |  | Completed | 1 | [9 empty] | Precious Construction |  | NC 2016
K10 | NCR | Pasay City | 136593 | Kalayaan Es | Pasay City | 0 | 1 | 9 | 4STY 9CL | BATCH 9 CL | 21170000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Pasay City | 136599 | Marcela Marcelo Es | Pasay City | 0 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Pasay City | 319602 | Philippine National School For The Blind | Pasay City | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.051 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Pasay City | 136601 | Timoteo Paez Es | Pasay City | 0 | 1 | 24 | 4STY24CL | BATCH 3 CL | 35596257.14 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot Sci (Respsci) | City Of Pasig | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31602890.27 |  |  | Completed | 1 |  |  | P00171699 LZ_CW1 | 0170B0120 | 2016-12-29 | 2017-01-06 | 2017-01-19 |  | 2017-10-24 | LPO Enterprises & R'CEL Gen. Con & Gen. Merchendise (J.V.) |  | NC 2016
K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa Es | Quezon City | 1 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa Es | Quezon City | 1 |  | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136501 | Esteban Abada Es | Quezon City | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136501 | Esteban Abada Es | Quezon City | 1 |  | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Quezon City | 305322 | Eulogio Rodriguez, Jr. Hs | Quezon City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City |  | Shs In Kaligayahan | Quezon City | 1 | 1 | 16 | 4STY16CL | BATCH 11 CL | 27709000 |  |  | Terminated | 1 | [10 empty] | DPWH REPORT: For Termination The contractor failed to resume to work; for mutual termination as per DPWH | NC 2016
K10 | NCR | Quezon City |  | Shs In Pasong Tamo | Quezon City | 1 | 1 | 32 | 4STY32CL | BATCH 9 CL | 44532220.04 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City |  | Toro Hills Es | Quezon City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136506 | Toro Hills Es | Quezon City | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Quezon City | 305331 | Commonwealth Hs | Quezon City | 2 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31252890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136542 | Dona Juana Es | Quezon City | 2 | 1 | 3 | Completion of 4STY14CL | BATCH 9 CL | 4754642.66 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 319501 | Shs In Batasan Hills (Ext. Of Batasan Hills Nhs) To Holy Spirit Nhs | Quezon City | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23018000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City |  | Shs In Harmony Hills (Accibal Property) | Quezon City | 2 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31252890.27 |  |  | Terminated | 0 | [10 empty] | DPWH REPORT: FOR TERMINATION / WITH ISFs | NC 2016
K10 | NCR | Quezon City |  | Shs In Harmony Hills (Accibal Property) | Quezon City | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23018000 |  |  | Terminated | 0 | [10 empty] | DPWH REPORT: FOR TERMINATION / WITH ISFs | NC 2016
K10 | NCR | Quezon City | 136564 | Pura V. Kalaw Es | Quezon City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136534 | Lagro Es | Quezon City | 5 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.02 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136534 | Lagro Es | Quezon City | 5 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136536 | Nagkaisang Nayon Es | Quezon City | 5 | 1 | 16 | 4STY16CL (L-Shape) | BATCH 11 CL | 26852469.42 |  |  | Terminated | 1 | [10 empty] | For Termination;The contractor failed to resume to work; No movement at all | NC 2016
K10 | NCR | Quezon City | 136538 | San Agustin Es | Quezon City | 5 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22177343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136525 | San Bartolome Es | Quezon City | 5 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26739923.9661 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136529 | San Gabriel Es | Quezon City | 5 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | San Juan City |  | San Juan Es To San Juan City Tech-Voc And Livelihood Shs | San Juan City | 0 | 1 | 24 | 4STY24CL | BATCH 11 CL | 35596257.14 |  |  | Reverted | 0 | [11 empty] | NC 2016
K10 | NCR | Taguig | 136892 | Aguho Es | Taguig | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Taguig | 136874 | Napindan Integrated School | Taguig City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22302343.52 |  |  | Terminated | 0 | [10 empty] | The project was terminated due to long period of suspension of the project due to pending demolition of the remaining existing structure by Dep-ed affecting the two grid line. - With request for funding which was received by Dep-Ed Central Office dated March 15, 2023 for the construction and completion of the building amounting Php62,500,00.00. | NC 2016
K10 | NCR | Taguig | 136896 | Pateros Elementary School | Pateros | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Taguig | 305466 | Pateros National High School | Pateros | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Taguig | 320611 | Taguig Integrated School | Taguig City | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22302343.52 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Taguig | 305460 | Taguig National High School | Taguig City | 1 | 1 | 32 | 4STY32CL | BATCH 9 CL | 44532220.04 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Taguig | 305464 | Tipas National High School | Taguig City | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Taguig | 136890 | Maharlika Elementary School | Taguig City | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22302343.52 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | NCR | Taguig | 305463 | Signal Village National High School | Taguig City | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Taguig | 136887 | Upper Bicutan Es | Taguig City | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Valenzuela City | 136801 | A. Fernando Es | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.8364 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Valenzuela City | 305438 | Malinta National High School | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.8364 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Valenzuela City | 136807 | Pio Valenzuela Es | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Valenzuela City |  | Shs In Arkong Bato, Valenzuela | City Of Valenzuela | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Valenzuela City |  | Shs In Paso De Blas, Valenzuela | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14897518.8364 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Valenzuela City |  | Shs In Punturin, Valenzuela | City Of Valenzuela | 1 | 1 | 24 | 4STY12CL | BATCH 5 CL | 44304687.24 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Valenzuela City | 136810 | Tugatog Es | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.8364 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Valenzuela City |  | Shs In Ugong | Valenzuela City | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Valenzuela City | 305446 | Sitero Francisco Mem. Nhs | City Of Valenzuela | 2 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Valenzuela City | 305441 | Valenzuela Nhs | Valenzuela City | 2 | 1 | 8 | Completion of 4STY32CL | BATCH 11 CL | 14747518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136492 | Ramon Magsaysay Es | Quezon City | 1 | 1 | 20 | 4STY20CL | BATCH 14 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 305322 | Eulogio Rodriguez, Jr. Hs | Quezon City | 1 | 1 | 8 | 4STY8CL | BATCH 14 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136525 | San Bartolome Es | Quezon City | 5 | 1 | 8 | 4STY8CL | BATCH 14 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City | 136533 | Kaligayahan Es | Quezon City | 5 | 1 | 12 | 4STY12CL | BATCH 14 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Quezon City |  | Atty. Alfredo D. Vargas, Sr. Memorial High School | Quezon City | 5 | 1 | 20 | 4STY20CL L- Type Building (included elevation of 0.80 -1.20m high) | BATCH 14 CL | 42150000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 | 1 | 12 | 4STY12CL | BATCH 4 | 32371949.57 |  |  | Completed | 1 |  |  | P00172458LZ-CW1 | 0170B0387 | 2017-09-26 | 2017-10-06 | 2017-10-10 | 2017-11-02 | 2017-11-14 | GR FEVEDAL CONSTRUCTION DEVELOPERS CORPORATION |  | NC 2017
K10 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 | 1 | 16 | 4STY16CL | BATCH 4 | 37165805.23 |  |  | Completed | 1 |  |  | P00172459LZ-CW1 | 0170B0385 | 2017-09-26 | 2017-10-06 | 2017-10-17 | 2017-11-02 | 2017-11-14 | BELL CONSTRUCTION |  | NC 2017
K10 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 | 1 | 12 | 4STY12CL | BATCH 4 | 37767415.24 |  |  | Completed | 1 |  |  | P00172460LZ-CW1 | 0170B0383 | 2017-09-26 | 2017-10-06 | 2017-10-17 | 2017-11-02 | 2017-11-14 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION |  | NC 2017
K10 | NCR | Marikina City | 136687 | Sto. Nino ES | CITY OF MARIKINA | 1 | 1 | 12 | 4STY12CL | BATCH 4 | 35423184.21 |  |  | Completed | 1 |  |  | P00172457LZ-CW1 | 0170B0386 | 2017-09-26 | 2017-10-06 | 2017-10-10 | 2017-11-02 |  | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION |  | NC 2017
K10 | NCR | Pasig City | 136729 | Bagong Ilog ES | CITY OF PASIG | 0 | 1 | 20 | 4STY20CL | BATCH 4 | 42574742.6 |  |  | Completed | 1 |  |  | P0072462 LZ_CW1 | 0170B0384 | 2017-09-26 | 2017-10-06 | 2017-10-17 | 2017-11-02 | 2017-11-20 | Henscita Phils., Inc. |  | NC 2017
K10 | NCR | Pasig City | 136725 | Buting ES | CITY OF PASIG | 0 | 1 | 9 | 4STY9CL | BATCH 4 | 32371949.57 |  |  | Completed | 1 |  |  | P0072461 LZ_CW1 | 0170B0388 | 2017-09-26 | 2017-10-06 | 2017-10-17 | 2017-11-02 | 2017-11-20 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION |  | NC 2017
TVL | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | CITY OF PASIG | 0 | 1 | 16 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 72278943.25 |  |  | Completed | 1 |  |  | P0072463 LZ_CW1 | 0170B0421 | 2017-10-30 | 2017-11-10 | 2017-11-21 | 2017-12-01 | 2017-12-19 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION |  | NC 2017
SHS | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG | 0 | 1 | 28 | 4STY28CL | BATCH 4 | 62945715.06 |  |  | Completed | 1 |  |  | P0072464 LZ_CW1 | 0170B0422 | 2017-10-30 | 2017-11-10 | 2017-12-12 | 2017-12-14 | 2017-12-28 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION |  | NC 2017
K10 | NCR | Malabon City | 136835 | Longos ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 20705296.99 |  | 19961055.45 | Completed | 1 | [8 empty] | 2017-12-13 | ISH Const. Inc |  | NC 2017
K10 | NCR | Malabon City | 136855 | Maysilo ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 23053022.14 |  | 22249624.04 | Completed | 1 | [8 empty] | 2017-12-13 | T.M. Abad Const. |  | NC 2017
K10 | NCR | Malabon City | 136846 | Santiago Syjuco Memorial School | CITY OF MALABON | 0 | 1 | 20 | 4STY20CL | BATCH 7 | 60000000 |  | 57848516.92 | Completed | 1 | [8 empty] | 2018-01-10 | St. Timothy Const. Corp. |  | NC 2017
SHS | NCR | Malabon City | 305452 | Tinajeros NHS | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 19744516.77 |  | 19032845.4 | Completed | 1 | [8 empty] | 2017-12-13 | JTC Cruz Const. co. inc. |  | NC 2017
K10 | NCR | Malabon City | 136839 | Tonsuya Elementary School | CITY OF MALABON | 0 | 1 | 15 | 3STY15CL | BATCH 7 | 46106889.97 |  | 45478773.82 | Completed | 1 | [8 empty] | 2017-12-13 | Edison Devt. Const. |  | NC 2017
K10 | NCR | Marikina City |  | Industrial Valley NHS | CITY OF MARIKINA | 1 | 1 | 36 | 4STY36CL | BATCH 7 | 109453944.7 |  |  | Completed | 1 |  |  | P00174788LZ-CW1 | 0170B0459 | 2017-12-06 | 2017-12-13 | 2017-10-22 | 2018-01-03 | 2018-01-04 | EDISON DEVELOPMENT CORPORATION |  | NC 2017
TVL | NCR | Navotas | 136856 | Bagumbayan Elementary School | CITY OF NAVOTAS | 0 | 1 | 3 | 3STY3CL | BATCH 7 | 10417126.08 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 27636000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Navotas | 136861 | Navotas I Elementary School | CITY OF NAVOTAS | 0 | 1 | 15 | 4STY16CL | BATCH 7 | 55558005.76 |  |  | Completed | 1 | [10 empty] | - Termination of Original Contract (17OA0097) - New Contract for Project Completion (17OA0106) - New Contract for Project Completion (17OA0106) | NC 2017
SHS | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 7 | 42036997.81 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 27636000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Navotas | 305455 | Tanza National High School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 7 | 42036997.81 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 28 | 4STY28CL | BATCH 7 | 68651344.94 |  |  | Terminated | 0 |  |  |  | 17OC0088 |  |  |  |  | 2017-12-27 | SPRING STAR Const. & Supply | Terminated; Suspended as of December 27, 2017 due to pending demolition of existing building since it is still being utilized by the students. The newly built 2 Units 12 CL is not sufficient to cater the number of students using the old building; Awaiting for the completion of the ongoing construction of 2 Units 28CL. (For Termination) | NC 2017
K10 | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 18812000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136512 | GSIS VILLAGE ELEMENTARY | QUEZON CITY | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 34234000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY | 5 | 1 | 12 | 4STY12CL | BATCH 7 | 34175000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6 | 1 | 16 | 4STY16CL | BATCH 7 | 39783000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136509 | Project 6 ES | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 7 | 45561000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City |  | Sta. Lucia ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | BATCH 7 | 18921000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Caloocan City | 305389 | Caloocan City City Science HS | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 45700000 |  |  | Completed | 1 |  |  | P00178672LZ | 17OD0170 |  |  | 2017-12-19 |  |  | Accelerated Metal Technology and Const. Inc. |  | NC 2017
K10 | NCR | Caloocan City | 136632 | Amparo ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178650LZ | 17OD0146 |  |  | 2017-11-28 |  |  | Aylan Construction and Trading |  | NC 2017
K10 | NCR | Caloocan City | 136632 | Amparo ES | Caloocan City | 1 |  | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178651LZ | 17OD0130 |  |  | 2017-11-23 |  |  | Aylan Construction and Trading |  | NC 2017
K10 | NCR | Caloocan City | 136625 | Baesa ES | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178649LZ | 17OD0131 |  |  | 2017-11-23 |  |  | Accelerated Metal Technology and Const. Inc. |  | NC 2017
K10 | NCR | Caloocan City | 136650 | Bagbaguin ES | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178656LZ | 17OD0159 |  |  | 2017-12-19 |  |  | C.B. Tampengco Const. & Supply |  | NC 2017
SHS | NCR | Caloocan City | 305383 | Bagong Barrio NHS | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178669LZ | 17OD0179 |  |  | 2017-12-12 |  |  | C.T. Leoncio Const. & Trading |  | NC 2017
SHS | NCR | Caloocan City | 305383 | Bagong Barrio NHS | Caloocan City | 1 |  | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178670LZ | 17OD0180 |  |  | 2017-12-12 |  |  | C.T. Leoncio Const. & Trading |  | NC 2017
K10 | NCR | Caloocan City | 136639 | Bagong Silang ES | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178653LZ | 17OD0147 |  |  | 2017-11-28 |  |  | E.A. Ramirez Const. Inc. |  | NC 2017
K10 | NCR | Caloocan City | 305381 | Bagong Silang HS | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 33600000 |  |  | Completed | 1 |  |  | P00178667LZ | 17OD0157 |  |  | 2017-11-29 |  |  | Alpha & Omega Gen. Contractor & Dev't. Corp. |  | NC 2017
K10 | NCR | Caloocan City | 305381 | Bagong Silang HS | Caloocan City | 1 |  | 12 | 4STY12CL | BATCH 10 | 33600000 |  |  | Completed | 1 |  |  | P00178667LZ | 17OD0157 |  |  | 2017-11-29 |  |  | Alpha & Omega Gen. Contractor & Dev't. Corp. |  | NC 2017
K10 | NCR | Caloocan City | 136651 | Bagumbong ES | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178657LZ | 17OD0132 |  |  | 2017-11-23 |  |  | T.M. Abad Construction |  | NC 2017
K10 | NCR | Caloocan City | 136617 | Caloocan Central Elementary School | Caloocan City | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178675LZ | 17OD0148 |  |  | 2017-11-28 |  |  | C.B. Tampengco Const. & Supply |  | NC 2017
K10 | NCR | Caloocan City | 136634 | Camarin Elementary School | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178652LZ | 17OD0181 |  |  | 2017-12-12 |  |  | Aylan Construction and Trading |  | NC 2017
K10 | NCR | Caloocan City | 305374 | Camarin High School | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178663LZ | 17OD0133 |  |  | 2017-11-23 |  |  | T.M. Abad Construction |  | NC 2017
K10 | NCR | Caloocan City | 136652 | Caybiga ES | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178658LZ | 17OD0160 |  |  | 2017-12-19 |  |  | First R + J Builders Phils. Corp. |  | NC 2017
K10 | NCR | Caloocan City | 305385 | Caybiga HS | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178671LZ | 17OD0134 |  |  | 2017-11-23 |  |  | Accelerated Metal Technology and Const. Inc. |  | NC 2017
K10 | NCR | Caloocan City | 136620 | Cecilio Apostol ES | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178648LZ | 17OD0135 |  |  | 2017-11-23 |  |  | Larsen-Dutcher Constractor |  | NC 2017
SHS | NCR | Caloocan City | 305375 | Ceilito Zamora SHS | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178664LZ | 17OD0136 |  |  | 2017-11-23 |  |  | Jagonbuild Construction Corp. |  | NC 2017
K10 | NCR | Caloocan City | 136653 | Deparo ES | Caloocan City | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178659LZ | 17OD0161 |  |  | 2017-12-19 |  |  | First R + J Builders Phils. Corp. |  | NC 2017
K10 | NCR | Caloocan City | 136641 | Kalayaan ES | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178654LZ | 17OD0162 |  |  | 2017-12-01 |  |  | Steven Construction and Supply |  | NC 2017
K10 | NCR | Caloocan City | 136654 | Llano ES | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178660LZ | 17OD0151 |  |  | 2017-11-29 |  |  | C.B. Tampengco Const. & Supply |  | NC 2017
K10 | NCR | Caloocan City | 305379 | Manuel L. Quezon HS | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178665LZ | 17OD0137 |  |  | 2017-11-23 |  |  | RCDG Construction Corporation |  | NC 2017
K10 | NCR | Caloocan City | 136655 | Sampaguita Elem. School | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178661LZ | 17OD0156 |  |  | 2017-11-29 |  |  | Accelerated Metal Technology and Const. Inc. |  | NC 2017
K10 | NCR | Caloocan City | 136642 | Silanganan ES (Star ES) | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178655LZ | 17OD0152 |  |  | 2017-12-13 |  |  | Aylan Construction and Trading |  | NC 2017
K10 | NCR | Caloocan City | 305380 | Tala High School | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00171688LZ | 17OD0126 |  |  | 2017-10-24 |  |  | Aylan Construction and Trading |  | NC 2017
K10 | NCR | Caloocan City | 305371 | Talipapa HS | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178662LZ | 17OD0153 |  |  | 2017-12-19 |  |  | First R + J Builders Phils. Corp. |  | NC 2017
K10 | NCR | Caloocan City | 136622 | Eulogio Rodriguez Elementary School | KALOOKAN CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178676LZ | 17OD0149 |  |  | 2017-11-29 |  |  | Alcel Construction |  | NC 2017
K10 | NCR | Caloocan City | 136608 | Kasarinlan ES | KALOOKAN CITY | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 49265000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Caloocan City | 136609 | Kaunlaran ES | KALOOKAN CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 41930000 |  |  | Completed | 1 |  |  | P00178674LZ | 17OD0177 |  |  | 2017-12-07 |  |  | Accelerated Metal Technology and Const. Inc. |  | NC 2017
K10 | NCR | Malabon City | 136840 | Amang Rodriguez ES | CITY OF MALABON | 0 | 1 | 6 | 3STY6CL | BATCH 10 | 20834252.16 |  | 20730027.02 | Completed | 1 | [8 empty] | 2018-01-10 | Square Meter Trading & Const. Corp. |  | NC 2017
K10 | NCR | Malabon City | 136853 | Catmon IS | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | BATCH 10 | 27000000 |  | 25520958.51 | Completed | 1 | [8 empty] | 2018-01-10 | ISH Const. Inc |  | NC 2017
K10 | NCR | Malabon City | 136849 | Potrero ES I | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 10 | 31649789.72 |  | 31455124.21 | Completed | 1 | [8 empty] | 2017-12-21 | Square Meter Trading & Const. Corp. |  | NC 2017
K10 | NCR | Malabon City | 136846 | Santiago Syjuco Memorial School | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 10 | 36000000 |  | 35469792.21 | Completed | 1 | [8 empty] | 2017-12-21 | Steven Const. & Supply |  | NC 2017
K10 | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1 | 1 | 24 | 4STY24CL | BATCH 10 | 64141000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136471 | Bacood Elementary School | SAMPALOC | 6 | 1 | 16 | 4STY16CL | BATCH 10 | 45350000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136480 | Bagong Barangay Elementary School | PANDACAN | 6 | 1 | 16 | 4STY16CL | BATCH 13 | 40760000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136482 | Bagong Diwa Elementary School | PANDACAN | 6 | 1 | 24 | 4STY24CL | BATCH 13 | 59785600 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Manila | 305299 | Dona Teodora Alonzo HS | SANTA CRUZ | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 47600000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 305317 | Elpidio Quirino High School | SANTA ANA | 6 | 1 | 12 | 4STY12CL | BATCH 10 | 53105000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136433 | Emilio Jacinto Elementary School | TONDO | 1 | 1 | 10 | 2STY10CL | BATCH 10 | 25185000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136433 | Emilio Jacinto Elementary School | TONDO | 1 |  | 6 | 2STY6CL | BATCH 10 | 17127000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Manila | 305302 | Jose Abad Santos High School | SANTA CRUZ | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 78400000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136449 | Juan Sumulong Elementary School | SANTA CRUZ | 3 | 1 | 24 | 4STY24CL | BATCH 10 | 84650000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136461 | Legarda Elementary School | SAMPALOC | 4 | 1 | 16 | 4STY16CL | BATCH 10 | 46570000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136438 | Magat Salamat Elementary School | TONDO | 1 | 1 | 32 | 4STY32CL | BATCH 10 | 98747000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Manila | 305312 | Manila Science High School | ERMITA | 5 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Manila | 305318 | Manuel A. Roxas High School | PACO | 5 | 1 | 16 | 4STY16CL | BATCH 12 | 40760000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Manila | 305316 | Mariano Marcos Memorial High School | SANTA ANA | 6 | 1 | 8 | 4STY8CL | BATCH 12 | 19025000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Manila | 305316 | Mariano Marcos Memorial High School | SANTA ANA | 6 | 1 | 16 | 4STY16CL | BATCH 13 | 40760000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136467 | P. Burgos ES | TONDO | 4 | 1 | 24 | 4STY24CL | BATCH 10 | 60956000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Marikina City | 136679 | Concepcion Integrated School | CITY OF MARIKINA | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 33137151.39 |  |  | Completed | 1 |  |  | P00178703LZ-CW1 | 0170B0432 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | 2017-12-22 | VINNELL_BELVOIR CORPORATION |  | NC 2017
K10 | NCR | Marikina City | 136673 | Kalumpang ES | CITY OF MARIKINA | 1 | 1 | 28 | 4STY28CL | BATCH 10 | 63685374.28 |  |  | Completed | 1 |  |  | P00178698LZ-CW1 | 0170B0454 | 2017-12-02 | 2017-12-08 | 2017-12-22 | 2018-01-03 | 2018-01-04 | ST. TIMOTHY CONSTRUCTION CORPORATION |  | NC 2017
K10 | NCR | Marikina City | 136674 | L. Victorino ES | CITY OF MARIKINA | 1 | 1 | 24 | 4STY24CL | BATCH 10 | 57582992.4 |  |  | Completed | 1 |  |  | P00178699LZ-CW1 | 0170B0462 | 2017-12-06 | 2017-12-13 | 2017-12-26 | 2018-01-03 | 2018-01-04 | ST. TIMOTHY CONSTRUCTION CORPORATION |  | NC 2017
K10 | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 32244946.68 |  |  | Completed | 1 |  |  | P00178700LZ-CW1 | 0170B0433 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | 2017-12-28 | GR FEVIDAL CONSTRUCTION DEVELOPERS CORPORATION |  | NC 2017
K10 | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 44030854.92 |  |  | Completed | 1 |  |  | P00178702LZ-CW1 | 0170B0428 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | 2017-12-22 | GR FEVIDAL CONSTRUCTION DEVELOPERS CORPORATION |  | NC 2017
SHS | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 37845984.62 |  |  | Completed | 1 |  |  | P00178704LZ-CW1 | 0170B0431 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | 2017-12-22 | VINNEL-BELVOIR CORPORATION |  | NC 2017
SHS | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 |  | 8 | 4STY8CL | BATCH 10 | 18094817.33 |  |  | Completed | 1 |  |  | P00178705LZ-CW1 | 0170B0436 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | 2017-12-22 | VINNELL_BELVOIR CORPORATION |  | NC 2017
K10 | NCR | Marikina City | 136678 | San Roque ES | CITY OF MARIKINA | 1 | 1 | 28 | 4STY28CL | BATCH 10 | 63865374.28 |  |  | Completed | 1 |  |  | P00178701LZ-CW1 | 0170B0455 | 2017-12-02 | 2017-12-08 | 2017-12-22 | 2018-01-03 | 2018-01-04 | GR FEVIDAL CONSTRUCTION DEVELOPERS CORPORATION |  | NC 2017
K10 | NCR | Paranaque City | 136753 | Fourth Estate ES | CITY OF PARAÑAQUE | 2 | 1 | 48 | 4STY48CL | BATCH 10 | 117688019.9 |  |  | Completed | 1 |  |  | P00178706LZ | 17OC0121 | 2017-11-28 |  | 2017-11-28 | 2017-12-12 | 2017-12-27 | New Big Four J Construction, Inc. |  | NC 2017
K10 | NCR | Pasay City | 136590 | Apelo Cruz ES | PASAY CITY | 0 | 1 | 20 | 4STY20CL | BATCH 10 | 45700000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Pasay City | 136590 | Apelo Cruz ES | PASAY CITY | 0 |  | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Pasay City | 319601 | Kalayaan NHS | PASAY CITY | 0 | 1 | 9 | 4STY9CL | BATCH 10 | 21403800 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Pasay City | 305367 | Pasay City East HS | PASAY CITY | 0 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Pasay City | 305370 | Pasay City South HIgh School | PASAY CITY | 0 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Pasay City | 305370 | Pasay City South HIgh School | PASAY CITY | 0 |  | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Pasay City | 500328 | Philippine National School for the Blind | PASAY CITY | 0 | 1 | 6 | 2STY6CL | BATCH 10 | 9525000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Pasay City | 500329 | Philippine School for the Deaf | PASAY CITY | 0 | 1 | 20 | 4STY20CL | BATCH 10 | 45700000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136567 | Aguinaldo ES | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 40139000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa ES | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 46046000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa ES | QUEZON CITY | 1 |  | 12 | 4STY12CL | BATCH 10 | 35238000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136552 | Bagumbayan ES | QUEZON CITY | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 34586000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136553 | Balara ES | QUEZON CITY | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 34600000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Quezon City | 305331 | Commonwealth HS | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 35741000 |  |  | COMpleted | 1 | [10 empty] | REDESIGNING OF THE PLAN & SPECS | NC 2017
TVL | NCR | Quezon City | 305360 | Don Alejandro Roces, Sr. Sci. & Tech. HS | QUEZON CITY | 4 | 1 | 27 | 4STY TVL | BATCH 10 | 95436000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136542 | Dona Juana ES | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 35741000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136546 | Manuel L. Quezon ES | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 35741000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136549 | Payatas B Annex ES | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 20495000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136563 | Project 3 ES | QUEZON CITY | 3 | 1 | 8 | 4STY8CL | BATCH 10 | 17628000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Quezon City | 305329 | Quezon City Science HS | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 47045000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Quezon City | 305329 | Quezon City Science HS | QUEZON CITY | 1 |  | 8 | 4STY8CL | BATCH 10 | 18980000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136492 | Ramon Magsaysay ES | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 45936000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Quezon City | 305327 | San Francisco HS | QUEZON CITY | 1 | 1 | 32 | 4STY32CL | BATCH 10 | 80870000 |  |  | COMpleted | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 49052000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136510 | Sto. Cristo ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34144000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136506 | Toro Hills ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19984000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Taguig | 305467 | Maria Concepcion Cruz HS | PATEROS | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 20667628.92 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Taguig | 136896 | Pateros Elementary School | PATEROS | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 49027051.57 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Taguig | 136895 | Paulina Manalo ES | PATEROS | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 41546562.56 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Taguig | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 7 | 4STY7CL | BATCH 10 | 17159570.67 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Taguig | 136883 | Cipriano P. Sta. Teresa Elementary School | TAGUIG CITY | 1 | 1 | 24 | 4STY24CL | BATCH 10 | 57497969.97 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Taguig | 136871 | Ciriaco P. Tiñga Elementary School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 32244946.68 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Taguig | 136886 | Kapitan Jose Cardones Memorial ES | TAGUIG CITY | 2 | 1 | 24 | 4STY24CL | BATCH 10 | 55961256.52 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Taguig | 500342 | Napindan Integrated School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 23410308.71 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Taguig | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 21279843.93 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Taguig | 136877 | Tipas Elementary School -Main | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34509193.16 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Taguig | 320605 | Upper Bicutan National High School | TAGUIG CITY | 2 | 1 | 6 | 4STY6CL | BATCH 10 | 10756889.78 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Taguig | 136879 | Ususan Elementary School | TAGUIG CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 55693407.06 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 45550000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136820 | Bitik ES | CITY OF VALENZUELA | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Valenzuela City | 305437 | Dalandanan NHS | CITY OF VALENZUELA | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 55760000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136815 | Lawang Bato Elementary School | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34820000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136797 | Malinta Elementary School | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 18875600 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 33600000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 |  | 12 | 4STY12CL | BATCH 10 | 33600000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136798 | Maysan ES | CITY OF VALENZUELA | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 45700000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136798 | Maysan ES | CITY OF VALENZUELA | 2 |  | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136806 | Pasolo ES | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 41930000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136806 | Pasolo ES | CITY OF VALENZUELA | 1 |  | 8 | 4STY8CL | BATCH 10 | 23670000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 305436 | Polo NHS | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 49265000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136819 | Silvestre Lazaro Elementary School | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 18875600 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136811 | WawangPulo ES | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 23520000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Caloocan City | 136615 | Andres Bonifacio ES | CALOOCAN CITY | 2 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 |  |  | P00181221LZ | 17OD0145 |  |  | 2017-11-28 |  |  | St. Timothy Const. Corp. |  | NC 2017
K10 | NCR | Caloocan City | 136615 | Andres Bonifacio ES | CALOOCAN CITY | 2 |  | 8 | 4STY8CL | BATCH 12 | 19025600 |  |  | Completed | 1 |  |  | P00181222LZ | 17OD0142 |  |  | 2017-11-28 |  |  | St. Timothy Const. Corp. |  | NC 2017
K10 | NCR | Caloocan City | 136637 | Horacio dela Costa ES | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 |  |  | P00181224LZ | 17OD0150 |  |  | 2017-11-29 |  |  | Accelerated Metal Technology and Const. Inc. |  | NC 2017
K10 | NCR | Caloocan City | 136646 | NHC ES | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 |  |  | P00181225LZ | 17OD0154 |  |  | 2017-11-29 |  |  | Orani Builders Supply |  | NC 2017
K10 | NCR | Caloocan City | 136646 | NHC ES | CALOOCAN CITY | 1 |  | 8 | 4STY8CL | BATCH 12 | 19025600 |  |  | Completed | 1 |  |  | P00181226LZ | 17OD0143 |  |  | 2017-11-28 |  |  | Orani Builders Supply |  | NC 2017
K10 | NCR | Caloocan City | 305373 | Sampaguita HS | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 12 | 19025600 |  |  | Completed | 1 |  |  | P00181227LZ | 17OD0144 |  |  | 2017-11-28 |  |  | Accelerated Metal Technology and Const. Inc. |  | NC 2017
K10 | NCR | Caloocan City | 136623 | San Jose ES | CALOOCAN CITY | 2 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 |  |  | P00181223LZ | 17OD0155 |  |  | 2017-11-29 |  |  | Alcel Construction |  | NC 2017
K10 | NCR | Las Piñas City | 136775 | Gatchalian ES | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 16355000 |  |  | Completed | 1 |  |  | P00181228 | 17OI0099 | 2017-09-06 | 2017-09-14 | 2017-09-26 | 2017-11-09 | 2017-12-05 | GF ROVERO MERCHANDISING |  | NC 2017
K10 | NCR | Las Piñas City | 305434 | Las Pinas East National High School | CITY OF LAS PIÑAS | 0 | 1 | 20 | 4STY20CL | BATCH 12 | 41780000 |  |  | Completed | 1 |  |  | P00181232 | 17OI0126 | 2017-11-02 | 2017-11-10 | 2017-11-23 | 2017-11-29 | 2017-12-15 | LMG CONSTRUCTION |  | NC 2017
K10 | NCR | Las Piñas City | 136777 | Las Pinas ES Central | CITY OF LAS PIÑAS | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 31800000 |  |  | Completed | 1 |  |  | P00181229 | 17OI0124 | 2017-11-02 | 2017-11-10 | 2017-11-23 | 2017-11-29 | 2017-12-15 | LMG CONSTRUCTION |  | NC 2017
K10 | NCR | Las Piñas City | 136788 | Pamplona ES I | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17455000 |  |  | Completed | 1 |  |  | P00181230 | 17OI0116 | 2017-10-16 | 2017-10-26 | 2017-11-07 | 2017-04-24 | 2017-09-06 | FRAMECON BUILDERS |  | NC 2017
K10 | NCR | Las Piñas City | 136789 | Pilar Village ES | CITY OF LAS PIÑAS | 0 | 1 | 16 | 4STY16CL | BATCH 12 | 37200000 |  |  | Completed | 1 |  |  | P00181232 | 17OI0125 | 2017-11-02 | 2017-11-10 | 2017-11-23 | 2017-11-29 | 2017-12-15 | DAVHEZ CONSTRUCTION |  | NC 2017
SHS | NCR | Mandaluyong City | 500051 | Andres Bonifacio Integrated School | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 32000000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | 24 | 4STY24CL | BATCH 12 | 54000000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Mandaluyong City |  | Sen. Neptali Gonzales Integrated School | Mandaluyong City | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 32000000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136452 | P. Gomez ES | SANTA CRUZ | 3 | 1 | 20 | 4STY20CL | BATCH 10 | 60895000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136452 | P. Gomez ES | SANTA CRUZ | 3 |  | 16 | 4STY16CL | BATCH 10 | 54256000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136472 | Pio del Pilar Elementary School | SAMPALOC | 6 | 1 | 20 | 4STY20CL | BATCH 10 | 58070000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136485 | Sta. Ana ES | SANTA ANA | 6 | 1 | 16 | 4STY16CL | BATCH 12 | 40760000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | BATCH 12 | 47990000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 |  | 20 | 4STY20CL | BATCH 12 | 43840000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 31904360.14 |  |  | Completed | 1 |  |  | 17O10120 | 17O10120 |  | 2017-10-26 | 2017-11-07 | 2017-11-21 | 2017-12-05 | Redcar Trading & Const |  | NC 2017
SHS | NCR | Muntinlupa City | 305469 | Muntinlupa Science High School | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 31904360.14 |  |  | Completed | 1 |  |  | 17O10121 | 17O10121 |  | 2017-10-26 | 2017-11-07 | 2017-11-21 | 2017-12-05 | Redcar Trading & Const/RDGD Const. (JV) |  | NC 2017
K10 | NCR | Muntinlupa City | 136904 | Putatan Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17429616.04 |  |  | Completed | 1 |  |  | 17O10117 | 17O10117 |  | 2017-10-26 | 2017-11-07 | 2017-11-21 | 2017-12-05 | Framecon Builders |  | NC 2017
K10 | NCR | Muntinlupa City | 136914 | Sucat Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17429616.04 |  |  | Completed | 1 |  |  | 17O10119 | 17O10119 |  | 2017-10-26 | 2017-11-07 | 2017-11-21 | 2017-12-05 | Vicvera Bldrs Inc |  | NC 2017
K10 | NCR | Muntinlupa City | 136907 | Victoria Homes ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17429616.04 |  |  | Completed | 1 |  |  | 17O10118 | 17O10118 |  | 2017-10-26 | 2017-11-07 | 2017-11-21 | 2017-12-05 | RV Rieta Trading & Gen. Const. |  | NC 2017
K10 | NCR | Quezon City |  | Harmony Hills NHS | QUEZON CITY | 2 | 1 | 32 | 4STY32CL | BATCH 12 | 79376000 |  |  | Terminated | 0 | [10 empty] | For Terminations with ISF's; WAITING FOR THE RESPONSE OF DPWH RE: COPY OF PERTINENT DOCUMENTS | NC 2017
K10 | NCR | Valenzuela City |  | Lingunan HS | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | BATCH 12 | 40760000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | City of San Juan | 136745 | Salapan ES | CITY OF SAN JUAN | 0 | 1 | 7 | 4STY7CL | BATCH 13 | 21350000 |  |  | Completed | 1 |  |  | 017OB0450 | P00182445LZ_CW1 | 2017-11-28 | 2017-12-08 | 2017-12-19 | 2017-12-22 | 2018-01-04 | B.BERNARDO CONSTRUCTION |  | NC 2017
K10 | NCR | City of San Juan | 136746 | San Juan ES | City of San Juan | 0 | 1 | 28 | 4STY28CL | BATCH 13 | 63798000 |  |  | Completed | 1 |  |  | 017OB0460 | P00182446LZ_CW1 | 2017-12-05 | 2107-12-26 | 2017-12-26 | 2018-01-03 | 2018-01-04 | ST. TIMOTHY CONSTRUCTION CORP. |  | NC 2017
SHS | NCR | City of San Juan | 305423 | San Juan National High School | CITY OF SAN JUAN | 0 | 1 | 28 | 4STY28CL | BATCH 13 | 61000000 |  |  | Completed | 1 |  |  | 017OB0461 | P00182448LZ_CW1 | 2017-12-05 | 2107-12-26 | 2017-12-26 | 2018-01-03 | 2018-01-04 | GR FEVIDAL CONST. AND DEV. CORP. |  | NC 2017
K10 | NCR | City of San Juan | 136747 | San Perfecto ES | CITY OF SAN JUAN | 0 | 1 | 36 | 4STY36CL | BATCH 13 | 70000000 |  |  | Completed | 1 |  |  | 017OB0445 | P00182447LZ_CW1 | 2017-11-28 | 2017-12-19 | 2017-12-19 | 2017-12-22 | 2018-01-04 | HENSCHA PHIL.INC. |  | NC 2017
K10 | NCR | Manila | 305289 | T. Paez Integrated School | TONDO | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 39143000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136431 | T. Paez Integrated School (Elem.) | TONDO | 1 | 1 | 32 | 4STY32CL | BATCH 10 | 98072000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Manila | 136466 | V. E. Fugoso Memorial School | SAMPALOC | 4 | 1 | 12 | 4STY12CL | BATCH 10 | 31808000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Taguig |  | Gat Andres Bonifacio HS | TAGUIG CITY | 2 | 1 | 20 | 4STY20CL | BATCH 13 | 41440293.15 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 14 | 41668504.32 |  | 41460161.8 | Completed | 1 | [8 empty] | 2018-01-10 | Alpha & Omega Gen. Contractor & Dev't. Corp. |  | NC 2017
K10 | NCR | Malabon City | 305451 | Tugatog NHS | CITY OF MALABON | 0 | 1 | 16 | 4STY16CL | BATCH 14 | 55558005.76 |  | 53360915.48 | Completed | 1 | [8 empty] | 2018-01-10 | Hexamindz Corp. |  | NC 2017
SHS | NCR | Navotas | 305457 | Tangos National High School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 14 | 42036997.81 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136500 | Bungad ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 34535000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Quezon City | 305320 | Balingasa HS | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 34234000 |  |  | Completed | 1 | [10 empty] | Completed as per DPWH; WAITING FOR THE PUMP TO BE INSTALLED | NC 2017
K10 | NCR | Quezon City |  | Bagong Silangan Annex HS | QUEZON CITY | 2 | 1 | 20 | 4STY20CL | BATCH 14 | 46046000 |  |  | Completed | 1 | [10 empty] | NO MOVEMENT, based on dpwh completed as per program | NC 2017
K10 | NCR | Quezon City | 136571 | Cruz na Ligas ES | QUEZON CITY | 4 | 1 | 12 | 4STY12CL | BATCH 14 | 35000000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY | 4 | 1 | 12 | 4STY12CL | BATCH 14 | 35000000 |  |  | Completed | 1 | [11 empty] | NC 2017
TVL | NCR | Quezon City | 305359 | Quezon City High School | QUEZON CITY | 4 | 1 | 3 | 3STY3CL | BATCH 14 | 10000000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Quezon City | 305361 | Manuel A. Roxas HS | QUEZON CITY | 4 | 1 | 12 | 4STY12CL | BATCH 14 | 35000000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5 | 1 | 12 | 4STY12CL | BATCH 14 | 35238000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136537 | North Fairview ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | BATCH 14 | 19984000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Quezon City | 136538 | San Agustin ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | BATCH 14 | 19984000 |  |  | Completed | 1 | [10 empty] | Completed as per DPWH; With Approved Buffer Funds 2018; NO MOVEMENT AT ALL, WAITING FOR THE RESPONSE OF DPWH RE: COPY OF PERTINENT DOCUMENTS | NC 2017
K10 | NCR | Quezon City | 136513 | New Era ES | QUEZON CITY | 6 | 1 | 16 | 4STY16CL | BATCH 14 | 40633000 |  |  | Completed | 1 | [10 empty] | COMPLETED AS PER DPWH; NO MOVEMENT AT ALL, WAITING FOR THE RESPONSE OF DPWH RE: COPY OF PERTINENT DOCUMENTS | NC 2017
K10 | NCR | Valenzuela City | 136818 | Punturin ES | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 34970000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 305439 | Canumay West NHS | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | BATCH 14 | 40760000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136817 | Paso de Blas ES | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19025600 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136822 | Caruhatan West ES | CITY OF VALENZUELA | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 34970000 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City | 136823 | Constantino ES | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19025600 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Valenzuela City | 305443 | Gen. T. de Leon NHS | CITY OF VALENZUELA | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 38130000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | NCR | Valenzuela City | 305446 | Sitero Francisco Mem. NHS | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19025600 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Valenzuela City |  | Bagbaguin NHS | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19025600 |  |  | Completed | 1 | [11 empty] | NC 2017
K10 | NCR | Caloocan City | 136627 | Bagong Barrio ES | KALOOKAN CITY | 1 | 1 | 20 | 4STY20CL | Batch 3 | 49570000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 136629 | Morning Breeze Elementary School | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 136630 | Sta. Quiteria ES | KALOOKAN CITY | 1 | 1 | 16 | 4STY16CL | Batch 3 | 46250000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 136631 | Talipapa ES | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 136633 | Camarin D ES | KALOOKAN CITY | 1 |  | 20 | 4STY20CL | Batch 3 | 49050000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 136634 | Camarin Elementary School | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | completed | 1 | [10 empty] | awaiting additional fund | NC 2018
K10 | NCR | Caloocan City | 136639 | Bagong Silang ES | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 136642 | Silanganan ES (Star ES) | KALOOKAN CITY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 38270000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 136643 | A. Mabini Elementary School | KALOOKAN CITY | 1 | 1 | 24 | 2 Units 4STY12CL | Batch 3 | 79200000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 136649 | Tala ES | KALOOKAN CITY | 1 | 1 | 16 | 4STY16CL | Batch 3 | 44050000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 136655 | Sampaguita Elementary School | KALOOKAN CITY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 39770000 |  |  | COMpleted | 1 | [10 empty] | Delayed Implementation | NC 2018
K10 | NCR | Caloocan City | 223501 | Caloocan North ES | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 305372 | Bagumbong High School | KALOOKAN CITY | 1 | 1 | 16 | 2 units 4STY8CL | Batch 3 | 44500000 |  |  | Completed | 1 | [10 empty] | Completed as per DPWH; 1 Unit partially completed (for installation of fire pro), 1 unit at 70% status though continous ongoing of works; Contractor committed to turn-over the buildings by April 30, 2023 Last Inspection: April 3 with UED, AM Nhey and Division Engrs | NC 2018
K10 | NCR | Caloocan City | 305374 | Camarin High School | KALOOKAN CITY | 1 | 1 | 20 | 4STY20CL | Batch 3 | 49330000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 305376 | Amparo High School | KALOOKAN CITY | 1 | 1 | 16 | 4STY16CL | Batch 3 | 46050000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 305386 | Deparo High School | KALOOKAN CITY | 1 |  | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City |  | CIELITO ZAMORA HS- BONIFACIO CAMPUS | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22450000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City |  | Bagong Silang Resettlement Project | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City |  | Bagong Silang Resettlement Project | KALOOKAN CITY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 40850000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City |  | Camarin Brixton Senior High School | KALOOKAN CITY | 1 | 1 | 20 | 4STY20CL | Batch 3 | 51150000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 136614 | Sampalukan ES | KALOOKAN CITY | 2 | 1 | 20 | 4STY20CL | Batch 3 | 51730000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 136618 | Gregoria de Jesus ES | KALOOKAN CITY | 2 | 1 | 20 | 4STY20CL | Batch 3 | 51650000 |  |  | completed | 1 | [11 empty] | NC 2018
K10 | NCR | Las Piñas City | 136784 | Dona Manuela ES | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | Batch 3 | 18655000 |  |  | COMpleted | 1 | [10 empty] | On-going construction, target completion in December 2020. Pump installed. For joint final inspection | NC 2018
K10 | NCR | Las Piñas City | 136785 | Moonwalk ES | CITY OF LAS PIÑAS | 0 | 1 | 20 | 4STY20CL | Batch 3 | 45780000 |  |  | COMpleted | 1 | [10 empty] | On-going construction, target completion in December 2020. Pump installed. For joint final inspection | NC 2018
SHS | NCR | Makati City | 305406 | Makati High School | CITY OF MAKATI | 1 | 1 | 12 | 6STY12CL | Batch 3 | 51691232.21 |  | 50402601.87 | COMpleted | 1 | [8 empty] | 2018-12-27 | C.B. GARAY PHILWIDE BUILDERS |  | NC 2018
K10 | NCR | Makati City | 136697 | Tibagan ES | CITY OF MAKATI | 2 | 1 | 24 | 6STY24CL | Batch 3 | 82782166.63 |  | 80720496.68 | COMpleted | 1 | [8 empty] | 2019-01-08 | DUMDUMA CONSTRUCTION AND TRADING CORPORATION / STUDIO 26 CONSTRUCTION INC. |  | NC 2018
K10 | NCR | Malabon City | 136836 | Ninoy Aquino ES | CITY OF MALABON | 0 | 1 | 24 | 4STY24CL | BATCH 1 | 81600000 |  | 78707083.61 | Completed | 1 | 2019-09-04 |  |  | 18OA0118 | [5 empty] | Cardrian Builders Inc. |  | NC 2018
K10 | NCR | Malabon City | 136852 | Acacia ES | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 40800000 |  | 38530451.32 | Completed | 1 | 2019-05-24 |  |  | 18OA0115 | [5 empty] | C.B. Tampengco Const. & Supply |  | NC 2018
SHS | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 40800000 |  | 39336781.16 | Completed | 1 | 2019-05-23 |  |  | 18OA0105 | [5 empty] | Hexamindz Corp. |  | NC 2018
K10 | NCR | Malabon City | 136834 | Imelda ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | Batch 3 | 30800000 |  | 29694849.81 | Completed | 1 | 2019-07-20 |  |  | 18OA0124 | [5 empty] | 124 Triumph Builders & Steel Inc. |  | NC 2018
K10 | NCR | Malabon City | 136838 | Tañong ES I | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | Batch 3 | 38240000 |  | 36901685.25 | Completed | 1 | 2019-09-29 |  |  | 18OA0122 | [5 empty] | M.G. Salazar Const |  | NC 2018
K10 | NCR | Malabon City | 136845 | Niugan ES | CITY OF MALABON | 0 | 1 | 16 | 4STY16CL | Batch 3 | 76480000 |  | 76085502.37 | Completed | 1 | 2019-12-06 |  |  | 18OA0123 | [5 empty] | NEW BIG FOURJ CONST |  | NC 2018
K10 | NCR | Malabon City | 136848 | Potrero ES | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | Batch 3 | 46200000 |  | 44579287.17 | Completed | 1 | 2019-10-24 |  |  | 18OA0121 | [5 empty] | St. Timothy Const. Corp. |  | NC 2018
K10 | NCR | Malabon City | 136855 | Maysilo ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | Batch 3 | 35840000 |  | 34696920.83 | Completed | 1 | 2019-08-27 |  |  | 18OA0125 | [5 empty] | Steven Const. & Supply |  | NC 2018
SHS | NCR | Mandaluyong City | 305395 | City of Mandaluyong Science HS | CITY OF MANDALUYONG | 0 | 1 | 4 | 4STY4CL | Batch 3 | 14364000 |  |  | Completed | 1 | [11 empty] | NC 2018
SHS | NCR | Mandaluyong City | 305395 | City of Mandaluyong Science HS | CITY OF MANDALUYONG | 0 |  | 24 | 4STY24CL | Batch 3 | 60000000 |  |  | Completed | 1 | [11 empty] | NC 2018
SHS | NCR | Mandaluyong City | 500333 | Eulogio Rodriguez Integrated School | CITY OF MANDALUYONG | 0 | 1 | 20 | 4STY20CL | Batch 3 | 50000000 |  |  | Completed | 1 | [11 empty] | NC 2018
SHS | NCR | Mandaluyong City | 500333 | Eulogio Rodriguez Integrated School | CITY OF MANDALUYONG | 0 |  | 12 | 4STY12CL | Batch 3 | 32572215.9469 |  |  | Completed | 1 | [11 empty] | NC 2018
SHS | NCR | Mandaluyong City | 500333 | Eulogio Rodriguez Integrated School | CITY OF MANDALUYONG | 0 |  | 4 | 4STY4CL | Batch 3 | 10000000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Mandaluyong City |  | Sen. Neptali A. Gonzales Integrated School | CITY OF MANDALUYONG | 0 | 1 | 32 | 4STY32CL | Batch 3 | 80000000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Mandaluyong City |  | Sen. Neptali A. Gonzales Integrated School | CITY OF MANDALUYONG | 0 |  | 12 | 4STY12CL | Batch 3 | 32572215.9469 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 136439 | I. Delos Reyes ES | TONDO | 1 | 1 | 16 | 4STY16CL | Batch 3 | 57300000 |  |  | COMpleted | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 136449 | Juan Sumulong Elementary School | SANTA CRUZ | 3 | 1 | 12 | 4STY12CL | Batch 3 | 50000000 |  |  | Completed | 1 | [11 empty] | NC 2018
SHS | NCR | Manila | 340599 | SHS within A.Maceda Intg. Sch.-(HS) | CITY OF MANILA | 4 | 1 | 4 | 4STY4CL (SPECIAL DESIGN) | Batch 3 | 23600000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 136476 | E. delos Santos Elementary School | CITY OF MANILA | 5 | 1 | 40 | 4STY40CL | Batch 3 | 116010000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 136489 | Tomas Earnshaw Elementary School | SANTA ANA | 6 | 1 | 24 | 4STY24CL | Batch 3 | 81902000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1 | 1 | 28 | 4STY28CL | Batch 5 | 229660358.78 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1 |  | 8 | 4STY8CL | Batch 5 | 49276374.28 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 136443 | Gen. Gregorio del Pilar ES | TONDO | 2 | 1 | 16 | 4STY16CL | Batch 5 | 90600000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2 | 1 | 16 | 4STY16CL | Batch 5 | 80300000 |  |  | COMpleted | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2 |  | 12 | 4STY12CL | Batch 5 | 65000000 |  |  | COMpleted | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 305298 | Florentino Torres High School | TONDO | 2 | 1 | 16 | 4STY16CL | Batch 5 | 81200000 |  |  | COMpleted | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 305298 | Florentino Torres High School | TONDO | 2 |  | 12 | 4STY12CL | Batch 5 | 70200000 |  |  | COMpleted | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 136466 | V. E. Fugoso Memorial School | SAMPALOC | 4 | 1 | 20 | 4STY20CL | Batch 5 | 54300000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 136476 | E. delos Santos Elementary School | CITY OF MANILA | 5 | 1 | 22 | 4STY22CL | Batch 5 | 67588702.95 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 136479 | Rafael Palma Elementary School | CITY OF MANILA | 5 | 1 | 24 | 4STY24CL | Batch 5 | 78327248.76 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Manila | 136489 | Tomas Earnshaw Elementary School | SANTA ANA | 6 | 1 | 28 | 4STY28CL | Batch 5 | 86806728.08 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 | 1 | 12 | 4STY12CL | Batch 3 | 60851765.74 |  |  | Completed | 1 | [9 empty] | Alpha-Omega Gen Con & Dep't. Corp |  | NC 2018
SHS | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 | 1 | 24 | 4STY24CL | Batch 3 | 67546019.91 |  |  | Completed | 1 | [8 empty] | 2019-01-14 | Vinnel-Belvoir Corporation |  | NC 2018
K10 | NCR | Muntinlupa City | 136900 | F. De Mesa ES | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | Batch 3 | 45992000 |  |  | Completed | 1 |  |  |  | 18OI0180 |  | 2018-11-29 | 2018-12-11 |  | 2018-12-28 | MRRM Trading & Const. |  | NC 2018
K10 | NCR | Muntinlupa City | 136901 | Itaas Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | Batch 3 | 45427500 |  |  | Completed | 1 |  |  |  | 18OI0179 |  | 2018-11-29 | 2018-12-11 |  | 2018-12-28 | ORANI BUILDERS SUPLY |  | NC 2018
K10 | NCR | Muntinlupa City | 136903 | Muntinlupa ES | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | Batch 3 | 34313000 |  |  | Completed | 1 |  |  |  | 18OI0183 |  | 2018-12-05 | 2018-12-17 |  | 2018-12-28 | G. F. ROVERO MERCHANDISING |  | NC 2018
K10 | NCR | Muntinlupa City | 136904 | Putatan Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 16 | 2 UNITS 4STY8CL | Batch 3 | 37800000 |  |  | Completed | 1 |  |  |  | 18OI0184 |  | 2018-12-05 | 2018-12-17 |  | 2018-12-28 | C. T. LEONCIO Const. & Trading/KP Gonzales Const. & Supply |  | NC 2018
K10 | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | Batch 3 | 34492000 |  |  | Completed | 1 |  |  |  | 18OI0186 |  | 2018-12-05 | 2018-12-17 |  | 2018-12-28 | ORANI BUILDERS SUPPLY |  | NC 2018
K10 | NCR | Muntinlupa City | 136912 | Cupang ES | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | Batch 3 | 46166000 |  |  | Completed | 1 |  |  |  | 18OI0181 |  | 2018-11-29 | 2018-12-11 |  | 2018-12-28 | REDCAR TRADING & CONST. |  | NC 2018
SHS | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 | 1 | 16 | 4STY16CL | Batch 3 | 40515000 |  |  | Completed | 1 |  |  |  | 18OI0185 |  | 2018-12-05 | 2018-12-17 |  | 2018-12-28 | MRRM Trading & Const. |  | NC 2018
K10 | NCR | Muntinlupa City | 305470 | PEDRO E. DIAZ HIGH SCHOOL | CITY OF MUNTINLUPA | 0 | 1 | 32 | 2 UNITS 4STY16CL | Batch 3 | 79620000 |  |  | Completed | 1 |  |  |  | 18OI0186 |  | 2018-12-05 | 2018-12-17 |  | 2018-12-28 | C. T. LEONCIO Const. & Trading/KP Gonzales Const. & Supply |  | NC 2018
K10 | NCR | Navotas | 136857 | Bangkulasi Elementary School | CITY OF NAVOTAS | 0 | 1 | 16 | 4STY16CL | BATCH 1 | 55410000 |  |  | COMpleted | 1 | [9 empty] | Dungan Contractor's & Trading Corp./ Jojalie Const. (JV) | For Punchlisting and Final Inspection | NC 2018
K10 | NCR | Navotas | 136859 | Kapitbahayan Elementary School | CITY OF NAVOTAS | 0 | 1 | 24 | 4STY24CL | BATCH 1 | 82750000 |  |  | Completed | 1 | [9 empty] | MRBll Const. Corp |  | NC 2018
K10 | NCR | Navotas | 136860 | Navotas Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 41190000 |  |  | Completed | 1 | [9 empty] | Orientech Const. & Devt. Corp. |  | NC 2018
K10 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 41140000 |  |  | Completed | 1 | [9 empty] | C.T. Leoncio Const. & Trading |  | NC 2018
SHS | NCR | Navotas | 305454 | San Rafael Technological High School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 41410000 |  |  | Completed | 1 | [9 empty] | St. Timothy Const. Corp. |  | NC 2018
K10 | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE | 1 | 1 | 16 | 4STY16CL | Batch 3 | 35522115.63 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Paranaque City | 136762 | Don Galo ES | CITY OF PARAÑAQUE | 1 | 1 | 4 | 4STY4CL | Batch 3 | 6825497.26 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Paranaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22432790.46 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Paranaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 |  | 20 | 4STY20CL | Batch 3 | 51169448.43 |  |  | Completed | 1 | [11 empty] | NC 2018
SHS | NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 28 | 4STY28CL | Batch 3 | 73737963.15 |  |  | Completed | 1 | [11 empty] | NC 2018
SHS | NCR | Paranaque City | 320201 | Paranaque Science HS | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | Batch 3 | 24747640.87 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Paranaque City | 136755 | Masville ES | CITY OF PARAÑAQUE | 2 | 1 | 12 | 4STY12CL (9mX7m) or 4STY16CL (Modified 8mX7m) | Batch 3 | 30851669.06 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Paranaque City | 136761 | Col. E. De Leon Elementary School | CITY OF PARAÑAQUE | 2 | 1 | 8 | 4STY8CL (9mX7m) or 4STY12CL (Modified 8mX7m) | Batch 3 | 20617779.37 |  |  | Completed | 1 | [10 empty] | Suspended 1/10/2019, Still finding a new site that will serve as temporary learning shelter for the displaced students that will be affected since the entire builing will be demolished | NC 2018
K10 | NCR | Paranaque City | 136761 | Col. E. De Leon Elementary School | CITY OF PARAÑAQUE | 2 |  | 24 | 4STY24CL (9mX7m) or 4STY36CL (Modified 8mX7m) | Batch 3 | 61553338.11 |  |  | Completed | 1 | [10 empty] | Suspended 1/10/2019, Still finding a new site that will serve as temporary learning shelter for the displaced students that will be affected since the entire builing will be demolished | NC 2018
K10 | NCR | Pasay City | 136604 | Jose Rizal ES | PASAY CITY | 0 | 1 | 20 | 4STY20CL | Batch 3 | 59975000 |  | 54427594.9 | Completed | 1 | 2019-09-12 |  |  | 18OH0174 |  |  | 2018-11-06 | 2018-11-21 | 2018-12-10 | St. Timothy Const. Corporation |  | NC 2018
K10 | NCR | Pasay City | 136604 | Jose Rizal ES | PASAY CITY | 0 |  | 24 | 4STY24CL | Batch 3 | 68891000 |  | 63466057.96 | Completed | 1 | 2019-10-12 |  |  | 18OH0173 |  |  | 2018-11-06 | 2018-11-21 | 2018-12-10 | Alpha & Omega Gen. Contractor & Dev't Corp. | Punchlist items still for acceptance. Ceiling is damaged by Typhoon Fabian, to be rectified by Contractor. | NC 2018
K10 | NCR | Pasig City | 136728 | San Joaquin ES | CITY OF PASIG | 0 | 1 | 20 | 4STY20CL | Batch 3 | 59295681.69 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Pasig City | 136732 | Pineda ES | CITY OF PASIG | 0 | 1 | 20 | 4STY20CL | Batch 3 | 56669465.54 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Pasig City | 136742 | Maybunga ES | CITY OF PASIG | 0 | 1 | 12 | 4STY12CL | Batch 3 | 41690415.08 |  |  | Completed | 1 | [11 empty] | NC 2018
SHS | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG | 0 | 1 | 24 | 4STY24CL | Batch 3 | 68269701.05 |  |  | Completed | 1 | [11 empty] | NC 2018
SHS | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | CITY OF PASIG | 0 | 1 | 8 | 4STY8CL | Batch 3 | 26218158.47 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136565 | Teodora Alonzo Elementary School | QUEZON CITY | 3 | 1 | 8 | 4STY8CL | BATCH 1 | 18100000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136490 | Balingasa Elementary School | QUEZON CITY | 1 | 1 | 20 | 4STY12CL & 4STY8CL | Batch 3 | 61450000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136508 | Mines Elementary School | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 23945000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 305323 | San Jose HS | QUEZON CITY | 1 | 1 | 24 | 4STY24CL | Batch 3 | 62600000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136549 | Payatas B Annex ES | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | Batch 3 | 23945000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 305332 | Bagong Silangan HS | QUEZON CITY | 2 | 1 | 16 | 4STY16CL | Batch 3 | 46860000 |  |  | Completed | 1 | [10 empty] | With Additional Funds intended for Connecting Bridge | NC 2018
SHS | NCR | Quezon City | 319501 | Holy Spirit SHS | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | Batch 3 | 22610000 |  |  | Completed | 1 | [11 empty] | NC 2018
SHS | NCR | Quezon City | 305350 | Quirino HS | QUEZON CITY | 3 | 1 | 8 | 4STY8CL | Batch 3 | 30555000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136573 | Pinyahan ES | QUEZON CITY | 4 | 1 | 16 | 4STY16CL | Batch 3 | 47500000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136579 | General Roxas Elementary School | QUEZON CITY | 4 | 1 | 8 | 4STY8CL | Batch 3 | 28195000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136583 | Aurora A. Quezon ES | QUEZON CITY | 4 | 1 | 8 | 4STY8CL | Batch 3 | 28120000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY | 4 | 1 | 8 | 4STY8CL | Batch 3 | 28150000 |  |  | Completed | 1 | [11 empty] | NC 2018
SHS | NCR | Quezon City | 305355 | Carlos L. Albert HS | QUEZON CITY | 4 | 1 | 20 | 4STY20CL | Batch 3 | 61650000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136531 | Damong Maliit ES | QUEZON CITY | 5 | 1 | 20 | 4STY20CL | Batch 3 | 54050000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136536 | Nagkaisang Nayon ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | Batch 3 | 23010000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City |  | ATTY. ALFRED VARGAS SR. HS | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | Batch 3 | 23945000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City |  | G.B. FRANCISCO | QUEZON CITY | 5 | 1 | 20 | 4STY20CL | Batch 3 | 54570000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6 | 1 | 20 | 4STY20CL | Batch 3 | 54050000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | Batch 5 | 22810000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 136505 | San Antonio ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | Batch 5 | 39510000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Quezon City | 305328 | Pugad Lawin HS | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | Batch 5 | 23410000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Taguig | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 27075203.01 |  | 25,932,552,52 | Completed | 1 | 2020-08-29 | 2020-12-15 | P00273636LZ_CW1 | 018OB0464 | 2018-10-29 | 2018-11-07 | 2018-11-16 | 2018-11-27 | 2018-12-12 | Hyper J Construction & Supply |  | NC 2018
K10 | NCR | Taguig | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS | 1 | 1 | 8 | 4STY8CL | Batch 3 | 25907137.3 |  | 24822894.92 | Completed | 1 | 2020-02-13 | 2020-12-15 | P00273637LZ_CW1 | 018OB0466 | 2018-10-25 | 2018-11-05 | 2018-11-16 | 2018-11-27 | 2018-12-12 | Hyper J Construction & Supply |  | NC 2018
K10 | NCR | Taguig | 136897 | Sta. Ana Elementary School | PATEROS | 1 | 1 | 8 | 4STY8CL | Batch 3 | 37565830.5 |  | 36066487.7 | Completed | 1 | 2021-04-27 |  | P00273638LZ_CW1 | 018OB0462 | 2018-10-25 | 2018-11-05 | 2018-11-16 | 2018-11-27 | 2018-12-12 | Hony Trading and Construction |  | NC 2018
K10 | NCR | Taguig | 136898 | Sto. Rosario Elementary School | PATEROS | 1 | 1 | 8 | 4STY8CL | Batch 3 | 33116745.66 |  | 31758084.98 | Completed | 1 | 2020-02-07 | 2020-03-13 | P00273639LZ_CW1 | 018OB0463 | 2018-10-25 | 2018-11-05 | 2018-11-16 | 2018-11-27 | 2018-12-12 | Dahl Construction Corporation |  | NC 2018
K10 | NCR | Taguig | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2 | 1 | 24 | 4STY24CL | Batch 3 | 62326754.78 |  | 60009167.37 | Completed | 1 | 2019-09-27 | 2020-01-02 | P00273640LZ_CW1 | 018OB0456 | 2018-10-25 | 2018-11-05 | 2018-11-16 | 2018-11-27 | 2018-12-12 | MRBII Construction Corporation |  | NC 2018
K10 | NCR | Taguig | 136887 | Upper Bicutan ES | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL | Batch 3 | 39012528.26 |  | 37461040.68 | Completed | 1 | 2020-01-31 | 2020-03-13 | P00273641LZ_CW1 | 018OB0461 | 2018-10-25 | 2018-11-05 | 2018-11-16 | 2018-11-27 | 2018-12-12 | MRBII Construction Corporation |  | NC 2018
K10 | NCR | Valenzuela City | 136794 | Dalandanan Elementary School | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 39400000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Valenzuela City | 136806 | Pasolo Elementary School | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | Batch 3 | 55800000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Valenzuela City |  | Disiplina Village ES | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 39050000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Valenzuela City |  | Disiplina Village NHS | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 39050000 |  | 37836609.18 | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Valenzuela City |  | Disiplina Village NHS | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | Batch 3 | 21150000 |  | 21043537.2 | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Valenzuela City |  | Malanday NHS | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 46600000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Valenzuela City |  | Malanday NHS | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | Batch 3 | 55400000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Valenzuela City | 136796 | Sitio Sto. Rosario ES (Malabo ES) | CITY OF VALENZUELA | 2 | 1 | 16 | 4STY16CL | Batch 3 | 47150000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Valenzuela City | 136823 | Constantino ES | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 21470000 |  |  | Completed | 1 | [11 empty] | NC 2018
SHS | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 21100000 |  |  | Completed | 1 | [11 empty] | NC 2018
K10 | NCR | Caloocan City | 305373 | Sampaguita HS | Caloocan City | 1 | 1 | 8 | 4STY8CL |  | 24060000 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | NC 2019
K10 | NCR | Caloocan City | 305386 | Deparo High School | Caloocan City | 1 | 1 | 8 | 4STY8CL |  | 24060000 |  | completed | 1 | [10 empty] | exiting bldg - for demolition | 0 | NC 2019
K10 | NCR | Caloocan City | 136633 | Camarin D ES | Caloocan City | 1 | 1 | 8 | 4STY8CL |  | 24060000 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | NC 2019
K10 | NCR | Caloocan City | 136633 | Camarin D ES | Caloocan City | 1 |  | 8 | 4STY8CL |  | 24060000 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | NC 2019
K10 | NCR | Caloocan City | 136639 | Bagong Silang ES | Caloocan City | 1 | 1 | 8 | 4STY8CL |  | 24060000 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | NC 2019
K10 | NCR | Caloocan City | 136613 | Maypajo ES | KALOOKAN CITY | 2 | 1 | 12 | 4STY12CL |  | 47418250 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | NC 2019
K10 | NCR | Caloocan City | 136606 | Grace Park ES (Main) | Caloocan City | 2 | 1 | 20 | 4STY20CL |  | 50947050 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | NC 2019
SHS | NCR | Caloocan City | 305388 | Caloocan HS | Caloocan City | 2 | 1 | 8 | 4STY8CL |  | 24060000 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | NC 2019
K10 | NCR | Malabon City | 136850 | Tinajeros ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL |  | 30877000 | 28446060 | Completed | 1 | [11 empty] | 0 | NC 2019
SHS | NCR | Malabon City | 305450 | Panghulo NHS | CITY OF MALABON | 0 | 1 | 16 | 4STY16CL |  | 76671200 | 68593280 | Completed | 1 | [11 empty] | 0 | NC 2019
SHS | NCR | Manila | 500566 | T. Paez Integrated School (Elem.) | CITY OF MANILA | 1 | 1 | 20 | 4STY20CL |  | 68370500 |  | completed | 1 | [10 empty] | DPWH Terminated the Contract under this project. | 0 | NC 2019
K10 | NCR | Manila | 136437 | Manuel L. Quezon Elementary School | CITY OF MANILA | 1 | 1 | 20 | 4STY20CL |  | 68370500 |  | Completed | 1 | [10 empty] | awaiting for the approval of central office for modification of plans and quantity of CLs | 0 | NC 2019
K10 | NCR | Manila | 136437 | Manuel L. Quezon Elementary School | CITY OF MANILA | 1 |  | 24 | 2UNITS 4STY12CL |  | 99448000 |  | Terminated | 0.82 | [10 empty] | DPWH Terminated the Contract under this project; Completion of the school building already funded under GAA 2023 | 0 | NC 2019
K10 | NCR | Manila | 136439 | I. Delos Reyes ES | CITY OF MANILA | 1 | 1 | 32 | 4STY16CL |  | 57443250 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Manila | 136456 | P. Guevara Elementary School | CITY OF MANILA | 3 | 1 | 12 | 4STY12CL |  | 42907000 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Manila | 136452 | P. Gomez ES | CITY OF MANILA | 3 | 1 | 12 | 4STY12CL |  | 52337464.7685 |  | Completed | 1 | [11 empty] | 0 | NC 2019
SHS | NCR | Manila | 305302 | Jose Abad Santos High School | CITY OF MANILA | 3 | 1 | 16 | 4STY16CL |  | 83876040.8241 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Manila | 305300 | Cayetano Arellano High School | CITY OF MANILA | 3 | 1 | 12 | 4STY12CL |  | 66203184.4932 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Manila | 136446 | Andres Bonifacio Elementary School | CITY OF MANILA | 3 | 1 | 12 | 4STY12CL |  | 54417594.5245 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Manila | 136460 | G. Lopez Jaena Elementary School | CITY OF MANILA | 4 | 1 | 20 | 4STY20CL (SPECIAL DESIGN) |  | 56541000 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Manila | 136472 | Pio del Pilar Elementary School | CITY OF MANILA | 5 | 1 | 8 | 4STY8CL |  | 29573750 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Manila | 136482 | Bagong Diwa Elementary School | CITY OF MANILA | 6 | 1 | 24 | 4STY24CL |  | 49724000 |  | Completed | 1 | [10 empty] | awaiting for the approval of central office for modification of plans and quantity of CLs | 0 | NC 2019
K10 | NCR | Manila | 136471 | Bacood Elementary School | CITY OF MANILA | 5 | 1 | 16 | 4STY16CL |  | 50726500 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL |  | 28070000 |  | Completed | 1 |  |  |  | 19OI0140 | 8/1/2019 | 2019-08-07 | 2019-09-03 | 2019-09-12 | 2019-09-27 |  |  | 0 | NC 2019
K10 | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL |  | 49122500 |  | Completed | 1 |  |  |  | 19OI0141 | 8/1/2019 | 2019-08-07 | 2019-08-19 | 2019-08-28 | 2019-09-09 |  |  | 0 | NC 2019
K10 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL |  | 38335600 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL |  | 38335600 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Quezon City | 136492 | Ramon Magsaysay ES | QUEZON CITY | 1 | 1 | 24 | 4STY24CL |  | 62756500 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Quezon City | 136492 | Ramon Magsaysay ES | QUEZON CITY | 1 |  | 20 | 4STY20CL |  | 54185125 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL |  | 22516150 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa Elementary School | QUEZON CITY | 1 | 1 | 20 | 4STY20CL |  | 54185125 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa Elementary School | QUEZON CITY | 1 |  | 16 | 4STY16CL |  | 46611237.5 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Quezon City | 136509 | Project 6 ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL |  | 22666525 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Quezon City | 136569 | Dona Josefa E. Marcos ES | QUEZON CITY | 3 | 1 | 8 | 4STY8CL |  | 30375750 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Quezon City | 136569 | Dona Josefa E. Marcos ES | QUEZON CITY | 3 |  | 12 | 4STY12CL |  | 38095000 |  | Completed | 1 | [11 empty] | 0 | NC 2019
SHS | NCR | Quezon City | 305353 | Krus na Ligas HS | QUEZON CITY | 4 | 1 | 12 | 4STY12CL |  | 40100000 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL |  | 24004862.5 |  | Completed | 1 | [11 empty] | 0 | NC 2019
SHS | NCR | Taguig | 305464 | Tipas National High School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL w/ ROOFDECK |  | 56381109.0094 |  | completed | 1 | [11 empty] | 0 | NC 2019
SHS | NCR | Valenzuela City | 320407 | Wawangpulo National High School | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL |  | 16040000 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Valenzuela City | 136807 | Pio Valenzuela ES | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL |  | 48440800 |  | Completed | 1 | [11 empty] | 0 | NC 2019
SHS | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 | 1 | 20 | 4STY20CL |  | 51648489.1147 |  | Completed | 1 | [11 empty] | 0 | NC 2019
SHS | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 |  | 16 | 4STY16CL |  | 45893588.7322 |  | Completed | 1 | [11 empty] | 0 | NC 2019
SHS | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 |  | 8 | 4STY8CL |  | 22502549.9446 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Valenzuela City | 320406 | Canumay East National High School | CITY OF VALENZUELA | 1 | 1 | 16 | 2UNITS 4STY8CL |  | 45120136.644 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL |  | 22697871.3705 |  | Completed | 1 | [11 empty] | 0 | NC 2019
SHS | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 | 1 | 20 | 4STY20CL |  | 47655164.2386 |  | Completed | 1 | [11 empty] | 0 | NC 2019
K10 | NCR | Caloocan City | 136640 | Sto. Niño Elementary School | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL |  | 24761750 |  |  | Completed | 1 | [11 empty] | NC 2020
K10 | NCR | Caloocan City | 319701 | Cielito Zamora Senior High School | KALOOKAN CITY | 1 | 1 | 12 | 4STY12CL |  | 41904500 |  |  | Completed | 1 | [11 empty] | NC 2020
K10 | NCR | Caloocan City | 136623 | Barrio San Jose ES | KALOOKAN CITY | 2 | 1 | 12 | 4STY12CL |  | 41603750 |  |  | Completed | 1 | [11 empty] | NC 2020
K10 | NCR | Las Piñas City | 136779 | Pulanlupa ES | CITY OF LAS PIÑAS | 0 | 1 | 12 | 4STY12CL |  | 38596250 |  | 37576003.99 | Completed | 1 |  |  |  | 20OI0090 | 2020-01-08 | 2020-01-15 | 2020-01-29 | 2020-01-29 | 2020-08-18 | RR Encado Constructors Inc./Rocksteel Const. & Dev`t Corp (Joint Venture) | Completed as per DPWH; very slow moving of the work accomplishment due to minimal delivery of constraction materials on site | NC 2020
SHS | NCR | Las Piñas City | 305430 | Las Piñas National High School | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL |  | 26967250 |  | 26335101.13 | completed | 1 |  | 2021-08-03 |  | 20OI0089 | 2020-01-08 | 2020-01-15 | 2020-01-29 | 2020-01-29 | 2020-08-18 | Metrics Construction and Trading | Turned-over | NC 2020
K10 | NCR | Malabon City | 136833 | Santulan ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL |  | 38596250 |  |  | COMpleted | 1 | 2020-05-02 |  |  | 20OA0075 |  |  | 2020-07-20 |  |  | solenko construction |  | NC 2020
SHS | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL |  | 38596250 |  |  | COMpleted | 1 | 2020-05-02 |  |  | 20OA0074 |  |  | 2020-07-20 |  |  | newbig four J construction inc |  | NC 2020
K10 | NCR | Mandaluyong City |  | Senate President Neptali A. Gonzales IS | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL |  | 27067500 |  |  | Completed | 1 | [11 empty] | NC 2020
K10 | NCR | Manila | 136423 | Mariano Ponce Elementary School | TONDO | 2 | 1 | 16 | 4STY16CL |  | 90773235.11 |  |  | Completed | 1 | [10 empty] | on-going concreting works at 1st floor | NC 2020
K10 | NCR | Manila | 500567 | F. G. Calderon Elementary School | TONDO | 2 | 1 | 12 | 4STY12CL |  | 69077262.5 |  |  | Completed | 1 | [10 empty] | Completed as per DPWH; Ongoing concreting at ground floor | NC 2020
K10 | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3 | 1 | 8 | 4STY8CL (COMPLETION) |  | 10075125 |  |  | Completed | 1 | [10 empty] | Completed | NC 2020
K10 | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ | 3 | 1 | 20 | 4STY20CL |  | 97267562.5 |  |  | COMpleted | 1 | [10 empty] | Ongoing concreting at ground floor | NC 2020
K10 | NCR | Manila | 136456 | P. Guevara Elementary School | SAN NICOLAS | 3 | 1 | 12 | 4STY12CL |  | 33040842.6 |  |  | COMpleted | 1 | [10 empty] | Ongoing concreting at ground floor | NC 2020
K10 | NCR | Manila | 136458 | Laong Laan ES | SAMPALOC | 4 | 1 | 12 | 4STY12CL |  | 62255250 |  |  | COMpleted | 1 | [10 empty] | on-going foundation works | NC 2020
K10 | NCR | Manila | 136480 | Bagong Barangay Elementary School | PANDACAN | 6 | 1 | 8 | 4STY8CL |  | 27067500 |  |  | COMpleted | 1 | [10 empty] | on-going foundation works | NC 2020
SHS | NCR | Marikina City | 319906 | Sto. Nino National High School | CITY OF MARIKINA | 1 | 1 | 8 | 4STY8CL with Mat Foundation |  | 34887000 |  |  | Completed | 1 | 2021-04-03 | 2021-04-03 |  | 20OB0421 | 2020-05-26 | 2020-06-03 | 2020-06-16 |  | 2020-08-07 | MRBII Construction Corporation |  | NC 2020
K10 | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL |  | 19548750 |  | 19051420.15 | Completed | 1 | 2021-03-21 | 2021-09-30 | P00470027LZ-CW1 | 20OI0092 | 2020-01-03 | 2020-01-15 | 2020-01-29 | 2020-02-20 | 2020-08-18 | RGDG Construction | Due to pandemic | NC 2020
K10 | NCR | Muntinlupa City | 281541 | Poblacion ES | Muntinlupa | 0 | 1 | 8 | 4STY8CL |  | 24761750 |  | 24391249.6 | Completed | 1 |  |  | P00470028LZ-CW1 | 20OI0093 | 2020-01-03 | 2020-01-15 | 2020-01-29 | 2020-02-20 | 2020-08-18 | GREAT PACIFIC Builders and Gen. Contractor Inc. | due to pandemic and demoliion of NAWASA elevated tank | NC 2020
SHS | NCR | Navotas City | 305453 | Navotas NHS | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL (7X8) |  | 38596250 |  |  | Completed | 1 | 2021-05-05 | [8 empty] | MRBll Construction Corporation |  | NC 2020
K10 | NCR | Paranaque City | 136768 | Baclaran ES Unit I | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL with ROOFDECK |  | 24747486.2 |  | 23944652.12 | Completed | 1 | 2021-09-13 |  | P00470030LZ-CWI |  |  |  | 2020-09-09 | 2020-09-15 | 2020-09-18 | J.A. Evangelista Construction |  | NC 2020
K10 | NCR | Paranaque City | 136763 | F. Serrano Sr. ES - Don Bosco | CITY OF PARAÑAQUE | 2 | 1 | 8 | 4STY8CL with ROOFDECK |  | 24747486.2 |  | 24191889.08 | COMpleted | 1 | 2021-09-13 |  | P00470031LZ-CWI |  |  |  | 2020-09-09 | 2020-09-15 | 2020-09-18 | GREAT PACIFIC Builders and Gen. Contractor Inc. |  | NC 2020
K10 | NCR | Pasig City | 136727 | Kalawaan ES | Pasig City | 0 | 1 | 8 | 4STY8CL |  | 40049665.93 |  |  | Completed | 1 | [11 empty] | NC 2020
K10 | NCR | Pasig City | 136731 | Oranbo ES | Pasig City | 0 | 1 | 16 | 4STY16CL |  | 59962819.77 |  |  | Completed | 1 | [11 empty] | NC 2020
K10 | NCR | Pasig City | 136743 | San Miguel Elementary School | CITY OF PASIG | 0 | 1 | 8 | 4STY8CL |  | 30032092.31 |  |  | Completed | 1 | [11 empty] | NC 2020
SHS | NCR | Pasig City | 340654 | SHS in Buting, Pasig City | Pasig City | 0 | 1 | 16 | 4STY16CL WITH ROOF DECK |  | 87205470 |  |  | Completed | 1 | [11 empty] | NC 2020
K10 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1 | 1 | 8 | 4STY8CL |  | 22556250 |  |  | COMPLETED | 1 | [11 empty] | NC 2020
K10 | NCR | Quezon City | 136546 | Manuel L. Quezon ES | QUEZON CITY | 2 | 1 | 28 | 4STY28CL |  | 87718750 |  |  | COMPLETED | 1 | [10 empty] | Completed as of DPWH; DEMOLITION COMPLETED | NC 2020
K10 | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5 | 1 | 12 | 4STY12CL |  | 40902000 |  |  | Completed | 1 | [11 empty] | NC 2020
K10 | NCR | Quezon City | 136528 | Rosa L. Susano - Novaliches ES | QUEZON CITY | 5 | 1 | 16 | 4STY16CL |  | 52130000 |  |  | COMPLETED | 1 | [10 empty] | 100 %, DEMOLITION COMPLETED | NC 2020
K10 | NCR | Quezon City | 136529 | San Gabriel ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL |  | 22556250 |  |  | Completed | 1 | [10 empty] | Mobilized | NC 2020
K10 | NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY | 5 | 1 |  | CONSTRUCTION OF RETAINING WALL |  | 13964825 |  |  | COMPLETED | 1 | [11 empty] | NC 2020
K10 | NCR | Quezon City | 136519 | Lucas R. Pascual Mem. ES | QUEZON CITY | 6 | 1 | 12 | 4STY12CL |  | 44957112.5 |  |  | COMPLETED | 1 | [11 empty] | NC 2020
K10 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6 | 1 | 12 | 4STY12CL |  | 40250375 |  |  | COMPLETED | 1 | [10 empty] | 100 %, DEMOLITION COMPLETED | NC 2020
K10 | NCR | Taguig City & Pateros | 136892 | Aguho Elementary School | PATEROS | 1 | 1 | 12 | 4STY12CL WITH ROOF DECK |  | 47151585 |  | 45551188.88 | Completed | 1 | 2021-07-21 |  | P00470044LZ | 20OB0433 |  |  | 2020-07-15 |  |  | Newbig Four J Construction Inc. |  | NC 2020
K10 | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | Pateros | 1 | 1 | 16 | 4STY16CL |  | 71177500 |  | 68609100.51 | Completed | 1 | 2021-06-06 |  | P00470045LZ | 20OB0423 |  |  | 2020-06-16 |  |  | MRBII Construction Corp. |  | NC 2020
SHS | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL WITH ROOF DECK |  | 46917000 |  | 45190402.5 | Completed | 1 | 2021-07-21 |  | P00470046LZ | 20OB0424 |  |  | 2020-06-16 |  |  | Flordes Construction and Trading Corp. |  | NC 2020
SHS | NCR | Taguig City & Pateros | 320601 | Taguig Science High School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL with roofdeck (With Provision for 4sty12Cl) |  | 35087500 |  | 33833315.44 | Completed | 1 | 2021-05-07 |  | P00470050LZ | 20OB0422 |  |  | 2019-12-19 |  |  | Hony Trading & Construction |  | NC 2020
K10 | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL |  | 35262937.5 |  | 34566172.31 | Completed | 1 | 2021-07-29 |  | P00470048LZ | 20OBD0171 |  |  | 2020-08-18 |  |  | St. Timothy Construction Corp. |  | NC 2020
K10 | NCR | Taguig City & Pateros | 228002 | Gat. Andres Bonifacio Elmentary School | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL WITH ROOF DECK |  | 50125000 |  | 4441598251 | Completed | 1 | 2021-05-22 |  | P00470049LZ | 20OB0172 |  |  | 2019-12-19 |  |  | MRBII Construction Corp. |  | NC 2020
SHS | NCR | Taguig City & Pateros | 305463 | Signal Village National High School | TAGUIG CITY | 2 | 1 | 20 | 4STY20CL |  | 64861750 |  | 62521178.4 | Completed | 1 |  |  | P00470050LZ | 20OB0422 |  |  | 2020-06-16 |  |  | Orani Builders and Supply |  | NC 2020
K10 | NCR | Valenzuela City | 136795 | Lingunan ES | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL |  | 24360750 |  |  | Completed | 1 | 2021-04-13 | 2021-07-06 | P00470051LZ | 20OD0103 |  |  |  |  | 2020-08-17 | Toughbuilt Const. & Trading Inc. |  | NC 2020
K10 | NCR | Valenzuela City |  | Veinte Reales HS | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL |  | 24482553.75 |  | 23853462.32 | Completed | 1 | 2021-04-13 | 2021-07-06 | P00470052LZ | 20OD0104 |  |  |  |  | 2020-08-17 | Toughbuilt Const. & Trading Inc. |  | NC 2020
K10 | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2 | 1 | 16 | 4STY16CL |  | 47167625 |  | 45850285.22 | Completed | 1 | 2021-07-12 |  | P00470053LZ | 20OD0193 |  |  |  |  | 2020-08-17 | DJB Const. Services | Suspended due to presence of ISF | NC 2020
K10 | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2 |  | 12 | 4STY12CL |  | 41653875 |  | 40530029.26 | Completed | 1 | 2021-06-12 |  | P00470054LZ | 20OD0192 |  |  |  |  | 2020-08-17 | DJB Const. Services | Suspended due to presence of ISF | NC 2020
K10 | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2 |  | 8 | 4STY8CL |  | 24711625 |  | 24081305.36 | COMpleted | 1 | 2021-04-13 |  | P00470055LZ | 20OD0194 |  |  |  |  | 2020-08-17 | DJB Const. Services | On Going | NC 2020
K10 | NCR | Caloocan City | 136634 | Camarin Elementary School | KALOOKAN CITY | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 1002500 | 1000000 | 996110.17 | completed | 1 | 2021-10-27 |  | P00575461LZ | 21OD0197 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Aylan Const. & Trading |  | NC 2021
K10 | NCR | Caloocan City | 136634 | Camarin Elementary School | KALOOKAN CITY | 1 |  | 8 | Construction/Completion (4STY8CL) |  | 2005000 | 2000000 | 1994008.08 | completed | 1 | 2021-11-26 |  | P00575462LZ | 21OD0200 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Aylan Const. & Trading |  | NC 2021
K10 | NCR | Caloocan City | 136654 | Llano ES | CALOOCAN CITY | 1 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 1494229.88 | completed | 1 | 2021-10-27 |  | P00575463LZ | 21OD0195 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | C.B. Tampengco Construction & Supply |  | NC 2021
K10 | NCR | Caloocan City | 305374 | Camarin HS | CALOOCAN CITY | 1 | 1 | 16 | Construction/Completion (2-4STY8CL) |  | 2005000 | 2000000 | 1996667.41 | completed | 1 | 2021-12-26 |  | P00575464LZ | 21OD0196 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Aylan Const. & Trading |  | NC 2021
SHS | NCR | Caloocan City | 305380 | Tala High School | KALOOKAN CITY | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 4010000 | 4000000 | 3989457.54 | completed | 1 | 2021-12-26 |  | P00575465LZ | 21OD0224 | 2021-08-04 | 2021-08-11 | 2021-08-23 | 2021-09-13 | 2021-09-27 | Aylan Const. & Trading |  | NC 2021
SHS | NCR | Caloocan City | 305381 | Bagong Silang HS | KALOOKAN CITY | 1 | 1 | 6 | Construction/Completion (3STY6CL) (construction of 1CL at 2nd Floor, Staircase, CR with Septic Tank & repair/refurbishment of 5CL)) |  | 4010000 | 4000000 | 3986234.57 | completed | 1 | 2021-12-26 |  | P00575466LZ | 21OD0206 | 2021-07-16 | 2021-07-23 | 2021-08-04 | 2021-08-23 | 2021-09-27 | AGH Const. Corp. |  | NC 2021
SHS | NCR | Caloocan City | 305383 | Bagong Barrio NHS | Caloocan City | 1 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 1495444.36 | completed | 1 | 2021-10-27 |  | P00575467LZ | 21OD0199 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Probuilds & Works Construction Corp. |  | NC 2021
SHS | NCR | Caloocan City | 305383 | Bagong Barrio NHS | Caloocan City | 1 |  | 8 | Construction/Completion (4STY8CL) |  | 1503750 | 1500000 | 1495444.36 | completed | 1 | 2021-10-27 |  | P00575468LZ | 21OD0198 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Probuilds & Works Construction Corp. |  | NC 2021
K10 | NCR | Paranaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 | 1 | 2 | Construction/Completion (4STY2CL) |  | 5012500 | 5000000 | 4849479.06 | COMPLETED | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | Jalenz Construction and Supply |  | NC 2021
SHS | NCR | Paranaque City | 320201 | Paranaque Science HS | CITY OF PARAÑAQUE | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 20050000 | 20000000 | 19500585.67 | COMPLETED | 1 | 2022-04-11 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | YPR General Contractor and Construction Supply Inc. |  | NC 2021
K10 | NCR | Paranaque City | 136761 | Col. E. De Leon Elementary School | CITY OF PARAÑAQUE | 2 | 1 | 32 | Construction/Completion (4STY32CL) |  | 10025000 | 10000000 | 9698075.4 | COMPLETED | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | Golden 3T Construction Corp, |  | NC 2021
K10 | NCR | Paranaque City | 136763 | F. Serrano Sr. ES | CITY OF PARAÑAQUE | 2 | 1 | 8 | Construction/Completion (4-STOREY) |  | 8020000 | 8000000 | 7757714.6 | COMPLETED | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | GMO Construction |  | NC 2021
K10 | NCR | Paranaque City | 226001 | Sun Valley ES | CITY OF PARAÑAQUE | 2 | 1 | 3 | Construction/Completion (3STY3CL) |  | 7518750 | 7500000 | 7274965.25 | COMPLETED | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | GMO Construction |  | NC 2021
SHS | NCR | Paranaque City | 305428 | Dr. Arcadio Santos NHS - Main | CITY OF PARAÑAQUE | 2 | 1 | 8 | Construction/Completion (4-STOREY) |  | 6015000 | 6000000 | 5819939.36 | COMPLETED | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | GMO Construction |  | NC 2021
SHS | NCR | Paranaque City | 320203 | Moonwalk National High School | CITY OF PARAÑAQUE | 2 | 1 | 1 | Construction/Completion (4STY4CL) |  | 2506250 | 2500000 | 2424970.58 | COMPLETED | 1 | 2022-01-11 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | RGDG Construction |  | NC 2021
K10 | NCR | Paranaque City |  | Marcelo Green HS | CITY OF PARAÑAQUE | 2 | 1 | 1 | Construction/Completion (4-STOREY) |  | 2005000 | 2000000 | 1939135.79 | COMPLETED | 1 | 2022-01-11 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | RGDG Construction |  | NC 2021
K10 | NCR | Paranaque City |  | Silverio Annex Elementary School | CITY OF PARAÑAQUE | 2 | 1 | 1 | Construction/Completion (Four (4) Storey & Three (3) Storey) |  | 1002500 | 1000000 | 979905.88 | COMPLETED | 1 | 2021-12-12 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | Lizvil Construction and Supply |  | NC 2021
K10 | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1002500 | 1000000 |  | Completed | 1 | [8 empty] | 2021-11-09 | RAMALLA CONSTRUCTION & TRADING | Completion Works | NC 2021
K10 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 4522277.5 | 4511000 |  | Completed | 1 | [8 empty] | 2021-11-09 | JYBL CONSTRUCTION & TRADING | Completion Works | NC 2021
K10 | NCR | Quezon City | 136498 | San Francisco ES | QUEZON CITY | 1 | 1 | 32 | Construction/Completion (4STY32CL) |  | 13032500 | 13000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 |  | no movement | NC 2021
SHS | NCR | Quezon City | 305327 | San Francisco High School | QUEZON CITY | 1 | 1 | 32 | Construction/Completion (2 units 4STY16CL) |  | 13032500 | 13000000 |  | Completed | 1 | [8 empty] | 2021-11-09 | AYLAN CONSTRUCTION & TRADING | Completion Works | NC 2021
K10 | NCR | Quezon City | 136546 | Manuel L. Quezon ES | QUEZON CITY | 2 | 1 | 28 | Construction/Completion (4STY28CL) |  | 6015000 | 6000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | J. SIMEON CONSTRUCTION | Completed based on DPWH; No movement yet, ongoing phase 1 | NC 2021
K10 | NCR | Quezon City | 136549 | Payatas B Annex ES | QUEZON CITY | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1002500 | 1000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | JYBL CONSTRUCTION & TRADING | Completed based on DPWH; No movement yet | NC 2021
SHS | NCR | Quezon City | 305331 | Commonwealth HS | QUEZON CITY | 2 | 1 | 12 | Construction/Completion (4STY12CL) |  | 7017500 | 7000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | AYLAN CONSTRUCTION & TRADING | Completed based on DPWH; no movement | NC 2021
K10 | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5 |  | 12 | Construction/Completion (4STY12CL) |  | 4957362.5 | 4945000 |  | COMpleted | 1 | [8 empty] | 2021-11-09 | JYBL CONSTRUCTION & TRADING | no movement | NC 2021
K10 | NCR | Quezon City | 136528 | Rosa L. Susano - Novaliches ES | QUEZON CITY | 5 | 1 | 16 | Construction/Completion (4STY16CL) |  | 2005000 | 2000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | J. SIMEON CONSTRUCTION | Completed based on DPWH; No movement yet, ongoing phase 1 | NC 2021
K10 | NCR | Quezon City | 136529 | San Gabriel ES | QUEZON CITY | 5 | 1 | 8 | Construction/Completion (4STY8CL) |  | 4736812.5 | 4725000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | TAPNIO AND TAN CONSTRUCTION AND DEVELOPMENT CORPORATION | no movement | NC 2021
K10 | NCR | Quezon City | 136530 | Villa Verde Elementary School | QUEZON CITY | 5 | 1 | 12 | Construction/Completion (4STY12CL) |  | 7017500 | 7000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | RAMALLA CONSTRUCTION & TRADING | Completed based on DPWH;; only 1 bldg constructed 4sty16cl needs to be removed in this list | NC 2021
K10 | NCR | Quezon City | 136530 | Villa Verde Elementary School | QUEZON CITY | 5 |  | 16 | Construction/Completion (4STY16CL) |  | 3007500 | 3000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 |  | no movement | NC 2021
K10 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 4957362.5 | 4945000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | E.I. VILLACORTE CONSTRUCTION | Completed based on DPWH;; no movement | NC 2021
K10 | NCR | Valenzuela City | 136807 | Pio Valenzuela ES | CITY OF VALENZUELA | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1503750 | 1500000 | 1473340.67 | completed | 1 | 2021-11-25 |  | P00575495LZ | 21OD0207 |  |  | 2021-08-04 |  | 2021-09-27 | J. Simeon Construction |  | NC 2021
K10 | NCR | Valenzuela City | 136811 | WawangPulo ES | CITY OF VALENZUELA | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1503750 | 1500000 | 1472681.08 | completed | 1 | 2021-11-25 |  | P00575492LZ | 21OD0225 |  |  | 2021-08-23 |  | 2021-09-27 | Toughbulit Const & Trading Inc |  | NC 2021
SHS | NCR | Valenzuela City | 305436 | Polo NHS | CITY OF VALENZUELA | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 2005000 | 2000000 | 1956107.88 | completed | 1 | 2021-11-25 |  | P00575493LZ | 21OD0209 |  |  | 2021-08-04 |  | 2021-09-27 | J. Simeon Construction |  | NC 2021
SHS | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 711229.8305 | 709456.19 | 696652.75 | completed | 1 | 2021-10-26 |  | P00575494LZ | 21OD0203 |  |  | 2021-07-28 |  | 2021-09-27 | C.L. Morales Const & Trading |  | NC 2021
SHS | NCR | Valenzuela City |  | SHS IN ARKONG BATO, VALENZUELA | CITY OF VALENZUELA | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 2005000 | 2000000 | 1961127.65 | completed | 1 | 2021-11-25 |  | P00575495LZ | 21OD0208 |  |  | 2021-08-04 |  | 2021-09-27 | J. Simeon Construction |  | NC 2021
K10 | NCR | Valenzuela City | 136823 | Constantino ES | CITY OF VALENZUELA | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 781950 | 780000 | 768429.01 | completed | 1 | 2021-10-26 |  | P00575496LZ | 21OD0205 |  |  | 2021-08-04 |  | 2021-09-27 | Carry On Const |  | NC 2021
K10 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 516396.7123 | 515108.94 | 504747.74 | completed | 1 | 2021-10-26 |  | P00575492LZ | 21OD0225 |  |  | 2021-08-23 |  | 2021-09-27 | Flordes Const & Trading |  | NC 2021
SHS | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 | 1 | 20 | Construction/Completion (4STY20CL) |  | 3483802.3564 | 3475114.57 | 3935191.55 | completed | 1 | 2022-01-24 |  | P00575498LZ | 21OD0223 |  |  | 2021-08-23 |  | 2021-09-27 | DJB Const |  | NC 2021
SHS | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 |  | 8 | Construction/Completion (4STY8CL) |  | 1152875 | 1150000 | 1127121.68 | completed | 1 | 2021-10-26 |  | P00575499LZ | 21OD0202 |  |  | 2021-07-28 |  | 2021-09-27 | Carry On Const |  | NC 2021
K10 | NCR | Valenzuela City |  | Disiplina Village NHS | CITY OF VALENZUELA | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1102750 | 1100000 | 1080261.59 | completed | 1 | 2021-10-26 |  | P00575400LZ | 21OD0201 |  |  | 2021-07-28 |  | 2021-09-27 | Miles Trading & Const |  | NC 2021
K10 | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | [10 empty] | Completed as of March 16, 2023 | NC 2022
K10 | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | Construction of School Building | 1 |  | 30450937.5 |  | Completed | 1 | 00:00:00 | [9 empty] | - ongoing embankment; - remaining activities, left side stairs and septic vault | NC 2022
K10 | NCR | Navotas | 136862 | North Bay Boulevard Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | Construction of School Building | 1 |  | 30450937.5 |  | Completed | 1 | 2023-08-05 | [9 empty] | Issued Suspension Order No. 1 (60 C.D.) with Contract Time Extension No. 1 (60 C.D.) due to the pending completion of demolition works implemented by the Navotas City DepED | NC 2022
K10 | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | 2023-05-25 | [9 empty] | Issued Suspension Order/Time Extension No. 1 (93C.D.) due to pending demolition of existing structure by DepEd Issued Time Extension No. 2 (15C.D.) due to limited access to project site | NC 2022
K10 | NCR | Navotas | 136866 | San Roque Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | [10 empty] | Completed as of April 01, 2023 | NC 2022
K10 | NCR | Navotas | 136867 | Tangos Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | Construction of School Building | 1 |  | 30450937.5 |  | Completed | 1 | 2023-06-06 | [9 empty] | Ongoing installation of second floor RSB | NC 2022
K10 | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | Construction of School Building | 1 |  | 30450937.5 |  | Completed | 1 | 2023-06-06 | [9 empty] | - on going chb laying - 15 columns at grids 1-5 to be poured by Tuesday | NC 2022
SHS | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | 2023-02-06 | [9 empty] | Completed as of January 24, 2023 | NC 2022
SHS | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | 2023-05-22 | [9 empty] | Issued Suspension Order/Time Extension No. 1 (60 C.D.) to give way to the construction of temporary acess points for entrance and exit of the adjacent school building Issued Suspension Order/Time Extension No. 2 (45 C.D.) due to suspended/unworkable days brought by inclement weather condition | NC 2022
K10 | NCR | Caloocan City | 223502 | Gabriela Silang ES (Bagong Silang ES - Annex) | KALOOKAN CITY |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29387423.33 | Completed | 1 | 2024-12-07 | 2024-10-01 | P00775063LZ | 23OD0237 | 2023-06-22 |  | 2023-07-11 |  | 2023-08-18 | Dreamworx Builder & Trading Inc. |  | NC 2023
K10 | NCR | Caloocan City | 136613 | Maypajo ES | KALOOKAN CITY |  | 1 |  | 8 | Batch 1 | 35457562.5 | 35150000 | 34423890.25 | Ongoing | 0.8 | 2024-10-11 |  | P00775064LZ | 23OD0238 | 2023-06-22 |  | 2023-07-11 |  | 2023-08-18 | Dreamworx Builder & Trading Inc. |  | NC 2023
K10 | NCR | Caloocan City | 136644 | Manuel L. Quezon ES | KALOOKAN CITY |  | 1 |  | 8 | Batch 1 | 29808562.5 | 29550000 | 28912136.52 | Completed | 1 | 2024-12-06 | 2024-12-11 | P00775065LZ | 23OD0236 | 2023-06-22 |  | 2023-07-11 |  | 2023-08-18 | DSA Prime Builders Corporation |  | NC 2023
K10 | NCR | City of San Juan | 136750 | Nicanor C. Ibuna ES | CITY OF SAN JUAN |  | 1 |  | 16 | Batch 1 | 8070000 | 8000000 | 7716515.22 | Completed | 1 | 2023-12-03 | 2024-01-02 | P00775067LZ | 23OB0454 | 2023-05-29 | 2023-05-26 | 2023-06-20 | 2023-06-27 | 2023-07-06 | Aylan Consrtruction & Trading |  | NC 2023
K10 | NCR | City of San Juan | 136751 | Pinaglabanan ES | CITY OF SAN JUAN |  | 1 |  | 4 | Batch 1 | 11096250 | 11000000 | 10614195.75 | Completed | 1 | 2024-01-02 | 2024-05-17 | P00775068LZ | 23OB0455 | 2023-05-29 | 2023-05-26 | 2023-06-20 | 2023-06-27 | 2023-07-06 | Sto. Cristo Construction & Trading Inc. |  | NC 2023
K10 | NCR | City of San Juan | 136746 | San Juan ES | CITY OF SAN JUAN |  | 1 |  | 28 | Batch 1 | 11096250 | 11000000 | 10615395.14 | Completed | 1 | 2023-12-03 | 2023-11-22 | P00775066LZ | 23OB0456 | 2023-05-29 | 2023-05-26 | 2023-06-20 | 2023-06-27 | 2023-07-06 | Magnificus Builders Inc. |  | NC 2023
SHS | NCR | Las Piñas City | 340548 | Las Piñas City National Senior High School - Manuyo Campus | CITY OF LAS PIÑAS |  | 1 |  | 4 | Batch 1 | 15131250 | 15000000 | 14549997.85 | Completed | 1 | 2024-03-03 | 2024-07-12 | P00775070LZ-CW1 | 23OI0110 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-19 | Dahvez Construction | turn-over on July 12, 2024 | NC 2023
K10 | NCR | Las Piñas City | 136777 | Las Piñas Elementary School Central | CITY OF LAS PIÑAS |  | 1 |  | 4 | Batch 1 | 15131250 | 15000000 | 14549991.09 | Completed | 1 | 2024-03-03 | 2024-07-12 | P00775069LZ-CW1 | 23OI0111 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-19 | Dahvez Construction | turn-over on July 12, 2024 | NC 2023
K10 | NCR | Malabon City | 305451 | Tugatog NHS | CITY OF MALABON |  | 1 |  | 12 | Batch 1 | 30262500 | 30000000 | 29384529.47 | Completed | 1 | 2024-06-26 | 2024-07-26 | P00775071-LG-CW1 | 230A0100 | 2023-06-28 | 2023-07-06 | 2023-07-18 |  | 2023-07-31 | AL-REM KONSTRUCT INC. | phase 1 only, Division Engineer will follow up on the documents/data from DPWH. | NC 2023
SHS | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG |  | 1 |  | 6 | Batch 1 | 33711931.83 | 33419511.11 |  | Not Yet Started | [11 empty] | FOR REALIGNMENT | NC 2023
K10 | NCR | Manila | 136439 | I. Delos Reyes ES | TONDO |  | 1 |  | 6 | Batch 1 | 30262500 | 30000000 | 29096416.08 | Completed | 1 | 2025-02-20 | 2024-09-20 | P00775073LZ | 23OE0231 | 2023-06-13 | 2023-06-22 | 2023-07-13 |  | 2023-07-25 | ROAD EDGE TRADING & DEV'T SERVICES | COMPLETED BUT NOT YET TURN OVER | NC 2023
K10 | NCR | Manila | 136429 | Librada Avelino ES | TONDO |  | 1 |  | 6 | Batch 1 | 30262500 | 30000000 | 29011653.71 | Completed | 1 | 2024-04-19 | 2024-04-19 | P00775074LZ | 23OE0230 | 2023-06-13 | 2023-06-22 | 2023-07-03 | 2023-07-11 | 2023-07-14 | El-Jake Builders | COMPLETED BUT NOT YET TURN OVER | NC 2023
K10 | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ |  | 1 |  | 6 | Batch 1 | 30262500 | 30000000 | 29092137.75 | Completed | 1 | 2024-10-15 | 2024-10-15 | P00775075LZ | 23OE232 | 2023-06-13 | 2023-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-14 | TRILEX BUILDERS AND CONSTRICTION SUPPLY, INC. | COMPLETED BUT NOT YET TURN OVER | NC 2023
K10 | NCR | Manila | 305304 | Esteban Abada High School | SAMPALOC |  | 1 |  | 6 | Batch 1 | 30262500 | 30000000 | 29086575.68 | Completed | 1 | 2024-06-24 | 2024-06-23 | P00775076LZ | 23OE228 | 2023-06-13 | 2024-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-14 | I & E Construction Corp. | COMPLETED | NC 2023
SHS | NCR | Manila | 305309 | M.Araullo High School | ERMITA |  | 1 |  | 9 | Batch 1 | 30262500 | 30000000 | 29415864.41 | Ongoing | 0.67 | 2024-07-23 | 2024-07-23 | 23OH0081 | 23OH0081 | 2023-08-02 |  |  |  |  | RDBT CONST. CORP. | Requested to revise to 6-classroom school building instead of 9-classroom since the allocation is just enough for 6-classroom | NC 2023
K10 | NCR | Manila | 305317 | Elpidio Quirino High School | SAMPALOC |  | 1 |  | 6 | Batch 1 | 30262500 | 30000000 | 29052919.5 | Ongoing | 0.95 | 2025-01-02 | 2024-12-16 | P00775078LZ | 23OE229 | 2023-06-13 | 2023-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-14 | Flordes Construction & Trading Corp. | COMPLETED BUT NOT YET TURN OVER | NC 2023
SHS | NCR | Marikina City | 305402 | Malanday National High School | CITY OF MARIKINA |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 28926115.59 | Completed | 1 | 2024-04-03 | 2024-06-28 | P00775079LZ | 23OB0457 | 2023-05-29 | 2023-06-07 | 2023-07-21 | 2023-07-26 | 2023-08-08 | Streamline Builders Corp. |  | NC 2023
K10 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA |  | 1 |  | 32 | Batch 1 | 30262500 | 30000000 | 28850946.22 | Not Yet Started | 0 |  |  | P00775080LZ | 23OB0458 | 2023-05-29 | 2323-06-07 | 2023-07-21 | 2023-07-26 | 2023-08-08 | Kai Construction | Work suspended; Application of demolition permit | NC 2023
K10 | NCR | Muntinlupa City | 228501 | Poblacion Elementary School | CITY OF MUNTINLUPA |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29999999.06 | Completed | 1 | 2024-04-02 | 2024-06-08 | P00775081LZ-CW1 | 230I0112 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-18 | 2023-10-05 | Greenwall Construction | with approved additional 30CD | NC 2023
K10 | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS |  | 1 |  | 8 | Batch 1 | 2017500 | 2000000 | 1958779.07 | Completed | 1 | 2023-09-25 | 2023-12-15 | P00775082LZ | 23OA0090 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-28 | T.M. Abad Const. Corporation |  | NC 2023
K10 | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS |  | 1 |  | 12 | Batch 1 | 3026250 | 3000000 | 2935041.11 | Completed | 1 | 2023-10-28 | 2023-10-28 | P00775083LZ | 23OA0089 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-31 | C.B. Tampengco Const. & Supply |  | NC 2023
SHS | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS |  | 1 |  | 8 | Batch 1 | 4035000 | 4000000 | 3919257.43 | Completed | 1 | 2023-10-28 | 2024-02-20 | P00775084LZ | 23OA0092 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-08-31 | Two Dimension Construction | Suspended due to On-Going Construction of Phase 2 Project | NC 2023
SHS | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS |  | 1 |  | 8 | Batch 1 | 1008750 | 1000000 | 982185.24 | Completed | 1 | 2023-08-26 | 2024-07-27 | P00775085LZ | 23OA0091 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-28 | T.M. Abad Const. Corporation | Suspended due to On-Going Construction of Phase 2 Project | NC 2023
K10 | NCR | Navotas | 136862 | North Bay Boulevard Elementary School | CITY OF NAVOTAS |  | 1 |  | 12 | Batch 1 | 13113750 | 13000000 | 12727742.97 | Completed | 1 | 2023-12-22 | 2024-02-20 | P00775086LZ | 23OA0097 | 2023-06-29 | 2023-06-21 | 2023-07-19 | 2023-07-25 | 2023-07-26 | Erish Builders& Supply |  | NC 2023
K10 | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS |  | 1 |  | 8 | Batch 1 | 22192500 | 22000000 | 21543817.73 | Completed | 1 | 2024-02-25 | 2024-03-26 | P00775087LZ | 23OA0096 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-31 | MRBll Construction Corporation |  | NC 2023
K10 | NCR | Navotas | 136866 | San Roque Elementary School | CITY OF NAVOTAS |  | 1 |  | 8 | Batch 1 | 22192500 | 22000000 | 21509297.96 | Completed | 1 | 2024-02-22 | 2024-02-22 | P00775088LZ | 23OA0095 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-28 | T.M. Abad Const. Corporation |  | NC 2023
K10 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS |  | 1 |  | 12 | Batch 1 | 13113750 | 13000000 | 12727513.81 | Ongoing | 0.95 | 2023-12-23 | 2024-07-27 | P00775089LZ | 23OA0093 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-08-27 | Justbilt Builders | Suspended due to On-Going Construction of Phase 2 Project | NC 2023
K10 | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS |  | 1 |  | 12 | Batch 1 | 33288750 | 33000000 | 32319015.9 | Completed | 1 | 2024-03-26 | 2024-03-26 | P00775090LZ | 23OA0094 | 2023-06-29 | 2023-06-21 | 2023-07-19 | 2023-07-25 | 2023-07-31 | B. Bernardo Construction Inc. |  | NC 2023
K10 | NCR | Navotas | 136870 | Wawa Elementary School | CITY OF NAVOTAS |  | 1 |  | 20 | Batch 1 | 30262500 | 30000000 | 29385432.95 | Completed | 1 | 2024-07-27 | 2024-07-27 | P00775091LZ | 23OA0101 | 2023-06-21 | 2023-06-28 | 2023-06-29 | 2023-07-28 | 2023-07-26 | P7 Builders Inc. |  | NC 2023
K10 | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9798127.34 | Completed | 1 | 2024-04-15 | 2024-04-15 | P00775092LZ | 23OC0119 | 2023-10-05 | 2023-10-13 | 2023-10-25 |  | 2023-12-18 | J.S. Rabano Construction and Supply Inc. | Suspended December 29, 2023 due to revision of plan | NC 2023
K10 | NCR | Paranaque City | 136765 | Sto. Niño Elementary School | CITY OF PARAÑAQUE |  | 1 |  | 4 | Batch 1 | 20175000 | 20000000 | 19600930.96 | Completed | 1 | 2024-05-15 | 2024-05-15 | P00775093LZ | 23OC0120 | 2023-10-06 | 2023-10-14 | 2023-10-26 |  | 2023-12-18 | AARCON Builders | Suspended dated December 29, 2023 due to pending issuance of demolition and building permit from the Local Government of Parañaque City and ongoing coordination with the DepEd regarding the demolition of existing building | NC 2023
K10 | NCR | Paranaque City | 136759 | San Antonio Elementary School | CITY OF PARAÑAQUE |  | 1 |  | 12 | Batch 1 | 30262500 | 30000000 | 29400545.83 | Ongoing | 0.95 | 2024-07-14 | 2024-07-14 | P00775094LZ | 23OC0121 | 2023-10-07 | 2023-10-15 | 2023-10-27 |  | 2023-12-18 | GRAC-TA Builders | Suspended December 18, 2023 due to pending issuance of demolition and building permit from the Local Government of Parañaque City and ongoing coordination with the DepEd regarding the demolition of existing building. | NC 2023
K10 | NCR | Pasay City | 136599 | Marcela Marcelo ES | PASAY CITY |  | 1 |  | 6 | Batch 1 | 30262500 | 30000000 | 29370451.32 | Completed | 1 |  | 2024-06-30 | 230H0084 | 230H0084 | 2023-07-24 | 2023-08-03 | 2023-08-15 |  |  | ST. GABRIEL BUILDERS / LCRUZ CONSTRUCTION (JV) | complete | NC 2023
SHS | NCR | Pasig City | 305422 | Rizal Experimental Station And Pilot School for Cottage Industries (RESPSCI) | CITY OF PASIG |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29999743.52 | Completed | 1 | 2024-04-15 | 2024-05-24 | P00775096LZ | 23OB0460 | 2023-07-10 | 2023-07-19 | 2023-08-01 | 2023-08-08 | 2023-08-14 | Magnificus Builders Inc. |  | NC 2023
SHS | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG |  | 1 |  | 28 | Batch 3 | 175000000 | 168875000 | 168875000 | Ongoing | 0.35 | 2025-10-22 |  |  | 23OB0498 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | Prudent Diamond Square Construction Co. |  | NC 2023
K10 | NCR | Quezon City | 136490 | Balingasa Elementary School | QUEZON CITY |  | 1 |  | 12 | Batch 1 | 33711931.83 | 33419511.11 | 33054465.68 | Not Yet Started |  |  |  | P00775097LZ-CW1 | 23OF0149 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | MILES TRADING AND CONSTRUCTION/OSCORD BUILDERS CORPORATION (JOINT VENTURE) | Waiting for the issuance of Demolition Permit for the existing school building and the approval from QC-LGU to demolish the buildig (Brgy. Day Care) located at the frontage of the school / waiting for the data from DPWH / Construction of 4STY 8CL | NC 2023
SHS | NCR | Quezon City | 340694 | Lucresia Kasilag Senior High School (SHS within E. Abada ES) | QUEZON CITY |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29802912.39 | Completed | 1 | 2024-08-30 | 2024-08-30 | P00775099LZ-CW1 | 23OF0151 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | AYANA CONSTRUCTION AND TRADING | waiting for the data from DPWH | NC 2023
K10 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29803158.14 | Completed | 1 | 2024-11-15 | 2024-11-15 | P00775098LW-CW1 | 23OF0150 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | WAY MAKER GENERAL CONTRACTOR OPC. | waiting for the data from DPWH | NC 2023
K10 | NCR | Quezon City | 305337 | Justice Cecilia Muñoz Palma High School | QUEZON CITY |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29851396.56 | Completed | 0.9 | 2024-12-12 |  | P00775100LW-CW1 | 23OF0152 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | R. ROSE CONSTRUCTION SERVICES | waiting for the data from DPWH | NC 2023
SHS | NCR | Quezon City | 305352 | Juan Sumulong High School | QUEZON CITY |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29549992.78 | Ongoing | 0.75 | 2025-01-21 |  |  | 23-OG-0112 | 2023-12-02 |  |  |  |  | WAY MAKER GENERAL CONTRACTOR OPC. | 4 Sty 4 Cl with Repair/Rehab of 2 Sty Imelda BLDG & Site Dev, Division Engineer will follow up on the documents/data from DPWH. | NC 2023
K10 | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29909975.54 | Completed | 1 | 2025-01-03 |  |  | 23-OG-0110 | 2023-12-02 |  |  |  |  | FRAMECON BUILDERS | Phase 1 - 3Sty 6Cl (6 Cl completed), Division Engineer will follow up on the documents/data from DPWH. | NC 2023
SHS | NCR | Quezon City | 360867 | Leandro Locsin Integrated School | QUEZON CITY |  | 1 |  | 0 | Batch 1 | 10087500 | 10000000 | 9910245.7 | Not Yet Started |  |  |  |  | 23OF0156 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | 10 BUILDERS AND DEVELOPMENT CORPORATION | Proposed 4Storey 4 Classrooms. waiting to commence once the 4sty-16cl is completed, Division Engineer will follow up on the documents/data from DPWH. | NC 2023
K10 | NCR | Quezon City | 305338 | Maligaya HS | QUEZON CITY |  | 1 |  | 0 | Batch 1 | 5043750 | 5000000 |  | Not Yet Started |  |  |  |  | 23OF0153 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | FRAMECON BUILDERS | UNIMPLEMENTABLE. For Reversion of Fund for Rehabilitation/Repair of School Building | NC 2023
SHS | NCR | Quezon City | 305341 | San Bartolome HS | QUEZON CITY |  | 1 |  | 0 | Batch 1 | 10087500 | 10000000 |  | Not Yet Started |  |  |  |  | 23OF0154 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | CG GENERAL CONSTRUCTION & DEVELOPMENT CORPORATION | UNIMPLEMENTABLE. For Reversion of Fund for Rehabilitation/Repair of School Building | NC 2023
K10 | NCR | Quezon City | 305635 | West Fairview High School | QUEZON CITY |  | 1 |  | 0 | Batch 1 | 5043750 | 5000000 | 4975914 | Completed | 1 | 2024-02-22 | 2024-02-22 | P00775105LW-CW1 | 23OF0155 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | MILES TRADING AND CONSTRUCTION | Construction of 3STY 2CL, waiting for the data from DPWH | NC 2023
K10 | NCR | Quezon City | 305344 | Sauyo HS | QUEZON CITY |  | 1 |  | 10 | Batch 1 | 30262500 | 30000000 | 29849908.6 | Ongoing | 0.4 | 2024-09-18 |  |  | 23OF0163 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | MILES TRADING AND CONSTRUCTION | Division Engineer will follow up on the documents/data from DPWH. | NC 2023
K10 | NCR | Taguig | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS |  | 1 |  | 8 | Batch 1 | 10087500 | 10000000 | 9886489.56 | Completed | 1 | 2024-04-10 | 2024-04-18 | P00775108LZ | 23OB0484 | 2023-12-07 | 2023-12-15 | 2023-12-28 | 2023-12-29 | 2024-01-12 | B. Valencerina Trading and Construction | completed | NC 2023
SHS | NCR | Taguig | 320601 | Taguig Science High School | TAGUIG CITY |  | 1 |  | 12 | Batch 1 | 20175000 | 20000000 | 18996358.85 | Ongoing | 0.95 | 2024-01-18 |  | P00775109LZ | 23OB0461 | 2023-07-10 | 2023-07-19 | 2023-08-01 | 2023-08-08 | 2023-08-15 | TWENTYSIX CONSTRUCTION INC. | DPWH Issued contract time extension and imposed liquidated damages. | NC 2023
K10 | NCR | Taguig | 502057 | Bagong Tanyag Integrated School | TAGUIG CITY |  | 1 |  | 9 | Batch 1 | 30262500 | 30000000 | 29644438.12 | Ongoing | 0.95 | 2024-08-05 |  | P00775110LZ | 23OB0468 | 2023-12-08 | 2023-12-08 | 2023-12-29 | 2023-12-29 | 2024-01-09 | B. Bernardo Construction Inc. | For punchlist | NC 2023
K10 | NCR | Valenzuela City |  | Pasolo National High School | CITY OF VALENZUELA |  | 1 |  | 12 | Batch 1 | 32280000 | 32000000 | 28782907.95 | Completed | 1 | 2024-04-11 |  | P00775112LZ | 23OD0235 | 2023-06-22 | 2023-06-29 | 2023-07-11 | 2023-07-17 | 2023-08-16 | Rworkmate Construction | Phase 1 only, for final inspection of DepEd | NC 2023
K10 | NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA |  | 1 |  | 8 | Batch 1 | 29657250 | 29400000 | 28782907.95 | Completed | 1 | 2024-04-11 |  | P00775112LZ | 23OD0235 | 2023-06-22 | 2023-06-29 | 2023-07-11 | 2023-07-17 | 2023-08-16 | Rworkmate Construction | Turn Over to School | NC 2023
| NCR | Caloocan City | 136625 | Baesa ES | KALOOKAN CITY |  | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | 19738193.69 | Ongoing | 0.32 | 2025-01-25 |  | P00875001LZ | 24OD0292 | 2024-06-20 | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-07-29 | FRAMECON BUILDERS |  | NC 2024
| NCR | Caloocan City | 319707 | Caloocan City Business High School | KALOOKAN CITY |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39398654.98 | Ongoing | 0.57 | 2025-05-25 |  | P00875002LZ | 24OD0291 | 2024-06-20 | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-07-29 | WAWAO BUILDERS |  | NC 2024
| NCR | Caloocan City | 319705 | Maypajo High School | KALOOKAN CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39167469.39 | Ongoing | 0.2 | 2025-04-16 |  | P00875003LZ | 24OD0295 | 2024-07-11 | 2024-07-18 | 2024-08-01 | 2024-08-13 | 2024-08-19 | ED1SON DEVELOPMENT & CONSTRUCTION INC./TWENTYSIX CONSTRUCTION INC. |  | NC 2024
| NCR | Caloocan City | 136632 | Amparo ES | KALOOKAN CITY |  | 1 | 12 | Completion of 4STY12CL | BATCH 1 | 2500000 |  | 2447832.87 | Ongoing | 0.96 | 2024-10-27 |  | P00875789LZ | 24OD0285 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-07-22 | 2024-07-29 | TM ABAD CONSTRUCTION CORP. |  | NC 2024
| NCR | Caloocan City | 136632 | Amparo ES | KALOOKAN CITY |  |  | 8 | Completion of 4STY8CL | BATCH 1 | 2500000 |  | 2460814.81 | Ongoing | 0.96 | 2024-10-27 |  | P00875790LZ | 24OD0289 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-07-22 | 2024-07-29 | TM ABAD CONSTRUCTION CORP. |  | NC 2024
| NCR | Caloocan City | 136617 | Caloocan Central Elementary School | KALOOKAN CITY |  | 1 | 12 | 4STY12CL | BATCH 1 | 45050000 |  | 44106806.77 | Ongoing | 0.22 | 2025-07-14 |  | P00875788LZ | 24OD0297 | 2024-08-17 | 2024-08-27 | 2024-09-05 | 2024-09-11 | 2024-09-17 | STRUKTURA TEKNIKA SERVICES CO. |  | NC 2024
| NCR | Caloocan City | 500330 | Tandang Sora IS | KALOOKAN CITY |  | 1 | 12 | Completion of 4STY12CL | BATCH 1 | 19998569.25 |  | 19595766.82 | Ongoing | 0.5 | 2025-01-25 |  | P00875791LZ | 24OD0288 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-07-22 | 2024-07-29 | AYLAN CONSTRUCTION & TRADING |  | NC 2024
| NCR | Caloocan City | 136637 | Horacio dela Costa ES | KALOOKAN CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 38954849.56 | Not Yet Started | 0 | 2025-03-26 |  | P00875004LZ | 24OD0286 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-07-22 | 2024-07-29 | MILES TRADING AND CONSTRUCTION/OSCORD BUILDERS CORPORATION | Permit to Demolish on Process | NC 2024
| NCR | Caloocan City | 136644 | Manuel L. Quezon ES | KALOOKAN CITY |  | 1 | 12 | 4STY12CL | BATCH 1 | 45050000 |  | 44083387.04 | Ongoing | 0.4 | 2025-07-14 |  | P00875792LZ | 24OD0298 | 2024-08-17 | 2024-08-27 | 2024-09-05 | 2024-09-11 | 2024-09-17 | DIADEMA CONSTRUCTION AND ENTERPRISES INC. |  | NC 2024
| NCR | Las Piñas City | 136774 | Daniel Fajardo Elementary School | CITY OF LAS PIÑAS |  | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | FOR REVERSION | Not Yet Started | [11 empty] | cancelled, limited right of way | NC 2024
| NCR | Las Piñas City | 136776 | Ilaya Elementary School | CITY OF LAS PIÑAS |  | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | 19502329.68 | Not Yet Started | 0 | 2025-07-23 |  | P00875008LZ-CW1 | 24OI0160 | 2024-12-26 |  | 2025-08-01 | 2025-12-02 | 2025-02-21 | Dahvez Construction | Awarded (waiting for approval of building permit), Approved modification of the project from 3stry6cls to 4stry4cls | NC 2024
| NCR | Las Piñas City | 320304 | Las Piñas City National Science High School | CITY OF LAS PIÑAS |  | 1 | 4 | 4STY4CL | GAA 17B | 20000000 |  | 19500175.61 | Not Yet Started | 0 | 2025-07-23 |  | P00875007LZ-CW1 | 24OI0159 | 2024-12-26 |  | 2025-08-01 | 2025-12-02 | 2025-02-21 | Dahvez Construction | Awarded (waiting for approval of building permit), Approved modification of the project from 3stry6cls to 4stry4cls | NC 2024
| NCR | Las Piñas City | 136779 | Pulanlupa Elementary School | CITY OF LAS PIÑAS |  | 1 | 4 | 4STY4CL | GAA 17B | 20000000 |  | 19501674.69 | Not Yet Started | 0 | 2025-07-23 |  | P00875006LZ-CW1 | 24OI0161 | 2024-12-26 |  | 2025-08-01 | 2025-12-02 | 2025-02-21 | Dahvez Construction | Awarded (waiting for approval of building permit), Approved modification of the project from 3stry6cls to 4stry4cls | NC 2024
| NCR | Malabon City | 302387 | Malabon City Techvoc and Entrepreneurship Senior High School (CMPI Campus) | CITY OF MALABON |  | 1 | 8 | 4STY8CL (Phase 1) | GAA 17B | 40000000 |  | 38991692.17 | Ongoing | 0.58 | 2025-06-21 |  |  | 24OA0091 | 2024-09-21 | 2024-09-21 | 2024-10-11 | 2024-10-15 | 2024-10-25 | Rotaflex Construction and Development Corp. |  | NC 2024
| NCR | Malabon City | 136836 | Ninoy Aquino ES | CITY OF MALABON |  | 1 | 8 | 4STY8CL | BATCH 1 | 44000000 |  | 29384529.47 | Not Yet Started | 0 | 2025-01-13 |  | P00875793LZ | 24OA0086 | 2024-03-27 |  | 2025-04-16 |  | 2024-05-07 | C.B. Tampengco Construction and Supply | Waiting for demolition permit | NC 2024
| NCR | Mandaluyong City | 500335 | Ilaya Barangka Integrated School | CITY OF MANDALUYONG |  | 1 |  | Multi-Storey School Building (Phase 2) | GAA 17B | 40000000 |  | 39800000 | Ongoing | 0.5 | 2026-01-06 |  |  | 24OB0495 | 2024-03-26 |  | 2024-04-17 | 2024-04-24 | 2024-08-05 |  | part of phase 1 construction of 7 storey 28 classrooms | NC 2024
| NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  | 38971545.94 | Ongoing | 0.65 |  |  | P00875011LZ | 24OE0186 | 2024-03-08 | 2024-03-01 | 2024-04-30 | 2024-05-07 | 2024-05-09 |  |  | NC 2024
| NCR | Manila | 305295 | Lakan Dula High School | TONDO |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  | 38935353.14 | Ongoing | 0.8 | 2025-03-25 | 2025-03-25 | P00875012LZ | 24OE0185 | 2024-03-08 | 2024-03-01 | 2024-04-16 | 2024-04-22 | 2024-04-25 |  |  | NC 2024
| NCR | Manila | 136450 | Antonio Regidor Elementary School | SANTA CRUZ |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  | 38956893.27 | Ongoing | 0.45 |  |  | P00875013LZ | 24OE0187 | 2024-03-08 | 2024-03-01 | 2024-04-02 | 2024-04-11 | 2024-04-17 |  |  | NC 2024
| NCR | Manila | 305307 | Claro M. Recto High School | SAMPALOC |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  | 38953493.53 | Ongoing | 0.95 | 2025-03-24 | 2025-03-14 | P00875014LZ | 24OE0183 | 2024-03-08 | 2024-03-01 | 2024-04-02 | 2024-04-11 | 2024-04-17 |  | for final inspection and punchlisting | NC 2024
| NCR | Manila | 136473 | Justo Lukban Elementary School | PACO |  | 1 | 6 | 2STY6CL | GAA 17B | 40000000 |  | 39345960.41 | Ongoing | 0.2 | 2025-11-26 |  | 24OH0148 | 24OH0148 | 2024-11-29 | 2025-12-12 | 2024-12-19 | 2024-12-31 | 2025-01-28 |  |  | NC 2024
| NCR | Manila | 136454 | Geronimo Santiago Elementary School | SAN MIGUEL |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  | 38976244.56 | Ongoing | 0.3 |  |  | P00875016LZ | 24OE0184 | 2024-03-08 | 2024-03-01 | 2024-04-02 | 2024-04-11 | 2024-04-17 |  |  | NC 2024
| NCR | Marikina City | 305402 | Malanday National High School | CITY OF MARIKINA |  | 1 | 8 | Completion of 4STY8CL with covered roof deck | GAA 17B | 30000000 |  |  | Ongoing | 0.6 |  |  | 24OB0531 |  |  |  | 2025-01-14 | 2025-11-03 | 2025-03-17 |  | On-going | NC 2024
| NCR | Marikina City | 136678 | San Roque ES | CITY OF MARIKINA |  | 1 | 2 | 2STY2CL | GAA 17B | 10000000 |  |  | Ongoing | 0 |  |  | 24OB0529 |  |  |  | 2025-01-14 | 2025-11-03 | 2025-03-17 |  | For Mobilization | NC 2024
| NCR | Marikina City | 319905 | San Roque National High School | CITY OF MARIKINA |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  |  | Ongoing | 0.05 |  |  | 24OB0530 |  |  |  | 2025-01-14 | 2025-11-03 | 2025-03-17 |  | On-going | NC 2024
| NCR | Marikina City | 305399 | Tañong HS | CITY OF MARIKINA |  | 1 | 16 | 3STY6CL | GAA 17B | 40000000 |  |  | Ongoing | 0.05 |  |  | 24OB0534 |  |  |  | 2025-01-14 | 2025-11-03 | 2025-03-17 |  | On-going | NC 2024
| NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA |  | 1 |  | Completion of 5STY30CL | GAA 17B | 75000000 |  |  | Ongoing | 0.05 |  |  | 24OB0535 |  |  |  | 2025-01-14 | 2025-11-03 | 2025-03-17 |  | On-going | NC 2024
| NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA |  |  | 12 | 4STY12CL | GAA 17B | 80000000 |  |  | Ongoing | 0.1 |  |  | 24OB0533 |  |  |  | 2025-01-14 | 2025-11-03 | 2025-03-17 |  | On-going | NC 2024
| NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA |  | 1 | 32 | 4STY32CL | GAA 17B | 150000000 |  |  | Ongoing | 0 |  |  | 24OB0500 |  |  |  | 2024-08-22 | 2024-08-30 | 2024-10-09 |  | Pending certificate of condemnation | NC 2024
| NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA |  | 1 | 24 | 4STY24CL with Roofdeck | GAA 17B | 30000000 |  |  | Completed | 1 | 2025-10-04 | 2025-01-04 | 24OB0496 |  |  |  | 2024-04-17 | 2024-05-24 | 2024-04-06 |  |  | NC 2024
| NCR | Muntinlupa City | 305469 | Muntinlupa Science HS | CITY OF MUNTINLUPA |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39001215.57 | Ongoing | 0.95 | 2025-10-06 |  | P00875025LZ-CW1 | 24OI0153 | 2024-05-28 | 2024-05-07 | 2024-07-18 | 2024-02-08 | 2024-12-08 | REDCAR TRADING AND CONSTRUCTION |  | NC 2024
| NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 38984013.3 | Ongoing | 0.31 | 2025-10-24 |  | 24OA0092 | 24OA0092 | 2024-09-21 | 2024-09-27 | 2024-11-10 | 2024-10-18 | 2024-10-25 | STRUKTURA TEKNIKA SERVICES CO. | On-going | NC 2024
| NCR | Paranaque City | 136767 | Baclaran Elementary School Central | CITY OF PARAÑAQUE |  | 1 |  | 3-Storey School Building | GAA 17B | 20000000 |  | 9850892.19 | Ongoing | 0.15 | 2025-01-06 |  | P00875027LZ-CW1 | 240CO141 | 2024-11-26 | 2024-03-12 | 2024-12-16 | 2024-12-26 | 2025-02-01 |  |  | NC 2024
| NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE |  | 1 |  | 4-Storey School Building (Phase 2) | GAA 17B | 10000000 |  | 9799081.22 | Ongoing | 0.6 | 2025-01-06 |  | P00875028LZ-CW1 | 240CO14 | 2024-11-26 | 2024-03-12 | 2024-12-16 | 2024-12-26 | 2025-02-01 |  |  | NC 2024
| NCR | Paranaque City | 136765 | Sto. Niño Elementary School | CITY OF PARAÑAQUE |  | 1 |  | 4-Storey School Building with Ancillary (Phase 2) | GAA 17B | 10000000 |  | 19600545.56 | Ongoing | 0.4 | 2025-10-09 |  | P00875029LZ-CW1 | 240CO139 | 2024-11-26 | 2024-03-12 | 2024-12-16 | 2024-12-26 | 2025-02-01 |  |  | NC 2024
| NCR | Paranaque City | 137129 | Don Bosco Elementary School | CITY OF PARAÑAQUE |  | 1 | 12 | 4STY12CL with Roofdeck | GAA 17B | 40000000 |  | 39400750.05 | Ongoing | 0.4 | 2025-09-29 |  | P00875030LZ-CW1 | 240CO140 | 2024-11-26 | 2024-03-12 | 2024-12-16 | 2024-12-26 | 2025-02-01 |  |  | NC 2024
| NCR | Pasay City | 136590 | Apelo Cruz ES | PASAY CITY |  | 1 | 6 | 4STY6CL | GAA 17B | 40000000 |  | 39171336.73 | Ongoing | 0.22 | 2025-11-16 |  | Project ID No. 240H0122 | Contract ID No. 240H0122 | 2024-11-10 | 2024-10-31 | 2024-10-31 | 2024-12-31 | 2025-04-02 | ALE BUILDERS CONST. & DEVT. CORP |  | NC 2024
| NCR | Pasig City | 305420 | Sta. Lucia High School | CITY OF PASIG |  | 1 | 3 | 4STY8CL (Phase 1 3STY3CL) | GAA 17B | 40000000 |  |  | Not Yet Started | 0 | [10 empty] | re-scheduled procurement activities | NC 2024
| NCR | Quezon City | 305321 | Judge Juan Luna HS | QUEZON CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39517388.5 | Ongoing | 0.5 |  |  |  | 24OF0168 | 2024-03-27 | 2024-04-04 | 2024-04-24 | 2024-04-23 | 2024-04-29 | FRAMECON BUILDERS | Demolition Ongoing | NC 2024
| NCR | Quezon City | 319501 | Holy Spirit National High School | QUEZON CITY |  | 1 | 12 | Completion of 4STY8CL | BATCH 1 | 3000000 |  | 2995001.99 | Completed | 1 | 2024-10-16 |  |  | 24OF0203 | 2024-05-17 | 2024-05-24 | 2024-05-06 | 2024-06-13 | 2024-06-19 | ALTIUS CONSTRUCTION AND TRADING |  | NC 2024
| NCR | Quezon City | 136549 | Raymundo Punongbayan ES | QUEZON CITY |  | 1 | 10 | 2STY10CL | GAA 17B | 40000000 |  |  | Ongoing | 0.15 | [10 empty] | Demolition Ongoing | NC 2024
| NCR | Quezon City | 136566 | 15th Avenue Elementary School | QUEZON CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39787695.03 | Ongoing | 0.25 | 2025-08-27 |  |  | 24-OG-0107 |  |  | 2024-03-04 |  | 2024-04-26 |  |  | NC 2024
| NCR | Quezon City | 305362 | Dr. Josefa Jara Martinez HS | QUEZON CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39680323.22 | Ongoing | 0.9 | 2025-12-04 |  |  | 24-OG-0106 |  |  | 2024-03-20 |  | 2024-04-26 | FRAMECON BUILDERS |  | NC 2024
| NCR | Quezon City | 319504 | Dona Rosario HS | QUEZON CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0 | [10 empty] | Ongoing Redesigning of Structural Foundation | NC 2024
| NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY |  | 1 |  | 2-Storey School Building | GAA 17B | 10000000 |  | 9868853.6 | Ongoing | 0.85 |  |  |  | 24OF0150 | 2024-03-27 | 2024-04-04 | 2024-04-24 | 2024-04-22 | 2024-04-29 | FRAMECON BUILDERS |  | NC 2024
| NCR | Quezon City | 360867 | Leandro Locsin Integrated School (SHS in Kaligayahan) | QUEZON CITY |  | 1 | 16 | Completion of 4STY16CL | BATCH 1 | 72000000 |  | 71538358.5 | Ongoing | 0.5 | 2025-05-15 |  |  | 24OF0176 | 2024-04-17 | 2024-04-25 | 2024-07-05 | 2024-05-15 | 2024-05-21 | RD8 BUILDERS CORPORATION |  | NC 2024
| NCR | Quezon City | 136536 | Nagkaisang Nayon ES | QUEZON CITY |  | 1 | 16 | Completion of 4STY16CL | BATCH 1 | 12000000 |  | 11820501.49 | Completed | 1 | 2024-11-16 |  |  | 24OF0173 | 2024-04-17 | 2024-04-25 | 2024-07-05 | 2024-05-15 | 2024-05-21 | R. ROSE CONSTRUCTION SERVICES |  | NC 2024
| NCR | Quezon City | 136525 | San Bartolome ES | QUEZON CITY |  | 1 | 16 | Completion of 4STY16CL | BATCH 1 | 5000000 |  | 4925150.5 | Completed | 1 | 2024-11-15 |  |  | 24OF0175 | 2024-04-17 | 2024-04-25 | 2024-07-05 | 2024-05-15 | 2024-05-21 | JOJEAN CONSTRUCTION AND DEVELOPMENT CORPORATION |  | NC 2024
| NCR | Quezon City | 136514 | Pasong Tamo ES | QUEZON CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0 | 2024-11-15 |  |  | 24OF0175 | 2024-04-17 | 2024-04-25 | 2024-07-05 | 2024-05-15 | 2024-05-21 | JOJEAN CONSTRUCTION AND DEVELOPMENT CORPORATION | With approved modification and Certificate of Coordination, waiting for approved demolition and revised plan | NC 2024
| NCR | Taguig City and Pateros | 500342 | Napindan Integrated School | TAGUIG CITY |  | 1 | 6 | 2STY6CL | GAA 17B | 40000000 |  | 38586354.32 | Ongoing | 0.25 | 2025-07-09 |  | P00875040LZ | 240B0520 | 2024-12-16 | 2024-12-26 | 2025-07-01 | 2025-03-03 | 2025-03-17 | GERCEL CONSTRUCTION & DEVELOPMENT | Phase 1 (2sty 6cl provision for 4sty 12cl) | NC 2024
| NCR | Valenzuela City |  | Pasolo National High School | CITY OF VALENZUELA |  | 1 | 12 | 4STY12CL (Phase 2) | GAA 17B | 20000000 |  | 19898880 | Ongoing | 1 | 2025-02-23 |  |  | 24OD0290 | 2024-10-07 | 2024-06-20 | 2024-10-07 | 2024-08-15 | 2024-07-29 | Nova Ventus Construction Inc. | Phase 2 | NC 2024
| NCR | Valenzuela City |  | Pasolo National High School | CITY OF VALENZUELA |  | 1 | 2 | 1STY2CL Phase 1 of 4STY12CL | GAA 17B | 20000000 |  | 19590117.48 | Ongoing | 0.15 | 2025-05-21 |  |  | 24OD0326 | 2024-12-18 | 2024-11-27 | 2024-12-18 | 2025-01-13 | 2024-12-23 | Nova Ventus Construction Inc. | Phase 1 (1st 2cl) | NC 2024
| NCR | Valenzuela City | 136812 | Roberta de Jesus Elementary School | CITY OF VALENZUELA |  | 1 | 8 | 4STY8CL | BATCH 1 | 29550000 |  | 29476125 | Ongoing | 0.45 | 2025-06-15 |  |  | 24OD0287 | 2024-04-06 | 2024-05-15 | 2024-04-06 | 2024-11-07 | 2024-07-29 | Diadema Construction and Enterprises Inc. |  | NC 2024
| NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA |  | 1 | 16 | 3STY12CL Phase 1 of 4STY16CL | BATCH 1 | 53050000 |  | 52783817.37 | Ongoing | 0.45 | 2025-07-13 |  |  | 24OD0296 | 2024-05-09 | 2024-08-16 | 2024-05-09 | 2024-11-10 | 2024-09-17 | Diadema Construction And Enterprises Inc. | Phase 1 | NC 2024
| NCR | Valenzuela City | 136827 | Serrano Elementary School | CITY OF VALENZUELA |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39796807.51 | Ongoing | 0.45 | 2025-06-15 |  |  | 24OD0294 | 2024-01-08 | 2024-10-07 | 2024-01-08 | 2024-06-09 | 2024-08-20 | Larsen-Dutcher Constractor Corporation |  | NC 2024

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.