## Sheet1
Region | Division | School ID | School Name | Municipality | Leg District | No. of Sites | Scope of Work | Total Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 4, 2025
Region I | Ilocos Sur | 100684 | Sta. Cruz CS | SANTA CRUZ | 2nd | 1 | PROPOSED TWO (2) - STOREY ALTERNATIVE LEARNING SYSTEM (ALS) BUILDING (22.50m x 9.50m) - with Roof Deck | 12871493.45 | Original: 9,322,239.10 Revised: Php 10,250,272.33 | ongoing | 0.8 | Original: 4/18/2025 Revised: 5/18/2025 |  | PB-015-2024 |  | October 2, 2024 | October 9, 2024 | October 22, 2024 | October 30, 2024 | November 20, 2024 | MA Tejada COnstruction | With additional works amounting to Php 928,033.23 due to revision of plans

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%