## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | Status as of July 4, 2025
REPAIR 2020 | Region I | Alaminos City | 101168 | Amandiego ES | CITY OF ALAMINOS | 1 | 1 | 8 | Repair of Classrooms | 3366258 | 1 | 3366257.28 | COMPLETED | 1 |  |  | INFRA-2020-01-01 | WAITING for sUB- SARO | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-30 | DPV BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region I | Alaminos City | 101184 | Maliga ES | CITY OF ALAMINOS | 1 | 1 | 7 | Repair of Classrooms | 2736298 | 1 | 2736298 | COMPLETED | 1 |  |  | INFRA-2020-01-02 | WAITING for sUB- SARO | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-30 | CLP BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | Batac City | 100091 | Baoa ES | CITY OF BATAC | 2 | 1 | 7 | Repair of Classrooms | 2571399 | 1 | 2551129.5 | COMPLETED | 1 |  |  |  |  | Nov 19,2019 | Nov 27,2019 | December 9,2019 |  |  | Abeian Construction | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | Batac City | 320803 | City of Batac National high school Payao | CITY OF BATAC | 2 | 1 | 6 | Repair of Classrooms | 2498035 | 1 | 2073396.55 | COMPLETED | 1 |  |  | BEFF-2018-11-0264 | PB-2018-11-010 | Nov 19,2019 | Nov 27,2019 | December 9,2019 | March 01,2019 | September 5,2019 | M.A. Tejada Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Batac City | 100083 | Parangopong ES | CITY OF BATAC | 2 | 1 | 9 | Repair of Classrooms | 3163364 | 1 | 3033698.62 | COMPLETED | 1 |  |  |  |  | Nov 19,2019 | Nov 27,2019 | December 9,2019 |  |  | Abeian Construction | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region I | Candon City | 100426 | Amguid Elementary School | CITY OF CANDON | 2 | 1 | 5 | Repair of Classrooms | 1587764 | 1 | 1587763.8499 | COMPLETED | 1 | 2020-12-30 | 2020-12-07 |  |  | 2019-11-26 | 2019-12-04 | 2019-12-16 | 2019-12-23 |  | M.A. TEJADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region I | Candon City | 100447 | Salvador Elementary School | CITY OF CANDON | 2 | 1 | 9 | Repair of Classrooms | 3077748 | 1 | 3077747.1659 | COMPLETED | 1 | 2020-12-30 | 2020-12-29 |  |  | 2019-11-26 | 2019-12-04 | 2019-12-16 | 2019-12-23 |  | MRK-SQUARE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region I | Candon City | 100449 | Tablac Elementary School | CITY OF CANDON | 2 | 1 | 10 | Repair of Classrooms | 3486773 | 1 | 3486772.7136 | COMPLETED | 1 | 2020-12-30 | 2020-12-29 |  |  | 2019-11-26 | 2019-12-04 | 2019-12-16 | 2019-12-23 |  | M.A. TEJADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY | 4 | 1 | 6 | Repair of Classrooms | 385994 | 1 | 385994 | COMPLETED | 1 | January 21, 2021 | December 18, 2020 |  |  |  | 2020-01-03 | 2020-01-17 | 2019-12-15 | 09/24/2020 | CHESTINAN CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Dagupan City | 102177 | Pantal ES | DAGUPAN CITY | 4 | 1 | 2 | Repair of Classrooms | 1368846 | 1 | 1368845.65 | COMPLETED | 1 | January 21, 2021 | December 18, 2020 |  |  | Nov 18-25, 2019 | 2019-11-25 | 2019-12-09 | 2019-12-15 | 09/24/2020 | ELGRAM TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Dagupan City | 500055 | Pugaro IS | DAGUPAN CITY | 4 | 1 | 2 | Repair of Classrooms | 1241291 | 1 | 1241290.83 | COMPLETED | 1 | January 21, 2021 | December 18, 2020 |  |  |  | 2020-01-03 | 2020-01-17 | 2019-12-15 | 09/24/2020 | CHESTINAN CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Dagupan City | 300370 | Salapingao National High School | DAGUPAN CITY | 4 | 1 | 2 | Repair of Classrooms | 231620 | 1 | 231619.77 | COMPLETED | 1 | January 21, 2021 | December 18, 2020 |  |  | Nov 18-25, 2019 | 2019-11-25 | 2019-12-09 | 2019-12-15 | 09/24/2020 | ELGRAM TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Dagupan City | 102153 | West CES II | DAGUPAN CITY | 4 | 1 | 4 | Repair of Classrooms | 2561838 | 1 | 2561837.42 | COMPLETED | 1 | January 21, 2021 | December 18, 2020 |  |  | Nov 18-25, 2019 | 2019-11-25 | 2019-12-09 | 2019-12-15 | 09/24/2020 | VIKING III BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Ilocos Norte | 100160 | Adams CES | ADAMS | 1 | 1 | 5 | Repair of Classrooms | 1846630 | 1 | 1846629.4665 | COMPLETED | 1 |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 2020-12-10 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region I | Ilocos Norte | 100004 | Ganagan Elementary School | BACARRA | 1 | 1 | 11 | Repair of Classrooms | 3535101 | 1 | 3530900.25 | COMPLETED | 1 |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 2020-12-10 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region I | Ilocos Norte | 100220 | Carasi ES | CARASI | 1 | 1 | 10 | Repair of Classrooms | 3022516 | 1 | 3022515.9108 | COMPLETED | 1 |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 10 14 2020 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region I | Ilocos Norte | 100218 | Boyboy ES | PIDDIG | 1 | 1 | 6 | Repair of Classrooms | 1998104 | 1 | 1998103.7322 | COMPLETED | 1 |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 10 14 2020 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Ilocos Norte | 100265 | Parang ES | SARRAT | 1 | 1 | 6 | Repair of Classrooms | 1994924 | 1 | 1994923.69 | COMPLETED | 1 |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 10 14 2020 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Ilocos Norte | 100295 | Dipilat ES | VINTAR | 1 | 1 | 3 | Repair of Classrooms | 981791 | 1 | 980829.4679 | COMPLETED | 1 |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 2020-09-10 | KRB Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Ilocos Norte | 100073 | Tabtabagan Elementary School | BANNA (ESPIRITU) | 2 | 1 | 9 | Repair of Classrooms | 3004849 | 1 | 3004207.94 | COMPLETED | 1 |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 2020-09-10 | KRB Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region I | Ilocos Norte | 100132 | Hilaria Salvatierra Mem. ES | DINGRAS | 2 | 1 | 11 | Repair of Classrooms | 3475934 | 1 | 3475933.45 | COMPLETED | 1 |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 2020-09-10 | KRB Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100504 | Maratudo ES | MAGSINGAL | 1 | 1 | 7 | Repair of Classrooms | 2619969 | 1 | 2619968.2 | COMPLETED | 1 | 2020-12-26 | 2021-01-18 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100591 | Asilang PS | SAN JUAN (LAPOG) | 1 | 1 | 2 | Repair of Classrooms | 900467 | 1 | 900466.01 | COMPLETED | 1 | 2020-11-26 | 2020-11-26 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100732 | Nagtupacan ES | SANTO DOMINGO | 1 | 1 | 10 | Repair of Classrooms | 3256297 | 1 | 3256296.68 | COMPLETED | 1 | 2021-01-25 | 2020-12-16 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100649 | Masadag ES | SINAIT | 1 | 1 | 9 | Repair of Classrooms | 2873937 | 1 | 2873936.84 | COMPLETED | 1 | 2020-12-26 | 2020-12-16 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MA TEJADA CONSTRUCTION | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100470 | Comillas North ES | CERVANTES | 2 | 1 | 9 | Repair of Classrooms | 3488144 | 1 | 3488143.73 | COMPLETED | 1 | 2021-01-26 | 2021-01-18 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-29 | JC Andulay Construction and Supply | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100578 | Mckinley PS | GALIMUYOD | 2 | 1 | 2 | Repair of Classrooms | 943222 | 1 |  | reverted | 0 |  |  | 6804205 | [7 empty] | Deferred | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100565 | Butarag PS | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 3 | Repair of Classrooms | 904445 | 1 | 900462.12 | COMPLETED | 1 | 2021-01-21 | 2021-01-20 | 7176296 |  | 2020-08-13 | 2020-08-20 | 2020-09-01 | 2020-09-08 | 2020-11-23 | CLEOFEL CONSTRUCTION | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100577 | Matue PS | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 3 | Repair of Classrooms | 1216449 | 1 | 1214939.32 | COMPLETED | 1 | 2021-01-21 | 2021-01-20 | 7176296 |  | 2020-08-13 | 2020-08-20 | 2020-09-01 | 2020-09-08 | 2020-11-23 | CLEOFEL CONSTRUCTION | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100535 | Cadacad ES | NAGBUKEL | 2 | 1 | 7 | Repair of Classrooms | 2489286 | 1 | 2489285.06 | COMPLETED | 1 | 2020-12-26 | 2020-12-15 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100486 | Patungcaleo ES | QUIRINO (ANGKAKI) | 2 | 1 | 8 | Repair of Classrooms | 3478514 | 1 | 3478513.65 | COMPLETED | 1 | 2021-01-26 | 2021-01-18 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-29 | JC Andulay Construction and Supply | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100556 | Arangin-Dinaratan ES | SALCEDO (BAUGEN) | 2 | 1 | 8 | Repair of Classrooms | 3137928 | 1 | 3137927.5 | COMPLETED | 1 | 2021-01-26 | 2021-01-25 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-29 | MRK-SQUARE CONSTRUCTION AND SUPPLY | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100675 | Padaoil Elementary School | SANTA CRUZ | 2 | 1 | 3 | Repair of Classrooms | 1320128 | 1 | 1252499.86 | COMPLETED | 1 | 2021-01-21 | 2021-01-04 | 7176296 |  | 2020-08-13 | 2020-08-20 | 2020-09-01 | 2020-09-08 | 2020-11-23 | CLEOFEL CONSTRUCTION | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100679 | Quinsoriano PS | SANTA CRUZ | 2 | 1 | 2 | Repair of Classrooms | 1027520 | 1 | 959056.72 | COMPLETED | 1 | 2021-01-06 | 2021-01-04 | 7176296 |  | 2020-08-13 | 2020-08-20 | 2020-09-01 | 2020-09-08 | 2020-11-23 | CLEOFEL CONSTRUCTION | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100704 | Butir Elementary School | SANTA MARIA | 2 | 1 | 4 | Repair of Classrooms | 1342677 | 1 | 1342676.31 | COMPLETED | 1 | 2020-11-26 | 2020-11-26 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100331 | Banga ES | SUGPON | 2 | 1 | 3 | Repair of Classrooms | 900466 | 1 | 900465.95 | COMPLETED | 1 | 2020-11-26 | 2021-01-04 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100333 | Calipayan ES | SUGPON | 2 | 1 | 2 | Repair of Classrooms | 683984 | 1 | 683983.23 | COMPLETED | 1 | 2020-11-12 | 2020-10-26 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-29 | MRK-SQUARE CONSTRUCTION AND SUPPLY | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100337 | DANAC ELEMENTARY SCHOOL | SUGPON | 2 | 1 | 7 | Repair of Classrooms | 2603072 | 1 | 2603071.82 | COMPLETED | 1 | 2021-01-26 | 2021-01-07 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-29 | MRK-SQUARE CONSTRUCTION AND SUPPLY | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | Ilocos Sur | 100755 | Lubnac ES | SUYO | 2 | 1 | 4 | Repair of Classrooms | 1711721 | 1 | 1711720.75 | COMPLETED | 1 | 2020-12-26 | 2021-01-15 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | La Union | 100846 | Bacnotan Central School | BACNOTAN | 1 | 1 | 10 | Repair of Classrooms | 3243011 | 1 | 3243010.91 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY | Constructors Risk ( Ongoing) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region I | La Union | 100873 | Apatut ES | BALAOAN | 1 | 1 | 9 | Repair of Classrooms | 3054363 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region I | La Union | 100878 | Butubut ES | BALAOAN | 1 | 1 | 15 | Repair of Classrooms | 4771100 | 1 | 4771099.33 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | M.O. DE GUZMAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region I | La Union | 300106 | Castor Concepcion MNHS | BALAOAN | 1 | 1 | 2 | Repair of Classrooms | 634777 | 1 | 634776.91 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | M.O. DE GUZMAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | La Union | 101051 | Lacong Elementary School | SAN GABRIEL | 1 | 1 | 6 | Repair of Classrooms | 2059883 | 1 | 2059882.73 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | LAV CONTRUCTION AND SUPPLY | Constructors Risk ( Ongoing) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | La Union | 151005 | Lacong ES-Annex | SAN GABRIEL | 1 | 1 | 3 | Repair of Classrooms | 1148808 | 1 | 1148807.34 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | LAV CONTRUCTION AND SUPPLY | Constructors Risk ( Ongoing) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | La Union | 101065 | Dasay ES | SAN JUAN | 1 | 1 | 11 | Repair of Classrooms | 3691340 | 1 | 3691339.82 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region I | La Union | 101072 | Sta. Rosa Elementary School | SAN JUAN | 1 | 1 | 12 | Repair of Classrooms | 3879143 | 1 | 3879142.31 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region I | La Union | 101080 | Liguay ES | SANTOL | 1 | 1 | 4 | Repair of Classrooms | 1575994 | 1 | 1575993.46 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | ARM ASIA ENGINEERING AND CONSTRUCTION | Constructors Risk ( Ongoing) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | La Union | 300141 | Santol Voc'l. HS - Liguay Annex | SANTOL | 1 | 1 | 6 | Repair of Classrooms | 2410644 | 1 | 2410643.02 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | ARM ASIA ENGINEERING AND CONSTRUCTION | Constructors Risk ( Ongoing) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | La Union | 101104 | Badang ES | SUDIPEN | 1 | 1 | 3 | Repair of Classrooms | 1133821 | 1 | 1133820.96 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | La Union | 101105 | Basig ES | SUDIPEN | 1 | 1 | 4 | Repair of Classrooms | 1691915 | 1 | 1691914.75 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | La Union | 101108 | Maliclico ES | SUDIPEN | 1 | 1 | 3 | Repair of Classrooms | 1133932 | 1 | 1133931.45 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | La Union | 100805 | Macalva ES | AGOO | 2 | 1 | 15 | Repair of Classrooms | 5287565 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region I | La Union | 100808 | San Vicente-San Agustin ES | AGOO | 2 | 1 | 9 | Repair of Classrooms | 3462718 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region I | La Union | 100819 | Aringay Central Elem.. School | ARINGAY | 2 | 1 | 15 | Repair of Classrooms | 5364289 | 1 | 5364288.66 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region I | La Union | 100826 | Immalog ES | ARINGAY | 2 | 1 | 5 | Repair of Classrooms | 1606932 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region I | La Union | 100838 | Sta. Lucia ES | ARINGAY | 2 | 1 | 8 | Repair of Classrooms | 3107956 | 1 | 3107955.3 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region I | La Union | 500350 | Baay Integrated School | BAGULIN | 2 | 1 | 3 | Repair of Classrooms | 1279165 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | La Union | 100868 | Tagudtud ES | BAGULIN | 2 | 1 | 5 | Repair of Classrooms | 1733523 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region I | La Union | 100912 | Bawanta ES | BAUANG | 2 | 1 | 9 | Repair of Classrooms | 3427303 | 1 | 3427302.76 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | VILLAR GEN. CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region I | La Union | 100919 | Bucayab Elementary School | BAUANG | 2 | 1 | 6 | Repair of Classrooms | 2200874 | 1 | 2200873.2 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | VILLAR GEN. CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | La Union | 100934 | Burgos CS | BURGOS | 2 | 1 | 12 | Repair of Classrooms | 3989948 | 1 | 3989947.65 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | VILLAR GEN. CONSTRUCTION & SUPPLY | Constructors Risk ( Ongoing) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region I | La Union | 100940 | Caba CES | CABA | 2 | 1 | 7 | Repair of Classrooms | 2985668 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | La Union | 100989 | Mamat-ing Sur ES | NAGUILIAN | 2 | 1 | 11 | Repair of Classrooms | 3859499 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region I | La Union | 300108 | Cuenca National High School | PUGO | 2 | 1 | 8 | Repair of Classrooms | 2867105 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region I | La Union | 101004 | Tavora ES | PUGO | 2 | 1 | 3 | Repair of Classrooms | 976327 | 1 | 976326.62 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | VILLAR GEN. CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | La Union | 101095 | Cupang ES | SANTO TOMAS | 2 | 1 | 9 | Repair of Classrooms | 2753850 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region I | La Union | 101103 | Ubagan Elementary School | SANTO TOMAS | 2 | 1 | 3 | Repair of Classrooms | 1216450 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Laoag City | 102193 | A. P. Santos ES (SPED Center) | LAOAG CITY (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1434851 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Laoag City | 102206 | Barit Elementary School | LAOAG CITY (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1321210 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Laoag City | 102197 | Cataban Elementary School | LAOAG CITY (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2438380 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101142 | Macaboboni ES | AGNO | 1 | 1 | 4 | Repair of Classrooms | 1781046 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 300250 | San Jose NHS | ANDA | 1 | 1 | 14 | Repair of Classrooms | 4633352 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 300192 | Dacap Norte NHS | BANI | 1 | 1 | 10 | Repair of Classrooms | 3706231 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101325 | BASING ES | BINMALEY | 1 | 1 | 1 | Repair of Classroom | 3021989 | 1 | 3011876.69 | COMPLETED | 1 | [9 empty] | Chestinan Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101346 | CATUNGI ES | BOLINAO | 1 | 1 | 1 | Repair of Classroom | 1746265 | 1 | 1735786.54 | COMPLETED | 1 | [9 empty] | ABC East Multi Builders and Traders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 500615 | Liwa-Liwa Integrated School | BOLINAO | 1 | 1 | 3 | Repair of Classrooms | 948931 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 300249 | Sampaloc NHS | BOLINAO | 1 | 1 | 7 | Repair of Classrooms | 2069244 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 300268 | Zaragoza NHS | BOLINAO | 1 | 1 | 6 | Repair of Classrooms | 2268927 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101382 | SAN FRANCISCO ES | BUGALLON | 1 | 1 | 1 | Repair of Classroom | 2047002 | 1 | 2016883.62 | COMPLETED | 1 | [9 empty] | Chestinan Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101401 | Burgos Central School | BURGOS | 1 | 1 | 6 | Repair of Classrooms and Construction of Fence | 3781378 | 1 | 3033987.04 | COMPLETED | 1 | [9 empty] | Elmuel Jay Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 300179 | Burgos NHS | BURGOS | 1 | 1 | 7 | Repair of Classrooms and Construction of Fence | 3744940 | 1 | 3253738.61 | COMPLETED | 1 | [9 empty] | Manimeld's Construction and Iron Works |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101403 | Cabongaoan ES | BURGOS | 1 | 1 | 1 | Repair and Construction of Fence | 400000 | 1 | 395110.89 | COMPLETED | 1 | [9 empty] | Manimeld's Construction and Iron Works |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101407 | Don Matias ES | BURGOS | 1 | 1 | 1 | Repair and Construction of Fence | 480000 | 1 | 474974.86 | COMPLETED | 1 | [9 empty] | Manimeld's Construction and Iron Works |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101409 | Papallasen ES | BURGOS | 1 | 1 | 1 | Repair and Construction of Fence | 600000 | 1 | 594931 | COMPLETED | 1 | [9 empty] | Elmuel Jay Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101454 | MALACAPAS ES | DASOL | 1 | 1 | 1 | Repair of Classroom | 2163366 | 1 | 1557621.1 | COMPLETED | 1 | [9 empty] | ABC East Multi Builders and Traders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101455 | TAMBOBONG ES | DASOL | 1 | 1 | 1 | Repair of Classroom | 1728314 | 1 | 1716214.56 | COMPLETED | 1 | [9 empty] | ABC East Multi Builders and Traders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101460 | Bamban Sur ES | INFANTA | 1 | 1 | 4 | Repair of Classrooms | 1850727 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101465 | Maringindingin ES | INFANTA | 1 | 1 | 3 | Repair of Classrooms | 1102421 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101485 | MATALAVA ES | LINGAYEN | 1 | 1 | 1 | Repair of Classroom | 2709003 | 1 | 2693876.94 | COMPLETED | 1 | [9 empty] | CWME Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101516 | CABANAETAN ES | MABINI | 1 | 1 | 1 | Repair of Classroom | 2063910 | 1 | 1762347.81 | COMPLETED | 1 | [9 empty] | WM Salayog Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101526 | San Pedro ES | MABINI | 1 | 1 | 7 | Repair of Classrooms | 2333356 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101530 | Villacorta ES | MABINI | 1 | 1 | 4 | Repair of Classrooms | 1630902 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101332 | MANAT ES | BINMALEY | 2 | 1 | 13 | Repair of Classrooms | 6026318 | 1 | 5975677.44 | COMPLETED | 1 | [9 empty] | Chestinan Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101334 | NAGUILAYAN ES | BINMALEY | 2 | 1 | 18 | Repair of Classrooms | 8344132 | 1 | 8293925.72 | COMPLETED | 1 | [9 empty] | Chestinan Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101322 | SAN ISIDRO SUR ES | BINMALEY | 2 | 1 | 11 | Repair of Classrooms | 5099192 | 1 | 5054675.63 | COMPLETED | 1 | [9 empty] | Szcon Builders Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101336 | STA. ROSA ES | BINMALEY | 2 | 1 | 5 | Repair of Classrooms | 2172951 | 1 | 2160486.45 | COMPLETED | 1 | [9 empty] | Szcon Builders Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101613 | Tagac ES | MANGATAREM | 2 | 1 | 6 | Repair of Classrooms | 1930252 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101266 | Bani ES | BAYAMBANG | 3 | 1 | 3 | Repair of Classrooms | 550304 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101275 | Macayocayo ES | BAYAMBANG | 3 | 1 | 9 | Repair of Classrooms | 2906423 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101429 | Buenlag CS | CALASIAO | 3 | 1 | 3 | Repair of Classrooms | 812667 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101422 | Calasiao Central School | CALASIAO | 3 | 1 | 8 | Repair of Classrooms | 2264869 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101437 | Mancup ES | CALASIAO | 3 | 1 | 7 | Repair of Classrooms | 1968215 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101531 | Abonagan - Bobon Elementary School | MALASIQUI | 3 | 1 | 3 | Repair of Classrooms | 810225 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101544 | Lokeb Sur ES | MALASIQUI | 3 | 1 | 4 | Repair of Classrooms | 1277066 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101620 | Lambayan ES | MAPANDAN | 3 | 1 | 6 | Repair of Classrooms | 1632176 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101796 | Doña Consolacion Sta. Maria ES | MANAOAG | 4 | 1 | 6 | Repair of Classrooms | 2163904 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101806 | San Ramon-Mermer ES | MANAOAG | 4 | 1 | 2 | Repair of Classrooms | 734513 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102127 | Doña Felisa Navarro ES | MANGALDAN | 4 | 1 | 4 | Repair of Classrooms | 1497824 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101829 | Talogtog ES | MANGALDAN | 4 | 1 | 8 | Repair of Classrooms | 2329972 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101926 | Lekep ES | SAN FABIAN | 4 | 1 | 2 | Repair of Classrooms | 686038 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101937 | Macayug ES | SAN JACINTO | 4 | 1 | 6 | Repair of Classrooms | 2302996 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101755 | Villanueva ES | BAUTISTA | 5 | 1 | 4 | Repair of Classrooms | 1128326 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101760 | Casantiagoan ES | BINALONAN | 5 | 1 | 4 | Repair of Classrooms | 1483682 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101764 | Moreno ES | BINALONAN | 5 | 1 | 4 | Repair of Classrooms | 1299611 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101777 | Tabuyoc ES | BINALONAN | 5 | 1 | 2 | Repair of Classrooms | 469201 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101781 | Cabu-Cala ES | LAOAC | 5 | 1 | 3 | Repair of Classrooms | 1137460 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101789 | Limos-Turko ES | LAOAC | 5 | 1 | 5 | Repair of Classrooms | 1750659 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101778 | Quevedo-Anisca ES | LAOAC | 5 | 1 | 3 | Repair of Classrooms | 1145381 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101859 | Palguyod Elementary School | POZORRUBIO | 5 | 1 | 6 | Repair of Classrooms | 2019003 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102017 | Artacho ES | SISON | 5 | 1 | 5 | Repair of Classrooms | 1723302 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102128 | Bacag Central School | VILLASIS | 5 | 1 | 5 | Repair of Classrooms | 1865153 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101713 | Carosucan Sur ES | ASINGAN | 6 | 1 | 2 | Repair of Classrooms | 1051679 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101724 | Don Teodorico Bauzon ES | ASINGAN | 6 | 1 | 6 | Repair of Classrooms | 2571721 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101725 | Palaris ES | ASINGAN | 6 | 1 | 6 | Repair of Classrooms | 2717755 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101717 | Sobol ES | ASINGAN | 6 | 1 | 3 | Repair of Classrooms | 1330034 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101728 | Toboy ES | ASINGAN | 6 | 1 | 2 | Repair of Classrooms | 874202 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101845 | San Miguel ES | NATIVIDAD | 6 | 1 | 4 | Repair of Classrooms | 1821560 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101898 | San Angel ES | ROSALES | 6 | 1 | 2 | Repair of Classrooms | 851953 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101900 | San Luis ES | ROSALES | 6 | 1 | 2 | Repair of Classrooms | 933671 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101953 | Juan C. Laya Central School SPED Center | SAN MANUEL | 6 | 1 | 7 | Repair of Classrooms | 2660607 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101956 | Lomboy Elementary School | SAN MANUEL | 6 | 1 | 2 | Repair of Classrooms | 848113 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101969 | Cabayawasan ES | SAN NICOLAS | 6 | 1 | 1 | Repair of Classroom | 599759 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101983 | Cabitnongan ES | SAN NICOLAS | 6 | 1 | 5 | Repair of Classrooms | 2216301 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101987 | East Central School | SAN NICOLAS | 6 | 1 | 4 | Repair of Classrooms | 1609999 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101995 | San Antonio West ES | SAN NICOLAS | 6 | 1 | 7 | Repair of Classrooms | 3056791 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101997 | Sta. Maria ES | SAN NICOLAS | 6 | 1 | 3 | Repair of Classrooms | 1332636 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102043 | Cal-litang ES | SANTA MARIA | 6 | 1 | 3 | Repair of Classrooms | 1153139 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102048 | Pugot Elementary School | SANTA MARIA | 6 | 1 | 2 | Repair of Classrooms | 831671 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102073 | Panganiban CES | TAYUG | 6 | 1 | 2 | Repair of Classrooms | 935881 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102078 | Annam ES | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 957513 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102098 | Carosalesan ES | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 976842 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102100 | Concepcion ES | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 974826 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102084 | Evangelista ES | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 962203 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102088 | Lubong Elementary School | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 967736 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | San Carlos City | 102243 | Gamata Elementary School | SAN CARLOS CITY | 3 | 1 | 2 | Repair of Classrooms | 796101 | 1 |  | COMPLETED | 1 | [10 empty] | Waiting for Saro | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | San Carlos City | 102231 | Lilimasan Elementary School | SAN CARLOS CITY | 3 | 1 | 8 | Repair of Classrooms | 3035305 | 1 |  | COMPLETED | 1 | [10 empty] | Waiting for Saro | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region I | San Carlos City | 300387 | Salinap NHS | SAN CARLOS CITY | 3 | 1 | 6 | Repair of Classrooms | 2230765 | 1 |  | COMPLETED | 1 | [10 empty] | Waiting for Saro | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | San Carlos City | 102265 | Turac Elementary School | SAN CARLOS CITY | 3 | 1 | 14 | Repair of Classrooms | 3352672 | 1 |  | COMPLETED | 1 | [10 empty] | Waiting for Saro | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region I | San Fernando City | 300116 | Dr. Quintin Balcita Sr. NHS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 11 | Repair of Classrooms | 4801438 | 1 | 4801437.28 | COMPLETED | 1 |  |  | CSFLU-INFRA-015-2019 |  | 2019-11-19 | 2019-11-26 | 2019-12-09 | 2019-12-16 |  | JL DE GUZMAN ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region I | San Fernando City | 300126 | Pao National High School | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 8 | Repair of Classrooms | 3103862 | 1 | 3103861.06 | COMPLETED | 1 |  |  | CSFLU-INFRA-016-2019 |  | 2019-11-19 | 2019-11-26 | 2019-12-09 | 2019-12-16 |  | DPV BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region I | Urdaneta City | 102286 | Anonas East ES | CITY OF URDANETA | 5 | 1 | 1 | Repair of Classroom | 272477 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region I | Urdaneta City | 102268 | Bactad ComS | CITY OF URDANETA | 5 | 1 | 2 | Repair of Classrooms | 660130 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region I | Urdaneta City | 102295 | Don Amadeo Perez, Sr. MECS - West | CITY OF URDANETA | 5 | 1 | 7 | Repair of Classrooms | 1287396 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region I | Urdaneta City | 102308 | Tabuyoc ES | CITY OF URDANETA | 5 | 1 | 4 | Repair of Classrooms | 999203 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region I | Vigan City | 100790 | Gov. Evaristo Singson II MES | CITY OF VIGAN (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2009192 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region I | Vigan City | 100791 | Jose Singson ES | CITY OF VIGAN (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2113088 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region I | Vigan City | 100794 | Pantay Elementary School | CITY OF VIGAN (Capital) | 1 | 1 | 10 | Repair of Classrooms | 2015147 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region I | Alaminos City | 101195 | San Roque ES | CITY OF ALAMINOS | 1 | 1 | 7 | Repair of Classrooms | 2930407.7 | 1 | 2917415.1 | COMPLETED | 1 | 2021-11-12 | 2021-10-25 | INFRA-BEFF-CY-2021-08-02 | INFRA-BEFF-CY-2021-08-02 | JULY 9-16, 2021 | 2021-07-15 | 2021-07-29 | 2021-08-04 | 2021-08-16 | DPV BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region I | Batac City | 100082 | P. Q. Pimentel ES | CITY OF BATAC | 2 | 1 | 6 | Repair of Classrooms | 2930501.36 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region I | Candon City | 100432 | Bugnay Elementary School | CITY OF CANDON | 2 | 1 | 7 | Repair of Classrooms | 2893673.92 | 1 | 2873551.02 | COMPLETED | 1 | [6 empty] | 2021-06-28 |  | 2021-07-28 | MA TEJADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region I | Dagupan City | 102162 | BLISS ES | DAGUPAN CITY | 4 | 1 | 3 | Repair of classrooms | 2053774.07 | 1 | 2049096.68 | COMPLETED | 1 |  |  |  |  | July 15-Aug 4, 2021 | July 23, 2021 | Aug 4, 2021 |  |  | VIKING III BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region I | Dagupan City | 102158 | Lasip Grande ES | DAGUPAN CITY | 4 | 1 | 3 | Repair of classrooms | 2053774.07 | 1 | 2048566.46 | COMPLETED | 1 |  |  |  |  | July 15-Aug 4, 2021 | July 23, 2021 | Aug 4, 2021 |  |  | ASS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region I | Ilocos Norte | 100228 | Piddig South CES | PIDDIG | 1 | 1 | 6 | Repair of Classrooms | 2599235.92 | 1 | 2589397.4039 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region I | Ilocos Norte | 100306 | Visaya ES | VINTAR | 1 | 1 | 6 | Repair of Classrooms | 3418730.85 | 1 | 2796516.9313 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region I | Ilocos Norte | 100071 | Quiaoit Memorial ES | BANNA (ESPIRITU) | 2 | 1 | 5 | Repair of Classrooms | 2475545.66 | 1 | 2018708.2516 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region I | Ilocos Norte | 100144 | Elizabeth ES | MARCOS | 2 | 1 | 9 | Repair of Classrooms | 5107009.86 | 1 | 5086958.2927 | COMPLETED | 1 | 2022-10-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region I | Ilocos Sur | 100725 | Calay-ab ES | SANTO DOMINGO | 1 | 1 | 10 | Repair of Classrooms | 4840360.43 | 1 | 3953523.63 | COMPLETED | 1 | 2021-12-10 | 2021-12-10 | 7807196 |  | 2021-06-30 | 2021-07-07 | 2021-07-22 | 2021-08-02 | 2021-08-13 | MA TEJADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region I | Ilocos Sur | 100329 | Apang ES | ALILEM | 2 | 1 | 5 | Repair of Classrooms | 2616874.49 | 1 | 2190525.61 | COMPLETED | 1 | 2021-11-17 | 2021-11-17 | 7807196 |  | 2021-06-30 | 2021-07-07 | 2021-07-22 | 2021-08-02 | 2021-08-20 | MRK-SQUARE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region I | Ilocos Sur | 100334 | Caoayan Elementary School | SUGPON | 2 | 1 | 4 | Repair of Classrooms | 2080224.67 | 1 | 1738402.32 | COMPLETED | 1 | 2021-11-17 | 2021-11-17 | 7807196 |  | 2021-06-30 | 2021-07-07 | 2021-07-22 | 2021-08-02 | 2021-08-20 | MRK-SQUARE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region I | La Union | 100885 | Pantar ES | BALAOAN | 1 | 1 | 12 | Repair of Classrooms | 5079914.98 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region I | La Union | 100964 | Oaqui ES | LUNA | 1 | 1 | 12 | Repair of Classrooms | 4555595.06 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region I | La Union | 101074 | Taboc ES | SAN JUAN | 1 | 1 | 13 | Repair of Classrooms | 6034970.66 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2021 | Region I | La Union | 101106 | Castro ES | SUDIPEN | 1 | 1 | 7 | Repair of Classrooms | 2760188.87 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region I | La Union | 100837 | Sta. Cecilia ES | ARINGAY | 2 | 1 | 9 | Repair of Classrooms | 4341954.42 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region I | La Union | 100861 | Cambaly Elementary School | BAGULIN | 2 | 1 | 6 | Repair of Classrooms | 2392239.02 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region I | La Union | 100915 | PUGO ELEMENTARY SCHOOL | BAUANG | 2 | 1 | 9 | Repair of Classrooms | 3589404.06 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region I | La Union | 100933 | Bilis ES | BURGOS | 2 | 1 | 4 | Repair of Classrooms | 1742137.63 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region I | La Union | 100945 | San Cornelio ES | CABA | 2 | 1 | 5 | Repair of Classrooms | 2235770.77 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region I | La Union | 101007 | Cadumanian ES | ROSARIO | 2 | 1 | 7 | Repair of Classrooms | 2845560.02 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region I | La Union | 101014 | Marcos Elementary School | ROSARIO | 2 | 1 | 8 | Repair of Classrooms | 2482537.12 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region I | Laoag City | 102200 | Navotas Elementary School | LAOAG CITY (Capital) | 1 | 1 | 2 | Repair of Classrooms | 1090679.4 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region I | Laoag City | 102201 | Pila Elementary School | LAOAG CITY (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1955641.96 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101135 | Aroas ES | AGNO | 1 | 1 | 8 | Repair of Classrooms | 2808060.82 | 1 | 2162080.59 | COMPLETED | 1 | [9 empty] | Elmuel Jay Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 500608 | BANI EAST INTEGRATED SCHOOL | BANI | 1 | 1 | 7 | Repair of classrooms | 3000000 | 1 | 2967912.84 | COMPLETED | 1 | [9 empty] | CLP Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101363 | Samang Elementary School | BOLINAO | 1 | 1 | 5 | Repair of Classrooms | 2216027.06 | 1 | 2211235.22 | COMPLETED | 1 | [9 empty] | Elgram Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101406 | Don Antonio Bonilla Mem. ES | BURGOS | 1 | 1 | 1 | Repair of Classrooms & Fence | 2254424.72 | 1 | 2244516.1 | COMPLETED | 1 | [9 empty] | ILS Power Engineering and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101411 | San Miguel ES | BURGOS | 1 | 1 | 1 | Repair of Classrooms & Fence | 1174242.24 | 1 | 1156860.08 | COMPLETED | 1 | [9 empty] | Elmuel Jay Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 500441 | Dasol Integrated School | DASOL | 1 | 1 | 7 | Repair of classrooms | 3000000 | 1 | 2995097.98 | COMPLETED | 1 | [9 empty] | Elgram Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 500609 | Barlo Integrated School | MABINI | 1 | 1 | 8 | Repair of Classrooms | 3500000 | 1 | 3483630.7 | COMPLETED | 1 | [9 empty] | Angelina T. Dizon Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 300180 | Cabanaetan NHS | MABINI | 1 | 1 | 11 | Repair of classrooms | 5108210.04 | 1 | 5100197.102 | COMPLETED | 1 | [9 empty] | DPV BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101523 | Mabini CS | MABINI | 1 | 1 | 10 | Repair of Classrooms | 3566269.42 | 1 | 3555928.78 | COMPLETED | 1 | [9 empty] | Casipit Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101327 | Camaley CS | BINMALEY | 2 | 1 | 3 | Repair of Classrooms | 1273542.02 | 1 | 1243526.82 | COMPLETED | 1 | [9 empty] | Rockwell Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101584 | Linmansangan ES | MANGATAREM | 2 | 1 | 8 | Repair of Classrooms | 2676608.6 | 1 | 2140420 | COMPLETED | 1 | 2022-11-30 | [8 empty] | CLP Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101682 | Duplac ES | URBIZTONDO | 2 | 1 | 5 | Repair of Classrooms | 1995473.57 | 1 | 1992410.41 | COMPLETED | 1 | [9 empty] | RC Gabriel Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 300247 | Real National High School | URBIZTONDO | 2 | 1 | 10 | Repair of Classrooms | 3442214.96 | 1 | 3392183.9 | COMPLETED | 1 | [9 empty] | Rockwell Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101278 | Nalsian ES | BAYAMBANG | 3 | 1 | 10 | Repair of Classrooms | 3484782.67 | 1 | 2508542.4 | COMPLETED | 1 | [9 empty] | MN Coloma Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101556 | Bakitiw ES | MALASIQUI | 3 | 1 | 3 | Repair of Classrooms | 1153088.69 | 1 | 808171.17 | COMPLETED | 1 | [9 empty] | MN Coloma Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 300265 | Torres NHS | MAPANDAN | 3 | 1 | 5 | Repair of Classrooms | 2444057.58 | 1 | 2032424.25 | COMPLETED | 1 | [9 empty] | Elmuel Jay Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101639 | Banaoang Central School | SANTA BARBARA | 3 | 1 | 29 | Repair of Classrooms | 3489897.45 | 1 | 2556231.41 | COMPLETED | 1 | [9 empty] | MN Coloma Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 29 | 0 | 0
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101647 | Maticmatic ES | SANTA BARBARA | 3 | 1 | 16 | Repair of Classrooms | 3155828.82 | 1 | 2208832.24 | COMPLETED | 1 | [9 empty] | MN Coloma Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101943 | Sta. Maria ES | SAN JACINTO | 4 | 1 | 15 | Repair of Classrooms | 8578901.99 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101696 | Atainan ES | ALCALA | 5 | 1 | 11 | Repair of Classrooms | 7839599.74 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101698 | Gualsic ES | ALCALA | 5 | 1 | 13 | Repair of Classrooms | 8267640.65 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101708 | South Central School | ALCALA | 5 | 1 | 6 | Repair of Classrooms | 3589345.23 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101770 | Balisa ES | BINALONAN | 5 | 1 | 6 | Repair of Classrooms | 3488516.86 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101772 | Bued ES | BINALONAN | 5 | 1 | 9 | Repair of Classrooms | 5326521.83 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101773 | Linmansangan ES | BINALONAN | 5 | 1 | 14 | Repair of Classrooms | 9820165.32 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101779 | Botigue ES | LAOAC | 5 | 1 | 3 | Repair of Classrooms | 1919125.89 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101784 | Don Rufino Tabayoyong CS | LAOAC | 5 | 1 | 7 | Repair of Classrooms | 1860998.89 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 300275 | Antonio P. Villar National High School | SANTO TOMAS | 5 | 1 | 55 | Repair of Classrooms | 25000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 55 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102057 | Doña Aurea ES | SANTO TOMAS | 5 | 1 | 19 | Repair of Classrooms | 15000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101722 | Bobonan Elementary School | ASINGAN | 6 | 1 | 2 | Repair of Classrooms | 1873121.68 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101728 | Toboy ES | ASINGAN | 6 | 1 | 4 | Repair of Classrooms | 4000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101745 | Don Francisco D. Toliao ES | BALUNGAO | 6 | 1 | 2 | Repair of Classrooms | 1873121.68 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101742 | San Leon ES | BALUNGAO | 6 | 1 | 3 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101832 | Batchelor Elementary School | NATIVIDAD | 6 | 1 | 4 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 300331 | Natividad NHS | NATIVIDAD | 6 | 1 | 3 | Repair of Classrooms | 2000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101846 | San Narciso Norte ES | NATIVIDAD | 6 | 1 | 2 | Repair of Classrooms | 1328655.61 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101878 | Carmen Elementary School | ROSALES | 6 | 1 | 3 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101899 | San Antonio ES | ROSALES | 6 | 1 | 2 | Repair of Classrooms | 1330763.74 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101886 | Tomana Elementary School SPED Center | ROSALES | 6 | 1 | 2 | Repair of Classrooms | 1891736.23 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101950 | Cabacaraan ES | SAN MANUEL | 6 | 1 | 3 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101991 | Nining ES | SAN NICOLAS | 6 | 1 | 1 | Repair of Classroom | 694127.88 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101997 | Sta. Maria ES | SAN NICOLAS | 6 | 1 | 6 | Repair of Classrooms | 6057408.38 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102004 | Don Luis Domingo Sr. ES | SAN QUINTIN | 6 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102049 | Samon Elementary School | SANTA MARIA | 6 | 1 | 4 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102055 | West Central School | SANTA MARIA | 6 | 1 | 2 | Repair of Classrooms | 1884545.91 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102061 | Agno Elementary School | TAYUG | 6 | 1 | 6 | Repair of Classrooms | 4000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102076 | Toketec ES | TAYUG | 6 | 1 | 2 | Repair of Classrooms | 1878557.34 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102079 | Barat ES | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 1328655.61 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102099 | Casilan ES | UMINGAN | 6 | 1 | 3 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102100 | Concepcion ES | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 1330763.74 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102088 | Lubong Elementary School | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 1324272.75 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102093 | Umingan CES | UMINGAN | 6 | 1 | 7 | Repair of Classrooms | 6295323.45 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region I | San Carlos City | 102224 | Quintong Elementary School | SAN CARLOS CITY | 3 | 1 | 5 | Repair of classrooms | 2755453.72 | 1 | 2,218,140.24. | COMPLETED | 1 | DEC. 21,2021 |  |  |  |  | AUGUST 12,2021 | AUGUST 31,2021 | SEPT. 8,2021 | SEPT.22,2021 | RGP SUCCESS VENTURES INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region I | San Fernando City | 101035 | Sevilla Elementary School | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 13 | Repair of classrooms | 6472844.79 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2021 | Region I | Urdaneta City | 300403 | Mariano Q. Umipig NHS | CITY OF URDANETA | 5 | 1 | 5 | Repair of Classrooms | 2973693.33 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region I | Vigan City | 100789 | Capangpangan ES | CITY OF VIGAN (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2852635.5 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region I | Ilocos Norte | 100160 | Adams CES | ADAMS | 1 | 1 | 3 | Repair of Classrooms | 1060794.6 | 1 | 972916.7355 | COMPLETED | 1 | October 2022 |  | PB-002-2022-1 |  | 11 13 2019 | 11 21 2019 | 2022-09-03 | 12 13 2019 | 2020-12-10 | ELOCIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region I | Ilocos Norte | 100107 | Paayas ES | BURGOS | 1 | 1 | 2 | Repair of Classrooms | 1319836.02 | 1 | 917631.5568 | COMPLETED | 1 | October 2022 |  | PB-002-2022-3 |  |  |  | 2022-09-03 |  |  | ELOCIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region I | Ilocos Norte | 100233 | Virbira-Angset ES | CARASI | 1 | 1 | 2 | Repair of Classrooms | 1147833.65 | 1 | 1121874.05 | COMPLETED | 1 | October 2022 |  | PB-002-2022-4 |  |  |  | 2022-09-03 |  |  | ELOCIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region I | Ilocos Norte | 100055 | San Isidro Elementary School | DUMALNEG | 1 | 1 | 3 | Repair of Classrooms | 1090731.29 | 1 | 1020136.54 | COMPLETED | 1 | October 2022 |  | PB-002-2022-2 |  |  |  | 2022-09-03 |  |  | ELOCIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region I | Ilocos Sur | 100616 | San Sebastian Elementary School | SAN VICENTE | 1 | 1 | 6 | Repair of Classrooms | 2202603.9 | 1 |  | COMPLETED | 1 |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | MA Tejada Construction | For award. Waiting for release of Sub-ARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region I | Ilocos Sur | 100659 | Cabuloan ES | SANTA CATALINA | 1 | 1 | 6 | Repair of Classrooms | 2732823.02 | 1 |  | COMPLETED | 1 |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | MA Tejada Construction | For award. Waiting for release of Sub-ARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region I | Ilocos Sur | 100345 | Tangilig ES | SUGPON | 1 | 1 | 3 | Repair of Classrooms | 1749456.98 | 1 |  | COMPLETED | 1 |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | MRK-Square Construction & Supply | For award. Waiting for release of Sub-ARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region I | Ilocos Sur | 300054 | Lidlidda National High School | LIDLIDDA | 2 | 1 | 4 | Repair of Classrooms | 1936258.06 | 1 |  | COMPLETED | 1 |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | MA Tejada Construction | For award. Waiting for release of Sub-ARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region I | Ilocos Sur | 100539 | Lapting ES | NAGBUKEL | 2 | 1 | 5 | Repair of Classrooms | 1610201.01 | 1 |  | COMPLETED | 1 |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | MA Tejada Construction | For award. Waiting for release of Sub-ARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region I | Ilocos Sur | 100386 | Ansad ES | SAN ESTEBAN | 2 | 1 | 2 | Repair of Classrooms | 1181156.93 | 1 |  | COMPLETED | 1 |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | Cleofel Construction | For award. Waiting for release of Sub-ARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region I | Ilocos Sur | 300079 | Sigay National High School | SIGAY | 2 | 1 | 3 | Repair of Classrooms | 1324194.15 | 1 |  | COMPLETED | 1 |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | Maple Leaf Engineering & Construction | For award. Waiting for release of Sub-ARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region I | La Union | 100858 | Alibangsay ES | BAGULIN | 2 | 1 | 5 | Repair of Classrooms | 1932199.32 | 1 | 1562163.94 | COMPLETED | 1 | 2022-09-08 |  |  |  | 2022-03-15 | 2022-03-23 | 2022-04-04 | 2022-04-12 | 2022-06-10 | LAV CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region I | La Union | 100938 | Tumapoc ES | BURGOS | 2 | 1 | 4 | Repair of Classrooms | 2110104.53 | 1 | 1809225.65 | COMPLETED | 1 | 2022-09-08 |  |  |  | 2022-03-15 | 2022-03-23 | 2022-04-04 | 2022-04-12 | 2022-06-10 | LAV CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region I | La Union | 500601 | Saytan Integrated School | PUGO | 2 | 1 | 11 | Repair of Classrooms | 5923501.12 | 1 | 5880521.45 | COMPLETED | 1 | 2022-09-08 |  |  |  | 2022-03-15 | 2022-03-23 | 2022-04-04 | 2022-04-12 | 2022-06-10 | EE MADAYAG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101400 | Anapao ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 394061.1 | 2 | 362840.2972 | COMPLETED | 1 | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | Chestinan Construction Corporation | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101401 | Burgos Central School | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 1198077.02 | 2 | 1108514.0994 | COMPLETED | 1 | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | Chestinan Construction Corporation | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 300179 | Burgos NHS | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 1055914.95 | 2 | 532489.6849 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101402 | Cabaruan ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 771100.79 | 2 | 469196.065 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101403 | Cabongaoan ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 676606.66 | 2 | 405792.7316 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101404 | Concordia ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 582072.66 | 2 | 274245.6633 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101405 | Don Antonio Bonilla ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 394061.1 | 2 | 309879.845 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | CLP Builders | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101406 | Don Antonio Bonilla Mem. ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 319291.31 | 2 | 767911.13 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | CLP Builders | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101407 | Don Matias ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 931312.42 | 2 | 661243.7004 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101408 | Ilio-Ilio ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 960761.74 | 2 | 469196.065 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 300239 | Jose Rivera Bonsay NHS (Pogoruac NHS) | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 771100.79 | 2 | 469196.065 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101409 | Papallasen ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 676606.66 | 2 | 535606.41 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | CLP Builders | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101410 | Poguruac ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 676606.66 | 2 | 673465.52 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | JFM Altitude Construction Corporation | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101411 | San Miguel ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 582072.66 | 2 | 610730.25 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | JFM Altitude Construction Corporation | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 500620 | Sapa Grande Integrated School | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 771100.79 | 2 | 1052773.81 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | JFM Altitude Construction Corporation | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101413 | Sapa Pequeña ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 676606.66 | 2 | 767959.65 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | JFM Altitude Construction Corporation | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101414 | Tambacan ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 613871.39 | 2 | 767959.65 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | JFM Altitude Construction Corporation | with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101224 | Ambabaay ES | BANI | 1st | 1 | 3 | Repair of Classrooms & Fence (Additional fromProject Modification) | 1390688.55 | 2 | 2808327.51 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | Chestinan Construction Corporation | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101243 | Ranao ES | BANI | 1st | 1 | 8 | Repair of Classrooms & Fence (Additional fromProject Modification) | 2828502.8 | 2 | 1358135.87 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | CLP Builders | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 500614 | Infanta Integrated School | INFANTA | 1st | 1 | 1 | Repair of Classrooms & Fence (Additional fromProject Modification) | 1055914.95 | 2 | 1050888.88 | COMPLETED | 1 | 2023-12-14 |  | 2023-04-011-INFRA |  |  | 2023-07-12 | 2023-07-24 | 2023-08-15 | 2023-08-17 | JFM Altitude Construction Corporation | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101326 | Calit ES | BINMALEY | 2nd | 1 | 10 | Repair of Classrooms & Fence (Additional fromProject Modification) | 4035628.5 | 2 | 3964910.11 | COMPLETED | 1 | 2023-11-03 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-07-05 | 2023-07-07 | Elmuel Jay Trading and Construction | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 300235 | Parayao National High School | BINMALEY | 2nd | 1 | 11 | Repair of Classrooms & Fence (Additional fromProject Modification) | 5099191.35 | 2 | 3136173.02 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | Elmuel Jay Trading and Construction | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101503 | BALOCOC ELEMENTARY SCHOOL | LINGAYEN (Capital) | 2nd | 1 | 5 | Repair of Classrooms & Fence (Additional fromProject Modification) | 2317814.24 | 2 | 1868152.4779 | COMPLETED | 1 | 2023-11-03 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-26 | 2023-07-07 | ABC East Multi Builders and Traders | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 300211 | Lasip NHS | LINGAYEN (Capital) | 2nd | 1 | 10 | Repair of Classrooms & Fence (Additional fromProject Modification) | 4035628.5 | 2 | 2744062.88 | COMPLETED | 1 | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | Mitzie Construction | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101484 | Magsaysay ES | LINGAYEN (Capital) | 2nd | 1 | 2 | Repair of Classrooms & Fence (Additional fromProject Modification) | 301821.02 | 2 | 243266.2968 | COMPLETED | 1 | 2023-11-03 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-26 | 2023-07-07 | ABC East Multi Builders and Traders | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101585 | Mangatarem I CS | MANGATAREM | 2nd | 1 | 10 | Repair of Classrooms & Fence (Additional fromProject Modification) | 4635628.5 | 2 | 3697907.44 | COMPLETED | 1 | 2023-11-03 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | Elmuel Jay Trading and Construction | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101689 | Don Pio B. Palisoc ES | URBIZTONDO | 2nd | 1 | 5 | Repair of Classrooms & Fence (Additional fromProject Modification) | 1767814.25 | 2 | 1752722.49 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | Elmuel Jay Trading and Construction | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101284 | Amancosiling Elementary School | BAYAMBANG | 3rd | 1 | 4 | Repair of Classrooms & Fence (Additional fromProject Modification) | 1854251.4 | 2 | 3025618.07 | COMPLETED | 1 | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | TG Ocampo Construction and Surveying Services | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101263 | Ataynan ES | BAYAMBANG | 3rd | 1 | 10 | Repair of Classrooms & Fence (Additional fromProject Modification) | 4035628.5 | 2 | 1427693.78 | COMPLETED | 1 | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | Macco Construction | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101288 | Carungay ES | BAYAMBANG | 3rd | 1 | 4 | Repair of Classrooms & Fence (Additional fromProject Modification) | 1854251.4 | 2 | 1848082.31 | COMPLETED | 1 | 2023-12-13 |  | 2023-04-011-INFRA |  |  | 2023-07-12 | 2023-07-24 | 2023-08-14 | 2023-08-16 | Szcon Builders Inc. | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101542 | Lokeb Este ES | MALASIQUI | 3rd | 1 | 8 | Repair of Classrooms & Fence (Additional fromProject Modification) | 3228502.8 | 2 | 3144928.81 | COMPLETED | 1 | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | ASS Construction | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101549 | Payar-Gomez ES | MALASIQUI | 3rd | 1 | 9 | Repair of Classrooms & Fence (Additional fromProject Modification) | 3165757.61 | 2 | 2420668.29 | COMPLETED | 1 | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | TG Ocampo Construction and Surveying Services | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101625 | Primicias Elementary School | MAPANDAN | 3rd | 1 | 8 | Repair of Classrooms & Fence (Additional fromProject Modification) | 3228502.8 | 2 | 2220224.26 | COMPLETED | 1 | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | Mitzie Construction | additional; with approved project modification change amount and scope of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2022 | Region I | Pangasinan II, Binalonan | 102058 | Ernesting Gonzalez CS | SANTO TOMAS | 5 | 1 | 2 | Repair of Classrooms | 1060635.37 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region I | Pangasinan II, Binalonan | 102060 | San Jose ES | SANTO TOMAS | 5 | 1 | 15 | Repair of Classrooms | 10000000 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2022 | Region I | Pangasinan II, Binalonan | 101735 | Mauban ES | BALUNGAO | 6 | 1 | 5 | Repair of Classrooms | 3000000 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region I | Pangasinan II, Binalonan | 101879 | Guiling-Coliling ES | ROSALES | 6 | 1 | 5 | Repair of Classrooms | 3000000 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region I | Pangasinan II, Binalonan | 102139 | Severo L. Castulo Elementary School | SAN QUINTIN | 6 | 1 | 6 | Repair of Classrooms | 4000000 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region I | San Fernando City | 101035 | Sevilla Elementary School | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 6 | Repair of Classrooms | 3201867.35 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | Batac City | 100077 | Cumcumraas-Manggaddi-Pitpitac ES | CITY OF BATAC | 2nd | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) | 2883055.04 | COMPLETED | 1 |  |  |  | 23AB0192 | [5 empty] | KRB Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | Batac City | 100081 | Naguirangan-Capacuan ES | CITY OF BATAC | 2nd | 1 | 2 | Repair of Classrooms | 2000000 | DPWH (Batch 2) | 1917176.65 | COMPLETED | 1 |  |  |  | 23AB0193 | [5 empty] | KRB Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region I | Candon City | 100425 | Allangigan Elementary School | CITY OF CANDON | 2nd | 1 | 6 | Repair of Classrooms | 2656157 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | ongoing ( For joint punchlisting) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | Candon City | 100431 | Balingaoan Elementary School | CITY OF CANDON | 2nd | 1 | 9 | Repair of Classrooms | 3620000 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | ongoing ( For joint punchlisting) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region I | Candon City | 100433 | Calaoa-an Elementary School | CITY OF CANDON | 2nd | 1 | 8 | Repair of Classrooms | 5360000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region I | Candon City | 100438 | Filomeno G. Gagarin Elementary School | CITY OF CANDON | 2nd | 1 | 2 | Repair of Classrooms | 451620 | DEPED (Batch 1) | 339198.12 | COMPLETED | 1 | 2023-11-02 | 2023-10-27 |  |  |  |  | 2023-09-14 | 2023-09-15 | 2023-09-19 | M.A TEJADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region I | Candon City | 100443 | Parioc East Elementary School | CITY OF CANDON | 2nd | 1 | 4 | Repair of Classrooms | 1771000 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | ongoing ( For joint punchlisting) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Candon City | 100448 | Sto. Tomas Elementary School | CITY OF CANDON | 2nd | 1 | 2 | Repair of Classrooms | 268000 | DEPED (Batch 1) | 223763.21 | COMPLETED | 1 | 2023-11-02 | 2023-10-27 |  |  |  |  | 2023-09-14 | 2023-09-15 | 2023-09-19 | M.A TEJADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region I | Candon City | 300083 | Sto. Tomas National High School | CITY OF CANDON | 2nd | 1 | 3 | Repair of Classrooms | 1206884.64 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | ongoing ( For joint punchlisting) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | Dagupan City | 300367 | Bonuan Buquig NHS | DAGUPAN CITY | 4th | 1 | 20 | Repair of Classrooms | 13000000 | DPWH (Batch 2) | 12168650 | COMPLETED | 1 | 2024-06-24 | 2024-06-04 | P00775560NP | 23AH0185 | 2023-09-28 | 2023-10-05 | 2023-09-28 | 2023-12-27 | 2024-01-12 | Alphatec Chemical Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2023 | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY | 4th | 1 | 24 | Repair of Classrooms | 20000000 | DPWH (Batch 2) | 16076900 | COMPLETED | 1 | 2024-08-08 | 2024-07-26 | P00775561NP | 23AH0186 | 2023-09-28 | 2023-10-05 | 2023-09-28 | 2023-12-27 | 2024-01-12 | Aquino-dela Cruz Engineering & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0
REPAIR 2023 | Region I | Dagupan City | 500054 | Federico N. Ceralde Integrated School | DAGUPAN CITY | 4th | 1 | 18 | Repair of Classrooms | 15000000 | DPWH (Batch 2) | 14040750 | COMPLETED | 1 | 2024-06-19 | 2024-06-19 | P00775563NP | 23AH0188 | 2023-10-04 | 2023-10-11 | 2023-10-04 | 2023-12-27 | 2024-01-12 | Alphatec Chemical Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2023 | Region I | Dagupan City | 102168 | Gen. Gregorio del Pilar ES | DAGUPAN CITY | 4th | 1 | 9 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4680250 | COMPLETED | 1 | 2024-08-23 | 2024-07-26 | P00775559NP | 23AH0184 | 2023-10-03 | 2023-10-10 | 2023-10-03 | 2023-12-27 | 2024-01-12 | Alphatec Chemical Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region I | Dagupan City | 300370 | Salapingao National High School | DAGUPAN CITY | 4th | 1 | 6 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 11232690 | COMPLETED | 1 | 2024-08-08 |  | P00775562NP | 23AH0187 | 2023-10-04 | 2023-10-11 | 2023-10-04 | 2024-03-26 | 2024-04-11 | JG Garcia Construction & Supply. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | Ilocos Norte | 300006 | Burgos Agro-Industrial School | Burgos | 1st | 1 | 6 | Repair of Classrooms | 1134028.03 | DPWH (Batch 1) |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | Ilocos Norte | 100108 | Saoit-Pagali Elementary School | Burgos | 1st | 1 | 3 | Repair of Classrooms | 861853.58 | DEPED (Batch 1) | 772141.52 | COMPLETED | 1 | 2024-02-01 | 2024-01-25 |  |  | 2023-09-29 |  | 2023-10-04 |  | 2023-11-28 | Plutus Construction | with variation order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | Ilocos Norte | 100233 | Virbira-Angset ES | Carasi | 1st | 1 | 2 | Repair of Classrooms | 1521626.4 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region I | Ilocos Norte | 300017 | Dumalneg NHS | Dumalneg | 1st | 1 | 4 | Repair of Classrooms | 2978059.35 | DPWH (Batch 1) |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Ilocos Norte | 320808 | Bamasesamar National High School | DINGRAS | 2nd | 1 | 4 | Repair of Classrooms | 4000000 | DPWH (Batch 2) |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Ilocos Norte | 320811 | Marcos NHS (Agunit) | MARCOS | 2nd | 1 | 4 | Repair of Classrooms | 4000000 | DPWH (Batch 2) |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Ilocos Norte | 150018 | Barikir ES | NUEVA ERA | 2nd | 1 | 4 | Repair of Classrooms | 2972000 | DPWH (Batch 2) |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Ilocos Norte | 150019 | Bugayong Elementary Sch. | NUEVA ERA | 2nd | 1 | 4 | Repair of Classrooms | 2972000 | DPWH (Batch 2) |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Ilocos Norte | 100142 | Cabittauran ES | NUEVA ERA | 2nd | 1 | 9 | Repair of Classrooms | 7320000 | DPWH (Batch 2) |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region I | Ilocos Norte | 100154 | Nueva Era Central Elementary School | NUEVA ERA | 2nd | 1 | 7 | Repair of Classrooms | 5834000 | DPWH (Batch 2) |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region I | Ilocos Norte | 300022 | NUEVA ERA NATIONAL HIGH SCHOOL | NUEVA ERA | 2nd | 1 | 2 | Repair of Classrooms | 1486000 | DPWH (Batch 2) |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100370 | Bantay East Central School | BANTAY | 1st | 1 | 1 | Repair of Classrooms | 171274.37 | DEPED (Batch 2) | 164776.32 | COMPLETED | 1 | 2024-09-04 | 2024-07-31 | PB-01-2024 |  | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100455 | Cal-laguip Elementary School | CAOAYAN | 1st | 1 | 1 | Repair of Classrooms | 650953.97 | DEPED (Batch 2) | 627991.64 | COMPLETED | 1 | 2024-09-04 | 2024-08-19 | PB-01-2024 |  | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100457 | Fuerte Elementary School | CAOAYAN | 1st | 1 | 1 | Repair of Classrooms | 67833.32 | DEPED (Batch 2) | 65000.25 | COMPLETED | 1 | 2024-09-04 | 2024-08-07 | PB-01-2024 |  | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 300040 | Belen NHS | SAN ILDEFONSO | 1st | 1 | 4 | Repair of Classrooms | 1566106.43 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  |  |  | 2024-05-30 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100605 | Sabangan Elementary School | SAN JUAN (LAPOG) | 1st | 1 | 1 | Repair of Classrooms | 746663.48 | DEPED (Batch 2) | 720286.69 | COMPLETED | 1 | 2024-09-04 | 2024-08-19 | PB-01-2024 |  | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100662 | Paratong ES | SANTA CATALINA | 1st | 1 | 1 | Repair of Classrooms | 341100.3 | DEPED (Batch 2) | 328902.72 | COMPLETED | 1 | 2024-09-04 | 2024-08-19 | PB-01-2024 |  | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100341 | Nagawa Elem. School | SUGPON | 1st | 1 | 3 | Repair of Classrooms | 2009000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 300041 | Burgos National High School | BURGOS | 2nd | 1 | 8 | Repair of Classrooms | 4420000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100395 | Padayao ES | BURGOS | 2nd | 1 | 4 | Repair of Classrooms | 2102500 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100555 | Alfonso Elementary School | GREGORIO DEL PILAR (CONCEPCION) | 2nd | 1 | 5 | Repair of Classrooms | 3397118.23 | DPWH (Batch 1) |  | Ongoing | 0.9 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100348 | Banucal Elementary School | LIDLIDDA | 2nd | 1 | 4 | Repair of Classrooms | 1771000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100516 | Banglayan Elementary School | NARVACAN | 2nd | 1 | 4 | Repair of Classrooms | 1671500 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100544 | Narvacan South Central School SPED Center | NARVACAN | 2nd | 1 | 1 | Repair of Classrooms | 355902.25 | DEPED (Batch 2) | 343295.67 | COMPLETED | 1 | 2024-09-04 | 2024-08-19 | PB-01-2024 |  | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 300070 | Quirino NHS | QUIRINO (ANGKAKI) | 2nd | 1 | 4 | Repair of Classrooms | 2501576.27 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  |  |  | 2024-05-30 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 500598 | KALUMSING INTEGRATED SCHOOL | SAN EMILIO | 2nd | 1 | 6 | Repair of Classrooms | 2265500 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  |  |  | 2024-05-30 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 300075 | San Esteban NHS | SAN ESTEBAN | 2nd | 1 | 10 | Repair of Classrooms | 6101308 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  |  |  | 2024-05-30 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 500346 | Mabilbila IS | SANTA | 2nd | 1 | 8 | Repair of Classrooms | 3700000 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  |  |  | 2024-05-30 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 300034 | Amarao NHS | SANTA CRUZ | 2nd | 1 | 4 | Repair of Classrooms | 1640000 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  |  |  | 2024-05-30 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100702 | Babal-lasioan ES | SANTA MARIA | 2nd | 1 | 6 | Repair of Classrooms | 364000 | DEPED (Batch 1) | 349195.1 | COMPLETED | 1 | 2023-12-30 | 2023-12-18 |  | 10284126 | 2023-11-07 |  | 2023-11-09 | 2023-11-10 | 2023-11-16 | M.A TEJADA CONSTRUCTION | . | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 150504 | Matallucod PS | SIGAY | 2nd | 1 | 1 | Repair of Classroom | 1220000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 300036 | Sugpon NHS | SUGPON | 2nd | 1 | 8 | Repair of Classrooms | 5383154.75 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region I | Ilocos Sur | 100744 | Bangcag ES | SUYO | 2nd | 1 | 1 | Repair of Classrooms | 319898.6 | DEPED (Batch 2) | 308326.76 | COMPLETED | 1 | 2024-09-04 | 2024-08-05 | PB-01-2024 |  | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | La Union | 100842 | Baroro Elementary School | BACNOTAN | 1st | 1 | 4 | Repair of Classrooms | 5635648.16 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  |  |  | 2024-05-30 | [5 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | La Union | 100883 | Nagsabaran Sur ES | BALAOAN | 1st | 1 | 9 | Repair of Classrooms | 7178402.12 | DPWH (Batch 2) |  | COMPLETED | 1 |  |  |  |  | 2024-05-30 | [5 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region I | La Union | 100885 | Pantar ES | BALAOAN | 1st | 1 | 3 | Repair of Classrooms | 3054148.66 | DPWH (Batch 2) |  | COMPLETED | 1 |  |  |  |  | 2024-05-30 | [5 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | La Union | 100888 | Patpata ES | BALAOAN | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 1 |  |  |  |  | 2024-05-30 | [5 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | La Union | 100899 | Ma. Cristina ES | BANGAR | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 1 |  |  |  |  | 2024-05-30 | [5 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | La Union | 100905 | Sinapangan ES | BANGAR | 1st | 1 | 8 | Repair of Classrooms | 6416677.87 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region I | La Union | 321018 | Luna National Vocational High School | LUNA | 1st | 1 | 5 | Repair of Classrooms | 1741895.36 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region I | La Union | 100962 | Nagrebcan ES | LUNA | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | La Union | 100953 | Nalvo Norte ES | LUNA | 1st | 1 | 4 | Repair of Classrooms | 4069020.57 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | La Union | 100954 | Rimos del Norte ES | LUNA | 1st | 1 | 8 | Repair of Classrooms | 7020859.31 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region I | La Union | 100955 | Rimos ES | LUNA | 1st | 1 | 3 | Repair of Classrooms | 3634688.88 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | La Union | 101047 | Amontoc ES | SAN GABRIEL | 1st | 1 | 2 | Repair of Classrooms | 2122094.77 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region I | La Union | 300097 | Balbalayang National High School | SAN GABRIEL | 1st | 1 | 2 | Repair of Classrooms | 2932062.07 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region I | La Union | 101050 | Bumbuneg ES | SAN GABRIEL | 1st | 1 | 5 | Repair of Classrooms | 4918234.85 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region I | La Union | 500356 | Lipay Integrated School | SAN GABRIEL | 1st | 1 | 8 | Repair of Classrooms | 6416677.87 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region I | La Union | 101060 | Bacsayan Elementary School | SAN JUAN | 1st | 1 | 1 | Repair of Classrooms | 1186264.29 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | La Union | 101066 | Legleg Elementary School | SAN JUAN | 1st | 1 | 1 | Repair of Classrooms | 1161310.95 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | La Union | 101072 | Sta. Rosa Elementary School | SAN JUAN | 1st | 1 | 7 | Repair of Classrooms | 5896259.41 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region I | La Union | 101074 | Taboc ES | SAN JUAN | 1st | 1 | 4 | Repair of Classrooms | 4054407.6 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | La Union | 101075 | Urbiztondo ES | SAN JUAN | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | La Union | 500471 | BAY-O ELEMENTARY SCHOOL | SANTOL | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | La Union | 101078 | Corrooy ES | SANTOL | 1st | 1 | 4 | Repair of Classrooms | 4095996.47 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | La Union | 300107 | Corrooy National High School | SANTOL | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | La Union | 101107 | Duplas ES | SUDIPEN | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | La Union | 300117 | Duplas National High School | SUDIPEN | 1st | 1 | 4 | Repair of Classrooms | 3998921.04 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | La Union | 500350 | Baay Integrated School | BAGULIN | 2nd | 1 | 4 | Repair of Classrooms | 14993885.31 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | La Union | 500352 | Dagup Integrated School | BAGULIN | 2nd | 1 | 7 | Repair of Classrooms | 4175991.07 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region I | La Union | 300149 | Suyo National High School | BAGULIN | 2nd | 1 | 2 | Repair of Classrooms | 3999536.28 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region I | La Union | 100907 | Acao Elementary School | BAUANG | 2nd | 1 | 1 | Repair of Classrooms | 1692994.44 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | La Union | 100908 | Baccuit Elementary School | BAUANG | 2nd | 1 | 4 | Repair of Classrooms | 3000000.6 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | La Union | 100913 | Bigbiga ES | BAUANG | 2nd | 1 | 4 | Repair of Classrooms | 3999549.4 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | La Union | 100919 | Bucayab Elementary School | BAUANG | 2nd | 1 | 4 | Repair of Classrooms | 2999805.61 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | La Union | 501196 | Parian Este Integrated School | BAUANG | 2nd | 1 | 6 | Repair of Classrooms | 5999842.13 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | La Union | 100914 | Paringao ES | BAUANG | 2nd | 1 | 4 | Repair of Classrooms | 14015971.39 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | La Union | 300128 | Paringao National High School | BAUANG | 2nd | 1 | 5 | Repair of Classrooms | 3999536.28 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region I | La Union | 100926 | Payocpoc Este ES | BAUANG | 2nd | 1 | 3 | Repair of Classrooms | 3000000.6 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | La Union | 100915 | PUGO ELEMENTARY SCHOOL | BAUANG | 2nd | 1 | 3 | Repair of Classrooms | 3000000.6 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | La Union | 500600 | Libtong Integrated School | BURGOS | 2nd | 1 | 10 | Repair of Classrooms | 8465065.66 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region I | La Union | 100991 | Naguilian CS | NAGUILIAN | 2nd | 1 | 6 | Repair of Classrooms | 5999842.13 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | La Union | 100993 | San Isidro ES | NAGUILIAN | 2nd | 1 | 6 | Repair of Classrooms | 5999842.13 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | La Union | 101093 | Casilagan ES | SANTO TOMAS | 2nd | 1 | 3 | Repair of Classrooms | 3000000.6 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | La Union | 101100 | Patac Elementary School | SANTO TOMAS | 2nd | 1 | 2 | Repair of Classrooms | 1999675.04 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region I | La Union | 101127 | Pideg Elementary school | TUBAO | 2nd | 1 | 3 | Repair of Classrooms | 5999842.13 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 101237 | Dacap Sur ES | BANI | 1st | 1 | 3 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 101446 | Eguia ES | DASOL | 1st | 1 | 3 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 101448 | Macalang ES | DASOL | 1st | 1 | 3 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 101461 | Bayambang ES | INFANTA | 1st | 1 | 3 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | LINGAYEN (Capital) | 2nd | 1 | 9 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | LINGAYEN (Capital) | 2nd |  | 12 | Repair of Classrooms | 15000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 101439 | Songkoy ES | CALASIAO | 3rd | 1 | 2 | Repair of Classrooms | 1345728.66 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 102058 | Ernesting Gonzalez CS | SANTO TOMAS | 5th | 1 | 2 | Repair of Classrooms | 1300000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300322 | Luciano Millan National HS | ASINGAN | 6th | 1 | 16 | Repair of Classrooms | 9315000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300339 | Rajal Angayan NHS | BALUNGAO | 6th | 1 | 1 | Repair of Classrooms | 366000 | DEPED (Batch 2) | 352644.42 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300331 | Natividad NHS | NATIVIDAD | 6th | 1 | 24 | Repair of Classrooms | 2700000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300309 | Eastern Pangasinan Agricultural College | SANTA MARIA | 6th | 1 | 26 | Repair of Classrooms | 18800000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 0 | 0
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 102070 | Evangelista ES | TAYUG | 6th | 1 | 6 | Repair of Classrooms | 1957849.1 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300363 | Tayug NHS | TAYUG | 6th | 1 | 32 | Repair of Classrooms | 20420000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300327 | Maseil-seil Alo-o NHS | UMINGAN | 6th | 1 | 4 | Repair of Classrooms | 2840770.36 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300365 | Umingan Central National High School | UMINGAN | 6th | 1 | 24 | Repair of Classrooms | 1767551.37 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0
REPAIR 2023 | Region I | Vigan City | 100785 | Burgos Memorial School East | CITY OF VIGAN (Capital) | 1st | 1 | 9 | Repair of Classrooms | 3304786.06 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region I | Vigan City | 100788 | Camangaan Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 4 | Repair of Classrooms | 1368182.96 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region I | Vigan City | 100792 | Mindoro Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 8 | Repair of Classrooms | 3109031.85 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region I | Vigan City | 100794 | Pantay Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 1 | Repair of Classrooms | 928788.93 | DEPED (Batch 2) | 795358.48 | COMPLETED | 1 | 2024-02-29 | 2024-02-29 | [8 empty] | with variation order with punchlist/corrective materials | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region I | Vigan City | 100795 | Raois Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 12 | Repair of Classrooms | 6626284.41 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | Region I | Vigan City | 100799 | Tamag Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 6 | Repair of Classrooms | 1422689.82 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region I | Alaminos City | 500564 | Pangapisan Integrated School | CITY OF ALAMINOS | 1st | 1 | 10 | Repair of Classrooms | 6315970.16 | 1 | 6252810.46 | COMPLETED | 1 | 2025-03-15 | 2025-02-10 | PB-Infra-2024-08-02 |  | 2024-08-28 | 2024-09-05 | 2024-09-17 | 2024-09-23 | 2024-10-17 | MANIMELDS CONSTRUCTION AND IRON WORKS | For Final Punchlisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region I | Batac City | 100088 | Benigno Macadaeg Mem. ES | CITY OF BATAC | 2nd | 1 | 6 | Repair of Classrooms | 4141414.14 | 1 | 3341308.11 | COMPLETED | 1 | Feb. 12, 2025 | 2024-12-19 | 2024-001 | 24006 | 2024-07-08 | 2024-07-17 | 2024-07-29 | Aug. 12, 2024 | 2024-10-15 | DPV BUILDERS AND CONSTRUCTION SUPPLY | Part of the savings (P 315,386.58) was used for the Variation Order for the Additional Works of the Project, while the remaining savings (P 443,305.30) was used to fund the project: Repair and Rehabilitation of DepEd Building (Office 12M x 7.5M) of the same school which is now also completed. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region I | Candon City | 100436 | Candon South Central School | CITY OF CANDON | 2nd | 1 | 3 | Repair of Classrooms | 2480710.23 | 1 | 1761336.18 | COMPLETED | 1 | 2025-01-23 | 2024-12-23 | PB-INFRA-01-2024 |  | 2024-08-14 | 2024-09-03 | 2024-09-06 | 2024-09-23 | 2024-09-25 | M.A. TEJADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region I | Candon City | 100445 | Patpata Elementary School | CITY OF CANDON | 2nd | 1 | 3 | Repair of Classrooms | 1813239.72 | 1 | 1601006.84 | COMPLETED | 1 | 2025-01-23 | 2024-12-18 | PB-INFRA-02-2024 |  | 2024-08-14 | 2024-09-03 | 2024-09-06 | 2024-09-23 | 2024-09-25 | AMBROCIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region I | Dagupan City | 102165 | Bonuan Buquig ES | DAGUPAN CITY | 4th | 1 | 2 | Repair of Classrooms | 1838383.84 | 1 | 1793495.08 | COMPLETED | 1 | 2025-03-10 | 2025-03-10 |  |  | October 14 - November 4, 2024 | 2024-10-22 | 2025-11-04 | 2024-11-08 | 2024-11-11 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region I | Dagupan City | 102155 | Caranglaan ES | DAGUPAN CITY | 4th | 1 | 11 | Repair of Classrooms | 2242424.24 | 1 | 2185766.11 | COMPLETED | 1 | 2025-03-10 | 2025-03-10 |  |  | October 14 - November 4, 2024 | 2024-10-22 | 2025-11-04 | 2024-11-08 | 2024-11-11 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2024 | Region I | Ilocos Norte | 300020 | Marcos NHS | MARCOS | 2nd | 1 | 4 | Repair of Classrooms | 4146464.65 | 1 | 4105000 | COMPLETED | 1 | 2025-03-06 | 2024-12-10 | PB-03-2024 | PB-03-2024 | 2024-07-29 | 2024-08-06 | 2024-08-19 | 2024-09-04 | 2024-10-07 | DPV Builders and Construction Supply | Savings was used for Contiguous Contract for the minor repair of 3 classroom BLSB school building amounting to P576,352.31 which is also completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region I | Ilocos Sur | 100471 | Comillas South ES | CERVANTES | 2nd | 1 | 10 | Repair of Classrooms | 6673787.01 | 1 | 6154175.11 | COMPLETED | 1 | 2025-02-20 | 2025-02-19 | PB-06-2024 |  |  | 2024-07-31 | 2024-08-13 | 2024-08-22 | 2024-09-23 | J.D. JR. GALUTAN BUILDERS | Savings (PhP 452,874.03) was utlized through variation oder (additional works) Revised contract amount: PhP 6,607,049.14 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region I | La Union | 101126 | Lloren ES | TUBAO | 2nd | 1 | 10 | Repair of Classrooms | 6363636.36 | 1 | 4, 270, 256. 04 | COMPLETED | 1 | 2024-12-22 | 2024-12-10 | 2024REPAIR-RO1-LU-01 | SDOLU - REPAIR 2024 | 2024-07-01 | 2024-07-10 | 2024-07-24 | 2024-08-02 | 2024-10-25 | DPV BUILDERS AND CONSTRUCTION SUPPLY | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region I | Laoag City | 102182 | Amarosa Elementary School | LAOAG CITY (Capital) | 1st | 1 | 8 | Repair of Classrooms | 6394702.3 | 1 | 4040610.2 | Ongoing | 0.7 | 2025-05-31 |  | 2024-PB1-001 |  | oct.04,2024 | Oct.11,2024 | Oct.28.2024 | Dec.04,2024 | Dec.19.2024 | Elocin Construction | On Going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
REPAIR 2024 | Region I | Pangasinan I, Lingayen | 300245 | Ranao National High School | BANI | 1st | 1 | 3 | Repair of Classrooms | 2302492.17 | 1 | 2302492.17 | COMPLETED | 1 | 2025-01-28 |  | 2024-09-004-INFRA |  | 2024-09-26 | 2024-10-04 | 2024-10-16 | 2024-10-30 | 2024-10-31 | JFM Altitude Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region I | Pangasinan I, Lingayen | 300256 | Tagudin NHS | MABINI | 1st | 1 | 2 | Repair of Classrooms | 1534994.78 | 1 | 1534994.78 | COMPLETED | 1 | 2025-02-03 |  | 2024-09-004-INFRA |  | 2024-09-26 | 2024-10-04 | 2024-10-16 | 2024-10-28 | 2024-11-06 | JFM Altitude Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region I | Pangasinan I, Lingayen | 101306 | Telbang ES | BAYAMBANG | 3rd | 1 | 2 | Repair of Classrooms | 1524893.77 | 1 | 1524893.77 | COMPLETED | 1 | 2025-01-28 |  | 2024-09-004-INFRA |  | 2024-09-26 | 2024-10-04 | 2024-10-16 | 2024-10-28 | 2024-10-31 | Elmuel Jay Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region I | Pangasinan I, Lingayen | 101623 | Nilombot ES | MAPANDAN | 3rd | 1 | 2 | Repair of Classrooms | 1292570.54 | 1 | 1292570.54 | COMPLETED | 1 | 2025-02-01 |  | 2024-09-004-INFRA |  | 2024-09-26 | 2024-10-04 | 2024-10-16 | 2024-10-29 | 2024-11-04 | SZCON Builders Incorporated |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region I | Pangasinan I, Lingayen | 101628 | Alibago ES | SANTA BARBARA | 3rd | 1 | 1 | Repair of Classrooms | 762446.89 | 1 | 762446.89 | COMPLETED | 1 | 2025-02-01 |  | 2024-09-004-INFRA |  | 2024-09-26 | 2024-10-04 | 2024-10-16 | 2024-10-29 | 2024-11-04 | Kalbs Builders and Construction Supply - OPC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2024 | Region I | Pangasinan II, Binalonan | 101914 | San Fabian West CES | SAN FABIAN | 4th | 1 | 10 | Repair of Classrooms | 4444444.44 | 1 |  | Completed | 1 | [9 empty] | Elmuel Jay Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region I | Pangasinan II, Binalonan | 300295 | Cabilaoan Agro-Industrial HS | LAOAC | 5th | 1 | 4 | Repair of Classrooms | 4242424.24 | 1 |  | Ongoing | 0.9 | [9 empty] | W.M. Salayog Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2024 | Region I | Pangasinan II, Binalonan | 101883 | Rosales South CS | ROSALES | 6th | 1 | 5 | Repair of Classrooms | 5303030.3 | 1 |  | Ongoing | 0.95 | [9 empty] | Rivbros Construction Factors and Development |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2024 | Region I | San Carlos City | 102246 | Mabalbalino Elementary School | SAN CARLOS CITY | 3rd | 1 | 10 | Repair of Classrooms | 6262626.26 | 1 | 5531200.08 | COMPLETED | 1 | APRIL 10,2025 | 2025-04-10 | - | 2024 - 014 | OCTOBER 17 - 24, 2024 | OCTOBER 29,2024 | 2024-11-11 | 2024-11-26 | 2024-12-11 | RGP SUCCESS VENTURES INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region I | San Fernando City | 101026 | Ilocanos Elementary School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 5 | Repair of Classrooms | 2245981.73 | 1 | 1888416.18 | COMPLETED | 1 | 2024-11-29 | 2024-11-29 | CSFLU-INFRA-02-2024 | CSFLU-INFRA-002-2024 | 2024-08-08 | 2024-08-16 | 2024-08-28 | 2024-09-04 | 2024-09-23 | DPV Builders & Construction Supply | Awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region I | San Fernando City | 500530 | Nagyubuyuban Integrated School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 2 | Repair of Classrooms | 1191453.91 | 1 | 1084431.83 | COMPLETED | 1 | 2024-11-29 | 2024-11-22 | CSFLU-INFRA-02-2024 | CSFLU-INFRA-002-2024 | 2024-08-08 | 2024-08-16 | 2024-08-28 | 2024-09-04 | 2024-09-23 | DPV Builders & Construction Supply | Awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region I | Urdaneta City | 102303 | Nancalobasaan Elementary School | CITY OF URDANETA | 5th | 1 | 6 | Repair of Classrooms | 4232323.23 | 1 | 2595166.7 | Ongoing | 0.7 | March 28,2025 |  | 11006619 | ITB-011-2024 | 2024-07-01 | 2024-07-09 | 2024-07-22 | 2024-11-19 | 2024-11-28 | MACCO Construction | With time extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2024 | Region I | Vigan City | 100792 | Mindoro Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 6 | Repair of Classrooms | 2020202.02 | 1 | 1587378.57 | COMPLETED | 1 | 2025-01-14 | 2025-01-14 | INFRA-2024-011 | 11202360 | 2024-08-30 | 2024-09-09 | 2024-09-23 | 2024-10-01 | 2024-10-14 | HEAF Engineering and Consultancy | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%