## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 4, 2025
QRF 2019 | Region II | Cagayan | 102366 | Carallangan ES | ALCALA | 1 | 1 | 2 | 1STY2CL | 3869401.2827 | 1 |  | Completed | 1 | [10 empty] | ONGOING/ compliance to VO
QRF 2019 | Region II | Cagayan | 102450 | San Antonio ES | APARRI | 1 | 1 | 3 | 1STY3CL | 5307755.7554 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102509 | Asassi ES | BAGGAO | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 579977.07 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102502 | Sta. Margarita West ES | BAGGAO | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 545932.86 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102653 | Capissayan Elementary School | GATTARAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 545932.86 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102664 | Tanglagan ES | GATTARAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 808067.17 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102898 | Casagan ES | SANTA ANA | 1 | 1 | 2 | 1STY2CL | 3821369.2801 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102899 | Casambalangan ES | SANTA ANA | 1 | 1 | 4 | 2 UNITS OF 1STY2CL | 7030500.1832 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102902 | Kapannikian ES | SANTA ANA | 1 | 1 | 2 | 1STY2CL | 3712494.5201 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102332 | Alinunu ES | ABULUG | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1692161.9 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102408 | Concepcion Elementary School | AMULUNG | 3 | 1 | 4 | 1STY4CL | 6791637.63 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102412 | Gabut ES | AMULUNG | 3 | 1 | 2 | 1STY2CL | 3672954.74 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102413 | GANGAUAN ES | AMULUNG | 3 | 1 | 2 | 1STY2CL | 3672954.74 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102417 | Monte Alegre ES | AMULUNG | 3 | 1 | 5 | 1STY3CL & 1STY2CL | 8646857.64 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102436 | Nangalasauan ES | AMULUNG | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 810920.67 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102441 | San Juan ES | AMULUNG | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 785664.88 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102638 | Maddarulug Sur ES | ENRILE | 3 | 1 | 6 | 2UNITS-1STY3CL | 10147535.9354 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102631 | Maracuru ES | ENRILE | 3 | 1 | 2 | 1STY2CL | 3672954.74 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102721 | Sta.Barbara Elementary School | IGUIG | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1164440.22 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102797 | Alitontong ES | PEÑABLANCA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 825291.4 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102810 | Baliwag Elementary School | PEÑABLANCA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 786475.77 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 155017 | Bauan E/S | PEÑABLANCA | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 349536.91 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102812 | Bugatay ES | PEÑABLANCA | 3 | 1 | 3 | 1STY3CL | 5322410.73 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102801 | Lapi ES | PEÑABLANCA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 739349.96 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102802 | Mangga ES | PEÑABLANCA | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1585443.73 | 1 |  | Completed | 1 | [10 empty] | ONGOING/ compliance to VO
QRF 2019 | Region II | Cagayan | 300457 | Penablanca East NHS | PEÑABLANCA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 739936.9 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 300445 | Penablanca National High School | PEÑABLANCA | 3 | 1 | 5 | 1STY5CL | 7882791.27 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102877 | Bantay ES | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 718499.38 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102871 | IRAGA ELEMENTARY SCHOOL | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1530030.26 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102885 | Lannig ES | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 742410.25 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102886 | Lingu ES | SOLANA | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 722670.51 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102873 | Malacabibi ES | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 798637.24 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102874 | Masin-San Pablo ES | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 699867.5 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102888 | Nabbotuan Elementary School | SOLANA | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 805439.39 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 155050 | Pataya ES | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 688813.62 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102895 | Solana South CS | SOLANA | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 362938.68 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102896 | Ubong ES | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 787939.53 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102897 | Villa Salud ES | SOLANA | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 805439.39 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102975 | Accusilian Elementary School | TUAO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 615267.63 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102978 | Bagumbayan ES | TUAO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 355493.09 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102958 | Bicok Elementary School | TUAO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 784782.71 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102959 | Bugnay ELEMENTARY SCHOOL | TUAO | 3 | 1 | 3 | 1STY3CL | 5307755.76 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102982 | Cagumitan ES | TUAO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 711424.54 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102960 | Culung ES | TUAO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1388646.32 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102985 | Lallayug ES | TUAO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 645557.81 | 1 |  | Completed | 1
QRF 2019 | Region II | Cagayan | 102972 | Sto. Tomas Elementary School | TUAO | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1067031.49 | 1 |  | Completed | 1
QRF 2019 | Region II | Cauayan City | 103227 | Alinam ES | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL | 5556311.66 | 1 |  | Completed | 1 |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30
QRF 2019 | Region II | Cauayan City | 103209 | Amobocan ES | CITY OF CAUAYAN | 3 | 1 | 7 | 1STY3CL | 6296144.55 | 1 |  | Completed | 1 |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30
QRF 2019 | Region II | Cauayan City | 103180 | Andarayan-Bugallon ES | CITY OF CAUAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 447616.16 | 1 |  | Completed | 1
QRF 2019 | Region II | Cauayan City | 103182 | Buyon ES | CITY OF CAUAYAN | 3 | 1 | 6 | 1STY3CL | 6244275.62 | 1 |  | Completed | 1 |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30
QRF 2019 | Region II | Cauayan City | 103184 | Casalatan ES | CITY OF CAUAYAN | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 952113.52 | 1 |  | Completed | 1
QRF 2019 | Region II | Cauayan City | 103185 | Cassap Fuera Elementary School | CITY OF CAUAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 768173.67 | 1 |  | Completed | 1
QRF 2019 | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 3 | 1 | 74 | REPAIR OF CLASSROOMS | 4216845.71 | 1 |  | Completed | 1
QRF 2019 | Region II | Cauayan City | 323901 | Cauayan City NHS - Research Annex | CITY OF CAUAYAN | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 965520.72 | 1 |  | Completed | 1 |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 | YZK CONSTRUCTION
QRF 2019 | Region II | Cauayan City | 103187 | DIPARICAO ELEMENTARY SCHOOL | CITY OF CAUAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 819485.28 | 1 |  | Completed | 1 |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 | ES PUA CONSTRUCTION
QRF 2019 | Region II | Cauayan City | 300538 | Gappal NHS | CITY OF CAUAYAN | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 570773.7 | 1 |  | Completed | 1 |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 | ES PUA CONSTRUCTION
QRF 2019 | Region II | Cauayan City | 155528 | Nagrumbuan ES - Annex | CITY OF CAUAYAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 466399.11 | 1 |  | Completed | 1
QRF 2019 | Region II | Cauayan City | 300567 | Pinoma NHS | CITY OF CAUAYAN | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 724294.42 | 1 |  | Completed | 1 |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 | YZK CONSTRUCTION
QRF 2019 | Region II | Cauayan City | 103199 | Rogus ES | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL | 5556311.66 | 1 |  | Completed | 1 |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30
QRF 2019 | Region II | Cauayan City | 103202 | Sinippil ES | CITY OF CAUAYAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 873835.51 | 1 |  | Completed | 1
QRF 2019 | Region II | Cauayan City | 300613 | Villa Concepcion HS | CITY OF CAUAYAN | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 881376.93 | 1 |  | Completed | 1 |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 | ES PUA CONSTRUCTION
QRF 2019 | Region II | Cauayan City | 300614 | Villaluna NHS | CITY OF CAUAYAN | 3 | 1 | 16 | REPAIR OF CLASSROOMS | 1349321.89 | 1 |  | Completed | 1 |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 | GCPK CONSTRUCTION
QRF 2019 | Region II | City of Ilagan | 103412 | Alibagu Elementary School | ILAGAN CITY (CAPITAL) | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 651366.96 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Edpin Construction
QRF 2019 | Region II | City of Ilagan | 103390 | Cabeceria 24 ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 332555.57 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Camberwell Construction and Supplies
QRF 2019 | Region II | City of Ilagan | 103392 | Cabeceria 27 ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 3 | 1STY3CL | 5159304.84 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Fragerr Construction
QRF 2019 | Region II | City of Ilagan | 500087 | Gayong-Gayong Sur Integrated School | ILAGAN CITY (CAPITAL) | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 468123.67 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Edpin Construction
QRF 2019 | Region II | City of Ilagan | 300545 | Ilagan Sports HS (INHS - Alibagu Annex) | ILAGAN CITY (CAPITAL) | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 638992.75 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Edpin Construction
QRF 2019 | Region II | City of Ilagan | 103424 | LULLUTAN ELEMENTARY SCHOOL | ILAGAN CITY (CAPITAL) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1685954.58 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Atlantic Construction
QRF 2019 | Region II | City of Ilagan | 500080 | Lupigue Integrated School (formerly Lupigue ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | 26 | REPAIR OF CLASSROOMS | 3702586.81 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Foref Construction
QRF 2019 | Region II | City of Ilagan | 103370 | Morado ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 629880.89 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | 4A's Construction
QRF 2019 | Region II | City of Ilagan | 103406 | San Antonio ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 13 | REPAIR OF CLASSROOMS | 3791888.79 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | SMT Construction
QRF 2019 | Region II | City of Ilagan | 300583 | San Antonio Nat'l. Agro-Ind'l. & Voc'l. HS | ILAGAN CITY (CAPITAL) | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 854958.12 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | 4A's Construction
QRF 2019 | Region II | City of Ilagan | 103383 | Villa Imelda ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 890751.71 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | 4A's Construction
QRF 2019 | Region II | Isabela | 103146 | Candanum Elementary School | CABANGAN | 1 | 1 | 3 | 1STY3CL | 5159304.84 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103535 | Bicobian Elementary School | DIVILACAN | 1 | 1 | 3 | 1STY3CL | 6020589.68 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103547 | Dikaruyan Primary School | DIVILACAN | 1 | 1 | 2 | 1STY2CL | 4396305.68 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103554 | Divilacan Central School | DIVILACAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 517294.57 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103560 | Sapinit Primary School | DIVILACAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 712942.34 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103555 | Maconacon Central School | MACONACON | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 869478.84 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300560 | Maconacon National High School | MACONACON | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 3621461.07 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103558 | Reina Mercedes Elementary School | MACONACON | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 766325.08 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103534 | Alomanay ES | PALANAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1643929.33 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103536 | Bisag Elementary School | PALANAN | 1 | 1 | 6 | 1STY4CL | 8430539.53 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 155520 | Centro West Primary School | PALANAN | 1 | 1 | 6 | 1STY3CL | 7456736 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103538 | Culasi Elementary School | PALANAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1183386.86 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103539 | Dialawyao Elementary School | PALANAN | 1 | 1 | 4 | 1STY3CL | 6415803.09 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103540 | Dibewan Elementary School | PALANAN | 1 | 1 | 3 | 1STY3CL | 6020589.68 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103542 | Dibungko Primary School | PALANAN | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 395213.41 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103543 | Dibutarek Elementary School | PALANAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1653889.49 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103545 | Didiyan Elementary School | PALANAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1362588.51 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | NOT-IN-NSBI | Didiyan Elementary School Annex | PALANAN | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2251806.77 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103546 | Dikadyuan Elementary School | PALANAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 819901.9 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 155525 | Dimalicu-licu Primary School | PALANAN | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 529688.49 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103549 | Dimasari Elementary School | PALANAN | 1 | 1 | 7 | 1STY2CL | 6225448.42 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103550 | Dimatican Elementary School | PALANAN | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 395213.41 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103553 | Ditambali Elementary School | PALANAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1041574.17 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300554 | Isabela School of Fisheries | PALANAN | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2521942.79 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103556 | Marikit Elementary School | PALANAN | 1 | 1 | 8 | 1STY4CL | 8705476.5 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103557 | Palanan Central School | PALANAN | 1 | 1 | 13 | REPAIR OF CLASSROOMS | 1970292.95 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300564 | Palanan National High School | PALANAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1180855.24 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103559 | San Isidro Elementary School | PALANAN | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2769537.26 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103561 | Taknalan Primary School | PALANAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1117478.43 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 342077 | Aurora Senior High School | AURORA | 2 | 1 | 30 | REPAIR OF CLASSROOMS | 469120.6 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300546 | Andabuen National High School | BENITO SOLIVEN | 2 | 1 | 11 | REPAIR OF CLASSROOMS | 732000.87 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103526 | San Manuel Elementary School | NAGUILIAN | 2 | 1 | 3 | 1STY3CL | 5435561.66 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103638 | San Pedro-Villa Concepcion Elementary School | ROXAS | 2 | 1 | 3 | 1STY3CL | 5419811.66 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103720 | Mananao Elementary School | SAN MANUEL | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 564083.35 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103005 | Alicia Central School | ALICIA | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 5727263.7 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300500 | Alicia National High School | ALICIA | 3 | 1 | 20 | REPAIR OF CLASSROOMS | 659657.59 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 102994 | MH del Pilar Elementary School | ALICIA | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 1101200.51 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 500023 | Sto. Niño Integrated School | ANGADANAN | 3 | 1 | 16 | REPAIR OF CLASSROOMS | 2112109.45 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103175 | Nueva Era Elementary School | CABATUAN | 3 | 1 | 3 | 1STY3CL | 5419811.66 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103487 | Luna Central School | LUNA | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 603963.12 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300575 | Reina Mercedes Vocational and Industrial School | REINA MERCEDES | 3 | 1 | 32 | REPAIR OF CLASSROOMS | 949555.94 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 500015 | Dietban Integrated School | SAN GUILLERMO | 3 | 1 | 8 | 1STY3CL | 6376910.1 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103783 | Dagupan Elementary School | SAN MATEO | 3 | 1 | 3 | 1STY3CL | 5435561.66 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103787 | San Marcos Elementary School | SAN MATEO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1006060.93 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103779 | San Mateo North Central School | SAN MATEO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1006060.93 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300508 | Cagasat National High School | CORDON | 4 | 1 | 26 | REPAIR OF CLASSROOMS | 7047822.26 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103247 | Cordon South Central School-Main | CORDON | 4 | 1 | 11 | REPAIR OF CLASSROOMS | 3657282.71 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300523 | Diadi Region High School | CORDON | 4 | 1 | 19 | REPAIR OF CLASSROOMS | 3975383.12 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300532 | Dona Josefa E. Marcos High School | CORDON | 4 | 1 | 14 | REPAIR OF CLASSROOMS | 5171378.06 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103250 | Gayong Elementary School | CORDON | 4 | 1 | 3 | 1STY3CL | 5159304.84 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103251 | Kakilingan Elementary School | CORDON | 4 | 1 | 6 | 2 UNITS OF 1STY3CL | 9953071.42 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103257 | Taringsing Elementary School | CORDON | 4 | 1 | 6 | 2 UNITS OF 1STY3CL | 9953071.42 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103259 | Turod Sur Elementary School | CORDON | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 2154361.77 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103261 | Villa Marzo Elementary School | CORDON | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 1388590.18 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300526 | Dinapigue National High School | DINAPIGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 980047.9 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103306 | Arabiat Elementary School | ECHAGUE | 4 | 1 | 10 | 1STY3CL | 6568628.88 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103328 | Buneg Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 871754.35 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300529 | Don Mariano Marcos National High School | ECHAGUE | 4 | 1 | 14 | REPAIR OF CLASSROOMS | 3868697.69 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300533 | Dona Magdalena H. Gaffud HIgh School | ECHAGUE | 4 | 1 | 11 | REPAIR OF CLASSROOMS | 5701423.59 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103290 | Echague East Central School | ECHAGUE | 4 | 1 | 4 | 1STY4CL | 6686637.63 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300612 | Echague National High School | ECHAGUE | 4 | 1 | 19 | REPAIR OF CLASSROOMS | 4929894.29 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103331 | Echague West Central School | ECHAGUE | 4 | 1 | 11 | REPAIR OF CLASSROOMS | 2680456.8 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103291 | Gumbauan Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 1963974.71 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103312 | Libertad Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 932908.6 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103295 | Malibago Elementary School | ECHAGUE | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 2066443.67 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103313 | Nilumisu Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 2190468.64 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103314 | Pangal Norte Elementary School | ECHAGUE | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1019388.25 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103318 | San Carlos Elementary School | ECHAGUE | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 799093.58 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103319 | San Felipe Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 1457026.53 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103320 | San Juan Elementary School | ECHAGUE | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 1414132.39 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103321 | San Manuel Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 1482307.08 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103325 | Sta. Monica Elementary School | ECHAGUE | 4 | 1 | 2 | 1STY2CL | 3787305.68 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103323 | Sta. Ana Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 1921483.42 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103324 | Sta. Maria Elementary School | ECHAGUE | 4 | 1 | 9 | REPAIR OF CLASSROOMS | 2476229.42 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103303 | Tuguegarao-Sto. Domingo Elementary School | ECHAGUE | 4 | 1 | 8 | REPAIR OF CLASSROOMS | 2072306 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300611 | Ugad High School | ECHAGUE | 4 | 1 | 30 | REPAIR OF CLASSROOMS | 5026636.73 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103326 | Villa Fermin Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 2376598.63 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103439 | A.C. Ruiz Elementary School | JONES | 4 | 1 | 5 | 1STY5CL | 8277774.82 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103463 | Diarao Elementary School | JONES | 4 | 1 | 10 | REPAIR OF CLASSROOMS | 4573937.57 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300524 | Dibuluan National High School | JONES | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 1323613.49 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300555 | Jones Rural School - Main | JONES | 4 | 1 | 24 | REPAIR OF CLASSROOMS | 610988.53 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300600 | Sgt. Prospero Bello HS - Main | JONES | 4 | 1 | 9 | REPAIR OF CLASSROOMS | 2795018.1 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103457 | Usol Elementary School | JONES | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1318267.9 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103599 | Gen. Aguinaldo ES - Main | RAMON | 4 | 1 | 3 | 1STY3CL | 5159304.84 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300572 | General Emilio Aguinaldo National High School | RAMON | 4 | 1 | 26 | REPAIR OF CLASSROOMS | 5109619.5 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 300574 | Raniag HIgh School | RAMON | 4 | 1 | 21 | REPAIR OF CLASSROOMS | 704142.04 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103702 | Nagbukel Elementary School | SAN ISIDRO | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1253804.29 | 1 |  | Completed | 1
QRF 2019 | Region II | Isabela | 103707 | San Isidro West Central School | SAN ISIDRO | 4 | 1 | 18 | 2 UNITS OF 1STY3CL | 15183576.17 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 104187 | Abuyo ES | ALFONSO CASTAÑEDA | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 5259872.71 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 306207 | Abuyo National High School | ALFONSO CASTAÑEDA | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2880390.89 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 306207 | Abuyo National High School | ALFONSO CASTAÑEDA | 0 |  | 0 | REPAIR OF CLASSROOMS | 14989065.18 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 300615 | Alfonso CastaÃ±eda NHS | ALFONSO CASTAÑEDA | 0 | 1 | 17 | REPAIR OF CLASSROOMS | 7271745.68 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 300617 | Ambaguio High School | AMBAGUIO | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 1145955.32 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 103987 | Cablahan Elementary School | AMBAGUIO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 9636832.14 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 103988 | DACLIG ELEMENTARY SCHOOL | AMBAGUIO | 0 | 1 | 1 | REPAIR OF CLASSROOMS | 342793.35 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 103914 | Canarem PS | ARITAO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 6682705.15 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 104021 | DIADI CENTRAL SCHOOL | DIADI | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 1984210.4346 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 300627 | Diadi NHS | DIADI | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 541074.39 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 300625 | Carolotan High School | DUPAX DEL SUR | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 6253511.38 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 300628 | Dupax del Sur NHS | DUPAX DEL SUR | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 3833601.25 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 300628 | Dupax del Sur NHS | DUPAX DEL SUR | 0 |  | 0 | REPAIR OF CLASSROOMS | 15169211.15 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 104078 | Biyoy ES | KASIBU | 0 | 1 | 2 | 1STY2CL | 4347951.69 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 104100 | Paquet ES | KASIBU | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 868314.25 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 300640 | NAPO-TUYAK HS | KAYAPA | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 6206778 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 500097 | Dagupan Elementary School | QUEZON | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1058459.43 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 104158 | Maddiangat ES | QUEZON | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1516886.5775 | 1 |  | Completed | 1
QRF 2019 | Region II | Nueva Vizcaya | 300644 | Quezon NHS | QUEZON | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 1884076.32 | 1 |  | Completed | 1
QRF 2019 | Region II | Quirino | 300652 | Aglipay NHS | AGLIPAY | 0 | 1 | 11 | REPAIR OF CLASSROOMS | 2004722.84 | 1 | 2004202.15 | Completed | 1 | 2020-02-21 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-12-23 | PROLINE CONSTRUCTION
QRF 2019 | Region II | Quirino | 104293 | Balagbag Elementary School | DIFFUN | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1051009.85 | 1 | 920966.39 | Completed | 1 |  |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-09-19 | 2019-09-30 | PROLINE CONSTRUCTION
QRF 2019 | Region II | Quirino | 300657 | Diffun HS | DIFFUN | 0 | 1 | 33 | REPAIR OF CLASSROOMS | 2744322.73 | 1 | 2439820.52 | Completed | 1 |  |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-09-19 | 2019-09-30 | PROLINE CONSTRUCTION
QRF 2019 | Region II | Quirino | 500109 | Ifugao Village IS | DIFFUN | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 1926593.7 | 1 | 1728766.59 | Completed | 1 |  |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-09-19 | 2019-09-30 | PROLINE CONSTRUCTION
QRF 2019 | Region II | Quirino | 104307 | Luttuad ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | 3549295.68 | 1 | 2740548.39 | Completed | 1 | 2020-02-10 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-09-19 | 2019-11-12 | AGT Builders
QRF 2019 | Region II | Quirino | 500104 | San Antonio Integrated School | DIFFUN | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 1318056.95 | 1 | 1251820.47 | Completed | 1 | 2020-01-21 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-11-22 | PROLINE CONSTRUCTION
QRF 2019 | Region II | Quirino | 104289 | Villa Pascua ES | DIFFUN | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 930656.45 | 1 | 850056.35 | Completed | 1 | 2020-01-21 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-11-22 | PROLINE CONSTRUCTION
QRF 2019 | Region II | Quirino | 104375 | La Paz ES | SAGUDAY | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 969299.97 | 1 | 800369.21 | Completed | 1 | 2020-01-24 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-11-25 | PROLINE CONSTRUCTION
QRF 2019 | Region II | Quirino | 300665 | Saguday NHS | SAGUDAY | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 365919.14 | 1 | 341435.96 | Completed | 1 | 2020-02-21 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-12-23 | PROLINE CONSTRUCTION
QRF 2019 | Region II | Quirino | 104378 | Salvacion ES | SAGUDAY | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 621313.58 | 1 | 498503.34 | Completed | 1 | 2020-01-24 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-11-25 | PROLINE CONSTRUCTION
QRF 2019 | Region II | Quirino | 104379 | Sto. Tomas ES | SAGUDAY | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 1040150.28 | 1 | 914949.61 | Completed | 1 | 2020-01-24 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-11-25 | PROLINE CONSTRUCTION
QRF 2019 | Region II | Santiago City | 103824 | Ambalatungan ES | CITY OF SANTIAGO | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 338916.67 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 500936 | Balintocatoc Integrated School | CITY OF SANTIAGO | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 724334.1 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103811 | Baptista Village ES | CITY OF SANTIAGO | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 300638.81 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103812 | Batal ES | CITY OF SANTIAGO | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 863961.66 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103825 | Buenavista Elementary School | CITY OF SANTIAGO | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 608862.75 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 300505 | Cabulay High School | CITY OF SANTIAGO | 4 | 1 | 9 | REPAIR OF CLASSROOMS | 1820821.32 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103837 | Calaocan ES | CITY OF SANTIAGO | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 838560.11 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103813 | Divisoria ES | CITY OF SANTIAGO | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 416018.99 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 300528 | Divisoria High School | CITY OF SANTIAGO | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 209830.85 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 325204 | Divisoria High School - Naggasican Extension | CITY OF SANTIAGO | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 101253.16 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103827 | Dubinan ES | CITY OF SANTIAGO | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 2167256.36 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103814 | Luna ES | CITY OF SANTIAGO | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 507769.91 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103815 | Mabini ES | CITY OF SANTIAGO | 4 | 1 | 3 | 1STY2CL | 4132677.94 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103816 | MALINI ELEMENTARY SCHOOL | CITY OF SANTIAGO | 4 | 1 | 5 | 1STY3CL | 5742135.64 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103817 | Nabbuan ES | CITY OF SANTIAGO | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 415103.01 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103818 | Nagassican Elementary School | CITY OF SANTIAGO | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 1261468.28 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103828 | Patul Elementary School | CITY OF SANTIAGO | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 1066614.87 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 306124 | Patul National High School | CITY OF SANTIAGO | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 804175.4 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 300578 | Rizal National High School | CITY OF SANTIAGO | 4 | 1 | 11 | REPAIR OF CLASSROOMS | 1754766.33 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103838 | ROSARIO ELEMENTARY SCHOOL | CITY OF SANTIAGO | 4 | 1 | 11 | REPAIR OF CLASSROOMS | 1063138.26 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 325203 | ROSARIO NHS | CITY OF SANTIAGO | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 181214.05 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103819 | Sagana Elementary School | CITY OF SANTIAGO | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 306395.01 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 325202 | Sagana National High School | CITY OF SANTIAGO | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 108318.03 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 500937 | Salvador Integrated School | CITY OF SANTIAGO | 4 | 1 | 10 | 1STY3CL | 5912801.72 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103829 | San Isidro ES | CITY OF SANTIAGO | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 693752.39 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 300599 | Santiago City National High School | CITY OF SANTIAGO | 4 | 1 | 38 | REPAIR OF CLASSROOMS | 1287298.32 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 325201 | Santiago City National High School - Sinsayon | CITY OF SANTIAGO | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 395389.8 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103822 | Santiago East Central School | CITY OF SANTIAGO | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 809218.98 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103830 | Santiago North CS SpEd Center | CITY OF SANTIAGO | 4 | 1 | 21 | 1STY5CL | 8969133.87 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103830 | Santiago North CS SpEd Center | CITY OF SANTIAGO | 4 |  | 3 | 1STY3CL | 5229005.76 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103840 | Santiago South CS | CITY OF SANTIAGO | 4 | 1 | 3 | 1STY2CL | 3940310.71 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103840 | Santiago South CS | CITY OF SANTIAGO | 4 |  | 3 | 1STY3CL | 5307755.76 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103841 | Sta. Rosa ES | CITY OF SANTIAGO | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 816028.56 | 1 |  | Completed | 1
QRF 2019 | Region II | Santiago City | 103833 | Villa Gonzaga ES | CITY OF SANTIAGO | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 895454.85 | 1 |  | Completed | 1
QRF 2020 | Region II | Cagayan | 102432 | Logung ES | AMULUNG | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1310550.15 | 1 |  | Completed | 1
QRF 2020 | Region II | Cauayan City | 103229 | EB Tomaneng ES | CITY OF CAUAYAN | 6 | 1 | 4 | REPAIR OF CLASSROOMS | 1094004.18 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102443 | Dodan ES | APARRI | 1 | 1 | 11 | TY ULYSSES | 1961193.0659 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102444 | Gaddang ES | APARRI | 1 | 1 | 12 | TY ULYSSES | 2706117.1772 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102445 | Macanaya ES | APARRI | 1 | 1 | 9 | Repair | 2141175.2013 | 1 |  | Completed | 1 | 2021-12-07 | [9 empty] | Action Taken: abondoned (Issued of notice of termination) but commited to resumed until its completion) *They Already resume on the project site and comtinue the remaining item of works hoping to finished by the end of January 2023
QRF 2021 | Region II | Cagayan | 102665 | Aguiguican ES | GATTARAN | 1 | 1 | 7 | TY ULYSSES | 2481050.2 | 1 |  | Completed | 1 | 2021-11-15
QRF 2021 | Region II | Cagayan | 102653 | Capissayan Elementary School | GATTARAN | 1 | 1 | 3 | TY ULYSSES | 1050018.12 | 1 |  | Completed | 1 | 2021-12-07
QRF 2021 | Region II | Cagayan | 102668 | Casicallan ES | GATTARAN | 1 | 1 | 8 | TY ULYSSES | 2900130.75 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102659 | Naddungan ES | GATTARAN | 1 | 1 | 7 | TY ULYSSES | 2490205.2 | 1 |  | Completed | 1 | 2021-11-15 | [9 empty] | implementation of corrective observation and variation oerder
QRF 2021 | Region II | Cagayan | 300475 | Logac National High School | LAL-LO | 1 | 1 | 7 | TY ULYSSES | 1969398.067 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102749 | Malanao Elementary School | LAL-LO | 1 | 1 | 7 | TY ULYSSES | 2339361.5155 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102605 | Bilibigao ES | CLAVERIA | 2 | 1 | 5 | TY ULYSSES | 1750000.69 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 300449 | Claveria NHS | CLAVERIA | 2 | 1 | 10 | TY ULYSSES | 4685211.96 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102920 | Mabnang ES | CLAVERIA | 2 | 1 | 3 | TY ULYSSES | 1681214.97 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102613 | Magdalena ES | CLAVERIA | 2 | 1 | 3 | TY ULYSSES | 726196.1333 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102621 | Santiago ES | CLAVERIA | 2 | 1 | 3 | TY ULYSSES | 2325142.58 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102755 | Aggunetan ES | LASAM | 2 | 1 | 1 | TY ULYSSES | 615737.8313 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102848 | Bangan ES | SANCHEZ-MIRA | 2 | 1 | 6 | TY ULYSSES | 2535057.7196 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 155007 | Niug Norte ES | SANTO NIÑO (FAIRE) | 2 | 1 | 4 | TY ULYSSES | 1283384.6162 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102402 | Abolo ES | AMULUNG | 3 | 1 | 6 | TY ULYSSES | 2998603.6336 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102633 | Enrile North CS | ENRILE | 3 | 1 | 20 | TY ULYSSES | 5606467.2195 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102634 | Enrile West CS | ENRILE | 3 | 1 | 12 | TY ULYSSES | 2924320.6537 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102641 | Sabino Acorda CS | ENRILE | 3 | 1 | 10 | TY ULYSSES | 2502488.1509 | 1 |  | Completed | 1
QRF 2021 | Region II | Cagayan | 102722 | Sta. Teresa ES | IGUIG | 3 | 1 | 3 | TY ULYSSES | 1050121.8 | 1 |  | Completed | 1 | 2021-12-04
QRF 2021 | Region II | Cagayan | 102804 | Nanguillattan E/S | PEÑABLANCA | 3 | 1 | 6 | TY ULYSSES | 1949536.599 | 1 |  | Completed | 1 | 2021-12-04 | [9 empty] | subtantially completed ( implementation of corrective observation and variation oerder
QRF 2021 | Region II | Cagayan | 102866 | Andarayan ES | SOLANA | 3 | 1 | 2 | TY ULYSSES | 832231.7522 | 1 |  | Completed | 1 | 2021-12-04 | [9 empty] | implementation of corrective observation and variation oerder
QRF 2021 | Region II | City of Ilagan | 103367 | Marana 2nd ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 2 | TY ULYSSES | 3932382.7094 | 1 |  | Completed | 1 | 2021-11-01
QRF 2021 | Region II | Isabela | 103139 | Aggub Elementary School | CABANGAN | 1 | 1 | 4 | TY ULYSSES | 2733999.3079 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103158 | Pilig Abajo Elementary School | CABANGAN | 1 | 1 | 7 | TY ULYSSES | 1341684.8855 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103159 | Pilig Alto Elementary School | CABANGAN | 1 | 1 | 9 | TY ULYSSES | 1774795.9471 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103270 | Jimenez Multigrade School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 2 | TY ULYSSES | 631161.8695 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103847 | Mozzozzin Elementary School | SANTA MARIA | 1 | 1 | 11 | TY ULYSSES | 3864847.0826 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103853 | San Rafael Elementary School | SANTA MARIA | 1 | 1 | 5 | TY ULYSSES | 932853.6959 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103872 | Ammugauan Primary School | SANTO TOMAS | 1 | 1 | 2 | TY ULYSSES | 309086.169 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103867 | Malapagay Elementary School | SANTO TOMAS | 1 | 1 | 5 | TY ULYSSES | 724487.0373 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103868 | San Rafael Abajo Primary School | SANTO TOMAS | 1 | 1 | 4 | TY ULYSSES | 1045842.6512 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103876 | Fugu Abajo Elementary School | TUMAUINI | 1 | 1 | 8 | TY ULYSSES | 1091831.4829 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103877 | Fugu Elementary School | TUMAUINI | 1 | 1 | 2 | TY ULYSSES | 4169034.1674 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 300586 | Josefina Albano National High School | TUMAUINI | 1 | 1 | 7 | TY ULYSSES | 1837727.1495 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103879 | Malamag Elementary School | TUMAUINI | 1 | 1 | 5 | TY ULYSSES | 1150062.2194 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103900 | Paragu Elementary School | TUMAUINI | 1 | 1 | 3 | TY ULYSSES | 5889429.2734 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103885 | San Mateo Elementary School | TUMAUINI | 1 | 1 | 6 | TY ULYSSES | 3398709.8655 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103883 | Sta. Catalina Elementary School | TUMAUINI | 1 | 1 | 3 | TY ULYSSES | 1918330.2681 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 103904 | Tumauini West Central School | TUMAUINI | 1 | 1 | 2 | TY ULYSSES | 3839412.9575 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 500075 | Banquero Integrated School | REINA MERCEDES | 2 | 1 | 2 | TY ULYSSES | 4169034.1674 | 1 |  | Completed | 1
QRF 2021 | Region II | Isabela | 501150 | Daragutan West Integrated School | SAN MARIANO | 2 | 1 | 2 | TY ULYSSES | 3839412.9575 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 300615 | Alfonso CastaÃ±eda NHS | ALFONSO CASTAÑEDA | 0 | 1 | 1 | TY ULYSSES | 1875000 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 300617 | Ambaguio High School | AMBAGUIO | 0 | 1 | 3 | TY ULYSSES | 1650000 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 103991 | Labang ES | AMBAGUIO | 0 | 1 | 4 | TY ULYSSES | 2440000 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 300525 | Tiblac National High School | AMBAGUIO | 0 | 1 | 5 | TY ULYSSES | 2750000 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 103966 | Abian ES | BAMBANG | 0 | 1 | 9 | TY ULYSSES | 4950000 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 103951 | Aliaga ES | BAMBANG | 0 | 1 | 5 | TY ULYSSES | 2750000 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 103964 | San Leonardo ES | BAMBANG | 0 | 1 | 6 | TY ULYSSES | 3000000 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 103990 | Kakilingan ES | BAYOMBONG (Capital) | 0 | 1 | 2 | TY ULYSSES | 1096000 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 104046 | Lamo ES | DUPAX DEL NORTE | 0 | 1 | 2 | TY ULYSSES | 5039545 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 306208 | Eastern Nueva Vizcaya National High School | KASIBU | 0 | 1 | 2 | TY ULYSSES | 1040000 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 104100 | Paquet ES | KASIBU | 0 | 1 | 4 | TY ULYSSES | 2200000 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 500097 | Dippog HS | QUEZON | 0 | 1 | 4 | TY ULYSSES | 2040000 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 300649 | Santa Fe National High School | SANTA FE | 0 | 1 | 3 | TY ULYSSES | 1100000 | 1 |  | Completed | 1
QRF 2021 | Region II | Nueva Vizcaya | 300651 | Uddiawan National High School | SOLANO | 0 | 1 | 4 | TY ULYSSES | 1680000 | 1 |  | Completed | 1
QRF 2021 | Region II | Quirino | 501561 | Der-an Integrated School | DIFFUN | 0 | 1 | 4 | TY ULYSSES | 1576661.54 | 1 | 1565908.07 | Completed | 1 |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-24 | 619 Builders Const. Corp. | completed including savings
QRF 2021 | Region II | Quirino | 156507 | Turayok Elementary School | DIFFUN | 0 | 1 | 3 | TY ULYSSES | 502430.56 | 1 | 499757.77 | Completed | 1 |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-24 | 619 Builders Const. Corp. | completed including savings
QRF 2021 | Region II | Quirino | 500105 | San Martin IS | MADDELA | 0 | 1 | 10 | TY ULYSSES | 2232025.25 | 1 |  | Completed | 1 |  |  |  |  | 2021-07-28 | 2021-08-03 | 2021-08-16 |  | 2021-10-11 | Proline Construction | completed including savings
QRF 2021 | Region II | Quirino | 104338 | San Salvador ES | MADDELA | 0 | 1 | 4 | TY ULYSSES | 1495055.32 | 1 | 1240011.28 | Completed | 1 |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-16 | Dalcon Construction | completed including savings
QRF 2021 | Region II | Quirino | 500626 | Villa Gracia IS | MADDELA | 0 | 1 | 6 | TY ULYSSES | 2040756.69 | 1 | 1693717.4 | Completed | 1 |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-16 | Dalcon Construction | completed including savings
QRF 2021 | Region II | Quirino | 501849 | Kimmabayo Integrated School | NAGTIPUNAN | 0 | 1 | 3 | TY ULYSSES | 337821.8 | 1 |  | Completed | 1 |  |  |  |  | 2021-07-28 | 2021-08-03 | 2021-08-16 |  | 2021-10-11 | Proline Construction | completed including savings
QRF 2021 | Region II | Quirino | 104380 | Tres Reyes ES | SAGUDAY | 0 | 1 | 7 | TY ULYSSES | 1989445.35 | 1 | 1979701.36 | Completed | 1 |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-24 | 619 Builders Const. Corp. | completed including savings
QRF 2022 | Region II | Batanes | 102311 | Basco Central School | BASCO (Capital) | 0 | 1 | 7 | REPAIR/ REHABILITATION | 5231221.642 | 1 | 4700000 | Completed | 1 | [10 empty] | with RTA
QRF 2022 | Region II | Batanes | 102311 | Basco Central School | BASCO (Capital) | 0 |  | 18 | REPAIR/ REHABILITATION | 12917785.63 | 1 | 9900121.12 | Completed | 1 | [10 empty] | with RTA
QRF 2022 | Region II | Batanes | 300411 | Batanes National Science High School | BASCO (Capital) | 0 | 1 | 12 | REPAIR/ REHABILITATION | 12975814.84 | 1 | 9450161.12 | Completed | 1 | [10 empty] | with RTA
QRF 2022 | Region II | Batanes | 500063 | Raele Integrated School | Itbayat | 0 | 1 | 1 | REPAIR/ REHABILITATION | 1301588.05 | 1 | 1154807.42 | Completed | 1 | [10 empty] | with RTA
QRF 2022 | Region II | Batanes | 102325 | Mahatao Elementary School | Mahatao | 0 | 1 | 2 | REPAIR/ REHABILITATION | 1731420.844 | 1 | 1506917.26 | Completed | 1 | [10 empty] | with RTA
QRF 2022 REPLENISHMENT | Region II | City of Ilagan | 306105 | Isabela School of Arts and Trades-Main | CITY OF ILAGAN | 1st | 1 | 0 | REPAIR OF CLASSROOMS | 2097038.4 | 1 | 1672031.73 | Completed | 1 | 2023-09-05 |  |  |  | 2023-02-16 | 2023-02-24 | 2023-03-08 | 2023-03-24 | 2023-05-02 | ARKHITEKTON BUILDERS AND CONSTRUCTION SUPPLY
QRF 2022 REPLENISHMENT | Region II | Isabela | 103854 | Sta. Maria Central School | Sta Maria | 1st | 1 | 6 | Replacement | 9000000 | 1 | 6497594.9 | Completed | 1
QRF 2022 REPLENISHMENT | Region II | Isabela | 103571 | Quezon Central School | Quezon | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 300000 | 1 | 2811053.126 | Completed | 1
QRF 2022 REPLENISHMENT | Region II | Isabela | 103311 | Echague South Central School | Echague | 4th | 1 | 1 | REPAIR OF CLASSROOMS | 75000 | 1 |  | Completed | 1
QRF 2022 REPLENISHMENT | Region II | Nueva Vizcaya | 300622 | Belance HS | DUPAX DEL NORTE | Lone | 1 | 8 | REPAIR OF CLASSROOMS | 5350000 | 1 | 4254236.78 | Completed | 1 | 90 Calendar Days | October 22, 2024 | PB 05-001 s. 2023 |  | 2023-03-13 | 2023-03-20 | 2023-04-03 | 2023-05-15 | June 9, 2023 | ZYMX CONSTRUCTION | with savings contract amount: 1,095,763.22
QRF 2022 REPLENISHMENT | Region II | Nueva Vizcaya | 104088 | Kasibu Central School | KASIBU | Lone | 1 | 7 | REPAIR OF CLASSROOMS | 4940000 | 1 | 3794462.33 | Completed | 1 | 65 Calendar Days | 2023-12-05 | PB 05-002 s. 2023 |  | 2023-03-13 | 2023-03-20 | 2023-04-03 | 2023-05-15 | 2023-05-22 | IA Castañeda Construction | with savings contract amount: 1,145, 537.67
QRF 2022 REPLENISHMENT | Region II | Nueva Vizcaya | 300623 | Bintawan NHS | VILLAVERDE | Lone | 1 | 10 | REPAIR OF CLASSROOMS | 6500000 | 1 | 5184581.51 | Completed | 1 | 95 Calendar Days | January 13, 2024 | PB 05-003 s. 2023 |  | 2023-03-13 | 2023-03-20 | 2023-04-03 | 2023-05-15 | 2023-05-22 | Mighty Construction | with savings contract amount: 1,315,418.48
QRF 2023 | Region II | Nueva Vizcaya | 103980 | Ambaguio CS | AMBAGUIO | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 6249523.32 | 2-R | 4415902.41 | Completed | 1 | 118 Calendar Days |  | PB12-001-QRF-Lot 1 |  | December 1, 2023 | December 11, 2023 | December 27, 2023 | January 24, 2024 | February 2, 2024 | IA Castañeda Construction | with savings contract amount: 4,415,902.41
QRF 2023 | Region II | Nueva Vizcaya | 306202 | Bonfa National High School | BAYOMBONG (Capital) | Lone | 1 | 1 | REPAIR OF CLASSROOMS | 600000 | 2-R | 562547.02 | Completed | 1 | 60 Calendar Days | April 15, 2024 | PB12-001-QRF-Lot 3 |  | December 1, 2023 | December 11, 2023 | December 27, 2023 | January 24, 2024 | February 16, 2024 | Mighty Construction | with additional works amount: 37,452.98
QRF 2023 | Region II | Nueva Vizcaya | 104223 | Villaverde Central School | VILLAVERDE | Lone | 1 | 2 | REPAIR OF CLASSROOMS | 1350000 | 2-R | 952179.1 | completed | 1 | 60 Calendar Days |  | PB12-001-QRF-Lot 2 |  | December 1, 2023 | December 11, 2023 | December 27, 2023 | January 24, 2024 | February 2, 2024 | IA Castañeda Construction | with savings contract amount: 397,820.9
QRF 2024 | Region II | Cagayan | 300438 | Cabatacan National High School | LASAM | 2nd | 1 | 21 | Repair of Classrooms | 9077261.28 | 1- R |  | Completed | 1
QRF 2024 | Region II | Cagayan | 300474 | Licerio Antiporda Sr. NHS | BUGUEY | 1st | 1 | 37 | Repair of Classrooms | 40000000 | 2-R |  | Ongoing | 0.2
QRF 2024 | Region II | Batanes | 102314 | Tukon Elementary School | BASCO (Capital) | Lone | 1 | 4 | REPAIR OF CLASSROOMS | 597975.19 | 3-R |  | Ongoing | 0
QRF 2024 | Region II | Batanes | 102311 | Basco Central School | BASCO (Capital) | Lone | 1 | 18 | REPAIR OF CLASSROOMS | 2212337.67 | 3-R |  | Ongoing | 0
QRF 2024 | Region II | Batanes | 102324 | Uyugan Elementary School | UYUGAN | Lone | 1 | 1 | REPAIR OF CLASSROOMS | 1570530.77 | 3-R |  | Ongoing | 0
QRF 2024 | Region II | Batanes | 102325 | Mahatao Elementary School | MAHATAO | Lone | 1 | 7 | REPAIR OF CLASSROOMS | 774860.41 | 3-R |  | Ongoing | 0
QRF 2024 | Region II | Batanes | 300411 | Batanes Nat"l Science High School | BASCO (Capital) | Lone | 1 | 8 | REPAIR OF CLASSROOMS | 921614.29 | 3-R |  | Ongoing | 0
QRF 2024 | Region II | Batanes | 300416 | Mahatao NHS | MAHATAO | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 867866.43 | 3-R |  | Ongoing | 0
QRF 2024 | Region II | Batanes | 500062 | Itbud Integrated School | UYUGAN | Lone | 1 | 4 | REPAIR OF CLASSROOMS | 1026956.74 | 3-R |  | Ongoing | 0.2
QRF 2024 | Region II | Batanes | 501736 | Valugan Integrated School | BASCO (Capital) | Lone | 1 | 2 | REPAIR OF CLASSROOMS | 933117.02 | 3-R |  | Ongoing | 0.5

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%