## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 4, 2025
SCHOOL HEALTH FACILITIES 2024 | Region IV-B | Romblon | 301769 | Odiongan National High School | ODIONGAN | Lone | 1 |  | Construction of School Clinic | 3104073.56 |  | 339381.46 | Completed | 1 | August 16, 2024 | August 15, 2024 | BEFF-H-001 | BEFF-H-001 | November 30, 2023 | December 11, 2023 | December 27, 2023 | January 12, 2024 | July 2, 2024 | N.T. Sotelo Construction and Supply Corporation
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 110741 | Algeciras ES | AGUTAYA | 1 | 1 | 3 | PROPOSED CONSTRUCTION OF THREE (3) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (UPDATED OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 665864.2309 | BATCH 1 |  | completed | 1 | [9 empty] | RBM2 CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 110964 | Cagayancillo CS | CAGAYANCILLO | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (UPDATED OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 447119.7178 | BATCH 1 |  | ongoing | 0 | [9 empty] | LCM | For Termination
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 110970 | Sta Cruz ES | CAGAYANCILLO | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (UPDATED OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH | 447119.7178 | BATCH 1 |  | ongoing | 0 | [9 empty] | LCM | For Termination
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 301677 | Cagayancillo NHS | CAGAYANCILLO | 1 | 1 | 3 | PROPOSED CONSTRUCTION OF THREE (3) UNIT GROUP HANDWASHING FACILITY - FOR SECONDARY (UPDATED OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH | 675176.8331 | BATCH 1 |  | ongoing | 0 | [9 empty] | LCM | For Termination
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 110949 | Nangalao ES | LINAPACAN | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (UPDATED OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH | 444710.0724 | BATCH 1 |  | Completed | 1 | [9 empty] | RBM2 CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 309165 | Nangalao NHS | LINAPACAN | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNIT GROUP HANDWASHING FACILITY - FOR SECONDARY (UPDATED OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 449394.4926 | BATCH 1 |  | Completed | 1 | [9 empty] | RBM2 CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 301689 | Danawan National High School | MAGSAYSAY | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNIT GROUP HANDWASHING FACILITY - FOR SECONDARY (UPDATED OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 425039.931 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 301698 | Gaudencio Abordo Mem. National High School - Rizal NHS | MAGSAYSAY | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (UPDATED OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH | 425039.931 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111192 | Macatumbalen Elementary School | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 266050.1778 | BATCH 1 |  | ongoing | 0 | [9 empty] | LCM | For Termination
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111193 | New Agutaya ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 266050.178 | BATCH 1 |  | ongoing | 0.05 | [9 empty] | LCM | For Termination
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111201 | San Vicente CS | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 263482.09 | BATCH 1 |  | ongoing | 0.05 | [9 empty] | LCM | For Termination
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111199 | Panindigan ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 263473.62 | BATCH 1 |  | ongoing | 0
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111200 | Port Barton ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 266050.1778 | BATCH 1 |  | ongoing | 0.1 | [9 empty] | LCM | For Termination
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111191 | Kemdeng ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 266050.1778 | BATCH 1 |  | ongoing | 0.05 | [9 empty] | LCM | For Termination
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111190 | Irawan ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 266050.1778 | BATCH 1 |  | ongoing | 0
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111204 | TDC ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 266050.1778 | BATCH 1 |  | ongoing | 0 | [9 empty] | LCM | For Termination
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 301660 | Alimanguan NHS | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 268172.9547 | BATCH 1 |  | ongoing | 0
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 301738 | San Vicente NHS | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 265604.86 | BATCH 1 |  | ongoing | 0
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 301723 | Port Barton NHS | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 265604.86 | BATCH 1 |  | ongoing | 0.5 | [9 empty] | LCM | For Termination
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 301777 | Tugdan NHS | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 178748.66 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111262 | Gui-ob Elementary School | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 177047.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111265 | San Roque Elementary School | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 177047.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111255 | Alcantara CES | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 171797.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111266 | Tugdan ES | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 177047.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 171004 | Felipe Madali MES | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 177047.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111261 | Don Manuel L. Solidum Memorial Elementary School | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 177047.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 301750 | Banton NHS | BANTON | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 199748.66 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111269 | Banton CES | BANTON | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 198047.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111393 | Balogo ES | CALATRAVA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 182297.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111397 | Calatrava Elementary School | CALATRAVA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 182297.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 309201 | Calatrava National High School | CALATRAVA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 183998.66 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111412 | Josefina Fetalino Malayo ES | CALATRAVA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 182297.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111319 | Tacasan ES | CORCUERA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 198047.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 301766 | Mabini NHS | CORCUERA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 199748.66 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111315 | Mahaba Elementary School | CORCUERA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 198047.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111307 | Alegria ES | CORCUERA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 198047.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 301757 | Corcuera National High School | CORCUERA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 199748.66 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111350 | Bunsoran ES | FERROL | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111351 | Claro M. Recto ES | FERROL | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111292 | Magdiwang ES | MAGDIWANG | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 182297.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111286 | Dulangan ES | MAGDIWANG | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 309207 | Agutay NHS | MAGDIWANG | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 189248.66 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111289 | Ipil ES | MAGDIWANG | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111297 | Tampayan ES | MAGDIWANG | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111394 | Bonga ES | SANTA MARIA (IMELDA) | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111401 | Concepcion Norte ES | SANTA MARIA (IMELDA) | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 182297.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111415 | Talamban Elementary School | SANTA MARIA (IMELDA) | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 |  | Completed | 1

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%