## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 4, 2025
QRF 2019 | Region IV-B | Calapan City | 309402 | Bucayao National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 668442 | 1 | 658416 | Completed | 1 | 11/28/2019 | 11/28/2019 |  | 2019-06 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | Karangyan Builders & Traders
QRF 2019 | Region IV-B | Calapan City | 111573 | Canubing I ES | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1554987 | 1 | 1544102 | Completed | 1 | 11/28/2019 | 11/28/2019 |  | 2019-06 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | Karangyan Builders & Traders
QRF 2019 | Region IV-B | Calapan City | 111574 | Canubing II ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1025876 | 1 | 1015617 | Completed | 1 | 11/28/2019 | 11/28/2019 |  | 2019-06 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | Karangyan Builders & Traders
QRF 2019 | Region IV-B | Calapan City | 111560 | Gutad ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1405062 | 1 | 1394529 | Completed | 1 | 12/18/2019 | 02/01/2020 |  | 2019-07 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | Karangyan Builders & Traders
QRF 2019 | Region IV-B | Calapan City | 111576 | Masipit ES | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1952400 | 1 | 1941661 | Completed | 1 | 12/04/2019 | 12/04/2019 |  | 2019-05 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | CMSEL Construction & Developer
QRF 2019 | Region IV-B | Calapan City | 301802 | Nag-iba National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1109501 | 1 | 1098960 | Completed | 1 | 12/18/2019 | 02/01/2020 |  | 2019-07 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | Karangyan Builders & Traders
QRF 2019 | Region IV-B | Calapan City | 111577 | Patas ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1511065 | 1 | 1500487 | Completed | 1 | 12/04/2019 | 12/04/2019 |  | 2019-05 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | CMSEL Construction & Developer
QRF 2019 | Region IV-B | Calapan City | 111569 | Sta. Cruz ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1481854 | 1 | 1471481 | Completed | 1 | 12/18/2019 | 02/01/2020 |  | 2019-07 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | Karangyan Builders & Traders
QRF 2019 | Region IV-B | Palawan | 111003 | Funda Elementary School | CUYO | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 780144.31 | 1 | 779259.89 | Completed | 1
QRF 2020 | Region IV-B | Calapan City | 111555 | Biga ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1149457.96 | 1 | 1067846.44 | Completed | 1 | November 10, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 014 | 2020-03 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 1
QRF 2020 | Region IV-B | Calapan City | 111558 | Camansihan ES | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1106478.4 | 1 | 1024709.64 | Completed | 1 | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 005 | 2020-06 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 6
QRF 2020 | Region IV-B | Calapan City | 111559 | Camilmil CS | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1151756.08 | 1 | 1063222.41 | Completed | 1 | October 31, 2020 |  | QRF 2020 - RIVB - CALAPAN CITY - 006 | 2020-04 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | ETVR TRADING & CONSTRUCTION | CLUSTER 2
QRF 2020 | Region IV-B | Calapan City | 111573 | Canubing I ES | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1096114.97 | 1 | 1015660.13 | Completed | 1 | December 9, 2020 | 11/28/2019 | QRF 2020 - R IVB - CALAPAN CITY - 023 | 2020-05 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS
QRF 2020 | Region IV-B | Calapan City | 301801 | Ceriaco A. Abes MNHS | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1718856.97 | 1 | 1591165.03 | Completed | 1 | October 31, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 020 | 2020-04 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | ETVR TRADING & CONSTRUCTION | CLUSTER 2
QRF 2020 | Region IV-B | Calapan City | 301797 | Community Voc. HS | CITY OF CALAPAN (Capital) | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2131209.83 | 1 | 1973713.43 | Completed | 1 | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 017 | 2020-06 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 6
QRF 2020 | Region IV-B | Calapan City | 111575 | F. Samaco MS | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2726741.15 | 1 | 2482076.21 | Completed | 1 | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 009 | 2020-08 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | ETVR TRADING & CONSTRUCTION | CLUSTER 8
QRF 2020 | Region IV-B | Calapan City | 111537 | Guinobatan ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1833943.77 | 1 | 1696397.99 | Completed | 1 | February 20, 2021 |  | QRF 2020 - R IVB - CALAPAN CITY - 011 |  | June 23, 2020 | July 1, 2020 | July 13, 2020 | September 1, 2020 | September 7, 2020 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 4
QRF 2020 | Region IV-B | Calapan City | 111560 | Gutad ES | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1567604.19 | 1 | 1456304.3 | Completed | 1 | November 10, 2020 | 02/01/2020 | QRF 2020 - R IVB - CALAPAN CITY - 007 | 2020-03 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS
QRF 2020 | Region IV-B | Calapan City | 111563 | M. Pesig MES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1512438.99 | 1 | 1405055.82 | Completed | 1 | November 10, 2020 |  | QRF 2020 - RIVB - CALAPAN CITY - 004 | 2020-03 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 1
QRF 2020 | Region IV-B | Calapan City | 111565 | Malamig ES | CITY OF CALAPAN (Capital) | 1 | 1 | 1 | REPAIR OF CLASSROOM | 559919.5 | 1 | 520501.17 | Completed | 1 | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 019 | 2020-07 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 7
QRF 2020 | Region IV-B | Calapan City | 301805 | Managpi NHS | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 2176105.41 | 1 | 2015291.22 | Completed | 1 | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 018 | 2020-06 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 6
QRF 2020 | Region IV-B | Calapan City | 111576 | Masipit ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1939391.94 | 1 | 1793937.55 | Completed | 1 | February 16, 2021 | 12/04/2019 | QRF 2020 - R IVB - CALAPAN CITY - 008 |  | June 23, 2020 | July 1, 2020 | July 13, 2020 | September 1, 2020 | September 7, 2020 | CMSEL CONSTRUCTION AND DEVELOPER
QRF 2020 | Region IV-B | Calapan City | 111542 | N. Aboboto MS | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 2006921.61 | 1 | 1856402.49 | Completed | 1 | February 20, 2021 |  | QRF 2020 - R IVB - CALAPAN CITY - 013 |  | June 23, 2020 | July 1, 2020 | July 13, 2020 | September 1, 2020 | September 7, 2020 |  | CLUSTER 4
QRF 2020 | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 6550389.71 | 1 | 6089569.8 | Completed | 1 | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 003 | 2020-07 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 7
QRF 2020 | Region IV-B | Calapan City | 111577 | Patas ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 2839995 | 1 | 2631648.51 | Completed | 1 | December 9, 2020 | 12/04/2019 | QRF 2020 - R IVB - CALAPAN CITY - 010 | 2020-05 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS
QRF 2020 | Region IV-B | Calapan City | 301803 | Pedro V. Panaligan NHS | CITY OF CALAPAN (Capital) | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 4501423.16 | 1 | 4016924.65 | Completed | 1 | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 016 | 2020-08 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | ETVR TRADING & CONSTRUCTION | CLUSTER 8
QRF 2020 | Region IV-B | Calapan City | 111546 | San Antonio ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1664056.86 | 1 | 1540616.68 | Completed | 1 | October 31, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 012 | 2020-04 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | ETVR TRADING & CONSTRUCTION | CLUSTER 2
QRF 2020 | Region IV-B | Calapan City | 111579 | Sta. Isabel ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1515105.36 | 1 | 1403896.63 | Completed | 1 | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 025 | 2020-05 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 5
QRF 2020 | Region IV-B | Calapan City | 111549 | Suqui ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1656112.6 | 1 | 1531904.15 | Completed | 1 | February 20, 2021 |  | QRF 2020 - R IVB - CALAPAN CITY - 002 |  | June 23, 2020 | July 1, 2020 | July 13, 2020 | September 1, 2020 | September 7, 2020 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 4
QRF 2020 | Region IV-B | Calapan City | 111581 | Tawagan ES | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 3180086.03 | 1 | 2941579.58 | Completed | 1 | February 16, 2021 |  | QRF 2020 - R IVB - CALAPAN CITY - 022 |  | June 23, 2020 | July 1, 2020 | July 13, 2020 | September 1, 2020 | September 7, 2020 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 3
QRF 2020 | Region IV-B | Occidental Mindoro | 110079 | BALANGABONG ES | CALINTAAN | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 900000 | 1 | 899863.16 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110081 | CALINTAAN CS | CALINTAAN | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 3000000 | 1 | 2999752.23 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110085 | IRIRON ES | CALINTAAN | 0 | 1 | 14 | REPAIR OF CLASSROOMS | 4200000 | 1 | 4199429.32 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110092 | TANYAG ES | CALINTAAN | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1500000 | 1 | 1499365.5 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110116 | ALIBOG ES | MAGSAYSAY | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199818.93 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110125 | CALAWAG ES | MAGSAYSAY | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1050000 | 1 | 1049150.16 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110128 | EMOK ES | MAGSAYSAY | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1750000 | 1 | 1749528.51 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110130 | GARZA PS | MAGSAYSAY | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1600000 | 1 | 1599083.86 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110133 | LASTE ES | MAGSAYSAY | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1400000 | 1 | 1399590.4 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110139 | PACLOLO ES | MAGSAYSAY | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1400000 | 1 | 1399780.26 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110140 | PURNAGA ES | MAGSAYSAY | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1750000 | 1 | 1749465.21 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110146 | TALABA ES | MAGSAYSAY | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 2450000 | 1 | 2449787.33 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110200 | MAGSIKAP ES | RIZAL | 0 | 1 | 8 | REPAIR OF CLASSROOMS | 2400000 | 1 | 2399128.56 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110201 | MALAWAAN ES | RIZAL | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 2500000 | 1 | 2498701 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110207 | SAN PEDRO ES | RIZAL | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1400000 | 1 | 1398913.51 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110208 | SANTO NINO ES | RIZAL | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199684.17 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110230 | BALANI MINORITY SCHOOL | SABLAYAN | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1600000 | 1 | 1578552.72 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110276 | AMBULONG ES ANNEX-BULWANG PS | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 798180.39 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110277 | AMBULONG ES ANNEX-PATAG PS | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799200.43 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 500153 | AMBULONG ISLAND INTEGRATED SHOOL | SAN JOSE | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2400000 | 1 | 2399204.12 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110278 | ANSIRAY ES | SAN JOSE | 0 | 1 | 8 | REPAIR OF CLASSROOMS | 3200000 | 1 | 3198350.41 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110249 | BAGONG SIKAT ES | SAN JOSE | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 3600000 | 1 | 3599083.88 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110279 | BANGKAL ES | SAN JOSE | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199113.05 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110251 | BUBOG 2 ES | SAN JOSE | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199294.28 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110280 | BUNLAO ES | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 798945.42 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110281 | BURI ES | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799710.45 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110283 | CATAYUNGAN ES | SAN JOSE | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199736.37 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110284 | CATAYUNGAN ES ANNEX-SILOM PS | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799200.43 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110285 | ILING ES | SAN JOSE | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2400000 | 1 | 2399778.21 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110286 | INASAKAN ES | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799109.03 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110287 | IPIL ES | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799455.44 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110288 | LABANGAN ES | SAN JOSE | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199299.83 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110290 | MANGA ES | SAN JOSE | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1600000 | 1 | 1599620.32 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110291 | NATANDOL ES | SAN JOSE | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1600000 | 1 | 1599927.25 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110292 | PAWICAN ES | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 900000 | 1 | 899605.36 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110293 | PAWICAN ES ANNEX-PITOGO PS | SAN JOSE | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2700000 | 1 | 2699401.16 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110294 | PAWICAN ES ANNEX-TABAY PS | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799378.93 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110295 | PAWICAN ES ANNEX-TIBAGO PS | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799225.93 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110268 | PULANG LUPA ES | SAN JOSE | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1750000 | 1 | 1749465.21 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110257 | BATO-ILI MINORITY SCHOOL | SAN JOSE | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199134.91 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110259 | DANLOG MINORITY SCHOOL | SAN JOSE | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1500000 | 1 | 1499526.59 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110302 | MABINI II ES | SAN JOSE | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 2700000 | 1 | 2699472.38 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 308901 | SAN JOSE NAT'L AGRI'L & IND'L HS | SAN JOSE | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 3000000 | 1 | 2998443.11 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110274 | TUGTUGIN ES | SAN JOSE | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 1800000 | 1 | 1799839.2 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110315 | YAWI-YAWI - I ES | SAN JOSE | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199949.59 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Occidental Mindoro | 110316 | YAWI-YAWI II PS | SAN JOSE | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2000000 | 1 | 1999753.49 | Completed | 1 | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18
QRF 2020 | Region IV-B | Oriental Mindoro | 110335 | LANTUYANG ES | BACO | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1512842.8 | 1 | 1499204.44 | Completed | 1 | Nov. 23, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | 2020-07-09 | Aug. 17, 2020 | FS Sugay Const & Supplies | NTP issued
QRF 2020 | Region IV-B | Oriental Mindoro | 110336 | LUMANGBAYAN ES | BACO | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2743732.77 | 1 | 2732012.5 | Completed | 1 | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | 2020-07-09 | Aug. 14, 2020 | Kasanga Const and Supplies | NTP issued
QRF 2020 | Region IV-B | Oriental Mindoro | 110337 | WATER ES | BACO | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1292745.36 | 1 | 1277035.62 | Completed | 1 | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | 2020-07-09 | Aug. 14, 2020 | Etvr Trading and Const | NTP issued
QRF 2020 | Region IV-B | Oriental Mindoro | 110545 | B. AGUILON ES | NAUJAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1586140.76 | 1 | 1583793.21 | Completed | 1 | Dec. 17, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | Aug. 28, 2020 | Sept. 11,200 | Etvr Trading and Const | To be awarded to second lowest bidder
QRF 2020 | Region IV-B | Oriental Mindoro | 110512 | DEL PILAR ES | NAUJAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1097794.26 | 1 | 1083472.5 | Completed | 1 | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | 2020-07-09 | Aug. 14, 2020 | Etvr Trading and Const | NTP issued
QRF 2020 | Region IV-B | Oriental Mindoro | 110606 | TIGUIHAN ES | POLA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1144602.79 | 1 | 1136949.8 | Completed | 1 | Dec. 17, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | Aug. 28, 2020 | Sept. 11,200 | Etvr Trading and Const | To be awarded to second lowest bidder
QRF 2020 | Region IV-B | Oriental Mindoro | 110626 | VILLAFLOR ES | PUERTO GALERA | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 691275.56 | 1 | 683925.98 | Completed | 1 | Nov. 23, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | 2020-07-09 | Aug. 17, 2020 | FS Sugay Const & Supplies | NTP issued
QRF 2020 | Region IV-B | Oriental Mindoro | 110710 | VICTORIA CS | VICTORIA | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 1745000 | 1 | 1709567.59 | Completed | 1 | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-02 | 2020-07-09 | Aug. 14, 2020 | Cmsel Const & Developer | NTP issued
QRF 2020 | Region IV-B | Oriental Mindoro | 110464 | CABALWA ES | MANSALAY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1649713.16 | 1 | 1447040.9205 | Completed | 1 |  |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-02 |  |  |  | For Re-Bid
QRF 2020 | Region IV-B | Oriental Mindoro | 110469 | M.MARCIANO MES | MANSALAY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 758019.65 | 1 | 670288.584 | Completed | 1 |  |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-02 |  |  |  | For Re-Bid
QRF 2020 | Region IV-B | Oriental Mindoro | 110560 | MALAYA ES | PINAMALAYAN | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2243438.96 | 1 | 2218635.78 | Completed | 1 | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-02 | 2020-07-09 | Aug. 14, 2020 | DK Construction | NTP issued
QRF 2020 | Region IV-B | Oriental Mindoro | 110575 | MALIANCOG ES | PINAMALAYAN | 2 | 1 | 1 | REPAIR OF CLASSROOMS | 402870.09 | 1 | 389902.59 | Completed | 1 | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-02 | 2020-07-09 | Aug. 14, 2020 | Cmsel Const & Developer | NTP issued
QRF 2020 | Region IV-B | Oriental Mindoro | 110565 | RANZO ES | PINAMALAYAN | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2101930.74 | 1 | 2051030.52 | Completed | 1 | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-02 | 2020-07-09 | Aug. 14, 2020 | Cmsel Const & Developer | NTP issued
QRF 2020 | Region IV-B | Palawan | 111001 | Cuyo Central School | CUYO | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2043892.81 | 1 | 1736380.99 | Completed | 1 |  |  |  |  | 2020-05-20 | 2020-06-03 | 2020-06-16 | 2020-06-22 | UPON ISSUANCE OF SARO |  | For Mobilization
QRF 2020 | Region IV-B | Puerto Princesa City | 111508 | Baruang ES | PUERTO PRINCESA CITY (Capital) | 2 |  | 2 | REPAIR OF CLASSROOMS | 877821.56 | 1 | 728565.44 | Completed | 1 |  |  |  |  | 2020-04-27 | 2020-05-04 | 2020-05-18 | 2020-05-22 | 2020-05-25
QRF 2020 | Region IV-B | Puerto Princesa City | 111508 | Baruang ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2023273.47 | 1 | 1679256 | Completed | 1 |  |  |  |  | 2020-04-27 | 2020-05-04 | 2020-05-18 | 2020-05-22 | 2020-05-25
QRF 2020 | Region IV-B | Puerto Princesa City | 111518 | Macarascas ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 1774004.76 | 1 | 1472370.49 | Completed | 1 |  |  |  |  | 2020-04-27 | 2020-05-04 | 2020-05-18 | 2020-05-22 | 2020-05-25
QRF 2020 | Region IV-B | Puerto Princesa City | 111520 | Makirawa Elementary School | PUERTO PRINCESA CITY (Capital) | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 4249630.93 | 1 | 3448396.36 | Completed | 1 |  |  |  |  | 2020-04-27 | 2020-05-04 | 2020-05-18 | 2020-05-22 | 2020-05-25
QRF 2020 | Region IV-B | Puerto Princesa City | 111485 | Mateo Jagmis | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2633464.68 | 1 | 2185696.32 | Completed | 1 |  |  |  |  | 2020-04-27 | 2020-05-04 | 2020-05-18 | 2020-05-22 | 2020-05-25
QRF 2020 | Region IV-B | Puerto Princesa City | 111491 | San Pedro CS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1705643.12 | 1 | 1415632.39 | Completed | 1 |  |  |  |  | 2020-04-27 | 2020-05-04 | 2020-05-18 | 2020-05-22 | 2020-05-25
QRF 2020 | Region IV-B | Romblon | 111278 | CAJIDIOCAN CENTRAL ES | CAJIDIOCAN | 0 | 1 | 32 | REPAIR OF CLASSROOMS | 6548401.38 | 1 | 5608240.38 | Completed | 1 | 2020-10-14 | 2020-10-14 |  |  | 2020-05-12 | 2020-05-19 | 2020-06-02 | 2020-06-05 | 2020-06-11 | NMDC CONSTRUCTION CORPORATION | Resumption on August 27, 2020
QRF 2020 | Region IV-B | Romblon | 111283 | CANTAGDA ES | CAJIDIOCAN | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 4013870.21 | 1 | 3171845.75 | Completed | 1 | 2020-10-14 | 2020-10-14 |  |  | 2020-05-12 | 2020-05-19 | 2020-06-02 | 2020-06-05 | 2020-06-11 | NMDC CONSTRUCTION CORPORATION | Resumption on August 27, 2020
QRF 2020 | Region IV-B | Romblon | 111388 | SABLAYAN ES | ROMBLON | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 4655023.4 | 1 | 3913640.07 | Completed | 1 | 2020-10-14 | 2020-10-14 |  |  | 2020-05-12 | 2020-05-19 | 2020-06-02 | 2020-06-05 | 2020-06-11 | NMDC CONSTRUCTION CORPORATION | Resumption on August 27, 2020
QRF 2021 | Region IV-B | Calapan City | 111570 | Adriatico Memorial School | CITY OF CALAPAN (Capital) | 1 | 1 | 7 | TY QUINTA | 4557110.36 | 1 | 4529768 | Completed | 1 | 2022-01-03 | 2021-12-29 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | MARC JILL CONSTRUCTION | CLUSTER 3
QRF 2021 | Region IV-B | Calapan City | 111552 | Batino Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | TY QUINTA | 2891497.22 | 1 | 2868365.24 | Completed | 1 | 2021-11-25 | 2021-11-12 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 5
QRF 2021 | Region IV-B | Calapan City | 111556 | Bucayao ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | TY QUINTA | 1038197.99 | 1 | 1033604.25 | Completed | 1 | 2021-11-20 | 2021-11-19 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | KARANGYAN BUILDERS & TRADERS | CLUSTER 4
QRF 2021 | Region IV-B | Calapan City | 309402 | Bucayao National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | TY QUINTA | 3286043.67 | 1 | 3270418.85 | Completed | 1 | 2021-11-20 | 2021-11-19 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | KARANGYAN BUILDERS & TRADERS
QRF 2021 | Region IV-B | Calapan City | 111561 | Caguisikan Eelementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 7 | TY QUINTA | 1637143.15 | 1 | 1624046 | Completed | 1 | 2021-11-25 | 2021-11-12 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 5
QRF 2021 | Region IV-B | Calapan City | 111559 | Camilmil Central School | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | TY QUINTA | 3630584.59 | 1 | 3593552.88 | Completed | 1 | 2022-01-30 | 2022-12-10 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | ETVR TRADING AND CONSTRUCTION | CLUSTER 2
QRF 2021 | Region IV-B | Calapan City | 111537 | Guinobatan Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | TY QUINTA | 2750105.37 | 1 | 2733605 | Completed | 1 | 2021-11-18 | 2021-11-10 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | MARC JILL CONSTRUCTION | CLUSTER 4
QRF 2021 | Region IV-B | Calapan City | 111560 | Gutad Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 8 | TY QUINTA | 3252320.95 | 1 | 3219147.32 | Completed | 1 | 2022-01-30 | 2022-12-10 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | ETVR TRADING AND CONSTRUCTION
QRF 2021 | Region IV-B | Calapan City | 301805 | Managpi National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | TY QUINTA | 1306718.37 | 1 | 1289731.03 | Completed | 1 | 2021-09-14 | 2021-09-28 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 6
QRF 2021 | Region IV-B | Calapan City | 111542 | N. Aboboto Memorial School | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | TY QUINTA | 1528104.26 | 1 | 1518936 | Completed | 1 | 2021-11-18 | 2021-11-10 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | MARC JILL CONSTRUCTION | CLUSTER 4
QRF 2021 | Region IV-B | Calapan City | 111546 | San Antonio Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | TY QUINTA | 2802699.27 | 1 | 2788699 | Completed | 1 | 2022-01-19 | 2022-01-19 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | F.S. SUGAY CONSTRUCTION & SUPPLIES | CLUSTER 2
QRF 2021 | Region IV-B | Calapan City | 111572 | Sta. Rita Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | TY QUINTA | 655485.33 | 1 | 649964.02 | Completed | 1 | 2021-09-14 | 2021-09-28 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 7
QRF 2021 | Region IV-B | Calapan City | 111548 | Sto. Niño Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 7 | TY QUINTA | 3685103.64 | 1 | 3671100 | Completed | 1 | 2022-01-19 | 2022-01-19 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | F.S. SUGAY CONSTRUCTION & SUPPLIES | CLUSTER 2
QRF 2021 | Region IV-B | Calapan City | 111549 | Suqui Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | TY QUINTA | 1370698.3 | 1 | 1362474 | Completed | 1 | 2022-01-03 | 2021-12-29 |  |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | MARC JILL CONSTRUCTION | CLUSTER 4
QRF 2021 | Region IV-B | Marinduque | 109887 | Bamban Elementary School | BOAC (Capital) | 0 | 1 | 7 | TY ROLLY/QUINTA | 3597158.1006 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109870 | Don Luis Hidalgo MS | BOAC (Capital) | 0 | 1 | 2 | TY ROLLY/QUINTA | 1427222.0394 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109881 | SAWI ES | BOAC NORTH | 0 | 1 | 8 | TY ROLLY/QUINTA | 3446116.6797 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109894 | CATUBUGAN ES | BOAC SOUTH | 0 | 1 | 5 | TY ROLLY/QUINTA | 2236369.685 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109915 | Pag-Asa ElmentarySchool | BUENAVISTA | 0 | 1 | 2 | TY ROLLY/QUINTA | 743165.8126 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109919 | YOOK ES | BUENAVISTA | 0 | 1 | 9 | TY ROLLY/QUINTA | 3419832.4691 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 169007 | Tiguion I ES | GASAN | 0 | 1 | 2 | TY ROLLY/QUINTA | 667532.217 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109951 | MENDEZ ES | MOGPOG | 0 | 1 | 5 | TY ROLLY/QUINTA | 1810247.8259 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109955 | PILI ES | MOGPOG | 0 | 1 | 1 | TY ROLLY/QUINTA | 434582.022 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 110001 | LIPA ELEMENTARY | SANTA CRUZ | 0 | 1 | 3 | TY ROLLY/QUINTA | 1212028.4378 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109964 | DEVILLA ES | SANTA CRUZ EAST | 0 | 1 | 4 | TY ROLLY/QUINTA | 1371797.2861 | 1 |  | Completed | 1 | 2022-01-18 |  |  | 2021-09-017 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109965 | HAGUIMIT ES | SANTA CRUZ EAST | 0 | 1 | 7 | TY ROLLY/QUINTA | 2113979.0439 | 1 |  | Completed | 1 | 2022-01-18 |  |  | 2021-09-017 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 301549 | MAKAPUYAT NHS | SANTA CRUZ EAST | 0 | 1 | 29 | TY ROLLY/QUINTA | 8500786.1742 | 1 |  | Completed | 1 | 2022-01-18 |  |  | 2021-09-017 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109968 | MASALUKOT ES | SANTA CRUZ EAST | 0 | 1 | 6 | TY ROLLY/QUINTA | 2265397.0587 | 1 |  | Completed | 1 | 2022-01-18 |  |  | 2021-09-017 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109980 | BALIIS ES | SANTA CRUZ NORTH | 0 | 1 | 5 | TY ROLLY/QUINTA | 1310502.0616 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109981 | BALOGO ES | SANTA CRUZ NORTH | 0 | 1 | 7 | TY ROLLY/QUINTA | 2407759.2219 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109993 | PUNONG ES | SANTA CRUZ NORTH | 0 | 1 | 8 | TY ROLLY/QUINTA | 2468258.0069 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109997 | GABALDON ES | SANTA CRUZ SOUTH | 0 | 1 | 17 | TY ROLLY/QUINTA | 5418256.7031 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 109998 | KAGANHAO ES | SANTA CRUZ SOUTH | 0 | 1 | 4 | TY ROLLY/QUINTA | 1129181.2663 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 110002 | MAKULAPNIT ES | SANTA CRUZ SOUTH | 0 | 1 | 5 | TY ROLLY/QUINTA | 1008983.8142 | 1 |  | Completed | 1 | 2022-01-28 |  |  | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 110015 | BONLIW ES | TORRIJOS | 0 | 1 | 13 | TY ROLLY/QUINTA | 3292252.9475 | 1 |  | Completed | 1 | 2022-01-18 |  |  | 2021-09-018 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 301533 | Bonliw National High School | TORRIJOS | 0 | 1 | 14 | TY ROLLY/QUINTA | 5697127.4403 | 1 |  | Completed | 1 | 2022-01-18 |  |  | 2021-09-018 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 110020 | Kay Duke PS | TORRIJOS | 0 | 1 | 2 | TY ROLLY/QUINTA | 1091716.3094 | 1 |  | Completed | 1 | 2022-01-18 |  |  | 2021-09-018 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 301562 | SIBUYAO NHS | TORRIJOS | 0 | 1 | 8 | TY ROLLY/QUINTA | 2997896.4227 | 1 |  | Completed | 1 | 2022-01-18 |  |  | 2021-09-018 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Marinduque | 110036 | TORRIJOS CS | TORRIJOS | 0 | 1 | 7 | TY ROLLY/QUINTA | 4575658.4189 | 1 |  | Completed | 1 | 2022-01-18 |  |  | 2021-09-018 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension
QRF 2021 | Region IV-B | Occidental Mindoro | 110077 | Alipondo Elementary School | CALINTAAN | 0 | 1 | 3 | TY QUINTA | 1031982.4068 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110078 | BAGONG SILANG ELEMENTARY SCHOOL | CALINTAAN | 0 | 1 | 10 | TY QUINTA | 4853129.3338 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 169501 | Bagong Silang ES Cansilaw ANNEX | Calintaan | 0 | 1 | 3 | TY QUINTA | 1509625.7726 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110082 | Concepcion ES | Calintaan | 0 | 1 | 7 | TY QUINTA | 3420199.2361 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110088 | Nayong Kalikasan Elementary School | CALINTAAN | 0 | 1 | 4 | TY QUINTA | 1987269.1385 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110089 | Nilapso ES | Calintaan | 0 | 1 | 7 | TY QUINTA | 3420199.2361 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110093 | Tanyag ES Annex - (Gutad PS) | CALINTAAN | 0 | 1 | 2 | TY QUINTA | 1031982.4068 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110122 | Cabag PS | Magsaysay | 0 | 1 | 3 | TY QUINTA | 1509625.7726 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110126 | Canabang ES | Magsaysay | 0 | 1 | 5 | TY QUINTA | 2464912.5044 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110147 | Tilaga ES | Magsaysay | 0 | 1 | 5 | TY QUINTA | 2464912.5044 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110198 | Jose Lopez Elementary School | RIZAL | 0 | 1 | 5 | TY QUINTA | 2464912.5044 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 169511 | Mendigorin Elementary School | Rizal | 0 | 1 | 6 | TY QUINTA | 2942555.8703 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110203 | Pitogo Elementary School | RIZAL | 0 | 1 | 10 | TY QUINTA | 4853129.3338 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110205 | Rumbang ES | Rizal | 0 | 1 | 9 | TY QUINTA | 4375485.9679 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110279 | Bangkal ES | San Jose | 0 | 1 | 5 | TY QUINTA | 2464912.5044 | 1 | 1199113.05 | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development
QRF 2021 | Region IV-B | Occidental Mindoro | 110250 | Bubog 1 ES | San Jose | 0 | 1 | 7 | TY QUINTA | 3420199.2361 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110280 | Bunlao ES | San Jose | 0 | 1 | 2 | TY QUINTA | 1031982.4068 | 1 | 798945.42 | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development
QRF 2021 | Region IV-B | Occidental Mindoro | 110262 | Camanggahan Elementary School | San Jose | 0 | 1 | 6 | TY QUINTA | 2942555.8703 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110299 | G.E. Ramirez Memorial School | San Jose | 0 | 1 | 10 | TY QUINTA | 4853129.3338 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110287 | Ipil ES | San Jose | 0 | 1 | 2 | TY QUINTA | 1031982.4068 | 1 | 799455.44 | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development
QRF 2021 | Region IV-B | Occidental Mindoro | 110252 | Labangan ES | San Jose | 0 | 1 | 9 | TY QUINTA | 4375485.9679 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110304 | MANGARIN ELEMENTARY SCHOOL | San Jose | 0 | 1 | 5 | TY QUINTA | 2576920.34 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110305 | Mapaya I ES | San Jose | 0 | 1 | 10 | TY QUINTA | 4853129.3338 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110269 | San Agustin ES | San Jose | 0 | 1 | 10 | TY QUINTA | 4853129.3338 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110270 | San Agustin ES ANNEX (D-6) | San Jose | 0 | 1 | 5 | TY QUINTA | 2464912.5044 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Occidental Mindoro | 110255 | San Roque 1 ES | San Jose | 0 | 1 | 3 | TY QUINTA | 1509625.7726 | 1 |  | Completed | 1 | 2021-11-21 | 2021-12-15 |  |  | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic
QRF 2021 | Region IV-B | Oriental Mindoro | 110709 | Tadyawan Minority School | Victoria | 1 | 1 | 3 | TY QUINTA | 915672.4726 | 1 | 908050.71 | Completed | 1 | Sept. 30, 2021 | Sept. 30, 2021 | QRF 2021-R IVB-Oriental Mindoro-028 | 013-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | CMSEL Const. & Developer
QRF 2021 | Region IV-B | Oriental Mindoro | 110409 | Alimawan ES | Bulalacao | 2 | 1 | 2 | TY QUINTA | 902019.9735 | 1 | 895000 | Completed | 1 | 2022-01-14 | 2021-12-13 | QRF 2021-R IVB-Oriental Mindoro-007 | 011-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak
QRF 2021 | Region IV-B | Oriental Mindoro | 110411 | Balatasan ES | Bulalacao | 2 | 1 | 4 | TY QUINTA | 1571924.1544 | 1 | 1550000 | Completed | 1 | 2021-10-31 | 2021-10-01 | QRF 2021-R IVB-Oriental Mindoro-018 | 012-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak
QRF 2021 | Region IV-B | Oriental Mindoro | 170035 | Bating ES | Bulalacao | 2 | 1 | 2 | TY QUINTA | 900193.4012 | 1 | 895000 | Completed | 1 | 2022-01-14 | 2021-12-03 | QRF 2021-R IVB-Oriental Mindoro-010 | 011-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak
QRF 2021 | Region IV-B | Oriental Mindoro | 110414 | Bulalacao CS | Bulalacao | 2 | 1 | 14 | TY QUINTA | 4299621.5274 | 1 | 4280000 | Completed | 1 | 2022-01-14 | 2022-01-11 | QRF 2021-R IVB-Oriental Mindoro-008 | 009-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak
QRF 2021 | Region IV-B | Oriental Mindoro | 309033 | Cabugao National High School | Bulalacao | 2 | 1 | 3 | TY QUINTA | 509380.63 | 1 | 505000 | Completed | 1 | 2022-01-14 | 2021-12-13 | QRF 2021-R IVB-Oriental Mindoro-005 | 010-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak
QRF 2021 | Region IV-B | Oriental Mindoro | 110422 | Maujao ES | Bulalacao | 2 | 1 | 3 | TY QUINTA | 1392252.2753 | 1 | 1385000 | Completed | 1 | 2022-01-14 | 2021-12-13 | QRF 2021-R IVB-Oriental Mindoro-009 | 010-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak
QRF 2021 | Region IV-B | Oriental Mindoro | 301621 | Maujao NHS | Bulalacao | 2 | 1 | 25 | TY QUINTA | 5638206.4248 | 1 | 5600000 | Completed | 1 | 2022-02-13 | 2022-02-11 | QRF 2021-R IVB-Oriental Mindoro-006 | 008-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak
QRF 2021 | Region IV-B | Romblon | 309205 | CARMEN NATIONAL HIGH SCHOOL | San Agustin | 0 | 1 | 4 | TISOY / ROLLY | 1758135.0613 | 1 | 1597519.23 | Completed | 1 | 2022-03-21 | 2022-02-14 |  | INF-SQR-2021-06 | 2021-07-20 | 2021-07-27 | 2021-08-08 | 2021-12-14 | 2021-12-14 | RG FLORENTINO CONSTRUCTION AND TRADING INC
QRF 2021 | Region IV-B | Romblon | 111424 | MARIGONDON NORTE ES | San Andres | 0 | 1 | 5 | TISOY | 2598887.5998 | 1 | 2472004.64 | Completed | 1 | 2022-03-31 | 2022-06-17 |  | INF-SQR-2021-04 | 2021-07-20 | 2021-07-27 | 2021-08-08 | 2021-12-14 | 2021-12-14 | RMR CONSTRUCTION AND TRADING
QRF 2021 | Region IV-B | Romblon | 111425 | Marigondon Sur ES | San Andres | 0 | 1 | 2 | TISOY | 1108455.088 | 1 | 1177104.5 | Completed | 1 | 2022-03-31 | 2022-06-17 |  | INF-SQR-2021-04 | 2021-07-20 | 2021-07-27 | 2021-08-08 | 2021-12-14 | 2021-12-14 | RMR CONSTRUCTION AND TRADING
QRF 2021 | Region IV-B | Romblon | 111429 | San Andres Central Elementary School | San Andres | 0 | 1 | 17 | TISOY / ROLLY | 5245186 | 1 | 4463037.89 | Completed | 1 | 2022-09-30 |  |  | INF-SQR-2021-05 | 2021-10-29 | 2021-11-04 | 2021-11-08 | 2022-01-28 | 2022-01-28 | TRIPLE PEAK MOUNTAIN CONSTRUCTION AND SUPPLY
QRF 2021 | Region IV-B | Romblon | 301771 | San Andres NHS | San Andres | 0 | 1 | 2 | TISOY | 1115165.5609 | 1 | 898845.93 | Completed | 1 | 2022-09-30 |  |  | INF-SQR-2021-05 | 2021-10-29 | 2021-11-04 | 2021-11-08 | 2022-01-28 | 2022-01-28 | TRIPLE PEAK MOUNTAIN CONSTRUCTION AND SUPPLY
QRF 2022 | Region IV-B | Palawan | 110749 | Araceli Central School | ARACELI | 1 | 1 | 11 | REPAIR/ REHABILITATION | 7012282.39 | 1 |  | Completed | 1
QRF 2022 | Region IV-B | Palawan | 110750 | Araceli North Central School | ARACELI | 1 | 1 | 8 | REPAIR/ REHABILITATION | 5415010.46 | 1 |  | Completed | 1
QRF 2022 | Region IV-B | Palawan | 110789 | Tinintinan Elementary School | ARACELI | 1 | 1 | 8 | REPAIR/ REHABILITATION | 5157828.99 | 1 |  | Completed | 1
QRF 2022 | Region IV-B | Palawan | 110767 | Dumaran CS | DUMARAN | 1 | 1 | 1 | REPAIR/ REHABILITATION | 282965.41 | 1 |  | completed | 1
QRF 2022 | Region IV-B | Palawan | 111164 | Roxas North CS | ROXAS | 1 | 1 | 9 | REPAIR/ REHABILITATION | 1497092.41 | 1 |  | completed | 1
QRF 2022 | Region IV-B | Palawan | 111167 | San Dionisio Elementary School | ROXAS | 1 | 1 | 4 | REPAIR/ REHABILITATION | 2683970.9 | 1 |  | Completed | 1
QRF 2022 | Region IV-B | Palawan | 111185 | Bunuangin ES | SAN VICENTE | 1 | 1 | 3 | REPAIR/ REHABILITATION | 2033552.6384 | 1 |  | completed | 1
QRF 2022 | Region IV-B | Palawan | 301681 | Caruray National High School | SAN VICENTE | 1 | 1 | 4 | REPAIR/ REHABILITATION | 2234236.49 | 1 |  | Completed | 1
QRF 2022 | Region IV-B | Palawan | 170530 | Casoyan ES | SAN VICENTE | 1 | 1 | 4 | REPAIR/ REHABILITATION | 2813770.5599 | 1 |  | completed | 1
QRF 2022 | Region IV-B | Palawan | 170530 | Casoyan ES | SAN VICENTE | 1 |  | 2 | NEW CONSTRUCTION | 3902365.91 | 1 | 3825427.78 | completed | 1
QRF 2022 | Region IV-B | Palawan | 111195 | New Caruray Elementary School | SAN VICENTE | 1 | 1 | 2 | REPAIR/ REHABILITATION | 1374418.02 | 1 |  | completed | 1
QRF 2022 | Region IV-B | Palawan | 111201 | San Vicente CS | SAN VICENTE | 1 | 1 | 6 | REPAIR/ REHABILITATION | 2276096.86 | 1 |  | Completed | 1 | [10 empty] | suspended, will resume after holyweek
QRF 2022 | Region IV-B | Palawan | 111201 | San Vicente CS | SAN VICENTE | 1 |  | 6 | NEW CONSTRUCTION | 16954914.25 | 1 | 16836299.29 | Completed | 1 | 2023-09-07 |  | 2022-11-006-INFRA | 2022-11-006-INFRA - LOT 3 | 2022-11-16 | 2022-11-28 | 2022-12-09 | 2022-12-19 | 2023-01-03 | EM Abin Trading and Construction | suspended, will resume after holyweek
QRF 2022 | Region IV-B | Palawan | 111211 | Bato CS | TAYTAY | 1 | 1 | 4 | REPAIR/ REHABILITATION | 2706331.4978 | 1 |  | Completed | 1
QRF 2022 | Region IV-B | Palawan | 111211 | Bato CS | TAYTAY | 1 |  | 10 | NEW CONSTRUCTION | 45000000 | 1 | 44662500 | Completed | 1 | 2023-09-01 |  | 2022-11-006-INFRA | 2022-11-006-INFRA - LOT 1 | 2022-11-16 | 2022-11-28 | 2022-12-09 | 2022-12-19 | 2023-01-03 | Maryknoll Builders & Supply
QRF 2022 | Region IV-B | Palawan | 309103 | Central Taytay NHS | TAYTAY | 1 | 1 | 16 | REPAIR/ REHABILITATION | 2996974.5083 | 1 |  | completed | 1
QRF 2022 | Region IV-B | Palawan | 111219 | Judge Cesar L. Rodriguez ES | TAYTAY | 1 | 1 | 11 | REPAIR/ REHABILITATION | 4025753.68 | 1 |  | Completed | 1
QRF 2022 | Region IV-B | Puerto Princesa City | 111516 | Langogan ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 13 | REPAIR/ REHABILITATION | 8109763.39 | 1 |  | completed | 1
QRF 2022 | Region IV-B | Puerto Princesa City | 111528 | Salvacion CS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 6 | REPAIR/ REHABILITATION | 3408366.312 | 1 |  | completed | 1
QRF 2022 | Region IV-B | Puerto Princesa City | 111528 | Salvacion CS | PUERTO PRINCESA CITY (Capital) | 2 |  | 4 | NEW CONSTRUCTION | 15811897.04 | 1 | 15007576.16 | completed | 1 | Sept. 24, 2023 |  |  | Infra 2022-11-002 | Nov. 29, 2022 | Dec. 6, 2022 | 2022-12-19 | 2022-01-11 | 2022-01-13 | GS MOTAR BUILDERS CONSTRUCTION & TRADING
QRF 2023 | Region IV-B | Oriental Mindoro | 301623 | Bulbugan NHS | GLORIA | 2nd | 1 | 6 | 2STY6CL | 30160867 | 2- NC | 29050000 | completed | 1 | 2024-11-22 | 2024-11-20 | QRF 2023-MIMAROPA-ORIENTAL MINDORO-002 | 018-2023 | 2023-11-08 | 2023-11-16 | 2023-11-29 | 2023-12-07 | 2023-12-18 | ADL Constrak OPC

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%