## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | Status as of July 4, 2025
REPAIR 2020 | Region IX | Dapitan City | 125913 | Burgos ES | DAPITAN CITY | 1 | 1 | 6 | Repair of Classrooms | 2555853 | 1 | 2555852.44 | COMPLETED | 1 | 2021-03-05 | 2021-09-30 | 2020-09-003 | 2020-09-003 | 2019-12-02 | 2019-12-02 | 2019-12-16 | 2020-09-29 | 2020-10-06 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Dapitan City | 125927 | Carang ES | DAPITAN CITY | 1 | 1 | 8 | Repair of Classrooms | 3242668 | 1 | 3242667.68 | COMPLETED | 1 | 2021-03-05 | 2021-09-30 | 2020-09-003 | 2020-09-003 | 2019-12-02 | 2019-12-02 | 2019-12-16 | 2020-09-29 | 2020-10-06 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IX | Dapitan City | 125929 | Guimputlan ES | DAPITAN CITY | 1 | 1 | 8 | Repair of Classrooms | 3209366 | 1 | 3209365.01 | COMPLETED | 1 | 2021-03-05 | 2021-09-16 | 2020-09-004 | 2020-09-004 | 2019-12-02 | 2019-12-02 | 2019-12-16 | 2020-09-29 | 2020-10-06 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IX | Dapitan City | 125932 | Oro ES | DAPITAN CITY | 1 | 1 | 6 | Repair of Classrooms | 2363194 | 1 | 2363193.49 | COMPLETED | 1 | 2021-03-05 | 2021-06-28 | 2020-09-004 | 2020-09-004 | 2019-12-02 | 2019-12-02 | 2019-12-16 | 2020-09-29 | 2020-10-06 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Dipolog City | 125982 | Dipolog Pilot Demonstration School | DIPOLOG CITY (Capital) | 2 | 1 | 14 | Repair of Classrooms | 4164359 | 1 | 4164358.89 | COMPLETED | 1 | 2021-04-30 | 2022-02-08 | Repair/Rehab of 14-Classroom at Dipolog Pilot Demonstration School | DepED-Repair-20-IX-Dip-DPDS | 2019-12-16 | 2019-12-23 | 2020-01-10 | 2020-09-16 | 2020-10-01 | Stars and Stripes Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region IX | Dipolog City | 125970 | Turno Elementary School | DIPOLOG CITY (Capital) | 2 | 1 | 3 | Repair of Classrooms | 997384 | 1 | 997383.03 | COMPLETED | 1 | 2020-12-31 | 2020-12-28 | Repair/Rehab of 3-Classroom at Turno ES | DepED-Repair-20-IX-Dip-TES | 2019-12-16 | 2019-12-23 | 2020-01-10 | 2020-09-16 | 2020-10-01 | RGS Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IX | Isabela City | 126002 | Isabela Central Elementary Pilot School | CITY OF ISABELA (Capital) | 0 | 1 | 13 | Repair of Classrooms | 5493434 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region IX | Isabela City | 126009 | Kauman Ekka E/S | CITY OF ISABELA (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1035623 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IX | Isabela City | 126013 | Palasanan Primary School | CITY OF ISABELA (Capital) | 0 | 1 | 4 | Repair of Classrooms | 1826545 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IX | Isabela City | 126006 | Simeon & Josefa Obsequio ES | CITY OF ISABELA (Capital) | 0 | 1 | 5 | Repair of Classrooms | 2090131 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IX | Pagadian City | 126086 | Banale ES | PAGADIAN CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2405483 | 1 | 2405482.2 | COMPLETED | 1 | 2021-03-03 | 2021-02-10 | Depep-Repair-2020-IX-PAG-2 | Depep-Repair-2020-IX-PAG-2 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | ARADEL CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Pagadian City | 126041 | Deborok ES | PAGADIAN CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2761439 | 1 | 2761438.08 | COMPLETED | 1 | 2021-03-03 | 2021-02-10 | Depep-Repair-2020-IX-PAG-2 | Depep-Repair-2020-IX-PAG-2 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | ARADEL CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Pagadian City | 126088 | Dumalian ES | PAGADIAN CITY (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2131551 | 1 | 2131550.1 | COMPLETED | 1 | 2021-03-03 | 2021-02-09 | Depep-Repair-2020-IX-PAG-1 | Depep-Repair-2020-IX-PAG-1 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | JZ MAGO CONST. & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IX | Pagadian City | 126063 | Kalasan ES | PAGADIAN CITY (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1346933 | 1 | 1346932.62 | COMPLETED | 1 | 2021-03-03 | 2021-02-10 | Depep-Repair-2020-IX-PAG-2 | Depep-Repair-2020-IX-PAG-2 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | ARADEL CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IX | Pagadian City | 126072 | La Suerte ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | Repair of Classrooms | 846400 | 1 | 846400 | COMPLETED | 1 | 2021-03-03 | 2021-02-09 | Depep-Repair-2020-IX-PAG-1 | Depep-Repair-2020-IX-PAG-1 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | JZ MAGO CONST. & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IX | Pagadian City | 303903 | Lison Valley NHS | PAGADIAN CITY (Capital) | 1 | 1 | 9 | Repair of Classrooms | 3591001 | 1 | 3591000.3 | COMPLETED | 1 | 2021-03-03 | 2021-02-09 | Depep-Repair-2020-IX-PAG-1 | Depep-Repair-2020-IX-PAG-1 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | JZ MAGO CONST. & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IX | Pagadian City | 126048 | Tomas Sagun ES | PAGADIAN CITY (Capital) | 1 | 1 | 17 | Repair of Classrooms | 6789638 | 1 | 6789637.66 | COMPLETED | 1 | 2021-03-03 | 2021-03-03 | Depep-Repair-2020-IX-PAG-3 | Depep-Repair-2020-IX-PAG-3 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | ALIÑAB CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga City | 126135 | ANULING ES | ZAMBOANGA CITY | 1 | 1 | 10 | Repair of Classrooms | 4029799 | 1 | 4029799 | COMPLETED | 1 | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-02 | ZC-REPAIR-2020-02 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | JM2K CONSTUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga City | 126105 | STO NINO ES | ZAMBOANGA CITY | 1 | 1 | 8 | Repair of Classrooms | 3601775 | 1 | 3601775 | COMPLETED | 1 | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-01 | ZC-REPAIR-2020-01 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | MMP CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga City | 126197 | BOALAN ES | ZAMBOANGA CITY | 2 | 1 | 6 | Repair of Classrooms | 2127334 | 1 | 2127334 | COMPLETED | 1 | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-09 | ZC-REPAIR-2020-09 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | ZAMBOANGA 3VC CONSTRUCTION, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga City | 126157 | DULIAN ES | ZAMBOANGA CITY | 2 | 1 | 9 | Repair of Classrooms | 3634752 | 1 | 3634752 | COMPLETED | 1 | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-03 | ZC-REPAIR-2020-03 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | IYADA BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga City | 126158 | ELIGNA ES | ZAMBOANGA CITY | 2 | 1 | 4 | Repair of Classrooms | 1697978 | 1 | 1697978 | COMPLETED | 1 | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-04 | ZC-REPAIR-2020-04 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | IYADA BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga City | 126188 | LUMBAYAO ES | ZAMBOANGA CITY | 2 | 1 | 5 | Repair of Classrooms | 2047334 | 1 | 2047334 | COMPLETED | 1 | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-07 | ZC-REPAIR-2020-07 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | ZAMBOANGA 3VC CONSTRUCTION, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga City | 126161 | MAGSAYSAY ES | ZAMBOANGA CITY | 2 | 1 | 6 | Repair of Classrooms | 2144572 | 1 | 2144572 | COMPLETED | 1 | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-05 | ZC-REPAIR-2020-05 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | HIGH RISER CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga City | 126189 | MERCEDES CS | ZAMBOANGA CITY | 2 | 1 | 6 | Repair of Classrooms | 2247334 | 1 | 2247334 | COMPLETED | 1 | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-08 | ZC-REPAIR-2020-08 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | ZAMBOANGA 3VC CONSTRUCTION, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga City | 303930 | SANGALI NHS | ZAMBOANGA CITY | 2 | 1 | 12 | Repair of Classrooms | 4236657 | 1 | 4236657 | COMPLETED | 1 | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-10 | ZC-REPAIR-2020-10 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | HIGH RISER CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga City | 126175 | TUMALUTAB ES | ZAMBOANGA CITY | 2 | 1 | 9 | Repair of Classrooms | 3787925 | 1 | 3787925 | COMPLETED | 1 | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-06 | ZC-REPAIR-2020-06 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | SK PATH CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 303679 | Dilawa NHS | PIÑAN (NEW PIÑAN) | 1 | 1 | 6 | Repair of Classrooms | 2319430 | 1 | 2319429.89 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-007 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124590 | Macleodes ES | POLANCO | 1 | 1 | 2 | Repair of Classrooms | 785342 | 1 | 785341.55 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-015 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124639 | Biayon ES | SERGIO OSMEÑA SR. | 1 | 1 | 6 | Repair of Classrooms | 2347360 | 1 | 2347359.89 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-021 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124751 | Sibutad CS | SIBUTAD | 1 | 1 | 10 | Repair of Classrooms | 4182786 | 1 | 4182785.64 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-031 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124339 | Tamarok ES | JOSE DALMAN (PONOT) | 2 | 1 | 8 | Repair of Classrooms | 3212723 | 1 | 3212722.36 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-057 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 303702 | Katipunan NHS Annex - Sitog | KATIPUNAN | 2 | 1 | 6 | Repair of Classrooms | 2360667 | 1 | 2360667 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-040 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124386 | San Vicente ES | KATIPUNAN | 2 | 1 | 6 | Repair of Classrooms | 2350813 | 1 | 2350812.28 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-036 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124510 | Manukan East Central School | MANUKAN | 2 | 1 | 9 | Repair of Classrooms | 3522691 | 1 | 3522690.49 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-048 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 303712 | Marupay NHS | PRES. MANUEL A. ROXAS | 2 | 1 | 6 | Repair of Classrooms | 2385342 | 1 | 2385341.73 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-044 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124483 | Nabilid ES | PRES. MANUEL A. ROXAS | 2 | 1 | 7 | Repair of Classrooms | 2774496 | 1 | 2774495.08 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-041 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 303730 | Siayan National High School | SIAYAN | 2 | 1 | 9 | Repair of Classrooms | 3673150 | 1 | 3673149.18 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-072 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124428 | Bacungan CS | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 7 | Repair of Classrooms | 2884501 | 1 | 2884500.15 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-074 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124346 | Daniel Maing ES | KALAWIT | 3 | 1 | 9 | Repair of Classrooms | 3743519 | 1 | 3743518.69 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-097 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124463 | Baybay Central School | LILOY | 3 | 1 | 14 | Repair of Classrooms | 5790685 | 1 | 5790684.5 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-081 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124447 | Causwagan ES | LILOY | 3 | 1 | 6 | Repair of Classrooms | 2510306 | 1 | 2510305.77 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-079 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124457 | Patawag ES | LILOY | 3 | 1 | 6 | Repair of Classrooms | 2507263 | 1 | 2507262.28 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-080 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124461 | Silucap ES | LILOY | 3 | 1 | 9 | Repair of Classrooms | 3740761 | 1 | 3740760.71 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-092 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 303671 | Bacong NHS | SALUG | 3 | 1 | 8 | Repair of Classrooms | 3334613 | 1 | 3334612.22 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-086 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124623 | Salug CS | SALUG | 3 | 1 | 7 | Repair of Classrooms | 2920936 | 1 | 2920935.08 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-083 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124733 | Sibuco CS | SIBUCO | 3 | 1 | 10 | Repair of Classrooms | 4304337 | 1 | 4304336.88 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-103 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124835 | Dacon Learning Center | SIRAWAI | 3 | 1 | 12 | Repair of Classrooms | 5253380 | 1 | 5253379.43 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-106 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124843 | Piacan ES | SIRAWAI | 3 | 1 | 5 | Repair of Classrooms | 2154703 | 1 | 2154702.05 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-107 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Norte | 124844 | Sirawai CS | SIRAWAI | 3 | 1 | 6 | Repair of Classrooms | 2582851 | 1 | 2582850.18 | COMPLETED | 1 |  |  | Repair2020-RIX-Zamboanga Del Norte-108 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 124867 | ANONANG ES | AURORA | 1 | 1 | 5 | Repair of Classrooms | 1762209 | 1 | 1762208.02 | COMPLETED | 1 | 2021-01-21 | 2021-01-21 | ZDS-20-RR-01 | ZDS-20-RR-01 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | AC DEMONI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 124889 | BALINTAWAK ES | AURORA | 1 | 1 | 3 | Repair of Classrooms | 1086798 | 1 | 3033931.32 | COMPLETED | 1 | 2021-01-21 | 2022-12-10 | ZDS-20-RR-04 | ZDS-20-RR-04 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | CPIN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 124873 | CAMPO UNO ES | AURORA | 1 | 1 | 8 | Repair of Classrooms | 2956766 | 1 | 2956765.74 | COMPLETED | 1 | 2021-01-21 | 2020-12-15 | ZDS-20-RR-02 | ZDS-20-RR-02 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | CHIOCO BUILDERS AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 303779 | JUAN LUMOSAD MEMORIAL NHS | AURORA | 1 | 1 | 7 | Repair of Classrooms | 3033932 | 1 | 1086797.52 | COMPLETED | 1 | 2021-01-21 | 2020-12-15 | ZDS-20-RR-05 | ZDS-20-RR-05 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | JOCODZ CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 124899 | MONTE ALEGRE ES | AURORA | 1 | 1 | 2 | Repair of Classrooms | 830503 | 1 | 830502.99 | COMPLETED | 1 | 2021-01-21 | 2020-12-15 | ZDS-20-RR-05 | ZDS-20-RR-05 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | JOCODZ CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 124879 | PABLO DONGALLO ES | AURORA | 1 | 1 | 9 | Repair of Classrooms | 3895978 | 1 | 3895977.93 | COMPLETED | 1 | 2021-02-20 | 2022-12-10 | ZDS-20-RR-03 | ZDS-20-RR-03 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | CPIN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 125113 | COMBO ES | LABANGAN | 1 | 1 | 4 | Repair of Classrooms | 1402138 | 1 | 1126630.55 | COMPLETED | 1 | 2021-01-21 | 2020-12-15 | ZDS-20-RR-05 | ZDS-20-RR-05 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | JOCODZ CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 125122 | OLD LABANGAN ES | LABANGAN | 1 | 1 | 7 | Repair of Classrooms | 2558050 | 1 | 2558049.76 | COMPLETED | 1 | 2021-02-20 | 2020-12-14 | ZDS-20-RR-06 | ZDS-20-RR-06 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | AYUS BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 125275 | ALICIA ES | MOLAVE | 1 | 1 | 5 | Repair of Classrooms | 1639671 | 1 | 1402137.5 | COMPLETED | 1 | 2021-02-20 | 2020-12-14 | ZDS-20-RR-06 | ZDS-20-RR-06 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | AYUS BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 125281 | LOWER DIMOROK ES | MOLAVE | 1 | 1 | 4 | Repair of Classrooms | 1859068 | 1 | 1639670.78 | COMPLETED | 1 | 2021-02-20 | 2020-12-15 | ZDS-20-RR-07 | ZDS-20-RR-07 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | ARADEL CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 125283 | MALILI ES | MOLAVE | 1 | 1 | 2 | Repair of Classrooms | 789265 | 1 | 1859067.22 | COMPLETED | 1 | 2021-02-20 | 2020-12-15 | ZDS-20-RR-07 | ZDS-20-RR-07 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | ARADEL CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 125290 | UPPER DIMOROK ES | MOLAVE | 1 | 1 | 6 | Repair of Classrooms | 2455074 | 1 | 789264.59 | COMPLETED | 1 | 2021-01-21 | 2020-01-21 | ZDS-20-RR-08 | ZDS-20-RR-08 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | CDTECH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 125317 | GAPASAN ES | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 3 | Repair of Classrooms | 1126631 | 1 | 2455073.24 | COMPLETED | 1 | 2021-01-21 | 2020-01-21 | ZDS-20-RR-08 | ZDS-20-RR-08 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | CDTECH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 124972 | LUDIONG ES | DINAS | 2 | 1 | 5 | Repair of Classrooms | 2171443 | 1 | 2171442.18 | COMPLETED | 1 | 2021-01-21 | 2021-05-20 | ZDS-20-RR-09 | ZDS-20-RR-09 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | A.M. TABAYAG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 124981 | SAN ISIDRO ES | DINAS | 2 | 1 | 1 | Repair of Classroom | 476098 | 1 | 476097.2 | COMPLETED | 1 | 2021-01-21 | 2021-05-20 | ZDS-20-RR-09 | ZDS-20-RR-09 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | A.M. TABAYAG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 314237 | Mecolong National High School | DUMALINAO | 2 | 1 | 1 | Repair of Classroom | 491647 | 1 | 491646.92 | COMPLETED | 1 | 2021-01-21 | 2020-12-10 | ZDS-20-RR-010 | ZDS-20-RR-010 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | KAYRO CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 303756 | Balongating National High School | GUIPOS | 2 | 1 | 5 | Repair of Classrooms | 2245689 | 1 | 2245688.45 | COMPLETED | 1 | 2021-01-21 | 2020-12-10 | ZDS-20-RR-010 | ZDS-20-RR-010 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | KAYRO CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 125340 | Langilan Elementary School | SAN MIGUEL | 2 | 1 | 3 | Repair of Classrooms | 1398474 | 1 | 1398473.45 | COMPLETED | 1 | 2021-01-21 | 2020-12-11 | ZDS-20-RR-011 | ZDS-20-RR-011 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | DASSAN CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 125348 | San Miguel CES | SAN MIGUEL | 2 | 1 | 3 | Repair of Classrooms | 1353966 | 1 | 1353965.2 | COMPLETED | 1 | 2021-01-21 | 2020-12-11 | ZDS-20-RR-011 | ZDS-20-RR-011 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | DASSAN CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 125455 | LACUPAYAN ES | TIGBAO | 2 | 1 | 1 | Repair of Classroom | 160490 | 1 | 160489.01 | COMPLETED | 1 | 2021-01-21 | 2020-12-11 | ZDS-20-RR-012 | ZDS-20-RR-012 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | MS CONSTRUCTION AND MARKETING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga del Sur | 125466 | Upper Nilo Elementary School | TIGBAO | 2 | 1 | 4 | Repair of Classrooms | 1797518 | 1 | 1797517.75 | COMPLETED | 1 | 2021-01-21 | 2020-12-11 | ZDS-20-RR-012 | ZDS-20-RR-012 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | MS CONSTRUCTION AND MARKETING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga Sibugay | 125522 | Lambuyogan ES | ALICIA | 1 | 1 | 2 | Repair of Classrooms | 822717 | 1 | 822716.78 | COMPLETED | 1 | March 05, 2021 | March 05, 2021 |  |  | Jan. 08, 2020 | Jan. 16, 2020 | Jan. 29, 2020 | March 05, 2020 | Oct. 23, 2020 | Lyra Mae Construction | WAITING FOR SARO RELEASE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga Sibugay | 125703 | Payag ES | MALANGAS | 1 | 1 | 8 | Repair of Classrooms | 3534348 | 1 | 3534347.95 | COMPLETED | 1 | March 13, 2020 | March 04, 2021 |  |  | Jan. 08, 2020 | Jan. 16, 2020 | Jan. 29, 2020 | March 05, 2020 | Nov. 03, 2020 | Lucky Saver Construction | WAITING FOR SARO RELEASE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga Sibugay | 125626 | Makilas ES | IPIL | 2 | 1 | 8 | Repair of Classrooms | 2445052 | 1 | 2445051.1 | COMPLETED | 1 | March 05, 2021 | March 05, 2021 |  |  | Jan. 08, 2020 | Jan. 16, 2020 | Jan. 29, 2020 | March 04, 2020 | Oct. 23, 2020 | CPAN Engineering & Enterprises | WAITING FOR SARO RELEASE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga Sibugay | 125713 | Bulansing ES | NAGA | 2 | 1 | 4 | Repair of Classrooms | 1316588 | 1 | 1316587.05 | COMPLETED | 1 | Feb. 19, 2021 | Feb. 19, 2021 |  |  | Jan. 08, 2020 | Jan. 16, 2020 | Jan. 29, 2020 | March 04, 2020 | Oct. 09, 2020 | StoneThrow Construction & Enterprises | WAITING FOR SARO RELEASE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IX | Zamboanga Sibugay | 303848 | Minsulao NHS | SIAY | 2 | 1 | 7 | Repair of Classrooms | 2658182 | 1 | 2658181.7 | COMPLETED | 1 | Feb. 19, 2021 | Feb. 19, 2021 |  |  | Jan. 08, 2020 | Jan. 16, 2020 | Jan. 29, 2020 | March 04, 2020 | Oct. 09, 2020 | StoneThrow Construction & Enterprises | WAITING FOR SARO RELEASE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region IX | Dapitan City | 125945 | Aseniero ES | DAPITAN CITY | 1 | 1 | 8 | Repair of Classrooms | 3961640.58 | 1 | 3880225.64 | COMPLETED | 1 | 2022-01-22 | 2022-01-25 | 2021-01 | 2021-01 | 2021-06-12 | 2021-06-21 | 2021-07-05 | 2021-08-04 | 2021-08-25 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IX | Dapitan City | 125918 | Maria Uray ES | DAPITAN CITY | 1 | 1 | 7 | Repair of Classrooms | 3455539.32 | 1 | 3441508.43 | COMPLETED | 1 | 2022-01-22 | 2021-12-27 | 2021-02 | 2021-02 | 2021-06-12 | 2021-06-21 | 2021-07-05 | 2021-08-04 | 2021-08-25 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region IX | Dipolog City | 125988 | Guinsangaan ES | DIPOLOG CITY (Capital) | 2 | 1 | 4 | Repair of Classrooms | 2993905.08 | 1 | 2543898.23 | COMPLETED | 1 | 2022-01-11 | 2022-01-17 | Repair and Rehabilitation of 4-CL School Building in Guinsangaan ES | DepED-Repair-21-IX-Dip-GES |  | 2021-07-30 | 2021-08-09 | Auguts 23, 2021 | 2021-09-13 | NGP Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IX | Isabela City | 126029 | Calvario Es | CITY OF ISABELA (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1391945.67 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IX | Isabela City | 126007 | Calvario Peak ES | CITY OF ISABELA (Capital) | 0 | 1 | 3 | Repair of Classrooms | 1584545.91 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IX | Pagadian City | 126058 | Alegria ES | PAGADIAN CITY (Capital) | 1 | 1 | 5 | Repair of Classrooms | 3637816.48 | 1 | 3287314.07 | COMPLETED | 1 | 2022-01-22 | 2022-01-21 | PAG-21-RR-2 | PAG-21-RR-2 | 2021-06-04 | 2021-06-11 | 2021-06-24 | 2021-08-26 | 2021-09-10 | JZ MAGO CONST. & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IX | Pagadian City | 126038 | Bulawan Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 4101827.24 | 1 | 4450466.88 | COMPLETED | 1 | 2022-01-21 | 2022-01-21 | PAG-21-RR-1 | PAG-21-RR-1 | 2021-06-04 | 2021-06-11 | 2021-06-24 | 2021-07-26 | 2021-08-23 | JZ MAGO CONST. & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga City | 126111 | Malagutay ES | ZAMBOANGA CITY | 1 | 1 | 5 | Repair of Classrooms | 2382246 | 1 | 2074307.48 | COMPLETED | 1 | December 6,2021 | December 16,2021 | ZC-REPAIR-2021-LOT-1 | ZC-REPAIR-2021-LOT-1 | June 18,2021 | July 2,2021 | July 16,2021 | July 30, 2021 | August 6,2021 | PM CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga City | 126144 | Mt. View ES | ZAMBOANGA CITY | 1 | 1 | 6 | Repair of Classrooms | 2700000 | 1 | 2375613.29 | COMPLETED | 1 | December 6,2021 | December 4,2021 | ZC-REPAIR-2021-LOT-2 | ZC-REPAIR-2021-LOT-2 | June 18,2021 | July 2,2021 | July 16,2021 | July 30, 2021 | August 6,2021 | JM2K CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga City | 126115 | Bagacay ES | ZAMBOANGA CITY | 2 | 1 | 5 | Repair of Classrooms | 2218170.5 | 1 | 2113666 | COMPLETED | 1 | December 6,2021 | January 5,2022 | ZC-REPAIR-2021-LOT-3 | ZC-REPAIR-2021-LOT-3 | June 18,2021 | July 2,2021 | July 16,2021 | July 30, 2021 | August 6,2021 | ZAMBOPEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga City | 126171 | Sapa Seco ES | ZAMBOANGA CITY | 2 | 1 | 9 | Repair of Classrooms | 3700000 | 1 | 3694930.02 | COMPLETED | 1 | December 6,2021 | January 26,2022 | ZC-REPAIR-2021-LOT-4 | ZC-REPAIR-2021-LOT-4 | June 18,2021 | July 2,2021 | July 16,2021 | July 30, 2021 | August 6,2021 | LONG ISLAND BUILDERS AND CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Norte | 124564 | Silano ES | PIÑAN (NEW PIÑAN) | 1 | 1 | 3 | Repair of Classrooms | 1929641.73 | 1 | 1921060.67 | COMPLETED | 1 | 2021-11-12 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 12, 2021 | STARS & STRIPES CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Norte | 124583 | Villahermosa ES | POLANCO | 1 | 1 | 4 | Repair of Classrooms | 2581516.35 | 1 | 2565006 | COMPLETED | 1 | 2021-11-12 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 12, 2021 | STARS & STRIPES CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Norte | 124608 | New Dapitan PS | RIZAL | 1 | 1 | 3 | Repair of Classrooms | 1932791.73 | 1 | 1929840.95 | COMPLETED | 1 | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Norte | 124337 | Siparok ES | JOSE DALMAN (PONOT) | 2 | 1 | 5 | Repair of Classrooms | 3170127.77 | 1 | 3165367.93 | COMPLETED | 1 | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Norte | 124377 | New Tambo ES | KATIPUNAN | 2 | 1 | 4 | Repair of Classrooms | 2521371.67 | 1 | 2517486.3 | COMPLETED | 1 | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Norte | 124497 | Gov. Jose Aseniero ES | PRES. MANUEL A. ROXAS | 2 | 1 | 5 | Repair of Classrooms | 3137582.45 | 1 | 3132056.76 | COMPLETED | 1 | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Norte | 124757 | Binuangan ES | SINDANGAN | 2 | 1 | 3 | Repair of Classrooms | 1945391.73 | 1 | 1942595.3 | COMPLETED | 1 | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Norte | 124347 | Fatima ES | KALAWIT | 3 | 1 | 5 | Repair of Classrooms | 3245500.71 | 1 | 3240239.26 | COMPLETED | 1 | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Norte | 124468 | Lamao ES | LILOY | 3 | 1 | 4 | Repair of Classrooms | 2611149.17 | 1 | 2607123.85 | COMPLETED | 1 | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Sur | 125080 | Josefina CES | JOSEFINA | 1 | 1 | 8 | Repair of Classrooms | 4373000 | 1 | 4146201.87 | COMPLETED | 1 | 2021-11-26 | 2021-11-25 | ZDS-21-RR-01 | ZDS-21-RR-01 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Sur | 125123 | San Isidro ES | LABANGAN | 1 | 1 | 1 | Repair of Classroom | 475000 | 1 | 450007.52 | COMPLETED | 1 | 2021-11-26 | 2021-11-24 | ZDS-21-RR-02 | ZDS-21-RR-02 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Sur | 125205 | San Isidro Central & SPED School (Special Science Education Program) | MAHAYAG | 1 | 1 | 6 | Repair of Classrooms | 2693000 | 1 | 2557383.82 | COMPLETED | 1 | 2021-11-26 | 2021-11-24 | ZDS-21-RR-02 | ZDS-21-RR-02 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Sur | 124935 | Bacayawan ES | DIMATALING | 2 | 1 | 3 | Repair of Classrooms | 1657000 | 1 | 1611890.1984 | COMPLETED | 1 | 2021-11-26 | 2021-11-24 | ZDS-21-RR-04 | ZDS-21-RR-04 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Sur | 124949 | Saloagan ES | DIMATALING | 2 | 1 | 3 | Repair of Classrooms | 1420000 | 1 | 1419614.9359 | COMPLETED | 1 | 2021-11-26 | 2021-11-24 | ZDS-21-RR-04 | ZDS-21-RR-04 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Sur | 314205 | Ignacio Garrata NHS | DINAS | 2 | 1 | 1 | Repair of Classroom | 552000 | 1 | 550906.44 | COMPLETED | 1 | 2021-11-26 | 2021-11-23 | ZDS-21-RR-03 | ZDS-21-RR-03 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Sur | 124980 | Sambulawan ES | DINAS | 2 | 1 | 2 | Repair of Classrooms | 1098000 | 1 | 1063409.03 | COMPLETED | 1 | 2021-11-26 | 2021-11-23 | ZDS-21-RR-03 | ZDS-21-RR-03 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga del Sur | 314238 | Tina NHS | DUMALINAO | 2 | 1 | 2 | Repair of Classrooms | 1062000 | 1 | 1058354.55 | COMPLETED | 1 | 2021-11-26 | 2021-11-23 | ZDS-21-RR-03 | ZDS-21-RR-03 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga Sibugay | 125573 | Lobing Paaralan ng Buhay PS | Diplahan | 1 | 1 | 2 | Repair of Classrooms | 1137855.16 | 1 | 1137855.16 | COMPLETED | 1 | 2021-11-27 |  | ZSY-2021R-01 |  | April 31, 2021 | June 08, 2021 | June 21, 2021 | July 07, 2021 | July 22, 2021 | Diplahan Commercial |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga Sibugay | 125603 | Lumpanac ES | Imelda | 1 | 1 | 1 | Repair of Classroom | 629442.31 | 1 | 629442.31 | COMPLETED | 1 | 2021-11-27 |  | ZSY-2021R-01 |  | April 31, 2021 | June 08, 2021 | June 21, 2021 | July 07, 2021 | July 22, 2021 | Diplahan Commercial |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga Sibugay | 314301 | Dalama NHS | Payao | 1 | 1 | 2 | Repair of Classroom | 1277945.79 | 1 | 1277945.79 | COMPLETED | 1 | 2021-11-27 |  | ZSY-2021R-01 |  | April 31, 2021 | June 08, 2021 | June 21, 2021 | July 07, 2021 | July 22, 2021 | Diplahan Commercial |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga Sibugay | 125787 | Habib Ibrahim Mem.ES | R.T. Lim | 2 | 1 | 4 | Repair of Classrooms | 2163800.31 | 1 | 2163800.31 | COMPLETED | 1 | 2021-11-27 | Nov. 27, 2021 | ZSY-2021R-02 |  | April 31, 2021 | June 08, 2021 | June 21, 2021 | July 07, 2021 | July 22, 2021 | Stone Throw Construction and Enterprise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IX | Zamboanga Sibugay | 314318 | Salip T. Hasim NHS | Titay | 2 | 1 | 4 | Repair of Classrooms | 1585855.86 | 1 | 1585855.86 | COMPLETED | 1 | 2021-11-27 | Nov. 27, 2021 | ZSY-2021R-02 |  | April 31, 2021 | June 08, 2021 | June 21, 2021 | July 07, 2021 | July 22, 2021 | Stone Throw Construction and Enterprise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region IX | Zamboanga del Norte | 124539 | Juan C. Dumaog Sr. ES | MUTIA | 1 | 1 | 3 | Repair of Classrooms | 2121271 | 1 | 2116893.07 | COMPLETED | 1 | 2022-09-30 | 2022-09-08 | REPAIR 2022 RIX - ZAMBOANGA DEL NORTE - 001 | Repair 2022 - BEFF - RIX - ZDN | 2022-02-08 | 2022-02-17 | 2022-03-02 | 2022-03-11 | 2022-05-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region IX | Zamboanga del Norte | 124744 | Libay ES | SIBUTAD | 1 | 1 | 3 | Repair of Classrooms | 2052859 | 1 | 2048537.01 | COMPLETED | 1 | 2022-09-30 | 2022-09-08 | REPAIR 2022 RIX - ZAMBOANGA DEL NORTE - 002 | Repair 2022 - BEFF - RIX - ZDN | 2022-02-08 | 2022-02-17 | 2022-03-02 | 2022-03-11 | 2022-05-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region IX | Zamboanga del Sur | 125084 | Mansanas ES | JOSEFINA | 1 | 1 | 5 | Repair of Classrooms | 2685000 | 1 | 2679797.98 | COMPLETED | 1 | 2022-10-22 | 2022-09-08 | ZDS-22-RR-01 | ZDS-22-RR-01 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-25 | 2022-06-24 | CPIN Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region IX | Zamboanga del Sur | 125451 | Caluma ES | TIGBAO | 2 | 1 | 4 | Repair of Classrooms | 2670000 | 1 | 2099420.5519 | COMPLETED | 1 | 2022-10-22 | 2022-10-20 | ZDS-22-RR-01 | ZDS-22-RR-01 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-24 | 2022-06-24 | JZ MAGO CONSTRUCTION & ENT. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region IX | Zamboanga del Sur | 125454 | Lacarayan Elementary School | TIGBAO | 2 | 1 | 5 | Repair of Classrooms | 4190000 | 1 | 3252206.5106 | COMPLETED | 1 | 2022-10-22 | 2022-10-20 | ZDS-22-RR-01 | ZDS-22-RR-01 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-24 | 2022-06-24 | JZ MAGO CONSTRUCTION & ENT. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region IX | Zamboanga Sibugay | 125844 | Bolingan ES | TALUSAN | 1 | 1 | 2 | Repair of Classrooms | 1340717.25 | 1 | 1337716.51 | COMPLETED | 1 | 2022-10-17 | 2022-10-17 | ZSY-2022R-01 | ZSY-2022R-01 | 2022-02-13 | 2022-02-21 | March 07, 2022 | March 31, 2022 | 2022-07-16 | CPAN Engineering & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region IX | Zamboanga Sibugay | 125850 | Mahayahay ES | TALUSAN | 1 | 1 | 2 | Repair of Classrooms | 1241738.1 | 1 | 1238891.52 | COMPLETED | 1 | 2022-10-17 | 2022-10-17 | ZSY-2022R-02 | ZSY-2022R-02 | 2022-02-13 | 2022-02-21 | March 07, 2022 | March 31, 2022 | 2022-07-16 | CPAN Engineering & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga City | 303923 | Don Pablo A. Lorenzo MHS | ZAMBOANGA CITY | 1st | 1 | 10 | Repair of Classrooms | 6000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124397 | El Paraiso ES | LA LIBERTAD | 1st | 1 | 2 | Repair of Classrooms | 1700000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124399 | La Union ES | LA LIBERTAD | 1st | 1 | 4 | Repair of Classrooms | 3300000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1st | 1 | 1 | Repair of Classroom | 1500000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124599 | Birayan ES | RIZAL | 1st | 1 | 3 | Repair of Classrooms | 2500000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124601 | La Esperanza ES | RIZAL | 1st | 1 | 2 | Repair of Classrooms | 1710000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124605 | Nangca ES | RIZAL | 1st | 1 | 2 | Repair of Classrooms | 1550000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124659 | Lebote ES | SERGIO OSMEÑA SR. | 1st | 1 | 6 | Repair of Classrooms | 4450000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124648 | San Jose ES | SERGIO OSMEÑA SR. | 1st | 1 | 4 | Repair of Classrooms | 3225000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124741 | Calube ES | SIBUTAD | 1st | 1 | 2 | Repair of Classrooms | 1700000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124745 | Magsaysay ES | SIBUTAD | 1st | 1 | 4 | Repair of Classrooms | 3350000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124748 | Oyan ES | SIBUTAD | 1st | 1 | 2 | Repair of Classrooms | 1700000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 303737 | Sibutad National High School | SIBUTAD | 1st | 1 | 4 | Repair of Classrooms | 3300000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124387 | Sanao ES | KATIPUNAN | 2nd | 1 | 4 | Repair of Classrooms | 2860435.26 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124691 | Mangilay II ES | SIAYAN | 2nd | 1 | 11 | Repair of Classrooms | 7890886.64 | DPWH (Batch 1) |  | Ongoing | 0.85 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124307 | Bayanihan ES | GUTALAC | 3rd | 1 | 2 | Repair of Classrooms | 1449529.21 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Norte | 124466 | Candelaria ES | LILOY | 3rd | 1 | 2 | Repair of Classrooms | 1555119.34 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Sur | 125085 | Moradje Elementary School | JOSEFINA | 1st | 1 | 6 | Repair of Classrooms | 5019137.25 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Sur | 125394 | Eastern Sominot ES | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | 5 | Repair of Classrooms | 4213574.79 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Sur | 125383 | Lantawan ES | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | 2 | Repair of Classrooms | 1711551.39 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Sur | 125464 | Tigbao CES | TIGBAO | 2nd | 1 | 10 | Repair of Classrooms | 6789564.69 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region IX | Zamboanga del Sur | 314208 | Sagucan NHS | VINCENZO A. SAGUN | 2nd | 1 | 4 | Repair of Classrooms | 3881865.41 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region IX | Dapitan City | 125949 | Potungan Central School | DAPITAN CITY | 1st | 1 | 4 | Repair of Classrooms | 3636363.64 | 1 | - | COMPLETED | 1 | - | - | - | - | - | - | - | - | - | - | Awaiting SARO Release | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region IX | Dipolog City | 125995 | San Alfonso Elementary School | DIPOLOG CITY (Capital) | 2nd | 1 | 7 | Repair of Classrooms | 6549218.22 | 1 | 6481501.28 | COMPLETED | 1 | 2025-03-25 | - | Repair/Rehabilitation of Classrooms of San Alfonso ES | DepED-Repair-24-IX-Dip-001 | September 9, 2024 | July 17, 2024 | July 30, 2024 | September 16, 2024 | September 25, 2024 | CPAN Engineering and Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2024 | Region IX | Isabela City | 126000 | Isabela Bliss Elementary School | CITY OF ISABELA (Capital) | Lone | 1 | 7 | Repair of Classrooms | 5656565.66 | 1 | - | Ongoing | 0.9 | - | - | - | - | - | - | - | - | - | - | Awaiting SARO Release | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0
REPAIR 2024 | Region IX | Isabela City | 198008 | M.S. Bernardo Elementary School | CITY OF ISABELA (Capital) | Lone | 1 | 2 | Repair of Classrooms | 1616161.62 | 1 | - | Ongoing | 0.98 | - | - | - | - | - | - | - | - | - | - | Awaiting SARO Release | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2024 | Region IX | Isabela City | 126017 | Tabiawan ES | CITY OF ISABELA (Capital) | Lone | 1 | 3 | Repair of Classrooms | 2424242.42 | 1 | - | Ongoing | 0.99 | - | - | - | - | - | - | - | - | - | - | Awaiting SARO Release | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2024 | Region IX | Pagadian City | 314701 | Francisco P. Consolacion National High School | PAGADIAN CITY (Capital) | 1st | 1 | 6 | Repair of Classrooms | 5552640.82 | 1 | 5487077.06 | COMPLETED | 1 | - | - | REPAIR 2024 - RIX - PAGADIAN CITY - 001 | REPAIR 2024 - RIX - PAGADIAN CITY - 001 | 2024-08-15 | 2024-08-23 | 2024-09-04 | 2024-09-23 | 2024-10-16 | ARADEL CONSTRUCTION AND SUPPLIES | Revised from 9CL to 6CL | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region IX | Zamboanga City | 126150 | Talisayan ES | ZAMBOANGA CITY | 1st | 1 | 6 | Repair of Classrooms | 3636363.64 | 1 | - | COMPLETED | 1 | Mar. 08,2025 | Mar. 05,2025 | 2024-08-0408-LOT-1 | ZC-24-REPAIR-1 | August 16,2024 | August 22, 2024 | Sept. 3,2024 | Oct. 18,2024 | Nov. 08,2024 | ZAMBOANGA 3VC CONSTRUCTION INC , | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region IX | Zamboanga City | 126165 | Manicahan Pob. ES | ZAMBOANGA CITY | 2nd | 1 | 12 | Repair of Classrooms | 7272727.27 | 1 | - | Ongoing | 0.98 | Mar. 08,2025 | - | 2024-08-0408-LOT-2 | ZC-24-REPAIR-2 | August 16,2024 | August 22, 2024 | Sept. 3,2024 | Oct. 18,2024 | Nov. 08,2024 | ZAMBOANGA 3VC CONSTRUCTION INC , | - | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0
REPAIR 2024 | Region IX | Zamboanga City | 126205 | Salaan ES | ZAMBOANGA CITY | 2nd | 1 | 9 | Repair of Classrooms | 5454545.45 | 1 | - | COMPLETED | 1 | Mar. 08,2025 | - | 2024-08-0408-LOT-3 | ZC-24-REPAIR-3 | August 16,2024 | August 22, 2024 | Sept. 3,2024 | Oct. 18,2024 | Nov. 08,2024 | ZAMBOANGA 3VC CONSTRUCTION INC , | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2024 | Region IX | Zamboanga del Norte | 124611 | Rizalina ES | RIZAL | 1st | 1 | 5 | Repair of Classrooms | 4691993.38 | 1 | 4631730.76 | COMPLETED | 1 | - | - | 2024-039-CBZN | 2024-039-CBZN | May 28, 2024 | June 05, 2024 | June 18, 2024 | June 26, 2024 | - | YSL Builders | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region IX | Zamboanga del Norte | 303731 | Diongan National High School | SIAYAN | 2nd | 1 | 7 | Repair of Classrooms | 6713038.58 | 1 | 6630234.4 | Ongoing | 0.4 | - | - | 2024-040-CBZN | 2024-040-CBZN | May 28, 2024 | June 05, 2024 | June 18, 2024 | June 26, 2024 | - | MDS Construcion & Enterprises | - | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0
REPAIR 2024 | Region IX | Zamboanga del Norte | 124429 | Bogabongan ES | BACUNGAN (LEON T. POSTIGO) | 3rd | 1 | 7 | Repair of Classrooms | 7070137.42 | 1 | 6981911.91 | COMPLETED | 1 | - | - | 2024-041-CBZN | 2024-041-CBZN | May 28, 2024 | June 05, 2024 | June 18, 2024 | July 03, 2024 | - | YSL Builders | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2024 | Region IX | Zamboanga del Sur | 196011 | Montela ES | AURORA | 1st | 1 | 5 | Repair of Classrooms | 3787878.79 | 1 | 3718090.72 | COMPLETED | 1 | 2025-01-18 | December 15, 2024 | ZDS-24-RR-02 | ZDS-24-RR-02 | 2024-06-19 | 2024-06-28 | 2024-07-10 | 2024-07-16 | 2024-09-13 | GENEMAR CONSTRUCTION | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region IX | Zamboanga del Sur | 125430 | Kapalaran ES | TAMBULIG | 1st | 1 | 3 | Repair of Classrooms | 2272727.27 | 1 | 2248454.12 | COMPLETED | 1 | 2024-12-19 | December 15, 2024 | ZDS-24-RR-01 | ZDS-24-RR-01 | 2024-06-19 | 2024-06-28 | 2024-07-10 | 2024-07-16 | 2024-09-13 | AYUS BUILDERS AND ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region IX | Zamboanga del Sur | 125061 | Baguitan ES | GUIPOS | 2nd | 1 | 5 | Repair of Classrooms | 3787878.79 | 1 | 3745121.3 | COMPLETED | 1 | 2025-01-18 | January 05, 2024 | ZDS-24-RR-03 | ZDS-24-RR-03 | 2024-06-19 | 2024-06-28 | 2024-07-10 | 2024-07-16 | 2024-09-13 | JZ MAGO CONSTRUCTION & ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region IX | Zamboanga Sibugay | 125520 | Kawayan Elementary School | ALICIA | 1st | 1 | 6 | Repair of Classrooms | 4443686.87 | 1 | 3939809.13 | Ongoing | 0.9 | Mar. 28, 2025 | - | ZSY-2024-REPAIR-01 | ZSY-2024-REPAIR-01 | Sept. 06, 2024 | Sept. 13, 2024 | Sept. 27, 2024 | - | November 28, 2024 | AFFIAH CONSTRUCTION | - | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2024 | Region IX | Zamboanga Sibugay | 125730 | Upper Sulitan Elementary School | NAGA | 2nd | 1 | 6 | Repair of Classrooms | 4410101.01 | 1 | 4205888.01 | Ongoing | 0.6 | June 16, 2025 | - | ZSY-2024-REPAIR-02 | ZSY-2024-REPAIR-02 | Sept. 06, 2024 | Sept. 13, 2024 | Sept. 27, 2024 | February 06, 2025 | February 17, 2025 | MKJ Construction | Nego-Procurement due to failure of bidding | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2024 | Region IX | Zamboanga Sibugay | 125815 | Batu Elementary School | SIAY | 2nd | 1 | 5 | Repair of Classrooms | 3677060.61 | 1 | 3522291.2 | Ongoing | 0.5 | June 16, 2025 | - | ZSY-2024-REPAIR-03 | ZSY-2024-REPAIR-03 | Sept. 06, 2024 | Sept. 13, 2024 | Sept. 27, 2024 | February 06, 2025 | February 17, 2025 | MKJ Construction | Nego-Procurement due to failure of bidding | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%