## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | Status as of July 4, 2025
REPAIR 2020 | Region V | Albay | 111601 | Banao Elementary School | BACACAY | 1 | 1 | 4 | Repair of Classrooms | 1139697 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Albay | 111588 | Busdac Elementary School | BACACAY | 1 | 1 | 3 | Repair of Classrooms | 941288 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Albay | 111591 | Igang Elementary School | BACACAY | 1 | 1 | 3 | Repair of Classrooms | 767667 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Albay | 111617 | Pigcobuhan Elementary School | BACACAY | 1 | 1 | 3 | Repair of Classrooms | 963121 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Albay | 111618 | Pili Elementary School | BACACAY | 1 | 1 | 8 | Repair of Classrooms | 1627797 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region V | Albay | 301878 | Sogod National High school | BACACAY | 1 | 1 | 9 | Repair of Classrooms | 1579316 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Albay | 111621 | Tambilagao Elementary School | BACACAY | 1 | 1 | 3 | Repair of Classrooms | 897469 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Albay | 172511 | Malolos Elementary School | MALINAO | 1 | 1 | 3 | Repair of Classrooms | 665481 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Albay | 111885 | Tanawan Elementary School | MALINAO | 1 | 1 | 2 | Repair of Classrooms | 543386 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Albay | 112058 | San Andres Elementary School | SANTO DOMINGO (LIBOG) | 1 | 1 | 3 | Repair of Classrooms | 627361 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Albay | 112059 | San Fernando Elementary School | SANTO DOMINGO (LIBOG) | 1 | 1 | 3 | Repair of Classrooms | 773030 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Albay | 172513 | Bagumbayan Elementary School | TIWI | 1 | 1 | 3 | Repair of Classrooms | 783440 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Albay | 111642 | Comun Elementary School | CAMALIG | 2 | 1 | 6 | Repair of Classrooms | 2337085 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Albay | 111643 | COTMON ES | CAMALIG | 2 | 1 | 10 | Repair of Classrooms | 4939038 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region V | Albay | 111634 | Manawan Elementary School | CAMALIG | 2 | 1 | 6 | Repair of Classrooms | 2348936 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Albay | 111638 | TUMPA ES | CAMALIG | 2 | 1 | 3 | Repair of Classrooms | 1785483 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Albay | 111679 | ALOBO ES | DARAGA | 2 | 1 | 2 | Repair of Classrooms | 1163892 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Albay | 111680 | ANISLAG ES | DARAGA | 2 | 1 | 17 | Repair of Classrooms | 8419062 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | Region V | Albay | 111660 | BANADERO ES | DARAGA | 2 | 1 | 12 | Repair of Classrooms | 5361485 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region V | Albay | 111682 | BIGAO ES | DARAGA | 2 | 1 | 6 | Repair of Classrooms | 3155884 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Albay | 111683 | BURGOS ES | DARAGA | 2 | 1 | 1 | Repair of Classroom | 646158 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region V | Albay | 111681 | Bascaran Elementary School | DARAGA (LOCSIN) | 2 | 1 | 9 | Repair of Classrooms | 3374262 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Albay | 111714 | Manases Olaybal Mem. ES (Sinungtan) | GUINOBATAN | 3 | 1 | 2 | Repair of classrooms | 809352 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Albay | 112004 | Kinale Elementary School | POLANGUI | 3 | 1 | 3 | Repair of classrooms | 1241578 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Albay | 112010 | Matacon Elementary School | POLANGUI | 3 | 1 | 8 | Repair of classrooms | 3230494 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region V | Albay | 111989 | Maynaga Elementary School | POLANGUI | 3 | 1 | 2 | Repair of classrooms | 390991 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Albay | 111994 | Pintor Elementary School | POLANGUI | 3 | 1 | 6 | Repair of classrooms | 2118154 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Albay | 111994 | Pintor Elementary School | POLANGUI | 3 |  | 3 | Repair of classrooms | 831759 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112201 | Bayabas ES | LABO | 1 | 1 | 5 | Repair of classrooms | 2202654 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112191 | Marcos Pimentel ES | LABO | 1 | 1 | 3 | Repair of classrooms | 1109596 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112243 | Calaburnay ES | PARACALE | 1 | 1 | 6 | Repair of classrooms | 2276041 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112083 | Balce ES | BASUD | 2 | 1 | 3 | Repair of classrooms | 1298106 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 301889 | Basud National High School | BASUD | 2 | 1 | 5 | Repair of classrooms | 3221415 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte |  | Basud NHS (ANNEX) | BASUD | 2 | 1 | 16 | Repair of classrooms | 3998179 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112131 | Alawihao ES | DAET (Capital) | 2 | 1 | 6 | Repair of classrooms | 2251264 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 301891 | Camarines Norte National HS | DAET (Capital) | 2 | 1 | 8 | Repair of 8 Toilets | 1581659 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112134 | Daet ES | DAET (Capital) | 2 | 1 | 9 | Repair of classrooms | 3358442 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112145 | F. Baldovino ES | DAET (Capital) | 2 | 1 | 1 | Repair of Classroom | 681885 | 1 | 2896889.8 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112147 | Gregorio Pimentel Memorial School | DAET (Capital) | 2 | 1 | 6 | Repair of classrooms | 2301225 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112136 | Mantagbac Elem School | DAET (Capital) | 2 | 1 | 6 | Repair of classrooms | 2172702 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 500030 | Moreno Integ. Sch. | DAET (Capital) | 2 | 1 | 3 | Repair of classrooms | 1209225 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112138 | Pandan Elementary School | DAET (Capital) | 2 | 1 | 6 | Repair of classrooms | 2248959 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112223 | Colasi ES | MERCEDES | 2 | 1 | 3 | Repair of classrooms | 1403213 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 | 1 | 8 | Repair of classrooms | 3618510 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112296 | Talisay ES | TALISAY | 2 | 1 | 8 | Repair of classrooms | 3053386 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region V | Camarines Norte | 112316 | Vinzons Pilot Elementary School | VINZONS | 2 | 1 | 12 | Repair of classrooms | 3381245 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112457 | Biong ES | Cabusao | 1 | 1 | 5 | Repair of classrooms | 2269484 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112461 | Pandan ES | Cabusao | 1 | 1 | 2 | Repair of classrooms | 888400 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112462 | San Pedro ES | Cabusao | 1 | 1 | 4 | Repair of classrooms | 1810771 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112463 | Sta. Cruz ES | Cabusao | 1 | 1 | 5 | Repair of classrooms | 2274700 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 302051 | Sta. Lutgarda National High School | Cabusao | 1 | 1 | 10 | Repair of classrooms | 5047271 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112576 | Cabasag Elementary School | Del Gallego | 1 | 1 | 3 | Repair of classrooms | 1371400 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112686 | MAMBULO VIEJO ES | LIBMANAN | 2 | 1 | 2 | Repair of classrooms | 777645 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112687 | Mancawayan Elementary School | LIBMANAN | 2 | 1 | 3 | Repair of classrooms | 1217756 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 173538 | Mandacanan PS | LIBMANAN | 2 | 1 | 2 | Repair of classrooms | 854235 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112697 | Tarum Elementary School | LIBMANAN | 2 | 1 | 7 | Repair of classrooms | 2869984 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112699 | USON ES | LIBMANAN | 2 | 1 | 1 | Repair of classroom | 529447 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 309748 | Milaor NHS - Dalipay Annex HS | MILAOR | 2 | 1 | 2 | Repair of classrooms | 898871 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112794 | Bingcay ES | MINALABAC | 2 | 1 | 2 | Repair of classrooms | 795816 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112798 | HOBO ES | MINALABAC | 2 | 1 | 5 | Repair of classrooms | 2056807 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112802 | MANAPAO ES | MINALABAC | 2 | 1 | 4 | Repair of classrooms | 1683820 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112803 | MATAOROC ES | MINALABAC | 2 | 1 | 4 | Repair of classrooms | 1533446 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112804 | MINALABAC CS | MINALABAC | 2 | 1 | 3 | Repair of classrooms | 1203855 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 302067 | Villamayor HS - Bagolatao Annex HS | MINALABAC | 2 | 1 | 1 | Repair of classroom | 393374 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112866 | BATANG ES | PAMPLONA | 2 | 1 | 6 | Repair of classrooms | 469288 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 113007 | Pipian ES | SAN FERNANDO | 2 | 1 | 2 | Repair of classrooms | 1020849 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112497 | Union Elementary School | CALABANGA | 3 | 1 | 20 | Repair of classrooms | 5756737 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112521 | Tacolod Elementary School - Main | CANAMAN | 3 | 1 | 6 | Repair of classrooms | 874095 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112770 | Sta. Lucia ES | MAGARAO | 3 | 1 | 3 | Repair of classrooms | 677704 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 301962 | Altamarino-Clasio High School (formerly Curry High School) | PILI (Capital) | 3 | 1 | 14 | Repair of classrooms | 4109500 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112937 | San Jose South ES | PILI (Capital) | 3 | 1 | 5 | Repair of classrooms | 2571940 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 301943 | Bikal Fisheries School | CARAMOAN | 4 | 1 | 2 | Repair of classrooms | 1187378 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 301949 | BURABOD NHS | GARCHITORENA | 4 | 1 | 2 | Repair of classrooms | 1149756 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112598 | Del Pilar ES | GARCHITORENA | 4 | 1 | 6 | Repair of classrooms | 2919492 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112628 | MAYSALAY ES | GOA | 4 | 1 | 9 | Repair of classrooms | 4246896 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 173516 | Kinahulogan CS | LAGONOY | 4 | 1 | 3 | Repair of classrooms | 1790500 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112668 | SAN ROQUE ES | LAGONOY | 4 | 1 | 4 | Repair of classrooms | 2110700 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112888 | Bulalacao Elementary School | PRESENTACION (PARUBCAN) | 4 | 1 | 7 | Repair of classrooms | 3840300 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112330 | Nababarera ES | BAAO | 5 | 1 | 1 | Repair of classroom | 455700 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112348 | Caroche ES | BALATAN | 5 | 1 | 2 | Repair of classrooms | 663100 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112350 | Coguit ES | BALATAN | 5 | 1 | 2 | Repair of classrooms | 900800 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112352 | Maguiron ES | BALATAN | 5 | 1 | 2 | Repair of classrooms | 963100 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112357 | San Francisco ES | BALATAN | 5 | 1 | 5 | Repair of classrooms | 2345300 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112368 | CRISTO REY ELEMENTARY SCHOOL | BATO | 5 | 1 | 2 | Repair of classrooms | 371100 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 330563 | Divine Shepherd High School | BATO | 5 | 1 | 2 | Repair of classrooms | 737600 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112371 | Lobong Elementary School | BATO | 5 | 1 | 2 | Repair of classrooms | 937600 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112376 | Neighborhood ES | BATO | 5 | 1 | 3 | Repair of classrooms | 1510700 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112377 | Nino Jesus ES | BATO | 5 | 1 | 2 | Repair of classrooms | 1070700 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112380 | Sagrada ES | BATO | 5 | 1 | 3 | Repair of classrooms | 1170500 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112385 | San Vicente ES | BATO | 5 | 1 | 1 | Repair of classroom | 455700 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112387 | Tagpolo ES | BATO | 5 | 1 | 1 | Repair of classroom | 540100 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112404 | Lourdes Elementary School | BUHI | 5 | 1 | 2 | Repair of classrooms | 821100 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Camarines Sur | 112844 | Sto. Domingo Elementary School | NABUA | 5 | 1 | 2 | Repair of classrooms | 887100 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113157 | Mavil ES | Bagamanoc | 0 | 1 | 8 | Repair of classrooms | 1511768 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113159 | San Vicente ES | Bagamanoc | 0 | 1 | 10 | Repair of classrooms | 1797634 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113165 | Suchan ES | Bagamanoc | 0 | 1 | 9 | Repair of classrooms | 2252853 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113196 | Buenavista Elementary School | Caramoran | 0 | 1 | 3 | Repair of classrooms | 2030585 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113197 | Camburo ES | Caramoran | 0 | 1 | 3 | Repair of classrooms | 1894021 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113202 | Panique ES | Caramoran | 0 | 1 | 3 | Repair of classrooms |  | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113214 | Sabloyon Elementary School | Caramoran | 0 | 1 | 6 | Repair of classrooms |  | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113203 | San Jose ES | Caramoran | 0 | 1 | 3 | Repair of classrooms |  | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113235 | Catamban ES | Pandan | 0 | 1 | 3 | Repair of classrooms | 1759996 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113240 | Panuto ES | Pandan | 0 | 1 | 3 | Repair of classrooms |  | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113244 | Alinawan ES | Panganiban (Payo) | 0 | 1 | 6 | Repair of classrooms | 1304299 | 1 |  | COMPLETED | 1 | [10 empty] | For Termination | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113268 | Agojo ES | SAN ANDRES (CALOLBON) | 0 | 1 | 9 | Repair of classrooms | 2415912 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113270 | Barihay ES | SAN ANDRES (CALOLBON) | 0 | 1 | 3 | Repair of classrooms | 906101 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113317 | Almojuela ES | Viga | 0 | 1 | 3 | Repair of classrooms |  | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113311 | Magsaysay ES | Viga | 0 | 1 | 6 | Repair of classrooms | 1802746 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113340 | Dugui Too Elementary School | Virac (Capital) | 0 | 1 | 9 | Repair of classrooms | 2435394 | 1 |  | COMPLETED | 1 |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  |  |  | bid valuation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113342 | Gogon Elementary School | Virac (Capital) | 0 | 1 | 9 | Repair of classrooms | 1700000 | 1 |  | COMPLETED | 1 |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  |  |  | bid valuation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113365 | Pajo Baguio ES | Virac (Capital) | 0 | 1 | 3 | Repair of classrooms |  | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113366 | Pajo San Isidro ES | Virac (Capital) | 0 | 1 | 3 | Repair of classrooms | 1173746 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Catanduanes | 113351 | Taytay ES | Virac (Capital) | 0 | 1 | 6 | Repair of classrooms | 1274178 | 1 |  | COMPLETED | 1 |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  |  |  | bid valuation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Iriga City | 114430 | CAWAYAN ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 7 | Repair of Classrooms | 3956619 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region V | Iriga City | 114448 | LA PURISIMA ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 9 | Repair of Classrooms | 5889144 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Iriga City | 114450 | SAN ANTONIO ES | Iriga City | 5 | 1 | 15 | Repair of classrooms | 5207367 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region V | Iriga City | 114428 | STA. CRUZ SUR ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 13 | Repair of Classrooms | 6585458 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region V | Iriga City | 114454 | STA. ELENA ES | Iriga City | 5 | 1 | 8 | Repair of classrooms | 2768499 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region V | Iriga City | 302250 | STA. MARIA HIGH SCHOOL | IRIGA CITY | 5 | 1 | 11 | Repair of Classrooms | 6951082 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region V | Iriga City | 302256 | STO. NIÑO NHS | Iriga City | 5 | 1 | 16 | Repair of classrooms | 6020363 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region V | Legazpi City | 302257 | Banquerohan NHS | LEGAZPI CITY (Capital) | 2 | 1 | 8 | Repair of classrooms | 1280830 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region V | Legazpi City | 114471 | Ems Barrio PS | LEGAZPI CITY (Capital) | 2 | 1 | 6 | Repair of classrooms | 1605708 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Legazpi City | 302259 | Homapon High School | LEGAZPI CITY (Capital) | 2 | 1 | 7 | Repair of classrooms | 2007013 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region V | Legazpi City | 114482 | Maslog ES | LEGAZPI CITY (Capital) | 2 | 1 | 2 | Repair of classrooms | 534530 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Legazpi City | 310205 | Maslog National High School | LEGAZPI CITY (Capital) | 2 | 1 | 3 | Repair of classrooms | 1026825 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Legazpi City | 114473 | San Francisco ES | LEGAZPI CITY (Capital) | 2 | 1 | 7 | Repair of classrooms | 1813256 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region V | Legazpi City | 500169 | Taysan Resettlement Integrated School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | Repair of classrooms | 1255355 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Ligao City | 111835 | Allang ES | CITY OF LIGAO | 3 | 1 | 1 | Repair of classrooms | 489730 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region V | Ligao City | 111810 | Baligang ES | CITY OF LIGAO | 3 | 1 | 10 | Repair of classrooms | 2912081 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region V | Ligao City | 111817 | Busac ES | CITY OF LIGAO | 3 | 1 | 5 | Repair of classrooms | 2511247 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Ligao City | 321702 | Maonon HS | CITY OF LIGAO | 3 | 1 | 7 | Repair of classrooms | 2204548 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region V | Ligao City | 231007 | Pandan ES, Macael Ext. | CITY OF LIGAO | 3 | 1 | 5 | Repair of Classroom | 1607571 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Ligao City | 111831 | Tinago ES | CITY OF LIGAO | 3 | 1 | 9 | Repair of classrooms | 3071712 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Masbate | 113574 | Calpi ELementary school | CLAVERIA | 1 | 1 | 2 | Repair of classrooms | 725543 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Masbate | 309905 | Osmeña NHS | Claveria | 1 | 1 | 4 | Repair of classrooms | 1367871 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Masbate | 113588 | Pasig ES | Claveria | 1 | 1 | 8 | Repair of classrooms | 2512195 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region V | Masbate | 302173 | Tiburcio A. Berdida, Sr. NHS | Claveria | 1 | 1 | 13 | Repair of classrooms | 4875583 | 1 | 1632669.02 | COMPLETED | 1 | 2019-11-18 |  | 2018-12-016 | 2019-02-007 | 2018-12-04 | 2018-12-12 | 2018-12-24 | 2019-08-05 | 2019-08-20 | Camsur Bicol Trading INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region V | Masbate | 302144 | Magdalena NHS | BALENO | 2 | 1 | 4 | Repair of classrooms | 1216913 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Masbate | 113442 | Tinapian ES | BALENO | 2 | 1 | 2 | Repair of classrooms | 684789 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Masbate | 113644 | Centro Elementary School | MANDAON | 2 | 1 | 2 | Repair of classrooms | 581833 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Masbate | 302125 | Cleofe A. Arce Memorial High School | MANDAON | 2 | 1 | 2 | Repair of classrooms | 1185607 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Masbate | 309907 | San Pablo National High School | MANDAON | 2 | 1 | 6 | Repair of classrooms | 1706161 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Masbate | 113753 | Polot Elementary School | MOBO | 2 | 1 | 2 | Repair of classrooms | 616278 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Masbate | 113513 | Emilio S. Boro Sr. CS | CATAINGAN | 3 | 1 | 10 | Repair of classrooms | 3164310 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region V | Masbate | 113521 | Nadawisan ES | CATAINGAN | 3 | 1 | 2 | Repair of classrooms | 809623 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Masbate | 113498 | Pawican Elementary School | CATAINGAN | 3 | 1 | 8 | Repair of classrooms | 2935001 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region V | Masbate | 113615 | San Vicente ES | DIMASALANG | 3 | 1 | 1 | Repair of Classroom | 446532 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region V | Masbate | 113945 | Candelaria ES | USON | 3 | 1 | 2 | Repair of classrooms | 990845 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Masbate City | 321801 | Bolo National High School | CITY OF MASBATE | 2 | 1 | 9 | Repair of classrooms | 2567003 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Masbate City | 231501 | Gutusan Elementary School | CITY OF MASBATE | 2 | 1 | 2 | Repair of classrooms | 815796 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Naga City | 302265 | Cararayan National High School | NAGA CITY | 3 | 1 | 8 | Repair of Classrooms | 2478286 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region V | Naga City | 302266 | Carolina National High School | NAGA CITY | 3 | 1 | 15 | Repair of Classrooms | 6956530 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region V | Naga City | 114514 | Jose Rizal Elementary School | NAGA CITY | 3 | 1 | 10 | Repair of classrooms |  | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region V | Naga City | 114508 | Julian B. Meliton Elementary School | NAGA CITY | 3 | 1 | 13 | Repair of classrooms | 9056339 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region V | Naga City | 302268 | Naga City Science HighSchool | NAGA CITY | 3 | 1 | 2 | Repair of classrooms |  | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Naga City | 114503 | Panicuason Elementary School | NAGA CITY | 3 | 1 | 7 | Repair of Classrooms | 2579955 | 1 | 773478 | COMPLETED | 1 |  |  |  |  | 2018-11-07 | 2018-11-12 | 2018-11-27 | 2019-08-16 | 2019-09-12 | MRP MERCHANDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region V | Naga City | 114510 | San Isidro Elementary School | NAGA CITY | 3 | 1 | 10 | Repair of Classrooms | 4237520 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region V | Naga City | 114513 | Villa Grande Homes Elementary School | NAGA CITY | 3 | 1 | 10 | Repair of classrooms | 7158588 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114117 | Amomonting ES | Castilla | 1 | 1 | 5 | Repair of classrooms | 1587337 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114124 | Loreto ES | CASTILLA | 1 | 1 | 6 | Repair of classrooms | 1336557 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 302226 | Mayon National High School | CASTILLA | 1 | 1 | 9 | Repair of classrooms | 1925443 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114135 | Sogoy ES | CASTILLA | 1 | 1 | 5 | Repair of classrooms | 1133279 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114276 | Cagbolo ES | Magallanes | 1 | 1 | 2 | Repair of classrooms | 721239 | 1 | 350390.39 | COMPLETED | 1 | [9 empty] | 0405 Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114283 | Sta. Elena Elementary School | Magallanes | 1 | 1 | 3 | Repair of classrooms | 889056 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114336 | Abas ES | Pilar | 1 | 1 | 4 | Repair of classrooms | 938327 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114365 | Bayasong Elementary School | Pilar | 1 | 1 | 7 | Repair of classrooms | 1809964 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 113991 | Putiao Elementary School | Barcelona | 2 | 1 | 4 | Repair of classrooms | 1569711 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114009 | Cocok-Cabitan E.S. | Bulan | 2 | 1 | 4 | Repair of classrooms | 1580311 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114010 | Daganas ES | Bulan | 2 | 1 | 1 | Repair of classrooms | 445198 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114051 | San Ramon ES | Bulan | 2 | 1 | 3 | Repair of classrooms | 1350766 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114065 | Sabang ES | Bulusan | 2 | 1 | 5 | Repair of classrooms | 1791896 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114075 | STA. BARBARA ES | BULUSAN | 2 | 1 | 6 | Repair of Classroom | 2156524 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114077 | TINAMPO ES | BULUSAN | 2 | 1 | 4 | Repair of classrooms | 1207989 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114184 | Aguinaldo ES | Gubat | 2 | 1 | 2 | Repair of classrooms | 544985 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114187 | Bonifacio ES | Gubat | 2 | 1 | 7 | Repair of classrooms | 1265041 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114220 | TOGAWE ES | GUBAT | 2 | 1 | 5 | Repair of classrooms | 1207330 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114228 | Carriedo ES | Irosin | 2 | 1 | 6 | Repair of classrooms | 2061337 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114268 | SANGKAYON ELEMENTARY SCHOOL | Juban | 2 | 1 | 4 | Repair of classrooms | 1464639 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114302 | Banogao Elementary School | Matnog | 2 | 1 | 4 | Repair of classrooms | 1426718 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Sorsogon | 114317 | Laboy ES | Matnog | 2 | 1 | 6 | Repair of classrooms | 2180201 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Sorsogon City | 114561 | Ambrosio J. Labrador Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of classrooms | 1675949 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Sorsogon City | 114537 | Gajo Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of classrooms | 1125556 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Sorsogon City | 114547 | San Vicente Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | Repair of classrooms | 803478 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region V | Sorsogon City | 114583 | Tublijon Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of classrooms | 888888 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Sorsogon City | 114561 | Ambrosio J. Labrador ES | Sorsogon East | 1 |  | 3 | Repair of classrooms |  | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region V | Sorsogon City | 114562 | San Lorenzo ES | Sorsogon East | 1 | 1 | 7 | Repair of classrooms | 2877167 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region V | Tabaco City | 114607 | Baranghawon ES | CITY OF TABACO | 1 | 1 | 8 | Repair of classrooms | 2670101 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region V | Tabaco City | 114614 | Fatima ES | CITY OF TABACO | 1 | 1 | 7 | Repair of classrooms | 2936931 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region V | Tabaco City | 114593 | Oras ES | CITY OF TABACO | 1 | 1 | 6 | Repair of classrooms | 2572112 | 1 | 1091142.38 | COMPLETED | 1 | 2020-01-20 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region V | Tabaco City | 114602 | Sua-Igot Elementary School | CITY OF TABACO | 1 | 1 | 9 | Repair of classrooms | 3282210 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region V | Tabaco City | 114624 | Tabaco South Central School | CITY OF TABACO | 1 | 1 | 6 | Repair of classrooms | 2680876 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Albay | 111592 | Langaton Elementary School | BACACAY | 1 | 1 | 1 | Repair of Classroom | 416664.67 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region V | Albay | 111611 | Mapulang Daga Elementary School | BACACAY | 1 | 1 | 6 | Repair of Classrooms | 1859093.31 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Albay | 111859 | Salvacion Elementary School | MALILIPOT | 1 | 1 | 14 | Repair of Classrooms | 4392296.95 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2021 | Region V | Albay | 111869 | Bariw Elementary School | MALINAO | 1 | 1 | 7 | Repair of Classrooms | 2286837.43 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region V | Albay | 301831 | Labnig National High School | MALINAO | 1 | 1 | 25 | Repair of Classrooms | 6842657.5 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 0 | 0
REPAIR 2021 | Region V | Albay | 111877 | Malinao Central School | MALINAO | 1 | 1 | 4 | Repair of Classrooms | 1506935.82 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Albay | 112054 | Fidel Surtida Elementary School | SANTO DOMINGO (LIBOG) | 1 | 1 | 3 | Repair of Classrooms | 634387.76 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Albay | 301879 | Sto. Domingo National High School | SANTO DOMINGO (LIBOG) | 1 | 1 | 15 | Repair of Classrooms | 3138408.38 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2021 | Region V | Albay | 112063 | Bariis Elementary School | TIWI | 1 | 1 | 5 | Repair of Classrooms | 1434930.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Albay | 111702 | Tabontabon Elementary School | DARAGA (LOCSIN) | 2 | 1 | 12 | Repair of Classrooms | 5731232.34 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region V | Albay | 111890 | Buyo Elementary School | MANITO | 2 | 1 | 6 | Repair of Classrooms | 2049393.41 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Albay | 111745 | Jovellar Central School | JOVELLAR | 3 | 1 | 29 | Repair of Classrooms | 11791022.41 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 29 | 0 | 0
REPAIR 2021 | Region V | Albay | 111762 | Libon East Central School | LIBON | 3 | 1 | 16 | Repair of Classrooms | 7192788.81 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2021 | Region V | Albay | 111773 | Sampongan Elementary School | LIBON | 3 | 1 | 1 | Repair of Classrooms & Toilets | 982617.04 | 1 |  | COMPLETED | 1 | [10 empty] | School site is in far-flung area .Slow or no movement is due to difficulty in hauling construction materials. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region V | Albay | 111960 | Macasitas Elementary School | PIO DURAN | 3 | 1 | 4 | Repair of Classrooms | 2107146.22 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Albay | 111968 | Panganiran Elementary School | PIO DURAN | 3 | 1 | 6 | Repair of Classrooms | 3210804.85 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Albay | 112003 | Cotnogan Elementary School | POLANGUI | 3 | 1 | 5 | Repair of Classrooms | 2458453.44 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112109 | Camacho Aler ES | CAPALONGA | 1 | 1 | 3 | Repair of classrooms | 1842011.13 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112115 | Esturas-Nabata ES | CAPALONGA | 1 | 1 | 5 | Repair of classrooms | 3478344.3 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112122 | Peter Sawmill ES | CAPALONGA | 1 | 1 | 6 | Repair of classrooms | 3648819.5 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112125 | San Roque ES | CAPALONGA | 1 | 1 | 5 | Repair of classrooms | 3655891.48 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112198 | G. Zabala-B. Placido ES | LABO | 1 | 1 | 3 | Repair of classrooms | 1859948.87 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112218 | Malibago ES | LABO | 1 | 1 | 3 | Repair of classrooms | 1875698.87 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112279 | Bulala ES | SANTA ELENA | 1 | 1 | 6 | Repair of classrooms | 3799856 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 173011 | Maulawin ES | SANTA ELENA | 1 | 1 | 3 | Repair of classrooms | 2077497.4 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 301913 | Rizal NHS-Annex | SANTA ELENA | 1 | 1 | 5 | Repair of classrooms | 1943210.9 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 500634 | Sta. Elena IS | SANTA ELENA | 1 | 1 | 3 | Repair of classrooms | 1854698.87 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 173012 | Tabugon ES | SANTA ELENA | 1 | 1 | 3 | Repair of classrooms | 1982435.44 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112085 | Brinas ES | BASUD | 2 | 1 | 3 | Repair of classrooms | 1833698.87 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112087 | Don Juan Pimentel ES | BASUD | 2 | 1 | 3 | Repair of classrooms | 1833698.87 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112091 | Langa ES | BASUD | 2 | 1 | 3 | Repair of classrooms | 1833698.87 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112094 | Mangcamagong ES | BASUD | 2 | 1 | 3 | Repair of classrooms | 1854698.87 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112141 | Calasgasan ES | DAET | 2 | 1 | 6 | Repair of classrooms | 3812860.32 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112226 | Hamoraon ES | MERCEDES | 2 | 1 | 5 | Repair of classrooms | 3363700.46 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112240 | Tarum ES | MERCEDES | 2 | 1 | 4 | Repair of classrooms | 2827875.8 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112307 | Juanita Balon ES | VINZONS | 2 | 1 | 3 | Repair of classrooms | 2059594.6 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Camarines Norte | 112315 | Trino P. Zenarosa ES | VINZONS | 2 | 1 | 5 | Repair of classrooms | 3467856.8 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112576 | Cabasag Elementary School | DEL GALLEGO | 1 | 1 | 2 | Repair of classrooms | 1138745.11 | 1 | 1082212.58 | COMPLETED | 1 | 3/19/2022 | 2/25/2022 |  | 2021-10-026 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112582 | Pasay ES | DEL GALLEGO | 1 | 1 | 5 | Repair of classrooms | 2983889.01 | 1 | 2835755.08 | COMPLETED | 1 | 3/19/2022 | 2/25/2022 |  | 2021-10-026 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112588 | Tabion Munti ES | DEL GALLEGO | 1 | 1 | 4 | Repair of classrooms | 2210619.62 | 1 | 2100874.33 | COMPLETED | 1 | 3/19/2022 | 2/25/2022 |  | 2021-10-026 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112741 | Cristo Rey ES | LUPI | 1 | 1 | 3 | Repair of classrooms | 1724019.79 | 1 | 1638431.54 | COMPLETED | 1 | 3/19/2022 | 2/25/2022 |  | 2021-10-026 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 301968 | Don Mariano C. Veneracion NHS | PAMPLONA | 2 | 1 | 14 | Repair of classrooms | 6501971.64 | 1 | 6194804.38 | COMPLETED | 1 | 3/29/2022 | 2/28/2022 |  | 2021-10-027 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | RD DAYAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112996 | BICAL ELEMENTARY SCHOOL | SAN FERNANDO | 2 | 1 | 8 | Repair of classrooms | 4728231.14 | 1 | 4505460.97 | COMPLETED | 1 | 3/29/2022 | 2/28/2022 |  | 2021-10-027 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | RD DAYAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 301953 | Quipayo National High School | CALABANGA | 3 | 1 | 33 | Repair of Classrooms | 5626843.69 | 1 | 5601003.79 | COMPLETED | 1 | 3/25/2022 | 2022-12-03 |  | 2021-10-028 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/25/2021 | RD DAYAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 33 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112859 | Ocampo Central School | OCAMPO | 3 | 1 | 17 | Repair of Classrooms | 5840966.01 | 1 | 5761221.88 | COMPLETED | 1 | 3/25/2022 | 2022-05-10 |  | 2021-10-028 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/25/2021 | RD DAYAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112932 | Pili Central School | PILI (Capital) | 3 | 1 | 23 | Repair of Classrooms | 11082687.77 | 1 | 10754162.29 | COMPLETED | 1 | 3/25/2022 | 2022-05-10 |  | 2021-10-029 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/25/2021 | EA AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112534 | Caramoan CS | CARAMOAN | 4 | 1 | 7 | Repair of classrooms | 5045606.91 | 1 | 3885107.07 | COMPLETED | 1 | 3/17/2022 | 2022-05-10 |  | 2021-10-031 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/17/2021 | 2 BROTHERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112600 | Garchitorena Central School | GARCHITORENA | 4 | 1 | 9 | Repair of classrooms | 6289238 | 1 | 6283024.12 | COMPLETED | 1 | 3/21/2022 | 2022-05-06 |  | 2021-10-030 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112882 | Bagong Sirang ES | PRESENTACION (PARUBCAN) | 4 | 1 | 5 | Repair of classrooms | 3313631.24 | 1 | 2776444.75 | COMPLETED | 1 | 3/17/2022 | 2022-05-10 |  | 2021-10-031 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/17/2021 | 2 BROTHERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 113024 | Obias (Pugay) ES | SAN JOSE | 4 | 1 | 11 | Repair of classrooms | 5426381.93 | 1 | 4362593.59 | COMPLETED | 1 | 3/17/2022 | 2022-03-25 |  | 2021-10-031 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/17/2021 | 2 BROTHERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 113104 | Salvacion ES | TIGAON | 4 | 1 | 8 | Repair of classrooms | 5739569.29 | 1 | 5735517.55 | COMPLETED | 1 | 3/21/2022 | 2/25/2022 |  | 2021-10-030 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112317 | Agdangan ES | BAAO | 5 | 1 | 12 | Repair of Classrooms & 1 Ext. Office | 6201087.3 | 1 | 6193300 | COMPLETED | 1 | 3/19/2022 | 2022-12-03 |  | 2021-10-2021 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112319 | Baao Central School | BAAO | 5 | 1 | 20 | Repair of Classrooms | 10484131.24 | 1 | 10471270.65 | COMPLETED | 1 | 3/24/2022 | 3/28/2022 |  | 2021-10-032 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | BOTEY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112351 | Duran ES | BALATAN | 5 | 1 | 19 | Repair of Classrooms | 8163121.09 | 1 | 8155759.49 | COMPLETED | 1 | 3/29/2022 | 2/25/2022 |  | 2021-10-033 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112377 | Nino Jesus ES | BATO | 5 | 1 | 4 | Repair of Classrooms | 1853498.7 | 1 | 1850473.51 | COMPLETED | 1 | 3/29/2022 | 2/25/2022 |  | 2021-10-033 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 500869 | Sto. Nino Integrated School (ES) | BULA | 5 | 1 | 8 | Repair of Classrooms | 5106314 | 1 | 4335550 | COMPLETED | 1 | 3/19/2022 | 2/25/2022 |  | 2021-10-2021 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112832 | Dolorosa ES | NABUA | 5 | 1 | 4 | Repair of Classrooms | 2453290 | 1 | 2392382.49 | COMPLETED | 1 | 3/25/2022 | 2/25/2022 |  | 2021-10-035 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/25/2021 | GMO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112837 | Malawag Elementary School | NABUA | 5 | 1 | 5 | Repair of Classrooms & 1 Ext. Office | 2907137.62 | 1 | 2903036.4 | COMPLETED | 1 | 3/25/2022 | 2/25/2022 |  | 2021-10-035 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/25/2021 | GMO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Camarines Sur | 112823 | Paloyon Oriental ES | NABUA | 5 | 1 | 7 | Repair of Classrooms | 4347199.71 | 1 | 4335550 | COMPLETED | 1 | 3/19/2022 | 2/25/2022 |  | 2021-10-2021 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 113174 | Caragumihan ES | BARAS | 0 | 1 | 3 | Repair of classrooms | 1647659.71 | 1 | 1631142.19 | COMPLETED | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 113170 | Puraran Elementary School | BARAS | 0 | 1 | 3 | Repair of classrooms | 2062944.49 | 1 | 2042276.29 | COMPLETED | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 113179 | Salvacion ES | BARAS | 0 | 1 | 3 | Repair of classrooms | 2202449.89 | 1 | 2180377.1 | COMPLETED | 1 | 2022-04-22 |  |  |  | November 6, 2018 | November 13, 2018 | Nov. 26 -29, 2018 | April 3, 2019 | 2021-08-06 | Lourbel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 113182 | Bato Central Elementary School | BATO | 0 | 1 | 30 | Repair of classrooms | 16554217.62 | 1 | 16388615.76 | COMPLETED | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 113194 | Sibacungan ES | BATO | 0 | 1 | 9 | Repair of classrooms | 5320459.13 | 1 | 5304497.75 | COMPLETED | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 302088 | Gigmoto Rural DHS | GIGMOTO | 0 | 1 | 25 | Repair of classrooms | 9813743.54 | 1 | 9715584.05 | COMPLETED | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 500033 | Sicmil Integrated School | GIGMOTO | 0 | 1 | 5 | Repair of classrooms | 1402770.83 | 1 | 1388659.72 | COMPLETED | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 113223 | Sioron ES | GIGMOTO | 0 | 1 | 10 | Repair of classrooms | 6111612.74 | 1 | 6050490.96 | COMPLETED | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 113272 | Cabcab CES | SAN ANDRES (CALOLBON) | 0 | 1 | 28 | Repair of classrooms | 10321056.81 | 1 | 10318329.02 | COMPLETED | 1 | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  | 2021-08-06 | Virac NRC Construction | bid valuation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 28 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 500160 | Lictin IS | SAN ANDRES (CALOLBON) | 0 | 1 | 29 | Repair of classrooms | 11144886.66 | 1 | 10954879.63 | COMPLETED | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 29 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 113290 | Mabato CES | SAN MIGUEL | 0 | 1 | 14 | Repair of classrooms | 7849938.34 | 1 | 7762166.3 | COMPLETED | 1 | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  | 2021-08-06 | Virac NRC Construction | bid valuation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 174007 | Pangilao ES | SAN MIGUEL | 0 | 1 | 3 | Repair of classrooms | 1992852.49 | 1 | 1960272.09 | COMPLETED | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 113359 | Cavinitan ES | VIRAC (Capital) | 0 | 1 | 13 | Repair of classrooms | 6045212.55 | 1 | 6026827.06 | COMPLETED | 1 | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  | 2021-08-06 | Lourbel Construction and Supply | bid valuation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 302090 | Magnesia National High School | VIRAC (Capital) | 0 | 1 | 2 | Repair of classrooms | 1230729.78 | 1 | 1227154.54 | COMPLETED | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 113349 | Sto. Domingo ES | VIRAC (Capital) | 0 | 1 | 9 | Repair of classrooms | 5426556.31 | 1 | 5410324.31 | COMPLETED | 1 | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  | 2021-08-06 | Lourbel Construction and Supply | bid valuation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region V | Catanduanes | 113373 | Virac CES | VIRAC (Capital) | 0 | 1 | 29 | Repair of classrooms | 14905904.15 | 1 | 14861547.1 | COMPLETED | 1 | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  | 2021-08-06 | Lourbel Construction and Supply | bid valuation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 29 | 0 | 0
REPAIR 2021 | Region V | Iriga City | 114449 | La Trinidad ES | IRIGA CITY | 5 | 1 | 8 | Repair of classrooms | 5606159.97 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region V | Iriga City | 114433 | Niño Jesus ES | IRIGA CITY | 5 | 1 | 1 | Repair of Classroom | 795079.58 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region V | Iriga City | 114422 | San Agustin ES | IRIGA CITY | 5 | 1 | 7 | Repair of classrooms | 5431280.07 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region V | Iriga City | 114424 | San Isidro ES | IRIGA CITY | 5 | 1 | 7 | Repair of classrooms | 5639456.63 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region V | Iriga City | 114438 | San Ramon ES | IRIGA CITY | 5 | 1 | 3 | Repair of classrooms | 3216846.91 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Iriga City | 114428 | Sta. Cruz Sur ES | IRIGA CITY | 5 | 1 | 3 | Repair of classrooms | 3063118.93 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Legazpi City | 114488 | Buyoan ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | Repair of classrooms | 1699111.23 | 1 | 1647560.51 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Legazpi City | 114460 | Homapon ES | LEGAZPI CITY (Capital) | 2 | 1 | 5 | Repair of classrooms | 2925315.74 | 1 | 2837168.77 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Legazpi City | 114461 | Imalnod ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | Repair of classrooms | 2863464.4 | 1 | 2776820.9 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Ligao City | 111843 | Ligao West CES (P) Dunao | CITY OF LIGAO | 3 | 1 | 32 | Repair of classrooms | 2738691.42 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0
REPAIR 2021 | Region V | Ligao City | 111851 | Tinampo ES | CITY OF LIGAO | 3 | 1 | 5 | Repair of classrooms | 2137426.63 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113771 | Morocborocan ES | MONREAL | 1 | 1 | 5 | Repair of classrooms | 3565020.8 | 1 | 3486715.49 | COMPLETED | 1 | 2022-03-13 |  | INFRA 2021-08-025 | 2021-062 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-12-06 | 2021-12-13 | JOHNCB CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113939 | Tuburan ES | SAN PASCUAL | 1 | 1 | 2 | Repair of classrooms | 1535139.52 | 1 | 1495115.15 | COMPLETED | 1 | 2022-03-10 |  | INFRA 2021-08-026 | 2021-063 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-12-06 | 2021-12-10 | RPN CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113399 | Bugui PS | AROROY | 2 | 1 | 3 | Repair of classrooms | 1854249.25 | 1 | 1805090.5 | COMPLETED | 1 | 2022-03-10 |  | INFRA 2021-08-027 | 2021-063 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-12-06 | 2021-12-10 | RPN CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113652 | Mabato-bato ES | MANDAON | 2 | 1 | 6 | Repair of classrooms | 3765802.97 | 1 | 3730000.07 | COMPLETED | 1 | 2022-02-24 |  | INFRA 2021-08-025 | 2021-048 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113507 | Cadulawan Elementary School | CATAINGAN | 3 | 1 | 4 | Repair of classrooms | 2577339.8 | 1 | 2571218.54 | COMPLETED | 1 | 2022-02-28 |  | INFRA 2021-08-026 | 2021-049 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-30 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Masbate | 309921 | Feliciano S. Samonte Memorial High School | CATAINGAN | 3 | 1 | 4 | Repair of classrooms | 2453675.42 | 1 | 2446192.53 | COMPLETED | 1 | 2022-02-28 |  | INFRA 2021-08-036 | 2021-055 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-30 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113555 | Pin-as ES | CAWAYAN | 3 | 1 | 4 | Repair of classrooms | 2931978.81 | 1 | 2927114.09 | COMPLETED | 1 | 2022-02-28 |  | INFRA 2021-08-039 | 2021-057 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-30 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113564 | Tubog ES | CAWAYAN | 3 | 1 | 2 | Repair of classrooms | 1371910.31 | 1 | 1368480.54 | COMPLETED | 1 | 2022-02-24 |  | INFRA 2021-08-028 | 2021-050 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | SIR HENRIK'S CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113615 | San Vicente ES | DIMASALANG | 3 | 1 | 1 | Repair of Classroom | 718335.9 | 1 | 717865.81 | COMPLETED | 1 | 2022-02-28 |  | INFRA 2021-08-027 | 2021-049 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-30 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113625 | Libertad Primary School | ESPERANZA | 3 | 1 | 2 | Repair of classrooms | 1386613.31 | 1 | 1377662.966 | COMPLETED | 1 | 2022-02-24 |  | INFRA 2021-08-031 | 2021-051 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | JOHNCB CONSTUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113619 | Trangia-Mahusay ES | ESPERANZA | 3 | 1 | 4 | Repair of classrooms | 2858561.11 | 1 | 2842223.034 | COMPLETED | 1 | 2022-02-24 |  | INFRA 2021-08-030 | 2021-051 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | JOHNCB CONSTUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113798 | Apolinario Etang ES | PALANAS | 3 | 1 | 6 | Repair of classrooms | 3974465.26 | 1 | 3964529.09 | COMPLETED | 1 | 2022-02-21 |  | INFRA 2021-08-033 | 2021-053 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-23 | JIMWELL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113789 | Biga-a Elem. School | PALANAS | 3 | 1 | 7 | Repair of classrooms | 4804236.42 | 1 | 4774456.1 | COMPLETED | 1 | 2022-02-24 |  | INFRA 2021-08-032 | 2021-052 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | MARABE GEN. CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113780 | Malibas ES | PALANAS | 3 | 1 | 5 | Repair of classrooms | 3369788.83 | 1 | 3354319.46 | COMPLETED | 1 | 2022-03-06 |  | INFRA 2021-08-028 | 2021-060 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-12-06 | 2021-12-06 | RPN CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113806 | Bunducan ES | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 6 | Repair of classrooms | 4098985.95 | 1 | 4095642.7 | COMPLETED | 1 | 2022-02-28 |  | INFRA 2021-08-034 | 2021-054 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-30 | MME CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113812 | Lampuyang ES | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 3 | Repair of classrooms | 2025697.13 | 1 | 2017865.54 | COMPLETED | 1 | 2022-02-28 |  | INFRA 2021-08-035 | 2021-055 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-30 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113822 | Burabod ES | PLACER | 3 | 1 | 3 | Repair of classrooms | 2110703.13 | 1 | 2095600 | COMPLETED | 1 | 2022-02-24 |  | INFRA 2021-08-037 | 2021-056 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | SANSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113842 | Celera-Inocencio CS | PLACER | 3 | 1 | 4 | Repair of classrooms | 2664431.02 | 1 | 2657769.94 | COMPLETED | 1 | 2022-02-24 |  | INFRA 2021-08-029 | 2021-050 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | SIR HENRIK'S CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Masbate | 113956 | Eugenio C. Clores Sr. ES | USON | 3 | 1 | 3 | Repair of classrooms | 2054951.35 | 1 | 2051733.57 | COMPLETED | 1 | 2022-02-24 |  | INFRA 2021-08-038 | 2021-056 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | SANSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Masbate City | 113701 | N. De Los Santos Elementary School | CITY OF MASBATE (Capital) | 2 | 1 | 7 | Repair of classrooms | 2124106.61 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region V | Masbate City | 113671 | Nicolas Danao ES | CITY OF MASBATE (Capital) | 2 | 1 | 6 | Repair of classrooms | 2050955.44 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Naga City | 302266 | Carolina National High School | NAGA CITY | 3 | 1 | 6 | Repair of Classrooms | 3474232.25 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region V | Naga City | 114506 | Del Rosario Elementary School | NAGA CITY | 3 | 1 | 4 | Repair of Classrooms | 3063718.78 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Naga City | 176502 | Grand View Elementary School | NAGA CITY | 3 | 1 | 3 | Repair of Classrooms | 1927041.59 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Naga City | 114509 | Mac Mariano Elementary School | NAGA CITY | 3 | 1 | 5 | Repair of Classrooms | 2522665.69 | 1 | 1307633.45 | COMPLETED | 1 |  |  |  |  | 2018-11-07 | 2018-11-12 | 2018-11-27 | 2019-08-16 | 2019-09-12 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Naga City | 176503 | Naga City SPED Center | NAGA CITY | 3 | 1 | 7 | Repair of Classrooms | 3310973.55 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region V | Naga City | 114503 | Panicuason Elementary School | NAGA CITY | 3 | 1 | 3 | Repair of Classrooms | 2566432.99 | 1 | 773478 | COMPLETED | 1 |  |  |  |  | 2018-11-07 | 2018-11-12 | 2018-11-27 | 2019-08-16 | 2019-09-12 | MRP MERCHANDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Naga City | 114510 | San Isidro Elementary School | NAGA CITY | 3 | 1 | 3 | Repair of Classrooms | 2029853.2 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Naga City | 114512 | Villa Corazon Elementary School | NAGA CITY | 3 | 1 | 11 | Repair of Classrooms | 5589846.56 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region V | Sorsogon | 114150 | Rawis Elementary School | DONSOL | 1 | 1 | 2 | Repair of classrooms | 1016947.45 | 1 | 752447.44 | COMPLETED | 1 | 2021-11-04 | December 14, 2021 |  | 21-07-007-01 | July 14, 2021 | July 22, 2021 | August 3, 2021 | August 26, 2021 | 2021-09-06 | Alhadrax Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region V | Sorsogon | 114338 | Banuyo ES | PILAR | 1 | 1 | 4 | Repair of classrooms | 1895945.38 | 1 | 1336895.1594 | COMPLETED | 1 | 2021-12-07 | December 7, 2021 |  | 21-07-007-02 | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 | 2021-09-09 | NJNY Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Sorsogon | 114356 | Pilar I Central School | PILAR | 1 | 1 | 4 | Repair of classrooms | 655461.49 | 1 | 450502.2506 | COMPLETED | 1 | 2021-12-07 | December 21, 2021 |  |  | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 |  | Alhadrax Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Sorsogon | 114383 | Pilar II CS | PILAR | 1 | 1 | 5 | Repair of classrooms | 3502026.47 | 1 | 2267011.04 | COMPLETED | 1 | 2021-12-22 | November 19, 2021 |  | 21-07-007-03 | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 | 2021-09-09 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Sorsogon | 114017 | Lahong ES | BULAN | 2 | 1 | 5 | Repair of classrooms | 3754283.32 | 1 | 2530681.1665 | COMPLETED | 1 | 2021-12-22 | December 22, 2021 |  | 21-07-007-04 | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 | 2021-09-09 | NJNY Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region V | Sorsogon | 114053 | Sigad Elementary School | BULAN | 2 | 1 | 1 | Repair of Classroom | 786814.36 | 1 | 503378.8135 | COMPLETED | 1 | 2021-12-22 | January 26, 2022 |  |  | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region V | Sorsogon | 114265 | Mario G. Guarina ES | JUBAN | 2 | 1 | 2 | Repair of classrooms | 1680982.43 | 1 | 1107599.034 | COMPLETED | 1 | 2021-12-07 | December 2, 2021 |  | 21-07-007-05 | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 | 2021-09-09 | NJNY Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region V | Sorsogon | 114268 | Sangkayon ES | JUBAN | 2 | 1 | 2 | Repair of classrooms | 1205298.9 | 1 | 784569.626 | COMPLETED | 1 | 2021-12-07 | December 2, 2021 |  |  | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region V | Sorsogon | 114410 | Manangkas ES | SANTA MAGDALENA | 2 | 1 | 2 | Repair of classrooms | 1543178.47 | 1 | 1178153.45 | COMPLETED | 1 | November 7, 2021 Revised to November 19, 2021 | November 19, 2021 |  | 21-07-007-06 | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 | 2021-09-09 | Araphil Construction and Development Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region V | Sorsogon City | 114534 | Bacon West Central School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of Classrooms | 850247.3 | 1 | 821298.56 | COMPLETED | 1 | February 14, 2022 |  |  | 21-10-001-01 | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | Kobe Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Sorsogon City | 114536 | Del Rosario Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1778811.38 | 1 | 1728769.6 | COMPLETED | 1 | 2022-09-30 |  |  | 21-10-001-02 | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | Araphil Const & Dev. Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region V | Sorsogon City | 114538 | Gayong Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1353567.57 | 1 | 1302877.15 | COMPLETED | 1 | March 3, 2022 Revised to March 23, 2022 |  |  | 21-11-002 | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | Araphil Const & Dev. Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Sorsogon City | 114575 | Pangpang Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 22 | Repair of Classrooms | 7653614.43 | 1 | 4974858.82 | COMPLETED | 1 |  |  |  |  | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | Alhadrax Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0
REPAIR 2021 | Region V | Sorsogon City | 302275 | Rawis National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1002552.14 | 1 | 977105.91 | COMPLETED | 1 |  |  |  |  | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | Kobe Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Sorsogon City | 500466 | Rizal Integrated National School (HS) | CITY OF SORSOGON (Capital) | 1 | 1 | 15 | Repair of Classrooms | 6321935.3 | 1 | 4109729.12 | COMPLETED | 1 |  |  |  |  | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | NJNY Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2021 | Region V | Sorsogon City | 114551 | Tiris Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of Classrooms | 933138.94 | 1 | 882436.69 | COMPLETED | 1 |  |  |  |  | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | Kobe Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region V | Tabaco City | 114608 | Basud ES | CITY OF TABACO | 1 | 1 | 9 | Repair of classrooms | 6828271.58 | 1 |  | COMPLETED | 1 | 2022-10-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region V | Tabaco City | 114617 | Malictay ES | CITY OF TABACO | 1 | 1 | 15 | Repair of classrooms | 10749457.85 | 1 |  | COMPLETED | 1 | 2022-11-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2021 | Region V | Tabaco City | 114620 | San Lorenzo ES | CITY OF TABACO | 1 | 1 | 24 | Repair of classrooms | 10877451.49 | 1 |  | COMPLETED | 1 | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0
REPAIR 2022 | Region V | Camarines Norte | 112268 | Pulantuna ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 3 | Repair of Classrooms | 2121271 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region V | Camarines Norte | 112277 | V. Ricafrente ES | SAN VICENTE | 2 | 1 | 3 | Repair of Classrooms | 2121271 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region V | Camarines Sur | 302051 | Sta. Lutgarda HS (Junior High) | Cabusao | 1 | 1 | 2 | Repair of Classrooms | 1522541.5 | 2 | 1517154.68 | COMPLETED | 1 | 2023-03-19 | 2023-02-23 |  | 2022-11-112 | SEPT. 16, 2022 | SEPT, 26, 2022 | 2022-10-06 | 2022-10-06 | 2022-12-19 | TGME CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region V | Camarines Sur | 112775 | Cagbunga Elementary School | GAINZA | 2 | 1 | 2 | Repair of Classrooms | 1060635.37 | 2 | 1055293.24 | COMPLETED | 1 | 2023-03-19 | 2023-02-23 |  | 2022-11-112 | SEPT. 16, 2022 | SEPT, 26, 2022 | 2022-10-06 | 2022-10-06 | 2022-12-19 | TGME CONST | project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region V | Camarines Sur | 302053 | Sulpicio A. Roco Memorial High School | BOMBON | 3 | 1 | 3 | Repair of Classrooms | 1672223.36 | 2 | 2111308.28 | COMPLETED | 1 | 2023-03-19 | 2023-02-23 |  | 2022-11-112 | SEPT. 16, 2022 | SEPT, 26, 2022 | 2022-10-06 | 2022-10-06 | 2022-12-19 | TGME CONST | project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region V | Camarines Sur | 112498 | Camaligan Central School | CAMALIGAN | 3 | 1 | 5 | Repair of Classrooms | 2121271 | 2 | 1662197.8 | COMPLETED | 1 | 2023-03-19 | 2023-02-23 |  | 2022-11-112 | SEPT. 16, 2022 | SEPT, 26, 2022 | 2022-10-06 | 2022-10-06 | 2022-12-19 | TGME CONST | project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region V | Catanduanes | 113158 | Sagrada ES | BAGAMANOC | 0 | 1 | 5 | Repair of Classrooms | 3197041.92 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region V | Catanduanes | 500412 | Bote IS | BATO | 0 | 1 | 6 | Repair of Classrooms | 4546320.5 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region V | Catanduanes | 174016 | Pananaogan Elementary School | BATO | 0 | 1 | 5 | Repair of Classrooms | 3324897.45 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region V | Masbate | 113478 | Burgos Elementary School | BATUAN | 1 | 1 | 5 | Repair of Classrooms | 3181906 | 2 | 2163696.08 | COMPLETED | 1 | 2023-03-12 |  | INFRA 2022-09-009 | 2022-004 | 2022-09-13 | 2022-09-20 | 2022-10-03 | 2022-12-02 | 2022-12-12 | JOHNCB CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region V | Masbate | 113875 | Salvacion ES | SAN FERNANDO | 1 | 1 | 2 | Repair of Classrooms | 1522541 | 2 | 1500159.65 | COMPLETED | 1 | 2023-03-12 |  | INFRA 2022-09-009 | 2022-005 | 2022-09-13 | 2022-09-20 | 2022-10-03 | 2022-12-02 | 2022-12-12 | RPN CONST. & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region V | Masbate | 113633 | Sorosimbahan ES | Esperanza | 3 | 1 | 2 | Repair of Classrooms | 1522541.5 | 2 | 1502162.59 | COMPLETED | 1 | 2023-03-12 |  | INFRA 2022-09-009 | 2022-006 | 2022-09-13 | 2022-09-20 | 2022-10-03 | 2022-12-02 | 2022-12-12 | RPN CONST. & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region V | Sorsogon | 113987 | Macabari Elementary School | BARCELONA | 2 | 1 | 3 | Repair of Classrooms | 1453495 | 2 | 756026.41 | COMPLETED | 1 | 2021-12-03 | 2021-12-03 | 22-07-003 | 22-07-003-01 | 2022-07-19 | 2023-07-27 | 2022-08-08 | 2022-08-22 | 2022-09-15 | La Abel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region V | Sorsogon | 114215 | Rizal ES | GUBAT | 2 | 1 | 10 | Repair of Classrooms | 6013327.41 | 2 | 3590336.04 | COMPLETED | 1 | 2023-02-01 | 2022-12-22 | 22-07-003 | 22-07-003-02 | 2022-07-19 | 2023-07-27 | 2022-08-09 | 2022-08-22 | 2022-09-15 | La Abel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2022 | Region V | Sorsogon | 114399 | San Fernando ES | PRIETO DIAZ | 2 | 1 | 4 | Repair of Classrooms | 2100000 | 2 | 1206255.75 | COMPLETED | 1 | 2023-01-12 | 2022-12-22 | 22-07-003 | 22-07-003-03 | 2022-07-19 | 2023-07-27 | 2022-08-09 | 2022-08-22 | 2022-09-15 | La Abel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region V | Sorsogon | 114414 | San Sebastian ES | SANTA MAGDALENA | 2 | 1 | 2 | Repair of Classrooms | 980000 | 2 | 575436.51 | COMPLETED | 1 | 2023-01-12 | 2022-12-06 | 22-07-003 | 22-07-003-04 | 2022-07-19 | 2023-07-27 | 2022-08-09 | 2022-08-22 | 2022-09-15 | La Abel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region V | Sorsogon | 114417 | Uson ES | SANTA MAGDALENA | 2 | 1 | 2 | Repair of Classrooms | 1300000 | 2 | 763788.28 | COMPLETED | 1 | 2023-01-12 | 2022-12-06 | 22-07-003 | 22-07-003-04 | 2022-07-19 | 2023-07-27 | 2022-08-09 | 2022-08-22 | 2022-09-15 | La Abel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region V | Albay | 301821 | Cawayan National High School | BACACAY | 1st | 1 | 6 | Repair of Classrooms | 13008225.92 | DPWH (Batch 2) |  | Ongoing | 0.9 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region V | Albay | 111608 | Gubat Elementary School | BACACAY | 1st | 1 | 4 | Repair of Classrooms | 9262235.97 | DPWH (Batch 2) |  | Ongoing | 0.75 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | Region V | Albay | 111613 | Misibis Elementary School | BACACAY | 1st | 1 | 3 | Repair of Classrooms | 6946676.98 | DPWH (Batch 2) |  | Ongoing | 0.85 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region V | Albay | 111596 | San Pablo Elementary School | BACACAY | 1st | 1 | 9 | Repair of Classrooms | 13980359.31 | DPWH (Batch 2) |  | Ongoing | 0.97 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
REPAIR 2023 | Region V | Albay | 111597 | Sogod Elementary School | BACACAY | 1st | 1 | 3 | Repair of Classrooms | 7909582.7 | DPWH (Batch 2) |  | Ongoing | 0.65 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region V | Albay | 111876 | Labnig Elementary School | MALINAO | 1st | 1 | 5 | Repair of Classrooms | 5112559.4 | DPWH (Batch 2) |  | Ongoing | 0.7 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region V | Albay | 301810 | Malinao National High School | MALINAO | 1st | 1 | 10 | Repair of Classrooms | 17792715.5 | DPWH (Batch 2) |  | Ongoing | 0.9 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
REPAIR 2023 | Region V | Albay | 112060 | San Isidro Elementary School | SANTO DOMINGO (LIBOG) | 1st | 1 | 3 | Repair of Classrooms | 2773790.78 | DPWH (Batch 2) |  | Ongoing | 0.85 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region V | Albay | 301879 | Sto. Domingo National High School | SANTO DOMINGO (LIBOG) | 1st | 1 | 2 | Repair of Classrooms | 4676970.64 | DPWH (Batch 2) |  | Ongoing | 0.9 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region V | Albay | 111664 | Budiao Elementary School | DARAGA (LOCSIN) | 2nd | 1 | 6 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Albay | 112024 | Calanaga Elementary School | RAPU-RAPU | 2nd | 1 | 2 | Repair of Classrooms | 8000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region V | Albay | 112000 | Agos Elementary School | POLANGUI | 3rd | 1 | 7 | Repair of Classrooms | 5050000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region V | Albay | 172507 | Alomon Elementary School | POLANGUI | 3rd | 1 | 4 | Repair of Classrooms | 3600000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region V | Albay | 111980 | Balinad Elementary School | POLANGUI | 3rd | 1 | 8 | Repair of Classrooms | 5200000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region V | Albay | 112007 | Lanigay Elementary School | POLANGUI | 3rd | 1 | 3 | Repair of Classrooms | 1950000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region V | Albay | 112009 | Magurang Elementary School | POLANGUI | 3rd | 1 | 8 | Repair of Classrooms | 6200000 | DPWH (Batch 2) |  | Ongoing | 0.4 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
REPAIR 2023 | Region V | Albay | 111990 | Maysua Elementary School | POLANGUI | 3rd | 1 | 2 | Repair of Classrooms | 1800000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region V | Albay | 301829 | Maysua High School | POLANGUI | 3rd | 1 | 2 | Repair of Classrooms | 1800000 | DPWH (Batch 2) |  | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region V | Albay | 301865 | Polangui General Comprehensive High School | POLANGUI | 3rd | 1 | 30 | Repair of Classrooms | 25500000 | DPWH (Batch 2) |  | Ongoing | 0.4 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0
REPAIR 2023 | Region V | Albay | 111996 | Ponso North Elementary School | POLANGUI | 3rd | 1 | 11 | Repair of Classrooms | 6979654 | DPWH (Batch 2) |  | Ongoing | 0.85 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112110 | Capalonga CS | CAPALONGA | 1st | 1 | 5 | Repair of Classrooms | 3142718.83 | DPWH (Batch 2) |  | Ongoing | 0.8 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112111 | Casiano Florendo Elementary School | CAPALONGA | 1st | 1 | 3 | Repair of Classrooms | 1682430.47 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112117 | Lukbanan ES | CAPALONGA | 1st | 1 | 2 | Repair of Classrooms | 1304151.37 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112127 | Talento-Roll Elementary School | CAPALONGA | 1st | 1 | 4 | Repair of Classrooms | 2548913.05 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112151 | Jose Panganiban Elementary School | JOSE PANGANIBAN | 1st | 1 | 10 | Repair of Classrooms | 8550880.56 | DPWH (Batch 2) |  | Ongoing | 0.8 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1st | 1 | 9 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | Ongoing | 0.8 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 301901 | Larap NHS | JOSE PANGANIBAN | 1st | 1 | 9 | Repair of Classrooms | 5431736.33 | DPWH (Batch 2) |  | Ongoing | 0.8 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112165 | Pag-asa ES | JOSE PANGANIBAN | 1st | 1 | 4 | Repair of Classrooms | 2277976.29 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112171 | Sta. Elena ES | JOSE PANGANIBAN | 1st | 1 | 3 | Repair of Classrooms | 1872261.15 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 301886 | Bagong Silang I HS | LABO | 1st | 1 | 6 | Repair of Classrooms | 4033853.04 | DPWH (Batch 2) |  | Ongoing | 0.8 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112179 | Bulhao Elementary School | LABO | 1st | 1 | 5 | Repair of Classrooms | 3142718.83 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 500156 | Dumagmang IS | LABO | 1st | 1 | 3 | Repair of Classrooms | 1954692.04 | DPWH (Batch 2) |  | Ongoing | 0.8 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112209 | Florence Elementary School | LABO | 1st | 1 | 6 | Repair of Classrooms | 3519407.01 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112182 | Fundado ES | LABO | 1st | 1 | 8 | Repair of Classrooms | 4947116.61 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 301899 | Labo National High School | LABO | 1st | 1 | 4 | Repair of Classrooms | 868022.46 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 301894 | Labo Science and Tech. HS | LABO | 1st | 1 | 2 | Repair of Classrooms | 974361.61 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112213 | Macogon Elementary School | LABO | 1st | 1 | 4 | Repair of Classrooms | 2424142.79 | DPWH (Batch 2) |  | Ongoing | 0.8 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 301908 | Pag-Asa High School | LABO | 1st | 1 | 3 | Repair of Classrooms | 1877567.28 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112195 | Severino Francisco Elementary Sch. | LABO | 1st | 1 | 5 | Repair of Classrooms | 3142718.83 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112254 | Paracale Central School | PARACALE | 1st | 1 | 10 | Repair of Classrooms | 6244345.53 | DPWH (Batch 2) |  | Ongoing | 0.8 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 112255 | Pedro V. Moreno Elementary School | PARACALE | 1st | 1 | 3 | Repair of Classrooms | 1924142.79 | DPWH (Batch 2) |  | Ongoing | 0.8 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region V | Camarines Norte | 500634 | Sta. Elena Integrated School | SANTA ELENA | 1st | 1 | 10 | Repair of Classrooms | 4033012.12 | DPWH (Batch 2) |  | Ongoing | 0.8 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
REPAIR 2023 | Region V | Camarines Sur | 112458 | Cabusao Central School | CABUSAO | 1st | 1 | 4 | Repair of Classrooms | 2859969.17 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region V | Camarines Sur | 112460 | Castillo ES | CABUSAO | 1st | 1 | 3 | Repair of Classrooms | 2859969.17 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region V | Camarines Sur | 112780 | Loob ES - Gainza | GAINZA | 2nd | 1 | 3 | Repair of Classrooms | 2544562.23 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region V | Camarines Sur | 112766 | San Antonio ES | BOMBON | 3rd | 1 | 8 | Repair of Classrooms | 4752458.29 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region V | Camarines Sur | 112768 | San Roque ES | BOMBON | 3rd | 1 | 7 | Repair of Classrooms | 5165841.35 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region V | Catanduanes | 113154 | Bugao CES | BAGAMANOC | Lone | 1 | 6 | Repair of Classrooms | 5250453.9 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-06-02 | 2024-06-02 | [7 empty] | Altev Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Catanduanes | 113155 | Cahan Bo. Sch. | BAGAMANOC | Lone | 1 | 2 | Repair of Classrooms | 1890151.3 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-02-11 | 2024-02-11 | [7 empty] | Tri-John Trading & Constrution |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region V | Catanduanes | 113162 | Pangcayanan ES | BAGAMANOC | Lone | 1 | 4 | Repair of Classrooms | 3382318.24 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-02-11 | 2024-02-11 | [7 empty] | Dawn Engineering Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region V | Catanduanes | 302100 | San Vicente National High School | BAGAMANOC | Lone | 1 | 4 | Repair of Classrooms | 3781963 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-02-11 | 2024-02-11 | [7 empty] | Dawn Engineering Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region V | Catanduanes | 174003 | Bagumbayan ES | BATO | Lone | 1 | 3 | Repair of Classrooms | 2537038.77 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-02-11 | 2024-02-11 | [7 empty] | NVR Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region V | Catanduanes | 113181 | Batalay ES | BATO | Lone | 1 | 3 | Repair of Classrooms | 2536352.7 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-02-27 | 2024-01-08 | [7 empty] | JYM Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region V | Catanduanes | 113187 | Libjo ES | BATO | Lone | 1 | 6 | Repair of Classrooms | 5072704.58 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-03-12 | 2024-03-12 | [7 empty] | Al-Jon Construction Dev. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Catanduanes | 113188 | Mintay Elementary School | BATO | Lone | 1 | 3 | Repair of Classrooms | 2536352.34 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-04-24 | 2024-05-10 | [7 empty] | TNB Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region V | Catanduanes | 113246 | Bayhan PS | PANGANIBAN (PAYO) | Lone | 1 | 3 | Repair of Classrooms | 2536172.7 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-02-11 | 2024-02-11 | [7 empty] | NVR Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region V | Catanduanes | 113251 | Maculiw Comm. Sch. | PANGANIBAN (PAYO) | Lone | 1 | 5 | Repair of Classrooms | 4676954.5 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-03-12 | 2024-03-12 | [7 empty] | NVR Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region V | Catanduanes | 113305 | San Miguel CES | SAN MIGUEL | Lone | 1 | 23 | Repair of Classrooms | 21283990.7 | DPWH (Batch 1) |  | Ongoing | 0.8 | [9 empty] | Tri-John Trading & Constrution |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0
REPAIR 2023 | Region V | Catanduanes | 113297 | Tobrehon ES | SAN MIGUEL | Lone | 1 | 2 | Repair of Classrooms | 2350781.8 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-04-11 | 2024-04-11 | [7 empty] | Dawn Engineering Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region V | Legaspi City | 114458 | Bogna Elementary School | LEGAZPI CITY (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 6000000 | DPWH (Batch 2) | 5613434.75 | Ongoing | 0 | 2024-05-01 |  |  | 23FB0230 |  |  | 2024-01-09 |  | 2024-02-01 | NEXT GENERATION CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | Region V | Legaspi City | 114483 | Puro Elementary School | LEGAZPI CITY (Capital) | 2nd | 1 | 14 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9347918.16 | Ongoing | 0 | 2024-05-01 |  |  | 23FB0232 |  |  | 2024-01-09 |  | 2024-02-01 | 9 LEAVES BUILDERS AND SUPPLY CORP. |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0
REPAIR 2023 | Region V | Legaspi City | 114496 | Tamaoyan ES | LEGAZPI CITY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 3000000 | DPWH (Batch 2) | 2805713.75 | Ongoing | 0 | 2024-04-01 |  |  | 23FB0233 |  |  | 2024-01-09 |  | 2024-02-01 | NEXT GENERATION CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region V | Legaspi City | 114474 | Taysan ES | LEGAZPI CITY (Capital) | 2nd | 1 | 16 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9337918.16 | Ongoing | 0 | 2024-06-30 |  |  | 23FB0231 |  |  | 2024-01-09 |  | 2024-02-01 | 9 LEAVES BUILDERS AND SUPPLY CORP. |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 113571 | Boca Engano Elementary School | CLAVERIA | 1st | 1 | 4 | Repair of Classrooms | 3582353.22 | DPWH (Batch 2) | 3411034.83 | Ongoing | 0.655 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 113577 | Claveria North CS | CLAVERIA | 1st | 1 | 13 | Repair of Classrooms | 11230264.95 | DPWH (Batch 2) | 10723313.99 | Ongoing | 0.3105 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 113581 | Mabiton Elementary School | CLAVERIA | 1st | 1 | 6 | Repair of Classrooms | 5355266.35 | DPWH (Batch 2) | 5141976.99 | Ongoing | 0.351 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 302163 | Quezon National High School | CLAVERIA | 1st | 1 | 6 | Repair of Classrooms | 5315078.35 | DPWH (Batch 2) | 5074974.33 | Ongoing | 0.3005 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 113770 | Monreal Central School | MONREAL | 1st | 1 | 10 | Repair of Classrooms | 8695825.3 | DPWH (Batch 2) | 8306135.92 | Ongoing | 0.9056 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 302152 | Monreal National High School | MONREAL | 1st | 1 | 12 | Repair of Classrooms | 10385160.58 | DPWH (Batch 2) | 9919485 | Ongoing | 0.9015 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 501273 | Buenavista Integrated School | SAN FERNANDO | 1st | 1 | 3 | Repair of Classrooms | 2599312.2 | DPWH (Batch 2) | 2483236.9 | COMPLETED | 0.998 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region V | Masbate | 113865 | Canelas ES | SAN FERNANDO | 1st | 1 | 2 | Repair of Classrooms | 1728321.7 | DPWH (Batch 2) | 1650678.98 | COMPLETED | 0.9975 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region V | Masbate | 113872 | P. Basas ES | SAN FERNANDO | 1st | 1 | 5 | Repair of Classrooms | 4412819.8 | DPWH (Batch 2) | 4214030.77 | Ongoing | 0.903 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 113888 | Calipat-an ES | SAN JACINTO | 1st | 1 | 5 | Repair of Classrooms | 4420258.25 | DPWH (Batch 2) | 4125743.79 | Ongoing | 0.8015 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 113894 | Leonardo Barrun ES | SAN JACINTO | 1st | 1 | 5 | Repair of Classrooms | 4502160.5 | DPWH (Batch 2) | 4298868.07 | Ongoing | 0.8724 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 302167 | San Jacinto National High School | SAN JACINTO | 1st | 1 | 15 | Repair of Classrooms | 13480215.03 | DPWH (Batch 2) | 12871609.07 | Ongoing | 0.8675 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 302108 | Adelina P. Laurio National High School | SAN PASCUAL | 1st | 1 | 6 | Repair of Classrooms | 5288153.45 | DPWH (Batch 2) | 5049661.09 | Ongoing | 0.954 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 302137 | Halabangbaybay National High School | SAN PASCUAL | 1st | 1 | 2 | Repair of Classrooms | 1753510.58 | DPWH (Batch 2) | 1674253.64 | Ongoing | 0.858 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 500161 | Iniwaran Integrated School | SAN PASCUAL | 1st | 1 | 11 | Repair of Classrooms | 9548028.05 | DPWH (Batch 2) | 9118339.59 | Ongoing | 0.324 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 113919 | Juanito G. Alburo Elementary School | SAN PASCUAL | 1st | 1 | 2 | Repair of Classrooms | 1802123.93 | DPWH (Batch 2) | 1720586.86 | Ongoing | 0.8361 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 501256 | Palani Integrated School | BALUD | 2nd | 1 | 8 | Repair of Classrooms | 14603252.3 | DPWH (Batch 2) | 14232366.2 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region V | Masbate | 302177 | Villahermosa National High School | CAWAYAN | 3rd | 1 | 6 | Repair of Classrooms | 8022938.63 | DPWH (Batch 2) |  | Ongoing | 0.0436 | 2024-04-29 | [9 empty] | suspended | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 113810 | Guindawahan ES | PIO V. CORPUZ (LIMBUHAN) | 3rd | 1 | 9 | Repair of Classrooms | 11365012.29 | DPWH (Batch 2) |  | Ongoing | 0.758 | 2024-05-29 | [10 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate | 113827 | Locso-an ES | PLACER | 3rd | 1 | 3 | Repair of Classrooms | 4105284.92 | DPWH (Batch 2) |  | Ongoing | 0.0928 | 2024-03-30 | [9 empty] | suspended | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region V | Masbate City | 321805 | Bantigue High School | CITY OF MASBATE (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 3161938.74 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region V | Masbate City | 321804 | Bayombon High School | CITY OF MASBATE (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 3037442.85 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region V | Masbate City | 302148 | Masbate National Comprehensive High School | CITY OF MASBATE (Capital) | 2nd | 1 | 15 | Repair of Classrooms | 9508908.36 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2023 | Region V | Sorsogon | 302192 | Bulusan High School | BULUSAN | 2nd | 1 | 6 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Sorsogon | 302225 | Matnog National High School | MATNOG | 2nd | 1 | 6 | Repair of Classrooms | 6700000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Sorsogon City | 114552 | Abuyog Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Sorsogon City | 114524 | Bon-ot Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Sorsogon City | 302271 | Buenavista National High School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Sorsogon City | 302280 | Lydia D. Martinez Memorial High School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Sorsogon City | 302274 | Osiao Paglingap National High School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Sorsogon City | 114575 | Pangpang Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) | 4974858.82 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Sorsogon City | 114560 | Rosa T. Arellano Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Sorsogon City | 114542 | San Isidro Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Sorsogon City | 114545 | San Ramon Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Sorsogon City | 114581 | Sorsogon Pilot Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region V | Tabaco City | 136936 | Guinobat Elementary School | CITY OF TABACO | 1st | 1 | 1 | Repair of Classroom | 1691410.42 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region V | Tabaco City | 114594 | Oson ES | CITY OF TABACO | 1st | 1 | 3 | Repair of Classrooms | 3215013.32 | DPWH (Batch 2) |  | Ongoing | 0.8 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region V | Tabaco City | 114595 | Pawa ES | CITY OF TABACO | 1st | 1 | 5 | Repair of Classrooms | 4915922.5 | DPWH (Batch 2) |  | Ongoing | 0.8 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region V | Tabaco City | 114603 | Tabaco North CS | CITY OF TABACO | 1st | 1 | 2 | Repair of Classrooms | 1966369 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region V | Albay | 111880 | Ogob Elementary School | MALINAO | 1st | 1 | 5 | Repair of Classrooms | 6455251.77 | 1 | 4530032.65 | COMPLETED | 1 |  |  | PV-ALBAYINFRA-24-02 | PV-ALBAYINFRA-24-02 | 2024-09-06 |  | 2024-09-27 | 2024-11-08 |  | 3G Builder and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region V | Camarines Norte | 112231 | Mambungalon Elementary School | MERCEDES | 2nd | 1 | 7 | Repair of Classrooms | 4595959.6 | 1 |  | COMPLETED | 1 | [10 empty] | MOBILIZATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2024 | Region V | Camarines Norte | 301918 | San Roque National High School | MERCEDES | 2nd | 1 | 10 | Repair of Classrooms | 6565656.57 | 1 |  | COMPLETED | 1 | [10 empty] | MOBILIZATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region V | Camarines Norte | 112239 | Tagongtong Elementary School | MERCEDES | 2nd | 1 | 6 | Repair of Classrooms | 3175781.28 | 1 |  | COMPLETED | 1 | [10 empty] | MOBILIZATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region V | Camarines Sur | 112566 | Salvacion Elementary School | CARAMOAN | 4th | 1 | 8 | Repair of Classrooms | 7507902.26 | 1 |  | Not yet started | 0 | [10 empty] | waiting for NTP | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
REPAIR 2024 | Region V | Camarines Sur | 112993 | Turague ES | SAGÑAY | 4th | 1 | 4 | Repair of Classrooms | 3765384.78 | 1 |  | Not yet started | 0 | [10 empty] | waiting for NTP | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
REPAIR 2024 | Region V | Catanduanes | 113310 | Buenavista ES | VIGA | Lone | 1 | 4 | Repair of Classrooms | 5050505.05 | 1 | 4163634.52 | COMPLETED | 1 | [10 empty] | for issuance of contract award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region V | Iriga City | 114426 | San Miguel Elementary School | IRIGA CITY | 5th | 1 | 1 | Repair of Classrooms | 2280005.28 | 1 |  | under procurement | 0 |  |  | 2024-06-24-PR-122 |  | 2024-06-28 | 2024-07-12 | 2024-07-25 | - |  |  | For Award | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
REPAIR 2024 | Region V | Iriga City | 114442 | Sta. Teresita Elementary School | IRIGA CITY | 5th | 1 | 5 | Repair of Classrooms | 4747474.75 | 1 |  | under procurement | 0 |  |  | 2024-06-24-PR-122 |  | 2024-06-28 | 2024-07-12 | 2024-07-25 | - |  |  | For Award | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0
REPAIR 2024 | Region V | Ligao City | 321701 | Ligao City National Technical Vocational High School | CITY OF LIGAO | 3rd | 1 | 3 | Repair of Classrooms | 4417204.97 | 1 |  | Under Procurement | 0 | [10 empty] | for award | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
REPAIR 2024 | Region V | Masbate | 113481 | Danao Elementary School | BATUAN | 1st | 1 | 7 | Repair of Classrooms | 6724383.84 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0
REPAIR 2024 | Region V | Masbate | 113586 | Nonoc Elemantary School | CLAVERIA | 1st | 1 | 5 | Repair of Classrooms | 4803030.3 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0
REPAIR 2024 | Region V | Masbate | 113588 | Pasig ES | CLAVERIA | 1st | 1 | 2 | Repair of Classrooms | 1921212.12 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
REPAIR 2024 | Region V | Masbate | 113916 | Gemino Elementary School | SAN PASCUAL | 1st | 1 | 6 | Repair of Classrooms | 4068769.7 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0
REPAIR 2024 | Region V | Masbate City | 113680 | Julian V. Antonio Elementary School | CITY OF MASBATE (Capital) | 2nd | 1 | 9 | Repair of Classrooms | 6739010.88 | 1 | 6622475.05 | COMPLETED | 1 | [10 empty] | revised program of works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2024 | Region V | Naga City | 302265 | Cararayan National High School | NAGA CITY | 3rd | 1 | 10 | Repair of Classrooms | 9212714.83 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0
REPAIR 2024 | Region V | Sorsogon | 302230 | Pilar National Comprehensive High School | PILAR | 1st | 1 | 7 | Repair of Classrooms | 6910782.67 | 1 | 6132057.75 | COMPLETED | 1 | 2025-04-24 |  | 24-11-002 | 24-11-002 | 2024-11-19 | 2024-11-27 | 2024-12-09 | 2024-12-23 | 2024-12-26 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2024 | Region V | Sorsogon City | 114541 | Rawis Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 8 | Repair of Classrooms | 2086653.56 | 1 | 2060786.04 | COMPLETED | 1 | 2025-06-01 |  |  |  | September 30, 2024-October 21, 2024 | 2024-10-08 | 2024-10-21 | 2024-10-24 | 2024-10-27 |  | SARO Released | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region V | Sorsogon City | 114533 | Sugod Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 14 | Repair of Classrooms | 4954004.55 | 1 | 4899463.03 | COMPLETED | 1 | 2025-06-01 |  |  |  | September 30, 2024-October 21, 2025 | 2024-10-09 | 2024-10-21 | 2024-10-25 | 2024-10-28 |  | REALIGNED FROM ROSA ARELLANO ES TO SUGOD ES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%