## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | WITH TRANSFOPMER (Y/N) | CATEGORY 2 | Status as of July 4, 2025
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 128423 | Anagase Elementary School | MONKAYO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 818399.6 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 204019 | Cabanggatan PS | MONTEVISTA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 575410.75 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 128467 | Mabanda PS | MONTEVISTA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 420762.11 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 128510 | Andap ES | NEW BATAAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 668672.61 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 204022 | Limot ES | LAAK (SAN VICENTE) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 632284.71 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 128351 | Kinuban ES | MACO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 934118.77 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 128356 | New Barili PS | MACO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 463178.19 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Davao del Norte | 128580 | Mahayahay PS | ASUNCION (SAUG) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 2067596.67 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Davao del Norte | 128707 | Kauswagan PS | NEW CORELLA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 3128902.13 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Davao del Norte | 128805 | Paiton ES | TALAINGOD | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 2573784.66 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Davao del Sur | 129083 | Langan ES | SANTA CRUZ | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 737544.94 |  | REVERTED | 0 | [11 empty] | road right of way, redflag area | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Davao del Sur | 129096 | Patulangon ES | SANTA CRUZ | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 842005.11 |  | REVERTED | 0 | [11 empty] | road right of way, redflag area | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Davao del Sur | 129087 | Tubison ES | SANTA CRUZ | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1713885.41 |  | REVERTED | 0 | [11 empty] | road right of way, redflag area | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Davao del Sur | 128885 | Mangili ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1692446.88 |  | REVERTED | 0 | [11 empty] | road right of way, redflag area | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Davao del Sur | 128890 | San Felipe ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 404576.81 |  | REVERTED | 0 | [11 empty] | road right of way, redflag area | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Davao del Sur | 205056 | Malandog PS | MALITA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 821644.79 |  | REVERTED | 0 | [11 empty] | road right of way, redflag area | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Davao Oriental | 129201 | Cauwayanan PS | BOSTON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 745934.81 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Davao Oriental | 129230 | Balete PS | CARAGA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 437974.54 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Island Garden City of Samal | 128741 | Tagluno ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 849741.28 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region XI | Island Garden City of Samal | 128742 | Tayapoc ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 461553.36 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 315819 | Bango NHS | COMPOSTELA | 1 | 1 | UPGRADING | 1 | 1577775.19 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304187 | Gabi NHS | COMPOSTELA | 1 | 1 | UPGRADING | 1 | 2215840.5 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304196 | Maparat NHS | COMPOSTELA | 1 | 1 | UPGRADING | 1 | 1842092.83 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304183 | San Miguel NHS | COMPOSTELA | 1 | 1 | UPGRADING | 1 | 1536512.2 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304210 | Siocon NHS | COMPOSTELA | 1 | 1 | UPGRADING | 1 | 1982927.43 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304198 | Maragusan NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | UPGRADING | 1 | 2216542.6 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304213 | Tupaz NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | UPGRADING | 1 | 2049802.28 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304200 | Awao NHS | MONKAYO | 1 | 1 | UPGRADING | 1 | 1590494.75 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304202 | Montevista NHS | MONTEVISTA | 1 | 1 | UPGRADING | 1 | 2256983.26 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304206 | New Bataan NHS | NEW BATAAN | 1 | 1 | UPGRADING | 1 | 3230614.47 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304185 | Don Vicente Romualdez NHS | LAAK (SAN VICENTE) | 2 | 1 | UPGRADING | 1 | 1815283.9 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 315812 | San Antonio NHS | LAAK (SAN VICENTE) | 2 | 1 | UPGRADING | 1 | 1611721.23 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304192 | Mabini NHS | MABINI (DOÑA ALICIA) | 2 | 1 | UPGRADING | 1 | 1967172.3 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 315805 | Pindasan NHS | MABINI (DOÑA ALICIA) | 2 | 1 | UPGRADING | 1 | 1973452.43 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304193 | Atty. Orlando S. Rimando National High School | MACO | 2 | 1 | UPGRADING | 1 | 2108048.83 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304194 | Mainit NHS | NABUNTURAN (Capital) | 2 | 1 | UPGRADING | 1 | 1527258.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304195 | Manat NHS | NABUNTURAN (Capital) | 2 | 1 | UPGRADING | 1 | 1584788.55 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304205 | Nabunturan NCHS | NABUNTURAN (Capital) | 2 | 1 | UPGRADING | 2 | 4870283.68 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 315818 | New Sibonga NHS | NABUNTURAN (Capital) | 2 | 1 | UPGRADING | 1 | 1656335.98 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304175 | Araibo NHS | PANTUKAN | 2 | 1 | UPGRADING | 2 | 1488006.88 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304179 | Bongabong NHS | PANTUKAN | 2 | 1 | UPGRADING | 1 | 1646320.97 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 315807 | Magnaga NHS | PANTUKAN | 2 | 1 | UPGRADING | 1 | 1444563.04 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 315816 | Napnapan NHS | PANTUKAN | 2 | 1 | UPGRADING | 1 | 1739949.59 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304208 | Pantukan NHS | PANTUKAN | 2 | 1 | UPGRADING | 1 | 2390105.78 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304211 | Tambongon NHS | PANTUKAN | 2 | 1 | UPGRADING | 1 | 1647295.44 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129711 | A. Mabini Elementary School | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 3755429.04 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129554 | Bolton ES | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 3370166.21 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129715 | Catalunan Grande ES | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 2693686.59 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129716 | Catalunan Pequeño Elementary School | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 1880086.11 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 316202 | Catalunan Pequeno National High School | DAVAO CITY | 1 | 1 | UPGRADING | 2 | 278196.92 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 316202 | Catalunan Pequeno National High School | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 2342306.55 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304359 | Daniel R. Aguinaldo NHS (Matina NHS) | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 3012928.03 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304360 | Davao City NHS | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 9527632.08 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304363 | Davao City Special National High School | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 836317.44 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129640 | Don Manuel Gutierrez ES | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 2710768.98 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304377 | JESUS J. SORIANO NATIONAL HIGH SCHOOL | DAVAO CITY | 1 | 1 | UPGRADING | 2 | 6449590.2 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129557 | Kapt. T. Monteverde Sr. CES | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 6321696.54 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129645 | Maa CES | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 4949650.65 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304376 | Mabini NHS | DAVAO CITY | 1 | 1 | UPGRADING | 2 | 525546.17 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129558 | Magallanes Elementary School | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 3557366.18 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129648 | Matina CES | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 3501218.5 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129708 | STA. ANA CENTRAL ELEM. SCHOOL | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 2927961.31 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304393 | Sta. Ana National High School | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 2746820.78 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304396 | Talomo National High School | DAVAO CITY | 1 | 1 | UPGRADING | 2 | 1136880.49 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 316201 | Bernardino B. Bosque NHS | DAVAO CITY | 2 | 1 | UPGRADING | 2 | 233327.26 |  | TERMINATED | 0.35 | [10 empty] | WITH ORDER OF TERMINATION | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304364 | E. Ramos NHS | DAVAO CITY | 2 | 1 | UPGRADING | 2 | 317915.81 |  | TERMINATED | 0.95 | [10 empty] | WITH ORDER OF TERMINATION | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304379 | Malabog National High School | DAVAO CITY | 2 | 1 | UPGRADING | 2 | 591519.51 |  | TERMINATED | 0.35 | [10 empty] | WITH ORDER OF TERMINATION | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304380 | Mandug NHS (Pablo Lorenzo NHS) | DAVAO CITY | 2 | 1 | UPGRADING | 2 | 412886.5 |  | TERMINATED | 0.35 | [10 empty] | WITH ORDER OF TERMINATION | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304350 | Binugao NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 499043.45 |  | TERMINATED | 0.95 | [10 empty] | WITH ORDER OF TERMINATION | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129531 | Calinan Central ES | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 4522920.58 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304354 | Calinan NHS | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 2924771.08 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304356 | CROSSING BAYABAS NHS | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 3392495.11 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304361 | Dona Carmen Denia NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 1150615.64 |  | TERMINATED | 0.9 | [10 empty] | WITH ORDER OF TERMINATION | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304395 | Emilio J. Estipona- Guinga NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 366616.43 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129734 | Imelda Elementary School | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 4241723.96 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129735 | Los Amigos Elementary School | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 2517477.99 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304373 | Los Amigos NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 256124.71 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304373 | Los Amigos NHS | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 2150634.55 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129538 | Lt. C. Villafuerte, Sr. ES | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 4173960.12 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304342 | Ma. Cristina P. Belcar Agricultural High School | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 331453.28 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304381 | Marilog High School of Agriculture (Tech-Voc School) | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 695170.9 |  | TERMINATED | 0.95 | [10 empty] | WITH ORDER OF TERMINATION | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304382 | Marilog National High School | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 380451.14 |  | TERMINATED | 0.95 | [10 empty] | WITH ORDER OF TERMINATION | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304385 | Mintal Comprehensive High School | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 1903999.24 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129738 | Mintal ES | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 1918342.63 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304387 | Mintal NCHS - Tugbok National HS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 370656.24 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304387 | Mintal NCHS - Tugbok National HS | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 2441028.74 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304388 | Optaciano Hilay NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 291703.36 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304392 | Sirib NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 329202.03 |  | TERMINATED | 0.95 | [10 empty] | WITH ORDER OF TERMINATION | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304386 | Sto. Niño National High School | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 388721.87 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304394 | Tagakpan NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 292433.51 |  | TERMINATED | 0.35 | [10 empty] | WITH ORDER OF TERMINATION | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304348 | Talandang National High School | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 699926.67 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 129743 | Tugbok Central ES SPED Center | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 4267840.04 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao City | 304355 | Wangan National High School | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 515482.7 |  | TERMINATED | 0.35 | [10 empty] | WITH ORDER OF TERMINATION | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304217 | Asuncion National High School | ASUNCION (SAUG) | 1 | 1 | UPGRADING | 1 | 4595542.1 | 4565466.8962 | COMPLETED | 1 | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304252 | Sonlon NHS | ASUNCION (SAUG) | 1 | 1 | UPGRADING | 3 | 4621351.67 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304233 | Kapalong National High School | KAPALONG | 1 | 1 | UPGRADING | 1 | 7579333.47 | 7535212.4937 | COMPLETED | 1 | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304243 | Semong NHS | KAPALONG | 1 | 1 | UPGRADING | 1 | 2515559.99 | 2495918.5425 | COMPLETED | 1 | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304239 | Limbaan NHS | NEW CORELLA | 1 | 1 | UPGRADING | 1 | 2198146.77 | 2179840.7665 | COMPLETED | 1 | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304248 | New Corella NHS | NEW CORELLA | 1 | 1 | UPGRADING | 1 | 7374066.58 | 7330665.0978 | COMPLETED | 1 | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304240 | Linao NHS | SAN ISIDRO | 1 | 1 | UPGRADING | 1 | 2119197.91 | 2101855.5785 | COMPLETED | 1 | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304286 | Marber NHS | BANSALAN | 1 | 1 | UPGRADING | 1 | 1637941.03 | 1596873.83 | COMPLETED | 1 | 2018-12-03 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-31 | NLC Construction and Supplies |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304275 | Hagonoy NHS | HAGONOY | 1 | 1 | UPGRADING | 1 | 1776384.43 | 1739801.33 | COMPLETED | 1 | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304274 | Gov. N. Llanos NHS | KIBLAWAN | 1 | 1 | UPGRADING | 1 | 1258038.7 | 1250520.38 | COMPLETED | 1 | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304277 | Ihan NHS | KIBLAWAN | 1 | 1 | UPGRADING | 1 | 1059283.01 | 1052188.73 | COMPLETED | 1 | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 316001 | Molopolo National High School | KIBLAWAN | 1 | 1 | UPGRADING | 1 | 1689841.2 | 1679718.85 | COMPLETED | 1 | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304270 | Davao Del Sur SOF | MALALAG | 1 | 1 | UPGRADING | 1 | 1532696.52 | 1523160.17 | COMPLETED | 1 | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304289 | Bangkal NHS | MATANAO | 1 | 1 | UPGRADING | 1 | 1438008.41 | 1541904.44 | COMPLETED | 1 | 2018-11-28 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-08-02 | Optimun Equipment Management & Exchange Inc. |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304288 | Matanao National High School | MATANAO | 1 | 1 | UPGRADING | 1 | 3208710.59 | 2958144.97 | COMPLETED | 1 | 2018-11-28 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-08-02 | Optimun Equipment Management & Exchange Inc. |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 316003 | SALUD CAGAS TECH.& VOC. H.S | MATANAO | 1 | 1 | UPGRADING | 1 | 1525198.43 | 1578855.9 | COMPLETED | 1 | 2018-11-28 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-08-02 | Optimun Equipment Management & Exchange Inc. |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 316002 | Padada NHS | PADADA | 1 | 1 | UPGRADING | 1 | 1528067.29 | 1518730.69 | COMPLETED | 1 | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304295 | Bato NHS | SANTA CRUZ | 1 | 1 | UPGRADING | 1 | 1636984.63 | 1617487.41 | COMPLETED | 1 | 2018-12-03 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-31 | NLC Construction and Supplies |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304294 | Sta. Cruz National High School | SANTA CRUZ | 1 | 1 | UPGRADING | 1 | 1931198.96 | 1916291.38 | COMPLETED | 1 | 2018-12-03 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-31 | NLC Construction and Supplies |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 316005 | Felipe-Inocencia Deluao NHS | SULOP | 1 | 1 | UPGRADING | 1 | 1415134.64 | 1405605.54 | COMPLETED | 1 | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304297 | Sulop NHS | SULOP | 1 | 1 | UPGRADING | 1 | 1673254.53 | 1663115.64 | COMPLETED | 1 | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304272 | Don Marcelino NHS | DON MARCELINO | 0 | 1 | UPGRADING | 1 | 1196696.01 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304291 | Lawa NHS | DON MARCELINO | 0 | 1 | UPGRADING | 1 | 1369552.62 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304264 | Balangonan NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | UPGRADING | 1 | 1247574.58 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304273 | Edna Guillermo MHS | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | UPGRADING | 1 | 1407917.46 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304281 | Jose Abad Santos NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | UPGRADING | 1 | 1912853.84 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304283 | Kalbay NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | UPGRADING | 1 | 1461438.74 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304271 | Demolok Valley NHS | MALITA | 0 | 1 | UPGRADING | 1 | 1406972.92 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304287 | Mariano Peralta NHS | MALITA | 0 | 1 | UPGRADING | 1 | 1586869.34 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304266 | Basiawan NHS | SANTA MARIA | 0 | 1 | UPGRADING | 1 | 1403358.25 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304276 | Heracleo Casco MNHS | SANTA MARIA | 0 | 1 | UPGRADING | 1 | 4916224.97 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304268 | Tubalan Comprehensive NHS | SANTA MARIA | 0 | 1 | UPGRADING | 1 | 1441567.12 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Oriental | 304300 | Baganga NHS | BAGANGA | 1 | 1 | UPGRADING | 2 | 3765128.18 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Davao Oriental | 304311 | Cateel Vocational High School | CATEEL | 1 | 1 | UPGRADING | 2 | 4353915.65 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Digos City | 129771 | Ramon Magsaysay CES | CITY OF DIGOS (Capital) | 1 | 1 | UPGRADING | 2 | 1574224.53 | 1566392.57 | COMPLETED | 1 | February 27, 2019 | February 27, 2019 | 18-04-059 | 18-04-059 | sept. 14-21, 2019 | sept.18, 2018 | sept. 21, 2018 | nov. 13, 2018 | Nov. 21, 2018 | NLC Construction and Supplies |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 128598 | Angel Villarica CES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 2121738.8 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 304216 | Anonang National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1720922.63 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 128599 | Balet ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1586670.16 |  | REVERTED | 0 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 330003 | Bandera NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1321344.21 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 304223 | Cogon NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1278338.16 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 323402 | Del Monte National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1376220.48 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 304236 | Kaputian National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1719112.37 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 330004 | Libertad NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1653793.35 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 304245 | Mambago-B NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1994248.56 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 304247 | Matanos NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1227424.98 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 323403 | Nieves Villarica NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1813766.35 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 330002 | San Jose NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1296202.48 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 304259 | Tagbitan-Ag NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1624588.6 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Mati City | 304326 | Mati SAT | CITY OF MATI (Capital) | 2 | 1 | UPGRADING | 2 | 6004556.65 | 5944653.73 | COMPLETED | 1 | 2019-01-24 |  |  |  | 2018-06-14 | 2018-05-29 | 2018-06-26 | 2018-07-10 | 2018-07-24 | MATT GLASS |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Mati City | 304321 | Lupon NCHS | LUPON | 2 | 1 | UPGRADING | 2 | 2039801.11 | 2024474.47 | COMPLETED | 1 | 2019-01-24 |  |  |  | 2018-06-14 | 2018-05-29 | 2018-06-26 | 2018-07-10 | 2018-07-24 | MATT GLASS |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Mati City | 304319 | Lupon Vocational High School | LUPON | 2 | 1 | UPGRADING | 2 | 6223202.35 | 6186729.69 | COMPLETED | 1 | 2019-01-24 |  |  |  | 2018-06-14 | 2018-05-29 | 2018-06-26 | 2018-07-10 | 2018-07-24 | MATT GLASS |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Panabo City | 304405 | Don Manuel A. Javellana Memorial National High School | CITY OF PANABO | 2 | 1 | UPGRADING | 2 | 2086018.36 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Panabo City | 316401 | Southern Davao National High School | CITY OF PANABO | 2 | 1 | UPGRADING | 2 | 2972771.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Tagum City | 322401 | Canocotan National High School | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING | 2 | 319590.45 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Tagum City | 304231 | Jose Tuason Jr. Memorial National High School | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING | 2 | 884175.83 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Tagum City | 500426 | PANDAPAN INTEGRATED SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING | 2 | 195718.99 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region XI | Tagum City | 304232 | Pipisan Maug National High School | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING | 2 | 523181.14 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304181 | Compostela NHS | COMPOSTELA | 1 | 1 | UPGRADING |  | 6295882.57 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304184 | Consuelo M. Valderrama NHS | COMPOSTELA | 1 | 1 | UPGRADING |  | 1436256.7 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304182 | Mangayon NHS | COMPOSTELA | 1 | 1 | UPGRADING | Batch 3 | 1680049.81 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304197 | Mapawa NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | UPGRADING |  | 1585552 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315815 | New Albay NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | UPGRADING |  | 2843195.97 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304176 | Babag NHS | MONKAYO | 1 | 1 | UPGRADING |  | 2770431.56 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304199 | Monkayo NHS | MONKAYO | 1 | 1 | UPGRADING |  | 3251134.22 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304212 | Tubo-Tubo NHS | MONKAYO | 1 | 1 | UPGRADING |  | 1344195.54 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315808 | Ulip NHS | MONKAYO | 1 | 1 | UPGRADING | Batch 3 | 2954167 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304214 | Union NHS | MONKAYO | 1 | 1 | UPGRADING | Batch 3 | 2627910.34 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315809 | Union NHS-Mt. Diwata HS Annex | MONKAYO | 1 | 1 | UPGRADING | Batch 3 | 1499867.61 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304204 | Mayaon NHS | MONTEVISTA | 1 | 1 | UPGRADING |  | 2689411.86 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304203 | Montevista NHS - Annex (DNAS Campus) | MONTEVISTA | 1 | 1 | UPGRADING | Batch 3 | 3129371.5 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304177 | Bantacan NHS | NEW BATAAN | 1 | 1 | UPGRADING |  | 2833856.9 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304188 | Kapatagan NHS | LAAK (SAN VICENTE) | 2 | 1 | UPGRADING |  | 3157939.34 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304190 | Kidawa NHS | LAAK (SAN VICENTE) | 2 | 1 | UPGRADING | Batch 3 | 3626561.46 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304189 | Laak NHS | LAAK (SAN VICENTE) | 2 | 1 | UPGRADING |  | 3027138.44 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315804 | Melale NHS | LAAK (SAN VICENTE) | 2 | 1 | UPGRADING | Batch 3 | 2915818.11 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304173 | Anibongan NHS | MACO | 2 | 1 | UPGRADING |  | 1449654.3 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304172 | Andili NHS | MAWAB | 2 | 1 | UPGRADING |  | 1353002.48 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315802 | Nuevo Iloco NHS | MAWAB | 2 | 1 | UPGRADING |  | 1580540.52 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315803 | Tuboran NHS | MAWAB | 2 | 1 | UPGRADING | Batch 3 | 2663450.68 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315806 | Kao NHS | NABUNTURAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2681581.53 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304209 | Tagugpo NHS | PANTUKAN | 2 | 1 | UPGRADING | Batch 3 | 1238368.68 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304218 | Sagayen NHS | ASUNCION (SAUG) | 1 | 1 | UPGRADING |  | 5622172.2 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304224 | Datu Balong NHS | KAPALONG | 1 | 1 | UPGRADING | Batch 3 | 5483946.82 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304228 | Doña Carmen Soriano National High School | KAPALONG | 1 | 1 | UPGRADING |  | 2952034.62 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304235 | Sua-on National High School | KAPALONG | 1 | 1 | UPGRADING | Batch 3 | 2635137.92 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304249 | Mesaoy NHS | NEW CORELLA | 1 | 1 | UPGRADING |  | 2837977.31 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304251 | Sawata NHS | SAN ISIDRO | 1 | 1 | UPGRADING |  | 6298939.34 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304257 | Sto. Nino NHS | TALAINGOD | 1 | 1 | UPGRADING |  | 5634420.73 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128812 | Bansalan Central Elem. School | BANSALAN | 1 | 1 | UPGRADING | Batch 1 | 2383359.59 | 2207451.03 | COMPLETED | 1 | December 22,2019 |  |  | 1-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | Maqueserg Construction and General Merchandise |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 304285 | Pedro A. Arches NHS | BANSALAN | 1 | 1 | UPGRADING | Batch 1 | 1447719.2 | 1411278.87 | COMPLETED | 1 | December 22,2019 |  |  | 2-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | NLC Construction and Supplies |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128836 | Villa Doneza CES | BANSALAN | 1 | 1 | UPGRADING | Batch 3 | 2335932.4 |  | COMPLETED | 1 |  |  |  | DS EM 2019-01 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128870 | Guihing Central Elementary School | HAGONOY | 1 | 1 | UPGRADING | Batch 1 | 2150399.76 | 2028932.94 | COMPLETED | 1 | December 24,2019 |  |  | 3-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | Maqueserg Construction and General Merchandise |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128855 | Hagonoy Central Elementary School | HAGONOY | 1 | 1 | UPGRADING | Batch 3 | 2087722.19 |  | COMPLETED | 1 |  |  |  | DS EM 2019-02 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128905 | Kiblawan CES | KIBLAWAN | 1 | 1 | UPGRADING | Batch 3 | 2322173.05 |  | COMPLETED | 1 |  |  |  | DS EM 2019-03 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128923 | Barayong CES | MAGSAYSAY | 1 | 1 | UPGRADING | Batch 3 | 2112248.8 |  | COMPLETED | 1 |  |  |  | DS EM 2019-04 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128936 | Magsaysay CES | MAGSAYSAY | 1 | 1 | UPGRADING | Batch 3 | 2269964.75 |  | COMPLETED | 1 |  |  |  | DS EM 2019-05 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 304298 | Tacul Agricultural High School | MAGSAYSAY | 1 | 1 | UPGRADING | Batch 1 | 4471791.79 | 4160109.59 | COMPLETED | 1 | December 22,2019 |  |  | 1-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | Maqueserg Construction and General Merchandise |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128954 | Malalag CES | MALALAG | 1 | 1 | UPGRADING | Batch 3 | 2078178.95 |  | COMPLETED | 1 |  |  |  | DS EM 2019-06 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 129041 | Manga CES | MATANAO | 1 | 1 | UPGRADING | Batch 3 | 2102644.57 |  | COMPLETED | 1 |  |  |  | DS EM 2019-07 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao del Sur | 129017 | Matanao CES | MATANAO | 1 | 1 | UPGRADING | Batch 1 | 2319612.99 | 2205974.51 | COMPLETED | 1 | December 22,2019 |  |  | 2-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | NLC Construction and Supplies |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 304290 | Sinawilan NHS | MATANAO | 1 | 1 | UPGRADING | Batch 1 | 1538968.47 | 1492297.94 | COMPLETED | 1 | December 22,2019 |  |  | 2-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | NLC Construction and Supplies |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 129049 | Padada CES | PADADA | 1 | 1 | UPGRADING | Batch 1 | 2369621.24 | 2232525.74 | COMPLETED | 1 | December 24,2019 |  |  | 3-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | Maqueserg Construction and General Merchandise |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 129146 | Sulop CES | SULOP | 1 | 1 | UPGRADING | Batch 1 | 2353750.85 | 2221067.45 | COMPLETED | 1 | December 24,2019 |  |  | 3-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | Maqueserg Construction and General Merchandise |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Occidental | 316007 | Benjamin Velasco Bautista Sr. National High School | MALITA | 0 | 1 | UPGRADING | Batch 3 | 1408615.22 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Occidental | 304267 | FISHING VILLAGE COMPREHENSIVE NHS | MALITA | 0 | 1 | UPGRADING |  | 1257921.45 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Occidental | 304293 | Ticulon NHS | MALITA | 0 | 1 | UPGRADING | Batch 3 | 1249661.24 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Occidental | 304296 | Sta. Maria NHS | SANTA MARIA | 0 | 1 | UPGRADING |  | 1250031.25 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Oriental | 304312 | Crispin E. Rojas National High School | BAGANGA | 1 | 1 | UPGRADING |  | 5914339.61 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Oriental | 304307 | Caraga National High School | CARAGA | 1 | 1 | UPGRADING | Batch 3 | 3808099.56 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Oriental | 304315 | Evaristo Moralizon National Vocational High School | MANAY | 1 | 1 | UPGRADING | Batch 3 | 3654778.26 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Davao Oriental | 304339 | Tarragona National High School | TARRAGONA | 1 | 1 | UPGRADING |  | 3970083.06 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Digos City | 129762 | Aplaya ES | CITY OF DIGOS (Capital) | 1 | 1 | UPGRADING | Batch 3 | 272386.5 | 269983.44 | COMPLETED | 1 | February 3, 2020 | February 2, 2020 | 19-06-044 | 19-06-044 | July 16-23, 2019 | July 24, 2019 | August 15, 2019 | Sept. 2, 2019 | November 28, 2019 | NLC Const. and Supplies |  | N | UPGRADING
ELECTRIFICATION 2019 | Region XI | Digos City | 129774 | Binaton ES | CITY OF DIGOS (Capital) | 1 | 1 | UPGRADING | Batch 3 | 195783.19 | 194098.66 | COMPLETED | 1 | February 3, 2020 | February 2, 2020 | 19-06-044 | 19-06-044 | July 16-23, 2019 | July 24, 2019 | August 15, 2019 | Sept. 2, 2019 | November 28, 2019 | NLC Const. and Supplies |  | N | UPGRADING
ELECTRIFICATION 2019 | Region XI | Digos City | 129757 | Pedro Basalan ES | CITY OF DIGOS (Capital) | 1 | 1 | UPGRADING | Batch 1 | 462830.42 | 583893.06 | COMPLETED | 1 | March 22, 2020 | July 23, 2020 | 19-11-167 | 19-11-167 |  | December 13, 2019 | December 17, 2019 | Dec 27, 2019 | January 30, 2020 | Kuplaer Indsutries Inc. |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Digos City | 129756 | Remedios N. Saplala ES (Matti ES) | CITY OF DIGOS (Capital) | 1 | 1 | UPGRADING | Batch 1 | 205576.2 | 204548.32 | COMPLETED | 1 | Oct. 27, 2019 | Oct. 23, 2019 | 18-10-163 | 18-10-163 | March 1-8, 2019 | March 5, 2019 | March 8, 2020 | March 8, 2020 | Sept. 19, 2019 | NLC Const. and Supplies |  | N | UPGRADING
ELECTRIFICATION 2019 | Region XI | Digos City | 129772 | San Miguel ES | CITY OF DIGOS (Capital) | 1 | 1 | UPGRADING | Batch 3 | 59571.4 | 58635.31 | COMPLETED | 1 | February 3, 2020 | February 2, 2020 | 19-06-044 | 19-06-044 | July 16-23, 2019 | July 24, 2019 | August 15, 2019 | Sept. 2, 2019 | November 28, 2019 | NLC Const. and Supplies |  | N | UPGRADING
ELECTRIFICATION 2019 | Region XI | Island Garden City of Samal | 304220 | Balet National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | Batch 1 | 1586709.82 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Island Garden City of Samal | 323406 | Diosdado Alorro Sr. National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | Batch 3 | 1336130.85 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Mati City | 304301 | Manuel B.Guiñez Sr. NHS | BANAYBANAY | 2 | 1 | UPGRADING | Batch 3 | 5729701.05 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Mati City | 304325 | Mati National Comprehensive High School | CITY OF MATI (Capital) | 2 | 1 | UPGRADING |  | 8131204.06 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Panabo City | 304403 | A. O. Floirendo National High School | CITY OF PANABO | 2 | 1 | UPGRADING | Batch 1 | 4196054.58 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Panabo City | 304408 | Quezon High School - Panabo NHS Annex | CITY OF PANABO | 2 | 1 | UPGRADING | Batch 3 | 1980612.04 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Tagum City | 500424 | Busaon Integrated School | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING | Batch 3 | 283755.57 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Tagum City | 304238 | La Filipina NHS | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING |  | 342147.58 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Tagum City | 304226 | Laureta National High School | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING |  | 475540.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region XI | Tagum City | 500425 | Liboganon Integrated School | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING |  | 378339.03 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2020 | Region XI | Compostela Valley | 128263 | Compostela Central Elementary School SPED Center | COMPOSTELA | 1 | 1 |  |  | 1560677.62 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Compostela Valley-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Compostela Valley | 128471 | Montevista CES | MONTEVISTA | 1 | 1 |  |  | 1523927.62 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Compostela Valley-004 | [9 empty] | ENERGIZATION
ELECTRIFICATION 2020 | Region XI | Compostela Valley | 128353 | Maco CES | MACO | 2 | 1 |  |  | 1718201.62 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Compostela Valley-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Compostela Valley | 315811 | New Leyte NHS | MACO | 2 | 1 |  |  | 1653399.34 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Compostela Valley-010 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Compostela Valley | 304191 | Lorenzo S. Sarmiento Sr. High School | Mawab | 2 | 1 |  |  | 2310998.15 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Compostela Valley-012 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Compostela Valley | 304178 | Bayabas NHS | NABUNTURAN (Capital) | 2 | 1 |  |  | 1705680.41 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Compostela Valley-008 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao City | 129684 | Batolusa ES | DAVAO CITY | 3 | 1 |  |  | 651274.85 |  | REVERTED | 0 |  |  | Elec2020-RXI-Davao City-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao City | 304362 | J. V. Ferriols National High School | DAVAO CITY | 3 | 1 |  |  | 913273.2 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao City-006 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao del Norte | 304234 | Baltazar Nicor Valenzuela NHS | KAPALONG | 1 | 1 |  |  | 7489046.81 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao del Norte-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao del Norte | 304241 | Luna National High School | KAPALONG | 1 | 1 |  |  | 6751858.56 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao del Norte-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao del Norte | 304242 | Mabantao National High School | KAPALONG | 1 | 1 |  |  | 4689161.56 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao del Norte-006 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao del Norte | 304229 | Dujali National High School | BRAULIO E. DUJALI | 2 | 1 |  |  | 4793017.8 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao del Norte-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao del Norte | 315903 | Anibongan NHS | CARMEN | 2 | 1 |  |  | 4692273.78 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao del Norte-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao del Sur | 316004 | SACUB National High School | HAGONOY | 0 | 1 |  |  | 1972000 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao del Sur-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao del Sur | 304265 | Barayong National High School | MAGSAYSAY | 0 | 1 |  |  | 1855000 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao del Sur-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao del Sur | 304284 | Lower Bala NHS | MAGSAYSAY | 0 | 1 |  |  | 2032000 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao del Sur-006 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao del Sur | 304278 | Inawayan National High School | SANTA CRUZ | 0 | 1 |  |  | 1885000 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao del Sur-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao Occidental | 128984 | Julian M. Turado Elementary School | MALITA | 0 | 1 |  |  | 2533221.94 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao Occidental-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao Occidental | 129002 | Mana CES | MALITA | 0 | 1 |  |  | 1596018.47 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao Occidental-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao Occidental | 128978 | Mariano Peralta Elementary School | MALITA | 0 | 1 |  |  | 2284424.31 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao Occidental-006 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao Occidental | 129103 | Basiawan CES | SANTA MARIA | 0 | 1 |  |  | 2386647.34 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Davao Occidental-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao Oriental | 304299 | BACULIN NATIONAL HIGH SCHOOL | BAGANGA | 1 | 1 |  |  | 8618757.26 |  | COMPLETED | 1 |  |  | ELECTRICAL 2020 - RXI - DAVAO ORIENTAL - 006 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao Oriental | 304316 | DR. BEATO C. MACAYRA NATIONAL HIGH SCHOOL | BAGANGA | 1 | 1 |  |  | 8412844.35 |  | COMPLETED | 1 |  |  | ELECTRICAL 2020 - RXI - DAVAO ORIENTAL - 002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao Oriental | 304333 | SAN LUIS NATIONAL HIGH SCHOOL | CARAGA | 1 | 1 |  |  | 7901843.39 |  | COMPLETED | 1 |  |  | ELECTRICAL 2020 - RXI - DAVAO ORIENTAL - 004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao Oriental | 304324 | MANAY NATIONAL HIGH SCHOOL | MANAY | 1 | 1 |  |  | 8914736.56 |  | COMPLETED | 1 |  |  | ELECTRICAL 2020 - RXI - DAVAO ORIENTAL - 001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao Oriental | 304336 | SIGABOY AGRI. VOCATIONAL HIGH SCHOOL | GOV. GENEROSO | 2 | 1 |  |  | 9768019.9 |  | COMPLETED | 1 |  |  | ELECTRICAL 2020 - RXI - DAVAO ORIENTAL - 003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Davao Oriental | 304332 | SAN ISIDRO NATIONAL HIGH SCHOOL | SAN ISIDRO | 2 | 1 |  |  | 9575438.29 |  | COMPLETED | 1 |  |  | ELECTRICAL 2020 - RXI - DAVAO ORIENTAL - 005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Digos City | 316302 | Matti NHS | CITY OF DIGOS (Capital) | 1 | 1 |  |  | 1297472.16 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Digos City-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Digos City | 341513 | SHS in Digos City | CITY OF DIGOS (Capital) | 1 | 1 |  |  | 15116168.56 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Digos City-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Panabo City |  | Cagangohan Vicente NHS | CITY OF PANABO | 2 | 1 |  |  | 4037769.03 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Panabo City-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Panabo City | 316402 | San Vicente National High School | CITY OF PANABO | 2 | 1 |  |  | 3815398.53 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Panabo City-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Tagum City | 305519 | Magdum NHS | CITY OF TAGUM (Capital) | 1 | 1 |  |  | 468969.95 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Tagum City-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Tagum City | 128780 | NUEVA FUERZA ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 |  |  | 326769.68 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Tagum City-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Tagum City | 128781 | PAGSABANGAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 |  |  | 697323.98 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Tagum City-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Tagum City | 128797 | SAN ISIDRO ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 |  |  | 687687.18 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Tagum City-007 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region XI | Tagum City | 128785 | UNION ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 |  |  | 635797.78 |  | COMPLETED | 1 |  |  | Elec2020-RXI-Tagum City-008 | [9 empty] | UPGRADING
ELECTRIFICATION 2023 | Region XI | Mati City | 305680 | City of Mati National High School | CITY OF MATI (Capital) | 2nd | 1 | Energization of Electrical System (Overhead System) | 1 | 5726197.75 | 5692850.92 | COMPLETED | 1 | June 10,2024 | June 10,2024 |  |  | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | September 06, 2023 | AN Escalante Group Of Corporation |  |  | ENERGIZATION
ELECTRIFICATION 2023 | Region XI | Mati City | 304313 | Dawan NHS | CITY OF MATI (Capital) | 2nd | 1 | Energization of Electrical System (Overhead System) | 1 | 6181854.59 | 6152414.48 | COMPLETED | 1 | June 10,2024 | June 10,2024 |  |  | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | September 06, 2023 | AN Escalante Group Of Corporation |  |  | ENERGIZATION
ELECTRIFICATION 2024 | Region XI | Davao City | 129713 | Baliok ES | DAVAO CITY | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2246820.76 | 2157934.14 | COMPLETED | 1 | Oct.3, 2024 |  | BEFF-L001-2024 | #2 s.2024 INF DL-XI | Oct.27, 2023-November 16,2023 | Nov.3, 2023 | Nov.16, 2023 | Jan.12, 2024 | June 6, 2024 | CCO Engineering | On-going |  | UPGRADING
ELECTRIFICATION 2024 | Region XI | Davao City | 129167 | Jose Porras ES | DAVAO CITY | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1646373.74 | 1018018.77 | COMPLETED | 1 | Oct.3, 2024 |  | BEFF-L001-2024 | #2 s.2024 INF DL-XI | Oct.27, 2023-November 16,2023 | Nov.3, 2023 | Nov.16, 2023 | Jan.12, 2024 | June 6, 2024 | CCO Engineering | On-going |  | UPGRADING
ELECTRIFICATION 2024 | Region XI | Davao City | 129605 | Datu Lompipi ES | DAVAO CITY | 3rd | 1 | Installation of Solar Panel | 1 | 3500000 |  | COMPLETED | 1 |  |  | BEFF-L005-2024 |  | June 28-July 18, 2024 | July 5, 2024 | July 18, 2024 |  |  |  | On going procurement process |  | SOLAR
ELECTRIFICATION 2024 | Region XI | Davao City | 129740 | Tacunan Elementary | DAVAO CITY | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 813791.45 | 796189.62 | COMPLETED | 1 | Oct.3, 2024 |  | BEFF-L001-2024 | #2 s.2024 INF DL-XI | Oct.27, 2023-November 16,2023 | Nov.3, 2023 | Nov.16, 2023 | Jan.12, 2024 | June 6, 2024 | CCO Engineering | on-going |  | UPGRADING
ELECTRIFICATION 2024 | Region XI | Davao De Oro | 500456 | Panansalan Integrated School | COMPOSTELA | 1st | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 4500000 | 3250176.26 | Under Procurement | 0 |  |  | SDDO-010-2024 |  | August 08, 2024 | August 16, 2024 | August 29,2024 |  |  |  | on-going docs process of award,contract and ntp previous remarks:RE-BID; |  | UPGRADING
ELECTRIFICATION 2024 | Region XI | Davao De Oro | 128308 | Laak CES | LAAK (SAN VICENTE) | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 4000000 | 3001391.69 | Under Procurement | 0 |  |  | SDDO-018-2024 |  | Sept. 06, 2024 | sept. 18, 2024 |  |  |  |  | on-going docs process of award,contract and ntp previous remarks:RE-BID; |  | UPGRADING
ELECTRIFICATION 2024 | Region XI | Davao del Norte | 501766 | New Casay Integrated School | BRAULIO E. DUJALI | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3000000 | 2992389.58 | ONGOING | 0.98 |  |  |  |  | 2024-01-10 | 2024-01-17 | 2024-01-30 | 2024-03-19 | 2024-06-04 | Magnum Builders Corp | this school belongs to the 2nd dist of davao del norte, for energization of DAVAOLIGHT |  | ENERGIZATION
ELECTRIFICATION 2024 | Region XI | Davao del Norte | 304222 | Carmen NHS | CARMEN | 2nd | 1 | Rewiring/Upgrading of Electrical Facilities of 32CL & Installation of 8 Units 25 KVA Transformer | 1 | 7443073.18 | 7435389.58 | ONGOING | 0.98 |  |  |  |  | 2024-01-10 | 2024-01-17 | 2024-01-30 | 2024-03-19 | 2024-06-04 | Magnum Builders Corp | for energization of DAVAOLIGHT |  | UPGRADING
ELECTRIFICATION 2024 | Region XI | Davao del Sur | 129099 | SANTA CRUZ CES | SANTA CRUZ | 1st | 1 | Energization of Electrical System (Overhead System) | 1 | 4522561.72 | 4501868.55 | COMPLETED | 1 |  |  | DS-SCHLBLDG-2024-G |  |  | July 16, 2024 | July 26, 2024 | August 09, 2024 |  | CCO ENGINEERING CONSTRUCTION & SUPPLY | for issuance of NTP |  | ENERGIZATION
ELECTRIFICATION 2024 | Region XI | Davao Occidental | 128845 | Lawa Central Elementary School | DON MARCELINO | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 3790450.02 | 3688458.36 | COMPLETED | 1 | January 16, 2025 |  | ITB W-04-2024 | contract no. 2024-010 | May 24, 2024 - June 05, 2024 | June 03, 2024 | June 05, 2024 | resolution no. 18,s. 2024 dated June 24, 2024 | September 18, 2024 | KUPLER INDUSTRIES INCORPORATED | on-going |  | ENERGIZATION
ELECTRIFICATION 2024 | Region XI | Davao Oriental | 129157 | Lambajon Central Elementary School SPED Center | BAGANGA | 1st | 1 | Energization of Electrical System (Overhead System) | 1 | 6099890.87 | 3778403.13 | COMPLETED | 1 | October 4, 2024 |  |  | 2024-013 | March 7, 2024 | March 14, 2024 | March 26, 2024 | April 8, 2024 | June 5, 2024 | CCO |  |  | ENERGIZATION
ELECTRIFICATION 2024 | Region XI | Davao Oriental | 316108 | Lavigan National High School | GOVERNOR GENEROSO | 2nd | 1 | Energization of Electrical System (Overhead System) | 1 | 2403408.83 | 1753059.4 | COMPLETED | 1 | October 4, 2024 |  |  | 2024-013 | March 7, 2024 | March 14, 2024 | March 26, 2024 | April 8, 2024 | June 5, 2024 | CCO | w/ Time Extension |  | ENERGIZATION
ELECTRIFICATION 2024 | Region XI | Digos City | 304402 | Ruparan NHS | CITY OF DIGOS (Capital) | 1st | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2593390.9 | 2525174.99 | COMPLETED | 1 | 90 CD from receipt of NTP | [8 empty] | KUPLER INDUSTRIES INCORPORATED | on-going |  | UPGRADING
ELECTRIFICATION 2024 | Region XI | Island Garden City of Samal | 128736 | Peñaplata Central Elementary School SPED Center | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 7252344.46 |  | not yet started | 0 |  |  |  |  | 2024-10-15 | October 21, 2024 | 2024-11-04 |  |  |  | Issued short of award due to elction ban |  | UPGRADING
ELECTRIFICATION 2024 | Region XI | Mati City | 325106 | Mayo NHS | CITY OF MATI (Capital) | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5497950.57 | 4062113.3427 | COMPLETED | 1 | March 01, 2025 |  |  |  | May 27, 2024 | June 04, 2024 | June 17,2024 | September 25, 2024 | October 02, 2024 | ABM1 BUILDERS & SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2024 | Region XI | Panabo City | 304408 | Panabo City National High School | CITY OF PANABO | 2nd | 1 | Upgrading of Electrical System (Underground System) | 1 | 9447723.66 | 8581388.7 | COMPLETED | 1 | 03/30/2025 |  |  |  | JUNE 28, 2024 | July 3, 2024 | JULY 18,2024 | August 8, 2024 | October 4, 2024 | RC CAPA ENGINEERING WORKS AND CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2024 | Region XI | Tagum City | 128791 | HERCULINA L. EDIG ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1st | 1 | Construction of Single Phase Line | 1 | 947410.22 |  | not yet started | 0 |  |  |  |  | 2024-06-28 | 2024-07-08 | 2024-07-22 |  |  |  | for issuance of NTP |  | UPGRADING

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%