## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Program-Year | Status as of July 4, 2025
SHS | REGION XI | Compostela Valley | 304200 | Awao Nhs | Monkayo | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9271461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304176 | Babag Nhs | Monkayo | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-02 |  | R. Semilla Const. & Marketing |  | NC 2016
SHS | REGION XI | Compostela Valley | 304177 | Bantacan Nhs | New Bataan | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304180 | Camanlangan Nhs | New Bataan | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2964910.9364 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-07 | 2016-06-29 | R.R. Seismundo Const. & Supply |  | NC 2016
SHS | REGION XI | Compostela Valley | 304181 | Compostela Nhs | Compostela | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Compostela Valley | 304181 | Compostela Nhs | Compostela | 1 |  | 12 | 3STY12CL | BATCH 11 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Compostela Valley | 304184 | Consuelo M. Valderrama Nhs | Compostela | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13972542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304187 | Gabi Nhs | Compostela | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-08-08 |  | Davao Concrete Products |  | NC 2016
SHS | REGION XI | Compostela Valley | 304187 | Gabi Nhs | Compostela | 1 |  | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2006-08-03 |  | Davao Concrete Products |  | NC 2016
K10 | REGION XI | Compostela Valley | 315813 | Langgawisan National High School | Maragusan (San Mariano) | 1 | 1 | 4 | 1STY2CL | BATCH 9 CL | 4391671.221 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-07 | 2016-06-29 | Mark Anthony Const. & Supply |  | NC 2016
SHS | REGION XI | Compostela Valley | 304182 | Mangayon Nhs | Compostela | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9121461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-07-22 |  | 2016-08-10 |  |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304196 | Maparat Nhs | Compostela | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-08-03 |  | Davao Concrete Products |  | NC 2016
SHS | REGION XI | Compostela Valley | 304197 | Mapawa Nhs | Maragusan (San Mariano) | 1 | 1 | 4 | 1STY4CL | BATCH 9 CL | 4111375.2325 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-09 | 2016-06-29 | Dingo Builders & Supply |  | NC 2016
SHS | REGION XI | Compostela Valley | 304198 | Maragusan Nhs | Maragusan (San Mariano) | 1 | 1 | 30 | 3STY15CL | BATCH 9 CL | 47212629.59 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-29 | 2016-08-08 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304204 | Mayaon Nhs | Montevista | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2964910.9364 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-24 | 2016-07-01 | Two Degrees Const. & Supply |  | NC 2016
SHS | REGION XI | Compostela Valley | 304199 | Monkayo Nhs | Monkayo | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23556314.795 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-29 | 2016-08-08 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304199 | Monkayo Nhs | Monkayo | 1 |  | 16 | 4STY16CL | BATCH 9 CL | 26902160 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-07-01 |  | Davao Concrete Products |  | NC 2016
K10 | REGION XI | Compostela Valley | 315801 | Monkayo Nhs- Casoon Hs Annex | Monkayo | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7086271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-02 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304202 | Montevista Nhs | Montevista | 1 | 1 | 18 | 3STY9CL | BATCH 9 CL | 27248390.256 |  |  | Completed | 1 |  |  |  |  | 2016-07-11 |  | 2016-08-01 |  |  |  |  | NC 2016
K10 | REGION XI | Compostela Valley | 304203 | Montevista Nhs - Annex (Dnas Campus) | Montevista | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6996271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 |  |  |  | NC 2016
K10 | REGION XI | Compostela Valley | 128442 | Mt. Diwata Es | Monkayo | 1 | 1 | 24 | 2STY8CL | BATCH 13 CL | 47507307.775 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Compostela Valley | 315815 | New Albay Nhs | Maragusan (San Mariano) | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 14272542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-29 | 2016-08-08 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304206 | New Bataan Nhs | New Bataan | 1 | 1 | 16 | 2STY8CL | BATCH 9 CL | 23960153.7017 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304207 | Paloc Nhs | Maragusan (San Mariano) | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3154910.9364 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-08-05 | 2016-08-12 | AB Aponesto Const. Parts & Supply |  | NC 2016
SHS | REGION XI | Compostela Valley | 304183 | San Miguel Nhs | Compostela | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 |  |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304210 | Siocon Nhs | Compostela | 1 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3811375.2325 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-08-03 | 2016-08-12 | AB Aponesto Const. Parts and Supply |  | NC 2016
SHS | REGION XI | Compostela Valley | 304212 | Tubo-Tubo Nhs | Monkayo | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6996271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304212 | Tubo-Tubo Nhs | Monkayo | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 9081461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-07-01 |  | Legacy Construction |  | NC 2016
SHS | REGION XI | Compostela Valley | 304213 | Tupaz Nhs | Maragusan (San Mariano) | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9521461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-06-28 | 2016-07-29 | R.R. Seismundo Const. & Supply |  | NC 2016
K10 | REGION XI | Compostela Valley | 315808 | Ulip National High School | Monkayo | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13932542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-02 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304172 | Andili Nhs | Mawab | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-08 | 2016-06-29 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304173 | Anibongan Nhs | Maco | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304174 | Anitapan Nhs | Mabini (Doña Alicia) | 2 | 1 | 4 | 1STY2CL | BATCH 9 CL | 4292428.3827 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-08 | 2016-06-29 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304175 | Araibo Nhs | Pantukan | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 14272542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-25 | 2016-08-08 |  |  | NC 2016
K10 | REGION XI | Compostela Valley | 304193 | Atty. Orlando S. Rimando National High School | Maco | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26952160 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-07-14 |  |  |  | NC 2016
K10 | REGION XI | Compostela Valley | 304193 | Atty. Orlando S. Rimando National High School | Maco | 2 |  | 20 | 4STY20CL | BATCH 9 CL | 32253160 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-07-14 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304178 | Bayabas Nhs | Nabunturan (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6996271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 |  |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304179 | Bongabong Nhs | Pantukan | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304185 | Don Vicente Romualdez Nhs | Laak (San Vicente) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9571461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 | 2016-08-12 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304186 | Elizalde Nhs | Maco | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-29 | 2016-08-08 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 315806 | Kao Nhs | Nabunturan (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-06-30 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304188 | Kapatagan National High School | Laak (San Vicente) | 2 | 1 | 4 | 1STY4CL | BATCH 9 CL | 4061375.2325 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-08 | 2016-06-29 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304190 | Kidawa Nhs | Laak (San Vicente) | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3195402.03 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-07 | 2016-06-29 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304189 | Laak Nhs | Laak (San Vicente) | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16350160 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-29 | 2016-08-08 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304189 | Laak Nhs | Laak (San Vicente) | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 20129495.669 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-29 | 2016-08-08 |  |  | NC 2016
K10 | REGION XI | Compostela Valley | 128311 | Longanapan Es | Laak (San Vicente) | 2 | 1 | 4 | 1STY4CL | BATCH 13 CL | 4284765.658 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Compostela Valley | 128311 | Longanapan Es | Laak (San Vicente) | 2 |  | 6 | 1STY3CL | BATCH 13 CL | 6585703.368 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Compostela Valley | 304191 | Lorenzo S. Sarmiento Sr. Nhs | Mawab | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-08-03 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304191 | Lorenzo S. Sarmiento Sr. Nhs | Mawab | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304192 | Mabini Nhs | Mabini (Doña Alicia) | 2 | 1 | 12 | 2STY6CL | BATCH 9 CL | 18042923.1122 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-06-30 | 2016-07-11 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 315807 | Magnaga Nhs | Pantukan | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 |  |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304194 | Mainit Nhs | Nabunturan (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-08-03 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304195 | Manat Nhs | Nabunturan (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 |  |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 315804 | Melale Nhs | Laak (San Vicente) | 2 | 1 | 4 | 1STY4CL | BATCH 9 CL | 4111375.2325 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-07 | 2016-07-29 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304205 | Nabunturan Nchs | Nabunturan (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 32253160 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 |  |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304205 | Nabunturan Nchs | Nabunturan (Capital) | 2 |  | 15 | 3STY15CL | BATCH 9 CL | 23606314.795 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 |  |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 315816 | Napnapan Nhs | Pantukan | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-04 | 2016-08-15 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 315818 | New Sibonga Nhs | Nabunturan (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-06-28 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 315802 | Nuevo Iloco Nhs | Mawab | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-05 |  |  |  | NC 2016
K10 | REGION XI | Compostela Valley | 128554 | Panganason Es | Pantukan | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2345713.3084 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Compostela Valley | 304208 | Pantukan National High School | Pantukan | 2 | 1 | 24 | 3STY12CL | BATCH 9 CL | 40258991.338 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 |  |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 315805 | Pindasan Nhs | Mabini (Doña Alicia) | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-14 |  |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 315812 | San Antonio National High School | Laak (San Vicente) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7436271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 | 2016-08-12 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304209 | Tagugpo Nhs | Pantukan | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3004910.9364 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-09 | 2016-06-29 |  |  | NC 2016
SHS | REGION XI | Compostela Valley | 304211 | Tambongon Nhs | Pantukan | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-07-29 |  |  |  | NC 2016
K10 | REGION XI | Compostela Valley | 315803 | Tuboran National High School | Mawab | 2 | 1 | 6 | 1STY2CL | BATCH 9 CL | 6088642.5741 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-20 | 2016-06-29 |  |  | NC 2016
SHS | REGION XI | Davao City | 304360 | Davao City National High School | Davao City | 1 | 1 | 40 | 4STY20CL | BATCH 11 CL | 62205780.54 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304360 | Davao City National High School | Davao City | 1 |  | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao City | 304363 | Davao City Special National High School | Davao City | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22277343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao City | 304365 | Erico T. Nograles Nhs | Davao City | 1 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10887131.51 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304377 | Jesus J. Soriano National High School | Davao City | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304377 | Jesus J. Soriano National High School | Davao City | 1 |  | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304375 | Maa National High School | Davao City | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26952469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304375 | Maa National High School | Davao City | 1 |  | 16 | 4STY8CL | BATCH 9 CL | 29895038 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City |  | Shs Within Cp Garcia Es (Formerly In Sta. Ana Es) | Davao City | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City |  | Shs Within Cp Garcia Es (Formerly In Sta. Ana Es) | Davao City | 1 |  | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao City |  | Shs Within Cp J.P Rizal Es (Formerly In Sta. Ana Es) | Davao City | 1 |  | 24 | 4STY24CL | BATCH 11 CL | 35596257.14 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao City | 304359 | Sir Es To Daniel R. Aguinaldo Nhs (Matina Nhs) | Davao City | 1 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62555780.54 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao City | 304359 | Sir Es To Daniel R. Aguinaldo Nhs (Matina Nhs) | Davao City | 1 |  | 16 | 4STY16CL | BATCH 9 CL | 26952469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304341 | Alejandra L. Navarro Nhs | Davao City | 2 | 1 | 32 | 4STY16CL | BATCH 5 CL | 53904938.84 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304346 | Cabantian Nhs | Davao City | 2 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21733013.45 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304366 | F. Bangoy Nhs | Davao City | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31277890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304366 | F. Bangoy Nhs | Davao City | 2 |  | 8 | 4STY8CL | BATCH 9 CL | 14947519 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304368 | F. Bustamante Nhs | Davao City | 2 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26952469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304368 | F. Bustamante Nhs | Davao City | 2 |  | 16 | 4STY8CL | BATCH 5 CL | 29895038 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao City | 304368 | F. Bustamante Nhs | Davao City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304354 | Calinan Nhs | Davao City | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31725000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304354 | Calinan Nhs | Davao City | 3 |  | 24 | 4STY12CL | BATCH 9 CL | 44970000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304356 | Crossing Bayabas Nhs | Davao City | 3 | 1 | 40 | 4STY20CL | BATCH 9 CL | 63450000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304356 | Crossing Bayabas Nhs | Davao City | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 22485000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao City | 304356 | Crossing Bayabas Nhs | Davao City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304361 | Dona Carmen Denia Nhs | Davao City | 3 | 1 | 80 | 4STY20CL | BATCH 9 CL | 126900000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304361 | Dona Carmen Denia Nhs | Davao City | 3 |  | 24 | 4STY12CL | BATCH 9 CL | 44970000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao City | 304361 | Dona Carmen Denia Nhs | Davao City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao City | 304362 | Dona Carmen Denia Nhs - J. V. Ferriols Hs | Davao City | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22485000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao City | 304362 | Dona Carmen Denia Nhs - J. V. Ferriols Hs | Davao City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao City | 316212 | Jose T. Quiboloy Sr. National High School | Davao City | 3 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11030000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304373 | Los Amigos Nhs | Davao City | 3 | 1 | 24 | 4STY12CL | BATCH 5 CL | 44970000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao City | 304387 | Mintal Nchs - Tugbok National Hs | Davao City | 3 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao City | 316208 | Suawan High School- Annex Of Lower Tamugan National High School | Davao City | 3 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11030000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304217 | Asuncion National High School | Asuncion (Saug) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2663550.36 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Norte | 304217 | Asuncion National High School | Asuncion (Saug) | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 22819748.25 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304234 | Capungangan Hs | Kapalong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304224 | Datu Balong Nhs | Kapalong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2670825.9001 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304258 | Datu Jose A. Libayao Memorial Nhs | Talaingod | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2673442.2285 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304228 | Doña Carmen Soriano National High School | Kapalong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304233 | Kapalong National High School | Kapalong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Norte | 304233 | Kapalong National High School | Kapalong | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31720020 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304239 | Limbaan Nhs | New Corella | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2661610.216 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304241 | Luna Nhs | Kapalong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Norte | 304248 | New Corella Nhs | New Corella | 1 | 1 | 24 | 4STY24CL | BATCH 3 CL | 37599959.52 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Norte | 304248 | New Corella Nhs To New Corella Nhs (Magcum Annex) | New Corella | 1 |  | 1 | 1STY1CL | BATCH 3 CL | 1076106.23 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304248 | New Corella Nhs | New Corella | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2783149.6 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304218 | Sagayen Nhs | Asuncion (Saug) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2663550.36 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304251 | Sawata Nhs | San Isidro | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2676213.7655 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Norte | 304251 | Sawata Nhs | San Isidro | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8518325.4119 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304243 | Semong Nhs | Kapalong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2513682.5141 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304252 | Sonlon Nhs | Asuncion (Saug) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2693622.5922 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304221 | Antonio V. Fruto Sr. Nhs | Braulio E. Dujali | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2663550.36 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Norte | 304222 | Carmen Nhs | Carmen | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304229 | Dujali National High School | Braulio E. Dujali | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304237 | Kimamon Nhs | Santo Tomas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304256 | Salvacion Nhs | Santo Tomas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Norte | 304254 | Sto Tomas Nhs | Santo Tomas | 2 | 1 | 32 | 4STY32CL | BATCH 3 CL | 48329389.36 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 304254 | Sto Tomas Nhs | Santo Tomas | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5510538.02 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 315901 | Tubod National High School | Carmen | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Norte | 315902 | Tulalian Nhs | Santo Tomas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 129089 | Agripina Es | Santa Cruz | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6398000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 129093 | Anastacio G. Canda Elementary School | Santa Cruz | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1970000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 129076 | Astorga Ces | Santa Cruz | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1970000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304289 | Bangkal Nhs | Matanao | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15197828 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304289 | Bangkal Nhs | Matanao | 1 |  | 6 | 3STY6CL | BATCH 9 CL | 10468132 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304265 | Barayong Nhs | Magsaysay | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22248344 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304265 | Barayong Nhs | Magsaysay | 1 |  | 8 | 4STY8CL | BATCH 9 CL | 14961519 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304265 | Barayong Nhs | Magsaysay | 1 |  | 6 | 3STY6CL | BATCH 9 CL | 10465132 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 304265 | Barayong Nhs | Magsaysay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2518000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304295 | Bato Nhs | Santa Cruz | 1 | 1 | 8 | 2STY4CL | BATCH 5 CL | 12812000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 129079 | Don Amancio Bendigo Sr. Es | Santa Cruz | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 205008 | Don Sergio Osmena Es | Padada | 1 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1115000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 304263 | Federico Yap National High School | Santa Cruz | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2525000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 304263 | Federico Yap National High School | Santa Cruz | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24496577.982 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 205011 | Fidel Razonable Ps | Padada | 1 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1115000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 129036 | Glot Towak Es | Matanao | 1 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2861000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 304275 | Hagonoy National High School | Hagonoy | 1 | 1 | 24 | 4STY12CL | BATCH 1 CL | 44544687.24 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 304275 | Hagonoy National High School | Hagonoy | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2517000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 205010 | Harada Butai Ps | Padada | 1 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1115000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 129081 | Inawayan Es | Santa Cruz | 1 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1114000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 129081 | Inawayan Es | Santa Cruz | 1 |  | 12 | 3STY12CL | BATCH 13 CL | 20077495.669 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 304278 | Inawayan National High School | Santa Cruz | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15202328 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 304278 | Inawayan National High School | Santa Cruz | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6342058.0075 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 304278 | Inawayan National High School | Santa Cruz | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2520000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304284 | Lower Bala Nhs | Magsaysay | 1 | 1 | 12 | 3STY12CL | BATCH 5 CL | 18324269 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 304284 | Lower Bala Nhs | Magsaysay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2518500 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 205009 | Lower Katipunan Es | Padada | 1 | 1 | 3 | 1STY2CL | BATCH 5 CL | 1995000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 128937 | Maibo Es | Magsaysay | 1 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2891000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 304286 | Marber Nhs | Bansalan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2518500 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 304288 | Matanao National High School | Matanao | 1 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62485781 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 304288 | Matanao National High School | Matanao | 1 |  | 12 | 3STY12CL | BATCH 5 CL | 18306269 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 316002 | Padada Nhs | Padada | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15184328 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 316002 | Padada Nhs | Padada | 1 |  | 6 | 3STY6CL | BATCH 5 CL | 10459132 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 316002 | Padada Nhs | Padada | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2517000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 304285 | Pedro A. Arches Nhs | Bansalan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2519000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304285 | Pedro A. Arches Nhs | Bansalan | 1 | 1 | 24 | 4STY12CL | BATCH 13 CL | 44520687.24 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 316004 | Sacub High School Annex | Hagonoy | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 316003 | Salud Cagas Tech.& Voc. H.S | Matanao | 1 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10471132 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 316003 | Salud Cagas Tech.& Voc. H.S | Matanao | 1 |  | 4 | 2STY4CL | BATCH 5 CL | 6418000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 316003 | Salud Cagas Tech.& Voc. H.S | Matanao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2520000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304279 | Sibulan Nhs | Santa Cruz | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15281328 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304279 | Sibulan Nhs | Santa Cruz | 1 |  | 1 | 1STY1CL | BATCH 5 CL | 1043000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304290 | Sinawilan Nhs | Matanao | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22236344 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304294 | Sta. Cruz National High School | Santa Cruz | 1 | 1 | 24 | 4STY24CL | BATCH 9 CL | 36270000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304294 | Sta. Cruz National High School | Santa Cruz | 1 |  | 12 | 3STY12CL | BATCH 9 CL | 18282269 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304294 | Sta. Cruz National High School | Santa Cruz | 1 |  | 15 | 3STY15CL | BATCH 9 CL | 21457082.1016 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Occidental | 304294 | Sta. Cruz National High School | Don Marcelino | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 304298 | Tacul Agrc'L Vhs (Tacul Nhs) | Magsaysay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2525000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304298 | Tacul Agrc'L Vhs (Tacul Nhs) | Magsaysay | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15202328 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 128944 | Tagaytay Es | Magsaysay | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1993000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 304280 | Tudaya National High School | Santa Cruz | 1 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8446000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128961 | Aglaungan Elementary School | Malita | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1998000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304262 | Alberto Olarte, Sr. Nhs | Sarangani | 0 | 1 | 12 | 3STY12CL | BATCH 5 CL | 16982000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304262 | Alberto Olarte, Sr. Nhs | Sarangani | 0 |  | 6 | 3STY6CL | BATCH 5 CL | 10687132 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 128895 | Bagong Negros Es | Kiblawan | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1978000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128837 | Baluntaya Es | Don Marcelino | 0 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1120000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128837 | Baluntaya Es | Don Marcelino | 0 |  | 4 | 2STY4CL | BATCH 5 CL | 6422000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304266 | Basiawan Nhs | Santa Maria | 0 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15211328 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304266 | Basiawan Nhs | Santa Maria | 0 |  | 4 | 2STY4CL | BATCH 5 CL | 6422000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304269 | B'Laan Nhs | Malita | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8392000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Occidental | 304269 | B'Laan Nhs | Malita | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2526000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 205033 | Bolo Bolo Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2891000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 205033 | Bolo Bolo Es | Malita | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 1998000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 129060 | Butulan Es (Kilakay Es) | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental |  | Cabalantian Es | Santa Maria | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2861000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128838 | Calian Elementary School | Don Marcelino | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2891000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 129058 | Camalian Es | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128879 | Culaman Es | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2906000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128839 | Dalupan Es | Don Marcelino | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6442000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 205019 | Datu Bacala Elementary School | Malalag | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1978000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128990 | Datu Danwata Es | Malita | 0 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10567131.51 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128990 | Datu Danwata Es | Malita | 0 |  | 1 | 1STY1CL | BATCH 5 CL | 1135000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304270 | Davao Del Sur Sof | Malalag | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18347269 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304270 | Davao Del Sur Sof | Malalag | 1 |  | 9 | 3STY9CL | BATCH 9 CL | 15196163 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 304270 | Davao Del Sur Sof | Malalag | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2518315 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304271 | Demolok Valley Nhs | Malita | 0 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16130139.898 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Occidental | 304271 | Demolok Valley Nhs | Malita | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2528000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128966 | Domingo Bautista Sr. Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2885000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128840 | Don Marcelino Maruya Es | Don Marcelino | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6430000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 304273 | Edna Guillermo Memorial National High School | Jose Abad Santos (Trinidad) | 0 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15346328 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 304273 | Edna Guillermo Memorial National High School | Jose Abad Santos (Trinidad) | 0 |  | 6 | 2STY6CL | BATCH 5 CL | 8446000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 205055 | Fagligdong | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 205055 | Fagligdong | Malita | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 2018000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128883 | Faustino K. Labiton Sr. Elementary School | Jose Abad Santos (Trinidad) | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6482000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 316005 | Felipe-Inocencia Deluao Nhs | Sulop | 1 | 1 | 12 | 3STY12CL | BATCH 5 CL | 16586000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128967 | Felis Elementary School | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2855000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304267 | Fishing Village Comprehensive Nhs | Malita | 0 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15202328 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304267 | Fishing Village Comprehensive Nhs | Malita | 0 |  | 6 | 3STY6CL | BATCH 5 CL | 10471132 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Occidental | 304267 | Fishing Village Comprehensive Nhs | Malita | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2519000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304274 | Gov. N. Llanos Nhs | Kiblawan | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15229328 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 304274 | Gov. N. Llanos Nhs | Kiblawan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2522000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 205045 | Gusatbak Ps | Don Marcelino | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2936000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304276 | Heracleo Casco Mnhs | Santa Maria | 0 | 1 | 24 | 4STY24CL | BATCH 9 CL | 36260328 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304276 | Heracleo Casco Mnhs | Santa Maria | 0 |  | 6 | 3STY6CL | BATCH 9 CL | 10444714 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304276 | Heracleo Casco Mnhs | Santa Maria | 0 |  | 16 | 4STY16CL | BATCH 9 CL | 26776021 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 129056 | Ignacia Guillermo Es (Butulan Es) | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304277 | Ihan Nhs | Kiblawan | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22296344 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304277 | Ihan Nhs | Kiblawan | 1 |  | 4 | 1STY4CL | BATCH 9 CL | 3859375.2325 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Del Sur | 304277 | Ihan Nhs | Kiblawan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2522000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 129004 | Jack Harvey Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2856500 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304292 | John Martin Johnson Hs (Lamidan) | Don Marcelino | 0 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20149496.669 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Occidental | 304292 | John Martin Johnson Hs (Lamidan) | Don Marcelino | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2530000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128881 | Jose Abad Santos Ces | Jose Abad Santos (Trinidad) | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8446000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304281 | Jose Abad Santos Nhs | Jose Abad Santos (Trinidad) | 0 | 1 | 16 | 4STY16CL | BATCH 9 CL | 27022469 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304282 | Jose De Arce Mhs (Sangkokdatal Hs) | Sarangani | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6582000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128984 | Julian M. Turado Elem. School | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2891000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128882 | Kalbay Es | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304283 | Kalbay Nhs | Jose Abad Santos (Trinidad) | 0 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18522269 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304283 | Kalbay Nhs | Jose Abad Santos (Trinidad) | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 15346328 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128993 | Kibalatong Es | Malita | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2148000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128971 | Kidalapong Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2853500 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128841 | Kinanga Es | Don Marcelino | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2859500 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128994 | Kinangan Es | Malita | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8356000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128973 | Kitana Ps | Malita | 0 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1120000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental |  | L. Payan Es | Santa Maria | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1979000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128997 | Lalon Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2936000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128997 | Lalon Es | Malita | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 2028000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304291 | Lawa Nhs | Don Marcelino | 0 | 1 | 12 | 3STY12CL | BATCH 5 CL | 18366269 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Occidental | 304291 | Lawa Nhs | Don Marcelino | 0 |  | 9 | 3STY9CL | BATCH 5 CL | 15256328 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Occidental | 304291 | Lawa Nhs | Don Marcelino | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2522000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128998 | Lenna Es | Malita | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1994000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 205013 | Libudon Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2906000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 129117 | Lilan Elementary School | Santa Maria | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2876000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128846 | Linadasan Es | Don Marcelino | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1994000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128999 | Little Baguio Es | Malita | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8416000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128884 | Malalan Es | Jose Abad Santos (Trinidad) | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8464000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 129119 | Malaygan Es | Santa Maria | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 304287 | Mariano Peralta National High School | Malita | 0 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62389661 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 304287 | Mariano Peralta National High School | Malita | 0 |  | 6 | 3STY6CL | BATCH 5 CL | 10444714 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 304287 | Mariano Peralta National High School | Malita | 0 |  | 12 | 4STY12CL | BATCH 5 CL | 22207508 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 205005 | Molopolo Es | Kiblawan | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6422000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 205005 | Molopolo Es | Kiblawan | 1 |  | 1 | 1STY1CL | BATCH 5 CL | 1120000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 316001 | Molopolo National High School | Kiblawan | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15220328 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 316001 | Molopolo National High School | Kiblawan | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 5746403.8743 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128979 | Mote Elementary School | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2891000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128980 | Nawan Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2891000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 129123 | Pongpong Es | Santa Maria | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1982000 |  |  | Completed | 1 |  |  | 16LF0021 |  |  | 2016-07-27 | 2016-07-27 | 2016-08-01 |  |  |  | NC 2016
K10 | REGION XI | Davao Occidental | 128889 | Rolando E. Pardinas Sr. Es | Jose Abad Santos (Trinidad) | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2008000 |  |  | Completed | 1 |  |  | 16LF008 |  | 2016-02-29 | 2016-03-10 | 2016-03-10 | 2016-03-17 | 2016-05-20 | LEGACY CONSTRUCTION |  | NC 2016
K10 | REGION XI | Davao Occidental | 129125 | San Antonio Es | Santa Maria | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2008000 |  |  | Completed | 1 |  |  | 16LF008 |  | 2016-02-29 | 2016-03-10 | 2016-03-10 | 2016-03-17 | 2016-05-20 | R. SEMILLA CONST. & MARKETING |  | NC 2016
K10 | REGION XI | Davao Occidental | 129069 | San Isidro Es | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2936000 |  |  | Completed | 1 |  |  | 16LF0022 |  |  | 2016-08-01 | 2016-08-01 | 2016-08-10 |  |  |  | NC 2016
K10 | REGION XI | Davao Del Sur | 205006 | San Pedro Ps | Kiblawan | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1978000 |  |  | Completed | 1 |  |  | 16LF0020 |  |  | 2016-07-27 | 2016-07-27 | 2016-08-01 |  |  |  | NC 2016
K10 | REGION XI | Davao Occidental | 129006 | Santagose Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2876000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 129006 | Santagose Es | Malita | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 1988000 |  |  | Completed | 1 |  |  |  | 16LD0012 | 2016-04-21 | 2016-04-28 | 2016-05-12 | 2016-05-27 | 2016-06-27 | Two Degrees Const & Supply |  | NC 2016
SHS | REGION XI | Davao Occidental | 304296 | Sta. Maria Nhs | Santa Maria | 0 | 1 | 18 | 3STY9CL | BATCH 5 CL | 30386656 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Davao Occidental | 304296 | Sta. Maria Nhs | Santa Maria | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2526000 |  |  | Completed | 1 |  |  |  | 16LD0006 | 2016-02-24 | 2016-02-26 | 2016-03-08 | 2016-03-11 | 2016-05-24 | R.C. Melgazo Builders |  | NC 2016
SHS | REGION XI | Davao Del Sur | 304297 | Sulop Nhs | Sulop | 1 | 1 | 12 | 3STY6CL | BATCH 1 CL | 21038263.02 |  |  | Completed | 1 |  |  |  | 16LD0008 | 2016-02-24 | 2016-02-26 | 2016-03-08 | 2016-03-11 | 2016-05-24 | R.C. Melgazo Builders |  | NC 2016
SHS | REGION XI | Davao Del Sur | 304297 | Sulop Nhs | Sulop | 1 |  | 12 | 3STY12CL | BATCH 1 CL | 18390268.79 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Del Sur | 304297 | Sulop Nhs | Sulop | 1 |  | 8 | 2STY4CL | BATCH 1 CL | 12900000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Del Sur | 128920 | Tacul Ps | Kiblawan | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6422000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 205039 | Tfs-Danaw Ps | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 205039 | Tfs-Danaw Ps | Malita | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 2018000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 205036 | Tfs-Malandeg Ps | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1 |  |  |  | 16LG0037 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
K10 | REGION XI | Davao Occidental | 205041 | Tfs-Tambelang Ps | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2936000 |  |  | Completed | 1 |  |  |  | 16L0032 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
K10 | REGION XI | Davao Occidental | 205041 | Tfs-Tambelang Ps | Malita | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 2028000 |  |  | Completed | 1 |  |  |  | 16LG0022 | 2016-02-19 | 2016-02-26 | 2016-03-11 | 2016-03-17 | 2016-05-20 | THREE W BUILDERS INC. |  | NC 2016
K10 | REGION XI | Davao Occidental | 129007 | Tical Es | Malita | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1988000 |  |  | Completed | 1 |  |  |  | 16LG0036 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
SHS | REGION XI | Davao Occidental | 304293 | Ticulon Nhs | Malita | 0 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15229328 |  |  | Completed | 1 |  |  |  | 16LG0031 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
SHS | REGION XI | Davao Occidental | 304293 | Ticulon Nhs | Malita | 0 |  | 4 | 2STY4CL | BATCH 5 CL | 6430000 |  |  | Completed | 1 |  |  |  | 16LG0040 | [5 empty] | 0 |  | NC 2016
SHS | REGION XI | Davao Occidental | 304268 | Tubalan Comprehensive Nhs | Santa Maria | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6410000 |  |  | Completed | 1 |  |  |  | 16LG0039 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
TECHVOC | REGION XI | Davao Occidental | 304268 | Tubalan Comprehensive Nhs | Santa Maria | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2517000 |  |  | Completed | 1 |  |  |  | 16LG0033 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
K10 | REGION XI | Davao Occidental | 129074 | Ubas Es | Sarangani | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2981000 |  |  | Completed | 1 |  |  |  | 16LG0034 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
K10 | REGION XI | Davao Occidental | 128844 | William Joyce Sr. Elementary School | Don Marcelino | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1988000 |  |  | Completed | 1 |  |  |  | 16LG0041 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | FJ CONSTRUCTION |  | NC 2016
K10 | REGION XI | Davao Occidental | 129053 | Balangonan Es | Jose Abad Santos (Trinidad) | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18582269 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128992 | Kablulan Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2921000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128992 | Kablulan Es | Malita | 0 |  | 8 | 1STY4CL | BATCH 13 CL | 8189531.316 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128892 | Manuel Medel Sr. Es | Jose Abad Santos (Trinidad) | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12150076.849 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128892 | Manuel Medel Sr. Es | Jose Abad Santos (Trinidad) | 0 |  | 1 | 1STY1CL | BATCH 13 CL | 1135000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128877 | Maria/Rita Medel Elementary School | Jose Abad Santos (Trinidad) | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12190076.849 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 128877 | Maria/Rita Medel Elementary School | Jose Abad Santos (Trinidad) | 0 |  | 1 | 1STY1CL | BATCH 13 CL | 1140000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 129065 | Molmol Es | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2951000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Occidental | 129065 | Molmol Es | Jose Abad Santos (Trinidad) | 0 |  | 8 | 1STY4CL | BATCH 13 CL | 8149531.316 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Davao Oriental | 304300 | Baganga Nhs | Baganga | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16LG0036 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
TECHVOC | REGION XI | Davao Oriental | 304309 | Cateel Nat'L. Agri. Hs | Cateel | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2539549.27 |  |  | Completed | 1 |  |  |  | 16LG0035 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
K10 | REGION XI | Davao Oriental | 304311 | Cateel Voc.Hs | Cateel | 1 | 1 | 16 | 2STY8CL | BATCH 5 CL | 22582794.06 |  |  | Completed | 1 |  |  |  | 16LG0024 | 2016-02-19 | 2016-02-26 | 2016-03-11 | 2016-03-17 | 2016-05-20 | FIVE MASSIVE INFRA & SUPPLY |  | NC 2016
K10 | REGION XI | Davao Oriental | 304311 | Cateel Voc.Hs | Cateel | 1 |  | 6 | 2STY6CL | BATCH 5 CL | 8128471.77 |  |  | Completed | 1 |  |  |  | 16LG0023 | 2016-02-19 | 2016-02-26 | 2016-03-11 | 2016-03-17 | 2016-05-20 | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
TECHVOC | REGION XI | Davao Oriental | 304312 | Crispin E. Rojas National High School | Baganga | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2539549.27 |  |  | Completed | 1 | [5 empty] | 2016-08-05 | 2016-08-18 |  |  |  |  | NC 2016
K10 | REGION XI | Davao Oriental | 304315 | E. Moralizon Nvhs | Manay | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1 | [5 empty] | 2016-08-05 | 2016-08-18 |  |  |  |  | NC 2016
K10 | REGION XI | Davao Oriental | 304324 | Manay Nhs | Manay | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15418925.24 |  |  | Completed | 1 | [5 empty] | 2016-08-05 | 2016-08-18 |  |  |  |  | NC 2016
TECHVOC | REGION XI | Davao Oriental | 304339 | Tarragona National High School | Tarragona | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2539549.27 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Davao Oriental | 304339 | Tarragona National High School | Tarragona | 1 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16429930.1 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Digos City | 316302 | Digos City Nhs - Matti Hs Annex | City Of Digos (Capital) | 1 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21543013.45 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Digos City | 316302 | Digos City Nhs - Matti Hs Annex | City Of Digos (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2439549.27 |  |  | Completed | 1 |  |  |  | 16LD0012 | 2016-04-21 | 2016-04-28 | 2016-05-12 | 2016-05-27 | 2016-06-27 | Two Degrees Const & Supply |  | NC 2016
SHS | REGION XI | Digos City | 304401 | Kapatagan Nhs | City Of Digos (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11080942.5917 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Digos City | 304401 | Kapatagan Nhs | City Of Digos (Capital) | 1 |  | 4 | 2STY4CL | BATCH 1 CL | 6436137.6381 |  |  | Completed | 1 |  |  |  | 16LD0006 | 2016-02-24 | 2016-02-26 | 2016-03-08 | 2016-03-11 | 2016-05-24 | R.C. Melgazo Builders |  | NC 2016
TECHVOC | REGION XI | Digos City | 304401 | Kapatagan Nhs | City Of Digos (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2499549.27 |  |  | Completed | 1 |  |  |  | 16LD0008 | 2016-02-24 | 2016-02-26 | 2016-03-08 | 2016-03-11 | 2016-05-24 | R.C. Melgazo Builders |  | NC 2016
TECHVOC | REGION XI | Island Garden City Of Samal | 304220 | Balet National High School | Island Garden City Of Samal | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2673214.6215 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Island Garden City Of Samal | 304245 | Mambago-B National High School | Island Garden City Of Samal | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2518227.1197 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Island Garden City Of Samal | 304245 | Mambago-B National High School | Island Garden City Of Samal | 2 | 1 | 10 | 2STY10CL | BATCH 13 CL | 14135065.799 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Island Garden City Of Samal | 323403 | Nieves Villarica National High School | Igacos | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 29560142.5235 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Island Garden City Of Samal | 128736 | Peñaplata Central Elementary School Sped Center | Island Garden City Of Samal | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Island Garden City Of Samal | 128736 | Peñaplata Central Elementary School Sped Center | Island Garden City Of Samal | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Island Garden City Of Samal | 304259 | Tagbitan-Ag National High School | Island Garden City Of Samal | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2697468.3545 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Mati City | 304320 | Bagumbayan Agro-Ind. Hs | Lupon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2669980.9742 |  |  | Completed | 1 |  |  |  | 16LG0037 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
TECHVOC | REGION XI | Mati City | 304313 | Dawan Nhs | City Of Mati (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2673368.6897 |  |  | Completed | 1 |  |  |  | 16L0032 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
K10 | REGION XI | Mati City | 316108 | Lavigan National High School | Governor Generoso | 2 | 1 | 6 | 2STY6CL | BATCH 5 CL | 10025000 |  |  | Completed | 1 |  |  |  | 16LG0022 | 2016-02-19 | 2016-02-26 | 2016-03-11 | 2016-03-17 | 2016-05-20 | THREE W BUILDERS INC. |  | NC 2016
K10 | REGION XI | Mati City | 304319 | Lupon Vocational High School | Lupon | 2 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16022138.898 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Mati City | 304319 | Lupon Vocational High School | Lupon | 2 |  | 2 | 1STY2CL | BATCH 13 CL | 2132466.644 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Mati City | 304323 | Macangao Agri. Vhs | Lupon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2670883.4521 |  |  | Completed | 1 |  |  |  | 16LG0036 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
SHS | REGION XI | Mati City |  | Macangao Agri. Vhs To Tagboa Agri-Vocational Hs | Lupon | 2 | 1 | 12 | 1STY12CL | BATCH 13 CL | 12058076.849 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Mati City | 304301 | Manuel B.Guiñez Sr. Nhs | Banaybanay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  |  | 16LG0031 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
K10 | REGION XI | Mati City | 304301 | Manuel B.Guiñez Sr. Nhs | Banaybanay | 2 | 1 | 16 | 2STY8CL | BATCH 13 CL | 23900153.698 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Mati City | 304317 | Manuel S. Nasser Sr. National High School | San Isidro | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2672099.3549 |  |  | Completed | 1 |  |  |  | 16LG0040 | [5 empty] | 0 |  | NC 2016
TECHVOC | REGION XI | Mati City | 316101 | Marayag Nhs | Lupon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2767283.2707 |  |  | Completed | 1 |  |  |  | 16LG0039 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
TECHVOC | REGION XI | Mati City | 304325 | Mati National Comprehensive High School | City Of Mati (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  |  | 16LG0033 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
K10 | REGION XI | Mati City | 304325 | Mati National Comprehensive High School | City Of Mati (Capital) | 2 | 1 | 20 | 2STY10CL | BATCH 13 CL | 28066882.198 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Mati City | 304326 | Mati Sat | City Of Mati (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  |  | 16LG0034 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
K10 | REGION XI | Mati City | 304327 | Matiao Nhs | City Of Mati (Capital) | 2 | 1 | 12 | 2STY6CL | BATCH 13 CL | 18042923.11 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION XI | Mati City | 304332 | San Isidro Nhs | San Isidro | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2669980.9742 |  |  | Completed | 1 |  |  |  | 16LG0041 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | FJ CONSTRUCTION |  | NC 2016
TECHVOC | REGION XI | Mati City | 304336 | Sigaboy Agri. Voc. Hs | Governor Generoso | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2681272.4838 |  |  | Completed | 1 |  |  |  | 16LG0036 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
TECHVOC | REGION XI | Mati City | 304338 | Taguibo Agri. Voc. High School | City Of Mati (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2680419.1339 |  |  | Completed | 1 |  |  |  | 16LG0035 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
K10 | REGION XI | Mati City | 129295 | Matigdao Es | Lupon | 3 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2218728 |  |  | Completed | 1 |  |  |  | 16LG0024 | 2016-02-19 | 2016-02-26 | 2016-03-11 | 2016-03-17 | 2016-05-20 | FIVE MASSIVE INFRA & SUPPLY |  | NC 2016
SHS | REGION XI | Mati City | 304340 | Tibanban Nhs | Governor Generoso | 3 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2952600 |  |  | Completed | 1 |  |  |  | 16LG0023 | 2016-02-19 | 2016-02-26 | 2016-03-11 | 2016-03-17 | 2016-05-20 | MARK ANTHONY CONST. & SUPPLY |  | NC 2016
SHS | REGION XI | Panabo City | 304403 | A. O. Floirendo National High School | City Of Panabo | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Panabo City | 304403 | A. O. Floirendo National High School | City Of Panabo | 2 |  | 4 | 2STY4CL | BATCH 13 CL | 6490110 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Panabo City | 304408 | Panabo National High School | City Of Panabo | 2 | 1 | 24 | 3STY12CL | BATCH 13 CL | 37990800 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Panabo City |  | Shs In Panabo City | City Of Panabo | 2 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31956000 |  |  | Completed | 1 |  |  | P0074937MN-CW1 | 16LC0075 | 2016-08-10 | 2016-08-05 | 2016-08-30 | 2016-09-20 | 2016-09-23 | FFJJ Construction |  | NC 2016
SHS | REGION XI | Panabo City |  | Shs In Panabo City | City Of Panabo | 2 |  | 12 | 4STY12CL | BATCH 11 CL | 22452343.62 |  |  | Completed | 1 |  |  | P0074938MN-CW1 | 16LC0067 | 2016-08-04 | 2016-08-05 | 2016-08-23 | 2016-09-13 | 2016-09-16 | FFJJ Construction |  | NC 2016
SHS | REGION XI | Panabo City |  | Shs In Panabo City | City Of Panabo | 2 |  | 8 | 4STY8CL | BATCH 11 CL | 15197518.84 |  |  | Completed | 1 |  |  | P0074936MN-CW1 | 16LC0063 | 2016-07-29 | 2016-08-05 | 2016-08-18 | 2016-09-06 | 2016-09-09 | FFJJ Construction |  | NC 2016
SHS | REGION XI | Panabo City | 316401 | Southern Davao National High School | City Of Panabo | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Tagum City | 304238 | La Filipina Nhs | City Of Tagum (Capital) | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Tagum City | 304226 | Laureta National High School | City Of Tagum (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11517510 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Tagum City | 128771 | Magugpo Pilot Central Elementary School | City Of Tagum (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Tagum City | 128795 | Mangga Elementary School | City Of Tagum (Capital) | 1 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16022138.898 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Tagum City | 304232 | Pipisan Maug National High School | City Of Tagum (Capital) | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14033441.1023 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Tagum City |  | Pipsan Maug Nhs-Liboganon Extension Campus | City Of Tagum (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9003810 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Tagum City | 304225 | Tagum City National Comprehensive High School | City Of Tagum (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Tagum City |  | Tagum City National Comprehensive Hs-Pandapan Extension Campus | Tagum City | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Tagum City | 304260 | Tagum City Nhs | City Of Tagum (Capital) | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 30537840 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Tagum City | 304260 | Tagum City Nhs | City Of Tagum (Capital) | 1 |  | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Tagum City |  | Tagum City Nhs-Canocotan Extension Campus | City Of Tagum (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Tagum City | 304261 | Tagum National Trade School | City Of Tagum (Capital) | 1 | 1 | 30 | 3STY15CL | BATCH 9 CL | 45881760 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION XI | Tagum City | 304261 | Tagum National Trade School | City Of Tagum (Capital) | 1 |  | 20 | 2STY10CL | BATCH 9 CL | 28066882.2047 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION XI | Tagum City | 128798 | Visayan Village Central Elementary School | City Of Tagum (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9003810 |  |  | Completed | 1 | [11 empty] | NC 2016

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.