## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 4, 2025
QRF 2023 | Region XI | Davao City | 129652 | Alejandra L. Navarro Central Elementary School | DAVAO CITY | 2nd | 1 | 8 | REPAIR OF CLASSROOMS | 2722196.51 | 2-R | 2252300.56 | Completed | 1 | June 19, 2024 | May 14, 2024 |  | 1s2024 |  |  | November 16, 2023 | January 16, 204 | February 20, 2024 | Panabo General Contractor & Development
QRF 2023 | Region XI | Davao De Oro | 315819 | Bango NHS | COMPOSTELA | 1st | [6 empty] | REALIGNED | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 128267 | Mangayon ES | COMPOSTELA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2809299.4999 | 2-R | 2121007.86 | Completed | 1 | 2024-07-23 |  | SDDO-017-2023-LOT1 |  |  | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP
QRF 2023 | Region XI | Davao De Oro | 128270 | New Alegria ES | COMPOSTELA | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 4108204.8708 | 2-R | 2755999.53 | Completed | 1 | 2024-07-23 |  | SDDO-017-2023-LOT1 |  |  | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP
QRF 2023 | Region XI | Davao De Oro | 128378 | Bagong Silang ES | MARAGUSAN (SAN MARIANO) | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2073961.6626 | 2-R | 1435695.91 | Completed | 1 | 2024-07-24 |  | SDDO-017-2023-LOT3 |  |  | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP
QRF 2023 | Region XI | Davao De Oro | 128380 | Cambagang ES | MARAGUSAN (SAN MARIANO) | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 5915104.5493 | 2-R | 4071586.69 | Completed | 1 | 2024-07-24 |  | SDDO-017-2023-LOT3 |  |  | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP
QRF 2023 | Region XI | Davao De Oro | 128387 | Mabugnao ES | MARAGUSAN (SAN MARIANO) | 1st | [6 empty] | REALIGNED | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 128390 | Mauswagon ES | MARAGUSAN (SAN MARIANO) | 1st | 1 | 4 | 1STY4CL | 13960812.88 | 2- NC |  | Ongoing | 0.85 | [5 empty] | January 31, 2024 | February 12, 2024 |  |  |  | Failed bidding; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 128393 | New Manay ES | MARAGUSAN (SAN MARIANO) | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 2079599.3422 | 2-R | 1462881.36 | Completed | 1 | 2024-07-24 | 2024-07-24 | SDDO-017-2023-LOT3 |  |  | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP | COMPLETED
QRF 2023 | Region XI | Davao De Oro | 204009 | Sapawan ES | MARAGUSAN (SAN MARIANO) | 1st | [6 empty] | REALIGNED | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 128403 | Tuburan ES | MARAGUSAN (SAN MARIANO) | 1st | [6 empty] | REALIGNED | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 128431 | Casoon ES | MONKAYO | 1st | [6 empty] | REALIGNED | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 304199 | Monkayo NHS | MONKAYO | 1st | 1 | 16 | REPAIR OF CLASSROOMS | 3921702.2494 | 2-R | 2761931.82 | Completed | 1 | 2024-07-26 |  | SDDO-017-2023-LOT9 |  |  | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP
QRF 2023 | Region XI | Davao De Oro | 500455 | Olaycon Integrated School | MONKAYO | 1st | 1 | 9 | REPAIR OF CLASSROOMS | 2193563.3169 | 2-R | 1590036.59 | Completed | 1 | 2024-07-23 |  | SDDO-017-2023-LOT2 |  |  | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP
QRF 2023 | Region XI | Davao De Oro | 315808 | ULIP NATIONAL HIGH SCHOOL | MONKAYO | 1st | 1 | 3 | 1STY3CL | 9707668.78 | 2- NC |  | Completed | 1 | 2025-02-19 |  | SDDO-015-2024 |  | 2024-06-08 | 08/18/2024 | 2024-09-09 |  |  |  | for award
QRF 2023 | Region XI | Davao De Oro | 315808 | ULIP NATIONAL HIGH SCHOOL | MONKAYO | 1st |  | 12 | REPAIR OF CLASSROOMS | 3289402.9498 | 2-R | 2333984.98 | Completed | 1 | 2024-07-26 |  | SDDO-017-2023-LOT9 |  |  | December 04, 2023 | December 18, 2023 |  |  | R. FABALE CONSTRUCTION CORP
QRF 2023 | Region XI | Davao De Oro | 304202 | Montevista NHS | MONTEVISTA | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 1553352.2934 | 2-R | 1149366.41 | Completed | 1 | 2024-07-23 |  | SDDO-017-2023-LOT2 |  |  | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP
QRF 2023 | Region XI | Davao De Oro | 128477 | Sambayon ES | MONTEVISTA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2916790.98 | 2-R | 1980451.57 | Completed | 1 | 2024-07-23 |  | SDDO-017-2023-LOT2 |  |  | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP
QRF 2023 | Region XI | Davao De Oro | 304206 | New Bataan NHS | NEW BATAAN | 1st | 1 | 42 | REPAIR OF CLASSROOMS | 16725290.86 | 2-R | 10972099.93 | Completed | 1 | 2024-07-26 |  | SDDO-017-2023-LOT8 |  |  | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-27 | TWO DEGREES CONSTRUCTION & SUPPLY
QRF 2023 | Region XI | Davao De Oro | 304173 | Anibongan NHS | MACO | 2nd | [6 empty] | REALIGNED | [6 empty] | December 04, 2023 | December 18, 2023 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 304193 | Atty. Orlando S. Rimando NHS | MACO | 2nd | 1 | 20 | REPAIR OF CLASSROOMS | 6257681.1187 | 2-R | 4373310.2 | Completed | 1 | 2024-07-18 |  | SDDO-017-2023-LOT6 |  |  | December 04, 2023 | December 18, 2023 | 2024-03-11 | 2024-03-15 | DQMB CONST. & SUPPLY CORP.
QRF 2023 | Region XI | Davao De Oro | 128345 | Bucana ES | MACO | 2nd | [6 empty] | REALIGNED | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 128349 | Gubatan ES | MACO | 2nd | 1 | 9 | 3-UNITS 1STY3CL | 31978668.37 | 2- NC | 31969553.96 | Completed | 1 | 2024-11-16 |  |  |  |  | January 31, 2024 | February 12, 2024 | 2024-03-22 | 2024-05-16 | TWO DEGREES CONSTRUCTION & SUPPLY
QRF 2023 | Region XI | Davao De Oro | 315811 | New Leyte NHS | MACO | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 1614972.4355 | 2-R | 1137605.79 | Completed | 1 | 2024-07-18 |  | SDDO-017-2023-LOT6 |  |  | December 04, 2023 | December 18, 2023 | 2024-03-11 | 2024-03-15 | DQMB CONST. & SUPPLY CORP.
QRF 2023 | Region XI | Davao De Oro | 301526 | Pangi NHS | MACO | 2nd | [6 empty] | REALIGNED | [6 empty] | December 04, 2023 | December 18, 2023 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 128362 | Taglawig ES | MACO | 2nd | 1 | 2 | 1STY2CL | 6848897.56 | 2- NC |  | Completed | 1 | 2025-02-19 |  |  |  | 2024-06-08 | 08/18/2024 | 2024-09-09 |  |  |  | FOR AWARD
QRF 2023 | Region XI | Davao De Oro | 128484 | Bukal ES | NABUNTURAN (Capital) | 2nd | [6 empty] | REALIGNED | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 128484 | Bukal ES | NABUNTURAN (Capital) | 2nd | [6 empty] | REALIGNED | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 128484 | Bukal ES | NABUNTURAN (Capital) | 2nd | [6 empty] | REALIGNED | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 128484 | Bukal ES | NABUNTURAN (Capital) | 2nd | [6 empty] | REALIGNED | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 128484 | Bukal ES | NABUNTURAN (Capital) | 2nd | [6 empty] | REALIGNED | [6 empty] | December 04, 2023 | December 18, 2023 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings
QRF 2023 | Region XI | Davao De Oro | 304203 | Monkayo CES | MONKAYO WEST | 1st |  | 10 | 2STY10CL | 37496099.9 | 2-NC |  | Ongoing | 0.55
QRF 2023 | Region XI | Davao De Oro | 304203 | Montevista Stand alone SHS | MONTEVISTA | 1st |  | 4 | 2STY4CL | 13964796.33 | 2-NC |  | Ongoing | 0.65
QRF 2023 | Region XI | Davao De Oro | 128389 | Maragusan CES | MARAGUSAN (SAN MARIANO) | 1st |  | 15 | Repair of Classrooms | 16326906.57 | 2-R |  | Ongoing | 0.85
QRF 2023 | Region XI | Davao De Oro | 128439 | Pangi ES | MACO NORTH | 2nd |  | 3 | 1STY3CL | 9547895.27 | 2-NC |  | Ongoing | 0.75
QRF 2023 | Region XI | Davao De Oro | 128358 | Nabunturan Comprehensive High School | NABUNTURAN WEST | 2nd |  | 10 | 2STY10CL | 36668264.18 | 2-NC |  | Ongoing | 0.55
QRF 2023 | Region XI | Davao De Oro | 301526 | PANGI NHS | MACO NORTH | 2nd |  | 4 | Repair of Classrooms | 4807238.72 | 2-R |  | Completed | 1
QRF 2023 | Region XI | Davao De Oro | 502373 | Antequera Integrated School | NABUNTURAN (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 3628369.14 | 2-R |  | Completed | 1 | 2024-07-26 |  | SDDO-017-2023-LOT9 |  |  | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP
QRF 2023 | Region XI | Davao De Oro | 304194 | Mainit NHS | NABUNTURAN (Capital) | 2nd | 1 | 20 | REPAIR OF CLASSROOMS | 5641678.2049 | 2-R | 3893058.15 | Completed | 1 | 2024-11-01 |  | SDDO-017-2023-LOT7 |  |  | December 04, 2023 | December 18, 2023 | 2024-03-22 | 2024-05-16 | TWO DEGREES CONSTRUCTION & SUPPLY | Ongoing
QRF 2023 | Region XI | Davao De Oro | 304195 | Manat NHS | NABUNTURAN (Capital) | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 4107035.1455 | 2-R | 2744050.32 | Completed | 1 | 2024-11-01 |  | SDDO-017-2023-LOT7 |  |  | December 04, 2023 | December 18, 2023 | 2024-03-22 | 2024-05-16 | TWO DEGREES CONSTRUCTION & SUPPLY
QRF 2024 | Region XI | Davao Occidental | 129064 | Mangahos PS | SARANGANI | Lone | 1 | 2 | 1STY2CL | 5650766.5 | 1- NC |  | Ongoing | 0.7 | 2025-06-18 |  | ITB W-13-2025 | 2024-021 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-03 | December 20, 2024 | MJTP CONSTRUCTION
QRF 2024 | Region XI | Davao Occidental | 304283 | Kalbay National High School | JOSE ABAD SANTOS (TRINIDAD) | Lone | 1 | 3 | 1STY3CL | 7661049.91 | 1- NC |  | Ongoing | 0.75 | 2025-06-18 |  | ITB W-12-2025 | 2024-020 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-03 | December 20, 2024 | MJTP CONSTRUCTION
QRF 2024 | Region XI | Island Garden City of Samal | 128690 | Kaputian Central Elementary School | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 | 3 | Repair of Classrooms | 3769336.35 | 1- R | 2015230.12 | completed | 1 | 04/20/2025 |  | infra-001-0802024 |  | 10/15/2024 | 10/21/2024 | 2024-04-11 |  | December 23, 2024 | 0 | with time extension
QRF 2024 | Region XI | Island Garden City of Samal | 128733 | Limao Elementary School | ISLAND GARDEN CITY OF SAMAL | 2nd |  | 3 | Repair of Classrooms | 2223978.46 | 1- R | 1571884 | completed | 1 | 2025-10-04 |  | infra-001-0802024 |  | 10/15/2024 | 10/21/2024 | 2024-04-11 |  | December 23, 2024 | 0 | with time extension

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%