## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM TERM COMPLETED | Unnamed: 46 | Status as of July 4, 2025
REPAIR 2020 | BARMM | Cotabato City | 131248 | L.R. Sebastian ES | COTABATO CITY | 1 | 1 | 6 | Repair of classrooms | 2001691 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | under procurement
REPAIR 2020 | BARMM | Cotabato City | 131243 | P.C. Hill ES | COTABATO CITY | 1 | 1 | 14 | Repair of classrooms | 4560581 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | under procurement
REPAIR 2020 | BARMM | Cotabato City | 131254 | Tamontaka Central School | COTABATO CITY | 1 | 1 | 8 | Repair of classrooms | 3169591 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | under procurement
REPAIR 2021 | BARMM | Basilan | 133137 | Bato-Bato ES | AKBAR | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 133186 | Caddayan ES | AKBAR | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 133196 | Languyan ES | HADJI MOHAMMAD AJUL | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 133062 | Landungan ES | LANTAWAN | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 133072 | Lukbaldaya PS | LANTAWAN | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 133046 | Tairan ES | LANTAWAN | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 304934 | Bubuan NHS-Saluping Annex | TABUAN-LASA | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 304954 | Tipo-Tipo NHS | TIPO-TIPO | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 133152 | Pipil ES | UNGKAYA PUKAN | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Cotabato City | 131260 | Datu Usman Elementary School | COTABATO CITY | 1 | 1 | 6 | Repair of classrooms | 3000000 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | under procurement
REPAIR 2021 | BARMM | Lamitan City | 132998 | Colony Central Elementary School | CITY OF LAMITAN | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 133224 | Nusa ES | BALINDONG (WATU) | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 304960 | Buadiposo-Buntong NHS | BUADIPOSO-BUNTONG | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 324601 | Datu Mamintal Adiong Sr. Mem. NHS | BUBONG | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 133270 | Buaya-an Elementary School | DITSAAN-RAMAIN | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 304968 | Mangurun Memorial NHS | KAPAI | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 304971 | Mulondo NHS | MULONDO | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 133451 | Saguiaran CES | SAGUIARAN | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 133293 | Mimbaguiang ES | TAGOLOAN II | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 318118 | Johayver Maulana NHS | TARAKA | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - II | 133784 | Ngingir Elementary School | CALANOGAS | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - II | 133586 | Don Pablo Hofer ES | KAPATAGAN | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - II | 133678 | Beta Elementary School | LUMBACA-UNAYAN | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - II | 133846 | Tangcal Central Elementary School | TUBARAN | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - II | 133858 | Tugaya Central Elementary School | TUGAYA | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao I | 134200 | Macasampen ES | GUINDULUNGAN | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao I | 134132 | Libutan ES | MAMASAPANO | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao I | 318310 | Sapakan NHS | RAJAH BUAYAN | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao I | 134197 | Kalantungan ES | TALAYAN | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao II | 133930 | Raranaon ES | BULDON | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao II | 134275 | Datu Sa Biwang ES | DATU BLAH T. SINSUAT | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao II | 133990 | Capiton PS | DATU ODIN SINSUAT (DINAIG) | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao II | 318325 | Datu Alamanza Dilangalen NHS | NORTHERN KABUNTALAN | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Marawi City | 318607 | Bacarat Memorial National H/S | MARAWI CITY | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Sulu | 134299 | Bwansa Elementary School | INDANAN | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Sulu | 134454 | Lapa ES | MAIMBUNG | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Sulu | 134488 | Bowal Bowal ES | PANGUTARAN | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Sulu | 134555 | Kadday Mampalam ES | PATIKUL | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Sulu | 134478 | Panglima Agga Central School | OLD PANAMAO | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Tawi-Tawi | 134686 | Batu-Batu Central School | PANGLIMA SUGALA (BALIMBING) (Capital) | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Tawi-Tawi | 134810 | Lawm Sikubong ES | SAPA-SAPA | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Tawi-Tawi | 134832 | Talisay ES | SIBUTU | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Tawi-Tawi | 305057 | Manuk Mangkaw NHS | SIMUNUL | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Tawi-Tawi | 134774 | Taganak ES | TURTLE ISLANDS | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Under Procurement

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%