## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | Unnamed: 45 | Status as of July 4, 2025
GABALDON 2020 | CAR | Abra | 134979 | Bangued West CS | BANGUED (Capital) | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 3477721.44 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | CAR | Benguet | 135397 | Topdac ES | ATOK | 0 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 12177572.29 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | CAR | Benguet | 135737 | Tublay Central Elementary School | TUBLAY | 0 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 13636660.38 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | CAR | Mt. Province | 136248 | Tambuan Elementary School | BESAO | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 12055183.04 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  | CY 2022 |  |  | Completed
GABALDON 2020 | CAR | Mt. Province | 136356 | Balaoa Elementary School | TADIAN | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 4108545.8707 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | CAR | Mt. Province | 136358 | Bantey Elementary School | TADIAN | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 12490756.76 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | CAR | Mt. Province | 136363 | Dacudac Elementary School | TADIAN | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 6837175.68 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | CAR | Mt. Province | 136367 | Kayan Elementary School | TADIAN | 0 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 17916759.49 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2021 | CAR | Abra | 134989 | Bucay CS | BUCAY | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 5216538 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office | CY 2022 |  |  | COMPLETED
GABALDON 2021 | CAR | Abra | 135017 | Dolores CS | DOLORES | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 4582774 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2021 | CAR | Abra | 135103 | Luba CS | LUBA | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 5026084 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2021 | CAR | Benguet | 135435 | Bokod CS | BOKOD | 0 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 16817332 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2022-12-01 | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2021 | CAR | Mt. Province | 136202 | Bauko Central School | BAUKO | 0 | 1 | 11 | 1 | Rehabilitation of Gabaldon Building | 38640021 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2022-12-01 | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2022 | CAR | Mt. Province | 136239 | Dandanac Elementary School | BESAO | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 14828997.48 | 1 | 147777975.49 | Completed | 1 | 5/31/2023 | August 10, 2023 | INF2022GAB001 | INF2022GAB001 | 7/30/2022 | 2022-02-08 | 8/15/2022 | Sept 19, 2022 | 11/25/2022 | JM-MAS Construction & Gen. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.23 | Division Office | CY 2023 |  |  | Completed
GABALDON 2022 | CAR | Mt. Province | 136342 | Ambasing Elementary School | SAGADA | 0 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 37800000 | 1 | 37720000 | Completed | 1 | 7/30/2023 | July 12, 2024 | INF2022GAB002 | INF2022GAB002 | 7/30/2023 | 2022-02-08 | 8/15/2022 | Sept 19, 2022 | 11/25/2022 | BAJE CONSTRUCTIOIN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.23 | Division Office | CY 2023 |  |  | Completed
GABALDON 2023 | CAR | Baguio City | 136382 | Baguio Central School | BAGUIO CITY | 0 | 1 | 1 | 1 | Restoration & Conservation of Gabaldon Building | 41223103.23 | 1 | 40014561 | Ongoing | 0.4 | November 5,2025 |  | No.027,s.2023 | No.027,s.2023 | December 9, 2023 | December 15, 2023 | December 29, 2023 | January 18, 2024 | February 20, 2024 | EZRAH Construction Services/HGW=3 Engineering and Construction | Project suspended as to LGU's order while the submission and approval of Conservation Management Plan and Building Permit | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.35 | 0.05 |  | 7.24 | Division Office |  |  |  | Ongoing
GABALDON 2023 | CAR | Benguet | 135402 | Bagu ES | BAKUN | 0 | 1 | 3 | 1 | Restoration & Conservation of Gabaldon Building | 10000000 | 1 | 10000000 | COMPLETED | 1 | 9/17/2024 | 12/13/2024 | GAB-2023-01 | GAB-2023-02 | 2023-05-05 | 2023-12-05 | 5/25/2023 | 7/28/2023 | 9/18/2023 | SCA JR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7.24 | Division Office |  |  |  | Completed
GABALDON 2024 | CAR | Abra | 134979 | Bangued West CS | BANGUED (Capital) | Lone | 1 | 10 | 1 | Conservation and Restoration of Gabaldon School Building | 12905610 | 1 | 12887697.3 | Completed | 1 | November 5, 2024 | November 5, 2024 | CAR-ABRA-2024-04-006 | 2024-07-007 | April 17, 2024 | April 24, 2024 | May 7, 2024 | May 16, 2024 | July 8, 2024 | BAJE CONSTRUCTIOIN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 1.25 | Division Office |  |  | 3 | Completed
GABALDON 2024 | CAR | Abra | 135223 | San Juan CS | SAN JUAN | Lone | 1 | 8 | 1 | Conservation and Restoration of Gabaldon School Building | 25000000 | 1 | 24988913.87 | Ongoing | 0.9 | February 3, 2025 |  | CAR-ABRA-2024-04-006 | 2024-07-007 | April 17, 2024 | April 24, 2024 | May 7, 2024 | May 16, 2024 | July 8, 2024 | BAJE CONSTRUCTIOIN |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.82 | 0.08 |  |  | Division Office |  |  | 3 | Ongoing
GABALDON 2024 | CAR | Benguet | 135438 | Daklan ES | BOKOD | Lone | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 19094390 | 1 | 18378750 | Ongoing | 0.45 | August 5,2025 |  | GAB-2024-02 | GAB-2024-02 | MAY 29. 2024 | 2024-10-06 | 6/24/2024 | September 26, 2024 | October 31, 2024 | MHIGS CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.4 | 0.05 |  |  | Division Office |  |  | 8 | Ongoing
GABALDON 2024 | CAR | Benguet | 135619 | Bekkel ES | LA TRINIDAD (Capital) | Lone | 1 | 11 | 1 | Conservation and Restoration of Gabaldon School Building | 23919100 | 1 | 22932793.89 | Ongoing | 0.7 | August 5,2025 |  | GAB-2024-01 | GAB-2024-01 | MAY 29. 2024 | 2024-10-06 | 6/24/2024 | September 26, 2024 | October 31, 2024 | JRF ANGOYNA GENERAL CONSTRUCTION/REKO KONSTRUCT-JV |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.55 | 0.15 |  |  | Division Office |  |  | 8 | Ongoing
GABALDON 2024 | CAR | Ifugao | 220020 | Ifugao SPED Center | LAGAWE (Capital) | Lone | 1 | 8 | 1 | Conservation and Restoration of Gabaldon School Building | 34222823.15 | 1 |  | Not Yet Started | 0 | [10 empty] | Ongoing Preparation of Plans, POW and CMP | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | Division Office |  | 1 | 0 | not yet started

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%