## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | No. of Classrooms | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated | Previous % | Difference | STOREY | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | Status as of July 4, 2025
NEWCON 2024 | CAR | Abra | 134982 | Patucannay ES | BANGUED (Capital) | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Abra | 135027 | Benben Elementary School | LA PAZ | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Abra | 135028 | Bulbulala ES | LA PAZ | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Abra | 135029 | Canan ES | LA PAZ | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Abra | 135034 | Liguis ES | LA PAZ | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Abra | 135035 | Malabbaga ES | LA PAZ | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Abra | 135043 | Toon ES | LA PAZ | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Apayao | 135249 | Sta. Filomena ES | CALANASAN (BAYAG) | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5743000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Apayao | 305112 | Conner National HS | Conner | Lone | 1 | 8 | 2STY8CL with Laboratory | BATCH 1 | 19839000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 8 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Apayao | 319010 | Musimut National High School | KABUGAO (Capital) | Lone | 1 | 3 | 1STY3CL | GAA 17B | 9091000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 3 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Apayao | 219026 | Lt. Balag ES | PUDTOL | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5765000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Apayao | 318805 | CONSUELO NATIONAL HIGH SCHOOL | SANTA MARCELA | Lone | 1 | 4 | 2STY4CL | GAA 17B | 19401000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 4 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Baguio City | 136392 | Alfonso Tabora ES | BAGUIO CITY | Lone | 1 | 2 | 2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Baguio City | 136407 | Crystal Cave Elementary School | BAGUIO CITY | Lone | 1 | 2 | 2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Baguio City |  | Pacdal (Liteng) Elementary School | BAGUIO CITY | Lone | 1 | 2 | 2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Baguio City | 305281 | Pines City National High School | BAGUIO CITY | Lone | 1 | 2 | 2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0.79 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0.79
NEWCON 2024 | CAR | Baguio City | 136396 | Pinget Elementary School | BAGUIO CITY | Lone | 1 | 3 | 3CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0.7418 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 3 | 0 | 0 | 0 |  | 0 | 0.7418
NEWCON 2024 | CAR | Baguio City | 136404 | Rizal Elementary School | BAGUIO CITY | Lone | 1 | 2 | 1STY2CL | BATCH 2 | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Baguio City | 305276 | Rizal National High School | BAGUIO CITY | Lone | 1 | 4 | 4CL | GAA 17B | 10000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 0 | 1
NEWCON 2024 | CAR | Baguio City | 136416 | San Vicente Elementary School | BAGUIO CITY | Lone | 1 | 2 | 2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Benguet | 306057 | Franklin Guy Haight National High School | ATOK | Lone | 1 | 15 | 3STY15CL | BATCH 1 | 43500000 |  |  | Not Yet Started | 0.45 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 15 | 0 | 0 | 0 |  | 0 | 0.45
NEWCON 2024 | CAR | Benguet | 305956 | Ambangeg National High School | BOKOD | Lone | 1 | 13 | 3STY13CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0.5 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 13 | 0 | 0 | 0 |  | 0 | 0.5
NEWCON 2024 | CAR | Benguet | 501757 | Lam-ayan Integrated School | BUGUIAS | Lone | 1 | 8 | 4STY8CL | BATCH 2 | 40000000 |  |  | On Going | 0.4 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.4
NEWCON 2024 | CAR | Benguet | 305138 | Loo National High School | BUGUIAS | Lone | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0.25 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 8 | 0 | 0 | 0 |  | 0 | 0.25
NEWCON 2024 | CAR | Benguet | 135507 | Liang PS | ITOGON | Lone | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0.25 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 4 | 0 | 0 | 0 |  | 0 | 0.25
NEWCON 2024 | CAR | Benguet | 305143 | Gov. Bado Dangwa Agro-Industrial School | KAPANGAN | Lone | 1 | 15 | 3STY15CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0.2 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 15 | 0 | 0 | 0 |  | 0 | 0.2
NEWCON 2024 | CAR | Benguet |  | Tacadang National High School | KIBUNGAN | Lone | 1 | 4 | 2STY4CL | GAA 17B | 25500000 |  |  | Not Yet Started | 0.4 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 4 | 0 | 0 | 0 |  | 0 | 0.4
NEWCON 2024 | CAR | Benguet | 135669 | Taneg ES | MANKAYAN | Lone | 1 | 15 | 3STY15CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0.96 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 15 | 0 | 0 | 0 |  | 0 | 0.96
NEWCON 2024 | CAR | Benguet | 135693 | Indaoac ES | TUBA | Lone | 1 | 6 | 2STY6CL | GAA 17B | 14500000 |  |  | Not Yet Started | 0.2 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 6 | 0 | 0 | 0 |  | 0 | 0.2
NEWCON 2024 | CAR | Ifugao | 305166 | Aguinaldo NHS | AGUINALDO | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Ifugao | 319002 | Rufino I. Chungalao Science HS | AGUINALDO | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Ifugao | 135797 | Maloy PS | ASIPULO | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0.95 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0.95
NEWCON 2024 | CAR | Ifugao | 135808 | Amganad ES | BANAUE | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Ifugao | 135846 | Abatan ES | HUNGDUAN | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Ifugao | 135909 | Panopdopan ES | LAMUT | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Ifugao | 305186 | Tulaed NHS (Senior High School) | MAYOYAO | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Ifugao | 220028 | Dengao ES | TINOC | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Kalinga | 135964 | Balbalasang Elementary School | BALBALAN | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Kalinga | 135983 | Sesec-An Primary School | BALBALAN | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Kalinga | 305227 | Western Kalinga National High School | BALBALAN | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Kalinga | 305223 | Lubuagan National High School | LUBUAGAN | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Kalinga | 305213 | Pasil National High School | PASIL | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Kalinga | 305197 | Allaguia National High School | PINUKPUK | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Kalinga | 305201 | Cal-owan Agricultural Vocational National High School | PINUKPUK | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Kalinga | 305542 | MALAGNAT NATIONAL HIGH SCHOOL | PINUKPUK | Lone | 1 | 9 | 3STY9CL | BATCH 1 | 34500000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 9 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | CAR | Mt. Province | 136236 | Besao Elementary School | BESAO | Lone | 1 | 2 | Completion of 1STY2CL | BATCH 1 | 1242987.22 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Mt. Province | 221006 | Mountain Province SPED Center | BONTOC (Capital) | Lone | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 0 | 1
NEWCON 2024 | CAR | Mt. Province | 319207 | Sta. Isabel National High School | NATONIN | Lone | 1 | 4 | 2STY4CL | BATCH 1 | 30493200.285 |  |  | Not Yet Started | 0.3 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 4 | 0 | 0 | 0 |  | 0 | 0.3
NEWCON 2024 | CAR | Mt. Province |  | Ambatutong Elementary School | PARACELIS | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Mt. Province | 305239 | Butigue National High School | PARACELIS | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Mt. Province | 137103 | Wellie Maclinic Elementary School | PARACELIS | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Mt. Province | 136336 | Demang Elementary School | SADANGA | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Mt. Province | 136338 | Sacasacan Elementary School | SADANGA | Lone | 1 | 2 | Completion of 1STY2CL | BATCH 1 | 1328582.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1
NEWCON 2024 | CAR | Mt. Province | 305265 | Sagada National High School | SAGADA | Lone | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0.4149 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 4 | 0 | 0 | 0 |  | 0 | 0.4149
NEWCON 2024 | CAR | Tabuk City | 501971 | Lacnog Integrated School | CITY OF TABUK (Capital) | Lone | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 |  | 0 | 2 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2023 | CAR | Abra | 134994 | Dugong ES | BUCAY | Lone | 1 | 4 | 2UNITS 1STY2CL | Batch 1 | 18157500 | 18000000 |  | On Going | 0.96 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.96 | 0 | 1
NEWCON 2023 | CAR | Abra | 135027 | Benben Elementary School | LA PAZ | Lone | 1 | 2 | 1STY2CL | Batch 1 | 7859831.58 | 7791654.6 | 7336207.75 | Completed | 1 | [9 empty] | 739 BUILDERS |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2023 | CAR | Abra |  | El Bernos Elementary School | LA PAZ | Lone | 1 | 2 | 1STY2CL | Batch 1 | 7565625 | 7500000 | 7178576.62 | Completed | 1 | [9 empty] | A.D. MARRERO GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2023 | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | Lone | 1 | 6 | 2STY6CL | Batch 1 | 15131250 | 15000000 |  | Completed | 1 | [10 empty] | with project modification | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 6 |  | 1 | 0 | 2
NEWCON 2023 | CAR | Abra | 318701 | MARC YSRAEL B. BERNOS MEMORIAL NATIONAL HIGH SCHOOL | LA PAZ | Lone | 1 | 4 | 2STY4CL | Batch 1 | 7565625 | 7500000 |  | On Going | 0.97 | [10 empty] | with project modification | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.97 | 0 | 2
NEWCON 2023 | CAR | Abra | 305087 | Langiden NHS | LANGIDEN | Lone | 1 | 4 | 2STY4CL | Batch 1 | 14122500 | 14000000 | 13440499.98 | On Going | 0.96 | [9 empty] | 739 BUILDERS |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.96 | 0 | 2
NEWCON 2023 | CAR | Abra | 500590 | Peñarrubia Integrated School | PEÑARRUBIA | Lone | 1 | 8 | 2UNITS 2STY4CL | Batch 1 | 28400289.84 | 28153942.84 | 26968882.38 | On Going | 0.97 | [9 empty] | 739 BUILDERS |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.97 | 0 | 2
NEWCON 2023 | CAR | Abra | 305077 | Bolbolo NHS | PILAR | Lone | 1 | 2 | 1STY2CL | Batch 1 | 7136870.33 | 7074964.39 | 6722053.3 | Completed | 1 | [9 empty] | 739 BUILDERS |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2023 | CAR | Abra | 305093 | Pilar Rural High School | PILAR | Lone | 1 | 4 | 1STY4CL | Batch 1 | 11542849.37 | 11442725.52 | 10969936.22 | Completed | 1 | [9 empty] | 739 BUILDERS |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 1 | 0 | 1
NEWCON 2023 | CAR | Abra | 135194 | Sal-lapadan CS | SALLAPADAN | Lone | 1 | 4 | 2STY4CL | Batch 1 | 22300441.7 | 22107005.4 | 21192624.56 | On Going | 0.96 | [9 empty] | 739 BUILDERS |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.96 | 0 | 2
NEWCON 2023 | CAR | Abra | 305095 | Quidaoen NHS | SAN JUAN | Lone | 1 | 2 | 1STY2CL | Batch 1 | 7387336.98 | 7323258.47 | 6966267.23 | On Going | 0.96 | [9 empty] | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.96 | 0 | 1
NEWCON 2023 | CAR | Abra | 500518 | An-anaao Integrated School | TAYUM | Lone | 1 | 8 | 2UNITS 2STY4CL | Batch 1 | 28573340.55 | 28325492.49 | 26907780.61 | On Going | 0.98 | [9 empty] | 739 BUILDERS |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.98 | 0 | 2
NEWCON 2023 | CAR | Apayao | 135229 | Apayao ES | CALANASAN (BAYAG) | Lone | 1 | 2 | 1STY2CL | Batch 1 | 6052500 | 6000000 |  | On Going | 0.9648 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.9648 | 0 | 1
NEWCON 2023 | CAR | Apayao | 305111 | Conner Central NHS Main | CONNER | Lone | 1 | 6 | 2STY6CL | Batch 1 | 19444496.37 | 19275832.83 |  | On Going | 0.9741 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.9741 | 0 | 2
NEWCON 2023 | CAR | Apayao | 135280 | Talifugo ES | CONNER | Lone | 1 | 3 | 1STY3CL | Batch 1 | 8934931.52 | 8857429.01 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 3 |  | 1 | 0 | 1
NEWCON 2023 | CAR | Apayao | 135285 | Atok Elementary School | FLORA | Lone | 1 | 2 | 1STY2CL | Batch 1 | 6052500 | 6000000 |  | Completed | 0.9969 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0.9969 | 0 | 1
NEWCON 2023 | CAR | Apayao | 502117 | San Jose Integrated School | FLORA | Lone | 1 | 2 | 1STY2CL | Batch 1 | 6052500 | 6000000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2023 | CAR | Apayao | 219004 | Luyon ES | LUNA | Lone | 1 | 2 | 1STY2CL | Batch 1 | 6052500 | 6000000 |  | On Going | 0.9684 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.9684 | 0 | 1
NEWCON 2023 | CAR | Apayao | 135347 | Sta. Lina ES | LUNA | Lone | 1 | 2 | 1STY2CL | Batch 1 | 6052500 | 6000000 |  | On Going | 0.9634 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.9634 | 0 | 1
NEWCON 2023 | CAR | Baguio City | 136380 | Adiwang Elementary School | BAGUIO CITY | Lone | 1 | 3 | 3STY3CL | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 3 |  | 1 | 0 | 3
NEWCON 2023 | CAR | Baguio City | 136382 | Baguio Central school | BAGUIO CITY | Lone | 1 | 8 | 4STY8CL | Batch 1 | 25218750 | 25000000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2023 | CAR | Benguet | 305158 | Sinipsip National High School | BUGUIAS | Lone | 1 | 9 | 3STY9CL | Batch 1 | 29512060.56 | 29256069.95 |  | On Going | 0.9628 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.9628 | 0 | 3
NEWCON 2023 | CAR | Benguet | 135562 | Balakbak ES | KAPANGAN | Lone | 1 | 4 | 2STY4CL | Batch 1 | 12862984.9 | 12751410.06 |  | On Going | 0.9647 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.9647 | 0 | 2
NEWCON 2023 | CAR | Benguet | 305539 | AMBIONG NATIONAL HIGH SCHOOL | LA TRINIDAD (Capital) | Lone | 1 | 12 | 3STY12CL | Batch 1 | 47553758.77 | 47141272.63 |  | On Going | 0.9844 | [10 empty] | with project modification | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.9844 | 0 | 3
NEWCON 2023 | CAR | Benguet | 135724 | Langbis PS | TUBLAY | Lone | 1 | 2 | 1STY2CL | Batch 1 | 5875945.12 | 5824976.57 |  | On Going | 0.05 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.05 | 0 | 1
NEWCON 2023 | CAR | Ifugao | 135741 | Awayan ES | AGUINALDO | Lone | 1 | 2 | 1STY2CL | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2023 | CAR | Ifugao | 135819 | Cambulo ES - Mattao Annex | BANAUE | Lone | 1 | 2 | 1STY2CL | Batch 1 | 5043750 | 5000000 |  | On Going | 0.95 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.95 | 0 | 1
NEWCON 2023 | CAR | Ifugao | 135845 | Umalbong ES | HINGYON | Lone | 1 | 6 | 2STY6CL | Batch 1 | 22179688.88 | 21987300 |  | On Going | 0.9 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.9 | 0 | 2
NEWCON 2023 | CAR | Ifugao | 135879 | Banga ES | LAGAWE (Capital) | Lone | 1 | 2 | 1STY2CL | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2023 | CAR | Ifugao | 135888 | Luta PS | LAGAWE (Capital) | Lone | 1 | 2 | 1STY2CL | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2023 | CAR | Ifugao | 135922 | Buninan PS | MAYOYAO | Lone | 1 | 2 | 1STY2CL | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2023 | CAR | Ifugao | 135936 | Nattum PS (Abagong) | MAYOYAO | Lone | 1 | 2 | 1STY2CL | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2023 | CAR | Kalinga | 319116 | Balbalan National High school | BALBALAN | Lone | 1 | 1 | 1STY1CL | Batch 1 | 2521875 | 2500000 |  | On Going | 0.3 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.3 | 0 | 1
NEWCON 2023 | CAR | Kalinga | 135970 | Bullalayao Primary School | BALBALAN | Lone | 1 | 1 | 1STY1CL | Batch 1 | 2521875 | 2500000 |  | On Going | 0.2 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.2 | 0 | 1
NEWCON 2023 | CAR | Kalinga | 306053 | Eastern Balbalan National High School | BALBALAN | Lone | 1 | 2 | 1STY2CL | Batch 1 | 5043750 | 5000000 |  | On Going | 0.2 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.2 | 0 | 1
NEWCON 2023 | CAR | Kalinga | 319107 | Camalog National High School-Pinococ Extension | PINUKPUK | Lone | 1 | 2 | 1STY2CL | Batch 1 | 5043750 | 5000000 |  | On Going | 0.2 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.2 | 0 | 1
NEWCON 2023 | CAR | Kalinga | 305210 | Limos National High School - Dao-angan Extension | PINUKPUK | Lone | 1 | 2 | 1STY2CL | Batch 1 | 5043750 | 5000000 |  | On Going | 0.2 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.2 | 0 | 1
NEWCON 2023 | CAR | Kalinga | 305542 | Malagnat National High School-Taggay Extension | PINUKPUK | Lone | 1 | 4 | 1STY4CL | Batch 1 | 10087500 | 10000000 |  | On Going | 0.2 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.2 | 0 | 1
NEWCON 2023 | CAR | Kalinga | 305218 | Macutay Palao National High School | RIZAL (LIWAN) | Lone | 1 | 15 | 3STY15CL W/ DEMOLITION | Batch 1 | 49291588 | 48864027.76 |  | On Going | 0.2 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.2 | 0 | 3
NEWCON 2023 | CAR | Mt. Province | 305257 | Namatec National High School | Sabangan | 0 | 1 | 4 | 2STY4CL | Batch 1 | 15282710.4 | 15150146.62 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 0.1 | 0.9 | 2
NEWCON 2023 | CAR | Mt. Province | 319219 | Saclit National High School | SADANGA | 0 | 1 | 4 | 2STY4CL | Batch 1 | 16855317.61 | 16709112.87 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 0.1 | 0.9 | 2
NEWCON 2023 | CAR | Mt. Province | 136233 | Ambagiw ES | BESAO | Lone | 1 | 4 | 2 units 1STY2CL | Batch 1 | 19494414.28 | 9283667.14 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 0.1 | 0.9 | 1
NEWCON 2023 | CAR | Mt. Province | 305924 | Mainit National High School | BONTOC (Capital) | Lone | 1 | 4 | 2STY4CL | Batch 1 | 15131250 | 15000000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 0.1 | 0.9 | 2
NEWCON 2023 | CAR | Mt. Province | 305231 | Paracelis Technical & Vocational High School | PARACELIS | Lone | 1 | 6 | 3STY6CL | Batch 1 | 16351837.5 | 16210000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 6 |  | 1 | 0 | 3
NEWCON 2023 | CAR | Mt. Province | 136350 | Payag-eo Elementary School | SAGADA | Lone | 1 | 2 | 1STY2CL | Batch 1 | 15282710.4 | 15150146.62 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0.1 | 0.9 | 1
NEWCON 2023 | CAR | Tabuk City | 136158 | Balawag Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 2 | 1STY2CL | Batch 1 | 5172870 | 5128000 |  | For Procurement | 0.9 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.9 | 1
NEWCON 2023 | CAR | Tabuk City | 136086 | Bulanao Central School | CITY OF TABUK (Capital) | Lone | 1 | 20 | 4STY20CL | Batch 1 | 52494341.25 | 52039000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 20 |  | 0 | 1 | 4
NEWCON 2023 | CAR | Tabuk City | 319101 | Bulo National High School | CITY OF TABUK (Capital) | Lone | 1 | 5 | 1STY5CL | Batch 1 | 11731762.5 | 11630000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 5 |  | 0 | 1 | 1
NEWCON 2023 | CAR | Tabuk City | 502123 | Guilayon Integrated School | CITY OF TABUK (Capital) | Lone | 1 | 7 | 1STY7CL | Batch 1 | 18039476.25 | 17883000 |  | For Procurement | 0.6 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.6 | 1
NEWCON 2023 | CAR | Tabuk City | 501889 | Toppan Integrated School | CITY OF TABUK (Capital) | Lone | 1 | 5 | 1STY5CL | Batch 1 | 11479575 | 11380000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 5 |  | 0 | 1 | 1
NEWCON 2023 | CAR | Tabuk City | 136183 | Western Tabuk CS | CITY OF TABUK (Capital) | Lone | 1 | 2 | 1STY2CL | Batch 1 | 5441157.15 | 5393960 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 0 | 1 | 1
NEWCON 2022 | CAR | Abra | 135058 | Cayapa ES | LAGANGILANG | 0 | 1 | 2 | 1STY2CL | 2 |  | 6032593.875 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2022 | CAR | Abra | 501729 | TABANGAO IS | LUBA | 0 | 1 | 4 | 2STY4CL | 2 |  | 14310542.1375 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 1 | 0 | 2
NEWCON 2022 | CAR | Abra | 501343 | Maguyepyep Integrated School | SALLAPADAN | 0 | 1 | 4 | 2STY4CL | 2 |  | 20705793.7459 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 1 | 0 | 2
NEWCON 2022 | CAR | Abra | 135140 | Palang PS | SAN QUINTIN | 0 | 1 | 2 | 1STY2CL | 2 |  | 6431538.75 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2022 | CAR | Abra | 135093 | Batayan PS | TUBO | 0 | 1 | 2 | 1STY2CL | 2 |  | 7437953.5125 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2022 | CAR | Benguet | 135735 | Ciriaco Magno ES | TUBLAY | 0 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2022 | CAR | Ifugao | 220021 | Duli ES Extension | ASIPULO | 0 | 1 | 4 | 2STY4CL | 2 |  | 16382955.25 |  | On Going | 0.88 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.88 | 0 | 2
NEWCON 2022 | CAR | Kalinga | 136029 | Pasil CS (Malucsad Annex) | PASIL | 0 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2022 | CAR | Mt. Province | 136236 | Besao Elementary School | BESAO | 0 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2022 | CAR | Mt. Province | 136335 | Betwagan Elementary School | SADANGA | 0 | 1 | 9 | 3STY9CL | 2 |  | 25062500 |  | On Going | 0.33 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.33 | 0 | 3
NEWCON 2022 | CAR | Mt. Province | 136338 | Sacasacan Elementary School | SADANGA | 0 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2022 | CAR | Tabuk City | 136086 | Bulanao Central School | CITY OF TABUK (Capital) | 0 | 1 | 20 | 4STY20CL | 2 |  | 52631250 |  | On Going | 0.11 | [10 empty] | Suspension made due to unfavorable weather conditions. With time extension | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.11 | 0 | 4
NEWCON 2022 | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | 0 | 1 | 6 | 3STY6CL | 2 |  | 20299989.9664 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 6 |  | 1 | 0 | 3
NEWCON 2022 | CAR | Benguet | 501203 | Datakan Integrated School | KAPANGAN | 0 | 1 | 20 | 4STY20CL | 2 |  | 46178212.5773 |  | On Going | 0.36 | [10 empty] | Modification was approved. Project was awarded on April 19, 2023. Preparation of Contract is ongoing. | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.36 | 0 | 4
NEWCON 2022 | CAR | Kalinga | 340131 | SHS in Lubuagan, Kalinga | LUBUAGAN | 0 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNITS ONE (1) REGULAR WORKSHOP BUILDING (WEAVING CENTER) | 2 |  | 10475567.8406 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 2 |  | 1 | 0 | 1
NEWCON 2021 | CAR | Abra | 305075 | Abra HS | BANGUED (Capital) | 0 | 1 | 4 | Construction/Completion (2STY4CL) |  | 9462572.4375 | 9438975 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 2
NEWCON 2021 | CAR | Abra | 305075 | Abra HS | BANGUED (Capital) | 0 |  | 8 | Construction/Completion (4STY8CL) |  | 18736725 | 18690000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | CAR | Baguio City | 136414 | Manuel L. Quezon Elementary School | BAGUIO CITY | 0 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1393475 | 1390000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | CAR | Baguio City | 305271 | Bakakeng National High School | BAGUIO CITY | 0 | 1 | 8 | Construction/Completion (4STY8CL) |  | 310775 | 310000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | CAR | Baguio City | 340055 | Baguio City National Science High School | BAGUIO CITY | 0 | 1 | 8 | Construction/Completion (4STY Reg. Workshop, 2 Sci. Lab., 2 ICT School Bldg) |  | 2686700 | 2680000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | CAR | Ifugao | 135825 | Kinakin ES | BANAUE | 0 | 1 |  | Construction of Slope Protection |  | 18546250 | 18500000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
NEWCON 2021 | CAR | Ifugao | 135826 | Patilong ES | BANAUE | 0 | 1 | 4 | Construction of Slope Protection |  | 5442834.343 | 5429261.19 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0
NEWCON 2021 | CAR | Kalinga | 305225 | Tanudan Vocational School | TANUDAN | 0 | 1 | 1 | Construction/Completion of School Buildings |  | 250625 | 250000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1
NEWCON 2021 | CAR | Kalinga | 305225 | Tanudan Vocational School | TANUDAN | 0 |  | 2 | Construction/Completion of School Buildings |  | 250625 | 250000 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1
NEWCON 2021 | CAR | Mt. Province | 221004 | Cabunagan Primary School | TADIAN | 0 | 1 | 4 | Construction of Slope Protection |  | 1327695.6016 | 1324384.64 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0
NEWCON 2020 | CAR | Abra | 305085 | Dugong NHS | Bucay | 0 | 1 | 4 | 2STY4CL |  | 10325750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0
NEWCON 2020 | CAR | Apayao | 135275 | Paddig Elementary School | CONNER | 0 | 1 | 3 | 1STY3CL w/ Toilet |  | 6891734.32 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0
NEWCON 2020 | CAR | Baguio City | 136416 | San Vicente Elementary School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL |  | 23558750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | CAR | Benguet | 135510 | Midas Elementary School | ITOGON | 0 | 1 | 6 | 2STY6CL |  | 17867814.88 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | 0
NEWCON 2020 | CAR | Benguet | 135603 | MOCGAO ES | Kibungan | 0 | 1 | 4 | 2STY4CL |  | 16955717.26 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0
NEWCON 2020 | CAR | Ifugao | 305189 | Caragasan NHS | ALFONSO LISTA (POTIA) | 0 | 1 | 4 | 2STY4CL |  | 10526250 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0
NEWCON 2020 | CAR | Kalinga | 305199 | Balbalan Agricultural and Industrial School-Extention Annex | BALBALAN | 0 | 1 | 4 | 2STY4CL |  | 13947911.95 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0
NEWCON 2020 | CAR | Mt. Province | 305244 | Guinzadan National High School | Bauko | 0 | 1 | 6 | 2STY6CL |  | 17543750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | 0
NEWCON 2020 | CAR | Tabuk City | 136085 | Agbannawag Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 8 | 2STY8CL (MODIFIED PLAN) |  | 22055000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | CAR | Tabuk City | 220521 | Pantar Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 4 | 2STY4CL (MODIFIED PLAN) |  | 11106460.06 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0
NEWCON 2019 | CAR | Abra | 305095 | Quidaoen NHS | SAN JUAN | 0 | 1 | 4 | 2STY4CL |  | 11725315.4181 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2019 | CAR | Apayao | 135321 | Magabta ES | KABUGAO (Capital) | 0 | 1 | 3 | 1STY3CL |  | 8012580.5176 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2019 | CAR | Baguio City | 305270 | Dona Aurora National High School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL |  | 24200650.75 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | CAR | Ifugao |  | Damag Elementary School (Jacmal Annex) | AGUINALDO | 0 | 1 | 6 | 2STY6CL |  | 17692436.0281 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2019 | CAR | Kalinga | 135992 | Lubuagan Central School | LUBUAGAN | 0 | 1 | 4 | 2STY4CL |  | 11337595.9266 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2019 | CAR | Kalinga | 135992 | Lubuagan Central School | LUBUAGAN | 0 |  | 6 | 2STY6CL |  | 15111409.3125 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2019 | CAR | Mt. Province | 136282 | Amolong Elementary School | PARACELIS | 0 | 1 | 3 | 1STY3CL |  | 5419234.3 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2019 | CAR | Mt. Province | 136267 | Apapawan Elementary School | NATONIN | 0 | 1 | 2 | 1STY2CL |  | 6265625 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2019 | CAR | Mt. Province | 136289 | Butigue Elementary School | PARACELIS | 0 | 1 | 12 | 3STY12CL |  | 32230375 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2019 | CAR | Mt. Province | 305261 | Paracelis National High School | PARACELIS | 0 | 1 | 12 | 4STY12CL |  | 35990162.0275 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2019 | CAR | Tabuk City | 220531 | Bulanao East Annex - Greenhills PS | CITY OF TABUK (Capital) | 0 | 1 | 6 | 3STY6CL (MODIFIED) |  | 20861894.7151 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Abra | 305082 | Cristina B. Gonzales MHS | BUCAY | 0 | 1 | 9 | 3STY9CL | BATCH 1 | 20200000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2018 | CAR | Abra | 305090 | Mataragan NAS | MALIBCONG | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3484000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Abra | 135011 | An-anaao ES | TAYUM | 0 | 1 | 4 | 2STY4CL | Batch 3 | 11433347.21 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Abra | 135077 | Paganao E/S | LAGANGILANG | 0 | 1 | 3 | 1STY3CL | Batch 3 | 6900000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2018 | CAR | Abra | 305104 | Tineg National High School | TINEG | 0 | 1 | 2 | 2 UNITS OF 1STY2CL | Batch 3 | 11180000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Abra | 318703 | Baay National High School - Extension | LACUB | 0 | 1 | 4 | 2STY4CL | Batch 3 | 12034563.75 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Abra | 500590 | Peñarrubia Integrated School | PEÑARRUBIA | 0 | 1 | 4 | 2STY4CL | Batch 3 | 11289064.71 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Apayao | 135230 | Butao ES | CALANASAN (BAYAG) | 0 | 1 | 4 | 2STY4CL W/ WATER SYSTEM | BATCH 1 | 13852014.07 |  |  | Completed | 1 |  |  |  |  | June 15, 2018 |  | July 18, 2018 | July 23, 2018 | August 2, 2018 | GKA ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Apayao | 135332 | Calabigan PS | LUNA | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3554895.27 |  |  | Completed | 1 |  |  |  |  | June 15, 2018 |  | July 18, 2018 | July 23, 2018 | August 2, 2018 | KVC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Apayao | 135336 | Luna CS | LUNA | 0 | 1 | 6 | 2STY6CL W/ WATER SYSTEM | BATCH 1 | 15319989.64 |  |  | Completed | 1 |  |  |  |  | June 15, 2018 |  | July 18, 2018 | July 23, 2018 | August 2, 2018 | GKA ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Apayao | 135359 | Swan ES | PUDTOL | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3549895.27 |  |  | Completed | 1 | [6 empty] | August 13, 2018 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Apayao | 305124 | Sipa-Imelda NHS | SANTA MARCELA | 0 | 1 | 4 | 2STY4CL W/ WATER SYSTEM | BATCH 1 | 12306503.07 |  |  | Completed | 1 |  |  |  |  | June 15, 2018 |  | July 18, 2018 | July 23, 2018 | August 2, 2018 | J.G YACAS CONSTRUCTION SUPPLY AND EQUIPMENT RENTAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Apayao | 135357 | Pudtol CS | PUDTOL | 0 | 1 | 6 | 2STY6CL W/ WATER SYSTEM | BATCH 1 | 16628084.39 |  |  | Completed | 1 |  |  |  |  | June 15, 2018 |  | July 18, 2018 | July 23, 2018 | August 2, 2018 | GKA ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Apayao | 318810 | Swan National Agricultural and Trade High School | PUDTOL | 0 | 1 | 4 | 2STY4CL W/ WATER SYSTEM | BATCH 1 | 12477649.55 |  |  | Completed | 1 |  |  |  |  | June 15, 2018 |  | July 18, 2018 | July 23, 2018 | August 2, 2018 | KVC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Apayao | 135238 | Malitao PS | CALANASAN (BAYAG) | 0 | 1 | 3 | 1STY3CL | Batch 3 | 8660173.52 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2018 | CAR | Apayao | 135348 | Tumog Elementary School | LUNA | 0 | 1 | 3 | 1STY3CL | Batch 3 | 7981287.77 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2018 | CAR | Apayao | 135361 | Barocboc ES | SANTA MARCELA | 0 | 1 | 3 | 1STY3CL | Batch 3 | 7651867.49 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2018 | CAR | Apayao | 135362 | Consuelo Elementary School | SANTA MARCELA | 0 | 1 | 3 | 1STY3CL | Batch 3 | 7702602.08 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2018 | CAR | Baguio City | 305275 | Mil-an National High School | BAGUIO CITY | 0 | 1 | 4 | 4STY 2 SCI LAB & 2 ICT | BATCH 1 | 18309570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Baguio City | 305278 | San Vicente National High School (Integrated Senior High School) | BAGUIO CITY | 0 | 1 | 4 | 4STY 2 SCI LAB & 2 ICT | BATCH 1 | 18729570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Baguio City | 305279 | Sto. Tomas National High School | BAGUIO CITY | 0 | 1 | 10 | 4STY 2 REG WORKSHOP, 2 SCI LAB, 2 ICT LAB, 4CL | BATCH 1 | 39550737 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2018 | CAR | Baguio City | 305280 | Irisan National High School | BAGUIO CITY | 0 | 1 | 4 | 4STY 2 SCI LAB & 2 ICT | BATCH 1 | 18229570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Baguio City | 305284 | Joaquin Smith National High School | BAGUIO CITY | 0 | 1 | 4 | 4STY 1 SCI LAB, 1 REG WORKSHOP & 2 ICT | BATCH 1 | 18729570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Baguio City | 340055 | Baguio City National Science High School (Senior High School-Stand Alone) | BAGUIO CITY | 0 | 1 | 8 | 4STY 4 REG WORKSHOP, 2 SCI LAB & 2 ICT | BATCH 1 | 42420046.32 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | CAR | Benguet | 305139 | Cabiten NHS (RA9087) | MANKAYAN | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 10175012 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Benguet | 135483 | Lam-ayan ES | BUGUIAS | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 11833070.3 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Benguet | 135383 | Celo Haights ES | ATOK | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 11735295 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Benguet | 135505 | Gumatdang ES | ITOGON | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 11594717.03 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Benguet | 135515 | Acupan ES | ITOGON | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 10128972.94 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Benguet | 135613 | Alapang Camp. Dangwa ES | LA TRINIDAD (Capital) | 0 | 1 | 6 | 3STY6CL | BATCH 1 | 13692657.98 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Benguet | 135620 | Benguet SPED Center | LA TRINIDAD (Capital) | 0 | 1 | 6 | 3STY6CL | BATCH 1 | 14952338.21 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Benguet | 135631 | Puguis Elementary School | LA TRINIDAD (Capital) | 0 | 1 | 16 | 4STY16CL | BATCH 1 | 37940289.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | CAR | Benguet | 305125 | Alejo M. Pacalso Memorial National High School | ITOGON | 0 | 1 | 4 | 2STY 2 REG WS 1 SCIENCE LAB 1 ICT LAB | BATCH 1 | 16541674.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Benguet | 305128 | Ampusongan NHS - Main | BAKUN | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 10280509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Benguet | 305130 | Camp 30 National High School | ATOK | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 9126483 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Benguet | 305133 | Benguet National High School-Main | LA TRINIDAD (Capital) | 0 | 1 | 12 | 4STY4CL 6REG WS 1 SCIENCE LAB 1 ICT LAB | BATCH 1 | 35859442.31 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | CAR | Benguet | 305133 | Benguet National High School-Main | LA TRINIDAD (Capital) | 0 |  | 13 | 4STY6CL 5REG WS 1 SCIENCE LAB 1 ICT LAB | BATCH 1 | 35859442.31 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0
NEWCON 2018 | CAR | Benguet | 305135 | Bokod NHS-Main | BOKOD | 0 | 1 | 9 | 4STY2CL 3 REG WS 2 SCIENCE LAB 2 ICT LAB | BATCH 1 | 31733107.43 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2018 | CAR | Benguet | 305140 | Cordillera Regional Science High School | LA TRINIDAD (Capital) | 0 | 1 | 4 | 4STY 2 SCIENCE LAB 2 ICT LAB | BATCH 1 | 19140030.7 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Benguet | 305141 | Evelio Javier Memorial NHS - Main | TUBA | 0 | 1 | 8 | 4STY4CL 2 SCIENCE LAB 2 ICT LAB | BATCH 1 | 27115555.07 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | CAR | Benguet | 305142 | Laurencio Fianza NHS - Main | ITOGON | 0 | 1 | 3 | 3STY 3 REG WS | BATCH 1 | 13921841.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2018 | CAR | Benguet | 305142 | Laurencio Fianza NHS - Main | ITOGON | 0 |  | 4 | 3STY2CL 2 ICT LAB | BATCH 1 | 13921841.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Benguet | 305145 | Kamora National High School | KABAYAN | 0 | 1 | 4 | 4STY 2 SCIENCE LAB 2 ICT LAB | BATCH 1 | 17150039.49 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Benguet | 305146 | Adaoay National High School | KABAYAN | 0 | 1 | 4 | 4STY 2 SCIENCE LAB 2 ICT LAB | BATCH 1 | 16799848.23 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Benguet | 305149 | Kibungan NHS | KIBUNGAN | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 13141937 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Benguet | 305157 | Sablan NHS | SABLAN | 0 | 1 | 4 | 4STY 2 SCIENCE LAB 2 ICT LAB | BATCH 1 | 16949936.22 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Benguet | 305159 | Fianza Memorial National High School | ITOGON | 0 | 1 | 5 | 4STY2CL 1 SCIENCE 2 ICT LAB | BATCH 1 | 17349697.07 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2018 | CAR | Benguet | 305160 | Tuba NHS (Nangalisan) | TUBA | 0 | 1 | 13 | 4STY6CL 3 REG WS 2 SCIENCE LAB 2 ICT LAB | BATCH 1 | 35859219.31 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0
NEWCON 2018 | CAR | Benguet | 305163 | Tublay School of Home Industries - Annex (Ambuklao) | BOKOD | 0 | 1 | 5 | 4STY2CL 1 REG WS 1 SCIENCE LAB 1 ICT LAB | BATCH 1 | 17010030.7 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2018 | CAR | Benguet | 305165 | Twin Peaks National High School | TUBA | 0 | 1 | 6 | 3STY 2 REG WS 2 SCIENCE LAB 2 ICT LAB | BATCH 1 | 25079838.26 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Benguet | 318901 | Bokod NHS Annex - Daklan | BOKOD | 0 | 1 | 8 | 4STY4CL 2 SCIENCE LAB 2 ICT LAB | BATCH 1 | 26470379.81 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | CAR | Benguet | 318905 | La Trinidad NHS | LA TRINIDAD (Capital) | 0 | 1 | 11 | 4STY6CL 1 REG WS 2 SCIENCE LAB 2 ICT LAB | BATCH 1 | 36040289.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0
NEWCON 2018 | CAR | Benguet | 318909 | Eastern La Trinidad NHS | LA TRINIDAD (Capital) | 0 | 1 | 12 | 4STY8CL 2 SCIENCE 2 ICT LAB | BATCH 1 | 32332800.93 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | CAR | Benguet | 318914 | Evelio Javier Memorial NHS Annex - Ansagan | TUBA | 0 | 1 | 3 | 3STY 3 REG WS | BATCH 1 | 13892124 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2018 | CAR | Benguet | 318914 | Evelio Javier Memorial NHS Annex - Ansagan | TUBA | 0 |  | 4 | 2STY 2 SCIENCE LAB 2 ICT LAB | BATCH 1 | 17252147.49 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Benguet | 318915 | Sablan NHS Extension-Balluay | SABLAN | 0 | 1 | 9 | 3STY9CL | BATCH 1 | 20951224.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2018 | CAR | Ifugao | 135862 | Baguinge ES | KIANGAN | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 12498400 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Ifugao | 135956 | Tukucan ES | TINOC | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 14375000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Ifugao | 305179 | Southern Hingyon NHS | HINGYON | 0 | 1 | 9 | 3STY9CL | BATCH 1 | 25967500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2018 | CAR | Ifugao | 305180 | Hungduan National High School | HUNGDUAN | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 14074500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Ifugao | 305181 | Ifugao Prov'l. Science HS | LAMUT | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 12409000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Ifugao | 305182 | Kiangan NHS (EXTENSION) | KIANGAN | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 13049700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Ifugao | 305193 | Kalanguya NHS | TINOC | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 16672300 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Ifugao | 135748 | Damag ES Annex (Damag Proper) | AGUINALDO | 0 | 1 | 9 | 3STY9CL | Batch 3 | 24899997.61 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2018 | CAR | Ifugao |  | Asipulo National High School Annex | ASIPULO | 0 | 1 | 4 | 2STY4CL | Batch 5 | 13863500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Ifugao | 135813 | Banaue CS | BANAUE | 0 | 1 | 20 | 4STY20CL | Batch 5 | 48214855.93 |  |  | Completed | 1 | [10 empty] | Substantially completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | CAR | Ifugao | 135826 | Patilong ES | BANAUE | 0 | 1 | 4 | 2STY4CL | Batch 5 | 10785167.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Ifugao | 135824 | Gohang ES | BANAUE | 0 | 1 | 4 | 2STY4CL | Batch 5 | 10904038.74 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Ifugao | 135827 | Poitan ES | BANAUE | 0 | 1 | 6 | 2STY6CL | Batch 5 | 17245000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Ifugao | 135825 | Kinakin ES | BANAUE | 0 | 1 | 6 | 2STY6CL | Batch 5 | 17338000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Ifugao | 135868 | Duit ES | KIANGAN | 0 | 1 | 8 | 2STY8CL | Batch 5 | 19965000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | CAR | Ifugao |  | Lagawe NHS Annex | LAGAWE (Capital) | 0 | 1 | 12 | 2UNITS 2STY6CL | Batch 5 | 34468190 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | CAR | Kalinga | 135978 | Pantikian ES | BALBALAN | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3477712.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Kalinga | 135983 | Sesec-An PS | BALBALAN | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3534011.15 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Kalinga | 136028 | Pasil CS (Guinaang Annex ) | PASIL | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3911119.03 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Kalinga | 136030 | Pasil CS ( Pugong Annex) | PASIL | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3742777.7 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Kalinga | 136033 | Ammacian ES | PINUKPUK | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 10212944.33 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Kalinga | 136072 | Liwan East ES | RIZAL (LIWAN) | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 11185966.6 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Kalinga | 136076 | Rizal Central School | RIZAL (LIWAN) | 0 | 1 | 10 | 2STY10CL | BATCH 1 | 21562021.85 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2018 | CAR | Kalinga | 136123 | Dacalan ES | TANUDAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 4364948.78 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2018 | CAR | Kalinga | 136129 | Taloctoc ES | TANUDAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 4012857.46 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Kalinga | 220511 | Baclas Elementary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3210083.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Kalinga | 305199 | Balbalan Agricultural and Industrial School | BALBALAN | 0 | 1 | 2 | UNIQUE WORKSHOP | BATCH 1 | 10231463.94 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Kalinga | 305199 | Balbalan Agricultural and Industrial School | BALBALAN | 0 |  | 1 | REG WORKSHOP | BATCH 1 | 3422795.41 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2018 | CAR | Kalinga | 305209 | Kinama National High School | RIZAL (LIWAN) | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3380872.87 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Kalinga | 305215 | Batong Buhay National High School | PASIL | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3666870.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Kalinga | 305225 | Tanudan Vocational School | TANUDAN | 0 | 1 | 8 | 8 UNITS WORKSHOP BLDG (7x18) | BATCH 1 | 35499850.43 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | CAR | Mt. Province | 136268 | Banawel Elementary School | NATONIN | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 12191374.72 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Mt. Province | 136287 | Bananao Elementary School | PARACELIS | 0 | 1 | 6 | 3STY6CL | BATCH 1 | 16034522.13 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Mt. Province | 136305 | Makilo Elementary School | PARACELIS | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 10204239.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Mt. Province | 136309 | Palitod Elementary School | PARACELIS | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 13529970.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Mt. Province | 305256 | Tocucan National High School | BONTOC (Capital) | 0 | 1 | 4 | 2STY4CL (SPECIAL DESIGN) | BATCH 1 | 8855004.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Mt. Province | 305261 | Paracelis National High School | PARACELIS | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 10173745.94 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Mt. Province | 319224 | Bunga National High School | TADIAN | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 11096074.94 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Mt. Province | 221004 | Cabunagan Primary School | TADIAN | 0 | 1 | 4 | 2STY4CL | Batch 3 | 11076528.66 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Mt. Province | 305233 | Banao National High School | BAUKO | 0 | 1 | 6 | 2STY6CL | Batch 3 | 16457140.6 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2018 | CAR | Tabuk City | 136009 | Magsaysay ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3129569.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Tabuk City | 136085 | Agbannawag ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3336559.78 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Tabuk City | 136109 | New Balbalan ES | CITY OF TABUK (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 9380003 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | CAR | Tabuk City | 136109 | New Balbalan ES | CITY OF TABUK (Capital) | 0 |  | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3336559.78 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Tabuk City | 136160 | Bantay ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3129559.78 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Tabuk City | 220501 | PA-O ELEMENTARY SCHOOL | CITY OF TABUK (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 1 | 4729943.7 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2018 | CAR | Tabuk City | 220501 | PA-O ELEMENTARY SCHOOL | CITY OF TABUK (Capital) | 0 |  | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3455584.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Tabuk City | 305195 | Agbannawag National High School | CITY OF TABUK (Capital) | 0 | 1 | 8 | WORKSHOP - 4STY8CL W/ LECTURE ROOM | BATCH 1 | 38271147 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | CAR | Tabuk City | 305198 | Balawag National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3450409.78 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2018 | CAR | Tabuk City | 305205 | Kalinga National High School | CITY OF TABUK (Capital) | 0 | 1 | 8 | WORKSHOP - 4STY8CL W/ LECTURE ROOM | BATCH 1 | 38071147 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | CAR | Tabuk City | 305205 | Kalinga National High School | CITY OF TABUK (Capital) | 0 |  | 8 | WORKSHOP - 4STY8CL W/ LECTURE ROOM | BATCH 1 | 38071147 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | CAR | Tabuk City | 305212 | Nambaran Agro-Industrial National High School | CITY OF TABUK (Capital) | 0 | 1 | 8 | WORKSHOP - 4STY8CL W/ LECTURE ROOM | BATCH 1 | 37921147 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 | 1 | 8 | WORKSHOP - 4STY8CL W/ LECTURE ROOM | BATCH 1 | 38071147 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 |  | 8 | WORKSHOP - 4STY8CL W/ LECTURE ROOM | BATCH 1 | 38071147 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | CAR | Tabuk City | 305222 | New Tanglag National High School | CITY OF TABUK (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 1 | 4393568.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Abra | 305082 | Cristina B. Gonzales MHS | BUCAY | 0 | 1 | 3 | 1STY2CL | BATCH 2 | 2768000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Abra | 135019 | Don Rosalio Eduarte ES | DOLORES | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3960012.58 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Abra | 305096 | Rosalio Eduarte NHS | DOLORES | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2768000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Abra | 305102 | Tagodtod National High School | LAGANGILANG | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2769000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Abra | 135056 | Caoayan PS | LICUAN-BAAY (LICUAN) | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2790000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Abra | 305098 | Manabo NHS (San Jose Catacdegan NHS) | MANABO | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2800000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Abra |  | Villa Mercedes ES | SAN QUINTIN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3960012.58 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Ifugao | 135792 | Duli E/S | Asipulo | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2813500 |  |  | Completed | 1 | [9 empty] | Southland Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135833 | Bangtinon E/S | Hingyon | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2625100 |  |  | Completed | 1 | [9 empty] | Jovic Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135848 | Awa P/S | Hungduan | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2888800 |  |  | Completed | 1 | [9 empty] | Southland Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135872 | Mappit E/S | Kiangan | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2625500 |  |  | Completed | 1 | [9 empty] | CarlyzConstruction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135878 | Abinuan E/S | Lagawe | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2669800 |  |  | Completed | 1 | [9 empty] | Southland Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135890 | Ollilicon E/S | Lagawe | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2686300 |  |  | Completed | 1 | [9 empty] | Southland Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135892 | Pullaan E/S | Lagawe | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2709100 |  |  | Completed | 1 | [9 empty] | Southland Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135898 | Dunuan E/S | Lamut | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2639500 |  |  | Completed | 1 | [9 empty] | Southland Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135903 | Lawig E/S | Lamut | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2582700 |  |  | Completed | 1 | [9 empty] | Jovic Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135914 | Salamague E/S | Lamut | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2601200 |  |  | Completed | 1 | [9 empty] | Jovic Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135946 | Eheb E/S | Tinoc | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2911100 |  |  | Completed | 1 | [9 empty] | Southland Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135947 | Gumhang E/S | Tinoc | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2885800 |  |  | Completed | 1 | [9 empty] | Mac Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135949 | Impugong E/S | Tinoc | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2905700 |  |  | Completed | 1 | [9 empty] | Southland Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135957 | Tulludan E/S | Tinoc | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2872100 |  |  | Completed | 1 | [9 empty] | Southland Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Mt. Province | 136272 | Nabhar Primary School | NATONIN | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 3012079.59 |  |  | Completed | 1 |  |  |  |  | 2017-09-05 |  | 2017-09-25 |  | 2017-11-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Mt. Province | 136279 | Tappo Elementary School | NATONIN | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 3012079.59 |  |  | Completed | 1 |  |  |  |  | 2017-09-05 |  | 2017-09-25 |  | 2017-11-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Mt. Province | 136281 | Addang Elementary School | PARACELIS | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 3012079.59 |  |  | Completed | 1 |  |  |  |  | 2017-09-05 |  | 2017-09-25 |  | 2017-11-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Mt. Province | 136283 | Anonat Primary School | PARACELIS | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 3012079.59 |  |  | Completed | 1 |  |  |  |  | 2017-09-05 |  | 2017-09-25 |  | 2017-11-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Mt. Province | 319209 | Buringal NHS | PARACELIS | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 3012079.59 |  |  | Completed | 1 |  |  |  |  | 2017-10-04 |  | 2017-10-24 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Mt. Province | 136291 | Camparadi Elementary School | PARACELIS | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 3012079.59 |  |  | Completed | 1 |  |  |  |  | 2017-10-04 |  | 2017-10-24 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Mt. Province | 221005 | Minoli Elementary School | PARACELIS | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 3012079.59 |  |  | Completed | 1 |  |  |  |  | 2017-09-05 |  | 2017-09-25 |  | 2017-11-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305110 | Calanasan NHS | CALANASAN (BAYAG) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3587382.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305110 | Calanasan NHS | CALANASAN (BAYAG) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3987382.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 219024 | Greenhills ES | FLORA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2988255.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135330 | Cagandungan East PS | LUNA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2583501.29 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305116 | Luna National High School | LUNA | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 7112975.74 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305116 | Luna National High School | LUNA | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 6133999.96 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305116 | Luna National High School | LUNA | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 6933999.96 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305117 | Marag Valley Agr'l. and Trade HS | LUNA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2988255.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 318809 | San Francisco National Agricultural and Trade HS | LUNA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2938255.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135749 | Galonogon ES | AGUINALDO | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2687565.85 |  |  | Completed | 1 | [9 empty] | Lucky A Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135757 | Manaot ES | AGUINALDO | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2891641.21 |  |  | Completed | 1 | [9 empty] | Lucky A Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135760 | Pojnaan ES | AGUINALDO | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2627021.43 |  |  | Completed | 1 | [9 empty] | Colby Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135762 | Ubao ES | AGUINALDO | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2615067.41 |  |  | Completed | 1 | [9 empty] | Colby Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136067 | Bagbag ES | RIZAL | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3446748.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136070 | Calaocan ES | RIZAL | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3421149.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136071 | Kinama ES | RIZAL | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3210526.06 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136122 | Pagugo ES | TANUDAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3192835.77 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136130 | Tanudan CS | TANUDAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3210526.06 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 136158 | Balawag Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3450897.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 319108 | Balong National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3569688.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 136094 | Banneng ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3416727.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 136090 | Bulanao West Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3151407.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 220522 | Dananao Primary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3241857.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 220510 | Gradual Discovery ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3079047.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 136102 | Magabbangon Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3189597.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305222 | New Tanglag National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3259947.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 136178 | Paligatto Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3626973.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 220501 | PA-O ELEMENTARY SCHOOL | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 4114197.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 220529 | San Pablo Primary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3556463.1 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 136089 | Southern Tabuk CS | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3139347.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 136180 | SUYANG ELEMENTARY SCHOOL | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3406677.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 136112 | Tannubong Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3387582.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305108 | BAC-DA National High School | LUNA | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3556487.87 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305108 | BAC-DA National High School | LUNA | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3066999.98 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305108 | BAC-DA National High School | LUNA | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3466999.98 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 318801 | Tumog National Agricultural and trade High School | LUNA | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3066999.98 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 318801 | Tumog National Agricultural and trade High School | LUNA | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3466999.98 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 219012 | Aga PS | PUDTOL | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2595432.81 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 219023 | Aurora PS | PUDTOL | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2611589.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135354 | Lower Maton Elementary School | PUDTOL | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2568002.15 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305118 | Mataguisi Comp. HS Main | PUDTOL | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3163547.76 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305118 | Mataguisi Comp. HS Main | PUDTOL | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3563547.76 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 319009 | Mataguisi Comprehensive NHS Cacalaggan Annex | PUDTOL | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2597029.47 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305123 | Pudtol NHS | PUDTOL | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 7154975.72 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305123 | Pudtol NHS | PUDTOL | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3087999.97 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305123 | Pudtol NHS | PUDTOL | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3487999.97 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 135360 | Upper Maton PS | PUDTOL | 0 | 1 | 3 | 1STY3CL | BATCH 7 | 3762789.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Apayao | 305120 | MAYOR GUILLERMO A. BARSATAN MEMORIAL SCHOOL OF ARTS AND TRADE | SANTA MARCELA | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 7317523.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305120 | MAYOR GUILLERMO A. BARSATAN MEMORIAL SCHOOL OF ARTS AND TRADE | SANTA MARCELA | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 6313547.76 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305120 | MAYOR GUILLERMO A. BARSATAN MEMORIAL SCHOOL OF ARTS AND TRADE | SANTA MARCELA | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 7088547.76 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135371 | Sta. Marcela CS | SANTA MARCELA | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2539005.85 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305109 | Sta. Marcela NHS | SANTA MARCELA | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3179290.5 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305109 | Sta. Marcela NHS | SANTA MARCELA | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3579290.5 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Benguet | 305145 | Kamora National High School | KABAYAN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3567183.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Benguet | 305145 | Kamora National High School | KABAYAN | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3567183.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Benguet | 305165 | Twin Peaks National High School | TUBA | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3567183.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Ifugao | 135742 | Awayan ES - Annex | AGUINALDO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2862051.78 |  |  | Completed | 1 | [9 empty] | Lucky A Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135745 | Buwag PS | AGUINALDO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2875120.51 |  |  | Completed | 1 | [9 empty] | Lucky A Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135748 | Damag Elementary School | AGUINALDO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2745241.81 |  |  | Completed | 1 | [9 empty] | Lucky A Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135753 | Halag E/S - Halag 3 (Riverside) | AGUINALDO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2719497.14 |  |  | Completed | 1 | [9 empty] | Lucky A Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135752 | Halag E/S- Halag 1 | AGUINALDO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2869893.02 |  |  | Completed | 1 | [9 empty] | Lucky A Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135759 | Nepojnoc PS | AGUINALDO | 0 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4157142.19 |  |  | Completed | 1 | [9 empty] | Lucky A Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Ifugao | 319008 | Ubao NHS Extension | AGUINALDO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2623310.54 |  |  | Completed | 1 | [9 empty] | Colby Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135769 | Caragasan ES | ALFONSO LISTA (POTIA) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2639883.38 |  |  | Completed | 1 | [9 empty] | 8J Builders and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 305171 | Eastern Potia National High School | ALFONSO LISTA (POTIA) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2875166.88 |  |  | Completed | 1 | [9 empty] | Bugani Consstruction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Ifugao | 220009 | Mabanutan ES | ALFONSO LISTA (POTIA) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2626910.96 |  |  | Completed | 1 | [9 empty] | 8J Builders and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135775 | Malalupa ES | ALFONSO LISTA (POTIA) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2665000.28 |  |  | Completed | 1 | [9 empty] | 8J Builders and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 305187 | Namillangan NHS | ALFONSO LISTA (POTIA) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2806710.52 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Ifugao | 135778 | Ngileb ES | ALFONSO LISTA (POTIA) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2632042.14 |  |  | Completed | 1 | [9 empty] | 8J Builders and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135810 | Anaba ES | BANAUE | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2729730.21 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 135939 | Talboc ES | MAYOYAO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3347305.7 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 305199 | Balbalan Agricultural and Industrial School | BALBALAN | 0 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 8495116.03 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 135963 | Balbalan ES | BALBALAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3570787.83 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 135980 | Sadsadan Primary School | BALBALAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3972819.5 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 135981 | Salegseg Comm. Sch. | BALBALAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3650349.94 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 135984 | Talalang Elementary School | BALBALAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3658074.03 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 340131 | SHS in Lubuagan, Kalinga | LUBUAGAN | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3417538.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Kalinga | 136013 | Ableg ES | PASIL | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3762752.47 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 220513 | Balinciagao ES - Limood Annex | PASIL | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3759633.74 |  | 3666467.94 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 305215 | Batong Buhay National High School | PASIL | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3669886.31 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 305213 | Pasil National High School | PASIL | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3489407.13 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136043 | Bayao Elementary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3226000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136040 | Camalog Elementary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3152000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136038 | Wagud Elementary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3267000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136079 | San Pedro Elementary School | RIZAL (LIWAN) | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3236000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136121 | Darulog Elementary School | TANUDAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3337000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 305220 | Bangad National High School | TINGLAYAN | 0 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 9201918.74 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 305221 | Bangad National High School | TINGLAYAN | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 4351312.57 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Kalinga | 305208 | Southern Tinglayan National High School | TINGLAYAN | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3928010.22 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Tabuk City | 220524 | Bulo West ES - Burobor Annex | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3223729.25 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 220532 | Kalinga Special Education Center | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3129297.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 220520 | Madapdappig Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3023729.25 |  |  | Reverted | 0 | [10 empty] | The project already delisted in the PCMA. The contract was terminated due to no site. | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2017 | CAR | Tabuk City | 305207 | Nambucayan National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3438729.25 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305106 | Apayao National Industrial Agricultural High School | CALANASAN (BAYAG) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3834861.47 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305106 | Apayao National Industrial Agricultural High School | CALANASAN (BAYAG) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3345373.58 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305106 | Apayao National Industrial Agricultural High School | CALANASAN (BAYAG) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3345373.58 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305106 | Apayao National Industrial Agricultural High School | CALANASAN (BAYAG) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3745373.58 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305122 | Pio Dalim Memorial SAT Main | CALANASAN (BAYAG) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3691400.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305122 | Pio Dalim Memorial SAT Main | CALANASAN (BAYAG) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3601912.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 318811 | Sta.Filomena School of Arts and Trade | CALANASAN (BAYAG) | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6217999.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 318811 | Sta.Filomena School of Arts and Trade | CALANASAN (BAYAG) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3508999.96 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 318811 | Sta.Filomena School of Arts and Trade | CALANASAN (BAYAG) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3121045.96 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 318804 | tanglagan national high school | CALANASAN (BAYAG) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3689400.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 318804 | tanglagan national high school | CALANASAN (BAYAG) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3599912.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 318804 | tanglagan national high school | CALANASAN (BAYAG) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6399825.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 318808 | Allig National Agricultural and Trade HS | FLORA | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3671218.23 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 318808 | Allig National Agricultural and Trade HS | FLORA | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6363460.68 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 318808 | Allig National Agricultural and Trade HS | FLORA | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3581730.34 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3163547.76 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3653035.65 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6327095.52 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 7127095.52 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305107 | Apayao Science High Shool | LUNA | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6133999.96 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305107 | Apayao Science High Shool | LUNA | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6933999.96 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305195 | Agbannawag National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 5530670.34 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305195 | Agbannawag National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 11004899.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305195 | Agbannawag National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 11205899.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 319104 | Bado Dangwa National High School | CITY OF TABUK (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2765335.16 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Tabuk City | 319104 | Bado Dangwa National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 15956548.33 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 319104 | Bado Dangwa National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 11004899.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 136162 | Bullaguian ES | CITY OF TABUK (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 4469993.4 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Tabuk City | 305205 | Kalinga National High School | CITY OF TABUK (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2790463.4 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Tabuk City | 305205 | Kalinga National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 16156548.33 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305205 | Kalinga National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 16156548.33 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305212 | Nambaran Agro-Industrial National High School | CITY OF TABUK (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2790460.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Tabuk City | 305212 | Nambaran Agro-Industrial National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 11205899.85 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305212 | Nambaran Agro-Industrial National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 11205899.85 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 136010 | San Juan Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3083729.25 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 136165 | Tuliao Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3023729.25 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Abra | 305082 | Cristina B. Gonzales MHS | BUCAY | 0 | 1 | 9 | 3STY9CL | BATCH 12 | 204000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2017 | CAR | Abra | 134994 | Dugong ES | BUCAY | 0 | 1 | 8 | 2- 2STY4CL | BATCH 12 | 17324634 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | CAR | Abra | 305105 | Western Abra NHS | DANGLAS | 0 | 1 | 6 | 3STY6CL | BATCH 12 | 13251000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | CAR | Abra | 218521 | Lourdes Zapata PS | DOLORES | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2771000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Abra | 135023 | Taping ES | DOLORES | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2771000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Abra | 135033 | La Paz CS | LA PAZ | 0 | 1 | 8 | 2- 2STY4CL | BATCH 12 | 17342400 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | CAR | Abra | 305087 | Langiden NHS | LANGIDEN | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 8620301.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Abra | 318702 | Penarrubia Integrated School | PEÑARRUBIA | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 8594490 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Abra | 305101 | Suyo National High School | PIDIGAN | 0 | 1 | 6 | 3STY6CL | BATCH 12 | 13213000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | CAR | Abra | 305091 | Northern Abra NHS | SAN JUAN | 0 | 1 | 6 | 2STY6CL | BATCH 12 | 11345000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | CAR | Abra | 305099 | San Quintin NHS | SAN QUINTIN | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 8725990.52 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Abra | 305103 | Tiempo NHS | TUBO | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9071702.49 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Abra | 135165 | Tamac ES | VILLAVICIOSA | 0 | 1 | 6 | 3- 1STY2CL | BATCH 12 | 8940000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | CAR | Baguio City | 136403 | Apolinario Mabini ES | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17359569.97 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | CAR | Baguio City | 305271 | Bakakeng National High School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 18159569.97 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | CAR | Baguio City | 319304 | BCNHS, Hillside Ext. | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17659570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | CAR | Benguet | 305134 | Binga National High School | ITOGON | 0 | 1 | 2 | 2STOREY 2 SCIENCE LAB | BATCH 12 | 8555554.33 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Benguet | 305134 | Binga National High School | ITOGON | 0 |  | 2 | 2STOREY 2 ICT LAB | BATCH 12 | 8555554.33 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Benguet | 305142 | Laurencio Fianza NHS - Main | ITOGON | 0 | 1 | 2 | 2STY2 SCIENCE LAB | BATCH 12 | 8745476.4 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Benguet | 305145 | Kamora National High School | KABAYAN | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 8755681.55 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Benguet | 305161 | Taloy Sur NHS | TUBA | 0 | 1 | 2 | 2STY 1 SCIENCE LAB 1 ICT LAB | BATCH 12 | 8556171.82 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Benguet | 305161 | Taloy Sur NHS | TUBA | 0 |  | 2 | 2STY 1 SCIENCE LAB 1 ICT LAB | BATCH 12 | 8556171.82 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Benguet | 305162 | Tublay School of Home Industries-Main | TUBLAY | 0 | 1 | 2 | 2STY2CL | BATCH 12 | 5853411.72 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Benguet | 305162 | Tublay School of Home Industries-Main | TUBLAY | 0 |  | 2 | 2STY2CL | BATCH 12 | 5853411.72 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Benguet | 305162 | Tublay School of Home Industries-Main | TUBLAY | 0 |  | 2 | 2STY2CL | BATCH 12 | 5853411.72 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Ifugao | 305182 | Kiangan NHS | KIANGAN | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 8997200 |  |  | Completed | 1 | [9 empty] | Southland Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Ifugao | 135880 | Boliwong ES | LAGAWE (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9447400 |  |  | Completed | 1 | [9 empty] | Verdant Mountain Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Ifugao | 135883 | Caba ES | LAGAWE (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9293100 |  |  | Completed | 1 | [9 empty] | Linsco Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Ifugao | 135895 | Alupapan ES | LAMUT | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9411200 |  |  | Completed | 1 | [9 empty] | Mac Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Ifugao | 135901 | Jolowon ES | LAMUT | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9700800 |  |  | Completed | 1 | [9 empty] | Jan Alexis Builder and Developer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Ifugao | 220003 | Lucban Elementary School | LAMUT | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9376800 |  |  | Completed | 1 | [9 empty] | Jovic Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Ifugao | 135908 | Nunhabatan ES | LAMUT | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9260900 |  |  | Completed | 1 | [9 empty] | Carlyz Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Ifugao | 135911 | Pugol Elementary School | LAMUT | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9303500 |  |  | Completed | 1 | [9 empty] | Dennise John Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Ifugao | 135944 | Cocoy ES (Cudiaman) | TINOC | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 10955600 |  |  | Completed | 1 | [9 empty] | Southland Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Ifugao | 220028 | DENGAO PS | TINOC | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 10501600 |  |  | Completed | 1 | [9 empty] | Mac Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Abra | 305075 | Abra HS | BANGUED (Capital) | 0 | 1 | 12 | 4STY12CL | BATCH 13 | 31649789 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2017 | CAR | Abra | 318701 | MARC YSRAEL B. BERNOS MEMORIAL NATIONAL HIGH SCHOOL | LA PAZ | 0 | 1 | 6 | 3STY6CL | BATCH 13 | 12991000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | CAR | Abra | 305094 | Pulot National High School | LAGAYAN | 0 | 1 | 12 | 2- 3STY6CL | BATCH 13 | 26534000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2017 | CAR | Abra | 305076 | Baay National High School | LICUAN-BAAY (LICUAN) | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 8859797.67 |  | 8266701.06 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Abra | 305101 | Suyo National High School | PIDIGAN | 0 | 1 | 6 | 2STY6CL | BATCH 13 | 11345000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | CAR | Abra | 305091 | Northern Abra NHS | SAN JUAN | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 8657451.71 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Abra | 135024 | Tayum CS | TAYUM | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 8576700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Apayao | 135234 | Kabugawan PS | CALANASAN (BAYAG) | 0 | 1 | 3 | 1STY3CL | BATCH 13 | 4231402.87 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Apayao | 135236 | Macalino PS | CALANASAN (BAYAG) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3088254.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135239 | Milagrosa ES | CALANASAN (BAYAG) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2943254.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135240 | Naguilian Norte PS | CALANASAN (BAYAG) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3038254.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135243 | Ninoy Aquino Elementary School | CALANASAN (BAYAG) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3038254.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135244 | Parina PS | CALANASAN (BAYAG) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2938254.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135252 | Allangigan ES | CONNER | 0 | 1 | 4 | 1STY4CL | BATCH 13 | 5335539.96 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Apayao | 219006 | Apaya PS | CONNER | 0 | 1 | 3 | 1STY2CL | BATCH 13 | 3111923.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Apayao | 135253 | Banban ES | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2848134.16 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135257 | Caglayan ES | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2841532.72 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135274 | Catub Primary School | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2865365 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 318803 | Conner Central NHS Cupis Annex | CONNER | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 3050000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 318812 | Conner Central NHS Ili Annex | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2865038.87 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305111 | Conner Central NHS Main | CONNER | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 6369218.94 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305111 | Conner Central NHS Main | CONNER | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5950000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135259 | Conner CS | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2857436.3 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305112 | Conner Natl. HS | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2823440.31 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 219025 | Cubet PS | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2851301.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135261 | Daga ES | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2972165.06 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135267 | Gassud ES | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2828352.11 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305114 | Gov. Benjamin Leguiab, Sr. Mem. NHS Main | CONNER | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 6470547.34 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305114 | Gov. Benjamin Leguiab, Sr. Mem. NHS Main | CONNER | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 6060000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135255 | Guedeged ES | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2959137.85 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135262 | Guina-ang ES | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2885429.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 219020 | Mabiga Elementary School | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2918281.01 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135270 | Manag ES | CONNER | 0 | 1 | 3 | 1STY3CL | BATCH 13 | 4086632.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Apayao | 135280 | Talifugo ES | CONNER | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2915520.3 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135282 | Allig ES | FLORA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2918254.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135286 | Bagutong ES | FLORA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2838254.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135288 | Balluyan ES | FLORA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2888254.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135294 | Mallig ES | FLORA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2968255.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135292 | Sta. Maria ES | FLORA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3018255.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135297 | Badduat ES | KABUGAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2917156.08 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135298 | Baliwanan ES | KABUGAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3653526.66 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135303 | Dagara ES | KABUGAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3731163.06 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 305115 | Kabugao Agro-Ind'l. HS | KABUGAO (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 3229946.37 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 305115 | Kabugao Agro-Ind'l. HS | KABUGAO (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 3150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 135307 | Kabugao CS | KABUGAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2939572.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 318806 | Kabugao National High School | KABUGAO (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 3233682.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 318806 | Kabugao National High School | KABUGAO (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 3135000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Apayao | 135308 | Kadikitan ES | KABUGAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3664673.55 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135313 | Lenneng ES | KABUGAO (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 9780858.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Apayao | 135318 | Lucab ES | KABUGAO (Capital) | 0 | 1 | 4 | 1STY2CL | BATCH 13 | 3779420.47 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Apayao | 135320 | Madduang ES | KABUGAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3129746.94 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135322 | Malabanig ES | KABUGAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3246659.83 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 319010 | Mayor Bartolome Serut NATHS Annex | KABUGAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3174435.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135324 | Musimut ES | KABUGAO (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 13 | 4192376.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Apayao | 135325 | Nagbabalayan ES | KABUGAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3565147.16 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 220025 | Paco Valley PS | KABUGAO (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2942436.35 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135334 | Catammoyoan ES | LUNA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2898254.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135336 | Luna CS | LUNA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2788255.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135353 | Dona Loreta ES | PUDTOL | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2838255.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135356 | Mataguisi ES | PUDTOL | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2938255.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Apayao | 135363 | Emiliana ES | SANTA MARCELA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2913255.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Baguio City | 340055 | Baguio City National Science High School (Senior High School-Stand Alone) | BAGUIO CITY | 0 | 1 | 6 | 4STY- 2 Science lab, 2 Regular Workshop and 2 ICT Lab | BATCH 13 | 42350046.32 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | CAR | Baguio City | 340055 | Baguio City National Science High School (Senior High School-Stand Alone) | BAGUIO CITY | 0 |  | 6 | 4STY- 2 Science lab, 2 Regular Workshop and 2 ICT Lab | BATCH 13 | 42350046.32 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
NEWCON 2017 | CAR | Baguio City | 136393 | Bonifacio Elementary school | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | BATCH 13 | 17169570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | CAR | Baguio City | 305282 | Guisad Valley National High School | BAGUIO CITY | 0 | 1 | 8 | 4STY- 4 regular Wokshop and 4 science lab | BATCH 13 | 34319141.34 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | CAR | Baguio City | 305282 | Guisad Valley National High School | BAGUIO CITY | 0 |  | 8 | 4STY- 4 regular Wokshop and 4 science lab | BATCH 13 | 34319141.34 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
NEWCON 2017 | CAR | Baguio City | 305280 | Irisan National High School | BAGUIO CITY | 0 | 1 | 4 | 4STY- 2 Science lab and 2 ICT Lab | BATCH 13 | 17359570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Baguio City | 305280 | Irisan National High School | BAGUIO CITY | 0 |  | 4 | 4STY- 2 Science lab and 2 ICT Lab | BATCH 13 | 17359570.67 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2017 | CAR | Baguio City | 305284 | Joaquin Smith National High School | BAGUIO CITY | 0 | 1 | 4 | 4STY- 2 Science lab and 2 Regular Workshop | BATCH 13 | 17759570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Baguio City | 305284 | Joaquin Smith National High School | BAGUIO CITY | 0 |  | 4 | 4STY- 2 Science lab and 2 Regular Workshop | BATCH 13 | 17759570.67 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2017 | CAR | Baguio City | 305283 | Magsaysay National High School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | BATCH 13 | 18159570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | CAR | Baguio City | 136414 | Manuel L. Quezon Elementary School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | BATCH 13 | 17169570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | CAR | Baguio City | 305275 | Mil-an National High School | BAGUIO CITY | 0 | 1 | 4 | 4STY- 2 Science lab and 2 ICT Lab | BATCH 13 | 17459570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Baguio City | 305275 | Mil-an National High School | BAGUIO CITY | 0 | 1 | 4 | 4STY- 2 Science lab and 2 ICT Lab | BATCH 13 | 17459570.67 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2017 | CAR | Baguio City | 305286 | PINGET NATIONAL HIGH SCHOOL | BAGUIO CITY | 0 | 1 | 12 | 4STY12CL | BATCH 13 | 32249788.72 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2017 | CAR | Baguio City | 305287 | Quezon Hill National High School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | BATCH 13 | 17659570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | CAR | Baguio City | 305276 | Rizal National High School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | BATCH 13 | 17259570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | CAR | Baguio City | 136389 | San Carlos Heights Elementary School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | BATCH 13 | 17559570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | CAR | Baguio City | 305278 | San Vicente National High School (Integrated Senior High School) | BAGUIO CITY | 0 | 1 | 4 | 4STY- 2 Science lab and 2 ICT Lab | BATCH 13 | 19159570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | CAR | Baguio City | 305278 | San Vicente National High School (Integrated Senior High School) | BAGUIO CITY | 0 |  | 4 | 4STY- 2 Science lab and 2 ICT Lab | BATCH 13 | 19159570.67 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2017 | CAR | Baguio City | 305279 | Sto. Tomas National High School | BAGUIO CITY | 0 | 1 | 6 | 4STY- 2 Science lab, 2 Regular Workshop and 2 ICT Lab | BATCH 13 | 38910737.96 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | CAR | Baguio City | 305279 | Sto. Tomas National High School | BAGUIO CITY | 0 |  | 6 | 4STY- 2 Science lab, 2 Regular Workshop and 2 ICT Lab | BATCH 13 | 38910737.96 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
NEWCON 2017 | CAR | Kalinga | 135959 | Ab-abaan Elementary School | BALBALAN | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 4528080.1 |  | 4433932.94 | Completed | 1 | [10 empty] | for final inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 135986 | Ubual Elementary School | BALBALAN | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 4803090.56 |  | 4717055.73 | Completed | 1 | [10 empty] | for final inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 305227 | Western Kalinga National High School | BALBALAN | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 4803090.56 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 135991 | Latawan PS | LUBUAGAN | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 3648370.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 220506 | Roadside Elementary School | LUBUAGAN | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 3627164.68 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 135997 | Sukiap PS | LUBUAGAN | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 4264087.35 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136015 | Balatoc Elementary School | PASIL | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 4538831.41 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136016 | Batong Buhay Elementary School | PASIL | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 3469538.53 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136022 | Colayo Elementary School | PASIL | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 5152125.4 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136024 | Dangtalan ES | PASIL | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 3376276.75 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136025 | Galdang ES | PASIL | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 3911119.03 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 220527 | Aguimitan Primary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 4563000 |  | 4474531.55 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136034 | Asibanglan Elementary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 4200000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 319112 | Asibanglan National High School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 4200000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136036 | Ballayangon Elementary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 4477000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136037 | Bonnong Primary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 4220000 |  | 4115029.22 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136035 | Lutab Primary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 4418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136049 | Malaap Elementary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3729000 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2017 | CAR | Kalinga | 136054 | Pakawit Elementary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3190000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136057 | Pinukpuk CS | PINUKPUK | 0 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 5409008 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Kalinga | 305216 | Pinukpuk Vocational School | PINUKPUK | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3397000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Kalinga | 136060 | Sagsag Primary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3594000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 319103 | Tappo Vocational High School | PINUKPUK | 0 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4195000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Kalinga | 136074 | Macutay Elementary School | RIZAL (LIWAN) | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3135000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 305218 | Macutay Palao National High School | RIZAL (LIWAN) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2836000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Kalinga | 305217 | Rizal National School of Arts & Trades | RIZAL (LIWAN) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3444000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Kalinga | 319114 | Rizal National School of Arts & Trades-Santor Annex | RIZAL (LIWAN) | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3317000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136077 | Romualdez Elementary School | RIZAL (LIWAN) | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3479000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 220530 | Babbanoy Elementary School | TANUDAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3686000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136124 | Gaang Elementary School | TANUDAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3693000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136125 | Liyang Elementary School | TANUDAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3787000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136126 | Lubo Elementary School | TANUDAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3797000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136131 | Mangali Centro Elementary School | TANUDAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 4042000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 319106 | Taloctoc General Comprehensive National High School | TANUDAN | 0 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4691000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | CAR | Kalinga | 305225 | Tanudan Vocational School | TANUDAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3395344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136133 | Bangad Centro Elementary School | TINGLAYAN | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 3432813.48 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 319115 | Kalinga NHS- Ambato Tinglayan Annex | TINGLAYAN | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 3698271.74 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136144 | Loccong Elementary School | TINGLAYAN | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 3902284.11 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 136148 | Ngibat Elementary School | TINGLAYAN | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 3766389.01 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Kalinga | 305208 | Southern Tinglayan National High School | TINGLAYAN | 0 | 1 | 1 | 1STY1CL Regular Workshop | BATCH 13 | 3423802.6 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2017 | CAR | Kalinga | 136149 | Sumadel Elementary School | TINGLAYAN | 0 | 1 | 2 | 1STY2CL w/ CR | BATCH 13 | 3920270.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305203 | Cudal National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 16156548.33 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305203 | Cudal National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 16156548.33 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305203 | Cudal National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 16156548.33 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305203 | Cudal National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 16156548.33 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305222 | New Tanglag National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 11205899.84 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305222 | New Tanglag National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 11205899.85 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305222 | New Tanglag National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 11205899.85 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 11405899.84 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 11405899.84 |  |  | Reverted | 0 | [10 empty] | Site Issue | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2017 | CAR | Tabuk City | 305226 | TUGA NATIONAL HIGH SCHOOL | CITY OF TABUK (Capital) | 0 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 11405899.84 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305226 | TUGA NATIONAL HIGH SCHOOL | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 11405899.84 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305226 | TUGA NATIONAL HIGH SCHOOL | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 11405899.84 |  |  | Completed | 1 | [10 empty] | Finishing works and Issuance of Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305226 | TUGA NATIONAL HIGH SCHOOL | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 11405899.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305226 | TUGA NATIONAL HIGH SCHOOL | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 11405899.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | CAR | Tabuk City | 305226 | TUGA NATIONAL HIGH SCHOOL | CITY OF TABUK (Capital) | 0 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 11405899.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Abra | 305074 | Abas Nhs | Sallapadan | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Abra | 305075 | Abra Hs | Bangued (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6435000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Abra | 135198 | Anayan Elementary School | Tineg | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2640828.124 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | CAR | Abra | 135053 | Bonglo Ps | Licuan-Baay (Licuan) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2640828.124 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | CAR | Abra | 305080 | Capitan Nhs | Daguioman | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Abra | 305081 | Cayapa Nhs | Lagangilang | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Abra | 135206 | Cogon Elementary School | Tineg | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2640828.124 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | CAR | Abra | 305089 | Luzong Nhs | Luba | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Abra | 135216 | Makingag Primary School | Tineg | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2640828.124 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | CAR | Abra | 135123 | Manayday Es | San Isidro | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2640828.124 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | CAR | Abra | 318701 | Marc Ysrael B. Bernos Memorial National High School | La Paz | 0 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6435000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Abra | 305092 | Pangtod Nhs | Bucay | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Abra | 305097 | San Isidro Nhs | San Isidro | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Abra | 305100 | Supo Nhs | Tubo | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Apayao | 135252 | Allangigan Es | Conner | 0 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3664886.575 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 318808 | Allig National Agricultural And Trade Hs | Flora | 0 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8514965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | CAR | Apayao | 305106 | Apayao National Industrial Agricultural High School | Calanasan (Bayag) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2700000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Apayao | 305106 | Apayao National Industrial Agricultural High School | Calanasan (Bayag) | 0 | 1 | 12 | 3STY12CL | BATCH 7 CL | 20053453.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | CAR | Apayao | 305107 | Apayao Science Hs | Luna | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 135228 | Assat Elementary School | Calanasan (Bayag) | 0 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1964740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Apayao | 305108 | Bac-Da National High School | Luna | 0 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8464965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | CAR | Apayao | 305108 | Bac-Da National High School | Luna | 0 |  | 6 | 2STY6CL | BATCH 3 CL | 8464965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | CAR | Apayao | 305110 | Calanasan Nhs | Calanasan (Bayag) | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6669337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 318803 | Conner Central Nhs Cupis Annex | Conner | 0 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11302342.5917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | CAR | Apayao | 318807 | Conner Central Nhs Guina-Ang Annex Iii | Conner | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6519337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 318812 | Conner Central Nhs Ili Annex | Conner | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 305111 | Conner Central Nhs Main | Conner | 0 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8514965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | CAR | Apayao | 135259 | Conner Central School | Conner | 0 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1914740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Apayao | 219025 | Cubet Ps | Conner | 0 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1914740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Apayao | 135233 | Ferdinand Ps | Calanasan (Bayag) | 0 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1964740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Apayao | 305113 | Flora National High School | Flora | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 318813 | Gov. Benjamin Laguiab, Sr. Mnhs Sacpil Annex | Conner | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6487200 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 305114 | Gov. Benjamin Leguiab, Sr. Mem. Nhs Main | Conner | 0 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8514965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | CAR | Apayao | 318806 | Kabugao Agro-Ind'L. Hs - Lenneng Annex | Kabugao (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15471327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | CAR | Apayao | 305115 | Kabugao Agro-Ind'L. Hs Main | Kabugao (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15471327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | CAR | Apayao | 305115 | Kabugao Agro-Ind'L. Hs Main | Kabugao (Capital) | 0 |  | 4 | 2STY4CL | BATCH 3 CL | 6469337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 135316 | Kalliat Elementary School | Kabugao (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6687200 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 305116 | Luna National High School Main | Luna | 0 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8464965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | CAR | Apayao | 318801 | Luna Nhs - Tumog Annex | Luna | 0 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8464965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | CAR | Apayao | 219018 | Mabaguio Ps | Conner | 0 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1914740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Apayao | 305118 | Mataguisi Comp. Hs Main | Pudtol | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6569337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 305120 | Mayor Guillermo A.Barsatan Memorial School Of Arts And Tarde | Santa Marcela | 0 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14915090.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | CAR | Apayao | 305120 | Mayor Guillermo A.Barsatan Memorial School Of Arts And Tarde | Santa Marcela | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2600000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Apayao | 305121 | Mayor Ricardo De San Jose, Sr. Comp. Hs | Flora | 0 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15471327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | CAR | Apayao | 318804 | Pio Da Lim Memorial Sat Tanglagan | Calanasan (Bayag) | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6537200 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 318804 | Pio Da Lim Memorial Sat Tanglagan | Calanasan (Bayag) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2610000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Apayao | 305122 | Pio Dalim Memorial Sat Main | Calanasan (Bayag) | 0 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8575100 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | CAR | Apayao | 305122 | Pio Dalim Memorial Sat Main | Calanasan (Bayag) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2610000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Apayao | 318811 | Pio Dalim Memorial Sat-Sta.Filomena | Calanasan (Bayag) | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 305123 | Pudtol Nhs | Pudtol | 0 | 1 | 12 | 3STY12CL | BATCH 3 CL | 18672268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | CAR | Apayao | 305123 | Pudtol Nhs | Pudtol | 0 |  | 2 | 1STY2CL | BATCH 3 CL | 1914740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Apayao | 305109 | Sta. Marcela Nhs | Santa Marcela | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Apayao | 219027 | Upper Swan Ps | Pudtol | 0 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1914740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Baguio City | 305269 | Baguio City National High School - Main | Baguio City | 0 | 1 | 20 | 4STY20CL | BATCH 1 CL | 32282747.79 |  |  | Completed | 1 |  |  | P00070001LZ_CW1 | 16PD0009 | 2016-02-02 | 2016-02-05 | 2016-02-23 | 2016-05-12 | 42514 | JOMARCANN GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | CAR | Baguio City | 305269 | Baguio City National High School - Main | Baguio City | 0 |  | 8 | 4STY8CL | BATCH 1 CL | 16103682.68 |  |  | Completed | 1 |  |  | P00070002LZ_CW1 | 16PD0010 | 2016-02-02 | 2016-02-05 | 2016-02-23 | 2016-05-11 | 42513 | JOMARCANN GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | CAR | Baguio City | 305269 | Baguio City National High School - Main | Baguio City | 0 |  | 12 | 4STY12CL | BATCH 1 CL | 22460158.98 |  |  | Completed | 1 |  |  | P00070003LZ_CW1 | 16PD0011 | 2016-04-01 | 2016-04-08 | 2016-04-22 | 2016-05-16 | 42515 | R.U. AQUINO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | CAR | Baguio City | 305282 | Guisad Valley National High School | Baguio City | 0 | 1 | 24 | 4STY24CL | BATCH 9 CL | 35980257.14 |  |  | Completed | 1 |  |  | P00072671LZ_CW1 |  | 2016-07-29 | 2016-08-05 | 2016-08-19 |  | 42668 | NORTHERN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | CAR | Baguio City | 305284 | Joaquin Smith National High School | Baguio City | 0 | 1 | 8 | 4STY8CL | BATCH 5 CL | 15113518.84 |  |  | Completed | 1 |  |  | P00070823LZ_CW1 | 16PD0019 | 2016-02-18 | 2016-02-26 | 2016-03-10 | 2016-05-12 | 42514 | JOMARCANN GENERAL CONSTRUCTION/GREATZONE ENTERPRISES (J.V.) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | CAR | Baguio City | 221501 | Kias Elementary School | Baguio City | 0 | 1 | 4 | 4STY4CL | BATCH 3 CL | 7523759.42 |  |  | Completed | 1 |  |  | P00070253LZ_CW1 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Baguio City | 305275 | Mil-An National High School | Baguio City | 0 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15090556.7045 |  |  | Completed | 1 |  |  | P00072672LZ_CW1 |  | 2016-07-29 | 2016-08-05 | 2016-08-19 |  | 42668 | KUATAKO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | CAR | Baguio City | 305275 | Mil-An National High School | Baguio City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417461.96 |  |  | Completed | 1 |  |  | P00074357LZ_CW1 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Baguio City | 136390 | San Luis Elementary School | Baguio City | 0 | 1 | 4 | 4STY4CL | BATCH 3 CL | 7523759.42 |  |  | Completed | 1 |  |  | P00070254LZ_CW1 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Baguio City | 305279 | Sto. Tomas National High School | Baguio City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2467461.96 |  |  | Completed | 1 | [8 empty] | 42666 | CCCORTEZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Baguio City | 340055 | Shs In Irisan, Baguio City | Baguio City | 1 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00070823LZ_CW1 | 16PD0020 | 2016-02-18 | 2016-02-26 | 2016-03-10 | 2016-05-12 | 42514 | R.U. AQUINO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | CAR | Benguet | 305125 | Alejo M. Pacalso Memorial National High School | Itogon | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11056980.07 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | CAR | Benguet | 305133 | Benguet National High School-Main | La Trinidad (Capital) | 0 | 1 | 24 | 4STY24CL | BATCH 11 CL | 37096257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | CAR | Benguet | 305154 | Madaymen National High School | Kibungan | 0 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10421033.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | CAR | Benguet | 305160 | Tuba Nhs (Nangalisan) | Tuba | 0 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15631203.07 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | CAR | Benguet | 305162 | Tublay School Of Home Industries-Main | Tublay | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24702577.982 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | CAR | Ifugao | 305168 | Ayangan National Agricultural & Vocational Hs | Lagawe (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2700828 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Ifugao | 305171 | Eastern Potia National High School | Alfonso Lista (Potia) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Ifugao | 305177 | Hapid Nhs - Bimpal Annex | Lamut | 0 | 1 | 20 | 4STY20CL | BATCH 5 CL | 34168780.69 |  |  | Completed | 1 |  |  |  |  | 2016-04-01 | 2016-04-11 | 2016-04-22 | 2016-05-16 | 42542 | ALFALFA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | CAR | Ifugao | 305183 | Lawig Nhs (Main) | Lamut | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 9206422.11 |  |  | Completed | 1 |  |  |  |  | 2016-04-01 | 2016-04-11 | 2016-04-22 | 2016-05-16 | 42542 | ALFALFA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | CAR | Ifugao | 305183 | Lawig Nhs (Main) | Lamut | 0 |  | 6 | 2STY6CL | BATCH 5 CL | 9205200.58 |  |  | Completed | 1 |  |  |  |  | 2016-04-01 | 2016-04-11 | 2016-04-22 | 2016-05-16 | 42542 | ALFALFA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | CAR | Ifugao | 135840 | Namulditan Es | Hingyon | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34388935.19 |  |  | Completed | 1 | [5 empty] | 2016-06-16 | 2016-06-27 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | CAR | Ifugao | 305188 | Pinto Nhs | Alfonso Lista (Potia) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2667236 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Ifugao | 305190 | Sta. Maria Nhs | Alfonso Lista (Potia) | 0 | 1 | 24 | 2STY12CL | BATCH 7 CL | 30321352.18 |  |  | Completed | 1 | [5 empty] | 2016-07-21 | 2016-08-02 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | CAR | Ifugao | 305190 | Sta. Maria Nhs | Alfonso Lista (Potia) | 0 |  | 8 | 2STY8CL | BATCH 7 CL | 11402811 |  |  | Completed | 1 | [5 empty] | 2016-07-21 | 2016-08-02 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | CAR | Ifugao | 305190 | Sta. Maria Nhs | Alfonso Lista (Potia) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2667236 |  |  | Completed | 1 | [5 empty] | 2016-07-21 | 2016-08-02 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Kalinga | 305216 | Pinukpuk Vocational School | Pinukpuk | 0 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31750000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | CAR | Kalinga | 305216 | Pinukpuk Vocational School | Pinukpuk | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4690000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Mt. Province | 319220 | Anonat National Agricultural And Vocational High School | Paracelis | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2860000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Mt. Province | 305230 | Bacarri National Trade & Agricultural School | Paracelis | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Mt. Province | 305242 | Eastern Bontoc Navhs | Barlig | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2790828 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Mt. Province | 305244 | Guinzadan National High School | Bauko | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Mt. Province | 305252 | Mt. Data National High School | Bauko | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Mt. Province | 305255 | Mt. Prov. Gen. Comprehensive Hs | Bontoc (Capital) | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24672577.982 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | CAR | Mt. Province | 136273SHS | Natonin Central School | Natonin | 0 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15682518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | CAR | Mt. Province | 305259 | Otucan-Bila National High School | Bauko | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Mt. Province | 305260 | Panabungen School Of Arts, Trades, And Home Industries | Besao | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2800000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Mt. Province | 305231 | Paracelis Technical & Vocational High School | Paracelis | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Mt. Province | 305262 | Pingad National High School | Sabangan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2790000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Mt. Province | 305263 | Sabangan National High School | Sabangan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2800000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Mt. Province | 305264 | Sadanga National High School | Sadanga | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2740000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Mt. Province | 305267 | Tadian School Of Arts & Trades | Tadian | 0 | 1 | 20 | 4STY20CL | BATCH 5 CL | 32082890.27 |  |  | Completed | 1 |  |  |  |  | 2016-03-03 | 2016-03-09 | 2016-03-21 | 2016-04-04 | 42500 | R.U. Aquino Const'n. & Dev't. Corp and JABEN Const'n., JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | CAR | Mt. Province | 305267 | Tadian School Of Arts & Trades | Tadian | 0 |  | 12 | 4STY12CL | BATCH 5 CL | 22884213.71 |  |  | Completed | 1 |  |  |  |  | 2016-03-03 | 2016-03-09 | 2016-03-21 | 2016-04-04 | 42500 | RAF General Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | CAR | Mt. Province | 305267 | Tadian School Of Arts & Trades | Tadian | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2750000 |  |  | Completed | 1 |  |  |  |  | 2016-05-20 | 2016-05-30 | 2016-06-10 | 2016-07-08 | 42565 | Tadian General Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Tabuk City | 305195 | Agbannawag National High School | City Of Tabuk (Capital) | 0 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13450000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | CAR | Tabuk City | 305195 | Agbannawag National High School | City Of Tabuk (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 3600000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Tabuk City | 319104 | Bado Dangwa National High School | City Of Tabuk (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | CAR | Tabuk City | 305198 | Balawag National High School | City Of Tabuk (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2924570 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | CAR | Tabuk City | 136096 | Cudal Es | City Of Tabuk (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1995632.7 |  |  | Completed | 1 | [8 empty] | Trinity Construction and Engineering |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Tabuk City | 305205 | Kalinga National High School | City Of Tabuk (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | CAR | Tabuk City | 305205 | Kalinga National High School | City Of Tabuk (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 3500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Tabuk City | 305205 | Kalinga National High School | City Of Tabuk (Capital) | 0 |  | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2700000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Tabuk City | 220532 | Kalinga Special Education Center | City Of Tabuk (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1845632.7 |  |  | Completed | 1 | [8 empty] | RMG Builders |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | CAR | Tabuk City | 305204 | Kalinga-Apayao State College Lab High School | City Of Tabuk (Capital) | 0 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22153000 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | CAR | Tabuk City | 305212 | Nambaran Agro-Industrial National High School | City Of Tabuk (Capital) | 0 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13450000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | CAR | Tabuk City | 305212 | Nambaran Agro-Industrial National High School | City Of Tabuk (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Tabuk City | 319117 | Naneng Nhs - Mosimos Extension | City Of Tabuk (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6550000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | CAR | Tabuk City | 220529 | San Pablo Ps | City Of Tabuk (Capital) | 0 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Tabuk City | 136111 | Sotto Es | City Of Tabuk (Capital) | 0 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | CAR | Tabuk City | 305221 | Tabuk City National High School | City Of Tabuk (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 32150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | CAR | Tabuk City | 305221 | Tabuk City National High School | City Of Tabuk (Capital) | 0 |  | 16 | 4STY16CL | BATCH 9 CL | 27150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | CAR | Tabuk City | 305221 | Tabuk City National High School | City Of Tabuk (Capital) | 0 |  | 8 | 4STY8CL | BATCH 9 CL | 15150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | CAR | Tabuk City | 305221 | Tabuk City National High School | City Of Tabuk (Capital) | 0 |  | 20 | 4STY20CL | BATCH 9 CL | 31150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | CAR | Tabuk City | 305226 | Tuga National High School | City Of Tabuk (Capital) | 0 | 1 | 8 | 4STY8CL | BATCH 3 CL | 16050000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | CAR | Abra | 134979 | Bangued West CS | BANGUED (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | CA0115S00010 | 15PA0077 | 2015-09-29 | 2015-10-01 | 2015-10-13 | 2015-10-20 | 2015-12-18 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Abra | 305078 | Boliney NHS | BOLINEY | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 7069338 |  |  | Completed | 1 |  |  | CA0115S00006 | 15PA0084 | 2015-10-14 | 2015-10-16 | 2015-10-29 | 2015-11-04 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Abra | 305080 | Capitan NHS | DAGUIOMAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2073606 |  |  | Completed | 1 |  |  | CA0115S00007 | 15PA0076 | 2015-09-30 | 2015-10-01 | 2015-10-13 | 2015-10-19 | 2015-11-17 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Abra | 305081 | Cayapa NHS | LAGANGILANG | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2013606 |  |  | Completed | 1 |  |  | CA0115S00008 | 15PA0075 | 2015-09-30 | 2015-10-01 | 2015-10-13 | 2015-10-19 | 2015-11-16 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Abra | 305082 | Cristina B. Gonzales MHS | BUCAY | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | Completed | 1 |  |  | CA0115S00001 | 15PA0045 | 2015-09-02 | 2015-09-04 | 2015-09-18 | 2015-09-28 | 2015-10-12 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Abra | 305090 | Mataragan NAS | MALIBCONG | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2488606.04 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Abra | 305090 | Mataragan NAS | MALIBCONG | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2488606.04 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Abra | 135126 | Olo ES | SAN ISIDRO | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2952592.44 |  |  | Completed | 1 |  |  | CA0115S00009 | 15PA0078 | 2015-09-29 | 2015-10-01 | 2015-10-13 | 2015-10-19 | 2015-11-16 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | CAR | Abra | 135106 | Pacpaca ES | LUBA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | Completed | 1 |  |  | CA0115S00011 | 15PA0083 | 2015-10-14 | 2015-10-16 | 2015-10-29 | 2015-11-04 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Abra | 305093 | Pilar Rural High School | PILAR | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8534965.051 |  |  | Completed | 1 |  |  | CA0115S00003 | 15PA0046 | 2015-08-17 | 2015-08-20 | 2015-09-01 | 2015-09-10 | 2015-11-03 | R.S. SEPIAN CONSTRUCTION & TRUCKING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Abra | 305096 | Rosalio Eduarte NHS | DOLORES | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6594337.6381 |  |  | Completed | 1 |  |  | CA0115S00002 | 15PA0039 | 2015-06-16 | 2015-06-20 | 2015-07-02 | 2015-09-10 | 2015-09-17 | R.S. SEPIAN CONSTRUCTION & TRUCKING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Abra | 305105 | Western Abra NHS | DANGLAS | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 |  |  | CA0115S00012 | 15PA0079 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-21 | 2015-11-20 | R.S. SEPIAN CONSTRUCTION & TRUCKING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Apayao | 135306 | Apadi ES | KABUGAO (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0715S00019 | 15PB0008 | 2015-12-07 |  |  |  |  | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Apayao | 219023 | Aurora PS | PUDTOL | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0715S00017 | 15PC0041 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-10-20 | 2015-11-09 | TRYST BUILDERS ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Apayao | 135263 | Buguit PS | CONNER | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0715S00013 | 15PB0008 | 2015-12-04 |  |  |  |  | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Apayao | 135256 | Buneg Elementary School | CONNER | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2158606.04 |  |  | Completed | 1 |  |  | CA0715S00012 | 15PB0008 | 2015-12-04 |  |  |  |  | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Apayao | 135265 | Ili ES | CONNER | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6769337.6381 |  |  | Completed | 1 |  |  | CA0715S00018 | 15PB0008 | 2015-12-15 |  |  |  |  | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Apayao | 219007 | Liwan Elementary School | CONNER | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0715S00015 | 15PB0008 | 2015-12-11 |  |  |  |  | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Apayao | 219009 | Lydia PS | PUDTOL | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0715S00011 | 15PC0041 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-10-20 | 2015-11-09 | TRYST BUILDERS ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Apayao | 135272 | Nabuangan PS | CONNER | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0715S00020 | 15PB0008 | 2015-12-08 |  |  |  |  | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Apayao | 135276 | Puguin ES | CONNER | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0715S00014 | 15PB0008 | 2015-12-08 |  |  |  |  | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Apayao | 219013 | San Jose ES | PUDTOL | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0715S00016 | 15PC0041 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-10-20 | 2015-11-09 | TRYST BUILDERS ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Apayao | 135251 | Tubongan ES | CALANASAN (BAYAG) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | Completed | 1 |  |  | CA0715S00010 | 15PC0036 | 2015-08-25 | 2015-08-26 | 2015-09-07 | 2015-09-16 | 2015-09-30 | B.A. LAGAZO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Baguio City | 221502 | Baguio Country Club ES | Baguio City | 0 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10417131.51 |  |  | Completed | 1 |  |  | CA0615S00004 | 15PD0052 | 2015-11-27 | 2015-11-27 | 2015-12-11 | 2015-12-22 |  | RAF GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Baguio City | 340055 | Proposed Stand-Alone SHS 1 | Baguio City | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31202890 |  |  | Completed | 1 |  |  | CA0615S00003 | 15PD0033 | 2015-10-20 | 2015-10-20 | 2015-11-03 | 2015-11-25 | 2015-12-01 | R.U. AQUINO CONSTRUCTION AND DEVELOPMENT CORP. (FO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | CAR | Benguet | 305146 | Adaoay National High School | KABAYAN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305126 | Ampucao National High School | ITOGON | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305128 | Ampusongan NHS | BAKUN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 318913 | Ampusongan NHS - Kayapa Ext. | BAKUN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 135540 | Anchokey PS | KABAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2118606.04 |  |  | Completed | 1 |  |  | CA0215S00014 | 15PE0033 | 2015-12-03 | 2015-12-14 | 2015-12-15 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305129 | Atok NHS | ATOK | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | CA0215S00009 | 15PF0038 | 2015-08-24 | 2015-09-01 | 2015-09-14 | 2015-09-28 | 2015-10-09 | DJY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Benguet | 305130 | Atok NHS - Caliking Annex | ATOK | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305131 | Bakun NHS | BAKUN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305152 | Balili NHS | MANKAYAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | CA0215S00003 | 15PF0037 | 2015-08-24 | 2015-09-01 | 2015-09-14 | 2015-09-28 | 2015-10-09 | SISSI-IT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Benguet | 318902 | Bangao NHS | BUGUIAS | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 135546 | Batan ES | KABAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2118606.04 |  |  | Completed | 1 |  |  | CA0215S00027 | 15PE0033 | 2015-12-03 | 2015-12-14 | 2015-12-15 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 219528 | Batanes Primary School | BAKUN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | CA0215S00023 | CA02-15-S-00023(CNTR) | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305132 | Bedbed NHS | MANKAYAN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305133 | Benguet NHS | LA TRINIDAD (Capital) | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | CA0215S00010 | 15PE0019 | 2015-10-06 | 2015-10-07 | 2015-10-20 | 2015-11-11 | 2015-11-27 | JV: 3K ROCK ENGINEERING/FIAT CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Benguet | 305134 | Binga NHS | ITOGON | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 318901 | Bokod NHS - Daclan Extension | BOKOD | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305135 | BOKOD NHS - MAIN | BOKOD | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | Completed | 1 |  |  | CA0215S00008 | 15PE0019 | 2015-10-06 | 2015-10-07 | 2015-10-20 | 2015-11-11 | 2015-11-27 | JV: 3K ROCK ENGINEERING/FIAT CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Benguet | 305136 | Buguias NHS | BUGUIAS | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305156 | Bulalacao NHS | MANKAYAN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 219507 | Bunagan Primary School | BOKOD | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | CA0215S00020 | 15PE0033 | 2015-12-03 | 2015-12-14 | 2015-12-15 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305139 | Cabiten NHS (RA9087) | MANKAYAN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305137 | Catlubong National High School | BUGUIAS | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6669338 |  |  | Completed | 1 |  |  | CA0215S00028 | 15PF0040 | 2015-08-24 | 2015-09-04 | 2015-09-14 | 2015-10-14 | 2015-10-26 | SISSI-IT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Benguet | 135477 | Catlubong-Adiston ES | BUGUIAS | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6469337.6381 |  |  | Completed | 1 |  |  | CA0215S00025 | CA02-15-S-00025(CNTR) | 2015-11-29 | 2015-12-01 | 2015-12-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Benguet | 305140 | Cordillera Regional Science HS | LA TRINIDAD (Capital) | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 219503 | Deccan PS | BUGUIAS | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | Completed | 1 |  |  | CA0215S00016 | CA02-15-S-00016(CNTR) | 2015-11-29 | 2015-12-01 | 2015-12-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Benguet | 318909 | Eastern La Trinidad NHS | LA TRINIDAD (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | CA0215S00007 | 15PE0019 | 2015-10-06 | 2015-10-07 | 2015-10-20 | 2015-11-11 | 2015-11-27 | JV: 3K ROCK ENGINEERING/FIAT CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Benguet | 305141 | Evelio Javier Memorial NHS | TUBA | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 318914 | Evelio Memorial NHS - Annex, Ansagan | TUBA | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305159 | Fianza Mem'l NHS - Tinongdan | ITOGON | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305143 | Gov. Bado Dangwa Agro-Industrial School | KAPANGAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | Completed | 1 |  |  | CA0215S00006 | 15PF0036 | 2015-10-04 | 2015-10-12 | 2015-10-30 | 2015-11-19 | 2015-12-01 | MOUNTAINEERS ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Benguet | 318908 | Gov. Bado Dangwa Agro-Industrial School Extension - Taba-ao Annex | KAPANGAN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305144 | Guinaoang NHS | MANKAYAN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305145 | Kamora NHS | KABAYAN | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | CA0215S00005 | 15PE0019 | 2015-10-06 | 2015-10-07 | 2015-10-20 | 2015-11-11 | 2015-11-27 | JV: 3K ROCK ENGINEERING/FIAT CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Benguet | 305147 | Kapangan Central NHS (RA8841) | KAPANGAN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 219514 | Karao Tribe ES | BOKOD | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | CA0215S00021 | 15PE0033 | 2015-12-03 | 2015-12-14 | 2015-12-15 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305149 | Kibungan NHS | KIBUNGAN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 135624 | La Trinidad CS | LA TRINIDAD (Capital) | 0 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10517131.51 |  |  | Completed | 1 |  |  | CA0215S00024 | 15PE0033 | 2015-12-03 | 2015-12-14 | 2015-12-15 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Benguet | 318905 | La Trinidad NHS | LA TRINIDAD (Capital) | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 135525 | Lab-ang Com. Sch. | ITOGON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | CA0215S00018 | 15PE0033 | 2015-12-03 | 2015-12-14 | 2015-12-15 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305142 | Laurencio Fianza National High School | ITOGON | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305151 | Lepanto NHS | MANKAYAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | Completed | 1 |  |  | CA0215S00004 | 15PF0035 | 2015-08-24 | 2015-09-01 | 2015-09-14 | 2015-09-28 | 2015-10-09 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Benguet | 135697 | Ligay ES | TUBA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2218606.04 |  |  | Completed | 1 |  |  | CA0215S00012 | 15PE0033 | 2015-12-03 | 2015-12-14 | 2015-12-15 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305127 | Loacan National High School | ITOGON | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305138 | Loo NHS | BUGUIAS | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | CA0215S00002 | 15PF0042 | 2015-10-04 | 2015-10-12 | 2015-10-26 | 2015-10-30 | 2015-11-11 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Benguet | 305155 | Mankayan NHS | MANKAYAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | Completed | 1 |  |  | CA0215S00001 | 15PF0034 | 2015-08-24 | 2015-09-01 | 2015-09-14 | 2015-09-28 | 2015-10-09 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Benguet | 135659 | Mantiyeng PS | MANKAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2258606.04 |  |  | Completed | 1 |  |  | CA0215S00017 | CA02-15-S-00017(CNTR) | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 135454 | Poodan ES | BOKOD | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Reverted | 0 |  |  | CA0215S00013 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Benguet | 305157 | Sablan NHS | SABLAN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 219522 | Sa'dul PS | SABLAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2318606.04 |  |  | Reverted | 0 |  |  | CA0215S00022 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Benguet | 318912 | Sinipsip NHS - Natubleng Ext. | BUGUIAS | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305150 | Tacadang NHS | KIBUNGAN | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Benguet | 305161 | Taloy Sur NHS | TUBA | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 135612 | Tonguey-Nalusbo PS | KIBUNGAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2318606.04 |  |  | Completed | 1 |  |  | CA0215S00026 | CA02-15-S-00026(CNTR) | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 135589 | Toplac Bo. Sch. | KAPANGAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | Completed | 1 |  |  | CA0215S00015 | CA02-15-S-00015(CNTR) | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305160 | Tuba NHS (Nangalisan) | TUBA | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | CA0215S00011 | 15PE0019 | 2015-10-06 | 2015-10-07 | 2015-10-20 | 2015-11-11 | 2015-11-27 | JV: 3K ROCK ENGINEERING/FIAT CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Benguet | 305163 | Tublay Sch. of Home Ind. - Ambuklao Annex | BOKOD | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305164 | Tublay Sch. of Home Ind. - Central Extension | TUBLAY | 0 | 1 | 2 | 2STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 2607308.316 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Benguet | 305162 | Tublay Sch. of Home Industries | TUBLAY | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | Completed | 1 |  |  | CA0215S00029 | CA02-15-S-00029(CNTR) | 2015-11-30 | 2015-12-12 | 2015-12-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Benguet | 135717 | Yagyagan ES | TUBA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2258606.04 |  |  | Reverted | 0 |  |  | CA0215S00019 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Ifugao | 135787 | Antipolo ES | ASIPULO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0315S00016 | 15PG0048 | 2015-09-30 | 2015-10-02 | 2015-10-15 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Ifugao | 135879 | Banga p/S | LAGAWE (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Reverted | 0 |  |  | CA0315S00017 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Ifugao | 135943 | Binablayan ES | TINOC | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2438606.04 |  |  | Reverted | 0 |  |  | CA0315S00007 | 15PG0049 | 2015-09-30 | 2015-10-02 | 2015-10-15 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Ifugao | 135922 | Buninan PS | MAYOYAO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2338606.04 |  |  | Reverted | 0 |  |  | CA0315S00019 | 15PJ0039 | 2015-09-29 | 2015-10-02 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Ifugao | 135881 | Burnay ES | LAGAWE (Capital) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3252592.44 |  |  | Completed | 1 |  |  | CA0315S00013 | 15PG0045 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-11-02 | 2015-11-27 | LINSCO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | CAR | Ifugao | 135744 | Butac ES | AGUINALDO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | Completed | 1 |  |  | CA0315S00003 | 15PJ0035 | 2015-11-05 | 2015-11-06 | 2015-11-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Ifugao | 135835 | Cababuyan ES | HINGYON | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6849337.6381 |  |  | Completed | 1 |  |  | CA0315S00012 | 15PG0039 | 2015-10-12 | 2015-10-16 | 2015-10-27 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Ifugao | 135747 | Chalalo ES - Annex | AGUINALDO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2308606.04 |  |  | Reverted | 0 |  |  | CA0315S00004 | 15PJ0038 | 2015-09-29 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Ifugao | 135771 | Dolowog PS | ALFONSO LISTA (POTIA) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2168606.04 |  |  | Completed | 1 |  |  | CA0315S00008 | 15PJ0032 | 2015-09-16 | 2015-09-18 | 2015-10-06 | 2015-10-21 | 2015-11-12 | ROJUNED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Ifugao | 220021 | Duli ES Extension | ASIPULO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2308606.04 |  |  | Reverted | 0 |  |  | CA0315S00011 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Ifugao | 135898 | Dunuan ES | LAMUT | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | CA0315S00015 | 15PG0047 | 2015-09-30 | 2015-10-02 | 2015-10-15 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Ifugao | 135947 | Gumhang ES | TINOC | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2638606.04 |  |  | Completed | 1 |  |  | CA0315S00002 | 15PG0051 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Ifugao | 305177 | Hapid NHS - Bimpal Annex | LAMUT | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 3159549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2015 | CAR | Ifugao | 220012 | Hulbo PS | AGUINALDO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2288606.04 |  |  | Reverted | 0 |  |  | CA0315S00010 | 15PJ0034 | 2015-09-16 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Ifugao | 135950 | Lama PS | TINOC | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2538606.04 |  |  | Reverted | 0 |  |  | CA0315S00009 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Ifugao | 135902 | Lamut CS | LAMUT | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | Completed | 1 |  |  | CA0315S00005 | 15PG0046 | 2015-09-30 | 2015-10-02 | 2015-10-15 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Ifugao | 135954 | Palabayan Elementary School | TINOC | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6849337.6381 |  |  | Completed | 1 |  |  | CA0315S00014 | 15PG0040 | 2015-10-12 | 2015-10-16 | 2015-10-27 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Ifugao | 135780 | Potia ES | ALFONSO LISTA (POTIA) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6419337.6381 |  |  | Completed | 1 |  |  | CA0315S00018 | 15PJ0033 | 2015-09-16 | 2015-09-18 | 2015-10-06 | 2015-10-21 | 2015-11-12 | ROJUNED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Ifugao | 135840 | Proposed Stand-Alone SHS 1(Namulditan ES) | HINGYON | 0 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 5 | 19822269 |  |  | Completed | 1 |  |  | CA0315S00001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | CAR | Ifugao | 135911 | Pugol PS | LAMUT | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2208606.04 |  |  | Completed | 1 |  |  | CA0315S00006 | 15PG0050 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-28 | 2015-11-27 | CARLYZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Kalinga | 220530 | Babbanoy Primary School | TANUDAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | Reverted | 0 |  |  | CA0415S00043 | 15PH0129 | 2015-08-20 | 2015-08-21 | 2015-11-24 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Kalinga | 136067 | Bagbag ES | RIZAL (LIWAN) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Kalinga | 136067 | Bagbag ES | RIZAL (LIWAN) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 8769337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Kalinga | 305199 | Balbalan Agricultural and Industrial School | BALBALAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8644965.051 |  |  | Completed | 1 |  |  | CA0415S00016 | 15PH0080 | 2015-07-06 | 2015-07-07 | 2015-10-13 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Kalinga | 305220 | Bangad National High School | TINGLAYAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8639965.051 |  |  | Completed | 1 |  |  | CA0415S00015 | 15PH0076 | 2015-07-06 | 2015-07-07 | 2015-07-20 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Kalinga | 136136 | Belong ES | TINGLAYAN | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6569337.6381 |  |  | Completed | 1 |  |  | CA0415S00042 | 15PH0126 | 2015-08-20 | 2015-08-21 | 2015-09-03 | 2015-09-22 | 2015-09-30 | SADLAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Kalinga | 136039 | Binansagan PS | PINUKPUK | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0415S00030 | 15PH0135 | 2015-08-23 | 2015-08-24 | 2015-11-24 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Kalinga | 136138 | Buscalan ES | TINGLAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | Completed | 1 |  |  | CA0415S00022 | 15PH0127 | 2015-08-20 | 2015-08-21 | 2015-11-24 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Kalinga | 305201 | Cal-owan Agricultural Vocational National High School | PINUKPUK | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8914965.051 |  |  | Completed | 1 |  |  | CA0415S00006 | 15PH0081 | 2015-07-08 | 2015-08-25 | 2015-11-12 | 2015-12-07 | 2015-12-16 | CNG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Kalinga | 305214 | Central Pasil National High School | PASIL | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 9064965.051 |  |  | Completed | 1 |  |  | CA0415S00014 | 15PH0077 | 2015-07-06 | 2015-08-04 | 2015-08-17 | 2015-09-14 | 2015-09-21 | CNG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Kalinga | 135990 | Dugnac PS | LUBUAGAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2268606.04 |  |  | Completed | 1 |  |  | CA0415S00027 | 15PH0128 | 2015-08-20 | 2015-08-21 | 2015-11-24 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Kalinga | 136044 | Dupagan ES | PINUKPUK | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6519337.6381 |  |  | Completed | 1 |  |  | CA0415S00028 | 15PH0137 | 2015-08-23 | 2015-08-24 | 2015-12-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Tabuk City | 305205 | Kalinga National High School | CITY OF TABUK (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8264965.051 |  |  | Completed | 1 |  |  | CA0415S00005 | 15PH0074 | 2015-06-28 | 2015-06-29 | 2015-11-12 | 2015-11-18 | 2015-11-24 | CNG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Kalinga | 135976 | Ligayan Community School | BALBALAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2168606.04 |  |  | Reverted | 0 |  |  | CA0415S00029 | 15PH0118 | 2015-08-17 | 2015-08-18 | 2015-11-24 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Kalinga | 305223 | Lubuagan National High School | LUBUAGAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6844337.6381 |  |  | Completed | 1 |  |  | CA0415S00017 | 15PH0101 | 2015-08-09 | 2015-08-11 | 2015-11-16 | 2015-12-07 | 2015-12-16 | E.T. LATAWAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Kalinga | 136074 | Macutay ES | RIZAL (LIWAN) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0415S00021 | 15PH0131 | 2015-08-23 | 2015-08-24 | 2015-10-29 | 2015-12-01 | 2015-12-16 | CSD ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Kalinga | 305218 | Macutay-Palao National High School | RIZAL (LIWAN) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8664965.051 |  |  | Completed | 1 |  |  | CA0415S00010 | 15PH0079 | 2015-07-06 | 2015-08-26 | 2015-09-08 | 2015-11-27 | 2015-12-04 | CSD ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Kalinga | 305211 | Magtoma Pangol NHS-Main | TANUDAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 7119337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Kalinga | 135995 | Mallongan ES | LUBUAGAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0415S00019 | 15PH0116 | 2015-10-14 | 2015-10-14 | 2015-11-24 | 2015-12-07 | 2015-12-16 | E.T. LATAWAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Kalinga | 136054 | Pakawit ES | PINUKPUK | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | Completed | 1 |  |  | CA0415S00024 | 15PH0134 | 2015-08-23 | 2015-08-24 | 2015-09-04 | 2015-09-22 | 2015-09-30 | TRINITY CONSTRUCTION AND ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Kalinga | 136128 | Pangol ES | TANUDAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Reverted | 0 |  |  | CA0415S00020 | 15PH0117 | 2015-10-14 | 2015-10-15 | 2015-11-24 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Kalinga | 220505 | Payao PS | LUBUAGAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0415S00044 | 15PH0119 | 2015-08-20 | 2015-08-21 | 2015-11-24 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Kalinga | 305216 | Pinukpuk Vocational School | PINUKPUK | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8664965.051 |  |  | Completed | 1 |  |  | CA0415S00011 | 15PH0082 | 2015-07-09 | 2015-07-10 | 2015-09-08 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Kalinga | 220519 | Poswoy ES - Mamaga Annex | BALBALAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | Reverted | 0 |  |  | CA0415S00040 | 15PH0130 | 2015-08-20 | 2015-08-21 | 2015-11-24 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Kalinga | 340131 | Proposed Stand-Alone SHS 1 | LUBUAGAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 8219338 |  |  | Completed | 1 |  |  | CA0415S00018 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Kalinga | 305217 | Rizal National School of Arts & Trades | RIZAL (LIWAN) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | Completed | 1 |  |  | CA0415S00013 | 15PH0078 | 2015-07-06 | 2015-08-26 | 2015-09-08 | 2015-09-14 | 2015-09-21 | CNG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Kalinga | 305208 | Southern Tinglayan National High School | TINGLAYAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6819337.6381 |  |  | Completed | 1 |  |  | CA0415S00007 | 15PH0109 | 2015-08-16 | 2015-08-17 | 2015-09-23 | 2015-10-05 | 2015-10-14 | SADLAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Kalinga | 136149 | Sumadel ES | TINGLAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | Completed | 1 |  |  | CA0415S00039 | 15PH0115 | 2015-08-17 | 2015-08-18 | 2015-11-24 | 2015-12-11 | 2015-12-16 | BALLIGI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8374965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Kalinga | 136052 | Taggay ES | PINUKPUK | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0415S00025 | 15PH0133 | 2015-08-23 | 2015-08-24 | 2015-09-04 | 2015-09-22 | 2015-09-30 | TRINITY CONSTRUCTION AND ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Kalinga | 305224 | Tanudan National High School | TANUDAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6919337.6381 |  |  | Reverted | 0 |  |  | CA0415S00009 | 15PH0108 | 2015-08-16 | 2015-08-17 | 2015-08-28 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Kalinga | 136038 | Wagud ES | PINUKPUK | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0415S00026 | 15PH0132 | 2015-08-23 | 2015-08-24 | 2015-09-04 | 2015-09-22 | 2015-09-30 | TRINITY CONSTRUCTION AND ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Mt. Province | 136282 | Amolong Primary School | PARACELIS | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3027592.44 |  |  | Completed | 1 |  |  | CA0515S00012 | 15PI0060 | 2015-10-08 | 2015-10-20 | 2015-10-28 | 2015-12-01 |  | RKKI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | CAR | Mt. Province | 136343 | Ankileng Elementary School | SAGADA | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6644337.6381 |  |  | Completed | 1 |  |  | CA0515S00016 | 15PI0072 | 2015-10-15 | 2015-10-27 | 2015-10-27 | 2015-12-01 |  | SADLAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Mt. Province | 305266 | Ankileng NHS | Sagada | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10817132 |  |  | Completed | 1 |  |  | CA0515S00009 | 15PI0089 | 2015-12-20 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | CAR | Mt. Province | 136283 | Anonat Primary School | PARACELIS | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | Completed | 1 |  |  | CA0515S00017 | 15PI0064 | 2015-10-08 | 2015-10-20 | 2015-10-28 | 2015-12-01 |  | BATAKAGAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Mt. Province | 319221 | Balaoa National High School | TADIAN | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6619338 |  |  | Completed | 1 |  |  | CA0515S00027 | 15PI0078 | 2015-10-18 | 2015-10-15 | 2015-10-30 | 2015-11-13 |  | MILIGAN CONSTRUCTION & GENERAL ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Mt. Province | 136303 | Balindan Elementary School | PARACELIS | 0 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4572048.49 |  |  | Completed | 1 |  |  | CA0515S00019 | 15PI0067 | 2015-10-08 | 2015-10-20 | 2015-10-27 | 2015-12-02 |  | DWD CONSTRUCTION AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Mt. Province | 136345 | Balugan Elementary School | SAGADA | 0 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4502048.49 |  |  | Completed | 1 |  |  | CA0515S00020 | 15PI0068 | 2015-11-05 | 2015-11-16 | 2015-11-18 | 2015-12-02 |  | RKKI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Mt. Province | 319215 | Banguitan National High School | Besao | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6569338 |  |  | Completed | 1 |  |  | CA0515S00026 | 15PI0077 | 2015-10-18 | 2015-10-15 | 2015-10-30 | 2015-11-13 |  | FOUR BROTHERS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Mt. Province | 305237 | Besao NHS | Besao | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6789337.6381 |  |  | Completed | 1 |  |  | CA0515S00003 | 15PI0057 | 2015-09-17 | 2015-09-29 | 2015-09-30 | 2015-11-02 |  | BENTRIX BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Mt. Province | 305239 | Butigue NHS | Paracelis | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6394337.6381 |  |  | Completed | 1 |  |  | CA0515S00004 | 15PI0056 | 2015-11-15 | 2015-11-26 | 2015-12-08 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Mt. Province | 305240 | Cagubatan NHS | Tadian | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6439337.6381 |  |  | Completed | 1 |  |  | CA0515S00005 | 15PI0055 | 2015-11-15 | 2015-11-27 | 2015-12-08 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Mt. Province | 136206 | Caotit Primary School | TADIAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | Completed | 1 |  |  | CA0515S00014 | 15PI0062 | 2015-10-08 | 2015-10-09 | 2015-10-28 | 2015-12-01 |  | BATAKAGAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Mt. Province | 136294 | Catao Elementary School | PARACELIS | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2952592.44 |  |  | Completed | 1 |  |  | CA0515S00013 | 15PI0061 | 2015-10-08 | 2015-10-20 | 2015-10-28 | 2015-12-01 |  | UPLAND CONSTRUCTION AND ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | CAR | Mt. Province | 136212 | Lagawa Elementary School | PARACELIS | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6394337.6381 |  |  | Completed | 1 |  |  | CA0515S00010 | 15PI0070 | 2015-10-08 | 2015-10-05 | 2015-10-27 | 2015-11-11 |  | JJJ-A CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Mt. Province | 221005 | Minoli Elementary School | BAUKO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | CA0515S00021 | 15PI0065 | 2015-10-15 | 2015-10-27 | 2015-11-18 | 2015-12-02 |  | JJJ-A CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Mt. Province | 305258 | Natonin National High School | PARACELIS | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6544338 |  |  | Completed | 1 |  |  | CA0515S00029 | 15PI0073 | 2015-11-15 | 2015-11-13 | 2015-12-08 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Mt. Province | 305263 | Sabangan NHS (Site 2) | Sabangan | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | CA0515S00006 | 15PI0054 | 2015-09-17 | 2015-09-28 | 2015-09-30 | 2015-10-26 | 2015-11-19 | HDG CONSTRUCTION AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Mt. Province | 305265 | Sagada NHS | Sagada | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 7034337.6381 |  |  | Completed | 1 |  |  | CA0515S00007 | 15PI0053 | 2015-09-17 | 2015-09-29 | 2015-09-30 | 2015-10-26 |  | JBA CONSTRUCTION AND BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Mt. Province | 340155 | Stand-Alone SHS | Natonin | 0 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 17371328 |  |  | Completed | 1 |  |  | CA0515S00008 | 15PI0082 | 2015-10-22 | 2015-11-03 | 2015-11-03 | 2015-11-19 |  | UPLAND CONSTRUCTION AND ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2015 | CAR | Mt. Province | 221015 | Tadian Elementary School | BAUKO | 0 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4597048.49 |  |  | Completed | 1 |  |  | CA0515S00022 | 15PI0069 | 2015-10-15 | 2015-10-15 | 2015-10-27 | 2015-11-12 |  | TADIAN GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Mt. Province | 305268 | Talubin National High School | BAUKO | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6569338 |  |  | Completed | 1 |  |  | CA0515S00023 | 15PI0074 | 2015-10-18 | 2015-10-15 | 2015-10-30 | 2015-11-13 |  | SADLAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Tabuk City | 220515 | Basao Isla ES | CITY OF TABUK (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6619337.6381 |  |  | Completed | 1 |  |  | CA0415S00038 | 15PH0125 | 2015-08-20 | 2015-08-21 | 2015-09-03 | 2015-09-22 | 2015-09-30 | BALLIGI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Tabuk City | 220531 | Bulanao East Annex - Greenhills PS | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Reverted | 0 |  |  | CA0415S00031 | 15PH0123 | 2015-08-20 | 2015-08-21 | 2015-09-02 | 2015-09-22 | 2015-09-30 | TRINITY CONSTRUCTION AND ENGINEERING |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Tabuk City | 220524 | Bulo West ES - Burobor Annex | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0415S00036 | 15PH0122 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-22 | 2015-09-30 | TRINITY CONSTRUCTION AND ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Tabuk City | 220525 | Burayukan PS | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0415S00045 | 15PH0121 | 2015-08-19 | 2015-08-20 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Tabuk City | 220510 | Gradual Discovery ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0415S00034 | 15PH0120 | 2015-08-19 | 2015-08-20 | 2015-09-29 | 2015-10-07 | 2015-10-14 | TRINITY CONSTRUCTION AND ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Tabuk City | 220520 | Madapdappig ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0415S00035 | 15PH0114 | 2015-08-17 | 2015-08-18 | 2015-09-01 | 2015-09-21 | 2015-09-30 | TRINITY CONSTRUCTION AND ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Tabuk City | 136102 | Magabbangon ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | Completed | 1 |  |  | CA0415S00032 | 15PH0136 | 2015-08-23 | 2015-08-24 | 2015-09-04 | 2015-09-22 | 2015-09-30 | MCPC BUILDERS & DEVELOPERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Tabuk City | 136184 | Nambucayan ES | CITY OF TABUK (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6469337.6381 |  |  | Completed | 1 |  |  | CA0415S00037 | 15PH0153 | 2015-10-13 | 2015-10-15 | 2015-11-24 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Tabuk City | 136178 | Paligatto ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | Completed | 1 |  |  | CA0415S00033 | 15PH0124 | 2015-08-19 | 2015-08-20 | 2015-09-29 | 2015-10-07 | 2015-10-14 | TRINITY CONSTRUCTION AND ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Tabuk City | 319224 | Bunga National High School | CITY OF TABUK (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6499338 |  |  | Completed | 1 |  |  | CA0515S00028 | 15PI0079 | 2015-10-18 | 2015-10-15 | 2015-10-30 | 2015-11-13 |  | BATAKAGAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Tabuk City | 136279 | Tappo Primary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2063606.04 |  |  | Reverted | 0 |  |  | CA0515S00015 | 15PI0063 | 2015-10-08 | 2015-10-20 | 2015-10-28 | 2015-11-13 |  | JJJ-A CONSTRUCTION AND SUPPLIES |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | CAR | Tabuk City | 319213 | Subaba National High School | CITY OF TABUK (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6669338 |  |  | Completed | 1 |  |  | CA0515S00025 | 15PI0076 | 2015-10-18 | 2015-10-15 | 2015-10-30 | 2015-11-13 |  | TADIAN GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Tabuk City | 319205 | Guinzadan National High School - Mayag Extension | CITY OF TABUK (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6394338 |  |  | Completed | 1 |  |  | CA0515S00024 | 15PI0075 | 2015-10-18 | 2015-10-15 | 2015-10-30 | 2015-11-13 |  | BATAKAGAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Tabuk City | 136292 | Canabo Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6419337.6381 |  |  | Completed | 1 |  |  | CA0515S00018 | 15PI0071 | 2015-11-05 | 2015-11-17 | 2015-11-18 | 2015-12-02 |  | JJA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | CAR | Tabuk City | 136288 | Burayoc Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4472048.49 |  |  | Completed | 1 |  |  | CA0515S00011 | 15PI0066 | 2015-10-08 | 2015-10-09 | 2015-10-28 | 2015-11-12 |  | JJA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Abra | 305074 | Abas NHS | SALLAPADAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2016-01-15 |  | CA0114S00022 | 15PA0036 (Package) | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-09 | 2015-08-25 | R.S. SEPIAN CONSTRUCTION & TRUCKING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Abra | 305075 | Abra HS | BANGUED (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8295486.7031 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Abra | 305075 | Abra HS | BANGUED (Capital) | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14997518.84 |  |  | Terminated | 0.23 | [10 empty] | Requested for completion of said project and it has been funded. The project is already completed. The contract is Terminated (Mutally terminated due to security reason during implementation). | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8
NEWCON 2014 | CAR | Abra | 135196 | Alawa ES | TINEG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1097049.6543 |  |  | Reverted | 0 |  |  | CA0114S00013 | 15PA0052 | 2015-09-14 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Abra | 305076 | Baay NHS | LICUAN-BAAY (LICUAN) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 |  |  | CA0114S00021 | 15PA0042 | 2015-09-02 | 2015-09-04 | 2015-09-17 | 2015-09-28 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Abra | 135205 | Caganayan ES | TINEG | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2098217.57 |  |  | Completed | 1 | 2015-02-28 | 2015-02-28 | CA0114S00002 | 14PA0022 | 2014-08-01 | 2014-08-07 | 2014-08-19 | 2014-09-16 | 2014-09-29 | A.P.B. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Abra | 134992 | Calao ES | BUCAY | 0 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3564886.575 |  |  | Completed | 1 | 2016-03-07 |  | CA0114S00010 | 15PA0053 | 2015-09-02 | 2015-09-10 | 2015-09-22 | 2015-10-06 | 2015-11-02 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Abra | 135206 | Cogon PS | TINEG | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1964740.174 |  |  | Reverted | 0 |  |  | CA0114S00014 | 15PA0043 | 2015-09-14 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Abra | 135208 | Collago ES | LAGAYAN | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2770828.124 |  |  | Completed | 1 | 2016-03-07 |  | CA0114S00012 | 15PA0054 | 2015-09-02 | 2015-09-10 | 2015-09-22 | 2015-10-06 | 2015-11-02 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Abra | 135152 | Dalit ES | PILAR | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3102592.44 |  |  | Completed | 1 | 2016-02-07 |  | CA0114S00034 | 15PA0064 | 2015-07-09 | 2015-08-20 | 2015-09-01 | 2015-09-08 | 2015-09-24 | R.S. SEPIAN CONSTRUCTION & TRUCKING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Abra | 305083 | Dalit NHS | PILAR | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6619337.6381 |  |  | Completed | 1 | 2015-12-29 |  | CA0114S00027 | 15PA0034 | 2015-06-15 | 2015-06-18 | 2015-06-30 | 2015-07-09 | 2015-08-25 | R.S. SEPIAN CONSTRUCTION & TRUCKING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Abra | 135062 | Gaddani ES | LAGANGILANG | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1889740.174 |  |  | Completed | 1 | 2016-02-09 |  | CA0114S00011 | 15PA0051 | 2015-09-02 | 2015-09-10 | 2015-09-22 | 2015-10-05 | 2015-11-12 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Abra | 305086 | Gaddani NHS | TAYUM | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | Completed | 1 | 2016-04-13 |  | CA0114S00028 | 15PA0050 | 2015-09-02 | 2015-09-04 | 2015-09-18 | 2015-09-28 | 2015-11-16 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Abra | 305087 | Langiden NHS | LANGIDEN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2016-02-20 |  | CA0114S00020 | 15PA0040 | 2015-09-02 | 2015-09-04 | 2015-09-17 | 2015-09-28 | 2015-11-16 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Abra | 305089 | Luzong NHS | LUBA | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6619337.6381 |  |  | Completed | 1 | 2016-01-04 |  | CA0114S00024 | 15PA0038 | 2015-06-16 | 2015-06-20 | 2015-07-02 | 2015-07-13 | 2015-09-01 | R.S. SEPIAN CONSTRUCTION & TRUCKING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Abra | 135138 | Malapaao ES | LANGIDEN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1146229.12 |  |  | Completed | 1 | 2014-12-16 | 2014-12-16 | CA0114S00007 | 14PA0020 | 2014-07-30 | 2014-08-01 | 2014-09-18 | 2014-09-24 | 2014-09-30 | A.P.B. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Abra | 135158 | Maliplipit PS | PILAR | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1141229.12 |  |  | Completed | 1 | 2014-12-13 | 2014-12-13 | CA0114S00004 | 14PA0019 | 2014-07-30 | 2014-08-01 | 2014-08-14 | 2014-09-23 | 2014-09-29 | A.P.B. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Abra | 305098 | Manabo NHS (San Jose Catacdegan NHS) | MANABO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | Completed | 1 | 2016-04-13 |  | CA0114S00029 | 15PA0047 | 2015-09-02 | 2015-09-04 | 2015-09-18 | 2015-09-28 | 2015-11-11 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Abra | 318701 | MARC YSRAEL B. BERNOS MEMORIAL NATIONAL HIGH SCHOOL | LA PAZ | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1121229.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Abra | 318701 | MARC YSRAEL B. BERNOS MEMORIAL NATIONAL HIGH SCHOOL | LA PAZ | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15097518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | CAR | Abra | 135073 | Metodio ES | LAGANGILANG | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2971874.43 |  |  | Completed | 1 | 2014-12-21 | 2014-12-21 | CA0114S00006 | 14PA0023 | 2014-08-01 | 2014-08-07 | 2014-08-19 | 2014-09-16 | 2014-09-29 | A.P.B. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Abra | 305091 | Northern Abra NHS | SAN JUAN | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15047518.84 |  |  | Completed | 1 | 2016-05-17 |  | CA0114S00023 | 15PA0065 | 2015-09-03 | 2015-09-11 | 2015-09-24 | 2015-10-12 | 2015-11-20 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | CAR | Abra | 305092 | Pangtod NHS | BUCAY | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2016-01-15 |  | CA0114S00019 | 15PA0036 (Package) | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-09 | 2015-08-25 | R.S. SEPIAN CONSTRUCTION & TRUCKING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Abra | 305094 | Pulot NHS | LAGAYAN | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | Completed | 1 | 2016-01-25 |  | CA0114S00031 | 15PA0037 | 2015-06-16 | 2015-06-20 | 2015-07-02 | 2015-07-13 | 2015-09-28 | R.S. SEPIAN CONSTRUCTION & TRUCKING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Abra | 135143 | San Diego ES | PIDIGAN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1126229.12 |  |  | Completed | 1 | 2015-01-12 | 2015-01-12 | CA0114S00005 | 14PA0020 | 2014-07-30 | 2014-08-01 | 2014-09-18 | 2014-09-24 | 2014-09-30 | A.P.B. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Abra | 305097 | San Isidro NHS | SAN ISIDRO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8664965.051 |  |  | Completed | 1 | 2016-04-20 |  | CA0114S00032 | 15PA0048 | 2015-09-02 | 2015-09-04 | 2015-09-18 | 2015-09-28 | 2015-11-16 | WERR CORPORATION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Abra | 305099 | San Quintin NHS | SAN QUINTIN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8614965.051 |  |  | Completed | 1 |  |  | CA0114S00033 | 15PA0044 | 2015-09-02 | 2015-09-04 | 2015-09-17 | 2015-10-02 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Abra | 305100 | Supo NHS | TUBO | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 |  |  | CA0114S00018 | 15PA0035 (Package) | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-09 | 2015-12-01 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Abra | 305101 | Suyo National High School | PIDIGAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | Completed | 1 |  |  | CA0114S00026 | 15PA0049 | 2015-09-02 | 2015-09-04 | 2015-09-18 | 2015-09-28 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Abra | 305102 | Tagodtod NHS | LAGANGILANG | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2016-01-15 |  | CA0114S00017 | 15PA0036 (Package) | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-09 | 2015-08-25 | R.S. SEPIAN CONSTRUCTION & TRUCKING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Abra | 305103 | Tiempo NHS | TUBO | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6819337.6381 |  |  | Completed | 1 |  |  | CA0114S00015 | 15PA0035 (Package) | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-09 | 2015-12-01 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Abra | 305104 | Tineg NHS | TINEG | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0 |  |  | CA0114S00016 | 15PA0041 | 2015-09-14 | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Abra | 135166 | Tuquib ES | VILLAVICIOSA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1141229.12 |  |  | Completed | 1 | 2014-12-29 | 2015-01-12 | CA0114S00003 | 14PA0020 | 2014-07-30 | 2014-08-01 | 2014-09-18 | 2014-09-24 | 2014-09-30 | A.P.B. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 318808 | Allig National Agricultural and Trade HS | FLORA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1221129.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 318808 | Allig National Agricultural and Trade HS | FLORA | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 305106 | Apayao Nat'l Ind'l. & Agr'l. HS | CALANASAN (BAYAG) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 9794965.051 |  |  | Completed | 1 |  |  | CA0714S00030 | 15PC0034 | 2015-12-03 | 2015-12-04 | 2015-12-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Apayao | 305107 | Apayao Science HS | LUNA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8469965.051 |  |  | Completed | 1 | 2016-05-07 |  | CA0714S00029 | 15PC0032 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-10-20 | 2015-11-09 | TRYST BUILDERS ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Apayao | 305108 | BAC-DA National High School | LUNA | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 |  |  | CA0714S00043 | 15PC0033 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-10-20 | 2015-11-09 | TRYST BUILDERS ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 135302 | Cabetayan ES | KABUGAO (Capital) | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1249829.12 |  |  | Completed | 1 | 2015-02-12 | 2015-05-31 | CA0714S00005 | 14PB0018 | 2014-08-12 | 2014-08-25 | 2014-08-27 | 2014-09-09 | 2014-09-19 | BLESSING BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 135351 | Cacalaggan ES | PUDTOL | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6404337.6381 |  |  | Completed | 1 |  |  | CA0714S00026 | 15PC0039 | 2015-12-03 | 2015-12-04 | 2015-12-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Apayao | 135258 | Calafug ES | CONNER | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2292417.57 |  |  | Completed | 1 | 2015-05-05 | 2015-05-31 | CA0714S00010 | 14PB0013 | 2014-09-04 | 2014-09-17 | 2014-09-18 | 2014-10-15 | 2014-10-24 | TECKCON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 305110 | Calanasan NHS | CALANASAN (BAYAG) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0 |  |  | CA0714S00045 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Apayao | 318803 | Conner Central NHS Cupis Annex | CONNER | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2016-03-09 |  | CA0714S00036 | 15PB0018 | 2015-08-19 | 2015-08-28 | 2015-09-02 | 2015-09-25 | 2015-10-16 | RMG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 305111 | Conner Central NHS Main | CONNER | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6404337.6381 |  |  | Reverted | 0 | 2015-02-12 | 2015-02-25 | CA0714S00016 | 14PB0014 | 2014-08-12 | 2014-08-25 | 2014-08-27 | 2014-09-09 | 2014-09-19 | BLESSING BUILDERS AND CONSTRUCTION SUPPLY |  | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Apayao | 219025 | Conner CS Cubet Annex | CONNER | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1248429.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 305112 | Conner NHS | CONNER | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1215529.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 305113 | Flora NHS | FLORA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 9159965.051 |  |  | Completed | 1 | 2016-04-08 |  | CA0714S00032 | 15PC0042 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-10-20 | 2015-11-09 | TRYST BUILDERS ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Apayao | 318813 | Gov. Benjamin Laguiab, Sr. Memorial NHS Sacpil Annex | CONNER | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1247029.12 |  |  | Completed | 1 | 2015-02-12 | 2015-05-31 | CA0714S00020 | 14PB0015 | 2014-08-12 | 2014-08-25 | 2014-08-27 | 2014-09-09 | 2014-09-19 | BLESSING BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 305114 | Gov. Benjamin Leguiab, Sr. Mem. NHS Main | CONNER | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2016-03-09 |  | CA0714S00046 | 15PB0019 | 2015-07-19 | 2015-08-28 | 2015-09-02 | 2015-09-25 | 2015-10-16 | RMG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 135264 | Guinamgaman ES | CONNER | 0 | 1 | 4 | 1STY4CL (All Wood) | 2014 K10 BATCH 4B | 2790000 |  |  | Completed | 1 | 2016-03-29 |  | CA0714S00024 |  | 2015-10-11 | 2015-10-25 | 2015-11-12 | 2015-11-23 | 2015-12-01 | BLESSING BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Apayao | 135364 | Imelda ES | SANTA MARCELA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1254029.12 |  |  | Completed | 1 | 2015-02-26 | 2015-03-05 | CA0714S00021 | 14PC0020 | 2014-08-20 | 2014-08-22 | 2014-09-03 | 2014-09-15 | 2014-09-29 | ARESEF ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 318806 | Kabugao Agro-Ind'l. HS - Lenneng Annex | KABUGAO (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 3060828.124 |  |  | Completed | 1 | 2016-04-08 |  | CA0714S00033 | 15PB0016 | 2015-08-19 | 2015-08-28 | 2015-09-02 | 2015-09-25 | 2015-10-16 | E.C.T. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Apayao | 305115 | Kabugao Agro-Ind'l. HS Main | KABUGAO (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 3101828.124 |  |  | Completed | 1 | 2016-04-08 |  | CA0714S00034 | 15PB0017 | 2015-08-19 | 2015-08-28 | 2015-09-02 | 2015-09-25 | 2015-10-16 | E.C.T. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Apayao | 135316 | Kalliat ES | KABUGAO (Capital) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2292417.57 |  |  | Completed | 1 | 2015-04-30 | 2015-04-30 | CA0714S00004 | 14PB0017 | 2014-08-12 | 2014-08-25 | 2014-08-27 | 2014-09-09 | 2014-09-19 | BLESSING BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 135336 | Luna CS | LUNA | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2292417.57 |  |  | Completed | 1 | 2015-03-05 | 2015-03-05 | CA0714S00003 | 14PC0017 | 2014-08-20 | 2014-08-22 | 2014-09-03 | 2014-09-22 | 2014-10-06 | VCD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 305116 | Luna National High School Main | LUNA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1193329.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 305116 | Luna National High School Main | LUNA | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6484337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Apayao | 318801 | Luna NHS Tumog Annex | LUNA | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2292417.57 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 318801 | Luna NHS - Tumog Annex | LUNA | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 3350828.124 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Apayao | 135293 | Malayugan ES | FLORA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1225329.12 |  |  | Completed | 1 | 2015-04-04 | 2015-04-04 | CA0714S00006 | 14PC0016 | 2014-08-20 | 2014-08-22 | 2014-09-03 | 2014-09-22 | 2014-10-06 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 135355 | Malibang ES | PUDTOL | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1240029.12 |  |  | Completed | 1 | 2015-03-05 | 2015-03-05 | CA0714S00012 | 14PC0019 | 2014-08-20 | 2014-08-22 | 2014-09-03 | 2014-09-22 | 2014-10-06 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 305118 | Mataguisi Comp. HS Main | PUDTOL | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2016-02-01 |  | CA0714S00047 | 15PC0038 | 2015-08-25 | 2015-08-26 | 2015-09-07 | 2015-09-16 | 2015-09-30 | FIRST RELIABLE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 319009 | Mataguisi Comprehensive NHS Cacalaggan Annex | PUDTOL | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6569337.6381 |  |  | Completed | 1 |  |  | CA0714S00049 | 15PC0040 | 2015-12-03 | 2015-12-04 | 2015-12-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Apayao | 135356 | Mataguisi ES | PUDTOL | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1208229.12 |  |  | Completed | 1 | 2015-03-05 | 2015-03-05 | CA0714S00013 | 14PC0019 | 2014-08-20 | 2014-08-22 | 2014-09-03 | 2014-09-22 | 2014-10-06 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 305120 | Mayor Guillermo Barsalan SAT | SANTA MARCELA | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2728328.124 |  |  | Completed | 1 | 2016-03-03 |  | CA0714S00038 | 15PC0044 | 2015-08-25 | 2015-08-26 | 2015-09-07 | 2015-09-16 | 2015-09-30 | ARESEF ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Apayao | 305121 | Mayor Ricardo de San Jose, Sr. Comp. HS | FLORA | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 3215828.124 |  |  | Completed | 1 | 2016-03-03 |  | CA0714S00039 | 15PC0043 | 2015-08-25 | 2015-08-26 | 2015-09-07 | 2015-09-16 | 2015-09-30 | ARESEF ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Apayao | 135274 | Paddaoan ES Catub Annex | CONNER | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1251229.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 135366 | Panay ES | SANTA MARCELA | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | Completed | 1 | 2016-02-01 |  | CA0714S00027 | 15PC0046 | 2015-08-25 | 2015-08-26 | 2015-09-07 | 2015-09-16 | 2015-09-30 | ARESEF ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 318811 | Pio Da Lim Memorail SAT Sta. Filomena | CALANASAN (BAYAG) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2016-02-01 |  | CA0714S00037 | 15PC0035 | 2015-08-25 | 2015-08-26 | 2015-09-07 | 2015-09-16 | 2015-09-30 | B.A. LAGAZO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 318804 | Pio Da Lim Memorial SAT Tanglagan | CALANASAN (BAYAG) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0 |  |  | CA0714S00048 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Apayao | 305122 | Pio Dalim Memorial SAT Main | CALANASAN (BAYAG) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0 |  |  | CA0714S00044 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Apayao | 305123 | Pudtol NHS | PUDTOL | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6779337.6381 |  |  | Completed | 1 | 2016-02-16 |  | CA0714S00040 | 15PC0037 | 2015-08-25 | 2015-08-26 | 2015-09-07 | 2015-09-16 | 2015-09-30 | FIRST RELIABLE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Apayao | 135277 | Ripang ES | CONNER | 0 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8714965.051 |  |  | Reverted | 0 |  |  | CA0714S00050 | 15PB0016 | 2015-12-14 | 2015-12-23 |  |  |  | E.C.T. CONSTRUCTION |  | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Apayao | 135279 | Sacpil ES | CONNER | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2292417.57 |  |  | Completed | 1 | 2015-05-08 | 2015-06-30 | CA0714S00008 | 14PB0016 | 2014-09-04 | 2014-09-17 | 2014-09-18 | 2014-10-15 | 2014-10-24 | BLESSING BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 135344 | San Isidro Norte PS | LUNA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1193329.12 |  |  | Completed | 1 | 2015-03-05 | 2015-03-05 | CA0714S00007 | 14PC0017 | 2014-08-20 | 2014-08-22 | 2014-09-03 | 2014-09-22 | 2014-10-06 | VCD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 135284 | San Jose ES | FLORA | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2292417.57 |  |  | Completed | 1 | 2015-04-04 | 2015-04-04 | CA0714S00011 | 14PC0016 | 2014-08-20 | 2014-08-22 | 2014-09-03 | 2014-09-22 | 2014-10-06 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Apayao | 135369 | San Mariano ES | SANTA MARCELA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1244929.12 |  |  | Completed | 1 | 2015-02-26 | 2015-03-05 | CA0714S00009 | 14PC0020 | 2014-08-20 | 2014-08-22 | 2014-09-03 | 2014-09-15 | 2014-09-29 | ARESEF ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 135368 | Santa Marcela West Central Elementary School | SANTA MARCELA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1245629.12 |  |  | Completed | 1 | 2015-02-26 | 2015-03-05 | CA0714S00014 | 14PC0020 | 2014-08-20 | 2014-08-22 | 2014-09-03 | 2014-09-15 | 2014-09-29 | ARESEF ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Apayao | 305109 | Sta. Marcela NHS (Barocboc NHS) | SANTA MARCELA | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6844337.6381 |  |  | Completed | 1 | 2016-03-03 |  | CA0714S00041 | 15PC0045 | 2015-08-25 | 2015-08-26 | 2015-09-07 | 2015-09-16 | 2015-09-30 | FIRST RELIABLE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Apayao | 219017 | Upper Katablangan ES | CONNER | 0 | 1 | 4 | 1STY4CL (All Wood) | 2014 K10 BATCH 4B | 2820000 |  |  | Completed | 1 |  |  | CA0714S00025 |  | 2015-11-13 | 2015-11-26 | 2015-12-03 | 2015-12-14 |  | BLESSING BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Baguio City | 305269 | Baguio City National High School - Main | BAGUIO CITY | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4A | 14045118.3984 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | CAR | Baguio City | 305269 | Baguio City National High School - Main | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15147518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | CAR | Baguio City | 305282 | Guisad Valley National High School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15147518.84 |  |  | Completed | 1 |  |  | CA0614S00008 | 15PD0019 | 2015-07-08 | 2015-07-10 | 2015-07-22 | 2015-08-19 | 2015-08-25 | JOMARCANN GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | CAR | Baguio City | 305280 | Irisan National High School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15047518.84 |  |  | Completed | 1 | 2016-02-19 |  | CA0614S00007 | 15PD0020 | 2015-07-08 | 2015-07-10 | 2015-07-22 | 2015-08-11 | 2015-08-24 | JOMARCANN GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | CAR | Baguio City | 305284 | Joaquin Smith National High School | BAGUIO CITY | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8534965.051 |  |  | Completed | 1 | 2016-04-29 |  | CA0614S00006 | 15PD0026 | 2015-10-30 | 2015-10-30 | 2015-11-13 | 2015-11-27 | 2015-12-02 | SUMAG BUILDERS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Baguio City | 305275 | Mil-an National High School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15027518.84 |  |  | Completed | 1 | 2016-03-21 |  | CA0614S00005 | 15PD0021 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-19 | 2015-08-25 | JOMARCANN GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | CAR | Baguio City | 305278 | San Vicente National High School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15447518.84 |  |  | Completed | 1 | 2016-02-19 |  | CA0614S00010 | 15PD0022 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-11 | 2015-08-24 | DWD CONSTRUCTION AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | CAR | Baguio City | 305279 | Santo Tomas National High School | BAGUIO CITY | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15147518.84 |  |  | Completed | 1 |  |  | CA0614S00009 | 15PD0018 | 2015-07-08 | 2015-07-10 | 2015-07-22 |  |  | DWD CONSTRUCTION AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | CAR | Benguet | 305146 | Adaoay National High School | KABAYAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305125 | Alejo M. Pacalso Mem. NHS | ITOGON | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Reverted | 0 |  |  | CA0214S00027 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Benguet | 305126 | Ampucao National High School | ITOGON | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305128 | Ampusongan NHS | BAKUN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 318913 | Ampusongan NHS - Kayapa Ext. | BAKUN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305130 | Atok NHS - Caliking Annex | ATOK | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305131 | Bakun NHS | BAKUN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 318917 | BALILI NHS-CABACAB ANNEX | MANKAYAN | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6819337.6381 |  |  | Completed | 1 | 2016-02-12 |  | CA0214S00033 | 15PF0039 | 2015-08-24 | 2015-09-01 | 2015-09-14 | 2015-09-28 | 2015-10-09 | SISSI-IT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Benguet | 318902 | Bangao NHS | BUGUIAS | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305132 | Bedbed NHS | MANKAYAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 318916 | BENGUET NHS-PUGUIS ANNEX | LA TRINIDAD (Capital) | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4772048.49 |  |  | Completed | 1 | 2016-03-02 |  | CA0214S00001 | 15PE0016 | 2015-08-31 | 2015-09-01 | 2015-09-15 | 2015-10-03 | 2015-10-28 | MOUNTAINEERS ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305134 | Binga NHS | ITOGON | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 318901 | Bokod NHS - Daclan Extension | BOKOD | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305136 | Buguias NHS | BUGUIAS | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305156 | Bulalacao NHS | MANKAYAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305139 | Cabiten NHS (RA9087) | MANKAYAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305140 | Cordillera Regional Science HS | LA TRINIDAD (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305141 | Evelio Javier Memorial NHS | TUBA | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 318914 | Evelio Memorial NHS - Annex, Ansagan | TUBA | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305159 | Fianza Mem'l NHS - Tinongdan | ITOGON | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 318908 | Gov. Bado Dangwa Agro-Industrial School Extension - Taba-ao Annex | KAPANGAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305144 | Guinaoang NHS | MANKAYAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305147 | Kapangan Central NHS (RA8841) | KAPANGAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305149 | Kibungan NHS | KIBUNGAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 318905 | La Trinidad NHS | LA TRINIDAD (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305142 | Laurencio Fianza National High School | ITOGON | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305127 | Loacan National High School | ITOGON | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305157 | Sablan NHS | SABLAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 318912 | Sinipsip NHS - Natubleng Ext. | BUGUIAS | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305150 | Tacadang NHS | KIBUNGAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Benguet | 305161 | Taloy Sur NHS | TUBA | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305163 | Tublay Sch. of Home Ind. - Ambuklao Annex | BOKOD | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Benguet | 305164 | Tublay Sch. of Home Ind. - Central Extension | TUBLAY | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Ifugao | 305167 | Asipulo NHS | ASIPULO | 0 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15521327.92 |  |  | Completed | 1 |  |  | CA0314S00024 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | CAR | Ifugao | 305168 | Ayangan National Agricultural & Vocational HS | LAGAWE (Capital) | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6734337.6381 |  |  | Completed | 1 |  |  | CA0314S00014 | 15PG0024 | 2015-09-18 | 2015-09-17 | 2015-09-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Ifugao | 305170 | Banaue NHS | BANAUE | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 9146965.051 |  |  | Completed | 1 | 2016-05-01 |  | CA0314S00023 | 15PJ0026 | 2015-09-15 | 2015-09-18 | 2015-10-06 | 2015-11-17 | 2015-11-27 | PAULA MAE BUHONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Ifugao | 135850 | Bangbang ES | HUNGDUAN | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4692048.49 |  |  | Completed | 1 |  |  | CA0314S00006 | 15PG0020 | 2015-09-28 | 2015-10-02 | 2015-10-13 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Ifugao | 319001 | Bangbang NHS | HUNGDUAN | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 7069337.6381 |  |  | Completed | 1 |  |  | CA0314S00026 | 15PG0022 | 2015-09-28 | 2015-10-02 | 2015-10-13 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Ifugao | 220002 | Cababuyan PS Annex | HINGYON | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4566133.9594 |  |  | Completed | 1 | 2015-07-24 |  | CA0314S00002 | 14PG0043 | 2014-12-01 | 2014-12-05 | 2014-12-16 | 2015-01-07 | 2015-01-26 | APD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Ifugao | 135769 | Caragasan ES | ALFONSO LISTA (POTIA) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | Completed | 1 |  |  | CA0314S00003 | 15PJ0030 | 2015-11-05 | 2015-11-06 | 2015-11-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Ifugao | 305171 | Eastern Potia National High School | ALFONSO LISTA (POTIA) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8484965.051 |  |  | Completed | 1 | 2016-03-14 |  | CA0314S00022 | 15PJ0017 | 2015-07-26 | 2015-07-31 | 2015-08-11 | 2015-08-27 | 2015-09-17 | PAULA MAE BUHONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Ifugao | 135946 | Eheb ES | TINOC | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1279069.12 |  |  | Completed | 1 | 2014-12-30 | 2015-04-15 | CA0314S00001 | 14PG0019 | 2014-08-19 | 2014-08-22 | 2014-09-04 | 2014-09-14 | 2014-09-25 | D AND A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Ifugao | 305172 | Gohang NHS | BANAUE | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15867518.84 |  |  | Completed | 1 |  |  | CA0314S00021 | 15PJ0059 | 2015-12-09 | 2015-12-10 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | CAR | Ifugao | 305173 | Haliap NHS | ASIPULO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8684965.051 |  |  | Completed | 1 |  |  | CA0314S00020 | 15PG0027 | 2015-09-13 | 2015-09-17 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Ifugao | 305176 | Hapid NHS | LAMUT | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8848965.051 |  |  | Completed | 1 |  |  | CA0314S00019 | 15PG0023 | 2015-09-04 | 2015-09-07 | 2015-09-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Ifugao | 305177 | Hapid NHS - Bimpal Annex | LAMUT | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8944965.051 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Ifugao | 305178 | Hingyon NHS | HINGYON | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8692965.051 |  |  | Completed | 1 |  |  | CA0314S00017 | 15PG0026 | 2015-09-28 | 2015-10-02 | 2015-10-13 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Ifugao | 305181 | Ifugao Prov'l. Science HS | LAMUT | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8394965.051 |  |  | Completed | 1 |  |  | CA0314S00016 | 15PG0025 | 2015-09-13 | 2015-09-17 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Ifugao | 305182 | Kiangan NHS | KIANGAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | Completed | 1 |  |  | CA0314S00013 | 15PG0021 | 2015-09-13 | 2015-09-17 | 2015-09-29 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Ifugao | 305183 | Lawig NHS | LAMUT | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8594965.051 |  |  | Completed | 1 |  |  | CA0314S00007 | 15PG0019 | 2015-09-13 | 2015-09-17 | 2015-09-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Ifugao | 305185 | Mayoyao NHS | MAYOYAO | 0 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 11277131.51 |  |  | Completed | 1 |  |  | CA0314S00008 | 15PJ0058 | 2015-12-09 | 2015-12-10 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Ifugao | 135874 | Nagacadan ES | KIANGAN | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4612048.49 |  |  | Completed | 1 |  |  | CA0314S00005 | 15PG0028 | 2015-09-28 | 2015-10-02 | 2015-10-13 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Ifugao | 305187 | Namillangan NHS | ALFONSO LISTA (POTIA) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8434965.051 |  |  | Completed | 1 | 2016-05-01 |  | CA0314S00009 | 15PJ0018 | 2015-09-15 | 2015-09-18 | 2015-10-06 | 2015-11-17 | 2015-11-27 | PAULA MAE BUHONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Ifugao | 135800 | Nankatengey ES | ASIPULO | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1082049.6543 |  |  | Reverted | 0 |  |  | CA0314S00004 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Ifugao | 305188 | Pinto NHS | ALFONSO LISTA (POTIA) | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6549337.6381 |  |  | Completed | 1 | 2016-05-01 |  | CA0314S00010 | 15PJ0019 | 2015-09-15 | 2015-09-18 | 2015-10-06 | 2015-11-17 | 2015-11-27 | PAULA MAE BUHONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Ifugao | 135782 | San Juan ES | ALFONSO LISTA (POTIA) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3052592.44 |  |  | Completed | 1 | 2016-02-12 |  | CA0314S00027 | 15PJ0029 | 2015-08-25 | 2015-08-27 | 2015-09-09 | 2015-09-23 | 2015-10-16 | ROJUNED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Ifugao | 305190 | Sta. Maria NHS | ALFONSO LISTA (POTIA) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8544965.051 |  |  | Completed | 1 | 2016-05-01 |  | CA0314S00015 | 15PJ0028 | 2015-09-15 | 2015-09-18 | 2015-10-06 | 2015-11-17 | 2015-11-27 | PAULA MAE BUHONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Ifugao | 305192 | Tinoc NHS | TINOC | 0 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22902343.62 |  |  | Completed | 1 |  |  | CA0314S00012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | CAR | Ifugao | 305194 | Ubao National High School | AGUINALDO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8739965.051 |  |  | Completed | 1 | 2016-05-01 |  | CA0314S00025 | 15PJ0027 | 2015-09-15 | 2015-09-18 | 2015-10-06 | 2015-11-17 | 2015-11-27 | PAULA MAE BUHONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Ifugao | 319008 | Ubao NHS Extension | AGUINALDO | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6869337.6381 |  |  | Completed | 1 | 2016-02-12 |  | CA0314S00028 | 15PJ0020 | 2015-08-19 | 2015-08-24 | 2015-09-03 | 2015-09-23 | 2015-10-16 | COLBY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Kalinga | 136031 | Aciga ES | PINUKPUK | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2167459.327 |  |  | Completed | 1 | 2015-03-04 | 2015-05-10 | CA0414S00013 | 14PH0042 | 2014-06-06 | 2014-06-16 | 2014-09-25 | 2014-10-17 | 2014-11-03 | FIRST RELIABLE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Tabuk City | 305195 | Agbannawag National High School | CITY OF TABUK (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8714965.051 |  |  | Completed | 1 | 2016-05-18 |  | CA0414S00023 | 15PH0085 | 2015-07-19 | 2015-07-20 | 2015-09-08 | 2015-12-07 | 2015-12-21 | J.C. BAAC CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Kalinga | 136063 | Apatan ES | PINUKPUK | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2217459.327 |  |  | Completed | 1 | 2014-12-17 | 2015-11-30 | CA0414S00009 | 14PH0017 | 2014-06-06 | 2014-08-12 | 2014-08-26 | 2014-09-05 | 2014-09-19 | KALINGA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Tabuk City | 319104 | Bado Dangwa National High School | CITY OF TABUK (Capital) | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | Completed | 1 |  |  | CA0414S00024 | 15PH0093 | 2015-08-09 | 2015-08-11 | 2015-09-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Tabuk City | 136160 | Bantay ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4301949.6094 |  |  | Completed | 1 | 2015-07-20 | 2015-12-20 | CA0414S00015 | 14PH0085 | 2014-11-19 | 2014-11-20 | 2014-12-02 | 2015-03-04 | 2015-03-16 | KALINGA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Kalinga | 136135 | Basao ES | TINGLAYAN | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6519337.6381 |  |  | Reverted | 0 |  |  | CA0414S00021 | 15PH0107 | 2015-08-17 | 2015-08-17 | 2015-12-02 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Kalinga | 136043 | Bayao PS | PINUKPUK | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3152592.44 |  |  | Completed | 1 | 2016-01-25 |  | CA0414S00041 | 15PH0097 | 2015-08-10 | 2015-08-11 | 2015-08-25 | 2015-09-14 | 2015-09-21 | FIRST RELIABLE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Tabuk City | 136161 | Binongsay ES | CITY OF TABUK (Capital) | 0 | 1 | 5 | 2STY4CL & 1STY1CL | 2014 K10 BATCH 4A | 7370199.7756 |  |  | Completed | 1 | 2015-08-26 | 2015-11-05 | CA0414S00018 | 14PH0093 | 2014-12-21 | 2014-12-22 | 2015-02-24 | 2015-05-15 | 2015-05-21 | MCPC BUILDERS & DEVELOPERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2014 | CAR | Kalinga | 136070 | Calaocan ES | RIZAL (LIWAN) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2118938.4485 |  |  | Completed | 1 | 2014-10-25 | 2014-10-25 | CA0414S00008 | 14PH0013 | 2014-06-06 | 2014-06-16 | 2014-06-26 | 2014-07-14 | 2014-07-25 | CSD ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Tabuk City | 136096 | Cudal ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2118938.4485 |  |  | Completed | 1 | 2014-11-29 | 2014-12-04 | CA0414S00005 | 14PH0011 | 2014-06-06 | 2014-07-15 | 2014-07-29 | 2014-08-18 | 2014-08-28 | RMG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Kalinga | 135973 | Gawaan ES | BALBALAN | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2217459.327 |  |  | Completed | 1 | 2015-03-04 | 2015-05-10 | CA0414S00012 | 14PH0042 | 2014-06-11 | 2014-06-26 | 2014-09-25 | 2014-10-17 | 2014-11-03 | FIRST RELIABLE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Kalinga | 136059 | Kullayanan PS | PINUKPUK | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3152592.44 |  |  | Completed | 1 | 2016-02-08 |  | CA0414S00033 | 15PH0098 | 2015-08-10 | 2015-08-11 | 2015-08-25 | 2015-09-29 | 2015-10-07 | FIRST RELIABLE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Kalinga | 136143 | Legleg ES | TINGLAYAN | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6619337.6381 |  |  | Reverted | 0 |  |  | CA0414S00034 | 15PH0103 | 2015-08-13 | 2015-08-14 | 2015-11-03 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Kalinga | 136051 | Liplipoken PS | PINUKPUK | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6519337.6381 |  |  | Completed | 1 | 2016-01-18 |  | CA0414S00032 | 15PH0100 | 2015-08-11 | 2015-08-11 | 2015-08-25 | 2015-09-08 | 2015-09-17 | FIRST RELIABLE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Kalinga | 136073 | Liwan West ES | RIZAL (LIWAN) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2118938.4485 |  |  | Completed | 1 | 2014-10-22 | 2014-10-22 | CA0414S00007 | 14PH0014 | 2014-06-06 | 2014-06-16 | 2014-06-26 | 2014-07-14 | 2014-07-25 | CSD ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Kalinga | 136145 | Luplupa ES | TINGLAYAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3202592.44 |  |  | Completed | 1 | 2016-02-01 |  | CA0414S00030 | 15PH0104 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-21 | 2015-09-30 | TRINITY CONSTRUCTION AND ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Kalinga | 136127 | Mabaca ES | TANUDAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 1071535.01 |  |  | Completed | 1 | 2015-07-12 | 2015-08-12 | CA0414S00016 | 14PH0097 | 2014-11-29 | 2014-12-23 | 2015-02-03 | 2015-05-15 | 2015-05-21 | CNG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Kalinga | 135994 | Mabongtot ES | LUBUAGAN | 0 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 4334918.654 |  |  | Completed | 1 | 2015-09-17 |  | CA0414S00001 | 14PH0063 | 2014-10-09 | 2014-10-21 | 2015-02-03 | 2015-05-05 | 2015-05-15 | PJ TAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Kalinga | 136026 | Magsilay ES | PASIL | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2267459.327 |  |  | Completed | 1 | 2015-03-04 | 2015-05-10 | CA0414S00011 | 14PH0042 | 2014-06-06 | 2014-06-16 | 2014-09-25 | 2014-10-17 | 2014-11-03 | FIRST RELIABLE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Kalinga | 305211 | Magtoma Pangol NHS Main | TANUDAN | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2265980.2055 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Tabuk City | 136104 | Maledda ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2118938.4485 |  |  | Completed | 1 | 2014-10-25 | 2014-10-25 | CA0414S00004 | 14PH0010 | 2014-06-10 | 2014-06-16 | 2014-06-26 | 2014-07-14 | 2014-07-24 | TNJ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Kalinga | 135996 | Manangol ES | LUBUAGAN | 0 | 3 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2167459.327 |  |  | Completed | 1 | 2015-06-27 | 2015-07-08 | CA0414S00010 | 14PH0075 | 2014-11-13 | 2014-11-14 | 2015-02-03 | 2015-03-13 | 2015-03-24 | JEP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Kalinga | 136147 | Manubal ES | TINGLAYAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3152592.44 |  |  | Completed | 1 | 2016-03-01 |  | CA0414S00035 | 15PH0102 | 2015-09-10 | 2015-09-09 | 2015-09-22 | 2015-10-20 | 2015-10-28 | TRINITY CONSTRUCTION AND ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Kalinga | 136053 | Mapaco ES | PINUKPUK | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6499664.7656 |  |  | Completed | 1 | 2016-02-24 |  | CA0414S00014 | 14PH0084 | 2015-07-29 | 2015-07-29 | 2015-08-10 | 2015-10-16 | 2015-10-23 | BALLIGI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Tabuk City | 136107 | Nambaran ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2118938.4485 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Kalinga | 305213 | Pasil National High School | PASIL | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6719337.6381 |  |  | Completed | 1 | 2016-02-11 |  | CA0414S00036 | 15PH0096 | 2015-08-10 | 2015-08-11 | 2015-09-23 | 2015-10-07 | 2015-10-12 | CNG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Kalinga | 135981 | Salegseg Comm. Sch. | BALBALAN | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4C | 4872048.49 |  |  | Completed | 1 | 2016-02-08 |  | CA0414S00031 | 15PH0099 | 2015-08-10 | 2015-08-11 | 2015-08-25 | 2015-09-28 | 2015-10-05 | TRINITY CONSTRUCTION AND ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Kalinga | 136078 | San Francisco ES | RIZAL (LIWAN) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2118938.4485 |  |  | Completed | 1 | 2014-10-25 | 2014-10-28 | CA0414S00006 | 14PH0015 | 2014-06-06 | 2014-06-16 | 2014-06-26 | 2014-07-14 | 2014-07-24 | CSD ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Kalinga | 136129 | Taloctoc ES | TANUDAN | 0 | 1 | 3 | 1STY2CL & 1STY1CL | 2014 K10 BATCH 4A | 2990371.9825 |  |  | Completed | 1 | 2015-07-12 | 2015-08-12 | CA0414S00017 | 14PH0086 | 2014-12-21 | 2014-12-22 | 2015-02-03 | 2015-05-15 | 2015-05-21 | CNG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Kalinga | 305225 | Tanudan Vocational School | TANUDAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8814965.051 |  |  | Reverted | 0 |  |  | CA0414S00028 | 15PH0105 | 2015-08-13 | 2015-08-14 | 2015-08-26 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | CAR | Tabuk City | 305226 | Tuga National High School | CITY OF TABUK (Capital) | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | Completed | 1 | 2016-01-18 |  | CA0414S00027 | 15PH0092 | 2015-08-09 | 2015-08-11 | 2015-08-24 | 2015-09-08 | 2015-09-21 | MCPC BUILDERS & DEVELOPERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Mt. Province | 319220 | Anonat National Agricultural and Vocational High School | PARACELIS | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8639965.051 |  |  | Completed | 1 |  |  | CA0514S00026 | 15PI0043 | 2015-10-05 | 2015-10-08 | 2015-10-28 | 2015-12-18 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Mt. Province | 305230 | Bacarri National Trade & Agricultural School | PARACELIS | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8239965.051 |  |  | Completed | 1 | 2016-04-20 |  | CA0514S00025 | 15PI0044 | 2015-09-08 | 2015-09-08 | 2015-09-22 | 2015-10-21 | 2015-11-16 | UPLAND CONSTRUCTION AND ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Mt. Province | 319226 | Bacarri National Trade Agricultural High School-Bunot Extension | PARACELIS | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2313606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Mt. Province | 319226 | Bacarri National Trade Agricultural High School-Bunot Extension | PARACELIS | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2313606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Mt. Province | 319216 | Banawel NHS | NATONIN | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2078938.4485 |  |  | Completed | 1 | 2015-02-19 | 2015-05-31 | CA0514S00003 | 14PI0022 | 2014-08-06 | 2014-08-08 | 2014-08-11 | 2014-09-17 | 2014-10-01 | BENTRIX BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Mt. Province | 319218 | Dalican NHS | BONTOC (Capital) | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6094 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Mt. Province | 136297 | Dannal ES | PARACELIS | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2009825.9214 |  |  | Completed | 1 | 2015-02-19 | 2015-05-31 | CA0514S00001 | 14PI0018 | 2014-08-06 | 2014-08-08 | 2014-08-11 | 2014-09-17 | 2014-10-01 | JJJ-A CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Mt. Province | 305242 | Eastern Bontoc NAVHS | BARLIG | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8479965.051 |  |  | Completed | 1 |  |  | CA0514S00024 | 15PI0045 | 2015-09-08 | 2015-09-08 | 2015-09-22 | 2015-11-02 |  | CPS ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Mt. Province | 305244 | Guinzadan NHS | BAUKO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8604965.051 |  |  | Completed | 1 | 2016-04-17 |  | CA0514S00023 | 15PI0041 | 2015-09-03 | 2015-09-04 | 2015-09-18 | 2015-10-30 | 2015-11-13 | SUMAG BUILDERS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Mt. Province | 305236 | Lias National High School | BARLIG | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1131578.9936 |  |  | Completed | 1 | 2015-02-06 | 2015-05-15 | CA0514S00008 | 14PI0020 | 2014-08-06 | 2014-08-08 | 2014-08-11 | 2014-09-17 | 2014-10-01 | BENTRIX BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Mt. Province | 305247 | Lubon NHS | TADIAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 |  |  | CA0514S00014 | 15PI0050 | 2015-09-10 | 2015-09-10 | 2015-09-24 | 2015-10-30 |  | TADIAN GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Mt. Province | 319223 | Lubon NHS Mabalite Extension | TADIAN | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2908826.1743 |  |  | Completed | 1 | 2015-01-27 | 2015-01-31 | CA0514S00009 | 14PI0018 | 2014-08-06 | 2014-08-08 | 2014-08-11 | 2014-09-17 | 2014-11-07 | MILIGAN CONSTRUCTION & GENERAL ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Mt. Province | 305251 | Masla NHS | TADIAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 |  |  | CA0514S00013 | 15PI0050 | 2015-09-10 | 2015-09-10 | 2015-09-24 | 2015-10-29 |  | TADIAN GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Mt. Province | 305252 | Mt. Data NHS | BAUKO | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | Completed | 1 | 2016-04-27 |  | CA0514S00022 | 15PI0042 | 2015-09-03 | 2015-09-04 | 2015-09-18 | 2015-10-19 | 2015-11-30 | OLSIM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Mt. Province | 305255 | Mt. Prov. Gen. Comprehensive HS | BONTOC (Capital) | 0 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10447131.51 |  |  | Completed | 1 |  |  | CA0514S00021 | 15PI0049 | 2015-11-15 | 2015-11-27 | 2015-12-08 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Mt. Province | 305259 | Otucan-Bila NHS | BAUKO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8309965.051 |  |  | Completed | 1 | 2016-04-25 |  | CA0514S00020 | 15PI0040 | 2015-08-28 | 2015-09-04 | 2015-09-18 | 2015-10-19 | 2015-11-20 | CPS ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Mt. Province | 305260 | Panabungen Sschool of Arts, trades, and Home Industries | BESAO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8724965.051 |  |  | Completed | 1 |  |  | CA0514S00019 | 15PI0051 | 2015-09-10 | 2015-09-10 | 2015-09-24 | 2015-10-30 | 2015-11-16 | SUMAG BUILDERS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Mt. Province | 305261 | Paracelis NHS | PARACELIS | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6394337.6381 |  |  | Completed | 1 |  |  | CA0514S00018 | 15PI0047 | 2015-09-10 | 2015-09-08 | 2015-09-22 | 2015-10-21 |  | JJJ-A CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Mt. Province | 305231 | Paracelis Technical & Vocational High School | PARACELIS | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | Completed | 1 |  |  | CA0514S00017 | 15PI0046 | 2015-09-08 | 2015-09-08 | 2015-09-22 | 2015-10-21 |  | CPS ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Mt. Province | 305262 | Pingad NHS | SABANGAN | 0 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10817131.51 |  |  | Completed | 1 |  |  | CA0514S00012 | 15PI0039 | 2015-11-15 | 2015-11-25 | 2015-12-08 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Mt. Province | 319219 | Saclit NHS | SADANGA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1121674.0568 |  |  | Completed | 1 | 2014-11-20 | 2015-01-15 | CA0514S00002 | 14PI0023 | 2014-08-06 | 2014-08-08 | 2014-08-11 | 2014-09-17 | 2014-09-28 | JJJ-A CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Mt. Province | 305264 | Sadanga NHS | SADANGA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8289965.051 |  |  | Completed | 1 |  |  | CA0514S00015 | 15PI0044 | 2015-09-10 | 2015-09-10 | 2015-09-24 | 2015-10-30 |  | UPLAND CONSTRUCTION AND ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Mt. Province | 136277 | Saliok ES | NATONIN | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2969129.6629 |  |  | Completed | 1 | 2015-02-19 | 2015-05-25 | CA0514S00007 | 14PI0017 | 2014-08-06 | 2014-08-08 | 2014-08-11 | 2014-09-17 | 2014-10-01 | JJA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Mt. Province | 136313 | San Rafael ES | PARACELIS | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2003621.7457 |  |  | Completed | 1 | 2015-01-20 | 2015-01-15 | CA0514S00005 | 14PI0019 | 2014-08-06 | 2014-08-08 | 2014-08-11 | 2014-09-17 | 2014-10-01 | JJJ-A CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Mt. Province | 305267 | Tadian School of Arts & Trades | TADIAN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1151929.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2014 | CAR | Mt. Province | 305267 | Tadian School of Arts & Trades | TADIAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8484965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Mt. Province | 136280 | Tonglayan ES | NATONIN | 0 | 1 | 3 | 1STY 2CL and 1STY 1CL | 2014 K10 BATCH 1 | 3219942.8241 |  |  | Completed | 1 | 2015-02-19 | 2015-05-30 | CA0514S00006 | 14PI0017 | 2014-08-06 | 2014-08-08 | 2014-08-11 | 2014-09-17 | 2014-10-01 | BENTRIX BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Mt. Province | 136266 | Ut Utan PS | BONTOC (Capital) | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4322049.6094 |  |  | Completed | 1 | 2015-08-15 | 2015-10-31 | CA0514S00010 | 14PI0005 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-31 | 2015-04-20 | JJJ-A CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Tabuk City | 305198 | Balawag National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-12-19 |  | CA0414S00022 | 15PH0066 | 2015-06-14 | 2015-07-10 | 2015-08-17 | 2015-09-08 | 2015-09-17 | BALLIGI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Tabuk City | 136001 | Balong ES | CITY OF TABUK (Capital) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3152592.44 |  |  | Completed | 1 | 2016-01-25 |  | CA0414S00038 | 15PH0094 | 2015-08-10 | 2015-08-11 | 2015-08-24 | 2015-09-14 | 2015-09-22 | BALLIGI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | CAR | Tabuk City | 136002 | Bayabat ES | CITY OF TABUK (Capital) | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6519337.6381 |  |  | Completed | 1 | 2016-01-25 |  | CA0414S00039 | 15PH0095 | 2015-08-10 | 2015-08-11 | 2015-08-24 | 2015-09-14 | 2015-09-22 | MCPC BUILDERS & DEVELOPERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | CAR | Tabuk City | 305203 | Cudal National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-10-19 | 2015-11-10 | CA0414S00026 | 15PH0067 | 2015-06-14 | 2015-06-16 | 2015-06-29 | 2015-07-08 | 2015-07-16 | RMG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Tabuk City | 220532 | Kalinga Special Education Center | CITY OF TABUK (Capital) | 0 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10517131.51 |  |  | Completed | 1 | 2016-03-23 |  | CA0414S00037 | 15PH0090 | 2015-08-10 | 2015-08-11 | 2015-08-24 | 2015-10-02 | 2015-10-19 | Hi-Tone Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | CAR | Tabuk City | 305212 | Nambaran Agro-Industrial National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2016-03-16 |  | CA0414S00029 | 15PH0064 | 2015-06-14 | 2015-07-10 | 2015-10-13 | 2015-11-20 | 2015-11-27 | BALLIGI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Tabuk City | 305222 | New Tanglag National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-10-31 | 2015-12-10 | CA0414S00025 | 15PH0065 | 2015-06-14 | 2015-06-16 | 2015-06-29 | 2015-07-22 | 2015-07-29 | RMG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | CAR | Tabuk City | 136010 | San Juan Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6519337.6381 |  |  | Completed | 1 | 2016-01-25 |  | CA0414S00040 | 15PH0091 | 2015-08-10 | 2015-08-11 | 2015-08-24 | 2015-09-14 | 2015-09-22 | MCPC BUILDERS & DEVELOPERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.