## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | DUE TO | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | SCOPE | Unnamed: 45 | Status as of July 4, 2025
QRF 2019 | CARAGA | Surigao City | 132249 | Day-asan ES | SURIGAO CITY (Capital) | 2 | 1 | 3 | 1STY3CL | 5211417.5351 | 1 | 5163772.87 | Completed | 1 | [5 empty] | 2019-06-20 | 2019-07-02 | 2019-07-18 | 2019-07-22 | RF Varquez Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | EARTHQUAKE |  |  |  | REPLACEMENT | Completed
QRF 2019 | CARAGA | Surigao City | 132257 | Ouano ES | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 3449081.1441 | 1 | 3440000 | Completed | 1 | [5 empty] | 2019-06-20 | 2019-07-02 | 2019-07-18 | 2019-07-22 | Windfall Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | EARTHQUAKE |  |  |  | REPLACEMENT | Completed
QRF 2020 | CARAGA | Butuan City | 304765 | Anticala NHS | BUTUAN CITY (Capital) | 1 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 3820757.9 | 1 | 3781533.97 | Completed | 1 | 2021-07-15 |  |  |  |  | 2019-06-20 | 2019-07-02 | 2019-07-18 | 2019-07-22 | Regerys Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CARAGA | Butuan City | 317507 | Consuelo National High School | BUTUAN CITY (Capital) | 1 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 3408125.05 | 1 | 3348273.9708 | Completed | 1 | 2021-07-15 |  |  |  |  | 2019-06-20 | 2019-07-02 | 2019-07-18 | 2019-07-22 | Two J.E. Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2022 | CARAGA | Agusan del Norte | 131450 | Kitcharao CES | KITCHARAO | 2 | 1 | 12 | NEW CONSTRUCTION | 26048980.31 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Agusan del Norte | 131533 | Panaytayon ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 2 | NEW CONSTRUCTION | 5400000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Cabadbaran City | 500312 | North Cabadbaran CES | CITY OF CABADBARAN | 2 | 1 | 16 | REPAIR/ REHABILITATION | 12932883.84 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Cabadbaran City | 131580 | South Cabadbaran CES | CITY OF CABADBARAN | 2 | 1 | 12 | REPAIR/ REHABILITATION | 9516868.87 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132505 | Rizal Central Elementary School | BASILISA (RIZAL) | 0 | 1 | 5 | REPAIR/ REHABILITATION | 4805281.92 | 1 | 4660850 | Completed | 1 |  |  | INFRA22 -004-08 |  | 2022-05-29 | 2022-06-17 | 2022-06-30 | 2022-07-21 |  | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 305745 | Roma National High School | BASILISA (RIZAL) | 0 | 1 | 4 | NEW CONSTRUCTION | 11799061.85 | 1 |  | Completed | 1 | [10 empty] | realigned from rizal ces to roman nhs | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-04-01 | 11.23 |  | 1 | 4 | 11799061.85 | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132510 | Tag-abaca Central Elementary School | BASILISA (RIZAL) | 0 | 1 | 13 | REPAIR/ REHABILITATION | 10440653.42 | 1 | 9151362.58 | Completed | 1 |  |  | INFRA22 -004-17 |  | 2022-05-29 | 2022-06-22 | 2022-07-08 | 2022-08-10 |  | J-R3 CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132510 | Tag-abaca Central Elementary School | BASILISA (RIZAL) | 0 |  | 2 | NEW CONSTRUCTION | 7651642.97 | 1 | 6884671.71 | Completed | 1 |  |  | INFRA22 -004-17 |  | 2022-05-29 | 2022-06-22 | 2022-07-08 | 2022-08-10 |  | CAPJ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132360 | Cagdianao Central Elementary School | CAGDIANAO | 0 | 1 | 13 | REPAIR/ REHABILITATION | 11716714.8 | 1 | 11361134.25 | Completed | 1 |  |  | INFRA22 -004-15 |  | 2022-05-29 | 2022-06-22 | 2022-07-08 | 2022-08-10 |  | RJB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132360 | Cagdianao Central Elementary School | CAGDIANAO | 0 |  | 5 | NEW CONSTRUCTION | 17737420.56 | 1 | 17289156.5 | Completed | 1 |  |  | INFRA22 -004-15 |  | 2022-05-29 | 2022-06-22 | 2022-07-08 | 2022-08-10 |  | RJB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132364 | Longos Primary School | CAGDIANAO | 0 | 1 | 2 | NEW CONSTRUCTION | 7491972.35 | 1 |  | Completed | 1 | [10 empty] | REALIGNED from Loreto CES to Longons PS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-04-01 | 12.24 |  | 1 | 2 | 7491972.35 | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132396 | Dinagat Central Elementary School | DINAGAT | 0 | 1 | 11 | REPAIR/ REHABILITATION | 6250248.57 | 1 | 6248000 | Completed | 1 |  |  | INFRA22 -004-04 |  | 2022-05-29 | 2022-06-10 | 2022-06-23 | 2022-07-21 |  | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132396 | Dinagat Central Elementary School | DINAGAT | 0 |  | 3 | NEW CONSTRUCTION | 10838276.55 | 1 | 10337426.55 | Completed | 1 |  |  | INFRA22 -004-03 |  | 2022-05-29 | 2022-06-10 | 2022-06-23 | 2022-07-21 |  | ALGAMON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 | 1 | 24 | REPAIR/ REHABILITATION | 18432877.62 | 1 | 18430831.63 | Completed | 1 |  |  | INFRA22 -004-02 |  | 2022-05-29 | 2022-06-10 | 2022-06-23 | 2022-07-21 |  | RJB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 |  | 15 | NEW CONSTRUCTION | 46467511.8 | 1 | 43182316.37 | Completed | 1 |  |  | INFRA22 -004-03 |  | 2022-05-29 | 2022-06-10 | 2022-06-23 | 2022-07-21 |  | CARTESAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 | 2023-03-01 | 11.23 |  | 1 | 15 | 46467511.8 | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132305 | Albor Central Elementary School | LIBJO (ALBOR) | 0 | 1 | 8 | REPAIR/ REHABILITATION | 8560664.04 | 1 | 7726785.36 | Completed | 1 | [9 empty] | CAPJ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 | 2023-04-01 | 5.24 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132305 | Albor Central Elementary School | LIBJO (ALBOR) | 0 |  | 4 | NEW CONSTRUCTION | 15373441.02 | 1 | 14596447.77 | Completed | 1 | [9 empty] | ALGAMON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-04-01 | 5.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132308 | Bolodbolod Central Elementary School | LIBJO (ALBOR) | 0 | 1 | 7 | REPAIR/ REHABILITATION | 5231820.18 | 1 | 4970229.76 | Completed | 1 |  |  | INFRA22 -004-12 |  | 2022-05-29 | 2022-06-21 | 2022-07-07 | 2022-08-10 |  | ALGAMON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2023-03-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132308 | Bolodbolod Central Elementary School | LIBJO (ALBOR) | 0 |  | 7 | NEW CONSTRUCTION | 23044703.29 | 1 | 20359995 | Completed | 1 |  |  | INFRA22 -004-13 |  | 2022-05-29 | 2022-06-21 | 2022-07-07 | 2022-08-10 |  | ALGAMON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132317 | Plaridel Elementary School | LIBJO (ALBOR) | 0 | 1 | 6 | NEW CONSTRUCTION | 20454827.35 | 1 | 20447120.22 | Completed | 1 |  |  | INFRA22 -004-14 |  | 2022-05-29 | 2022-06-21 | 2022-07-07 | 2022-08-10 |  | ARDRAW CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 2023-04-01 | 5.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132424 | Loreto Central Elementary School | LORETO | 0 | 1 | 18 | REPAIR/ REHABILITATION | 5797868.93 | 1 | 5792000 | Completed | 1 |  |  | INFRA22 -004-07 |  | 2022-05-29 | 2022-06-17 | 2022-06-30 | 2022-07-21 |  | WINDFALL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132513 | Aurelio Elementary School | SAN JOSE (Capital) | 0 | 1 | 10 | REPAIR/ REHABILITATION | 10981671.28 | 1 |  | Completed | 1 | [10 empty] | realigned from cab-ilan to aurelio | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 | 2023-04-01 | 11.23 |  | 1 | 10 | 10981671.28 | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132522 | San Jose CES-SPED Center | SAN JOSE (Capital) | 0 | 1 | 20 | REPAIR/ REHABILITATION | 10356113.41 | 1 | 9722672.08 | Completed | 1 |  |  | INFRA22 -004-09 |  | 2022-05-29 | 2022-06-17 | 2022-06-30 | 2022-07-21 |  | AMA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132559 | Tubajon Central Elementary School | TUBAJON | 0 | 1 | 5 | REPAIR/ REHABILITATION | 4361481.87 | 1 | 4270000 | Completed | 1 |  |  | INFRA22 -004-05 |  | 2022-05-29 | 2022-06-17 | 2022-06-30 | 2022-07-21 |  | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132559 | Tubajon Central Elementary School | TUBAJON | 0 |  | 8 | NEW CONSTRUCTION | 23418608.29 | 1 | 23390000 | Completed | 1 |  |  | INFRA22 -004-06 |  | 2022-05-29 | 2022-06-17 | 2022-06-30 | 2022-07-21 |  | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 | 2023-04-01 | 11.23 |  | 1 | 8 | 23418608.29 | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132215 | Baybay Elementary School | BURGOS | 1 | 1 | 7 | REPAIR/ REHABILITATION | 2730000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132215 | Baybay Elementary School | BURGOS | 1 |  | 6 | NEW CONSTRUCTION | 16684552.75 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 2023-02-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132216 | Bitaug Elementary School | BURGOS | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1530000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132216 | Bitaug Elementary School | BURGOS | 1 |  | 2 | NEW CONSTRUCTION | 6478614.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132217 | Burgos Central Elementary School | BURGOS | 1 | 1 | 11 | REPAIR/ REHABILITATION | 4965000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132217 | Burgos Central Elementary School | BURGOS | 1 |  | 6 | NEW CONSTRUCTION | 16714552.75 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1 | 1 | 13 | REPAIR/ REHABILITATION | 4412499.08 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 | 2023-02-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1 |  | 4 | NEW CONSTRUCTION | 10265937.89 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-02-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132218 | Matin-ao Elementary School | BURGOS | 1 | 1 | 3 | REPAIR/ REHABILITATION | 2445000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132218 | Matin-ao Elementary School | BURGOS | 1 |  | 4 | NEW CONSTRUCTION | 10250937.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132219 | San Mateo Elementary School | BURGOS | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1835000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132219 | San Mateo Elementary School | BURGOS | 1 |  | 4 | NEW CONSTRUCTION | 10230937.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132139 | Dapa Central Elementary School & SPED Center | DAPA | 1 | 1 | 39 | REPAIR/ REHABILITATION | 11650000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 39 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132139 | Dapa Central Elementary School & SPED Center | DAPA | 1 |  | 12 | NEW CONSTRUCTION | 33369105.5 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132179 | Sayak Elementary School | DEL CARMEN | 1 | 1 | 5 | REPAIR/ REHABILITATION | 4414304.45 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132179 | Sayak Elementary School | DEL CARMEN | 1 |  | 4 | NEW CONSTRUCTION | 10310937.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132225 | Bongdo Elementary School | SAN BENITO | 1 | 1 | 5 | REPAIR/ REHABILITATION | 3225244.54 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132225 | Bongdo Elementary School | SAN BENITO | 1 |  | 4 | NEW CONSTRUCTION | 10230937.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132226 | Maribojoc Elementary School | SAN BENITO | 1 | 1 | 3 | REPAIR/ REHABILITATION | 2345000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132226 | Maribojoc Elementary School | SAN BENITO | 1 |  | 5 | NEW CONSTRUCTION | 14966112.57 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132227 | Nuevo Campo Elementary Schoool | SAN BENITO | 1 | 1 | 2 | NEW CONSTRUCTION | 6495614.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132228 | Pitogo Elementary School | SAN BENITO | 1 | 1 | 2 | NEW CONSTRUCTION | 6583614.88 | 1 |  | Completed | 1 | [10 empty] | under posqua | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132230 | San Benito Central Elementary School | SAN BENITO | 1 | 1 | 14 | REPAIR/ REHABILITATION | 5528191.84 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132230 | San Benito Central Elementary School | SAN BENITO | 1 |  | 2 | NEW CONSTRUCTION | 6477614.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 1 | 1 | 12 | REPAIR/ REHABILITATION | 8000000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132229 | San Juan Elementary School | SAN BENITO | 1 | 1 | 2 | REPAIR/ REHABILITATION | 1614929.15 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132229 | San Juan Elementary School | SAN BENITO | 1 |  | 2 | NEW CONSTRUCTION | 6483614.89 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132234 | Nueva Estrella Central Elementary School | SOCORRO | 1 | 1 | 7 | REPAIR/ REHABILITATION | 6492671.48 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132234 | Nueva Estrella Central Elementary School | SOCORRO | 1 |  | 3 | NEW CONSTRUCTION | 8407192.02 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132224 | Socorro Central Elementary School and SPED Center | SOCORRO | 1 | 1 | 14 | REPAIR/ REHABILITATION | 12220934.1957 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132224 | Socorro Central Elementary School and SPED Center | SOCORRO | 1 |  | 6 | NEW CONSTRUCTION | 16714552.75 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao City | 132290 | C.V. Diez Mem. CES | SURIGAO CITY (Capital) | 2 | 1 | 35 | REPAIR/ REHABILITATION | 9865890.42 | 1 | 9850760.1575 | Completed | 1 | 2023-01-14 |  |  |  |  | 2022-05-20 | 2022-06-03 | 2022-08-08 | 2022-08-17 | E-JOB CONSTRUCTION & SUPPLY, OPC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 1 | 0 | 2023-02-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao City | 132290 | C.V. Diez Mem. CES | SURIGAO CITY (Capital) | 2 |  | 4 | NEW CONSTRUCTION | 9464507.64 | 1 | 9098337.3574 | Completed | 1 | 2023-01-24 |  |  |  |  | 2022-05-20 | 2022-06-06 | 2022-08-08 | 2022-08-17 | EYT CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-02-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao City | 132247 | Canlanipa Central Elementary School | SURIGAO CITY (Capital) | 2 | 1 | 20 | REPAIR/ REHABILITATION | 10034402.06 | 1 | 10023076.224 | Completed | 1 | 2023-01-14 |  |  |  |  | 2022-05-20 | 2022-06-03 | 2022-08-08 | 2022-08-17 | E-JOB CONSTRUCTION & SUPPLY, OPC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 1 | 0 | 2023-02-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao City | 132299 | Mat-i Central Elementary School | SURIGAO CITY (Capital) | 2 | 1 | 10 | REPAIR/ REHABILITATION | 8671265.02 | 1 | 6032737.6594 | Completed | 1 | 2022-12-15 |  |  |  |  | 2022-05-20 | 2022-06-03 | 2022-08-09 | 2022-08-17 | J-R3 CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 | 2023-02-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao City | 132299 | Mat-i Central Elementary School | SURIGAO CITY (Capital) | 2 |  | 8 | NEW CONSTRUCTION | 19143244.17 | 1 | 18709118.816 | Completed | 1 | 2023-03-05 |  |  |  |  | 2022-05-20 | 2022-06-06 | 2022-08-08 | 2022-08-17 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 | 2023-02-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao City | 132271 | Surigao City CES | SURIGAO CITY (Capital) | 2 | 1 | 21 | REPAIR/ REHABILITATION | 7918271.28 | 1 | 7906780.6257 | Completed | 1 | 2022-12-15 |  |  |  |  | 2022-05-20 | 2022-06-03 | 2022-08-08 | 2022-08-17 | P & G CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao City | 132271 | Surigao City CES | SURIGAO CITY (Capital) | 2 |  | 2 | NEW CONSTRUCTION | 6092191.78 | 1 | 5049241.825 | Completed | 1 | 2022-11-25 |  |  |  |  | 2022-05-20 | 2022-06-06 | 2022-08-08 | 2022-08-17 | AMALGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-02-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao City | 132287 | Surigao West Central Elementary School | SURIGAO CITY (Capital) | 2 | 1 | 32 | REPAIR/ REHABILITATION | 15985858.62 | 1 | 15971503.82 | Completed | 1 | 2023-02-13 |  |  |  |  | 2022-05-20 | 2022-06-03 | 2022-08-08 | 2022-08-17 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 1 | 0 | 2023-02-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao City | 132287 | Surigao West Central Elementary School | SURIGAO CITY (Capital) | 2 |  | 3 | NEW CONSTRUCTION | 7885468.72 | 1 | 7602801.87 | Completed | 1 | 2022-12-30 |  |  |  |  | 2022-05-20 | 2022-06-06 | 2022-08-08 | 2022-08-17 | AMALGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-02-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132342 | Bacuag CES | BACUAG | 2 | 1 | 11 | REPAIR/ REHABILITATION | 3540791.78 | 1 | 3358544.92 | Completed | 1 | 2022-11-29 |  | 003-QRF 2022-CARAGA | 018-2022 | 2022-04-20 | 2022-04-28 | 2022-05-12 | 2022-05-27 | 2022-05-28 | JJRC CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132342 | Bacuag CES | BACUAG | 2 |  | 4 | NEW CONSTRUCTION | 9918782.27 | 1 | 8620681.42 | Completed | 1 | 2022-11-29 |  | 015-QRF 2022-CARAGA | 018-2022 | 2022-06-13 | 2022-06-21 | 2022-07-04 | 2022-05-27 | 2022-05-28 | AMALGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132346 | Campo ES | BACUAG | 2 | 1 | 8 | REPAIR/ REHABILITATION | 5262784.16 | 1 |  | Completed | 1 |  |  | 004-QRF 2022-CARAGA |  | 2022-04-20 | 2022-04-28 | 2022-05-12 |  |  |  | For Rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132346 | Campo ES | BACUAG | 2 |  | 3 | NEW CONSTRUCTION | 8170250.96 | 1 | 7756361.03 | Completed | 1 |  |  | 016-QRF 2022-CARAGA |  | 2022-06-13 | 2022-06-21 | 2022-07-04 |  |  | AMALGO CONSTRUCTION | For Rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132378 | Claver Central Elementary School | CLAVER | 2 | 1 | 9 | REPAIR/ REHABILITATION | 1584096.46 | 1 | 1580797.14 | Completed | 1 | 2022-12-30 |  | 007-QRF 2022-CARAGA | 021-2022 | 2022-04-21 | 2022-04-29 | 2022-05-13 | 2022-06-06 | 2022-05-28 | SEGUA CONSTRUCTION AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132378 | Claver Central Elementary School | CLAVER | 2 |  | 4 | NEW CONSTRUCTION | 9884507.64 | 1 | 1580797.14 | Completed | 1 | 2022-12-30 |  | 018-QRF 2022-CARAGA | 021-2022 | 2022-04-21 | 2022-04-29 | 2022-05-13 | 2022-06-06 | 2022-05-28 | SEGUA CONSTRUCTION AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132407 | Gigaquit Central Elementary School | GIGAQUIT | 2 | 1 | 6 | REPAIR/ REHABILITATION | 4493535.97 | 1 |  | Completed | 1 |  |  | 008-QRF 2022-CARAGA | [7 empty] | For Rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132407 | Gigaquit Central Elementary School | GIGAQUIT | 2 |  | 3 | NEW CONSTRUCTION | 8170250.96 | 1 |  | Completed | 1 |  |  | 019-QRF 2022-CARAGA | [7 empty] | For Rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132434 | Mainit CES | MAINIT | 2 | 1 | 15 | REPAIR/ REHABILITATION | 10718781.28 | 1 | 10670726.85 | Completed | 1 |  |  | 011-QRF 2022-CARAGA |  | 2022-04-21 | 2022-04-29 | 2022-05-13 |  |  | MICAH CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132434 | Mainit CES | MAINIT | 2 |  | 8 | NEW CONSTRUCTION | 20071355.67 | 1 | 20066581.62 | Completed | 1 |  |  | 022-QRF 2022-CARAGA |  | 2022-06-13 | 2022-06-21 | 2022-07-04 |  |  | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132437 | Matin-ao CES | MAINIT | 2 | 1 | 16 | REPAIR/ REHABILITATION | 10746950.83 | 1 |  | Completed | 1 |  |  | 012-QRF 2022-CARAGA |  | 2022-04-20 | 2022-04-29 | 2022-05-13 |  |  |  | For, reconsideration of the 2nd lowest bidder | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132437 | Matin-ao CES | MAINIT | 2 |  | 2 | NEW CONSTRUCTION | 6240190.85 | 1 |  | Completed | 1 |  |  | 023-QRF 2022-CARAGA |  | 2022-04-20 | 2022-04-29 | 2022-05-13 |  |  |  | For, reconsideration of the 2nd lowest bidder | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132478 | Placer Central Elementary School | PLACER | 2 | 1 | 4 | REPAIR/ REHABILITATION | 588886.08 | 1 | 585886.08 | Completed | 1 | 2022-10-30 |  | 009-QRF 2022-CARAGA | 022-2022 | 2022-04-21 | 2022-04-29 | 2022-05-13 | 2022-05-27 | 2022-05-28 | DJNC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132478 | Placer Central Elementary School | PLACER | 2 |  | 4 | NEW CONSTRUCTION | 9884507.64 | 1 | 9879769.75 | Completed | 1 | 2022-10-30 |  | 020-QRF 2022-CARAGA | 022-2022 | 2022-06-13 | 2022-06-21 | 2022-07-04 | 2022-05-27 | 2022-05-28 | AMALGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132479 | Placer West CES | PLACER | 2 | 1 | 4 | REPAIR/ REHABILITATION | 550250.03 | 1 | 547043.86 | Completed | 1 | 2022-10-30 |  | 010-QRF 2022-CARAGA | 023-2022 | 2022-04-21 | 2022-04-29 | 2022-05-13 | 2022-05-27 | 2022-05-28 | DJNC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132479 | Placer West CES | PLACER | 2 |  | 2 | NEW CONSTRUCTION | 6135190.85 | 1 | 6114918.5 | Completed | 1 | 2022-10-30 |  | 021-QRF 2022-CARAGA | 023-2022 | 2022-06-13 | 2022-06-21 | 2022-07-04 | 2022-05-27 | 2022-05-28 | AMALGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132331 | Anao-aon CES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 21 | REPAIR/ REHABILITATION | 14288696.79 | 1 | 12572561.43 | Completed | 1 | 2023-02-24 |  | 001-QRF 2022-CARAGA | 016-2022 | 2022-04-20 | 2022-04-28 | 2022-05-12 | 2022-05-27 | 2022-05-28 | BAMBOE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132331 | Anao-aon CES | SAN FRANCISCO (ANAO-AON) | 2 |  | 2 | NEW CONSTRUCTION | 6817690.85 | 1 | 6795903.07 | Completed | 1 | 2023-02-24 |  | 013-QRF 2022-CARAGA | 016-2022 | 2022-06-13 | 2022-06-21 | 2022-07-04 | 2022-05-27 | 2022-05-28 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132333 | Banbanon ES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 6 | REPAIR/ REHABILITATION | 4921929.24 | 1 | 3636090.36 | Completed | 1 | 2023-01-29 |  | 002-QRF 2022-CARAGA | 017-2022 | 2022-04-20 | 2022-04-28 | 2022-05-12 | 2022-05-24 | 2022-05-28 | 3C'SL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132333 | Banbanon ES | SAN FRANCISCO (ANAO-AON) | 2 |  | 4 | NEW CONSTRUCTION | 9412007.64 | 1 | 9402006.78 | Completed | 1 | 2023-01-29 |  | 014-QRF 2022-CARAGA | 017-2022 | 2022-06-13 | 2022-06-21 | 2022-07-04 | 2022-05-24 | 2022-05-28 | EYT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132526 | Dakung Patag ES | SISON | 2 | 1 | 6 | REPAIR/ REHABILITATION | 4493535.97 | 1 | 3544784.88 | Completed | 1 | 2022-11-30 |  | 006-QRF 2022-CARAGA | 020-2022 | 2022-04-21 | 2022-04-29 | 2022-05-13 | 2022-05-27 | 2022-05-28 | JR3 CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132534 | Sison CES | SISON | 2 | 1 | 10 | REPAIR/ REHABILITATION | 4043914.75 | 1 | 4036000 | Completed | 1 | 2023-01-25 |  | 005-QRF 2022-CARAGA | 019-2022 | 2022-04-21 | 2022-04-29 | 2022-05-13 | 2022-05-24 | 2022-05-28 | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132534 | Sison CES | SISON | 2 |  | 2 | NEW CONSTRUCTION | 6660190.85 | 1 | 5124396.34 | Completed | 1 | 2023-01-25 |  | 017-QRF 2022-CARAGA | 019-2022 | 2022-06-13 | 2022-06-21 | 2022-07-04 | 2022-05-24 | 2022-05-28 | FHD CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Cabadbaran City | 131520 | Del Pilar CES | CITY OF CABADBARAN | 2nd | 1 | 2 | Replacement | 6233080.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Cabadbaran City | 131520 | Del Pilar CES | CITY OF CABADBARAN | 2nd | 1 | 11 | REPAIR OF CLASSROOMS | 8638383.7717 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132176 | Numancia Central Elementary School | DEL CARMEN | 1st | 1 | 6 | Replacement | 16825000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132176 | Numancia Central Elementary School | DEL CARMEN | 1st | 1 | 11 | REPAIR OF CLASSROOMS | 11185525 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132152 | General Luna CES | GENERAL LUNA | 1st | 1 | 6 | Replacement | 21971961.6669 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132152 | General Luna CES | GENERAL LUNA | 1st | 1 | 41 | REPAIR OF CLASSROOMS | 18420393.95 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41 | 1 | 0 |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132190 | Pilar Central Elementary School | PILAR | 1st | 1 | 2 | Replacement | 6493614.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132190 | Pilar Central Elementary School | PILAR | 1st | 1 | 15 | REPAIR OF CLASSROOMS | 7449645.76 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132199 | San Isidro Central Elementary School | SAN ISIDRO | 1st | 1 | 5 | Replacement | 15070000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132199 | San Isidro Central Elementary School | SAN ISIDRO | 1st | 1 | 14 | REPAIR OF CLASSROOMS | 4290000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132213 | Sapao Central Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 6 | Replacement | 16910000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 10.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132213 | Sapao Central Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 10 | REPAIR OF CLASSROOMS | 6355506.77 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao City | 132289 | B. Vasquez Memorial Central Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 4 | Replacement | 9464507.64 | 1 | 6473723.23 | Completed | 1 | 2024-04-11 | 2024-11-12 |  | FY-2023-INFRA-002 |  | 2023-03-17 | 2023-03-30 | 2023-07-05 | 2023-06-16 | NMSJ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 4.25 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao City | 132289 | B. Vasquez Memorial Central Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3871843.67 | 1 | 2575796.82 | completed | 1 | 2023-10-12 | 2023-09-27 |  | FY-2023-INFRA-005 |  | 2023-03-17 | 2023-03-30 | 2023-05-26 | 2023-06-14 | LVRO CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 12.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao City | 132298 | Margarita Mem. CES | SURIGAO CITY (Capital) | 2nd | 1 | 8 | Replacement | 19298722.35 | 1 | 15565860.14 | completed | 1 | 2024-02-17 | 2024-03-01 |  | FY-2023-INFRA-003 |  | 2023-03-17 | 2023-03-30 | 2023-06-09 | 2023-06-23 | LVRO CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | 4.25 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao City | 132298 | Margarita Mem. CES | SURIGAO CITY (Capital) | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2955303.79 | 1 | 1949806.42 | completed | 1 | 2023-10-12 | 2023-09-08 |  | FY-2023-INFRA-006 |  | 2023-03-17 | 2023-03-30 | 2023-05-26 | 2023-06-15 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 12.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao City | 132254 | Mariano Espina Memorial Central Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 11 | REPAIR OF CLASSROOMS | 9832305.46 | 1 | 6460000 | completed | 1 | 2023-11-11 | 2023-10-24 |  | FY-2023-INFRA-004 |  | 2023-03-17 | 2023-03-30 | 2023-05-26 | 2023-06-15 | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | 12.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao City | 132266 | Martinez ES | SURIGAO CITY (Capital) | 2nd | 1 | 2 | Replacement | 6092191.78 | 1 | 4187236.06 | completed | 1 | 2023-11-12 | 2024-01-21 |  | FY-2023-INFRA-001 |  | 2023-03-17 | 2023-03-30 | 2023-05-26 | 2023-06-16 | NMSJ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 4.25 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao del Norte | 132321 | Alegria CES | ALEGRIA | 2nd | 1 | 4 | Replacement | 10043464.8 | 1 | 7116915.56 | Completed | 1 | 2023-08-31 | 2023-10-10 | 2023-001-QRF-CARAGA | 006-2023 | 2023-02-14 | 2023-02-22 | 2023-03-06 | 2023-03-20 | 2023-03-22 | JVM BOLLARD CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao del Norte | 132460 | Malimono Central Elementary School | MALIMONO | 2nd | 1 | 2 | Replacement | 6914571.58 | 1 | 4839178.48 | Completed | 1 | 2023-07-02 | 2024-02-02 | 2023-002-QRF-CARAGA | 007-2023 | 2023-02-14 | 2023-02-22 | 2023-03-06 | 2023-03-20 | 2023-03-22 | DANREV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao del Norte | 132548 | Tagana-an CES | TAGANA-AN | 2nd | 1 | 2 | Replacement | 6935571.58 | 1 | 5743445.77 | Completed | 1 | 2023-08-06 | 2024-02-02 | 2023-003-QRF-CARAGA | 008-2023 | 2023-02-14 | 2023-02-22 | 2023-03-06 | 2023-03-20 | 2023-03-22 | LVRO CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao del Norte | 132568 | Tubod CES | TUBOD | 2nd | 1 | 3 | Replacement | 8275250.96 | 1 | 5842493.81 | Completed | 1 | 2023-08-06 | 2023-10-10 | 2023-004-QRF-CARAGA | 009-2023 | 2023-02-14 | 2023-02-22 | 2023-03-06 | 2023-03-20 | 2023-03-22 | JVM BOLLARD CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2023 | CARAGA | Agusan del Norte | 131431 | Colorado ES | JABONGA | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 5714123.73 | 1 |  | Ongoing | 0.7 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0.7 | 0 |  |  | SHEARLINE & LPA & TY ODETTE |  |  |  | REPAIR | Ongoing
QRF 2023 | CARAGA | Butuan City | 132034 | Imelda ES | BUTUAN CITY (Capital) | 1 | 1 | 0 | SLOPE PROTECTION | 3526609.12 | 1 |  | Ongoing | 0.1 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 |  |  | SOIL EROSION/LANDSLIDE |  |  |  | SLOPE PROTECTION | Ongoing
QRF 2023 | CARAGA | Butuan City | 137019 | Sinaka IPED Elementary School | BUTUAN CITY (Capital) | 1st | 1 | 4 | 1STY4CL | 12000000 | 2- NC | 9800419.2 | Ongoing | 0.03 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.03 | 0 | [6 empty] | REPLACEMENT | Ongoing
QRF 2023 | CARAGA | Surigao del Norte | 132344 | Cabugao ES | BACUAG | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 3191536.58 | 1 | 2261196.39 | Completed | 1 | 2023-09-23 | 2023-10-18 | 001-QRF 2023-CARAGA | 007B-2023 | 2023-04-20 | 2023-04-28 | 2023-05-10 | 2023-05-24 | 2023-05-26 | J-R3 CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 132352 | Payapag Elementary School | BACUAG | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 3393326.28 | 1 | 2459559.14 | Completed | 1 | 2023-09-23 | 2023-10-18 | 002-QRF 2023-CARAGA | 008B-2023 | 2023-04-20 | 2023-04-28 | 2023-05-10 | 2023-05-24 | 2023-05-26 | J-R3 CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 304826 | Gigaquit National School of Home Industries | GIGAQUIT | 2 | 1 | 14 | REPAIR OF CLASSROOMS | 8340458.83 | 1 | 6174329.9 | Completed | 1 | 2023-11-22 | 2023-03-05 | 006-QRF 2023-CARAGA | 0013B-2023 | 2023-04-20 | 2023-04-28 | 2023-05-10 | 2023-05-24 | 2023-05-26 | J-R3 CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | 8.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 132412 | Poniente Elementary School | GIGAQUIT | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 4022170.9 | 1 | 2841767.04 | Completed | 1 | 2023-10-08 | 2023-11-02 | 003-QRF 2023-CARAGA | 009B-2023 | 2023-04-20 | 2023-04-28 | 2023-05-10 | 2023-05-24 | 2023-05-26 | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 132435 | Mansayao ES | MAINIT | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 4518379.12 | 1 | 3213539.36 | Completed | 1 | 2023-11-02 | 2023-11-27 | 004-QRF 2023-CARAGA | 010-2023 | 2023-04-20 | 2023-04-28 | 2023-05-10 | 2023-05-24 | 2023-05-26 | J-R3 CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 304845 | Amando A. Fabio Memorial National High School (Sta. Cruz National School) | PLACER | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3278625.08 | 1 | 2129798.35 | Completed | 1 | 2023-09-23 | 2023-09-23 | 008-QRF 2023-CARAGA | 015-2023 | 2023-04-20 | 2023-04-28 | 2023-05-10 | 2023-05-24 | 2023-05-26 | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 304838 | Lakandula National High School | PLACER | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 910185.26 | 1 | 908916.88 | Completed | 1 | 2023-08-09 | 2023-08-09 | 007-QRF 2023-CARAGA | 014-2023 | 2023-04-20 | 2023-04-28 | 2023-05-10 | 2023-05-24 | 2023-05-26 | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 132476 | Pananay-an ES | PLACER | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1410767.81 | 1 | 1154062.1 | Completed | 1 | 2023-08-09 | 2023-09-03 | 005-QRF 2023-CARAGA | 011B-2023 | 2023-04-20 | 2023-04-28 | 2023-05-10 | 2023-05-24 | 2023-05-26 | ILMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Tandag City | 132964 | Engr. Nestor Ty Memorial Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 3 | 1STY3CL (WITH COMMON TOILET) | 10525907.02 | 1 |  | Ongoing | 0.1 | [8 empty] | 2023-07-04 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.1 | 0 |  |  | SHEARLINE & LPA |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | CARAGA | Tandag City | 132980 | Telaje Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 3 | 1STY3CL (WITH COMMON TOILET) | 10520708.47 | 1 |  | Ongoing | 0.1 | [8 empty] | 2023-07-04 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.1 | 0 |  |  | SHEARLINE & LPA |  |  |  | REPLACEMENT | Ongoing
QRF 2024 | CARAGA | Agusan del Norte | 131453 | San Isidro ES | KITCHARAO | 2nd | 1 | 7 | Repair of Classrooms | 14561894.93 | 1- R |  | Under Procurement | 0 | [10 empty] | tagbuaya es realigned to san isidro es | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Hinatuan) | 1 | 7 | 14561894.93 | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 131459 | Casiklan ES | LAS NIEVES | 1st | 1 | 4 | Repair of Classrooms | 8314893.17 | 1- R |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 131445 | Bliss Elementary School | KITCHARAO | 2nd | 1 | 5 | Repair of Classrooms | 9832308.28 | 1- R |  | Under Procurement | 0 | [10 empty] | E. G. Montilla ES realigned to bliss es | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Hinatuan) | 1 | 5 | 9832308.28 | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 131477 | Sagbuco ES | LAS NIEVES | 1st | 1 | 3 | Repair of Classrooms | 3609571.17 | 1- R |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 131480 | Tinucoran ES | LAS NIEVES | 1st | 1 | 3 | Repair of Classrooms | 3608521.17 | 1- R |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 131541 | La Paz ES | SANTIAGO | 2nd | 1 | 1 | Repair of Classrooms | 1517415.11 | 1- R |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 131549 | Bagang ES | BUENAVISTA | 2nd | 1 | 3 | Repair of Classrooms | 8457296.24 | 1- R |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 304683 | Guinabsan National High School - Simbalan National High School Annex | BUENAVISTA | 2nd | 1 | 2 | Repair of Classrooms | 2834759.63 | 1- R |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 317301 | Guinabsan National High School - Sangay National High School Annex | BUENAVISTA | 2nd | 1 | 4 | Repair of Classrooms | 9345844.95 | 1- R |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bayugan City | 131598 | Gethsemane ES | CITY OF BAYUGAN | 1st | 1 | 3 | Repair of Classrooms | 3609571.17 | 1- R |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132608 | Bebiano Alba Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 443180.99 | 1- R | 441862.82 | Ongoing | 0.85 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.85 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132609 | Bislig Central Elementary School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 215612.47 | 1- R | 214859.6 | Ongoing | 0.72 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.72 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132610 | Bucto Elementary School | CITY OF BISLIG | 2nd | 1 | 4 | Repair of Classrooms | 7644763.4 | 1- R | 442038.54 | Ongoing | 0.85 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.85 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132611 | Burboanan Elementary School | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 655408.84 | 1- R | 654212.19 | Ongoing | 0.59 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.59 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132612 | Caguyao Elementary School | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 7333326.75 | 1- R | 223314.49 | Ongoing | 0.65 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.65 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132613 | Coleto Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 435708.46 | 1- R | 428772.05 | Ongoing | 0.84 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.84 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132615 | F. C. Pedraverde-Lindo Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 435444.72 | 1- R | 434413.83 | Ongoing | 0.76 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.76 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132616 | Maharlika Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 435708.46 | 1- R | 427087.11 | Ongoing | 0.85 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.85 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132617 | Gerardo D. Verano Jr. Elementary School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 234381.7 | 1- R | 232280.97 | Ongoing | 0.71 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.71 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132618 | Isabelo Landeta Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 436939.23 | 1- R | 436084.86 | Ongoing | 0.59 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.59 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132619 | Mabog Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 447840.33 | 1- R | 446745.08 | Ongoing | 0.85 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.85 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132622 | Mantuyom Elementary School | CITY OF BISLIG | 2nd | 1 | 4 | Repair of Classrooms | 874669.67 | 1- R | 872863.55 | Ongoing | 0.85 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.85 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132623 | Ser-Fel Mone Elementary School | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 653123.13 | 1- R | 652420.61 | Ongoing | 0.57 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.57 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132624 | Olayvar Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 437554.61 | 1- R | 435387.95 | Ongoing | 0.81 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.81 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132627 | Puerto Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 438257.91 | 1- R | 429282.38 | Ongoing | 0.85 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.85 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132628 | R. Castillo Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 433334.83 | 1- R | 432366.6 | Completed | 1 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0.9 | 0.1 |  | 5.25 | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132631 | San Fernando Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 431664.5 | 1- R | 430982.92 | Ongoing | 0.61 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.61 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132632 | San Isidro Elementary School | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 651013.24 | 1- R | 650478.66 | Ongoing | 0.62 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.62 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132633 | Gaspar Serrano Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 448279.89 | 1- R | 445531.5 | Ongoing | 0.75 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.75 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132635 | San Roque Central Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 434917.25 | 1- R | 429020.2 | Ongoing | 0.85 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.85 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132638 | SIMON EDGAR A. GARAY ES | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 648903.35 | 1- R | 647637 | Completed | 1 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0.85 | 0.15 |  | 5.25 | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132639 | Sote Elementary School | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 660156.1 | 1- R | 659585.76 | Completed | 1 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0.9 | 0.1 |  | 5.25 | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132833 | Mangagoy Central Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 435708.46 | 1- R | 435198.86 | Ongoing | 0.66 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.66 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132834 | Mangagoy East Elementary School | CITY OF BISLIG | 2nd | 1 | 5 | Repair of Classrooms | 1081271.15 | 1- R | 1079250.33 | Ongoing | 0.61 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0.61 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132837 | Mangagoy South Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 435972.19 | 1- R | 435171.51 | Ongoing | 0.57 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.57 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132839 | Espiritu Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 438961.2 | 1- R | 436266.85 | Ongoing | 0.75 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.75 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132840 | Labisma Elementary School | CITY OF BISLIG | 2nd | 1 | 4 | Repair of Classrooms | 875900.44 | 1- R | 873565.55 | Ongoing | 0.76 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.76 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132841 | Lawigan Elementary School | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 666573.68 | 1- R | 664525.12 | Ongoing | 0.76 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.76 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132842 | Paler Lumayog Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 437202.96 | 1- R | 435176.18 | Ongoing | 0.76 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.76 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132843 | Plaza Central Elementary School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 221458.62 | 1- R | 219440.92 | Ongoing | 0.76 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.76 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 132844 | Requina Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 436851.31 | 1- R | 434665.95 | Ongoing | 0.76 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.76 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 235001 | P. M. Clar Elementary School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 233063.02 | 1- R | 230609.86 | Ongoing | 0.77 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.77 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 235004 | New Jerusalem Elementary School | CITY OF BISLIG | 2nd | 1 | 6 | Repair of Classrooms | 1302273 | 1- R | 1300032.87 | Ongoing | 0.75 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0.75 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 304865 | Bislig City National High School | CITY OF BISLIG | 2nd | 1 | 8 | Repair of Classrooms | 1721031.65 | 1- R | 1717351.44 | Ongoing | 0.61 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0.61 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 304867 | Mone National High School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 224008.07 | 1- R | 223292.71 | Completed | 1 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0.9 | 0.1 |  | 5.25 | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 304868 | San Vicente National High School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 440104.06 | 1- R | 436695.71 | Ongoing | 0.85 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.85 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 304918 | Danipas National High School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 439049.12 | 1- R | 436873.59 | Ongoing | 0.76 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.76 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 322501 | San Jose National High School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 233766.31 | 1- R | 231654.35 | Ongoing | 0.74 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.74 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 322502 | Tumanan National High School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 446873.29 | 1- R | 435368.52 | Ongoing | 0.85 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.85 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 322504 | San Isidro National High School | CITY OF BISLIG | 2nd | 1 | 4 | Repair of Classrooms | 866318.02 | 1- R | 865392.85 | Ongoing | 0.6 | 2025-05-31 |  | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.6 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 322505 | Mabog National High School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 232711.37 | 1- R | 230109.14 | Ongoing | 0.85 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.85 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 322506 | Coleto National High School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 220491.59 | 1- R | 209688.01 | Ongoing | 0.85 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.85 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 322507 | Labisma National High School | CITY OF BISLIG | 2nd | 1 | 5 | Repair of Classrooms | 1086944.78 | 1- R | 1084170.22 | Ongoing | 0.76 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0.76 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 322508 | San Fernando Integrated School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 216975.11 | 1- R | 207536.83 | Ongoing | 0.85 | 2025-04-11 |  | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.85 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Bislig City | 501292 | Pamaypayan Integrated School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 241502.58 | 1- R | 239179.57 | Ongoing | 0.7 | 2025-05-01 |  | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | 2024-12-02 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.7 | 0 |  |  | TD KABAYAN |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Dinagat Island | 132515 | Cuarenta Elementary School | SAN JOSE (Capital) | Lone | 1 | 2 | 1STY2CL WITH COMMON TOILET | 8801976.29 | 1- NC | ₱ 6,679,436.19 | Ongoing | 0.82 | 2025-04-25 |  | INFRA2024-002 | INFRA2024-002 | 2024-08-08 | August 20, 2w024 | 2024-09-04 | 2023-10-19 | 2024-10-28 | ARDRAW |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.82 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Ongoing
QRF 2024 | CARAGA | Dinagat Island | 304836 | Melgar NHS | BASILISA (RIZAL) | Lone | 1 | 2 | Repair of Classrooms | 2455106.77 | 1- R | 1841257.65 | completed | 1 | 2025-01-25 | 2024-12-05 | INFRA2024-004 | INFRA2024-004 | 2024-08-08 | August 20, 2w024 | 2024-09-04 | 2023-10-19 | 2024-10-28 | WINDAFALL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 4.25 | Fire |  |  |  | REPAIR | completed
QRF 2024 | CARAGA | Siargao | 132148 | Consuelo Elementary School | GENERAL LUNA | 1st | 1 | 6 | Repair of Classrooms | 18279803.53 | 1- R | 18259257.53 | Completed | 1 | 2024-12-17 |  |  |  | 2024-09-05 | 2025-09-19 | 2025-09-23 | 2024-10-10 | 2024-10-18 | RBEP CONSTRUCTION | for punch listing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0.95 | 0.05 |  | 5.25 | SHEARLINE |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Siargao | 132174 | Mabuhay Primary School | DEL CARMEN | 1st | 1 | 6 | Repair of Classrooms | 10467818.59 | 1- R | 10443668.43 | Completed | 1 | 2024-12-17 |  |  |  | 2024-09-05 | 2025-09-19 | 2025-09-23 | 2024-10-10 | 2024-10-18 | RBEP CONSTRUCTION | for punch listing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0.95 | 0.05 |  | 5.25 | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Surigao del Sur | 132644 | Bacolod Elementary School | CAGWAIT | 1st | 1 | 4 | 2-UNITS 1STY2CL | 12710324.73 | 1- NC | 6,336,697.28 6,335,565.88 | Ongoing | 0.4 | May 26, 2025 June 02, 2025 |  | QRF 2024 - R XIII - SURIGAO DEL SUR - 001 and 002 | 001 - 2025 002 - 2025 | October 18, 2024 | October 25, 2024 | November 07, 2024 | November 20, 2024 | January 20, 2025 January 27, 2025 | TRIDENT ENGINEERING SERVICES; CYL CONSTRUCTION & SUPPLY | Project Ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.4 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Ongoing
QRF 2024 | CARAGA | Surigao del Sur | 304890 | Hinatuan National Comprehensive High School | HINATUAN | 2nd | 1 | 8 | 2-UNITS 1STY4CL | 19938649.56 | 1- NC | 9,689,479.13 9,714,500.55 | Ongoing | 0.16 | June 25, 2025 July 02, 2025 |  | QRF 2024 - R XIII - SURIGAO DEL SUR - 003 and 004 | 003 - 2025 004 - 2025 | October 18, 2024 | October 25, 2024 | November 07, 2024 | November 20, 2024 | January 20, 2025 January 27, 2025 | ETP BUILDERS; J-R3 CONSTRUCTION & SUPPLY | Project Ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0.16 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Ongoing
QRF 2024 | CARAGA | Surigao del Sur | 500584 | Sta. Maria Integrated School | TAGBINA | 2nd | 1 | 4 | 1STY4CL | 9956134.23 | 1- NC | 9872544.27 | Ongoing | 0.19 | June 25, 2025 |  | QRF 2024 - R XIII - SURIGAO DEL SUR - 005 | 005 - 2025 | October 18, 2024 | October 25, 2024 | November 07, 2024 | November 20, 2024 | 2025-01-20 | ILMAR CONSTRUCTION AND SUPPLY | Project Ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.19 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Ongoing
QRF 2024 | CARAGA | Tandag City | 132957 | Awasian Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 3 | 1STY3CL WITH COMMON TOILET | 11289692.93 | 1- NC |  | Under Procurement | 0 | [10 empty] | ONGOING PROCUREMENT | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | CARAGA | Tandag City | 132977 | San Jose Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 3 | 1STY3CL WITH COMMON TOILET | 11289692.93 | 1- NC |  | Under Procurement | 0 | [10 empty] | for realignment san jose to quintos (awaiting approval) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | CARAGA | Tandag City | 132980 | Telaje Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 3 | 1STY3CL WITH COMMON TOILET | 10656067.46 | 1- NC | 10122191.88 | Ongoing | 0.6 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.6 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Ongoing
QRF 2024 | CARAGA | Tandag City | 304892 | Jacinto P. Elpa National High School | CITY OF TANDAG (Capital) | 1st | 1 | 2 | Repair of Classrooms | 2794585.69 | 1- R | 1927574.12 | Ongoing | 0.6 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.6 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Tandag City | 501274 | Meliton M. Ajos Memorial Integrated School | CITY OF TANDAG (Capital) | 1st | 1 | 3 | 1STY3CL WITH COMMON TOILET | 10821883.46 | 1- NC | 7704691.29 | Ongoing | 0.3 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.3 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Ongoing
QRF 2024 | CARAGA | Tandag City | 132971 | Quezon Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 6 | Repair of Classrooms | 9445989.04 | 1- R |  | Ongoing | 0.6 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0.6 | 0 |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Tandag City | 502042 | Rosario Integrated School | CITY OF TANDAG (Capital) | 1st | 1 | 4 | Repair of Classrooms | 7882447.55 | 1- R | 592930.05 | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 4.25 | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | completed
QRF 2024 | CARAGA | Surigao del Norte | 304834 | Matin-ao National High School | MAINIT | 2nd | 1 | 39 | REPAIR OF CLASSROOMS | 19648076.16 | 3-R |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%