## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | No. of Classrooms | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated | Previous % | Difference | STOREY | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | Status as of July 4, 2025
NEWCON 2024 | NCR | Caloocan City | 136625 | Baesa ES | KALOOKAN CITY | 1st | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | 19738193.69 | On Going | 0.32 | 25/01/2025 |  | P00875001LZ | 24OD0292 | 20/06/2024 | 28/06/2024 | 2024-10-07 | 22/07/2024 | 29/07/2024 | FRAMECON BUILDERS |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.32 | 0
NEWCON 2024 | NCR | Caloocan City | 319707 | Caloocan City Business High School | KALOOKAN CITY | 1st | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39398654.98 | On Going | 0.57 | 25/05/2025 |  | P00875002LZ | 24OD0291 | 20/06/2024 | 28/06/2024 | 2024-10-07 | 22/07/2024 | 29/07/2024 | WAWAO BUILDERS |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.57 | 0
NEWCON 2024 | NCR | Caloocan City | 319705 | Maypajo High School | KALOOKAN CITY | 1st | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39167469.39 | On Going | 0.2 | 16/04/2025 |  | P00875003LZ | 24OD0295 | 2024-11-07 | 18/07/2024 | 2024-01-08 | 13/08/2024 | 19/08/2024 | ED1SON DEVELOPMENT & CONSTRUCTION INC./TWENTYSIX CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.2 | 0
NEWCON 2024 | NCR | Caloocan City | 136632 | Amparo ES | KALOOKAN CITY | 2nd | 1 | 12 | Completion of 4STY12CL | BATCH 1 | 2500000 |  | 2447832.87 | On Going | 0.96 | 27/10/2024 |  | P00875789LZ | 24OD0285 | 16/05/2024 | 23/05/2024 | 2024-04-06 | 22/07/2024 | 29/07/2024 | TM ABAD CONSTRUCTION CORP. |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.96 | 0
NEWCON 2024 | NCR | Caloocan City | 136632 | Amparo ES | KALOOKAN CITY | 2nd |  | 8 | Completion of 4STY8CL | BATCH 1 | 2500000 |  | 2460814.81 | On Going | 0.96 | 27/10/2024 |  | P00875790LZ | 24OD0289 | 16/05/2024 | 23/05/2024 | 2024-04-06 | 22/07/2024 | 29/07/2024 | TM ABAD CONSTRUCTION CORP. |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.96 | 0
NEWCON 2024 | NCR | Caloocan City | 136617 | Caloocan Central Elementary School | KALOOKAN CITY | 2nd | 1 | 12 | 4STY12CL | BATCH 1 | 45050000 |  | 44,106,806.77 | On Going | 0.22 | 2025-07-14 |  | P00875788LZ | 24OD0297 | 17/08/2024 | 27/08/2024 | 2024-05-09 | 2024-11-09 | 17/09/2024 | STRUKTURA TEKNIKA SERVICES CO. |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.22 | 0 |  | 1 | 12 | 45050000
NEWCON 2024 | NCR | Caloocan City | 500330 | Tandang Sora IS | KALOOKAN CITY | 2nd | 1 | 12 | Completion of 4STY12CL | BATCH 1 | 19998569.25 |  | 19595766.82 | On Going | 0.5 | 25/01/2025 |  | P00875791LZ | 24OD0288 | 16/05/2024 | 23/05/2024 | 2024-04-06 | 22/07/2024 | 29/07/2024 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.5 | 0
NEWCON 2024 | NCR | Caloocan City | 136637 | Horacio dela Costa ES | KALOOKAN CITY | 3rd | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 38954849.56 | For Demolition | 0 | 26/03/2025 |  | P00875004LZ | 24OD0286 | 16/05/2024 | 23/05/2024 | 2024-04-06 | 22/07/2024 | 29/07/2024 | MILES TRADING AND CONSTRUCTION/OSCORD BUILDERS CORPORATION | Permit to Demolish on Process | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | NCR | Caloocan City | 136644 | Manuel L. Quezon ES | KALOOKAN CITY | 3rd | 1 | 12 | 4STY12CL | BATCH 1 | 45050000 |  | 44083387.04 | On Going | 0.4 | 14/07/2025 |  | P00875792LZ | 24OD0298 | 17/08/2024 | 27/08/2024 | 2024-05-09 | 2024-11-09 | 17/09/2024 | DIADEMA CONSTRUCTION AND ENTERPRISES INC. |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.4 | 0 |  | 1 | 12 | 45050000
NEWCON 2024 | NCR | Las Piñas City | 136774 | Daniel Fajardo Elementary School | CITY OF LAS PIÑAS | Lone | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | FOR REVERSION | Not Yet Started | 0 | [10 empty] | cancelled, limited right of way | 0 | 1 | 0 | 0 | 0 |  | 0 | 6 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | NCR | Las Piñas City | 136776 | Ilaya Elementary School | CITY OF LAS PIÑAS | Lone | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  |  | Not Yet Started | 0 |  |  | 24-160 | 24-160 |  |  | 2025-08-01 |  | 2025-02-24 | Dahvez Construction | Awarded (waiting for approval of building permit), Approved modification of the project from 3stry6cls to 4stry4cls | 0 | 1 | 0 | 0 | 0 |  | 0 | 6 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | NCR | Las Piñas City | 320304 | Las Piñas City National Science High School | CITY OF LAS PIÑAS | Lone | 1 | 4 | 4STY4CL | GAA 17B | 20000000 |  |  | Not Yet Started | 0 |  |  | 24-159 | 24-159 |  |  | 2025-08-01 |  |  | Dahvez Construction | Awarded (waiting for approval of building permit), Approved modification of the project from 3stry6cls to 4stry4cls | 0 | 1 | 0 | 0 | 0 |  | 0 | 4 | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 3STY6CL | 20000000
NEWCON 2024 | NCR | Las Piñas City | 136779 | Pulanlupa Elementary School | CITY OF LAS PIÑAS | Lone | 1 | 4 | 4STY4CL | GAA 17B | 20000000 |  |  | Not Yet Started | 0 |  |  | 24-161 | 24-161 |  |  | 2025-08-01 |  |  | Dahvez Construction | Awarded (waiting for approval of building permit), Approved modification of the project from 3stry6cls to 4stry4cls | 0 | 1 | 0 | 0 | 0 |  | 0 | 4 | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 3STY6CL | 20000000
NEWCON 2024 | NCR | Malabon City | 302387 | Malabon City Techvoc and Entrepreneurship Senior High School (CMPI Campus) | CITY OF MALABON | Lone | 1 | 8 | 4STY8CL (Phase 1) | GAA 17B | 40000000 |  |  | On Going | 0.5 |  |  |  | 24OA0091 | 21/9/2024 |  | 2024-11-10 |  | 25/10/2024 | Rotaflex Construction and Development Corp. |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.5 | 0
NEWCON 2024 | NCR | Malabon City | 136836 | Ninoy Aquino ES | CITY OF MALABON | Lone | 1 | 8 | 4STY8CL | BATCH 1 | 44000000 |  |  | Suspended | 0 | 13/1/2025 |  | P00875793LZ | 24OA0086 | 27/3/2024 |  | 16/4/2025 |  | 2024-07-05 | C.B. Tampengco Construction and Supply | Waiting for demolition permit | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | NCR | Mandaluyong City | 500335 | Ilaya Barangka Integrated School | CITY OF MANDALUYONG | Lone | 1 |  | Multi-Storey School Building (Phase 2) | GAA 17B | 40000000 |  |  | On Going | 0.5 | [10 empty] | part of phase 1 construction of 7 storey 28 classrooms | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.5 | 0
NEWCON 2024 | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1st | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  |  | On Going | 0.65 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.65 | 0
NEWCON 2024 | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2nd | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  |  | On Going | 0.8 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.8 | 0
NEWCON 2024 | NCR | Manila | 136450 | Antonio Regidor Elementary School | SANTA CRUZ | 3rd | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  |  | On Going | 0.45 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.45 | 0
NEWCON 2024 | NCR | Manila | 305307 | Claro M. Recto High School | SAMPALOC | 4th | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  |  | On Going | 0.95 | [10 empty] | for final inspection and punchlisting | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.95 | 0
NEWCON 2024 | NCR | Manila | 136473 | Justo Lukban Elementary School | PACO | 5th | 1 | 6 | 2STY6CL | GAA 17B | 40000000 |  |  | On Going | 0.2 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.2 | 0 |  | 1 | 6 | 40000000
NEWCON 2024 | NCR | Manila | 136454 | Geronimo Santiago Elementary School | SAN MIGUEL | 6th | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  |  | On Going | 0.3 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.3 | 0
NEWCON 2024 | NCR | Marikina City | 305402 | Malanday National High School | CITY OF MARIKINA | 1st | 1 | 8 | Completion of 4STY8CL with covered roof deck | GAA 17B | 30000000 |  |  | On Going | 0.6 | [10 empty] | On-going | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.6 | 0 |  | 1 | Completion of 4STY8CL with covered roof deck | 30000000
NEWCON 2024 | NCR | Marikina City | 136678 | San Roque ES | CITY OF MARIKINA | 1st | 1 | 2 | 2STY2CL | GAA 17B | 10000000 |  |  | On Going | 0 | [10 empty] | For Mobilization | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 2 | 10000000
NEWCON 2024 | NCR | Marikina City | 319905 | San Roque National High School | CITY OF MARIKINA | 1st | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  |  | On Going | 0.03 | [10 empty] | On-going | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.03 | 0 |  | 1 | 15 | 40000000
NEWCON 2024 | NCR | Marikina City | 305399 | Tañong HS | CITY OF MARIKINA | 1st | 1 | 16 | 3STY6CL | GAA 17B | 40000000 |  |  | On Going | 0.05 | [10 empty] | On-going | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.05 | 0 |  | 1 | 16 | 40000000
NEWCON 2024 | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA | 2nd | 1 |  | Completion of 5STY30CL | GAA 17B | 75000000 |  |  | On Going | 0.05 | [10 empty] | On-going | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.05 | 0 |  | 1 |  | 75000000
NEWCON 2024 | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA | 2nd |  | 12 | 4STY12CL | GAA 17B | 80000000 |  |  | On Going | 0.1 | [10 empty] | On-going | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.1 | 0 |  | 1 | 30 | 80000000
NEWCON 2024 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2nd | 1 | 32 | 4STY32CL | GAA 17B | 150000000 |  |  | On Going | 0 | [10 empty] | Pending certificate of condemnation | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
NEWCON 2024 | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2nd | 1 | 24 | 4STY24CL with Roofdeck | GAA 17B | 30000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 24 |  | 1 | 0
NEWCON 2024 | NCR | Muntinlupa City | 305469 | Muntinlupa Science HS | CITY OF MUNTINLUPA | Lone | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  |  | On Going | 0.9 | 2025-03-15 |  |  |  | 2024-04-11 |  | 2024-05-02 | 2024-08-02 | 2024-08-16 | REDCAR TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.9 | 0
NEWCON 2024 | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | Lone | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  |  | On Going | 0.252 | 2025-06-21 |  |  |  | 2024-09-21 |  | 2024-10-11 |  | 2024-10-25 | STRUKTURA TEKNIKA SERVICES CO. | On-going | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.252 | 0
NEWCON 2024 | NCR | Paranaque City | 136767 | Baclaran Elementary School Central | CITY OF PARAÑAQUE | 1st | 1 |  | 3-Storey School Building | GAA 17B | 20000000 |  |  | On Going | 0.15 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.15 | 0
NEWCON 2024 | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE | 1st | 1 |  | 4-Storey School Building (Phase 2) | GAA 17B | 10000000 |  |  | On Going | 0.6 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.6 | 0
NEWCON 2024 | NCR | Paranaque City | 136765 | Sto. Niño Elementary School | CITY OF PARAÑAQUE | 1st | 1 |  | 4-Storey School Building with Ancillary (Phase 2) | GAA 17B | 10000000 |  |  | On Going | 0.4 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.4 | 0
NEWCON 2024 | NCR | Paranaque City | 137129 | Don Bosco Elementary School | CITY OF PARAÑAQUE | 2nd | 1 | 12 | 4STY12CL with Roofdeck | GAA 17B | 40000000 |  |  | On Going | 0.4 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.4 | 0
NEWCON 2024 | NCR | Pasay City | 136590 | Apelo Cruz ES | PASAY CITY | Lone | 1 | 6 | 4STY6CL | GAA 17B | 40000000 |  | 39171336.73 | On Going | 0.22 | 2025-11-16 |  | Project ID No. 240H0122 | Contract ID No. 240H0122 | 2024-10-11 | 2024-10-31 | 2024-10-31 | 2024-12-31 | 2025-02-04 | ALE BUILDERS CONST. & DEVT. CORP |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.22 | 0 |  | 1 | 12 | 40000000
NEWCON 2024 | NCR | Pasig City | 305420 | Sta. Lucia High School | CITY OF PASIG | Lone | 1 | 3 | 4STY8CL (Phase 1 3STY3CL) | GAA 17B | 40000000 |  |  | For Procurement | 0 |  |  |  |  | 2024-12-24 | 2025-01-02 | 2025-01-14 |  |  |  | re-scheduled procurement activities | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 8 | 40000000
NEWCON 2024 | NCR | Quezon City | 305321 | Judge Juan Luna HS | QUEZON CITY | 1st | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39517388.5 | On Going | 0.5 |  |  |  | 24OF0168 | 2024-03-27 | 2024-04-04 | 2024-04-24 | 2024-04-23 | 2024-04-29 | FRAMECON BUILDERS | Demolition Ongoing | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.5 | 0
NEWCON 2024 | NCR | Quezon City | 319501 | Holy Spirit National High School | QUEZON CITY | 2nd | 1 | 12 | Completion of 4STY8CL | BATCH 1 | 3000000 |  |  | Completed | 1 | 2024-10-16 |  |  | 24OF0203 | 2024-05-17 | 2024-05-24 | 2024-06-05 | 2024-06-13 | 2024-06-19 | ALTIUS CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 12 |  | 1 | 0
NEWCON 2024 | NCR | Quezon City | 136549 | Raymundo Punongbayan ES | QUEZON CITY | 2nd | 1 | 10 | 2STY10CL | GAA 17B | 40000000 |  |  | On Going | 0.15 | [10 empty] | Demolition Ongoing | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.15 | 0
NEWCON 2024 | NCR | Quezon City | 136566 | 15th Avenue Elementary School | QUEZON CITY | 3rd | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  |  | On Going | 0.25 | [11 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.25 | 0
NEWCON 2024 | NCR | Quezon City | 305362 | Dr. Josefa Jara Martinez HS | QUEZON CITY | 4th | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 9868853.6 | On Going | 0.9 |  |  |  | 24OF0150 | 2024-03-27 | 2024-04-04 | 2024-04-24 | 2024-04-22 | 2024-04-29 | FRAMECON BUILDERS |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.9 | 0
NEWCON 2024 | NCR | Quezon City | 319504 | Dona Rosario HS | QUEZON CITY | 5th | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  |  | For Procurement | 0 | [10 empty] | Ongoing Redesigning of Structural Foundation | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 12 | 40000000
NEWCON 2024 | NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY | 5th | 1 |  | 2-Storey School Building | GAA 17B | 10000000 |  | 9868853.6 | On Going | 0.85 |  |  |  | 24OF0150 | 2024-03-27 | 2024-04-04 | 2024-04-24 | 2024-04-22 | 2024-04-29 | FRAMECON BUILDERS |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.85 | 0
NEWCON 2024 | NCR | Quezon City | 360867 | Leandro Locsin Integrated School (SHS in Kaligayahan) | QUEZON CITY | 5th | 1 | 16 | Completion of 4STY16CL | BATCH 1 | 72000000 |  |  | On Going | 0.5 | 2025-05-15 |  |  | 24OF0176 | 2024-04-17 | 2024-04-25 | 2024-05-07 | 2024-05-15 | 2024-05-21 | RD8 BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.5 | 0
NEWCON 2024 | NCR | Quezon City | 136536 | Nagkaisang Nayon ES | QUEZON CITY | 5th | 1 | 16 | Completion of 4STY16CL | BATCH 1 | 12000000 |  |  | Completed | 1 | 2024-11-16 |  |  | 24OF0173 | 2024-04-17 | 2024-04-25 | 2024-05-07 | 2024-05-15 | 2024-05-21 | R. ROSE CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 16 |  | 1 | 0
NEWCON 2024 | NCR | Quezon City | 136525 | San Bartolome ES | QUEZON CITY | 5th | 1 | 16 | Completion of 4STY16CL | BATCH 1 | 5000000 |  |  | Completed | 1 | 2024-11-15 |  |  | 24OF0175 | 2024-04-17 | 2024-04-25 | 2024-05-07 | 2024-05-15 | 2024-05-21 | JOJEAN CONSTRUCTION AND DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 16 |  | 1 | 0
NEWCON 2024 | NCR | Quezon City | 136514 | Pasong Tamo ES | QUEZON CITY | 6th | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  |  | For Procurement | 0 | 2024-11-15 |  |  | 24OF0175 | 2024-04-17 | 2024-04-25 | 2024-05-07 | 2024-05-15 | 2024-05-21 | JOJEAN CONSTRUCTION AND DEVELOPMENT CORPORATION | With approved modification and Certificate of Coordination, waiting for approved demolition and revised plan | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 8 | 40000000
NEWCON 2024 | NCR | Taguig City and Pateros | 500342 | Napindan Integrated School | TAGUIG CITY | 1st | 1 | 6 | 2STY6CL | GAA 17B | 40000000 |  |  | On Going | 0.2 |  |  |  | 240B0520 | 2024-12-16 | 2024-12-26 | 2025-01-07 |  |  | GERCEL CONSTRUCTION & DEVELOPMENT | Phase 1 (2sty 6cl provision for 4sty 12cl) | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.2 | 0 |  | 1 | 21 | 40000000
NEWCON 2024 | NCR | Valenzuela City |  | Pasolo National High School | CITY OF VALENZUELA | 1st | 1 | 12 | 4STY12CL (Phase 2) | GAA 17B | 20000000 |  | 19898880 | On Going | 1 | 2025-02-23 |  |  | 24OD0290 | 2024-07-10 | 2024-06-20 | 2024-07-10 | 2024-08-15 | 2024-07-29 | Nova Ventus Construction Inc. | Phase 2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 0
NEWCON 2024 | NCR | Valenzuela City |  | Pasolo National High School | CITY OF VALENZUELA | 1st | 1 | 2 | 1STY2CL Phase 1 of 4STY12CL | GAA 17B | 20000000 |  | 19590117.48 | On Going | 0.15 | 2025-05-21 |  |  | 24OD0326 | 2024-12-18 | 2024-11-27 | 2024-12-18 | 2025-01-13 | 2024-12-23 | Nova Ventus Construction Inc. | Phase 1 (1st 2cl) | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.15 | 0 |  | 1 | 12 | 20000000
NEWCON 2024 | NCR | Valenzuela City | 136812 | Roberta de Jesus Elementary School | CITY OF VALENZUELA | 1st | 1 | 8 | 4STY8CL | BATCH 1 | 29550000 |  | 29476125 | On Going | 0.45 | 2025-06-15 |  |  | 24OD0287 | 2024-06-04 | 2024-05-15 | 2024-06-04 | 2024-07-11 | 2024-07-29 | Diadema Construction and Enterprises Inc. |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.45 | 0
NEWCON 2024 | NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA | 2nd | 1 | 16 | 3STY12CL Phase 1 of 4STY16CL | BATCH 1 | 53050000 |  | 52783817.37 | On Going | 0.45 | 2025-07-13 |  |  | 24OD0296 | 2024-09-05 | 2024-08-16 | 2024-09-05 | 2024-10-11 | 2024-09-17 | Diadema Construction And Enterprises Inc. | Phase 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.45 | 0 |  | 1 | 16 | 53050000
NEWCON 2024 | NCR | Valenzuela City | 136827 | Serrano Elementary School | CITY OF VALENZUELA | 2nd | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39796807.51 | On Going | 0.45 | 2025-06-15 |  |  | 24OD0294 | 2024-08-01 | 2024-07-10 | 2024-08-01 | 2024-09-06 | 2024-08-20 | Larsen-Dutcher Constractor Corporation |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.45 | 0
NEWCON 2023 | NCR | Caloocan City | 223502 | Gabriela Silang ES (Bagong Silang ES - Annex) | KALOOKAN CITY | 1st | 1 | 8 | 4STY8CL | Batch 1 | 30262500 | 30000000 | 29387423.33 | Completed | 1 | 2024-12-07 | 2024-10-01 | P00775063LZ | 23OD0237 | 22/06/2023 | 29/06/2023 | 2023-07-11 | 17/07/2023 | 2023-08-18 | Dreamworx Builder & Trading Inc. |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Caloocan City | 136613 | Maypajo ES | KALOOKAN CITY | 2nd | 1 | 8 | 4STY8CL | Batch 1 | 35457562.5 | 35150000 | 34423890.25 | On Going | 0.8 | 2024-10-11 |  | P00775064LZ | 23OD0238 | 22/06/2023 | 29/06/2023 | 2023-07-11 | 17/07/2023 | 2023-08-18 | Dreamworx Builder & Trading Inc. |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.45 | 0.35 | 4
NEWCON 2023 | NCR | Caloocan City | 136644 | Manuel L. Quezon ES | KALOOKAN CITY | 3rd | 1 | 8 | 4STY8CL | Batch 1 | 29808562.5 | 29550000 | 28912136.52 | Completed | 1 | 2024-12-06 | 2024-12-11 | P00775065LZ | 23OD0236 | 22/06/2023 | 29/06/2023 | 2023-07-11 | 17/07/2023 | 2023-08-18 | DSA Prime Builders Corporation |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 0.95 | 0.05 | 4
NEWCON 2023 | NCR | City of San Juan | 136750 | Nicanor C. Ibuna ES | CITY OF SAN JUAN | Lone | 1 | 16 | COMPLETION OF 4STY16CL | Batch 1 | 8070000 | 8000000 | 7716515.22 | Completed | 1 | 2023-12-03 |  | P00775067LZ | 23OB0454 | 2023-05-29 | 2023-05-26 | 2023-06-20 | 2023-06-27 | 2023-07-06 | Aylan Consrtruction & Trading |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 16 |  | 1 | 0 | 4
NEWCON 2023 | NCR | City of San Juan | 136751 | Pinaglabanan ES | CITY OF SAN JUAN | Lone | 1 | 4 | 4STY4CL | Batch 1 | 11096250 | 11000000 | 10614195.75 | Completed | 1 | 2024-01-02 |  | P00775068LZ | 23OB0455 | 2023-05-29 | 2023-05-26 | 2023-06-20 | 2023-06-27 | 2023-07-06 | Sto. Cristo Construction & Trading Inc. |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 1 | 0 | 4
NEWCON 2023 | NCR | City of San Juan | 136746 | San Juan ES | CITY OF SAN JUAN | Lone | 1 | 28 | COMPLETION OF 4STY28CL | Batch 1 | 11096250 | 11000000 | 10615395.14 | Completed | 1 | 2023-12-03 |  | P00775066LZ | 23OB0456 | 2023-05-29 | 2023-05-26 | 2023-06-20 | 2023-06-27 | 2023-07-06 | Magnificus Builders Inc. |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 28 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Las Piñas City | 340548 | Las Piñas City National Senior High School - Manuyo Campus | CITY OF LAS PIÑAS | Lone | 1 | 4 | 4STY4CL | Batch 1 | 15131250 | 15000000 | 14549997.85 | Completed | 1 | 2024-03-03 | 2024-07-12 | P00775070LZ-CW1 | 23OI0110 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-19 | Dahvez Construction | turn-over on July 12, 2024 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Las Piñas City | 136777 | Las Piñas Elementary School Central | CITY OF LAS PIÑAS | Lone | 1 | 4 | 4STY4CL | Batch 1 | 15131250 | 15000000 | 14549991.09 | Completed | 1 | 2024-03-03 | 2024-07-12 | P00775069LZ-CW1 | 23OI0111 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-19 | Dahvez Construction | turn-over on July 12, 2024 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Malabon City | 305451 | Tugatog NHS | CITY OF MALABON | Lone | 1 | 12 | 4STY12CL (Phase 1) | Batch 1 | 30262500 | 30000000 | 29384529.47 | Completed | 1 | 2024-06-26 | 2024-07-26 | P00775071-LG-CW1 | 230A0100 | 2023-06-28 | 2023-07-06 | 2023-07-18 |  | 2023-07-31 | AL-REM KONSTRUCT INC. | phase 1 only | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 12 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | Lone | 1 | 6 | 7STY School Building Phase I (2STY6CL) | Batch 1 | 33711931.83 | 33419511.11 |  | Realignment | [11 empty] | FOR REALIGNMENT | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 4 | 1 | 12 | 33711931.83
NEWCON 2023 | NCR | Manila | 136439 | I. Delos Reyes ES | TONDO | 1st | 1 | 6 | 3STY6CL | Batch 1 | 30262500 | 30000000 | 29096416.08 | Completed | 1 |  |  |  | 23OE0231 | 2023-06-13 | 2023-06-22 | 2023-07-13 |  | 2023-07-25 | ROAD EDGE TRADING & DEV'T SERVICES | Physically completed but not yet officially turn over to the school | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 6 |  | 0.9 | 0.1 | 3
NEWCON 2023 | NCR | Manila | 136429 | Librada Avelino ES | TONDO | 2nd | 1 | 6 | 3STY6CL | Batch 1 | 30262500 | 30000000 | 29011653.71 | Completed | 1 |  |  |  | 23OE0230 | 2023-06-13 | 2023-06-22 | 2023-07-03 | 2023-07-11 | 2023-07-14 | El-Jake Builders | Physically completed but not yet officially turn over to the school | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 6 |  | 1 | 0 | 3
NEWCON 2023 | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ | 3rd | 1 | 6 | 3STY6CL | Batch 1 | 30262500 | 30000000 | 29092137.75 | Completed | 1 |  |  |  | 23OE232 | 2023-06-13 | 2023-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-14 | TRILEX BUILDERS AND CONSTRICTION SUPPLY, INC. | Physically completed but not yet officially turn over to the school | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 6 |  | 0.65 | 0.35 | 3
NEWCON 2023 | NCR | Manila | 305304 | Esteban Abada High School | SAMPALOC | 4th | 1 | 6 | 3STY6CL | Batch 1 | 30262500 | 30000000 | 29086575.68 | Completed | 1 |  |  |  | 23OE228 | 2023-06-13 | 2024-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-14 | I & E Construction Corp. |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 6 |  | 1 | 0 | 3
NEWCON 2023 | NCR | Manila | 305309 | M.Araullo High School | ERMITA | 5th | 1 | 9 | 3STY9CL | Batch 1 | 30262500 | 30000000 | 29415864.41 | On Going | 0.67 | 2024-07-23 | [8 empty] | RDBT CONST. CORP. | Requested to revise to 6-classroom school building instead of 9-classroom since the allocation is just enough for 6-classroom | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.67 | 0 | 3
NEWCON 2023 | NCR | Manila | 305317 | Elpidio Quirino High School | SAMPALOC | 6th | 1 | 6 | 3STY6CL | Batch 1 | 30262500 | 30000000 | 29052919.5 | On Going | 0.95 |  |  |  | 23OE229 | 2023-06-13 | 2023-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-14 | Flordes Construction & Trading Corp. | for final inspection and punchlisting | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.4 | 0.55 | 3
NEWCON 2023 | NCR | Marikina City | 305402 | Malanday National High School | CITY OF MARIKINA | 1st | 1 | 8 | 4STY8CL | Batch 1 | 30262500 | 30000000 | 28926115.59 | Completed | 1 | 2024-04-03 | 2024-07-19 | P00775079LZ | 23OB0457 | 2023-05-29 | 2023-06-07 | 2023-07-21 | 2023-07-26 | 2023-08-08 | Streamline Builders Corp. |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2nd | 1 | 32 | 4STY32CL | Batch 1 | 30262500 | 30000000 | 28850946.22 | For Demolition | 0 | Work Suspended |  | P00775080LZ | 23OB0458 | 2023-05-29 | 2323-06-07 | 2023-07-21 | 2023-07-26 | 2023-08-08 | Kai Construction | Work suspended; Pending certificate of condemnation | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 4
NEWCON 2023 | NCR | Muntinlupa City | 228501 | Poblacion Elementary School | CITY OF MUNTINLUPA | Lone | 1 | 8 | 4STY8CL | Batch 1 | 30262500 | 30000000 | 29999999.06 | Completed | 1 | 2024-04-02 | 2024-06-08 | P00775081LZ-CW1 | 230I0112 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-18 | 2023-10-05 | Greenwall Construction | with approved additional 30CD | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | Lone | 1 | 8 | 4STY8CL | Batch 1 | 2017500 | 2000000 | 1958779.07 | Completed | 1 | 2023-09-25 | 2023-12-15 |  | 23OA0090 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-28 | T.M. Abad Const. Corporation |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS | Lone | 1 | 12 | 4STY12CL | Batch 1 | 3026250 | 3000000 | 2935041.11 | Completed | 1 | 2023-10-28 |  |  | 23OA0089 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-31 | C.B. Tampengco Const. & Supply |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 12 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | Lone | 1 | 8 | 4STY8CL | Batch 1 | 4035000 | 4000000 | 3919257.43 | Completed | 1 | 2023-10-28 |  |  | 23OA0092 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-08-31 | Two Dimension Construction | Suspended due to On-Going Construction of Phase 2 Project | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | Lone | 1 | 8 | 4STY8CL | Batch 1 | 1008750 | 1000000 | 982185.24 | Completed | 1 | 2023-08-26 |  |  | 23OA0091 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-28 | T.M. Abad Const. Corporation | Suspended due to On-Going Construction of Phase 2 Project | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Navotas | 136862 | North Bay Boulevard Elementary School | CITY OF NAVOTAS | Lone | 1 | 12 | 4STY12CL | Batch 1 | 13113750 | 13000000 | 12727742.97 | Completed | 1 | 2023-12-22 | 2024-02-20 |  | 23OA0097 | 2023-06-29 | 2023-06-21 | 2023-07-19 | 2023-07-25 | 2023-07-26 | Erish Builders& Supply |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 12 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | Lone | 1 | 8 | 4STY8CL | Batch 1 | 22192500 | 22000000 | 21543817.73 | Completed | 1 | 2024-02-25 |  |  | 23OA0096 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-31 | MRBll Construction Corporation |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 0.95 | 0.05 | 4
NEWCON 2023 | NCR | Navotas | 136866 | San Roque Elementary School | CITY OF NAVOTAS | Lone | 1 | 8 | 4STY8CL | Batch 1 | 22192500 | 22000000 | 21509297.96 | Completed | 1 | 2024-02-22 |  |  | 23OA0095 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-28 | T.M. Abad Const. Corporation |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | Lone | 1 | 12 | 4STY12CL | Batch 1 | 13113750 | 13000000 | 12727513.81 | On Going | 0.95 | 2023-12-23 |  |  | 23OA0093 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-08-27 | Justbilt Builders | Suspended due to On-Going Construction of Phase 2 Project | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.9 | 0.05 | 4
NEWCON 2023 | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS | Lone | 1 | 12 | 4STY12CL | Batch 1 | 33288750 | 33000000 | 32319015.9 | Completed | 1 | 2024-03-26 |  |  | 23OA0094 | 2023-06-29 | 2023-06-21 | 2023-07-19 | 2023-07-25 | 2023-07-31 | B. Bernardo Construction Inc. |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 12 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Navotas | 136870 | Wawa Elementary School | CITY OF NAVOTAS | Lone | 1 | 20 | 4STY20CL (Phase 1) | Batch 1 | 30262500 | 30000000 | 29385432.95 | Completed | 1 | 2024-07-27 |  |  | 23OA0101 | 2023-06-21 | 2023-06-28 | 2023-06-29 | 2023-07-28 | 2023-07-26 | P7 Builders Inc. |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 20 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE | 1st | 1 | 4 | 4STY4CL | Batch 1 | 10087500 | 10000000 | 9798127.34 | Completed | 1 | 2024-04-15 | 2024-04-15 | P00775092LZ | 23OC0119 | 2023-10-05 | 2023-10-13 | 2023-10-25 |  | 2023-12-18 | J.S. Rabano Construction and Supply Inc. | Suspended December 29, 2023 due to revision of plan | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 0.2 | 0.8 | 4
NEWCON 2023 | NCR | Paranaque City | 136765 | Sto. Niño Elementary School | CITY OF PARAÑAQUE | 1st | 1 | 4 | 4STY4CL with Ancilliary Room | Batch 1 | 20175000 | 20000000 | 19600930.96 | Completed | 1 | 2024-05-15 | 2024-05-15 | P00775093LZ | 23OC0120 | 2023-10-06 | 2023-10-14 | 2023-10-26 |  | 2023-12-18 | AARCON Builders | Suspended dated December 29, 2023 due to pending issuance of demolition and building permit from the Local Government of Parañaque City and ongoing coordination with the DepEd regarding the demolition of existing building | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 4 |  | 0.8 | 0.2 | 4
NEWCON 2023 | NCR | Paranaque City | 136759 | San Antonio Elementary School | CITY OF PARAÑAQUE | 2nd | 1 | 12 | 4STY12CL | Batch 1 | 30262500 | 30000000 | 29400545.83 | On Going | 0.95 | 2024-07-14 | 2024-07-14 | P00775094LZ | 23OC0121 | 2023-10-07 | 2023-10-15 | 2023-10-27 |  | 2023-12-18 | GRAC-TA Builders | Suspended December 18, 2023 due to pending issuance of demolition and building permit from the Local Government of Parañaque City and ongoing coordination with the DepEd regarding the demolition of existing building. | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.15 | 0.8 | 4
NEWCON 2023 | NCR | Pasay City | 136599 | Marcela Marcelo ES | PASAY CITY | Lone | 1 | 6 | 3STY6CL | Batch 1 | 30262500 | 30000000 | 29370451.32 | Completed | 1 | 3/23/2024 (Time Extension : June 30, 2024) | 2024-06-30 | 230H0084 | 230H0084 | July 24,2023 | 2023-08-03 | 2023-08-15 | Sept. 5, 2023 | Sept. 19, 2023 | ST. GABRIEL BUILDERS / LCRUZ CONSTRUCTION (JV) | complete | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 6 |  | 1 | 0 | 3
NEWCON 2023 | NCR | Pasig City | 305422 | Rizal Experimental Station And Pilot School for Cottage Industries (RESPSCI) | CITY OF PASIG | Lone | 1 | 8 | 4STY8CL | Batch 1 | 30262500 | 30000000 | 28949334.68 | Completed | 1 |  |  | P00775096LZ |  | 2023-07-10 | 2023-07-19 | 2023-08-01 | 2023-08-08 | 2023-08-14 | Magnificus Builders Inc. |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 0.7 | 0.3 | 4
NEWCON 2023 | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG | Lone | 1 | 28 | 4STY28CL | Batch 3 | 175000000 | 168875000 | 33054465.68 | On Going | 0.35 |  |  |  | 23OF0149 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | MILES TRADING AND CONSTRUCTION/OSCORD BUILDERS CORPORATION (JOINT VENTURE) |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.35
NEWCON 2023 | NCR | Quezon City | 136490 | Balingasa Elementary School | QUEZON CITY | 1st | 1 | 12 | 4STY12CL | Batch 1 | 33711931.83 | 33419511.11 | 33054465.68 | Suspended |  |  |  |  | 23OF0149 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | MILES TRADING AND CONSTRUCTION/OSCORD BUILDERS CORPORATION (JOINT VENTURE) | Waiting for the issuance of Demolition Permit for the existing school building and the approval from QC-LGU to demolish the buildig (Brgy. Day Care) located at the frontage of the school. | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 4
NEWCON 2023 | NCR | Quezon City | 340694 | Lucresia Kasilag Senior High School (SHS within E. Abada ES) | QUEZON CITY | 1st | 1 | 8 | 4STY8CL | Batch 1 | 30262500 | 30000000 | 29802912.39 | Completed | 1 | 2024-08-30 |  |  | 23OF0151 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | AYANA CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 0.82 | 0.18 | 4
NEWCON 2023 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1st | 1 | 8 | 4STY8CL | Batch 1 | 30262500 | 30000000 | 29803158.14 | Completed | 1 | 2024-11-15 |  |  | 23OF0150 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | WAY MAKER GENERAL CONTRACTOR OPC. |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 0.85 | 0.15 | 4
NEWCON 2023 | NCR | Quezon City | 305337 | Justice Cecilia Muñoz Palma High School | QUEZON CITY | 2nd | 1 | 8 | 4STY8CL | Batch 1 | 30262500 | 30000000 | 29851396.56 | Completed | 0.9 | 2024-12-12 |  |  |  | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | R. ROSE CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 0.1 | 0.8 | 4
NEWCON 2023 | NCR | Quezon City | 305352 | Juan Sumulong High School | QUEZON CITY | 3rd | 1 | 8 | 4STY8CL | Batch 1 | 30262500 | 30000000 |  | On Going | 0.75 | [10 empty] | 4 Sty 4 Cl with Repair/Rehab of 2 Sty Imelda BLDG & Site Dev, Pending issuance of Certificate of Coordination (to be issued by QC LGU) and Demolition Permit | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.15 | 0.6 | 4
NEWCON 2023 | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY | 4th | 1 | 8 | 4STY8CL | Batch 1 | 30262500 | 30000000 |  | Completed | 1 | [10 empty] | Phase 1 - 3Sty 6Cl, Pending issuance of Certificate of Coordination (issued by QC LGU) | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 0.65 | 0.35 | 4
NEWCON 2023 | NCR | Quezon City | 360867 | Leandro Locsin Integrated School | QUEZON CITY | 5th | 1 | 0 | Construction of School Building | Batch 1 | 10087500 | 10000000 |  | Suspended |  |  |  |  | 23OF0156 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | 10 BUILDERS AND DEVELOPMENT CORPORATION | Proposed 4Storey 4 Classrooms. waiting to commence once the 4sty-16cl is completed | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1
NEWCON 2023 | NCR | Quezon City | 305338 | Maligaya HS | QUEZON CITY | 5th | 1 | 0 | Construction of School Building | Batch 1 | 5043750 | 5000000 |  | Delisted |  |  |  |  | 23OF0153 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | FRAMECON BUILDERS | UNIMPLEMENTABLE. For Reversion of Fund for Rehabilitation/Repair of School Building | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1
NEWCON 2023 | NCR | Quezon City | 305341 | San Bartolome HS | QUEZON CITY | 5th | 1 | 0 | Construction of School Building | Batch 1 | 10087500 | 10000000 |  | Delisted |  |  |  |  | 23OF0154 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | CG GENERAL CONSTRUCTION & DEVELOPMENT CORPORATION | UNIMPLEMENTABLE. For Reversion of Fund for Rehabilitation/Repair of School Building | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1
NEWCON 2023 | NCR | Quezon City | 305635 | West Fairview High School | QUEZON CITY | 5th | 1 | 0 | Construction of School Building | Batch 1 | 5043750 | 5000000 | 4975914 | Completed | 1 | 2024-02-22 |  |  | 23OF0155 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | MILES TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 1
NEWCON 2023 | NCR | Quezon City | 305344 | Sauyo HS | QUEZON CITY | 6th | 1 | 10 | 2STY10CL | Batch 1 | 30262500 | 30000000 | 29849908.6 | On Going | 0.4 | 2024-09-18 |  |  | 23OF0163 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | MILES TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.1 | 0.3 | 2
NEWCON 2023 | NCR | Taguig | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS | 1st | 1 | 8 | 4STY8CL | Batch 1 | 10087500 | 10000000 | 9886489.56 | Completed | 1 | 2024-04-10 |  | P00775108LZ | 23OB0484 | 2023-12-07 | 2023-12-15 | 2023-12-28 | 2023-12-29 | 2024-01-12 | B. Valencerina Trading and Construction | On-going plumbing,sanitary works, and painting works | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2023 | NCR | Taguig | 320601 | Taguig Science High School | TAGUIG CITY | 1st | 1 | 12 | 4STY12CL | Batch 1 | 20175000 | 20000000 | 18996358.85 | On Going | 0.95 |  |  | P00775109LZ | 23OB0461 | 2023-07-10 | 2023-07-19 | 2023-08-01 | 2023-08-08 | 2023-08-15 | TWENTYSIX CONSTRUCTION INC. | Roofdeck and Masonry Works | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.6 | 0.35 | 4
NEWCON 2023 | NCR | Taguig | 502057 | Bagong Tanyag Integrated School | TAGUIG CITY | 2nd | 1 | 9 | 3STY9CL | Batch 1 | 30262500 | 30000000 | 29644438.12 | On Going | 0.95 | 2024-08-05 |  | P00775110LZ | 23OB0468 | 2023-12-08 | 2023-12-08 | 2023-12-29 | 2023-12-29 | 2024-01-09 | B. Bernardo Construction Inc. | For punchlist | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0.85 | 0.1 | 3
NEWCON 2023 | NCR | Valenzuela City |  | Pasolo National High School | CITY OF VALENZUELA | 1st | 1 | 12 | 4STY12CL | Batch 1 | 32280000 | 32000000 | 28782907.95 | Completed | 1 | 2024-04-11 |  | P00775112LZ | 23OD0235 | 2023-06-22 | 2023-06-29 | 2023-07-11 | 2023-07-17 | 2023-08-16 | Rworkmate Construction | Phase 1 only, for final inspection of DepEd | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 12 |  | 0.95 | 0.05 | 4
NEWCON 2023 | NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA | 2nd | 1 | 8 | 4STY8CL | Batch 1 | 29657250 | 29400000 | 28782907.95 | Completed | 1 | 2024-04-11 |  | P00775112LZ | 23OD0235 | 2023-06-22 | 2023-06-29 | 2023-07-11 | 2023-07-17 | 2023-08-16 | Rworkmate Construction | Turn Over to School | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 0.95 | 0.05 | 4
NEWCON 2022 | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | [10 empty] | Completed as of March 16, 2023 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2022 | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | Construction of School Building | 1 |  | 30450937.5 |  | Completed | 1 | 00:00:00 | [9 empty] | - ongoing embankment; - remaining activities, left side stairs and septic vault | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 12 |  | 1 | 0 | 4
NEWCON 2022 | NCR | Navotas | 136862 | North Bay Boulevard Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | Construction of School Building | 1 |  | 30450937.5 |  | Completed | 1 | August 5, 2023 | [9 empty] | Issued Suspension Order No. 1 (60 C.D.) with Contract Time Extension No. 1 (60 C.D.) due to the pending completion of demolition works implemented by the Navotas City DepED | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 12 |  | 1 | 0 | 4
NEWCON 2022 | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | 2023-05-25 | [9 empty] | Issued Suspension Order/Time Extension No. 1 (93C.D.) due to pending demolition of existing structure by DepEd Issued Time Extension No. 2 (15C.D.) due to limited access to project site | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2022 | NCR | Navotas | 136866 | San Roque Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | [10 empty] | Completed as of April 01, 2023 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2022 | NCR | Navotas | 136867 | Tangos Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | Construction of School Building | 1 |  | 30450937.5 |  | Completed | 1 | June 6, 2023 | [9 empty] | Ongoing installation of second floor RSB | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 12 |  | 1 | 0 | 4
NEWCON 2022 | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | Construction of School Building | 1 |  | 30450937.5 |  | Completed | 1 | June 6, 2023 | [9 empty] | - on going chb laying - 15 columns at grids 1-5 to be poured by Tuesday | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 12 |  | 1 | 0 | 4
NEWCON 2022 | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | 2023-02-06 | Januarty 24, 2023 | [8 empty] | Completed as of January 24, 2023 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2022 | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | 2023-05-22 | [9 empty] | Issued Suspension Order/Time Extension No. 1 (60 C.D.) to give way to the construction of temporary acess points for entrance and exit of the adjacent school building Issued Suspension Order/Time Extension No. 2 (45 C.D.) due to suspended/unworkable days brought by inclement weather condition | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 8 |  | 1 | 0 | 4
NEWCON 2021 | NCR | Caloocan City | 136634 | Camarin Elementary School | KALOOKAN CITY | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 1002500 | 1000000 | 996110.17 | Completed | 1 | 2021-10-27 |  | P00575461LZ | 21OD0197 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Aylan Const. & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Caloocan City | 136634 | Camarin Elementary School | KALOOKAN CITY | 1 |  | 8 | Construction/Completion (4STY8CL) |  | 2005000 | 2000000 | 1994008.08 | Completed | 1 | 2021-11-26 |  | P00575462LZ | 21OD0200 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Aylan Const. & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Caloocan City | 136654 | Llano ES | CALOOCAN CITY | 1 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 1494229.88 | Completed | 1 | 2021-10-27 |  | P00575463LZ | 21OD0195 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | C.B. Tampengco Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Caloocan City | 305374 | Camarin HS | CALOOCAN CITY | 1 | 1 | 16 | Construction/Completion (2-4STY8CL) |  | 2005000 | 2000000 | 1996667.41 | Completed | 1 | 2021-12-26 |  | P00575464LZ | 21OD0196 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Aylan Const. & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Caloocan City | 305380 | Tala High School | KALOOKAN CITY | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 4010000 | 4000000 | 3989457.54 | Completed | 1 | 2021-12-26 |  | P00575465LZ | 21OD0224 | 2021-08-04 | 2021-08-11 | 2021-08-23 | 2021-09-13 | 2021-09-27 | Aylan Const. & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Caloocan City | 305381 | Bagong Silang HS | KALOOKAN CITY | 1 | 1 | 6 | Construction/Completion (3STY6CL) (construction of 1CL at 2nd Floor, Staircase, CR with Septic Tank & repair/refurbishment of 5CL)) |  | 4010000 | 4000000 | 3986234.57 | Completed | 1 | 2021-12-26 |  | P00575466LZ | 21OD0206 | 2021-07-16 | 2021-07-23 | 2021-08-04 | 2021-08-23 | 2021-09-27 | AGH Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | 0 | 3
NEWCON 2021 | NCR | Caloocan City | 305383 | Bagong Barrio NHS | Caloocan City | 1 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 1495444.36 | Completed | 1 | 2021-10-27 |  | P00575467LZ | 21OD0199 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Probuilds & Works Construction Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Caloocan City | 305383 | Bagong Barrio NHS | Caloocan City | 1 |  | 8 | Construction/Completion (4STY8CL) |  | 1503750 | 1500000 | 1495444.36 | Completed | 1 | 2021-10-27 |  | P00575468LZ | 21OD0198 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Probuilds & Works Construction Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Paranaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 | 1 | 2 | Construction/Completion (4STY2CL) |  | 5012500 | 5000000 | 4849479.06 | Completed | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | Jalenz Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Paranaque City | 320201 | Paranaque Science HS | CITY OF PARAÑAQUE | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 20050000 | 20000000 | 19500585.67 | Completed | 1 | 2022-04-11 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | YPR General Contractor and Construction Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Paranaque City | 136761 | Col. E. De Leon Elementary School | CITY OF PARAÑAQUE | 2 | 1 | 32 | Construction/Completion (4STY32CL) |  | 10025000 | 10000000 | 9698075.4 | Completed | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | Golden 3T Construction Corp, |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Paranaque City | 136763 | F. Serrano Sr. ES | CITY OF PARAÑAQUE | 2 | 1 | 8 | Construction/Completion (4-STOREY) |  | 8020000 | 8000000 | 7757714.6 | Completed | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | GMO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Paranaque City | 226001 | Sun Valley ES | CITY OF PARAÑAQUE | 2 | 1 | 3 | Construction/Completion (3STY3CL) |  | 7518750 | 7500000 | 7274965.25 | Completed | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | GMO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 3
NEWCON 2021 | NCR | Paranaque City | 305428 | Dr. Arcadio Santos NHS - Main | CITY OF PARAÑAQUE | 2 | 1 | 8 | Construction/Completion (4-STOREY) |  | 6015000 | 6000000 | 5819939.36 | Completed | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | GMO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Paranaque City | 320203 | Moonwalk National High School | CITY OF PARAÑAQUE | 2 | 1 | 1 | Construction/Completion (4STY4CL) |  | 2506250 | 2500000 | 2424970.58 | Completed | 1 | 2022-01-11 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | RGDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Paranaque City |  | Marcelo Green HS | CITY OF PARAÑAQUE | 2 | 1 | 1 | Construction/Completion (4-STOREY) |  | 2005000 | 2000000 | 1939135.79 | Completed | 1 | 2022-01-11 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | RGDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Paranaque City |  | Silverio Annex Elementary School | CITY OF PARAÑAQUE | 2 | 1 | 1 | Construction/Completion (Four (4) Storey & Three (3) Storey) |  | 1002500 | 1000000 | 979905.88 | Completed | 1 | 2021-12-12 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | Lizvil Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1002500 | 1000000 |  | Completed | 1 | [8 empty] | 2021-11-09 | RAMALLA CONSTRUCTION & TRADING | Completion Works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 4522277.5 | 4511000 |  | Completed | 1 | [8 empty] | 2021-11-09 | JYBL CONSTRUCTION & TRADING | Completion Works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 136498 | San Francisco ES | QUEZON CITY | 1 | 1 | 32 | Construction/Completion (4STY32CL) |  | 13032500 | 13000000 |  | Completed | 1 | [8 empty] | 2021-11-09 |  | no movement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 305327 | San Francisco High School | QUEZON CITY | 1 | 1 | 32 | Construction/Completion (2 units 4STY16CL) |  | 13032500 | 13000000 |  | Completed | 1 | [8 empty] | 2021-11-09 | AYLAN CONSTRUCTION & TRADING | Completion Works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 136546 | Manuel L. Quezon ES | QUEZON CITY | 2 | 1 | 28 | Construction/Completion (4STY28CL) |  | 6015000 | 6000000 |  | Completed | 1 | [8 empty] | 2021-11-09 | J. SIMEON CONSTRUCTION | Completed based on DPWH; No movement yet, ongoing phase 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 136549 | Payatas B Annex ES | QUEZON CITY | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1002500 | 1000000 |  | Completed | 1 | [8 empty] | 2021-11-09 | JYBL CONSTRUCTION & TRADING | Completed based on DPWH; No movement yet | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 305331 | Commonwealth HS | QUEZON CITY | 2 | 1 | 12 | Construction/Completion (4STY12CL) |  | 7017500 | 7000000 |  | Completed | 1 | [8 empty] | 2021-11-09 | AYLAN CONSTRUCTION & TRADING | Completed based on DPWH; no movement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5 |  | 12 | Construction/Completion (4STY12CL) |  | 4957362.5 | 4945000 |  | Completed | 1 | [8 empty] | 2021-11-09 | JYBL CONSTRUCTION & TRADING | no movement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 136528 | Rosa L. Susano - Novaliches ES | QUEZON CITY | 5 | 1 | 16 | Construction/Completion (4STY16CL) |  | 2005000 | 2000000 |  | Completed | 1 | [8 empty] | 2021-11-09 | J. SIMEON CONSTRUCTION | Completed based on DPWH; No movement yet, ongoing phase 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 136529 | San Gabriel ES | QUEZON CITY | 5 | 1 | 8 | Construction/Completion (4STY8CL) |  | 4736812.5 | 4725000 |  | Completed | 1 | [8 empty] | 2021-11-09 | TAPNIO AND TAN CONSTRUCTION AND DEVELOPMENT CORPORATION | no movement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 136530 | Villa Verde Elementary School | QUEZON CITY | 5 | 1 | 12 | Construction/Completion (4STY12CL) |  | 7017500 | 7000000 |  | Completed | 1 | [8 empty] | 2021-11-09 | RAMALLA CONSTRUCTION & TRADING | Completed based on DPWH;; only 1 bldg constructed 4sty16cl needs to be removed in this list | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 136530 | Villa Verde Elementary School | QUEZON CITY | 5 |  | 16 | Construction/Completion (4STY16CL) |  | 3007500 | 3000000 |  | Completed | 1 | [8 empty] | 2021-11-09 |  | no movement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 4957362.5 | 4945000 |  | Completed | 1 | [8 empty] | 2021-11-09 | E.I. VILLACORTE CONSTRUCTION | Completed based on DPWH;; no movement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Valenzuela City | 136807 | Pio Valenzuela ES | CITY OF VALENZUELA | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1503750 | 1500000 | 1473340.67 | Completed | 1 | 2021-11-25 |  | P00575495LZ | 21OD0207 |  |  | 2021-08-04 |  | 2021-09-27 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Valenzuela City | 136811 | WawangPulo ES | CITY OF VALENZUELA | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1503750 | 1500000 | 1472681.08 | Completed | 1 | 2021-11-25 |  | P00575492LZ | 21OD0225 |  |  | 2021-08-23 |  | 2021-09-27 | Toughbulit Const & Trading Inc |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Valenzuela City | 305436 | Polo NHS | CITY OF VALENZUELA | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 2005000 | 2000000 | 1956107.88 | Completed | 1 | 2021-11-25 |  | P00575493LZ | 21OD0209 |  |  | 2021-08-04 |  | 2021-09-27 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 711229.8305 | 709456.19 | 696652.75 | Completed | 1 | 2021-10-26 |  | P00575494LZ | 21OD0203 |  |  | 2021-07-28 |  | 2021-09-27 | C.L. Morales Const & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Valenzuela City | PSA328384 | SHS IN ARKONG BATO, VALENZUELA | CITY OF VALENZUELA | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 2005000 | 2000000 | 1961127.65 | Completed | 1 | 2021-11-25 |  | P00575495LZ | 21OD0208 |  |  | 2021-08-04 |  | 2021-09-27 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Valenzuela City | 136823 | Constantino ES | CITY OF VALENZUELA | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 781950 | 780000 | 768429.01 | Completed | 1 | 2021-10-26 |  | P00575496LZ | 21OD0205 |  |  | 2021-08-04 |  | 2021-09-27 | Carry On Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 516396.7123 | 515108.94 | 504747.74 | Completed | 1 | 2021-10-26 |  | P00575492LZ | 21OD0225 |  |  | 2021-08-23 |  | 2021-09-27 | Flordes Const & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 | 1 | 20 | Construction/Completion (4STY20CL) |  | 3483802.3564 | 3475114.57 | 3935191.55 | Completed | 1 | 2022-01-24 |  | P00575498LZ | 21OD0223 |  |  | 2021-08-23 |  | 2021-09-27 | DJB Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 |  | 8 | Construction/Completion (4STY8CL) |  | 1152875 | 1150000 | 1127121.68 | Completed | 1 | 2021-10-26 |  | P00575499LZ | 21OD0202 |  |  | 2021-07-28 |  | 2021-09-27 | Carry On Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2021 | NCR | Valenzuela City |  | Disiplina Village NHS | CITY OF VALENZUELA | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1102750 | 1100000 | 1080261.59 | Completed | 1 | 2021-10-26 |  | P00575400LZ | 21OD0201 |  |  | 2021-07-28 |  | 2021-09-27 | Miles Trading & Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 4
NEWCON 2020 | NCR | Caloocan City | 136640 | Sto. Niño Elementary School | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL |  | 24761750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Caloocan City | 319701 | Cielito Zamora Senior High School | KALOOKAN CITY | 1 | 1 | 12 | 4STY12CL |  | 41904500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Caloocan City | 136623 | Barrio San Jose ES | KALOOKAN CITY | 2 | 1 | 12 | 4STY12CL |  | 41603750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Las Piñas City | 136779 | Pulanlupa ES | CITY OF LAS PIÑAS | 0 | 1 | 12 | 4STY12CL |  | 38596250 |  | 37576003.99 | Completed | 1 |  |  |  | 20OI0090 | 2020-01-08 | 2020-01-15 | 2020-01-29 | 2020-01-29 | 2020-08-18 | RR Encado Constructors Inc./Rocksteel Const. & Dev`t Corp (Joint Venture) | Completed as per DPWH; very slow moving of the work accomplishment due to minimal delivery of constraction materials on site | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Las Piñas City | 305430 | Las Piñas National High School | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL |  | 26967250 |  | 26335101.13 | Completed | 1 |  | 2021-08-03 |  | 20OI0089 | 2020-01-08 | 2020-01-15 | 2020-01-29 | 2020-01-29 | 2020-08-18 | Metrics Construction and Trading | Turned-over | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Malabon City | 136833 | Santulan ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL |  | 38596250 |  |  | Completed | 1 | 2020-05-02 |  |  | 20OA0075 |  |  | 2020-07-20 |  |  | solenko construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL |  | 38596250 |  |  | Completed | 1 | 2020-05-02 |  |  | 20OA0074 |  |  | 2020-07-20 |  |  | newbig four J construction inc |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Mandaluyong City |  | Senate President Neptali A. Gonzales IS | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL |  | 27067500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Manila | 136423 | Mariano Ponce Elementary School | TONDO | 2 | 1 | 16 | 4STY16CL |  | 90773235.11 |  |  | Completed | 1 | [10 empty] | on-going concreting works at 1st floor | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2020 | NCR | Manila | 500567 | F. G. Calderon Elementary School | TONDO | 2 | 1 | 12 | 4STY12CL |  | 69077262.5 |  |  | Completed | 1 | [10 empty] | Completed as per DPWH; Ongoing concreting at ground floor | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3 | 1 | 8 | 4STY8CL (COMPLETION) |  | 10075125 |  |  | Completed | 1 | [10 empty] | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ | 3 | 1 | 20 | 4STY20CL |  | 97267562.5 |  |  | Completed | 1 | [10 empty] | Ongoing concreting at ground floor | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2020 | NCR | Manila | 136456 | P. Guevara Elementary School | SAN NICOLAS | 3 | 1 | 12 | 4STY12CL |  | 33040842.6 |  |  | Completed | 1 | [10 empty] | Ongoing concreting at ground floor | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Manila | 136458 | Laong Laan ES | SAMPALOC | 4 | 1 | 12 | 4STY12CL |  | 62255250 |  |  | Completed | 1 | [10 empty] | on-going foundation works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Manila | 136480 | Bagong Barangay Elementary School | PANDACAN | 6 | 1 | 8 | 4STY8CL |  | 27067500 |  |  | Completed | 1 | [10 empty] | on-going foundation works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Marikina City | 319906 | Sto. Nino National High School | CITY OF MARIKINA | 1 | 1 | 8 | 4STY8CL with Mat Foundation |  | 34887000 |  |  | Completed | 1 | April 3,2021 | April 3,2021 |  | 20OB0421 | May 26,2020 | June 3,2020 | June 16,2020 |  | August 7,2020 | MRBII Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL |  | 19548750 |  | 19051420.15 | Completed | 1 | 03/21/21 | 2021-09-30 | P00470027LZ-CW1 | 20OI0092 | 2020-01-03 | 2020-01-15 | 2020-01-29 | 2020-02-20 | 2020-08-18 | RGDG Construction | Due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Muntinlupa City | 281541 | Poblacion ES | Muntinlupa | 0 | 1 | 8 | 4STY8CL |  | 24761750 |  | 24391249.6 | Completed | 1 |  |  | P00470028LZ-CW1 | 20OI0093 | 2020-01-03 | 2020-01-15 | 2020-01-29 | 2020-02-20 | 2020-08-18 | GREAT PACIFIC Builders and Gen. Contractor Inc. | due to pandemic and demoliion of NAWASA elevated tank | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Navotas City | 305453 | Navotas NHS | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL (7X8) |  | 38596250 |  |  | Completed | 1 | 2021-05-05 | [8 empty] | MRBll Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Paranaque City | 136768 | Baclaran ES Unit I | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL with ROOFDECK |  | 24747486.2 |  | 23944652.12 | Completed | 1 | 2021-09-13 |  | P00470030LZ-CWI |  |  |  | 2020-09-09 | 2020-09-15 | 2020-09-18 | J.A. Evangelista Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Paranaque City | 136763 | F. Serrano Sr. ES - Don Bosco | CITY OF PARAÑAQUE | 2 | 1 | 8 | 4STY8CL with ROOFDECK |  | 24747486.2 |  | 24191889.08 | Completed | 1 | 2021-09-13 |  | P00470031LZ-CWI |  |  |  | 2020-09-09 | 2020-09-15 | 2020-09-18 | GREAT PACIFIC Builders and Gen. Contractor Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Pasig City | 136727 | Kalawaan ES | Pasig City | 0 | 1 | 8 | 4STY8CL |  | 40049665.93 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Pasig City | 136731 | Oranbo ES | Pasig City | 0 | 1 | 16 | 4STY16CL |  | 59962819.77 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2020 | NCR | Pasig City | 136743 | San Miguel Elementary School | CITY OF PASIG | 0 | 1 | 8 | 4STY8CL |  | 30032092.31 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Pasig City | 340654 | SHS in Buting, Pasig City | Pasig City | 0 | 1 | 16 | 4STY16CL WITH ROOF DECK |  | 87205470 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2020 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1 | 1 | 8 | 4STY8CL |  | 22556250 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Quezon City | 136546 | Manuel L. Quezon ES | QUEZON CITY | 2 | 1 | 28 | 4STY28CL |  | 87718750 |  |  | Completed | 1 | [10 empty] | Completed as of DPWH; DEMOLITION COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1 | 0
NEWCON 2020 | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5 | 1 | 12 | 4STY12CL |  | 40902000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Quezon City | 136528 | Rosa L. Susano - Novaliches ES | QUEZON CITY | 5 | 1 | 16 | 4STY16CL |  | 52130000 |  |  | Completed | 1 | [10 empty] | 100 %, DEMOLITION COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2020 | NCR | Quezon City | 136529 | San Gabriel ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL |  | 22556250 |  |  | Completed | 1 | [10 empty] | Mobilized | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY | 5 | 1 |  | CONSTRUCTION OF RETAINING WALL |  | 13964825 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2020 | NCR | Quezon City | 136519 | Lucas R. Pascual Mem. ES | QUEZON CITY | 6 | 1 | 12 | 4STY12CL |  | 44957112.5 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6 | 1 | 12 | 4STY12CL |  | 40250375 |  |  | Completed | 1 | [10 empty] | 100 %, DEMOLITION COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Taguig City & Pateros | 136892 | Aguho Elementary School | PATEROS | 1 | 1 | 12 | 4STY12CL WITH ROOF DECK |  | 47151585 |  | 45551188.88 | Completed | 1 | July 21, 2021 |  | P00470044LZ | 20OB0433 |  |  | July 15, 2020 |  |  | Newbig Four J Construction Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | Pateros | 1 | 1 | 16 | 4STY16CL |  | 71177500 |  | 68609100.51 | Completed | 1 | June 6, 2021 |  | P00470045LZ | 20OB0423 |  |  | June 16, 2020 |  |  | MRBII Construction Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2020 | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL WITH ROOF DECK |  | 46917000 |  | 45190402.5 | Completed | 1 | July 21, 2021 |  | P00470046LZ | 20OB0424 |  |  | June 16, 2020 |  |  | Flordes Construction and Trading Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Taguig City & Pateros | 320601 | Taguig Science High School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL with roofdeck (With Provision for 4sty12Cl) |  | 35087500 |  | 33833315.44 | Completed | 1 | May 7, 2021 |  | P00470050LZ | 20OB0422 |  |  | December 19, 2019 |  |  | Hony Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL |  | 35262937.5 |  | 34566172.31 | Completed | 1 | July 29, 2021 |  | P00470048LZ | 20OBD0171 |  |  | August 18, 2020 |  |  | St. Timothy Construction Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Taguig City & Pateros | 228002 | Gat. Andres Bonifacio Elmentary School | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL WITH ROOF DECK |  | 50125000 |  | 44,415,982,51 | Completed | 1 | May 22, 2021 |  | P00470049LZ | 20OB0172 |  |  | December 19, 2019 |  |  | MRBII Construction Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Taguig City & Pateros | 305463 | Signal Village National High School | TAGUIG CITY | 2 | 1 | 20 | 4STY20CL |  | 64861750 |  | 62521178.4 | Completed | 1 | June 21, 20221 |  | P00470050LZ | 20OB0422 |  |  | June 16, 2020 |  |  | Orani Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2020 | NCR | Valenzuela City | 136795 | Lingunan ES | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL |  | 24360750 |  |  | Completed | 1 | 2021-04-13 | 2021-07-06 | P00470051LZ | 20OD0103 |  |  |  |  | 2020-08-17 | Toughbuilt Const. & Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Valenzuela City |  | Veinte Reales HS | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL |  | 24482553.75 |  | 23853462.32 | Completed | 1 | 2021-04-13 | 2021-07-06 | P00470052LZ | 20OD0104 |  |  |  |  | 2020-08-17 | Toughbuilt Const. & Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2020 | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2 | 1 | 16 | 4STY16CL |  | 47167625 |  | 45850285.22 | Completed | 1 | 2021-07-12 |  | P00470053LZ | 20OD0193 |  |  |  |  | 2020-08-17 | DJB Const. Services | Suspended due to presence of ISF | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2020 | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2 |  | 12 | 4STY12CL |  | 41653875 |  | 40530029.26 | Completed | 1 | 2021-06-12 |  | P00470054LZ | 20OD0192 |  |  |  |  | 2020-08-17 | DJB Const. Services | Suspended due to presence of ISF | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2020 | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2 |  | 8 | 4STY8CL |  | 24711625 |  | 24081305.36 | Completed | 1 | 2021-04-13 |  | P00470055LZ | 20OD0194 |  |  |  |  | 2020-08-17 | DJB Const. Services | On Going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2019 | NCR | Caloocan City | 305373 | Sampaguita HS | Caloocan City | 1 | 1 | 8 | 4STY8CL |  | 24060000 |  |  | Completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Caloocan City | 305386 | Deparo High School | Caloocan City | 1 | 1 | 8 | 4STY8CL |  | 24060000 |  |  | Completed | 1 | [10 empty] | exiting bldg - for demolition | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Caloocan City | 136633 | Camarin D ES | Caloocan City | 1 | 1 | 8 | 4STY8CL |  | 24060000 |  |  | Completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Caloocan City | 136633 | Camarin D ES | Caloocan City | 1 |  | 8 | 4STY8CL |  | 24060000 |  |  | Completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Caloocan City | 136639 | Bagong Silang ES | Caloocan City | 1 | 1 | 8 | 4STY8CL |  | 24060000 |  |  | Completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Caloocan City | 136613 | Maypajo ES | KALOOKAN CITY | 2 | 1 | 12 | 4STY12CL |  | 47418250 |  |  | Completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2019 | NCR | Caloocan City | 136606 | Grace Park ES (Main) | Caloocan City | 2 | 1 | 20 | 4STY20CL |  | 50947050 |  |  | Completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2019 | NCR | Caloocan City | 305388 | Caloocan HS | Caloocan City | 2 | 1 | 8 | 4STY8CL |  | 24060000 |  |  | Completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Malabon City | 136850 | Tinajeros ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL |  | 30877000 |  | 28446060 | Completed | 1 | [9 empty] | JUSTBILT Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Malabon City | 305450 | Panghulo NHS | CITY OF MALABON | 0 | 1 | 16 | 4STY16CL |  | 76671200 |  | 68593280 | Completed | 1 | [9 empty] | A.L. Salazar Construction inc./Rotaflex Cosntruction Dev.t Corp. (joint venture) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2019 | NCR | Manila | 500566 | T. Paez Integrated School (Elem.) | CITY OF MANILA | 1 | 1 | 20 | 4STY20CL |  | 68370500 |  |  | Completed | 1 | [10 empty] | DPWH Terminated the Contract under this project. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2019 | NCR | Manila | 136437 | Manuel L. Quezon Elementary School | CITY OF MANILA | 1 | 1 | 20 | 4STY20CL |  | 68370500 |  |  | Completed | 1 | [10 empty] | awaiting for the approval of central office for modification of plans and quantity of CLs | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2019 | NCR | Manila | 136437 | Manuel L. Quezon Elementary School | CITY OF MANILA | 1 |  | 24 | 2UNITS 4STY12CL |  | 99448000 |  |  | Terminated | 0.82 | [10 empty] | DPWH Terminated the Contract under this project; Completion of the school building already funded under GAA 2023 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24
NEWCON 2019 | NCR | Manila | 136439 | I. Delos Reyes ES | CITY OF MANILA | 1 | 1 | 32 | 4STY16CL |  | 57443250 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2019 | NCR | Manila | 136456 | P. Guevara Elementary School | CITY OF MANILA | 3 | 1 | 12 | 4STY12CL |  | 42907000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2019 | NCR | Manila | 136452 | P. Gomez ES | CITY OF MANILA | 3 | 1 | 12 | 4STY12CL |  | 52337464.7685 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2019 | NCR | Manila | 305302 | Jose Abad Santos High School | CITY OF MANILA | 3 | 1 | 16 | 4STY16CL |  | 83876040.8241 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2019 | NCR | Manila | 305300 | Cayetano Arellano High School | CITY OF MANILA | 3 | 1 | 12 | 4STY12CL |  | 66203184.4932 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2019 | NCR | Manila | 136446 | Andres Bonifacio Elementary School | CITY OF MANILA | 3 | 1 | 12 | 4STY12CL |  | 54417594.5245 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2019 | NCR | Manila | 136460 | G. Lopez Jaena Elementary School | CITY OF MANILA | 4 | 1 | 20 | 4STY20CL (SPECIAL DESIGN) |  | 56541000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2019 | NCR | Manila | 136472 | Pio del Pilar Elementary School | CITY OF MANILA | 5 | 1 | 8 | 4STY8CL |  | 29573750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Manila | 136482 | Bagong Diwa Elementary School | CITY OF MANILA | 6 | 1 | 24 | 4STY24CL |  | 49724000 |  |  | Completed | 1 | [10 empty] | awaiting for the approval of central office for modification of plans and quantity of CLs | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2019 | NCR | Manila | 136471 | Bacood Elementary School | CITY OF MANILA | 5 | 1 | 16 | 4STY16CL |  | 50726500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2019 | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL |  | 28070000 |  |  | Completed | 1 |  |  | P00370024LZ-CW1 | 19OI0140 | 08/01/2019 | 2019-08-07 | 2019-09-03 | 2019-09-12 | 2019-09-27 | I.F. CLEMENTE Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL |  | 49122500 |  |  | Completed | 1 |  |  | P00370025LZ-CW1 | 19OI0141 | 2019-08-01 | 2019-08-07 | 2019-08-19 | 2019-08-28 | 2019-09-09 | MRRM Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2019 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL |  | 38335600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL |  | 38335600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Quezon City | 136492 | Ramon Magsaysay ES | QUEZON CITY | 1 | 1 | 24 | 4STY24CL |  | 62756500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2019 | NCR | Quezon City | 136492 | Ramon Magsaysay ES | QUEZON CITY | 1 |  | 20 | 4STY20CL |  | 54185125 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2019 | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL |  | 22516150 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Quezon City | 136507 | Bagong Pag-Asa Elementary School | QUEZON CITY | 1 | 1 | 20 | 4STY20CL |  | 54185125 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2019 | NCR | Quezon City | 136507 | Bagong Pag-Asa Elementary School | QUEZON CITY | 1 |  | 16 | 4STY16CL |  | 46611237.5 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2019 | NCR | Quezon City | 136509 | Project 6 ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL |  | 22666525 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Quezon City | 136569 | Dona Josefa E. Marcos ES | QUEZON CITY | 3 | 1 | 8 | 4STY8CL |  | 30375750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Quezon City | 136569 | Dona Josefa E. Marcos ES | QUEZON CITY | 3 |  | 12 | 4STY12CL |  | 38095000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2019 | NCR | Quezon City | 305353 | Krus na Ligas HS | QUEZON CITY | 4 | 1 | 12 | 4STY12CL |  | 40100000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2019 | NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL |  | 24004862.5 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Taguig | 305464 | Tipas National High School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL w/ ROOFDECK |  | 56381109.0094 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2019 | NCR | Valenzuela City | 320407 | Wawangpulo National High School | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL |  | 16040000 |  |  | Completed | 1 | [9 empty] | Chrizmarie Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Valenzuela City | 136807 | Pio Valenzuela ES | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL |  | 48440800 |  |  | Completed | 1 | [9 empty] | Greenplains Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2019 | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 | 1 | 20 | 4STY20CL |  | 51648489.1147 |  |  | Completed | 1 | [9 empty] | St. Timothy Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2019 | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 |  | 16 | 4STY16CL |  | 45893588.7322 |  |  | Completed | 1 | [9 empty] | St. Timothy Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2019 | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 |  | 8 | 4STY8CL |  | 22502549.9446 |  |  | Completed | 1 | [9 empty] | C.L. Morales Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Valenzuela City | 320406 | Canumay East National High School | CITY OF VALENZUELA | 1 | 1 | 16 | 2UNITS 4STY8CL |  | 45120136.644 |  |  | Completed | 1 | [9 empty] | Alpha & Omega General Contractor and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2019 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL |  | 22697871.3705 |  |  | Completed | 1 | [9 empty] | Flordes Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2019 | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 | 1 | 20 | 4STY20CL |  | 47655164.2386 |  |  | Completed | 1 | [9 empty] | Alpha & Omega General Contractor and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Caloocan City | 136627 | Bagong Barrio ES | KALOOKAN CITY | 1 | 1 | 20 | 4STY20CL | Batch 3 | 49570000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Caloocan City | 136629 | Morning Breeze Elementary School | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Caloocan City | 136630 | Sta. Quiteria ES | KALOOKAN CITY | 1 | 1 | 16 | 4STY16CL | Batch 3 | 46250000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Caloocan City | 136631 | Talipapa ES | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Caloocan City | 136633 | Camarin D ES | KALOOKAN CITY | 1 |  | 20 | 4STY20CL | Batch 3 | 49050000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Caloocan City | 136634 | Camarin Elementary School | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | Completed | 1 | [10 empty] | awaiting additional fund | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Caloocan City | 136639 | Bagong Silang ES | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Caloocan City | 136642 | Silanganan ES (Star ES) | KALOOKAN CITY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 38270000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Caloocan City | 136643 | A. Mabini Elementary School | KALOOKAN CITY | 1 | 1 | 24 | 2 Units 4STY12CL | Batch 3 | 79200000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Caloocan City | 136649 | Tala ES | KALOOKAN CITY | 1 | 1 | 16 | 4STY16CL | Batch 3 | 44050000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Caloocan City | 136655 | Sampaguita Elementary School | KALOOKAN CITY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 39770000 |  |  | Completed | 1 | [10 empty] | Delayed Implementation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Caloocan City | 223501 | Caloocan North ES | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Caloocan City | 305372 | Bagumbong High School | KALOOKAN CITY | 1 | 1 | 16 | 2 units 4STY8CL | Batch 3 | 44500000 |  |  | Completed | 1 | [10 empty] | Completed as per DPWH; 1 Unit partially completed (for installation of fire pro), 1 unit at 70% status though continous ongoing of works; Contractor committed to turn-over the buildings by April 30, 2023 Last Inspection: April 3 with UED, AM Nhey and Division Engrs | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Caloocan City | 305374 | Camarin High School | KALOOKAN CITY | 1 | 1 | 20 | 4STY20CL | Batch 3 | 49330000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Caloocan City | 305376 | Amparo High School | KALOOKAN CITY | 1 | 1 | 16 | 4STY16CL | Batch 3 | 46050000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Caloocan City | 305386 | Deparo High School | KALOOKAN CITY | 1 |  | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Caloocan City |  | CIELITO ZAMORA HS- BONIFACIO CAMPUS | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22450000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Caloocan City |  | Bagong Silang Resettlement Project | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Caloocan City |  | Bagong Silang Resettlement Project | KALOOKAN CITY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 40850000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Caloocan City |  | Camarin Brixton Senior High School | KALOOKAN CITY | 1 | 1 | 20 | 4STY20CL | Batch 3 | 51150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Caloocan City | 136614 | Sampalukan ES | KALOOKAN CITY | 2 | 1 | 20 | 4STY20CL | Batch 3 | 51730000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Caloocan City | 136618 | Gregoria de Jesus ES | KALOOKAN CITY | 2 | 1 | 20 | 4STY20CL | Batch 3 | 51650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Las Piñas City | 136784 | Dona Manuela ES | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | Batch 3 | 18655000 |  |  | Completed | 1 | [10 empty] | On-going construction, target completion in December 2020. Pump installed. For joint final inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Las Piñas City | 136785 | Moonwalk ES | CITY OF LAS PIÑAS | 0 | 1 | 20 | 4STY20CL | Batch 3 | 45780000 |  |  | Completed | 1 | [10 empty] | On-going construction, target completion in December 2020. Pump installed. For joint final inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Makati City | 305406 | Makati High School | CITY OF MAKATI | 1 | 1 | 12 | 6STY12CL | Batch 3 | 51691232.21 |  | 50402601.87 | Completed | 1 | [8 empty] | December 27, 2018 | C.B. GARAY PHILWIDE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Makati City | 136697 | Tibagan ES | CITY OF MAKATI | 2 | 1 | 24 | 6STY24CL | Batch 3 | 82782166.63 |  | 80720496.68 | Completed | 1 | [8 empty] | January 8, 2019 | DUMDUMA CONSTRUCTION AND TRADING CORPORATION / STUDIO 26 CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Malabon City | 136836 | Ninoy Aquino ES | CITY OF MALABON | 0 | 1 | 24 | 4STY24CL | BATCH 1 | 81600000 |  | 78707083.61 | Completed | 1 | 2019-09-04 |  |  | 18OA0118 |  |  | 8/31/18 (338) |  |  | Cardrian Builders Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Malabon City | 136852 | Acacia ES | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 40800000 |  | 38530451.32 | Completed | 1 | 2019-05-24 |  |  | 18OA0115 | [5 empty] | C.B. Tampengco Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 40800000 |  | 39336781.16 | Completed | 1 | 2019-05-23 |  |  | 18OA0105 |  |  | 8/16/2018 (240) |  |  | Hexamindz Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Malabon City | 136834 | Imelda ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | Batch 3 | 30800000 |  | 29694849.81 | Completed | 1 | 2019-07-20 |  |  | 18OA0124 | [5 empty] | 124 Triumph Builders & Steel Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Malabon City | 136838 | Tañong ES I | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | Batch 3 | 38240000 |  | 36901685.25 | Completed | 1 | 2019-09-29 |  |  | 18OA0122 | [5 empty] | M.G. Salazar Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Malabon City | 136845 | Niugan ES | CITY OF MALABON | 0 | 1 | 16 | 4STY16CL | Batch 3 | 76480000 |  | 76085502.37 | Completed | 1 | 2019-12-06 |  |  | 18OA0123 | [5 empty] | NEW BIG FOURJ CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Malabon City | 136848 | Potrero ES | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | Batch 3 | 46200000 |  | 44579287.17 | Completed | 1 | 2019-10-24 |  |  | 18OA0121 | [5 empty] | St. Timothy Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Malabon City | 136855 | Maysilo ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | Batch 3 | 35840000 |  | 34696920.83 | Completed | 1 | 2019-08-27 |  |  | 18OA0125 | [5 empty] | Steven Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Mandaluyong City | 305395 | City of Mandaluyong Science HS | CITY OF MANDALUYONG | 0 | 1 | 4 | 4STY4CL | Batch 3 | 14364000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | NCR | Mandaluyong City | 305395 | City of Mandaluyong Science HS | CITY OF MANDALUYONG | 0 |  | 24 | 4STY24CL | Batch 3 | 60000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Mandaluyong City | 500333 | Eulogio Rodriguez Integrated School | CITY OF MANDALUYONG | 0 | 1 | 20 | 4STY20CL | Batch 3 | 50000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Mandaluyong City | 500333 | Eulogio Rodriguez Integrated School | CITY OF MANDALUYONG | 0 |  | 12 | 4STY12CL | Batch 3 | 32572215.9469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Mandaluyong City | 500333 | Eulogio Rodriguez Integrated School | CITY OF MANDALUYONG | 0 |  | 4 | 4STY4CL | Batch 3 | 10000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | NCR | Mandaluyong City |  | Sen. Neptali A. Gonzales Integrated School | CITY OF MANDALUYONG | 0 | 1 | 32 | 4STY32CL | Batch 3 | 80000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2018 | NCR | Mandaluyong City |  | Sen. Neptali A. Gonzales Integrated School | CITY OF MANDALUYONG | 0 |  | 12 | 4STY12CL | Batch 3 | 32572215.9469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Manila | 136439 | I. Delos Reyes ES | TONDO | 1 | 1 | 16 | 4STY16CL | Batch 3 | 57300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Manila | 136449 | Juan Sumulong Elementary School | SANTA CRUZ | 3 | 1 | 12 | 4STY12CL | Batch 3 | 50000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Manila | 340599 | SHS within A.Maceda Intg. Sch.-(HS) | CITY OF MANILA | 4 | 1 | 4 | 4STY4CL (SPECIAL DESIGN) | Batch 3 | 23600000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | NCR | Manila | 136476 | E. delos Santos Elementary School | CITY OF MANILA | 5 | 1 | 40 | 4STY40CL | Batch 3 | 116010000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2018 | NCR | Manila | 136489 | Tomas Earnshaw Elementary School | SANTA ANA | 6 | 1 | 24 | 4STY24CL | Batch 3 | 81902000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1 | 1 | 28 | 4STY28CL | Batch 5 | 229660358.78 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0
NEWCON 2018 | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1 |  | 8 | 4STY8CL | Batch 5 | 49276374.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Manila | 136443 | Gen. Gregorio del Pilar ES | TONDO | 2 | 1 | 16 | 4STY16CL | Batch 5 | 90600000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2 | 1 | 16 | 4STY16CL | Batch 5 | 80300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2 |  | 12 | 4STY12CL | Batch 5 | 65000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Manila | 305298 | Florentino Torres High School | TONDO | 2 | 1 | 16 | 4STY16CL | Batch 5 | 81200000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Manila | 305298 | Florentino Torres High School | TONDO | 2 |  | 12 | 4STY12CL | Batch 5 | 70200000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Manila | 136466 | V. E. Fugoso Memorial School | SAMPALOC | 4 | 1 | 20 | 4STY20CL | Batch 5 | 54300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Manila | 136476 | E. delos Santos Elementary School | CITY OF MANILA | 5 | 1 | 22 | 4STY22CL | Batch 5 | 67588702.95 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 22 | 0
NEWCON 2018 | NCR | Manila | 136479 | Rafael Palma Elementary School | CITY OF MANILA | 5 | 1 | 24 | 4STY24CL | Batch 5 | 78327248.76 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Manila | 136489 | Tomas Earnshaw Elementary School | SANTA ANA | 6 | 1 | 28 | 4STY28CL | Batch 5 | 86806728.08 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0
NEWCON 2018 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 | 1 | 12 | 4STY12CL | Batch 3 | 60851765.74 |  |  | Completed | 1 | [9 empty] | Alpha-Omega Gen Con & Dep't. Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 | 1 | 24 | 4STY24CL | Batch 3 | 67546019.91 |  |  | Completed | 1 | [8 empty] | 2019-01-14 | Vinnel-Belvoir Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Muntinlupa City | 136900 | F. De Mesa ES | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | Batch 3 | 45992000 |  |  | Completed | 1 |  |  |  | 18OI0180 | November 22-Decembr 11, 2018 | November 29, 2018 | December 11, 2018 |  | 12/28/18 | MRRM Trading & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Muntinlupa City | 136901 | Itaas Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | Batch 3 | 45427500 |  |  | Completed | 1 |  |  |  | 18OI0179 | November 22-Decembr 11, 2018 | November 29, 2018 | December 11, 2018 |  | 12/28/18 | ORANI BUILDERS SUPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Muntinlupa City | 136903 | Muntinlupa ES | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | Batch 3 | 34313000 |  |  | Completed | 1 |  |  |  | 18OI0183 | November 28-Decembr 17, 2018 | December 5, 2018 | December 17, 2018 |  | 12/28/18 | G. F. ROVERO MERCHANDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Muntinlupa City | 136904 | Putatan Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 16 | 2 UNITS 4STY8CL | Batch 3 | 37800000 |  |  | Completed | 1 |  |  |  | 18OI0184 | November 28-Decembr 17, 2018 | December 5, 2018 | December 17, 2018 |  | 12/28/18 | C. T. LEONCIO Const. & Trading/KP Gonzales Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | Batch 3 | 34492000 |  |  | Completed | 1 |  |  |  | 18OI0186 | November 28-Decembr 17, 2018 | December 5, 2018 | December 17, 2018 |  | 12/28/18 | ORANI BUILDERS SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Muntinlupa City | 136912 | Cupang ES | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | Batch 3 | 46166000 |  |  | Completed | 1 |  |  |  | 18OI0181 | November 22-Decembr 11, 2018 | November 29, 2018 | December 11, 2018 |  | 12/28/18 | REDCAR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 | 1 | 16 | 4STY16CL | Batch 3 | 40515000 |  |  | Completed | 1 |  |  |  | 18OI0185 | November 28-Decembr 17, 2018 | December 5, 2018 | December 17, 2018 |  | 12/28/18 | MRRM Trading & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Muntinlupa City | 305470 | PEDRO E. DIAZ HIGH SCHOOL | CITY OF MUNTINLUPA | 0 | 1 | 32 | 2 UNITS 4STY16CL | Batch 3 | 79620000 |  |  | Completed | 1 |  |  |  | 18OI0186 | November 28-Decembr 17, 2018 | December 5, 2018 | December 17, 2018 |  | 12/28/18 | C. T. LEONCIO Const. & Trading/KP Gonzales Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2018 | NCR | Navotas | 136857 | Bangkulasi Elementary School | CITY OF NAVOTAS | 0 | 1 | 16 | 4STY16CL | BATCH 1 | 55410000 |  |  | Completed | 1 | [9 empty] | Dungan Contractor's & Trading Corp./ Jojalie Const. (JV) | For Punchlisting and Final Inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Navotas | 136859 | Kapitbahayan Elementary School | CITY OF NAVOTAS | 0 | 1 | 24 | 4STY24CL | BATCH 1 | 82750000 |  |  | Completed | 1 | [9 empty] | MRBll Const. Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Navotas | 136860 | Navotas Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 41190000 |  |  | Completed | 1 | [9 empty] | Orientech Const. & Devt. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 41140000 |  |  | Completed | 1 | [9 empty] | C.T. Leoncio Const. & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Navotas | 305454 | San Rafael Technological High School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 41410000 |  |  | Completed | 1 | [9 empty] | St. Timothy Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE | 1 | 1 | 16 | 4STY16CL | Batch 3 | 35522115.63 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Paranaque City | 136762 | Don Galo ES | CITY OF PARAÑAQUE | 1 | 1 | 4 | 4STY4CL | Batch 3 | 6825497.26 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2018 | NCR | Paranaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22432790.46 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Paranaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 |  | 20 | 4STY20CL | Batch 3 | 51169448.43 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 28 | 4STY28CL | Batch 3 | 73737963.15 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0
NEWCON 2018 | NCR | Paranaque City | 320201 | Paranaque Science HS | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | Batch 3 | 24747640.87 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Paranaque City | 136755 | Masville ES | CITY OF PARAÑAQUE | 2 | 1 | 12 | 4STY12CL (9mX7m) or 4STY16CL (Modified 8mX7m) | Batch 3 | 30851669.06 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Paranaque City | 136761 | Col. E. De Leon Elementary School | CITY OF PARAÑAQUE | 2 | 1 | 8 | 4STY8CL (9mX7m) or 4STY12CL (Modified 8mX7m) | Batch 3 | 20617779.37 |  |  | Completed | 1 | [10 empty] | Suspended 1/10/2019, Still finding a new site that will serve as temporary learning shelter for the displaced students that will be affected since the entire builing will be demolished | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Paranaque City | 136761 | Col. E. De Leon Elementary School | CITY OF PARAÑAQUE | 2 |  | 24 | 4STY24CL (9mX7m) or 4STY36CL (Modified 8mX7m) | Batch 3 | 61553338.11 |  |  | Completed | 1 | [10 empty] | Suspended 1/10/2019, Still finding a new site that will serve as temporary learning shelter for the displaced students that will be affected since the entire builing will be demolished | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Pasay City | 136604 | Jose Rizal ES | PASAY CITY | 0 | 1 | 20 | 4STY20CL | Batch 3 | 59975000 |  | 54427594.9 | Completed | 1 | September 12, 2019 |  |  | 18OH0174 |  |  | November 06, 2018 | November 21, 2018 | December 10, 2018 | St. Timothy Const. Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Pasay City | 136604 | Jose Rizal ES | PASAY CITY | 0 |  | 24 | 4STY24CL | Batch 3 | 68891000 |  | 63466057.96 | Completed | 1 | October 12, 2019 |  |  | 18OH0173 |  |  | November 06, 2018 | November 21, 2018 | December 10, 2018 | Alpha & Omega Gen. Contractor & Dev't Corp. | Punchlist items still for acceptance. Ceiling is damaged by Typhoon Fabian, to be rectified by Contractor. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Pasig City | 136728 | San Joaquin ES | CITY OF PASIG | 0 | 1 | 20 | 4STY20CL | Batch 3 | 59295681.69 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Pasig City | 136732 | Pineda ES | CITY OF PASIG | 0 | 1 | 20 | 4STY20CL | Batch 3 | 56669465.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Pasig City | 136742 | Maybunga ES | CITY OF PASIG | 0 | 1 | 12 | 4STY12CL | Batch 3 | 41690415.08 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG | 0 | 1 | 24 | 4STY24CL | Batch 3 | 68269701.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | CITY OF PASIG | 0 | 1 | 8 | 4STY8CL | Batch 3 | 26218158.47 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Quezon City | 136565 | Teodora Alonzo Elementary School | QUEZON CITY | 3 | 1 | 8 | 4STY8CL | BATCH 1 | 18100000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Quezon City | 136490 | Balingasa Elementary School | QUEZON CITY | 1 | 1 | 20 | 4STY12CL & 4STY8CL | Batch 3 | 61450000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Quezon City | 136508 | Mines Elementary School | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 23945000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Quezon City | 305323 | San Jose HS | QUEZON CITY | 1 | 1 | 24 | 4STY24CL | Batch 3 | 62600000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Quezon City | 136549 | Payatas B Annex ES | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | Batch 3 | 23945000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Quezon City | 305332 | Bagong Silangan HS | QUEZON CITY | 2 | 1 | 16 | 4STY16CL | Batch 3 | 46860000 |  |  | Completed | 1 | [10 empty] | With Additional Funds intended for Connecting Bridge | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Quezon City | 319501 | Holy Spirit SHS | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | Batch 3 | 22610000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Quezon City | 305350 | Quirino HS | QUEZON CITY | 3 | 1 | 8 | 4STY8CL | Batch 3 | 30555000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Quezon City | 136573 | Pinyahan ES | QUEZON CITY | 4 | 1 | 16 | 4STY16CL | Batch 3 | 47500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Quezon City | 136579 | General Roxas Elementary School | QUEZON CITY | 4 | 1 | 8 | 4STY8CL | Batch 3 | 28195000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Quezon City | 136583 | Aurora A. Quezon ES | QUEZON CITY | 4 | 1 | 8 | 4STY8CL | Batch 3 | 28120000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY | 4 | 1 | 8 | 4STY8CL | Batch 3 | 28150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Quezon City | 305355 | Carlos L. Albert HS | QUEZON CITY | 4 | 1 | 20 | 4STY20CL | Batch 3 | 61650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Quezon City | 136531 | Damong Maliit ES | QUEZON CITY | 5 | 1 | 20 | 4STY20CL | Batch 3 | 54050000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Quezon City | 136536 | Nagkaisang Nayon ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | Batch 3 | 23010000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Quezon City |  | ATTY. ALFRED VARGAS SR. HS | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | Batch 3 | 23945000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Quezon City |  | G.B. FRANCISCO | QUEZON CITY | 5 | 1 | 20 | 4STY20CL | Batch 3 | 54570000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6 | 1 | 20 | 4STY20CL | Batch 3 | 54050000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2018 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | Batch 5 | 22810000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Quezon City | 136505 | San Antonio ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | Batch 5 | 39510000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Quezon City | 305328 | Pugad Lawin HS | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | Batch 5 | 23410000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Taguig | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 27075203.01 |  | 25,932,552,52 | Completed | 1 | August 29, 2020 | December 15, 2020 | P00273636LZ_CW1 | 018OB0464 | October 29, 2018 | November 7, 2018 | November 16, 2018 | November 27, 2018 | December 12, 2018 | Hyper J Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Taguig | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS | 1 | 1 | 8 | 4STY8CL | Batch 3 | 25907137.3 |  | 24822894.92 | Completed | 1 | February 13, 2020 | December 15, 2020 | P00273637LZ_CW1 | 018OB0466 | October 25, 2018 | November 5, 2018 | November 16, 2018 | November 27, 2018 | December 12, 2018 | Hyper J Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Taguig | 136897 | Sta. Ana Elementary School | PATEROS | 1 | 1 | 8 | 4STY8CL | Batch 3 | 37565830.5 |  | 36066487.7 | Completed | 1 | April 27, 2021 |  | P00273638LZ_CW1 | 018OB0462 | October 25, 2018 | November 5, 2018 | November 16, 2018 | November 27, 2018 | December 12, 2018 | Hony Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Taguig | 136898 | Sto. Rosario Elementary School | PATEROS | 1 | 1 | 8 | 4STY8CL | Batch 3 | 33116745.66 |  | 31758084.98 | Completed | 1 | February 7, 2020 | March 13, 2020 | P00273639LZ_CW1 | 018OB0463 | October 25, 2018 | November 5, 2018 | November 16, 2018 | November 27, 2018 | December 12, 2018 | Dahl Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Taguig | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2 | 1 | 24 | 4STY24CL | Batch 3 | 62326754.78 |  | 60009167.37 | Completed | 1 | September 27, 2019 | January 2, 2020 | P00273640LZ_CW1 | 018OB0456 | October 25, 2018 | November 5, 2018 | November 16, 2018 | November 27, 2018 | December 12, 2018 | MRBII Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2018 | NCR | Taguig | 136887 | Upper Bicutan ES | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL | Batch 3 | 39012528.26 |  | 37461040.68 | Completed | 1 | January 31, 2020 | March 13, 2020 | P00273641LZ_CW1 | 018OB0461 | October 25, 2018 | November 5, 2018 | November 16, 2018 | November 27, 2018 | December 12, 2018 | MRBII Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Valenzuela City | 136794 | Dalandanan Elementary School | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 39400000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Valenzuela City | 136806 | Pasolo Elementary School | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | Batch 3 | 55800000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Valenzuela City |  | Disiplina Village ES | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 39050000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Valenzuela City |  | Disiplina Village NHS | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 39050000 |  | 37836609.18 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Valenzuela City |  | Disiplina Village NHS | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | Batch 3 | 21150000 |  | 21043537.2 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Valenzuela City |  | Malanday NHS | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 46600000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2018 | NCR | Valenzuela City |  | Malanday NHS | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | Batch 3 | 55400000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Valenzuela City | 136796 | Sitio Sto. Rosario ES (Malabo ES) | CITY OF VALENZUELA | 2 | 1 | 16 | 4STY16CL | Batch 3 | 47150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2018 | NCR | Valenzuela City | 136823 | Constantino ES | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 21470000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2018 | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 21100000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2017 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 | 1 | 12 | 4STY12CL | BATCH 4 | 32371949.57 |  |  | Completed | 1 |  |  | P00172458LZ-CW1 | 0170B0387 | 2017-09-26 | 2017-10-06 | 2017-10-10 | 2017-11-02 | November 14,2017 | GR FEVEDAL CONSTRUCTION DEVELOPERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 | 1 | 16 | 4STY16CL | BATCH 4 | 37165805.23 |  |  | Completed | 1 |  |  | P00172459LZ-CW1 | 0170B0385 | 2017-09-26 | 2017-10-06 | 2017-10-17 | 2017-11-02 | November 14,2017 | BELL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 | 1 | 12 | 4STY12CL | BATCH 4 | 37767415.24 |  |  | Completed | 1 |  |  | P00172460LZ-CW1 | 0170B0383 | 2017-09-26 | 2017-10-06 | 2017-10-17 | 2017-11-02 | November 14,2017 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Marikina City | 136687 | Sto. Nino ES | CITY OF MARIKINA | 1 | 1 | 12 | 4STY12CL | BATCH 4 | 35423184.21 |  |  | Completed | 1 |  |  | P00172457LZ-CW1 | 0170B0386 | 2017-09-26 | 2017-10-06 | 2017-10-10 | 2017-11-02 | Novenber 14,2018 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Pasig City | 136729 | Bagong Ilog ES | CITY OF PASIG | 0 | 1 | 20 | 4STY20CL | BATCH 4 | 42574742.6 |  |  | Completed | 1 |  |  | P0072462 LZ_CW1 | 0170B0384 | 2017-09-26 | 2017-10-06 | 2017-10-17 | 2017-11-02 | 2017-11-20 | Henscita Phils., Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Pasig City | 136725 | Buting ES | CITY OF PASIG | 0 | 1 | 9 | 4STY9CL | BATCH 4 | 32371949.57 |  |  | Completed | 1 |  |  | P0072461 LZ_CW1 | 0170B0388 | 2017-09-26 | 2017-10-06 | 2017-10-17 | 2017-11-02 | 2017-11-20 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0
NEWCON 2017 | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | CITY OF PASIG | 0 | 1 | 16 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 72278943.25 |  |  | Completed | 1 |  |  | P0072463 LZ_CW1 | 0170B0421 | 2017-10-30 | 2017-11-10 | 2017-11-21 | 2017-12-01 | 2017-12-19 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG | 0 | 1 | 28 | 4STY28CL | BATCH 4 | 62945715.06 |  |  | Completed | 1 |  |  | P0072464 LZ_CW1 | 0170B0422 | 2017-10-30 | 2017-11-10 | 2017-12-12 | 2017-12-14 | 2017-12-28 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1 | 0
NEWCON 2017 | NCR | Malabon City | 136835 | Longos ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 20705296.99 |  | 19961055.45 | Completed | 1 | [8 empty] | 2017-12-13 | ISH Const. Inc |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Malabon City | 136855 | Maysilo ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 23053022.14 |  | 22249624.04 | Completed | 1 | [8 empty] | 2017-12-13 | T.M. Abad Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Malabon City | 136846 | Santiago Syjuco Memorial School | CITY OF MALABON | 0 | 1 | 20 | 4STY20CL | BATCH 7 | 60000000 |  | 57848516.92 | Completed | 1 | [8 empty] | 2018-01-10 | St. Timothy Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Malabon City | 305452 | Tinajeros NHS | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 19744516.77 |  | 19032845.4 | Completed | 1 | [8 empty] | 2017-12-13 | JTC Cruz Const. co. inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Malabon City | 136839 | Tonsuya Elementary School | CITY OF MALABON | 0 | 1 | 15 | 3STY15CL | BATCH 7 | 46106889.97 |  | 45478773.82 | Completed | 1 | [8 empty] | 2017-12-13 | Edison Devt. Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 1 | 0
NEWCON 2017 | NCR | Marikina City |  | Industrial Valley NHS | CITY OF MARIKINA | 1 | 1 | 36 | 4STY36CL | BATCH 7 | 109453944.7 |  |  | Completed | 1 |  |  | P00174788LZ-CW1 | 0170B0459 | 2017-12-06 | 2017-12-13 | 2017-10-22 | 2018-01-03 | January 04,2018 | EDISON DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 1 | 0
NEWCON 2017 | NCR | Navotas | 136856 | Bagumbayan Elementary School | CITY OF NAVOTAS | 0 | 1 | 3 | 3STY3CL | BATCH 7 | 10417126.08 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0
NEWCON 2017 | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 27636000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Navotas | 136861 | Navotas I Elementary School | CITY OF NAVOTAS | 0 | 1 | 15 | 4STY16CL | BATCH 7 | 55558005.76 |  |  | Completed | 1 | [10 empty] | - Termination of Original Contract (17OA0097) - New Contract for Project Completion (17OA0106) - New Contract for Project Completion (17OA0106) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0.85 | 0.15
NEWCON 2017 | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 7 | 42036997.81 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0.95 | 0.05
NEWCON 2017 | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 27636000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Navotas | 305455 | Tanza National High School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 7 | 42036997.81 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 28 | 4STY28CL | BATCH 7 | 68651344.94 |  |  | Terminated | 0 |  |  |  | 17OC0088 |  |  |  |  | 2017-12-27 | SPRING STAR Const. & Supply | Terminated; Suspended as of December 27, 2017 due to pending demolition of existing building since it is still being utilized by the students. The newly built 2 Units 12 CL is not sufficient to cater the number of students using the old building; Awaiting for the completion of the ongoing construction of 2 Units 28CL. (For Termination) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0
NEWCON 2017 | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 18812000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136512 | GSIS VILLAGE ELEMENTARY | QUEZON CITY | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 34234000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY | 5 | 1 | 12 | 4STY12CL | BATCH 7 | 34175000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6 | 1 | 16 | 4STY16CL | BATCH 7 | 39783000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136509 | Project 6 ES | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 7 | 45561000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City |  | Sta. Lucia ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | BATCH 7 | 18921000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 305389 | Caloocan City City Science HS | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 45700000 |  |  | Completed | 1 |  |  | P00178672LZ | 17OD0170 |  |  | 2017-12-19 |  |  | Accelerated Metal Technology and Const. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136632 | Amparo ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178650LZ | 17OD0146 |  |  | 2017-11-28 |  |  | Aylan Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136632 | Amparo ES | Caloocan City | 1 |  | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178651LZ | 17OD0130 |  |  | 2017-11-23 |  |  | Aylan Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136625 | Baesa ES | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178649LZ | 17OD0131 |  |  | 2017-11-23 |  |  | Accelerated Metal Technology and Const. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136650 | Bagbaguin ES | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178656LZ | 17OD0159 |  |  | 2017-12-19 |  |  | C.B. Tampengco Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 305383 | Bagong Barrio NHS | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178669LZ | 17OD0179 |  |  | 2017-12-12 |  |  | C.T. Leoncio Const. & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 305383 | Bagong Barrio NHS | Caloocan City | 1 |  | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178670LZ | 17OD0180 |  |  | 2017-12-12 |  |  | C.T. Leoncio Const. & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136639 | Bagong Silang ES | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178653LZ | 17OD0147 |  |  | 2017-11-28 |  |  | E.A. Ramirez Const. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 305381 | Bagong Silang HS | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 33600000 |  |  | Completed | 1 |  |  | P00178667LZ | 17OD0157 |  |  | 2017-11-29 |  |  | Alpha & Omega Gen. Contractor & Dev't. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 305381 | Bagong Silang HS | Caloocan City | 1 |  | 12 | 4STY12CL | BATCH 10 | 33600000 |  |  | Completed | 1 |  |  | P00178667LZ | 17OD0157 |  |  | 2017-11-29 |  |  | Alpha & Omega Gen. Contractor & Dev't. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136651 | Bagumbong ES | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178657LZ | 17OD0132 |  |  | 2017-11-23 |  |  | T.M. Abad Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136617 | Caloocan Central Elementary School | Caloocan City | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178675LZ | 17OD0148 |  |  | 2017-11-28 |  |  | C.B. Tampengco Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136634 | Camarin Elementary School | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178652LZ | 17OD0181 |  |  | 2017-12-12 |  |  | Aylan Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 305374 | Camarin High School | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178663LZ | 17OD0133 |  |  | 2017-11-23 |  |  | T.M. Abad Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136652 | Caybiga ES | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178658LZ | 17OD0160 |  |  | 2017-12-19 |  |  | First R + J Builders Phils. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 305385 | Caybiga HS | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178671LZ | 17OD0134 |  |  | 2017-11-23 |  |  | Accelerated Metal Technology and Const. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136620 | Cecilio Apostol ES | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178648LZ | 17OD0135 |  |  | 2017-11-23 |  |  | Larsen-Dutcher Constractor |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 305375 | Ceilito Zamora SHS | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178664LZ | 17OD0136 |  |  | 2017-11-23 |  |  | Jagonbuild Construction Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136653 | Deparo ES | Caloocan City | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178659LZ | 17OD0161 |  |  | 2017-12-19 |  |  | First R + J Builders Phils. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136641 | Kalayaan ES | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178654LZ | 17OD0162 |  |  | 2017-12-01 |  |  | Steven Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136654 | Llano ES | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178660LZ | 17OD0151 |  |  | 2017-11-29 |  |  | C.B. Tampengco Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 305379 | Manuel L. Quezon HS | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178665LZ | 17OD0137 |  |  | 2017-11-23 |  |  | RCDG Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136655 | Sampaguita Elem. School | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178661LZ | 17OD0156 |  |  | 2017-11-29 |  |  | Accelerated Metal Technology and Const. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136642 | Silanganan ES (Star ES) | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178655LZ | 17OD0152 |  |  | 2017-12-13 |  |  | Aylan Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 305380 | Tala High School | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00171688LZ | 17OD0126 |  |  | 2017-10-24 |  |  | Aylan Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 305371 | Talipapa HS | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178662LZ | 17OD0153 |  |  | 2017-12-19 |  |  | First R + J Builders Phils. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136622 | Eulogio Rodriguez Elementary School | KALOOKAN CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178676LZ | 17OD0149 |  |  | 2017-11-29 |  |  | Alcel Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136608 | Kasarinlan ES | KALOOKAN CITY | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 49265000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136609 | Kaunlaran ES | KALOOKAN CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 41930000 |  |  | Completed | 1 |  |  | P00178674LZ | 17OD0177 |  |  | 2017-12-07 |  |  | Accelerated Metal Technology and Const. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Malabon City | 136840 | Amang Rodriguez ES | CITY OF MALABON | 0 | 1 | 6 | 3STY6CL | BATCH 10 | 20834252.16 |  | 20730027.02 | Completed | 1 | [8 empty] | 2018-01-10 | Square Meter Trading & Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | 0
NEWCON 2017 | NCR | Malabon City | 136853 | Catmon IS | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | BATCH 10 | 27000000 |  | 25520958.51 | Completed | 1 | [8 empty] | 2018-01-10 | ISH Const. Inc |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0
NEWCON 2017 | NCR | Malabon City | 136849 | Potrero ES I | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 10 | 31649789.72 |  | 31455124.21 | Completed | 1 | [8 empty] | 2017-12-21 | Square Meter Trading & Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Malabon City | 136846 | Santiago Syjuco Memorial School | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 10 | 36000000 |  | 35469792.21 | Completed | 1 | [8 empty] | 2017-12-21 | Steven Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1 | 1 | 24 | 4STY24CL | BATCH 10 | 64141000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136471 | Bacood Elementary School | SAMPALOC | 6 | 1 | 16 | 4STY16CL | BATCH 10 | 45350000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136480 | Bagong Barangay Elementary School | PANDACAN | 6 | 1 | 16 | 4STY16CL | BATCH 13 | 40760000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136482 | Bagong Diwa Elementary School | PANDACAN | 6 | 1 | 24 | 4STY24CL | BATCH 13 | 59785600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 305299 | Dona Teodora Alonzo HS | SANTA CRUZ | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 47600000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 305317 | Elpidio Quirino High School | SANTA ANA | 6 | 1 | 12 | 4STY12CL | BATCH 10 | 53105000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136433 | Emilio Jacinto Elementary School | TONDO | 1 | 1 | 10 | 2STY10CL | BATCH 10 | 25185000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136433 | Emilio Jacinto Elementary School | TONDO | 1 |  | 6 | 2STY6CL | BATCH 10 | 17127000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 305302 | Jose Abad Santos High School | SANTA CRUZ | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 78400000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136449 | Juan Sumulong Elementary School | SANTA CRUZ | 3 | 1 | 24 | 4STY24CL | BATCH 10 | 84650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136461 | Legarda Elementary School | SAMPALOC | 4 | 1 | 16 | 4STY16CL | BATCH 10 | 46570000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136438 | Magat Salamat Elementary School | TONDO | 1 | 1 | 32 | 4STY32CL | BATCH 10 | 98747000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 305312 | Manila Science High School | ERMITA | 5 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 305318 | Manuel A. Roxas High School | PACO | 5 | 1 | 16 | 4STY16CL | BATCH 12 | 40760000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 305316 | Mariano Marcos Memorial High School | SANTA ANA | 6 | 1 | 8 | 4STY8CL | BATCH 12 | 19025000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 305316 | Mariano Marcos Memorial High School | SANTA ANA | 6 | 1 | 16 | 4STY16CL | BATCH 13 | 40760000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136467 | P. Burgos ES | TONDO | 4 | 1 | 24 | 4STY24CL | BATCH 10 | 60956000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1 | 0
NEWCON 2017 | NCR | Marikina City | 136679 | Concepcion Integrated School | CITY OF MARIKINA | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 33137151.39 |  |  | Completed | 1 |  |  | P00178703LZ-CW1 | 0170B0432 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | December 22,2017 | VINNELL_BELVOIR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Marikina City | 136673 | Kalumpang ES | CITY OF MARIKINA | 1 | 1 | 28 | 4STY28CL | BATCH 10 | 63685374.28 |  |  | Completed | 1 |  |  | P00178698LZ-CW1 | 0170B0454 | 2017-12-02 | 2017-12-08 | 2017-12-22 | 2018-01-03 | January 04,2018 | ST. TIMOTHY CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1 | 0
NEWCON 2017 | NCR | Marikina City | 136674 | L. Victorino ES | CITY OF MARIKINA | 1 | 1 | 24 | 4STY24CL | BATCH 10 | 57582992.4 |  |  | Completed | 1 |  |  | P00178699LZ-CW1 | 0170B0462 | 2017-12-06 | 2017-12-13 | 2017-12-26 | 2018-01-03 | 2018-01-04 | ST. TIMOTHY CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1 | 0
NEWCON 2017 | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 32244946.68 |  |  | Completed | 1 |  |  | P00178700LZ-CW1 | 0170B0433 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | December 28,2017 | GR FEVIDAL CONSTRUCTION DEVELOPERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 44030854.92 |  |  | Completed | 1 |  |  | P00178702LZ-CW1 | 0170B0428 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | December 22,2017 | GR FEVIDAL CONSTRUCTION DEVELOPERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 37845984.62 |  |  | Completed | 1 |  |  | P00178704LZ-CW1 | 0170B0431 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | December 22,2017 | VINNEL-BELVOIR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 |  | 8 | 4STY8CL | BATCH 10 | 18094817.33 |  |  | Completed | 1 |  |  | P00178705LZ-CW1 | 0170B0436 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | December 22,2017 | VINNELL_BELVOIR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Marikina City | 136678 | San Roque ES | CITY OF MARIKINA | 1 | 1 | 28 | 4STY28CL | BATCH 10 | 63865374.28 |  |  | Completed | 1 |  |  | P00178701LZ-CW1 | 0170B0455 | 2017-12-02 | 2017-12-08 | 2017-12-22 | 2018-01-03 | 2018-01-04 | GR FEVIDAL CONSTRUCTION DEVELOPERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1 | 0
NEWCON 2017 | NCR | Paranaque City | 136753 | Fourth Estate ES | CITY OF PARAÑAQUE | 2 | 1 | 48 | 4STY48CL | BATCH 10 | 117688019.9 |  |  | Completed | 1 |  |  | P00178706LZ | 17OC0121 | 2017-11-28 |  | 2017-11-28 | 2017-12-12 | 2017-12-27 | New Big Four J Construction, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 1 | 0
NEWCON 2017 | NCR | Pasay City | 136590 | Apelo Cruz ES | PASAY CITY | 0 | 1 | 20 | 4STY20CL | BATCH 10 | 45700000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Pasay City | 136590 | Apelo Cruz ES | PASAY CITY | 0 |  | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Pasay City | 319601 | Kalayaan NHS | PASAY CITY | 0 | 1 | 9 | 4STY9CL | BATCH 10 | 21403800 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 1 | 0
NEWCON 2017 | NCR | Pasay City | 305367 | Pasay City East HS | PASAY CITY | 0 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Pasay City | 305370 | Pasay City South HIgh School | PASAY CITY | 0 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Pasay City | 305370 | Pasay City South HIgh School | PASAY CITY | 0 |  | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Pasay City | 500328 | Philippine National School for the Blind | PASAY CITY | 0 | 1 | 6 | 2STY6CL | BATCH 10 | 9525000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | 0
NEWCON 2017 | NCR | Pasay City | 500329 | Philippine School for the Deaf | PASAY CITY | 0 | 1 | 20 | 4STY20CL | BATCH 10 | 45700000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136567 | Aguinaldo ES | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 40139000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136507 | Bagong Pag-Asa ES | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 46046000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136507 | Bagong Pag-Asa ES | QUEZON CITY | 1 |  | 12 | 4STY12CL | BATCH 10 | 35238000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136552 | Bagumbayan ES | QUEZON CITY | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 34586000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136553 | Balara ES | QUEZON CITY | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 34600000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 305331 | Commonwealth HS | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 35741000 |  |  | Completed | 1 | [10 empty] | REDESIGNING OF THE PLAN & SPECS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0.95 | 0.05
NEWCON 2017 | NCR | Quezon City | 305360 | Don Alejandro Roces, Sr. Sci. & Tech. HS | QUEZON CITY | 4 | 1 | 27 | 4STY TVL | BATCH 10 | 95436000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136542 | Dona Juana ES | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 35741000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136546 | Manuel L. Quezon ES | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 35741000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136549 | Payatas B Annex ES | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 20495000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136563 | Project 3 ES | QUEZON CITY | 3 | 1 | 8 | 4STY8CL | BATCH 10 | 17628000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 305329 | Quezon City Science HS | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 47045000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 305329 | Quezon City Science HS | QUEZON CITY | 1 |  | 8 | 4STY8CL | BATCH 10 | 18980000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136492 | Ramon Magsaysay ES | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 45936000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 305327 | San Francisco HS | QUEZON CITY | 1 | 1 | 32 | 4STY32CL | BATCH 10 | 80870000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0.95 | 0.05
NEWCON 2017 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 49052000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136510 | Sto. Cristo ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34144000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136506 | Toro Hills ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19984000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig | 305467 | Maria Concepcion Cruz HS | PATEROS | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 20667628.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig | 136896 | Pateros Elementary School | PATEROS | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 49027051.57 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig | 136895 | Paulina Manalo ES | PATEROS | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 41546562.56 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 7 | 4STY7CL | BATCH 10 | 17159570.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig | 136883 | Cipriano P. Sta. Teresa Elementary School | TAGUIG CITY | 1 | 1 | 24 | 4STY24CL | BATCH 10 | 57497969.97 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig | 136871 | Ciriaco P. Tiñga Elementary School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 32244946.68 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig | 136886 | Kapitan Jose Cardones Memorial ES | TAGUIG CITY | 2 | 1 | 24 | 4STY24CL | BATCH 10 | 55961256.52 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig | 500342 | Napindan Integrated School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 23410308.71 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 21279843.93 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig | 136877 | Tipas Elementary School -Main | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34509193.16 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig | 320605 | Upper Bicutan National High School | TAGUIG CITY | 2 | 1 | 6 | 4STY6CL | BATCH 10 | 10756889.78 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig | 136879 | Ususan Elementary School | TAGUIG CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 55693407.06 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 45550000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136820 | Bitik ES | CITY OF VALENZUELA | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 305437 | Dalandanan NHS | CITY OF VALENZUELA | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 55760000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136815 | Lawang Bato Elementary School | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34820000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136797 | Malinta Elementary School | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 18875600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 33600000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 |  | 12 | 4STY12CL | BATCH 10 | 33600000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136798 | Maysan ES | CITY OF VALENZUELA | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 45700000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136798 | Maysan ES | CITY OF VALENZUELA | 2 |  | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136806 | Pasolo ES | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 41930000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136806 | Pasolo ES | CITY OF VALENZUELA | 1 |  | 8 | 4STY8CL | BATCH 10 | 23670000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 305436 | Polo NHS | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 49265000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136819 | Silvestre Lazaro Elementary School | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 18875600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136811 | WawangPulo ES | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 23520000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136615 | Andres Bonifacio ES | CALOOCAN CITY | 2 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 |  |  | P00181221LZ | 17OD0145 |  |  | 2017-11-28 |  |  | St. Timothy Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136615 | Andres Bonifacio ES | CALOOCAN CITY | 2 |  | 8 | 4STY8CL | BATCH 12 | 19025600 |  |  | Completed | 1 |  |  | P00181222LZ | 17OD0142 |  |  | 2017-11-28 |  |  | St. Timothy Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136637 | Horacio dela Costa ES | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 |  |  | P00181224LZ | 17OD0150 |  |  | 2017-11-29 |  |  | Accelerated Metal Technology and Const. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136646 | NHC ES | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 |  |  | P00181225LZ | 17OD0154 |  |  | 2017-11-29 |  |  | Orani Builders Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136646 | NHC ES | CALOOCAN CITY | 1 |  | 8 | 4STY8CL | BATCH 12 | 19025600 |  |  | Completed | 1 |  |  | P00181226LZ | 17OD0143 |  |  | 2017-11-28 |  |  | Orani Builders Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 305373 | Sampaguita HS | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 12 | 19025600 |  |  | Completed | 1 |  |  | P00181227LZ | 17OD0144 |  |  | 2017-11-28 |  |  | Accelerated Metal Technology and Const. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Caloocan City | 136623 | San Jose ES | CALOOCAN CITY | 2 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 |  |  | P00181223LZ | 17OD0155 |  |  | 2017-11-29 |  |  | Alcel Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Las Piñas City | 136775 | Gatchalian ES | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 16355000 |  |  | Completed | 1 |  |  | P00181228 | 17OI0099 | 2017-09-06 | 2017-09-14 | 2017-09-26 | 2017-11-09 | 2017-12-05 | GF ROVERO MERCHANDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Las Piñas City | 305434 | Las Pinas East National High School | CITY OF LAS PIÑAS | 0 | 1 | 20 | 4STY20CL | BATCH 12 | 41780000 |  |  | Completed | 1 |  |  | P00181232 | 17OI0126 | 2017-11-02 | 2017-11-10 | 2017-11-23 | 2017-11-29 | 2017-12-15 | LMG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Las Piñas City | 136777 | Las Pinas ES Central | CITY OF LAS PIÑAS | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 31800000 |  |  | Completed | 1 |  |  | P00181229 | 17OI0124 | 2017-11-02 | 2017-11-10 | 2017-11-23 | 2017-11-29 | 2017-12-15 | LMG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Las Piñas City | 136788 | Pamplona ES I | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17455000 |  |  | Completed | 1 |  |  | P00181230 | 17OI0116 | 2017-10-16 | 2017-10-26 | 2017-11-07 | 2017-04-24 | 2017-09-06 | FRAMECON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Las Piñas City | 136789 | Pilar Village ES | CITY OF LAS PIÑAS | 0 | 1 | 16 | 4STY16CL | BATCH 12 | 37200000 |  |  | Completed | 1 |  |  | P00181232 | 17OI0125 | 2017-11-02 | 2017-11-10 | 2017-11-23 | 2017-11-29 | 2017-12-15 | DAVHEZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Mandaluyong City | 500051 | Andres Bonifacio Integrated School | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 32000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | 24 | 4STY24CL | BATCH 12 | 54000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 1 | 0
NEWCON 2017 | NCR | Mandaluyong City |  | Sen. Neptali Gonzales Integrated School | Mandaluyong City | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 32000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136452 | P. Gomez ES | SANTA CRUZ | 3 | 1 | 20 | 4STY20CL | BATCH 10 | 60895000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136452 | P. Gomez ES | SANTA CRUZ | 3 |  | 16 | 4STY16CL | BATCH 10 | 54256000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136472 | Pio del Pilar Elementary School | SAMPALOC | 6 | 1 | 20 | 4STY20CL | BATCH 10 | 58070000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0.95 | 0.05
NEWCON 2017 | NCR | Manila | 136485 | Sta. Ana ES | SANTA ANA | 6 | 1 | 16 | 4STY16CL | BATCH 12 | 40760000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | BATCH 12 | 47990000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 |  | 20 | 4STY20CL | BATCH 12 | 43840000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 31904360.14 |  |  | Completed | 1 |  |  | 17O10120 | 17O10120 | Oct. 16-23, 2017 | Oct. 26, 2017 | Nov. 7, 2017 | Nov. 21,2017 | 2017-12-05 | Redcar Trading & Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Muntinlupa City | 305469 | Muntinlupa Science High School | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 31904360.14 |  |  | Completed | 1 |  |  | 17O10121 | 17O10121 | Oct. 16-23, 2017 | Oct. 26, 2017 | Nov. 7, 2017 | Nov. 21,2017 | 2017-12-05 | Redcar Trading & Const/RDGD Const. (JV) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Muntinlupa City | 136904 | Putatan Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17429616.04 |  |  | Completed | 1 |  |  | 17O10117 | 17O10117 | Oct. 16-23, 2017 | Oct. 26, 2017 | Nov. 7, 2017 | Nov. 21,2017 | 2017-12-05 | Framecon Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Muntinlupa City | 136914 | Sucat Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17429616.04 |  |  | Completed | 1 |  |  | 17O10119 | 17O10119 | Oct. 16-23, 2017 | Oct. 26, 2017 | Nov. 7, 2017 | Nov. 21,2017 | 2017-12-05 | Vicvera Bldrs Inc |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Muntinlupa City | 136907 | Victoria Homes ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17429616.04 |  |  | Completed | 1 |  |  | 17O10118 | 17O10118 | Oct. 16-23, 2017 | Oct. 26, 2017 | Nov. 7, 2017 | Nov. 21,2017 | 2017-12-05 | RV Rieta Trading & Gen. Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City |  | Harmony Hills NHS | QUEZON CITY | 2 | 1 | 32 | 4STY32CL | BATCH 12 | 79376000 |  |  | Terminated | 0 | [10 empty] | For Terminations with ISF's; WAITING FOR THE RESPONSE OF DPWH RE: COPY OF PERTINENT DOCUMENTS | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0
NEWCON 2017 | NCR | Valenzuela City |  | Lingunan HS | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | BATCH 12 | 40760000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | City of San Juan | 136745 | Salapan ES | CITY OF SAN JUAN | 0 | 1 | 7 | 4STY7CL | BATCH 13 | 21350000 |  |  | Completed | 1 |  |  | 017OB0450 | P00182445LZ_CW1 | NOV. 28,2017 | DEC.8,2017 | DEC.19,2017 | DEC.22,2017 | JANUARY 4,2018 | B.BERNARDO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 1 | 0
NEWCON 2017 | NCR | City of San Juan | 136746 | San Juan ES | City of San Juan | 0 | 1 | 28 | 4STY28CL | BATCH 13 | 63798000 |  |  | Completed | 1 |  |  | 017OB0460 | P00182446LZ_CW1 | DEC.5,2017 | DEC.26,2107 | DEC.26,2017 | JAN. 3,2018 | JANUARY 4,2018 | ST. TIMOTHY CONSTRUCTION CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1 | 0
NEWCON 2017 | NCR | City of San Juan | 305423 | San Juan National High School | CITY OF SAN JUAN | 0 | 1 | 28 | 4STY28CL | BATCH 13 | 61000000 |  |  | Completed | 1 |  |  | 017OB0461 | P00182448LZ_CW1 | DEC.5,2017 | DEC.26,2107 | DEC.26,2017 | JAN. 3,2018 | JANUARY 4,2018 | GR FEVIDAL CONST. AND DEV. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 1 | 0
NEWCON 2017 | NCR | City of San Juan | 136747 | San Perfecto ES | CITY OF SAN JUAN | 0 | 1 | 36 | 4STY36CL | BATCH 13 | 70000000 |  |  | Completed | 1 |  |  | 017OB0445 | P00182447LZ_CW1 | NOV.28,2017 | DEC.19,2017 | DEC.19,2017 | DEC.22,2017 | JANUARY 4,2018 | HENSCHA PHIL.INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 305289 | T. Paez Integrated School | TONDO | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 39143000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136431 | T. Paez Integrated School (Elem.) | TONDO | 1 | 1 | 32 | 4STY32CL | BATCH 10 | 98072000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 1 | 0
NEWCON 2017 | NCR | Manila | 136466 | V. E. Fugoso Memorial School | SAMPALOC | 4 | 1 | 12 | 4STY12CL | BATCH 10 | 31808000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Taguig |  | Gat Andres Bonifacio HS | TAGUIG CITY | 2 | 1 | 20 | 4STY20CL | BATCH 13 | 41440293.15 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1 | 0
NEWCON 2017 | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 14 | 41668504.32 |  | 41460161.8 | Completed | 1 | [8 empty] | 2018-01-10 | Alpha & Omega Gen. Contractor & Dev't. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Malabon City | 305451 | Tugatog NHS | CITY OF MALABON | 0 | 1 | 16 | 4STY16CL | BATCH 14 | 55558005.76 |  | 53360915.48 | Completed | 1 | [8 empty] | 2018-01-10 | Hexamindz Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Navotas | 305457 | Tangos National High School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 14 | 42036997.81 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0.95 | 0.05
NEWCON 2017 | NCR | Quezon City | 136500 | Bungad ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 34535000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 305320 | Balingasa HS | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 34234000 |  |  | Completed | 1 | [10 empty] | Completed as per DPWH; WAITING FOR THE PUMP TO BE INSTALLED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0.95 | 0.05
NEWCON 2017 | NCR | Quezon City | NOT IN BEIS | Bagong Silangan Annex HS | QUEZON CITY | 2 | 1 | 20 | 4STY20CL | BATCH 14 | 46046000 |  |  | Completed | 1 | [10 empty] | NO MOVEMENT, based on dpwh completed as per program | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0.65 | 0.35
NEWCON 2017 | NCR | Quezon City | 136571 | Cruz na Ligas ES | QUEZON CITY | 4 | 1 | 12 | 4STY12CL | BATCH 14 | 35000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY | 4 | 1 | 12 | 4STY12CL | BATCH 14 | 35000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 305359 | Quezon City High School | QUEZON CITY | 4 | 1 | 3 | 3STY3CL | BATCH 14 | 10000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 305361 | Manuel A. Roxas HS | QUEZON CITY | 4 | 1 | 12 | 4STY12CL | BATCH 14 | 35000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5 | 1 | 12 | 4STY12CL | BATCH 14 | 35238000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136537 | North Fairview ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | BATCH 14 | 19984000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Quezon City | 136538 | San Agustin ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | BATCH 14 | 19984000 |  |  | Completed | 1 | [10 empty] | Completed as per DPWH; With Approved Buffer Funds 2018; NO MOVEMENT AT ALL, WAITING FOR THE RESPONSE OF DPWH RE: COPY OF PERTINENT DOCUMENTS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0.6 | 0.4
NEWCON 2017 | NCR | Quezon City | 136513 | New Era ES | QUEZON CITY | 6 | 1 | 16 | 4STY16CL | BATCH 14 | 40633000 |  |  | Completed | 1 | [10 empty] | COMPLETED AS PER DPWH; NO MOVEMENT AT ALL, WAITING FOR THE RESPONSE OF DPWH RE: COPY OF PERTINENT DOCUMENTS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0.62 | 0.38
NEWCON 2017 | NCR | Valenzuela City | 136818 | Punturin ES | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 34970000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 305439 | Canumay West NHS | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | BATCH 14 | 40760000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136817 | Paso de Blas ES | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19025600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136822 | Caruhatan West ES | CITY OF VALENZUELA | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 34970000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 136823 | Constantino ES | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19025600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 305443 | Gen. T. de Leon NHS | CITY OF VALENZUELA | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 38130000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | 305446 | Sitero Francisco Mem. NHS | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19025600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2017 | NCR | Valenzuela City | NOT IN BEIS | Bagbaguin NHS | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19025600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 1 | 0
NEWCON 2016 | NCR | Caloocan City | 305376 | Amparo High School | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22153000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Caloocan City | 305376 | Amparo High School | Caloocan City | 1 |  | 2 | 1STY2CL | BATCH 13 CL | 2132466.644 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | NCR | Caloocan City | 136639 | Bagong Silang Es | Caloocan City | 1 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10567131.51 |  |  | Completed | 1 |  |  | P00074635LZ | 16OD0069 |  |  | 2016-09-06 |  |  | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | NCR | Caloocan City | 136639 | Bagong Silang Es | Caloocan City | 1 | 1 | 2 | Completion of 4STY8CL | BATCH 11 CL | 2000000 |  |  | Completed | 1 |  |  | P00074644LZ P00171687LZ | 17OD0121 |  |  | 2017-07-20 |  |  | Aylan Const. & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | NCR | Caloocan City | 319707 | Caloocan City Business High School | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 |  |  | P00074645LZ | 16OD0072 |  |  | 2016-09-13 |  |  | Prismodial Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Caloocan City | 340539 | Caloocan North Shs | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074639LZ P00181048LZ | 16OD0117 |  |  | 2017-09-04 |  |  | C.B. Tampengco Const. and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Caloocan City | 305374 | Camarin Hs | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074642LZ | 16OD0073 |  |  | 2016-09-15 |  |  | Victoria Dev't. & Const. Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Caloocan City | 305374 | Camarin Hs | Caloocan City | 1 |  | 16 | 4STY8CL | BATCH 11 CL | 29795037.68 |  |  | Completed | 1 |  |  | P00074643LZ | 16OD0074 |  |  | 2016-09-15 |  |  | Aylan Const. & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Caloocan City |  | Camarin Shs (Brixton) | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Caloocan City | 136652 | Caybiga Es | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Caloocan City | 319701 | Cielito Zamora High School (Bonifacio Campus) | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Caloocan City | 136636 | Congress Es | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14898000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Caloocan City | 305387 | Llano Hs | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00074647LZ | 16OD0078 |  |  | 2016-09-27 |  |  | Prismodial Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Caloocan City |  | Samalla Tala Shs | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074650LZ | 16OD0076 |  |  | 2016-09-22 |  |  | St. Gerrard Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Caloocan City |  | Sampaguita Shs | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074649LZ | 16OD0075 |  |  | 2016-09-22 |  |  | Prismodial Const. Corp. | TO VERIFY APPROPRIATION FROM DPWH REPORT: 14,897,518.84 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Caloocan City | 305380 | Tala Hs | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 |  |  | P00074648LZ | 16OD0083 |  |  | 2016-10-25 |  |  | Aylan Const. & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Caloocan City | 136615 | Andres Bonifacio Es | Caloocan City | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31103000 |  |  | Completed | 1 |  |  | P00072840LZ | 16OD0059 |  |  | 2016-08-02 |  |  | St. Gerrard Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Caloocan City | 136615 | Andres Bonifacio Es | Caloocan City | 2 |  | 16 | 4STY16CL | BATCH 9 CL | 26703000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Caloocan City | 136606 | Grace Park Es (Main) | Caloocan City | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Caloocan City | 319706 | Kasarinlan Hs | Caloocan City | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 |  |  | P00074638LZ | 17OD0119 |  |  | 2017-07-20 |  |  | St. Timothy Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Caloocan City | 305391 | M. B. Asistio Sr. Hs (Main) | Caloocan City | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 |  |  | P00074636LZ P00171689LZ | 17OD0120 |  |  | 2017-07-20 |  |  | Omicron Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Caloocan City | 305391 | M. B. Asistio Sr. Hs Unit 1 To M. B. Asistio, Sr. Hs | Caloocan City | 2 |  | 32 | 4STY32CL | BATCH 13 CL | 44532220.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | NCR | Las Piñas City | 136773 | Caa Elementary School Main | City Of Las Piñas | 0 | 1 | 40 | 4STY20CL | BATCH 13 CL | 62205780.54 |  |  | Completed | 1 |  |  | P00075393LZ | 17OI0077 | 2017-06-13 | 2017-06-21 | 2017-07-04 | 2017-07-19 | 43024 | REDCAR TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | NCR | Las Piñas City | 136790 | Daniel Fajardo Es To Talon Es | City Of Las Piñas | 0 | 1 | 12 | 4STY12CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 17OI0123 | 2017-11-02 | 2017-11-10 | 2017-11-23 | 2017-11-29 | 43084 | DAVHEZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Las Piñas City | 136784 | Dona Manuela Es | City Of Las Piñas | 0 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00075394LZ | 17OI0051 | 2017-03-17 | 2017-03-24 | 2017-04-05 | 2017-04-24 | 43024 | DAVHEZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Las Piñas City | 136775 | Gatchalian Es | City Of Las Piñas | 0 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 |  |  | P0007031LZ | 16OI0027 | 2017-02-23 | 2017-03-02 | 2017-03-14 | 2017-03-21 | 42892 | MRRM Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Las Piñas City | NEWLY-ESTABLISHED SCHOOL | Moonwalk Es To Realign To Repsci Las Pinas | City Of Las Piñas | 0 | 1 | 16 | 4STY16CL | BATCH 3 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00070312LZ | 16OI0095 | 2017-09-29 | 2017-10-06 | 2017-10-13 | 2017-10-28 | 43061 | DAVHEZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Las Piñas City | NEWLY-ESTABLISHED SCHOOL | Shs In Martinville, Las Piñas City/ Realign To Golden Acres Las Pinas | Las Piñas City | 0 | 1 | 32 | 4STY32CL | BATCH 3 CL | 44532220.04 |  |  | Completed | 1 |  |  | P00070310LZ | 17OI0098 | 2017-09-06 | 2017-09-14 | 2017-09-26 | 2017-10-06 | 43084 | DAVHEZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | NCR | Las Piñas City | 136791 | Zapote Es | City Of Las Piñas | 0 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00075395LZ | 17OI0052 | 2017-03-17 | 2017-03-24 | 2017-04-05 | 2017-12-24 | 43084 | LMG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Malabon City | 136834 | Imelda Es | City Of Malabon | 0 | 1 | 24 | 4STY24CL | BATCH 7 CL | 35596257.14 |  |  | Completed | 1 | [8 empty] | 10/27/2016 | edison devt & const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | NCR | Malabon City | 136836SHS | Ninoy Aquino Es | City Of Malabon | 0 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [8 empty] | 42955 | hexamindz corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Malabon City | 136846 | Santiago Syjuco Memorial School | City Of Malabon | 0 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [8 empty] | 42502 | LTM builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | NCR | Malabon City | 136838 | Tañong Es I | City Of Malabon | 0 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [8 empty] | 11/15/2016 | victoria devt |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | NCR | Malabon City | 136850 | Tinajeros Es | City Of Malabon | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18222268.79 |  |  | Completed | 1 | [8 empty] | 10/16/17 | alpha & omega general contractor |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Malabon City | 320504 | Tinajeros Nhs - Acacia Annex | City Of Malabon | 0 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1 | [8 empty] | 42655 | framecon builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | NCR | Mandaluyong City | 500051 | Andres Bonifacio Is | Mandaluyong City | 0 | 1 | 16 | 4STY16CL | BATCH 11 CL | 33300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Mandaluyong City | 136657 | Filemon Javier Es | Mandaluyong City | 0 | 1 | 12 | 4STY12CL (INCL. SITE DEV & DEMOLITION) WITH COVERED HIGH COLUMN SUPPORT FOR MULTI-PURPOSE HALL/ROOF DECK | BATCH 11 CL | 35300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Mandaluyong City | 136831 | Hulo Integrated School | Mandaluyong City | 0 | 1 | 24 | 4STY24CL | BATCH 11 CL | 52300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | NCR | Mandaluyong City | 500335 | Ilaya Barangka Is | Mandaluyong City | 0 | 1 | 12 | 4STY12CL | BATCH 11 CL | 35450000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Mandaluyong City | 319804 | Jose Fabella Memorial School | City Of Mandaluyong | 0 | 1 | 16 | 4STY16CL | BATCH 3 CL | 32150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Mandaluyong City | 305394 | Mataas Na Paaralang Neptali A. Gonzales | City Of Mandaluyong | 0 | 1 | 48 | 4STY48CL | BATCH 13 CL | 100950000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | NCR | Manila | 136488 | Gen. Emilio Aguinaldo Is | Manila | 6 | 1 | 12 | 4STY12CL | BATCH 11 CL | 24352577.982 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Marikina City | 136681 | Fortune Es | Marikina City | 2 | 1 | 4 | Completion of 3STY9CL | BATCH 11 CL | 5959577.43 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | NCR | Marikina City | 136685 | Sss Village Es | City Of Marikina | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Marikina City | 136685 | Sss Village Es | City Of Marikina | 2 |  | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Muntinlupa City | 136908 | Alabang Es (Main) | City Of Muntinlupa | 0 | 1 | 32 | 4STY16CL | BATCH 7 CL | 53404938.84 |  |  | Completed | 1 |  |  |  | 16OI0049 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 42528 | MRRM Trading & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | NCR | Muntinlupa City | 136908 | Alabang Es (Main) | City Of Muntinlupa | 0 |  | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16OI0043 | 2016-02-29 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 42528 | RV Rieta Trading & Gen Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Muntinlupa City | 136910 | Bayanan Elementary School Unit I | City Of Muntinlupa | 0 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16OI0050 | 2016-03-02 | 2016-03-09 | 2016-03-21 |  |  | R. V. Rieta Trading & Gen. Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Muntinlupa City | 136912 | Cupang Es | City Of Muntinlupa | 0 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16OI0042 | 2016-02-29 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 42534 | Redcar Trading & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Muntinlupa City | 136900 | F. De Mesa Es | City Of Muntinlupa | 0 | 1 | 16 | 4STY8CL | BATCH 7 CL | 29795837.68 |  |  | Completed | 1 |  |  |  | 16OI0053 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 42528 | MRRM Trading & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Muntinlupa City | 136901 | Itaas Elementary School | City Of Muntinlupa | 0 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16OI0054 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 42528 | MRRM Trading & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Muntinlupa City | 136903 | Muntinlupa Es | City Of Muntinlupa | 0 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16OI0051 | 2016-03-02 | 2016-03-09 | 2016-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Muntinlupa City | 136903 | Muntinlupa Es | City Of Muntinlupa | 0 |  | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16OI0057 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 42534 | Orani Builders Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Muntinlupa City | 305468 | Muntinlupa Nhs | City Of Muntinlupa | 0 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897918.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Muntinlupa City | 305468 | Muntinlupa Nhs | City Of Muntinlupa | 0 |  | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Muntinlupa City | 305468 | Muntinlupa Nhs | City Of Muntinlupa | 0 |  | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Muntinlupa City | 305470 | Pedro E. Diaz High School | City Of Muntinlupa | 0 | 1 | 24 | 4STY12CL | BATCH 7 CL | 44304687.24 |  |  | Completed | 1 |  |  |  | 16OI0055 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 42534 | Orani Builders Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | NCR | Muntinlupa City | 305470 | Pedro E. Diaz High School | City Of Muntinlupa | 0 |  | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16OI0052 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 42534 | Precious Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Muntinlupa City | 136905 | Soldiers' Hills Es | City Of Muntinlupa | 0 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Muntinlupa City | 136914 | Sucat Elementary School | City Of Muntinlupa | 0 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16OI0056 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 42528 | E. M. Paule Const. & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Muntinlupa City | 136914 | Sucat Elementary School | City Of Muntinlupa | 0 |  | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16OI0068 | 2016-04-22 | 2016-03-09 | 2016-05-11 | 2016-05-19 | 42554 | Orani Builders Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Navotas City | 136858 | Dagat-Dagatan Elementary School | City Of Navotas | 0 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Navotas City | 305454 | San Rafael Technological High School | City Of Navotas | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Navotas City | 136867 | Tangos Elementary School | City Of Navotas | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Navotas City | 305457 | Tangos National High School | City Of Navotas | 0 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Navotas City | 305453 | Navotas National High School | Navotas City | 0 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26852469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Navotas City |  | Navotas Science High School | Navotas City | 0 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Navotas City | 136863 | North Bay Boulevard North Elementary School | City Of Navotas | 0 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Navotas City | 340628 | Shs In Lisan, Navotas City | City Of Navotas | 0 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Paranaque City | 305424 | Paranaque National High School Main | City Of Parañaque | 0 |  | 56 | 4STY28CL | BATCH 11 CL | 80135892.28 |  |  | Completed | 1 | [9 empty] | Flordes Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 56 | 0
NEWCON 2016 | NCR | Paranaque City | 136754 | La Huerta Elementary School | City Of Parañaque | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [9 empty] | Triple 8 Construction & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Paranaque City | 136754 | La Huerta Elementary School | City Of Parañaque | 1 |  | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Reverted | 0 | [9 empty] | Flordes Construction & Trading | Mutual termination; cancelled effective December 23, 2021 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | NCR | Paranaque City | 136757 | Paranaque Elementary School Unit Ii | City Of Parañaque | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [9 empty] | Flordes Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Paranaque City | 136756 | Paranaque Es Central | City Of Parañaque | 1 | 1 | 16 | 4STY8CL | BATCH 13 CL | 29795037.68 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Paranaque City | 136756SHS | Paranaque Es Central | City Of Parañaque | 1 | 1 | 16 | 4STY8CL | BATCH 11 CL | 29795037.68 |  |  | Completed | 1 | [9 empty] | Redcar Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Paranaque City | 305426 | Paranaque National High School - Baclaran | City Of Parañaque | 1 | 1 | 28 | 4STY28CL | BATCH 3 CL | 40067946.14 |  |  | Completed | 1 | [9 empty] | MRRM Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0
NEWCON 2016 | NCR | Paranaque City | 305426 | Paranaque National High School - Baclaran | City Of Parañaque | 1 |  | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 | [9 empty] | R.E. Orlina Construction Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Paranaque City | 305426 | Paranaque National High School - Baclaran | City Of Parañaque | 1 |  | 16 | 4STY16CL | BATCH 3 CL | 26702469.42 |  |  | Completed | 1 | [9 empty] | R.E. Orlina Construction Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Paranaque City | 305424 | Paranaque National High School Main | City Of Parañaque | 1 | 1 | 24 | 4STY12CL | BATCH 11 CL | 44304687.24 |  |  | Completed | 1 | [9 empty] | Hexamindz Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | NCR | Paranaque City | 305427 | Paranaque Nhs - Don Galo Annex | City Of Parañaque | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [9 empty] | Omicron Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Paranaque City | 305427 | Paranaque Nhs - Don Galo Annex | City Of Parañaque | 1 |  | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 | [9 empty] | Henscha Philippines Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Paranaque City | 136765SHS | Sto. Nino Es | City Of Parañaque | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [9 empty] | R.E. Orlina Construction Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Paranaque City | 136765 | Sto. Nino Es | City Of Parañaque | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Paranaque City | 136766 | Tambo Es | City Of Parañaque | 1 | 1 | 32 | 4STY32CL | BATCH 7 CL | 44532220.04 |  |  | Completed | 1 | [9 empty] | Precious Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | NCR | Pasay City | 136593 | Kalayaan Es | Pasay City | 0 | 1 | 9 | 4STY 9CL | BATCH 9 CL | 21170000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | NCR | Pasay City | 136599 | Marcela Marcelo Es | Pasay City | 0 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Pasay City | 319602 | Philippine National School For The Blind | Pasay City | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | NCR | Pasay City | 136601 | Timoteo Paez Es | Pasay City | 0 | 1 | 24 | 4STY24CL | BATCH 3 CL | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot Sci (Respsci) | City Of Pasig | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31602890.27 |  |  | Completed | 1 |  |  | P00171699 LZ_CW1 | 0170B0120 | 2016-12-29 | 2017-01-06 | 2017-01-19 |  | 43032 | LPO Enterprises & R'CEL Gen. Con & Gen. Merchendise (J.V.) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Quezon City | 136507 | Bagong Pag-Asa Es | Quezon City | 1 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Quezon City | 136507 | Bagong Pag-Asa Es | Quezon City | 1 |  | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Quezon City | 136501 | Esteban Abada Es | Quezon City | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Quezon City | 136501 | Esteban Abada Es | Quezon City | 1 |  | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Quezon City | 305322 | Eulogio Rodriguez, Jr. Hs | Quezon City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Quezon City | PSA328372 | Shs In Kaligayahan | Quezon City | 1 | 1 | 16 | 4STY16CL | BATCH 11 CL | 27709000 |  |  | Terminated | 0.65 | [10 empty] | DPWH REPORT: For Termination The contractor failed to resume to work; for mutual termination as per DPWH | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16
NEWCON 2016 | NCR | Quezon City | PSA328375 | Shs In Pasong Tamo | Quezon City | 1 | 1 | 32 | 4STY32CL | BATCH 9 CL | 44532220.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | NCR | Quezon City | 136506SHS | Toro Hills Es | Quezon City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Quezon City | 136506 | Toro Hills Es | Quezon City | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Quezon City | 305331 | Commonwealth Hs | Quezon City | 2 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31252890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Quezon City | 136542 | Dona Juana Es | Quezon City | 2 | 1 | 3 | Completion of 4STY14CL | BATCH 9 CL | 4754642.66 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | NCR | Quezon City | 319501 | Shs In Batasan Hills (Ext. Of Batasan Hills Nhs) To Holy Spirit Nhs | Quezon City | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23018000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Quezon City | PSA328570 | Shs In Harmony Hills (Accibal Property) | Quezon City | 2 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31252890.27 |  |  | Terminated | 0 | [10 empty] | DPWH REPORT: FOR TERMINATION / WITH ISFs | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20
NEWCON 2016 | NCR | Quezon City | PSA328570 | Shs In Harmony Hills (Accibal Property) | Quezon City | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23018000 |  |  | Terminated | 0 | [10 empty] | DPWH REPORT: FOR TERMINATION / WITH ISFs | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12
NEWCON 2016 | NCR | Quezon City | 136564 | Pura V. Kalaw Es | Quezon City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Quezon City | 136534 | Lagro Es | Quezon City | 5 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.02 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Quezon City | 136534 | Lagro Es | Quezon City | 5 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Quezon City | 136536 | Nagkaisang Nayon Es | Quezon City | 5 | 1 | 16 | 4STY16CL (L-Shape) | BATCH 11 CL | 26852469.42 |  |  | Terminated | 0.77 | [10 empty] | For Termination;The contractor failed to resume to work; No movement at all | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16
NEWCON 2016 | NCR | Quezon City | 136538 | San Agustin Es | Quezon City | 5 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22177343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Quezon City | 136525 | San Bartolome Es | Quezon City | 5 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26739923.9661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Quezon City | 136529 | San Gabriel Es | Quezon City | 5 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | San Juan City | NEWLY-ESTABLISHED SCHOOL | San Juan Es To San Juan City Tech-Voc And Livelihood Shs | San Juan City | 0 | 1 | 24 | 4STY24CL | BATCH 11 CL | 35596257.14 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | NCR | Taguig | 136892 | Aguho Es | Taguig | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Taguig | 136874 | Napindan Integrated School | Taguig City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22302343.52 |  |  | Terminated | 0.33 | [10 empty] | The project was terminated due to long period of suspension of the project due to pending demolition of the remaining existing structure by Dep-ed affecting the two grid line. - With request for funding which was received by Dep-Ed Central Office dated March 15, 2023 for the construction and completion of the building amounting Php62,500,00.00. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12
NEWCON 2016 | NCR | Taguig | 136896 | Pateros Elementary School | Pateros | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Taguig | 305466 | Pateros National High School | Pateros | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Taguig | 320611 | Taguig Integrated School | Taguig City | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22302343.52 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Taguig | 305460 | Taguig National High School | Taguig City | 1 | 1 | 32 | 4STY32CL | BATCH 9 CL | 44532220.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | NCR | Taguig | 305464 | Tipas National High School | Taguig City | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Taguig | 136890 | Maharlika Elementary School | Taguig City | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22302343.52 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Taguig | 305463 | Signal Village National High School | Taguig City | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Taguig | 136887 | Upper Bicutan Es | Taguig City | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Valenzuela City | 136801 | A. Fernando Es | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.8364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Valenzuela City | 305438 | Malinta National High School | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.8364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Valenzuela City | 136807 | Pio Valenzuela Es | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Valenzuela City | PSA328384 | Shs In Arkong Bato, Valenzuela | City Of Valenzuela | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Valenzuela City | PSA328387 | Shs In Paso De Blas, Valenzuela | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14897518.8364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Valenzuela City | PSA328381 | Shs In Punturin, Valenzuela | City Of Valenzuela | 1 | 1 | 24 | 4STY12CL | BATCH 5 CL | 44304687.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | NCR | Valenzuela City | 136810 | Tugatog Es | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.8364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Valenzuela City | PSA328386 | Shs In Ugong | Valenzuela City | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Valenzuela City | 305446 | Sitero Francisco Mem. Nhs | City Of Valenzuela | 2 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | NCR | Valenzuela City | 305441 | Valenzuela Nhs | Valenzuela City | 2 | 1 | 8 | Completion of 4STY32CL | BATCH 11 CL | 14747518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Quezon City | 136492 | Ramon Magsaysay Es | Quezon City | 1 | 1 | 20 | 4STY20CL | BATCH 14 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | NCR | Quezon City | 305322 | Eulogio Rodriguez, Jr. Hs | Quezon City | 1 | 1 | 8 | 4STY8CL | BATCH 14 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Quezon City | 136525 | San Bartolome Es | Quezon City | 5 | 1 | 8 | 4STY8CL | BATCH 14 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | NCR | Quezon City | 136533 | Kaligayahan Es | Quezon City | 5 | 1 | 12 | 4STY12CL | BATCH 14 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | NCR | Quezon City |  | Atty. Alfredo D. Vargas, Sr. Memorial High School | Quezon City | 5 | 1 | 20 | 4STY20CL L- Type Building (included elevation of 0.80 -1.20m high) | BATCH 14 CL | 42150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Caloocan City | 136650 | Bagbaguin ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | Completed | 1 |  |  | NC0215S00138 | 15OD0094 | 2015-09-18 | 2015-10-30 | 2015-10-01 | 2015-10-06 | 2015-11-05 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Caloocan City | 136641 | Kalayaan ES | Caloocan City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Caloocan City | 319705 | Maypajo HS | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 7 | 22152344 |  |  | Completed | 1 |  |  | NC0215S00154 | [6 empty] | PRISMOIDIAL CONST. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Caloocan City | 136629 | Morning Breeze ES | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 3 | 14897518.84 |  |  | Completed | 1 |  |  | NC0215S00092 | 15OD0089 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-29 | 2015-10-23 | TM ABAD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Caloocan City | 136646 | NHC ES | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | Completed | 1 |  |  | NC0215S00140 | 15OD0102 | 2015-10-07 | 2015-10-16 | 2015-10-20 | 2015-10-26 | 2015-11-17 | CARDRIAN BUILDERS CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Caloocan City |  | Proposed Stand Alone 1 (Caloocan City Business High School) | Caloocan City | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | Completed | 1 |  |  |  |  | 2015-11-26 |  |  |  |  | ORIENTECH CONSTRUCTION & DEVELOPMENT CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Caloocan City |  | Proposed Stand Alone 11 (Caloocan National Science & Technology High School) | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | Completed | 1 |  |  |  |  | 2015-09-04 | 2015-09-22 | 2015-09-24 | 2015-09-29 | 2015-11-05 | H.T.L. CONS'T |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Caloocan City |  | Proposed Stand Alone 2 (Cielito Zamora High School) | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | Completed | 1 |  |  |  |  | 2015-09-04 | 2015-09-22 | 2015-09-24 | 2015-09-29 | 2015-11-05 | T.M. ABAD CONS'T |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Caloocan City |  | Proposed Stand Alone 4 (NHC HS) | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 |  |  |  |  | 2015-09-11 | 2015-09-29 | 2015-10-01 | 2015-10-05 | 2015-11-05 | CARDRIAN BUILDERS CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Caloocan City |  | Proposed Stand Alone 6 (Bagong Barrio NHS - Annex) | Caloocan City | 1 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | Completed | 1 |  |  |  |  | 2015-11-26 |  |  |  |  | SUPREME ABF CONST. & CONST. SUPPLY CO. INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2015 | NCR | Caloocan City |  | Proposed Stand Alone 7 (AHS-Horacio Dela Costa Annex) | Caloocan City | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | Completed | 1 |  |  |  |  | 2015-11-26 |  |  |  |  | GENETIAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Caloocan City |  | Proposed Stand Alone 9 (Bagumbong High School) | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 |  |  |  |  | 2015-09-11 | 2015-09-29 | 2015-10-01 | 2015-10-05 | 2015-11-05 | VICTORIA DEV'T & CONS'T CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Caloocan City | 136649 | Tala ES | Caloocan City | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 30952890.27 |  |  | Completed | 1 |  |  | NC0215S00143 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Caloocan City | 136631 | Talipapa ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | Completed | 1 |  |  | NC0215S00082 | 15OD0095 | 2015-09-18 | 2015-09-30 | 2015-10-01 | 2015-10-06 | 2015-11-05 | CARDRIAN BUILDERS CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Caloocan City | 305371 | Talipapa HS | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 7 | 22152344 |  |  | Completed | 1 |  |  | NC0215S00150 |  | 2015-09-18 | 2015-09-30 | 2015-10-01 | 2015-10-09 | 2015-11-05 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Caloocan City | 136638 | Urduja ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Caloocan City | 136638 | Urduja ES | Caloocan City | 1 |  | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26552469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Caloocan City | 136618 | Gregoria de Jesus ES | Caloocan City | 2 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | Completed | 1 |  |  | NC0215S00137 | 15OD0096 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-10-01 | 2015-10-23 | CARDRIAN BUILDERS CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Caloocan City | 136609 | Kaunlaran ES | Caloocan City | 2 | 1 |  | Completion of 4STY6CL (Open Ground) | 2015 COMPLETION BATCH 4 | 843004.5563 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | Caloocan City | 2 | 1 |  | Completion of 2 UNITSof 4STY20CL | 2015 COMPLETION BATCH 4 | 4993346.46 |  |  | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Caloocan City | 305390 | Maria Clara HS | Caloocan City | 2 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 3 | 26702469.42 |  |  | Completed | 1 |  |  | NC0215S00083 | 15OD0092 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-30 | 2015-10-23 | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Caloocan City | 305392 | Proposed Stand Alone 3 (M. B. Asistio Sr. HS Unit 1) | Caloocan City | 2 | 1 | 32 | 4STY16CL | 2015 SHS BATCH 8 | 53404938.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2015 | NCR | Caloocan City | 500330 | Proposed Stand Alone 5 (Tandang Sora IS) | Caloocan City | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | Completed | 1 |  |  |  |  | 2015-11-05 |  |  |  |  | EDISON DEV'T CONST. | ongoing; rebidded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Caloocan City | 500330 | Proposed Stand Alone 5 (Tandang Sora IS) | Caloocan City | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | Completed | 1 | [9 empty] | C.B. TAMPENGCO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Caloocan City | 136614 | Sampalukan ES | Caloocan City | 2 | 1 |  | Completion of 3STY6CL | 2015 COMPLETION BATCH 4 | 2088779.1753 |  |  | 0 | 1 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Caloocan City | 500330 | Tandang Sora IS | Caloocan City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 3780074.83 |  |  | 0 | 0 |  |  | NC0215S00165 | 15OD0088 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-30 | 2015-10-23 | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | City of San Juan |  | Proposed Stand Alone SHS 1 (Tech-Voc) (Pinaglabanan ES) | City of San Juan | 0 | 1 | 9 | 4STY12CL (open 3 cl @ ground) | 2015 SHS BATCH 5 | 21192344 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | City of San Juan | 305423 | San Juan National HS (Academic) | City of San Juan | 0 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | Reverted | 0 |  |  | NC0215S00128 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Las Piñas City | 320304 | Las Pinas City National Science High School | CITY OF LAS PIÑAS | 0 | 1 |  | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Las Piñas City | 320304 | Las Pinas City National Science High School | CITY OF LAS PIÑAS | 0 | 1 | 16 | 2UNITS 4STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 21280072.63 |  |  | Completed | 1 |  |  | NC0215S00075 |  | 2015-08-17 |  | 2015-09-07 |  | 2016-03-01 | DAVHEZ TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Las Piñas City | 305430 | Las Piñas National HIgh School | CITY OF LAS PIÑAS | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | Completed | 1 |  |  | NC0215S00068 |  | 2015-12-17 |  | 2016-01-05 |  | 2016-03-23 | ORANI BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Las Piñas City | 305430 | Las Piñas National HIgh School | CITY OF LAS PIÑAS | 0 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | Completed | 1 |  |  | NC0215S00069 |  | 2015-12-17 |  | 2016-01-05 |  | 2016-03-23 | ORANI BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Las Piñas City | 136778 | Manuyo Elementary School | CITY OF LAS PIÑAS | 0 | 1 | 3 | 3STY3CL | 2015 K10 BATCH 6 | 6653472.88 |  |  | Completed | 1 |  |  | NC0215S00136 | 15OI0154 | 2015-12-03 |  | 2015-12-22 |  | 2016-01-15 | MRJR CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | NCR | Las Piñas City |  | Proposed Stand Alone SHS 1 (Las Pinas CES) | CITY OF LAS PIÑAS | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 |  |  |  |  | 2015-10-28 |  | 2015-11-23 |  | 2015-12-22 | ORANI BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Malabon City | 136840 | Amang Rodriguez ES | CITY OF MALABON | 0 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 1718800.4616 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | 0 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 1718800.4616 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | 15 | 3sty15cl | 2015 ADDITIONAL FUND BATCH 9 | 6111685.53 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2015 | NCR | Malabon City | 320502 | Malabon NHS - Concepcion Voc-Tech Annex | CITY OF MALABON | 0 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 7 | 10417132 |  |  | Completed | 1 |  |  | NC0215S00153 | [5 empty] | 2016-03-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | NCR | Malabon City | 136831 | Panghulo ES | CITY OF MALABON | 0 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 1718800.4616 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Malabon City | 305450 | Panghulo NHS | CITY OF MALABON | 0 | 1 |  | Completion of Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 1718800.4616 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Malabon City |  | Proposed Stand Alone SHS 1 (TNHS-Acacia Annex) | CITY OF MALABON | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | Completed | 1 | [8 empty] | 2016-01-11 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | NCR | Malabon City |  | Proposed Stand Alone SHS 2 (Dampalit ES) | CITY OF MALABON | 0 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 5 | 18222269 |  |  | Completed | 1 | [8 empty] | 2016-07-19 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Malabon City |  | Proposed Stand Alone SHS 4 (Imelda ES) | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15121328 |  |  | Completed | 1 | [8 empty] | 2016-06-07 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2015 | NCR | Malabon City |  | Proposed Stand Alone SHS 4 (Imelda ES) | CITY OF MALABON | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | Completed | 1 | [8 empty] | 2016-01-25 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | NCR | Malabon City |  | Proposed Stand Alone SHS 6 (Santiago Syjuco Memorial School) | CITY OF MALABON | 0 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 5 | 21383013 |  |  | Completed | 1 | [8 empty] | 2016-04-11 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2015 | NCR | Malabon City | 500339 | Tanong IS | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 7 | 15121328 |  |  | Completed | 1 |  |  | NC0215S00152 | [5 empty] | 2016-03-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2015 | NCR | Malabon City | 136839 | Tonsuya ES | CITY OF MALABON | 0 | 1 |  | Completion of 3STY3CL | 2015 COMPLETION BATCH 4 | 612128.4262 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Mandaluyong City | 319802 | Highway Hills Integrated School | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 30152344 |  |  | Completed | 1 |  |  | NC0215S00116 | 0150B0301 | 2015-10-08 | 2015-10-09 | 2015-10-22 | 2015-11-04 | 2015-11-16 | TRACSOM BUILDERS, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Mandaluyong City | 500331 | Isaac Lopez Integrated School | CITY OF MANDALUYONG | 0 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 |  |  | NC0215S00070 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Mandaluyong City | 319804 | Jose Fabella Memorial School | CITY OF MANDALUYONG | 0 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 2 | 35596257.14 |  |  | Reverted | 0 |  |  | NC0215S00073 | 0150B300 | 2015-10-08 | 2015-10-09 | 2015-10-22 | 2015-11-12 |  | TRACSOM BUILDERS, INC. |  | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Mandaluyong City | 305393 | Mandaluyong High School | CITY OF MANDALUYONG | 0 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 37202469.42 |  |  | Completed | 1 |  |  | NC0215S00067 | 0150B0299 | 2015-10-09 | 2015-10-09 | 2015-10-22 | 2015-10-30 | 2015-11-05 | TRACSOM BUILDERS, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 38002890 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 26252344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | Completed | 1 |  |  | NC0115S00021 | 15-OE0159 | 2015-11-20 | 2015-11-20 | 2015-12-03 |  |  | R.D. TALENS CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1 | 1 |  | Completion of 4STY20CL | 2015 COMPLETION BATCH 4 | 142465.625 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Manila | 305291 | Tondo High School | TONDO | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | Completed | 1 |  |  | NC0115S00016 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Manila | 305296 | Pres. Sergio Osmena, Sr. High School | TONDO | 2 | 1 |  | Completion of 4STY8CL | 2015 COMPLETION BATCH 4 | 7694435.2484 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3 | 1 |  | Completion of 4STY16CL | 2015 COMPLETION BATCH 4 | 10909209.6668 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Manila | 305302 | Jose Abad Santos High School | SANTA CRUZ | 3 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | Reverted | 0 |  |  | NC0115S00015 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Manila | 136464 | Moises Salvador Elementary School | Manila | 4 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | Completed | 1 |  |  | NC0115S00017 | 15-OE0158 | 2015-11-20 | 2015-11-20 | 2015-12-03 |  |  | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Manila | 305308 | Valeriano E. Fugoso Memorial High School | MANILA | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 |  |  | NC0115S00020 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Manila | 305309 | M.Araullo High School | ERMITA | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 |  |  | NC0115S00014 | 15OH0097 | 2015-10-11 | 2015-10-26 | 2015-10-27 |  |  | WERR CONSTRUCTION INTERNATIONAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Manila | 305318 | Manuel A. Roxas High School | PACO | 5 | 1 |  | Completion of 4STY8CL | 2015 COMPLETION BATCH 4 | 5577284.5063 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Manila | 305314 | Gen. Emilio Aguinaldo IS- Annex | Manila | 6 | 1 |  | Completion of 4STY16CL | 2015 COMPLETION BATCH 4 | 9983526.165 |  |  | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Manila |  | Proposed Stand Alone SHS 6 (Bacood ES) | SAMPALOC | 6 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | Completed | 1 | [9 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Marikina City | 136672 | Industrial Valley ES | Marikina City | 1 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 5999172.5916 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Marikina City | 136675 | Malanday ES | Marikina City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 2239374.87 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Marikina City | 136676 | Marikina ES | Marikina City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 7213523.0963 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Marikina City | 136676 | Marikina ES | Marikina City | 1 |  |  | Completion of 4STY12CL (Batch 4A) | 2015 COMPLETION BATCH 4 | 7462337.94 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Marikina City | 319905 | San Roque National High School | Marikina City | 1 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 3 | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Marikina City | 319905 | San Roque National High School | Marikina City | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Marikina City | 136680 | Concepcion ES | Marikina City | 2 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | Completed | 1 |  |  | NC0215S00085 | 0150B0293 | 2015-09-23 | 2015-10-05 | 2015-10-06 | 2015-10-29 | 2015-11-06 | ORANI BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Marikina City | 305403 | Concepcion Integrated School | Marikina City | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 |  |  | NC0215S00115 | 0150B0292 | 2015-09-23 | 2015-09-25 | 2015-10-06 | 2015-10-27 | 2015-11-23 | C.B. GARAY PHILWIDE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Marikina City | 136682 | H. Bautista ES | Marikina City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 7213523.0963 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Marikina City | 305398 | Marikina HS | Marikina City | 2 | 1 |  | Completion of 2 Units 4STY12CL & Completion of 4STY8CL | 2015 COMPLETION BATCH 4 | 15730030.3788 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Marikina City | 136677 | Nangka ES | Marikina City | 2 | 1 |  | Completion 4STY12CL | 2015 COMPLETION BATCH 4 | 7213523.0963 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Marikina City | 136684 | Parang ES | Marikina City | 2 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | Completed | 1 |  |  | NC0215S00086 | 0150B0285 | 2015-09-23 | 2015-09-25 | 2015-10-06 | 2015-10-22 | 2015-12-01 | ORANI BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Marikina City | 305404 | Parang HS | Marikina City | 2 | 1 |  | Completion of 2 Units 4STY12CL | 2015 COMPLETION BATCH 4 | 13266387.7325 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Marikina City | 305404 | Parang HS | Marikina City | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Marikina City | 136685 | SSS Village ES | Marikina City | 2 | 1 |  | Completion of 2 units of 4STY/12CL | 2015 COMPLETION BATCH 4 | 13266387.7325 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Marikina City | 136686 | St. Mary ES | Marikina City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | Completed | 1 |  |  | NC0215S00087 | 15OI0109 | 2015-08-31 | 2015-09-02 | 2015-09-14 | 2015-09-25 | 2015-10-20 | PRECIOUS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Muntinlupa City | 320702 | Muntinlupa Business High School - Sucat Annex | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 3 | 14897518.84 |  |  | Completed | 1 |  |  | NC0215S00088 | 15OI0159 | 2015-12-14 | 2015-12-16 | 2015-12-28 | 2016-12-29 | 2016-01-19 | LMG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 |  | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Muntinlupa City |  | Proposed Stand Alone SHS 1 (Muntinlupa NHS) | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Muntinlupa City |  | Proposed Stand Alone SHS 2 (Cupang SHS) | CITY OF MUNTINLUPA | 0 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2015 | NCR | Muntinlupa City | 136904 | Putatan ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | Completed | 1 |  |  | NC0215S00139 | 15OI0143 | 2015-11-12 | 2015-11-13 | 2015-11-25 | 2015-12-11 | 2015-12-23 | ORANI BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | 0 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 14971327.92 |  |  | Completed | 1 |  |  | NC0215S00145 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2015 | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | 0 | 1 | 20 | Completion of 3STY12CL. (Upgrading of 3STY12CL to 4STY20CL INCLUDING COST for soil improvement and additional 1m elevation | 2015 COMPLETION BATCH 4 | 13422977.41 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Navotas | 340628 | Lisan SHS Stand Alone | CITY OF NAVOTAS | 0 | 1 | 17 | 2 units 3STY9CL(1 unit with 1 cl open at the ground floor; 1.5m addl elevation) | 2015 SHS BATCH 5 | 31836524 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Navotas | 136860 | Navotas Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | Completed | 1 |  |  | NC0215S00144 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Navotas | 305454 | San Rafael Technological High School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 19897518.84 |  |  | Completed | 1 |  |  | NC0215S00080 | 015OA0091 | 2015-09-18 | 2015-09-28 | 2015-10-08 | 2015-10-16 | 2015-10-27 | VRV CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | Completed | 1 |  |  | NC0215S00089 | 015OA0097 | 2015-11-02 | 2015-11-19 | 2015-11-27 |  |  | STRUKTURA TEKNIKA SERVICES CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | 0 | 1 | 12 | Completion of 3STY12CL. (Upgrading of 3STY12CL to 4STY12CL INCLUDING COST for soil improvement and additional 1m elevation | 2015 COMPLETION BATCH 4 | 4379706.6847 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Parañaque City | 136768 | Baclaran ES Unit I | CITY OF PARAÑAQUE | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 30952890.27 |  |  | Completed | 1 |  |  | NC0215S00146 | 15OC0075 | 2015-08-20 | 2015-08-21 | 2015-09-03 | 2015-09-07 | 2015-09-18 | PRECIOUS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Parañaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | Completed | 1 |  |  | NC0215S00141 | 15OC0069 | 2015-08-17 | 2015-08-20 | 2015-09-01 | 2015-09-08 | 2015-09-18 | MPJR BUILDERS COMPANY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Parañaque City | 136762 | Don Galo ES | CITY OF PARAÑAQUE | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 30952890.27 |  |  | Completed | 1 |  |  | NC0215S00149 | 15OC0076 | 2015-08-20 | 2015-08-21 | 2015-09-03 | 2015-09-07 | 2015-09-18 | PRECIOUS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Parañaque City | 136754 | La Huerta ES | CITY OF PARAÑAQUE | 1 | 1 |  | Completion of 4STY32CL | 2015 COMPLETION BATCH 4 | 5228199.416 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Parañaque City | 136756 | Paranaque ES Central | CITY OF PARAÑAQUE | 1 | 1 |  | Completion of 4STY24CL & 4STY/12CL | 2015 COMPLETION BATCH 4 | 14094676.5723 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Parañaque City | 305426 | Paranaque National High School - Baclaran | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Parañaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 18 | 4STY20CL (2cl open at ground floor) | 2015 SHS BATCH 5 | 29822890 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2015 | NCR | Parañaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Parañaque City |  | Proposed Stand Alone SHS 3 (PNHS-Sto. Nino) | CITY OF PARAÑAQUE | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Parañaque City |  | Proposed Stand Alone SHS 4 (PNHS-Don Bosco) | CITY OF PARAÑAQUE | 2 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Pasay City | 319601 | Kalayaan NHS | PASAY CITY | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Pasay City | 319601 | Kalayaan NHS | PASAY CITY | 0 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Pasay City | 319602 | Philippine HS for the Blind | PASAY CITY | 0 | 1 | 4 | 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 4354597.47 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | NCR | Pasay City | 136595 | Rivera Village ES | Pasay City | 0 | 1 |  | 4STY9CL (Completion of 4STY12CL open GF) | 2015 COMPLETION BATCH 4 | 3192828.2063 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Pasay City | 136601 | Timoteo Paez ES | Pasay City | 0 | 1 |  | Completion of 4STY20CL | 2015 COMPLETION BATCH 4 | 6454915.895 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Pasig City |  | Porposed Stand Alone SHS 2 (Ugong Pasig City National) | CITY OF PASIG | 0 | 1 | 12 | 4STY12CL (L-Shape) | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Pasig City |  | Proposed Stand Alone SHS 3 (RHS) | CITY OF PASIG | 0 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2015 | NCR | Quezon City | 305320 | Balingasa HS | QUEZON CITY | 1 | 1 | 24 | 4STY24CL | 2015 ADDITIONAL FUND BATCH 9 | 13293913.52 |  |  | Completed | 1 |  |  | NC0315S00043 | 15OF0127 | 2015-08-12 | 2015-08-13 | 2015-12-15 | 2015-12-22 |  | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2015 | NCR | Quezon City | 136500 | Bungad ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 4330387.33 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Quezon City | 319506 | National Orthopedic Hospital School for Crippled Children | QUEZON CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | NC0315S00033 | 15OF0102 | 2015-07-23 | 2015-07-10 | 2015-08-05 | 2015-08-06 | 2015-08-28 | SUMMIT MERIDIEN CONSTRUCTION GROUP INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | NCR | Quezon City |  | Proposed Stand Alone SHS 1 (Balingasa HS; from Masambong HS & San Jose HS) | QUEZON CITY | 1 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2015 | NCR | Quezon City |  | Proposed Stand Alone SHS 4 (Toro Hills; from Pugad Lawin & E Rod HS) | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Quezon City |  | Proposed Stand Alone SHS 5 (E. Abada; from SFHS) | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Quezon City |  | Proposed Stand Alone SHS 6 (Bagong Pag-asa ES) | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Quezon City | 136505 | San Antonio ES | Quezon City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 3780074.83 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Quezon City | 136498 | San Francisco ES | Quezon City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 3780074.83 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Quezon City | 305330 | Batasan Hills National HS | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | Completed | 1 |  |  | NC0315S00032 | 15OF0122 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-23 | RCDG CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Quezon City | 305345 | Balara HS | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | Completed | 1 |  |  | NC0315S00031 | 15OG0099 | 2015-08-20 | 2015-09-04 | 2015-09-07 | 2015-09-22 | 2015-09-30 | MPJR BUILDERS COMPANY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Quezon City | 305346 | Camp Gen. E. Aguinaldo HS | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | Completed | 1 |  |  | NC0315S00030 | 15OG0090 | 2015-08-11 | 2015-08-22 | 2015-08-24 | 2015-08-28 | 2015-09-01 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Quezon City | 136558 | Eulogio Rodriguez, Sr. ES | QUEZON CITY | 3 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | Completed | 1 |  |  | NC0315S00044 | 15OG0103 | 2015-10-02 | 2015-10-18 | 2015-10-20 | 2015-11-04 | 2015-11-05 | R.E. ORLINA CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Quezon City | 136559 | Quirino ES | QUEZON CITY | 3 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | Completed | 1 |  |  | NC0315S00045 | 15OG-0104 | 2015-10-01 | 2015-10-15 | 2015-10-20 | 2015-11-04 | 2015-11-05 | METRICS CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Quezon City | 305350 | Quirino HS | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Quezon City | 305350 | Quirino HS | QUEZON CITY | 3 |  | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Quezon City | 305355 | Carlos L. Albert HS | QUEZON CITY | 4 | 1 | 16 | additional 2 units 4STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 29795037.68 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Quezon City | 305360 | Don Alejandro Roces, Sr. Sci. & Tech. HS | QUEZON CITY | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | Completed | 1 |  |  | NC0315S00026 | 15OG0089 | 2015-08-11 | 2015-08-22 | 2015-08-24 | 2015-08-28 | 2015-09-01 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Quezon City | 136576 | Pedro Tuason ES | QUEZON CITY | 4 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | Completed | 1 |  |  | NC0315S00046 | 15OG-0111 | 2015-10-16 | 2015-10-27 | 2015-11-04 | 2015-11-20 | 2015-11-23 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Quezon City | 136580 | Proposed Stand Alone SHS10 (Kamuning A&D ES; for Media Arts students from all over QC) | QUEZON CITY | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Quezon City | 136581 | Proposed Stand AloneSHS 9 (MH del Pilar; from R Magsaysay) | QUEZON CITY | 4 | 1 | 16 | 4STY8CL | 2015 SHS BATCH 5 | 29795038 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Quezon City | 136533 | Kaligayahan ES | Quezon City | 5 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | Completed | 1 |  |  | NC0315S00035 | 15OF0130 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-23 | LMG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Quezon City | 305336 | Lagro HS | QUEZON CITY | 5 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 2 | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2015 | NCR | Quezon City | 305338 | Maligaya HS | Quezon City | 5 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 3780074.83 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Quezon City | 136530 | Villa Verde Elementary School | QUEZON CITY | 5 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26552469.42 |  |  | Completed | 1 |  |  | NC0315S00047 | 15OF0132 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-08 | 2015-09-23 | PRISMODIAL CONSTRUCTION CORPORATION (FOR. PRISMODI |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Quezon City | 305333 | Culiat HS | Quezon City | 6 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | Completed | 1 |  |  | NC0315S00034 | 15OF0133 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-14 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Quezon City | 136519 | Lucas R. Pascual ES | Quezon City | 6 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | Completed | 1 |  |  | NC0315S00036 | 15OF0134 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-14 | MPJR BUILDERS COMPANY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | Taguig City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 136894 | Capt. H. Francisco ES Annex | Taguig City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 5222963.07 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 136893 | Capt. Hipolito Francisco Elementary School - Main | Taguig City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 136883 | Cipriano P. Sta. Teresa Elementary School | Taguig City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 5222963.07 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 136871 | Ciriaco P. Tiñga Elementary School | Taguig City | 1 | 1 |  | Completion of 4STY16CL | 2015 COMPLETION BATCH 4 | 6383621.53 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 136874 | Napindan Elementary School | Taguig City | 1 | 1 |  | Completion of 4STY24CL | 2015 COMPLETION BATCH 4 | 9285267.68 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | Taguig City | 1 | 1 |  | Completion of 4STY8CL | 2015 COMPLETION BATCH 4 | 3481975.38 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Taguig City & Pateros |  | Proposed Stand Alone SHS 2 (Taguig ES) | TAGUIG CITY | 1 | 1 | 24 | 4STY12CL | 2015 SHS BATCH 5 | 44304687 |  |  | Completed | 1 | [10 empty] | CONTRACT TO BE TERMINATED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2015 | NCR | Taguig City & Pateros |  | Proposed Stand Alone SHS 3 (DANES) | TAGUIG CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Taguig City & Pateros |  | Proposed Stand Alone SHS 4 (Brgy. Fort Bonifacio SHS) | TAGUIG CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 136876 | Taguig Elementary School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | Completed | 1 |  |  | NC0215S00147 | 0150B0352 | 2015-11-19 | 2015-11-23 | 2015-12-03 | 2015-12-23 |  | VERZONTAL BUILDERS, INC. (FORMERLY VERZONTAL BUILD |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 320601 | Taguig Science High School | TAGUIG CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | Completed | 1 |  |  | NC0215S00107 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Taguig City & Pateros |  | DepED Property | Taguig City | 2 | 1 |  | Completion of 2 units 4STY12CL(elevated @ 1.5m) | 2015 COMPLETION BATCH 4 | 602647.6184 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | Taguig City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 320606 | Pres. Diosdado Macapagal HS - Signal VNHS Annex | TAGUIG CITY | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Reverted | 0 |  |  | NC0215S00081 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 305463 | Signal Village NHS | Taguig City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Taguig City & Pateros | 305463 | Signal Village NHS | TAGUIG CITY | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Valenzuela City | 136800 | A. Deato ES | Valenzuela City | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 3 | 14897518.84 |  |  | Completed | 1 |  |  | NC0215S00090 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Valenzuela City | 136802 | Coloong ES | CITY OF VALENZUELA | 1 | 1 |  | Completion 4STY8CL | 2015 COMPLETION BATCH 4 | 3043971.8762 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Valenzuela City | 136806 | Pasolo ES | CITY OF VALENZUELA | 1 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 776209.5191 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Valenzuela City | 136811 | WawangPulo ES | CITY OF VALENZUELA | 1 | 1 |  | Completion of 3STY6CL | 2015 COMPLETION BATCH 4 | 2932013.3353 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | NCR | Valenzuela City | 305445 | Caruhatan NHS | CITY OF VALENZUELA | 2 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 7 | 22152344 |  |  | Completed | 1 |  |  | NC0215S00151 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | NCR | Valenzuela City | 320408 | DALANDANAN NHS- Bagbaguin Annex | Valenzuela City | 2 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 3 | 26702469.42 |  |  | Completed | 1 |  |  | NC0215S00091 | 15OD0104 | 2015-10-07 | 2015-10-16 | 2015-10-19 | 2015-10-22 | 2015-11-17 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | NCR | Valenzuela City | 136817 | Paso de Blas ES | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | Completed | 1 |  |  | NC0215S00148 | 15OD0099 | 2015-09-18 | 2015-09-30 | 2015-10-01 | 2015-10-15 | 2015-11-05 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | NCR | Valenzuela City | 305446 | Sitero Francisco Mem. NHS | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15082518.84 |  |  | Completed | 1 |  |  | NC0215S00071 | 15OD0103 | 2015-10-07 | 2015-10-19 | 2015-10-20 | 2015-10-26 | 2015-11-17 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Caloocan City | 305384 | Baesa HS | Caloocan City | 1 | 1 | 8 | 4STY 8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | 2015-09-24 | 2015-09-23 | NC0214S00072 | 14OD0076 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-25 | 2015-02-27 | ORANI BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Caloocan City | 136651 | Bagumbong ES | Caloocan City | 1 | 1 | 18 | 3STY 18CL | 2014 K10 BATCH 3 | 27120494.0625 |  |  | Completed | 1 |  |  | NC0214S00061 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2014 | NCR | Caloocan City | 223501 | Caloocan North ES | Caloocan City | 1 | 1 | 48 | 4STY28CL & 4STY20CL | 2014 K10 BATCH 4B | 71170836.41 |  |  | Completed | 1 |  |  | NC0214S00114 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2014 | NCR | Caloocan City | 136641 | Kalayaan ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Caloocan City | 305379 | Manuel L. Quezon HS | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | 2015-09-24 | 2015-09-23 | NC0214S00059 | 14OD0073 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-25 | 2015-02-27 | ORANI BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Caloocan City | 136640 | Sto. Nino ES | Caloocan City | 1 | 1 | 8 | 4STY 8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | 2015-10-24 | 2015-10-23 | NC0214S00060 | 14OD0074 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-25 | 2015-02-27 | ST. GERRARD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Caloocan City | 305388 | Caloocan HS | Caloocan City | 2 | 1 | 36 | 4STY20CL & 4STY16CL | 2014 K10 BATCH 4B | 57805359.69 |  |  | Completed | 1 |  |  | NC0214S00113 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0
NEWCON 2014 | NCR | Caloocan City | 136606 | Grace Park ES (Main) | Caloocan City | 2 | 1 | 8 | 4STY/8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | 2015-09-24 | 2015-07-25 | NC0214S00065 | 14OD0075 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-16 | 2015-02-27 | ORANI BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Caloocan City | 136608 | Kasarinlan ES | Caloocan City | 2 | 1 | 9 | 3STY/9CL and installation of remaining bored piles | 2014 K10 BATCH 4B | 16565073.8707 |  |  | Completed | 1 |  |  | NC0214S00097 | 15OD0070 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-14 | 2015-09-04 | J. SIMEON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | NCR | Caloocan City | 136609 | Kaunlaran ES | Caloocan City | 2 | 1 | 6 | 4STY6CL (Open Ground) | 2014 K10 BATCH 4A | 15035522.3438 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | NCR | Caloocan City | 136609 | Kaunlaran ES | Caloocan City | 2 | 1 | 12 | Completion of 4STY/12CL(remaining 4CL), 4STY/8CL and installation of remaining bored piles | 2014 K10 BATCH 4B | 30789912.22 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | Caloocan City | 2 | 1 | 40 | 2 UNITS 4STY20CL | 2014 K10 BATCH 3 | 64101168.75 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2014 | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | Caloocan City | 2 | 1 | 9 | 3STY/9CL and installation of remaining bored piles | 2014 K10 BATCH 4B | 16565073.8707 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | NCR | Caloocan City | 136613 | Maypajo ES | Caloocan City | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | Completed | 1 |  |  | NC0214S00108 | [7 empty] | termination of contract on process | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Caloocan City | 136614 | Sampalukan ES | Caloocan City | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10817093.5547 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | NCR | Caloocan City | 500330 | Tandang Sora IS | Caloocan City | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | Completed | 1 | [10 empty] | ongoing; rebidded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Las Piñas City | 136773 | CAA ES | CITY OF LAS PIÑAS | 0 | 1 | 32 | 2 Units 4STY 16CL | 2014 K10 BATCH 3 | 55078781.25 |  |  | Completed | 1 | 2016-08-10 |  | NC0214S00066 | 15OI0047 | 2015-04-13 | 2015-04-15 | 2015-05-04 | 2015-06-03 | 2015-06-18 | PRECIOUS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2014 | NCR | Las Piñas City | 305432 | Golden Acres NHS | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 |  |  | NC0214S00123 |  | 2015-07-17 |  | 2015-08-05 |  | 2015-09-02 | RGDG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Las Piñas City | 136788 | Pamplona ES I | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | Completed | 1 |  |  | NC0214S00100 | 15OI0140 | 2015-07-23 | 2015-07-24 | 2015-11-23 |  |  | DAVHEZ TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Malabon City | 136840 | Amang Rodriguez ES | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 19220118.3984 |  |  | Completed | 1 | [8 empty] | 2015-10-30 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | NCR | Malabon City | 500337 | Catmon IS | CITY OF MALABON | 0 | 1 | 24 | 3STY15CL (1CL open) & 3STY9CL | 2014 K10 BATCH 4B | 36184341.37 |  |  | Completed | 1 |  |  | NC0214S00101 | 016OA0017 | 2015-12-09 | 2015-12-17 | 2015-12-29 |  | 2016-02-03 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2014 | NCR | Malabon City | 136828 | Dampalit ES | CITY OF MALABON | 0 | 1 | 2 | Completion of 2STY/4CL(construction of remaining 2CL) | 2014 K10 BATCH 4B | 5078460.2437 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | NCR | Malabon City | 136854 | Epifanio de los Santos ES | CITY OF MALABON | 0 | 1 | 15 | 3STY15CL | 2014 K10 BATCH 4B | 21383013.45 |  |  | Completed | 1 |  |  | NC0214S00102 | 016OA0019 | 2015-12-09 | 2015-12-17 | 2015-12-29 |  | 2016-02-03 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2014 | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 19220118.3984 |  |  | Completed | 1 | [8 empty] | 2015-10-30 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | 0 | 1 | 7 | Completion of 2STY/10CL(construction of remaining 7CL) | 2014 K10 BATCH 4B | 7383047.4188 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0
NEWCON 2014 | NCR | Malabon City | 305447 | Malabon NHS | Malabon City | 0 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | NCR | Malabon City | 136844 | Muzon ES | CITY OF MALABON | 0 | 1 | 5 | Completion of 2STY/6CL(construction of remaining 5CL) | 2014 K10 BATCH 4B | 8023252.8469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2014 | NCR | Malabon City | 136831 | Panghulo ES | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 19220118.3984 |  |  | Completed | 1 | [8 empty] | 2015-10-30 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | NCR | Malabon City | 136832 | Panghulo ES I | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 23904509.7656 |  |  | Completed | 1 | 2016-05-05 |  | NC0214S00069 | 015OA0079 | 2015-07-29 | 2015-08-07 | 2015-08-19 | 2015-08-27 | 2015-09-09 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Malabon City | 305450 | Panghulo NHS | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 19220118.3984 |  |  | Completed | 1 | [8 empty] | 2015-10-30 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | NCR | Malabon City | 305449 | Potrero NHS | Malabon City | 0 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | Completed | 1 |  |  | NC0214S00136 | 016OA0016 | 2015-12-09 | 2015-12-17 | 2015-12-29 |  | 2016-02-03 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | NCR | Malabon City | 136850 | Tinajeros ES | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4B | 15121327.92 |  |  | Completed | 1 | 2016-06-29 |  | NC0214S00103 | 015OA0095 | 2015-10-22 | 2015-11-11 | 2015-11-11 | 2015-11-23 | 2015-12-03 | R.D. TALENS CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | NCR | Malabon City | 320504 | Tinajeros NHS - Acacia Annex | CITY OF MALABON | 0 | 1 | 0 | Completion of 3STY/9CL | 2014 K10 BATCH 4B | 1505105.4375 |  |  | Completed | 1 | 2015-09-21 | 2015-09-21 | NC0214S00105 | 015OA0062 | 2015-06-10 | 2015-06-18 | 2015-06-29 | 2015-07-08 | 2015-07-24 | DREAMWORX BUILDER & TRADING, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Malabon City | 136839 | Tonsuya ES | CITY OF MALABON | 0 | 1 | 3 | 3STY3CL | 2014 K10 BATCH 3 | 7323603.6303 |  |  | Completed | 1 | [8 empty] | 2015-09-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | NCR | Malabon City | 136839 | Tonsuya ES | CITY OF MALABON | 0 | 1 | 3 | Completion of 3STY/9CL(construction of remaining 3CL) | 2014 K10 BATCH 4B | 3995299.9594 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | NCR | Mandaluyong City | 319803 | Eulogio Rodriguez Integ. Sch. | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | 2016-03-01 |  | NC0214S00135 | 0150B0159 | 2015-06-30 | 2015-08-17 | 2015-08-27 | 2015-09-18 | 2015-09-30 | TRACSOM BUILDERS, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1 | 1 | 20 | 4STY20CL w/ provision for micropiles @ 250mm, 15m depth (Replacement of Burned Bldg.) | 2014 K10 BATCH 3 | 46161534.375 |  |  | Completed | 1 | [9 empty] | ORANI BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2014 | NCR | Manila | 305296 | Pres. Sergio Osmena, Sr. High School | TONDO | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | [9 empty] | M.V CALDO CONST. ENGINEERING & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Manila | 305296 | Pres. Sergio Osmena, Sr. High School | Manila | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | [9 empty] | SUPREME ABF CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 28544390.625 |  |  | Completed | 1 | [9 empty] | PRECIOUS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2014 | NCR | Manila | 305299 | Dona Teodora Alonzo HS | Manila | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 |  |  | NC0114S00027 | 15-OE0091 | 2015-07-02 | 2015-07-02 | 2015-07-14 |  |  | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Manila | 305303 | Raja Soliman Science and Technology High School | Manila | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Reverted | 0 |  |  | NC0114S00021 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Manila | 305307 | Claro M. Recto High School | Manila | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 |  |  | NC0114S00026 | 15-OE0090 | 2015-07-02 | 2015-07-02 | 2015-07-14 |  |  | SUPREME ABF CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Manila | 305312 | Manila Science High School | Manila | 5 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Reverted | 0 |  |  | NC0114S00030 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Manila | 305318 | Manuel A. Roxas High School | PACO | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | [9 empty] | TRIPLE 8 CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Manila | 305314 | Gen. Emilio Aguinaldo IS- Annex | Manila | 6 | 1 | 16 | 4STY 16CL(proposed for SHS) | 2014 K10 BATCH 3 | 27539390.625 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Marikina City | 136671 | Barangka ES | Marikina City | 1 | 1 | 10 | 3STY 30CL (phase 2) | 2014 K10 BATCH 4A | 12864000 |  |  | Completed | 1 | 2015-07-05 | 2015-07-03 | NC0214S00090 | 0140B0258 | 2014-12-10 | 2014-12-11 | 2014-12-23 | 2015-01-06 | 2015-01-07 | NVF CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2014 | NCR | Marikina City | 136672 | Industrial Valley ES | Marikina City | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14195118.3984 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | NCR | Marikina City | 319907 | Jesus dela Pena NHS | Marikina City | 1 | 1 | 16 | 4STY 16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | Completed | 1 | 2016-01-06 |  | NC0214S00084 | 0150B0290 | 2014-12-10 | 2014-12-11 | 2015-03-30 | 2015-04-28 | 2015-05-12 | FIRMABUILT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2014 | NCR | Marikina City | 319904 | Kalumpang National High School | Marikina City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Marikina City | 319904 | Kalumpang National High School | Marikina City | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 32050584.375 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2014 | NCR | Marikina City | 319904 | Kalumpang National High School | Marikina City | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4A | 31900584.375 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2014 | NCR | Marikina City | 136675 | Malanday ES | Marikina City | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4A | 19861783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Marikina City | 305402 | Malanday NHS | Marikina City | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | 2016-07-01 |  | NC0214S00133 | 0150B0295 | 2015-10-01 | 2015-10-02 | 2015-10-15 | 2015-10-21 | 2015-11-04 | R.D. TALENS CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Marikina City | 136676 | Marikina ES | Marikina City | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Marikina City | 136676 | Marikina ES | Marikina City | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4A | 19861783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Marikina City |  | San Roque National High School | Marikina City | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 32050584.375 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2014 | NCR | Marikina City | 136687 | Sto. Nino ES | Marikina City | 1 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | Completed | 1 | 2016-02-05 |  | NC0214S00082 | 0140B0238 | 2014-12-04 | 2014-12-11 | 2015-03-30 | 2015-04-30 | 2015-05-08 | JEMN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2014 | NCR | Marikina City | 319906 | Sto. Nino National High School | Marikina City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Marikina City | 319906 | Sto. Nino National High School | Marikina City | 1 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2014 | NCR | Marikina City | 136679 | Concepcion Integrated School | Marikina City | 2 | 1 | 3 | Completion of 4STY12CL (Construction of remaining 3CL) | 2014 K10 BATCH 4B | 5625000 |  |  | Completed | 1 | 2015-12-11 | 2015-12-04 | NC0214S00219 | 0150B0127 | 2015-05-13 | 2015-05-15 | 2015-05-26 | 2015-06-16 | 2015-08-14 | LTDL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | NCR | Marikina City | 136682 | H. Bautista ES | Marikina City | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Marikina City | 305398 | Marikina HS | Marikina City | 2 | 1 | 32 | 2 UNITS 4STY12CL & 4STY8CL | 2014 K10 BATCH 3 | 55209089.5312 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2014 | NCR | Marikina City | 136677 | Nangka ES | Marikina City | 2 | 1 | 12 | 4STY 12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Marikina City | 136677 | Nangka ES | Marikina City | 2 | 1 | 0 | Construction of remaining 1 bay of stairs for both buildings (4STY20CL & 3STY9CL) and connecting bridge | 2014 K10 BATCH 4B | 4968750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Marikina City | 305404 | Parang HS | Marikina City | 2 | 1 | 24 | 2UNITS 4STY12CL | 2014 K10 BATCH 3 | 40023567.1875 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2014 | NCR | Marikina City | 136685 | SSS Village ES | Marikina City | 2 | 1 | 24 | 2 units of 4STY/12CL | 2014 K10 BATCH 3 | 40023567.1875 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2014 | NCR | Marikina City | 136686 | St. Mary ES | Marikina City | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Muntinlupa City | 136910 | Bayanan Elementary School Unit I | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Muntinlupa City | 136900 | F. de Mesa ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15205622.3438 |  |  | Completed | 1 | 2015-10-30 | 2015-10-30 | NC0214S00086 | 150I0005 | 2015-01-26 | 2015-01-26 | 2015-02-09 | 2015-02-20 | 2015-03-05 | MRRM TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Muntinlupa City | 136901 | Itaas Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4B | 31102890.27 |  |  | Completed | 1 |  |  | NC0214S00145 | 15OI0161 | 2015-12-14 | 2015-12-16 | 2015-12-28 | 2016-12-29 | 2016-01-15 | CHIARA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2014 | NCR | Muntinlupa City | 136902 | Lakeview ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15205622.3438 |  |  | Completed | 1 | 2015-09-30 |  | NC0214S00077 | 15OI0004 | 2015-01-26 | 2015-01-28 | 2015-02-09 | 2014-02-16 | 2015-03-05 | VICVERA BUILDERS,INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 | 1 | 60 | 3 UNITS 4STY20CL | 2014 K10 BATCH 3 | 96181903.125 |  |  | Completed | 1 |  |  | NC0214S00142 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 60 | 0
NEWCON 2014 | NCR | Muntinlupa City | 305469 | Muntinlupa Science High School | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22692343.62 |  |  | Completed | 1 | 2016-06-18 |  | NC0214S00131 | 15OI0107 | 2015-08-25 | 2015-08-19 | 2015-09-07 | 2015-09-15 | 2015-10-21 | ORANI BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Muntinlupa City | 136914 | Sucat Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | 2015-09-08 | 2015-09-08 | NC0214S00051 | 140I0099 | 2015-01-04 | 2015-01-07 | 2015-01-20 | 2015-02-06 | 2015-02-26 | REDCAR TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Muntinlupa City | 136906 | Tunasan ES | CITY OF MUNTINLUPA | 0 | 1 | 16 | 2UNITS 4STY8CL | 2014 K10 BATCH 4B | 29795037.68 |  |  | Reverted | 0 |  |  | NC0214S00144 | 15OI0164 | 2015-12-14 | 2015-12-16 | 2015-12-28 | 2016-12-29 | 2016-01-15 | ORANI BUILDERS & SUPPLY |  | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Navotas |  | Bangkulasi NHS | CITY OF NAVOTAS | 0 | 1 | 12 | 3STY 12CL | 2014 K10 BATCH 3 | 28929509.7656 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Navotas | 136858 | Dagat-dagatan Elementary School | CITY OF NAVOTAS | 0 | 1 | 6 | Micropiles | 2014 K10 BATCH 4A | 7543437.8817 |  |  | Completed | 1 | 2015-05-08 | 2015-05-08 | NC0214S00095 | 014OA0051 | 2014-12-04 | 2014-12-05 | 2014-12-09 | 2014-12-24 | 2015-01-09 | STRUKTURA TEKNIKA SERVICES CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | NCR | Navotas | 136859 | Kapitbahayan Elementary School | CITY OF NAVOTAS | 0 | 1 | 6 | Micropiles | 2014 K10 BATCH 4A | 7543437.8817 |  |  | Completed | 1 | 2015-05-08 | 2015-05-08 | NC0214S00092 | 014OA0047 | 2014-12-04 | 2014-12-05 | 2014-12-09 | 2014-12-24 | 2015-01-09 | STRUKTURA TEKNIKA SERVICES CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | 0 | 1 | 4 | cement grouting at 10 meter depth | 2014 K10 BATCH 4A | 1593230.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | 0 | 1 |  | 3STY12CL | 2014 K10 BATCH 3 | 28929509.7656 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | 0 | 1 | 0 | cement grouting at 13.5 meter depth | 2014 K10 BATCH 4A | 1433787.4509 |  |  | Completed | 1 | 2015-03-09 | 2015-03-07 | NC0214S00096 | 014OA0050 | 2014-12-04 | 2014-12-05 | 2014-12-09 | 2014-12-24 | 2015-01-09 | FEL-GENE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 22937518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | 0 | 1 |  | 3STY12CL | 2014 K10 BATCH 3 | 23904509.7656 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 3 | 28929509.7656 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Navotas | 305457 | Tangos National High School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 27397518.84 |  |  | Completed | 1 | 2016-04-23 |  | NC0214S00129 | 015OA0093 | 2015-09-18 | 2015-09-28 | 2015-10-08 | 2015-10-15 | 2015-10-27 | J. SIMEON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Navotas | 305455 | Tanza National High School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 19897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Navotas | 305455 | Tanza National High School | CITY OF NAVOTAS | 0 | 1 | 3 | cement grouting | 2014 K10 BATCH 4A | 3242509.8498 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | NCR | Parañaque City | 136754 | La Huerta ES | CITY OF PARAÑAQUE | 1 | 1 | 32 | 4STY32CL | 2014 K10 BATCH 3 | 51340935 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2014 | NCR | Parañaque City | 136757 | Paranaque Elementary School Unit II | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Parañaque City | 136756 | Paranaque ES Central | CITY OF PARAÑAQUE | 1 | 1 | 36 | 4STY24CL & 4STY/12CL | 2014 K10 BATCH 3 | 58442484.8438 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0
NEWCON 2014 | NCR | Parañaque City | 305426 | Paranaque National High School - Baclaran | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 19205522.3438 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Parañaque City | 136765 | Sto. Niño ES | CITY OF PARAÑAQUE | 1 | 1 | 12 | 4STY12CL only since a 3STY3CL bldg was already constructed at the proposed site | 2014 K10 BATCH 4B | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Parañaque City |  | Don Bosco ES (El Dorado) | CITY OF PARAÑAQUE | 2 | 1 | 24 | 4STY24CL | 2014 K10 BATCH 3 | 38430701.25 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2014 | NCR | Parañaque City |  | Marcelo Green HS | CITY OF PARAÑAQUE | 2 | 1 | 16 | 4STY16CL(open 4CL @ GF) | 2014 K10 BATCH 3 | 20768199.0547 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2014 | NCR | Parañaque City | 136758 | Sampaloc Site II ES | CITY OF PARAÑAQUE | 2 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4B | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2014 | NCR | Pasay City | 305367 | Pasay City East HS | Pasay City | 0 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | 2016-04-01 |  | NC0114S00023 | 15OH0074 | 2015-07-15 | 2015-07-27 | 2015-08-27 | 2015-08-30 | 2015-09-10 | HERBANA BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Pasay City | 319602 | Philippine National School for the Blind | Pasay City | 0 |  |  | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Pasay City | 136595 | Rivera Village ES | Pasay City | 0 | 1 | 9 | 4STY9CL (using 4STY12CL open GF) | 2014 K10 BATCH 3 | 19107283.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | NCR | Pasay City | 136601 | Timoteo Paez ES | Pasay City | 0 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 32050584.375 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2014 | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | CITY OF PASIG | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-02-23 |  | NC0214S00119 | 0150B0167 | 2015-07-01 | 2015-07-03 | 2015-07-14 | 2015-08-04 | 2015-08-27 | L.P.O. ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | NCR | Quezon City | 136490 | Balingasa Elementary School | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | 2015-10-06 | 2015-10-06 | NC0314S00021 | 14OF0130 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 136500 | Bungad ES | QUEZON CITY | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | 2015-10-07 | 2015-10-07 | NC0314S00022 | 14OF0131 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 305322 | Eulogio Rodriguez, Jr. HS | Quezon City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | 2016-04-23 |  | NC0314S00061 | 15OF0111 | 2015-07-15 | 2015-07-24 | 2015-08-05 | 2015-08-24 | 2015-08-25 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 305321 | Judge Juan Luna HS | Quezon City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 |  |  | NC0314S00067 | 15OF0123 | 2015-08-12 | 2015-08-13 | 2015-08-25 |  |  | TAPNIO AND TAN CONSTRUCTION AND DEVT. CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 136509 | Project 6 ES | QUEZON CITY | 1 | 1 | 0 | Completion of 4STY/8CL(Ramp, plumbing, sanitary & tile works(incl masonry for toilet cubicles), security grilles, railings) | 2014 K10 BATCH 4B | 364687.5 |  |  | Completed | 1 | 2015-10-25 | 2015-10-25 | NC0314S00046 | 15OF0120 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-21 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Quezon City | 305329 | Quezon City Science HS | Quezon City | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | 2016-05-23 |  | NC0314S00065 | 15OF0112 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | JYBL CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Quezon City | 136505 | San Antonio ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Quezon City | 136498 | San Francisco ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | Completed | 1 | 2016-05-23 |  | NC0314S00044 | 15OF0103 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Quezon City | 305327 | San Francisco HS | Quezon City | 1 | 1 | 16 | 4STY16CL | 2014 SHS BATCH 1 | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2014 | NCR | Quezon City | 305327 | San Francisco HS | Quezon City | 1 | 1 | 16 | 4STY16CL | 2014 SHS BATCH 1 | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2014 | NCR | Quezon City | 305324 | Sergio Osmena, Sr. HS to BALINGASA HS | Quezon City | 1 | 1 |  | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | 2016-10-12 |  | NC0314S00052 | 15OF0136 | 2015-08-18 | 2015-09-04 | 2015-09-29 | 2015-10-09 | 2015-10-13 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Quezon City | 136506 | Toro Hills ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 136506 | Toro Hills ES | QUEZON CITY | 1 | 1 | 0 | Completion of 4STY/12CL(Plumbing, sanitary & tile works, blackboards) | 2014 K10 BATCH 4B | 279375 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Quezon City | 136539 | Bagong Silangan ES | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 136539 | Bagong Silangan ES | QUEZON CITY | 2 | 1 | 0 | Completion of 4STY/8CL(Plumbing (incl. septic tank), sanitary & tile works, security grilles) | 2014 K10 BATCH 4B | 414375 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Quezon City | 305331 | Commonwealth HS | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15105522.3438 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 305331 | Commonwealth HS | Quezon City | 2 | 1 | 20 | 4STY20CL | 2014 SHS BATCH 1 | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2014 | NCR | Quezon City | 136542 | Dona Juana ES | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | 2015-12-15 | 2015-11-30 | NC0314S00026 | 14OF0133 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-12 | JAMARI CONSTRUCTION (FORMERLY FRAE CONSTRUCTION) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Quezon City | 319505 | Judge Feliciano Belmonte, Sr. HS | QUEZON CITY | 2 | 1 | 24 | 4STY16CL & 4STY8CL | 2014 K10 BATCH 3 | 42564912.9688 |  |  | Completed | 1 | 2016-08-01 |  | NC0314S00034 | 15OF0062 | 2014-12-04 | 2015-03-13 | 2015-06-03 | 2015-06-11 | 2015-06-25 | TAPNIO AND TAN CONSTRUCTION AND DEVT. CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2014 | NCR | Quezon City |  | New Holy Spirit HS (Annex) | Quezon City | 2 | 1 | 40 | 2 UNITS OF 4STY 20CL | 2014 K10 BATCH 3 | 64101168.75 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2014 | NCR | Quezon City | 136548 | Payatas B ES | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | 2015-11-08 | 2015-10-07 | NC0314S00024 | 14OF0127 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | HONEYVILLE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 136540 | Pres. Corazon C. Aquino ES (Batasan Hills ES) | QUEZON CITY | 2 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | Completed | 1 | 2016-03-06 |  | NC0314S00020 | 14OF0126 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2014 | NCR | Quezon City | 305347 | Carlos P. Garcia HS | QUEZON CITY | 3 | 1 | 8 | 4STY/8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 305347 | Carlos P. Garcia HS | Quezon City | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 136557 | Cubao ES | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4B | 26702469.42 |  |  | Completed | 1 | 2016-05-13 |  | NC0314S00048 | 15OG0088 | 2015-08-05 | 2015-08-20 | 2015-08-24 | 2015-09-01 | 2015-09-17 | RCDG CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2014 | NCR | Quezon City | 305352 | Juan Sumulong HS | Quezon City | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | 2016-02-17 |  | NC0314S00060 | 15OG0093 | 2015-08-05 | 2015-08-15 | 2015-08-24 | 2015-09-10 | 2015-09-21 | GREENWALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | NCR | Quezon City | 136565 | Teodora Alonzo ES | QUEZON CITY | 3 | 1 | 4 | 4STY4CL | 2014 K10 BATCH 3 | 10205307.6562 |  |  | Completed | 1 | 2015-04-05 | 2015-04-05 | NC0314S00019 | 14og00088 | 2014-11-07 | 2014-11-20 | 2014-11-25 | 2014-12-16 | 2014-12-19 | METRICS CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | NCR | Quezon City | 305355 | Carlos L. Albert HS | Quezon City | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Quezon City | 305362 | Dr. Josefa Jara Martinez HS | Quezon City | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | 2016-04-24 |  | NC0314S00058 | 15OG0100 | 2015-08-20 | 2015-09-01 | 2015-09-07 | 2015-09-22 | 2015-09-28 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Quezon City | 305361 | Manuel Roxas HS | Quezon City | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | 2016-06-06 |  | NC0314S00057 | 15-OG084 | 2015-07-28 | 2015-08-07 | 2015-10-20 | 2015-11-02 | 2015-11-06 | ST. GERRARD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Quezon City | 305356 | Ponciano Bernardo HS | Quezon City | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | 2016-03-19 |  | NC0314S00056 | 15-OG083 | 2015-07-27 | 2015-08-10 | 2015-08-10 | 2015-08-29 | 2015-09-01 | GRAIA CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 305359 | Quezon City HS | Quezon City | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | 2016-03-02 |  | NC0314S00053 | 15OG-0085 | 2015-07-22 | 2015-08-08 | 2015-08-10 | 2015-09-01 | 2015-09-04 | E.A. RAMIREZ CONSTRUCTION, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 136527 | Dona Rosario Elementary School | Quezon City | 5 | 1 | 0 | Completion of 4STY/8CL(2 units toilets, catch basins, electric fans, security grilles) | 2014 K10 BATCH 4B | 398437.5 |  |  | Completed | 1 | 2015-10-25 | 2015-10-25 | NC0314S00039 | 15OF0120 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-21 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Quezon City | 319504 | Dona Rosario HS | Quezon City | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | 2015-10-08 | 2015-10-08 | NC0314S00032 | 14OF0125 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | JYBL CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 136534 | Lagro ES | Quezon City | 5 | 1 | 3 | Completion of 3STY 9CL: 3CL at 3rd Floor (masongry, carpentry. Electrical, painting), roofing and steel works, plumbing and sanitary works. Security grilles for the whole building | 2014 K10 BATCH 4A | 3718500 |  |  | Completed | 1 | 2015-04-11 | 2015-05-11 | NC0314S00035 | 14OF0047 | 2014-11-28 | 2014-11-29 | 2014-12-04 | 2014-12-28 | 2015-01-06 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | NCR | Quezon City | 305336 | Lagro HS | Quezon City | 5 | 1 | 0 | Completion of 4STY/16CL (Finishing work, plumbing, sanitary, tile works, cubicles, septic tank, security grills) | 2014 K10 BATCH 4B | 564375 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Quezon City | 136535 | Maligaya ES | Quezon City | 5 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4B | 26702469.42 |  |  | Completed | 1 | 2016-06-28 |  | NC0314S00040 | 15OF0106 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | R.D. MANDANAS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2014 | NCR | Quezon City | 305338 | Maligaya HS | Quezon City | 5 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Quezon City | 136537 | North Fairview ES | Quezon City | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | Completed | 1 | 2016-05-17 |  | NC0314S00049 | 15OF0108 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | E.A. RAMIREZ CONSTRUCTION, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 136523 | Odelco ES | Quezon City | 5 | 1 | 4 | 4STY4CL | 2014 K10 BATCH 3 | 10205307.6562 |  |  | Completed | 1 | 2015-07-10 | 2015-09-07 | NC0314S00030 | 14OF0123 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | TAPNIO AND TAN CONSTRUCTION AND DEVT. CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | NCR | Quezon City | 136528 | Rosa L. Susano - Novaliches ES | Quezon City | 5 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4B | 31102890.27 |  |  | Completed | 1 | 2016-08-27 |  | NC0314S00047 | 15OF0107 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | MPJR BUILDERS COMPANY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2014 | NCR | Quezon City | 136538 | San Agustin ES | Quezon City | 5 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | 2015-11-07 | 2015-11-05 | NC0314S00031 | 14OF0124 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | PRISMODIAL CONSTRUCTION CORPORATION (FOR. PRISMODI |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Quezon City | 136529 | San Gabriel ES | Quezon City | 5 | 1 | 0 | Completion of 4STY/12CL(Plumbing, sanitary & tile works (incl masonry for cubicles), septic tank, security grilles) | 2014 K10 BATCH 4B | 564375 |  |  | Completed | 1 | 2015-10-25 | 2015-10-25 | NC0314S00041 | 15OF0120 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-21 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Quezon City | 305342 | Sta. Lucia HS | Quezon City | 5 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | 2016-10-22 |  | NC0314S00055 | 15OF0143 | 2015-08-18 | 2015-09-04 | 2015-09-29 | 2015-10-06 | 2015-10-22 | JYBL CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Quezon City | 222501 | West Fairview Elementary School | Quezon City | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | Completed | 1 | 2016-04-29 |  | NC0314S00042 | 15OF0109 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | MPJR BUILDERS COMPANY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 305335 | Ismael Mathay, Sr. HS | Quezon City | 6 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | 2016-04-30 |  | NC0314S00054 | 15OF0114 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | M O M ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 136522 | Leopoldo B. Santos ES | Quezon City | 6 | 1 | 8 | 4STY/8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | 2015-10-08 | 2015-10-08 | NC0314S00033 | 14OF0122 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | HONEYVILLE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Quezon City | 136524 | Placido del Mundo ES | Quezon City | 6 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | Completed | 1 | 2016-04-30 |  | NC0314S00037 | 15OF0110 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-28 | MPJR BUILDERS COMPANY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 320607 | Agripino Manalo National HS | Taguig City & Pateros | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Reverted | 0 |  |  | NC0214S00120 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 136894 | Capt. H. Francisco ES Annex | Pateros | 1 | 1 | 12 | 4STY 12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 136883 | Cipriano P. Sta. Teresa Elementary School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 136871 | Ciriaco P. Tiñga Elementary School | TAGUIG CITY | 1 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 305467 | Maria Concepcion Cruz HS | Taguig City & Pateros | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Reverted | 0 |  |  | NC0214S00121 | 0150B0164 | 2015-07-05 | 2015-07-06 | 2015-07-16 | 2015-07-31 |  | ORANI BUILDERS & SUPPLY |  | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 136874 | Napindan Elementary School | TAGUIG CITY | 1 | 1 | 24 | 4STY24CL | 2014 K10 BATCH 3 | 38430701.25 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | PATEROS | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | 2015-09-12 |  | NC0214S00048 | 0140B0253 | 2014-12-10 | 2014-12-11 | 2014-12-23 | 2015-01-16 | 2015-02-14 | E.R. VENZON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 305460 | Taguig National High School | Taguig City & Pateros | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | 2016-06-05 |  | NC0214S00122 | 0150B0271 | 2015-08-13 | 2015-08-17 | 2015-08-27 | 2015-09-18 | 2015-10-07 | R.T. MORABE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 305464 | Tipas National High School | Taguig City & Pateros | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | 2016-06-13 |  | NC0214S00124 | 0150B0303 | 2015-10-08 | 2015-10-09 | 2015-10-22 | 2015-11-10 | 2015-11-16 | R.S. MESA CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Taguig City & Pateros |  | DepED Property | Taguig- Pateros | 2 | 1 | 24 | 2 Units 4STY 12CL(elevated @ 1.5m) | 2014 K10 BATCH 3 | 44137296.8717 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 320602 | Maria Asuncion Rodriguez Tiñga High School | Taguig City & Pateros | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Reverted | 0 | 2016-03-05 |  | NC0214S00125 | 015B0164 | 2015-07-01 | 2015-07-03 | 2015-07-14 | 2015-08-04 | 2015-09-07 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 305463 | Signal Village NHS | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | NCR | Taguig City & Pateros | 305465 | Western Bicutan NHS | TAGUIG CITY | 2 | 1 | 7 | 4STY7CL (with 1 stair open below 1cl) | 2014 K10 BATCH 3 | 15064922.3438 |  |  | Completed | 1 | 2016-03-12 |  | NC0214S00034 | 0140B0254 | 2014-12-10 | 2014-12-11 | 2014-12-23 | 2015-01-06 | 2015-01-07 | HONY TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0
NEWCON 2014 | NCR | Valenzuela City | 320404 | Bignay NHS | CITY OF VALENZUELA | 1 | 1 | 0 | Completion of 4STY8CL | 2014 K10 BATCH 4B | 1363279.6969 |  |  | Completed | 1 | 2015-10-18 |  |  |  | 2015-07-22 |  | 2015-08-18 |  |  | C.B. Tampengco Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Valenzuela City | 320404 | Bignay NHS | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14907518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Valenzuela City | 136802 | Coloong ES | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Valenzuela City | 305440 | Lawang Bato NHS | CITY OF VALENZUELA | 1 | 1 | 3 | 3STY3CL | 2014 K10 BATCH 3 | 7323603.6328 |  |  | Completed | 1 | 2015-09-24 | 2015-09-10 | NC0214S00040 | 14OD0077 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-25 | 2015-02-27 | R.D. TALENS CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | NCR | Valenzuela City | 136797 | Malinta ES | CITY OF VALENZUELA | 1 | 1 | 8 | Completion of 3STY12CL (incl. finishing works, toilets, roofing, carpentry) | 2014 K10 BATCH 4B | 4523437.5 |  |  | Completed | 1 | 2015-12-02 |  | NC0214S00111 | 15OD0065 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-18 | 2015-09-04 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Valenzuela City | 305438 | Malinta NHS | Valenzuela City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14907518.84 |  |  | Completed | 1 |  |  | NC0214S00138 | 15OD0101 | 2015-10-07 | 2015-10-19 | 2015-10-20 | 2015-10-26 | 2015-11-17 | CARDRIAN BUILDERS CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Valenzuela City | 136806 | Pasolo ES | CITY OF VALENZUELA | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14195118.4009 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | NCR | Valenzuela City | 136807 | Pio Valenzuela ES | CITY OF VALENZUELA | 1 | 1 | 8 | Completion of 3STY12CL(construction of remaining 8CL) | 2014 K10 BATCH 4B | 5533060.275 |  |  | Completed | 1 | 2016-01-01 |  | NC0214S00110 | 15OD0071 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-18 | 2015-09-04 | LARSEN-DUTCHER CONSTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Valenzuela City | 136812 | Roberta de Jesus ES | CITY OF VALENZUELA | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | Completed | 1 | 2016-02-17 |  | NC0214S00116 | 15OD0074 | 2015-08-14 | 2015-08-26 | 2015-08-27 | 2015-09-04 | 2015-09-21 | CARDRIAN BUILDERS CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | NCR | Valenzuela City | 320402 | Vicente Trinidad NHS (Punturin NHS) | CITY OF VALENZUELA | 1 | 1 | 0 | Completion of 4STY8CL | 2014 K10 BATCH 4B | 1382887.575 |  |  | Completed | 1 | 2015-10-18 | 2015-10-16 | NC0214S00118 | 15OD0067 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-16 | 2015-09-04 | J. SIMEON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2014 | NCR | Valenzuela City | 136811 | WawangPulo ES | CITY OF VALENZUELA | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10817093.5547 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | NCR | Valenzuela City | 320407 | Wawangpulo National High School | Valenzuela City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14907518.84 |  |  | Completed | 1 |  |  | NC0214S00127 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | NCR | Valenzuela City | 136822 | Caruhatan West ES | CITY OF VALENZUELA | 2 | 1 | 2 | Completion of 3STY/6CL | 2014 K10 BATCH 4B | 2863237.8662 |  |  | Completed | 1 | 2015-11-17 |  | NC0214S00115 | 15OD0064 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-18 | 2015-11-05 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | NCR | Valenzuela City | 136825 | Marulas Central ES | CITY OF VALENZUELA | 2 | 1 | 0 | Completion of 4STY/8CL & 3STY/9CL | 2014 K10 BATCH 4B | 1274735.0159 |  |  | Completed | 1 | 2015-11-02 | 2015-11-02 | NC0214S00109 | 15OD0066 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-17 | 2015-09-04 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.