## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | No. of Classrooms | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated | Previous % | Difference | STOREY | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | Status as of July 4, 2025
NEWCON 2017 | REGION I | ILOCOS NORTE | 100216 | AB-ABUT ES | PIDDIG | 1 | 1 | 2 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100217 | ABUCAY ES | PIDDIG | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 10854421.2 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100218 | BOYBOY ES | PIDDIG | 1 | 1 | 4 | 1STY4CL | BATCH 14 | 4903351.15 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100219 | CALAMBEG E/S | PIDDIG | 1 | 1 | 3 | 1STY3CL | BATCH 14 | 3788435.02 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100221 | DUPITAC E/S | PIDDIG | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 8158972.094 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100222 | ESTANCIA ES | PIDDIG | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 10944421.2 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100223 | Gayamat PS | PIDDIG | 1 |  | 4 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100224 | Lagandit ES | PIDDIG | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 10884421.2 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100225 | Libnaoan ES | PIDDIG | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 10904421.2 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100227 | Piddig Central ES | PIDDIG | 1 | 1 | 10 | 2STY10CL | BATCH 14 | 18046128.7 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100228 | PIDDIG SOUTH CES | PIDDIG | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 10854421.2 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100229 | San Antonio ES | PIDDIG | 1 | 1 | 5 | 1STY5CL | BATCH 14 | 6122650.72 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100230 | Sta. Maria ES | PIDDIG | 1 | 1 | 4 | 1STY2CL | BATCH 14 | 2643745.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100231 | TANGAOAN ES | PIDDIG | 1 |  | 6 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2017 | REGION I | ILOCOS NORTE | 100232 | TONOTON E/S | PIDDIG | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 10854421.2 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Alaminos City | 300155 | Alaminos City Nhs | City Of Alaminos | 1 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62505780.54 |  |  | Completed | 1 | [7 empty] | JUNE 17, 2016 | BERSON CONSTRUCTION | JANUARY 28, 2017 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION I | Alaminos City | 300155 | Alaminos City Nhs | City Of Alaminos | 1 |  | 16 | 4STY8CL | BATCH 5 CL | 30295037.68 |  |  | Completed | 1 | [7 empty] | JUNE 17, 2016 | BERSON CONSTRUCTION | DECEMBER 14, 2016 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | Alaminos City | 300208 | Inerangan Nhs | City Of Alaminos | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1 | [7 empty] | 2016-05-16 | ALCEL CONSTRUCTION | JANUARY 17, 2017 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Alaminos City | 300253 | San Vicente Nhs | City Of Alaminos | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12771310.09 |  |  | Completed | 1 | [7 empty] | 2017-05-26 | BERSON CONSTRUCTION | JANUARY 20, 2017 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION I | Alaminos City | 300253 | San Vicente Nhs | City Of Alaminos | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2430000 |  |  | Completed | 1 | [7 empty] | JUNE 22, 2016 | CHIARA CONSTRUCTION | DECEMBER 19, 2016 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Alaminos City | 300260 | Telbang Nhs | City Of Alaminos | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15121327.92 |  |  | Completed | 1 | [7 empty] | JUNE 22, 2016 | SMANTHA CONSTRUCTION | SEPTEMBER 19, 2016 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Batac City | 300005 | Batac National High School | City Of Batac | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22652343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Batac City | 300005 | Batac National High School | City Of Batac | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Batac City | 320803 | Batac Nhs (Payao Campus) | City Of Batac | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Batac City | 320804 | Batac Nhs (Poblacion Campus) | City Of Batac | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Batac City | 100092 | Bil-Loca Es | City Of Batac | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Batac City | 300012 | Crispina Marcos Valdez Nhs | City Of Batac | 2 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Batac City | 300012 | Crispina Marcos Valdez Nhs | City Of Batac | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Candon City | 300047 | Candon City High School | City Of Candon | 2 | 1 | 12 | 2STY12CL | BATCH 3 CL | 14724000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Candon City | 300044 | Candon National High School | Candon City | 2 | 1 | 40 | 4STY20CL | BATCH 1 CL | 62305780.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION I | Candon City | 300044 | Candon National High School | Candon City | 2 |  | 4 | 2STY4CL | BATCH 1 CL | 6332000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Candon City | 300051 | Dr. Ricardo Gacula Memorial National High School | City Of Candon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2770000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Candon City | 300083 | Sto. Tomas National High School | City Of Candon | 2 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15122000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Dagupan City | 305502 | Federico N. Ceralde Is | Dagupan City | 4 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15171327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Dagupan City | 500055 | Pugaro Is | Dagupan City | 4 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15221327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 100043 | Abaca Es | Bangui | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300001 | Adams National High School | Adams | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6469337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300002 | Bacarra Nchs | Bacarra | 1 | 1 | 32 | 4STY32CL | BATCH 1 CL | 44532220.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300002 | Bacarra Nchs | Bacarra | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2804549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320801 | Banban Nhs | Bangui | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 100047 | Bangui Ces | Bangui | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320802 | Bangui Nhs (Lanao Campus) | Bangui | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300006 | Burgos Agro-Industrial School | Burgos | 1 | 1 | 20 | 2STY10CL | BATCH 7 CL | 25542620.18 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300007 | Cadaratan National High School | Bacarra | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300009 | Carasi Nhs | Carasi | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2313627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300014 | Davila National High School | Pasuquin | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300017 | Dumalneg Nhs | Dumalneg | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300017 | Dumalneg Nhs | Dumalneg | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320827 | Florentino Camaquin Integrated School | Vintar | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.5917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320827 | Florentino Camaquin Integrated School | Vintar | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | Pasuquin | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | Pasuquin | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320821 | Isic-Isic Nhs | Vintar | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1914740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300019 | Luzong Nhs | Pagudpud | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12821310.093 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300024 | Pagudpud Nhs | Pagudpud | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12821310.093 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300024 | Pagudpud Nhs | Pagudpud | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2288627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320819 | Pallas Integrated School | Vintar | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10952342.5917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320825 | Pandan Is | Sarrat | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 100208 | Pasuquin Central Elementary School | Pasuquin | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300016 | Piddig National High School | Piddig | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.093 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300016 | Piddig National High School | Piddig | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 100303 | Sagpat Es | Vintar | 1 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1012049.65 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320822 | Salpad Integrated School | Vintar | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6369337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 150009 | San Pedro Elementary School | Sarrat | 1 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1012049.65 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300029 | Sarrat National High School | Sarrat | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300029 | Sarrat National High School | Sarrat | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320816 | Sta. Rosa National High School | Sarrat | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320816 | Sta. Rosa National High School | Sarrat | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300031 | Vintar Nhs | Vintar | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6394337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300031 | Vintar Nhs | Vintar | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2313627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320820 | Adriano P. Arzadon Nhs | Nueva Era | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 100025 | Badoc North Central School | Badoc | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300004 | Banna National High School | Banna (Espiritu) | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320815 | Bingao National High School | San Nicolas | 2 | 1 | 10 | 2STY10CL | BATCH 5 CL | 13217082.76 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320815 | Bingao National High School | San Nicolas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300008 | Caestebanan Nhs | Banna (Espiritu) | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15221327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300008 | Caestebanan Nhs | Banna (Espiritu) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2708700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320826 | Caraitan Integrated School | Badoc | 2 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8914965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300010 | Caribquib Nhs | Banna (Espiritu) | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300011 | Catagtaguen Nhs | Banna (Espiritu) | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300011 | Catagtaguen Nhs | Banna (Espiritu) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300013 | Currimao Nhs | Currimao | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320805 | Currimao Nhs (Pias-Gaang Campus) | Currimao | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 24002343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 100120 | Dingras Central Es | Dingras | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300015 | Dingras Nhs/Lt. Edgar Foz Mem. Nhs | Dingras | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300015 | Dingras Nhs/Lt. Edgar Foz Mem. Nhs | Dingras | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320806 | Dingras Nhs/Lt. Edgar Foz Mem. Nhs (Barong Campus) | Dingras | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11402342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320808 | Dingras Nhs/Lt. Edgar Foz Mem. Nhs (San Marcos Campus) | Dingras | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320809 | Dingras Nhs/Lt. Edgar Foz Mem. Nhs- (Sulquiano Campus) | Dingras | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 100147 | Ferdinand Es | Marcos | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 100031 | Lasien School | Badoc | 2 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2790828.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320823 | Malaguip Integrated School | Paoay | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300020 | Marcos Nhs | Marcos | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320811 | Marcos Nhs (Agunit Campus) | Marcos | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320812 | Marcos Nhs (Santiago Campus) | Marcos | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320812 | Marcos Nhs (Santiago Campus) | Marcos | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 150003 | Nagbacalan West Elelementary School | Paoay | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300021 | Nagrebcan Nhs | Badoc | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11402342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 100154 | Nueva Era Central Elementary School | Nueva Era | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300022 | Nueva Era National High School | Nueva Era | 2 | 1 | 10 | 2STY10CL | BATCH 5 CL | 13217082.76 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300023 | Pagsanahan Nhs | Badoc | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300025 | Paoay Lake Nhs | Paoay | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11402342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320814 | Paoay National High School | Paoay | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11402342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300027 | Pinili Nhs | Pinili | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11402342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320824 | Sacritan Integrated School | Pinili | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320807 | San Marcelino National High School | Dingras | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300028 | San Nicolas Nhs | San Nicolas | 2 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 300030 | Solsona National High School, Maananteng Campus | Solsona | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 24002343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320817 | Solsona Nhs (Bagbag Campus) | Solsona | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320818 | Solsona Nhs (Talugtog Campus) | Solsona | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320818 | Solsona Nhs (Talugtog Campus) | Solsona | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320810 | Suyo National High School | Dingras | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320810 | Suyo National High School | Dingras | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 100041 | Turod Es | Badoc | 2 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1012049.65 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Norte | 320828 | Uguis Integrated School | Nueva Era | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6329337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300045 | Caoayan Nhs | Caoayan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300057 | Magsingal Nhs | Magsingal | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300058 | Manzante Nhs | Magsingal | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300035 | San Juan Nhs | San Juan (Lapog) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2497016.25 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 500349 | Ambalayat Is | Tagudin | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300041 | Burgos Nhs | Burgos | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300050 | Dinaratan National High School | Salcedo (Baugen) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2515000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300063 | Narvacan Nat'L. Central Hs | Narvacan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300063 | Narvacan Nat'L. Central Hs | Narvacan | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300070 | Quirino Nhs | Quirino (Angkaki) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2530000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300077 | Santa Maria Nhs | Santa Maria | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300077 | Santa Maria Nhs | Santa Maria | 2 |  | 12 | 4STY12CL | BATCH 9 CL | 22302343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300077 | Santa Maria Nhs | Santa Maria | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300036 | Sugpon Nhs | Sugpon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2510000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300085 | Suyo Nhs | Suyo | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300086 | Tagudin Nhs | Tagudin | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300086 | Tagudin Nhs | Tagudin | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1 | [9 empty] | 739 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | Ilocos Sur | 300072 | Teodoro Hernaez Nhs | Santa Lucia | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22302343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | La Union | 300114 | Doña Francisca Lacsamana De Ortega Memorial National High School | Bangar | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22850000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | La Union | 321018 | Luna National Vocational High School | Luna | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | La Union | 300120 | Luna Nhs | Luna | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22850000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | La Union | 101071 | San Juan Ces | San Juan | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | La Union | 300093 | Aringay Nhs | Aringay | 2 | 1 | 8 | 4STY8CL | BATCH 7 CL | 15150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | La Union | 300094 | Baccuit Nhs | Bauang | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6800000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | La Union | 300105 | Cambaly Nhs | Bagulin | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 7450000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | La Union | 321020 | Casilagan Integrated School | Bauang | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6800000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | La Union | 300109 | Damortis Nhs | Santo Tomas | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15750000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | La Union | 321022 | Daramuangan Integrated School | Naguilian | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6800000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | La Union | 300130 | Don Eufemio F. Eriguel Mnhs | Agoo | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | La Union | 300112 | Don Eulogio De Guzman Mnhs | Bauang | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | La Union | 300122 | Naguilian National Hs | Naguilian | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | La Union | 300133 | Rosario Integrated School | Rosario | 2 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | La Union | 300138 | San Luis Nhs | Pugo | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6850000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | La Union | PSA328391 | Shs In Aringay, La Union | Aringay | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22317774.775 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | La Union | PSA328392 | Shs In Naguilian, La Union | Naguilian | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | La Union | 300150 | Tagudtud Nhs | Bagulin | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | La Union | 300151 | Tanglag Nhs | Rosario | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6800000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | La Union | 300152 | Tubao National High School | Tubao | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | La Union | 300153 | Wenceslao National Hs | Caba | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6800000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Laoag City | 305602 | Balatong Integrated School | Laoag City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Laoag City | 102189 | Darayday Es | Laoag City (Capital) | 1 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1012049.6543 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Laoag City | 300372 | Gabu Nhs | Laoag City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Laoag City | 300373 | Ilocos Norte College Of Arts & Trades | Laoag City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 11 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | Laoag City | 300373 | Ilocos Norte College Of Arts & Trades | Laoag City (Capital) | 1 |  | 16 | 4STY8CL | BATCH 11 CL | 29795037.68 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | Laoag City | 300374 | Ilocos Norte Nhs | Laoag City (Capital) | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | Laoag City | 300374 | Ilocos Norte Nhs | Laoag City (Capital) | 1 |  | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | Laoag City | 300374 | Ilocos Norte Nhs | Laoag City (Capital) | 1 |  | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Laoag City | 305601 | Ilocos Norte Nhs - Caaoacan Annex | Laoag City (Capital) | 1 | 1 | 6 | 1STY6CL | BATCH 5 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Laoag City | 300375 | Ilocos Norte Regional School Of Fisheries | Laoag City (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Laoag City | 300375 | Ilocos Norte Regional School Of Fisheries | Laoag City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2363000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321131 | Anda Integrated School | Anda | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | 16AG0050 | [5 empty] | 42503 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321106 | Bacnit Integrated School | Mabini | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 |  |  | 16AG0049 | [5 empty] | 42503 | CASIPIT CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300161 | Balingasay Nhs | Bolinao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 |  |  | 16AG0087 | [5 empty] | 42225 | JONIK TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321126 | Barlo Integrated School | Mabini | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300169 | Bayambang Nhs (Infanta) | Infanta | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | 16AG0051 | [5 empty] | 42503 | CASIPIT CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321117 | Bolinao Integrated School | Bolinao | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 |  |  | 16AG0056 | [5 empty] | 42503 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300179 | Burgos Nhs | Burgos | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1 |  |  | 16AG0059 | [5 empty] | 42503 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300180 | Cabanaetan Nhs | Mabini | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | 16AG0057 | [5 empty] | 42503 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300189 | Cato Nhs | Infanta | 1 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321111 | Catubig Integrated School | Bolinao | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | 16AG0086 | [5 empty] | 42591 | JONIK TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300201 | Eguia National High School | Dasol | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 |  |  | 16AG0053 | [5 empty] | 42503 | JONIK TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321127 | Gayusan Integrated School | Agno | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | 16AG0055 | [5 empty] | 42503 | BERSONs CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321109 | Liwa Liwa Integrated School | Bolinao | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | 16AG0075 | [5 empty] | 42503 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300215 | Luna National High School | Bolinao | 1 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  | 16AG0085 | [5 empty] | 42591 | SAMANTHA ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300221 | Malimpin Nhs | Dasol | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | 16AG0054 | [5 empty] | 42503 | JASA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321104 | Pangascasan Integrated School | Sual | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | 16AG0052 | [5 empty] | 42503 | JONIK TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300255 | Sual National High School | Sual | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | 16AG0083 | [6 empty] | R.A.Matias |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321108 | Tupa Integrated School | Bolinao | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | 16AG0084 | [6 empty] | R.A.Matias |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321128 | Aguilar Integrated School | Aguilar | 2 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321128 | Aguilar Integrated School | Aguilar | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4860000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 500374 | Ambayat Is | Aguilar | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300167 | Basista Nhs | Basista | 2 | 1 | 32 | 4STY16CL | BATCH 3 CL | 53404938.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300232 | Binmaley Sof (Pangasinan Cof) | Binmaley | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321107 | Bugallon Is | Bugallon | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321107 | Bugallon Is | Bugallon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321113 | Dalanguiring Is | Urbiztondo | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321114 | Domalandan Center Is | Lingayen (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300199 | Dulag National High School | Binmaley | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2460000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300202 | Enrico T. Prado Nhs | Aguilar | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300203 | Estanza Nhs | Lingayen (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300204 | Galarin National High School | Urbiztondo | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300209 | Labrador Nhs | Labrador | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300209 | Labrador Nhs | Labrador | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300218 | Macarang National High School | Mangatarem | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 101377 | Magsaysay Elementary School | Bugallon | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321118 | Malawa Is | Lingayen (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300222 | Mangatarem Nhs | Mangatarem | 2 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300222 | Mangatarem Nhs | Mangatarem | 2 |  | 4 | 2STY4CL | BATCH 3 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321132 | Mapita Integrated School | Aguilar | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1864740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | Lingayen (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | Lingayen (Capital) | 2 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | Lingayen (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300234 | Pangasinan Sat | Lingayen (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300241 | Polong National High School | Bugallon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300247 | Real National High School | Urbiztondo | 2 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300248 | Salomague Nhs | Bugallon | 2 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321115 | Urbiztondo Integrated School | Urbiztondo | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 321115 | Urbiztondo Integrated School | Urbiztondo | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300168 | Bayambang Nhs (Bayambang) | Bayambang | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300176 | Botao Nhs | Santa Barbara | 3 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300177 | Bued National High School | Calasiao | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300177 | Bued National High School | Calasiao | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300183 | Calasiao Comprehensive Nhs | Calasiao | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28007601.243 |  |  | Completed | 1 |  |  | 16AJ0064 | [6 empty] | T.J VELASCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300193 | Daniel Maramba Nhs | Santa Barbara | 3 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  | 16AJ0065 | [6 empty] | CAD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300193 | Daniel Maramba Nhs | Santa Barbara | 3 |  | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 |  |  | 16AJ0066 | [6 empty] | KENWOOD CONSTRUCTION ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300193 | Daniel Maramba Nhs | Santa Barbara | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300197 | Don Pedro National High School | Malasiqui | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300197 | Don Pedro National High School | Malasiqui | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300216 | Lunec Nhs | Malasiqui | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300220 | Malasiqui Nhs | Malasiqui | 3 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300220 | Malasiqui Nhs | Malasiqui | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300224 | Mapandan National High School | Mapandan | 3 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300225 | Matic-Matic Nhs | Santa Barbara | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300188 | Moises B. Rebamontan Nhs | Bayambang | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300259 | Tanolong National High School | Bayambang | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 |  |  | 16AJ0061 | [6 empty] | KENWOOD CONSTRUCTION ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300263 | Tococ National High School | Bayambang | 3 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | 16AJ0059 | [6 empty] | KENWOOD CONSTRUCTION ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300265 | Torres Nhs | Mapandan | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1 |  |  | 16AJ0060 | [6 empty] | ORIENTAL SALES CENTER & CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan I, Lingayen | 300265 | Torres Nhs | Mapandan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300274 | Anonang Nhs | San Fabian | 4 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300280 | Baguinay Nhs | Manaoag | 4 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 152001 | Bisbisocol Es | San Fabian | 4 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1135000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 321220 | Gueguesangen Is | Mangaldan | 4 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300323 | Mabilao Nhs | San Fabian | 4 | 1 | 24 | 4STY12CL | BATCH 7 CL | 44304687.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300325 | Manaoag Nhs | Manaoag | 4 | 1 | 60 | 4STY20CL | BATCH 9 CL | 93308670.81 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 60 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300325 | Manaoag Nhs | Manaoag | 4 |  | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 500383 | Mangaldan Is | Mangaldan | 4 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300326 | Mangaldan Nhs | Mangaldan | 4 | 1 | 24 | 4STY24CL | BATCH 7 CL | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300326 | Mangaldan Nhs | Mangaldan | 4 |  | 24 | 4STY12CL | BATCH 7 CL | 44304687.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300315 | San Fabian Integrated School | San Fabian | 4 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300345 | San Fabian Nhs | San Fabian | 4 | 1 | 24 | 4STY24CL | BATCH 9 CL | 39140882.854 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300345 | San Fabian Nhs | San Fabian | 4 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300348 | San Jacinto National High School | San Jacinto | 4 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300271 | Amamperez Agro-Industrial Hs | Villasis | 5 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300275 | Antonio P. Villar National High School | Santo Tomas | 5 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300276 | Arboleda Nhs | Alcala | 5 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 321204 | Bantay Insik Integrated School | Sison | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 321204 | Bantay Insik Integrated School | Sison | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300284 | Barangobong Nhs | Villasis | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300286 | Bautista Nhs | Bautista | 5 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300286 | Bautista Nhs | Bautista | 5 |  | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300287 | Benigno V. Aldana Nhs | Pozzorubio | 5 | 1 | 40 | 4STY20CL | BATCH 9 CL | 68396358.594 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300301 | Cipriano P. Primicias Nhs | Alcala | 5 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300308 | Don Ramon E. Costales Mnhs | Villasis | 5 |  | 16 | 4STY16CL | BATCH 9 CL | 24047222.478 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300308 | Don Ramon E. Costales Mnhs | Villasis | 5 |  | 8 | 4STY8CL | BATCH 9 CL | 13913507.9237 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300308 | Don Ramon E. Costales Mnhs | Villasis | 5 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 321205 | Don Valentin Torres Integrated School | Sison | 5 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300311 | Eugenio P. Perez Nhs | Pozzorubio | 5 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300307 | Juan G. Macaraeg Nhs | Binalonan | 5 | 1 | 40 | 4STY20CL | BATCH 9 CL | 68396358.594 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300334 | Piaz National High School | Villasis | 5 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 321203 | San Antonio Nhs | Santo Tomas | 5 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300346 | San Felipe National High School | Binalonan | 5 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 500375 | Sison Central Is | Sison | 5 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300362 | Sumabnit National High School | Binalonan | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300366 | Unzad Nhs | Villasis | 5 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101887 | Acop Es | Rosales | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300273 | Angela Valdez Ramos Nhs | Asingan | 6 | 1 | 18 | 3STY9CL | BATCH 7 CL | 30242655.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300273 | Angela Valdez Ramos Nhs | Asingan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101729 | Balungao Cs | Balungao | 6 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300281 | Balungao Nhs | Balungao | 6 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102094 | Bantug Es | Umingan | 6 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102095 | Baracbac Elementary School | Umingan | 6 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300283 | Baracbac Nhs | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102002 | Cabalaoangan Es | San Quintin | 6 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12898000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101876 | Cabalaoangan Es | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101969 | Cabayawasan Es | San Nicolas | 6 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1221000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300296 | Cacabugaoan Nhs | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101710 | Calepaan Comm. Sch. | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101877 | Camangaan Es | Rosales | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101891 | Capitan Tomas Pine Es | Rosales | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101730 | Capulaan Es | Balungao | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101892 | Carmay Elementary School | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101878 | Carmen Elementary School | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102098 | Carosalesan Es | Umingan | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1110000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300303 | Dalumpinas Nhs | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 152007 | Decreto Community School | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101714 | Domanpot Es | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6473000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101714 | Domanpot Es | Asingan | 6 |  | 8 | 2STY8CL | BATCH 13 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102004 | Don Luis Domingo Sr. Es | San Quintin | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1110000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102105 | Don Montano Elementary School | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101987 | East Central School | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300309 | Eastern Pangasinan Agricultural College | Santa Maria | 6 | 1 | 16 | 2STY8CL | BATCH 13 CL | 21970000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300309 | Eastern Pangasinan Agricultural College | Santa Maria | 6 |  | 2 | 1STY1CL | BATCH 13 CL | 2226509.2394 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102070 | Evangelista Es | Tayug | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300312 | Flores Integrated School | San Manuel | 6 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300312 | Flores Integrated School | San Manuel | 6 |  | 6 | 3STY6CL | BATCH 13 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300312 | Flores Integrated School | San Manuel | 6 |  | 2 | 1STY1CL | BATCH 13 CL | 2226509.2394 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300313 | Flores Nhs | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102005 | Gonzalo Es | San Quintin | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300314 | Guiling-Coliling Nhs | Rosales | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101953 | Juan C. Laya Memorial School | San Manuel | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101733 | Kita-Kita Es | Balungao | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101988 | Kulangew Elementary School | San Nicolas | 6 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1221000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101955 | Lapalo Es | San Manuel | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102064 | Legaspi Elementary School | Tayug | 6 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101894 | Li Seng Giap Es | Rosales | 6 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2132466.644 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300322 | Luciano Millan National Hs | Asingan | 6 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300322 | Luciano Millan National Hs | Asingan | 6 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 321214 | Lumayao Integrated School | San Quintin | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300324 | Malico Nhs | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6432000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300327 | Maseil-Seil Alo-O Nhs | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300328 | Mataas Na Paaralang Juan C. Laya | San Manuel | 6 | 1 | 28 | 4STY28CL | BATCH 13 CL | 40067946.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300328 | Mataas Na Paaralang Juan C. Laya | San Manuel | 6 |  | 9 | 3STY9CL | BATCH 13 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300328 | Mataas Na Paaralang Juan C. Laya | San Manuel | 6 |  | 1 | 1STY1CL | BATCH 13 CL | 1113254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101715 | Narciso R. Ramos Es Sped Center | Asingan | 6 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101837 | Natividad Cs | Natividad | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6473000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101837 | Natividad Cs | Natividad | 6 |  | 8 | 2STY8CL | BATCH 13 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300331 | Natividad Nhs | Natividad | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102111 | Pangangaan Es | Umingan | 6 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300333 | Panganiban Nhs | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300333 | Panganiban Nhs | Tayug | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102090 | Papallasen Es | Umingan | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102048 | Pugot Elementary School | Santa Maria | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1110000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101993 | Puyao Es | San Nicolas | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1873000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101882 | Rabago Es | Rosales | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101895 | Rizal Es | Rosales | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300340 | Robert B. Estrella Memorial Nhs | Rosales | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300341 | Rosales Nhs | Rosales | 6 | 1 | 60 | 4STY20CL | BATCH 9 CL | 93308670.81 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 60 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101738 | San Aurelio 3Rd Es | Balungao | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1110000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300344 | San Aurelio Nhs | Balungao | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101960 | San Bonifacio Es | San Manuel | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 500379 | San Felipe Is | San Nicolas | 6 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300347 | San Isidro Nhs | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300347 | San Isidro Nhs | San Nicolas | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300350 | San Leon Nhs | Balungao | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300351 | San Luis Nhs | Rosales | 6 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300352 | San Macario Nhs | Natividad | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101743 | San Marcelino Es | Balungao | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1958000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300353 | San Miguel Nhs | Natividad | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300354 | San Nicolas Nhs | San Nicolas | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102117 | San Pablo Es | Umingan | 6 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102051 | San Pablo Es | Santa Maria | 6 | 1 | 4 | 1STY4CL | BATCH 7 CL | 3705000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300356 | San Quintin Nhs | San Quintin | 6 | 1 | 18 | 3STY9CL | BATCH 13 CL | 30242655.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300356 | San Quintin Nhs | San Quintin | 6 |  | 18 | 3STY9CL | BATCH 13 CL | 30242655.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101977 | San Rafael Es | San Nicolas | 6 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102012 | Sisenando V. Tecson Es | San Quintin | 6 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 101717 | Sobol Es | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 321212 | Sta. Cruz Is | Santa Maria | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 321219 | Sta. Maria East Integrated School | Santa Maria | 6 | 1 | 18 | 3STY9CL | BATCH 7 CL | 30242655.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102056 | Sta. Rosa Es | Santa Maria | 6 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 102075 | Sto. Domingo Es | Tayug | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1110000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300361 | Sto. Tomas Nhs | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300363 | Tayug Nhs | Tayug | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300363 | Tayug Nhs | Tayug | 6 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62205780.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300364 | Toboy Nhs | Asingan | 6 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300364 | Toboy Nhs | Asingan | 6 |  | 2 | 1STY1CL | BATCH 13 CL | 2226509.2394 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Pangasinan Ii, Binalonan | 300365 | Umingan Central Nhs | Umingan | 6 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | San Carlos City | 300378 | Bolingit National High School | San Carlos City | 3 | 1 | 8 | 4STY8CL | BATCH 1 CL | 14897518.84 |  |  | Completed | 1 | [7 empty] | MAY 13,2016 | MAY 20,2016 | SARGASSO CONSTRUCTION & DEV'T CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION I | San Carlos City | 300386 | Pangalangan Nhs | San Carlos City | 3 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22200000 |  |  | Completed | 1 | [7 empty] | MAY 13,2016 | MAY 20,2016 | SARGASSO CONSTRUCTION & DEV'T CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | San Carlos City | 300388 | Speaker Eugenio Perez Nat;L. Agr'L. Sch. | San Carlos City | 3 | 1 | 24 | 4STY12CL | BATCH 5 CL | 44400000 |  |  | Completed | 1 | [7 empty] | MAY 13,2016 | MAY 20,2016 | KENWOOD CONSTRUCTION ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION I | San Carlos City | 300388 | Speaker Eugenio Perez Nat;L. Agr'L. Sch. | San Carlos City | 3 |  | 15 | 3STY15CL | BATCH 5 CL | 21395200 |  |  | Completed | 1 | [7 empty] | MAY 13,2016 | MAY 20,2016 | MANIMELDS CONST'N & IRON WORKS/KENWOOD CONST'N ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION I | San Carlos City | 300388 | Speaker Eugenio Perez Nat;L. Agr'L. Sch. | San Carlos City | 3 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 7800000 |  |  | Completed | 1 | [7 empty] | 2016-03-16 | 42452 | KENWOOD CONSTRUCTION ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION I | San Carlos City | 300391 | Turac Nhs | San Carlos City | 3 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | San Fernando City | 300099 | Bangbangolan Nhs | City Of San Fernando (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6385000 |  |  | Completed | 1 |  |  |  | - | - | - | - | - | - | - |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | San Fernando City | 101039 | Catbangen Es | City Of San Fernando (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22202343.62 |  |  | Completed | 1 |  |  |  | 16AE0085 | 2016-06-25 | 2016-07-06 | 2016-07-25 | 2016-07-28 | 42601 | ECDI ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION I | San Fernando City | 300116 | Dr. Quintin Balcita Sr. Nhs | City Of San Fernando (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6335000 |  |  | Completed | 1 |  |  |  | 16AE0084 | 2016-06-25 | 2016-07-06 | 2016-07-18 | 2016-07-25 | 42587 | MY Builders & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | San Fernando City | 300118 | La Union Nhs | City Of San Fernando (Capital) | 1 | 1 | 24 | 4STY24CL | BATCH 5 CL | 35600200 |  |  | Completed | 1 |  |  |  | - | - | - | - | - | - | - |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION I | San Fernando City | 321001 | La Union Nhs - Sacyud Annex | City Of San Fernando (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6450000 |  |  | Completed | 1 |  |  |  | 16AE0086 | 2016-07-06 | 2016-07-14 | 2016-07-27 | 2016-07-29 | 42601 | MY Builders & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | San Fernando City | 321001 | La Union Nhs - Sacyud Annex | City Of San Fernando (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2518000 |  |  | Completed | 1 |  |  |  | - | - | - | - | - | - | - |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION I | San Fernando City | 300126 | Pao National High School | City Of San Fernando (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6345000 |  |  | Completed | 1 |  |  |  | 16AE0087 | 2016-07-14 | 2016-07-25 | 2016-08-15 | - | - | - |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | San Fernando City | 324102 | San Fernando City Sped High School | City Of San Fernando (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6355000 |  |  | Completed | 1 |  |  |  | 16AE0091 | 2016-07-26 | 2016-08-03 | 2016-08-15 | - | - | - |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | San Fernando City | 324101 | San Fernando South Central Integrated School | City Of San Fernando (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6365000 |  |  | Completed | 1 |  |  |  | 16AE0090 | 2016-07-26 | 2016-08-03 | 2016-08-15 | - | - | - |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Urdaneta City | 300395 | Cabaruan National High School | City Of Urdaneta | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  |  | 16A10105 CY 2016 BEEF Batch 7 | 3/3-9/16 | 2016-03-10 | 3/23/2016 | 5-16-2016 | 42522 | Teachnowood Construction Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Urdaneta City | 300397 | Camabu Nhs | City Of Urdaneta | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  |  | 16A10106 CY 2016 BEEF Batch 7 | 3/3-9/16 | 2016-03-10 | 3/23/2016 | 5-16-2016 | 42522 | 2R Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Urdaneta City | 300400 | Catablan Integrated School | City Of Urdaneta | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  |  | 16A10107 CY 2016 BEFF Batch 7 | 3/3-9/16 | 2016-03-10 | 3/23/2016 | 5-16-2016 | 42522 | T.J Velasco Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Urdaneta City | 500061 | Don Alipio Fernandez ,Sr. Is | Urdaneta City | 5 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8314965.05 |  |  | Completed | 1 |  |  |  | 16A10108 CY 2016 BEFF Bacth 7 | 3/3-9/16 | 2016-03-10 | 3/23/2016 | 05-13-2016 | 05-26-2016 | Aquino-Dela Cruz Eng'g.& Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION I | Urdaneta City | 300406 | Nancalobasaan National High School | City Of Urdaneta | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  |  | 16A10109 CY 2016 BEFF Batch 7 | 3/3-9/16 | 2016-03-10 | 3/23/2016 | 5-16-2016 | 42522 | MKM Marketing |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Urdaneta City | 300409 | Pedro T. Orata Nhs | City Of Urdaneta | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Urdaneta City | 500060 | San Jose Leet Is | Urdaneta City | 5 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6390000 |  |  | Completed | 1 |  |  |  | 16A10054 CY 2016 BEFF | 2/23-29/16 | 2016-03-01 | 2016-03-15 | 5-16-2016 | 42522 | Teachnowood Construction Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION I | Urdaneta City | 300410 | Urdaneta City Nhs | City Of Urdaneta | 5 | 1 | 20 | 4STY20CL | BATCH 11 CL | 34198179.297 |  |  | Completed | 1 |  |  |  | 16A10055 CY 2016 BEFF | 2/23-29/16 | 2016-03-01 | 2016-03-15 | 05-13-2016 | 05-26-2016 | Teachnowood Construction Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION I | Vigan City | 300052 | Ilocos Sur National High School | Vigan City | 1 | 1 | 24 | 4STY24CL | BATCH 1 CL | 35900000 |  |  | Completed | 1 | [9 empty] | NA Ibarra Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION I | Vigan City | 300052 | Ilocos Sur National High School | Vigan City | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2800000 |  |  | Completed | 1 | [9 empty] | 739 builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION I | Vigan City | 300052 | Ilocos Sur National High School | Vigan City | 1 |  | 16 | 4STY16CL | BATCH 1 CL | 27450000 |  |  | Completed | 1 |  |  |  |  | September 01,2016 | 2016-09-06 | Seotember 19, 2016 | 2016-09-22 | 42643 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION I | Vigan City | 100800 | Vigan Central School | City Of Vigan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1958000 |  |  | Completed | 1 | [9 empty] | NA Ibarra Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.