## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM TERM COMPLETED | Unnamed: 46 | Status as of July 4, 2025
REPAIR 2020 | Region II | Batanes | 102313 | Diptan Elementary School | BASCO (Capital) | 0 | 1 | 3 | Repair of Classrooms | 2100459 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Batanes | 102325 | Mahatao Elementary School | MAHATAO | 0 | 1 | 3 | Repair of Classrooms | 2014835 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102360 | Angkiray ES | ALCALA | 1 | 1 | 5 | Repair of Classrooms | 1409654 | 1 | 509555.55 | COMPLETED | 1 | [10 empty] | COMPLETED WITH DEDUCTION;For Issuance of Termination Order *Issued notice of termination and still ignored and failed to comply on the show cause order requested * Next step is to issued termination order due the continuous refusal to undertake the awarded contract. *All the Project sites are substantially completed as stated in the Statement of Work accomplishments however failed to execute the issued variation orders to complete e the project) The classroom was fully rehabilitated and all functional as classroom as of this time | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 44621 | 9.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102363 | Baybayog ES | ALCALA | 1 | 1 | 6 | Repair of Classrooms | 1477000 | 1 | 664079.14 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102367 | DALAOIG ELEMENTARY SCHOOL | ALCALA | 1 | 1 | 6 | Repair of Classrooms | 1427456 | 1 | 758275.68 | COMPLETED | 1 | [10 empty] | COMPLETED WITH DEDUCTION;For Issuance of Termination Order *Issued notice of termination and still ignored and failed to comply on the show cause order requested * Next step is to issued termination order due the continuous refusal to undertake the awarded contract. *All the Project sites are substantially completed as stated in the Statement of Work accomplishments however failed to execute the issued variation orders to complete e the project) The classroom was fully rehabilitated and all functional as classroom as of this time | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 44621 | 9.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102369 | Jurisdiccion ES | ALCALA | 1 | 1 | 5 | Repair of Classrooms | 1506286 | 1 | 603348.24 | COMPLETED | 1 | [10 empty] | COMPLETED WITH DEDUCTION;For Issuance of Termination Order *Issued notice of termination and still ignored and failed to comply on the show cause order requested * Next step is to issued termination order due the continuous refusal to undertake the awarded contract. *All the Project sites are substantially completed as stated in the Statement of Work accomplishments however failed to execute the issued variation orders to complete e the project) The classroom was fully rehabilitated and all functional as classroom as of this time | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 44621 | 9.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102456 | Binalan Elementary School | APARRI | 1 | 1 | 7 | Repair of Classrooms | 1782270 | 1 | 2574796 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102450 | San Antonio ES | APARRI | 1 | 1 | 4 | Repair of Classrooms | 782183 | 1 | 214852.42 | COMPLETED | 1 | [10 empty] | abandoned (for issuace of notice for termination) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102476 | Agaman Proper ES | BAGGAO | 1 | 1 | 6 | Repair of Classrooms | 1181000 | 1 | 2548680 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102479 | Alba ES | BAGGAO | 1 | 1 | 5 | Repair of Classrooms | 1326203 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102528 | San Luis ES | BAGGAO | 1 | 1 | 7 | Repair of Classrooms | 1970162 | 1 | 904721 | COMPLETED | 1 | [10 empty] | For Issuance of Termination Order *Issued notice of termination and still ignored and failed to comply on the show cause order requested * Next step is to issued termination order due the continuous refusal to undertake the awarded contract. *All the Project site are substantially completed as stated in the Statement of Work accomplishments however failed to execute the issued variation orders to complete e the project) The classroom was fully rehabilitated and all functional as classroom as of this time. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 | 44621 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 155015 | Centro West Elementary School | BUGUEY | 1 | 1 | 4 | Repair of Classrooms | 1490133 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102597 | Camalaniugan Central School | CAMALANIUGAN | 1 | 1 | 6 | Repair of Classrooms | 1210600 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102724 | Bagumbayan ES | LAL-LO | 1 | 1 | 1 | Repair of Classroom | 370000 | 1 | 1139853 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102738 | Bangag ES | LAL-LO | 1 | 1 | 1 | Repair of Classroom | 295000 | 1 | 1936890 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102739 | Bicud ES | LAL-LO | 1 | 1 | 7 | Repair of Classrooms | 825000 | 1 | 1157995 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102726 | Binag ES | LAL-LO | 1 | 1 | 4 | Repair of Classrooms | 675000 | 1 | 3585178 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102740 | Cabayabasan ES | LAL-LO | 1 | 1 | 6 | Repair of Classrooms | 1825000 | 1 | 932388 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102741 | Catayauan ES | LAL-LO | 1 | 1 | 7 | Repair of Classrooms | 1500000 | 1 | 1305251 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102742 | Catugan ES | LAL-LO | 1 | 1 | 6 | Repair of Classrooms | 1120000 | 1 | 3352574 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102728 | Cullit ES | LAL-LO | 1 | 1 | 5 | Repair of Classrooms | 475000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102744 | Dalaya ES | LAL-LO | 1 | 1 | 2 | Repair of Classrooms | 400000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102731 | Lallo North CS | LAL-LO | 1 | 1 | 15 | Repair of Classrooms | 2000000 | 1 | 1332046 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102747 | Logac ES | LAL-LO | 1 | 1 | 7 | Repair of Classrooms | 1680000 | 1 | 1221313 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102748 | Magapit ES | LAL-LO | 1 | 1 | 6 | Repair of Classrooms | 1300000 | 1 | 3618098 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102732 | Maxingal ES | LAL-LO | 1 | 1 | 9 | Repair of Classrooms | 1800000 | 1 | 2689300 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102733 | Naguillan ES | LAL-LO | 1 | 1 | 7 | Repair of Classrooms | 900000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102734 | San Antonio ES | LAL-LO | 1 | 1 | 1 | Repair of Classroom | 600000 | 1 | 2555566 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102751 | San Lorenzo ES | LAL-LO | 1 | 1 | 2 | Repair of Classrooms | 680000 | 1 | 1282703 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102754 | Sta.Maria CS | LAL-LO | 1 | 1 | 11 | Repair of Classrooms | 2400000 | 1 | 2700146 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102336 | Calog Sur ES | ABULUG | 2 | 1 | 5 | Repair of Classrooms | 350000 | 1 | 1680443 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102347 | San Julian ES | ABULUG | 2 | 1 | 5 | Repair of Classrooms | 800000 | 1 | 1282703 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102350 | Sirit ES | ABULUG | 2 | 1 | 5 | Repair of Classrooms | 900000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102584 | Calayan CS | CALAYAN | 2 | 1 | 5 | Repair of Classrooms | 1040092 | 1 | 1175337 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 155035 | Kadinakan PS | CALAYAN | 2 | 1 | 2 | Repair of Classroom | 452536 | 1 | 1624679 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102592 | Minabel ES | CALAYAN | 2 | 1 | 8 | Repair of Classroom | 1834320 | 1 | 5975009 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 300443 | Callao National High School | LASAM | 2 | 1 | 7 | Repair of Classroom | 2595359 | 1 | 2251823 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102761 | Finugo Norte ES | LASAM | 2 | 1 | 2 | Repair of Classroom | 519420 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102764 | Lasam CS | LASAM | 2 | 1 | 10 | Repair of Classrooms | 1500000 | 1 | 1282703 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102767 | Minanga Norte ES | LASAM | 2 | 1 | 3 | Repair of Classroom | 342698 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102772 | Nicolas Agatep ES | LASAM | 2 | 1 | 3 | Repair of Classroom | 757021 | 1 | 6086958 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102777 | Tucalan Passing ES | LASAM | 2 | 1 | 6 | Repair of Classroom | 1473970 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102830 | Villa Rey ES | PIAT | 2 | 1 | 2 | Repair of Classrooms | 275000 | 1 | 5975009 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102834 | Dungan Elementary School | RIZAL | 2 | 1 | 6 | Repair of Classroom | 1070678 | 1 | 4274531 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 501172 | Dungao Integrated School | SANTO NIÑO (FAIRE) | 2 | 1 | 6 | Repair of Classrooms | 1500000 | 1 | 376770 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102949 | Niug ES | SANTO NIÑO (FAIRE) | 2 | 1 | 4 | Repair of Classrooms | 500000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102950 | San Manuel ES | SANTO NIÑO (FAIRE) | 2 | 1 | 2 | Repair of Classrooms | 350000 | 1 | 397800 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102953 | Sto. Nino Central Elementary School | SANTO NIÑO (FAIRE) | 2 | 1 | 18 | Repair of Classrooms | 3200000 | 1 | 769629 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102954 | Tabang ES | SANTO NIÑO (FAIRE) | 2 | 1 | 2 | Repair of Classrooms | 280000 | 1 | 689089 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102956 | Virginia Elementary School | SANTO NIÑO (FAIRE) | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 | 1949077 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cauayan City | 103191 | Doña Pacita C. Bautista ES | CITY OF CAUAYAN | 3 | 1 | 8 | Repair of Classrooms | 2020197 | 1 | 453800 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cauayan City | 103224 | San Francisco ES - Annex | CITY OF CAUAYAN | 3 | 1 | 3 | Repair of Classrooms | 1025687 | 1 | 1583979 | COMPLETED | 1 | 2019-02-05 |  | CW-053 s. 2019 | CW-053 s. 2019 | 2019-07-30 | 2019-08-08 | 2019-08-20 | 2019-09-23 | 2019-11-05 | NEW AMSON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cauayan City | 103200 | San Luis ES | CITY OF CAUAYAN | 3 | 1 | 10 | Repair of Classrooms | 2604986 | 1 | 2248779 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cauayan City | 155504 | Sta. Luciana ES Annex | CITY OF CAUAYAN | 3 | 1 | 2 | Repair of Classrooms | 754871 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cauayan City | 103207 | Villa Luna ES - Annex | CITY OF CAUAYAN | 3 | 1 | 5 | Repair of Classrooms | 1374066 | 1 | 1316449 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | City of Ilagan | 103416 | Bigao Elementary School | ILAGAN CITY (CAPITAL) | 1 | 1 | 5 | Repair of Classrooms | 1234174 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | City of Ilagan | 103386 | Cadu ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 7 | Repair of Classrooms | 635625 | 1 | 1522505 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | City of Ilagan | 103402 | Ilagan South CS | ILAGAN CITY (CAPITAL) | 1 | 1 | 37 | Repair of Classrooms | 7596213 | 1 | 2888624 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | City of Ilagan | 103434 | Siffu Elementary School | ILAGAN CITY (CAPITAL) | 1 | 1 | 7 | Repair of Classrooms | 1604725 | 1 | 1958177 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | City of Ilagan | 103380 | Sta. Victoria ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 4 | Repair of Classrooms | 1057440 | 1 | 1780840 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103098 | Andabuen Elementary School - Main | BENITO SOLIVEN | 2 | 1 | 6 | Repair of Classrooms | 2548680 | 1 | 1551493 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103118 | San Francisco Elementary School | BENITO SOLIVEN | 2 | 1 | 4 | Repair of Classrooms | 1522505 | 1 | 2943908 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103120 | Sevillana Elementary School | BENITO SOLIVEN | 2 | 1 | 1 | Repair of Classroom | 467054 | 1 | 467054 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103351 | Union Elementary School | GAMU | 2 | 1 | 9 | Repair of Classrooms | 3735752 | 1 | 406835 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 300554 | Isabela School of Fisheries | PALANAN | 2 | 1 | 27 | Repair of Classrooms | 6086958 | 1 | 1895365 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103750 | Casala Elementary School | SAN MARIANO | 2 | 1 | 7 | Repair of Classrooms | 2555566 | 1 | 1282703 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103751 | Cataguing Elementary School | SAN MARIANO | 2 | 1 | 4 | Repair of Classrooms | 932388 | 1 | 1008538 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103733 | Caunayan Elementary School | SAN MARIANO | 2 | 1 | 3 | Repair of Classrooms | 1305251 | 1 | 461849 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 300595 | Ueg National High School | SAN MARIANO | 2 | 1 | 4 | Repair of Classrooms | 366729 | 1 | 1845751 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103056 | Consular Elementary School | ANGADANAN | 3 | 1 | 9 | Repair of Classrooms | 3352574 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103058 | Dalakip Elementary School | ANGADANAN | 3 | 1 | 10 | Repair of Classrooms | 3618098 | 1 | 366729 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103068 | Sinabbaran Elementary School | ANGADANAN | 3 | 1 | 2 | Repair of Classrooms | 406835 | 1 | 3735752 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103165 | Cabatuan East Central School | CABATUAN | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 3585178 | 1 | 643920 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103167 | Calaocan Elementary School | CABATUAN | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1332046 | 1 | 6126341 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103171 | La Paz Elementary School | CABATUAN | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 2251823 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103783 | Dagupan Elementary School | SAN MATEO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1221313 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103787 | San Marcos Elementary School | SAN MATEO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1958177 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 306143 | Cagasat HS-Magsaysay Annex | CORDON | 4 | 1 | 21 | Repair of Classrooms | 3167768 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103246 | Capirpiriwan Elementary School | CORDON | 4 | 1 | 6 | Repair of Classrooms | 2158715 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103251 | Kakilingan Elementary School | CORDON | 4 | 1 | 6 | Repair of Classrooms | 4386238 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 500073 | Wigan Integrated School | CORDON | 4 | 1 | 15 | REPAIR OF CLASSROOMS | 6126341 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 300498 | Addalam Region HS - Main | JONES | 4 | 1 | 9 | REPAIR OF CLASSROOMS | 2574796 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103465 | Disimpit Elementary School | JONES | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 2700146 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103475 | Pungpongan PS | Jones | 4 | 1 | 1 | Repair of Classroom | 376770 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103482 | Tubar Elementary School | JONES | 4 | 1 | 5 | Repair of Classrooms | 1764251 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103650 | Bautista Elementary School - Annex | SAN AGUSTIN | 4 | 1 | 2 | Repair of classrooms | 904721 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103649 | Bautista Elementary School - Main | SAN AGUSTIN | 4 | 1 | 8 | Repair of Classrooms | 1740581 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103653 | Dabubu Elementary School | SAN AGUSTIN | 4 | 1 | 10 | Repair of Classrooms | 3520968 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103656 | Mapalad Elementary School | SAN AGUSTIN | 4 | 1 | 12 | REPAIR OF CLASSROOMS | 4274531 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103658 | Masaya Sur Elementary School | SAN AGUSTIN | 4 | 1 | 10 | Repair of Classrooms | 3368895 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103659 | Nemmatan Primary School | SAN AGUSTIN | 4 | 1 | 1 | Repair of Classroom | 397800 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103663 | Quimalabasa Sur Primary School | SAN AGUSTIN | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 453800 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103665 | San Agustin Central School | SAN AGUSTIN | 4 | 1 | 16 | Repair of Classrooms | 6243110 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103666 | San Antonio Elementary School | SAN AGUSTIN | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1780840 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103669 | Sinaoangan Sur Elementary School | SAN AGUSTIN | 4 | 1 | 1 | Repair of Classroom | 461849 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103670 | Sto. Nino Elementary School | SAN AGUSTIN | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 1845751 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103129 | Catabban Elementary School | BURGOS | 5 | 1 | 5 | Repair of Classrooms | 1157995 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103137 | San Miguel Elementary School | BURGOS | 5 | 1 | 10 | Repair of Classrooms | 2943908 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103585 | San Mateo Elementary School | QUIRINO | 5 | 1 | 5 | Repair of Classrooms | 1551493 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103282 | Annafunan Elementary School | ECHAGUE | 6 | 1 | 8 | Repair of Classrooms | 5679661 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103328 | Buneg Elementary School | ECHAGUE | 6 | 1 | 2 | Repair of Classroom | 3472005 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103286 | Castillo Elementary School | ECHAGUE | 6 | 1 | 6 | REPAIR OF CLASSROOMS | 1936890 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103330 | Dammang Malitao Elementary School | ECHAGUE | 6 | 1 | 4 | REPAIR OF CLASSROOMS | 1282703 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103332 | Fugu Elementary School | ECHAGUE | 6 | 1 | 4 | REPAIR OF CLASSROOMS | 1282703 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103333 | Garit Elementary School | ECHAGUE | 6 | 1 | 10 | Repair of Classrooms | 3265082.02 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103334 | Gucab Elementary School | ECHAGUE | 6 | 1 | 10 | REPAIR OF CLASSROOMS | 5975009 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 300541 | Imelda R. Marcos High School | ECHAGUE | 6 | 1 | 11 | Repair of Classrooms | 5531986 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 306120 | Imelda R. Marcos HS - Mabbayad Annex | ECHAGUE | 6 | 1 | 4 | Repair of Classrooms | 4458685 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103336 | Malitao Elementary School | ECHAGUE | 6 | 1 | 4 | REPAIR OF CLASSROOMS | 1282703 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103315 | Pangal Sur Elementary School | ECHAGUE | 6 | 1 | 2 | REPAIR OF CLASSROOMS | 689089 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 300566 | Pangal Sur High School | ECHAGUE | 6 | 1 | 10 | REPAIR OF CLASSROOMS | 1949077 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103301 | Sinabbaran Elementary School | ECHAGUE | 6 | 1 | 6 | REPAIR OF CLASSROOMS | 1895365 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103337 | Soyung Elementary School | ECHAGUE | 6 | 1 | 4 | REPAIR OF CLASSROOMS | 1282703 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103325 | Sta. Monica Elementary School | ECHAGUE | 6 | 1 | 3 | REPAIR OF CLASSROOMS | 1008538 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103675 | Burgos West Elementary School | SAN GUILLERMO | 6 | 1 | 3 | REPAIR OF CLASSROOMS | 1139853 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103683 | Guam Elementary School | SAN GUILLERMO | 6 | 1 | 3 | REPAIR OF CLASSROOMS | 1175337 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 500083 | Palawan Integrated School | SAN GUILLERMO | 6 | 1 | 2 | REPAIR OF CLASSROOMS | 769629 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 500022 | Rizal Integrated School | SAN GUILLERMO | 6 | 1 | 3 | REPAIR OF CLASSROOMS | 1583979 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103690 | San Guillermo Central School | SAN GUILLERMO | 6 | 1 | 11 | REPAIR OF CLASSROOMS | 2888624 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103698 | Villa Teresita Primary School | SAN GUILLERMO | 6 | 1 | 2 | REPAIR OF CLASSROOMS | 643920 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 155521 | Camarag Elementary School | SAN ISIDRO | 6 | 1 | 4 | REPAIR OF CLASSROOMS | 2689300 | 1 | 7596212.3 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103708 | Dona Paulina Elementary School | SAN ISIDRO | 6 | 1 | 5 | REPAIR OF CLASSROOMS | 1680443 | 1 | 1234173.09 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103701 | Gud Elementary School | SAN ISIDRO | 6 | 1 | 5 | REPAIR OF CLASSROOMS | 1624679 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 306123 | Manuel L. Quezon National High School | SAN ISIDRO | 6 | 1 | 10 | REPAIR OF CLASSROOMS | 5975009 | 1 | 1604724.29 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103705 | Ramos Elementary School | SAN ISIDRO | 6 | 1 | 8 | REPAIR OF CLASSROOMS | 2248779 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 155510 | Ramos West Elementary School | SAN ISIDRO | 6 | 1 | 7 | REPAIR OF CLASSROOMS | 1316449 | 1 | 635624.46 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 300591 | San Isidro National High School | SAN ISIDRO | 6 | 1 | 23 | Repair of Classroom | 4458685 | 1 | 1057439.69 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104187 | Abuyo ES | ALFONSO CASTAÑEDA | 0 | 1 | 3 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104188 | Alfonso Castañeda Central School | ALFONSO CASTAÑEDA | 0 | 1 | 5 | Repair of Classrooms | 5000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104199 | Galintuja ES | ALFONSO CASTAÑEDA | 0 | 1 | 3 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104204 | Lipuga ES | ALFONSO CASTAÑEDA | 0 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103909 | Beti ES | ARITAO | 0 | 1 | 3 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103910 | Bone North Elementary School | ARITAO | 0 | 1 | 8 | Repair of Classrooms | 6000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103914 | Canarem PS | ARITAO | 0 | 1 | 3 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103922 | Nagcuartelan ES | ARITAO | 0 | 1 | 3 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103923 | Sta. Clara ES | ARITAO | 0 | 1 | 6 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103926 | Ukaw ES | ARITAO | 0 | 1 | 4 | Repair of Classrooms | 4000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103927 | Yaway ES | ARITAO | 0 | 1 | 4 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103986 | Busilac ES | BAYOMBONG (Capital) | 0 | 1 | 10 | Repair of Classrooms | 3394851 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104010 | Labbu ES | BAYOMBONG (Capital) | 0 | 1 | 4 | Repair of Classrooms | 1589487 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103997 | Paitan ES | BAYOMBONG (Capital) | 0 | 1 | 10 | Repair of Classrooms | 2812660 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104037 | Belance Elementary School | DUPAX DEL NORTE | 0 | 1 | 6 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104038 | Binuangan Elementary School | DUPAX DEL NORTE | 0 | 1 | 6 | Repair of Classrooms | 4000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 156007 | Naruron ES | DUPAX DEL NORTE | 0 | 1 | 3 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104052 | New Gumiad ES | DUPAX DEL NORTE | 0 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104057 | Banila ES | DUPAX DEL SUR | 0 | 1 | 4 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104060 | Carolotan ES | DUPAX DEL SUR | 0 | 1 | 4 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104061 | Castro ES | DUPAX DEL SUR | 0 | 1 | 4 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104063 | Ecameging ES | DUPAX DEL SUR | 0 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104065 | Ganao Elementary School | DUPAX DEL SUR | 0 | 1 | 6 | Repair of classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104068 | Lukidnon ES | DUPAX DEL SUR | 0 | 1 | 4 | Repair of classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104072 | Talbec ES | DUPAX DEL SUR | 0 | 1 | 4 | Repair of Classrooms | 2000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104082 | Catarawan ES | Kasibu | 0 | 1 | 3 | Repair of Classroom | 1580200 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104103 | Siguem ES | KASIBU | 0 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104179 | Commonal ES | Solano | 0 | 1 | 2 | Repair of Classroom | 725641 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 300655 | BURGOS NHS | Cabarroguis | 0 | 1 | 14 | Repair of Classrooms | 6273122 | 1 | 6273121.05 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 500872 | Cabarroguis CS - Integrated SPED Center | Cabarroguis | 0 | 1 | 8 | Repair of Classrooms | 2790188 | 1 | 2790187.6 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 104269 | UPPER DIBIBI ES | Cabarroguis | 0 | 1 | 3 | Repair of Classrooms | 999835 | 1 | 999834.16 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 104284 | LOWER GABRIELA ES | Diffun | 0 | 1 | 8 | Repair of Classrooms | 2345432 | 1 | 2345431.41 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 104312 | Pimentel ES | Diffun | 0 | 1 | 4 | Repair of Classrooms | 1129544 | 1 | 1129543.01 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 104317 | ABBAG ES | Maddela | 0 | 1 | 5 | Repair of Classrooms | 1444003 | 1 | 1444002.8 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 104321 | Dialanese ES | MADDELA | 0 | 1 | 3 | Repair of Classrooms | 1390578 | 1 | 1390577.71 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Santiago City | 103840 | Santiago South CS | CITY OF SANTIAGO | 4 | 1 | 1 | Repair of Classroom | 5300000 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Santiago City | 103842 | Santiago West Central School-Special Science Elementary School | CITY OF SANTIAGO | 4 | 1 | 6 | Repair of Classrooms | 2936962 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Santiago City | 103817 | Nabbuan ES | Santiago City | 4 | 1 | 6 | Repair of Classrooms | 1427298 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Tuguegarao City | 157001 | Dadda ES | TUGUEGARAO CITY(Capital) | 3 | 1 | 2 | Repair of Classrooms | 181932 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Tuguegarao City | 300670 | Linao National High School | TUGUEGARAO CITY(Capital) | 3 | 1 | 12 | Repair of Classrooms | 618079 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Batanes | 102330 | Sumnanga Elementary School | SABTANG | 0 | 1 | 6 | Repair of Classrooms | 3032100.24 | 1 | 2609212.82 | COMPLETED | 1 | 2023-01-23 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 44927 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 300422 | BAYBAYOG NATIONAL HIGH SCHOOL | ALCALA | 1 | 1 | 25 | Repair of Classrooms | 4540622.6 | 1 | 3520000 | COMPLETED | 1 | 2022-01-23 | [8 empty] | Achanzar Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102368 | Damurog Elementary School | ALCALA | 1 | 1 | 3 | Repair of Classrooms | 1161744.71 | 1 | 1146214.5 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102513 | Bitag Grande ES | BAGGAO | 1 | 1 | 8 | Repair of Classrooms | 1652432.55 | 1 | 1575479.9 | COMPLETED | 1 | [9 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102570 | Buguey South CS (Pattao ES) | BUGUEY | 1 | 1 | 5 | Repair of Classrooms | 2250000 | 1 | 2209809.65 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102564 | Maddalero ES | BUGUEY | 1 | 1 | 6 | Repair of Classrooms | 2700000 | 1 | 2664606.59 | COMPLETED | 1 | 2022-01-23 | [8 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102580 | Villa Gracia ES | BUGUEY | 1 | 1 | 3 | Repair of Classrooms | 1350000 | 1 | 1334816.05 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102595 | Alilinu ES | CAMALANIUGAN | 1 | 1 | 5 | Repair of Classrooms | 2500000 | 1 | 2469478.83 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102599 | Catotoran ES | CAMALANIUGAN | 1 | 1 | 4 | Repair of Classrooms | 2000000 | 1 | 1979874.28 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102696 | Gonzaga South CS | GONZAGA | 1 | 1 | 4 | Repair of Classrooms | 3500000 | 1 | 2554772.63 | COMPLETED | 1 | [9 empty] | RPF Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102698 | Isca ES | GONZAGA | 1 | 1 | 5 | Repair of Classrooms | 3500000 | 1 | 3492180.47 | COMPLETED | 1 | [9 empty] | RPF Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 155054 | CAMBONG ELEMENTARY SCHOOL | LALLO | 1 | 1 | 5 | Repair of Classrooms | 990181.08 | 1 | 989887.78 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102738 | Bangag ES | LAL-LO | 1 | 1 | 4 | Repair of Classrooms | 450000 | 1 | 439812.38 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102725 | Bical ES | LAL-LO | 1 | 1 | 6 | Repair of Classrooms | 1500000 | 1 | 1474223.2 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102739 | Bicud ES | LAL-LO | 1 | 1 | 10 | Repair of Classrooms | 1200000 | 1 | 1184936.93 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102727 | Cagoran Elementary School | LAL-LO | 1 | 1 | 4 | Repair of Classrooms | 500000 | 1 | 489987.63 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102741 | Catayauan Elementary School | LAL-LO | 1 | 1 | 4 | Repair of Classrooms | 650000 | 1 | 639888.95 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102742 | Catugan ES | LAL-LO | 1 | 1 | 9 | Repair of Classrooms | 1000000 | 1 | 989940.92 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 300469 | LAL-LO NATIONAL HIGH SCHOOL | LAL-LO | 1 | 1 | 23 | Repair of Classrooms | 4100000 | 1 | 4039791.71 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 306003 | Lal-lo NHS - Cabayabasan Annex | LAL-LO | 1 | 1 | 14 | Repair of Classrooms | 3450000 | 1 | 3448460.86 | COMPLETED | 1 | 2022-01-22 | [8 empty] | RPF Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102748 | Magapit ES | LAL-LO | 1 | 1 | 8 | Repair of Classrooms | 700000 | 1 | 689895.1 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102732 | Maxingal Elementary School | LAL-LO | 1 | 1 | 4 | Repair of Classrooms | 2500000 | 1 | 2496276.85 | COMPLETED | 1 | [9 empty] | RPF Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102750 | Paranum Elementary School | LAL-LO | 1 | 1 | 2 | Repair of Classrooms | 600000 | 1 | 589571.52 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 155030 | San Mariano Elementary School | LAL-LO | 1 | 1 | 10 | Repair of Classrooms | 1250000 | 1 | 1234279.66 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102754 | Sta. Maria CS | LAL-LO | 1 | 1 | 1 | Repair of Classroom | 400000 | 1 | 389954.61 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102735 | Sta. Teresa Elementary School | LAL-LO | 1 | 1 | 8 | Repair of Classrooms | 1200000 | 1 | 1179629.91 | COMPLETED | 1 | [9 empty] | JIRK Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102902 | Kapanikian ES | SANTA ANA | 1 | 1 | 3 | Repair of Classrooms | 908534.57 | 1 | 904857.14 | COMPLETED | 1 | [9 empty] | RPF Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 155018 | Visitacion Elementary School | SANTA ANA | 1 | 1 | 6 | Repair of Classrooms | 1654807.23 | 1 | 1207924.37 | COMPLETED | 1 | [9 empty] | RPF Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102924 | Alucao Elementary School | SANTA TERESITA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 | 1497118.65 | COMPLETED | 1 | [9 empty] | RPF Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102933 | Simpatuyo ES | SANTA TERESITA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 | 1497549.79 | COMPLETED | 1 | [9 empty] | RPF Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102342 | Lucban ES | ABULUG | 2 | 1 | 5 | Repair of Classrooms | 1200000 | 1 | 1192013.97 | COMPLETED | 1 | [9 empty] | BA Lagazo Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102536 | Ballesteros CS | BALLESTEROS | 2 | 1 | 6 | Repair of Classrooms | 1900000 | 1 | 1899001.31 | COMPLETED | 1 | [9 empty] | BA Lagazo Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102550 | Sta. Cruz ES | BALLESTEROS | 2 | 1 | 3 | Repair of Classrooms | 950000 | 1 | 949739.88 | COMPLETED | 1 | [9 empty] | BA Lagazo Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 300442 | Calayan HS - Camiguin Annex | CALAYAN | 2 | 1 | 4 | Repair of Classrooms | 1370984.22 | 1 | 1355701.19 | COMPLETED | 1 | 2023-12-22 | [8 empty] | JIRK Construction | isolated island | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 306427 | Calayan HS- Dilam Extension | CALAYAN | 2 | 1 | 7 | Repair of Classrooms | 2119294.92 | 1 | 2116992.67 | COMPLETED | 1 | 2023-12-22 | [8 empty] | BA Lagazo Builders | isolated island | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102585 | Camiguin ES | CALAYAN | 2 | 1 | 8 | Repair of Classrooms | 1926243.69 | 1 | 1910651.04 | COMPLETED | 1 | 2023-12-22 | [8 empty] | JIRK Construction | isolated island | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102587 | Dadao ES | CALAYAN | 2 | 1 | 5 | Repair of Classrooms | 1318985.64 | 1 | 1303023.61 | COMPLETED | 1 | 2023-12-22 | [8 empty] | JIRK Construction | isolated island | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 155012 | Dilam East PS | CALAYAN | 2 | 1 | 4 | Repair of Classrooms | 1260892.67 | 1 | 1245218.95 | COMPLETED | 1 | 2023-12-22 | [8 empty] | JIRK Construction | isolated island | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102590 | Dilam ES | CALAYAN | 2 | 1 | 6 | Repair of Classrooms | 1207379.16 | 1 | 1205543.66 | COMPLETED | 1 | 2023-12-22 | [8 empty] | BA Lagazo Builders | isolated island | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102591 | Magsidel ES | CALAYAN | 2 | 1 | 8 | Repair of Classrooms | 2182236.64 | 1 | 2180899.08 | COMPLETED | 1 | 2023-12-22 | [8 empty] | BA Lagazo Builders | isolated island | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102618 | Pata Elementary School | CLAVERIA | 2 | 1 | 5 | Repair of Classrooms | 1200000 | 1 | 1199027.61 | COMPLETED | 1 | [9 empty] | BA Lagazo Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102760 | Callao ES | LASAM | 2 | 1 | 6 | Repair of Classrooms | 1800000 | 1 | 1798582.71 | COMPLETED | 1 | [9 empty] | BA Lagazo Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102765 | Magsaysay ES | LASAM | 2 | 1 | 3 | Repair of Classrooms | 800000 | 1 | 796141.97 | COMPLETED | 1 | [9 empty] | BA Lagazo Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102784 | Bidduang ES | PAMPLONA | 2 | 1 | 11 | Repair of Classrooms | 2300000 | 1 | 2297947.79 | COMPLETED | 1 | [9 empty] | BA Lagazo Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102820 | Apayao ES | PIAT | 2 | 1 | 5 | Repair of Classrooms | 1450000 | 1 | 1448831.65 | COMPLETED | 1 | [9 empty] | Bifesa Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102821 | Catarauan ES | PIAT | 2 | 1 | 1 | Repair of Classroom | 194600 | 1 | 190311.7 | COMPLETED | 1 | [9 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102822 | Dugayung ES | PIAT | 2 | 1 | 1 | Repair of Classroom | 630000 | 1 | 596791.95 | COMPLETED | 1 | [9 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102823 | Gumarueng ES | PIAT | 2 | 1 | 1 | Repair of Classroom | 508985 | 1 | 485701.6 | COMPLETED | 1 | [9 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102824 | Macapil ES | PIAT | 2 | 1 | 3 | Repair of Classrooms | 300000 | 1 | 284216.77 | COMPLETED | 1 | [9 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102826 | Minanga ES | PIAT | 2 | 1 | 1 | Repair of Classroom | 1310000 | 1 | 1309799.21 | COMPLETED | 1 | [9 empty] | 4MD JSL Construction Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102827 | Piat CS | PIAT | 2 | 1 | 1 | Repair of Classroom | 1340000 | 1 | 1339004.96 | COMPLETED | 1 | [9 empty] | 4MD JSL Construction Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102828 | Sicatna ES | PIAT | 2 | 1 | 4 | Repair of Classrooms | 2000000 | 1 | 1889026.82 | COMPLETED | 1 | 2022-01-18 | [8 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102825 | Sta. Barbara-Maguilling E/S | PIAT | 2 | 1 | 1 | Repair of Classroom | 1300000 | 1 | 1296445.52 | COMPLETED | 1 | [9 empty] | Bifesa Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102829 | Sto. Domingo ES | PIAT | 2 | 1 | 3 | Repair of Classrooms | 900000 | 1 | 858524.11 | COMPLETED | 1 | [9 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102831 | Warat ES | PIAT | 2 | 1 | 1 | Repair of Classroom | 471985 | 1 | 443710.09 | COMPLETED | 1 | [9 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102833 | Cambabangan ES | RIZAL | 2 | 1 | 4 | Repair of Classrooms | 1084632.51 | 1 | 1080367.75 | COMPLETED | 1 | [9 empty] | 4MD JSL Construction Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102835 | Duyun ES | RIZAL | 2 | 1 | 5 | Repair of Classrooms | 1112471.11 | 1 | 1059525.94 | COMPLETED | 1 | [9 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102836 | Gaddangao ES | RIZAL | 2 | 1 | 5 | Repair of Classrooms | 1209499.3 | 1 | 1144430.34 | COMPLETED | 1 | 2022-01-18 | [8 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 155003 | Balagan Elementary School | SANTO NIÑO (FAIRE) | 2 | 1 | 6 | Repair of Classrooms | 1900000 | 1 | 1781062.5 | COMPLETED | 1 | [9 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102955 | Tamucco ES | SANTO NIÑO (FAIRE) | 2 | 1 | 7 | Repair of Classrooms | 2000000 | 1 | 1999184.05 | COMPLETED | 1 | 2022-01-18 | [8 empty] | Bifesa Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102800 | Lagum ES | PEÑABLANCA | 3 | 1 | 2 | Repair of Classrooms | 850000 | 1 | 812269.08 | COMPLETED | 1 | [9 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102803 | Minanga ES | PEÑABLANCA | 3 | 1 | 5 | Repair of Classrooms | 2100000 | 1 | 1991245.35 | COMPLETED | 1 | [9 empty] | GCPK Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cauayan City | 103227 | Alinam ES | CITY OF CAUAYAN | 6 | 1 | 1 | Repair of Classroom | 479698.73 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cauayan City | 103218 | Labinab Angeles ES | CITY OF CAUAYAN | 6 | 1 | 6 | Repair of Classrooms | 4021985.88 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cauayan City | 103219 | Rizal ES | CITY OF CAUAYAN | 6 | 1 | 3 | Repair of Classrooms | 1969460.51 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | City of Ilagan | 500018 | San Lorenzo Integrated School (San Lorenzo ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | 15 | Repair of Classrooms | 4819746.79 | 1 | 3362233.71 | COMPLETED | 1 | 2021-11-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | City of Ilagan | 103408 | San Rafael ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 1 | Repair of Classroom | 541590.21 | 1 | 438190.87 | COMPLETED | 1 | 2021-11-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | City of Ilagan | 103436 | Sta. Isabel Sur ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 9 | Repair of Classrooms | 2630096.89 | 1 | 1838477.86 | COMPLETED | 1 | 2021-11-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103242 | Aguinaldo Elementary School | CORDON | 4 | 1 | 5 | Repair of Classrooms | 2059183.1 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103258 | Cordon North Central School | CORDON | 4 | 1 | 5 | Repair of Classrooms | 2059183.11 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103249 | Dallao Elementary School | CORDON | 4 | 1 | 4 | Repair of Classrooms | 1609558.49 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103250 | Gayong Elementary School | CORDON | 4 | 1 | 3 | Repair of Classrooms | 1379043.13 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103252 | Malapat Elementary School | CORDON | 4 | 1 | 3 | Repair of Classrooms | 1372227.51 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103255 | San Juan Elementary School | CORDON | 4 | 1 | 4 | Repair of Classrooms | 1826976 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103440 | Bannawag Elementary School | JONES | 4 | 1 | 4 | Repair of Classrooms | 1878025.6 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 306134 | Sgt. Prospero G. Bello HS - Dumawing Annex | JONES | 4 | 1 | 3 | Repair of Classrooms | 1466253.52 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103636 | Roxas Central School | ROXAS | 5 | 1 | 18 | Repair of Classrooms | 8000734.08 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103645 | San Francisco Elementary School | ROXAS | 5 | 1 | 5 | Repair of Classrooms | 2089258.59 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103285 | Carulay Elementary School | ECHAGUE | 6 | 1 | 4 | Repair of Classrooms | 1768069.09 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103287 | Diasan Elementary School | ECHAGUE | 6 | 1 | 3 | Repair of Classrooms | 1561016.93 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103288 | Dicaraoyan Elementary School | ECHAGUE | 6 | 1 | 6 | Repair of Classrooms | 2502953.17 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103312 | Libertad Elementary School | ECHAGUE | 6 | 1 | 4 | Repair of Classrooms | 1997013.28 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103292 | Mabbayad Elementary School | ECHAGUE | 6 | 1 | 4 | Repair of Classrooms | 1838784.3 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103707 | San Isidro West Central School | SAN ISIDRO | 6 | 1 | 5 | Repair of Classrooms | 2081569.06 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 103981 | Ammococan ES | BAYOMBONG (Capital) | 0 | 1 | 7 | Repair of Classrooms | 1930797.18 | 1 | 1905726.67 | COMPLETED | 1 | 70 CD | [5 empty] | 2021-09-29 |  |  | IA castaneda Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104000 | Villa Adriano PS | BAYOMBONG (Capital) | 0 | 1 | 4 | Repair of Classrooms | 1922979.53 | 1 | 1898185.46 | COMPLETED | 1 | 60 CD | [5 empty] | 2021-09-29 |  |  | South East Horizon 818 Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104103 | Siguem ES | KASIBU | 0 | 1 | 2 | Repair of Classrooms | 1219022.13 | 1 | 1149434.19 | COMPLETED | 1 | 37 CD | [5 empty] | 2021-09-29 |  |  | Zyronne Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104109 | Acacia PS | KAYAPA | 0 | 1 | 5 | Repair of Classrooms | 3102941.72 | 1 | 3093258.46 | COMPLETED | 1 | 80 CD | [5 empty] | 2021-09-29 |  |  | Boyet Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104141 | Baan Elementary School | KAYAPA | 0 | 1 | 8 | Repair of Classrooms | 2780775.44 | 1 | 2754509.38 | COMPLETED | 1 | 71 CD | [5 empty] | 2021-09-29 |  |  | Boyet Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104123 | Dempeg Elementary school | KAYAPA | 0 | 1 | 5 | Repair of Classrooms | 4752582.53 | 1 | 4635888.72 | COMPLETED | 1 | 82 CD | [5 empty] | 2021-09-29 |  |  | Mighty Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104138 | Pangawan ES | KAYAPA | 0 | 1 | 6 | Repair of Classrooms | 3750000 | 1 | 3732418.23 | COMPLETED | 1 | 65 CD | [5 empty] | 2021-09-29 |  |  | Boyet Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104149 | Bonifacio Elementary School | QUEZON | 0 | 1 | 6 | Repair of Classrooms | 1572452.24 | 1 | 1331486.9 | COMPLETED | 1 | 70 CD | [5 empty] | 2021-09-29 |  |  | Ambaguio Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104163 | Tutong Elementary School | QUEZON | 0 | 1 | 4 | Repair of Classrooms | 1205008.96 | 1 | 1115423.5 | COMPLETED | 1 | 66 CD | [5 empty] | 2021-09-29 |  |  | Rosa Mystica |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104201 | Genato ES | SANTA FE | 0 | 1 | 6 | Repair of Classrooms | 2311886.4 | 1 | 2246747.23 | COMPLETED | 1 | 65 CD | [5 empty] | 2021-09-29 |  |  | Zyronne Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Quirino | 500108 | Dumabel IS | AGLIPAY | 0 | 1 | 8 | Repair of Classrooms | 2301846.22 | 1 | 0 | COMPLETED | 1 |  |  |  |  | 2021-07-28 | 2021-08-03 | 2021-08-16 |  |  |  | for Contract Signing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Quirino | 104234 | Osmena P/S Annex | AGLIPAY | 0 | 1 | 2 | Repair of Classrooms | 514962.77 | 1 | 505601.99 | COMPLETED | 1 |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-27 | Atlantic Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Quirino | 104294 | Bikibik ES | DIFFUN | 0 | 1 | 3 | Repair of Classrooms | 872126.15 | 1 | 868139.78 | COMPLETED | 1 |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-24 | 619 Builders Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Quirino | 104308 | Macate ES | DIFFUN | 0 | 1 | 6 | Repair of Classrooms | 1906391.03 | 1 | 1860661.77 | COMPLETED | 1 |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-24 | 619 Builders Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Quirino | 300661 | Magsaysay National High School | DIFFUN | 0 | 1 | 9 | Repair of Classrooms | 4438598.02 | 1 | 0 | COMPLETED | 1 |  |  |  |  | 2021-07-28 | 2021-08-03 | 2021-08-16 |  |  |  | for Contract Signing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Quirino | 104356 | La Conwap ES | NAGTIPUNAN | 0 | 1 | 4 | Repair of Classrooms | 1716600.17 | 1 | 1706378.11 | COMPLETED | 1 |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-27 | Atlantic Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Santiago City | 500938 | Sinili Integrated School | CITY OF SANTIAGO | 4 | 1 | 8 | Repair of Classrooms | 2789132.95 | 1 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Tuguegarao City | 104384 | Balzain East ES | TUGUEGARAO CITY(Capital) | 3 | 1 | 12 | Repair of classrooms | 1046550.08 | 1 | 0 | COMPLETED | 1 | [10 empty] | procured | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Tuguegarao City | 300668 | Cagayan National High Sschool | TUGUEGARAO CITY(Capital) | 3 | 1 | 48 | Repair of classrooms | 1953449.9 | 1 | 0 | COMPLETED | 1 | [10 empty] | procured | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2022 | Region II | Batanes | 501736 | Valugan Integrated School | BASCO (Capital) | 0 | 1 | 6 | Repair of Classrooms | 3487110.41 | 1 | 2950000 | COMPLETED | 1 | [10 empty] | SARO received last August 8, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 44986 | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Batanes | 102328 | Sabtang Central School | SABTANG | 0 | 1 | 7 | Repair of Classrooms | 2539099.16 | 1 | 2100000 | COMPLETED | 1 | [9 empty] | KNB Construction | SARO received last August 8, 2022. Waiting for the Variation Order. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 | 44986 | 5.24 |  |  |  |  | COMPLETED
REPAIR 2022 | Region II | Cagayan | 102838 | Illuru ES | RIZAL | 2 | 1 | 3 | Repair of Classrooms | 1001370.08 | 1 | 0 | COMPLETED | 1 | 2023-01-20 | 2022-11-18 | REPAIR 2022-RII-CAGAYAN-001 | INFRA 2022-068 LOT 1 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region II | Cagayan | 102842 | Mauanan Elementary School | RIZAL | 2 | 1 | 4 | Repair of Classrooms | 1277209.13 | 1 | 0 | COMPLETED | 1 | 2023-01-20 | 2023-01-27 | REPAIR 2022-RII-CAGAYAN-001 | INFRA 2022-068 LOT 1 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Cagayan | 102921 | Sta. Praxedes CS | SANTA PRAXEDES | 2 | 1 | 7 | Repair of Classrooms | 1433625.6 | 1 | 0 | COMPLETED | 1 | 2023-01-20 |  | REPAIR 2022-RII-CAGAYAN-001 | INFRA 2022-068 LOT 1 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103344 | Guibang Elementary School | GAMU | 2 | 1 | 12 | Repair of Classrooms | 4911086.63 | 2 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 45017 | 6.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 300565 | Palayan Region High School | ALICIA | 3 | 1 | 17 | Repair of Classrooms | 6381474.7 | 2 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103052 | Angadanan Central School | ANGADANAN | 3 | 1 | 6 | Repair of Classrooms | 3073731.89 | 2 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103067 | San Ambrocio Elementary School | ANGADANAN | 3 | 1 | 2 | Repair of Classrooms | 1611819.42 | 2 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 300502 | Villa Domingo National High School | ANGADANAN | 3 | 1 | 9 | Repair of Classrooms | 2242253.51 | 2 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103484 | Bustamante Elementary School | LUNA | 5 | 1 | 2 | Repair of Classrooms | 700749.68 | 1 | 0 | COMPLETED | 1 |  |  |  | 44715 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | Arevalo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region II | Isabela | 500970 | Sto. Domingo-San Isidro Integrated School | LUNA | 5 | 1 | 6 | Repair of Classrooms | 3224814.73 | 1 | 0 | COMPLETED | 1 |  |  |  | 44715 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | Arevalo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103719 | San Manuel Central School | SAN MANUEL | 5 | 1 | 14 | Repair of Classrooms | 8222849.33 | 2 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 1 | 0 | 45017 | 5.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103334 | Gucab Elementary School | ECHAGUE | 6 | 1 | 10 | Repair of Classrooms | 2957750.54 | 2 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 | 45017 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 300590 | San Guillermo Vocational & Industrial High School | SAN GUILLERMO | 6 | 1 | 14 | Repair of Classrooms | 5899546.51 | 2 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 1 | 0 | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103699 | Capayacan Elementary School | SAN ISIDRO | 6 | 1 | 5 | Repair of Classrooms | 1676883.48 | 1 | 0 | COMPLETED | 1 |  |  |  | 44714 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | Arevalo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103708 | Dona Paulina Elementary School | SAN ISIDRO | 6 | 1 | 1 | Repair of Classroom | 856701.71 | 2 | 1234173.09 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 45017 | 6.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 306123 | Manuel L. Quezon National High School | SAN ISIDRO | 6 | 1 | 12 | Repair of Classrooms | 3015522.35 | 2 | 1604724.29 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103702 | Nagbukel Elementary School | SAN ISIDRO | 6 | 1 | 4 | Repair of Classrooms | 1544709.37 | 2 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 45017 | 6.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103705 | Ramos Elementary School | SAN ISIDRO | 6 | 1 | 14 | Repair of Classrooms | 2854123.08 | 2 | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 1 | 0 | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103709 | Villaflor Elementary School | SAN ISIDRO | 6 | 1 | 4 | Repair of Classrooms | 1076711.08 | 1 | 0 | COMPLETED | 1 |  |  |  | 44714 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | Arevalo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region II | Nueva Vizcaya | 281559 | Hukhukyung Primary School | AMBAGUIO | 0 | 1 | 2 | Repair of Classrooms | 1590953 | 1 | 1351108.85 | COMPLETED | 1 | 2023-02-21 |  | PB10-01-CY2022 BEFF-RoC-Infra-Lot 1 |  | 2020-10-26 | 2022-11-03 | 2022-11-15 | 2022-12-19 | 2022-12-19 | Mighty Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Nueva Vizcaya | 104221 | Turod Elementary School | VILLAVERDE | 0 | 1 | 3 | Repair of Classrooms | 1672224 | 1 | 1412362.55 | COMPLETED | 1 | 2023-03-30 |  | PB10-01-CY2022 BEFF-RoC-Infra-Lot 2 |  | 2020-10-26 | 2022-11-03 | 2022-11-15 | 2022-12-01 | 2022-12-16 | I.A. Castaneda Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Quirino | 104373 | Dibul ES | SAGUDAY | 0 | 1 | 2 | Repair of Classrooms | 186296.13 | 2 | 186296.13 | COMPLETED | 1 | [7 empty] | 2022-09-09 | 2022-10-17 | FNS Builders & Enterprise | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Quirino | 104381 | Lumagui ES | SAGUDAY | 0 | 1 | 4 | Repair of Classrooms & Toilets | 974789.14 | 1 | 842413.23 | COMPLETED | 1 |  |  |  |  | 2022-04-28 | 2022-05-05 | 2022-05-23 | 2022-06-15 | 2022-08-26 | FNS Builders & Enterprise | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region II | Quirino | 104376 | Magsaysay ES | SAGUDAY | 0 | 1 | 12 | Repair of Classrooms | 1226272.55 | 1 | 1155941.97 | COMPLETED | 1 |  |  |  |  | 2022-04-28 | 2022-05-05 | 2022-05-23 | 2022-06-15 | 2022-08-26 | FNS Builders & Enterprise | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2023 | Region II | Batanes | 300411 | Batanes Nat"l Science High School | BASCO (Capital) | Lone | 1 | 21 | Repair of Classrooms | 5441432.43 | DPWH (Batch 1) | 4724632.2 | COMPLETED | 1 | January 21, 2024 | January 21, 2024 |  | 23BA0059 | [5 empty] | J.F GABOTERA INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Batanes | 300414 | Itbayat National Agricultural High School | ITBAYAT | Lone | 1 | 6 | Repair of Classrooms | 2784191.27 | DPWH (Batch 1) | 2685153.17 | COMPLETED | 1 | December 8, 2023 | November 16, 2023 |  | 23BA0062 | [5 empty] | MOJR CONST., TRADING AND GE. SERVICES LTD. CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Batanes | 102322 | Ivana Elementary School | IVANA | Lone | 1 | 3 | Repair of Classrooms | 2086393.1 | DPWH (Batch 1) | 2013368.34 | COMPLETED | 1 | December 12, 2023 | January 15, 2024 |  | 23BA0064 | [5 empty] | PC VALENCIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Batanes | 300417 | Sabtang National School of Fisheries | SABTANG | Lone | 1 | 8 | Repair of Classrooms | 8623639.08 | DPWH (Batch 1) | 6728184.78 | Ongoing | 0.85 | February 14, 2024 |  |  | 23BA0066 | [5 empty] | JERIS CONSTRUCTION AND SUPPLY | Ongoing contract subejct to liquidated damages | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0.85 | 0 | [6 empty] | ongoing
REPAIR 2023 | Region II | Batanes | 300413 | Batanes Gen. Comp. HS | UYUGAN | Lone | 1 | 6 | Repair of Classrooms | 2021931.7 | DPWH (Batch 1) | 1946156.1 | COMPLETED | 1 | December 8, 2023 | January 24, 2024 |  | 23BA0061 | [5 empty] | SWIFT DEV'T AND SUPPLIES CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Batanes | 102324 | Uyugan Elementary School | UYUGAN | Lone | 1 | 8 | Repair of Classrooms | 4162420.7 | DPWH (Batch 1) | 3711074.29 | COMPLETED | 1 | December 9, 2023 | February 28, 2024 |  | 23BA0060 | [5 empty] | J.F GABOTERA INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102331 | Abulug Central Elementary School | ABULUG | 2nd | 1 | 5 | Repair of Classrooms | 2678156.25 | DPWH (Batch 2) | 2557794.55 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0266 |  |  |  | 12/27/23 | 12/27/23 | JG YAKAS CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300418 | Abulug National Rural and Vocational High School | ABULUG | 2nd | 1 | 4 | Repair of Classrooms | 1827157.13 | DPWH (Batch 2) | 1745479.65 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0240 |  |  |  | 12/27/2023 | 12/27/2023 | JG YAKAS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300419 | Abulug SOF | ABULUG | 2nd | 1 | 9 | Repair of Classrooms | 5260296.29 | DPWH (Batch 2) | 5024938.59 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING WITH 9 CL | 23BC0245 | October 26, 2023 | November 6, 2023 | November 20, 2023 | 12/21/2024 | 12/21/2024 | JG YAKAS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | 12.24 |  |  |  |  | completed
REPAIR 2023 | Region II | Cagayan | 102333 | Bagu ES | ABULUG | 2nd | 1 | 3 | Repair of Classrooms | 1712200.98 | DPWH (Batch 2) | 1635484.62 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-3CL | 23BC0259 |  |  |  | 12/27/23 | 12/27/23 | JG YAKAS CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102334 | Banguian ES | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1227187.5 | DPWH (Batch 2) | 1172334.44 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-2CL | 23BC0212 |  |  |  | 12/27/2023 | 12/27/2023 | JG YAKAS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102335 | Calog Norte ES | ABULUG | 2nd | 1 | 1 | Repair of Classrooms | 1732500 | DPWH (Batch 2) | 1654668.7 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-1-CL | 23BC0213 |  |  |  | 12/27/2023 | 12/27/2023 | JG YAKAS CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102336 | CALOG SUR ELEMENTARY SCHOOL | ABULUG | 2nd | 1 | 4 | Repair of Classrooms | 1386000 | DPWH (Batch 2) | 1386000 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102337 | Canayun ES | ABULUG | 2nd | 1 | 1 | Repair of Classrooms | 1198312.5 | DPWH (Batch 2) | 1134423.11 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING 1CL | 23BC0249 |  |  |  | 12/27/23 | 12/27/23 | OLIVA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102338 | Dana-ili ES | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1227718.5 | DPWH (Batch 2) | 1160880.2 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-2CL | 23BC0248 |  |  |  | 12/27/23 | 12/27/23 | OLIVA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102340 | Guiddam ES | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1227187.5 | DPWH (Batch 2) | 1227187.5 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102341 | Libertad Elementary School | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1176656.25 | DPWH (Batch 2) | 1124101 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-2CL | 23BC0236 |  |  |  | 12/27/2023 | 12/27/2023 | JG YAKAS CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102342 | Lucban ES | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1422093.75 | DPWH (Batch 2) | 1422093.75 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102343 | Macugay ES | ABULUG | 2nd | 1 | 4 | Repair of Classrooms | 1155000 | DPWH (Batch 2) | 1103303.18 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0242 |  |  |  | 12/27/2023 | 12/27/23 | JG YAKAS CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102344 | Muru ES | ABULUG | 2nd | 1 | 3 | Repair of Classrooms | 1849443.75 | DPWH (Batch 2) | 1741849.36 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-3CL | 23BC0247 | October 26, 2023 | November 6, 2023 | November 20, 2023 | 12/27/23 | 12/27/23 | OLIVA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 1.25 |  |  |  |  | completed
REPAIR 2023 | Region II | Cagayan | 102345 | Pinili ES | ABULUG | 2nd | 1 | 3 | Repair of Classrooms | 1227187.5 | DPWH (Batch 2) | 1172387.2 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-3CL | 23BC0207 |  |  |  | 12/27/2023 |  | JG YAKAS CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102346 | San Agustin ES | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1010625 | DPWH (Batch 2) | 965491.39 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-2CL | 23BC0241 |  |  |  | 12/27/2023 | 12/27/2023 | JG YAKAS CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102347 | San Julian ES | ABULUG | 2nd | 1 | 1 | Repair of Classrooms | 2165625 | DPWH (Batch 2) | 2074828.12 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING -4CL | 23BC0205 |  |  |  | December 21, 2023 | December 21, 2023 | ILIVA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102349 | Simayung ES | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1082812.5 | DPWH (Batch 2) | 1023601.61 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-2 CL | 23BC0243 |  |  |  | 12/27/23 | 12/27/23 | OLIVA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102351 | Sta. Filomena ES | ABULUG | 2nd | 1 | 4 | Repair of Classrooms | 1118906.25 | DPWH (Batch 2) | 1068759.65 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0250 |  |  |  | 12/27/2023 | 12/27/23 | JG YAKAS CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102354 | Tayak ES | ABULUG | 2nd | 1 | 4 | Repair of Classrooms | 1479843.75 | DPWH (Batch 2) | 1479843.75 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102603 | Alimoan ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1481826.35 | DPWH (Batch 2) | 1406765.15 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0224 |  |  |  | 12/27/202 | 12/27/2023 | BA Lagazo |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102605 | Bilibigao ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1429129.76 | DPWH (Batch 2) | 1368760.88 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0232 |  |  |  | 12/27/2023 | 12/27/2023 | JPO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102606 | Buenavista-San Isidro ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1343792.21 | DPWH (Batch 2) | 1270855.92 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4cl | 23bc0225 |  |  |  | 12/27/2023 | 12/27/2023 | BJMBJ CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102608 | Claveria CS | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1429129.76 | DPWH (Batch 2) | 1365308.64 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0257 |  |  |  | 12/27/23 | 12/27/23 | VG ALCANTARA INTERPRICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102609 | Claveria East CS | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1404969.94 | DPWH (Batch 2) | 135463.32 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0231 |  |  |  | 12/27/2023 | 12/27/2023 | VG ALCANTARA INTERPRICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300450 | Claveria RVS | CLAVERIA | 2nd | 1 | 5 | Repair of Classrooms | 1915078.41 | DPWH (Batch 2) | 1820329.91 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0221 |  |  |  | 12/27/2023 | 12/27/2023 | OLIVA DESIGN CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300451 | Claveria SAT | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1648763.23 | DPWH (Batch 2) | 1575145.95 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0216 |  |  |  | 12/27/2023 | 12/27/2023 | RJJ ARISTOTEL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102610 | Culao ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1404969.94 | DPWH (Batch 2) | 1339799.71 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0223 |  |  |  | 12/27/2023 | 12/27/2023 | 5RD KECK CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102611 | Dibalio ES | CLAVERIA | 2nd | 1 | 5 | Repair of Classrooms | 1648763.23 | DPWH (Batch 2) | 1556671.53 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0244 |  |  |  | 12/27/23 | 12/27/23 | MARTHA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102919 | Lablabig ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1445475.27 | DPWH (Batch 2) | 1374738.96 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING 4 CL | 23BC0208 |  |  |  | 12/27/2023 |  | A. NIDUAZA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102612 | Luzon ES | CLAVERIA | 2nd | 1 | 2 | Repair of Classrooms | 1115354.62 | DPWH (Batch 2) | 1115354.62 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102920 | Mabnang ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1445475.27 | DPWH (Batch 2) | 1363897.54 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING - 4CL | 23BC0207 |  |  |  | 12/27/2023 |  | 5RDKECK CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102615 | Malilitao ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1404969.94 | DPWH (Batch 2) | 1328640.59 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0229 |  |  |  | 12/27/2023 | 12/27/2023 | BJMJB CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102616 | Mapulapula Elementary School | CLAVERIA | 2nd | 1 | 5 | Repair of Classrooms | 1481826.35 | DPWH (Batch 2) | 1406302.94 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0217 |  |  |  | 12/27/2023 | 12/27/2023 | BA LAGAZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102617 | Nagsabaran ES | CLAVERIA | 2nd | 1 | 2 | Repair of Classrooms | 1115354.62 | DPWH (Batch 2) | 1054791.25 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-2CL | 23BC0238 |  |  |  | 12/27/2023 | 12/27/2023 | BJMBJ CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102619 | Pinas ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1404969.94 | DPWH (Batch 2) | 1328865.35 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0218 |  |  |  | 12/27/2023 | 12/27/2023 | OLIVA DESIGN CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102620 | San Vicente Primary School | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1481826.35 | DPWH (Batch 2) | 1481826.35 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102621 | Santiago ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1450732.52 | DPWH (Batch 2) | 1371992.86 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0226 |  |  |  | 12/27/2023 | 12/27/2023 | BJMJB CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102622 | Sta. Maria PS | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1404969.94 | DPWH (Batch 2) | 1329120.32 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0260 | November 8, 2023 | November 16, 2023 | November 28, 2023 | 12/27/23 | 12/27/23 | DANDEX CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 12.24 |  |  |  |  | completed
REPAIR 2023 | Region II | Cagayan | 102623 | Sto. Tomas PS | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1481826.35 | DPWH (Batch 2) | 1404433.81 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC027 |  |  |  | 12/27/2023 | 12/27/2023 | BJMJB CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 155032 | Taggat Norte Elementary School | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1481826.35 | DPWH (Batch 2) | 1409925.69 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING 4 CL | 23BC0209 |  |  |  | 12/27/2023 | 12/27/2023 | 5RDKECK CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102922 | Taggat Sur ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1481826.35 | DPWH (Batch 2) | 1415662.81 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0222 |  |  |  | 12/27/2023 | 12/27/2023 | RJJ ARISTOTEL CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102923 | UNION ELEMENTARY SCHOOL | CLAVERIA | 2nd | 1 | 5 | Repair of Classrooms | 1915078.41 | DPWH (Batch 2) | 1825279.4 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING- 5CL | 23BC02010 |  |  |  | 12/27/2023 | 12/27/2023 | A. NIDUAZA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102784 | Bidduang ES | PAMPLONA | 2nd | 1 | 5 | Repair of Classrooms | 4000000 | DPWH (Batch 2) | 3743792.65 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING5CL | 23BC0244 |  |  |  | 12/27/23 | 12/27/23 | OLIVA DESIGN CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300436 | Bidduang National High School | PAMPLONA | 2nd | 1 | 5 | Repair of Classrooms | 1915078.41 | DPWH (Batch 2) | 1801665.02 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0229 |  |  |  | 12/27/2023 | 12/27/2023 | OLIVA DESIGN CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102788 | Curva Elementary School | PAMPLONA | 2nd | 1 | 5 | Repair of Classrooms | 2000000 | DPWH (Batch 2) | 1914999.29 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0230 |  |  |  | 12/27/2023 | 02/27/2023 | OLIVA DESIGN CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102792 | Pimpila ES | PAMPLONA | 2nd | 1 | 5 | Repair of Classrooms | 4463486.51 | DPWH (Batch 2) | 4178015.24 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0261 |  |  |  | 12/27/23 | 12/27/23 | OLIVA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102839 | Lattut ES | RIZAL | 2nd | 1 | 2 | Repair of Classrooms | 1321776.89 | DPWH (Batch 1) | 1321776.89 | Ongoing | 0.7222 |  |  | REPAIR OF CLASSROOM | 23BC125 | September 1, 2023 | September 8, 2023 | September 25, 2023 | 2023-03-10 | 2023-03-10 | KSC CONST |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0.651 | 0.0712 | [6 empty] | ongoing
REPAIR 2023 | Region II | Cagayan | 102844 | Rizal CS | RIZAL | 2nd | 1 | 4 | Repair of Classrooms | 1436921.32 | DPWH (Batch 2) | 1368896.49 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0219 | October 6, 2023 | October 16, 2023 | October 27, 2023 | 12/27/2023 | 12/27/2023 | KSC CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | completed
REPAIR 2023 | Region II | Cagayan | 102846 | Sinicking ES | RIZAL | 2nd | 1 | 3 | Repair of Classrooms | 1936863.12 | DPWH (Batch 1) | 1850382.18 | Completed | 1 |  |  | REPAIR OF CLASSROOM | 23BC0124 | September 1, 2023 | September 8, 2023 | September 25, 2023 | 2023-03-10 | 2023-03-10 | KSC CONST | ABANDONED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0.3177 | 0.6823 |  | 5.25 |  |  |  |  | ongoing
REPAIR 2023 | Region II | Cagayan | 102848 | Bangan ES | SANCHEZ-MIRA | 2nd | 1 | 5 | Repair of Classrooms | 3200000 | DPWH (Batch 2) | 3052938.24 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0214 |  |  |  | 12/27/2023 | 12/27/2023 | JPO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 155046 | Pureg Elementary School | SANCHEZ-MIRA | 2nd | 1 | 5 | Repair of Classrooms | 3000000 | DPWH (Batch 2) | 3000000 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2nd | 1 | 5 | Repair of Classrooms | 4500000 | DPWH (Batch 2) | 4299168.59 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0258 |  |  |  | 12/27/23 | 12/27/23 | JPO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102915 | Cadcadir ES | SANTA PRAXEDES | 2nd | 1 | 4 | Repair of Classrooms | 1446232.87 | DPWH (Batch 2) | 1367702.43 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0211 |  |  |  | 12/27/2023 | 12/27/2023 | BMJB CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102917 | Capacuan ES | SANTA PRAXEDES | 2nd | 1 | 5 | Repair of Classrooms | 2000000 | DPWH (Batch 2) | 1910682.1 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0215 |  |  |  | 12/27/2023 | 12/27/2023 | JPO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102921 | Sta. Praxedes CS | SANTA PRAXEDES | 2nd | 1 | 5 | Repair of Classrooms | 3500000 | DPWH (Batch 2) | 3343725.46 | COMPLETED | 1 |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0220 |  |  |  | 12/27/2023 | 12/27/2023 | JPO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300489 | Sta. Praxedes High School | SANTA PRAXEDES | 2nd | 1 | 15 | Repair of Classrooms | 3202208.92 | DPWH (Batch 1) | 3042863.65 | COMPLETED | 1 |  |  | REPAIR OF SCHHOL BUILDING | 23B123 |  |  |  | 2023-03-10 | 2023-03-10 | A. NIDUAZA BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300489 | Sta. Praxedes High School | SANTA PRAXEDES | 2nd | 1 | 5 | Repair of Classrooms | 3200000 | DPWH (Batch 2) | 3042863.65 | COMPLETED | 1 |  |  | REPAIR OF SCHHOL BUILDING | 23BC123 |  |  |  | 2023-03-10 | 2023-03-10 | A. NIDUAZA BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | City of Ilagan | 103359 | Batong Labang ES | CITY OF ILAGAN | 1st | 1 | 7 | Repair of Classrooms | 6192545.4 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  |  | 23BE0152 | July 21, 2023 to July 27, 2023 | 2023-07-28 | August 10, 2023 | 2023-08-30 | September 8, 2023 | SMT Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Isabela | 103277 | San Macario Elementary School | DELFIN ALBANO (MAGSAYSAY) | 1st | 1 | 4 | Repair of Classrooms | 3172583.45 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0.95 | 0.05 |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region II | Isabela | 103733 | Caunayan Elementary School | SAN MARIANO | 2nd | 1 | 2 | Repair of Classrooms | 2080135.57 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0.8 | 0.2 |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region II | Isabela | 103484 | Bustamante Elementary School | LUNA | 5th | 1 | 3 | Repair of Classrooms | 1945125 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  | 23BF0104 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Isabela | 103489 | Harana Elementary School | LUNA | 5th | 1 | 1 | Repair of Classroom | 1296750 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  | 23BF0108 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Isabela | 103486 | Lalog Elementary School | LUNA | 5th | 1 | 2 | Repair of Classrooms | 1945125 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  | 23BF0105 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Isabela | 103487 | Luna Central School | LUNA | 5th | 1 | 1 | Repair of Classroom | 4538625 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  | 23BF0102 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Isabela | 306150 | Luna General Comprehensive High School | LUNA | 5th | 1 | 2 | Repair of Classrooms | 1304021.86 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  | 23BF0106 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Isabela | 300558 | Luna National High School | LUNA | 5th | 1 | 4 | Repair of Classrooms | 2593500 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  | 23BF0103 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Isabela | 103488 | Mambabanga Elementary School | LUNA | 5th | 1 | 2 | Repair of Classrooms | 1296750 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  | 23BF0107 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Isabela | 103565 | Callangigan Elementary School | Quezon | 5th | 1 | 3 | Repair of Classrooms | 950000 | DEPED (Batch 1) | 1449861.74 | COMPLETED | 1 | 90 days after the receipt of the Notice to Proceed |  |  | Contract No. 2023-10-03 |  | 2023-09-26 | 2023-10-09 | 2023-10-17 | 2023-11-03 | Fragerr Construction | Same Contractor for CY 2023 BASIC EDUCATION FACILITIES FUND (BEFF) REPAIR OF CLASSROOMS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region II | Isabela | 500067 | Dolores Integrated School | Quirino | 5th | 1 | 2 | Repair of Classrooms | 950000 | DEPED (Batch 1) | 1449861.74 | COMPLETED | 1 | 90 days after the receipt of the Notice to Proceed |  |  | Contract No. 2023-10-03 |  | 2023-09-26 | 2023-10-09 | 2023-10-17 | 2023-11-03 | Fragerr Construction | Same Contractor for CY 2023 BASIC EDUCATION FACILITIES FUND (BEFF) REPAIR OF CLASSROOMS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1.24 | 12.23 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region II | Isabela | 103699 | Capayacan Elementary School | SAN ISIDRO | 6th | 1 | 6 | Repair of Classrooms | 1477032.01 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  | 23BH0245 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Isabela | 103704 | Quezon Elementary School | SAN ISIDRO | 6th | 1 | 11 | Repair of Classrooms | 4907044.15 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  | 23BH0247 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Isabela | 103705 | Ramos Elementary School | SAN ISIDRO | 6th | 1 | 9 | Repair of Classrooms | 1595303.57 | DPWH (Batch 1) |  | COMPLETED | 1 |  |  | 23BH0246 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Nueva Vizcaya | 156012 | Lihlit PS | AMBAGUIO | Lone | 1 | 3 | Repair of Classrooms | 2274570 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Nueva Vizcaya | 104213 | Bintawan North Elementary School | VILLAVERDE | Lone | 1 | 3 | Repair of Classrooms | 2145220 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Nueva Vizcaya | 104214 | Bintawan South Elementary School | VILLAVERDE | Lone | 1 | 3 | Repair of Classrooms | 1974080 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Nueva Vizcaya | 104216 | Nagbitin ES | VILLAVERDE | Lone | 1 | 3 | Repair of Classrooms | 2186015 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Nueva Vizcaya | 104217 | Ocapon Elementary School | VILLAVERDE | Lone | 1 | 1 | Repair of Classroom | 768050 | DEPED (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Quirino | 104376 | Magsaysay ES | SAGUDAY | Lone | 1 | 2 | Repair of Classrooms | 1287500 | DPWH (Batch 1) | 1242437.41 | COMPLETED | 1 | 2024-01-23 | 2024-01-07 | P00775089NP | 23BK0128 | 2023-08-25 | 2023-09-07 | 2023-09-19 | 2023-09-29 | 2023-10-10 | JMD-68 BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Quirino | 104377 | SAGUDAY CENTRAL SCHOOL | SAGUDAY | Lone | 1 | 3 | Repair of Classrooms | 1937500 | DPWH (Batch 1) | 1869396.75 | COMPLETED | 1 | 2024-02-18 | 2024-01-19 | P00775090NP | 23BK0129 | 2023-09-08 | 2023-09-21 | 2023-10-03 | 2023-10-12 | 2023-10-25 | JMD-68 BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Quirino | 300665 | Saguday NHS | SAGUDAY | Lone | 1 | 5 | Repair of Classrooms | 3237500 | DPWH (Batch 1) | 3030207.84 | COMPLETED | 1 | 2024-05-24 | 2024-04-12 | P00775091NP | 23BK0127 | 2023-08-25 | 2023-09-07 | 2023-09-19 | 2023-09-26 | 2024-01-04 | JMD-68 BUILDERS | for Final Inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Batanes | 501736 | Valugan Integrated School | BASCO (Capital) | Lone | 1 | 2 | Repair of Classrooms | 1326118.32 | 1 | 1304928.76 | Ongoing | 0.9 | June 23, 2025 | N/a | 2024-08-04 | 2024-08-04 | 09-16-24 | August 22, 2024 | September 16, 2024 |  | October 16, 2024 | Knb Construction | Resumption Date : January 15, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0.75 | 0.15 | [6 empty] | Ongoing
REPAIR 2024 | Region II | Batanes | 300415 | Ivana NHS | IVANA | Lone | 1 | 4 | Repair of Classrooms | 2686868.69 | 1 | 2652129.98 | Ongoing | 0 | June 23, 2025 | N/a | 2024-08-04 | 2024-08-04 | 09-16-24 | August 22, 2024 | September 16, 2024 |  | October 16, 2024 | Knb Construction | Resumption Date : January 15, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Ongoing
REPAIR 2024 | Region II | Batanes | 102330 | Sumnanga Elementary School | SABTANG | Lone | 1 | 2 | Repair of Classrooms | 1356421.35 | 1 | 1340480.07 | Ongoing | 0 | June 23, 2025 | N/a | 2024-08-04 | 2024-08-04 | 09-16-24 | August 22, 2024 | September 16, 2024 |  | October 16, 2024 | Knb Construction | Resumption Date : January 15, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Ongoing
REPAIR 2024 | Region II | Batanes | 500062 | Itbud Integrated School | UYUGAN | Lone | 1 | 2 | Repair of Classrooms | 1343434.34 | 1 | 1328045.66 | Ongoing | 0.2 | June 23, 2025 | N/a | 2024-08-04 | 2024-08-04 | 09-16-24 | August 22, 2024 | September 16, 2024 |  | October 16, 2024 | Knb Construction | Resumption Date : January 15, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0.2 | [6 empty] | Ongoing
REPAIR 2024 | Region II | Cagayan | 102370 | Malalatan ES | ALCALA | 1st | 1 | 8 | Repair of Classrooms | 3507780.79 | 1 |  | COMPLETED | 1 |  |  | Repair rehabilitation of Classroom under cy 2024 beff batch 1 | Infra2024-076 LOT 1 | July 16, 2024 | AUGUST 6, 2024 | AUGUST 6, 2024 |  |  |  | UNDER PROCUREMENT: ONGOING OF ARITHMETIC AND DOCUMENTS EVALUATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Cagayan | 300456 | Don Severino Pagalilauan National High School | PEÑABLANCA | 3rd | 1 | 4 | Repair of Classrooms | 2114928.35 | 1 |  | COMPLETED | 1 |  |  | Repair rehabilitation of Classroom under cy 2024 beff batch 1 | Infra2024-076 LOT 2 | July 16, 2024 | AUGUST 6, 2024 | AUGUST 6, 2024 |  |  |  | UNDER PROCUREMENT: ONGOING OF ARITHMETIC AND DOCUMENTS EVALUATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Cagayan | 102806 | Penablanca East CS | PEÑABLANCA | 3rd | 1 | 6 | Repair of Classrooms | 2605614.16 | 1 |  | COMPLETED | 1 |  |  | Repair rehabilitation of Classroom under cy 2024 beff batch 1 | Infra2024-076 LOT 3 | July 16, 2024 | AUGUST 6, 2024 | AUGUST 6, 2024 |  |  |  | UNDER PROCUREMENT: ONGOING OF ARITHMETIC AND DOCUMENTS EVALUATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Cagayan | 102819 | Sisim ES | PEÑABLANCA | 3rd | 1 | 3 | Repair of Classrooms | 1569656.49 | 1 |  | COMPLETED | 1 |  |  | Repair rehabilitation of Classroom under cy 2024 beff batch 1 | Infra2024-076 LOT 4 | July 16, 2024 | AUGUST 6, 2024 | AUGUST 6, 2024 |  |  |  | UNDER PROCUREMENT: ONGOING OF ARITHMETIC AND DOCUMENTS EVALUATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Cauayan City | 103214 | Duminit ES | CITY OF CAUAYAN | 3rd | 1 | 3 | Repair of Classrooms | 1818181.82 | 1 | 1102412.45 | COMPLETED | 1 | 2025-01-11 |  | Repair/Rehabilitation of Classroom of Duminit Elementary School (Lot 1) | CW-001 S. 2024 (LOT 1) | 2024-06-29 | 2024-07-08 | 2024-07-22 | 2024-08-06 | 2024-10-14 | GCPK Construction and Supply | For Final Inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Cauayan City | 103217 | Guayabal ES | CITY OF CAUAYAN | 3rd | 1 | 8 | Repair of Classrooms | 4363636.36 | 1 | 2811753.92 | COMPLETED | 1 | 2025-01-11 |  | Repair/Rehabilitation of Classroom of Guayabal Elementary School (Lot 2) | CW-001 S. 2024 (LOT 2) | 2024-06-29 | 2024-07-08 | 2024-07-22 | 2024-08-06 | 2024-10-14 | GCPK Construction and Supply | For Final Inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Cauayan City | 300613 | Villa Concepcion National High School | CITY OF CAUAYAN | 3rd | 1 | 9 | Repair of Classrooms | 3616161.62 | 1 | 2253082.76 | COMPLETED | 1 | 2025-01-11 |  | Repair/Rehabilitation of Classroom of Villa Concepcion National High School (Lot 3) | CW-001 S. 2024 (LOT 3) | 2024-06-29 | 2024-07-08 | 2024-07-22 | 2024-08-06 | 2024-10-14 | GCPK Construction and Supply | For Final Inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | City of Ilagan | 103418 | Cabannungan 1st Elementary School | ILAGAN CITY (CAPITAL) | 1st | 1 | 3 | Repair of Classrooms | 2595959.6 | 1 | 2595959.6 | COMPLETED | 1 | 2024-12-27 | 2024-09-22 |  | INF-2024-R02 | 2024-08-03 | 2024-08-12 | 2024-08-28 | 2024-09-09 | 2024-09-26 | Oroset Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region II | City of Ilagan | 103419 | Cabannungan 2nd ES | ILAGAN CITY (CAPITAL) | 1st | 1 | 3 | Repair of Classrooms | 2393939.39 | 1 | 2357905.57 | completed | 1 | 2024-02-14 |  |  |  | September 20, 2024 | September 30, 2024 | October 14, 2024 | October 30, 2024 | Novemner 12, 2024 | RSKC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0.9 | 0.1 |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region II | City of Ilagan | 103427 | Mangcuram ES | ILAGAN CITY (CAPITAL) | 1st | 1 | 4 | Repair of Classrooms | 3191919.19 | 1 | 3109253.81 | completed | 1 | 2024-02-14 |  |  |  | September 20, 2024 | September 30, 2024 | October 14, 2024 | October 30, 2024 | Novemner 12, 2024 | RSKC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0.6 | 0.4 |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region II | City of Ilagan | 103369 | Minabang Elementary School | ILAGAN CITY (CAPITAL) | 1st | 1 | 5 | Repair of Classrooms | 1616161.62 | 1 | 1589149.96 | COMPLETED | 1 | 2024-12-27 |  |  | INF-2024-R02 | 2024-08-03 | 2024-08-12 | 2024-08-28 | 2024-09-09 | October 4, 2024 | Atlantic Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 1.25 |  |  |  |  | completed
REPAIR 2024 | Region II | Isabela | 501317 | Bayabo East Integrated School | TUMAUINI | 1st | 1 | 7 | Repair of Classrooms | 2869807.43 | 1 | 2803801.8625 | COMPLETED | 1 |  |  |  |  | August 02,2024 | August 13, 2024 | August 27,2024 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region II | Isabela | 500732 | New Magsaysay Integrated School | BENITO SOLIVEN | 2nd | 1 | 6 | Repair of Classrooms | 3632179.02 | 1 |  | COMPLETED | 1 |  |  |  |  | August 02,2024 | August 13, 2024 | August 27,2024 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Isabela | 103168 | Canan Elementary School | CABATUAN | 3rd | 1 | 3 | Repair of Classrooms | 1799433.72 | 1 |  | COMPLETED | 1 |  |  |  |  | August 02,2024 | August 13, 2024 | August 27,2024 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Isabela | 306160 | Nueva Era National High School | SAN MANUEL | 5th | 1 | 2 | Repair of Classrooms | 1565873.82 | 1 |  | COMPLETED | 1 |  |  |  |  | August 02,2024 | August 13, 2024 | August 27,2024 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Nueva Vizcaya | 103908 | Banganan ES | ARITAO | Lone | 1 | 4 | Repair of Classrooms | 3434343.43 | 1 | 2263457.35 | Ongoing | 0.75 |  |  | PB 12-001 s. 2024 |  | September 9, 2024 | October 2, 2024 | October 14, 2024 | December 4, 2024 | December 16, 2024 | IA CASTAÑEDA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0.453 | 0.297 | [6 empty] | ONGOING
REPAIR 2024 | Region II | Nueva Vizcaya | 103913 | Canabuan Elementary School | ARITAO | Lone | 1 | 3 | Repair of Classrooms | 2929292.93 | 1 | 2033876.43 | Ongoing | 0.78 |  |  | PB 12-002 s. 2024 |  | September 9, 2024 | October 2, 2024 | October 14, 2024 | December 4, 2024 | December 16, 2024 | IA CASTAÑEDA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0.4223 | 0.3577 | [6 empty] | ONGOING
REPAIR 2024 | Region II | Nueva Vizcaya | 103974 | Mabuslo ES | BAMBANG | Lone | 1 | 4 | Repair of Classrooms | 3434343.43 | 1 | 2187406.39 | Ongoing | 0.8 |  |  | PB 12-003 s. 2024 |  | September 9, 2024 | October 2, 2024 | October 14, 2024 | December 4, 2024 | December 27, 2024 | KNB CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0.344 | 0.456 | [6 empty] | ONGOING
REPAIR 2024 | Region II | Quirino | 104233 | Osmena ES | AGLIPAY | Lone | 1 | 6 | Repair of Classrooms | 2740027.61 | 1 | 1957660.11 | COMPLETED | 1 | 2025-01-08 |  | CY2024 REPAIR/REHAB - II - QUIRINO - 001 | 26-07-19-2024 | 2024-07-20 | 2024-07-26 | 2024-08-07 | 2024-09-18 | 2024-10-10 | WINLEI CONSTRUCTION & SUPPLY | Ongoing / with Contract Time Extension due to continuous rains in the area | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0.7 | 0.3 |  | 5.25 |  |  |  |  | ONGOING
REPAIR 2024 | Region II | Quirino | 104246 | San Ramon ES | AGLIPAY | Lone | 1 | 6 | Repair of Classrooms | 1829716.35 | 1 | 1397714.37 | COMPLETED | 1 | 2025-01-29 |  | CY2024 REPAIR/REHAB - II - QUIRINO - 002 | 27-07-19-2024 | 2024-09-17 | 2024-09-23 | 2024-10-07 | 2024-10-10 | 2024-10-31 | WINLEI CONSTRUCTION & SUPPLY | Ongoing / with Contract Time Extension due to continuous rains in the area | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0.7 | 0.3 |  | 5.25 |  |  |  |  | ONGOING
REPAIR 2024 | Region II | Quirino | 104276 | Andres Bonifacio ES | DIFFUN | Lone | 1 | 9 | Repair of Classrooms | 3914837.05 | 1 | 2935532.63 | COMPLETED | 1 | 2025-01-02 |  | CY2024 REPAIR/REHAB - II - QUIRINO - 003 | 24-07-19-2024 | 2024-07-20 | 2024-07-26 | 2024-08-07 | 2024-09-18 | 2024-10-04 | ACES 3 CONSTRUCTION | Ongoing / with Contract Time Extension due to continuous rains in the area | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0.7 | 0.3 |  | 5.25 |  |  |  |  | ONGOING
REPAIR 2024 | Region II | Quirino | 104305 | Liwanag Elementary School | DIFFUN | Lone | 1 | 3 | Repair of Classrooms | 1388952.1 | 1 | 1150230.96 | COMPLETED | 1 | 2024-12-08 |  | CY2024 REPAIR/REHAB - II - QUIRINO - 004 | 25-07-19-2024 | 2024-07-20 | 2024-07-26 | 2024-08-07 | 2024-09-18 | 2024-10-09 | HJM Construction Services | Ongoing / with Contract Time Extension due to continuous rains in the area | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0.95 | 0.05 |  | 5.25 |  |  |  |  | ONGOING
REPAIR 2024 | Region II | Santiago City | 103811 | Baptista Village ES | CITY OF SANTIAGO | 4th | 1 | 3 | Repair of Classrooms | 1911414.63 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Santiago City | 103837 | Calaocan ES | CITY OF SANTIAGO | 4th | 1 | 6 | Repair of Classrooms | 3499091.07 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Santiago City | 103828 | Patul Elementary School | CITY OF SANTIAGO | 4th | 1 | 4 | Repair of Classrooms | 2582747.67 | 1 |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0.7 | 0.3 |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region II | Santiago City | 501147 | San Jose Integrated School | CITY OF SANTIAGO | 4th | 1 | 3 | Repair of Classrooms | 1800130.7 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Tuguegarao City | 300668 | Cagayan National High School - Junior HS | TUGUEGARAO CITY(Capital) | 3rd | 1 | 12 | Repair of Classrooms | 4242424.24 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0.56 | 0.44 |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region II | Tuguegarao City | 104400 | Tuguegarao North CS | TUGUEGARAO CITY(Capital) | 3rd | 1 | 4 | Repair of Classrooms | 1414141.41 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0.75 | 0.25 |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region II | Tuguegarao City | 104406 | Tuguegarao West CS | TUGUEGARAO CITY(Capital) | 3rd | 1 | 6 | Repair of Classrooms | 2121212.12 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 3.25 |  |  |  |  | Completed

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%