## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | No. of Classrooms | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated | Previous % | Difference | STOREY | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | Status as of July 4, 2025
NEWCON 2016 | REGION III | Angeles City | 500131 | Amsic Is | Angeles City | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [8 empty] | 42523 | J.S. LIM CONST. AND TRADING/511 BUILDERS (JV) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Angeles City | 301038 | Angeles City Nat'L. Trade School | Angeles City | 1 |  | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [8 empty] | 42523 | AL-B DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Angeles City | 301038 | Angeles City Nat'L. Trade School | Angeles City | 1 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [8 empty] | 42523 | B-12 CONSTRUCTION AND TRADING CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Angeles City | 301039 | Angeles City Nhs | Angeles City | 1 |  | 8 | 4STY8CL | BATCH 1 CL | 15634894.782 |  |  | Completed | 1 | [8 empty] | 42523 | J.S. LIM CONST. AND TRADING/511 BUILDERS (JV) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Angeles City | 301039 | Angeles City Nhs | Angeles City | 1 |  | 12 | 4STY12CL | BATCH 1 CL | 23252460.801 |  |  | Completed | 1 | [8 empty] | 42523 | A.D. GONZALES JR. CONST. AND TRADING CO. INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Angeles City | 301039 | Angeles City Nhs | Angeles City | 1 |  | 12 | 4STY12CL | BATCH 1 CL | 23252460.801 |  |  | Completed | 1 | [8 empty] | 42523 | MRRM TRADING AND CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Angeles City | 301039 | Angeles City Nhs | Angeles City | 1 | 1 | 8 | 4STY8CL | BATCH 1 CL | 14897518.84 |  |  | Completed | 1 | [8 empty] | 42523 | MARKNEST CONST AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Angeles City | 301042 | Bonifacio V. Romero Hs | Angeles City | 1 | 1 | 12 | 4STY12CL | BATCH 1 CL | 22152343.62 |  |  | Completed | 1 | [8 empty] | 42523 | BP CRUZ BUILDERS AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Angeles City | 107041 | Gueco Balibago Es | Angeles City | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8296000 |  |  | Completed | 1 | [8 empty] | 42523 | MCB ZAMORA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Angeles City | 107032 | Pineda-Gutierrez Es | Angeles City | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8296000 |  |  | Completed | 1 | [8 empty] | 42523 | RG DIAZ BUILDERS AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Angeles City | PSA328417 | Shs In Brgy. Pandan, Angeles City | Angeles City | 1 | 1 | 12 | 4STY12CL | BATCH 1 CL | 22152343.62 |  |  | Completed | 1 | [8 empty] | 42523 | R.M. VITUG CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Angeles City | PSA328417 | Shs In Brgy. Pandan, Angeles City | Angeles City | 1 |  | 12 | 4STY12CL | BATCH 1 CL | 22152343.62 |  |  | Completed | 1 | [8 empty] | 42523 | R.D. SADSAD CONST. & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Angeles City | 107048 | Sta. Teresita Elementary School | Angeles City | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Aurora | 104452 | Abungan Es To Cabog Es | Dingalan | 0 |  | 1 | 1STY1CL | BATCH 5 CL | 1085000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Aurora | 300672 | Aurora National Science Hs | Baler (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8550000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Aurora | 300673 | Aurora Nhs | Baler (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Aurora | 300677 | Baler Nhs | Baler (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Aurora | 300674 | Bayanihan Nhs | Maria Aurora | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1895000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Aurora | 104452 | Cabog Is | Dingalan | 0 | 1 | 3 | 1STY3CL | BATCH 13 CL | 3000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Aurora | 300679 | Canili Area Nhs | Maria Aurora | 0 | 1 | 4 | 1STY4CL | BATCH 5 CL | 3500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Aurora | 300680 | Casiguran Nhs | Casiguran | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13256310.093 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Aurora | 300680 | Casiguran Nhs | Casiguran | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5392400 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Aurora | 306504 | Diagyan High School | Dilasag | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2560000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Aurora | 306504 | Diagyan High School | Dilasag | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8709965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Aurora | 306507 | Diarabasin Nhs | Dipaculao | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2790000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Aurora | 104433 | Dicabasan Es | Dilasag | 0 | 1 | 3 | 1STY3CL | BATCH 13 CL | 3000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Aurora | 300681 | Dikapinisan Nhs | San Luis | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2540000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Aurora | 300682 | Dilasag Nhs | Dilasag | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13171310.093 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Aurora | 104469 | Dinadiawan Es | Dipaculao | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Aurora | 104469 | Dinadiawan Es | Dipaculao | 0 |  | 10 | 2STY10CL | BATCH 9 CL | 13063810.093 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Aurora | 300685 | Dingalan Nhs | Dingalan | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11177342.5917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Aurora | 300685 | Dingalan Nhs | Dingalan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2540000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Aurora | 306509 | Diniog Nhs | Dilasag | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Aurora | 300686 | Ditumabo Nhs | San Luis | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12771310.093 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Aurora | 300686 | Ditumabo Nhs | San Luis | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2540000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Aurora | 300687 | Eliseo C. Ronquillo Sr. Memorial Nhs | Maria Aurora | 0 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Aurora | 157510 | Florida Es | Maria Aurora | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1895000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Aurora | 300688 | Ibona Nhs | Dingalan | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13191310.093 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Aurora | 300688 | Ibona Nhs | Dingalan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2540000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Aurora | 300689 | Juan C. Angara Memorial Nhs | Dinalungan | 0 | 1 | 16 | 2STY8CL | BATCH 7 CL | 23198734.83 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Aurora | 300689 | Juan C. Angara Memorial Nhs | Dinalungan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2540000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Aurora | 104515 | Kamalatan Es To Dibut Es | San Luis | 0 | 1 | 5 | 1STY5CL | BATCH 9 CL | 4071272.138 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2016 | REGION III | Aurora | 104475 | Lipit Es | Dipaculao | 0 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1098449.69 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Aurora | 300690 | Lual Nhs | Casiguran | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2540000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Aurora | 300690 | Lual Nhs | Casiguran | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11382342.5917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Aurora | 300692 | Manggitahan Nhs | Dilasag | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2550000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Aurora | 300691 | Maria Aurora Nhs | Maria Aurora | 0 | 1 | 12 | 2STY6CL | BATCH 9 CL | 16429930.102 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Aurora | 306501 | Mariano D. Marquez High School | Dinalungan | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Aurora | 306501 | Mariano D. Marquez Memorial National High School | Dinalungan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2540000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Aurora | 300694 | Mayor Cesario A. Pimentel Nhs | San Luis | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2700000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Aurora | 157501 | Paraiso Es | Casiguran | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Aurora | 306508 | Rosauro R. Tangson, Sr. Nhs | San Luis | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10917342.5917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Aurora | 306508 | Rosauro R. Tangson, Sr. Nhs | San Luis | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Aurora | 104527 | San Isidro Es | San Luis | 0 | 1 | 5 | 1STY5CL | BATCH 5 CL | 4300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2016 | REGION III | Aurora | 306514 | Tinib-Calangcuasan Is | Casiguran | 0 | 1 | 4 | 1STY4CL | BATCH 13 CL | 3667968.78 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Aurora | 104442 | Ura Es | Dilasag | 0 | 1 | 3 | 1STY3CL | BATCH 13 CL | 3000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Balanga City | 300702 | Bataan National High School | City Of Balanga (Capital) | 2 | 1 | 40 | 2STY10CL | BATCH 1 CL | 52685890.16 |  |  | Completed | 1 |  |  |  | 42536 | 2016-06-29 | 2016-07-12 | 2016-07-20 | 2016-07-26 | Edison Development and Construction | 42482 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION III | Balanga City | 322901 | City Of Balanga National High School | City Of Balanga (Capital) | 2 | 1 | 12 | 2STY6CL | BATCH 1 CL | 16279930.102 |  |  | Completed | 1 |  |  |  | 42419 | 2016-03-04 | 2016-03-16 | 2016-03-23 | 2016-05-26 | Orani Builders & Supply | 42701 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Balanga City | 322901 | City Of Balanga National High School | City Of Balanga (Capital) | 2 |  | 8 | 2STY8CL | BATCH 1 CL | 11327342.59 |  |  | Completed | 1 |  |  |  | 42419 | 2016-03-04 | 2016-03-16 | 2016-03-23 | 2016-05-26 | VESA Eng'g & Construction | 42669 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Bataan | 104658 | Alikabok Es | Orani | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6400000 |  |  | Completed | 1 |  |  | P00072131LZ | 16CA0034 | March 4-11, 2016 | 2016-02-24 | 2016-06-14 |  | 42563 | Pascal Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bataan | 300701 | Balsik Nhs | Hermosa | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6500000 |  |  | Completed | 1 |  |  | P00072128LZ | 16CA0031 | March 4-11, 2016 | 2016-02-24 | 2016-06-14 |  | 42555 | Sto. Cristo Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bataan | 104607 | Bamban Es | Hermosa | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 2000000 |  |  | Completed | 1 |  |  | P00072129LZ | 16CA0019 | March 4-11, 2016 | 2016-02-24 | 2016-03-23 |  | 42517 | Builders Exponent Enterprise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bataan | 300705 | Hermosa Nhs | Hermosa | 1 | 1 | 24 | 4STY12CL | BATCH 1 CL | 44154687.24 |  |  | Completed | 1 |  |  | P00070070LZ | 16CA0032 | June 27-July 3, 2016 | 2016-06-19 | 2016-06-20 |  | 42587 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Bataan | 300704 | Jose C. Payumo Jr. Memorial High School | Dinalupihan | 1 | 1 | 20 | 4STY20CL | BATCH 1 CL | 32602890.27 |  |  | Completed | 1 |  |  | P00070069LZ | 16CA0030 | March 4-11, 2016 | 2016-02-24 | 2016-03-23 |  | 42517 | Orani Builders Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Bataan | 300704 | Jose C. Payumo Jr. Memorial High School | Dinalupihan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2600000 |  |  | Completed | 1 |  |  | P00070198L2 | 16CA0044 | June 3-9, 2016 | 2016-05-30 | 2016-06-27 |  | 42562 | De Jesus Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bataan | 104661 | Kaparangan Es | Orani | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8350000 |  |  | Completed | 1 |  |  | P00072132LZ | 16CA0035 | March 4-11, 2016 | 2016-02-24 | 2016-08-02 |  | 42594 | LTM Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Bataan | 300708 | Luakan Nhs | Dinalupihan | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14947518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Bataan | 300709 | Mabatang Nhs | Abucay | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1900000 |  |  | Completed | 1 |  |  | P00072123LZ | 16CA0021 | March 4-11, 2016 | 2016-02-24 | 2016-03-23 |  | 42517 | Builders Exponent Enterprise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bataan | 104652 | Mabayo Es | Morong | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6400000 |  |  | Completed | 1 |  |  | P00072130LZ | 16CA0036 | March 4-11, 2016 | 2016-02-24 | 2016-06-14 |  | 42555 | Pascal Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bataan | 300713 | Morong Nhs | Morong | 1 | 1 | 16 | 4STY16CL | BATCH 1 CL | 27202469.42 |  |  | Completed | 1 |  |  | P00070071LZ | 16CA0037 | March 4-11, 2016 | 2016-02-24 | 2016-06-14 |  | 42555 | DM House Const. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Bataan | 300713 | Morong Nhs | Morong | 1 |  | 4 | 2STY4CL | BATCH 1 CL | 6169337.64 |  |  | Completed | 1 |  |  | P00070072LZ | 16CA0038 | March 4-11, 2016 | 2016-02-24 | 2016-03-23 |  | 42517 | Pascal Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bataan | 300713 | Morong Nhs | Morong | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 5100000 |  |  | Completed | 1 |  |  | P00070199L2 | 16CA0043 | June 3-9, 2016 | 2016-05-30 | 2016-06-27 |  | 42562 | Builders Exponent Enterprise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bataan | 158001 | Naparing Es | Dinalupihan | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1900000 |  |  | Completed | 1 |  |  | P00072124LZ | 16CA0023 | March 4-11, 2016 | 2016-02-24 | 2016-05-23 |  | 42517 | Builders Exponent Enterprise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bataan | 300715 | Orani Nhs | Orani | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Bataan | 104664 | Orani South Es | Orani | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6400000 |  |  | Completed | 1 |  |  | P00072133LZ | 16CA0033 | March 4-11, 2016 | 2016-02-24 | 2016-05-14 |  | 42555 | Pascal Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bataan | 104585 | Pagalanggang Es | Dinalupihan | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6400000 |  |  | Completed | 1 |  |  | 16CA0029 | March 4-11, 2016 | 2016-02-24 | 2016-05-14 |  | 2016-07-04 | DM House Const. Inc. | 42696 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bataan | 104668 | Paraiso Es | Orani | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1900000 |  |  | Completed | 1 |  |  | 16CA0022 | March 4-11, 2016 | 2016-02-24 | 2016-05-23 |  | 2016-05-27 | Orani Builders Supply | 42626 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bataan | 104589 | Pinulot Es | Dinalupihan | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 2000000 |  |  | Completed | 1 |  |  | 16CA0020 | March 4-11, 2016 | 2016-02-24 | 2016-05-23 |  | 2016-05-27 | Jepa Construction & Supplies | 42626 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bataan | 104589 | Pinulot Es | Dinalupihan | 1 |  | 1 | 1STY1CL | BATCH 7 CL | 1100000 |  |  | Completed | 1 |  |  | 16CA0024 | March 4-11, 2016 | 2016-02-24 | 2016-05-23 |  | 2016-05-27 | Jepa Construction & Supplies | 42596 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bataan | 300719 | Samal Nhs | Samal | 1 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Bataan | 300719 | Samal Nhs | Samal | 1 |  | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bataan | 300719 | Samal Nhs | Samal | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5000000 |  |  | Completed | 1 |  |  | P00070764L2 | 16CA0025 | April 22-29, 2016 | 2016-04-19 | 2016-05-17 |  | 42517 | Orani Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bataan | 300703 | Bataan School Of Fisheries | Orion | 2 | 1 | 12 | 3STY12CL | BATCH 1 CL | 18972268.79 |  |  | Completed | 1 |  |  |  | 42419 | 2016-03-04 | 2016-03-16 | 2016-03-23 | 2016-05-26 | Orani Builders & Supply | 42701 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bataan | 300703 | Bataan School Of Fisheries | Orion | 2 |  | 9 | 3STY9CL | BATCH 1 CL | 15471327.92 |  |  | Completed | 1 |  |  |  | 42419 | 2016-03-04 | 2016-03-16 | 2016-03-23 | 2016-05-26 | VESA Eng'g & Construction | 42669 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Bataan | 300703 | Bataan School Of Fisheries | Orion | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2750000 |  |  | Completed | 1 |  |  | P00070201L2 | 16CB0017 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-05-23 | 42521 | N. V. Balbuena Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bataan | 300699 | E. C. Bernabe Nhs | Bagac | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bataan | 306601 | Justice Emilio Angeles Gancayco Memorial High School | Orion | 2 | 1 | 20 | 4STY20CL | BATCH 1 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00070078L2 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Bataan | 306601 | Justice Emilio Angeles Gancayco Memorial High School | Orion | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2500000 |  |  | Completed | 1 |  |  | P00070202L2 | 16CB0018 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-05-23 | 42542 | Victoria Builders & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bataan | 300706 | Lamao Nhs | Limay | 2 | 1 | 18 | 3STY9CL | BATCH 5 CL | 30242655.84 |  |  | Completed | 1 |  |  | P00070944L2 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION III | Bataan | 300706 | Lamao Nhs | Limay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2500000 |  |  | Completed | 1 |  |  | P00071563L2 | 16CB0021 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-05-17 | 42516 | N. V. Balbuena Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bataan | 300707 | Limay Nhs | Limay | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [10 empty] | With approved additional funds; reported completed based on DPWH Letter dated Oct 14, 2022 Subject: Joint Special Task Force | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bataan | 300707 | Limay Nhs | Limay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  | P00075067L2 | 16CB0057 | 2016-08-01 | 2016-08-09 | 2016-08-16 | 2016-08-24 | 42613 | De Jesus Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bataan | 300710 | Mariveles Nhs, Cabcaben | Mariveles | 2 | 1 | 16 | 2STY4CL | BATCH 1 CL | 26677350.56 |  |  | Completed | 1 |  |  | P00070073L2 | 16B0030 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-03-17 | 42455 | Orani Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Bataan | 300710 | Mariveles Nhs, Cabcaben | Mariveles | 2 |  | 9 | 3STY9CL | BATCH 1 CL | 15721327.92 |  |  | Completed | 1 |  |  | P00070074L2 | 16B0060 | 2016-08-08 | 2016-08-16 | 2016-08-23 | 2016-09-06 | 42627 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Bataan | 300711 | Mariveles Nhs,Poblacion | Mariveles | 2 | 1 | 40 | 4STY20CL | BATCH 1 CL | 64255780.54 |  |  | Completed | 1 |  |  | P00070075L2 | 16B0058 | 2016-08-01 | 2016-08-09 | 2016-08-16 | 2016-08-24 | 42613 | Orani Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION III | Bataan | 300711 | Mariveles Nhs,Poblacion | Mariveles | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2550000 |  |  | Completed | 1 |  |  | P00070200L2 | 16CB0019 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-05-17 | 42516 | Poly-mervic Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bataan | 300716 | P. Roman Nhs | Pilar | 2 | 1 | 30 | 2STY10CL | BATCH 1 CL | 38913930.27 |  |  | Completed | 1 |  |  | P00070079L2 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION III | Bataan | 300716 | P. Roman Nhs | Pilar | 2 |  | 12 | 2STY12CL | BATCH 1 CL | 14779217.18 |  |  | Completed | 1 |  |  | P00070080L2 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bataan | 300716 | P. Roman Nhs | Pilar | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2625000 |  |  | Completed | 1 |  |  | P00070203L2 | 16CB0020 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-05-23 | 42521 | N. V. Balbuena Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bulacan | 158522 | Bagumbayan Ps | Bulacan | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 158506 | Basyo Es | Doña Remedios Trinidad | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2031993.117 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bulacan | 104945 | Cabayunan Elementary School | Doña Remedios Trinidad | 1 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1126464.405 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bulacan | 300770 | Frances National High School | Calumpit | 1 | 1 | 12 | 2STY12CL | BATCH 5 CL | 15085996.11 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 158509 | Kambubuyugan Elementary School | Doña Remedios Trinidad | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2031993.117 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bulacan | 300744 | Kapitangan National High School | Paombong | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 105019 | M. Del Rosario Ms | Pulilan | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15418925.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Bulacan | 104804 | Northville 9 Elementary School To F. Mendoza Memorial Es | Calumpit | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15418925.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Bulacan | 158510 | Pinag-Anakan Es | Doña Remedios Trinidad | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2031993.117 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bulacan | 300754 | Ramona S. Trillana Hs (Mayor Ramon Trillana Mem. Hs (Iba Nhs)) | Hagonoy | 1 | 1 | 24 | 2STY8CL | BATCH 3 CL | 33874191.09 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Bulacan | 306724 | Romeo Acuña Santos Memorial High School | Bulacan | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 306711 | San Francisco Xavier High School | Bulacan | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 306723 | San Miguel-Meysulao High School | Calumpit | 1 | 1 | 10 | 2STY10CL | BATCH 5 CL | 13183972.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Bulacan | 300755 | San Pedro National High School | Hagonoy | 1 | 1 | 24 | 4STY12CL | BATCH 3 CL | 44337636.41 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Bulacan | 300745 | San Roque National Hs | Paombong | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Bulacan | 300736 | Sta. Lucia High School | Calumpit | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bulacan | 300756 | Sta. Monica National High School | Hagonoy | 1 | 1 | 12 | 4STY12CL | BATCH 3 CL | 20167107.46 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 300756 | Sta. Monica National High School | Hagonoy | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 300737 | Sta. Peregrina Hs | Pulilan | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 17127665.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 104783 | Taliptip Es | Bulacan | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 17127665.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 300779 | Taliptip Nhs | Bulacan | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13183972.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Bulacan | 300720 | Alexis G. Santos National High School | Bustos | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 300721 | Balagtas National Agricultural Hs | Balagtas (Bigaa) | 2 | 1 | 48 | 4STY24CL | BATCH 7 CL | 71192514.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION III | Bulacan | 300721 | Balagtas National Agricultural Hs | Balagtas (Bigaa) | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 7290000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Bulacan | 104761 | Bambang Es | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 306730 | Banga High School | Plaridel | 2 | 1 | 20 | 4STY20CL | BATCH 3 CL | 28520975.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Bulacan | 104762 | Batia Es | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 300726 | Bintog Hs (Jose J. Mariano Mhs) | Plaridel | 2 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Bulacan | 104764 | Bunducan Es | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 104765 | Bunlo Elementary School | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 104972 | Bunsuran Es | Pandi | 2 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Bulacan | 300728 | Bunsuran Nhs | Pandi | 2 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Bulacan | 300728 | Bunsuran Nhs | Pandi | 2 |  | 12 | 4STY12CL | BATCH 5 CL | 22302344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 300734 | Dampol 1St National High School | Plaridel | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15418925.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Bulacan | 104767 | Duhat Elementary School | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 104741 | Engr. Vicente R. Cruz Memorial School | Baliuag | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6872696.155 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 300741 | Felizardo C. Lipana Mhs (Sta. Rita Hs) | Guiguinto | 2 | 1 | 20 | 4STY20CL | BATCH 3 CL | 28520975.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Bulacan | 300742 | Guiguinto Nat'L Voc'L. High School | Guiguinto | 2 | 1 | 72 | 4STY24CL | BATCH 5 CL | 106788771.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 72 | 0
NEWCON 2016 | REGION III | Bulacan | 300742 | Guiguinto Nat'L Voc'L. High School | Guiguinto | 2 |  | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Bulacan | 300742 | Guiguinto Nat'L Voc'L. High School | Guiguinto | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bulacan | 300746 | Lolomboy National Nhs | Bocaue | 2 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Bulacan | 300729 | Masagana Hs | Pandi | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14750043.6516 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Bulacan | 104975 | Matias B. Salvador Memorial Elementary School | Pandi | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 158540 | Pandi Heights Elementary School | Pandi | 2 | 1 | 18 | 3STY9CL | BATCH 5 CL | 30837850.48 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION III | Bulacan | 158539 | Pandi Residences Es | Pandi | 2 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Bulacan | 104984 | Real De Cacarong Elementary Schol | Pandi | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 104735 | Santol Elementary School | Balagtas (Bigaa) | 2 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Bulacan | 158542 | St. Martha Elementary School | Bocaue | 2 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Bulacan | 158542 | St. Martha Elementary School | Bocaue | 2 |  | 3 | 3STY3CL | BATCH 5 CL | 7118301.78 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Bulacan | 104828 | Sta.Cruz Elementary | Guiguinto | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 158515 | Sto. Nino Es | Pandi | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1847266.47 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bulacan | 306712 | Sto. Nino High School | Baliuag | 2 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15418925.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Bulacan | 306712 | Sto. Nino High School | Baliuag | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bulacan | 300778 | Sulivan National High School | Baliuag | 2 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10316033.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Bulacan | 300778 | Sulivan National High School | Baliuag | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4860000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bulacan | 104769 | Taal Elementary School | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 300747 | Taal High School | Bocaue | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8128471.77 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Bulacan | 104769 | Taal High School To Taal Es | Bocaue | 2 |  | 15 | 3STY15CL | BATCH 7 CL | 21923487.88 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | Bulacan | 104770 | Tambubong Elementary School | Bocaue | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10316033.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Bulacan | 300780 | Tiaong Nhs | Guiguinto | 2 | 1 | 10 | 2STY10CL | BATCH 5 CL | 13183972.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Bulacan | 300780 | Tiaong Nhs | Guiguinto | 2 |  | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 104760 | V Delas Flores Es | Baliuag | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Bulacan | 300731 | Akle Hs | San Ildefonso | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11332636.597 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Bulacan | 158541 | Alejandro E. Flores, Sr. Elementary School | Doña Remedios Trinidad | 3 | 1 | 4 | 1STY2CL | BATCH 5 CL | 3879259.63 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 306702 | Angat Hs (Binagbag Nhs - Taboc Nhs) | Angat | 3 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 158505 | Bato Elementary School | Doña Remedios Trinidad | 3 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1126464.405 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bulacan | 306707 | Binagbag Hs - Angel M. Del Rosario Hs | Angat | 3 | 1 | 12 | 2STY4CL | BATCH 5 CL | 19490250.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 300748 | Carlos F. Gonzales Hs (Maguinao Cruz Na Daan Nhs) | San Rafael | 3 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 104716 | Don Pablo Amisola Memorial School | Angat | 3 | 1 | 12 | 2STY6CL | BATCH 5 CL | 17115358.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 158507 | Duplas Es | Doña Remedios Trinidad | 3 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2954711.133 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Bulacan | 158525 | Durumugan Es | Doña Remedios Trinidad | 3 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1126464.405 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bulacan | 300774 | John J. Russel Mhs (Sibul Nhs) | San Miguel | 3 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 306703 | Julian B. Sumbillo High School | Norzagaray | 3 | 1 | 15 | 3STY15CL | BATCH 9 CL | 24100836.668 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | Bulacan | 158526 | Karahumi Elementary School | Norzagaray | 3 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2031993.12 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION III | Bulacan | 158511 | Kawit Es | Doña Remedios Trinidad | 3 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1126464.405 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bulacan | 104960 | Luis Gravador Elementary School | Norzagaray | 3 | 1 | 16 | 4STY16CL | BATCH 3 CL | 27002469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Bulacan | 104960 | Luis Gravador Elementary School | Norzagaray | 3 |  | 12 | 4STY12CL | BATCH 3 CL | 22302344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 306718 | Lydia D. Villangca Trade School | San Rafael | 3 | 1 | 12 | 4STY12CL | BATCH 3 CL | 20167107.46 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 105054 | Maasim Elementary School | San Ildefonso | 3 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 306708 | Maronquillo National High School | San Rafael | 3 | 1 | 6 | 3STY6CL | BATCH 3 CL | 10315033.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Bulacan | 300758 | Minuyan National High School | Norzagaray | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18825432.182 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 104952 | Norzagaray Es | Norzagaray | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Bulacan | 300760 | Norzagaray National High School | Norzagaray | 3 | 1 | 24 | 4STY24CL | BATCH 7 CL | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Bulacan | 105058 | Palapala Elementary School | San Ildefonso | 3 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 300772 | Partida Hs (San Miguel Nhs - Partida Hs) | San Miguel | 3 | 1 | 8 | 2STY8CL | BATCH 5 CL | 12415536.73 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Bulacan | 300749 | Salapungan Hs | San Rafael | 3 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15418925.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Bulacan | 300732 | San Ildefonso National High School | San Ildefonso | 3 | 1 | 24 | 4STY24CL | BATCH 9 CL | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Bulacan | 300732 | San Ildefonso National High School | San Ildefonso | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bulacan | 300771 | San Miguel Nhs | San Miguel | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 20167107.46 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 300771 | San Miguel Nhs | San Miguel | 3 |  | 16 | 4STY8CL | BATCH 9 CL | 26845533.912 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Bulacan | 300771 | San Miguel Nhs | San Miguel | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 22168818.206 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 300724 | Sapang Bulac High School | Doña Remedios Trinidad | 3 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2031993.117 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Bulacan | 306728 | Sta. Catalina Bata National High School | San Ildefonso | 3 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 300740 | Assemblywoman Felicita G. Bernardino Memorial Trade School | Marilao | 4 |  | 24 | 4STY12CL | BATCH 11 CL | 44604688 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Bulacan | 300740 | Assemblywoman Felicita G. Bernardino Memorial Trade School | Marilao | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bulacan | 105141 | Balasing Elementary School | Santa Maria | 4 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21923487.88 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | Bulacan | 306714 | Catmon Hs | Santa Maria | 4 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10316033.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Bulacan | 105147 | Cay Pombo Es | Santa Maria | 4 | 1 | 24 | 4STY24CL | BATCH 5 CL | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Bulacan | 105149 | Caysio Elementary School | Santa Maria | 4 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15418925.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Bulacan | 105144 | Cornelia M. De Jesus Memorialcentral School | Santa Maria | 4 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15418925.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Bulacan | 300739 | F. F. Halili Nat'L. Agr'L. School | Santa Maria | 4 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Bulacan | 300739 | F. F. Halili Nat'L. Agr'L. School | Santa Maria | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Bulacan | 105151 | Guyong Es | Santa Maria | 4 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10567132 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Bulacan | 300765 | Parada Nhs | Santa Maria | 4 | 1 | 48 | 4STY24CL | BATCH 9 CL | 71192514.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION III | Bulacan | 300767 | Pulong Buhangin Nhs | Santa Maria | 4 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31358073.237 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Bulacan | 105163 | San Vicente (Hulo) Es | Santa Maria | 4 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15271328 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Bulacan | PSA328420 | Shs In Obando, Bulacan | Obando | 4 | 1 | 16 | 2STY8CL | BATCH 5 CL | 22582794.06 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Bulacan | 105166 | Sta. Clara Es | Santa Maria | 4 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22302344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Bulacan | 306726 | Sta. Cruz High School | Santa Maria | 4 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13183972.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Bulacan | 105167 | Sta. Cruz Es | Santa Maria | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Bulacan | 300777 | Sta. Maria National High School | Santa Maria | 4 | 1 | 20 | 4STY20CL | BATCH 3 CL | 33936211.03 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Bulacan | 300777 | Sta. Maria National High School | Santa Maria | 4 |  | 6 | 3STY6CL | BATCH 3 CL | 10567132 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Bulacan | 105170 | Tumana Es | Santa Maria | 4 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 107096 | Bakod Bayan Es | Cabanatuan City | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 107072 | Barlis Es | Cabanatuan City | 3 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 107073 | Buliran Elementary School | Cabanatuan City | 3 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1900000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 301045 | Camp Tinio Nhs | Cabanatuan City | 3 | 1 | 20 | 4STY20CL | BATCH 1 CL | 31738176.93 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 301045 | Camp Tinio Nhs | Cabanatuan City | 3 |  | 15 | 3STY15CL | BATCH 1 CL | 23610688 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 307301 | Cesar E. Vergara Mhs | Cabanatuan City | 3 | 1 | 9 | 3STY9CL | BATCH 1 CL | 15311797.32 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 307303 | Daan Sarile Integrated School | Cabanatuan City | 3 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1900000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 301049 | Eastern Cabu Nhs | Cabanatuan City | 3 | 1 | 12 | 3STY12CL | BATCH 1 CL | 18678518.39 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 301044 | Honorato C. Perez Sr. Mshs | Cabanatuan City | 3 | 1 | 8 | 4STY8CL | BATCH 1 CL | 15932002.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 301047 | Marciano Del Rosario Mnhs | Cabanatuan City | 3 | 1 | 24 | 4STY12CL | BATCH 1 CL | 46435388.33 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 301046 | Mayapyap Nhs | Cabanatuan City | 3 | 1 | 16 | 4STY16CL | BATCH 1 CL | 27024547.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 301046 | Mayapyap Nhs | Cabanatuan City | 3 |  | 8 | 4STY8CL | BATCH 1 CL | 15289461.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 301048 | San Josef National High School | Cabanatuan City | 3 | 1 | 24 | 4STY12CL | BATCH 11 CL | 46103799.53 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Cabanatuan City | 107091 | Talipapa Es | Cabanatuan City | 3 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Gapan City | 300812 | Juan R. Liwag Mem. Nhs | City Of Gapan | 4 | 1 | 24 | 2STY8CL | BATCH 13 CL | 34236560.49 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Mabalacat City | 300931 | Camachiles National High School | Mabalacat | 1 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26702469.42 |  |  | Completed | 1 |  |  |  |  | 2016-02-26 | 2016-03-05 | 2016-03-17 | 2016-05-12 | 42516 | B.P. Cruz Builders & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Mabalacat City | 106076 | Dau Elementary School | Mabalacat | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23252460.801 |  |  | Completed | 1 |  |  |  |  | 2016-05-11 | 2016-05-19 | 2016-05-31 | 2016-06-14 | 42553 | Sto. Cristo Const'n & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Mabalacat City | 306927 | Dona Asuncion Lee Integrated School | Mabalacat | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Mabalacat City | 306916 | Mabalacat Comm. Hs | Mabalacat | 1 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 |  |  |  |  | 2016-05-11 | 2016-05-19 | 2016-05-31 | 2016-06-14 | 42553 | Al-B Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Mabalacat City | 300895 | Mabalacat Nhs | Mabalacat | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Mabalacat City | 306909 | Mabalacat Technical Vocational School | Mabalacat | 1 | 1 | 16 | 4STY16CL | BATCH 1 CL | 30530092.891 |  |  | Completed | 1 |  |  |  |  | 2016-02-26 | 2016-03-05 | 2016-03-17 | 2016-05-12 | 42516 | B.P. Cruz Builders & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Mabalacat City | 300900 | Mauaque Hs (Res) | Mabalacat | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8296000 |  |  | Completed | 1 |  |  |  |  | 2016-02-26 | 2016-03-05 | 2016-03-17 | 2016-05-12 | 42516 | R.G. Diaz Builders & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Mabalacat City | 300900 | Mauaque Hs (Res) | Mabalacat | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6382000 |  |  | Completed | 1 |  |  |  |  | 2016-02-26 | 2016-03-05 | 2016-03-17 | 2016-05-12 | 42516 | E.M. Danan Trading & Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Mabalacat City | 306942 | Santos Ventura Nhs | Mabalacat | 1 | 1 | 24 | 4STY24CL | BATCH 1 CL | 35596257.14 |  |  | Completed | 1 |  |  |  |  | 2016-02-26 | 2016-03-05 | 2016-03-17 | 2016-05-12 | 42516 | Sto. Cristo Const'n & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Mabalacat City | 106071 | Sapang Biabas Resettlement Es | Mabalacat | 1 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 |  |  |  |  | 2016-05-11 | 2016-05-19 | 2016-05-31 | 2016-06-14 | 42553 | Al-B Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Malolos City | 240001 | Bangkal Es | City Of Malolos (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10425630 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Malolos City | 104864 | Barihan Es | City Of Malolos (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11175630 |  |  | Reverted | 0 | [10 empty] | DPWH Report: Negotiation on project site produced negative result; funds reverted | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION III | Malolos City | 104865 | Bulihan Elementary School | City Of Malolos (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10575630 |  |  | Completed | 1 |  |  | P00070992LZ | 16CC0173 | 2016-10-04 | 2016-10-13 | 2016-10-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Malolos City | 323601 | Bulihan Nhs | City Of Malolos (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15121327.92 |  |  | Completed | 1 | [10 empty] | Reported by DPWH | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Malolos City | 323607 | City Of Malolos High School - Canalate | City Of Malolos (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Reverted | 0 | [10 empty] | DPWH Report: Negotiation on project site produced negative result; funds reverted | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION III | Malolos City | 323606 | City Of Malolos Integrated School - Sto. Rosario | City Of Malolos (Capital) | 1 | 1 | 30 | 3STY15CL | BATCH 7 CL | 42766026.9 |  |  | Completed | 1 |  |  | P00072136LZ | 16CC0187 | 2016-10-05 | 2016-10-14 | 2016-10-28 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION III | Malolos City | 323606 | City Of Malolos Integrated School - Sto. Rosario | City Of Malolos (Capital) | 1 |  | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 |  |  | P00072137LZ | 16CC0174 | 2016-10-04 | 2016-10-13 | 2016-10-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Malolos City | 300750 | Malolos Marine Fishery School & Laboratory | City Of Malolos (Capital) | 1 | 1 | 30 | 3STY15CL | BATCH 5 CL | 43446975.76 |  |  | Completed | 1 |  |  | P00070993LZ | 16CC0186 | 2016-10-05 | 2016-10-14 | 2016-10-28 |  |  |  | Reported by DPWH | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION III | Malolos City | 300751 | Marcelo H. Del Pilar National Hs | City Of Malolos (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 |  |  | P00075068LZ | 16CC0113 | 2016-08-03 | 2016-08-12 | 2016-08-25 | 2016-09-08 | 42668 | JMK BUILDERS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Meycauayan City | 104915 | Bagbaguin Es | City Of Meycauayan | 4 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26852469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Meycauayan City | 104916 | Bahay Pare Elementary School | City Of Meycauayan | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6469338 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Meycauayan City | 300757 | Meycauayan Nhs | City Of Meycauayan | 4 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Meycauayan City | 104935 | Meycauayan West Central School | City Of Meycauayan | 4 | 1 | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Meycauayan City | 104926 | Pandayan Es | City Of Meycauayan | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6469338 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Meycauayan City | 104928 | Perez Es | City Of Meycauayan | 4 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10567132 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Meycauayan City | PSA328423 | Shs In Meycauayan City | City Of Meycauayan | 4 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Munoz Science City | 300824 | Munoz National Hs | Science City Of Muñoz | 2 | 1 | 40 | 4STY20CL | BATCH 13 CL | 63054977.86 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION III | Munoz Science City | 322802 | San Antonio Integrated School | Science City Of Muñoz | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300783 | Aliaga National Nhs | Aliaga | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300786 | Baloy Hs | Cuyapo | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300809 | Bartolome R Sangalang National High School | Guimba | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300809 | Bartolome R Sangalang National High School | Guimba | 1 |  | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300788 | Batitang National High School | Zaragoza | 1 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8665011.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300796 | Carmen Nhs | Zaragoza | 1 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26572907.4417 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300801 | Cuyapo National High School | Cuyapo | 1 | 1 | 30 | 3STY15CL | BATCH 9 CL | 47012629.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 105817 | Dimasalang Norte Es To Dimasalang Sur Es | Talavera | 1 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3811375.2325 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300804 | Eduardo L. Joson Mem. Hs | Quezon | 1 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31377488.93 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300845 | Exequiel R. Lina National High School | Licab | 1 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31377488.93 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300806 | Galvan National High School | Guimba | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 306808 | Ganduz National High School | Pantabangan | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300814 | Julia Ortiz Luiz Nhs | Santo Domingo | 1 | 1 | 30 | 3STY15CL | BATCH 9 CL | 47012629.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 306810 | Pacac High School | Guimba | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300827 | Paitan Sur Nhs | Cuyapo | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300842 | Salagusog National High School | Cuyapo | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300843 | San Andres Hs | Guimba | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300857 | Sto. Domingo Nts | Santo Domingo | 1 | 1 | 48 | 4STY24CL | BATCH 5 CL | 73886079.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300864 | Talavera National High School | Talavera | 1 | 1 | 40 | 4STY20CL | BATCH 5 CL | 63054977.86 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300869 | Triala Nhs | Guimba | 1 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8665011.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 306811 | Umangan National High School | Aliaga | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23506314.795 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300871 | Zaragoza National High School | Zaragoza | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300795 | Canaan East Nhs | Rizal | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300802 | Doña Juana Chioco National High School | Lupao | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300841 | Rizal Nhs | Rizal | 2 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31377488.93 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300841 | Rizal Nhs | Rizal | 2 |  | 16 | 4STY16CL | BATCH 5 CL | 26572907.4417 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 306802 | San Felipe Integrated High School | Llanera | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 306828 | Talugtug Nhs Annex-Saverona | Talugtug | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 105658 | Villa Labrador Es | Rizal | 2 | 1 | 5 | 1STY5CL | BATCH 9 CL | 4700731.4693 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 159034 | Angel'S Ville Es | Santa Rosa | 3 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 159012 | Atate Annex Primary School | Palayan City (Capital) | 3 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1900000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300790 | Bongabon Nhs | Bongabon | 3 | 1 | 60 | 4STY20CL | BATCH 3 CL | 94132466.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 60 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300790 | Bongabon Nhs | Bongabon | 3 |  | 10 | 2STY10CL | BATCH 3 CL | 13150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 306813 | Bongabon Nhs Annex (Vega Hs) | Bongabon | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 159029 | Dupinga Elementary School | Gabaldon (Bitulok & Sabani) | 3 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 306287 | F. Buencamino Sr. Integrated School | Gabaldon (Bitulok & Sabani) | 3 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6672664.78 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300805 | Gabaldon Voc'L. Agric. Hs | Gabaldon (Bitulok & Sabani) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300805 | Gabaldon Voc'L. Agric. Hs | Gabaldon (Bitulok & Sabani) | 3 |  | 6 | 2STY6CL | BATCH 9 CL | 8665011.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 159018 | Gawad Kalinga Es(Tagumpay Es Annex | Gabaldon (Bitulok & Sabani) | 3 | 1 | 4 | 1STY4CL | BATCH 13 CL | 3667968.78 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300862 | Gen. Mamerto Natividad National Hs | General Mamerto Natividad | 3 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26172907.4417 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300810 | Hilario E. Hermosa Mem. Hs | Laur | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300810 | Hilario E. Hermosa Mem. Hs | Laur | 3 |  | 6 | 2STY6CL | BATCH 9 CL | 8665011.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 105578 | Langka Es | Palayan City (Capital) | 3 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1900000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 105354 | Mag-Asawang Sampaloc Es | General Mamerto Natividad | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300819 | Maligaya Nhs | Palayan City (Capital) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300819 | Maligaya Nhs | Palayan City (Capital) | 3 |  | 6 | 2STY6CL | BATCH 9 CL | 8665011.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300826 | Nueva Ecija Nhs | Cabanatuan City | 3 |  | 40 | 4STY20CL | BATCH 11 CL | 62754977.86 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300828 | Palayan City National High School | Palayan City (Capital) | 3 | 1 | 24 | 4STY24CL | BATCH 3 CL | 36793039.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300828 | Palayan City National High School | Palayan City (Capital) | 3 |  | 20 | 4STY20CL | BATCH 3 CL | 31377488.93 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 306801 | Santa Rosa National High School | Santa Rosa | 3 | 1 | 24 | 4STY24CL | BATCH 3 CL | 36793039.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300861 | Talabutab Norte National High School | General Mamerto Natividad | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300792 | Cabiao National High School | Cabiao | 4 | 1 | 60 | 4STY20CL | BATCH 11 CL | 93308670.81 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 60 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300794 | Calaba National High School | San Isidro | 4 | 1 | 20 | 2STY10CL | BATCH 3 CL | 26300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 306821 | Dr. Jose Lapuz Salonga Hs (Former San Mariano Nhs Annex) | San Antonio | 4 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 306821 | Dr. Jose Lapuz Salonga Hs (Former San Mariano Nhs Annex) | San Antonio | 4 |  | 6 | 2STY6CL | BATCH 9 CL | 8665011.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300808 | General Tinio Nhs | General Tinio (Papaya) | 4 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Nueva Ecija |  | Gregorio Crespo Nhs | Entablado Cabiao | 4 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 306816 | Jaen Nhs (Former Putlod-San Jose Nhs-Annex) | Jaen | 4 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8665011.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 306809 | Leonor M. Bautista Hs (Pias Campus Annex) | General Tinio (Papaya) | 4 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300817 | Magpapalayok Nhs | San Leonardo | 4 | 1 | 16 | 2STY8CL | BATCH 9 CL | 22824373.66 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300817 | Magpapalayok Nhs | San Leonardo | 4 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300820 | Mallorca National High School | San Leonardo | 4 | 1 | 12 | 4STY12CL | BATCH 3 CL | 20300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300820 | Mallorca National High School | San Leonardo | 4 |  | 6 | 3STY6CL |  | 10787131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 105588 | Sabangan Es To Palale Es | General Tinio (Papaya) | 4 | 1 | 2 | 1STY2CL |  | 2138606 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Nueva Ecija |  | Mambangnan Hs Annex | San Leonardo | 4 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300821 | Mambangnan Nhs | San Leonardo | 4 | 1 | 16 | 2STY8CL | BATCH 5 CL | 22824373.66 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Nueva Ecija |  | Mariano Llanera Nhs | San Vicente | 4 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300832 | Penaranda National Nhs | Peñaranda | 4 | 1 | 10 | 2STY10CL | BATCH 13 CL | 13150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300834 | Pulo Nhs | San Isidro | 4 | 1 | 12 | 2STY6CL | BATCH 5 CL | 17330023.34 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300835 | Putlod-San Jose Nhs | Jaen | 4 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31377488.93 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300840 | Rio Chico National High School | General Tinio (Papaya) | 4 | 1 | 16 | 2STY8CL | BATCH 5 CL | 22824373.66 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300844 | San Anton Nhs | San Leonardo | 4 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300844 | San Anton Nhs | San Leonardo | 4 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300846 | San Francisco Nhs | San Antonio | 4 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300846 | San Francisco Nhs | San Antonio | 4 |  | 6 | 2STY6CL | BATCH 9 CL | 8665011.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija |  | San Leonardo Nhs | San Leonardo | 4 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300856 | Sta. Rita Nhs | Cabiao | 4 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8665011.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300867 | Teodoro A. Dionisio Nhs | San Isidro | 4 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300867 | Teodoro A. Dionisio Nhs | San Isidro | 4 |  | 6 | 2STY6CL | BATCH 9 CL | 8665011.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Nueva Ecija | 300854 | Zacarias C. Aquilizan Hs (Sta. Barbara Nhs Annex) | San Antonio | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6672664.78 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Olongapo City | 107132SHS | Barretto I Es | Olongapo City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Olongapo City | 162003 | Iram Ii Es | Olongapo City | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1964740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Olongapo City | 500027 | James L. Gordon Is | Olongapo City | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Olongapo City | 301056 | Kalalake Nhs | Olongapo City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Olongapo City | 107122 | New Cabalan Es | Olongapo City | 1 | 1 | 12 | 3STY12CL | BATCH 1 CL | 18500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Olongapo City | 107122 | New Cabalan Es | Olongapo City | 1 |  | 24 | 4STY24CL | BATCH 1 CL | 36150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Olongapo City | 107122 | New Cabalan Es | Olongapo City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2550000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Olongapo City | 107123 | Old Cabalan Integrated School | Olongapo City | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Olongapo City | 301058 | Regional Science High School | Olongapo City | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 306938 | Ayala | Magalang | 1 | 1 | 16 | 2STY8CL | BATCH 1 CL | 22054685.18 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Pampanga | PSA328428 | Shs In Magalang, Pampanga | Magalang | 1 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6627321.081 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 300943 | Tinajero Nhs - Sta. Lucia Hs Annex | Magalang | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Pampanga | 306911 | Ambrocio S.Simpao Educational And Tradet Center Of Learning | Santa Rita | 2 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11353662.8677 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Pampanga | 300879 | Basa Air Base High School | Floridablanca | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8364965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Pampanga | 300892 | Gutad Nhs | Floridablanca | 2 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8364965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Pampanga | 300902 | Natividad Nhs | Guagua | 2 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6627321.081 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 300904 | Pagyuruan Nhs | Floridablanca | 2 | 1 | 12 | 2STY6CL | BATCH 1 CL | 16279930.102 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Pampanga | 300909 | Pulung Santol National High School | Porac | 2 | 1 | 8 | 4STY8CL | BATCH 1 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Pampanga | 300912 | Remedios Nhs | Lubao | 2 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8364965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Pampanga | 300881 | San Basilio Hs (Becuran Nhs Annex) | Santa Rita | 2 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6658917.7692 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 300929 | San Vicente Nhs, Lubao | Lubao | 2 | 1 | 8 | 4STY8CL | BATCH 1 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Pampanga | 306935 | Bacolor Hs | Bacolor | 3 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 300901 | Mexico National High School | Mexico | 3 | 1 | 12 | 2STY6CL | BATCH 1 CL | 16976379.0515 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Pampanga | 300872 | Nicanor David Vergara Hs (Anao Nhs) | Mexico | 3 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8364965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Pampanga | 105923 | Potrero Es | Bacolor | 3 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 300921 | San Juan Nhs, Mexico | Mexico | 3 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Pampanga | 106300 | San Matias Es | Santo Tomas | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8364965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Pampanga | 300874 | Bahay Pare Nhs | Candaba | 4 | 1 | 8 | 4STY8CL | BATCH 1 CL | 15494444.4052 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Pampanga | 300883 | Caduang Tete Hs | Macabebe | 4 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 300927 | Concepcion Is | San Simon | 4 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8611414.0015 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Pampanga | 306946 | Conrado P. Macapinlac , Sr. Nhs | Minalin | 4 | 1 | 12 | 2STY6CL | BATCH 1 CL | 16976379.0515 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Pampanga | 106255 | Dela Paz Es | San Simon | 4 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 306934 | Emigdio A. Bondoc High School | San Luis | 4 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6658917.7692 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 106152 | Masantol Es | Masantol | 4 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16729930.1 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Pampanga | 300933 | Masantol Hs (Sta. Lucia Nhs, Masantol) | Masantol | 4 | 1 | 12 | 2STY6CL | BATCH 13 CL | 17729930.1 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Pampanga | 300906 | Pasig Nhs | Candaba | 4 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Pampanga | 300914 | Salapungan Nhs - Annex Mandili | Candaba | 4 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 106256 | San Agustin Es | San Simon | 4 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 106240 | San Carlos Es | San Luis | 4 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 306944 | San Luis Nhs | San Luis | 4 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8611414.0015 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Pampanga | 300924 | San Matias Nhs | Santo Tomas | 4 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15302343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Pampanga | PSA328427 | Shs In Apalit, Pampanga | Apalit | 4 | 1 | 8 | 4STY8CL | BATCH 1 CL | 15419956.811 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Pampanga | 106266 | Sto. Nino Es | San Simon | 4 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 300936 | Sto. Rosario Nhs | Minalin | 4 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8364965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Pampanga | 300939 | Tagulod Nhs | Candaba | 4 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6627321.081 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Pampanga | 306906 | Tarik Suliman High School | Masantol | 4 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6758917.7692 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | San Fernando City | 301064 | Pampanga Nhs | City Of San Fernando (Capital) | 3 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | San Jose City | 300800 | Constancio Padilla National High School | San Jose City | 2 | 1 | 24 | 4STY24CL | BATCH 11 CL | 36793039.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | San Jose City | 300800 | Constancio Padilla National High School | San Jose City | 2 |  | 15 | 3STY15CL | BATCH 11 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | San Jose City | 325802 | Tayabo High School - Cpnhs Annex | San Jose City | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 107144 | Bagong Buhay E Es | City Of San Jose Del Monte | 0 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10567132 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 107146 | Bagong Buhay G Es | City Of San Jose Del Monte | 0 | 1 | 28 | 4STY28CL | BATCH 9 CL | 40067946.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 107147 | Bagong Buhay I Es (Lawang Pari) | City Of San Jose Del Monte | 0 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15677614.1562 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 307508 | Citrus National Hs | City Of San Jose Del Monte | 0 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22302344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 307508 | Citrus National Hs | City Of San Jose Del Monte | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 307506 | City Of San Jose Del Monte National Science High School | City Of San Jose Del Monte | 0 | 1 | 8 | 4STY8CL | BATCH 7 CL | 15047519 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 107156 | Gumaok Es | City Of San Jose Del Monte | 0 | 1 | 16 | 4STY8CL | BATCH 7 CL | 30095038 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 307510 | Kaypian National High School | City Of San Jose Del Monte | 0 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 307510 | Kaypian National High School | City Of San Jose Del Monte | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 307511 | Marangal National High School | City Of San Jose Del Monte | 0 | 1 | 40 | 4STY20CL | BATCH 7 CL | 62205780.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 107158 | Muzon (Pabahay 2000) Es | City Of San Jose Del Monte | 0 |  | 16 | 4STY16CL | BATCH 9 CL | 26852469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 107158 | Muzon (Pabahay 2000) Es | City Of San Jose Del Monte | 0 | 1 | 24 | 4STY24CL | BATCH 9 CL | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 301059 | Paradise Farms Nhs | City Of San Jose Del Monte | 0 | 1 | 16 | 4STY16CL | BATCH 5 CL | 27002469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 301059 | Paradise Farms Nhs | City Of San Jose Del Monte | 0 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 301059 | Paradise Farms Nhs | City Of San Jose Del Monte | 0 |  | 8 | 2STY8CL | BATCH 5 CL | 11291397.03 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 107160 | S. Palay Proper Es | City Of San Jose Del Monte | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6469338 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 107161 | San Jose Del Monte Central School | City Of San Jose Del Monte | 0 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22302344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 301060 | San Jose Del Monte National Hs | City Of San Jose Del Monte | 0 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31020975.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 301061 | San Jose Del Monte Nat'L. Trade School | City Of San Jose Del Monte | 0 | 1 | 24 | 4STY12CL | BATCH 9 CL | 44604688 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 301061 | San Jose Del Monte Nat'L. Trade School | City Of San Jose Del Monte | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 107162 | San Martin Es (Bbc) | City Of San Jose Del Monte | 0 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 307507 | San Martin National Hs | City Of San Jose Del Monte | 0 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 307507 | San Martin National Hs | City Of San Jose Del Monte | 0 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 307507 | San Martin National Hs | City Of San Jose Del Monte | 0 |  | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 301062 | Sapang Palay National High School | City Of San Jose Del Monte | 0 | 1 | 48 | 4STY24CL | BATCH 5 CL | 71492514.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 301062 | Sapang Palay National High School | City Of San Jose Del Monte | 0 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 301062 | Sapang Palay National High School | City Of San Jose Del Monte | 0 |  | 6 | 3STY6CL | BATCH 5 CL | 10567132 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 107164 | Sta. Cruz (Bbd) Elementary School | City Of San Jose Del Monte | 0 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | San Jose Del Monte City | 107151 | Sto. Cristo Es | City Of San Jose Del Monte | 0 | 1 | 16 | 4STY8CL | BATCH 7 CL | 30095038 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Tarlac | 300946 | Anao Nhs | Anao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300946 | Anao Nhs | Anao | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Tarlac | 300948 | Balaoang Nhs | Paniqui | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Tarlac | 300948 | Balaoang Nhs | Paniqui | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300950 | Bamban Nhs | San Clemente | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 300950 | Bamban Nhs | San Clemente | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Tarlac | 300952 | Bilad High School | Camiling | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12898000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Tarlac | 300973 | Birbira High School | Camiling | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 300973 | Birbira High School | Camiling | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300953 | Buenavista High School | Pura | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 300955 | Caanamongan High School | Santa Ignacia | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 300955 | Caanamongan High School | Santa Ignacia | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 307010 | Calipayan Nhs | Santa Ignacia | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Tarlac | 300958 | Camiling School Of Home Industries | Camiling | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Tarlac | 300958 | Camiling School Of Home Industries | Camiling | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 307008 | Carabaoan-Caocaoayan High School | Mayantoc | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 307008 | Carabaoan-Caocaoayan High School | Mayantoc | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300998 | Eduardo Cojuangco National Vocational High School | Paniqui | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4860000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Tarlac | 300998 | Eduardo Cojuangco National Vocational High School | Paniqui | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31413000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Tarlac | 300964 | Estipona Nhs | Pura | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15272000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Tarlac | 307019 | Josephine M. Cojuangco National Technicalvocationalhigh School | Mayantoc | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Tarlac | 307006 | Malacampa Nhs | Camiling | 1 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12764000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Tarlac | 307006 | Malacampa Nhs | Camiling | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300972 | Marawi Nhs | Camiling | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15272000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Tarlac | 307011 | Moncada National High School | Moncada | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26968000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Tarlac | 307011 | Moncada National High School | Moncada | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300975 | Nambalan Nhs | Santa Ignacia | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 300978 | Padapada Nhs | Santa Ignacia | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26968000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Tarlac | 300980 | Pitombayog Nhs | Mayantoc | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Tarlac | 300980 | Pitombayog Nhs | Mayantoc | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300982 | Ramos National High School | Ramos | 1 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21596000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | Tarlac | 300983 | Sacata Nhs | Santa Ignacia | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 300984 | San Bartolome Nhs | Mayantoc | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 300985 | San Felipe Hs | San Manuel | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300985 | San Felipe Hs | San Manuel | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15272000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Tarlac | 300989 | San Pedro Nhs | Moncada | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22373000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Tarlac | 300991 | Sapang High School | Moncada | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 300992 | Sta. Ines Nhs | Santa Ignacia | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Tarlac | 300992 | Sta. Ines Nhs | Santa Ignacia | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300999 | Vargas High School | Santa Ignacia | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 307004 | Ventinilla Hs | Paniqui | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Tarlac | 300954 | Buenlag Nhs | Gerona | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Tarlac | 300959 | Cardona Nhs | Gerona | 2 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Tarlac | 307007 | Corazon C. Aquino High School | Gerona | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22372400 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Tarlac | 307007 | Corazon C. Aquino High School | Gerona | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2550000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 106789 | Don Casimiro G. Tanedo Es | Victoria | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Tarlac | 300965 | Gerona Western Public High School | Gerona | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Tarlac | 307001 | Moriones High School | San Jose | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Tarlac | 307001 | Moriones High School | San Jose | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300981 | Quezon Nhs | Gerona | 2 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Tarlac | 300986 | San Jose Nhs | Gerona | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 106456 | Sembrano Es | Gerona | 2 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Tarlac | 300995 | Tagumbao Nhs | Gerona | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 301000 | Victoria Nhs | Victoria | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26968000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Tarlac | 301001 | Villa Aglipay Nhs | San Jose | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Tarlac | 300949 | Anastacio G. Yumul High School | Concepcion | 3 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Tarlac | 300949 | Anastacio G. Yumul High School | Concepcion | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300951 | Benigno S. Aquino National High School | Concepcion | 3 | 1 | 24 | 4STY24CL | BATCH 13 CL | 35950800 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Tarlac | 300951 | Benigno S. Aquino National High School | Concepcion | 3 |  | 12 | 4STY12CL | BATCH 13 CL | 22372400 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Tarlac | 160010 | Burog Elementary School | Bamban | 3 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 300956 | Calangitan Hs (Resettlement School) | Capas | 3 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Tarlac | 300956 | Calangitan Hs (Resettlement School) | Capas | 3 |  | 4 | 2STY4CL | BATCH 3 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 300957 | Caluluan High School | Concepcion | 3 | 1 | 15 | 3STY15CL | BATCH 3 CL | 21596000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | Tarlac | 307017 | Caluluan High School Annex | Concepcion | 3 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Tarlac | 307017 | Caluluan High School Annex | Concepcion | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300994 | Capas High School | Capas | 3 | 1 | 24 | 4STY24CL | BATCH 13 CL | 35950800 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION III | Tarlac | 300961 | Comillas High School | La Paz | 3 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15271500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION III | Tarlac | 300976 | Cristo Rey Hs (Ores) | Capas | 3 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21595500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION III | Tarlac | 300962 | Dapdap Hs | Bamban | 3 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26968000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Tarlac | 300966 | Guevara Nhs | La Paz | 3 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18403000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Tarlac | 300966 | Guevara Nhs | La Paz | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300967 | La Paz Nhs | La Paz | 3 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31413000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION III | Tarlac | 300967 | La Paz Nhs | La Paz | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 106490 | Lara Ps | La Paz | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1958000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Tarlac | 300977 | O'Donnell High School | Capas | 3 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22373000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Tarlac | 300977 | O'Donnell High School | Capas | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac | 300990 | San Roque Nhs | Bamban | 3 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26968000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Tarlac | 106389 | Sta. Juliana Es | Capas | 3 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2668000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION III | Tarlac | 307005 | Sta. Juliana High School (O'Donnell Hs Annex) | Capas | 3 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac | 307005 | Sta. Juliana High School (O'Donnell Hs Annex) | Capas | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Tarlac | 106390 | Sta. Lucia Es | Capas | 3 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12898000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Tarlac | 300997 | Tarlac National Hs - Annex | City Of Tarlac (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION III | Tarlac | 300997 | Tarlac National Hs - Annex | City Of Tarlac (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2550000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac City | 321403 | Balibago Primero Integrated School | City Of Tarlac (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac City | 300960 | Central Azucarera De Tarlac Nhs Main | City Of Tarlac (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10878000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Tarlac City | 300970 | Maliwalo Nhs | City Of Tarlac (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION III | Tarlac City | 300970 | Maliwalo Nhs | City Of Tarlac (Capital) | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Tarlac City | 106759 | Pag-Asa Es | City Of Tarlac (Capital) | 2 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1015000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Tarlac City | 106759 | Pag-Asa Es | City Of Tarlac (Capital) | 2 |  | 2 | 1STY2CL | BATCH 5 CL | 1930000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION III | Tarlac City | 321408 | Sto. Cristo Is | City Of Tarlac (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 10877342.5917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Tarlac | 300996 | Tarlac National High School | City Of Tarlac (Capital) | 2 | 1 | 36 | 4STY12CL | BATCH 13 CL | 67117500 |  |  | Completed | 1 | [10 empty] | With approved additional funds | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0
NEWCON 2016 | REGION III | Tarlac City | 106774 | Tibagan Es | City Of Tarlac (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 301015 | Castillejos National High School | Castillejos | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14033441.1023 |  |  | Completed | 1 |  |  |  |  | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-21 | 42586 | M.V. Guballa Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Zambales | 301012 | Cawag Hs (Resettlement School) | Subic | 1 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8564965.05 |  |  | Completed | 1 |  |  |  |  | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-21 | 42586 | Sto. Cristo Const. & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Zambales | 160525 | Hanjin Integrated School | Castillejos | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6469337.64 |  |  | Completed | 1 |  |  |  |  | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-21 | 42586 | Repolman Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 107013 | Mapanao Es | Subic | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8294965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Zambales | 301029 | San Guillermo National High School | San Marcelino | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 11509179.0837 |  |  | Completed | 1 |  |  |  |  | 2016-05-23 | 2016-06-02 | 2016-06-14 | 2016-07-21 | 42586 | Repolman Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Zambales | 301029 | San Guillermo National High School | San Marcelino | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8364965.05 |  |  | Completed | 1 |  |  |  |  | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-21 | 42586 | MCB Zamora Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Zambales | 301035 | Sta. Fe Nhs | San Marcelino | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-23 | 2016-06-02 | 2016-06-14 | 2016-07-21 | 42586 | M.V. Guballa Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 301036 | Subic National High School | Subic | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 11509179.0837 |  |  | Completed | 1 |  |  |  |  | 2016-05-23 | 2016-06-02 | 2016-06-14 | 2016-07-21 | 42586 | MCB Zamora Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Zambales | 106869 | Amungan Es | Iba (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 301004 | Amungan Nhs | Iba (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8250000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Zambales | 301004 | Amungan Nhs | Iba (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-03 | 2016-03-10 | 2016-03-22 | 2016-07-01 | 42203 | E. R. DELACRUZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Zambales | 106825 | Arew Es | Cabangan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 301007 | Bani National High School - Coto Annex | Masinloc | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6470000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | HIGH STRENGTH DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 106887 | Bani Relocation Es | Masinloc | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | STO CRISTO CONST. & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 106989 | Bayto Es (Biay Es) | Santa Cruz | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6350000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 301025 | Botolan National High School | Botolan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Zambales | 301010 | Cabangan National High School | Cabangan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Zambales | 301011 | Candelaria School Of Fisheries | Candelaria | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Zambales | 106829 | Casa-Tondo Es | Cabangan | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 106906 | Cauyan Es | Palauig | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | FERMIDA CONST. SERVICES & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 106907 | Dampay Es | Palauig | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | NEW MASINLOC HENRY'S CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 301021 | Gov. Manuel D. Barretto National High School | San Felipe | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.5917 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | MCB ZAMORA CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Zambales | 301014 | Guisguis Nhs | Santa Cruz | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Zambales | 106876 | Lipay-Dingin Es | Iba (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8250000 |  |  | Completed | 1 |  |  |  |  | 2016-03-03 | 2016-03-10 | 2016-03-22 | 2016-07-01 | 42203 | E. R. DELACRUZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Zambales | 301028 | Locloc National High School | Palauig | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Zambales | 106892 | Mandaloy Es | Masinloc | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6450000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | HIGH STRENGTH DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 307115 | Mena Mem. Nhs - San Fernando Hs | Santa Cruz | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 7408468.5459 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | STO. CRISTO CONST. & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Zambales | 301022 | Mena Mem. Nhs (Bolitoc Nhs) | Santa Cruz | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8400000 |  |  | Completed | 1 |  |  |  |  | 2016-03-03 | 2016-03-10 | 2016-03-22 | 2016-07-01 | 42203 | STO. CRISTO CONST. & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Zambales | 301022 | Mena Mem. Nhs (Bolitoc Nhs) | Santa Cruz | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-03 | 2016-03-10 | 2016-03-22 | 2016-07-01 | 42203 | E. R. DELACRUZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Zambales | 106965 | Namatacan Es | San Narciso | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6450000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | NEW MASINLOC HENRY'S CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 301018 | Paite-Balincaguing National High School | San Felipe | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6419337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | MICKAJETTE CONST. & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 106916 | Palauig Central School | Palauig | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8250000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | NEW MASINLOC HENRY'S CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Zambales | 301027 | Rofulo M. Landa Hs (Salaza Nhs) | Palauig | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10950000 |  |  | Completed | 1 |  |  |  |  | 2016-03-03 | 2016-03-10 | 2016-03-22 | 2016-07-01 | 42197 | STO. CRISTO CONST. & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION III | Zambales | 106880 | San Agustin Integrated School | Iba (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8250000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | MCB ZAMORA CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION III | Zambales | 307107 | San Antonio National High School | San Antonio | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Zambales | 106968 | San Jose-Patrocinio Elementary | San Narciso | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | MICKAJETTE CONST. & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 301032 | San Miguel National High School | San Antonio | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | NEW MASINLOC HENRY'S CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Zambales | 106970 | San Narciso Elementary School | San Narciso | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | MICKAJETTE CONST. & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 301033 | Sta. Cruz Nhs | Santa Cruz | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Zambales | 301034 | Sta. Cruz Nhs - Lipay Hs | Santa Cruz | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Zambales | 301006 | Taltal National High School | Masinloc | 2 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12850000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION III | Zambales | 301006 | Taltal National High School | Masinloc | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION III | Zambales | 106930 | West Dirita Es | San Antonio | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 42591 | FERMIDA CONST. SERVICES & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION III | Zambales | 301037 | Zambales Nhs | Iba (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.