## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | Unnamed: 45 | Status as of July 4, 2025
GABALDON 2020 | Region IV-A | Laguna | 108446 | Santa Cruz CES | SANTA CRUZ (Capital) | 4 | 1 | 14 | 1 | Rehabilitation of Gabaldon Building | 18433661.59 | 1 | 18351437.96 | Completed | 1 |  | 2021-12-13 | Gabaldon 2020 - R IVA - Laguna - 001 |  | 2020-08-21 |  | 2020-09-14 | 2020-09-17 | 2020-11-25 | VRV Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region IV-A | Lucena City | 109742 | Lucena West I ES | LUCENA CITY (Capital) | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 25231446.67 | 1 |  | Completed | 1 | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  | CY 2022 |  |  | Completed
GABALDON 2020 | Region IV-A | San Pablo City | 109761 | Placido Escudero Memorial School | San Pablo City | 3 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2233477.93 | 1 | 1981761.12 | Completed | 1 |  | 2021-02-12 | GAB 2020 - RIV-A - San Pablo - 003 |  | 2019-11-18 |  | 2019-12-10 | 2020-09-02 | 2020-09-14 | M2 Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region IV-A | San Pablo City | 109758 | Stmo. Rosario Elementary School | San Pablo City | 3 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2086153.2721 | 1 | 2035730.39 | Completed | 1 |  | 2021-02-12 | GAB 2020 - RIV-A - San Pablo - 002 |  | 2019-11-18 |  | 2019-12-10 | 2020-09-02 | 2020-09-14 | M2 Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2021 | Region IV-A | Laguna | 108357 | Crisanto Guysayko MES | NAGCARLAN | 1 | 1 | 13 | 1 | Rehabilitation of Gabaldon Building | 16342158.44 | 1 |  | Completed | 1 |  | 2021-11-11 | Gabaldon 2021 - R IVA - Laguna - 001 |  | 2021-03-10 |  | 2021-04-05 | 2021-04-07 | 2021-07-14 | Hackstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office |  |  |  | Completed
GABALDON 2022 | Region IV-A | Laguna | 108364 | Rizal ES | RIZAL | 3 | 1 | 1 | 1 | Restoration of Gabaldon-Home Economics Building | 4782422.34 | 1 | 4221580.35 | Completed | 1 | 4/25/2023 | 4/25/2023 | R4A-2022-025 | R4A-2022-025 | 2022-09-09 | 9/15/2022 | 9/27/2022 | 11/21/2022 | 11/24/2022 | Open Builders Incorporated | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.23 | Division Office | CY 2023 |  |  | Completed
GABALDON 2023 | Region IV-A | Cavite | 108068 | Naic Elementary School | NAIC | 8 | 1 | 40 | 1 | Restoration & Conservation of Gabaldon Building | 73500276.2 | 1 | 170000000 | Ongoing | 0.7 | 2025-11-09 | N/A - ONGOING |  | RIVACaviteBAC-Infra 001-2024 | 5/14/2024 | 5/21/2024 | 2024-07-06 | 8/29/2024 | 9/16/2024 | JS LIM CONSTRUCTION AND TRADING, OPC | Waiting for the delivery of wood and already finishing the removal of plastering on the adobe walls | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.7 | 0 |  |  | Division Office |  |  |  | Ongoing
GABALDON 2023 | Region IV-A | Laguna | 108194 | San Benito ES | ALAMINOS | 3 | 1 | 4 | 1 | Restoration & Conservation of Gabaldon Building | 9433708.8 | 1 | 7063460.67 | Completed | 1 | 2/29/2024 | 2024-09-02 | 9822217 | R4A-2023-002 | 6/5-14/2023 | 6/13/2023 | 6/26/2023 | 6/29/2023 | 2023-05-07 | J.B. Alarcon Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 3.24 | Division Office | cy 2024 |  |  | Completed
GABALDON 2023 | Region IV-A | Quezon | 108847 | Lopez West Elementary School Bldg. I | LOPEZ | 4 | 1 | 22 | 1 | Restoration & Conservation of Gabaldon Building | 28732371.6 | 1 | 28714340 | Completed | 1 | 5/21/2024 | 2024-06-05 | 2023-02A-INFRA | 2023-02A-INFRA | 5/26/2023 | 2023-02-06 | 6/14/2023 | 8/16/2023 | 8/23/2023 | Hawkstow Construction and Development | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7.24 | Division Office |  |  |  | Completed
GABALDON 2023 | Region IV-A | Quezon | 108996 | Perez CS | PEREZ | 4 | 1 | 2 | 1 | Restoration & Conservation of Gabaldon Building | 2913266.4 | 1 | 2903257.83 | Completed | 1 | 12/22/2023 | 2023-01-12 | 2023-03R-INFRA | 2023-03R-INFRA | 2023-08-08 | 8/16/2023 | 8/29/2023 | 2023-06-09 | 9/13/2023 | M.G Villamin Construction | The school name is incorrect, it should be Perez West ES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4.24 | Division Office | cy 2024 |  |  | Completed
GABALDON 2024 | Region IV-A | Antipolo City | 109327 | Juan Sumulong ES | CITY OF ANTIPOLO | 2nd | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 7211999.95 | 1 |  | Not Yet Started | 0 | [10 empty] | Awaiting approval of submitted CMP | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | Division Office |  | 1 | 0 | Not Yet Started
GABALDON 2024 | Region IV-A | Batangas | 107263 | Bauan East Central School | BAUAN | 2nd | 1 | 18 | 1 | Conservation and Restoration of Gabaldon School Building | 20221416 | 1 |  | Not Yet Started | 0 | [10 empty] | Waiting approval of NHCP | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | Division Office |  | 1 | 0 | Not Yet Started
GABALDON 2024 | Region IV-A | Batangas | 107736 | Venancio Trinidad Sr. Memorial School | TALISAY | 3rd | 1 | 1 | 1 | Conservation and Restoration of Gabaldon School Building | 4322959.77 | 1 |  | Not Yet Started | 0 | [10 empty] | Waiting approval of NHCP | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | Division Office |  | 1 | 0 | Not Yet Started
GABALDON 2024 | Region IV-A | Cavite | 107994 | Indang Central Elementary School | Indang | 7th | 1 | 10 | 1 | Conservation and Restoration of Gabaldon School Building | 25823069.04 | 1 | 17000000 | Ongoing | 0.7 | 5/14/2025 | N/A - ONGOING |  | RIVACaviteBAC-Infra 002-2024 | 5/14/2024 | 5/21/2024 | 2024-07-06 | 8/29/2024 | 9/16/2024 | JS LIM CONSTRUCTION AND TRADING, OPC | With Approved Extension due to scarcity of wood | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.7 | 0 |  |  | Division Office |  |  | 7 | Ongoing
GABALDON 2024 | Region IV-A | Cavite | 108068 | Naic Elementary School | NAIC | 8th | 1 | 40 | 1 | Conservation and Restoration of Gabaldon School Building | 99704396.58 | 1 | Combined with Phase 1 | Ongoing | 0.7 | 2025-11-09 | N/A - ONGOING |  | RIVACaviteBAC-Infra 001-2024 | 5/14/2024 | 5/21/2024 | 2024-07-06 | 8/29/2024 | 9/16/2024 | JS LIM CONSTRUCTION AND TRADING, OPC |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.7 | 0 |  |  | Division Office |  |  | 7 | Ongoing
GABALDON 2024 | Region IV-A | Cavite City | 109629 | Julian R. Felipe ES | CAVITE CITY | 1st | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 11565863.92 | 1 | 7798828.33 | Completed | 1 | 4/22/2025 | 2025-03-06 | 2024-06-0006 | 2024-06-0006 | 2024-04-06 | 6/13/2024 | 6/26/2024 | 2024-04-07 | 9/24/2024 | ASS Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0.8 | 0.2 |  | 5.25 | Division Office |  |  | 7 | Ongoing
GABALDON 2024 | Region IV-A | Dasmarinas City | 107911 | Sabang Elementary School | CITY OF DASMARIÑAS | 4th | 1 | 6 | 1 | Conservation and Restoration of Gabaldon School Building | 21481580.08 | 1 | 15021854.56 | Not Yet Started | 0 |  |  | CY2024 BEFF - | CY2024 BEFF - | March 13, 2024- | 3/21/2024 | 2024-03-04 | 2024-03-05 |  | GS Motar Builders | Waiting for Approval of CMP from NCCA (CMP IS ALREADY APPROVED BY NHCP) | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | Division Office |  |  | 4 | Ongoing
GABALDON 2024 | Region IV-A | Gen. Trias City | 107957 | Bacao Elementary School | CITY OF GENERAL TRIAS | 6th | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 4888490 | 1 |  | Not Yet Started | 0 |  |  | Conservation and Restoration | Gabaldon | March 20, 2024 |  |  |  |  | Construction and Trading | Waiting for Approval of CMP from NCCA and NHCP | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | Division Office |  | 1 | 0 | Not Yet Started
GABALDON 2024 | Region IV-A | Laguna | 301278 | Upland INHS | NAGCARLAN | 3rd | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 5800201.57 | 1 | 4325917.97 | Ongoing | 0.7 | 2025-11-09 | - | of Gabaldon Building | [7 empty] | Ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.1 | 0.6 |  |  | Division Office |  |  | 10 | Ongoing
GABALDON 2024 | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School | LIPA CITY | 6th | 1 | 11 | 1 | Conservation and Restoration of Gabaldon School Building | 31535799.71 | 1 | 31485799.71 | Completed | 1 | 3/30/2025 | 4/26/2025 | [7 empty] | Open Builders Incorporated |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0.95 | 0.05 |  | 5.25 | Division Office |  |  | 4 | Ongoing
GABALDON 2024 | Region IV-A | Lipa City | 109703 | Tambo ES | LIPA CITY | 6th | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 18284448.8 | 1 | 18234448.8 | Completed | 1 | 3/30/2025 | 2024-05-12 | R4A-2024-008 | R4A-2024-008 | 2024-02-05 | May 9, 2025 | May 23,2024 | 2024-07-08 | 2025-03-04 | gs motar builders/ marakesh enterprises jv |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 12.24 | Division Office |  |  | 4 | Completed
GABALDON 2024 | Region IV-A | Lipa City | 109669 | Teodoro M. Kalaw MS | LIPA CITY | 6th | 1 | 5 | 1 | Conservation and Restoration of Gabaldon School Building | 13347715.85 | 1 | 13297705.45 | Completed | 1 | 1/29/2025 | 11/13/2024 |  |  |  | (Pre-Bid Conference) |  |  |  | gs motar builders/ tpmcs corp jv |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 11.24 | Division Office |  |  | 4 | Completed
GABALDON 2024 | Region IV-A | Lucena City | 109742 | Lucena West I Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 18 | 1 | Conservation and Restoration of Gabaldon School Building | 16591885.38 | 1 | 16540591.57 | Completed | 1 | 5/31/2025 | 1/25/2025 | GAB 2024-RIVA-LIPA CITY-002 | GAB 2024-RIVA-LIPA CITY-002 | 2024-06-05 | 5/14/2024 | 5/27/2024 | 2024-10-06 | 2024-02-08 | marakesh enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0.85 | 0.15 |  | 5.25 | Division Office |  |  | 7 | Ongoing
GABALDON 2024 | Region IV-A | Quezon | 109272 | Claro M. Recto Memorial CS | TIAONG | 2nd | 1 | 13 | 1 | Conservation and Restoration of Gabaldon School Building -13CL (39.00m x 35.00m) | 16923003.49 | 1 | 16870000 | Completed | 1 | 2/18/2025 | 11/15/2024 | GAB 2024-RIVA-LIPA CITY-003 | GAB 2024-RIVA-LIPA CITY-003 | 2024-06-05 | 5/14/2024 | 5/27/2024 | 2024-10-06 | 2024-02-08 | GS MOTAR BUILDERS CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 11.24 | Division Office |  |  | 4 | Completed
GABALDON 2024 | Region IV-A | Quezon | 108649 | Catanauan CS | CATANAUAN | 3rd | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 9477101.16 | 1 | 9450000 | Completed | 1 | 1/19/2025 | 2025-07-01 | GAB 2024-RIVA-LIPA CITY-001 | GAB 2024-RIVA-LIPA CITY-001 | 2024-06-05 | 5/14/2024 | 5/27/2024 | 2024-10-06 | 2024-02-08 | Botey Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0.95 | 0.05 |  | 5.25 | Division Office |  |  | 4 | Ongoing
GABALDON 2024 | Region IV-A | San Pablo City | 109763 | San Cristobal Elementary School | SAN PABLO CITY | 3rd | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 6400000 | 1 |  | Under Procurement | 0 |  |  | 2023-LUCENA CITY-005 | 2023-LUCENA CITY-005 | 6/27/2024 | 2024-05-07 | 7/17/2024 | 9/27/2024 | 2024-04-10 | Botey Construction | for approval of CMP | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | Division Office |  | 1 | 0 | Under Procurement
GABALDON 2024 | Region IV-A | Tanauan City | 107782 | Tanauan South Central School | CITY OF TANAUAN | 3rd | 1 | 10 | 1 | Conservation and Restoration of Gabaldon School Building | 17478526.17 | 1 | 17421569.07 | Completed | 1 |  | 2/28/2025 | 2024-01-INFRAEPA | 2024-01-INFRAEPA | 3/27/2024 | 2024-03-04 | 4/15/2024 | 2024-12-07 | 7/24/2024 |  | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0.53 | 0.47 |  | 5.25 | Division Office |  |  | 6 | Ongoing

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%