## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | No. of Classrooms | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated | Previous % | Difference | STOREY | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | Status as of July 4, 2025
NEWCON 2016 | REGION IV-A | Antipolo City | 301448 | Mambugan Nhs | City Of Antipolo | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 32150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 301422 | Mayamot Nhs | City Of Antipolo | 1 | 1 | 32 | 4STY8CL | BATCH 13 CL | 60640075.36 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 301422 | Mayamot Nhs | City Of Antipolo | 1 |  | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109341 | Sapinit Es | Antipolo City | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109342SHS | Sta. Cruz Es | City Of Antipolo | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 32950000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109361 | Sumilang Es | Antipolo City | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 321502 | Antipolo Nhs - Canumay Extension | City Of Antipolo | 2 | 1 | 6 | 3STY6CL | BATCH 1 CL | 10650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 301421 | Antipolo Nhs - Kaysakat Extension | City Of Antipolo | 2 | 1 | 8 | 4STY8CL | BATCH 1 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DNO036 | 2016-02-28 | 2016-03-04 | 2016-03-17 | 2016-03-21 | 42451 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109335 | Cabading Es | City Of Antipolo | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15470000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 301431 | Calawis Nhs | City Of Antipolo | 2 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6500000 |  |  | Completed | 1 |  |  |  | 16DNO021 | 2016-02-18 | 2016-02-24 | 2016-03-08 | 2016-03-15 | 42447 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 230002 | Cupang Es Annex | City Of Antipolo | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15470000 |  |  | Reverted | 0 | [10 empty] | CY 2015-2016 BEFF REVERSIONS (BATCH 1) | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 301420 | Dalig Nhs To Cupang Nhs | City Of Antipolo | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22650000 |  |  | Reverted | 0 | [10 empty] | Realigned to Cupang NHS. Construction was not started because of the informal settlers. Requested for termination by DPWH (terminated) | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109326 | Inuman Es | City Of Antipolo | 2 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15470000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109350 | Isaias S. Tapales Es | City Of Antipolo | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109352 | From Kaysakat Es, Old Boso Boso Es And Pantay Es To Kaysakat Es | City Of Antipolo | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 7806036.0641 |  |  | Completed | 1 | [10 empty] | Terminated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 321501 | Marcelino M. Santos Nhs | City Of Antipolo | 2 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 301450 | Maximo L. Gatlabayan Memorial Nhs | City Of Antipolo | 2 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15470000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 308101 | Maximo L. Gatlabayan Mnhs - Old Boso-Boso Extension | City Of Antipolo | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109333 | Nazarene Ville Es | City Of Antipolo | 2 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31650000 |  |  | Reverted | 0 | [10 empty] | CY 2015-2016 BEFF REVERSIONS (BATCH 1) | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109334 | Old Boso-Boso Es | City Of Antipolo | 2 |  |  | 1STY3CL | BATCH 9 CL |  |  |  | Reverted | 0 | [10 empty] | Realigned to Kaysakat ES Terminated | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109354 | Pantay Es | City Of Antipolo | 2 |  |  | 1STY3CL | BATCH 9 CL |  |  |  | Reverted | 0 | [10 empty] | Realigned to Kaysakat ES Terminated | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109338 | Peñafrancia Es Annex | City Of Antipolo | 2 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109357 | Rizza Es | City Of Antipolo | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6650000 |  |  | Completed | 1 |  |  |  | 16DNO034 | 2016-02-26 | 2016-03-04 | 2016-03-17 | 2016-03-21 | 42451 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 301457 | San Jose Nhs | City Of Antipolo | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 301427 | San Juan Nhs | City Of Antipolo | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15470000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 109340 | San Luis Es | City Of Antipolo | 2 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22650000 |  |  | Reverted | 0 | [10 empty] | CY 2015-2016 BEFF REVERSIONS (BATCH 1) | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION IV-A | Antipolo City | 230001 | Tanza Es | City Of Antipolo | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15470000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107877 | Aniban Cs | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107867 | Bacoor Es | Bacoor | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1 |  |  |  | 16DF0161 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107867 | Bacoor Es | Bacoor | 2 |  | 6 | 3STY6CL | BATCH 9 CL | 10420000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 307803 | Bacoor Nhs - Gawaran Annex | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16DF0151 | [5 empty] | OMNICON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107878 | Bayanan Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24702577.982 |  |  | Completed | 1 |  |  |  | 16DF0160 | [5 empty] | OMNICON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107869 | Dulong Bayan Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16DF0152 | [5 empty] | R.D MANDANAS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 301188 | Eastern Bacoor Nhs | Bacoor | 2 | 1 | 16 | 4STY8CL | BATCH 9 CL | 32744541.448 |  |  | Completed | 1 |  |  |  | 16DF0163 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107879 | Gawaran Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16DF0153 | [5 empty] | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107880 | Gov. P. F. Espiritu Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24562577.982 |  |  | Completed | 1 |  |  |  | 16DF0157 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107881 | Ligas I Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16DF0154 | [5 empty] | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107872 | Maliksi Es | Bacoor | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29612716.362 |  |  | Completed | 1 |  |  |  | 16DF0162 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107885 | Malipay Es | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 |  |  |  | 16DF0147 | [5 empty] | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107873 | Mambog Es | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 |  |  |  | 16DF0148 | [5 empty] | D.V SALUD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107886 | Molino Elementary School | Bacoor | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1 |  |  |  | 16DF0165 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107886 | Molino Elementary School | Bacoor | 2 |  | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 |  |  |  | 16DF0149 | [5 empty] | N.B AVILA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 164009 | Poblacion Es (Bacoor Es (Annex)) | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 |  |  |  | 16DF0150 | [5 empty] | N.B AVILA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107888 | Queen'S Row Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16DF0155 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107875 | Salinas Es | Bacoor | 2 | 1 | 16 | 4STY8CL | BATCH 9 CL | 32744541.448 |  |  | Completed | 1 |  |  |  | 16DF0164 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107889 | San Nicolas Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24563880.2731 |  |  | Completed | 1 |  |  |  | 16DF0159 | [5 empty] | R.A DEL ROSARIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | PSA328431 | Shs In Progressive, Bacoor City | Bacoor City | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16DF0156 | [5 empty] | N.B AVILA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | PSA328432 | Shs In San Nicholas Iii, Bacoor City | Bacoor City | 2 | 1 | 40 | 4STY20CL | BATCH 9 CL | 68396358.594 |  |  | Completed | 1 |  |  |  | 16DF0166 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107890 | Sineguelasan Es To Talaba Es | Bacoor | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 31451110.2855 |  |  | Completed | 1 |  |  |  | 16DF0229 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Bacoor City | 107891 | Zapote Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24562577.982 |  |  | Terminated | 0.07 |  |  |  | 16DF0158 | [5 empty] | BAQPRINCE CONSTRUCTION | CONTRACT TERMINATED (no access to site due to informal settlers) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12
NEWCON 2016 | REGION IV-A | Batangas | 307728 | Angeles Luistro Nhs | San Juan | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2690828.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION IV-A | Batangas | 307729 | Aplaya National High School | San Juan | 1 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301088 | Bolbok Nhs | Tuy | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6469337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107228 | Caloocan Es | Balayan | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107228 | Caloocan Es | Balayan | 1 |  | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107229 | Canda Es | Balayan | 1 | 1 | 24 | 4STY24CL | BATCH 5 CL | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107229 | Canda Es | Balayan | 1 |  | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107236 | Cipriana Ascue Mes | Balayan | 1 | 1 | 6 | 2STY6CL | BATCH 11 CL | 10691021.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107727 | Cubamba-Gahol Es | Taal | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1914740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301102 | Gov. Feliciano Leviste Mnhs | Lemery | 1 | 1 | 48 | 4STY24CL | BATCH 9 CL | 78281765.708 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301102 | Gov. Feliciano Leviste Mnhs | Lemery | 1 |  | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301102 | Gov. Feliciano Leviste Mnhs | Lemery | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4836000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Batangas | 307710 | Jose Lopez Manzano Community Hs | Tuy | 1 | 1 | 2 | 1STY2CL | BATCH 11 CL | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301111 | Lucsuhin Nhs | Calatagan | 1 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107511 | Nasugbu East Central School | Nasugbu | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107514SHS | Pantalan Es | Nasugbu | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107514 | Pantalan Es | Nasugbu | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | Newly established school | Santol Es Realigned To Balayan Shs | Balayan | 1 | 1 | 24 | 4STY24CL | BATCH 9 CL | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Batangas | Newly established school | Santol Es Realigned To Balayan Shs | Balayan | 1 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas | 307718 | Sen. Gil Puyat Nhs | Nasugbu | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6369337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328446 | Shs In Calaca | Calaca | 1 | 1 | 24 | 4STY24CL | BATCH 5 CL | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328446 | Shs In Calaca | Calaca | 1 |  | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328446 | Shs In Calaca | Calaca | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328450 | Shs In Calatagan | Calatagan | 1 | 1 | 48 | 4STY24CL | BATCH 1 CL | 71442514.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328447 | Shs In Lian | Lian | 1 | 1 | 24 | 4STY24CL | BATCH 11 CL | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328448 | Shs In Tuy | Tuy | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328448 | Shs In Tuy | Tuy | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107734 | Taal Cs | Taal | 1 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107734 | Taal Cs | Taal | 1 |  | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107521 | Wawa Es | Nasugbu | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14991327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107668 | Alalum Es | San Pascual | 2 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10467131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301115 | Anselmo Sandoval Mnhs (Mabini Nhs) | Mabini | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301115 | Anselmo Sandoval Mnhs (Mabini Nhs) | Mabini | 2 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301115 | Anselmo Sandoval Mnhs (Mabini Nhs) | Mabini | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107260 | Baguilawa Es | Bauan | 2 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10492131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301080 | Bauan Technical High School | Bauan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107431 | Bignay Ps | Lobo | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1062049.65 |  |  | Completed | 1 |  |  | P00073165LZ-CW1 | [6 empty] | TRISTAN TEJADA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107645 | Calumpang Es | San Luis | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301104 | Inicbulan Nhs | Bauan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6394337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107675 | Malakimpook Es | San Pascual | 2 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107273 | Manghinao Es | Bauan | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107442 | Nagtoctoc Ps | Lobo | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1087049.65 |  |  | Completed | 1 |  |  | P00073169LZ-CW1 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | 307730 | Rosario Technical High School | Rosario | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22227343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107683SHS | San Antonio Es | San Pascual | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328462 | Shs In Batangas City (Sports) | Batangas City (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328451 | Shs In Lobo | Lobo | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26882469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328461 | Shs In Rosario, Batangas | Rosario | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328458 | Shs In Sto. Tomas | Santo Tomas | 2 | 1 | 48 | 4STY24CL | BATCH 5 CL | 71192514.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328458 | Shs In Sto. Tomas | Santo Tomas | 2 |  | 40 | 4STY20CL | BATCH 5 CL | 62205780.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328458 | Shs In Sto. Tomas | Santo Tomas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107817 | Sto. Tomas Ps | Tingloy | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107820 | Tingloy Cs | Tingloy | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107264 | West Bauan Cs | Bauan | 2 | 1 | 24 | 4STY24CL | BATCH 9 CL | 39140882.854 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107215 | Alitagtag Central School | Alitagtag | 3 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301073 | Balete Nhs | Balete | 3 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301076 | Banyaga Nhs | Agoncillo | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6394337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107336 | Briccio Pantas Mes | Cuenca | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107371 | Bugaan Es | Laurel | 3 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10492131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107662 | Calangay Es | San Nicolas | 3 | 1 | 6 | 2STY6CL | BATCH 11 CL | 10691021.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107339 | Cuenca Cs | Cuenca | 3 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107339 | Cuenca Cs | Cuenca | 3 |  | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107486 | Lumanglipa Es | Mataas Na Kahoy | 3 | 1 | 6 | 2STY6CL | BATCH 11 CL | 10691021.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107254 | Malabanan Es | Balete | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6369337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107218 | Munlawin Es | Alitagtag | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107218 | Munlawin Es | Alitagtag | 3 |  | 3 | 1STY3CL | BATCH 7 CL | 2640828.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107256 | Palsara Es | Balete | 3 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107212 | Pook Es | Agoncillo | 3 | 1 | 4 | 1STY2CL | BATCH 7 CL | 3629480.34 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107382 | San Gregorio Es - Annex | Laurel | 3 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10492131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 307713 | San Nicolas Nhs | San Nicolas | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328455 | Shs In Agoncillo | Agoncillo | 3 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328445 | Shs In Brgy. Bugaan East, Laurel, Batangas | Laurel | 3 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328445 | Shs In Brgy. Bugaan East, Laurel, Batangas | Laurel | 3 |  | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328445 | Shs In Brgy. Bugaan East, Laurel, Batangas | Laurel | 3 |  | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328445 | Shs In Brgy. Bugaan East, Laurel, Batangas | Laurel | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328456 | Shs In Malvar | Malvar | 3 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107695 | Tambo Es | Santa Teresita | 3 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8314965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107736 | Venancio Trinidad Sr. Memorial School | Talisay | 3 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301069 | Alupay Nhs | Rosario | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2483000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107584 | Aya Es | San Jose | 4 | 1 | 2 | 1STY1CL | BATCH 7 CL | 2099099.3 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107525 | Bawi Es | Padre Garcia | 4 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301082 | Baybayin Nhs | Rosario | 4 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301082 | Baybayin Nhs | Rosario | 4 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301090 | Buhaynasapa Nhs | San Juan | 4 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301090 | Buhaynasapa Nhs | San Juan | 4 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107548 | Calantas Es | Rosario | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301098 | Dagatan Nhs | Taysan | 4 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301098 | Dagatan Nhs | Taysan | 4 |  | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301098 | Dagatan Nhs | Taysan | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | 307714 | Dr. Bonifacio A. Masilungan National High School | San Jose | 4 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas | 307714 | Dr. Bonifacio A. Masilungan National High School | San Jose | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301153 | Dr. Juan A. Pastor Mnhs (Talaibon Nhs) | Ibaan | 4 | 1 | 15 | 3STY15CL | BATCH 11 CL | 21383013.45 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107597 | Florencia A. Masilungan Mes | San Jose | 4 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2640828.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107355 | Ibaan Cs | Ibaan | 4 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301105 | Itlugan Nhs | Rosario | 4 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107552 | Julian D. Luna Es | Rosario | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301108 | Laiya Nhs | San Juan | 4 | 1 | 32 | 4STY16CL | BATCH 5 CL | 53404938.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107593 | Lapolapo Es | San Jose | 4 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2640828.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION IV-A | Batangas | 307725 | Lipahan National High School | San Juan | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6394337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107529 | Manggas-Tamak Es | Padre Garcia | 4 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107561 | Masaya Es | Rosario | 4 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 307707 | Nagsaulay Nhs | San Juan | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107564 | Namuco Es | Rosario | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107635 | Paaralang Elementarya Ng Talahiban 1.0 1.0 | San Juan | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6394337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301129 | Padre Garcia Nhs | Padre Garcia | 4 | 1 | 24 | 4STY24CL | BATCH 9 CL | 39140882.854 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301129 | Padre Garcia Nhs | Padre Garcia | 4 |  | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301130 | Palahanan Nhs | San Juan | 4 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62205780.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301132 | Pansol Nhs | Padre Garcia | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6394337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107595 | Pinagtungulan Es | San Jose | 4 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 107591 | Roman Ozaeta M/S | San Jose | 4 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301139 | Rosario Nhs | Rosario | 4 | 1 | 16 | 4STY16CL | BATCH 1 CL | 26802469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Batangas | 1076631SHS | San Juan East Shs | San Juan | 4 | 1 | 6 | 2STY6CL | BATCH 11 CL | 10691021.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Batangas | PSA328460 | Shs In Taysan | Taysan | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301155 | Taysan Nhs | San Jose | 4 | 1 | 24 | 4STY12CL | BATCH 5 CL | 44304687.24 |  |  | Completed | 1 | [10 empty] | With approved additional funds | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301156 | Tilambo Nhs | Taysan | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Batangas | 301160 | Tipas Nhs | San Juan | 4 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas City | 109582 | Alangilan Es | Batangas City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26782469.42 |  |  | Completed | 1 |  |  |  |  | 2016-07-08 | 2016-07-15 | 2016-07-28 | 2016-08-16 | 42608 | W. Rivera Construction & Equipment |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Batangas City | 301470 | Balete National High School | Batangas City (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22272343.62 |  |  | Completed | 1 |  |  |  |  | 2016-02-24 | 2016-03-02 | 2016-03-16 | 2016-05-11 | 42516 | Granby Trading & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Batangas City | 109550SHS | Gulod Es | Batangas City (Capital) | 2 | 1 | 32 | 4STY16CL | BATCH 11 CL | 53693014.0853 |  |  | Completed | 1 | [8 empty] | 42688 | Great Swiss Metal Builders Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION IV-A | Batangas City | 301474 | Paharang Nhs | Batangas City (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14997518.84 |  |  | Completed | 1 |  |  |  |  | 2016-02-24 | 2016-03-02 | 2016-03-16 | 2016-05-11 | 42516 | Granby Trading & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas City | 301475 | Pedro S. Tolentino Mnhs | Batangas City (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11065000 |  |  | Completed | 1 |  |  |  |  | 2016-02-24 | 2016-03-02 | 2016-03-16 | 2016-05-11 | 42516 | Granby Trading & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Batangas City | 301479 | San Agustin Nhs | Batangas City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6782000 |  |  | Completed | 1 |  |  |  | 16DE-0135 | 2016-10-09 | 2016-10-13 | 2016-10-25 | 2016-11-13 | 42695 | W. Rivera Construction & Equipment |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Biñan City | PSA328504 | Stand Alone 3 (Bsc) | Binan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31252890 |  |  | Completed | 1 |  |  |  | 16DI0103 |  |  |  | September 5, 2016 | September 14, 2016 | Miclover General Construction & Iron Works |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Biñan City | PSA328504 | Stand Alone 3 (Bsc) | Binan City | 1 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DI0102 |  |  |  | September 5, 2016 | September 14, 2016 | 11 Diamond Eagle Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Biñan City | PSA328505 | Stand Alone 4 (Colegio San Antonio) | Binan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31252890 |  |  | Completed | 1 |  |  |  | 16DI0106 |  |  |  | September 26, 2016 | October 4, 2016 | St. Gerrard Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Biñan City | PSA328505 | Stand Alone 4 (Colegio San Antonio) | Binan City | 1 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DI0104 |  |  |  | September 26, 2016 | October 4, 2016 | Power K Construction Supply & Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Calamba City | 301514 | Calamba Bayside National High School | City Of Calamba | 2 | 1 | 16 | 4STY8CL | BATCH 11 CL | 29893354.4723 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Calamba City | 301516 | Camp Vicente Lim Nhs | City Of Calamba | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 29029387.4 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Calamba City | 301516 | Camp Vicente Lim Nhs | City Of Calamba | 2 |  | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108087 | Agustin Abadilla Es | Rosario | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16DF0112 | [5 empty] | R.D MANDANAS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108084 | Ambrocio Robles Mes (San Jose Es) | Noveleta | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00073182LZ | 16DF0185 | [5 empty] | FE S. REYES GEN CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301189 | Emiliano T. Tirona Mnhs | Kawit | 1 | 1 | 40 | 4STY20CL | BATCH 7 CL | 62205780.54 |  |  | Completed | 1 |  |  |  | 16DF0120 | [5 empty] | C.T LEONCIO CONST. & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108020 | Gahak-Marulas Es | Kawit | 1 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10517131.51 |  |  | Completed | 1 |  |  |  | 16DF0092 | [5 empty] | ALMAKAR BUILDERS & METAL WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108081 | Noveleta Es | Noveleta | 1 | 1 | 24 | 4STY12CL | BATCH 7 CL | 44304687.24 |  |  | Completed | 1 |  |  |  | 16DF0116 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108091 | Rosario Es | Rosario | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0107 | [5 empty] | R.A DEL ROSARIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108095 | Bagong Buhay Es | Silang | 5 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108095 | Bagong Buhay Es | Silang | 5 |  | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301180 | Bulihan Nhs | Silang | 5 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301180 | Bulihan Nhs | Silang | 5 |  | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301192 | Gen. Mariano Alvarez Tech. Hs | Gen. Mariano Alvarez | 5 | 1 | 40 | 4STY20CL | BATCH 13 CL | 62505780.54 |  |  | Completed | 1 |  |  |  | 16DF0216 | [5 empty] | HAUSLAND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301193 | Gen. Vito Belarmino Nhs | Silang | 5 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301197 | Kaong Nhs | Silang | 5 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301203 | Malabag Nhs | Silang | 5 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 307813 | Munting Ilog Nhs (Silang West Annex) | Silang | 5 | 1 | 16 | 4STY8CL | BATCH 7 CL | 29795037.68 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Cavite | 107940 | San Gabriel I Es | Gen. Mariano Alvarez | 5 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0105 | [5 empty] | OMNICON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 107940 | San Gabriel I Es | Gen. Mariano Alvarez | 5 |  | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0099 | [5 empty] | OMNICON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301213 | San Jose Community Hs | Gen. Mariano Alvarez | 5 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | PSA328465 | Shs In Carmona | Carmona | 5 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0174 | [5 empty] | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Cavite | PSA328465 | Shs In Carmona | Carmona | 5 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0173 | [5 empty] | OMNICON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108136 | Tartaria Es | Silang | 5 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301180 | Ulat Es Realigned To Bulihan Nhs | Silang | 5 |  | 16 | 4STY16CL | BATCH 1 CL | 27702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301166 | Amadeo Nhs | Amadeo | 6 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0206 | [5 empty] | C.T LEONCIO CONST& TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108155 | Amaya Es | Tanza | 6 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0108 | [5 empty] | N.B AVILA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301167 | Amaya Sch. Of Home Industries | Tanza | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0213 | [5 empty] | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108163 | Bienvenido R. Fojas Mes | Tanza | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14997518.84 |  |  | Completed | 1 |  |  |  | 16DF0101 | [5 empty] | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | General Trias City | 107946 | Buenavista Es | General Trias | 6 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0176 | [5 empty] | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108170 | Felipe Calderon Es (Tanza Es) | Tanza | 6 | 1 | 24 | 4STY12CL | BATCH 7 CL | 44304687.24 |  |  | Completed | 1 |  |  |  | 16DF0117 | [5 empty] | C.T LEONCIO CONST. & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Cavite | 307808 | Francisco Osorio Nhs (Trece Martires City Nhs (Osorio Annex)) | Trece Martires City (Capital) | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0098 | [5 empty] | J.S. CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | General Trias City | 301194 | Gov. Ferrer Mnhs (Main) | General Trias | 6 | 1 | 32 | 4STY16CL | BATCH 7 CL | 53404938.84 |  |  | Completed | 1 |  |  |  | 16DF0118 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION IV-A | General Trias City | 307802 | Governor Ferrer Memorial National High School (Buenavista Annex) | General Trias | 6 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22352343.62 |  |  | Completed | 1 |  |  |  | 16DF0111 | [5 empty] | D.V SALUD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108157 | Gregorio B. Fojas Ms | Tanza | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0096 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | General Trias City | 107953 | Juliano C. Brosas Es | General Trias | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0172 | [5 empty] | MONTADEL ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | General Trias City | 307822 | Luis Y. Ferrer Jr. West National High School | General Trias | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0093 | [5 empty] | N.B AVILA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | General Trias City | 307823 | Luis Y. Ferrer, Jr. North National High School | General Trias | 6 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0207 | [5 empty] | N.B AVILA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108165 | Paradahan Es | Tanza | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0100 | [5 empty] | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | General Trias City | 107964 | Pasong Camachile Es | General Trias | 6 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10517131.51 |  |  | Completed | 1 |  |  |  | 16DF0182 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | General Trias City | 107954 | Pasong Kawayan Ii Es | General Trias | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0094 | [5 empty] | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | General Trias City | 107965 | San Francisco Es | General Trias | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0095 | [5 empty] | N.B AVILA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | General Trias City | 107966 | Santiago Es | General Trias | 6 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0106 | [5 empty] | D.V SALUD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108168 | Santol Es | Tanza | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14997518.84 |  |  | Completed | 1 |  |  |  | 16DF0102 | [5 empty] | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | General Trias City | PSA328466 | Shs In Gen. Trias | Gen. Trias | 6 | 1 | 16 | 4STY8CL | BATCH 11 CL | 29795037.68 |  |  | Completed | 1 |  |  |  | 16DF0200 | [5 empty] | OMNICON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Cavite | PSA328472 | Shs In Tanza | Tanza | 6 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0104 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | PSA328472 | Shs In Tanza | Tanza | 6 |  | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0113 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Cavite | PSA328473 | Shs In Trece Martires | Trece Martires City | 6 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16DF0186 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | General Trias City | 164017 | Sunny Brooke Elementary School | General Trias | 6 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0114 | [5 empty] | D.V SALUD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301219 | Tanza Nts | Tanza | 6 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16DF0199 | [5 empty] | OMNICON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301222 | Trece Martires City Nhs | Trece Martires City (Capital) | 6 | 1 | 40 | 4STY20CL | BATCH 7 CL | 62205780.54 |  |  | Completed | 1 |  |  |  | 16DF0119 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IV-A | Cavite | 307819 | Trece Martirez City Nhs (Cabezas Annex) | Trece Martires City (Capital) | 6 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0109 | [5 empty] | J.S. GEN CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108171 | Tres Cruses Es | Tanza | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14997518.84 |  |  | Completed | 1 |  |  |  | 16DF0103 | [5 empty] | HEXAMINDZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301165 | Alfonso National High School | Alfonso | 8 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301173 | Bendita Nhs | Magallanes | 8 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301175 | Bucal Nhs | Maragondon | 8 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301178 | Cavite Nat'L. Science Hs | Maragondon | 8 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108055 | Galicia Es | Mendez (Mendez-Nuñez) | 8 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301191 | Gen. Emilio Aguinaldo Nhs (Bailen) | General Emilio Aguinaldo | 8 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301198 | Kaytitinga Nhs | Alfonso | 8 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301204 | Maragondon Nhs | Maragondon | 8 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108056 | Mendez Cs | Mendez (Mendez-Nuñez) | 8 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301206 | Naic Coastal Nhs | Naic | 8 | 1 | 5 | 1STY5CL | BATCH 13 CL | 4523636.82 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301206 | Naic Coastal Nhs | Naic | 8 |  | 4 | 1STY2CL | BATCH 13 CL | 3877212.08 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301207 | Naic Nhs | Naic | 8 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301207 | Naic Nhs | Naic | 8 |  | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 108077 | Petronilo L. Torres Mes (Sabang Es) | Naic | 8 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301211 | Pulo Ni Sara Nhs | Maragondon | 8 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Cavite | PSA328467 | Shs In Mendez | Mendez | 8 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301216 | Tagaytay City National High School | Tagaytay City | 8 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Cavite | 301221 | Ternate Nhs | Ternate | 8 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite City | 109635 | Dalahican Elem. School | Cavite City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22314343.62 |  |  | Completed | 1 |  |  |  | 16DF0211 | [5 empty] | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Cavite City | 109637 | Manuel S. Rojas Es | Cavite City | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 33861208.37 |  |  | Terminated | 0.9 |  |  |  | 16DF0222 | [5 empty] | BAQPRINCE CONSTRUCTION | CONTRACT TERMINATED (insufficient area for size of building and building permit issues) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20
NEWCON 2016 | REGION IV-A | Cavite City | 301485 | Sangley Point Nhs To Sangley Es | Cavite City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24514577.982 |  |  | Completed | 1 |  |  |  | 16DF0228 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 301179 | Congressional Nhs | City Of Dasmariñas | 4 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0196 |  |  | November 4, 2016 |  | 42692 | Baqprince Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 301183 | Dasmarinas East Nhs (Annex C) | City Of Dasmariñas | 4 | 1 | 32 | 4STY32CL | BATCH 13 CL | 44532220.04 |  |  | Completed | 1 |  |  |  | 16DF0215 |  |  | December 20, 2016 |  | January 27, 2017 | KLDS Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107917 | Dasmariñas Ii Cs (Dasmariñas Bbes B) | City Of Dasmariñas | 4 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16DF0212 |  |  | December 20, 2016 |  | January 27, 2017 | KLDS Trading and Construction | Completed as per POW, Requested for additional fund | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107917 | Dasmariñas Ii Cs (Dasmariñas Bbes B) | City Of Dasmariñas | 4 |  | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0208 |  |  | December 20, 2016 |  | January 27, 2017 | KLDS Trading and Construction | Completed as per POW, Requested for additional fund | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 301186 | Dasmarinas Nhs | City Of Dasmariñas | 4 | 1 | 28 | 4STY28CL | BATCH 11 CL | 40067946.14 |  |  | Completed | 1 |  |  |  | 16DF0202 |  |  | November 4, 2016 |  | 42692 | D.V. Salud Construction / KLDS Trading & Construction (JV) | Completed as per POW, Requested for additional fund | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 301186 | Dasmarinas Nhs | City Of Dasmariñas | 4 |  | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0201 |  |  | November 4, 2016 |  | 42692 | D.V. Salud Construction / KLDS Trading & Construction (JV) | Completed as per POW, Requested for additional fund | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 301186 | Dasmarinas Nhs | City Of Dasmariñas | 4 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0195 |  |  | November 4, 2016 |  | 42692 | C.T. LEONCIO CONST. & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107921 | Dr. J. P. Rizal Es (Dasmariñas Bbes A-1) | City Of Dasmariñas | 4 | 1 | 24 | 4STY24CL | BATCH 7 CL | 35596257.14 |  |  | Completed | 1 |  |  |  | 16DF0115 |  |  | March 16 2016 |  | 42558 | C.T. Leoncio Construction & Trading , Omnicon builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107902 | Francisco E. Barzaga Ms | City Of Dasmariñas | 4 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0170 |  |  | 2016-06-22 |  | 42558 | KLDS Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107907 | Paliparan Es | City Of Dasmariñas | 4 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0175 |  |  | 2016-06-22 |  | 42558 | KLDS Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 325902 | Paliparan Ii National High School | City Of Dasmariñas | 4 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16DF0198 |  |  | November 4, 2016 |  | 42692 | R.A. Del Rosario | Completed as per POW, Requested for additional fund | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107908 | Paliparan Iii Es | City Of Dasmariñas | 4 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0110 |  |  | 2016-03-15 |  | 42515 | Baqprince Construction | Completed as per POW, Requested for additional fund | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107910 | Ramona S. Tirona Ms | City Of Dasmariñas | 4 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0183 |  |  | 2016-06-28 |  | 42564 | Baqprince Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107911 | Sabang Es | City Of Dasmariñas | 4 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0097 |  |  | 2016-03-15 |  | 42564 | Baqprince Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107924 | Salitran Elementary | City Of Dasmariñas | 4 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0210 |  |  | December 20, 2016 |  | January 27, 2017 | R.A. Del Rosario |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107922 | San Miguel Es (Dasmariñas Bbes A-3) | City Of Dasmariñas | 4 | 1 | 2 | 2STY2CL | BATCH 9 CL | 5014253.339 |  |  | Completed | 1 |  |  | P00073191LZ | 16DF0181 |  |  | 2016-06-28 |  | 42564 | Fe S. Reyes General Contractor |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107919 | San Nicolas Es (Dasmariñas Bbes D) | City Of Dasmariñas | 4 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0171 |  |  | 2016-06-22 |  | 42558 | KLDS Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107919 | San Nicolas Es (Dasmariñas Bbes D) | City Of Dasmariñas | 4 |  | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0184 |  |  | 2016-06-28 |  | 42564 | Fe S. Reyes General Contractor |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107918 | Sta. Cristina Es (Dasmariñas Bbes C) | City Of Dasmariñas | 4 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0205 |  |  | December 20, 2016 |  | January 27, 2017 | RAMON F. JAVALERA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107920 | Sta. Cruz Es (Dasmariñas Bbes E) | City Of Dasmariñas | 4 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0209 |  |  | December 20, 2016 |  | January 27, 2017 | KLDS Trading and Construction | Completed as per POW, Requested for additional fund | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Dasmarinas City | 107920 | Sta. Cruz Es (Dasmariñas Bbes E) | City Of Dasmariñas | 4 |  | 24 | 4STY24CL | BATCH 13 CL | 35596257.14 |  |  | Completed | 1 |  |  |  | 16DF0214 |  |  | December 20, 2016 |  | January 27, 2017 | KLDS Trading and Construction | Completed as per POW, Requested for additional fund | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Imus City | 107968 | Anabu I Es | Imus | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 19060000 |  |  | Completed | 1 |  |  | P00073194LZ | 16DF0131 | February 26,2016 | 2016-03-04 | March 16,2016 | May 16,2106 | May 25,2016 | Montadel Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Imus City | 107969 | Anabu Ii Elementary School | Imus | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16370000 |  |  | Completed | 1 |  |  | P00073195LZ | 16DF0128 | February 26,2016 | 2016-03-04 | March 16,2016 | May 16,2106 | May 25,2016 | N. B. Avila Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Imus City | 107971 | Bayan Luma Ii Elementary School | Imus | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16370000 |  |  | Completed | 1 |  |  | P00073196LZ | 16DF0129 | February 26,2016 | 2016-03-04 | March 16,2016 | May 16,2106 | May 25,2016 | J. S. Gen Contractor |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Imus City | 107972 | Buhay Na Tubig Elementary School | Imus | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24555000 |  |  | Completed | 1 |  |  | P00073197LZ | 16DF0133 | February 26,2016 | 2016-03-04 | March 16,2016 | May 16,2106 | May 25,2016 | Omnicon Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Imus City | 107982 | Bukandala Es | Imus | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34148000 |  |  | Completed | 1 |  |  | P00073198LZ | 16DF0139 | February 26,2016 | 2016-03-04 | March 16,2016 | May 16,2106 | May 25,2016 | Omnicon Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Imus City | 107983 | Carsadang Bago Es | Imus | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24555000 |  |  | Completed | 1 |  |  | P00073199LZ | 16DF0134 | February 26,2016 | 2016-03-04 | March 16,2016 | May 16,2106 | May 25,2016 | Baqprice Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Imus City | PSA328487 | Gen. Flaviano Yengko Shs (Shs In Pasong Buaya) | Imus City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16078602.8 |  |  | Completed | 1 |  |  | P00073203LZ | 16DF0126 | February 26,2016 | 2016-03-04 | March 16,2016 | May 16,2106 | May 25,2016 | Omnicon Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Imus City | PSA328485 | Gen. Pantaleon Garcia Shs (Shs In Pedro Reyes) | Imus City | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34023208.37 |  |  | Completed | 1 |  |  | P00073204LZ | 16DF0137 | February 26,2016 | 2016-03-04 | March 16,2016 | May 16,2106 | May 25,2016 | Baqprice Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Imus City | 107985 | Gov. D. M. Camerino Es | Imus | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00073200LZ | 16DF0125 | February 26,2016 | 2016-03-04 | March 16,2016 | May 16,2106 | May 25,2016 | Omnicon Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Imus City | PSA328488 | Gov. Juanito Reyes Remulla Shs (Shs In Toclong) | Imus City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16127354.99 |  |  | Completed | 1 |  |  | P00073205LZ | 16DF0127 | February 26,2016 | 2016-03-04 | March 16,2016 | May 16,2106 | May 25,2016 | Montadel Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Imus City | 301196 | Imus Nhs | Imus | 3 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29350000 |  |  | Completed | 1 |  |  | P00073201LZ | 16DF0136 | February 26,2016 | 2016-03-04 | March 16,2016 | May 16,2106 | May 25,2016 | R. V. Rieta Trading & Gen. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Imus City | 107987 | Malagasang Ii Es | Imus | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34140000 |  |  | Completed | 1 |  |  | P00073202LZ | 16DF0138 | February 26,2016 | 2016-03-04 | March 16,2016 | May 16,2106 | May 25,2016 | Almakr Bldrs. & Metal Works/KLDS Trading & Construction (JV) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Laguna | PSA328512 | Stand Alone Shs No. 20 Santa Cruz | Santa Cruz | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Laguna | PSA328492 | Stand Alone Shs No. 4 Sta. Cruz | Santa Cruz | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Laguna | PSA328495 | Stand Alone Shs No. 7 San Antonio Lb | Los Banos | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7139736.1681 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Laguna | 307903 | Cristobal S. Conducto Mnhs | Rizal | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24485957.982 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Laguna | 307903 | Cristobal S. Conducto Mnhs | Rizal | 3 |  | 6 | 3STY6CL | BATCH 9 CL | 11506366.536 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Laguna | 307903 | Cristobal S. Conducto Mnhs | Rizal | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2674056.25 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Laguna | 307927 | Dayap Nhs (Calauan Annex) | Calauan | 3 | 1 | 24 | 4STY12CL | BATCH 9 CL | 48971915.964 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301258 | Plaridel Nhs | Nagcarlan | 3 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29524441.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301258 | Plaridel Nhs | Nagcarlan | 3 |  | 24 | 4STY12CL | BATCH 9 CL | 48838535.964 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Laguna | PSA328493 | Stand Alone Shs No. 5 Nagcarlan | Nagcarlan | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301226 | Balian Nhs | Pangil | 4 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301226 | Balian Nhs | Pangil | 4 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Laguna | 307918 | Balian Nhs (Galalan Annex) | Pangil | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6528871.7478 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Laguna | 307940 | Calangay Elementary School To Sta. Maria Nhs-Calangay Annex | Santa Maria | 4 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8288590.65 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Laguna | 307926 | Cavinti Nhs (Calminue Ext.) | Cavinti | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6528871.7478 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Laguna | 307926 | Cavinti Nhs (Calminue Ext.) | Cavinti | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2490750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Laguna | 108459 | Cueva Es | Santa Maria | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2061872.3726 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301240 | Famy National High School | Famy | 4 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301270 | Gaudencio Octavio National High School | Santa Maria | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301243 | Kabulusan National High School | Pakil | 4 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15495611.118 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301243 | Kabulusan National High School | Pakil | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2490750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Laguna | 108407 | Labuin Es | Pila | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6373289.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Laguna | 164506 | Laurel Es | Santa Maria | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2061872.3726 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301279 | Lumban National High School | Lumban | 4 | 1 | 12 | 3STY12CL | BATCH 9 CL | 19680456.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Laguna | 307937 | Magdalena Nhs (Buenavista Annex) | Magdalena | 4 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Laguna | 108400 | Maulawin Es | Pakil | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2050929.3424 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Laguna | 164507 | New Little Baguio Es | Santa Maria | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2061872.3726 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301253 | Pagsanjan National High School | Pagsanjan | 4 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301253 | Pagsanjan National High School | Pagsanjan | 4 |  | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Laguna | 108401 | Pakil Es | Pakil | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6373289.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Laguna | 108376 | Papatahan Es | Paete | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6373289.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Laguna | 108412 | Pinagbayanan Es | Pila | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Laguna | 307935 | San Buenaventura Nhs Annex | Luisiana | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6528871.7478 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Laguna | 307920 | San Juan Nhs (San Antonio Annex) | Kalayaan | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6528871.7478 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Laguna | 108403 | Saray Es | Pakil | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2050929.3424 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301273 | Siniloan National High School | Siniloan | 4 | 1 | 15 | 3STY15CL | BATCH 11 CL | 23037143.68 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301273 | Siniloan National High School | Siniloan | 4 |  | 6 | 3STY6CL | BATCH 11 CL | 11443844.661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Laguna | 164519 | Sitio Pulot/Bay Es | Kalayaan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2050929.3424 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301268 | Sta. Catalina Nhs | Majayjay | 4 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301268 | Sta. Catalina Nhs | Majayjay | 4 |  | 4 | 2STY4CL | BATCH 11 CL | 6373289.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Laguna | 301269 | Sta. Maria Nhs | Santa Maria | 4 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Laguna | PSA328489 | Stand Alone Shs No. 1 Kalayaan | Kalayaan | 4 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Laguna | PSA328489 | Stand Alone Shs No. 1 Kalayaan | Kalayaan | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2490750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Laguna | PSA328491 | Stand Alone Shs No. 3 Pagsanjan | Pagsanjan | 4 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11141456.81 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Laguna | PSA328491 | Stand Alone Shs No. 3 Pagsanjan | Pagsanjan | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Laguna | 108280 | Sumucab Es | Cavinti | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2050929.3424 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Lipa City | 301489 | Bulacnin Nhs | Lipa City | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6419338 |  |  | Completed | 1 |  |  |  | 16DD0201 |  |  |  | 2016-07-05 | 42564 | EDISON DEV'T CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Lipa City | 301491 | Inosloban-Marawoy Nhs | Lipa City | 4 | 1 | 40 | 4STY20CL | BATCH 13 CL | 68396358.594 |  |  | Completed | 1 |  |  |  | 16DD0233 |  |  |  | 2017-04-02 | 42835 | PRECIOUS CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IV-A | Lipa City | 301495 | Lumbang Nhs | Lipa City | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319338 |  |  | Completed | 1 |  |  |  | 16DD0197 |  |  |  | 2016-06-22 | 42551 | A.SANDOVAL CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Lucena City | 308502 | Cotta National High School | Lucena City (Capital) | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23944914.795 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION IV-A | Lucena City | 308503 | Gulang-Gulang Nhs | Lucena City (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34783029.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Lucena City | 109740 | Isabang Es | Lucena City (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20398270.669 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Lucena City | 308501 | Lucena Dalahican Nhs | Lucena City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29845066.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Lucena City | 109707 | Lucena East I Es | Lucena City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11628224.661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Lucena City | 109714 | Lucena East Vii Es | Lucena City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11628344.661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Lucena City | 109744 | Lucena West Iii Es | Lucena City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7010521.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Lucena City | 109736 | Talao-Talao Es | Lucena City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7059196.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301332 | Infanta Nhs | Infanta | 1 | 1 | 15 | 3STY15CL | BATCH 11 CL | 21383013.45 |  |  | Completed | 1 |  |  |  | 16DK0062 | 2016-08-11 | 2016-08-17 | 2016-09-02 | 2016-10-13 | 42667 | LUCBAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301332 | Infanta Nhs | Infanta | 1 |  | 9 | 3STY9CL | BATCH 11 CL | 14941327.92 |  |  | Completed | 1 |  |  |  | 16DK0063 | 2016-08-11 | 2016-08-17 | 2016-09-02 | 2016-10-13 | 42667 | SARCA STATE & DEVT CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301297 | Bukal Sur Nhs | Candelaria | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301348 | Lusacan Nhs | Tiaong | 2 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301349 | Lutucan National High Scool | Sariaya | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301380 | Recto Mnhs | Tiaong | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301403 | Sta. Catalina Nhs | Candelaria | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301295 | Bondoc Peninsula Agri. Hs | Mulanay | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301304 | Calauag Nhs | Calauag | 4 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 |  |  | P00070472LZ | 16-DL-0058 | Apr. 29, 2016 |  | May 23, 2016 | May 27, 2016 | 42528 | JUNCAN ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301304 | Calauag Nhs | Calauag | 4 |  | 6 | 3STY6CL | BATCH 3 CL | 10417131.51 |  |  | Completed | 1 |  |  | P00070473LZ | 16-DL-0050 | 2016-03-17 |  | April 12, 2016 | April 21, 2016 | 42513 | JUNCAN ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301323 | Guinayangan Nhs | Guinayangan | 4 | 1 | 12 | 3STY12CL | BATCH 11 CL | 18222268.79 |  |  | Completed | 1 |  |  | P00074788LZ-CW1 | 16-DL-0093 | Aug. 25, 2016 | Sept. 8, 2016 | Sept. 20, 2016 | Sept. 29, 2016 | 42650 | JUNCAN ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301328 | Guites Nhs | Lopez | 4 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8514965.05 |  |  | Completed | 1 |  |  | P00075549LZ-CW1 | 17-DL-0102 | Jan. 26, 2017 | 2017-02-02 | Feb. 15, 2017 | Feb. 17, 2017 | 42788 | C.T. Leoncio Construction & Trading/Katha Builders & Supplies (J.V.) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301325 | Gumaca National High School | Gumaca | 4 | 1 | 27 | 3STY9CL | BATCH 13 CL | 49855382.136 |  |  | Completed | 1 |  |  | P00075550LZ-CW1 | 17-DL-0100 | Jan. 26, 2017 | 2017-02-02 | Feb. 15, 2017 | Feb. 17, 2017 | 42788 | Katha Builders & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 27 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301325 | Gumaca National High School | Gumaca | 4 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 |  |  | P00074789LZ-CW1 | 16-DL-0094 | Aug. 25, 2016 | Sept. 8, 2016 | Sept. 20, 2016 | Sept. 29, 2016 | 42650 | ZELAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301387 | Ilayang Ilog-A Nhs (Formerly San Francisco B Nhs Ilayang Ilog A Ext.) | Lopez | 4 | 1 | 2 | 1STY2CL | BATCH 11 CL | 2132466.644 |  |  | Completed | 1 |  |  | P00074792LZ-CW1 | 16-DL-0095 | Aug. 25, 2016 | Sept. 8, 2016 | Sept. 20, 2016 | Sept. 29, 2016 | 42650 | RA MENDIOLA CONSTRUCTION AND DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301338 | Kinatakutan Nhs | Tagkawayan | 4 | 1 | 5 | 1STY5CL | BATCH 9 CL | 4648392.2452 |  |  | Completed | 1 |  |  | P00075551LZ-CW1 | 17-DL-0103 | Jan. 26, 2017 | 2017-02-02 | Feb. 15, 2017 | Feb. 17, 2017 | 42788 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301345 | Lopez National Comprehensive High School | Lopez | 4 | 1 | 20 | 2STY10CL | BATCH 13 CL | 25542620.18 |  |  | Completed | 1 |  |  | P00075552LZ-CW1 | 17-DL-0101 | Jan. 26, 2017 | 2017-02-02 | Feb. 15, 2017 | Feb. 17, 2017 | 42788 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301345 | Lopez National Comprehensive High School | Lopez | 4 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 |  |  | P00074793LZ-CW1 | 16-DL-0096 | Aug. 25, 2016 | Sept. 8, 2016 | Sept. 20, 2016 | Sept. 29, 2016 | 42650 | RA MENDIOLA CONSTRUCTION AND DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Quezon | 301352 | Pisipis Nhs (Formerly Magallanes Nhs Pisipis Extension) | Lopez | 4 | 1 | 2 | 1STY2CL | BATCH 11 CL | 2132466.644 |  |  | Completed | 1 |  |  | P00073251LZ | 16-DL-0055 | April 12, 2016 |  | May 3, 2016 | May 12, 2016 | 42507 | ZELAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301417 | Angono Nhs | Angono | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 23912531.11 |  |  | Completed | 1 |  |  | P00074795LZ | 16DN0087 | 2016-07-14 | 2016-07-20 | 2016-08-02 | 2016-08-16 | 42611 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301417 | Angono Nhs | Angono | 1 |  | 16 | 4STY8CL | BATCH 11 CL | 29795037.68 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION IV-A | Rizal | PSA328524 | Stand Alone 8 | Taytay | 1 | 1 | 40 | 4STY20CL | BATCH 11 CL | 62505780.54 |  |  | Completed | 1 |  |  | P0074809LZ | 16DN0108 | 2016-12-09 | 2016-12-16 | 2016-12-29 | 2016-12-29 | 43081 | D.R. ROBLES CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IV-A | Rizal | PSA328519 | Stand Alone Shs 3 | Cainta | 1 | 1 | 60 | 4STY20CL | BATCH 11 CL | 93758671 |  |  | Completed | 1 |  |  | P0074803LZ | 16DN0102 | 2016-11-25 | 2016-12-01 | 2016-12-15 | 2016-12-27 | 42821 | ATLANTIC ERECTORS INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 60 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301469 | Vicente Madrigal Nhs | Binangonan | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 32650534.78 |  |  | Completed | 1 |  |  | P0074802LZ | 16DN0083 | 2016-07-08 | 2016-07-15 | 2016-07-28 | 2016-08-10 | 42606 | GENETIAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301428 | Bagumbong Nhs | Jala-Jala | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 23912531.11 |  |  | Completed | 1 |  |  | P00075559LZ-CW1 | 160050 | 2016-12-03 | December 9, 2016 | December 23, 2016 | December 28, 2016 | January 11, 2017 | Atlantic Erectors Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301434 | Catalino D. Salazar Nhs | Cardona | 2 | 1 | 6 | 3STY6CL | BATCH 13 CL | 12573229.1271 |  |  | Completed | 1 |  |  | P00075557LZ-CW1 | 160059 | 2017-01-20 | January 27, 2017 | February 9, 2017 | March 16, 2017 | March 29, 2017 | Flag Const. Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301434 | Catalino D. Salazar Nhs | Cardona | 2 |  | 1 | 1STY1CL | BATCH 13 CL | 1103134.12 |  |  | Completed | 1 |  |  | P00075558LZ-CW1 | 160059 | 2017-01-20 | January 27, 2017 | February 9, 2017 | March 16, 2017 | March 29, 2017 | Flag Const. Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Rizal | 308120 | Jalajala Nhs | Jala-Jala | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00074794LZ-CW1 | 16D00039 | October 3, 2016 | October 7, 2016 | October 20, 2016 | October 27, 2016 | November 7, 2016 | ALPHA & OMEGA GENERAL CONTRACTOR & DEV'T. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301447 | Malaya Nhs | Pililla | 2 | 1 | 15 | 3STY15CL | BATCH 11 CL | 22444664.12 |  |  | Completed | 1 |  |  | P00074797LZ-CW1 | 16D00034 | September 9, 2016 | September 16, 2016 | September 30, 2016 | October 6, 2016 | October 14, 2016 | HEXAMINDZ CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301452 | Morong National High School | Morong | 2 | 1 | 20 | 4STY20CL | BATCH 11 CL | 32850534.78 |  |  | Completed | 1 |  |  | P00074798LZ-CW1 | 16D00035 | September 9, 2016 | September 16, 2016 | September 30, 2016 | October 6, 2016 | October 14, 2016 | ALPHA & OMEGA GENERAL CONTRACTOR & DEV'T. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301452 | Morong National High School | Morong | 2 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00074798LZ-CW1 | 16D00035 | September 2, 2016 | September 9, 2016 | September 22, 2016 | September 28, 2016 | October 5, 2016 | GENETIAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Rizal | 308123 | Pantay Nhs (Teresa Nhs - Pantay Annex) | Teresa | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 28826666.97 |  |  | Completed | 1 |  |  | P00075561LZ-CW1 | 160051 | 2016-12-03 | December 9, 2016 | December 23, 2016 | December 29, 2016 | January 19, 2017 | Alpha & Omega General Contractor & Devl't Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301453 | Pililla Nhs | Pililla | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 |  |  | P00074804LZ-CW1 | 160040 | 2016-10-03 | October 7, 2016 | October 20, 2016 | November 21, 2016 | December 2, 2016 | Honeyville Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301454 | Quisao Nhs | Pililla | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 16077320.35 |  |  | Completed | 1 |  |  | P00074810LZ-CW1 | 160025 | 2016-08-22 | September 1, 2016 | September 13, 2016 | September 20, 2016 | September 23, 2016 | Alpha & Omega General Contractor & Devl't Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301456 | Sampaloc Nhs | Tanay | 2 | 1 | 12 | 3STY12CL | BATCH 11 CL | 19668050.29 |  |  | Completed | 1 |  |  | P00074800LZ-CW1 | 16D00033 | September 9, 2016 | September 16, 2016 | September 30, 2016 | October 6, 2016 | October 14, 2016 | HEXAMINDZ CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Rizal | 301462 | Silangan National High School | San Mateo | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16224795.54 |  |  | Completed | 1 |  |  | P00075560LZ-CW1 | 160052 | 2016-12-03 | December 9, 2016 | December 23, 2016 | December 29, 2016 | January 19, 2017 | IM Const. Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Rizal | PSA328526 | Stand Alone 10 ( Rizal Arts Academy) | Tanay 2 | 2 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00074808LZ-CW1 | 160044 | 2016-11-19 | November 25, 2016 | December 9, 2016 | December 28, 2016 | January 19, 2017 | MPJR Builders Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Rizal | PSA328523 | Stand Alone 7 | Baras | 2 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074801LZ-CW1 | 16D00041 | October 3, 2016 | October 7, 2016 | October 20, 2016 | November 21, 2016 | November 29, 2016 | HONEYVILLE CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Rizal | PSA328525 | Stand Alone 9 | Rodriguez Ii Eastwood | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 |  |  | P00074805LZ-CW1 | 160031 | 2016-09-02 | September 9, 2016 | September 22, 2016 | September 28, 2016 | October 5, 2016 | Chrisman Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Rizal | PSA328525 | Stand Alone 9 | Rodriguez Ii Eastwood | 2 |  | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 |  |  | P00074806LZ-CW1 | 160030 | 2016-09-02 | September 9, 2016 | September 22, 2016 | September 28, 2016 | October 5, 2016 | Precious Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Rizal | PSA328518 | Stand Alone Shs 2 | San Mateo | 2 | 1 | 40 | 4STY20CL | BATCH 11 CL | 67158242.98 |  |  | Completed | 1 |  |  | P00074807LZ-CW1 | 160060 | 2017-09-18 | March 24, 2017 | April 7, 2017 | April 21, 2017 | May 4, 2017 | Atlantic Erectors Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IV-A | Rizal | PSA328520 | Stand Alone Shs 4 | Tanay | 2 | 1 | 32 | 4STY16CL | BATCH 11 CL | 53404938.84 |  |  | Completed | 1 |  |  | P00074811LZ-CW1 | 160046 | 2016-11-09 | November 25, 2016 | December 9, 2016 | December 28, 2016 | January 19, 2017 | Sarca Estates Development Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION IV-A | Rizal | PSA328521 | Stand Alone Shs 5 | Rodriguez I Litex | 2 | 1 | 40 | 4STY20CL | BATCH 11 CL | 67158242.98 |  |  | Completed | 1 |  |  | P00074812LZ-CW1 | 160029 | 2016-09-02 | September 9, 2016 | September 22, 2016 | September 28, 2016 | October 5, 2016 | Hexamindz Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IV-A | Rizal | PSA328521 | Stand Alone Shs 5 | Rodriguez I Litex | 2 |  | 8 | 4STY8CL | BATCH 11 CL | 16077320.35 |  |  | Completed | 1 |  |  | P00074813LZ-CW1 | 160045 | 2016-11-19 | November 25, 2016 | December 9, 2016 | December 16, 2016 | December 23, 2016 | Hexamindz Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | San Pablo City | 109749 | Ambray Elementary School | San Pablo City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11500313.8843 |  |  | Completed | 1 |  |  | P00073252LZ_CW1 | 16DP0034 | 2016-06-10 | 2016-06-16 | 2016-07-01 | August 3 - 5, 2016 | 42599 | DSO ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | San Pablo City | 301506 | Del Remedio National High School | San Pablo City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11500313.8843 |  |  | Completed | 1 |  |  | P00073253LZ_CW1 | 16DP0021 | 2016-05-02 | 2016-05-12 | 2016-05-24 | May 30 - June 1, 2016 | 42551 | STO CRISTO CONST & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | San Pablo City | 308606 | Prudencia D. Fule Memorial National High School | San Pablo City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11500313.8843 |  |  | Completed | 1 |  |  | P00073254LZ_CW1 | 16DP0019 | 2016-05-02 | 2016-05-12 | 2016-05-24 | May 30 - June 1, 2016 | 42551 | POWER K CONST. SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | San Pablo City | 308602 | San Jose National High School | San Pablo City | 3 | 1 | 24 | 4STY12CL | BATCH 9 CL | 48705155.964 |  |  | Completed | 1 |  |  | P00073255LZ_CW1 | 16DP0029 | 2016-05-13 | 2016-05-18 | 2016-06-02 | 2016-07-26 | 42557 | STO CRISTO CONST & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | San Pablo City | 301504 | San Pablo City National High School | San Pablo City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11500313.8843 |  |  | Completed | 1 |  |  | P00073256LZ_CW1 | 16DP0022 | 2016-05-02 | 2016-05-12 | 2016-05-24 | May 30 - June 1, 2016 | 42551 | POWER K CONST. SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | San Pablo City | 308605 | San Pablo City Science High School | San Pablo City | 3 | 1 | 24 | 4STY12CL | BATCH 9 CL | 48705155.964 |  |  | Completed | 1 |  |  | P00073257LZ_CW1 | 16DP0027 | 2016-05-13 | 2016-05-18 | 2016-06-02 | 2016-07-26 | 42557 | STO CRISTO CONST & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | San Pablo City | PSA328527 | San Pablo City Senior High School (Stand Alone) | San Pablo City | 3 | 1 | 40 | 4STY20CL | BATCH 9 CL | 68396358.594 |  |  | Completed | 1 |  |  | P00073258LZ_CW1 | 16DP0023 | 2016-05-02 | 2016-05-12 | 2016-05-24 | May 30 - June 1, 2016 | 42551 | JAIME B. CHING ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IV-A | San Pablo City | PSA328527 | San Pablo City Senior High School (Stand Alone) | San Pablo City | 3 |  | 48 | 4STY16CL | BATCH 9 CL | 88073149.086 |  |  | Completed | 1 |  |  | P00073259LZ_CW1 | 16DP0024 | 2016-05-13 | 2016-05-18 | 2016-06-02 | 2016-07-26 | 42599 | NEW BIG FOUR J CONST. INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION IV-A | San Pablo City | PSA328527 | San Pablo City Senior High School (Stand Alone) | San Pablo City | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5317400 |  |  | Completed | 1 |  |  | P00074444LZ_CW1 | 16DP0017 | 2016-05-02 | 2016-05-12 | 2016-05-24 | May 30 - June 1, 2016 | 42551 | R'CEL GEN. CONT. 7 GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | San Pablo City | 308601 | San Vicente National High School | San Pablo City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11500313.8843 |  |  | Completed | 1 |  |  | P00073260LZ_CW1 | 16DP0020 | 2016-05-02 | 2016-05-12 | 2016-05-24 | May 30 - June 1, 2016 | 42551 | POWER K CONST. SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | San Pablo City | 301509 | Santisimo Rosario National High School | San Pablo City | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION IV-A | San Pablo City | 301509 | Santisimo Rosario National High School | San Pablo City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION IV-A | Sta. Rosa City | 301224 | Aplaya Nhs | City Of Santa Rosa | 1 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15421327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IV-A | Sta. Rosa City | 108471 | Caingin Elementary School | City Of Santa Rosa | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1 |  |  |  | 16DI0089 | 2016-06-29 | 2016-07-04 | 2016-07-19 | 2016-07-26 | 42583 | ST. GERRARD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Sta. Rosa City | 301239 | Don Jose Nhs | City Of Santa Rosa | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Sta. Rosa City | 108479 | Pulong Sta. Cruz Elementary School | City Of Santa Rosa | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15047518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Sta. Rosa City | PSA328483 | Shs In Santa Rosa1 | Santa Rosa City | 1 | 1 | 16 | 4STY8CL | BATCH 7 CL | 30095037.68 |  |  | Completed | 1 |  |  |  | 16DI0075 | 2016-04-21 | 2016-04-28 | 2016-05-06 | 2016-05-14 | 42512 | ST. GERRARD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Sta. Rosa City | PSA328483 | Shs In Santa Rosa1 | Santa Rosa City | 1 |  | 16 | 4STY16CL | BATCH 7 CL | 26852469 |  |  | Completed | 1 |  |  |  | 16DI0074 | 2016-04-21 | 2016-04-28 | 2016-05-06 | 2016-05-14 | 42506 | ST. GERRARD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Sta. Rosa City | PSA328484 | Shs In Santa Rosa2 | Santa Rosa City | 1 | 1 | 24 | 4STY12CL | BATCH 11 CL | 44604688 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IV-A | Sta. Rosa City | PSA328484 | Shs In Santa Rosa2 | Santa Rosa City | 1 |  | 16 | 4STY16CL | BATCH 11 CL | 26852469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Sta. Rosa City | PSA328484 | Shs In Santa Rosa2 | Santa Rosa City | 1 |  | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Sta. Rosa City | PSA328484 | Shs In Santa Rosa2 | Santa Rosa City | 1 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Sta. Rosa City | 108485 | Tagapo Elementary School | City Of Santa Rosa | 1 | 1 | 8 | 4STY8CL | BATCH 7 CL | 15047518.84 |  |  | Completed | 1 |  |  |  | 16DI0089 | 2016-02-28 | 2016-03-05 | 2016-03-18 | 2016-03-23 | 42512 | ST. GERRARD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IV-A | Tanauan City | 321602 | Balele National High School | City Of Tanauan | 3 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IV-A | Tanauan City | 321604 | Dr. Alcantara National High School | City Of Tanauan | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Tanauan City | 107760 | Janopol Es | City Of Tanauan | 3 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Tanauan City | 321603 | Janopol Oriental National High School | City Of Tanauan | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IV-A | Tanauan City | 301119 | Malaking Pulo National High School | City Of Tanauan | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1959000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Tanauan City | 107776 | Santol Elementary School | City Of Tanauan | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1959000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Tanauan City | 321601 | Tanauan City Nhs | City Of Tanauan | 3 | 1 | 15 | 3STY15CL | BATCH 13 CL | 23506314.795 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION IV-A | Tanauan City | 321601 | Tanauan City Nhs | City Of Tanauan | 3 |  | 12 | 3STY12CL | BATCH 13 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IV-A | Tanauan City | 321605 | Ulango Integrated School | City Of Tanauan | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1959000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IV-A | Tayabas City | 301347 | Luis Palad Nhs | City Of Tayabas | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26852469 |  |  | Completed | 1 |  |  |  | 16DK0019 | 2016-02-24 | 2016-03-04 | 2016-03-17 | 2016-03-23 | 42464 | DQT Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IV-A | Tayabas City | 301347 | Luis Palad Nhs | City Of Tayabas | 1 |  | 6 | 3STY6CL | BATCH 7 CL | 10763758.08 |  |  | Completed | 1 |  |  |  | 16DK0020 | 2016-02-24 | 2016-03-04 | 2016-03-17 | 2016-03-23 | 42464 | Lucban Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IV-A | Tayabas City | 109258 | Stand Aloneshs To Potol Es | Tayabas | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2606823.98 |  |  | Completed | 1 |  |  |  | 16DK0064 | 2016-08-11 | 2016-08-17 | 2016-09-02 | 2016-09-12 | 42632 | WJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IV-A | Tayabas City | 109262 | Tayabas West Cs Iv | City Of Tayabas | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 |  |  |  | 16DK0043 | 2016-04-11 | 2016-04-18 | 2016-04-29 | 2016-05-06 | 42502 | Tan Tay Lim Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | ANTIPOLO CITY | 321505 | Antipolo NHS - Dela Paz Extension | CITY OF ANTIPOLO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0615S00004 | 15DN0101 | 2015-09-10 | 2015-09-10 | 2015-09-23 | 2015-10-06 | 2015-10-16 | HI-TRI DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | ANTIPOLO CITY | 301426 | San Isidro NHS | CITY OF ANTIPOLO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0615S00007 | 15DN0102 | 2015-09-10 | 2015-09-10 | 2015-09-23 | 2015-10-06 | 2015-10-16 | HI-TRI DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | ANTIPOLO CITY | 321502 | Antipolo NHS - Canumay Extension | CITY OF ANTIPOLO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | Completed | 1 |  |  | 4A0615S00011 | 16DNO002 | 2016-01-15 | 2016-01-15 | 2016-02-04 | 2016-02-12 | 2016-02-23 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | ANTIPOLO CITY | 301421 | Antipolo NHS - Kaysakat Extension | CITY OF ANTIPOLO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0615S00008 | 15DN0096 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-12 | 2H2L CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | ANTIPOLO CITY | 301431 | Calawis NHS | CITY OF ANTIPOLO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Completed | 1 |  |  | 4A0615S00012 | 15DN0104 | 2015-09-10 | 2015-09-10 | 2015-09-23 | 2015-10-06 | 2015-10-16 | KRBS CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | ANTIPOLO CITY | 321503 | Calawis NHS - Apia Extension | CITY OF ANTIPOLO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | Completed | 1 |  |  | 4A0615S00044 | 16DNO006 | 2016-01-28 | 2016-02-03 | 2016-02-16 | 2016-02-24 | 2016-03-03 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | ANTIPOLO CITY | 230006 | Paglitaw PS | CITY OF ANTIPOLO | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0615S00024 | 15DN0161 | 2015-11-26 | 2015-12-02 | 2015-12-15 | 2015-12-23 | 2016-01-09 | KRBS CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | ANTIPOLO CITY | 301427 | San Juan NHS | CITY OF ANTIPOLO | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0615S00009 | 15DN0118 | 2015-10-22 | 2015-10-23 | 2015-11-05 | 2015-11-18 | 2015-11-25 | M. DEL ROSARIO CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | ANTIPOLO CITY | 109341 | Sapinit ES | CITY OF ANTIPOLO | 2 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 1663480.88 |  |  | Reverted | 0.001 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | ANTIPOLO CITY | 109361 | Sumilang ES | ANTIPOLO CITY | 2 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 1833528.635 |  |  | Reverted | 0.001 |  |  | 4A0615S00025 | 4A06-15-S-00025 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | ANTIPOLO CITY | 109363 | Upper Kilingan ES | CITY OF ANTIPOLO | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0615S00023 | 15DN0125 | 2015-11-05 | 2015-11-05 | 2015-11-19 | 2015-12-01 | 2015-12-08 | KRBS CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Bacoor City |  | Proposed Stand-Alone SHS 1- Dulong Bayan | BACOOR | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Bacoor City |  | Proposed Stand-Alone SHS 4- Sineguelasan | BACOOR | 2 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | Bacoor City | 107867 | Proposed Stand-Alone SHS 5- Bacoor ES | Bacoor City | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 28002469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand Alone SHS- Tuy | TUY | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Batangas | 107405 | Doña Matilde MES | LEMERY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0215S00064 | 15DB0098 | 2015-09-09 | 2015-09-15 | 2015-09-15 | 2015-09-28 | 2015-10-05 | RICH ADS CONSTRUCTION CORP. (FORMERLY RICH ADS CON |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Batangas | 307710 | Jose Lopez Manzano Tuy National High School | TUY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | Completed | 1 |  |  | 4A0215S00065 | 15DB0100 | 2015-09-09 | 2015-09-14 | 2015-09-15 | 2015-09-28 | 2015-10-20 | VRV CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | Batangas | 107512 | Nasugbu West CS | NASUGBU | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0215S00061 | 15DB0102 | 2015-09-09 | 2015-09-18 | 2015-09-21 | 2015-10-20 | 2015-10-30 | SANDSTORM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | Batangas | 107516 | Papaya ES | NASUGBU | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0215S00058 | 15DB0099 | 2015-09-09 | 2015-09-15 | 2015-09-15 | 2015-09-28 | 2015-10-05 | M.E. BANING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand Alone SHS- Calaca | CALACA | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand Alone SHS- Lemery | LEMERY | 1 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 8 | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 13 (LIAN SHS) | LIAN | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 3 (NASUGBU SHS 1) | NASUGBU | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 4 (NASUGBU SHS 2) | NASUGBU | 1 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 8 | 35596257.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 5 (NASUGBU SHS 3) | NASUGBU | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Prposed Stand-Alone SHS 2 (TAAL SHS) | TAAL | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Batangas | 107230 | Troadio A. Frontera MES | BALAYAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | Completed | 1 |  |  | 4A0215S00057 | 15DB0097 | 2015-09-09 | 2015-09-15 | 2015-09-15 | 2015-09-28 | 2015-10-05 | 830 BUILDERS & DEVELOPERS CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Batangas | 307719 | Tuy NHS | TUY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | Completed | 1 |  |  | 4A0215S00069 | 15DB0101 | 2015-09-09 | 2015-09-14 | 2015-09-15 | 2015-09-28 | 2015-10-20 | VRV CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301115 | Anselmo Sandoval MNHS (Mabini NHS) | MABINI | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0215S00037 | 15DE0076 | 2015-08-17 | 2015-08-18 | 2015-09-03 | 2015-09-08 | 2015-09-14 | E.M.L. CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301077 | Batangas Province High School for Culture and Arts | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6399338 |  |  | Completed | 1 |  |  | 4A0215S00050 | 15DE0088 | 2015-10-14 | 2015-10-15 | 2015-10-27 | 2015-10-30 |  | SANDSTORM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301079 | Bauan Mun. Agric'l & Voc. HS | BAUAN | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0215S00038 | 15DE0077 | 2015-08-17 | 2015-08-18 | 2015-09-03 | 2015-09-08 | 2015-09-14 | E.M.L. CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301080 | Bauan Technical HS | BAUAN | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2015 | REGION IV-A | Batangas | 107434 | Jaybanga ES | LOBO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0215S00053 | 15DE0131 | 2015-11-30 | 2015-12-01 | 2015-12-15 | 2015-12-18 | 2015-12-28 | WESTHOME ENTERPRISES & BUILDERS SUPPLIES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Batangas | 107438 | Malabrigo ES | LOBO | 2 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | Completed | 1 |  |  | 4A0215S00062 | 15DE0105 | 2015-11-04 | 2015-11-05 | 2015-11-19 | 2015-11-25 | 2015-12-04 | STO. CRISTO CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 18 (SAN LUIS SHS) | SAN LUIS | 2 | 1 | 12 | 3STY6CL | 2015 SHS BATCH 5 | 21084263 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 19 (SAN PASCUAL SHS 1) | SAN PASCUAL | 2 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 20 (SAN PASCUAL SHS 2) | SAN PASCUAL | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand Alone SHS- Agoncillo | AGONCILLO | 3 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 10 (MATAASNAKAHOY SHS) | MATAASNAKAHOY | 3 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 8 | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 22 (MALVAR SHS) | MALVAR | 3 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 23 (TALISAY SHS) | TALISAY | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 7 (ALITAGTAG SHS) | ALITAGTAG | 3 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 8 (BALETE SHS) | BALETE | 3 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 9 (CUENCA SHS) | CUENCA | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 8 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | Batangas | 307713 | San Nicolas NHS- Maabud Annex | San Nicolas | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26752469.42 |  |  | Completed | 1 |  |  | 4A0215S00040 | 15DC0111 | 2015-10-14 | 2015-10-26 | 2015-10-27 |  |  | N.B. AVILA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301147 | Santa Clara NHS | SANTO TOMAS | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1988606 |  |  | Completed | 1 |  |  | 4A0215S00070 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301149 | Santa Teresita NHS | SANTA TERESITA | 3 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | Completed | 1 |  |  | 4A0215S00041 | 15DC0090 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-09-03 | 2015-09-09 | I.A . BOSQUE CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Batangas | 107383 | Sta. Maria ES | LAUREL | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0215S00063 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301069 | Alupay NHS | Rosario | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10817131.51 |  |  | Completed | 1 |  |  | 4A0215S00042 | 15DD0182 | 2015-08-26 | 2015-09-01 | 2015-09-14 | 2015-09-23 | 2015-10-07 | VRV CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301090 | Buhaynasapa NHS | SAN JUAN | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0215S00033 | 15DD0181 | 2015-08-26 | 2015-09-01 | 2015-09-14 | 2015-09-23 | 2015-10-07 | N.B. AVILA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Batangas | 307714 | Dr. Bonifacio Masilungan MNHS | San Jose | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | Completed | 1 |  |  | 4A0215S00023 | 15DD0176 | 2015-08-03 | 2015-08-06 | 2015-08-10 | 2015-08-18 | 2015-09-09 | VRV CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301105 | Itlugan NHS | Rosario | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8914965.051 |  |  | Completed | 1 |  |  | 4A0215S00029 | 15DD0177 | 2015-07-27 | 2015-08-05 | 2015-08-10 | 2015-08-18 | 2015-09-09 | VRV CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301108 | Laiya NHS | SAN JUAN | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Batangas | 107621 | Paaralang Elementarya ng Nagsaulay | SAN JUAN | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0215S00060 | 15DD0209 | 2015-11-20 | 2015-11-26 | 2015-12-09 | 2015-12-18 |  | MANUEL A. DELA TORRE, JR. BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301129 | Padre Garcia NHS | PADRE GARCIA | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301130 | Palahanan NHS | SAN JUAN | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 |  |  | 4A0215S00026 | 15DD0185 | 2015-09-04 | 2015-09-10 | 2015-09-22 | 2015-09-29 | 2015-10-14 | BERTO LUCCI BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | Batangas | 107625 | Pinagbayanan ES | SAN JUAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0215S00059 | elem & jhs batch 6 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand Alone SHS- Taysan | TAYSAN | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 8 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 25 (IBAAN SHS) | IBAAN | 4 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | REGION IV-A | Batangas |  | Proposed Stand-Alone SHS 27 (CALANTAS SHS) | ROSARIO | 4 | 1 | 6 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 5955185 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301139 | Rosario NHS | Rosario | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0215S00043 | 15DD0183 | 2015-08-26 | 2015-09-01 | 2015-09-14 | 2015-09-23 | 2015-10-07 | BERTO LUCCI BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Batangas | 307708 | Sico 1.0 National High School | SAN JUAN | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | Completed | 1 |  |  | 4A0215S00068 | 15DD0208 | 2015-11-20 | 2015-11-26 | 2015-12-09 | 2015-12-18 |  | MANUEL A. DELA TORRE, JR. BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301155 | Taysan NHS | SAN JOSE | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2058606 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | Batangas | 301155 | Taysan NHS | SAN JOSE | 4 |  | 6 | 3STY6CL | 2015 K10 BATCH 7 | 10417132 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | BATANGAS CITY | 301471 | Banaba West NHS | BATANGAS CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10487131.51 |  |  | Completed | 1 |  |  | 4A0215S00027 | 15DE0078 | 2015-08-17 | 2015-08-18 | 2015-09-03 | 2015-09-08 | 2015-09-14 | GREAT SWISS METAL BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | BATANGAS CITY |  | Proposed Stand-Alone SHS 1(Gulod) | BATANGAS CITY (Capital) | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | BATANGAS CITY |  | Proposed Stand-Alone SHS 2(Alangilan) | BATANGAS CITY (Capital) | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 8 | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | BATANGAS CITY | 301479 | San Agustin NHS | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6639337.6381 |  |  | Completed | 1 |  |  | 4A0215S00025 | 15DE0083 | 2015-09-03 | 2015-09-04 | 2015-09-18 | 2015-09-23 | 2015-09-30 | W. RIVERA CONSTRUCTION & EQUIPMENT RENTALS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | CALAMBA CITY | 301511 | Bubuyan National High School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | Completed | 1 |  |  | 4A0415S00068 | 15DI0152 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-16 | 2015-11-18 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CALAMBA CITY | 301514 | Calamba Bayside National High School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 |  |  | 4A0415S00043 | 15DI0123 | 2015-09-09 | 2015-09-21 | 2015-09-22 | 2015-09-27 | 2015-10-09 | POWER K CONSTRUCTION SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CALAMBA CITY | 301516 | Camp Vicente Lim NHS | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 |  |  | 4A0415S00047 | 15DI0107 | 2015-07-20 | 2015-08-03 | 2015-08-05 | 2015-08-20 | 2015-08-26 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CALAMBA CITY | 301521 | Kapayapaan National HS | CITY OF CALAMBA | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | CALAMBA CITY | 308701 | Lawa National High School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 15197519 |  |  | Completed | 1 |  |  | 4A0415S00065 | 15DI0153 | 2015-10-15 | 2015-10-27 | 2015-10-30 | 2015-11-16 | 2015-11-18 | POWER K CONSTRUCTION SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CALAMBA CITY | 301523 | Makiling National High School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | Completed | 1 |  |  | 4A0415S00066 | 15DI0151 | 2015-10-15 | 2015-10-27 | 2015-10-30 | 2015-11-16 | 2015-11-18 | POWER K CONSTRUCTION SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CALAMBA CITY | 109856 | Palo Alto ES | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | Completed | 1 |  |  | 4A0415S00078 | 15DI0129 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CALAMBA CITY | 301524 | Palo Alto National High School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 |  |  | 4A0415S00038 | 15DI0108 | 2015-07-20 | 2015-08-03 | 2015-08-05 | 2015-08-20 | 2015-08-26 | HONEYVILLE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CALAMBA CITY | 109857 | Post ES | CITY OF CALAMBA | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0415S00077 | 15DI0149 | 2015-10-15 | 2015-10-27 | 2015-10-28 | 2015-11-13 | 2015-11-18 | POWER K CONSTRUCTION SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | CALAMBA CITY | 301525 | Punta National High School | CITY OF CALAMBA | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 |  |  | 4A0415S00062 | 15DI0148 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-11-09 | 2015-11-13 | GAB-ZION ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301172 | Bagbag NHS (Ligtong NHS) | ROSARIO | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301189 | Emiliano T. Tirona MNHS | KAWIT | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 24152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301192 | Gen. Mariano Alvarez Tech. HS | GEN. MARIANO ALVAREZ | 5 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 32102890 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301193 | Gen. Vito Belarmino NHS | SILANG | 5 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 2 | 21383013.45 |  |  | Completed | 1 |  |  | 4A0315S00011 | 15DG0060 | 2015-07-27 | 2015-08-08 | 2015-08-18 | 2015-08-27 | 2015-09-01 | ALMAKAR BUILDERS & METAL WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 107895 | Lantic ES | CARMONA | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0315S00043 | 15DF0125 | 2015-09-15 | 2015-09-22 | 2015-10-06 | 2015-10-12 | 2015-10-21 | KLDS TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 108116 | Mataas Na Burol ES (Burol ES) | SILANG | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Completed | 1 |  |  | 4A0315S00041 | 15DG0077 | 2015-09-09 | 2015-09-21 | 2015-09-30 | 2015-10-14 | 2015-10-27 | OMNICON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301205 | Munting Ilog NHS | SILANG | 5 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22352344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 107941 | San Gabriel II ES | GEN. MARIANO ALVAREZ | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0315S00042 | 15DF0124 | 2015-09-15 | 2015-09-22 | 2015-10-06 | 2015-10-12 | 2015-10-21 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301213 | San Jose Community HS | GEN. MARIANO ALVAREZ | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 107943 | San Jose ES | GEN. MARIANO ALVAREZ | 5 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | Completed | 1 |  |  | 4A0315S00044 | 15DF0125 | 2015-09-15 | 2015-09-22 | 2015-10-06 | 2015-10-12 | 2015-10-21 | KLDS TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | CAVITE | PSA328465 | SHS in Carmona | CARMONA | 5 | 1 | 40 | 4STY20CL | 2015 SHS BATCH 5 | 64205781 |  |  | Completed | 1 |  |  | 4A0315S00030 | 15DF0170 | 2015-11-06 | 2015-11-13 | 2015-12-04 | 2015-12-10 | 2015-12-18 | JV: R.A. DEL ROSARIO CONSTRUCTION/KLDS TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 108138SHS | SHS within Ulat ES | SILANG | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | Completed | 1 |  |  | 4A0315S00060 | 15DG0085 | 2015-11-02 | 2015-11-14 | 2015-11-24 | 2015-12-11 |  | J.S. GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301166 | Amadeo NHS | AMADEO | 6 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 |  |  | 4A0315S00013 | 15DG0052 | 2015-07-14 | 2015-07-26 | 2015-08-04 | 2015-08-18 | 2015-09-01 | R.D. MANDANAS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301167 | Amaya Sch. of Home Industries | TANZA | 6 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301195 | Halang Banaybanay NHS | AMADEO | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10817132 |  |  | Completed | 1 |  |  | 4A0315S00028 | 15DG0072 | 2015-08-28 | 2015-09-09 | 2015-09-18 | 2015-10-02 | 2015-10-16 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | GENERAL TRIAS CITY | 107951 | Manggahan ES | GENERAL TRIAS | 6 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | Completed | 1 |  |  | 4A0315S00045 | 15DF0114 | 2015-09-10 | 2015-09-17 | 2015-10-20 | 2015-10-26 | 2015-11-05 | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301217 | Talon NHS | AMADEO | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Completed | 1 |  |  | 4A0315S00027 | 15DG0070 | 2015-08-27 | 2015-09-08 | 2015-09-17 | 2015-10-02 | 2015-10-16 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301219 | Tanza NTS | TANZA | 6 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301168 | Anuling NHS | MENDEZ (MENDEZ-NUÑEZ) | 8 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Completed | 1 |  |  | 4A0315S00034 | 15DG0075 | 2015-09-03 | 2015-09-15 | 2015-09-24 | 2015-10-13 | 2015-10-27 | PRIJOLES TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301175 | Bucal NHS | MARAGONDON | 8 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 307805 | Buck Estate National HS | ALFONSO | 8 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Completed | 1 |  |  | 4A0315S00023 | 15DG0076 | 2015-09-03 | 2015-09-15 | 2015-09-24 | 2015-10-14 | 2015-10-27 | PRIJOLES TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301191 | Gen. Emilio Aguinaldo NHS (Bailen) | GENERAL EMILIO AGUINALDO | 8 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | Completed | 1 |  |  | 4A0315S00025 | 15DG0073 | 2015-08-28 | 2015-09-09 | 2015-09-18 | 2015-10-02 | 2015-10-16 | R.A. YOLANGCO CONSTRUCTION AND TRADING (FORMERLY: |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301199 | Lucsuhin National High School | ALFONSO | 8 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10917132 |  |  | Completed | 1 |  |  | 4A0315S00026 | 15DG0071 | 2015-08-28 | 2015-09-09 | 2015-09-18 | 2015-10-05 | 2015-10-16 | R.D. MANDANAS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301201 | Lumampong NHS - Indang NHS Annex | INDANG | 7 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301207 | Naic NHS | NAIC | 8 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301211 | Pulo ni Sara NHS | MARAGONDON | 8 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | Completed | 1 |  |  | 4A0315S00032 | 15DG0074 | 2015-09-03 | 2015-09-15 | 2015-09-24 | 2015-10-13 | 2015-10-27 | N.B. AVILA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301216 | Tagaytay City National High School | TAGAYTAY CITY | 8 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15197518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CAVITE | 301215 | Tagaytay City Nat'l. Science HS | TAGAYTAY CITY | 8 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 |  |  | 4A0315S00017 | 15DG0096 | 2015-11-17 | 2015-11-29 | 2015-12-09 | 2015-12-28 |  | HAUSLAND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CAVITE CITY | 301484 | Cavite National High School | CAVITE CITY | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | Completed | 1 |  |  | 4A0315S00018 | 15DF0087 | 2015-08-07 | 2015-08-14 | 2015-08-28 | 2015-09-04 | 2015-09-14 | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | REGION IV-A | CAVITE CITY | 109629 | Julian R. Felipe ES | CAVITE CITY | 1 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | Completed | 1 |  |  | 4A0315S00046 | 15DF0113 | 2015-09-10 | 2015-09-17 | 2015-09-29 | 2015-10-05 | 2015-10-14 | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | CAVITE CITY |  | Proposed Stand Alone SHS (Sangley ES) | Cavite City | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 23052344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | CAVITE CITY | 301485 | Sangley Point NHS | CAVITE CITY | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | CITY OF BIÑAN |  | Proposed Stand-Alone SHS 14 | Biñan # 1 | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | CITY OF BIÑAN |  | Proposed Stand-Alone SHS 15 | Biñan # 2 | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | CITY OF BIÑAN |  | Propsoed Stand-Alone SHS 16 | Biñan # 3 | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | CITY OF BIÑAN | 307931 | Saint Francis NHS | CITY OF BIÑAN | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | Completed | 1 |  |  | 4A0415S00020 | 15DI0087 | 2015-06-30 | 2015-07-14 | 2015-07-15 | 2015-07-22 | 2015-07-27 | 11 DIAMOND EAGLE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | CITY OF BIÑAN | 307934 | SOUTHVILLE 5-A NATIONAL HIGH SCHOOL | CITY OF BIÑAN | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | Dasmarinas City | 107904 | Langkaan ES | CITY OF DASMARIÑAS | 4 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | Completed | 1 |  |  | 4A0315S00047 | 15DF0111 | 2015-09-10 | 2015-09-17 | 2015-09-29 | 2015-10-05 | 2015-10-14 | R.A. YOLANGCO CONSTRUCTION AND TRADING (FORMERLY: |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Dasmarinas City | 107905 | Malinta ES | CITY OF DASMARIÑAS | 4 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | Completed | 1 |  |  | 4A0315S00049 | 15DF0112 | 2015-09-10 | 2015-09-17 | 2015-09-29 | 2015-10-05 | 2015-10-14 | L.B. SPIRES BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Dasmarinas City |  | Stand Alone 1 - San Jose Site | Dasmariñas City | 4 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31602890 |  |  | Completed | 1 | [9 empty] | KLDS Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | REGION IV-A | Dasmarinas City |  | Stand Alone 2 - Paliparan Site | Dasmariñas City | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | Completed | 1 | [9 empty] | Almakar Builders and Metal Works |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | Dasmarinas City |  | Stand Alone 3 - Dr. Jose P. Rizal ES Site | Dasmariñas City | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22552344 |  |  | Completed | 1 | [9 empty] | Ramon F. Jabalera Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Dasmarinas City |  | Stand Alone 4 - Dasmariñas NHS Site | Dasmariñas City | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15921328 |  |  | Completed | 1 | [9 empty] | Bacprince Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2015 | REGION IV-A | Dasmarinas City |  | Stand Alone 5 - New Era ES Site | Dasmariñas City | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 | [9 empty] | R.A. Del Rosario Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Imus City | 107980 | Alapan I ES | IMUS | 3 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | Completed | 1 |  |  | 4A0315S00048 | 15DF0116 | 2015-09-10 | 2015-09-17 | 2015-09-29 | 2015-10-05 | 2015-10-14 | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Imus City |  | Proposed Stand Alone SHS (Pedro Reyes) | Imus City | 3 | 1 | 32 | 4STY16CL | 2015 SHS BATCH 5 | 53404939 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2015 | REGION IV-A | Imus City |  | Proposed Stand Alone SHS (Toclong) | Imus City | 3 | 1 | 32 | 4STY16CL | 2015 SHS BATCH 5 | 56404939 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2015 | REGION IV-A | LAGUNA |  | Proposed Stand-Alone SHS 23 (Pacita I ES) | San Pedro | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | LAGUNA | 108428 | Rosario Complex ES | SAN PEDRO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0415S00079 | 15DI0128 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | L.P.O. ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | LAGUNA | 307914 | San Pedro Relocation CHS - Landayan Annex | SAN PEDRO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8514965.051 |  |  | Completed | 1 |  |  | 4A0415S00028 | 4A04-15-S-00028 | 2015-12-10 | 2015-12-22 | 2015-12-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301229 | Bigaa NHS | CABUYAO | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15271327.92 |  |  | Completed | 1 |  |  | 4A0415S00041 | 4A04-15-S-00041 | 2015-11-07 | 2015-11-15 | 2015-11-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301235 | Cabuyao NHS - Casile NHS Annex | CABUYAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2238606.04 |  |  | Completed | 1 |  |  | 4A0415S00040 | 15DI0126 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | R.D. MANDANAS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301251 | Masaya NHS | BAY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10567131.51 |  |  | Completed | 1 |  |  | 4A0415S00039 | 15DI0111 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-09-11 | 2015-09-15 | POWER K CONSTRUCTION SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna |  | Proposed Stand-Alone SHS 10 (Bayog) | LOS BAÑOS | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301259 | Proposed Stand-Alone SHS 12 (Pulo NHS) | Cabuyao # 1(Pulo) | 2 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | REGION IV-A | Laguna |  | Proposed Stand-Alone SHS 8 (Bambang Elementary School) | LOS BAÑOS | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna |  | Proposed Stand-Alone SHS 9 (Lalakay) | LOS BAÑOS | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Laguna |  | Proposed Stand-Alone SHS 11 (BN. Calara) | Los Baños # 5 | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | Laguna | 108313 | San Antonio Elementary School | LOS BAÑOS | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0415S00081 | 15DI0121 | 2015-09-10 | 2015-09-22 | 2015-09-24 | 2015-10-02 | 2015-10-09 | POWER K CONSTRUCTION SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | Laguna | 307923 | Southville I NHS | CABUYAO | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22302343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Laguna | 108210 | Sto Domingo ES | BAY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0415S00082 | 15DI0125 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | POWER K CONSTRUCTION SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Laguna | 307933 | Tuntungin-Putho NHS | LOS BAÑOS | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0415S00044 | 15DI0086 | 2015-06-30 | 2015-07-13 | 2015-07-15 | 2015-07-22 | 2015-07-27 | ST. GERRARD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301265 | Alaminos NHS | ALAMINOS | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10467131.51 |  |  | Completed | 1 |  |  | 4A0415S00045 | 15DP0072 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301228 | Banca-Banca NHS | VICTORIA | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10467131.51 |  |  | Completed | 1 |  |  | 4A0415S00056 | 15DP0073 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | MJACQ ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 307924 | Buenaventura Fandialan Memo. NHS | ALAMINOS | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | Completed | 1 |  |  | 4A0415S00049 | 15DP0074 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301237 | Calumpang NHS - Lowland NHS Annex | NAGCARLAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | Completed | 1 |  |  | 4A0415S00050 | 15DP0075 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | NEW RICH GENERAL CONTRACTOR SERVICES & TRADING Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 307903 | Cristobal S. Conducto MNHS | RIZAL | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | Completed | 1 |  |  | 4A0415S00051 | 15DP0076 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 307927 | Dayap NHS (Calauan Annex) | CALAUAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2952592.44 |  |  | Completed | 1 |  |  | 4A0415S00052 | 15DP0070 | 2015-09-21 | 2015-09-22 | 2015-10-06 | 2015-10-24 | 2015-11-03 | DMLC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | REGION IV-A | Laguna | 108497 | Masapang ES | VICTORIA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0415S00083 | 15DP0085 | 2015-09-21 | 2015-09-22 | 2015-10-06 | 2015-10-24 | 2015-11-03 | R CEL GENERAL CONTRACTOR & GEN MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301250 | Masapang NHS | VICTORIA | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10467131.51 |  |  | Completed | 1 |  |  | 4A0415S00053 | 15DP0077 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | 11 DIAMOND EAGLE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301258 | Plaridel NHS | NAGCARLAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10467131.51 |  |  | Completed | 1 |  |  | 4A0415S00054 | 15DP0078 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | MJACQ ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna |  | Proposed Stand-Alone SHS 21 | Calauan | 3 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301264 | San Francisco NHS | VICTORIA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | Completed | 1 |  |  | 4A0415S00029 | 15DP0071 | 2015-08-13 | 2015-08-13 | 2015-08-26 | 2015-09-13 | 2015-09-21 | STO. CRISTO CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301276 | Talangan NHS | NAGCARLAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10617131.51 |  |  | Completed | 1 |  |  | 4A0415S00048 | 15DP0079 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | 11 DIAMOND EAGLE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301278 | Upland NHS | NAGCARLAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10617131.51 |  |  | Completed | 1 |  |  | 4A0415S00046 | 15DP0080 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | STO. CRISTO CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 108374 | Ibaba ES | PAETE | 4 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 1344160.8418 |  |  | Reverted | 0.001 |  |  | 4A0415S00090 | 4A04-15-S-00057 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | Laguna | 108446 | Santa Cruz ES | STA. CRUZ | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 969303.02 |  |  | Completed | 1 |  |  | 4A0415S00087 | 15DH0100 | 2015-10-23 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Laguna | 307918 | Balian NHS (Galalan Annex) | PANGIL | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2288606.04 |  |  | Completed | 1 |  |  | 4A0415S00019 | 15DH0053 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | ENC ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301232 | Buenavista NHS | MAGDALENA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | Completed | 1 |  |  | 4A0415S00018 | 15DH0054 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | MAR-VEL CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 108339 | Buenavista-Cigaras ES | MAGDALENA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0415S00086 | 15DH0069 | 2015-08-20 | 2015-09-03 | 2015-09-15 | 2015-09-25 | 2015-10-08 | DMLC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | Laguna | 108340 | Bungkol ES | MAGDALENA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0415S00080 | 15DH0068 | 2015-08-20 | 2015-09-03 | 2015-09-15 | 2015-09-25 | 2015-10-23 | POWER K CONSTRUCTION SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | Laguna | 307911 | Cavinti NHS | CAVINTI | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14947518.84 |  |  | Completed | 1 |  |  | 4A0415S00023 | 15DH0063 | 2015-08-17 | 2015-08-27 | 2015-09-08 | 2015-09-22 | 2015-10-05 | POWER K CONSTRUCTION SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | Laguna | 307926 | Cavinti NHS (Calminue Ext.) | CAVINTI | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0415S00017 | 15DH0083 | 2015-10-23 | 2015-11-04 | 2015-11-16 | 2015-11-27 | 2015-12-14 | JOBEL ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301240 | Famy National High School | FAMY | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15271327.92 |  |  | Reverted | 0.001 |  |  | 4A0415S00025 | 4A04-15-S-00025 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | Laguna | 307906 | FELICISIMO T. SAN LUIS NHS | SANTA CRUZ (Capital) | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26852469.42 |  |  | Completed | 1 |  |  | 4A0415S00026 | 15DH0071 | 2015-09-07 | 2015-09-11 | 2015-09-23 | 2015-09-29 | 2015-10-13 | J.B. ALARCON ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301270 | Gaudencio Octavio National High School | SANTA MARIA | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10617131.51 |  |  | Completed | 1 |  |  | 4A0415S00037 | 15DH0064 | 2015-08-17 | 2015-08-27 | 2015-09-08 | 2015-09-22 | 2015-10-05 | POWER K CONSTRUCTION SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 164501 | Gisgis ES | PANGIL | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0415S00085 | 15DH0099 | 2015-11-24 | 2015-12-04 | 2015-12-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301274 | GOV. FELICISIMO T. SAN LUIS NATIONAL AGRO-INDUSTRIAL HIGH SCHOOL | SINILOAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | Completed | 1 |  |  | 4A0415S00016 | 15DH0055 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | L.P.O. ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301243 | Kabulusan National High School | PAKIL | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301249 | Mabitac NHS | MABITAC | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15221327.92 |  |  | Completed | 1 |  |  | 4A0415S00032 | 15DH0066 | 2015-08-17 | 2015-08-27 | 2015-09-08 | 2015-09-22 | 2015-10-05 | DSO ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2015 | REGION IV-A | Laguna | 307937 | Magdalena NHS (Buenavista Annex) | MAGDALENA | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0415S00033 | 15DH0061 | 2015-07-31 | 2015-08-12 | 2015-08-24 | 2015-09-02 | 2015-09-17 | PROTECH CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301253 | Pagsanjan NHS | PAGSANJAN | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | Completed | 1 |  |  | 4A0415S00034 | 15DH0062 | 2015-07-31 | 2015-08-12 | 2015-08-24 | 2015-09-02 | 2015-09-17 | 11 DIAMOND EAGLE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna |  | Proposed Stand-Alone SHS 3 | Pagsanjan | 4 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10877343 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | Laguna |  | Proposed Stand-Alone SHS 19 (Paete Central Elementary School) | Paete (Paete ES) | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Laguna | 108412 | Proposed Stand-Alone SHS 20 (Pinagbayanan ES) | Pila | 4 | 1 | 30 | 3STY15CL | 2015 SHS BATCH 5 | 42766027 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2015 | REGION IV-A | Laguna | 108343 | Ricardo A. Pronove ES | MAGDALENA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0.001 |  |  | 4A0415S00084 | 15DH0027 | [5 empty] | PHILIPPINE CHEMSTEEL INDUSTRIES, INC. |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301263 | San Buenaventura NHS | LUISIANA | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | Completed | 1 |  |  | 4A0415S00035 | 15DH0067 | 2015-08-17 | 2015-08-27 | 2015-09-08 | 2015-09-22 | 2015-09-30 | C.T. LEONCIO CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 307935 | San Buenaventura NHS Annex | LUISIANA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2188606.04 |  |  | Completed | 1 |  |  | 4A0415S00015 | 15DH0056 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | ILG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Laguna | 307920 | San Juan NHS (San Antonio Annex) | KALAYAAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | Completed | 1 |  |  | 4A0415S00014 | 15DH0057 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | POWER K CONSTRUCTION SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301271 | Santa Maria NHS - J. Santiago Annex | SANTA MARIA | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10617131.51 |  |  | Completed | 1 |  |  | 4A0415S00055 | 15DH0072 | 2015-09-01 | 2015-09-11 | 2015-09-23 | 2015-09-29 | 2015-10-13 | NEW RICH GENERAL CONTRACTOR SERVICES & TRADING Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301268 | Sta. Catalina NHS | MAJAYJAY | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10617131.51 |  |  | Completed | 1 |  |  | 4A0415S00027 | 15DH0073 | 2015-09-01 | 2015-09-11 | 2015-09-23 | 2015-09-29 | 2015-10-13 | PROTECH CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | Laguna | 301269 | Sta. Maria NHS | SANTA MARIA | 4 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 2 | 21533013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2015 | REGION IV-A | Laguna | PSA328512 | Stand Alone SHS No. 20 Santa Cruz | Santa Cruz | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | Completed | 1 |  |  | 4A0415S00099 | 15DH0097 | 2015-11-24 | 2015-12-04 | 2015-12-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | Laguna | PSA328492 | Stand Alone SHS No. 4 Sta. Cruz | Santa Cruz | 4 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | Completed | 1 |  |  | 4A0415S00070 | 15DH0080 | 2015-10-19 | 2015-10-22 | 2015-11-03 | 2015-11-16 | 2015-12-01 | C.T. LEONCIO CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2015 | REGION IV-A | LIPA CITY | 301487 | BOLBOK NATIONAL HIGH SCHOOL | LIPA CITY | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | Completed | 1 |  |  |  | 15DD0189 |  |  |  |  | 2016-10-22 | RV RIETA TRADING AND GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | LIPA CITY | 301490 | Fernando Air Base NHS | LIPA CITY | 4 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | Completed | 1 |  |  | 4A0215S00031 | 15DD0178 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-08-27 | 2015-09-15 | F.F. ROSALES GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | LIPA CITY | 301491 | Inosloban-Marawoy NHS | LIPA CITY | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14967518.84 |  |  | Completed | 1 |  |  |  | 15DD0184 |  |  |  |  | 2015-12-01 | RV RIETA TRADING AND GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | LIPA CITY | 109693 | Padre Valerio Malabanan MS | LIPA CITY | 4 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0215S00054 | 16DD0078 | 2015-11-20 | 2015-11-26 |  |  | 2016-04-05 | JBL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | LIPA CITY | 301497 | Pinagtongulan NHS | LIPA CITY | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | Completed | 1 |  |  |  | 15DD0187 |  |  |  |  | 2015-10-22 | RV RIETA TRADING AND GENERAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | LIPA CITY | 301499 | San Celestino National High School | LIPA CITY | 4 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10957343 |  |  | Completed | 1 |  |  | 4A0215S00046 | 15DD0191 | 2015-10-17 | 2015-10-23 | 2015-11-04 | 2015-11-12 | 2015-12-01 | THREE W BUILDERS, INC. | No Remarks | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | LIPA CITY | 109686 | San Guillermo ES | LIPA CITY | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0215S00055 | 16DD0076 |  |  |  |  | 2016-04-05 | JBL BUILDERS | No Remarks | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | LIPA CITY | 109667 | Sen. Ma. E. Kalaw Katigbak MS | LIPA CITY | 4 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0215S00056 | 15DD0202 | 2015-11-20 | 2015-11-26 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | LUCENA CITY | 308503 | Gulang-Gulang NHS | LUCENA CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | Completed | 1 |  |  | 4A0515S00028 | 15DJ0069 | 2015-07-16 | 2015-08-04 | 2015-08-06 | 2015-08-11 | 2015-08-12 | MGDJ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | LUCENA CITY | 167502 | Isabang ES-Bocohan Annex | LUCENA CITY (Capital) | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0515S00099 | 15DJ0077 | 2015-08-31 | 2015-09-02 | 2015-09-15 | 2015-09-21 | 2015-09-24 | MGDJ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | LUCENA CITY | 301501 | Lucena City National High School | LUCENA CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | LUCENA CITY | 308505 | Lucena City NHS -Mayao Parada Extension | LUCENA CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00026 | 15DJ0071 | 2015-07-16 | 2015-07-20 | 2015-08-04 | 2015-08-07 | 2015-08-12 | SOUTHERN DAWN DEVELOPMENT COMPANY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | LUCENA CITY | 308501 | Lucena Dalahican NHS | LUCENA CITY (Capital) | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | Completed | 1 |  |  | 4A0515S00025 | 15DJ0074 | 2015-07-29 | 2015-07-31 | 2015-08-13 | 2015-08-17 | 2015-08-25 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301292 | Batangan National High School | GENERAL NAKAR | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00124 | 15DK0132 | October 8, 2015 | October 16, 2015 | October 30, 2015 | November 10, 2015 | November 20, 2015 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308028 | Busdak NHS (Formerly Busdak NHS - Patnanungan NHS Annex) | PATNANUNGAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00122 | 15DK0128 | 2015-10-08 | 2015-10-13 | 2015-10-30 | 2015-11-10 | 2015-11-20 | E.A. AYALA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108907 | Cagsiay II ES | MAUBAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00107 | 15DK0098 | 2015-10-07 | 2015-10-09 | 2015-10-30 | 2015-11-10 | 2015-11-20 | L.A. CLAMOR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301397 | Calasumanga NHS (Formerly San Juan NHS - Calasumanga Ext.) | PANUKULAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00121 | 15DK0131 | 2015-10-08 | 2015-10-13 | 2015-10-30 | 2015-11-10 | 2015-11-20 | E.A. AYALA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301333 | Jomalig NHS | JOMALIG | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00024 | 15DK0061 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-08-07 | 2015-08-13 | E.A. AYALA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301343 | Langgas NHS | INFANTA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00023 | 15DK0059 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-08-07 | 2015-08-13 | E.A. AYALA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108568 | Palasan ES | BURDEOS | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | Completed | 1 |  |  | 4A0515S00098 | 15DK0100 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 109041 | Pandan ES | PANUKULAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | Completed | 1 |  |  | 4A0515S00097 | 15DK0101 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108990 | Patnanungan Norte ES | PATNANUNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00096 | 15DK0099 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | E.A. AYALA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 165002 | Remedios I ES (Annex) Bulusok | MAUBAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | Completed | 1 |  |  | 4A0515S00106 | 15DK0102 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | E.A. AYALA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301382 | Sabang NHS | POLILLO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00108 | 15DK0130 | 2015-10-08 | 2015-10-13 | 2015-10-30 | 2015-11-10 | 2015-11-20 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301396 | San Juan NHS | PANUKULAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00022 | 15DK0060 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-07-31 | 2015-08-13 | E.A. AYALA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301408 | Taluong NHS | POLILLO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00111 | 15DK0129 | 2015-10-08 | 2015-10-13 | 2015-10-30 | 2015-11-10 | 2015-11-20 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108571 | Tulan ES | BURDEOS | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | Completed | 1 |  |  | 4A0515S00089 | 15DK0103 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | ANNCON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301412 | Ungos NHS | REAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | Completed | 1 |  |  | 4A0515S00018 | 15DK0126 | 2015-10-15 | 2015-10-16 | 2015-10-30 | 2015-11-10 | 2015-11-20 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301413 | Ungos NHS - Extension (Llavac) | REAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | Completed | 1 |  |  | 4A0515S00018 | 15DK0126 | October 8, 2015 | October 16, 2015 | October 30, 2015 | November 10, 2015 | November 20, 2015 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308043 | Bignay NHS | SARIAYA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00123 | 15DJ0085 | 2015-09-27 | 2015-09-28 | 2015-10-20 | 2015-10-26 | 2015-10-28 | M.G. VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308041 | Castañas NHS | SARIAYA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0515S00119 | 15DJ0088 | 2015-09-28 | 2015-09-30 | 2015-10-22 | 2015-10-27 | 2015-10-30 | M.G. VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301317 | Dagatan NHS | DOLORES | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0515S00020 | 15JD0068 | 2015-07-16 | 2015-07-20 | 2015-08-04 | 2015-08-07 | 2015-08-12 | DL ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308040 | Dr. Panfilo Castro NHS - Masalukot I Annex | CANDELARIA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00029 | 15DJ0070 | 2015-07-16 | 2015-07-20 | 2015-08-04 | 2015-08-10 | 2015-08-12 | MGDJ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308012 | Gloria Umali NHS | TIAONG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00117 | 15DJ0089 | 2015-09-28 | 2015-09-30 | 2015-10-22 | 2015-10-27 | 2015-10-30 | M.A. GUINTO CONSTRUCTION (SAN JOSE BRANCH) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308016 | Manuel M. Macasaet NHS (Formerly Sta. Catalina NHS - Amland Ext.) | CANDELARIA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0515S00113 | 15DJ0084 | 2015-09-27 | 2015-09-28 | 2015-10-20 | 2015-10-26 | 2015-10-28 | M.G. VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308032 | Pili NHS (Formerly Lutucan NHS Pili Ext.) | SARIAYA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0515S00112 | 15DJ0086 | 2015-09-27 | 2015-09-28 | 2015-10-20 | 2015-10-26 | 2015-10-28 | M.G. VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301280 | Abuyon NHS | SAN NARCISO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | Completed | 1 |  |  | 4A0515S00110 | 4A05-15-S-00110 | 2015-09-03 | 2015-08-24 | 2015-09-03 | 2015-12-09 | 2015-12-16 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108918 | Acaciahan ES | MULANAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00070 | 4A05-15-S-00070 | 2015-08-12 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108643 | Ajos ES | CATANAUAN | 3 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4523636.82 |  |  | Completed | 1 |  |  | 4A0515S00093 | 4A05-15-S-00093 | 2015-09-16 | 2015-09-04 | 2015-09-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108920 | Anonang ES | MULANAY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | Completed | 1 |  |  | 4A0515S00104 | 4A05-15-S-00104 | 2015-08-12 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301288 | Bagupaye NHS | MULANAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 109089 | Banaba ES | SAN ANDRES | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | Completed | 1 |  |  | 4A0515S00101 | 4A05-15-S-00101 | 2015-09-16 | 2015-09-04 | 2015-09-16 | 2015-09-22 | 2015-10-27 | JSP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301296 | Buenavista NHS | BUENAVISTA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | Completed | 1 |  |  | 4A0515S00040 | 4A05-15-S-00040 | 2015-08-12 | 2015-08-13 | 2015-08-25 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301298 | Busdak NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3747969 |  |  | Completed | 1 |  |  | 4A0515S00030 | 4A05-15-S-00030. | 2015-08-12 | 2015-08-13 | 2015-08-25 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308014 | Cabong NHS | BUENAVISTA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2008606 |  |  | Completed | 1 |  |  | 4A0515S00059 | 4A05-15-S-00059 | 2015-08-12 | 2015-08-13 | 2015-08-25 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301300 | Cabulihan NHS | PITOGO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | Completed | 1 |  |  | 4A0515S00050 | 4A05-15-S-00050 | 2015-08-12 | 2015-08-13 | 2015-08-25 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108946 | Cabuyao ES | PADRE BURGOS | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00071 | 4A05-15-S-00071 | 2015-09-14 | 2015-09-15 | 2015-09-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108925 | Calangcang ES | MULANAY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | Completed | 1 |  |  | 4A0515S00103 | 15DM0109 | 2015-09-16 | 2015-09-04 | 2015-09-16 | 2015-09-22 | 2015-11-06 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 109002 | Cawayanin ES | PITOGO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00072 | 4A05-15-S-00072 | 2015-09-16 | 2015-09-04 | 2015-09-16 | 2015-09-22 | 2015-12-16 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301322 | Gregorio Reyes NHS | SAN NARCISO | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6519338 |  |  | Completed | 1 |  |  | 4A0515S00042 | 4A05-15-S-00042 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-31 | 2015-12-10 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308044 | Huyon-Uyon NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3967969 |  |  | Completed | 1 |  |  | 4A0515S00033 | 4A05-15-S-00033 | 2015-08-27 | 2015-08-28 | 2015-09-09 | 2015-10-09 | 2015-10-27 | KKT CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301371 | Leonarda D. Vera Cruz NHS (Formerly Panaon NHS) | UNISAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10517132 |  |  | Completed | 1 |  |  | 4A0515S00049 | 4A05-15-S-00049 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-30 | 2015-11-17 | RGP BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301337 | Lina Gayeta-Lasquety NHS (Formerly Kinagunan Ibaba NHS) | PADRE BURGOS | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308039 | LUALHATI D. EDAÑO NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00115 | 4A05-15-S-00115 | 2015-09-03 | 2015-08-24 | 2015-09-03 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301283 | Magsaysay NHS (Formerly Ajos NHS - Magsaysay Extension) | MULANAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1998606 |  |  | Completed | 1 |  |  | 4A0515S00052 | 4A05-15-S-00052 | 2015-08-12 | 2015-08-13 | 2015-08-25 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108879 | Malabahay ES | MACALELON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00087 | 4A05-15-S-00087 | 2015-08-12 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301354 | Malaya NHS | GENERAL LUNA | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00114 | 4A05-15-S-00114 | 2015-08-21 | 2015-08-24 | 2015-09-03 | 2015-09-10 | 2015-11-17 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108933 | Malibago ES | MULANAY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | Completed | 1 |  |  | 4A0515S00102 | 4A05-15-S-00102 | 2015-09-16 | 2015-09-04 | 2015-09-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308008 | Maligaya NHS | BUENAVISTA | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3727969 |  |  | Completed | 1 |  |  | 4A0515S00048 | 15DM0106 | 2015-08-27 | 2015-08-28 | 2015-09-09 | 2015-10-09 | 2015-10-27 | L.A. PROFUGO CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108934 | Matataja ES | MULANAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00066 | 4A05-15-S-00066 | 2015-10-28 | 2015-10-16 | 2015-10-28 | 2015-11-03 | 2015-12-16 | RGP BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301330 | PAKIING NATIONALHIGH SCHOOL | MULANAY | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3747969 |  |  | Reverted | 0 |  |  | 4A0515S00051 | 4A05-15-S-00051 | 2015-08-12 | 2015-08-13 | 2015-08-25 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301376 | Pitogo Community High School | PITOGO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | Completed | 1 |  |  | 4A0515S00056 | 4A05-15-S-00056 | 2015-08-12 | 2015-08-13 | 2015-08-25 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108691 | Recto ES | GENERAL LUNA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00076 | 4A05-15-S-00076 | 2015-10-20 | 2015-10-08 | 2015-10-20 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301368 | Renato Edano Vicencio NHS (Formerly Pagsangahan NHS-Don Juan Vercelos Annex) | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 4027969 |  |  | Completed | 1 |  |  | 4A0515S00037 | 4A05-15-S-00037 | 2015-08-12 | 2015-08-13 | 2015-08-25 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 109149 | Rizal ES | SAN NARCISO | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0515S00100 | 4A05-15-S-00100 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-09-03 | 2015-09-14 | RAPID FOREMOST CONST. CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108693 | San Ignacio Ilaya ES | GENERAL LUNA | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | Completed | 1 |  |  | 4A0515S00105 | 4A05-15-S-00105 | 2015-10-20 | 2015-10-08 | 2015-10-20 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108661 | San Pablo Suha ES | CATANAUAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00092 | 4A05-15-S-00092 | 2015-08-12 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308010 | San Vicente Kanluran NHS (Formerly San Isidro NHS - San Vicente Kanluran Ext) | CATANAUAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | Completed | 1 |  |  | 4A0515S00062 | 15DM0081 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-30 | 2015-11-17 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308003 | Sto. Niño National High School (Formerly Pagsangahan NHS Ext. Sto. Niño) | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 4077212 |  |  | Completed | 1 |  |  | 4A0515S00057 | 4A05-15-S-00057 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-11-20 | 2015-11-26 | RAPID FOREMOST CONST. CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108697 | Sumilang ES | GENERAL LUNA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00069 | 4A05-15-S-00069 | 2015-10-20 | 2015-10-08 | 2015-10-20 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301392 | Tagabas Ibaba NHS (Formerly San Isidro NHS - Tagabas Ibaba Ext) | CATANAUAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | Completed | 1 |  |  | 4A0515S00065 | 15DM0100 | 2015-08-27 | 2015-08-28 | 2015-09-09 | 2015-10-09 | 2015-10-27 | KKT CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108669 | Tagbacan Ilaya ES | CATANAUAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00091 | 4A05-15-S-00091 | 2015-09-16 | 2015-09-04 | 2015-09-16 | 2015-11-20 | 2015-11-26 | RAPID FOREMOST CONST. CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108671 | Tuhian ES | CATANAUAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00090 | 4A05-15-S-00090 | 2015-08-12 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 109135 | Tumbaga ES | SAN FRANCISCO (AURORA) | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00073 | 4A05-15-S-00073 | 2015-08-12 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308031 | White Cliff NHS | SAN NARCISO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2038606 |  |  | Completed | 1 |  |  | 4A0515S00032 | 4A05-15-S-00032 | 2015-08-12 | 2015-08-13 | 2015-08-25 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301342 | Aloneros NHS (Formerly LBS of Fisheries Ext. - Aloneros | GUINAYANGAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Completed | 1 |  |  | 4A0515S00053 | 15DL0163 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-11-02 | E.A. VILLANUEVA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308017 | Apad NHS (Formerly Sto. Domingo NHS - Apad Ext. Classes) | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2138606 |  |  | Completed | 1 |  |  | 4A0515S00041 | 15DL0152 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-10-23 | JUNCAN ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301287 | Bagong Silang NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2038606 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301289 | Bamban NHS | TAGKAWAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Completed | 1 |  |  | 4A0515S00058 | 15DL0161 | 2015-09-24 | 2015-10-01 | 2015-10-19 | 2015-10-22 | 2015-10-28 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108594 | Bantulinao ES | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00077 | 15DL0141 | 2015-09-14 | 2015-09-15 | 2015-09-29 | 2015-10-03 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308038 | Cabibihan NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2013606 |  |  | Completed | 1 |  |  | 4A0515S00043 | 15DL0154 | 2015-09-22 | 2015-09-23 | 2015-10-06 | 2015-10-09 | 2015-10-18 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301307 | Camohaguin NHS | GUMACA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | Completed | 1 |  |  | 4A0515S00120 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308042 | Cogorin Ibaba NHS - Jongo Ext. | LOPEZ | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00118 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301316 | Concepcion National High School | PLARIDEL | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0515S00126 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301388 | Dao National High School (Formerly San Francisco B NHS - San Miguel Dao II Ext.) | LOPEZ | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2048606 |  |  | Completed | 1 |  |  | 4A0515S00031 | 15DL0151 | 2015-09-21 | 2015-09-23 | 2015-09-15 | 2015-10-08 | 2015-10-23 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108577 | Dapdap ES | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00075 | 15DL0136 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-03 | 2015-10-21 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308021 | Dr. Arsenio C. Nicolas NHS | CALAUAG | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6369338 |  |  | Completed | 1 |  |  | 4A0515S00047 | 15DL0150 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-10-21 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308027 | Dr. Arsenio C. Nicolas NHS - Dominlog Ext. | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2038606 |  |  | Completed | 1 |  |  | 4A0515S00044 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301320 | Dungawan NHS | GUINAYANGAN | 4 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3717969 |  |  | Completed | 1 |  |  | 4A0515S00060 | 15DL0157 | 2015-09-22 | 2015-09-23 | 2015-10-06 | 2015-10-09 | 2015-10-18 | ZELAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108735 | Dungawan Paalyunan ES | GUINAYANGAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00067 | 15DL0135 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-02 | 2015-10-14 | ZELAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108737 | Gregorio M. Mendoza ES | GUINAYANGAN | 4 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | Completed | 1 |  |  | 4A0515S00094 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301331 | Inaclagan NHS | GUMACA | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00109 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108808 | Inalusan ES | LOPEZ | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00080 | 15DL0137 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-03 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108846 | Jongo ES | LOPEZ | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00083 | 15DL0138 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301336 | Katimo NHS | TAGKAWAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | Completed | 1 |  |  | 4A0515S00063 | 15DL0160 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-10-28 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301341 | Lamon Bay SOF Annex - Capalohan, Calauag | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2238606 |  |  | Completed | 1 |  |  | 4A0515S00064 | 15DL0149 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-10-23 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 109055 | Ma. Febrer Maningas ES | QUEZON | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00078 | 15DL0140 | 2015-09-14 | 2015-09-15 | 2015-09-29 | 2015-10-03 | 2015-10-21 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308045 | Mansilay NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1948606 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308002 | Mapulot NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1953606 |  |  | Completed | 1 |  |  | 4A0515S00055 | 15DL0155 | 2015-09-22 | 2015-09-23 | 2015-10-06 | 2015-10-09 | 2015-10-18 | C.G. CABANA CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301375 | Perez National High School | PEREZ | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108814 | Pisipis ES | LOPEZ | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00081 | 15DL0141 | 2015-09-14 | 2015-09-15 | 2015-09-29 | 2015-10-03 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308022 | Rufina P. Trinidad Mem. NHS | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2138606 |  |  | Completed | 1 |  |  | 4A0515S00046 | 15DL0149 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-10-23 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301395 | San Isidro NHS, Tagkawayan | TAGKAWAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6389338 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301398 | SANMANDELCAR NHS | TAGKAWAYAN | 4 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3877969 |  |  | Completed | 1 |  |  | 4A0515S00038 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108531 | Sta. Catalina ES | ATIMONAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00074 | 15DL0140 | 2015-09-11 | 2015-09-15 | 2015-09-29 | 2015-10-03 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301324 | STA. CRUZ NATIONAL HIGH SCHOOL | GUINAYANGAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | Completed | 1 |  |  | 4A0515S00061 | 15DL0158 | 2015-09-22 | 2015-09-23 | 2015-10-06 | 2015-10-09 | 2015-10-18 | ZELAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108748 | Sta. Maria ES | GUINAYANGAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00079 | 15DL0135 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-03 | 2015-10-21 | ZELAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108820 | Sto. Niño ES | LOPEZ | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0515S00068 | 15DL0143 | 2015-09-14 | 2015-09-15 | 2015-09-29 | 2015-10-03 | 2015-10-21 | JUNCAN ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301389 | Sto. Nino Ilaya NHS (Formerly San Francisco B NHS Sto. Niño Ilaya Ext.) | LOPEZ EAST | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00136 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 301405 | Tabason NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1948606 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108587 | Talingting ES | CALAUAG | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | Completed | 1 |  |  | 4A0515S00095 | 15DL0139 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108588 | Tamis ES | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00088 | 15DL0136 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-21 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 109060 | Teofilo Olivera ES | QUEZON | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00084 | 15DL0142 | 2015-09-14 | 2015-09-15 | 2015-09-29 | 2015-10-05 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 108823 | Vegaflor Elementary School | LOPEZ | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0515S00082 | 15DL0137 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-21 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | QUEZON | 308013 | Villa San Isidro NHS | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2138606 |  |  | Completed | 1 |  |  | 4A0515S00045 | 15DL0150 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-10-23 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109307 | Angono ES | ANGONO | 1 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26552469.42 |  |  | Completed | 1 |  |  | 4A0615S00029 | 15DN0119 | 2015-10-22 | 2015-10-23 | 2015-11-05 | 2015-11-18 |  | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109393 | Balanti ES | CAINTA | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Reverted | 0 |  |  | 4A0615S00032 | 4A06-15-S-00032 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 301433 | Carlos "Botong" Francisco MNHS | ANGONO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | Completed | 1 |  |  | 4A0615S00017 | 15DN0127 | 2015-11-05 | 2015-11-05 | 2015-11-19 | 2015-12-01 | 2015-12-14 | ONE EULUZ CONSTRUCTION CORPORATION (FORMERLY: EULUZ CONSTRUCTION & SUPPLY) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109366 | Casimiro A. Ynares, Sr. ES | BINANGONAN | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0615S00033 | 15DN0130 | 2015-11-12 | 2015-11-13 | 2015-11-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 308131 | Dr. Vivencio B. Villamayor NHS | ANGONO | 1 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 7 | 15121328 |  |  | Completed | 1 |  |  | 4A0615S00041 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 301445 | Janosa National High School | BINANGONAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | Completed | 1 |  |  | 4A0615S00046 | 15DN0128 | 2015-11-05 | 2015-11-05 | 2015-11-19 | 2015-12-01 | 2015-12-14 | FRAMECON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 308104 | Margarito A. Duavit MNHS | BINANGONAN | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | Completed | 1 |  |  | 4A0615S00013 | 15DN0123 | 2015-11-04 | 2015-11-04 | 2015-11-17 | 2015-11-27 | 2015-12-14 | STO. CRISTO CONSTRUCTION & TRADING | No Remarks | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109404 | Marick ES | CAINTA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0615S00031 | 15DN0111 | 2015-10-07 | 2015-10-07 | 2015-10-20 | 2015-11-02 | 2015-11-13 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 308113 | Regional Lead School for the Arts in Angono | ANGONO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | Completed | 1 |  |  | 4A0615S00021 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109315 | San Vicente ES | ANGONO | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0615S00034 | 15DN0129 | 2015-11-12 | 2015-11-13 | 2015-11-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 301463 | Talim Point NHS | BINANGONAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0615S00005 | 15DN0090 | 2015-08-26 | 2015-08-26 | 2015-09-08 | 2015-09-18 | 2015-10-01 | MARK CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109499 | Balimbing ES | TANAY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | Completed | 1 |  |  | 4A0615S00036 | 15DO0065 | 2015-10-06 | 2015-10-09 | 2015-10-22 | 2015-10-30 | 2015-11-11 | JRD-D2 ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109505 | Daraetan ES | TANAY | 2 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 6 | 12621310.093 |  |  | Reverted | 0 |  |  | 4A0615S00039 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 165503 | Hulo ES | PILILLA | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0615S00028 | 15DO0117 | 2015-12-24 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 308121 | Hulo NHS | PILILLA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0615S00006 | 15DO0054 | 2015-07-21 | 2015-07-23 | 2015-08-05 | 2015-08-13 | 2015-08-26 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109489 | Justice Vicente Santiago ES | SAN MATEO | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | Completed | 1 |  |  | 4A0615S00030 | 15DO0094 | 2015-11-10 | 2015-11-13 | 2015-11-25 | 2015-12-10 | 2015-12-21 | R.F. DIAZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109510 | Madilay-dilay ES | TANAY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0615S00035 | 15DO0064 | 2015-10-06 | 2015-10-09 | 2015-10-22 | 2015-10-30 | 2015-11-11 | NVF CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109473 | Mascap ES - Magalipit Annex | RODRIGUEZ (MONTALBAN) | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0615S00022 | 15DO0115 | 2015-12-24 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 301452 | Morong National High School | MORONG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | Completed | 1 |  |  | 4A0615S00045 | 15DO0093 | 2015-11-10 | 2015-11-13 | 2015-11-25 | 2015-12-10 | 2015-12-21 | MINROCK MULTI-BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 308123 | Pantay NHS (Teresa NHS - Pantay Annex) | TERESA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | Completed | 1 |  |  | 4A0615S00018 | 15DO0109 | 2015-12-02 | 2015-12-01 | 2015-12-18 |  |  | MEGASTRUCTURE BUILDER & TRADING CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109493 | Pintong Bukawe ES | SAN MATEO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Completed | 1 |  |  | 4A0615S00040 | 15DO0068 | 2015-10-21 | 2015-10-22 | 2015-11-04 | 2015-11-12 | 2015-11-27 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 301459 | Pintong Bukawe National High School | SAN MATEO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Completed | 1 |  |  | 4A0615S00014 | 15DO0075 | 2015-10-21 | 2015-10-22 | 2015-11-04 | 2015-11-12 | 2015-11-27 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | RIZAL |  | Proposed Stand-Alone SHS 4 | TANAY | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109459 | Quisao ES | PILILLA | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0615S00038 | 15DO0116 | 2015-12-24 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109442 | San Guillermo Elementary School | MORONG | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0615S00027 | 15DO0063 | 2015-10-06 | 2015-10-09 | 2015-10-22 | 2015-10-30 | 2015-11-11 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 109494 | San Mateo ES | SAN MATEO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0615S00037 | 15DO0062 | 2015-10-06 | 2015-10-09 | 2015-10-22 | 2015-10-27 | 2015-11-11 | R.F. DIAZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 308135 | Southville 8C NHS | RODRIGUEZ (MONTALBAN) | 2 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 7 | 26702469 |  |  | Reverted | 0 |  |  | 4A0615S00043 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 308128 | TANAY EAST NATIONAL HIGH SCHOOL | TANAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Reverted | 0 |  |  | 4A0615S00015 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 308141 | Tanay North NHS | TANAY | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 7 | 4572048 |  |  | Completed | 1 |  |  | 4A0615S00042 | 15DO0118 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 308138 | Tanay West NHS | TANAY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | Completed | 1 |  |  | 4A0615S00016 | 15DO0108 | 2015-12-02 | 2015-12-01 | 2015-12-18 |  |  | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 301467 | Teresa NHS | TERESA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | RIZAL | 301468 | Tuna-Balibago NHS | CARDONA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0615S00003 | 15DO0055 | 2015-07-21 | 2015-07-23 | 2015-08-05 | 2015-08-13 | 2015-08-26 | C.P.F. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | San Pablo City | 301505 | Col. Lauro D. Dizon Memorial National High School | SAN PABLO CITY | 3 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 7 | 26702469 |  |  | Completed | 1 |  |  | 4A0415S00091 | 15DP0097 | 2015-10-28 | 2015-10-30 | 2015-11-12 | 2015-11-21 | 2015-11-25 | STO. CRISTO CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | San Pablo City | 301508 | San Bartolome National High School | SAN PABLO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | Completed | 1 |  |  | 4A0415S00092 | 15DP0094 | 2015-10-28 | 2015-10-30 | 2015-11-12 | 2015-11-21 | 2015-11-25 | STO. CRISTO CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | San Pablo City | 301503 | San Cristobal National High School | SAN PABLO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | Completed | 1 |  |  | 4A0415S00093 | 15DP0095 | 2015-10-28 | 2015-10-30 | 2015-11-12 | 2015-11-21 | 2015-11-25 | NEW RICH GENERAL CONTRACTOR SERVICES & TRADING Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | San Pablo City | 308605 | San Pablo City Science High School | SAN PABLO CITY | 3 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15196327.92 |  |  | Completed | 1 |  |  | 4A0415S00059 | 15DP0081 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | STO. CRISTO CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2015 | REGION IV-A | Sta. Rosa City | 301224 | Aplaya NHS | CITY OF SANTA ROSA | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | Completed | 1 |  |  |  | 15DI0146 | 2015-11-13 | 2015-11-19 | 2015-12-02 | 2015-12-09 | 2015-12-15 | JUNCAN ENTERPRISES | No Remarks | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2015 | REGION IV-A | Sta. Rosa City | 108473 | Dita Elementary School | CITY OF SANTA ROSA | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0415S00089 | 15IDI0176 | 2015-10-30 | 2015-11-05 | 2015-11-18 | 2015-11-25 | 2015-12-04 | 11 DIAMOND EAGLE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | Sta. Rosa City | 108477 | Macabling Elementary School | CITY OF SANTA ROSA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Completed | 1 |  |  | 4A0415S00088 | 15IDI0177 | 2015-10-30 | 2015-11-05 | 2015-11-18 | 2015-11-25 | 2015-12-04 | LAKE CITY BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | TANAUAN CITY | 301089 | Boot NHS | CITY OF TANAUAN | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14927518.84 |  |  | Completed | 1 |  |  | 4A0215S00035 | 4A02-15-S-00035 | [5 empty] | EDRES CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2015 | REGION IV-A | TANAUAN CITY | 301133 | Pantay NHS | CITY OF TANAUAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8264965 |  |  | Completed | 1 |  |  | 4A0215S00051 | 15DC0109 | 2015-10-01 | 2015-10-13 | 2015-10-14 |  |  | EDRES CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2015 | REGION IV-A | TANAUAN CITY | 321601 | Tanauan City HS | CITY OF TANAUAN | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26732469.42 |  |  | Completed | 1 |  |  | 4A0215S00034 | 15DC0102 | 2015-10-01 | 2015-10-13 | 2015-10-14 |  |  | MICLOVER GENERAL CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | TANAUAN CITY | 301154 | Tanuan School of Fisheries | CITY OF TANAUAN | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26772469.42 |  |  | Completed | 1 |  |  | 4A0215S00032 | 15DC0103 | 2015-10-01 | 2015-10-13 | 2015-10-14 |  |  | MICLOVER GENERAL CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2015 | REGION IV-A | TAYABAS CITY | 109253 | Ipilan-Alitao ES | CITY OF TAYABAS | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0515S00085 | 15DK0104 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | F. JIMENEZ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION IV-A | TAYABAS CITY |  | Proposed SHS 1 | Tayabas City | 1 | 1 | 40 | 4STY20CL | 2015 SHS BATCH 5 | 62205781 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2015 | REGION IV-A | TAYABAS CITY | 308036 | Quezon Science High School | CITY OF TAYABAS | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | Completed | 1 |  |  | 4A0515S00021 | 15DK0062 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-07-31 | 2015-08-13 | BOMEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2015 | REGION IV-A | TAYABAS CITY | 109260 | Tayabas West Central School II | CITY OF TAYABAS | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Completed | 1 |  |  | 4A0515S00086 | 15DK0105 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | ANNCON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION IV-A | ANTIPOLO CITY | 301422 | Mayamot NHS | CITY OF ANTIPOLO | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | ANTIPOLO CITY | 301423 | Muntindilaw NHS | CITY OF ANTIPOLO | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15497518.84 |  |  | Completed | 1 | 2016-03-13 |  | 4A0614S00022 | 15DN0099 | 2015-09-10 | 2015-09-10 | 2015-09-23 | 2015-10-06 | 2015-10-16 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | ANTIPOLO CITY | 321501 | Marcelino M. Santos NHS | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | 2016-04-04 |  | 4A0614S00024 | 15DN0098 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-12 | RCM CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | ANTIPOLO CITY | 308101 | Maximo L. Gatlabayan MNHS - Boso-boso Extension | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | 2016-04-04 |  | 4A0614S00033 | 15DN0097 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-12 | RCM CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | ANTIPOLO CITY | 321504 | Maximo L. Gatlabayan MNHS - Rizza Extension | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15397518.84 |  |  | Completed | 1 | 2016-04-23 |  | 4A0614S00034 | 15DN0108 | 2015-09-16 | 2015-09-16 | 2015-09-29 | 2015-10-13 | 2015-10-26 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | BATANGAS CITY | 301470 | Balete NHS | BATANGAS CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14967518.84 |  |  | Completed | 1 | 2016-01-06 |  | 4A0214S00124 | 15DE0053 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | BERTO LUCCI BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | BATANGAS CITY | 301473 | Conde Labac NHS | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6389337.6381 |  |  | Completed | 1 | 2015-12-12 | 2015-12-12 | 4A0214S00123 | 15DE0049 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | 6 JEWELS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | BATANGAS CITY | 308201 | Natalia V. Ramos Memorial National High School | BATANGAS CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14967518.84 |  |  | Completed | 1 | 2016-01-06 |  | 4A0214S00122 | 15DE0054 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | JV: OIC CONSTRUCTION & SUPPLY(FORMERLY:OIC CONST.)/NBL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | BATANGAS CITY | 301474 | Paharang NHS | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6389337.6381 |  |  | Completed | 1 | 2015-12-12 | 2015-12-12 | 4A0214S00121 | 15DE0050 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | 6 JEWELS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | BATANGAS CITY | 301475 | Pedro S. Tolentino MNHS | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | Completed | 1 | 2015-12-11 | 2015-12-11 | 4A0214S00120 | 15DE0052 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | SANDSTORM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | BATANGAS CITY | 301476 | Pinamukan NHS | BATANGAS CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15017518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | BATANGAS CITY | 301481 | Tabangao NHS | BATANGAS CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14967518.84 |  |  | Completed | 1 | 2016-01-17 |  | 4A0214S00117 | 15DE0055 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | JASMIG CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | BATANGAS CITY | 308202 | Tinga Sorosoro National High School (TISISI) | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6389337.6381 |  |  | Completed | 1 | 2015-12-11 | 2015-12-11 | 4A0214S00126 | 15DE0051 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | 6 JEWELS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | Calamba City | 301515 | Calamba National High School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | 2016-01-01 |  | 4A0414S00034 | 15DI0066 | 2015-06-03 | 2015-06-09 | 2015-06-10 | 2015-06-22 | 2015-06-26 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | CAVITE | 301202 | Lumil NHS | SILANG | 5 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | Completed | 1 | 2016-03-14 |  | 4A0314S00088 | 15DG0050 | 2015-07-02 | 2015-07-14 | 2015-07-22 | 2015-07-31 | 2015-08-18 | ALMAKAR BUILDERS & METAL WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | REGION IV-A | CAVITE | 307808 | Francisco Osorio NHS (Trece Martires City NHS (Osorio Annex)) | TRECE MARTIRES CITY (Capital) | 6 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | 2016-04-18 |  | 4A0314S00089 | 15DF0058 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-03 | 2015-08-12 | BAQPRINCE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | CAVITE | 301165 | Alfonso NHS | ALFONSO | 8 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | 2016-01-05 |  | 4A0314S00090 | 15DG0059 | 2015-07-27 | 2015-08-08 | 2015-08-18 | 2015-08-28 | 2015-09-08 | HAUSLAND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | REGION IV-A | CAVITE | 301173 | Bendita NHS | MAGALLANES | 8 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | 2016-02-13 |  | 4A0314S00091 | 15DG0049 | 2015-07-02 | 2015-07-14 | 2015-07-22 | 2015-08-03 | 2015-08-13 | HAUSLAND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | CAVITE | 301178 | Cavite Nat'l. Science HS | MARAGONDON | 8 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | 2016-01-03 |  | 4A0314S00092 | 15DG0045 | 2015-06-19 | 2015-07-04 | 2015-07-09 | 2015-07-29 | 2015-08-06 | N.B. AVILA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | CAVITE | 301198 | Kaytitinga NHS | ALFONSO | 8 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15097518.84 |  |  | Completed | 1 | 2016-02-02 |  | 4A0314S00093 | 15DG0048 | 2015-06-22 | 2015-07-04 | 2015-07-09 | 2015-07-21 | 2015-08-06 | HAUSLAND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | CAVITE | 301200 | Lumampong NHS | INDANG | 7 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | 2016-01-03 |  | 4A0314S00095 | 15DG0044 | 2015-06-19 | 2015-07-04 | 2015-07-09 | 2015-07-27 | 2015-08-07 | ALMAKAR BUILDERS & METAL WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | CAVITE | 301221 | Ternate NHS | TERNATE | 8 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | Completed | 1 | 2016-03-03 |  | 4A0314S00086 | 15DG0047 | 2015-06-22 | 2015-07-04 | 2015-07-09 | 2015-07-21 | 2015-08-06 | OMNICON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | REGION IV-A | CITY OF BIÑAN | 301230 | Biñan National High School | CITY OF BIÑAN | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0414S00039 | 15DI0182 | [5 empty] | MICLOVER GENERAL CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | Dasmarinas City | 301183 | Dasmarinas East NHS (Annex C) | CITY OF DASMARIÑAS | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | [9 empty] | J.S. General Contractor |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | REGION IV-A | Laguna | 307907 | San Pedro Relocation Center National High School, Main (Langgam) Campus | SAN PEDRO | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10617131.51 |  |  | Completed | 1 |  |  | 4A0414S00033 | 15DI0183 | [5 empty] | MAR-VEL CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | Laguna | 301234 | Cabuyao NHS | CABUYAO | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10467131.51 |  |  | Completed | 1 | 2016-02-05 |  | 4A0414S00040 | 15DI0122 | 2015-09-18 | 2015-09-30 | 2015-10-01 | 2015-10-05 | 2015-10-09 | POWER K CONSTRUCTION SUPPLY & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | Laguna | 301262 | Nicolas L. Galvez Mem. NHS (San Antonio NHS) | BAY | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 |  |  | 4A0414S00042 | 15DI0184 | [5 empty] | PROTECH CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | Laguna | 301244 | Liliw National High School | LILIW | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10667131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | Laguna | 301226 | Balian NHS | PANGIL | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10467131.51 |  |  | Completed | 1 | 2016-03-31 |  | 4A0414S00044 | 15DH0050 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | MAR-VEL CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | Laguna | 301279 | Lumban NHS | LUMBAN | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | 2016-03-31 |  | 4A0414S00045 | 15DH0051 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | MAR-VEL CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | Laguna | 301273 | Siniloan NHS | SINILOAN | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10617131.51 |  |  | Completed | 1 | 2016-03-31 |  | 4A0414S00046 | 15DH0052 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | MAR-VEL CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | LUCENA CITY | 308502 | Cotta National High School | LUCENA CITY (Capital) | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | Completed | 1 | 2016-04-15 |  | 4A0514S00163 | 15DJ0050 | 2015-06-28 | 2015-06-29 | 2015-07-14 | 2015-07-21 | 2015-07-24 | JEMAK CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | LUCENA CITY | 308504 | Gulang-Gulang NHS - Iba. Talim Ext. | LUCENA CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-12-25 |  | 4A0514S00164 | 15DJ0026 | 2015-05-26 | 2015-05-27 | 2015-06-09 | 2015-06-17 | 2015-06-22 | R.T.Y. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 500028 | BinulAsan IS | INFANTA | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | 2016-03-02 | March 01, 2016 | 4A0514S00111 | 15DK0068 | 2015-07-24 | 2015-07-29 | 2015-08-11 | 2015-08-14 | 2015-09-04 | PRECIOUS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301334 | Burdeos NHS (Judith NHS) | BURDEOS | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | February 12, 2016 | February 12, 2016 | 4A0514S00099 | 15DK0075 | August 05, 2015 | August 07, 2015 | August 24, 2014 | September 03, 2015 | September 16, 2015 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301301 | Cagbalete Island NHS | MAUBAN | 1 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | Completed | 1 | 2015-10-28 | 2015-10-28 | 4A0514S00140 | 15DK0051 | 2015-06-24 | 2015-06-25 | 2015-07-09 | 2015-07-20 | 2015-07-31 | E.A. AYALA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 308005 | Cagsiay I NHS | MAUBAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | Completed | 1 | 2015-12-10 | 2015-12-10 | 4A0514S00100 | 15DK0057 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-07-31 | 2015-08-13 | BOMEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301319 | Dr. Maria D. Pastrana National High School | MAUBAN | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | May 17, 2016 | August 15, 2016 | 4A0514S00165 | 15DK0069 | October 8, 2015 | October 16, 2015 | October 30, 2015 | November 10, 2015 | November 20, 2015 | C.J. CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301332 | Infanta NHS | INFANTA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | Completed | 1 | February 12, 2016 | February 12, 2016 | 4A0514S00102 | 15DK0076 | July 29, 2015 | August 07, 2015 | August 24, 2014 | September 03, 2015 | September 16, 2015 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301344 | Libo NHS | PANUKULAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6669337.6381 |  |  | Completed | 1 | 2015-12-17 | 2015-12-17 | 4A0514S00103 | 15DK0056 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-08-07 | 2015-08-20 | ZELAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 308007 | Liwayway NHS | MAUBAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | Completed | 1 | 2016-01-16 | December 17, 2015 | 4A0514S00104 | 15DK0058 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-08-07 | 2015-08-20 | BOMEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301350 | Manuel S. Enverga Memorial School of Arts and Trades | MAUBAN | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | February 18, 2016 | April 18, 2016 | 4A0514S00196 | 15DK0070 | October 8, 2015 | October 16, 2015 | October 30, 2015 | November 10, 2015 | November 20, 2015 | C.J. CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301361 | Paaralang Sek. Ng Hen. Nakar | GENERAL NAKAR | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10567131.51 |  |  | Completed | 1 | 2016-03-02 | March 01, 2016 | 4A0514S00106 | 15DK0071 | 2015-07-24 | 2015-07-29 | 2015-08-11 | 2015-08-19 | 2015-09-04 | W.J. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301363 | Paaralang Sek. Ng Hen. Nakar - Umiray Extension | GENERAL NAKAR | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-09-28 | 2015-09-28 | 4A0514S00098 | 15DK0052 | 2015-06-24 | 2015-06-25 | 2015-07-09 | 2015-07-17 | 2015-07-31 | E.A. AYALA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301364 | Paaralang Sek. Ng Lukban | LUCBAN | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | 2016-06-08 |  | 4A0514S00108 | 15DK0080 | 2015-09-03 | 2015-09-03 | 2015-09-22 | 2015-09-30 | 2015-10-12 | BCVILLASENOR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301367 | Pagbilao Grande Island NHS | PAGBILAO | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10517131.51 |  |  | Completed | 1 | 2016-03-02 | March 01, 2016 | 4A0514S00093 | 15DK0072 | 2015-07-24 | 2015-07-29 | 2015-08-11 | 2015-08-24 | 2015-09-04 | W.J. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 308004 | Pagbilao NHS | PAGBILAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-02-12 | February 12, 2016 | 4A0514S00110 | 15DK0077 | 2015-08-05 | 2015-08-07 | 2015-08-24 | 2015-09-03 | 2015-09-16 | SOUTH BUILDERS & CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301374 | Patnanungan NHS | PATNANUNGAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-02-12 | March 13, 2016 | 4A0514S00105 | 15DK0078 | 2015-08-05 | 2015-08-07 | 2015-08-20 | 2015-09-03 | 2015-09-16 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301377 | Polillo NHS | POLILLO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-03-10 | March 09, 2016 | 4A0514S00112 | 15DK0109 | 2015-09-03 | 2015-09-03 | 2015-09-22 | 2015-09-30 | 2015-10-12 | SARCA ESTATE DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301384 | Sampaloc NHS, Sampaloc | SAMPALOC | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-09-28 | 2015-09-28 | 4A0514S00113 | 15DK0053 | 2015-06-24 | 2015-06-25 | 2015-07-09 | 2015-07-17 | 2015-07-31 | E.A. AYALA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 308030 | Silangang Malicboy NHS | PAGBILAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-02-12 | February 12, 2016 | 4A0514S00114 | 15DK0079 | 2015-08-05 | 2015-08-07 | 2015-08-24 | 2015-09-03 | 2015-09-16 | SOUTH BUILDERS & CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301407 | Talipan NHS | PAGBILAO | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | 2016-03-02 | March 01, 2016 | 4A0514S00107 | 15DK0073 | 2015-07-24 | 2015-07-29 | 2015-08-11 | 2015-08-19 | 2015-09-04 | ALT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301410 | Tongohin NHS | INFANTA | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | March 01, 2016 | March 01, 2016 | 4A0514S00091 | 15DK0074 | July 17, 2015 | July 29, 2015 | August 11, 2015 | August 24, 2015 | September 04, 2015 | SARCA ESTATE DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301299 | Cabay NHS | TIAONG | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | Completed | 1 | 2016-03-15 |  | 4A0514S00086 | 15DJ0029 | 2015-05-31 | 2015-06-02 | 2015-06-16 | 2015-06-23 | 2015-06-29 | MGDJ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301305 | Callejon NHS | SAN ANTONIO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301308 | Canda NHS | SARIAYA | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 308019 | Dr. Panfilo Castro NHS (Formerly Bukal Sur NHS-Mangilag Annex) | CANDELARIA | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | 2016-03-05 |  | 4A0514S00101 | 15DJ0047 | 2015-06-22 | 2015-06-24 | 2015-07-07 | 2015-07-14 | 2015-07-16 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 308020 | Governor Anacleto C. Alcala NHS | SARIAYA | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | Completed | 1 | 2016-02-05 |  | 4A0514S00137 | 15DJ0053 | 2015-07-01 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-28 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301348 | Lusacan NHS | TIAONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-02-03 |  | 4A0514S00136 | 15DJ0041 | 2015-06-08 | 2015-06-10 | 2015-06-23 | 2015-06-30 | 2015-07-03 | M.G. VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301349 | Lutucan NHS | SARIAYA | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301370 | Paiisa NHS | TIAONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-01-25 |  | 4A0514S00134 | 15DJ0037 | 2015-06-03 | 2015-06-04 | 2015-06-18 | 2015-06-25 | 2015-06-30 | M.G. VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301380 | Recto MNHS | TIAONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301385 | San Antonio NHS | SAN ANTONIO | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | 2016-03-25 |  | 4A0514S00132 | 15DJ0027 | 2015-05-26 | 2015-05-27 | 2015-06-09 | 2015-06-17 | 2015-06-22 | JOJR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301403 | Sta. Catalina NHS | CANDELARIA | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | 2016-04-15 |  | 4A0514S00131 | 15DJ0042 | 2015-06-14 | 2015-06-17 | 2015-06-30 | 2015-07-07 | 2015-07-10 | L.A. CLAMOR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301318 | Sta. Lucia NHS (Formerly Dagatan NHS Annex - Sta. Lucia) | DOLORES | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | Completed | 1 | 2016-03-23 |  | 4A0514S00130 | 15DJ0049 | 2015-06-28 | 2015-06-29 | 2015-07-14 | 2015-07-21 | 2015-07-24 | E.A. AYALA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301285 | Amontay NHS | PITOGO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301295 | Bondoc Peninsula Agri. HS | MULANAY | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2015-12-28 | 2015-12-28 | 4A0514S00116 | 15DM0063 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-02 | M.G. VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301303 | Calantas NHS | MACALELON | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-10-12 | 2015-09-12 | 4A0514S00127 | 15DM0045 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-15 | RAPID FOREMOST CONST. CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 308024 | Camflora National High School (Annex) | SAN ANDRES | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | Completed | 1 | 2015-10-20 | 2015-09-20 | 4A0514S00138 | 15DM0046 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-06-23 | JSP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301306 | Camflora NHS | SAN ANDRES | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301309 | Casay NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6569337.6381 |  |  | Completed | 1 | 2015-11-28 | 2015-11-28 | 4A0514S00124 | 15DM0066 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301310 | Catanauan National High School | CATANAUAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-01-10 |  | 4A0514S00123 | 15DM0060 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-15 | RGP BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 308023 | Danlagan NHS (Formerly Kinagunan Ibaba NHS Ext. Classes) | PADRE BURGOS | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | Completed | 1 | 2015-10-15 | 2015-09-15 | 4A0514S00122 | 15DM0047 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-06-18 | DEMALARAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301311 | Doongan Ilaya NHS (Formerly Catanauan NHS - Doongan Ilaya Ext.) | CATANAUAN | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2790828.124 |  |  | Completed | 1 | 2015-10-15 | 2015-09-15 | 4A0514S00121 | 15DM0048 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-06-18 | JOJR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301321 | Elias A. Salvador NHS | AGDANGAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-01-10 |  | 4A0514S00120 | 15DM0055 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-15 | ZELAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301399 | Godofredo M. Tan Mem. SAT (Formerly San Narciso Voc. HS) | SAN NARCISO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 308006 | Hagonghong Integrated HS | BUENAVISTA | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2715828.124 |  |  | Completed | 1 | 2015-09-29 | 2015-09-29 | 4A0514S00118 | 15DM0049 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-02 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301326 | Hinguiwin NHS | PADRE BURGOS | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | 2016-05-13 |  | 4A0514S00117 | 15DM0077 | 2015-07-18 | 2015-07-27 | 2015-07-31 | 2015-08-05 | 2015-08-18 | ALT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301329 | Ilayang Yuni NHS | MULANAY | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301390 | Marcial B. Villanueva NHS (Formerly San Francisco NHS, San Francisco) | SAN FRANCISCO (AURORA) | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-01-27 |  | 4A0514S00151 | 15DM0067 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 308001 | Matandang Sabang NHS | CATANAUAN | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | Completed | 1 | 2015-09-29 | 2015-09-29 | 4A0514S00128 | 15DM0050 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301360 | Olongtao NHS | MACALELON | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2015-12-26 | 2015-12-26 | 4A0514S00160 | 15DM0058 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-01 | SOUTH BUILDERS & CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301369 | Pagsangahan NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | Completed | 1 | 2015-11-28 | 2015-11-28 | 4A0514S00159 | 15DM0068 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301373 | Patabog NHS | MULANAY | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301379 | Pugon NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-10-29 | 2015-09-29 | 4A0514S00157 | 15DM0051 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-02 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301391 | San Isidro NHS, Catanauan | CATANAUAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301393 | San Isidro NHS, Gen. Luna | GENERAL LUNA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301394 | San Isidro NHS, Padre Burgos | PADRE BURGOS | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-10-23 | 2015-10-23 | 4A0514S00154 | 15DM0052 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-01 | A.V. CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301401 | San Roque NHS, Catanauan | CATANAUAN | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | Completed | 1 | 2015-12-11 | 2015-12-11 | 4A0514S00153 | 15DM0062 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-15 | RAPID FOREMOST CONST. CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301312 | Tagbacan NHS (Formerly Tagbacan Ilaya IS) | CATANAUAN | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301409 | Tayuman National High School | SAN FRANCISCO (AURORA) | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-10-10 | 2015-08-15 | 4A0514S00139 | 15DM0054 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-13 | RAPID FOREMOST CONST. CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301414 | Unisan NHS | UNISAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-01-04 |  | 4A0514S00150 | 15DM0056 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-09 | RGP BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301284 | Alabat Island NHS | ALABAT | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301286 | Atimonan NCHS | ATIMONAN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301291 | Bantulinao IS | CALAUAG | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | Completed | 1 | 2015-11-01 | 2015-11-01 | 4A0514S00147 | 15-DL-0077 | 2015-05-24 | 2015-05-28 | 2015-06-06 | 2015-06-12 | 2015-06-29 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301304 | Calauag NHS | CALAUAG | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | Completed | 1 | 2016-01-01 |  | 4A0514S00146 | 15-DL-0076 | 2015-05-27 | 2015-06-10 | 2015-06-11 | 2015-06-18 | 2015-06-29 | T.A.D. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301346 | Cogorin Ibaba NHS (Formerly Lopez NCHSl - Cogorin Ibaba Extension) | LOPEZ | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2865828.124 |  |  | Completed | 1 | 2016-01-01 |  | 4A0514S00145 | 15-DL-0079 | 2015-05-27 | 2015-06-09 | 2015-06-10 | 2015-06-17 | 2015-06-29 | ZELAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301314 | Cometa NHS Annex | QUEZON | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | Completed | 1 | 2015-12-30 | 2015-12-30 | 4A0514S00144 | 15-DL-0089 | 2015-06-03 | 2015-06-16 | 2015-06-17 | 2015-06-20 | 2015-06-29 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301323 | Guinayangan NHS | GUINAYANGAN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | Completed | 1 | 2016-01-05 |  | 4A0514S00143 | 15DL0134 | 2015-08-29 | 2015-09-03 | 2015-09-04 | 2015-09-08 | 2015-09-15 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301325 | Gumaca National High School | GUMACA | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-01-10 |  | 4A0514S00142 | 15-DL-0092 | 2015-06-09 | 2015-06-15 | 2015-06-30 | 2015-07-04 | 2015-07-13 | ZELAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301327 | Hondagua NHS | LOPEZ | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-01-30 |  | 4A0514S00141 | 15-DL-0083 | 2015-05-27 | 2015-06-08 | 2015-06-09 | 2015-06-13 | 2015-06-29 | T.A.D. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301340 | Lamon Bay SOF - Main Gumaca | GUMACA | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | Completed | 1 | 2016-01-30 |  | 4A0514S00109 | 15-DL-0087 | 2015-06-03 | 2015-06-15 | 2015-06-16 | 2015-06-22 | 2015-06-29 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301345 | Lopez National Comprehensive High School | LOPEZ | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-01-10 |  | 4A0514S00161 | 15-DL-0090 | 2015-06-09 | 2015-06-22 | 2015-06-23 | 2015-06-27 | 2015-07-13 | ZELAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301351 | Magallanes NHS | LOPEZ | 4 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3464886.575 |  |  | Completed | 1 | 2016-01-08 |  | 4A0514S00126 | 15-DL-0080 | 2015-05-27 | 2015-06-02 | 2015-06-03 | 2015-06-11 | 2015-06-16 | R.C. TAGALA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301357 | Malusak NHS | ATIMONAN | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | Completed | 1 | 2015-11-30 | 2015-11-30 | 4A0514S00096 | 15-DL-0084 | 2015-05-28 | 2015-06-09 | 2015-06-10 | 2015-06-16 | 2015-06-29 | R.C. TAGALA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301359 | Nabangka NHS | GUINAYANGAN | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | Completed | 1 | 2015-12-30 | 2015-12-30 | 4A0514S00095 | 15-DL-0085 | 2015-05-28 | 2015-06-09 | 2015-06-10 | 2015-06-14 | 2015-06-29 | ZELAN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 308009 | Pamampangin NHS | LOPEZ | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2016-01-08 |  | 4A0514S00094 | 15-DL-0081 | 2015-05-27 | 2015-06-08 | 2015-06-09 | 2015-06-13 | 2015-06-16 | R.C. TAGALA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301372 | Panikihan NHS | GUMACA | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | Completed | 1 | 2016-01-10 |  | 4A0514S00085 | 15-DL-0091 | 2015-06-09 | 2015-06-15 | 2015-06-30 | 2015-07-03 | 2015-07-13 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301386 | San Francisco B NHS | LOPEZ | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2715828.124 |  |  | Completed | 1 | 2016-01-08 |  | 4A0514S00092 | 15-DL-0082 | 2015-05-27 | 2015-06-08 | 2015-06-09 | 2015-06-13 | 2015-06-16 | R.C. TAGALA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301402 | San Roque-Ilaya NHS, Calauag | CALAUAG | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | Completed | 1 | 2016-01-30 |  | 4A0514S00089 | 15-DL-0088 | 2015-06-03 | 2015-06-15 | 2015-06-16 | 2015-06-20 | 2015-06-29 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301404 | Sto. Domingo NHS | CALAUAG | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-01-23 |  | 4A0514S00088 | 15-DL-0078 | 2015-05-24 | 2015-06-05 | 2015-06-06 | 2015-06-10 | 2015-06-22 | T.A.D. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | QUEZON | 301406 | Tagkawayan NHS | TAGKAWAYAN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2015-12-30 | 2015-12-30 | 4A0514S00087 | 15-DL-0074 | 2015-05-21 | 2015-06-02 | 2015-06-03 | 2015-06-07 | 2015-06-22 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 301417 | Angono NHS | ANGONO | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 |  |  | 4A0614S00031 | 15DN0095 | 2015-09-02 | 2015-09-02 | 2015-09-15 | 2015-09-25 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 301469 | Vicente Madrigal NHS | BINANGONAN | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 308103 | Abuyod NHS | TERESA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-01-22 |  | 4A0614S00029 | 15DO0048 | 2015-07-14 | 2015-07-16 | 2015-07-29 | 2015-08-13 | 2015-08-26 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 301428 | Bagumbong NHS | JALA-JALA | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | Completed | 1 | 2015-12-23 | 2015-12-23 | 4A0614S00028 | 15DO0053 | 2015-07-21 | 2015-07-23 | 2015-08-05 | 2015-08-13 | 2015-08-26 | STEVEN CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 301430 | Bayugo NHS | JALA-JALA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-01-22 |  | 4A0614S00027 | 15DO0049 | 2015-07-14 | 2015-07-16 | 2015-07-29 | 2015-08-13 | 2015-08-26 | STEVEN CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 301432 | Bernardo F. San Juan NHS | CARDONA | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 308132 | Bugarin NHS | PILILLA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-10-03 | 2015-10-03 | 4A0614S00025 | 15DO0041 | 2015-07-06 | 2015-07-09 | 2015-07-21 | 2015-07-28 | 2015-08-05 | JRD-D2 ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 301434 | Catalino D. Salazar NHS | CARDONA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-02-20 |  | 4A0614S00015 | 15DO0050 | 2015-07-14 | 2015-07-16 | 2015-07-29 | 2015-08-13 | 2015-08-26 | EL KAPITAN CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 308133 | Laiban NHS | TANAY | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-10-03 | 2015-10-03 | 4A0614S00023 | 15DO0040 | 2015-07-06 | 2015-07-09 | 2015-07-21 | 2015-07-28 | 2015-08-05 | JRD-D2 ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 301454 | Quisao NHS | PILILLA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | 2016-01-22 |  | 4A0614S00020 | 15DO0046 | 2015-07-14 | 2015-07-16 | 2015-07-29 | 2015-08-13 | 2015-08-26 | NEW RICH GENERAL CONTRACTOR SERVICES & TRADING Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 301456 | Sampaloc NHS | TANAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 301462 | Silangan NHS | SAN MATEO | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | 2016-02-21 |  | 4A0614S00018 | 15DO0052 | 2015-07-14 | 2015-07-16 | 2015-07-29 | 2015-08-13 | 2015-08-26 | MEGASTRUCTURE BUILDER & TRADING CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | RIZAL | 301461 | Sto. Niño NHS | TANAY | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-10-03 | 2015-10-03 | 4A0614S00016 | 15DO0039 | 2015-07-06 | 2015-07-09 | 2015-07-21 | 2015-07-28 | 2015-08-05 | JRD-D2 ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION IV-A | San Pablo City | 308602 | San Jose National High School | SAN PABLO CITY | 3 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15171327.92 |  |  | Completed | 1 | 2016-04-18 | 2016-04-17 | 4A0414S00035 | 15DP0068 | 2015-08-13 | 2015-08-13 | 2015-08-26 | 2015-09-13 | 2015-09-21 | DSO ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | REGION IV-A | San Pablo City | 301509 | Santisimo Rosario National High School | SAN PABLO CITY | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10517131.51 |  |  | Completed | 1 | 2016-03-19 | 2016-04-02 | 4A0414S00036 | 15DP0069 | 2015-08-13 | 2015-08-13 | 2015-08-26 | 2015-09-13 | 2015-09-21 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2014 | REGION IV-A | Sta. Rosa City | 301227 | Balibago National High School | CITY OF SANTA ROSA | 1 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | Completed | 1 | 2016-06-28 | Decemeber 20, 2016 | 4A0414S00037 | 15DI0187 | 2015-06-10 | 2015-06-15 | 2015-06-29 | 2016-11-25 | 2016-01-31 | HEXAMINDS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2014 | REGION IV-A | Sta. Rosa City | 301239 | Don Jose NHS | CITY OF SANTA ROSA | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Completed | 1 | 2016-01-01 |  | 4A0414S00038 | 15DI0065 | 2015-06-02 | 2015-06-09 | 2015-06-10 | 2015-06-22 | 2015-06-26 | MAR-VEL CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2014 | REGION IV-A | Sta. Rosa City | 307902 | Sta. Rosa Science & Technology HS | CITY OF SANTA ROSA | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Completed | 1 | 2016-01-09 |  | 4A0414S00047 | 15DI0077 | 2015-06-16 | 2015-06-25 | 2015-06-29 | 2015-07-10 | 2015-07-14 | L.P.O. ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2014 | REGION IV-A | Sta. Rosa City | 301272 | Sto. Domingo National High School | CITY OF SANTA ROSA | 1 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | Completed | 1 | 2016-02-11 |  | 4A0414S00041 | 15DI0112 | 2015-08-12 | 2015-08-24 | 2015-08-26 | 2015-09-11 | 2015-09-15 | MAR-VEL CONSTRUCTION & SUPPLY | no remarks | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.