## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2 | Unnamed: 43 | Status as of July 4, 2025
ELECTRIFICATION 2017 | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High school | CITY OF CALAPAN (Capital) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 402289.69 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Marinduque | 169005 | Sinambahan PS | TORRIJOS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 205929.74 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | REVERTED
ELECTRIFICATION 2017 | Region IV-B | Occidental Mindoro | 110086 | Layaban Min. Sch. | CALINTAAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 292608.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Occidental Mindoro | 110166 | Karyandangan Min. School | MAMBURAO (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 264530.17 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Occidental Mindoro | 110175 | Pola Min. Sch. | MAMBURAO (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 259843.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Occidental Mindoro | 110191 | Tuguilan Min. Sch. | MAMBURAO (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 373145.16 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Occidental Mindoro | 110316 | Yawi-Yawi II PS | SAN JOSE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 361588.04 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110544 | MALINAO ELEMENTARY SCHOOL | NAUJAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 222965.53 | 222644.72 | COMPLETED | 1 | May 31, 2018 | May 28, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 062-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 301627 | DOMINGO YU CHU NATIONAL HIGH SCHOOL | POLA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1259439.16 | 1249794.2 | COMPLETED | 1 | May 31, 2018 | May 28, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 062-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 301634 | LEUTEBORO NATIONAL HIGH SCHOOL | SOCORRO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 645323.62 | 641648.42 | COMPLETED | 1 | May 31, 2018 | May 28, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 062-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110370 | BAGONG BAYAN CENTRAL SCHOOL | BONGABONG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 546247.31 | 545009.9 | COMPLETED | 1 | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110392 | CAMANTIGUE ELEMENTARY SCHOOL | BONGABONG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 444682.51 | 444418.36 | COMPLETED | 1 | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110391 | CASTOR F. SOLABO ELEMENTARY SCHOOL | BONGABONG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 507738.64 | 507738.64 | COMPLETED | 1 | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110382 | MORENTE ELEMENTARY SCHOOL | BONGABONG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 460639.07 | 460639.07 | COMPLETED | 1 | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110435 | BANUS ELEMENTARY SCHOOL | GLORIA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 480732.42 | 480183.75 | COMPLETED | 1 | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 309002 | PRESIDENT DIOSDADO MACAPAGAL MNHS | GLORIA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 723876.34 | 720010.25 | COMPLETED | 1 | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110478 | STA. MARIA ELEMENTARY SCHOOL | MANSALAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 331845.6616 | 331845.66 | COMPLETED | 1 | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110573 | INCLANAY ELEMENTARY SCHOOL | PINAMALAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 401469.4 | 400885.55 | COMPLETED | 1 | May 31, 2018 | May 28, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 062-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110559 | LUMAMBAYAN ELEMENTARY SCHOOL | PINAMALAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 410423.58 | 410229.59 | COMPLETED | 1 | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 301646 | PAMBISAN NATIONAL HIGH SCHOOL | PINAMALAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 874426.51 | 868065.61 | COMPLETED | 1 | May 31, 2018 | May 28, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 062-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110562 | PAPANDAYAN ELEMENTARY SCHOOL | PINAMALAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 699122.06 | 696696.05 | COMPLETED | 1 | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110564 | QUINABIGAN ELEMENTARY SCHOOL | PINAMALAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 498665.2 | 497890.51 | COMPLETED | 1 | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110631 | HAPPY VALLEY ELEMENTARY SCHOOL | ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 387643.91 | 387643.91 | COMPLETED | 1 | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110633 | LIBTONG ELEMENTARY SCHOOL | ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 372026.15 | 372026.15 | COMPLETED | 1 | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 301639 | MARCELO I. CABRERA VOCATIONAL HIGH SCHOOL | ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 866786.68 | 866786.68 | COMPLETED | 1 | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110645 | SAN RAFAEL ELEMENTARY SCHOOL | ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 456224.49 | 456224.49 | COMPLETED | 1 | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110649 | UYAO ELEMENTARY SCHOOL | ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 391381.72 | 391381.72 | COMPLETED | 1 | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 170533 | Calawit PS | BUSUANGA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 744618.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110965 | Calusa ES | CAGAYANCILLO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 348234.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110966 | Cawili Elementary School | CAGAYANCILLO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 342234.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110920 | Abud-Abod ES | CULION | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 415435.9 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110930 | Cabulihan ES | CULION | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 363584.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110933 | Canimango ES | CULION | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 395639.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110942 | Halsey ES | CULION | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 476354.92 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301667 | Barotuan NHS | EL NIDO (BACUIT) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1680000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301693 | El Nido NHS | EL NIDO (BACUIT) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1780000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 111025 | Lamoro ES | EL NIDO (BACUIT) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 279614.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301713 | New Ibajay NHS | EL NIDO (BACUIT) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1420000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility, No utility can provide in this area only Solar Power is the source of Energy in this Area. | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 111136 | Andres Soriano MES | ROXAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 910000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301705 | Magara School for Philippine Crafstmen | ROXAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1750000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 111155 | Maragoc ES | ROXAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 231510.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 170512 | Ramon Gacayan Elementary School | ROXAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 230019.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301731 | ROXAS NATIONAL COMPREHENSIVE HIGH SCHOOL | ROXAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1800000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301732 | San Jose (Roxas) NHS | ROXAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1640000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, Coop suggest Platform for 100 kVA | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301660 | Alimanguan NHS | SAN VICENTE | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1520000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301723 | Port Barton NHS | SAN VICENTE | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1430000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301738 | San Vicente NHS | SAN VICENTE | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1760000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301658 | Abongan NHS | TAYTAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1490000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301669 | Bato NHS | TAYTAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1520000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 309103 | Central Taytay NHS | TAYTAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1500000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan |  | Central Taytay Senior HS | TAYTAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1490000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, X'former Not Installed | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301703 | Liminangcong NHS | TAYTAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1500000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301659 | Aborlan NHS | ABORLAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1821855.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301701 | Isaub National High school | ABORLAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1674473.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301722 | Plaridel NHS | ABORLAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1821855.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, Not finished rewiring of Classroom | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 170556 | Tina PS | ABORLAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 502744.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301668 | Bataraza NHS | BATARAZA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2628689.896 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301730 | Rio Tuba NHS | BATARAZA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, Not yet finished installed of distribution line | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301671 | Brooke's Point NHS - Pangobilian NHS | BROOKE'S POINT | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301699 | GOV. ALFREDO ABUEG SR. NATIONAL TECHNOLOGY & VOCATIONAL MEMORIAL HIGH SCHOOL | BROOKE'S POINT | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, Adjustment of Pole due to New Construction | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301704 | Maasin NHS (Bernas NHS) | BROOKE'S POINT | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110884 | Mate ES | BROOKE'S POINT | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 168715.21 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110892 | Saraza ES | BROOKE'S POINT | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 196968.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301663 | Aramaywan NHS | NARRA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1418751.1081 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Relocation of Pole due to Road Widening | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301690 | Dumaguena NHS | NARRA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2000000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301710 | NARRA NHS | NARRA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, Relocation of Steel Pole due to New Construction | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301718 | Panacan NHS | NARRA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1666214.844 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301724 | Princess Urduja NHS | NARRA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301739 | Sandoval National High School | NARRA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 111107 | Magara ES | QUEZON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 194424.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 111118 | Pinaglabanan ES | QUEZON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 427669.95 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301726 | Quezon NHS | QUEZON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 3000000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301728 | Quezon-Panitian NHS | QUEZON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1418750.52 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301743 | Tagusao NHS | QUEZON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 438813.56 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301702 | J. P. Rizal NHS | RIZAL (MARCOS) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2628689.896 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, Rewiring of some Classroom | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 170567 | Rancho II PS | RIZAL (MARCOS) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 595235.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301657 | Abo-Abo NHS | SOFRONIO ESPAÑOLA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1821855.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301725 | Pulot National High School | SOFRONIO ESPAÑOLA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2722839.896 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301787 | Babuyan NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1560756.5353 | 1554389.1 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301779 | Bacungan NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1373645.9305 | 1366136.85 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 111474 | Bagong Bayan ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 377032.32 | 369942.77 | COMPLETED | 1 | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301780 | Bahile NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1224743.0953 | 1219441.76 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 111475 | Bualbualan ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 386899.49 | 379825.91 | COMPLETED | 1 | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301783 | Irawan NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1084304.2345 | 1075130.11 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301784 | Langogan National High School | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1284745.8793 | 1276994.46 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301788 | Luzviminda NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 488070.24 | 487128.72 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 171505 | Mabuhay PS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 295333.32 | 291228.44 | COMPLETED | 1 | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301785 | Macarascas NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1345563.3193 | 1339176.5 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301789 | Mangingisda NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1193587.5625 | 1186017.07 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301792 | Marcelino Abadiano Javarez National High School | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1526126.741 | 1518143.21 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 111490 | Napsan ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 457672.08 | 445810.72 | COMPLETED | 1 | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301786 | Napsan National High School | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1036069.4938 | 1028557.39 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301791 | Pto. Princesa City Nat. Sci. HS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1344217.7065 | 1337629.01 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301793 | San Jose NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1402395.6173 | 1395073.25 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301794 | San Miguel National High School | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1194273.3466 | 1400532.14 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301795 | San Rafael National High School | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1545008.2744 | 1193294.52 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301796 | Sicsican NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1291533.4441 | 1515931.36 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 111493 | Simpokan ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 458845.5 | 446705.74 | COMPLETED | 1 | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301790 | Sta. Lourdes NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1272309.3197 | 1264470.49 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City |  | Sta. Monica HS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1287640.1449 | 1284918.68 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 111496 | Sto. Niño ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 577862.51 | 563544.73 | COMPLETED | 1 | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 171503 | Tagbarungis ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 779958.37 | 761800.67 | COMPLETED | 1 | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City |  | Tagburos Annex | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1425145.3202 | 1280095.95 | COMPLETED | 1 | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Calapan City | 301798 | Canubing National High School | CITY OF CALAPAN (Capital) | 1 | 1 | UPGRADING | 1 | 415231.83 | 392996.4016 | COMPLETED | 1 | 10/25/2018 |  |  | 2018-18 | 07/17/2018 | 07/23/2018 | 08/06/2018 | 08/13/2018 | 08/22/2018 | ETVR TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Calapan City | 301802 | Nag-iba National High School | CITY OF CALAPAN (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 446113.47 | 423592.7535 | COMPLETED | 1 | 10/25/2018 |  |  | 2018-18 | 07/17/2018 | 07/23/2018 | 08/06/2018 | 08/13/2018 | 08/22/2018 | ETVR TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Marinduque | 109930 | Gaspar ES | GASAN | 0 | 1 | SOLAR PANEL | 1 | 897069.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Marinduque | 301557 | Mogpog NCHS | MOGPOG | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 437061.38 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | ENERGIZATION | REVERTED
ELECTRIFICATION 2018 | Region IV-B | Marinduque | 301558 | Mongpong NHS | SANTA CRUZ | 0 | 1 | SOLAR PANEL | 1 | 897069.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Marinduque | 301553 | Maranlig National High School | TORRIJOS | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 437061.38 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | ENERGIZATION | REVERTED
ELECTRIFICATION 2018 | Region IV-B | Marinduque | 301556 | Matuyatuya NHS | TORRIJOS | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 626955.35 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | ENERGIZATION | REVERTED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301583 | Looc National School Of Fisheries | LOOC | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 876671.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301605 | Sta Teresa NHS | MAGSAYSAY | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 562469.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301594 | Paluan NHS | PALUAN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 866324.22 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301595 | RIZAL NATIONAL HIGH SCHOOL | RIZAL | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 817030.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301582 | Paulino Legaspi, Sr. Memorial. NHS | SABLAYAN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 852498.82 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301600 | Central NHS | SAN JOSE | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 881194.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301589 | Magsaysay NHS - Mapaya Annex | SAN JOSE | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 849048.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 308908 | San Jose NAIHS - Mangarin Annex | SAN JOSE | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 562469.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 308901 | San Jose National Agricultural and Industrial High School | SAN JOSE | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 869277.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro |  | Pinagturilan NHS | SANTA CRUZ | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 824424.34 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro |  | Anastacio Dela Chica High School | BACO | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1517078.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 309004 | Puerto Galera NHS | PUERTO GALERA | 1 | 1 | UPGRADING | 1 | 631356.09 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 309035 | Puerto Galera NHS - San Isidro Ext. | PUERTO GALERA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 583660.05 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301653 | San Teodoro NHS | SAN TEODORO | 1 | 1 | UPGRADING | 1 | 1324535.19 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 309019 | Pag-asa NHS | BANSUD | 2 | 1 | UPGRADING | 2 | 747780.62 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301655 | Villapagasa NHS | BANSUD | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1384901.13 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301624 | Cawayan National High School | BONGABONG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 938249.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301625 | Dayhagan NHS | BONGABONG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1343352.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 309005 | Labasan National High School | BONGABONG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1075277.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301621 | Maujao National High School | BULALACAO (SAN PEDRO) | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1494745.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301622 | San Roque NHS | BULALACAO (SAN PEDRO) | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1325200.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301617 | Balugo NHS | MANSALAY | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 908171.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301652 | San Mariano NHS | ROXAS | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 944527.21 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 110742 | Concepcion ES | AGUTAYA | 1 | 1 | SOLAR PANEL | 1 | 2124271.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309120 | Concepcion National High School | AGUTAYA | 1 | 1 | SOLAR PANEL | 1 | 2509183.3 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301695 | Gaudencio E. Abordo Mem. NHS | AGUTAYA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1244774.41 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301662 | Araceli NHS | ARACELI | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1348153.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301678 | Calandagan NHS | ARACELI | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1856418.02 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309134 | Cheey NHS | BUSUANGA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1436313.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309167 | Concepcion NHS | BUSUANGA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1415684.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301711 | New Busuanga NHS | BUSUANGA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1629060.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301734 | Salvacion NHS | BUSUANGA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1764088.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301677 | Cagayancillo NHS | CAGAYANCILLO | 1 | 1 | SOLAR PANEL | 1 | 1443595.29 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 110965 | Calusa ES | CAGAYANCILLO | 1 | 1 | SOLAR PANEL | 1 | 2429697.81 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 110966 | Cawili Elementary School | CAGAYANCILLO | 1 | 1 | SOLAR PANEL | 1 | 2080947.05 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 110973 | Banuang Daan ES | CORON | 1 | 1 | SOLAR PANEL | 1 | 859977.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301685 | Borac National High School | CORON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1426067.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 110979 | Cabugao ES | CORON | 1 | 1 | SOLAR PANEL | 1 | 966266.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301684 | Coron SOF | CORON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1653895.31 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309168 | Decalachao NHS | CORON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1246826.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301687 | Culion Sanitarium Special NHS | CULION | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1374419.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301688 | Cuyo NHS | CUYO | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1278597.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301691 | Dumaran NHS | DUMARAN | 1 | 1 | SOLAR PANEL | 1 | 1319944.07 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301740 | Santa Teresita NHS | DUMARAN | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1419892.76 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301737 | San Miguel NHS (Gaudencio Abordo NHS) | LINAPACAN | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1411416.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301689 | Danawan NHS | MAGSAYSAY | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1246964.61 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 111155 | Maragoc ES | ROXAS | 1 | 1 | SOLAR PANEL | 1 | 1942556.02 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 170512 | Ramon Gacayan Elementary School | ROXAS | 1 | 1 | SOLAR PANEL | 1 | 1970006.99 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 111166 | Salvador ES | ROXAS | 1 | 1 | SOLAR PANEL | 1 | 2576686.91 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 111223 | Casian ES | TAYTAY | 1 | 1 | SOLAR PANEL | 1 | 2928722.65 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301682 | Casian NHS | TAYTAY | 1 | 1 | SOLAR PANEL | 1 | 4966964.86 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301666 | Balabac NHS | BALABAC | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1502475 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309113 | Bancalaan National High School | BALABAC | 2 | 1 | SOLAR PANEL | 1 | 3065598.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309127 | Sibaring NHS | BALABAC | 2 | 1 | SOLAR PANEL | 1 | 730635 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309149 | Taburi NHS | BALABAC | 2 | 1 | SOLAR PANEL | 1 | 1202985 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309129 | Southern Bataraza NHS | BATARAZA | 2 | 1 | SOLAR PANEL | 1 | 2374815 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309126 | Tarusan NHS | BATARAZA | 2 | 1 | SOLAR PANEL | 1 | 3048165 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301727 | Quezon-Aramaywan NHS | QUEZON | 2 | 1 | SOLAR PANEL | 1 | 2594910 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301729 | Quinlogan NHS | QUEZON | 2 | 1 | SOLAR PANEL | 1 | 2221050 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309160 | Canipaan NHS | RIZAL | 2 | 1 | SOLAR PANEL | 1 | 2070300 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309146 | Panalingaan NHS | RIZAL | 2 | 1 | SOLAR PANEL | 1 | 2107485 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301680 | Candawaga NHS | RIZAL (MARCOS) | 2 | 1 | SOLAR PANEL | 1 | 1402980 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301719 | Panitian National High School | SOFRONIO ESPAÑOLA | 2 | 1 | UPGRADING | 1 | 1430115 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 301785 | Buenavista Annex | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 462343.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 111510 | Buenavista ES | Puerto Princesa City | 3 | 1 | SOLAR PANEL | 2 | 472895.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 301781 | Cabayugan NHS | Puerto Princesa City | 3 | 1 | SOLAR PANEL | 2 | 770482.17 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 301781 | Cabayugan NHS | Puerto Princesa City | 3 |  | SOLAR PANEL | 2 | 1506969.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 111467 | East Central School | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 2493419.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 301782 | Inagawan NHS | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 1125863.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 301783 | Irawan NHS - Matahimik - Bucana Annex | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 919823.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 301785 | Macarascas NHS - Buenavista Annex | Puerto Princesa City | 3 |  | SOLAR PANEL | 2 | 826086.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 111520 | Makirawa Elementary School | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 462343.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City |  | Mandaragat - San Miguel Senior HS | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 1472587.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 111485 | Mateo Jagmis MES | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 2779446.87 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 309301 | PALAWAN NATIONAL SCHOOL | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 6802283.04 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 111470 | Puerto Princesa Pilot ES | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 3735812.41 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 309302 | Simpucan NHS (Napsan NHS - Simpucan Annex) | Puerto Princesa City | 3 | 1 | SOLAR PANEL | 2 | 770482.16 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 309302 | Simpucan NHS (Napsan NHS - Simpucan Annex) | Puerto Princesa City | 3 |  | UPGRADING | 2 | 1509331.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 309303 | Tagabinet High School | Puerto Princesa City | 3 | 1 | SOLAR PANEL | 2 | 590961.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 309303 | Tagabinet High School | Puerto Princesa City | 3 |  | SOLAR PANEL | 2 | 946895.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 300400 | Ubaldo L. Conde High School | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 1070770.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301750 | Banton NHS | BANTON | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1836679.92 | 1811342.4 | Terminated | 0.8 | 2019-01-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.8 | 0 |  |  | ENERGIZATION | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301755 | Cambalo NHS | CAJIDIOCAN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1461469.76 | 1409881.03 | Terminated | 0.9 | 2019-01-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.9 | 0 |  |  | ENERGIZATION | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301753 | Lumbang East National High School | CAJIDIOCAN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1231361.43 | 1204491.32 | Terminated | 0.8 | 2019-01-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.8 | 0 |  |  | ENERGIZATION | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 309201 | Calatrava NHS | CALATRAVA | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1323540.82 | 1269933.37 | Terminated | 0.9 | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.9 | 0 |  |  | ENERGIZATION | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301757 | Corcuera NHS | CORCUERA | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1282934.39 | 1261369.12 | Terminated | 0.8 | 2019-01-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.8 | 0 |  |  | ENERGIZATION | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301761 | Ferrol National High School | FERROL | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1565256.73 | 1479621.63 | Terminated | 0.9 | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.9 | 0 |  |  | ENERGIZATION | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301769 | Odiongan, National High School | ODIONGAN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 2144933.9 | 1997168.88 | Terminated | 0.9 | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.9 | 0 |  |  | ENERGIZATION | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 309205 | Carmen NHS (Cabolutan NHS Ext.) | SAN AGUSTIN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1374449.99 | 1324624.29 | Terminated | 0.9 | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.9 | 0 |  |  | ENERGIZATION | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301749 | Esteban Madrona National High School | SAN AGUSTIN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1515602.48 | 1488591.8 | Terminated | 0.9 | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.9 | 0 |  |  | ENERGIZATION | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301771 | San Andres NHS | SAN ANDRES | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1416442.65 | 1340420.86 | Terminated | 0.9 | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.9 | 0 |  |  | ENERGIZATION | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301763 | Sta. Fe NHS | SANTA FE | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1464802.14 | 1405144.61 | Terminated | 0.9 | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.9 | 0 |  |  | ENERGIZATION | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301774 | Santa Maria NHS | SANTA MARIA (IMELDA) | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1707966.77 | 1647944.34 | Terminated | 0.9 | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.9 | 0 |  |  | ENERGIZATION | Terminated
ELECTRIFICATION 2019 | Region IV-B | Calapan City | 301797 | Community Vocational High School | CITY OF CALAPAN (Capital) | 1 | 1 | UPGRADING |  | 1595784.93 | 1582805.23 | COMPLETED | 1 | November 1, 2019 |  |  |  | November 12, 2019 | November 19, 2019 | December 10, 2018 | December 21, 2018 | August 27, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Calapan City | 111539 | Lazareto ES | CITY OF CALAPAN (Capital) | 1 | 1 | UPGRADING | Batch 3 | 617623.12 | 603780 | COMPLETED | 1 | January 10, 2020 |  |  |  | September 30, 2019 | October 7, 2019 | October 21, 2019 | October 29, 2019 | November 11, 2019 | CMSEL Construction and Developer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Oriental Mindoro | 301611 | Apitong NHS | NAUJAN | 1 | 1 | UPGRADING |  | 2056773.01 | 2041436.28 | COMPLETED | 1 | Mar. 8,, 2020 | Mar. 6, 2020 |  | 098-2019 | Nov. 16, 2018 | Nov. 23, 2018 | Dec. 07,2018 | Dec. 17, 2018 | Oct 11, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Oriental Mindoro | 301645 | Naujan Municipal High School | NAUJAN | 1 | 1 | UPGRADING |  | 2130617.28 | 2113878.26 | COMPLETED | 1 | Mar. 8,, 2020 | Mar. 6, 2020 |  | 09-2019 | Nov. 16, 2018 | Nov. 23, 2018 | Dec. 07,2018 | Dec. 17, 2018 | Oct 11, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Oriental Mindoro | 301648 | Porfirio Comia MNHS | NAUJAN | 1 | 1 | UPGRADING |  | 2511941.82 | 2493940.48 | COMPLETED | 1 | Mar. 8,, 2020 | Mar. 6, 2020 |  | 099-2019 | Nov. 16, 2018 | Nov. 23, 2018 | Dec. 07,2018 | Dec. 17, 2018 | Oct 11, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Oriental Mindoro | 110535 | Porfirio G. Comia MES | NAUJAN | 1 | 1 | UPGRADING |  | 1304954.82 | 1295767.37 | COMPLETED | 1 | Mar. 8,, 2020 | Mar. 6, 2020 |  | 099-2019 | Nov. 16, 2018 | Nov. 23, 2018 | Dec. 07,2018 | Dec. 17, 2018 | Oct 11, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Oriental Mindoro | 301618 | Bansud NHS - Regional Science High School | BANSUD | 2 | 1 | UPGRADING |  | 1007628.26 | 1000767.73 | COMPLETED | 1 | Mar. 8,, 2020 | Mar. 6, 2020 |  | 099-2019 | Nov. 16, 2018 | Nov. 23, 2018 | Dec. 07,2018 | Dec. 17, 2018 | Oct 11, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Oriental Mindoro | 301649 | Quinabigan NHS | PINAMALAYAN | 2 | 1 | UPGRADING |  | 237655.81 | 236022.89 | COMPLETED | 1 | Mar. 8,, 2020 | Mar. 6, 2020 |  | 099-2019 | Nov. 16, 2018 | Nov. 23, 2018 | Dec. 07,2018 | Dec. 17, 2018 | Oct 11, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 110754 | Bohol Elementary School | DUMARAN | 1 | 1 | UPGRADING |  | 2225476.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 110767 | Dumaran Central School | DUMARAN | 1 | 1 | UPGRADING |  | 2211333.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 301691 | Dumaran National High School | DUMARAN | 1 | 1 | UPGRADING |  | 2297517.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 110768 | Ilian Elementary School | DUMARAN | 1 | 1 | UPGRADING |  | 2197393.11 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 309135 | Ilian National High School | DUMARAN | 1 | 1 | UPGRADING |  | 2130380.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 301714 | Nicanor Zabala National High School | ROXAS | 1 | 1 | UPGRADING |  | 1147438.92 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 111183 | Binga Elementary School | SAN VICENTE | 1 | 1 | UPGRADING |  | 2158156.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Romblon | 111356 | Odiongan South CES | ODIONGAN | 0 | 1 | UPGRADING |  | 4392551.95 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Calapan City | 301805 | Managpi National High School | CITY OF CALAPAN (Capital) | 1 | 1 | UPGRADING |  | 571845.06 |  | COMPLETED | 1 |  |  | Elec2020-RIV-B-Calapan City -001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1 | 1 | UPGRADING |  | 1145148.62 |  | COMPLETED | 1 |  |  | Elec2020-RIV-B-Calapan City -002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Marinduque | 301531 | BANGBANG NATIONAL HIGH SCHOOL | GASAN | 0 | 1 |  |  | 967324.13 |  | COMPLETED | 1 |  |  | ELEC2020-RIV B - Marinduque - 001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Marinduque | 301563 | TAGUM NATIONAL HIGH SCHOOL | STA.CRUZ | 0 | 1 |  |  | 829485.25 |  | COMPLETED | 1 |  |  | ELEC2020-RIV B - Marinduque - 004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Marinduque | 110026 | MARLANGGA ELEMENTARY SCHOOL | TORRIJOS | 0 | 1 |  |  | 718943.51 |  | COMPLETED | 1 |  |  | ELEC2020-RIV B - Marinduque - 005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Oriental Mindoro | 110656 | CALSAPA ELEMENTARY SCHOOL | SAN TEODORO | 1 | 1 |  |  | 929677.83 | 911843.35 | COMPLETED | 1 | Feb. 15, 2021 | Jan. 20, 2021 | ELEC2020-RIV B - Oriental Mindoro - 008 | 017-2020 | Nov. 19, 2019 | Nov. 27, 2019 | Dec. 12, 2019 | March 4, 2020 | November 09, 2020 | CMSEL Const. & Developer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Oriental Mindoro | 301619 | Bayuin NHS | SOCORRO | 1 | 1 |  |  | 2713634.88 | 2705358.6 | COMPLETED | 1 | Feb. 15, 2021 | Feb. 15, 2021 | ELEC2020-RIV B - Oriental Mindoro - 0014 | 018-2020 | Nov. 19, 2019 | Nov. 27, 2019 | Dec. 12, 2019 | March 4, 2020 | November 09, 2020 | CMSEL Const. & Developer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Oriental Mindoro | 110402 | FIDEL REYES MEMORIAL ELEMENTARY SCHOOL | BONGABONG | 2 | 1 |  |  | 1175848.45 | 1145817.09 | COMPLETED | 1 | Feb. 15, 2021 | Feb. 08, 2021 | ELEC2020-RIV B - Oriental Mindoro - 006 | 019-2020 | Nov. 19, 2019 | Nov. 27, 2019 | Dec. 12, 2019 | March 4, 2020 | November 09, 2020 | ETVR Trading & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Oriental Mindoro | 110449 | MALUSAK ELEMENTARY SCHOOL | GLORIA | 2 | 1 | UPGRADING |  | 1102581.15 | 1094932.31 | COMPLETED | 1 | Dec. 15, 2021 | Dec. 13, 2021 | ELEC2020-RIV B - Oriental Mindoro - 011 | 018-2021 | July 06, 2021 | July 14, 2021 | July 27, 2021 | Aug. 11, 2021 | Sept. 20, 2021 | TCC Powerserve Trading and Eng'g. Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Oriental Mindoro | 110630 | DANGAY ELEMENTARY SCHOOL | ROXAS | 2 | 1 | UPGRADING |  | 1550236.69 | 1541975.2 | COMPLETED | 1 | Dec. 15, 2021 | Dec. 13, 2021 | ELEC2020-RIV B - Oriental Mindoro - 007 | 017-2021 | July 06, 2021 | July 14, 2021 | July 27, 2021 | Aug. 11, 2021 | Sept. 20, 2021 | TCC Powerserve Trading and Eng'g. Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Palawan | 110964 | CAGAYANCILLO CS | CAGAYANCILLO | 1 | 1 | UPGRADING |  | 2569207.37 |  | COMPLETED | 1 |  |  | Elec2020-RIVB-PALAWAN-029 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Palawan | 110967 | MAGSAYSAY ES | CAGAYANCILLO | 1 | 1 | UPGRADING |  | 1195876.16 |  | COMPLETED | 1 |  |  | Elec2020-RIVB-PALAWAN-030 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Palawan | 110968 | MAMPIO ES | CAGAYANCILLO | 1 | 1 | UPGRADING |  | 1008565.24 |  | COMPLETED | 1 |  |  | Elec2020-RIVB-PALAWAN-031 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Palawan | 110970 | STA. CRUZ ES | CAGAYANCILLO | 1 | 1 | UPGRADING |  | 1274852.97 |  | COMPLETED | 1 |  |  | Elec2020-RIVB-PALAWAN-032 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Palawan | 110940 | LAMUD ELEMENTARY SCHOOL | CULION | 1 | 1 | UPGRADING |  | 856352.76 |  | COMPLETED | 1 |  |  | Elec2020-RIVB-PALAWAN-025 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Puerto Princesa City | 171502 | Talaudyong Elementary School | PUERTO PRINCESA CITY (Capital) | 2 | 1 |  |  | 1777613.88 |  | COMPLETED | 1 |  |  | ELEC2020-RIV-B-PUERTO PRINCESA -003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Puerto Princesa City | 111514 | Kandes Elementary School | PUERTO PRINCESA CITY (Capital) | 3 | 1 |  |  | 653089.58 |  | COMPLETED | 1 | January 3, 2021 |  | ELEC2020-RIV-B-PUERTO PRINCESA -001 |  | Nov. 26, 2019 | Dec. 3, 2019 | Dec. 16, 2019 | January 31, 2020 | Sept. 28, 2020 | Ian Jason Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Puerto Princesa City | 111492 | Sicsican Elementary School | PUERTO PRINCESA CITY (Capital) | 3 | 1 |  |  | 1801632.05 |  | COMPLETED | 1 | January 3, 2021 |  | ELEC2020-RIV-B-PUERTO PRINCESA -002 |  | Nov. 26, 2019 | Dec. 3, 2019 | Dec. 16, 2019 | January 31, 2020 | Sept. 28, 2020 | Ian Jason Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Romblon | 301767 | Macario Molina NHS | ROMBLON (Capital) | 0 | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools |  | 1795333.47 |  | COMPLETED | 1 |  |  | Elec2020-RIV-B-ROMBLON-006 | INF-EUP-2021-07 | 2021-10-29 | 2021-11-04 | 2021-11-08 | 2021-12-10 | 2022-01-28 | TCC POWER SERVE TRADING AND ENGINEERING SERVICES | Ongoing fabrication of steel posts and its plate, fabrication of steel bars for concrete pedestal and preparation of formworks for concrete pedestal. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Romblon | 301770 | Romblon NHS, Romblon | ROMBLON (Capital) | 0 | 1 |  |  | 4253061.64 |  | COMPLETED | 1 |  |  | Elec2020-RIV-B-ROMBLON-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region IV-B | Palawan | 110741 | Algeciras Elementry School | AGUTAYA | 1st | 1 | Provision of Solar-Powered Energy System | 1 | 1490439.83 |  | COMPLETED | 1 | [10 empty] | Obligated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2.25 | SOLAR | COMPLETED
ELECTRIFICATION 2023 | Region IV-B | Palawan | 110743 | Diit Elementary School | AGUTAYA | 1st | 1 | Provision of Solar-Powered Energy System | 1 | 1204739.14 |  | COMPLETED | 1 | [10 empty] | Obligated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2.25 | SOLAR | COMPLETED
ELECTRIFICATION 2023 | Region IV-B | Palawan | 110745 | Matarawis Elementary School | AGUTAYA | 1st | 1 | Provision of Solar-Powered Energy System | 1 | 679038.39 |  | COMPLETED | 1 | [10 empty] | Obligated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2.25 | SOLAR | COMPLETED
ELECTRIFICATION 2023 | Region IV-B | Palawan | 110925 | Barangonan Elementary School | LINAPACAN | 1st | 1 | Provision of Solar-Powered Energy System | 1 | 571490.34 |  | COMPLETED | 1 | [10 empty] | Obligated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 1.25 | SOLAR | COMPLETED
ELECTRIFICATION 2023 | Region IV-B | Palawan | 110952 | New Colaylayan Elementary School | LINAPACAN | 1st | 1 | Provision of Solar-Powered Energy System | 1 | 1251132.87 |  | COMPLETED | 1 | [10 empty] | Obligated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 1.25 | SOLAR | COMPLETED
ELECTRIFICATION 2023 | Region IV-B | Palawan | 110956 | Pical Elementary School | LINAPACAN | 1st | 1 | Provision of Solar-Powered Energy System | 1 | 803159.43 |  | COMPLETED | 1 | [10 empty] | Obligated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 1.25 | SOLAR | COMPLETED
ELECTRIFICATION 2024 | Region IV-B | Calapan City | 111570 | Adriatico Memorial School | CITY OF CALAPAN (Capital) | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 975022.82 | 907608 | COMPLETED | 1 | 2024-07-12 | 2024-12-12 | 2023-11-140 | 2023-11-140 | 2023-11-23 | 2023-11-29 | 2023-11-29 | 2023-12-18 | 2024-05-14 | PACE General Merch. | Build Platform for Transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2.25 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2024 | Region IV-B | Marinduque | 301554 | Marinduque NHS | BOAC (Capital) | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1245436.28 |  | COMPLETED | 1 | [10 empty] | COMPLETED BUT WITH RECTRIFICATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2.25 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2024 | Region IV-B | Occidental Mindoro | 110053 | Kulanguan PS | ABRA DE ILOG | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3000000 |  | Under procurement | 0 | [10 empty] | for procurement with Approved Project Modification | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | Under Procurement
ELECTRIFICATION 2024 | Region IV-B | Oriental Mindoro | 110453 | Pakpaklawin Elementary School | GLORIA | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1245436.28 |  | NOT YET started | 0 |  |  |  |  | 2025-03-19 | 2025-03-27 | 2025-04-08 | 2025-04-21 |  |  | Waiting for Sub-ARO | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | not yet started
ELECTRIFICATION 2024 | Region IV-B | Palawan | 110752 | Baeng Elementary School | Araceli | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1500224.29 |  | ONGOING | 0 | [10 empty] | MOBILIZATION | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region IV-B | Palawan | 110794 | Banglos Elementary School | BALABAC | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1063409.85 |  | ONGOING | 0 | [10 empty] | MOBILIZATION | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region IV-B | Puerto Princesa City | 111475 | Bualbualan ES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1245436.28 |  | COMPLETED | 1 | August 18, 2024 |  | ELEC 2024 - R IVB - PUERTO PRINCESA CITY - 001 | INFRA 2024-01-001 | Nov. 22, 2024 | Nov. 28, 2014 | Dec. 11, 2024 | Jan. 30, 2024 | May 13, 2024 | Ian Jason Construction | 1240436.28 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 11.24 | ENERGIZATION | COMPLETED

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%