## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | Unnamed: 45 | Status as of July 4, 2025
GABALDON 2020 | Region IV-B | Marinduque | 109870 | Don Luis Hidalgo MS | BOAC (Capital) | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 14026827.51 | 1 | 14026827.51 | Completed | 1 |  |  |  |  | 2020-01-14 | 2020-01-21 | 2020-04-02 | 2020-01-10 | 2020-10-29 | GS Mortar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region IV-B | Marinduque | 109957 | Sayao ES | MOGPOG | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 17278471.82 | 1 | 9955505.71 | Completed | 1 | 2022-03-30 | 2022-05-15 |  |  | 2021-05-27 | 2020-01-14 | 2020-04-02 | 2020-01-10 | 2020-10-29 | CMSEL Construction & Developer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region IV-B | Oriental Mindoro | 110490 | Jose L. Basa Memorial School | NAUJAN | 1 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 9955505.71 | 1 | 16923951.09 | Completed | 1 | 2022-03-30 |  |  |  | 2021-05-27 | 2021-04-06 | 2021-06-16 | 2021-07-23 | 2021-02-08 | GS Mortar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region IV-B | Oriental Mindoro | 110662 | San Teodoro CS | SAN TEODORO | 1 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 9411119.41 | 1 | 8046318.19 | Completed | 1 | 2022-09-30 |  |  |  | 2021-05-27 | 2021-04-06 | 2021-06-16 | 2021-09-07 | 2021-02-08 | NMDC Construction Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  | CY 2022 |  |  | Completed
GABALDON 2020 | Region IV-B | Romblon | 111329 | Looc CES | LOOC | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 11297198.88 | 1 | 9032617.13 | Completed | 1 | 2022-01-30 |  |  |  | 2021-05-27 | 2021-04-06 | 2021-06-16 | 2021-09-07 | 2021-02-08 | RMR Construction & Trading Hawkstow Construction & Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region IV-B | Romblon | 111356 | Odiongan South CES | ODIONGAN | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6016250.46 | 1 | 5032593.98 | Completed | 1 | 2021-12-30 | 2021-12-29 |  |  | 2021-05-27 | 2021-04-06 | 2021-06-16 | 2021-07-23 | 2021-02-08 | RMR Construction & Trading Hawkstow Construction & Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region IV-B | Romblon | 111411 | San Agustin CES | SAN AGUSTIN | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6037432.64 | 1 | 5049882.03 | Completed | 1 | 2021-12-30 | 2021-12-29 |  |  | 2021-05-27 | 2021-04-06 | 2021-06-16 | 2021-09-07 | 2021-02-08 | RMR Construction & Trading Hawkstow Construction & Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2021 | Region IV-B | Oriental Mindoro | 110558 | Juan Morente Sr. Mem. Pilot Sch. | PINAMALAYAN | 2 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 3145338 | 1 | 3145338 | COMPLETED | 1 |  |  |  |  | 2021-04-07 | 2021-04-07 | 2021-04-26 | 2021-05-07 | 2021-05-11 | CMSEL Construction & Developer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2022 | Region IV-B | Marinduque | 109952 | Mogpog Central School | MOGPOG | 0 | 1 | 15 | 1 | Rehabilitation of Gabaldon Building | 5234939.52 | 1 | 5182728.28 | COMPLETED | 1 | 2023-02-08 | 7/28/2023 | 2022-10-BEFF-04 | 2022-11-020 | 2022-10-10 | 10/21/2022 | 2022-03-11 | 11/23/2022 | 2022-05-12 | GS Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7.23 | Division Office | CY 2023 |  |  | COMPLETED
GABALDON 2023 | Region IV-B | Marinduque | 109924 | Bangbang ES | GASAN | 0 | 1 | 5 | 1 | Restoration & Conservation of Gabaldon Building | 10616143.68 | 1 | 10616143.68 | COMPLETED | 1 | 4/28/2024 | 2024-10-06 | 2023-OSEC-4B-23-1799-002 | 2023-08-006 | 6/16/2023 | 6/27/2023 | 2023-11-07 | 7/18/2023 | 8/25/2023 | GS Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7.24 | Division Office |  |  |  | COMPLETED
GABALDON 2024 | Region IV-B | Marinduque | 109952 | Mogpog CS | GASAN | Lone | 1 | 16 | 1 | Conservation and Restoration of Gabaldon School Building (2 bldgs) | 14164230.3 | 1 |  | Under Procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | Division Office |  | 1 | 0 | Under Procurement

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%