## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | Unnamed: 45 | Status as of July 4, 2025
GABALDON 2020 | Region IX | Zamboanga City | 126121 | Curuan CS | Zamboanga City | 2 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 5000000 | 1 | 4750000 | Completed | 1 | January 31,2022 | February 8,2022 | ZC-GAB-2020-B | ZC-GAB-2020-B | May 3, 2021 | May 17, 2021 | May 31,2021 | July 8, 2021 | July 30,2021 | Zamboanga 3VC Constrution,INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region IX | Zamboanga City | 126189 | Mercedes CS | Zamboanga City | 2 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 8000000 | 1 | 7600000 | Completed | 1 | January 31,2022 | February 5,2022 | ZC-GAB-2020-A | ZC-GAB-2020-A | May 3, 2021 | May 17, 2021 | May 31,2021 | July 8, 2021 | July 30,2021 | Zamboanga 3VC Constrution,INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2021 | Region IX | Zamboanga City | 126226 | Mampang Elementary School | ZAMBOANGA CITY | 2 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 5000000 | 1 | 4995000 | Completed | 1 | January 31,2022 | November 30,2021 | ZC-GAB-2021 | ZC-GAB-2021 | May 3, 2021 | May 17, 2021 | May 31,2021 | July 8, 2021 | July 30,2021 | Zamboanga 3VC Constrution,INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Division Office |  |  |  | Completed
GABALDON 2023 | Region IX | Zamboanga del Norte | 124369 | Katipunan Central School | KATIPUNAN | 2 | 1 | 16 | 1 | Restoration & Conservation of Gabaldon Building | 17112890.01 | 1 | 17093932.97 | Completed | 1 | 2023-07-11 | - | 2023-7-CBZN | CB-2023-007 | 2023-05-04 | 4/14/2023 | 4/27/2023 | 5/30/2023 | 2023-07-06 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 5.24 | Division Office | cy 2024 |  |  | Completed
GABALDON 2023 | Region IX | Zamboanga del Sur | 125371 | San Pablo CES | SAN PABLO | 2 | 1 | 2 | 1 | Restoration & Conservation of Gabaldon Building | 4907365.3 | 1 | 4877195.13 | Completed | 1 | 2023-04-11 | November 4, 2023 | ZDS-23-RG-01 | ZDS-23-RG-01 | 4/13/2023 | 4/26/2023 | 2023-08-05 | 5/22/2023 | 5/31/2023 | ASCS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2.24 | Division Office | cy 2024 |  |  | Completed
GABALDON 2024 | Region IX | Dapitan City | 125916 | Ilaya Elementary School | DAPITAN CITY | 1st | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 5000000 | 1 | 4956744.84 | Ongoing | 0.8 | 2025-02-06 | - | CY2024-10-12 | CY2024-10-12 | 8/22/2024 | 2024-09-11 | 9/25/2024 | 10/16/2024 | 2025-03-01 | Stars and Stripes Construction | ON-GOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.8 | 0 |  |  | Division Office |  |  | 10 | Ongoing
GABALDON 2024 | Region IX | Isabela City | 126002 | Isabela Central Elementary Pilot School | CITY OF ISABELA (Capital) | Lone | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 18000000 | 1 | - | Not Yet Started | 0 | - | - | - | - | - | - | - | - | - | - | With RTA waiting for SARO | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | Division Office |  | 1 | 0 | not yet started
GABALDON 2024 | Region IX | Zamboanga del Norte | 124588 | Lapayanbaja ES | POLANCO | 1st | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building with 16KW Solar PV | 23015000 | 1 | 22999627.62 | Ongoing | 0.85 | February 09, 2025 | - | 2024-026-CBZN | CB-2024-037 | April 23, 2024 | May 02,2024 | May 15, 2024 | June 25, 2024 | July 07, 2024 | YSL BUILDERS | - | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.85 | 0 |  |  | Division Office |  |  | 3 | Ongoing
GABALDON 2024 | Region IX | Zamboanga del Norte | 124596 | Sianib ES | POLANCO | 1st | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 24015000 | 1 | 23995323.36 | Ongoing | 0.9 | February 09, 2025 | - | 2024-025-CBZN | CB-2024-036 | April 23, 2024 | May 02,2024 | May 15, 2024 | June 25, 2024 | July 07, 2024 | YSL BUILDERS | - | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.9 | 0 |  |  | Division Office |  |  | 3 | Ongoing

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%