## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | No. of Classrooms | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated | Previous % | Difference | STOREY | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | Status as of July 4, 2025
NEWCON 2016 | REGION IX | Dapitan City | 125911 | Baao Es | Dapitan City | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2000214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Dapitan City | 303877 | Barcelona National High School | Dapitan City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2668064.9172 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Dapitan City | 303878 | Baylimango Nhs | Dapitan City | 1 | 1 | 12 | 3STY12CL | BATCH 3 CL | 17070000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Dapitan City | 125937 | Capucao Ps | Dapitan City | 1 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1128000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Dapitan City | 303879 | Dakak National High School | Dapitan City | 1 | 1 | 12 | 3STY12CL | BATCH 3 CL | 17070000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Dapitan City | 303880 | Dapitan City National High School | Dapitan City | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28350000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IX | Dapitan City | 303880 | Dapitan City National High School | Dapitan City | 1 |  | 6 | 3STY6CL | BATCH 9 CL | 11503844.661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IX | Dapitan City | 303880 | Dapitan City National High School | Dapitan City | 1 |  | 9 | 3STY9CL | BATCH 9 CL | 16708460.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Dapitan City | 303880 | Dapitan City National High School/Talisay Extension | Dapitan City | 1 |  | 15 | 3STY15CL | BATCH 9 CL | 21300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION IX | Dapitan City | 303881 | Ilaya Nhs | Dapitan City | 1 | 1 | 10 | 2STY10CL | BATCH 5 CL | 14133441.1023 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Dapitan City | 303883 | Potungan Nhs | Dapitan City | 1 | 1 | 10 | 2STY10CL | BATCH 5 CL | 14138441.1023 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Dapitan City | 303884 | Sulangon Nhs | Dapitan City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2668064.9172 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Dipolog City | 303885 | Alberto Q. Ubay Mem. Agro-Tech'L. Sci. Hs | Dipolog City (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11141570 |  |  | Completed | 1 |  |  | P00072438MN - CW1 | 16JB0020 | May 06, 2016 | May 20, 2016 | June 07, 2016 | June 28, 2016 | August 08, 2016 | Dipolog Top Construction & Devt. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IX | Dipolog City | 303885 | Alberto Q. Ubay Mem. Agro-Tech'L. Sci. Hs | Dipolog City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2788710 |  |  | Completed | 1 |  |  | P00072634MN - CW1 | 16JB0029 | May 06, 2016 | May 20, 2016 | June 07, 2016 | June 28, 2016 | August 08, 2016 | Dipolog Top Construction & Devt. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Dipolog City | 303886 | Cogon Nhs | Dipolog City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6545000 |  |  | Completed | 1 | [6 empty] | June 22, 2017 |  |  | Rudhil Construction & Enterprises, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Dipolog City | 303887 | Dipolog City Nhs (Barra) | Dipolog City (Capital) | 2 | 1 | 16 | 2STY8CL | BATCH 5 CL | 22283140 |  |  | Completed | 1 |  |  | P00071085MN - CW1 | 16JB0023 | May 06, 2016 | May 20, 2016 | June 07, 2016 | July 25, 2016 | Contract on Process | Rudhil Construction & Enterprises, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IX | Dipolog City | 125972 | Galas Nhs To Galas Es | Dipolog City (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18267268.79 |  |  | Completed | 1 | [6 empty] | June 22, 2017 |  |  | Rudhil Construction & Enterprises, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Dipolog City | 303890 | Pamansalan Eco. Tech. Hs | Dipolog City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6545000 |  |  | Completed | 1 |  |  | P00072439MN - CW1 | 16JB0019 | May 06, 2016 | May 20, 2016 | June 07, 2016 | July 25, 2016 | Contract on Process | Rudhil Construction & Enterprises, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Dipolog City | 303890 | Pamansalan Eco. Tech. Hs | Dipolog City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2788710 |  |  | Completed | 1 |  |  | P00072635MN - CW1 | 16JB0030 | May 06, 2016 | May 20, 2016 | June 07, 2016 | July 25, 2016 | Contract on Process | Rudhil Construction & Enterprises, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Dipolog City | 303891 | Punta National High School | Dipolog City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6535000 |  |  | Completed | 1 |  |  | P00072440MN - CW1 | 16JB0018 | May 06, 2016 | May 20, 2016 | June 07, 2016 | July 25, 2016 | Contract on Process | Rudhil Construction & Enterprises, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Dipolog City | 303893 | Zamboanga Norte Nhs | Dipolog City (Capital) | 2 | 1 | 120 | 4STY20CL | BATCH 9 CL | 192423168 |  |  | Completed | 1 |  |  | P00073354MN - CW1 | 16JB0032 | May 06, 2016 | May 20, 2016 | June 07, 2016 | July 04, 2016 | Contract on Process | Vicente T. Lao Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 120 | 0
NEWCON 2016 | REGION IX | Dipolog City | 303893 | Zamboanga Norte Nhs | Dipolog City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 |  |  | P00074474MN - CW1 | 16JB0028 | May 06, 2016 | May 20, 2016 | June 07, 2016 | June 28, 2016 | August 08, 2016 | Dipolog Top Construction & Devt. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Isabela City | 126018 | Badjao Es | City Of Isabela (Capital) | 0 | 1 | 4 | 1STY4CL | BATCH 5 CL | 3971375.2325 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Isabela City | 126018 | Badjao Es | City Of Isabela (Capital) | 0 |  | 3 | 1STY3CL | BATCH 5 CL | 3024910.9364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION IX | Isabela City | 198005 | Balawatin Ps | City Of Isabela (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2056214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Isabela City | 303894 | Basilan Nhs | City Of Isabela (Capital) | 0 | 1 | 60 | 4STY20CL | BATCH 9 CL | 103794537.891 |  |  | Completed | 1 | [10 empty] | With approved additional funds | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 60 | 0
NEWCON 2016 | REGION IX | Isabela City | 303894 | Basilan Nhs | City Of Isabela (Capital) | 0 |  | 10 | 2STY10CL | BATCH 9 CL | 14233441.1023 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Isabela City | 303897 | Begang Nhs | City Of Isabela (Capital) | 0 | 1 | 18 | 2STY6CL | BATCH 1 CL | 25334895.153 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION IX | Isabela City | 314602 | Calvario Peak Nhs | City Of Isabela (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2994910.9364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION IX | Isabela City | 133031 | Caro Elementary School | City Of Isabela (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6270000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Isabela City | 126019 | Diki Es | City Of Isabela (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2076214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Isabela City | 198012 | Geras Es | City Of Isabela (Capital) | 0 | 1 | 12 | 2STY4CL | BATCH 5 CL | 18690000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Isabela City | 198012 | Geras Es | City Of Isabela (Capital) | 0 |  | 1 | 1STY1CL | BATCH 5 CL | 1133254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Isabela City | 314601 | Isabela City Nhs | City Of Isabela (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2705618.2353 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Isabela City | 198015 | Ismael Primary School | City Of Isabela (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6230000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Isabela City | 198015 | Ismael Primary School | City Of Isabela (Capital) | 0 |  | 1 | 1STY1CL | BATCH 5 CL | 1133254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Isabela City | 303899 | Kumalarang Nhs | City Of Isabela (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2964910.9364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION IX | Isabela City | 126022 | Lukbuton Es | City Of Isabela (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2036214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Isabela City | 198008 | M.S. Bernardo Elementary School | City Of Isabela (Capital) | 0 | 1 | 4 | 1STY4CL | BATCH 5 CL | 3931375.2325 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Isabela City | 198008 | M.S. Bernardo Elementary School | City Of Isabela (Capital) | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 2036214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Isabela City | 303895 | Malamawi National High School | City Of Isabela (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2752536.4706 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Isabela City | 303895 | Malamawi National High School | City Of Isabela (Capital) | 0 | 1 | 12 | 2STY6CL | BATCH 13 CL | 18762923.11 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Isabela City | 198009 | Masola Es | City Of Isabela (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2056214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Isabela City | 198013 | N.R. Hugo Ps | City Of Isabela (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2964910.9364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION IX | Isabela City | 303898 | Tandung Ahas Nhs | City Of Isabela (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2964910.9364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION IX | Pagadian City | 126081 | Bagong Silang Es | Pagadian City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6386012.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Pagadian City | 303903 | Lison Valley Nhs | Pagadian City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2636730 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Pagadian City | 314702 | Norberta Guillar Memorial Nhs | Pagadian City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26482375 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IX | Pagadian City | 303906 | Pagadian City National Comprehensive High School | Pagadian City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2612200 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Pagadian City | 303908 | Pagadian City Nhs | Pagadian City (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22655968.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Pagadian City | 303908 | Pagadian City Nhs | Pagadian City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2612125 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Pagadian City | 314704 | Pagadian City Science High School | Pagadian City (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 17199085.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Pagadian City | 303910 | Zamboanga Del Sur Nhs | Pagadian City (Capital) | 1 | 1 | 48 | 4STY24CL | BATCH 11 CL | 71865115.9179 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION IX | Pagadian City | 345814 | Zamboanga Del Sur Sports Academy | Pagadian City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 28475000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 303915 | Ayala Nhs | Zamboanga City | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 32402890 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 303915 | Ayala Nhs | Zamboanga City | 1 |  | 24 | 4STY24CL | BATCH 9 CL | 36296257 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 126108 | Baliwasan Cs | Zamboanga City | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31752891 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 126110 | John Spirig S. Mes | Zamboanga City | 1 | 1 | 40 | 4STY20CL | BATCH 13 CL | 62905782 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 126104 | Labuan Cs To Sinunuc Es | Zamboanga City | 1 |  | 15 | 3STY15CL | BATCH 3 CL | 21740665.56 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION IX | Zamboanga City |  | Labuan Cs 2Sty4Cl To Sinunuc Es | Zamboanga City | 1 |  |  |  | BATCH 3 CL |  |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 303924 | Ramon Enriquez Hs | Zamboanga City | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29857716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 126104 | Sinunuc Es | Zamboanga City | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 24852577.982 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 126210 | Sta. Barbara Cs | Zamboanga City | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15471328 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 303918 | Bunguiao Nhs | Zamboanga City | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15571328 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 303921 | Curuan Nhs | Zamboanga City | 2 | 1 | 24 | 4STY24CL | BATCH 9 CL | 36546257 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 126182 | Guisao Es | Zamboanga City | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8564965 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 314806 | Mangusu Is | Zamboanga City | 2 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15571328 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 126204 | Putik Cs | Zamboanga City | 2 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18422269 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 126231 | Tugbungan Es | Zamboanga City | 2 | 1 | 6 | 3STY6CL | BATCH 13 CL | 11843844.661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IX | Zamboanga City | 126206 | Zambowood Es | Zamboanga City | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6619338 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303715 | Pinan National High School | Piñan (New Piñan) | 1 | 1 | 16 | 2STY8CL | BATCH 9 CL | 22020000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303715 | Pinan National High School | Piñan (New Piñan) | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303715 | Pinan National High School | Piñan (New Piñan) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303728 | Sergio Osmena Nhs | Sergio Osmeña Sr. | 1 | 1 | 24 | 2STY8CL | BATCH 9 CL | 33005000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303728 | Sergio Osmena Nhs | Sergio Osmeña Sr. | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303737 | Sibutad National High School | Jose Dalman (Ponot) | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31152890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303696 | Katipunan National High School | Katipunan | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21423013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303696 | Katipunan National High School | Katipunan | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 18262268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303696 | Katipunan National High School | Katipunan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303710 | Manukan Nhs | Manukan | 2 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62230780.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303738 | Sindangan National Agricultural School | Sindangan | 2 | 1 | 36 | 3STY12CL | BATCH 9 CL | 54716806.37 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303738 | Sindangan National Agricultural School | Sindangan | 2 | 1 | 4 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 9958040 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303739 | Sindangan Nhs | Bacungan (Leon T. Postigo) | 2 | 1 | 40 | 4STY20CL | BATCH 13 CL | 68471358.594 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303672 | Bacungan Nhs | Bacungan (Leon T. Postigo) | 3 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21433013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303672 | Bacungan Nhs | Bacungan (Leon T. Postigo) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303686 | Gutalac Nhs | Gutalac | 3 | 1 | 45 | 3STY15CL | BATCH 9 CL | 64199040.35 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 45 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303686 | Gutalac Nhs | Gutalac | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303703 | Kipit Agro-Fishery Nhs | Labason | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2771079.0067 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303706 | Liloy National High School | Liloy | 3 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62255780.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303706 | Liloy National High School | Liloy | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4979020 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303721 | Salug National High School | Salug | 3 | 1 | 40 | 2STY10CL | BATCH 9 CL | 51642000 |  |  | Terminated | 0.5 | [10 empty] | MUTUAL AND PARTIAL TERMINATION (Only 50% of the contract was terminated, instead of 4 units of 2 storey 10 classroom only 2 units was implemented due to no buildable space to construct the remaining units) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303721 | Salug National High School | Salug | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303740 | Siocon National High School | Sirawai | 3 | 1 | 24 | 3STY12CL | BATCH 3 CL | 36494537.58 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303742 | Sirawai National High School | Sirawai | 3 | 1 | 32 | 2STY8CL | BATCH 9 CL | 43990000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303742 | Sirawai National High School | Sirawai | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303745 | Tampilisan Nhs | Tampilisan | 3 | 1 | 16 | 2STY8CL | BATCH 9 CL | 22020000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303745 | Tampilisan Nhs | Tampilisan | 3 |  | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303745 | Tampilisan Nhs | Tampilisan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303750 | Ubay Nhs | Labason | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2771079.0067 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Norte | 303750 | Ubay Nhs | Labason | 3 | 1 | 10 | 2STY10CL | BATCH 13 CL | 13018000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303780 | Aurora National High School | Aurora | 1 | 1 | 30 | 3STY15CL | BATCH 5 CL | 48433129.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303780 | Aurora National High School | Aurora | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2624700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 314203 | Boniao National High School | Mahayag | 1 | 1 | 8 | 2STY4CL | BATCH 3 CL | 13617375 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 314203 | Boniao National High School | Mahayag | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5252750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303766 | Commonwealth Nhs | Aurora | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2624700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303773 | Dumingag National High School | Dumingag | 1 | 1 | 40 | 2STY8CL | BATCH 5 CL | 61684484.2543 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303773 | Dumingag National High School | Dumingag | 1 |  | 4 | 2STY4CL | BATCH 5 CL | 6804875 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303773 | Dumingag National High School | Dumingag | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2701200 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303792 | Leonardo Nhs | Josefina | 1 | 1 | 9 | 3STY9CL | BATCH 11 CL | 16797750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303792 | Leonardo Nhs | Josefina | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2624700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303803 | Mahayag School Of Arts And Trade (Mahayag Nhs) | Mahayag | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 33604750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303803 | Mahayag School Of Arts And Trade (Mahayag Nhs) | Mahayag | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5352000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303796 | Midsalip Nhs- Main | Midsalip | 1 | 1 | 32 | 4STY16CL | BATCH 3 CL | 54132400 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303796 | Midsalip Nhs- Main | Midsalip | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2639640 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303797 | Molave Vocational Technical School | Molave | 1 | 1 | 24 | 4STY24CL | BATCH 11 CL | 40334132.854 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | PSA328568 | Shs In Labangan, Zamboanga Del Sur | Labangan | 1 | 1 | 12 | 3STY12CL | BATCH 11 CL | 18696088.4293 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303817 | Sominot National High School | Sominot (Don Mariano Marcos) | 1 | 1 | 6 | 2STY6CL | BATCH 5 CL | 9321681.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303817 | Sominot National High School | Sominot (Don Mariano Marcos) | 1 |  | 8 | 2STY4CL | BATCH 5 CL | 13701540 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303819 | Tambulig Nhs | Tambulig | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 33604750 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303819 | Tambulig Nhs | Tambulig | 1 |  | 9 | 3STY9CL | BATCH 3 CL | 15203700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303819 | Tambulig Nhs | Tambulig | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2651200 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303811 | Tukuran Tech. Voc'L. Hs | Tukuran | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14412150 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303811 | Tukuran Tech. Voc'L. Hs | Tukuran | 1 |  | 30 | 3STY15CL | BATCH 9 CL | 44180526.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303811 | Tukuran Tech. Voc'L. Hs | Tukuran | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2612000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303753 | Antonio Nhs | Tigbao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2610000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303757 | Bayog Nhs | Bayog | 2 | 1 | 32 | 4STY16CL | BATCH 9 CL | 55632400 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303757 | Bayog Nhs | Bayog | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2570000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303791 | Betinan Nhs | San Miguel | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14775000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303791 | Betinan Nhs | San Miguel | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5100000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303770 | Dimataling National High School | Dimataling | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2570000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303771 | Dinas Nhs | Dinas | 2 | 1 | 36 | 4STY12CL | BATCH 9 CL | 62308950 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303771 | Dinas Nhs | Dinas | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4852956.8627 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303776 | Eugenia Andrin Nhs | San Pablo | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14775000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303776 | Eugenia Andrin Nhs | San Pablo | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2550000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303778 | Guipos Nhs | Guipos | 2 | 1 | 24 | 4STY12CL | BATCH 5 CL | 44304687.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303782 | Kabatan Nhs | Vincenzo A. Sagun | 2 | 1 | 16 | 4STY16CL | BATCH 4 TVL | 2570000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303782 | Kabatan Nhs | Vincenzo A. Sagun | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 27776200 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303782 | Kabatan Nhs | Vincenzo A. Sagun | 2 |  | 1 | SHS UNIQUE WORKSHOP | BATCH 3 CL | 11180000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303783 | Kalian Nhs | Margosatubig | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22212343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303783 | Kalian Nhs | Margosatubig | 2 |  | 9 | 3STY9CL | BATCH 5 CL | 14820000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303783 | Kalian Nhs | Margosatubig | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2560000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303788 | Lapuyan Nhs | Lapuyan | 2 | 1 | 24 | 4STY12CL | BATCH 3 CL | 41619300 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303788 | Lapuyan Nhs | Lapuyan | 2 |  | 6 | 3STY6CL | BATCH 3 CL | 10680000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303764 | Laureano Salusod Nhs | Dimataling | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 20809650 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303764 | Laureano Salusod Nhs | Dimataling | 2 |  | 9 | 3STY9CL | BATCH 7 CL | 14820000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 314252 | Locuban Nhs Realigned To Maria Clara L. Lobregat Nhs | Dumalinao | 2 | 1 | 8 | 2STY8CL | BATCH 3 CL | 13858100 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 314217 | Locuban Nhs Realigned Bibilik Nhs | Dumalinao | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 13858100 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303804 | Paulino Dari Nhs | Pitogo | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14800000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303804 | Paulino Dari Nhs | Pitogo | 2 |  | 4 | 2STY4CL | BATCH 7 CL | 6675000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303804 | Paulino Dari Nhs | Pitogo | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5125000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303808 | Rebokon Avhs | Dumalinao | 2 | 1 | 8 | 2STY4CL | BATCH 7 CL | 13300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303808 | Rebokon Avhs | Dumalinao | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5100000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303768 | Tabina Nhs | Tabina | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 20949650 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303822 | Toribio Minor Nhs | Margosatubig | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14775000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303822 | Toribio Minor Nhs | Margosatubig | 2 |  | 12 | 4STY12CL | BATCH 7 CL | 20749650 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303822 | Toribio Minor Nhs | Margosatubig | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5100000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Del Sur | 303823 | Tubod Nhs | Lakewood | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2550000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303824 | Alicia National High School | Alicia | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12871310.09 |  |  | Completed | 1 |  |  |  |  | 2016-08-30 | 2016-08-16 | 2016-08-30 | 2016-09-14 | 42640 | RAMONA CONST. & ENT. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303824 | Alicia National High School | Alicia | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12871310.09 |  |  | Completed | 1 |  |  |  |  | 2016-08-30 | 2016-08-16 | 2016-08-30 | 2016-09-14 | 42640 | JAYKRIS ENT. & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303824 | Alicia National High School | Alicia | 1 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18347268.79 |  |  | Completed | 1 |  |  |  |  | 2016-08-30 | 2016-08-16 | 2016-08-30 | 2016-09-14 | 42640 | GENETIAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303825 | Dawa-Dawa Nhs | Alicia | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11235000 |  |  | Completed | 1 |  |  |  |  | 2016-08-30 | 2016-08-16 | 2016-08-30 | 2016-09-14 | 42640 | MINDANAO ROCK |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303825 | Dawa-Dawa Nhs | Alicia | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9171461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-08-15 | 2016-08-31 | 42628 | GENETIAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303828 | Diplahan Nhs | Diplahan | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.09 |  |  | Terminated | 0.41 |  |  |  |  | 2016-07-25 | 2016-07-12 | 2016-07-25 | 2016-08-09 | 42605 | RUDHIL CONST. & ENT. INC. | Due to NGCP work stoppage order; Contract Termination;With approved buffer fund 2019 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303828 | Diplahan Nhs | Diplahan | 1 |  | 16 | 2STY8CL | BATCH 7 CL | 21754685.18 |  |  | Terminated | 0.37 |  |  |  |  | 2016-08-30 | 2016-08-16 | 2016-08-30 | 2016-09-14 | 42640 | RCDG CONST. CROP JV DIPLAHAN COMM. & CONST. | With approved buffer fund 2019 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303828 | Diplahan Nhs | Diplahan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2417461.96 |  |  | Completed | 1 |  |  |  |  | 2016-04-21 | 2016-04-08 | 2016-04-21 | 2016-05-06 | 42566 | JAYKRIS ENT. & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 314314 | Ditay Nhs | Diplahan | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 |  |  |  |  | 2016-07-25 | 2016-07-12 | 2016-07-25 | 2016-08-09 | 42605 | MJMARI BUILD. & ENT. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303837 | Imelda Nhs | Imelda | 1 | 1 | 20 | 2STY10CL | BATCH 7 CL | 25542620.18 |  |  | Completed | 1 |  |  |  |  | 2016-07-25 | 2016-07-12 | 2016-07-25 | 2016-08-09 | 42605 | GENETIAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303837 | Imelda Nhs | Imelda | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 |  |  |  |  | 2016-07-25 | 2016-07-12 | 2016-07-25 | 2016-08-09 | 42605 | GENETIAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303837 | Imelda Nhs | Imelda | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4834923.92 |  |  | Completed | 1 |  |  |  |  | 2016-04-21 | 2016-04-08 | 2016-04-21 | 2016-05-06 | 42555 | JAYKRIS ENT. & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 314315 | Mabuhay Agro-Industrial Hs | Mabuhay | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11077342.59 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-09-07 | 2016-09-22 | 42647 | JAYKRIS ENT. & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303852 | Mabuhay Nhs | Mabuhay | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12896310.09 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-09-07 | 2016-09-22 | 42647 | JAYKRIS ENT. & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303845 | Malangas Nhs | Malangas | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12846310.09 |  |  | Completed | 1 |  |  |  |  | 2016-07-10 | 9/26/16 | 10/24/16 | 2016-03-11 | 42685 | HENSO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303845 | Malangas Nhs | Malangas | 1 |  | 16 | 2STY8CL | BATCH 9 CL | 21854685.18 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-08-15 | 2016-08-31 | 42628 | RUDHIL CONST. & ENT. INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303845 | Malangas Nhs | Malangas | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417461.96 |  |  | Completed | 1 |  |  |  |  | 2016-04-21 | 2016-04-08 | 2016-04-21 | 2016-05-06 | 42566 | JAYKRIS ENT. & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303851 | Olutanga National High School | Olutanga | 1 | 1 | 18 | 2STY6CL | BATCH 9 CL | 25094895.18 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-09-07 | 2016-09-22 | 42647 | RAMONA CONST. & ENT. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303851 | Olutanga National High School | Olutanga | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4984923.92 |  |  | Completed | 1 |  |  |  |  | 2016-04-21 | 2016-04-08 | 2016-04-21 | 2016-05-06 | 42566 | ST. JOSEPH CONST. & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303856 | Payao National High School | Payao | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12896310.09 |  |  | Completed | 1 |  |  |  |  | 2016-08-30 | 2016-08-16 | 2016-08-30 | 2016-09-14 | 42640 | RAMONA CONST. & ENT. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303870 | Talusan Nhs | Talusan | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12921310.09 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-09-07 | 2016-09-22 | 42647 | RAMONA CONST. & ENT. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303870 | Talusan Nhs | Talusan | 1 |  | 8 | 2STY8CL | BATCH 7 CL | 10977342.59 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-09-07 | 2016-09-22 | 42647 | JAYKRIS ENT. & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 125640 | Diampak Elementary School | Kabasalan | 2 | 1 | 2 | 1STY1CL | BATCH 13 CL | 2396899.38 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303827 | Francisco Ramos Nhs (Formerly Buayan Nhs) | Kabasalan | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | BARILLO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303827 | Francisco Ramos Nhs (Formerly Buayan Nhs) | Kabasalan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417461.96 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | JGC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303838 | Ipil Nhs | Ipil | 2 | 1 | 24 | 4STY24CL | BATCH 3 CL | 35596000 |  |  | Completed | 1 |  |  |  |  | 2016-03-01 | 2016-03-10 | 2016-03-22 | 2016-05-24 | 407764 | LONG ISLAND BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303839 | Kabasalan Nhs | Kabasalan | 2 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26702000 |  |  | Completed | 1 |  |  |  |  | 2016-03-01 | 2016-03-10 | 2016-03-22 | 2016-05-24 | 42537 | JGC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303840 | Kabasalan Science & Technology High School | Kabasalan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.63 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42604 | JGC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 125826 | Mahayahay Es | Siay | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2038606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303867 | Malubal Nhs | Roseller Lim | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12921310.09 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | LONG ISLAND BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303849 | Naga Nhs | Naga | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | HENSO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303849 | Naga Nhs | Naga | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 8214965.06 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | HENSO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303849 | Naga Nhs | Naga | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417461.96 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | JGC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303859 | Pioneer Nhs | Tungawan | 2 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | LONG ISLAND BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303859 | Pioneer Nhs | Tungawan | 2 |  | 1 | 1STY1CL | BATCH 7 CL | 1098449.69 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | GJD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303860 | San Antonio Nhs | Titay | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12921310.09 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | RUDHIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303864 | Siay National High School | Siay | 2 | 1 | 28 | 4STY28CL | BATCH 3 CL | 40067000 |  |  | Completed | 1 |  |  |  |  | 2016-03-01 | 2016-03-10 | 2016-03-22 | 2016-05-24 | 42551 | ESR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303861 | Sta. Clara National High School | Naga | 2 | 1 | 16 | 2STY8CL | BATCH 7 CL | 21854685.18 |  |  | Completed | 1 |  |  |  |  | 2016-06-29 | 2016-06-02 | 2016-07-19 | 2016-08-01 | 42598 | RUDHIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303866 | Surabay National High School | Roseller Lim | 2 | 1 | 36 | 3STY12CL | BATCH 9 CL | 54666806.37 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | OG SANTOS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303866 | Surabay National High School | Roseller Lim | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834923.92 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | BARILLO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303872 | Titay National High School | Titay | 2 | 1 | 45 | 3STY15CL | BATCH 9 CL | 64149040.35 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | OG SANTOS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 45 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303872 | Titay National High School | Titay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417461.96 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-07-21 | 42598 | GJD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303874 | Tungawan National High School | Tungawan | 2 | 1 | 32 | 4STY16CL | BATCH 9 CL | 58715432.724 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | ESR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303854 | Zamboanga Sibugay Nhs | Ipil | 2 | 1 | 20 | 2STY10CL | BATCH 9 CL | 25542620.18 |  |  | Completed | 1 |  |  |  |  | 2016-06-29 | 2016-06-02 | 1900-02-08 | 2016-08-01 | 42598 | LONG ISLAND BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303854 | Zamboanga Sibugay Nhs | Ipil | 2 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | LONG ISLAND BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION IX | Zamboanga Sibugay | 303854 | Zamboanga Sibugay Nhs | Ipil | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834923.92 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 42598 | GJD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.