## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | Unnamed: 45 | Status as of July 4, 2025
GABALDON 2020 | Region V | Albay | 111630 | Camalig North CS | Camalig | 2 | 1 | 9 | 1 | Rehabilitation of Gabaldon Building | 12541895.31 | 1 |  | Completed | 1 | [9 empty] | JagVail Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region V | Albay | 111727 | Guinobatan West CS | Guinobatan | 3 | 1 | 11 | 1 | Rehabilitation of Gabaldon Building | 11628072.02 | 1 | 7885654.93 | Completed | 1 | 2022-02-18 |  | Infra 2021-02 | 2021-09-222 | [5 empty] | Law-an Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  | CY 2022 |  |  | Completed
GABALDON 2020 | Region V | Camarines Sur | 112745 | Lupi CS | LUPI | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 9529471.9 | 1 | 7647166.69 | Completed | 1 | 2022-03-24 |  | Infra 2021-02 | 2021-10-260 | [5 empty] | Riders Corners Const & Gen. Merch. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region V | Camarines Sur | 113067 | Sipocot North Central School | Sipocot | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 7773645.3689 | 1 |  | Completed | 1 | [9 empty] | Jurassic Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region V | Camarines Sur | 112506 | Canaman Central School | Canaman | 3 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 4064090.3945 | 1 |  | Completed | 1 | [9 empty] | Jurassic Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region V | Camarines Sur | 112427 | Bula Central School | BULA | 5 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 3275410.57 | 1 |  | Completed | 1 | [9 empty] | Jurassic Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region V | Sorsogon | 114235 | Irosin Central School | IROSIN | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 3365279.79 | 1 |  | Completed | 1 | [8 empty] | 2020-12-16 | Cam. Sur Bicol Trading, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region V | Sorsogon City | 114534 | Bacon West Central School | Bacon West | 1 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 4467718.18 | 1 | 3089669.02 | Completed | 1 | 2022-02-18 |  | Infra 2021-02 | 2021-09-219 |  |  |  |  | 2021-10-21 | Law-an Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region V | Tabaco City | 114624 | Tabaco South CES | CITY OF TABACO | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 9438616.92 | 1 |  | Completed | 1 | [8 empty] | 2020-12-16 | Cam. Sur Bicol Trading, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2021 | Region V | Catanduanes | 113182 | Bato Central Elementary School | BATO | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 1421396 | 1 | 1390915.91 | COMPLETED | 1 | 2022-02-18 | 2022-02-18 | Infra 2021-02 | 2021-09-220 |  |  |  |  | 2021-09-29 | Duamon Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2021 | Region V | Catanduanes | 113352 | Virac Pilot Elementary School | VIRAC | 0 | 1 | 38 | 1 | Rehabilitation of Gabaldon Building | 19675334 | 1 | 15284032.31 | COMPLETED | 1 | 2022-04-17 | 2022-04-17 | Infra 2021-02 | 2021-09-221 |  |  |  |  | 2021-11-03 | LDN Builders & Const. Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2021 | Region V | Sorsogon | 114263 | Jose Alindogan CS | JUBAN | 2 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 18047175 | 1 | 17697175 | COMPLETED | 1 | 2022-05-08 | 2022-09-30 | Infra 2021-02 | 2021-09-218 |  |  |  |  | 2021-11-09 | Alhadrax Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office | CY 2022 |  |  | COMPLETED
GABALDON 2021 | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 | 1 | 28 | 1 | Rehabilitation of Gabaldon Building | 47362452 | 1 | 39888038.97 | COMPLETED | 1 | 2023-01-29 |  | Infra 2021-04 | 2021-12-482 | 2021-07-02 |  | 2021-07-27 |  |  | ZKR Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2022-12-01 | previous yrs | Regional Office | CY 2022 |  |  | COMPLETED
GABALDON 2021 | Region V | Tabaco City | 114624 | Tabaco South CES | CITY OF TABACO | 1 | 1 | 20 | 1 | Rehabilitation of Gabaldon Building | 16213839 | 1 | 8643152.52 | Reverted | 0.46 | 2022-12-22 |  | Infra 2021-04 | 2021-12-405 | 2021-07-02 |  | 2021-07-27 | 2021-12-02 |  | Gemwealth Const. & Trading | Terminated on Sep. 12, 2023, for reprogramming | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0.46 | 0 |  |  | Regional Office |  |  |  | REVERTED
GABALDON 2023 | Region V | Sorsogon | 114235 | Irosin Central School | IROSIN | 2 | 1 | 7 | 1 | Restoration & Conservation of Gabaldon Building | 18897276.98 | 1 | 15966021.18 | COMPLETED | 1 | 4/25/2024 | 9/26/2024 | 2023-09-001 | 23-09-001 | 2023-05-09 | 9/13/2023 | 9/25/2023 | 11/24/2023 | 12/28/2023 | Duamon Construction and Supply | NTP conforme December 28, 2023 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 12.24 | Division Office |  |  |  | COMPLETED
GABALDON 2024 | Region V | Sorsogon | 114034 | Bulan South CS | BULAN | 2nd | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 2717489.2 | 1 | 2714939.05 | Ongoing | 0.85 | 2025-09-09 |  | 24-09-001 | 24-09-001 | 2024-03-09 | 2024-11-09 | 9/23/2024 | 11/13/2024 | 3/14/2025 | 144 CUBITS BUILDERS & SUPPLY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.85 |  |  | Division Office |  |  | 11 | not yet started
GABALDON 2024 | Region V | Sorsogon | 114263 | Jose G. Alindogan ES | JUBAN | 2nd | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 17571213.3 | 1 | 17563523.95 | Ongoing | 0.4 | 2025-09-09 |  | 24-09-001 | 24-09-001 | 2024-03-09 | 2024-11-09 | 9/23/2024 | 11/13/2024 | 3/14/2025 | 144 CUBITS BUILDERS & SUPPLY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.4 |  |  | Division Office |  |  | 11 | not yet started
GABALDON 2024 | Region V | Tabaco City | 114624 | Tabaco South CES | CITY OF TABACO | 1st | 1 | 20 | 1 | Conservation and Restoration of Gabaldon School Building | 10693357.76 | 1 |  | Under Procurement | 0 |  |  | 2024-10-172 |  | 10/29/2024 | 2024-06-11 | 2024-03-12 | 2024-10-12 |  |  | Submitted RTA to Central Office; awaiting subaro release | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | Division Office |  |  | 12 | not yet started

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%