## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | No. of Classrooms | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated | Previous % | Difference | STOREY | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | Status as of July 4, 2025
NEWCON 2016 | REGION V | Albay | 301816 | Bonga National High School | Bacacay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Albay | 309515 | Cabasan National High School To Malilipot Nhs | Bacacay | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6910526.07 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Albay | 301880 | Cawayan National High School To Tiwi Agro-Industrial School | Bacacay | 1 |  | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Albay | 301821 | Cawayan National High School | Bacacay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Albay | 301810 | Malinao National High School | Malinao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Albay | 301810 | Malinao National High School | Malinao | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8860595.15 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Albay | 301853 | Naga National High School | Tiwi | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Albay | 301853 | Naga National High School | Tiwi | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6782016.72 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Albay | 301863 | Pili National High School | Bacacay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Albay | 301875 | San Jose National High School | Malilipot | 1 | 1 | 20 | 4STY20CL | BATCH 1 CL | 50013141.81 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION V | Albay | 301875 | San Jose National High School | Malilipot | 1 |  | 6 | 2STY6CL | BATCH 1 CL | 8928770.16 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Albay | 301875 | San Jose National High School | Malilipot | 1 | 1 | 4 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 11252547.49 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Albay | 309515 | Malilipot National High School |  | 1 | 1 | 2 | SHS UNIQUE WORKSHOP |  | 5626273.74 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Albay | 301879 | Sto. Domingo National High School |  | 1 | 1 | 1 | SHS UNIQUE WORKSHOP |  | 2813136.87 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Albay | 301810 | Malinao National High School |  | 1 | 1 | 1 | SHS UNIQUE WORKSHOP |  | 2813136.87 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Albay | 301816 | San Pablo High School To Bonga Nhs | Bacacay | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Albay | 301878 | Sogod National High School | Bacacay | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Albay | 301879 | Sto. Domingo National High School | Santo Domingo (Libog) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Albay | 301879 | Sto. Domingo National High School | Santo Domingo (Libog) | 1 | 1 | 8 | 2STY4CL | BATCH 13 CL | 13585698.5 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Albay | 301879 | Sto. Domingo National High School | Santo Domingo (Libog) | 1 |  | 6 | 2STY6CL | BATCH 13 CL | 8892671.82 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Albay | 301880 | Tiwi Agro-Industrial School | Tiwi | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8890910.7 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Albay | 301885 | Vinisitahan National High School | Bacacay | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9002029.2 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Albay | 301808 | Anislag National High School | Daraga (Locsin) | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23656314.795 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION V | Albay | 301808 | Anislag National High School | Daraga (Locsin) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2465078.77 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Albay | 301825 | Daraga National High School | Daraga (Locsin) | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION V | Albay | 301841 | Malabog National High School | Daraga (Locsin) | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Albay | 301845 | Manito National High School | Manito | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23506314.795 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION V | Albay |  | Manito National High School | Manito | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7443652.41 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Albay | 301869 | Rapu-Rapu National High School | Rapu-Rapu | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 11531152.7485 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Albay | 301828 | Itaran National High School | Polangui | 3 | 1 | 12 | 4STY12CL | BATCH 3 CL | 20767107.46 |  |  | Completed | 1 |  |  | P00070495LZ | 16FO0088 | 2017-10-26 | 2017-11-03 | 2017-11-15 | 2017-12-15 | 43086 | HI-TONE CONST. & DEV'T. CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Albay | 301833 | Libon Agro-Industrial High School | Libon | 3 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 7318809.93 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Albay | 301833 | Libon Agro-Industrial High School | Libon | 3 | 1 | 20 | 4STY20CL | BATCH 3 CL | 28520975.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION V | Albay | 301833 | Libon Agro-Industrial High School | Libon | 3 |  | 3 | 1STY3CL | BATCH 3 CL | 2686101.03 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Albay | 301865 | Polangui General Comprehensive High School | Polangui | 3 | 1 | 48 | 4STY16CL | BATCH 9 CL | 73169025.93 |  |  | Completed | 1 |  |  | P00073556LZ | 17FO0062 | 2017-09-08 | 2017-09-15 | 2017-09-27 | 2017-09-30 | 43026 | HERBANA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112206 | Daguit Es | Labo | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6519337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Norte | 173013 | Dancalan Es | Paracale | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1964740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112114 | Diezmo-Urena Es | Capalonga | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112209 | Florence Es | Labo | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112203 | G. Cale Es | Labo | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1062049.65 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301896 | Gonzalo Aler Nhs | Capalonga | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6376848.0401 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301896 | Gonzalo Aler Nhs | Capalonga | 1 |  | 2 | 1STY2CL | BATCH 11 CL | 1978606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112247 | Gumaus Es | Paracale | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2815828.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301898 | Jose Panganiban Nhs | Jose Panganiban | 1 | 1 | 30 | 3STY15CL | BATCH 9 CL | 42766026.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301898 | Jose Panganiban Nhs | Jose Panganiban | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301898 | Jose Panganiban Nhs | Jose Panganiban | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4859098.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112210 | Kabatuhan Es | Labo | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6369337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301917 | Leocadio Alejo Entienza Hs | Sta Elena | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10517131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301917 | Leocadio Alejo Entienza Hs | Sta Elena | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2509549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112117 | Lukbanan Es | Capalonga | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1889740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 309614 | Magsaysay Nhs | Capalonga | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6369337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112217 | Malaya Es | Labo | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2690828.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112219 | Maligaya Es | Labo | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2572332.196 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112119 | Marca-Murillo Es | Capalonga | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2695828.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112253 | Mateo Era Es | Paracale | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1087049.65 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112220 | Palali Es | Labo | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1889740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112284 | R. Oquindo Es | Santa Elena | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1883458.7763 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112152 | Regino A. Yet Es (Luklukan Es) | Jose Panganiban | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301913 | Rizal Nhs | Sta Elena | 1 | 1 | 12 | 3STY12CL | BATCH 3 CL | 18422268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301922 | Tulay Na Lupa Nhs | Labo | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21408013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301922 | Tulay Na Lupa Nhs | Labo | 1 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301922 | Tulay Na Lupa Nhs | Labo | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2509549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112175 | V. Gabo Es | Jose Panganiban | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1062049.65 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Norte | 173014 | Villa San Isidro Es | Santa Elena | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1087049.65 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Norte | 309613 | Alawihao Nhs | Daet (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Camarines Norte | 309613 | Alawihao Nhs | Daet (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Norte | 173019 | Anita V. Romero | Daet (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112298 | Banocboc Es | Vinzons | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2740828.12 |  |  | Completed | 1 | [10 empty] | Terminated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301889 | Basud Nhs | Basud | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301889 | Basud Nhs | Basud | 2 |  | 12 | 3STY6CL | BATCH 9 CL | 20834263.02 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301889 | Basud Nhs | Basud | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7288647.81 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301891 | Camarines Norte Nhs | Daet (Capital) | 2 | 1 | 30 | 3STY15CL | BATCH 9 CL | 42766026.9 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301891 | Camarines Norte Nhs | Daet (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2479549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112222 | Cayucyucan Es | Mercedes | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301892 | D.Q. Liwag Nhs | Vinzons | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301892 | D.Q. Liwag Nhs | Vinzons | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301919 | Froilan Lopez Hs (V) | San Vicente | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8264965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112090 | Hinampacan Es | Basud | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1914740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 173002 | Julia A. Abilgos Es | Daet (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112230 | Lope Manlangit Es | Mercedes | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2790828.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112231 | Mambungalon Es | Mercedes | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2690828.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301902 | Manguisoc Nhs | Mercedes | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6519337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301905 | Mercedes Hs | Mercedes | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301906 | Moreno Integrated School | Daet (Capital) | 2 | 1 | 24 | 3STY12CL | BATCH 9 CL | 36444537.58 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301906 | Moreno Integrated School | Daet (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2479549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Norte | 173018 | Paciano A. Magana Es | Daet (Capital) | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1012049.65 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112236 | Pambuhan Es | Mercedes | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2740828.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112237 | Quinapaguian Es | Mercedes | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1919740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112269 | Resettlement Es | San Lorenzo Ruiz (Imelda) | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1087049.65 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301914 | Sabang Nhs | Vinzons | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6519337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301918 | San Roque Nhs | Mercedes | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION V | Camarines Norte | 112139 | Up Alawihao Resettlement Es | Daet (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1889740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Norte | 301925 | Vinzons Pilot Nhs | Vinzons | 2 | 1 | 30 | 3STY15CL | BATCH 3 CL | 42766026.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309724 | Agay-Ayan Nhs | Tinambac | 4 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2650000 |  |  | Completed | 1 |  |  | P0070520LZ | 16FF0034 | June 6-28, 2016 | June 14, 2016 | June 28, 2016 | July 18, 2016 | 42583 | Grosin Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301928 | Antipolo National High School, Tinambac | Tinambac | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6681000 |  |  | Completed | 1 |  |  | P00070521LZ | 16FF0044 | June 13 - July 5, 2016 | June 21, 2016 | July 5, 2016 | August 5, 2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309774 | Antipolo Heights Integrated School | Pasacao | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-07-05 | 2016-07-13 | 2016-07-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112525 | Antolon Es | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  | P00073462LZ | 16FF0055 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112881 | Ayugao Ps | Presentacion (Parubcan) | 4 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1939740 |  |  | Completed | 1 |  |  | P00070527LZ | 16FF0035 | June 6-28, 2016 | June 14, 2016 | June 28, 2016 | July 18, 2016 | 42585 | HRB Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301931 | Baao National High School | Baao | 5 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112526 | Bacgong Ps | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  | P00073463LZ | 16FF0055 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301934 | Bagacay Hs | Tinambac | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6451273.8579 |  |  | Completed | 1 |  |  | P00073536LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112700 | Bagamelon Es | Libmanan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2146214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-12 | 2016-07-20 | 2016-08-02 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112790 | Bagolatao Es | Minalabac | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-12 | 2016-07-20 | 2016-08-02 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301937 | Bahi National Hs | Garchitorena | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 9374965 |  |  | Completed | 1 |  |  | P00070511LZ | 16FF0047 | June 13 - July 5, 2016 | June 21, 2016 | July 5, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112772 | Bal-Flor Es | Milaor | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 42521 | E. GARCIA CONST. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301941 | Banga Hs | Tinambac | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6685000 |  |  | Completed | 1 |  |  | P00070522LZ | 16FF0044 | June 13 - July 5, 2016 | June 21, 2016 | July 5, 2016 | August 5, 2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301942 | Barcelonita Fisheries School | Cabusao | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9081461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301942 | Barcelonita Fisheries School | Cabusao | 1 |  | 2 | 1STY1CL | BATCH 9 CL | 2246509.2394 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301944 | Binagasbasan Nhs | Garchitorena | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 7170500 |  |  | Completed | 1 |  |  | P00070512LZ | 16FF0041 | June 13 - July 5, 2016 | June 21, 2016 | July 5, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112794 | Bingcay Es | Minalabac | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 42521 | E. GARCIA CONST. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309703 | Bitaogan National High School | Presentacion (Parubcan) | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 7190500 |  |  | Completed | 1 |  |  | P00070513LZ | 16FF0046 | June 13 - July 5, 2016 | June 21, 2016 | July 5, 2016 | August 8, 2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112638 | Bocogan Es | Lagonoy | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073491LZ | 16FF0059 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302060 | Bonifacio D. Borebor Sr. Hs (Formerly:Tawog Nhs) | Caramoan | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8550000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309734 | Buenavista National Hs | Tinambac | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6446953.9604 |  |  | Completed | 1 |  |  | P00073537LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301947 | Bula Nhs | Bula | 5 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309768 | Cabotonan High School | Lagonoy | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6494205.4849 |  |  | Completed | 1 |  |  | P00073492LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112530 | Cadong Ps | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1929758.9174 |  |  | Completed | 1 |  |  | P00073464LZ | 16FF0055 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112593 | Cagamutan Ps | Garchitorena | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073484LZ | 16FF0058 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309757 | Cagbibi National High School | Pamplona | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6529337.64 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 42526 | HGG BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112707 | Camdilancha Elementary School | Libmanan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 42521 | E. GARCIA CONST. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 173525 | Candami Elementary School | Libmanan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 42526 | HGG BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112902 | Caranan Es (North) | Pasacao | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-12 | 2016-07-20 | 2016-08-02 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112903 | Caranan Es (South) | Pasacao | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6356887.0226 |  |  | Completed | 1 |  |  |  |  | 2016-02-19 | 2016-02-29 | 2016-03-15 |  | 42528 | ROLA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309708 | Catalotoan Hs | Sagñay | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8274000 |  |  | Completed | 1 |  |  | P00070515LZ | 16FF0040 | June 13 - July 05, 2016 | June 21, 2016 | July 5, 2016 | July 18, 2016 | 42583 | ZKR Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301960 | Coguit High School | Balatan | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2741627.1841 |  |  | Completed | 1 |  |  |  |  | 2016-07-19 | 2016-07-29 | 2016-08-09 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301961 | Colacling High School | Lupi | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9061461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301961 | Colacling High School | Lupi | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1123254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301963 | Dahat National Vocational Hs | Lagonoy | 4 | 1 | 6 | 3STY6CL | BATCH 9 CL | 9600418.359 |  |  | Completed | 1 |  |  | P00073493LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112778 | Dalipay Es | Milaor | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2046214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-05 | 2016-07-13 | 2016-07-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301964 | Dalupaon National High School | Pasacao | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8514965.05 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 42526 | HGG BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309718 | Dalupaon Nhs - Tinalmud Phs Annex | Pasacao | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8614965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112536 | Daraga Es | Caramoan | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073465LZ | 16FF0056 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112639 | Del Carmen Es | Lagonoy | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073494LZ | 16FF0059 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301966 | Del Gallego National High School | Del Gallego | 1 | 1 | 20 | 2STY10CL | BATCH 9 CL | 28246882.2047 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301966 | Del Gallego National High School | Del Gallego | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1133254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309723 | Del Rosario National Hs | Pamplona | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6519337.64 |  |  | Completed | 1 |  |  |  |  | 2016-07-05 | 2016-07-13 | 2016-07-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309744 | Don Mariano C. San Juan Hs | Libmanan | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6589337.64 |  |  | Completed | 1 |  |  |  |  | 2016-07-05 | 2016-07-13 | 2016-07-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301967 | Don Mariano Gonzalvo Memorial High School | Ragay | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14153441.1023 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301967 | Don Mariano Gonzalvo Memorial High School | Ragay | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6986271.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301969 | Don Servillano Platon Memorial Nhs | Tinambac | 4 | 1 | 12 | 2STY6CL | BATCH 13 CL | 17898494.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309758 | Eduardo V. Agomaa National High School | Libmanan | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6529337.64 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301989 | Federico P. Condat Nhs (Frmerly: Maangas Hs ) | Presentacion (Parubcan) | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 9065748.78 |  |  | Completed | 1 |  |  | P00070514LZ | 16FF0046 | June 13 - July 5, 2016 | June 21, 2016 | July 5, 2016 | August 8, 2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301974 | Gibgos National High School | Caramoan | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7614898.5421 |  |  | Completed | 1 |  |  | P00073466LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301975 | Goa National High School | Goa | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9361461.555 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301977 | Godofredo Reyes Sr. National High School | Ragay | 1 | 1 | 12 | 2STY6CL | BATCH 9 CL | 18162923.1122 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112539 | Gogon Elementary School | Caramoan | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073467LZ | 16FF0056 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301950 | Gregorio Ocampo Bercasio Mhs (Frmerly: Cagliliog Hs) | Tinambac | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8780000 |  |  | Completed | 1 |  |  | P00070523LZ | 16FF0039 | June 13 - July 05, 2016 | June 21, 2016 | July 5, 2016 | August 9, 2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301978 | Guijalo National High School | Caramoan | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6930000 |  |  | Completed | 1 |  |  | P00070509LZ | 16FF0045 | June 13 - July 05, 2016 | June 21, 2016 | July 5, 2016 | August 8, 2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112622 | Halawig-Gogon Elementary School | Goa | 4 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2020417 |  |  | Completed | 1 |  |  | P0070526LZ | 16FF0034 | June 6-28, 2016 | June 14, 2016 | June 28, 2016 | July 18, 2016 | 42583 | Grosin Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309721 | Huyonhuyon Hs | Tigaon | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6381638.831 |  |  | Completed | 1 |  |  | P00073535LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309741 | Juan L. Filipino Memorial High School | Goa | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6444716.2139 |  |  | Completed | 1 |  |  | P00073490LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 173516 | Kinahulogan Cs | Lagonoy | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2146214.1914 |  |  | Completed | 1 |  |  | P00073495LZ | 16FF0061 | August 15-Sept.6, 2016 | August 23, 2016 | September 6, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112547 | Lidong Es | Caramoan | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073468LZ | 16fFF0060 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112548 | Lubas Ps | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1955318.6381 |  |  | Completed | 1 |  |  | P00073469LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301990 | Malansad Nuevo High School | Libmanan | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8424965.05 |  |  | Completed | 1 |  |  |  |  | 2016-02-19 | 2016-02-29 | 2016-03-15 |  | 42526 | CHA CONST. AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112551 | Malindog Ps | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  | P00073470LZ | 16FF0053 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301993 | Mambayawas Hs | Libmanan | 2 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10910000 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309767 | Manangle High School | Sipocot | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9081461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112802 | Manapao Es | Minalabac | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2046214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-14 | 2016-07-21 | 2016-08-04 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112553 | Mandiclom Es | Caramoan | 4 | 1 | 3 | 1STY3CL | BATCH 3 CL | 3060000 |  |  | Completed | 1 |  |  | P00070525LZ | 16FF0035 | June 6-28, 2016 | June 14, 2016 | June 28, 2016 | July 18, 2016 | 42585 | HRB Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301996 | Mansalaya National High School | Del Gallego | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9101461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301996 | Mansalaya National High School | Del Gallego | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1133254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302032 | Maura N. Sibulo High School | Pamplona | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8414965.05 |  |  | Completed | 1 |  |  |  |  | 2016-07-05 | 2016-07-13 | 2016-07-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112555 | Minalaba Es | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  | P00073471LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302000 | Minalabac Nhs | Minalabac | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8364965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302001 | Nabua National High School | Nabua | 5 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309715 | Nato National High School | Sagñay | 4 | 1 | 12 | 2STY6CL | BATCH 13 CL | 17190000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309745 | Northern Plain Hs | Libmanan | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6589337.64 |  |  | Completed | 1 |  |  |  |  | 2016-07-05 | 2016-07-13 | 2016-07-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112645 | Olas Es | Lagonoy | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2948000 |  |  | Completed | 1 |  |  | P00073496LZ | 16FF0059 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302008 | Oring National High School | Caramoan | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7245000 |  |  | Completed | 1 |  |  | P00073472LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112689 | Padlos Es | Libmanan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2046214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-14 | 2016-07-21 | 2016-08-04 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309765 | Pag-Oring Nuevo National Hs | Libmanan | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6589337.64 |  |  | Completed | 1 |  |  |  |  | 2016-02-19 | 2016-02-29 | 2016-03-15 |  | 42526 | R.K.X ODIAMAR CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112911 | Pasacao Cs | Pasacao | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6356887.0226 |  |  | Completed | 1 |  |  |  |  | 2016-02-19 | 2016-02-29 | 2016-03-15 |  | 42521 | PHIL MANNA CONST. AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309769 | Pasacao Municipal High School | Pasacao | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8404965.05 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 42526 | E.P.L. GENERAL CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112896 | Pili Elementary School | Presentacion (Parubcan) | 4 | 1 | 3 | 1STY3CL | BATCH 3 CL | 3035610 |  |  | Completed | 1 |  |  | P00070528LZ | 16FF0035 | June 6-28, 2016 | June 14, 2016 | June 28, 2016 | July 18, 2016 | 42585 | HRB Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112563 | Pili-Centro Ps | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1955318.6381 |  |  | Completed | 1 |  |  | P00073473LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301976 | Pinaglabanan High School | Goa | 4 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9071461.5561 |  |  | Completed | 1 |  |  | P00073488LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301976 | Pinaglabanan High School | Goa | 4 |  | 1 | 1STY1CL | BATCH 9 CL | 1142329 |  |  | Completed | 1 |  |  | P00073488LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302019 | Presentacion Nhs (Formerly:Pili Nhs) | Presentacion (Parubcan) | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9324965.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309764 | R.T. Subastil Memorial Hs | Milaor | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6529337.64 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302020 | Ragay National Agricultural And Fisheries School (Rnafs) | Ragay | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14153441.1023 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302020 | Ragay National Agricultural And Fisheries School (Rnafs) | Ragay | 1 |  | 3 | 1STY1CL | BATCH 9 CL | 3399763.8591 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309714 | Sagñay Southeastern Hs | Sagñay | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6480000 |  |  | Completed | 1 |  |  | P00070516LZ | 16FF0048 | June 20 - July 12, 2016 | June 28, 2016 | July 12, 2016 | August 15, 2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309714 | Sagñay Southeastern Hs | Sagñay | 4 |  | 6 | 2STY6CL | BATCH 3 CL | 8404000 |  |  | Completed | 1 |  |  | P00070516LZ | 16FF0048 | June 20 - July 12, 2016 | June 28, 2016 | July 12, 2016 | August 15, 2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302023 | Sagrada Nhs, Tinambac | Tinambac | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6465703.8928 |  |  | Completed | 1 |  |  | P00073538LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112605 | Sagrada Ps | Garchitorena | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073485LZ | 16FF0058 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112717 | Salvacion Es | Libmanan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112913 | Salvacion Es | Pasacao | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-07-14 | 2016-07-21 | 2016-08-04 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309770 | San Pablo Integrated School | Libmanan | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6529337.64 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 42521 | E.P.L. GENERAL CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112807 | San Antonio Es | Minalabac | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-02-23 | 2016-03-02 | 2016-03-16 |  | 42521 | E.P.L. GENERAL CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112914 | San Antonio Es | Pasacao | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-07-14 | 2016-07-21 | 2016-08-04 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112567 | San Francisco Es | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2146214.1914 |  |  | Completed | 1 |  |  | P00073474LZ | 16FF0057 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 113010 | San Joaquin Es | San Fernando | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112809 | San Jose - Annex Ps | Minalabac | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302036 | San Jose Nhs | San Jose | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8684965 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302037 | San Juan National Hs | Libmanan | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8424965.05 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302038 | San Rafael National High School | Tigaon | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8950197.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302039 | San Ramon Pilot Nhs, Lagonoy (Frmerly:Sn.Ramon Pilot Hs) | Lagonoy | 4 | 1 | 6 | 2STY6CL | BATCH 9 CL | 15026937.0918 |  |  | Completed | 1 |  |  | P00073497LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302039 | San Ramon Pilot Nhs, Lagonoy (Frmerly:Sn.Ramon Pilot Hs) | Lagonoy | 4 |  | 4 | 2STY4CL |  |  |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302042 | San Ramon Provincial High School | Tinambac | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6781000 |  |  | Completed | 1 |  |  | P00070524LZ | 16FF0039 | June 13 - July 05, 2016 | June 21, 2016 | July 5, 2016 | August 9, 2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302046 | Sinuknipan National High School | Del Gallego | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13972542.8037 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302046 | Sinuknipan National High School | Del Gallego | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1133254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302047 | Sipocot Nhs | Sipocot | 1 | 1 | 30 | 2STY10CL | BATCH 1 CL | 39063930.2791 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301930 | Sisa Feliciano Mhs | Ragay | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14153441.1023 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION V | Camarines Sur | 301930 | Sisa Feliciano Mhs | Ragay | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1133254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112720 | Sogod Es | Libmanan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  |  | 2016-07-06 | 2016-07-14 | 2016-07-27 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112569 | Sta. Cruz Es | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2176214.1914 |  |  | Completed | 1 |  |  | P00073475LZ | 16FF0057 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112608 | Sumaoy Es | Garchitorena | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3124000 |  |  | Completed | 1 |  |  | P00073486LZ | 16FF0058 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302055 | Tabgon Nhs, Caramoan | Caramoan | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8900000 |  |  | Completed | 1 |  |  | P00070510LZ | 16FF0045 | June 13 - July 05, 2016 | June 21, 2016 | July 5, 2016 | August 8, 2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112571 | Tabiguian Es | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  | P00073476LZ | 16FF0057 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 112572 | Tabog Es | Caramoan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  | P00073477LZ | 16FF0057 | August 8-30, 2016 | August 16, 2016 | August 30, 2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302029 | Tinawagan Nhs | Tigaon | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 9072000 |  |  | Completed | 1 |  |  | P00070519LZ | 16FF0042 | June 13 - July 05, 2016 | June 21, 2016 | July 5, 2016 | July 18, 2016 | 42589 | ZKR Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302064 | Tomas A. Andaya Sr. National High School | Ragay | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14153441.1023 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302064 | Tomas A. Andaya Sr. National High School | Ragay | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 9093461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302064 | Tomas A. Andaya Sr. National High School | Ragay | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1133254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309771 | Villafuerte-Peña High School | San Jose | 4 | 1 | 12 | 2STY6CL | BATCH 3 CL | 17369930 |  |  | Completed | 1 |  |  | P00070518LZ | 16FF0043 | June 13 - July 5, 2016 | June 21, 2016 | July 5, 2016 | August 5, 2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302068 | Villazar National High School | Sipocot | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14133441.1023 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302068 | Villazar National High School | Sipocot | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6976271.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Camarines Sur | 302068 | Villazar National High School | Sipocot | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1128254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Camarines Sur | 309740 | Visita De Salog Hs | Goa | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6444641.316 |  |  | Completed | 1 |  |  | P00073490LZ | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Catanduanes | 302074 | Bato Rural Dhs | Bato | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 14033442.099 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Catanduanes | 302082 | Caramoran School Of Fisheries | Caramoran | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 11693844.661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Catanduanes | 302083 | Catanduanes Nhs | Virac (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198180.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION V | Catanduanes | 302094 | Pandan Sat | Pandan | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 39225883.854 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION V | Catanduanes | 302096 | San Andres Vocational School | San Andres (Calolbon) | 0 | 1 | 18 | 3STY18CL | BATCH 9 CL | 44059741.754 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION V | Catanduanes | 302107 | Viga Rural Dhs | Viga | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 14088442.099 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Iriga City | 500167 | Cristo Rey Is | Iriga City | 5 | 1 | 5 | 1STY5CL | BATCH 9 CL | 4700731.4693 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2016 | REGION V | Iriga City | 114453 | Iriga City Division Integrated Special School (Sped) To Santiago Is | Iriga City | 5 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6635102.46 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Iriga City | 302249 | Perpetual Help Nhs | Iriga City | 5 | 1 | 12 | 3STY12CL | BATCH 5 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Iriga City | 302252 | Sagrada Nhs | Iriga City | 5 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6635102.46 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Iriga City | 302252 | Sagrada Nhs | Iriga City | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2565263.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Iriga City | 114422 | San Agustin Es | Iriga City | 5 | 1 | 18 | 3STY9CL | BATCH 9 CL | 27248390.256 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION V | Iriga City | 302254 | San Antonio Nhs | Iriga City | 5 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Iriga City | 302254 | San Antonio Nhs | Iriga City | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2565263.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Iriga City | 302255 | San Pedro Nhs | Iriga City | 5 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1945386.46 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Iriga City | 114438 | San Ramon Es | Iriga City | 5 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1945386.46 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Iriga City | 302250 | Sta. Maria Hs | Iriga City | 5 | 1 | 6 | 3STY6CL | BATCH 3 CL | 10692131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Iriga City | 302250 | Sta. Maria Hs | Iriga City | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2565263.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Iriga City | 302256 | Sto. Niño Nhs | Iriga City | 5 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6635102.46 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Legaspi City | 310201 | Arimbay High School | Legazpi City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936272.404 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Legaspi City | 302257 | Banquerohan Nhs | Legazpi City (Capital) | 2 | 1 | 18 | 2STY6CL | BATCH 7 CL | 25660155.15 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION V | Legaspi City | 302257 | Banquerohan Nhs | Legazpi City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2444549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Legaspi City | 302262 | Gogon High School | Legazpi City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11443844.661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Legaspi City | 302262 | Gogon High School | Legazpi City (Capital) | 2 |  | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Legaspi City | 302259 | Homapon High School | Legazpi City (Capital) | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13260088.91 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION V | Legaspi City | 302259 | Homapon High School | Legazpi City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2444549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Legaspi City | 114475 | Legaspi City Hs To Bitano Es | Legazpi City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6670639.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Legaspi City | 114474 | Maslog National High School To Taysan Es | Legazpi City (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8553385.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Legaspi City | 302261 | Pag-Asa National High School | Legazpi City (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Legaspi City | 302263 | Pawa High School | Legazpi City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6670639.14 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Legaspi City | 114483 | Puro Elementary School | Legazpi City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11443844.661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Legaspi City | 310204 | Taysan Resettlement Integrated School | Legazpi City (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021462.555 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Ligao City | 301838 | Bacong Hs | City Of Ligao | 3 | 1 | 20 | 2STY20CL | BATCH 1 CL | 30521475.67 |  |  | Completed | 1 |  |  | P00070100LZ | 17FO0063 | 2017-09-08 | 2017-09-15 | 2017-10-26 | 2017-10-30 | 43055 | HERBANA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION V | Ligao City | 301838 | Bacong Hs | City Of Ligao | 3 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 8123309.93 |  |  | Completed | 1 |  |  | P00070208LZ | 16FO0056 | 2016-07-06 | 2016-07-14 | 2016-07-26 | 2016-08-11 | 42612 | WATERTON CONST. & REALTY CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Ligao City | 111813 | Basag Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1054558.55 |  |  | Completed | 1 |  |  | P00071052LZ | 16FO0054 | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-28 | 42590 | GROSIN CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Ligao City | 301814 | Bicol Regional Science Hs | City Of Ligao | 3 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1 |  |  | P00071062LZ | 16FO0073 | 2016-08-22 | 2016-08-30 | 2016-09-19 | 2016-10-06 | 42657 | AVIC CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Ligao City | 301817 | Cabarian Nhs | City Of Ligao | 3 | 1 | 15 | 3STY15CL | BATCH 5 CL | 23011987.88 |  |  | Completed | 1 |  |  | P00071063LZ | 16FO0086 | 2016-10-26 | 2016-11-03 | 2016-11-15 | 2017-01-09 | 42772 | ELKAN KONSTRAK & DEV'T. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION V | Ligao City | 301817 | Cabarian Nhs | City Of Ligao | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 5122706.62 |  |  | Completed | 1 |  |  | P00071671LZ | 16FO0059 | 2016-07-06 | 2016-07-14 | 2016-07-26 | 2016-08-12 | 42608 | AVIC CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Ligao City | 111839 | Catburawan Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1120558.55 |  |  | Completed | 1 |  |  | P00073552LZ | 16FO0066 | 2016-07-27 | 2016-08-04 | 2016-08-16 | 2016-09-03 | 42629 | EMRA CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Ligao City | 301820 | Deogracias P. Princesa Memorial Hs | City Of Ligao | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2463603.31 |  |  | Completed | 1 |  |  | P00074508LZ | 16FOO0061 | 2016-07-06 | 2016-07-14 | 2016-07-26 | 2016-08-12 | 42608 | GROSIN CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Ligao City | 301820 | Deogracias P. Princesa Memorial Hs | City Of Ligao | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18422268.79 |  |  | Completed | 1 |  |  | P00073553LZ | 17FO0064 | 2016-07-21 | 2016-07-29 | 2016-08-10 | 2016-08-26 | 42620 | HERBANA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Ligao City | 111819 | Herrera Es | City Of Ligao | 3 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1902266.47 |  |  | Completed | 1 |  |  | P00071053LZ | 16FO0072 | 2016-08-22 | 2016-08-30 | 2016-09-13 | 2016-09-29 | 42656 | NGS CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Ligao City | 321701 | Ligao City National Technical -Vocational High School | City Of Ligao | 3 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8753465.051 |  |  | Completed | 1 |  |  | P00070096LZ | 16FO0036 | 2016-03-31 | 2016-04-08 | 2016-04-12 | 2016-05-23 | 42523 | ALXM CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Ligao City | 321701 | Ligao City National Technical -Vocational High School | City Of Ligao | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 5208206.62 |  |  | Completed | 1 |  |  | P00070205LZ | 16FOO0058 | 2016-07-06 | 2016-07-14 | 2016-07-26 | 2016-08-11 | 42608 | EMRA CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Ligao City | 301837 | Ligao Nhs | City Of Ligao | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00073554LZ | 17FO0067 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-12 | 43038 | HI-TONE CONST. & DEV'T. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION V | Ligao City | 301837 | Ligao Nhs | City Of Ligao | 3 |  | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 |  |  | P00073555LZ | 17FO0068 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-12 | 43038 | WCS CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION V | Ligao City | 301837 | Ligao Nhs | City Of Ligao | 3 |  | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00073556LZ | 17FO0066 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-12 | 43038 | PEDXING BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Ligao City | 111845 | Mahaba Es | City Of Ligao | 3 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6374451.05 |  |  | Completed | 1 |  |  | P00071059LZ | 16FO0071 | 2016-08-22 | 2016-08-30 | 2016-09-13 | 2016-09-29 | 42656 | QDC CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Ligao City | 111845 | Mahaba Es | City Of Ligao | 3 |  | 8 | 2STY8CL | BATCH 5 CL | 11513897.03 |  |  | Completed | 1 |  |  | P00071060LZ | 16FO0070 | 2016-08-22 | 2016-08-30 | 2016-09-13 | 2016-09-29 | 42656 | ATHENA CONST. & DEV'T. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Ligao City | 231008 | Malama Es, Bagacay Ext. | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1126058.55 |  |  | Completed | 1 |  |  | P00071061LZ | 16FO0065 | 2016-07-21 | 2016-07-29 | 2016-08-10 | 2016-08-26 | 42620 | EMRA CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Ligao City | 301858 | Oma-Oma Nhs | City Of Ligao | 3 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8980471.77 |  |  | Completed | 1 |  |  | P00070097LZ | 16FO0060 | 2016-07-06 | 2016-07-14 | 2016-07-26 | 2016-08-12 | 42607 | ZKR CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Ligao City | 301858 | Oma-Oma Nhs | City Of Ligao | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2743603.31 |  |  | Completed | 1 |  |  | P00070206LZ | 16FO0067 | 2016-07-27 | 2016-08-04 | 2016-08-16 | 2016-09-05 | 42632 | AVIC CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Ligao City | 111826 | Paulba Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1105558.55 |  |  | Completed | 1 |  |  | P00071054LZ | 16FO0064 | 2016-07-21 | 2016-07-29 | 2016-08-10 | 2016-08-26 | 42620 | EMRA CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Ligao City | 301862 | Paulba Nhs | City Of Ligao | 3 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11736897.03 |  |  | Completed | 1 |  |  | P00070485LZ | 16FO0075 | 2016-09-07 | 2016-09-15 | 2016-09-27 | 2016-10-11 | 42667 | MAKAPA CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Ligao City | 301862 | Paulba Nhs | City Of Ligao | 3 |  | 12 | 2STY6CL | BATCH 3 CL | 16894943.54 |  |  | Completed | 1 |  |  | P00070486LZ | 16FO0076 | 2016-09-07 | 2016-09-15 | 2016-09-27 | 2016-10-11 | 42667 | WCS CONST. INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Ligao City | 111828 | Pinamaniquian Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1095558.55 |  |  | Completed | 1 |  |  | P00071055LZ | 16FO0063 | 2016-07-21 | 2016-07-29 | 2016-08-10 | 2016-08-26 | 42620 | HERBANA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Ligao City | 111829 | Tambo Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1054558.55 |  |  | Completed | 1 |  |  | P00071056LZ | 16FO0055 | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-28 | 42610 | GROSIN CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Ligao City | 111832 | Tiongson Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1126058.55 |  |  | Completed | 1 |  |  | P00071057LZ | 16FO0053 | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-28 | 42610 | GROSIN CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Ligao City | 111833 | Tupas Es | City Of Ligao | 3 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1126058.55 |  |  | Completed | 1 |  |  | P00071058LZ | 16FO0062 | 2016-07-21 | 2016-07-29 | 2016-08-10 | 2016-10-26 | 42620 | EMRA CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Masbate | 302121 | Buenavista National High School | Uson | 3 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8567395.36 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Masbate | 302129 | Cataingan National High School | Cataingan | 3 | 1 | 30 | 2STY10CL | BATCH 9 CL | 38562931.8577 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION V | Masbate | 302131 | Del Carmen National High School | Uson | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9056462.555 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Masbate | 302131 | Del Carmen National High School | Uson | 3 |  | 12 | 2STY12CL | BATCH 9 CL | 15872795.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Masbate | 302129 | Del Carmen National High School To Catingan Nhs | Uson | 3 |  | 8 | 2STY8CL | BATCH 9 CL | 11883466.88 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Masbate | 302132 | Dimasalang National High School | Dimasalang | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6334066.1721 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Masbate | 302132 | Dimasalang National High School | Dimasalang | 3 |  | 18 | 2STY6CL | BATCH 9 CL | 25642186.08 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION V | Masbate | 309914 | Mayor Tomas V. Rivera Memorial High School | Cawayan | 3 | 1 | 20 | 2STY4CL | BATCH 3 CL | 32962868.01 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION V | Masbate | 309942 | San Carlos Nhs | Palanas | 3 | 1 | 6 | 1STY3CL | BATCH 9 CL | 5869821.8728 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Masbate | 302171 | Santos E. Conag National High School | Esperanza | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22847878.13 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | Uson | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8559395.36 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | Uson | 3 |  | 6 | 2STY6CL | BATCH 9 CL | 8562395.36 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | Uson | 3 |  | 4 | 2STY4CL | BATCH 9 CL | 6582573.6 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Masbate City | 321803 | A. Delos Reyes Integrated School | City Of Masbate (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2567708.3333 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Masbate City | 321805 | Bantigue High School | City Of Masbate (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2536458.3333 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Masbate City | 321804 | Bayombon High School | City Of Masbate (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2557291.6667 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Masbate City | 302133 | Capitolina O. Legaspi Mhs | City Of Masbate (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2536458.3333 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Masbate City | 302148 | Masbate National Comprehensive High School | City Of Masbate (Capital) | 2 | 1 | 15 | 3STY15CL | BATCH 11 CL | 21650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION V | Masbate City | 302148 | Masbate National Comprehensive High School | City Of Masbate (Capital) | 2 |  | 9 | 3STY9CL | BATCH 11 CL | 15150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION V | Masbate City | 302148 | Masbate National Comprehensive High School | City Of Masbate (Capital) | 2 |  | 8 | 2STY8CL | BATCH 11 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Masbate City | 321806 | Nursery High School | City Of Masbate (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Naga City | 302264 | Camarines Sur National High School | Naga City | 3 | 1 | 48 | 4STY24CL | BATCH 11 CL | 71192514.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION V | Naga City | 302265 | Cararayan National High School | Naga City | 3 | 1 | 12 | 2STY6CL | BATCH 9 CL | 17300000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Naga City | 302265 | Cararayan National High School | Naga City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Naga City | 302268 | Naga City Science High School | Naga City | 3 | 1 | 9 | 3STY9CL | BATCH 9 CL | 14150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION V | Naga City | 310301 | Tinago National High School | Naga City | 3 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 302179 | Abucay Nhs | Pilar | 1 | 1 | 8 | 2STY8CL | BATCH 11 CL | 12379170.5527 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Sorsogon | 302179 | Abucay Nhs | Pilar | 1 |  | 4 | 2STY4CL | BATCH 11 CL | 7365365.1077 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 114137 | Alin Elementary School | Donsol | 1 | 1 | 6 | 1STY3CL | BATCH 13 CL | 5605184.88 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 114137 | Alin Elementary School | Donsol | 1 |  | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 302183 | Bagatao Nhs | Magallanes (34 Brgys) | 1 | 1 | 4 | 1STY4CL | BATCH 11 CL | 3811375.2325 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 114338 | Banuyo Es | Pilar | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1974900.8435 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114274 | Behia Elementary School | Magallanes (34 Brgys) | 1 | 1 | 6 | 1STY3CL | BATCH 13 CL | 6133350.5048 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 114275 | Biga Es | Magallanes (34 Brgys) | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2120080.0574 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 310007 | Biton High School | Magallanes (34 Brgys) | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 302199 | Buenavista Nhs | Castilla | 1 | 1 | 6 | 2STY6CL | BATCH 11 CL | 9021461.555 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 114366 | Cabiguan Es | Pilar | 1 | 1 | 4 | 1STY2CL | BATCH 13 CL | 3986096.4904 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 302194 | Cabugao Nhs | Donsol | 1 | 1 | 6 | 1STY3CL | BATCH 11 CL | 6782273.7048 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 302221 | Cagbolo National Vocational Hs | Magallanes (34 Brgys) | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 114082 | Casay Es | Casiguran | 1 | 1 | 6 | 1STY3CL | BATCH 13 CL | 5605184.88 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 114082 | Casay Es | Casiguran | 1 |  | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 302197 | Casiguran Technical Vocational School | Casiguran | 1 | 1 | 32 | 2STY8CL | BATCH 13 CL | 43509370.3668 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION V | Sorsogon | 114370 | Comapo-Capo Es | Pilar | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114122 | Cumadcad Cs | Castilla | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1974900.8435 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 302201 | Cumadcad Nhs | Castilla | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 302201 | Cumadcad Nhs | Castilla | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 114372 | Del Rosario Es | Pilar | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 302206 | Donsol National Comprehensive Hs - Sta. Cruz Extension Hs | Donsol | 1 | 1 | 6 | 2STY6CL | BATCH 11 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 302207 | Donsol Vocational Hs | Donsol | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 17217313.8288 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION V | Sorsogon | 114146 | Gura Elementary School | Donsol | 1 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Sorsogon | 114294 | Lapinig Es | Magallanes (34 Brgys) | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2029343.0487 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114349 | Lumbang Es | Pilar | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 302222 | Magallanes National High School | Magallanes (34 Brgys) | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.5917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Sorsogon | 302220 | Magallanes National Vocational Hs | Magallanes (34 Brgys) | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION V | Sorsogon | 114352 | Marifosque Es | Pilar | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114126 | Mayon Es | Castilla | 1 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Sorsogon | 302226 | Mayon National High School | Castilla | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Sorsogon | 114149 | Ogod Es | Donsol | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 114149 | Ogod Es | Donsol | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 302229 | Palanas Nhs | Pilar | 1 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8376264.352 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 302230 | Pilar National Comprehensive Hs | Pilar | 1 | 1 | 10 | 2STY10CL | BATCH 11 CL | 13149949.3958 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION V | Sorsogon | 302230 | Pilar National Comprehensive Hs | Pilar | 1 |  | 8 | 2STY8CL | BATCH 11 CL | 11199162.8695 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Sorsogon | 302230 | Pilar National Comprehensive Hs | Pilar | 1 |  | 6 | 2STY6CL | BATCH 11 CL | 8456914.0025 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 114282 | Pili Es | Magallanes (34 Brgys) | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1993048.2452 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114385 | Poctol Es | Pilar | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114150 | Rawis Elementary School | Donsol | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 114131 | Rosal Es | Castilla | 1 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Sorsogon | 114388 | Salvacion Es | Pilar | 1 | 1 | 6 | 1STY3CL | BATCH 13 CL | 5710818.005 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 302236 | Salvacion Nhs | Pilar | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 7150818.2558 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 302236 | Salvacion Nhs | Pilar | 1 |  | 6 | 2STY6CL | BATCH 11 CL | 8376264.352 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 114152 | San Isidro Es | Donsol | 1 | 1 | 3 | 1STY3CL | BATCH 13 CL | 3082851.684 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Sorsogon | 114152 | San Isidro Es | Donsol | 1 |  | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114093 | San Juan Es | Casiguran | 1 | 1 | 6 | 1STY3CL | BATCH 13 CL | 5605184.88 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 114093 | San Juan Es | Casiguran | 1 |  | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 310008 | San Rafael Nhs | Pilar | 1 | 1 | 3 | 1STY3CL | BATCH 11 CL | 3391136.8524 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Sorsogon | 310008 | San Rafael Nhs | Pilar | 1 |  | 4 | 1STY2CL | BATCH 11 CL | 3670964.8894 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 114134 | San Vicente Es | Castilla | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 114135 | Sogoy Es | Castilla | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114181 | Tinanogan Es | Donsol | 1 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Sorsogon | 114185 | Bagacay Es | Gubat | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 302184 | Barcelona National Comprehensive High School | Barcelona | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8380614.751 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 114206 | Bongsaran Es | Gubat | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 302190 | Bulan Nhs | Bulan | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11275889.3917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Sorsogon | 302190 | Bulan Nhs | Bulan | 2 |  | 30 | 2STY10CL | BATCH 13 CL | 39204569.5791 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION V | Sorsogon | 302192 | Bulusan Nhs | Bulusan | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6442031.0381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 114209 | Cabigaan Es | Gubat | 2 | 1 | 4 | 1STY2CL | BATCH 13 CL | 3999905.48 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 114391 | Calao Es | Prieto Diaz | 2 | 1 | 4 | 1STY2CL | BATCH 13 CL | 3877212.08 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 114189 | Carriedo Es | Gubat | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114228 | Carriedo Es | Irosin | 2 | 1 | 6 | 1STY2CL | BATCH 13 CL | 6009618.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 114190 | Cogon Es | Gubat | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114011 | Danao Es | Bulan | 2 | 1 | 9 | 1STY3CL | BATCH 13 CL | 9172777.32 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION V | Sorsogon | 114038 | G. Del Pilar Es | Bulan | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2061299.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114232 | Gabao Es | Irosin | 2 | 1 | 6 | 1STY2CL | BATCH 13 CL | 5815818.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 302212 | Gallanosa National High School | Irosin | 2 | 1 | 16 | 2STY8CL | BATCH 13 CL | 22145232.0334 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION V | Sorsogon | 302212 | Gallanosa National High School | Irosin | 2 |  | 6 | 2STY6CL | BATCH 13 CL | 8389614.751 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 302214 | Gubat National High School | Gubat | 2 | 1 | 24 | 2STY8CL | BATCH 13 CL | 33217847.9751 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION V | Sorsogon | 302187 | Juban National High School | Juban | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6422031.0381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 114193 | Jupi Es | Gubat | 2 | 1 | 6 | 1STY3CL | BATCH 13 CL | 5798984.88 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 114318 | Lajong Es | Matnog | 2 | 1 | 4 | 1STY2CL | BATCH 13 CL | 4122598.08 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 302225 | Matnog Nhs | Matnog | 2 | 1 | 12 | 2STY4CL | BATCH 13 CL | 19275092.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Sorsogon | 114020 | Monte Calvario E/S | Bulan | 2 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2986550.94 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION V | Sorsogon | 114043 | N. Roque Es | Bulan | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2061299.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 175006 | Nenita E. Oandasan Mem. Sch. | Prieto Diaz | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114199 | Payawin Es | Gubat | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 302232 | Prieto Diaz Nhs | Prieto Diaz | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8380614.751 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Sorsogon | 302232 | Prieto Diaz Nhs | Prieto Diaz | 2 |  | 4 | 2STY4CL | BATCH 13 CL | 6422031.0381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 175016 | Severino E. Fortes Mem. School Es | Irosin | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2061299.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114030 | Somagongsong Es | Bulan | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2061299.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114217 | Sta. Ana Es | Gubat | 2 | 1 | 4 | 1STY2CL | BATCH 13 CL | 3999905.48 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon | 113996 | Sta. Lourdes Elementary School | Barcelona | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2061299.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 302245 | Sta. Magdalena Nhs | Santa Magdalena | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12871755.3761 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION V | Sorsogon | 114054 | Sta. Teresita Es | Bulan | 2 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1163049.69 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Sorsogon | 114269 | Taboc Es | Juban | 2 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1208294.659 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Sorsogon | 114202 | Tiris Es | Gubat | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon | 114246 | Tongdol Es | Irosin | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2003206.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Sorsogon City | 310405 | Bogña Integrated School | City Of Sorsogon (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon City | 302272 | Celestino G. Tabuena Memorial Nhs | City Of Sorsogon (Capital) | 1 | 1 | 10 | 2STY10CL | BATCH 11 CL | 12771310.09 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION V | Sorsogon City | 302280 | Lydia D. Martinez Memorial High School | City Of Sorsogon (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION V | Sorsogon City | 302275 | Rawis National High School | City Of Sorsogon (Capital) | 1 | 1 | 10 | 2STY10CL | BATCH 11 CL | 12771310.093 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION V | Sorsogon City | 302279 | Sorsogon National High School | City Of Sorsogon (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22937798.35 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Sorsogon City | 302279 | Sorsogon National High School | City Of Sorsogon (Capital) | 1 |  | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Sorsogon City | 302279 | Sorsogon National High School | City Of Sorsogon (Capital) | 1 |  | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION V | Tabaco City | 302281 | Bantayan Nhs | City Of Tabaco | 1 | 1 | 2 | 1STY1CL | BATCH 9 CL | 2226509.2394 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Tabaco City | 302281 | Bantayan Nhs | City Of Tabaco | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Tabaco City | 302281 | Bantayan Nhs | City Of Tabaco | 1 |  | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION V | Tabaco City | 310501 | Bogñabong High School | City Of Tabaco | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Tabaco City | 302282 | San Antonio Nhs, Tabaco | City Of Tabaco | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION V | Tabaco City | 114599 | San Carlos Es | City Of Tabaco | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Tabaco City | 302283 | San Lorenzo Nhs | City Of Tabaco | 1 | 1 | 2 | 1STY1CL | BATCH 9 CL | 2226509.2394 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION V | Tabaco City | 302283 | San Lorenzo Nhs | City Of Tabaco | 1 |  | 12 | 3STY6CL | BATCH 9 CL | 22887689.322 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Tabaco City | 302283 | San Lorenzo Nhs | City Of Tabaco | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION V | Tabaco City | 302285 | Tabaco National High School | City Of Tabaco | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Tabaco City | 302285 | Tabaco National High School | City Of Tabaco | 1 |  | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Tabaco City | 302285 | Tabaco National High School | City Of Tabaco | 1 |  | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION V | Tabaco City | 302285 | Tabaco National High School | City Of Tabaco | 1 |  | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION V | Tabaco City | 302285 | Tabaco National High School | City Of Tabaco | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8665776.7976 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION V | Tabaco City | 302285 | Tabaco National High School | City Of Tabaco | 1 |  | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2014 | REGION V | CATANDUANES | 309802 | Cobo IS | PANDAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | 2015-12-08 | 2015-12-04 | 050414S00020 | 15FH0027 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-05 | 2015-08-13 | SULVIR ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2014 | REGION V | CATANDUANES | 302095 | Panganiban NHS | PANGANIBAN (PAYO) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.