## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | DUE TO | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | SCOPE | Unnamed: 45 | Status as of July 4, 2025
QRF 2019 | Region V | Albay | 112066 | Biyong Elementary School | TIWI | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 640582.05 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 112067 | Bolo Elementary School | TIWI | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 608083.5 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 172502 | Lourdes Elementary School | TIWI | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 632989.47 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 112073 | Mayong Elementary School | TIWI | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 404054.19 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 112077 | Putsan Elementary School | TIWI | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 778044.54 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 301880 | Tiwi Agro-Industrial School | TIWI | 1 | 1 | 13 | REPAIR OF CLASSROOMS | 2355385.99 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111663 | Bongalon Elementary School | DARAGA (LOCSIN) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1344607.94 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 309518 | Kilicao High School | DARAGA (LOCSIN) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1832632.12 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111673 | Maroroy ES | DARAGA (LOCSIN) | 2 | 1 | 1 | REPAIR OF CLASSROOMS | 455094.43 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 301809 | San Vicente Grande High School | DARAGA (LOCSIN) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2332171.43 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111704 | Villahermosa Elementary School | DARAGA (LOCSIN) | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2878059.57 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111900 | Manumbalay Elementary School | MANITO | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2712324.78 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 112041 | Nagcalsot Elementary School | RAPU-RAPU | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3029604.97 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111787 | Bonbon Elementary School | LIBON | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 947712.97 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111791 | Caguscos Elementary School | LIBON | 3 | 1 | 1 | REPAIR OF CLASSROOMS | 459045.81 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111762 | Libon East Central School | LIBON | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 3213751.79 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 309504 | Rawis High School | LIBON | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 755548.38 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111802 | Sagrada Familia Elementary School | LIBON | 3 | 1 | 1 | REPAIR OF CLASSROOMS | 315926.71 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 500155 | San Agustin Integrated School | LIBON | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1371797.93 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111779 | San Vicente Elementary School | LIBON | 3 | 1 | 1 | REPAIR OF CLASSROOMS | 456804.45 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111780 | Sta. Cruz Elementary School | LIBON | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 2070117.73 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111782 | West Carisac Elementary School | LIBON | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 740098.86 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111971 | Don Jose Pavia Central School | PIO DURAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 687525.54 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112116 | Francisco V. Aler ES | CAPALONGA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1275934.09 | 1 | 1218019.62 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301896 | Gonzalo Aler NHS | CAPALONGA | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 4700864.88 | 1 |  | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 309614 | Magsaysay National High School | CAPALONGA | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 1780252.76 | 1 |  | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 309610 | Victoria J. Tuacar National HS | CAPALONGA | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 2406465.85 | 1 |  | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112129 | Villa Aurora ES | CAPALONGA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1275934.09 | 1 | 3862545.49 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112149 | Calero ES | JOSE PANGANIBAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1171604.8 | 1 | 1043690.82 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112150 | Calogcog ES | JOSE PANGANIBAN | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 2087168.86 | 1 | 1162707.13 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112170 | Cresencia B. Enverga ES (Sta. Cruz ES) | JOSE PANGANIBAN | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 3536970.92 | 1 | 1017159.47 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 309619 | Gawad Kalinga HS | JOSE PANGANIBAN | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 1465034 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 309619 | Gawad Kalinga HS | JOSE PANGANIBAN | 1 |  | 3 | REPAIR OF CLASSROOMS | 1431252.09 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112151 | Jose Panganiban ES | JOSE PANGANIBAN | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 4269793.61 | 1 | 3163194.92 | Completed | 1 | 2023-11-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112163 | Larap ES | JOSE PANGANIBAN | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 3170013.15 | 1 | 1196211.45 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112154 | Osmena ES (Lukban ES) | JOSE PANGANIBAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1254934.09 | 1 | 1948834.94 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112166 | San Isidro ES | JOSE PANGANIBAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1981255.73 | 1 | 1061960.82 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112158 | Segundo Aguirre (Sta Rosa Norte.) | JOSE PANGANIBAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1392514.58 | 1 | 3525952.5 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112172 | Sta. Milagrosa ES | JOSE PANGANIBAN | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1352545.62 | 1 | 967137.57 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112173 | Tawig ES | JOSE PANGANIBAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1275934.09 | 1 | 1017159.47 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112199 | Bagong Silang II ES | LABO | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2038285.57 | 1 | 1254750.45 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112200 | Bagong Silang III ES | LABO | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2038285.57 | 1 | 1309904.74 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301893 | Daguit NHS | LABO | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 5733405.76 | 1 |  | Completed | 1 | 2020-04-14 | [7 empty] | 2019-12-16 | FIRST QUANTUM BUILDERS ID BUILDERS CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112180 | Don Miguel Lukban ES | LABO | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1274608.94 | 1 | 1017159.47 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112181 | E. Obmana ES | LABO | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1187452.91 | 1 | 1982137.28 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112212 | Kanapawan ES | LABO | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2450236.7 | 1 | 1235407.56 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301894 | Labo Science and Tech. HS | LABO | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 6018846.22 | 1 |  | Completed | 1 | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112190 | Malasugui ES | LABO | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1275934.09 | 1 | 1213812.24 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 500635 | Palali Integrated School | LABO | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 2406465.85 | 1 |  | Completed | 1 | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112194 | Pampang ES | LABO | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1254934.09 | 1 | 1960342.34 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112195 | Severino Francisco Elementary Sch. | LABO | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 1465034 | 1 | 1384603.19 | Completed | 1 | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 3470256.44 | 1 |  | Completed | 1 | 2020-04-14 | [7 empty] | 2019-12-16 | FIRST QUANTUM BUILDERS ID BUILDERS CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301890 | Batobalani National High School | PARACALE | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 5877100.25 | 1 |  | Completed | 1 | 2020-04-14 | [7 empty] | 2019-12-16 | FIRST QUANTUM BUILDERS ID BUILDERS CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301890 | Batobalani National High School | PARACALE | 1 |  | 4 | REPAIR OF CLASSROOMS | 1563467.03 | 1 |  | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | GOLDEN FLEECE CONSTRUCTION AND SUPPLY INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112246 | Dalnac ES | PARACALE | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1353013.75 | 1 | 1184532.47 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | GOLDEN FLEECE CONSTRUCTION AND SUPPLY INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112259 | Tawig ES | PARACALE | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 2118668.86 | 1 | 1205924.25 | Completed | 1 | 2020-04-14 | [7 empty] | 2019-12-16 | FIRST QUANTUM BUILDERS ID BUILDERS CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112259 | Tawig ES | PARACALE | 1 |  | 3 | REPAIR OF CLASSROOMS | 1275934.09 | 1 | 1184406.13 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | GOLDEN FLEECE CONSTRUCTION AND SUPPLY INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112260 | Tugos ES | PARACALE | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2462463.07 | 1 | 5231752.85 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | GOLDEN FLEECE CONSTRUCTION AND SUPPLY INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112279 | Bulala Elementary School | SANTA ELENA | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 4872710.06 | 1 | 1146074.8 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112280 | Dygico ES | SANTA ELENA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1208452.91 | 1 | 2277001.9 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | YAKAL CONSTRUCTION AND SUPPLY | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112281 | Earth'S Bounty ES | SANTA ELENA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1187452.91 | 1 | 2617131.57 | Completed | 1 | 2020-04-14 | [7 empty] | 2019-12-16 | AVZ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301917 | Leocadio Alejo Entienza HS | SANTA ELENA | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 3491256.44 | 1 |  | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112282 | M. Hebrado ES | SANTA ELENA | 1 | 1 | 13 | REPAIR OF CLASSROOMS | 5248371.39 | 1 | 2431393.54 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | YAKAL CONSTRUCTION AND SUPPLY | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 173011 | Maulawin ES | SANTA ELENA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1622046.91 | 1 | 1196766.21 | Completed | 1 | 2020-04-14 | [7 empty] | 2019-12-16 | AVZ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 173007 | Patag Ilaya ES | SANTA ELENA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1759004.21 | 1 | 2280114.95 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | YAKAL CONSTRUCTION AND SUPPLY | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301913 | Rizal NATIONAL HIGH SCHOOL | SANTA ELENA | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 5293807.27 | 1 |  | Completed | 1 | 2020-04-14 | [7 empty] | 2019-12-16 | AVZ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112089 | Guinatungan ES | BASUD | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1228127.76 | 1 | 1203796.49 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112101 | Plaridel ES | BASUD | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 975804.32 | 1 | 1220029.49 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | GREATWALL ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301915 | San Felipe NHS | BASUD | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1345218.15 | 1 |  | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301915 | San Felipe NHS | BASUD | 2 |  | 0 | REPAIR OF CLASSROOMS | 1847862.76 | 1 |  | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | GREATWALL ENGINEERING | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 309608 | Tuaca HS | BASUD | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 4012269.69 | 1 |  | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | GREATWALL ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112130 | A. Pabico Abordo ES | DAET (Capital) | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 4148623.17 | 1 | 1290352.09 | Completed | 1 | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112133 | Bagasbas ES | DAET (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1340014.58 | 1 | 1221587.09 | Completed | 1 | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301891 | Camarines Norte National HS | DAET (Capital) | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 227523.06 | 1 |  | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | GREATWALL ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112135 | Dogongan ES | DAET (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1227594.64 | 1 | 1798122.15 | Completed | 1 | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112146 | Goito Pimentel ES | DAET (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1227594.64 | 1 | 1145879.22 | Completed | 1 | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112138 | Pandan Elementary School | DAET (Capital) | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1942607.32 | 1 | 1180521.05 | Completed | 1 | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112148 | ZURBANO ELEMENTARY SCHOOL | DAET (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1207426.77 | 1 | 969616.54 | Completed | 1 | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112224 | F. P. Ibasco ES | MERCEDES | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1387861.78 | 1 | 2375085.7 | Completed | 1 | 2020-04-08 | [7 empty] | 2019-12-10 | WCVC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112225 | Gaboc Elementary School | MERCEDES | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1279601.61 | 1 | 812566.4 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301907 | Pablo S. Villafuerte HS | MERCEDES | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 4269793.61 | 1 |  | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | GREATWALL ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301918 | San Roque National High School | MERCEDES | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1227101.61 | 1 |  | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112270 | S. DELOS SANTOS ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 829119.55 | 1 | 2247907.29 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 173003 | Cabanbanan ES | SAN VICENTE | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 881619.55 | 1 | 1377953.48 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112277 | V. Ricafrente ES | SAN VICENTE | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1208452.91 | 1 | 2689235.23 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 173004 | Cahabaan Elementary School | TALISAY | 2 | 1 | 1 | REPAIR OF CLASSROOMS | 494485.89 | 1 | 1202621.87 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | JCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112290 | Gabon ES | TALISAY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2268004.32 | 1 | 2235026.42 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | JCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301916 | San Francisco National High School | TALISAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1389994.15 | 1 |  | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | JCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112295 | Sta. Elena Elementary School | TALISAY | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2709144.85 | 1 | 1716306.77 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | JCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112296 | Talisay ES | TALISAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1155952.91 | 1 | 863518.68 | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | JCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112299 | Cagbalogo ES | VINZONS | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2290708.27 | 1 | 493657.3 | Completed | 1 | 2020-04-08 | [7 empty] | 2019-12-10 | WCVC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112300 | Calangcawan Norte ES | VINZONS | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2673117.76 | 1 | 1757608.03 | Completed | 1 | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112300 | Calangcawan Norte ES | VINZONS | 2 |  | 3 | 1STY3CL | 6390999.24 | 1 | 1618051.92 | Completed | 1 | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | FIRE DAMAGED |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Camarines Norte | 112303 | El Trino P. Zenarosa ES | VINZONS | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2486217.88 | 1 | 1515933.88 | Completed | 1 | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112312 | P. Barbin ES | VINZONS | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2236866.82 | 1 | 5280653.42 | Completed | 1 | 2020-04-08 | [7 empty] | 2019-12-10 | WCVC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112313 | Pinagtigasan ES | VINZONS | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1717706.58 | 1 | 1318031.15 | Completed | 1 | 2020-04-08 | [7 empty] | 2019-12-10 | WCVC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301925 | Vinzons Pilot High School | VINZONS | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2337557.23 | 1 |  | Completed | 1 | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112577 | Del Gallego CS | DEL GALLEGO | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 5052394.14 | 1 | 5040300 | Completed | 1 | 2/14/2020 |  |  | 2019-08-022 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112580 | Mansalaya ES | DEL GALLEGO | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1696694.81 | 1 | 2970300 | Completed | 1 | 2/14/2020 |  |  | 2019-08-022 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112581 | Palaspas ES | DEL GALLEGO | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2978361.34 | 1 | 2645600 | Completed | 1 | 2/14/2020 |  |  | 2019-08-022 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112586 | Sinuknipan Elementary School | DEL GALLEGO | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2650647.45 | 1 | 1693600 | Completed | 1 | 2/14/2020 |  |  | 2019-08-023 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112587 | Sta. Rita ES | DEL GALLEGO | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1716496.65 | 1 | 1714400 | Completed | 1 | 2/14/2020 |  |  | 2019-08-023 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112733 | Bel-Cruz ELementary School | LUPI | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2517490.74 | 1 | 2515400 | Completed | 1 | 2/14/2020 |  |  | 2019-08-023 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301961 | Colacling National High School | LUPI | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2801981.36 | 1 | 2795343.35 | Completed | 1 | 2/13/2020 |  |  | 2019-08-024 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | AVZ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301979 | Haluban NHS | LUPI | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2601739.46 | 1 | 2595644.37 | Completed | 1 | 2/13/2020 |  |  | 2019-08-024 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | AVZ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112945 | Apad ES | RAGAY | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2880755.75 | 1 | 2878700 | Completed | 1 | 2/14/2020 |  |  | 2019-08-023 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112960 | Liboro Elementary School | RAGAY | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2885756.65 | 1 | 2880750 | Completed | 1 | 2/14/2020 |  |  | 2019-08-023 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113051 | Alteza ES | SIPOCOT | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1197403.6 | 1 | 1197350 | Completed | 1 | 2/13/2020 |  |  | 2019-08-025 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113084 | Gaongan ES | SIPOCOT | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2769937.55 | 1 | 2763292.18 | Completed | 1 | 2/13/2020 |  |  | 2019-08-024 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | AVZ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113089 | Manangle ES | SIPOCOT | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2668679.08 | 1 | 2662334.39 | Completed | 1 | 2/13/2020 |  |  | 2019-08-024 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | AVZ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302047 | Sipocot NHS | SIPOCOT | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 3416864.94 | 1 | 3416850 | Completed | 1 | 2/13/2020 |  |  | 2019-08-025 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113091 | Sipocot South CS | SIPOCOT | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2795099.35 | 1 | 2795090 | Completed | 1 | 2/13/2020 |  |  | 2019-08-025 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302068 | Villazar National High School | SIPOCOT | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 4582486.95 | 1 | 4576555 | Completed | 1 | 2/13/2020 |  |  | 2019-08-025 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112775 | Cagbunga Elementary School | GAINZA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1024763.62 | 1 | 1000150 | Completed | 1 | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112672 | Bahay ES | LIBMANAN | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1049769.31 | 1 | 1048300 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112677 | Fundado ES | LIBMANAN | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1624163.21 | 1 | 1622160 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-028 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112712 | Loba-Loba ES | LIBMANAN | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2534373.47 | 1 | 2532370 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-028 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301990 | Malansad Nuevo High School | LIBMANAN | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3709186.47 | 1 | 3707185 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-028 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112698 | Umalo ES | LIBMANAN | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1884869.4 | 1 | 1882870 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-028 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112785 | Milaor CS | MILAOR | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1390117.26 | 1 | 1358100 | Completed | 1 | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301999 | Milaor National High School | MILAOR | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 753825.02 | 1 | 736400 | Completed | 1 | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112789 | Antipolo ES | MINALABAC | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1736993.21 | 1 | 1697000 | Completed | 1 | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112792 | Baliuag Nuevo ES | MINALABAC | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2246632.47 | 1 | 2194900 | Completed | 1 | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112793 | Baliuag Viejo ES | MINALABAC | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 934131.39 | 1 | 912600 | Completed | 1 | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301981 | Hobo National High School | MINALABAC | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2790245.88 | 1 | 2788700 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112867 | Burabod ES | PAMPLONA | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1724595.88 | 1 | 1723100 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112870 | Del Rosario ES | PAMPLONA | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1721854.62 | 1 | 1720300 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 309723 | Del Rosario National HS | PAMPLONA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 484473.89 | 1 | 482900 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112876 | San Ramon ES | PAMPLONA | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1758810.84 | 1 | 1757300 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112877 | San Vicente ES | PAMPLONA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1049769.31 | 1 | 1048200 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112879 | Tambo ES | PAMPLONA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 693848.99 | 1 | 692300 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112880 | Tampadong ES | PAMPLONA | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1785525.4 | 1 | 1784520 | Completed | 1 | Feb. 12, 2020 |  |  | 2019-08-028 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113009 | San Fernando CS | SAN FERNANDO | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 2773608.86 | 1 | 2679800 | Completed | 1 | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113010 | San Joaquin ES | SAN FERNANDO | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 765775.82 | 1 | 748100 | Completed | 1 | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112759 | Bombon Central School | BOMBON | 3 | 1 | 17 | REPAIR OF CLASSROOMS | 4853831.86 | 1 | 4826563.36 | Completed | 1 | Feb. 11, 2020 |  |  | 2019-08-030 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | JANSHA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112771 | Sto. Domingo Elementary School | BOMBON | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 659479.39 | 1 | 655550 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-031 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 173511 | Binaliw Elem School | CALABANGA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 553756.04 | 1 | 543750 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-029 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112471 | Calabanga Central Division Pilot School | CALABANGA | 3 | 1 | 19 | REPAIR OF CLASSROOMS | 4399009.72 | 1 | 4372482.21 | Completed | 1 | Feb. 11, 2020 |  |  | 2019-08-030 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | JANSHA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112472 | Calabanga West Central School | CALABANGA | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1481128.28 | 1 | 1471120 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-029 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301983 | Jose De Villa NHS | CALABANGA | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 3134495.24 | 1 | 3024495 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-029 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112482 | Manguiring ES | CALABANGA | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1914348.56 | 1 | 1890350 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-029 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301998 | Medroso-Mendoza NHS | CALABANGA | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 3277321.56 | 1 | 3167320 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-029 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112483 | Pagatpat ES | CALABANGA | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1624296.92 | 1 | 1614290 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-029 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112490 | Sabang ES | CALABANGA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1241846.22 | 1 | 1235923.21 | Completed | 1 | Feb. 11, 2020 |  |  | 2019-08-030 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | JANSHA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112495 | Taculod ES | CALABANGA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1067116.17 | 1 | 1048904.2 | Completed | 1 | Feb. 11, 2020 |  |  | 2019-08-030 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | JANSHA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112503 | Tarosanan-San Francisco Elementary School | CAMALIGAN | 3 | 1 | 12 | REPAIR OF CLASSROOMS | 4319050.34 | 1 | 4250000 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-031 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112506 | Canaman CS | CANAMAN | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 2972748.71 | 1 | 2900800 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-031 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301995 | Mangayawan High School | CANAMAN | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1911571.91 | 1 | 1850570 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-031 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112855 | La Purisima Nuevo ES | OCAMPO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 822023.59 | 1 | 817000 | Completed | 1 | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112856 | May-Ogob ES | OCAMPO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 870256.1 | 1 | 865200 | Completed | 1 | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112859 | Ocampo Central School | OCAMPO | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 3989414.46 | 1 | 3755200 | Completed | 1 | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112861 | San Antonio ES | OCAMPO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 811415.33 | 1 | 801400 | Completed | 1 | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112920 | Binanuaanan Norte ES | PILI (Capital) | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 750678.78 | 1 | 745650 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-031 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 309749 | BINOBONG HIGH SCHOOL | PILI (Capital) | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1790016.53 | 1 | 1785000 | Completed | 1 | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112923 | Cabocladan Elementary School | PILI (Capital) | 3 | 1 | 1 | REPAIR OF CLASSROOMS | 428408.73 | 1 | 423400 | Completed | 1 | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112932 | Pili Central School | PILI (Capital) | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1091952.09 | 1 | 1086900 | Completed | 1 | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302017 | Pili NHS, Pili - Gov.Mariano E. Villafuerte Annex HS | PILI (Capital) | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 1113508.65 | 1 | 1050510 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-031 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112941 | Tagbong ES | PILI (Capital) | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 2367678.48 | 1 | 2321300 | Completed | 1 | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112564 | Pili-Tabiguian Elementary School | CARAMOAN | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 3046636.88 | 1 | 3044608.79 | Completed | 1 | Feb. 13, 2020 |  |  | 2019-08-037 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | SEVEN R |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112568 | San Roque ES | CARAMOAN | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 2514615.34 | 1 | 2511634.48 | Completed | 1 | Feb. 13, 2020 |  |  | 2019-08-037 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | SEVEN R |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112571 | Tabiguian ES | CARAMOAN | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 3057822.13 | 1 | 3052798.95 | Completed | 1 | Feb. 13, 2020 |  |  | 2019-08-037 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | SEVEN R |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112592 | Burabod Elementary School | GARCHITORENA | 4 | 1 | 8 | REPAIR OF CLASSROOMS | 2194961.56 | 1 | 2193960 | Completed | 1 | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112593 | Cagamutan PS | GARCHITORENA | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1294057.67 | 1 | 1293050 | Completed | 1 | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 500468 | Harrison Integrated School | GARCHITORENA | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 2296000.78 | 1 | 2293962.25 | Completed | 1 | Feb. 13, 2020 |  |  | 2019-08-037 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | SEVEN R |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112604 | Pambuhan Elementary School | GARCHITORENA | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 888262.2 | 1 | 887260 | Completed | 1 | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112615 | Balaynan Elementary School | GOA | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 846262.2 | 1 | 845200 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112617 | Cagaycay ES | GOA | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 527787.33 | 1 | 527700 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112619 | Digdigon ES | GOA | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 903123.65 | 1 | 903100 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112620 | Gimaga ES | GOA | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1430014.43 | 1 | 1425000 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301976 | Pinaglabanan High School | GOA | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 3030198.81 | 1 | 2937400 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-034 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112634 | Tabgon ES | GOA | 4 | 1 | 9 | REPAIR OF CLASSROOMS | 3940509.41 | 1 | 3920100 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-034 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112637 | Taytay Elementary School | GOA | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 961554.34 | 1 | 951700 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-034 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112652 | Amoguis Community School | LAGONOY | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1405655.67 | 1 | 1404650 | Completed | 1 | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112657 | Dahat Elementary School | LAGONOY | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 1050121.96 | 1 | 1048109.59 | Completed | 1 | Feb.28, 2020 |  |  | 2019-08-039 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112639 | Del Carmen ES | LAGONOY | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 478013.75 | 1 | 473200 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-034 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112641 | Himanag Elementary School | LAGONOY | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 540810.98 | 1 | 535400 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-034 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112642 | Lagonoy North CS | LAGONOY | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 2496027.78 | 1 | 2483800.82 | Completed | 1 | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112662 | Manamoc ES | LAGONOY | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 527787.33 | 1 | 523910.69 | Completed | 1 | Feb. 13, 2020 |  |  | 2019-08-037 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | SEVEN R |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112644 | Mapid ES | LAGONOY | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1531536.31 | 1 | 1514130.45 | Completed | 1 | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112645 | Olas ES | LAGONOY | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 956027.49 | 1 | 936847.28 | Completed | 1 | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112646 | Paghaluban Community School | LAGONOY | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 1052567.61 | 1 | 1029643.33 | Completed | 1 | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112647 | Pagsimbugan Elementary School | LAGONOY | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 1998437.51 | 1 | 1979093.48 | Completed | 1 | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302040 | Panagan National High School | LAGONOY | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 3150426.74 | 1 | 3149420 | Completed | 1 | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112666 | San Rafael-Agpo ES | LAGONOY | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1231057.67 | 1 | 1230050 | Completed | 1 | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112650 | Sta. Cruz ES | LAGONOY | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1466625.85 | 1 | 1449530.78 | Completed | 1 | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 309715 | Nato National High School | SAGÑAY | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 2089578.46 | 1 | 2085500 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112993 | Turague ES | SAGÑAY | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 820156.99 | 1 | 820100 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113015 | Bahay PS | SAN JOSE | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 1055574.66 | 1 | 1045000 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-034 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 173518 | Calawit Community School | SAN JOSE | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 506506.63 | 1 | 498199.2 | Completed | 1 | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113045 | Siruma Central School | SIRUMA | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 472763.75 | 1 | 471763.75 | Completed | 1 | March 5, 2020 |  |  | 2019-08-040 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302048 | Siruma NHS | SIRUMA | 4 | 1 | 9 | REPAIR OF CLASSROOMS | 4122564.33 | 1 | 4121564.33 | Completed | 1 | March 5, 2020 |  |  | 2019-08-040 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 173535 | Consocep E/S | TIGAON | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 1428908.1 | 1 | 1427900 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113111 | Vinagre Elementary School | TIGAON | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 2115357.17 | 1 | 2110300 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113134 | Bagacay ES | TINAMBAC | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1405126.53 | 1 | 1389993.54 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-038 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | CPR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113114 | Banga Elementary School | TINAMBAC | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 2021827.6 | 1 | 1995484.14 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-038 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | CPR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301941 | Banga HS | TINAMBAC | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1393705.56 | 1 | 1392705.56 | Completed | 1 | March 5, 2020 |  |  | 2019-08-040 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113116 | Bataan ES | TINAMBAC | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1266932.61 | 1 | 1248742.14 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-038 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | CPR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113137 | Buenavista ES | TINAMBAC | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 3130697.18 | 1 | 3124697.77 | Completed | 1 | Feb.28, 2020 |  |  | 2019-08-039 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113120 | Magsaysay ES | TINAMBAC | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 870063.95 | 1 | 869063.95 | Completed | 1 | March 5, 2020 |  |  | 2019-08-040 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113121 | Malibtong ES | TINAMBAC | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1233440.52 | 1 | 1213670.2 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-038 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | CPR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113124 | PAG-ASA ELEMENTARY SCHOOL | TINAMBAC | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 1882050.04 | 1 | 1855413.24 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-038 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | CPR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113130 | San Ramon ES | TINAMBAC | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 2679973.53 | 1 | 2655108.73 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-038 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | CPR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113133 | TAMBANG CENTRAL SCHOOL | TINAMBAC | 4 | 1 | 15 | REPAIR OF CLASSROOMS | 6255858.59 | 1 | 6243870.37 | Completed | 1 | Feb.28, 2020 |  |  | 2019-08-039 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113150 | Tierra Nevada Elementary School | TINAMBAC | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 2460982.63 | 1 | 2459982.63 | Completed | 1 | March 5, 2020 |  |  | 2019-08-040 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113152 | Tinambac South CS II | TINAMBAC | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1319009.93 | 1 | 1318009.93 | Completed | 1 | March 5, 2020 |  |  | 2019-08-040 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112317 | Agdangan ES | BAAO | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1687934.67 | 1 | 1659566.02 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112318 | Antipolo Elementary School | BAAO | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1889000 | 1 | 1859467.88 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112319 | Baao Central School | BAAO | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2291158.64 | 1 | 2290000 | Completed | 1 | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112323 | Caranday Elementary School | BAAO | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 1092000 | 1 | 1090182.33 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | NOT-IN-NSBI | Caranday High School (IYAGAN Annex) | BAAO | 5 | 1 | 3 | 1STY3CL | 5753304.36 | 1 | 5742990 | completed | 1 | Jan. 12, 2020 |  |  | 2019-08-021 | 2019-08-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | completed
QRF 2019 | Region V | Camarines Sur | 301956 | Caranday HS | BAAO | 5 | 1 | 0 | REPAIR OF CLASSROOMS | 17607006.52 | 1 | 17595555 | Completed | 1 | March 19, 2020 |  |  | 2019-08-047 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112335 | San Isidro-Santa Teresita ES | BAAO | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 2147336.22 | 1 | 2145400 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112342 | Tapol Elementary School | BAAO | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 691505.84 | 1 | 690386.49 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112343 | Bagong Lipunan ES | BALATAN | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1387593.38 | 1 | 1386593.38 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112344 | Balatan CS | BALATAN | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 1979737.06 | 1 | 1976488.18 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112355 | PARARAO E/S | BALATAN | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1455898.23 | 1 | 1454600 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302014 | Pararao High School | BALATAN | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 720646.28 | 1 | 719488.18 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112356 | Pulang Daga ES | BALATAN | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2114536.93 | 1 | 2109500 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112358 | Santiago Elementary School | BALATAN | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 336440.23 | 1 | 336400 | Completed | 1 | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112362 | ATIPOLO ELEM. SCHOOL | BATO | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1357511.28 | 1 | 1357000 | Completed | 1 | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 173546 | Del Rosario PS | BATO | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 158446.28 | 1 | 158180.34 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112374 | Mangga Elementary School | BATO | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 325075.5 | 1 | 325000 | Completed | 1 | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112381 | Salvacion ES | BATO | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1142712.86 | 1 | 1140801.75 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302027 | San Roque High School | BATO | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 585416.76 | 1 | 584472.54 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112390 | Buhi Central School | BUHI | 5 | 1 | 15 | REPAIR OF CLASSROOMS | 4978478.38 | 1 | 4973400 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 173523 | Buhi SPED CENTER | BUHI | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 924784.84 | 1 | 923235.52 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 309709 | Buhi SPED Integrated School | BUHI | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 173510.42 | 1 | 172510.42 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112392 | Burocbusoc ES | BUHI | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2418082.87 | 1 | 2413100 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 173543 | Caloocan Elementary School | BUHI | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 679113.59 | 1 | 679000 | Completed | 1 | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112398 | Ibayugan ES | BUHI | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1042944.22 | 1 | 1042000 | Completed | 1 | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112399 | Igbac ES | BUHI | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 348926.29 | 1 | 347926.29 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112400 | Ipil Elementary School | BUHI | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1150416.53 | 1 | 1149400 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112401 | Iraya lementary School | BUHI | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 1817395.3 | 1 | 1816395 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112422 | Penafrancia ES (Tawagan ES) | BUHI | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1308509.3 | 1 | 1306357.83 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112415 | San Vicente Elementary School | BUHI | 5 | 1 | 9 | REPAIR OF CLASSROOMS | 2542948.39 | 1 | 2540500 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112416 | Sta. Cruz Elementary School | BUHI | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 1479174.58 | 1 | 1477800 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112418 | Sta. Justina East ES | BUHI | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 1927477.43 | 1 | 1895771.4 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112420 | Sto. Nino PS | BUHI | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 316434.81 | 1 | 316400 | Completed | 1 | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112421 | Tambo ES | BUHI | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 671508.02 | 1 | 671500 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112426 | Balaogan ES | BULA | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2862403.54 | 1 | 2861403.54 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301938 | Balaogan National High School | BULA | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1077462.97 | 1 | 1077000 | Completed | 1 | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112427 | Bula Central School | BULA | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1569845.52 | 1 | 1568845.52 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301947 | Bula NHS | BULA | 5 | 1 | 13 | REPAIR OF CLASSROOMS | 4127314.05 | 1 | 4057987.41 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301948 | Bula NHS - Caorasan Annex HS | BULA | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 533882.86 | 1 | 533880 | Completed | 1 | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112428 | Caorasan ES | BULA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 743489.18 | 1 | 742489.18 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301959 | Casugad High School | BULA | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 953826.55 | 1 | 952251.72 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112432 | Felipe P. Panton Elementary School | BULA | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1758856.29 | 1 | 1757300 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112438 | Lopez Palsong Elementary School | BULA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 892096.25 | 1 | 891250 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112440 | Macalinao Elementary School | BULA | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2111991.24 | 1 | 2110991.24 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302007 | Ombao HS | BULA | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 470921.8 | 1 | 470144.07 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112445 | Panoypoyan ES | BULA | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 309642.87 | 1 | 309600 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112450 | San Jose Elementary School | BULA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 679511.83 | 1 | 679500 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112451 | San Ramon Elementary School | BULA | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 436590.03 | 1 | 436500 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112453 | Sto. Domingo Elementary School | BULA | 5 | 1 | 9 | REPAIR OF CLASSROOMS | 2453513.17 | 1 | 2450000 | Completed | 1 | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112833 | Don Telesforo Llorin ES | NABUA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1037889.24 | 1 | 1020464.09 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302002 | Lourdes PHS | NABUA | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 1321850.92 | 1 | 1299540.35 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112836 | Madawon ES | NABUA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 727834.25 | 1 | 726834.25 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301991 | Malawag National High School | NABUA | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 997092.07 | 1 | 995433.56 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112839 | Nierva ES | NABUA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 852697.62 | 1 | 852600 | Completed | 1 | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Catanduanes | 113292 | Pagsangahan ES | SAN MIGUEL | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 5065398.16 | 1 | 8176194.98 | Completed | 1 |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 | Sept. 10, 2019 | Sept. 17, 2019 | JAYRO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Catanduanes | 113294 | Paraiso B ES | SAN MIGUEL | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1910446.83 | 1 |  | Completed | 1 |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 | Sept. 10, 2019 | Sept. 17, 2019 | JAYRO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Catanduanes | 113332 | Summit ES | VIGA | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 4082974.42 | 1 |  | Completed | 1 |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 | Sept. 10, 2019 | Sept. 17, 2019 | JAYRO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114429 | Antipolo ES | IRIGA CITY | 5 | 1 | 9 | REPAIR OF CLASSROOMS | 2797256.67 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114418 | Don Lazaro Madara Memorial School | IRIGA CITY | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2042400.48 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114446 | La Anunciacion ES | IRIGA CITY | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2398188.55 | 1 | 2773643.61 | Completed | 1 | 2020-02-26 |  | 2019-INFRA-04 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-22 | Cam Sur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 302251 | Rinconada National Technical Vocational School | IRIGA CITY | 5 | 1 | 18 | REPAIR OF CLASSROOMS | 5190953.21 | 1 | 1727402.25 | Completed | 1 | 2020-02-26 |  | 2019-INFRA-04 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-22 | Cam Sur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114423 | San Francisco ES | IRIGA CITY | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2268340.7 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114425 | San Jose ES | IRIGA CITY | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2393236.58 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114451 | San Juan ES | IRIGA CITY | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2354069.78 | 1 | 2764042.66 | Completed | 1 | 2020-02-27 |  | 2019-INFRA-05 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114439 | San Vicente Norte ES | IRIGA CITY | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 774176.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114440 | Sta. Cruz Norte ES | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1472741.58 | 1 | 2078919.98 | Completed | 1 | 2020-03-04 |  | 2019-INFRA-08 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114440 | Sta. Cruz Norte ES | IRIGA CITY | 5 |  | 0 | REPAIR OF CLASSROOMS | 6093347.94 | 1 | 1089542.18 | Completed | 1 | 2019-12-30 |  | 2019-INFRA-06 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-24 | 3T Construction & Gen Mdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114441 | Sta. Isabel ES | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1285568.78 | 1 | 1205736.73 | Completed | 1 | 2020-02-12 |  | 2019-INFRA-03 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114457 | Albay CS | LEGAZPI CITY (Capital) | 2 | 1 | 14 | REPAIR OF CLASSROOMS | 4356804.44 | 1 | 2586399.61 | Completed | 1 | 2020-03-04 |  | 2019-INFRA-07 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 310201 | Arimbay High School | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 501884.42 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114465 | Bagacay ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1285281.17 | 1 | 1360741.97 | Completed | 1 | 2019-12-30 |  | 2019-INFRA-06 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-24 | 3T Construction & Gen Mdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114486 | Bagong Abre ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 949023.4 | 1 | 1240697.63 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 100182 | Banquerohan Resettlement Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 653402.01 | 1 | 2880113.11 | Completed | 1 | 2020-02-27 |  | 2019-INFRA-05 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114468 | Bariis ES | LEGAZPI CITY (Capital) | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 1208542.05 | 1 | 2357636.09 | Completed | 1 | 2020-03-04 |  | 2019-INFRA-08 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114475 | Bitano ES | LEGAZPI CITY (Capital) | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 1512240.5 | 1 | 2548007.13 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-022 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114469 | Buenavista ES | LEGAZPI CITY (Capital) | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 1508542.05 | 1 | 1508957.42 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-025 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114488 | Buyoan ES | LEGAZPI CITY (Capital) | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2527115.33 | 1 | 1544321.83 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-024 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114470 | Cagbacong Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1285281.17 | 1 | 638471.42 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114472 | Estanza ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1106728.09 | 1 | 1066699.08 | Completed | 1 | 2020-02-09 |  | 2019-07-006 | 2019-09-026 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-16 | 2019-11-11 | Sansa Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114472 | Estanza ES | LEGAZPI CITY (Capital) | 2 |  | 0 | REPAIR OF CLASSROOMS | 1308542.05 | 1 | 928399.95 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-024 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114479 | Ibalon Central School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 832005.23 | 1 | 1228432.13 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 310202 | Legazpi City Science High School | LEGAZPI CITY (Capital) | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 435005.25 | 1 | 5290754.91 | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114462 | Mabinit ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1106728.09 | 1 | 2492003.41 | Completed | 1 | 2020-03-04 |  | 2019-INFRA-07 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114482 | Maslog ES | LEGAZPI CITY (Capital) | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 647539.29 | 1 | 698792.93 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114482 | Maslog ES | LEGAZPI CITY (Capital) | 2 |  | 0 | REPAIR OF CLASSROOMS | 805145.35 | 1 | 1270935.32 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-022 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City |  | Pag-asa National High School (Main & Annex) | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2752009.27 | 1 | 5512411.59 | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | St. Bernardine Construction and Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 302263 | Pawa High School | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 351884.42 | 1 | 3314638.49 | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114493 | Rawis ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2652009.27 | 1 | 1441100.27 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114473 | San Francisco ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1116728.09 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114495 | San Roque Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1073399.87 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114496 | Tamaoyan ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 260910.17 | 1 | 4045105.42 | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | DELPAR Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 500169 | Taysan Resettlement Integrated School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1410203.52 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 500169 | Taysan Resettlement Integrated School | LEGAZPI CITY (Capital) | 2 |  | 0 | REPAIR OF CLASSROOMS | 1208542.05 | 1 | 6062075.37 | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | A.E. Compuesto Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114484 | Victory Village Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 462396.98 | 1 | 1379386.62 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 201-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111837 | Balanac ES | CITY OF LIGAO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1222811.93 | 1 | 1205736.73 | Completed | 1 | 2020-02-12 |  | 2019-INFRA-03 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111837 | Balanac ES | CITY OF LIGAO | 3 | 1 | 3 | 1STY3CL | 5663811.66 | 1 | 5806283.41 | Completed | 1 | 2020-06-25 |  | 2019-INFRA-02 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-25 | J.Purisima Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Ligao City | 111837 | Balanac ES | CITY OF LIGAO | 3 | 1 | 2 | 1STY2CL | 3836305.68 | 1 | 3992246.74 | Completed | 1 | 2020-02-12 |  | 2019-INFRA-03 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Ligao City | 231003 | Batang ES, Tobgon Ext | CITY OF LIGAO | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1374903.28 | 1 | 2492003.41 | Completed | 1 | 2020-03-04 |  | 2019-INFRA-07 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111838 | Cabarian ES | CITY OF LIGAO | 3 | 1 | 14 | 1STY3CL | 8467935.21 | 1 | 5609871.56 | Completed | 1 | 2020-03-12 |  | 2019-INFRA-01 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-22 | GMO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Ligao City | 111842 | Francia ES | CITY OF LIGAO | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 2784439.41 | 1 | 2773643.61 | Completed | 1 | 2020-02-26 |  | 2019-INFRA-04 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-22 | Cam Sur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 231002 | Macalidong ES | CITY OF LIGAO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2512773.31 | 1 | 2586399.61 | Completed | 1 | 2020-03-04 |  | 2019-INFRA-07 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 231006 | Macalidong ES, Quiasa Ext. | CITY OF LIGAO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1287472.29 | 1 | 2357636.09 | Completed | 1 | 2020-03-04 |  | 2019-INFRA-08 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111846 | Maonon ES | CITY OF LIGAO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1747067.95 | 1 | 2764042.66 | Completed | 1 | 2020-02-27 |  | 2019-INFRA-05 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111823 | Nabonton ES | CITY OF LIGAO | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 2091230.49 | 1 | 2078919.98 | Completed | 1 | 2020-03-04 |  | 2019-INFRA-08 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 231004 | Nabonton ES, Buga Ext. | CITY OF LIGAO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2385229.15 | 1 | 1360741.97 | Completed | 1 | 2019-12-30 |  | 2019-INFRA-06 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-24 | 3T Construction & Gen Mdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111849 | San Vicente ES | CITY OF LIGAO | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 2900461.96 | 1 | 1727402.25 | Completed | 1 | 2020-02-26 |  | 2019-INFRA-04 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-22 | Cam Sur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111829 | Tambo ES | CITY OF LIGAO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1104418.38 | 1 | 1089542.18 | Completed | 1 | 2019-12-30 |  | 2019-INFRA-06 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-24 | 3T Construction & Gen Mdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111853 | Tula-Tula Grande ES | CITY OF LIGAO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2615795.68 | 1 | 2880113.11 | Completed | 1 | 2020-02-27 |  | 2019-INFRA-05 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113569 | ALBASAN ELEMENTARY SCHOOL | CLAVERIA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1535207.42 | 1 | 1508957.42 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-025 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 302135 | Felixberto Del Rosario, Sr. Mem. HS | CLAVERIA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1461094.49 | 1 | 1441100.27 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 174510 | Gaway-Gaway ES | CLAVERIA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1255766.83 | 1 | 1240697.63 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113579 | Imelda ES | CLAVERIA | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 648194.34 | 1 | 638471.42 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 309935 | MABABANGBAYBAY NHS | CLAVERIA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1030957.8 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113589 | Peñafrancia ES | CLAVERIA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1080300.61 | 1 | 1066699.08 | Completed | 1 | 2020-02-09 |  | 2019-07-006 | 2019-09-026 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-16 | 2019-11-11 | Sansa Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113590 | Quezon ES | CLAVERIA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 942538.02 | 1 | 928399.95 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-024 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 302126 | Tito R. Espinosa Memorial National Agricultural School | CLAVERIA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1567263.52 | 1 | 1544321.83 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-024 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113916 | Gemino Elementary School | SAN PASCUAL | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1243352.36 | 1 | 1228432.13 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113920 | Laurente ES | SAN PASCUAL | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 706565.15 | 1 | 698792.93 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113921 | Lukban ES | SAN PASCUAL | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1288035.77 | 1 | 1270935.32 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-022 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113906 | San Rafael E/S | SAN PASCUAL | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2584185.74 | 1 | 2548007.13 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-022 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113936 | Sta. Cruz ES | SAN PASCUAL | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1398568.01 | 1 | 1379386.62 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 201-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113719 | Bangad Elementary School | MILAGROS | 2 | 1 | 2 | 1STY2CL | 4421535.5 | 1 | 4397888.77 | Completed | 1 | 2020-01-08 | Mar. 2020 | INFRA 2019-07-006 | 2019-09-018 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-08-23 | 2019-10-10 | GACT Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Masbate | 309908 | Mary Perpetua E. Brioso Memorial High School | MILAGROS | 2 | 1 | 4 | 1STY4CL | 8316428.43 | 1 | 8294796.29 | Completed | 1 | 2020-03-08 | Mar. 2020 | INFRA 2019-07-007 | 2019-09-019 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-08-23 | 2019-10-10 | GACT Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Masbate | 113713 | Tigbao Elementary School | MILAGROS | 2 | 1 | 2 | 1STY2CL | 4521131.29 | 1 | 4498525.63 | Completed | 1 | 2020-01-08 | Mar. 2020 | INFRA 2019-07-005 | 2019-09-017 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-08-23 | 2019-10-10 | GACT Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Masbate | 113790 | Catoogan PS | PALANAS | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 1029220.76 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113790 | Catoogan PS | PALANAS | 3 |  | 2 | 1STY2CL | 5583444.04 | 1 | 5562672.2 | Completed | 1 | 2020-03-10 |  | INFRA 2019-07-008 | 2019-09-020 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-16 | 2019-11-11 | Sansa Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Naga City | 302267 | Concepcion PequeÃ±a National High School | NAGA CITY | 3 | 1 | 30 | REPAIR OF CLASSROOMS | 7131597.33 | 1 | 5512411.59 | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | St. Bernardine Construction and Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 176502 | Grand View Elementary School | NAGA CITY | 3 | 1 | 20 | REPAIR OF CLASSROOMS | 6082736.85 | 1 | 6062075.37 | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | A.E. Compuesto Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 302269 | Naga City School of Arts and Trades | NAGA CITY | 3 | 1 | 21 | REPAIR OF CLASSROOMS | 4032988.41 | 1 | 2940000 | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | Sulvir Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 114502 | Pacol Elementary School | NAGA CITY | 3 | 1 | 13 | REPAIR OF CLASSROOMS | 5948684.44 | 1 | 4045105.42 | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | DELPAR Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 114504 | Rosario V. Maramba Elementary School | NAGA CITY | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1347298.62 | 1 | 3314638.49 | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 114510 | San Isidro Elementary School | NAGA CITY | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 3207953.55 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 114511 | Tinago Central School | NAGA CITY | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 3477905.69 | 1 | 5290754.91 | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 114519 | Triangulo Elementary School | NAGA CITY | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 1862441.93 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114109 | Milagrosa Elementary School | CASTILLA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2218783.75 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114134 | San Vicente ES | CASTILLA | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2424103.9 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 302183 | Bagatao NHS | MAGALLANES | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 797212.24 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114278 | Dona Olimpia. De Castro Mella ES | MAGALLANES | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2146208.74 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 302222 | Magallanes National High School | MAGALLANES | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 2210864.72 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114282 | Pili ES | MAGALLANES | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1953675.9 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 302179 | Abucay National High School | PILAR | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 2741432.83 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114351 | Mabanate ES | PILAR | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 2302650.63 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 302236 | Salvacion National High School | PILAR | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 566510.15 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 113998 | Abad Santos Elementary School | BULAN | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2433066.74 | 1 | 2406422.68 | Completed | 1 | 2019-11-21 | [8 empty] | NJNY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114032 | Aguinaldo ES | BULAN | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2602358.07 | 1 | 2597153.28 | Completed | 1 | 2019-12-11 | [8 empty] | VINMOR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114005 | C.M. Recto ES | BULAN | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 1059015.78 | 1 | 1056897.62 | Completed | 1 | 2019-12-11 | [8 empty] | VINMOR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114029 | San Juan Daan ES | BULAN | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2428652.48 | 1 | 2400177.1 | Completed | 1 | 2019-11-21 | [8 empty] | NJNY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114210 | Casili ES | GUBAT | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 2635721.7 | 1 | 2230402.56 | Completed | 1 | 2019-11-18 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114190 | Cogon ES | GUBAT | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1666468.49 | 1 | 1623012.24 | Completed | 1 | 2019-11-21 | [8 empty] | 144 CUBITS BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114192 | Gubat North CS | GUBAT | 2 | 1 | 25 | REPAIR OF CLASSROOMS | 8351280.11 | 1 | 8319956.81 | Completed | 1 | 2020-02-05 | [8 empty] | JAYRO CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114211 | Gubat South CS | GUBAT | 2 | 1 | 16 | REPAIR OF CLASSROOMS | 5385435.18 | 1 | 5320435.17 | Completed | 1 | 2019-12-03 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114212 | Manapao ES | GUBAT | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 1862599.57 | 1 | 1576170.52 | Completed | 1 | 2019-11-18 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114218 | Tabi ES | GUBAT | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 3332670.31 | 1 | 3295720.85 | Completed | 1 | 2019-11-21 | [8 empty] | 144 CUBITS BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114224 | Batang ES | IROSIN | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3643825.42 | 1 | 3585486.75 | Completed | 1 | 2019-11-27 | [8 empty] | RMH CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114237 | Macawayan ES | IROSIN | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 3023399.54 | 1 | 2972749.04 | Completed | 1 | 2019-11-21 | [8 empty] | NJNY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114305 | Bon-ot (Big) ES | MATNOG | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2182199.25 | 1 | 2162199.13 | Completed | 1 | 2019-11-17 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114318 | Lajong ES | MATNOG | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1148556.64 | 1 | 1143556.13 | Completed | 1 | 2019-11-17 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114396 | Prieto Diaz CS | PRIETO DIAZ | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 3465672.14 | 1 | 3400668.12 | Completed | 1 | 2019-11-03 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114396 | Prieto Diaz CS | PRIETO DIAZ | 2 |  | 3 | REPAIR OF CLASSROOMS | 3274700.13 | 1 | 3209696.45 | Completed | 1 | 2019-11-03 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114411 | Salvacion ES | SANTA MAGDALENA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2642110.99 | 1 | 2234045.82 | Completed | 1 | 2019-11-27 | [8 empty] | STEVEN CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 114556 | Cabid-an Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1643638.72 | 1 | 1593635.07 | Completed | 1 | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Sept. 16, 2019 | Alhadrax C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 302272 | Celestino G. Tabuena Memorial NHS | CITY OF SORSOGON (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1924969.86 | 1 | 1874448.65 | Completed | 1 | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Sept. 16, 2019 | NJNY C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 114572 | Gimaloto Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1047790.32 | 1 | 1026081.51 | Completed | 1 | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Sept. 16, 2019 | Jayro C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 114577 | Peñafrancia Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 2929470.32 | 1 | 2887746.51 | Completed | 1 | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Sept. 16, 2019 | Duamon C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 114578 | Pio Jebulan Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2134339.85 | 1 | 2092352.35 | Completed | 1 | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Oct. 10, 2019 | Duamon C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 302275 | Rawis National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 3271423.54 | 1 | 3242506.78 | Completed | 1 | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Oct. 3, 2019 | Duamon C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 500463 | Sto. Nino Integrated School | CITY OF SORSOGON (Capital) | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 3995603.48 | 1 | 3994159.12 | Completed | 1 | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Sept. 16, 2019 | NJNY C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114585 | Bantayan ES | CITY OF TABACO | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 3993624.8 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 177501 | Basagan ES | CITY OF TABACO | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 864630.67 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114609 | Bognabong Elementary School | CITY OF TABACO | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1206622.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114586 | Bonot ES | CITY OF TABACO | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1433409.36 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114612 | Cobo ES | CITY OF TABACO | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1961250.32 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114613 | Comon ES | CITY OF TABACO | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 3174874.62 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114592 | Nagsipit ES | CITY OF TABACO | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1635378.74 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114597 | Quinastillojan ES | CITY OF TABACO | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 809881.1 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114622 | San Ramon ES | CITY OF TABACO | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 3466869.15 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114601 | San Vicente ES | CITY OF TABACO | 1 | 1 | 17 | REPAIR OF CLASSROOMS | 5071568.89 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 1 | 0 |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111584 | Bacacay East CS | Bacacay | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1265327.07 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111586 | Bogna ES | BACACAY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 934692.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111590 | Cajugotan ES | Bacacay | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 596674.38 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 301863 | Pili NHS | Bacacay | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 1752253.3 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111622 | Tambongon ES | BACACAY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 992361.32 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111598 | Tanagan Elementary School | BACACAY | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2422849.89 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 172509 | Basud Elementary School | MALILIPOT | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1296144.09 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Albay | 301876 | San Isidro National High School | MALILIPOT | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1440607.57 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 172508 | Dapdap ES | Tiwi | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 802842.44 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112076 | Nagas ES | Tiwi | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 786157.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112081 | Tiwi CS | Tiwi | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 1636944.53 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111625 | ANOLING ES | CAMALIG | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3068380.92 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111639 | Baligang ES | CAMALIG | 2 | 1 | 13 | REPAIR OF CLASSROOMS | 6003896.38 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111640 | CAGUIBA ES | CAMALIG | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2267858.78 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111631 | ILULUAN ES | CAMALIG | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3907352.41 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111646 | MAGOGON ES | CAMALIG | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1326206.59 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111655 | TALOTO ES | CAMALIG | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2053160.56 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111662 | BINITAYAN ES | DARAGA | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 3094477.46 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 172512 | CAROLINA ES | DARAGA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1576427.28 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111686 | GABAWAN ES | DARAGA | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 4482826.76 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111687 | GAPO ES | DARAGA | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 4876975.86 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111671 | KIWALO ES | DARAGA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 1307663.15 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 301832 | LACAG NHS | DARAGA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3264205.74 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111674 | MATNOG ES | DARAGA | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2570353.5 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111696 | NAMANTAO ES | DARAGA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2822655.29 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111902 | PAWA ES | DARAGA | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 4019599.55 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111702 | TABONTABON ES | DARAGA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3087824.1 | 1 |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2020 | Region V | Albay | 111677 | TAGAS ES | DARAGA | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3538992.27 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111703 | TALAHIB ES | DARAGA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1759429.92 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111889 | BAMBAN ES | MANITO | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1760502.73 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111893 | CAVIT ES | MANITO | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1511291.51 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111894 | Cawayan Elementary School | MANITO | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2444541.1 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111901 | NAGOTGOT ES | MANITO | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3000621.21 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112017 | Bagaobawan Elementary School | RAPU-RAPU | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2103549.71 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112020 | BINOSAWAN ES | RAPU-RAPU | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2896661.8 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112024 | CALANAGA ES | RAPU-RAPU | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2968332.23 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Albay | 112029 | GALICIA ES | RAPU-RAPU | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2456754.62 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Albay | 112032 | LAGUNDI ES | RAPU-RAPU | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 3100806.42 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112035 | Mananao Elementary School | RAPU-RAPU | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3436558.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112043 | RAPU-RAPU CS | RAPU-RAPU | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3672802.28 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111722 | BINOGSACAN ELEMENTARY SCHOOL | GUINOBATAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1081532.93 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111706 | BOLOLO ELEMENTARY SCHOOL | GUINOBATAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2146032.2 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111710 | GUINOBATAN EAST CENTRAL SCHOOL | GUINOBATAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1081532.93 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111747 | LILIBDON ELEMENTARY SCHOOL | JOVELLAR | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 773801.51 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111753 | SAN ROQUE ELEMENTARY SCHOOL | JOVELLAR | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 843609.19 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111783 | ALONGONG ELEMENTARY SCHOOL | LIBON | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2338643.51 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111794 | J. CORTES ELEMENTARY SCHOOL | LIBON | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 3868494.3 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111764 | MABAYAWAS ELEMENTARY SCHOOL | LIBON | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1159713.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111797 | MOLOSBOLOS ELEMENTARY SCHOOL | LIBON | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1250758.77 | 1 |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2020 | Region V | Albay | 111775 | SAN ANTONIO ELEMENTARY SCHOOL | LIBON | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 2072980.25 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111805 | Tagbac Elementary School | LIBON | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 856248.37 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111808 | VILLA PETRONA ELEMENTARY SCHOOL | LIBON | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 561699.68 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111905 | BADIAN ELEMENTARY SCHOOL | OAS | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 4376009.38 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111928 | BALOGO WEST ELEMENTARY SCHOOL | OAS | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2434862.97 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111909 | BUSAC ELEMENTARY SCHOOL | OAS | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2220892.75 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111934 | MAPORONG ELEMENTARY SCHOOL | OAS | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 2953494.63 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111916 | MARAMBA ELEMENTARY SCHOOL | OAS | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1243161.9 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111918 | NAGAS ELEMENTARY SCHOOL | OAS | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 841131.75 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111939 | SAN AGUSTIN ELEMENTARY SCHOOL | OAS | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1224294.69 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111941 | SAN JUAN ELEMENTARY SCHOOL | OAS | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1321939.7 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111943 | SAN RAMON ELEMENTARY SCHOOL | OAS | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 2820151.48 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111955 | DR. SOFRONIO S. GARCIA ELEMENTARY SCHOOL | PIODURAN | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 2531819.25 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111961 | MALAPAY ELEMENTARY SCHOOL | PIODURAN | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1955145.77 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111966 | MARIGONDON ELEMENTARY SCHOOL | pioDURAN | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 4151434.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111969 | ORINGON ELEMENTARY SCHOOL | PIODURAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 844869.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112001 | APAD ELEMENTARY SCHOOL | POLANGUI | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1227951.7 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111985 | JOSE DURAN ELEMENTARY SCHOOL | POLANGUI | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 844869.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111998 | STA. CRUZ ELEMENTARY SCHOOL | POLANGUI | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 835568.7 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Norte | 309610 | Victoria J. Tuacar National HS | CAPALONGA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1620084.24 | 1 |  | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Norte | 112169 | San Pedro ES | JOSE PANGANIBAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1453192.48 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112174 | Ulipanan ELementary School | JOSE PANGANIBAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1453192.48 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112245 | Dagang ES | PARACALE | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1801027.12 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112247 | Gumaus Elementary School | PARACALE | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 4297116.47 | 1 |  | COMPLETED | 1 | 2023-11-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 309621 | MAXIMO MANARANG HIGH SCHOOL | PARACALE | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 492624.59 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 301910 | PARACALE NATIONAL HIGH SCHOOL | PARACALE | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1488785.65 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112278 | BASIAD ELEMENTARY SCHOOL | SANTA ELENA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2357851.92 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 173008 | Don Tomas ES | SANTA ELENA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1475060.03 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 173010 | Kagtalaba ES | SANTA ELENA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 2108214.78 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 309602 | Maulawin National High School | SANTA ELENA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1803000.61 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112096 | Mocong ES | BASUD | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1915285.03 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 309613 | Alawihao National High School | DAET (Capital) | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 11511274.91 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Camarines Norte | 301900 | Lalawigan National High School | MERCEDES | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 1176499.84 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 301909 | Pambuhan National High School | MERCEDES | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2833241.08 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112263 | Imelda ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3819153.72 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112267 | Manlimonsito ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1536027.33 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112273 | San Isidro ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1588527.33 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112275 | San Vicente CS | SAN VICENTE | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 4315111.76 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112301 | Calangcawan Sur ES | VINZONS | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 4495649.17 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112302 | Don Miguel Lukban ES | VINZONS | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1427546.82 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112308 | Mangcawayan Island ES | VINZONS | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3091453.12 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112740 | COLACLING ES | LUPI | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 4349926.15 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112744 | Lourdes Elementary School | LUPI | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 926801.17 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112975 | UPPER STA. CRUZ | RAGAY | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 2190811.91 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 302068 | NORTH VILLAZAR NHS | SIPOCOT | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 5087315.9 | 1 | 4576555 | Completed | 1 | 2/13/2020 |  |  | 2019-08-025 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 302047 | SIPOCOT NHS | SIPOCOT | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 6244020.54 | 1 | 3416850 | Completed | 1 | 2/13/2020 |  |  | 2019-08-025 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112673 | Bigajo Sur Ps | LIBMANAN | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1897469.08 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112710 | Duang Niog ES | LIBMANAN | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1164536.02 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112681 | Libmanan North Cs | LIBMANAN | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2290243.47 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112713 | Mambulo Nuevo ES | LIBMANAN | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2458547.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 301994 | Mambulo Nuevo High School | LIBMANAN | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1658479.86 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 309745 | Northern Plain Hs | LIBMANAN | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1372186.59 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112772 | Bal-Flor Es | MILAOR | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1471651.81 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 309731 | Antipolo HS, Minalabac | MINALABAC | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 3057682.74 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 302025 | Sagrada Familia Hs | MINALABAC | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 2654590.69 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112812 | Timbang ES | MINALABAC | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 873260.22 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 302066 | Villamayor Hs | MINALABAC | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1303412.34 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112873 | Salvacion Es | PAMPLONA | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1621955.06 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112875 | San Isidro Es | PAMPLONA | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1782776.92 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112906 | Dalupaon Es | PASACAO | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3676477.72 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112910 | Odicon Es | PASACAO | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2169670.69 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 113009 | San Fernando Cs | SAN FERNANDO | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2110564.41 | 1 | 2679800 | Completed | 1 | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 303542 | Severo High School | CALABANGA | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 1687994.5 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112919 | Bagong Sirang ES | PILI (Capital) | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 2299792.87 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112928 | La Purisima ES | PILI (Capital) | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1483352.94 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 302040 | Panagan National High School | LAGONOY | 4 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 9218565.91 | 1 | 3149420 | Completed | 1 | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Camarines Sur | 302019 | Presentacion NHS (formerly:Pili NHS) | PRESENTACION (PARUBCAN) | 4 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 13469395.03 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Camarines Sur | 112317 | Agdangan ES | BAAO | 5 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 1405524.04 | 1 | 1659566.02 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Camarines Sur | 301926 | Agdangan National High School | BAAO | 5 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 10377046.86 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Camarines Sur | 112341 | Sta. Teresa PS | BAAO | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 810527.89 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112345 | CABANBANAN ES | BALATAN | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2265820.25 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112357 | San Francisco ES | BALATAN | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 3242867.09 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112368 | CRISTO REY ELEMENTARY SCHOOL | BATO | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 1163774.26 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112389 | Antipolo Elementary School | BUHI | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1918784.43 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112395 | De La Fe Elementary School | BUHI | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 404093.67 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112396 | Divino Rostro ES | BUHI | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1596149.25 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112405 | Macaangay Elementary School | BUHI | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1506085.41 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112409 | Sagrada ES | BUHI | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 886468.42 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112410 | Salay Elementary School | BUHI | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 3425049.01 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112412 | San Isidro Elementary School | BUHI | 5 | 1 | 12 | REPAIR OF CLASSROOMS | 4786870.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112415 | San Vicente Elementary School | BUHI | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 886468.42 | 1 | 2540500 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112418 | Sta. Justina East ES | BUHI | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1152912.09 | 1 | 1895771.4 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112420 | Sto. Nino PS | BUHI | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1437483.29 | 1 | 316400 | Completed | 1 | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112423 | Anayan ES | BULA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 263373.94 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112425 | Bagumbayan ES | BULA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 926801.17 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 301947 | Bula NHS | BULA | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 2402139.47 | 1 | 4057987.41 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112444 | Bula South CS (Formerly Palsong ES) | BULA | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 2122587.05 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 173554 | Catasan ES | BULA | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1837493.58 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112431 | Fabrica ES | BULA | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 4885443.02 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112436 | La Purisima Elementary School | BULA | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1797043.46 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112435 | Lanipga ES | BULA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 919057.47 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112440 | Macalinao Elementary School | BULA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1693093.39 | 1 | 2110991.24 | Completed | 1 | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 302007 | Ombao HS | BULA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 745090.7 | 1 | 470144.07 | Completed | 1 | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112445 | Panoypoyan ES | BULA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1339019.07 | 1 | 309600 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112448 | San Agustin ES | BULA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 832549.5 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112451 | San Ramon Elementary School | BULA | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 1798680.88 | 1 | 436500 | Completed | 1 | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112816 | La Opinion ES | NABUA | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 2158919.69 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112817 | Lourdes ES | NABUA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 926801.17 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112837 | Malawag Elementary School | NABUA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 926801.17 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112820 | Ogbon Elementary School | NABUA | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1779359.72 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112822 | Paloyon ES | NABUA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 898933.45 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 500167 | CRISTO REY ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1386834.69 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114418 | DON LAZARO MADARA MEMORIAL SCHOOL | IRIGA CITY | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1510865.62 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114420 | IRIGA CENTRAL SCHOOL | IRIGA CITY | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 1086522.13 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114433 | NIÑO JESUS ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1617998.66 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 302252 | SAGRADA NATIONAL HIGH SCHOOL | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1068197.22 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114421 | SALVACION ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 3202262.06 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114424 | SAN ISIDRO ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 1391637.07 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114427 | SAN NICOLAS ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 2553336.87 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114438 | SAN RAMON ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 2078200.03 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114439 | SAN VICENTE NORTE ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 2126618.06 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114455 | STO. NIÑO ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 14 | REPAIR OF CLASSROOMS | 6571130.2 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114456 | TIRIKTIRIKAN ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1510865.62 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 310201 | Arimbay High School | LEGAZPI CITY (Capital) | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 886853.76 | 1 |  | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114465 | Bagacay ES | LEGAZPI CITY (Capital) | 2 | 1 | 1 | REPAIR OF CLASSROOM | 236257.08 | 1 | 1360741.97 | Completed | 1 | 2019-12-30 |  | 2019-INFRA-06 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-24 | 3T Construction & Gen Mdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114467 | Banquerohan Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2368010.34 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 176003 | Banquerohan Elementary school-SPED | LEGAZPI CITY (Capital) | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1287834.11 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 100182 | Banquerohan Resettlement Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 1 | REPAIR OF CLASSROOM | 420724.75 | 1 | 2880113.11 | Completed | 1 | 2020-02-27 |  | 2019-INFRA-05 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114468 | Bariis ES | LEGAZPI CITY (Capital) | 2 | 1 | 1 | REPAIR OF CLASSROOM | 358452.9 | 1 | 2357636.09 | Completed | 1 | 2020-03-04 |  | 2019-INFRA-08 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114487 | Bigaa Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1567235.76 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114459 | Bogtong ES | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1652348.84 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114469 | Buenavista ES | LEGAZPI CITY (Capital) | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 3346300 | 1 | 1508957.42 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-025 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Legaspi City | 114476 | Buraguis ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 788818.98 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 310206 | Cagbacong High School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1592920.59 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 176001 | Division SPED Center | LEGAZPI CITY (Capital) | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3012048.46 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114472 | Estanza ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1204513.64 | 1 | 1066699.08 | Completed | 1 | 2020-02-09 |  | 2019-07-006 | 2019-09-026 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-16 | 2019-11-11 | Sansa Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114490 | Gogon CS | LEGAZPI CITY (Capital) | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1761948.04 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 302262 | Gogon High School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1060153.41 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114460 | Homapon ES | LEGAZPI CITY (Capital) | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 1092091.44 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Legaspi City | 302259 | Homapon High School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 549247.95 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114479 | Ibalon Central School | LEGAZPI CITY (Capital) | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 526564.89 | 1 | 1228432.13 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114461 | Imalnod ES | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1716632.97 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Legaspi City | 114480 | Lamba ES | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1652348.84 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114481 | Legazpi Port Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 454365.35 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114462 | Mabinit ES | LEGAZPI CITY (Capital) | 2 | 1 | 1 | REPAIR OF CLASSROOM | 356640.87 | 1 | 2492003.41 | Completed | 1 | 2020-03-04 |  | 2019-INFRA-07 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114482 | Maslog ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2905821.3 | 1 | 698792.93 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 302258 | Oro Site High School | LEGAZPI CITY (Capital) | 2 | 1 | 16 | REPAIR OF CLASSROOMS | 1060153.41 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 302261 | Pag-asa National High School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 986843.12 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114483 | Puro Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 454365.35 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114493 | Rawis ES | LEGAZPI CITY (Capital) | 2 | 1 | 1 | REPAIR OF CLASSROOM | 305702.32 | 1 | 1441100.27 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114473 | San Francisco ES | LEGAZPI CITY (Capital) | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 3586350.32 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Ligao City | 111836 | Bacong ES | CITY OF LIGAO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1354097.97 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301838 | Bacong HS | CITY OF LIGAO | 3 | 1 | 35 | REPAIR OF CLASSROOMS | 7417286.21 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301811 | Barayong NHS | CITY OF LIGAO | 3 | 1 | 14 | REPAIR OF CLASSROOMS | 2332096.87 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111814 | Batang ES | CITY OF LIGAO | 3 | 1 | 22 | REPAIR OF CLASSROOMS | 5458391.23 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301814 | Bicol Regional Science HS | CITY OF LIGAO | 3 | 1 | 22 | REPAIR OF CLASSROOMS | 5123952.66 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111812 | Busay ES | CITY OF LIGAO | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 683090.53 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111838 | Cabarian ES | CITY OF LIGAO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 625351.4 | 1 | 5609871.56 | Completed | 1 | 2020-03-12 |  | 2019-INFRA-01 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-22 | GMO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301820 | Deogracias P. Princesa Memorial HS | CITY OF LIGAO | 3 | 1 | 20 | REPAIR OF CLASSROOMS | 2650482.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111820 | Layon ES | CITY OF LIGAO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 580702.02 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 321701 | Ligao City National Technical -Vocational High School | CITY OF LIGAO | 3 | 1 | 34 | REPAIR OF CLASSROOMS | 6149058.23 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 34 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111821 | Ligao East CS | CITY OF LIGAO | 3 | 1 | 20 | REPAIR OF CLASSROOMS | 2166909.43 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301837 | Ligao NHS | CITY OF LIGAO | 3 | 1 | 86 | REPAIR OF CLASSROOMS | 4542055.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 86 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111844 | Ligao West CES (Binatagan) | CITY OF LIGAO | 3 | 1 | 30 | REPAIR OF CLASSROOMS | 2725800.81 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111843 | Ligao West CES (P) Dunao | CITY OF LIGAO | 3 | 1 | 32 | REPAIR OF CLASSROOMS | 4697796.57 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111845 | Mahaba ES | CITY OF LIGAO | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 1833094.51 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301858 | Oma-Oma NHS | CITY OF LIGAO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 704801.19 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111826 | Paulba ES | CITY OF LIGAO | 3 | 1 | 13 | REPAIR OF CLASSROOMS | 4184346.37 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301862 | Paulba NHS | CITY OF LIGAO | 3 | 1 | 14 | REPAIR OF CLASSROOMS | 1646249.63 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111850 | Sta. Cruz ES | CITY OF LIGAO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2371143.48 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 231001 | Tambac Elementary School | CITY OF LIGAO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 1007311.91 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111781 | Tastas ES | CITY OF LIGAO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1471135.94 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111809 | Amtic ES | Ligao City | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1420798.01 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111811 | Barayong ES | Ligao City | 3 | 1 | 9 | REPAIR OF CLASSROOMS | 3212280.52 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301817 | Cabarian NHS | Ligao City | 3 | 1 | 19 | REPAIR OF CLASSROOMS | 2412609.3 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111818 | Don Teotimo ES | Ligao City | 3 | 1 | 1 | REPAIR OF CLASSROOM | 339237.14 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111819 | Herrera ES | Ligao City | 3 | 1 | 9 | REPAIR OF CLASSROOMS | 1774685.06 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111825 | Pandan ES | Ligao City | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 4004273.42 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111827 | Paulog ES | Ligao City | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 869969.51 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111770 | Pinit ES | Ligao City | 3 | 1 | 1 | REPAIR OF CLASSROOM | 238602.03 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111853 | Tula-Tula Grande ES | Ligao City | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1012709.16 | 1 | 2880113.11 | Completed | 1 | 2020-02-27 |  | 2019-INFRA-05 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate | 113572 | BODEGA ES | CLAVERIA | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2221949.85 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113573 | BUYO ES | CLAVERIA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1260093.62 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113575 | CANOMAY ES | CLAVERIA | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2226605.06 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113576 | CAWAYAN ES | CLAVERIA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1665993.25 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113577 | CLAVERIA NORTH CS | CLAVERIA | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 2740943.95 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113911 | CUEVA ES | CLAVERIA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1127354.29 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113579 | IMELDA ES | CLAVERIA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 418052.49 | 1 | 638471.42 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate | 113580 | MABABANGBAYBAY | CLAVERIA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1271354.02 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113582 | MADANILOG ES | CLAVERIA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1594770.3 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113592 | SAN ISIDRO ES | CLAVERIA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2097574.03 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302166 | SAN ISIDRO NHS | CLAVERIA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2043225.18 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113595 | TAGUILID ES | CLAVERIA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1253150.24 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302126 | TITO R. ESPINOSA | CLAVERIA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1229257.56 | 1 | 1544321.83 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-024 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate | 113762 | CARTORNA ES | MONREAL | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1352979.03 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174511 | Cogon ES | MONREAL | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 794658.3 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309923 | Cogon High School | MONREAL | 1 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 7865465.89 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 113763 | Dalakit ES | MONREAL | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1574618.22 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113764 | FAMOSA ES | MONREAL | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1985381.32 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113765 | FLOOR MORES ES | MONREAL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1036659.1 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309930 | Gerardo C. CardiÃ±o Sr. HS | MONREAL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1233628.87 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113766 | MABABOY ES (GUINHADAP EXT.) | MONREAL | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1188350.37 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113768 | MACARTHUR ES | MONREAL | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 4053310.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113771 | Morocborocan ES | MONREAL | 1 | 1 | 1 | REPAIR OF CLASSROOM | 408698.88 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113772 | REAL ES | MONREAL | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 4556541.63 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113774 | STO. NIÑO ES | MONREAL | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 2915314.33 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113859 | Benitinan ES | SAN FERNANDO | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 848149.88 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113860 | BUENASUERTE ES | SAN FERNANDO | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1833056.81 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113863 | CABUG ES | SAN FERNANDO | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1780164.17 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302113 | Bagahanglad NHS | SAN JACINTO | 1 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 7616535.32 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 309928 | Emilio Lee-Llacer Sr. HS | SAN JACINTO | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 786317.13 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113907 | BAYANIHAN ES | SAN PASCUAL | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2442291.49 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113913 | Donato Dela Pena ES | SAN PASCUAL | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 989518.53 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113920 | LAURENTE ES | SAN PASCUAL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 375695.06 | 1 | 698792.93 | Completed | 1 | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate | 113922 | LUKSOHON ES | SAN PASCUAL | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1722412.57 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113931 | RAMONA ES | SAN PASCUAL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 881119.82 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate |  | Roxas Integrated School | SAN PASCUAL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1256052.72 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate | 113934 | SAN PASCUAL CS | SAN PASCUAL | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 3571113.88 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174523 | Segundina L. Rivera Elementary School | SAN PASCUAL | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 699563.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309937 | VICENTE D. ALBURO | SAN PASCUAL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 458132.33 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113374 | AROROY EAST CENTRAL SCHOOL | AROROY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1862555.28 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302111 | AROROY NATIONAL HIGH SCHOOL | AROROY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1591222.32 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113395 | AROROY WEST ELEMENTRY SCHOOL | AROROY | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 2724824.58 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113398 | BONACAN ELEMETARY SCHOOL | AROROY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1673495.41 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113401 | CALANAY ELEMENTARY SCHOOL | AROROY | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 3068702.84 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113403 | DAYHAGAN ELEMENTARY SCHOOL | AROROY | 2 | 1 | 1 | REPAIR OF CLASSROOM | 453625.06 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309901 | DELAVIN-RUBIA NATIONAL HIGH SCHOOL | AROROY | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3426275.1 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309947 | EASTERN CAPSAY INTEGRATED SCHOOL | AROROY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1248941.03 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113377 | ELISA E. CORPUS ELMENTARY SCHOOL | AROROY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1592365.28 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113415 | GREGORIO R. DONGON ELEMENTARY SCHOOL | AROROY | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2345169.62 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174517 | ISIDORO CALIMUTAN SR. ELEMENTARY SCHOOL | AROROY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1521081.58 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113382 | JABOYO-AN ELEMENTARY SCHOOL | AROROY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 886833.95 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113418 | JACINTO R. RAMILO ELEMENTARY SCHOOL | AROROY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1783524.29 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113405 | LADIAWAN PRIMARY SCHOOL | AROROY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 943219.49 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302143 | LUY-A NATIONAL HIGH SCHOOL | AROROY | 2 | 1 | 12 | REPAIR OF CLASSROOMS | 4488884.77 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113697 | MAGSALANGI ELEMENTARY SCHOOL | AROROY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1286243.36 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113407 | MALUBAGO ELEMENTARY SCHOOL | AROROY | 2 | 1 | 1 | REPAIR OF CLASSROOM | 463878.84 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113408 | MARIPOSA ELEMENTARY SCHOOL | AROROY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1216362.56 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113411 | MATONGOG ELEMENTARY SCHOOL | AROROY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2020116.16 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302157 | PANIQUE NATIONAL HIGH SCHOOL | AROROY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1555718.45 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113412 | RUFO C. PAJES CENTRAL SCHOOL | AROROY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1211236.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113413 | SAN AGUSTIN ELEMENTARY SCHOOL | AROROY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 828964.41 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113414 | SAN ISIDRO ELEMENTARY SCHOOL | AROROY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 775372.85 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309909 | TERESITA C. YOUNG MEM. HIGH SCHOOL | AROROY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1250695.22 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 500163 | TIGBAO INTEGRATED SCHOOL | AROROY | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2709447.3 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302174 | TINIGBAN NATIONAL HIGH SCHOOL | AROROY | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3115657.77 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309931 | Amador-Bello HS | BALENO | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2391615.9 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 113420 | BALENO CENTRAL SCHOOL | BALENO | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3415148.19 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113424 | CAGPANDAN ELEMENTARY SCHOOL | BALENO | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1520512.17 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113431 | GABI ELEMENTARY SCHOOL | BALENO | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 791737.38 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302140 | LAGTA NATIONAL HIGH SCHOOL | BALENO | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 4151248.82 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113433 | LAHONG ELEMENTARY SCHOOL | BALENO | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2589685.52 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113434 | LAHONG INTERIOIR ELEMENTARY SCHOOL | BALENO | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1235447.02 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302141 | LAHONG NATIONAL HIGH SCHOOL | BALENO | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1140251.4 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113437 | MAGDALENA ELEMENTARY SCHOOL | BALENO | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 763016.96 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113445 | BALUD CENTRAL SCHOOL | BALUD | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1085533.65 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302156 | BRICCIO A. ANINANG SR. MEMORIAL HIGH SCHOOL | BALUD | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1272623.67 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 501611 | CASAMONGAN INTEGRATED SCHOOL | BALUD | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1227774.72 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113451 | DANAO ELEMENTARY SCHOOL | BALUD | 2 | 1 | 1 | REPAIR OF CLASSROOM | 456268.65 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174503 | PURO ELEMENTARY SCHOOL | BALUD | 2 | 1 | 1 | REPAIR OF CLASSROOM | 454326.81 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 501525 | UBO INTEGRATED SCHOOL | BALUD | 2 | 1 | 1 | REPAIR OF CLASSROOM | 466100.62 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 501252 | ZAPATOS INTEGRATED SCHOOL | BALUD | 2 | 1 | 1 | REPAIR OF CLASSROOM | 487975.83 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302122 | BUGTONG NATIONAL HIGH SCHOOL | MANDAON | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2628111.93 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302125 | CLEOFE A. ARCE MEMORIAL HIGH SCHOOL | MANDAON | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1956066.79 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113650 | LANTANGAN ELEMENTARY SCHOOL | MANDAON | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 805327.01 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113656 | NANIPSAN ELEMENTARY SCHOOL | MANDAON | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 748410.41 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113659 | SAN JUAN ELEMENTARY SCHOOL | MANDAON | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1240221.67 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309907 | SAN PABLO NATIONAL HIGH SCHOOL | MANDAON | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1161589.43 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113664 | YANEZA LANDED ESTATE ELEMENTARY SCHOOL | MANDAON | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1673627.04 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113720 | BONBON ELEMENTARY SCHOOL | MILAGROS | 2 | 1 | 1 | REPAIR OF CLASSROOM | 444059.68 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174521 | JOSE ANINANG SR. ES | MILAGROS | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1110806.84 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302147 | MASBATE SCHOOL OF FISHERIES | MILAGROS | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1205934.91 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302150 | Milagros National High School | MILAGROS | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2555575.52 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 113718 | PEDRO Y. BAUTISTA ELMENTARY SCHOOL | MILAGROS | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1316623.49 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113705 | SAN ANTONIO ELEMENTARY SCHOOL | MILAGROS | 2 | 1 | 1 | REPAIR OF CLASSROOM | 434339.27 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309941 | CRISTETA BAGANO MEMORIAL SCHOOL | MOBO | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 734806.58 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113750 | MOBO CENTRAL SCHOOL | MOBO | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1073388.67 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113758 | Tugbo ES | MOBO | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 806110.86 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113506 | BAGUMBAYAN ES | CATAINGAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 893666.08 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113511 | DIVISORIA ES | CATAINGAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1167158.69 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309921 | Feliciano S. Samonte Memorial High School | CATAINGAN | 3 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 6750380 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 302128 | MARCELO A. ANONUEVO NHS | CATAINGAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1375552.94 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174506 | AGOHO ES | CAWAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 941495.17 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113530 | CABUNGAHAN ES | CAWAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 882768.03 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113533 | CAWAYAN WEST CS | CAWAYAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1402557.73 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113534 | CHICO ELEMENTARY SCHOOL | CAWAYAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1125335.97 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113540 | GUIOM ELEMENTARY SCHOOL | CAWAYAN | 3 | 1 | 1 | REPAIR OF CLASSROOM | 410011.39 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113545 | LOOC ELEMENTARY SCHOOL | CAWAYAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2846633.57 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113548 | MAHAYAHAY ES | CAWAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 980812.62 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113551 | NARO ELEMENTARY SCHOOL | CAWAYAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1004670.83 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113557 | PUNTA BATSAN ELEMENTARY SCHOOL | CAWAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 959894.69 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113562 | TABERNA ES | CAWAYAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1379096.6 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113563 | TALISAY ELEMENTARY SCHOOL | CAWAYAN | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 2439999.87 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113599 | BURACAN ELEMENTARY SCHOOL | DIMASALANG | 3 | 1 | 1 | REPAIR OF CLASSROOMS | 485606.22 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113542 | ITOMBATO ES | DIMASALANG | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 827671.88 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113611 | MAMBOG ELEMENTARY SCHOOL | DIMASALANG | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1520205.98 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113613 | RANILE ES | DIMASALANG | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 888045.71 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113618 | FLORENCIO Y. FRANCISCO ELEMENTARY SCHOOL | ESPERANZA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1315391.8 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113627 | MASBARANON ELEMENTARY SCHOOL | ESPERANZA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1520205.98 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113631 | SAN ROQUE ELEMENTARY SCHOOL | ESPERANZA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1492306.57 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113619 | TRANGIA-MAHUSAY ELEMENTARY SCHOOL | ESPERANZA | 3 | 1 | 1 | REPAIR OF CLASSROOM | 485606.22 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113635 | TUNGA ELEMENTARY SCHOOL | ESPERANZA | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 1035173.06 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113798 | APOLINARIO ETANG ES | PALANAS | 3 | 1 | 1 | REPAIR OF CLASSROOM | 488940.54 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113778 | BUENASUERTE ES | PALANAS | 3 | 1 | 1 | REPAIR OF CLASSROOM | 489286.04 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113794 | MALATAWAN ELEMENTARY SCHOOL | PALANAS | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 854540.12 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302153 | Rondina-Atendido NHS | Palanas | 3 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 15650725 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 302172 | TANQUE NHS | PIO V. CORPUS | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1857124.37 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309903 | ARRIESGADO-SEVILLENO NHS | PLACER | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 927277.69 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113851 | FELIFRANCO AVENIDO SR. MES | PLACER | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 2011873.85 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113825 | GUIN-AWAYAN ELEMENTARY SCHOOL | PLACER | 3 | 1 | 1 | REPAIR OF CLASSROOM | 488749.5 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113516 | LIBTONG ES | PLACER | 3 | 1 | 1 | REPAIR OF CLASSROOM | 487404.95 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113827 | LOCSO-AN ES | PLACER | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1764259.48 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113849 | LUNA ES | PLACER | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 964006.48 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174501 | NAGARAO ELEMENTARY SCHOOL | PLACER | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1290448.64 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113834 | SAN MARCOS ES | PLACER | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1276167.7 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302121 | Buenavista NHS | Uson | 3 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 9756349 | 1 |  | COMPLETED | 1 | 00:00:00 | [9 empty] | Waiting for the Approval of Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 113947 | DEL CARMEN ES | USON | 3 | 1 | 1 | REPAIR OF CLASSROOM | 495971.03 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113952 | MONGAHAY ELEMENTARY SCHOOL | USON | 3 | 1 | 1 | REPAIR OF CLASSROOMS | 485606.22 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113972 | QUEZON ES | USON | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 955471.76 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. MHS | Uson | 3 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 6480560 | 1 |  | COMPLETED | 1 | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate City | 113666 | Anas ES | MASBATE CITY | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1630897.79 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 113686 | Asid ES | MASBATE CITY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 667001.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 321801 | Bolo National High School | MASBATE CITY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2239480.57 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 113674 | Cawayan Exterioi ES | MASBATE CITY | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1774402.13 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 113683 | Electo T. Verano Elementary School | MASBATE CITY | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1926092.98 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 113678 | Florentino C. Versoza ES | MASBATE CITY | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 2552796.75 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 113680 | Julian V antonio ES | MASBATE CITY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1341497.43 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 302148 | Masbate National Comprehensive HS | MASBATE CITY | 2 | 1 | 14 | REPAIR OF CLASSROOMS | 1221576.5 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 113675 | Timoteo T. Buncaras ES | MASBATE CITY | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1744568.28 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Naga City | 176506 | Balatas Elementary School | NAGA CITY | 3 | 1 | 1 | REPAIR OF CLASSROOM | 511595.44 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Naga City | 114506 | Del Rosario Elementary School | NAGA CITY | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 4259320.57 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Naga City | 114507 | Don Manuel I. Abella Central School | NAGA CITY | 3 | 1 | 32 | REPAIR OF CLASSROOMS | 12017471.99 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1474122.93 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 7826211.16 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Naga City | 114500 | Naga Central School I | NAGA CITY | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1933054.92 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Naga City | 114503 | Panicuason Elementary School | NAGA CITY | 3 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 3931074 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Naga City | 114516 | Sabang Elementary School | NAGA CITY | 3 | 1 | 1 | REPAIR OF CLASSROOM | 498016.46 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114084 | Colambis Elem. School | Casiguran | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 205060.63 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114088 | Mabini ES | CASIGURAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 352957.13 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114096 | Tigbao ES | CASIGURAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 543810.52 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114098 | Trece Martires ES | CASIGURAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 532257.51 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114100 | Bagong Sirang ES | CASTILLA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1454288.29 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114101 | Bogna ES | CASTILLA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1660509.17 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114118 | Buenavista ES | CASTILLA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1701487.23 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114119 | Burabod Elementary School | CASTILLA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1245750 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114120 | Caburacan ES | CASTILLA | 1 | 1 | 1 | REPAIR OF CLASSROOM | 359910.8 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302201 | Cumadcad NHS | CASTILLA | 1 | 1 | 16 | REPAIR OF CLASSROOMS | 1118444.32 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114125 | Macalaya ES | CASTILLA | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 772005.17 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114111 | Oras Elementary School | CASTILLA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1007426.93 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302228 | Oras National High School | CASTILLA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1762738.13 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114114 | San Isidro Elem. School | Castilla | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1087693.33 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114133 | San Roque Elem. School | Castilla | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1014119.47 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114139 | Banuang-Gurang ES | DONSOL | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2825728.53 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114141 | Bayawas Elem. School | Donsol | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 2095052.52 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302204 | Donsol NCHS | Donsol | 1 | 1 | 19 | REPAIR OF CLASSROOMS | 2800805.97 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114161 | Donsol West Central School | Donsol | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1452547.66 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114163 | Girawan Elementary School | DONSOL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1025896.53 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114148 | Nagalon Elem. School | Donsol | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1957753.9 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114170 | Pangpang Elem School | Donsol | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 492188.41 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114154 | San Vicente ES | DONSOL | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1487705.8 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114177 | Sibago Elementary School | DONSOL | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 2957360.66 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114179 | Sta. Cruz ES | DONSOL | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 3147231.51 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114181 | Tinanogan ES | DONSOL | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2652509.34 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114286 | Iluminado Carranza Elem.School | MAGALLANES | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1075693.95 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114282 | Pili ES | MAGALLANES | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 830016.5 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114283 | Sta. Elena Elementary School | MAGALLANES | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1692943.42 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114337 | Bantayan Elem. School | Pilar | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1756965.67 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 310006 | Bantayan National High School | PILAR | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1073917.69 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114341 | Calongay Elem. School | Pilar | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1414781.77 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114373 | Esmerada ES | PILAR | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1239931.23 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114347 | Inapugan ES | PILAR | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 873695.9 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114349 | Lumbang Elem. School | Pilar | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1784012.22 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114352 | Marifosque Elem. School | Pilar | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 277926.87 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114356 | Pilar I Central School | Pilar | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 2540965.23 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114363 | Tingco Elementary School | PILAR | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2680017.44 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302248 | Tingco NHS | PILAR | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 889352.27 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 113978 | Alegria Elementary School | BARCELONA | 2 | 1 | 1 | REPAIR OF CLASSROOM | 379998.46 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 113985 | Fabrica Elementary School | BARCELONA | 2 | 1 | 1 | REPAIR OF CLASSROOM | 377458.3 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 113990 | Paghaluban Elementary School | BARCELONA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 743598.5 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302191 | Beguin HS | BULAN | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3637179.83 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302190 | Bulan National High School | Bulan | 2 | 1 | 24 | REPAIR OF CLASSROOMS | 5728979.16 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114011 | Danao ES | BULAN | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 786667.41 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 310002 | J. P. Laurel HS | BULAN | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 1052678.11 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114021 | Namo ES | BULAN | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2315793.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114048 | Sagrada ES | BULAN | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2366203.27 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114059 | Bulusan CS | BULUSAN | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1083792.33 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302192 | Bulusan NHS | BULUSAN | 2 | 1 | 16 | REPAIR OF CLASSROOMS | 5285917.65 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114064 | Porog ES | BULUSAN | 2 | 1 | 1 | REPAIR OF CLASSROOM | 369656.15 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114074 | San Roque ES | BULUSAN | 2 | 1 | 19 | REPAIR OF CLASSROOMS | 5103105.4 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114185 | Bagacay ES | GUBAT | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1078500 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302182 | Bagacay NHS | GUBAT | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1800923.54 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114188 | Cabiguhan ES | GUBAT | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 982648.23 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114189 | Carriedo ES | GUBAT | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 766831.5 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2 | 1 | 20 | REPAIR OF CLASSROOMS | 6481932.63 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114211 | Gubat South CS | GUBAT | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 215687.99 | 1 | 5320435.17 | Completed | 1 | 2019-12-03 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114199 | Payawin ES | GUBAT | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1716073.31 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114230 | Cawayan ES | IROSIN | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 981036.99 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302212 | Gallanosa National High School | Irosin | 2 | 1 | 16 | REPAIR OF CLASSROOMS | 2903831.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114235 | Irosin Central School | IROSIN | 2 | 1 | 16 | REPAIR OF CLASSROOMS | 6065708.8 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114240 | Patag ES | IROSIN | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1842997.47 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114252 | Biriran Ele. School | Juban | 2 | 1 | 12 | REPAIR OF CLASSROOMS | 3657186.54 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114262 | Jagusara Elem. School | Juban | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 726345.49 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114272 | Tublijon Elem. School | Juban | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3166413.99 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114309 | Calpi Elementary School | MATNOG | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 743159.24 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114310 | Coron-Coron ES | MATNOG | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3248746.91 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114322 | Matnog CS | MATNOG | 2 | 1 | 13 | REPAIR OF CLASSROOMS | 4174487 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114332 | Sua ES | MATNOG | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3228053.33 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114393 | Gogon ES | PRIETO DIAZ | 2 | 1 | 1 | REPAIR OF CLASSROOM | 369241.59 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 175006 | Nenita E. Oandasan Mem. Sch. | PRIETO DIAZ | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1858816.01 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302232 | Prieto Diaz National High School | PRIETO DIAZ | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 2404947.77 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114403 | San Ramon ES | PRIETO DIAZ | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1193316.66 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114415 | Sta. Magdalena CS | SANTA MAGDALENA | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3739365.34 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302245 | Sta. Magdalena National High School | SANTA MAGDALENA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2302784.2 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114409 | Bilaoyon Elem. School | Sta. Magdalena | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1084051.61 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon City | 114520 | BACON EAST CENTRAL SCHOOL | CITY OF SORSOGON (Capital) | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 3835469.32 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon City | 114534 | Bacon West Central School | CITY OF SORSOGON (Capital) | 1 | 1 | 1 | REPAIR OF CLASSROOM | 243663.46 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon City | 114547 | SAN VICENTE ELEMENTARY SCHOOL | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1574816.88 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114606 | Agñas Elementary School | Tabaco City | 1 | 1 | 1 | REPAIR OF CLASSROOM | 265034.46 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 302281 | Bantayan National High School | Tabaco City | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1514093.33 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114616 | Hacienda Elementary School | Tabaco City | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1460846.77 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 310503 | Hacienda High School | Tabaco City | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1265859.91 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114587 | Mayon Elementary School | Tabaco City | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 4823433.09 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114619 | Sagurong Elementary School | Tabaco City | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2490592.75 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114598 | San Antonio Elementary School | Tabaco City | 1 | 1 | 19 | REPAIR OF CLASSROOMS | 12589191.02 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 302282 | San Antonio National High School | Tabaco City | 1 | 1 | 34 | REPAIR OF CLASSROOMS | 2491420.97 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 34 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114620 | San Lorenzo Elementary School | Tabaco City | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 318785.03 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114621 | San Miguel Elementary School | Tabaco City | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 802219.81 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 302284 | San Miguel National High School | Tabaco City | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 1416604.44 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114623 | San Roque Elementary School | Tabaco City | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 3040431.13 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 302285 | Tabaco National High School | Tabaco City | 1 | 1 | 135 | REPAIR OF CLASSROOMS | 9453981.5 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 135 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114604 | Tabaco Northwest Central School | Tabaco City | 1 | 1 | 27 | REPAIR OF CLASSROOMS | 9061671.11 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114624 | Tabaco South Elementary School | Tabaco City | 1 | 1 | 18 | REPAIR OF CLASSROOMS | 6420883.78 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114605 | Tabiguian Elementary School | Tabaco City | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2206540.16 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 301818 | Cabasan National High School | Bacacay | 1 | 1 | 22 | TY QUINTA/ROLLY/ULYSSES | 6025500.14 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111878 | Balza Elementary School | Malinao | 1 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 1766953.9 | 1 |  | Completed | 1 | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111870 | Baybay Elementary School | Malinao | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1317875.54 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111873 | Comun Elementary School | Malinao | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 1460377.93 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111875 | Jonop Elementary School | Malinao | 1 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 2559072.72 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111879 | Matalipni Elementary School | Malinao | 1 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 3029271.97 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111884 | Tagoytoy Elementary School | Malinao | 1 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 2051881.74 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 112075 | Cararayan-Naga Elementary School | TIWI | 1 | 1 | 17 | FROM REGULAR REPAIR 2021 | 5233904.42 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 112073 | MAYONG ES | Tiwi | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 1078621.6 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111640 | Caguiba Elementary School | CAMALIG | 2 | 1 | 11 | FROM REGULAR REPAIR 2021 | 5651432.44 | 1 |  | Completed | 1 | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 301808 | Anislag National High School | DARAGA (LOCSIN) | 2 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2340280.34 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111672 | Malobago Elementary School | DARAGA (LOCSIN) | 2 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2340461.24 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111895 | Hologan Elementary School | MANITO | 2 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 3472066.77 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 112022 | Buenavista Elementary School | RAPU-RAPU | 2 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3437186.16 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 112033 | Liguan Elementary School | RAPU-RAPU | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1718952.25 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 112036 | Mancao Elementary School | RAPU-RAPU | 2 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4493900.33 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 172523 | Pagcolbon Elementary School | RAPU-RAPU | 2 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 1115567.37 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 112043 | Rapu-Rapu Central School | RAPU-RAPU | 2 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3667975.96 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 112044 | Sagrada Elementary School | RAPU-RAPU | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1710607.89 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111721 | Balite Elementary School | Guinobatan | 3 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1249812.18 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111806 | Talin-Talin Elementary School | LIBON | 3 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 1895890.79 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111978 | ALNAY ELEMENTARY SCHOOL | OAS | 3 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 3631828.5682 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111927 | BALOGO EAST ELEMENTARY SCHOOL | OAS | 3 | 1 | 6 | TY NINA | 2439787.7051 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111937 | Oas South Central School | OAS | 3 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 2307639.31 | 1 |  | reverted | 0 | [10 empty] | Not included in SARo | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | repair | reverted
QRF 2021 | Region V | Albay | 301854 | Marigondon National High School | PIODURAN | 3 | 1 | 16 | Repair | 5122870.63 | 1 |  | Completed | 1 | 2022-11-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 | 2023-02-01 | 2.23 |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 172525 | Anopol Elementary School | POLANGUI | 3 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 1380826.63 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 112001 | Apad Elementary School | POLANGUI | 3 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1348570.83 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111981 | Cepres Elementary School | POLANGUI | 3 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2418275.11 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 172522 | Cotmon Elementary School | POLANGUI | 3 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 2707627.39 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111982 | Dalogo Elementary School | POLANGUI | 3 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2132402.96 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111986 | Kinuartelan Elementary School | POLANGUI | 3 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 1540957.07 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 301867 | La Medalla High School | POLANGUI | 3 | 1 | 10 | TY NINA | 3501355.07 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 309513 | Lanigay High School | POLANGUI | 3 | 1 | 5 | TY NINA | 2665080.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111987 | Lidong Elementary School | POLANGUI | 3 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2446556.79 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 172524 | Luisevera Matza Elementary School | POLANGUI | 3 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 714924.7 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 112010 | Matacon Elementary School | POLANGUI | 3 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1739428.81 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111989 | Maynaga Elementary School | POLANGUI | 3 | 1 | 5 | TY NINA | 2256065.48 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111995 | POLANGUI NORTH CENTRAL SCHOOL | POLANGUI | 3 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 2579077.1757 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 112011 | POLANGUI SOUTH CENTRAL SCHOOL | POLANGUI | 3 | 1 | 31 | TY NINA | 10330773.5192 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 31 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 112013 | San Roque Elementary School | POLANGUI | 3 | 1 | 7 | TY NINA | 2756908.16 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111998 | Sta. Cruz Elementary School | POLANGUI | 3 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 1949799.25 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111999 | Sugcad Elementary School | POLANGUI | 3 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1214077.72 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301896 | Gonzalo Aler National High School | CAPALONGA | 1 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1112806.52 | 1 |  | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112118 | Mabini ES | CAPALONGA | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1716830.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 305631 | San Antonio High School | CAPALONGA | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1614482.46 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112151 | Jose Panganiban ES | JOSE PANGANIBAN | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1685330.18 | 1 | 3163194.92 | Completed | 1 | 2023-11-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112162 | L. D. Bamba ES | JOSE PANGANIBAN | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1261478.78 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112252 | MAMPUNGO ELEMENTARY SCHOOL | JOSE PANGANIBAN | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1737977.1 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112167 | San Jose ES | JOSE PANGANIBAN | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1812371.45 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112157 | San Rafael ES | JOSE PANGANIBAN | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1695830.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 500156 | Dumagmang Integrated School | LABO | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2358544.91 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112204 | F. Caudilla E/S | LABO | 1 | 1 | 6 | FROM REGULAR REPAIR 2021 | 3840116.11 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112182 | Fundado ES | LABO | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 3492226.81 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112211 | Kabungahan ES | LABO | 1 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1064365.29 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112186 | Labo Elementary school | LABO | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1671318.96 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 501259 | Malaya Integrated School | LABO | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1716830.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 513828.69 | 1 |  | Completed | 1 | 2020-04-14 | [7 empty] | 2019-12-16 | FIRST QUANTUM BUILDERS ID BUILDERS CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112242 | Batobalani Elementary School | PARACALE | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2247130.7 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112254 | Paracale Central School | PARACALE | 1 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 355015.96 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 309616 | Bulala High School | SANTA ELENA | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 524328.69 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301888 | E.P. Borja High School | SANTA ELENA | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 1154414.95 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112285 | Rizal ES | SANTA ELENA | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1674830.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112287 | San Pedro ES | SANTA ELENA | 1 | 1 | 3 | FROM REGULAR REPAIR 2021 | 2076456.44 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112291 | M. Cacho ES | TALISAY | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1674830.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301916 | San Francisco National High School | TALISAY | 1 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 355015.96 | 1 |  | Completed | 1 | 2020-04-09 | [7 empty] | 2019-12-11 | JCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112297 | Zantua-Abordo ES | TALISAY | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1801871.45 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 309604 | Eugenia Morana - Quintela Memorial High School | VINZONS | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2014908.27 | 1 |  | Completed | 1 | 2023-11-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112305 | Gorgonio Obusan ES | VINZONS | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1801871.45 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112304 | Gregorio Jardin ES | VINZONS | 1 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 586207.72 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112311 | Menandro Guinto ES | VINZONS | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2197383.97 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301914 | Sabang National High School, Vinzons | VINZONS | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2070943.41 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 309620 | Sarah Jane Ferrer High School | VINZONS | 1 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 524328.69 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301889 | Basud National High School | BASUD | 2 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 1103792.46 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112092 | Mampili ES | BASUD | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1064365.29 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112103 | San Felipe ES | BASUD | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1685330.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112142 | Cobangbang Elementary School | DAET (Capital) | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1074317.28 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112134 | Daet ES | DAET (Capital) | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1135112.03 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 173001 | Don Emiliano L. Pabico ES | DAET (Capital) | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1138194.28 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112148 | ZURBANO ELEMENTARY SCHOOL | DAET (Capital) | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1621897.13 | 1 | 969616.54 | Completed | 1 | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112232 | Manguisoc ES | MERCEDES | 2 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 3660106.17 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301902 | Manguisoc National High School | MERCEDES | 2 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 2179604.36 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 979766.86 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301909 | Pambuhan National High School | MERCEDES | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 524328.69 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301918 | San Roque National High School | MERCEDES | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 672641.41 | 1 |  | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112271 | Salvacion (B) ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1102306.52 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 309606 | San Isidro High School | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 1852810.55 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112261 | Bernardo Olis ES | SAN VICENTE | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1674830.18 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 173003 | Cabanbanan ES | SAN VICENTE | 2 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 548800.29 | 1 | 1377953.48 | Completed | 1 | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 309605 | Fabrica High School | SAN VICENTE | 2 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 365515.96 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112739 | Casay ES | LUPI | 1 | 1 | 3 | FROM REGULAR REPAIR 2021 | 1598693 | 1 | 1586193 | Completed | 1 | 2/17/2022 | 2/25/2022 |  | 2021-10-036 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112960 | Liboro Elementary School | RAGAY | 1 | 1 | 4 | FROM REGULAR REPAIR 2021 | 2398964.78 | 1 | 2386464.78 | Completed | 1 | 2/17/2022 | 2/25/2022 |  | 2021-10-036 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112711 | Libmanan South CS | LIBMANAN | 2 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4605609.87 | 1 | 4595600 | Completed | 1 | 3/29/2022 | 2/28/2022 |  | 2021-10-038 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112908 | Itulan ES | PASACAO | 2 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3982140.4 | 1 | 3979885.87 | Completed | 1 | 3/29/2022 | 2/28/2022 |  | 2021-10-037 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | JVM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112911 | Pasacao CS | PASACAO | 2 | 1 | 15 | TY QUINTA/ROLLY/ULYSSES | 6784642.24 | 1 | 6776658.43 | Completed | 1 | 3/29/2022 | 2/28/2022 |  | 2021-10-037 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | JVM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 113000 | Daculang Tubig ES | SAN FERNANDO | 2 | 1 | 2 | FROM REGULAR REPAIR 2021 | 1389548.35 | 1 | 1379500 | Completed | 1 | 3/29/2022 | 2/28/2022 |  | 2021-10-038 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112491 | Salvacion-Baybay Elementary School | Calabanga | 3 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3622215.25 | 1 | 3579215 | Completed | 1 | 3/19/2022 | 3/3/2022 |  | 20221-10-041 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302034 | Magarao National High School, Magarao | Magarao | 3 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 9256238.75 | 1 | 7882421.58 | Completed | 1 | 3/19/2022 | 3/3/2022 |  | 20221-10-041 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302006 | Ocampo National High School | OCAMPO | 3 | 1 | 26 | TY QUINTA/ROLLY/ULYSSES | 12935583.52 | 1 | 12818967.89 | Completed | 1 | 3/29/2022 |  |  | 202-10-040 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | JVM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302016 | Pili National High School - Pili | PILI (Capital) | 3 | 1 | 16 | TY QUINTA/ROLLY/ULYSSES | 9948815.76 | 1 | 9860886.22 | Completed | 1 | 3/24/2022 |  |  | 2021-10-039 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302017 | Pili NHS, Pili - Gov.Mariano E. Villafuerte Annex HS | PILI (Capital) | 3 | 1 | 6 | FROM REGULAR REPAIR 2021 | 818712.01 | 1 | 787372.94 | Completed | 1 | 3/24/2022 | 2/17/2022 |  | 2021-10-039 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302018 | V. Bagasina Sr. Memorial High School | PILI (Capital) | 3 | 1 | 6 | FROM REGULAR REPAIR 2021 | 2438686.94 | 1 | 2431585.83 | Completed | 1 | 3/24/2022 | 2/17/2022 |  | 2021-10-039 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 301978 | Guijalo National High School | CARAMOAN | 4 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 6773474.04 | 1 | 6690990.5 | Completed | 1 | 3/19/2022 | 4/13/2022 |  | 2021-10-043 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112542 | Hanopol ES | CARAMOAN | 4 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 4973566.36 | 1 | 4920220.7 | Completed | 1 | 3/19/2022 | 2/17/2022 |  | 2021-10-043 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112664 | Panicuan PS | LAGONOY | 4 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1547411.4 | 1 | 1523299.16 | Completed | 1 | 3/19/2022 | 2/23/2022 |  | 2021-10-044 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | RD DAYAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112884 | Bantugan ES | PRESENTACION | 4 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1624648.33 | 1 | 1619769.34 | Completed | 1 | 3/24/2022 |  |  | 2021-10-042 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112889 | Cagnipa ES | PRESENTACION | 4 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 5965427.99 | 1 | 5962335.22 | Completed | 1 | 3/24/2022 |  |  | 2021-10-042 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112977 | Atulayan ES | SAGÑAY | 4 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 4203692.97 | 1 | 4201518.65 | Completed | 1 | 3/24/2022 | 4/19/2022 |  | 2021-10-042 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112979 | Bongalon ES | SAGÑAY | 4 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 3164982.61 | 1 | 2973836.7 | Completed | 1 | 3/19/2022 | 2/23/2022 |  | 2021-10-044 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | RD DAYAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 300310 | Adiangao High School | SAN JOSE | 4 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1547411.4 | 1 | 1516894.16 | Completed | 1 | 3/19/2022 | 2/23/2022 |  | 2021-10-044 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | RD DAYAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 301950 | Gregorio O. Bercasio Memorial High School | TINAMBAC | 4 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 6709924.31 | 1 | 6047564.99 | Completed | 1 | 3/19/2022 | 2/23/2022 |  | 2021-10-044 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | RD DAYAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112326 | Ikpan ES | BAAO | 5 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1981838.89 | 1 | 1975647.5 | Completed | 1 | 3/29/2022 | 2/10/2022 |  | 2021-10-048 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112344 | Balatan CS | BALATAN | 5 | 1 | 17 | FROM REGULAR REPAIR 2021 | 4663042.91 | 1 | 4661020.07 | Completed | 1 | 3/29/2022 | 2/10/2022 |  | 2021-10-048 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112389 | Antipolo Elementary School | BUHI | 5 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1272042.58 | 1 | 1252880.5 | Completed | 1 | 3/19/2022 | 3/10/2022 |  | 2021-10-047 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112390 | Buhi Central School | BUHI | 5 | 1 | 18 | TY QUINTA/ROLLY/ULYSSES | 9895239.39 | 1 | 9760990 | Completed | 1 | 3/19/2022 | 3/10/2022 |  | 2021-10-047 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112391 | Buhi North Central School | BUHI | 5 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 3926646.22 | 1 | 3924092.03 | Completed | 1 | 3/29/2022 | 2/10/2022 |  | 2021-10-048 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112404 | Lourdes Elementary School | BUHI | 5 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4164588.85 | 1 | 4056003.77 | Completed | 1 | 3/15/2022 | 2/15/2022 |  | 2021-10-049 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/15/2021 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112409 | Sagrada ES | BUHI | 5 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 3113366.82 | 1 | 3089770.42 | Completed | 1 | 3/15/2022 | 2/15/2022 |  | 2021-10-049 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/15/2021 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112413 | San Rafael ES | BUHI | 5 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 4073945.08 | 1 | 3998732.11 | Completed | 1 | 3/16/2022 | 2/15/2022 |  | 2021-10-050 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/16/2021 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302043 | San Vicente National High School - Buhi | BUHI | 5 | 1 | 18 | TY QUINTA/ROLLY/ULYSSES | 11646335.03 | 1 | 11145550.5 | Completed | 1 | 3/19/2022 | 2022-10-03 |  | 2021-10-046 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112425 | Bagumbayan ES | BULA | 5 | 1 | 2 | FROM REGULAR REPAIR 2021 | 1312828.71 | 1 | 1311882.22 | Completed | 1 | 3/16/2022 | 2/15/2022 |  | 2021-10-050 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/16/2021 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112439 | Lubgan Elementary School | BULA | 5 | 1 | 5 | FROM REGULAR REPAIR 2021 | 3360007.4 | 1 | 3338088.36 | Completed | 1 | 3/15/2022 | 2/15/2022 |  | 2021-10-049 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/15/2021 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112816 | La Opinion ES | NABUA | 5 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 4286526.56 | 1 | 4244309.38 | Completed | 1 | 3/16/2022 | 2/15/2022 |  | 2021-10-050 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/16/2021 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302001 | Nabua National High School | NABUA | 5 | 1 | 69 | TY QUINTA/ROLLY/ULYSSES | 21627436.11 | 1 | 19240337.13 | Completed | 1 | 3/19/2022 |  |  | 2021-10-045 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | JVM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 69 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113161 | Bagamanoc CES | BAGAMANOC | 0 | 1 | 13 | TY QUINTA/ROLLY/ULYSSES | 7057850.69 | 1 | 6987272.71 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302076 | Bugao National High School | BAGAMANOC | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2458858.17 | 1 | 2434269.5 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113156 | Hinipaan Elementary School | BAGAMANOC | 0 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 6305789.86 | 1 | 6242732.07 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113172 | Abihao ES | BARAS | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1482900.42 | 1 | 1444984.54 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113166 | Agban Central Elementary School | BARAS | 0 | 1 | 15 | TY QUINTA/ROLLY/ULYSSES | 7366003.61 | 1 | 7288560.38 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302070 | Agban NHS | BARAS | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 5132951.85 | 1 | 5075582.34 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113173 | Baras CES | BARAS | 0 | 1 | 17 | TY QUINTA/ROLLY/ULYSSES | 7365090.31 | 1 | 7364905.82 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302073 | Baras Rural DHS | BARAS | 0 | 1 | 26 | TY QUINTA/ROLLY/ULYSSES | 9181323.54 | 1 | 9154819.02 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113167 | Benticayan ES | BARAS | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 3681449.28 | 1 | 3680785.74 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113168 | Genitligan ES | BARAS | 0 | 1 | 3 | FROM REGULAR REPAIR 2021 | 3282775.73 | 1 | 3217259.2 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113175 | Macutal Elementary School | BARAS | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2999500.98 | 1 | 2956944.39 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113176 | Moning ES | BARAS | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 1881258.93 | 1 | 1862093.54 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113177 | Paniquihan ES | BARAS | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2999500.98 | 1 | 2956944.39 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113178 | Putsan-Danao ES | BARAS | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 3120045.28 | 1 | 3108676.54 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113171 | San Miguel Elementary School | BARAS | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3430304.42 | 1 | 3404027.31 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 174002 | Sta. Maria ES | BARAS | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 954338.96 | 1 | 941641.98 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113180 | Tilod ES | BARAS | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 3681449.28 | 1 | 3647471.04 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 500412 | Bote IS | BATO | 0 | 1 | 26 | TY QUINTA/ROLLY/ULYSSES | 14923145.7 | 1 |  | reverted | 0 | [10 empty] | Not included in SARo | 1 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | REPAIR | reverted
QRF 2021 | Region V | Catanduanes | 500032 | Cabugao IS | BATO | 0 | 1 | 9 | FROM REGULAR REPAIR 2021 | 5017810.4 | 1 | 4967632.29 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113185 | Cagraray Elementary School | BATO | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3722431.99 | 1 | 3685427.28 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113186 | Carorian ES | BATO | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 3087312.68 | 1 | 3056784.9 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113192 | Guinobatan ES | BATO | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 4087124.18 | 1 | 4046429.71 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113193 | Oguis ES | BATO | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3517156.85 | 1 | 3481498.82 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113189 | San Pedro ES | BATO | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 5266080.48 | 1 | 5213417.95 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113190 | San Roque ES | BATO | 0 | 1 | 13 | TY QUINTA/ROLLY/ULYSSES | 7662858.44 | 1 | 7586229.86 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113195 | Sipi ES | BATO | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 5565154.49 | 1 | 5509502.95 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113198 | Caramoran CES | CARAMORAN | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 4232110.42 | 1 | 4189789.36 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302086 | Dariao NHS | CARAMORAN | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 5523844.11 | 1 | 5468605.69 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113207 | Guiamlong ES | CARAMORAN | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2967697.43 | 1 | 2938020.47 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113213 | Obi ES | CARAMORAN | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2497352.94 | 1 | 2472379.51 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113202 | Panique ES | CARAMORAN | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1652978.2 | 1 | 1636448.44 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113203 | San Jose ES | CARAMORAN | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1336767.85 | 1 | 1323400.19 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113218 | Biong ES | GIGMOTO | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2232918.7976 | 1 | 2210830.19 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 174010 | Dominador C. Guerrero ES | GIGMOTO | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1030728.9416 | 1 | 1020347.63 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113219 | Dororian E/S | GIGMOTO | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 2366076.9456 | 1 | 2327882.46 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302087 | Dororian NHS | GIGMOTO | 0 | 1 | 5 | FROM REGULAR REPAIR 2021 | 3558081.73 | 1 | 3505282.07 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113220 | Gigmoto CES | GIGMOTO | 0 | 1 | 21 | TY QUINTA/ROLLY/ULYSSES | 7995483.2873 | 1 | 7917901.93 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113221 | San Pedro ES | GIGMOTO | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1074001.8 | 1 | 1063231.69 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113233 | Bagawang ES | PANDAN | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2540323.9924 | 1 | 2514920.74 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302103 | Leandro I.Verceles Sr. NHS | PANDAN | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2660814.2559 | 1 | 2634206.13 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113239 | Pandan CES | PANDAN | 0 | 1 | 13 | TY QUINTA/ROLLY/ULYSSES | 14557732.5287 | 1 | 14412155.36 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113253 | Panganiban Central Elementary School | PANGANIBAN | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1043616.243 | 1 | 1033137.16 | Completed | 1 | 2011-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302095 | Panganiban National High School | PANGANIBAN | 0 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 5566236.0175 | 1 | 5510490.64 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113254 | San Miguel ES | PANGANIBAN | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2742252.8289 | 1 | 2714751.43 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113257 | Batong Paloway ES | SAN ANDRES | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 4180763.41 | 1 | 4056031.42 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113271 | Bislig ES | SAN ANDRES | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 4891107.82 | 1 | 4743976.56 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113258 | Bon-ot ES | SAN ANDRES | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2538181.56 | 1 | 2461664.86 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302078 | Cabcab NHS | SAN ANDRES | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 4472873.99 | 1 | 4340686.3 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113259 | Caragñag ES | SAN ANDRES | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 4746977.04 | 1 | 4598422.49 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113274 | Catagbacan ES | SAN ANDRES | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3629135.08 | 1 | 3525577.92 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113275 | Codon ES | SAN ANDRES | 0 | 1 | 12 | TY QUINTA/ROLLY/ULYSSES | 6567640.64 | 1 | 6364693.43 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302085 | Codon National High School | SAN ANDRES | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 5315909.49 | 1 | 5152100.72 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113260 | Comagaycay ES | SAN ANDRES | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2984527.02 | 1 | 2893461.09 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113276 | Datag Elementary School | SAN ANDRES | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1535502.92 | 1 | 1490831.68 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113277 | JMA (Asgad) Elementary School | SAN ANDRES | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3753985.49 | 1 | 3642389.87 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113261 | Jose Rizal ES | SAN ANDRES | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 4305245.93 | 1 | 4196650.16 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113278 | Manambrag ES | SAN ANDRES | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2221819.33 | 1 | 2199601 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302091 | Manambrag NHS | SAN ANDRES | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 2896350.78 | 1 | 2867387.26 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113279 | Maygnaway ES | SAN ANDRES | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2620312.41 | 1 | 2594109.28 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302092 | Mayngaway NHS | SAN ANDRES | 0 | 1 | 16 | TY QUINTA/ROLLY/ULYSSES | 6522895.52 | 1 | 6457666.56 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113263 | Palawig ES | SAN ANDRES | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 4816246.53 | 1 | 4665426.65 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113280 | Puting Baybay ES | SAN ANDRES | 0 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 650503.76 | 1 | 643998.73 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113281 | San Isidro ES | SAN ANDRES | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 4351715.31 | 1 | 4308198.2 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113265 | San Jose ES | SAN ANDRES | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2166006.86 | 1 | 2101490.43 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113282 | San Vicente Elementary School | SAN ANDRES | 0 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 309069.81 | 1 | 305979.11 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113283 | Tibang ES | SAN ANDRES | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1891622.53 | 1 | 1872706.3 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113266 | Timbaan ES | SAN ANDRES | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3790057.18 | 1 | 3672647.75 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113284 | Tominawog ES | SAN ANDRES | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 4992256.8 | 1 | 4845672.27 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113267 | Yocti ES | SAN ANDRES | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4313818.58 | 1 | 4179328.34 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113285 | Alma ES | SAN MIGUEL | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 4064730.67 | 1 | 4021181.6 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113286 | Balatohan ES | SAN MIGUEL | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 4061382.42 | 1 | 4023218.23 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 174015 | Boton PS | SAN MIGUEL | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1062562.04 | 1 | 1049674.04 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113299 | Buhi Elementary School | SAN MIGUEL | 0 | 1 | 8 | FROM REGULAR REPAIR 2021 | 4696273.48 | 1 | 4663634.28 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113287 | Caglatawan Elementary School | SAN MIGUEL | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 2119579.48 | 1 | 2098973.03 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113300 | Dayawa ES | SAN MIGUEL | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2057008.12 | 1 | 2036570.23 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113301 | Katipunan ES | SAN MIGUEL | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 4618843.34 | 1 | 4575730.32 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113289 | Kilikilihan ES | SAN MIGUEL | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 6662184.65 | 1 | 6592895.95 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302099 | Mabato NHS (SMRDHS Annex) | SAN MIGUEL | 0 | 1 | 20 | TY QUINTA/ROLLY/ULYSSES | 10322437.28 | 1 | 10208274.56 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113302 | Obo ES | SAN MIGUEL | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 6141725.34 | 1 | 6080415.15 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113291 | Pacogon ES | SAN MIGUEL | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 2354792.06 | 1 | 2331226.32 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113292 | Pagsangahan ES | SAN MIGUEL | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 6502317.88 | 1 | 6437771 | Completed | 1 | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 | Sept. 10, 2019 | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113294 | Paraiso B ES | SAN MIGUEL | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2952877.47 | 1 | 2923291.08 | Completed | 1 | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 | Sept. 10, 2019 | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113293 | Paraiso-A Elementary School | SAN MIGUEL | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3961161.68 | 1 | 3921701.53 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113295 | San Marcos ES | SAN MIGUEL | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 3156845.89 | 1 | 3125574.26 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302098 | San Miguel Rural DHS | SAN MIGUEL | 0 | 1 | 17 | FROM REGULAR REPAIR 2021 | 7509797.52 | 1 | 7419023.83 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113296 | Siay Elementery School | SAN MIGUEL | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2248421.55 | 1 | 2225023.57 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113306 | Solong PS | SAN MIGUEL | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1036704.27 | 1 | 1023119.78 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113308 | Begonia ES | VIGA | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4059597.0148 | 1 | 4018966.95 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113309 | Botinagan ES | VIGA | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1351728.5127 | 1 | 1338188.83 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113321 | Mabini ES | VIGA | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1118530.6374 | 1 | 1107325.01 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113332 | Summit ES | VIGA | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2769214.99 | 1 |  | Completed | 1 |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 | Sept. 10, 2019 | Sept. 17, 2019 | JAYRO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113314 | Tambongon CES | VIGA | 0 | 1 | 15 | TY QUINTA/ROLLY/ULYSSES | 6411747.6466 | 1 | 6347566.72 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113315 | Tinago Elementary School | VIGA | 0 | 1 | 12 | TY QUINTA/ROLLY/ULYSSES | 6236755.7573 | 1 | 6174384.94 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113316 | Villa Aurora Elementary School | VIGA | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2733514.7131 | 1 | 2706154.56 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113353 | Antipolo ES | VIRAC | 0 | 1 | 15 | TY QUINTA/ROLLY/ULYSSES | 10183222.12 | 1 | 10156385.26 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302071 | Antipolo NHS | VIRAC | 0 | 1 | 13 | TY QUINTA/ROLLY/ULYSSES | 5883749.25 | 1 | 5853134.49 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113354 | Balite Elementary School | VIRAC | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4603770.12 | 1 | 4580203.05 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113355 | Batag ES | VIRAC | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1999664.27 | 1 | 1988159.72 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113334 | Bigaa ES | VIRAC | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 4496763.22 | 1 | 4474859.96 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113356 | Buenavista ES | VIRAC | 0 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 736710.36 | 1 | 733436.57 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 500031 | Buyo Integrated School | VIRAC | 0 | 1 | 29 | TY QUINTA/ROLLY/ULYSSES | 15604524.22 | 1 | 15526215.65 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 29 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113336 | Calabnigan ES | VIRAC | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1268081.07 | 1 | 1262189.91 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113357 | Calampong ES | VIRAC | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1398724.69 | 1 | 1391846.62 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113337 | Calatagan ES | VIRAC | 0 | 1 | 17 | TY QUINTA/ROLLY/ULYSSES | 10513757.31 | 1 | 10461343.32 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302084 | Calatagan High School | VIRAC | 0 | 1 | 18 | TY QUINTA/ROLLY/ULYSSES | 11049307.34 | 1 | 10993917.93 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 174012 | Capilihan ES | VIRAC | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2754161.31 | 1 | 2740581.25 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | A.V. Laynes Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113358 | Casoocan ES | VIRAC | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1664497.81 | 1 | 1655033.89 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302083 | Catanduanes NHS | VIRAC | 0 | 1 | 33 | TY QUINTA/ROLLY/ULYSSES | 17752951.93 | 1 | 17653201.11 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | A.V. Laynes Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 33 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113340 | Dugui Too Elementary School | VIRAC | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 5308151.36 | 1 | 5281006.12 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113341 | Dugui Wala ES | VIRAC | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 3035240.3 | 1 | 3020079.95 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 174013 | F. Tacorda Village ES | VIRAC | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 2092884.77 | 1 | 2083057.46 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-06 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113360 | Hawan ES | VIRAC | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 7326705.5 | 1 | 7290153.88 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113361 | Hawan Ilaya ES | VIRAC | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2100635.89 | 1 | 2090378.71 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302089 | Hawan National High School | VIRAC | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 8179886.34 | 1 | 8139137.92 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113343 | Hicming ES | VIRAC | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 4576259.95 | 1 | 4553446.68 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113362 | Igang Elementary School | VIRAC | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2802622.88 | 1 | 2784412.39 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113345 | Juan M. Alberto Memorial ES | VIRAC | 0 | 1 | 25 | TY QUINTA/ROLLY/ULYSSES | 12497282.07 | 1 | 11936782.26 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113363 | Magnesia ES | VIRAC | 0 | 1 | 13 | TY QUINTA/ROLLY/ULYSSES | 7605272.85 | 1 | 7563498.81 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113364 | Marilima ES | VIRAC | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 1913652.19 | 1 | 1903873.52 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113366 | Pajo San Isidro ES | VIRAC | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3205671.79 | 1 | 3184936.87 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113367 | Palnab ES | VIRAC | 0 | 1 | 13 | TY QUINTA/ROLLY/ULYSSES | 7364206.61 | 1 | 7322922.27 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113368 | Palta ES | VIRAC | 0 | 1 | 15 | TY QUINTA/ROLLY/ULYSSES | 9927581.75 | 1 | 9880095.92 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302093 | Palta NHS | VIRAC | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4285753.72 | 1 | 4253983.5 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113369 | Palta Saday ES | VIRAC | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 4412135.07 | 1 | 4390345.22 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 174006 | San Isidro Village ES | VIRAC | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 3413056.06 | 1 | 3386806.08 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | A.V. Laynes Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113370 | Sto. Cristo ES | VIRAC | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 4079050.32 | 1 | 4057404.09 | Completed | 1 | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113371 | Talisoy ES | VIRAC | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2253749.9 | 1 | 2238142.45 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113351 | Taytay ES | VIRAC | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 2069559.75 | 1 | 2059747.85 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | A.V. Laynes Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113372 | Valencia ES | VIRAC | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2153928.43 | 1 | 2143150.87 | Completed | 1 | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113352 | Virac Pilot Elementary School | VIRAC | 0 | 1 | 35 | TY QUINTA/ROLLY/ULYSSES | 23451909.2 | 1 | 11929312.77 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113342 | Gogon Elementary School | VIRAC (Capital) | 0 | 1 | 10 | FROM REGULAR REPAIR 2021 | 7719792.54 | 1 | 7681550.74 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | A.V. Laynes Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113346 | San Vicente ES | VIRAC (Capital) | 0 | 1 | 8 | FROM REGULAR REPAIR 2021 | 3733979.05 | 1 | 3733220.39 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | A.V. Laynes Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113347 | Simamla ES | VIRAC (Capital) | 0 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 6690740.87 | 1 | 6657486.64 | Completed | 1 | 2022-04-22 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Iriga City | 114432 | Iriga North CS | IRIGA CITY | 5 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 7924696.19 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Iriga City | 114445 | Iriga South CS | IRIGA CITY | 5 | 1 | 19 | TY QUINTA/ROLLY/ULYSSES | 13145539.73 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Legaspi City | 114457 | Albay CS | LEGAZPI CITY (Capital) | 2 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 5525850.055 | 1 | 5288133.49 | Completed | 1 | 2020-03-04 |  | 2019-INFRA-07 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Legaspi City | 114466 | Bagumbayan CS | LEGAZPI CITY (Capital) | 2 | 1 | 17 | TY QUINTA/ROLLY/ULYSSES | 8838628.945 | 1 | 8443993.01 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Legaspi City | 114467 | Banquerohan ES | LEGAZPI CITY (Capital) | 2 | 1 | 17 | TY QUINTA/ROLLY/ULYSSES | 7090858.11 | 1 | 6897939.6 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Legaspi City | 302257 | Banquerohan National High School | LEGAZPI CITY (Capital) | 2 | 1 | 14 | TY QUINTA/ROLLY/ULYSSES | 7746464.94 | 1 | 7533634.17 | Completed | 1 | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Legaspi City | 114481 | Legazpi Port Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 18 | TY QUINTA/ROLLY/ULYSSES | 8337194.4 | 1 | 8114138.47 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Legaspi City | 114474 | Taysan ES | LEGAZPI CITY (Capital) | 2 | 1 | 14 | TY QUINTA/ROLLY/ULYSSES | 7485244.06 | 1 | 7269167.9 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Ligao City | 301807 | Amtic National High School | CITY OF LIGAO | 3 | 1 | 19 | TY QUINTA/ROLLY/ULYSSES | 6933571.6677 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Ligao City | 301858 | Oma-Oma National High School | CITY OF LIGAO | 3 | 1 | 18 | TY QUINTA/ROLLY/ULYSSES | 5444091.3059 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113587 | Osmena ES | CLAVERIA | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 3157404.59 | 1 | 3124251.84 | Completed | 1 | 2022-02-24 |  | INFRA 2021-08-024 |  | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113593 | San Ramon Elementary School | CLAVERIA | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 2129035.65 | 1 | 2104551.74 | Completed | 1 | 2022-02-24 |  | INFRA 2021-08-024 | 2021-064 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 501273 | Buenavista Integrated School (ES) | SAN FERNANDO | 1 | 1 | 3 | FROM REGULAR REPAIR 2021 | 1692314.15 | 1 | 1653898.62 | Completed | 1 | 2022-03-10 |  | INFRA 2021-10-037 | 2021-064 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-11-29 | 2021-12-10 | RPN CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113877 | San Fernando East ES | SAN FERNANDO | 1 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3726271.62 | 1 | 3713800.45 | Completed | 1 | 2022-02-24 |  | INFRA 2021-08-024 | 2021-041 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | MME CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113893 | Jagna-an ES | SAN JACINTO | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2786236.98 | 1 | 2736641.96 | Completed | 1 | 2022-03-10 |  | INFRA 2021-10-036 | 2021-064 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-11-29 | 2021-12-10 | RPN CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113894 | Leonardo Barrun ES | SAN JACINTO | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 3265362.4 | 1 | 3209851.23 | Completed | 1 | 2022-03-06 |  | INFRA 2021-10-035 | 2021-059 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-11-29 | 2021-12-06 | RPN CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 302137 | Halabangbaybay National High School | SAN PASCUAL | 1 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1396189.08 | 1 | 1376358.36 | Completed | 1 | 2022-02-24 |  | INFRA 2021-08-024 | 2021-064 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 500034 | Maximino S. Lazaro Integrated School | SAN PASCUAL | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 3441161.88 | 1 | 3400212.05 | Completed | 1 | 2022-02-24 |  | INFRA 2021-08-024 |  | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 174520 | Patrocenio G. Dela Torre Elementary School | SAN PASCUAL | 1 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1222370.69 | 1 | 1205868.69 | Completed | 1 | 2022-02-24 |  | INFRA 2021-08-024 |  | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113932 | Rizal Elementary School | SAN PASCUAL | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 3707609.3 | 1 | 3713800.45 | Completed | 1 | 2022-02-24 |  | INFRA 2021-08-024 | 2021-041 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | MME CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 302168 | San Pascual National High School | SAN PASCUAL | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2916319.7 | 1 | 2890656.09 | Completed | 1 | 2022-02-24 |  | INFRA 2021-08-024 |  | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113937 | Sulficio Elliot ES | SAN PASCUAL | 1 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 807654.62 | 1 | 801597.21 | Completed | 1 | 2022-02-24 |  | INFRA 2021-08-024 |  | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 309932 | Nabongsoran High School | AROROY | 2 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3234345.74 | 1 | 3183863.05 | Completed | 1 | 2022-03-09 |  | INFRA 2021-10-038 |  | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-11-29 | 2021-12-09 | 3R3M CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113756 | Sta. Maria Elementary School | MOBO | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1308914.87 | 1 | 1305642.58 | Completed | 1 | 2022-02-24 |  | INFRA 2021-08-024 | 2021-046 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | SANSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113630 | Rizal PS | ESPERANZA | 3 | 1 | 1 | FROM REGULAR REPAIR 2021 | 738363.65 | 1 | 736517.74 | Completed | 1 | 2022-02-24 |  | INFRA 2021-08-024 | 2021-046 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | SANSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113818 | Tubigan Elementary School | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 6 | FROM REGULAR REPAIR 2021 | 4181112.18 | 1 | 4170659.79 | Completed | 1 | 2022-02-24 |  | INFRA 2021-08-024 | 2021-047 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | L2A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate City | 113673 | Biyong Elementary School | CITY OF MASBATE (Capital) | 2 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 2690340.85 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate City | 130949 | Calolod Elementary School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 591578.32 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Naga City | 114505 | Concepcion Grande ES | NAGA CITY | 3 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 6110866.95 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Naga City | 114499 | Dr. Domingo G. Abcede Elementary School | NAGA CITY | 3 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 6241294.52 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 6240581 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Naga City | 114501 | Naga Central School II | NAGA CITY | 3 | 1 | 12 | TY QUINTA/ROLLY/ULYSSES | 6334316.31 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Naga City | 114502 | Pacol Elementary School | NAGA CITY | 3 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 6138659.81 | 1 | 4045105.42 | Completed | 1 |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | DELPAR Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Naga City | 114517 | Sta.Cruz Elementary School | NAGA CITY | 3 | 1 | 22 | TY QUINTA/ROLLY/ULYSSES | 13651331.75 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon | 302241 | San Rafael High School | CASTILLA | 1 | 1 | 12 | TY QUINTA/ROLLY/ULYSSES | 2781079.77 | 1 | 1852483.39 | Completed | 1 | 2021-12-19 |  |  | 21-07-006-01 |  |  |  |  | 2021-09-06 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon | 114243 | Sto. Domingo ES (Lamboon) | IROSIN | 2 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2854182.3 | 1 | 2007137.18 | Completed | 1 | 2021-12-07 |  |  | 21-07-006-02 |  |  |  |  | 2021-09-09 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon | 114416 | Talaonga ES | SANTA MAGDALENA | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1829435.96 | 1 | 1354285.64 | Completed | 1 | 2021-12-07 |  |  | 21-07-006-03 |  |  |  |  | 2021-09-09 | Araphil Construction and Development Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon City | 114565 | Basud Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2237929.79 | 1 | 1551085.73 | Completed | 1 | 2022-09-30 |  | August 9, 2021 | August 12, 2021 | August 16, 2021 | Camsur Bicol Trading INC |  |  |  |  | temporarily stopped | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon City | 114554 | Bibincahan Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 17 | TY QUINTA/ROLLY/ULYSSES | 6152930.87 | 1 | 6102898.92 | Completed | 1 | 2022-09-30 |  | August 9, 2021 | August 12, 2021 | August 16, 2021 | NJNY Construction & Supply | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon City | 114527 | Gatbo Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 3932421.1 | 1 | 2726009.16 | Completed | 1 | 2022-09-30 |  | August 9, 2021 | August 12, 2021 | August 16, 2021 | Camsur Bicol Trading INC | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon City | 302274 | Osiao Paglingap National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 3625080.13 | 1 | 3594870.83 | Completed | 1 | July 20-August 9, 2021 | July 14, 2021 | August 9, 2021 | August 12, 2021 | August 16, 2021 | Jayro Construction & Supply | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon City | 114546 | San Roque Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 2907519.15 | 1 | 2165303.64 | Completed | 1 | 2022-09-30 |  | August 9, 2021 | August 12, 2021 | August 16, 2021 | Camsur Bicol Trading INC | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon City | 114563 | Sorsogon East Central School | CITY OF SORSOGON (Capital) | 1 | 1 | 32 | TY QUINTA/ROLLY/ULYSSES | 3576898.84 | 1 | 2479334.52 | Completed | 1 | 2022-09-30 |  | August 9, 2021 | August 12, 2021 | August 16, 2021 | Camsur Bicol Trading INC | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Tabaco City | 302283 | San Lorenzo National High School | CITY OF TABACO | 1 | 1 | 35 | TY QUINTA/ROLLY/ULYSSES | 16520322.49 | 1 |  | Completed | 1 | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Tabaco City | 302284 | San Miguel National High School | CITY OF TABACO | 1 | 1 | 23 | Repair | 16946096.5 | 1 |  | Completed | 1 | 2022-10-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 1 | 0 | 2023-03-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 | 1 | 121 | Repair | 39313174.22 | 1 |  | Completed | 1 | 2022-10-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 121 | 1 | 0 | 2023-03-01 | 2.23 |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Tabaco City | 114624 | Tabaco South CES | CITY OF TABACO | 1 | 1 | 32 | TY QUINTA/ROLLY/ULYSSES | 13755640.77 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Camarines Norte | 112161 | Dahican Elementary School | JOSE PANGANIBAN | 1st | 1 | 3 | 1STY3CL | 8750694 | 1 | 8248310.41 | Completed | 1 | 2023-11-01 |  |  | 286.58.488s2023 | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-26 | Meltri Construction Services | ONGOING CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112151 | Jose Panganiban Elementary School | JOSE PANGANIBAN | 1st | 1 | 3 | 1STY3CL | 8481294 | 1 | 6932320.69 | Completed | 1 | 2023-11-01 |  |  |  | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-07-05 | MBC Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112151 | Jose Panganiban Elementary School | JOSE PANGANIBAN | 1st | 1 | 4 | 1STY4CL | 11095757.25 | 1 | 9077808.62 | Completed | 1 | 2023-11-01 |  |  |  | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-07-05 | MBC Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112151 | Jose Panganiban Elementary School | JOSE PANGANIBAN | 1st | 1 | 0 | SLOPE PROTECTION | 20215246.12 | 1 | 20149399.76 | Completed | 1 | 2023-11-01 |  |  |  | 2023-05-30 | 2023-06-06 | 2023-06-29 | 2022-07-18 |  | JAEJR Electrical, Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Camarines Norte | 112155 | Parang Elementary School | JOSE PANGANIBAN | 1st | 1 | 2 | 1STY2CL | 6034952.59 | 1 | 3713765.02 | Completed | 1 | 2023-11-01 |  |  | 374.76.9s2023 | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-07-03 | Century Glass Construction and Supply | ONGOING CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112152 | Regino A. Yet Elementary School | JOSE PANGANIBAN | 1st | 1 | 3 | 1STY3CL | 8720694 | 1 | 7379093.56 | Completed | 1 | 2023-11-01 |  |  | 31.7.489s2023 | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-22 | 2023-07-03 | Meltri Construction Services | ONGOING CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 12.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112156 | San Mauricio Elementary School | JOSE PANGANIBAN | 1st | 1 | 3 | 1STY3CL | 8720694 | 1 | 6019892.2 | Completed | 1 | 2023-11-01 |  |  | 388.79.9s2023 | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-30 | EPL General Construction and Supply | ONGOING CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 4.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112206 | Daguit Elementary School | LABO | 1st | 1 | 3 | 1STY3CL | 8481294 | 1 | 6743528.22 | Completed | 1 | 2023-11-01 |  |  | 359.73.46s2023 | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-29 | Araphil Construction and Development Corp. | ONGOING CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 4.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112208 | Felix Asis Elementary School | LABO | 1st | 1 | 2 | 1STY2CL | 6034952.59 | 1 | 5099972.96 | Completed | 1 | 2023-11-01 |  |  | 32.7.489s2023 | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-22 | 2023-07-03 | Meltri Construction Services | ONGOING CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 12.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 500909 | Kabatuhan Integrated School | LABO | 1st | 1 | 2 | 1STY2CL | 6586051.82 | 1 | 8685821.38 | Completed | 1 | 2024-01-01 |  |  | 200.41.16s2023 | 2023-07-04 | 2023-06-30 | 2023-07-27 | JUNE 20-21, 2023 | JUNE 20-21, 2023 | LA ABEL CONSTRUCTION AND SUPPLY | ONGOING CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 500909 | Kabatuhan Integrated School | LABO | 1st | 1 | 2 | 1STY2CL | 6586051.82 | 1 | 5498272.77 | Completed | 1 | 2023-11-01 |  |  | 200.41.16s2023 | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-26 | LA ABEL CONSTRUCTION AND SUPPLY | ONGOING CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112213 | Macogon Elementary School | LABO | 1st | 1 | 3 | 1STY3CL | 8876595.59 | 1 | 6146720.44 | Completed | 1 | 2023-11-01 |  |  | 387.79.9s2023 | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-30 | EPL General Construction and Supply | ONGOING CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 4.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112247 | Gumaus Elementary School | PARACALE | 1st | 1 | 2 | 1STY2CL | 6009036.68 | 1 | 5498272.77 | Completed | 1 | 2023-11-01 |  |  |  | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-13 | 2023-06-29 | RidersCorner Construction & Gen. Mdse. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112083 | Balce Elementary School | BASUD | 2nd | 1 | 0 | SLOPE PROTECTION | 8000000 | 1 | 7941528.03 | Completed | 1 | 2023-11-01 |  |  | 176.37.ivs2023 | 2023-05-30 | 2023-06-06 | 2023-06-29 | 2023-07-18 | 2023-07-26 | NEB Construction and Supply | FOR FINAL INSPECTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Camarines Norte | 112224 | F. P. Ibasco Elementary School | MERCEDES | 2nd | 1 | 3 | 1STY3CL | 8720694 | 1 | 8631104.39 | Completed | 1 | 2023-11-01 |  |  |  | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-13 | 2023-06-29 | RidersCorner Construction & Gen. Mdse. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112298 | Banocboc Elementary School | VINZONS | 2nd | 1 | 3 | 1STY3CL | 8683413.32 | 1 | 6251672.23 | Completed | 1 | 2023-11-01 |  |  | 324.66IIIs2023 | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-29 | RidersCorner Construction & Gen. Mdse. | ONGOING CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112298 | Banocboc Elementary School | VINZONS | 2nd | 1 | 3 | 1STY3CL | 8683413.32 | 1 | 4525434.65 | Completed | 1 | 2023-11-01 |  |  | 324.66IIIs2023 | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-07-05 | La Abel Construction and Supply | ONGOING CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 309604 | Eugenia Morana - Quintela Memorial High School | VINZONS | 2nd | 1 | 2 | 1STY2CL | 6274352.59 | 1 | 4525434.65 | Completed | 1 | 2023-11-01 |  |  |  | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-07-05 | La Abel Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 502249 | Pinagtigasan Calaguas Island Integrated School | VINZONS | 2nd | 1 | 3 | 1STY3CL | 8720694 | 1 | 8685821.38 | Completed | 1 | 2023-11-01 |  |  | 299.61.9s2023 | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-26 | O.L. De Leon Construction | ONGOING CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 500165 | Antonio Lee Llacer Sr. Integrated School | BATUAN | 1st | 1 | 9 | REPAIR OF CLASSROOMS | 5978075.08 | 1 | 5972113.34 | Ongoing | 0.7 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0.7 | 0 |  |  | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Ongoing
QRF 2023 | Region V | Masbate | 500165 | Antonio Lee Llacer Sr. Integrated School | BATUAN | 1st |  | 3 | 1STY3CL | 8571900.92 | 1 | 8561119.62 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0.85 | 0.15 |  | 5.25 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region V | Masbate | 113478 | Burgos Elementary School | BATUAN | 1st | 1 | 2 | 1STY2CL | 6093809.88 | 1 | 6083147.5 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302134 | F. Alindogan National High School | BATUAN | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 5326059.93 | 1 | 5322804.23 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302134 | F. Alindogan National High School | BATUAN | 1st |  | 4 | 1STY4CL | 11104764.36 | 1 | 11100536.54 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113484 | Matabao ES | BATUAN | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3362054.88 | 1 | 3357791.02 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0.95 | 0.05 |  | 5.25 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Ongoing
QRF 2023 | Region V | Masbate | 113484 | Matabao ES | BATUAN | 1st |  | 3 | 1STY3CL | 8615718.84 | 1 | 8610317.09 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0.95 | 0.05 |  | 5.25 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region V | Masbate | 113486 | Panisihan ES | BATUAN | 1st | 1 | 3 | 1STY3CL | 8626673.32 | 1 | 8621271.56 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113488 | Royroy Elementary School | BATUAN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2054044.78 | 1 | 2051603.85 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113489 | Sawang ES | BATUAN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1400039.73 | 1 | 1397914.08 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113489 | Sawang ES | BATUAN | 1st |  | 2 | 1STY2CL | 6138577.25 | 1 | 6133044.97 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113578 | Dapdap ES | CLAVERIA | 1st | 1 | 0 | SLOPE PROTECTION | 6513275.3 | 1 | 6504278.01 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | GINA'S CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 113585 | Nabasagan ES | CLAVERIA | 1st | 1 | 7 | REPAIR OF CLASSROOMS | 4676034.68 | 1 | 4670322.97 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113587 | Osmena ES | CLAVERIA | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1574858.78 | 1 | 1570734.39 | Completed | 1 | 2023-12-01 |  | INFRA 2021-08-024 |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113589 | Peñafrancia ES | CLAVERIA | 1st | 1 | 3 | 1STY3CL | 8962800.23 | 1 | 8957445.08 | Completed | 1 | 2023-12-01 |  | 2019-07-006 | 2019-09-026 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113767 | Lapu-Lapu ES | MONREAL | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2057029.63 | 1 | 2053560.04 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113769 | Maglambong Elementary School | MONREAL | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2058024.58 | 1 | 2054323.53 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 501537 | Rizal Integrated School | MONREAL | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2059019.53 | 1 | 2057265.74 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 501537 | Rizal Integrated School | MONREAL | 1st |  | 3 | 1STY3CL | 8662380.08 | 1 | 8660210.74 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302109 | Andres Clemente Jr.National High School | SAN FERNANDO | 1st | 1 | 10 | REPAIR OF CLASSROOMS | 6645014.53 | 1 | 6636888.36 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302109 | Andres Clemente Jr.National High School | SAN FERNANDO | 1st |  | 5 | 1STY5CL | 13663334.56 | 1 | 13646287.9 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113860 | Buenasuerte ES | SAN FERNANDO | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 4026009.43 | 1 | 4021037.97 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113862 | Buenos Aires ES | SAN FERNANDO | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2717004.38 | 1 | 2714524.44 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113862 | Buenos Aires ES | SAN FERNANDO | 1st |  | 2 | 1STY2CL | 6175238.49 | 1 | 6170487 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302127 | Buyo National High School | SAN FERNANDO | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3372999.33 | 1 | 3370355.28 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302127 | Buyo National High School | SAN FERNANDO | 1st |  | 2 | 1STY2CL | 6186192.97 | 1 | 6182233.4 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 7.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113867 | Ipil ES | SAN FERNANDO | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1408994.28 | 1 | 1407184.38 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113867 | Ipil ES | SAN FERNANDO | 1st |  | 3 | 1STY3CL | 8697147.45 | 1 | 8693893.44 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113871 | Minio ES | SAN FERNANDO | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1409989.23 | 1 | 1403329.55 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113871 | Minio ES | SAN FERNANDO | 1st |  | 5 | 1STY5CL | 13708101.93 | 1 | 13697873.93 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113873 | Progreso ES | SAN FERNANDO | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2065984.18 | 1 | 2063497.58 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113873 | Progreso ES | SAN FERNANDO | 1st |  | 4 | 1STY4CL | 11219056.41 | 1 | 11212085.67 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113880 | Talisay ES | SAN FERNANDO | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2066979.13 | 1 | 2064517.93 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302113 | Bagahanglad National High School | SAN JACINTO | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2722974.12 | 1 | 2714529.01 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113891 | Guiwanon ES | SAN JACINTO | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2723969.03 | 1 | 2721512.73 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | HKP CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113894 | Leonardo Barrun ES | SAN JACINTO | 1st | 1 | 3 | 1STY3CL | 8732859.24 | 1 | 8721989.66 | Completed | 1 | 2023-12-01 |  | INFRA 2021-10-035 | 2021-059 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113900 | San Jacinto CS | SAN JACINTO | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3380958.93 | 1 | 3376882.32 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113900 | San Jacinto CS | SAN JACINTO | 1st |  | 6 | 1STY6CL | 16243813.72 | 1 | 16232937.05 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302167 | San Jacinto National High School | SAN JACINTO | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2726953.88 | 1 | 2723654.7 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113901 | Tacdugan ES | SAN JACINTO | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2072948.83 | 1 | 2070439.95 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113901 | Tacdugan ES | SAN JACINTO | 1st |  | 3 | 1STY3CL | 8755717.65 | 1 | 8744878.07 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113902 | Tutuban Elementary School | SAN JACINTO | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3383943.78 | 1 | 3379814.1 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113903 | Washington Elementary School | SAN JACINTO | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2074938.73 | 1 | 2064458.82 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | COLINA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113903 | Washington Elementary School | SAN JACINTO | 1st |  | 3 | 1STY3CL | 8767621.58 | 1 | 8756740.87 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | COLINA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113905 | Acacia Elementary School | SAN PASCUAL | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1420933.68 | 1 | 1418574.15 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113908 | Boca Chica ES | SAN PASCUAL | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2076928.63 | 1 | 2074389.9 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113915 | Florentino D. Peñalosa Elementary School | SAN PASCUAL | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 4042923.58 | 1 | 4040487.9 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113917 | Halabangbaybay ES | SAN PASCUAL | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2733918.53 | 1 | 2730785.75 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113930 | Quintina Elementary School | SAN PASCUAL | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 5354913.48 | 1 | 5351640.43 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113393 | Amoroy ES | AROROY | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1478686.89 | 1 | 1474072.41 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113393 | Amoroy ES | AROROY | 2nd |  | 2 | 1STY2CL | 7153545.65 | 1 | 7152603.62 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113374 | Aroroy East CS | AROROY | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 764352.22 | 1 | 758553.45 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | MARABE GEN. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113374 | Aroroy East CS | AROROY | 2nd |  | 2 | 1STY2CL | 7110437.12 | 1 | 7107419.51 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | MARABE GEN. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 309925 | Damaso R. Rubia Memorial High School | AROROY | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1545684.33 | 1 | 1544464.61 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 309925 | Damaso R. Rubia Memorial High School | AROROY | 2nd |  | 2 | 1STY2CL | 7561464.35 | 1 | 7558586.69 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113403 | Dayhagan Elementary School | AROROY | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 2199354.33 | 1 | 2196406.8 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | MARABE GEN. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113403 | Dayhagan Elementary School | AROROY | 2nd |  | 0 | 1STY 3CL | 10598933.77 | 1 | 10596079.91 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | MARABE GEN. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302143 | Luy-a National High School | AROROY | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1465255.55 | 1 | 1459341.09 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | COLINA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302143 | Luy-a National High School | AROROY | 2nd |  | 0 | SLOPE PROTECTION | 8384656.58 | 1 | 8381317.59 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 302143 | Luy-a National High School | AROROY | 2nd |  | 2 | 1STY2CL | 7123598.56 | 1 | 7120440.61 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113385 | Malubi Elementary School | AROROY | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 4968352.45 | 1 | 4965459.87 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 502253 | Manamoc Upland Integrated School | AROROY | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1506872.36 | 1 | 1504691.41 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 500162 | Mataba Integrated School | AROROY | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1548336.45 | 1 | 1544789.32 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 4.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 500162 | Mataba Integrated School | AROROY | 2nd |  | 2 | 1STY2CL | 7691464.35 | 1 | 7688416.42 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113416 | Talib Elementary School | AROROY | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3587688.56 | 1 | 3584914.73 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113420 | Baleno Central School | BALENO | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 2146833.66 | 1 | 2144247.71 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302144 | Magdalena National High School | BALENO | 2nd | 1 | 2 | 1STY2CL | 7477683.45 | 1 | 7477115.36 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302144 | Magdalena National High School | BALENO | 2nd |  | 0 | SLOPE PROTECTION | 2535466.48 | 1 | 2535760.25 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 113447 | Andronico A. Maybay ES | BALUD | 2nd | 1 | 5 | 1STY5CL | 13582855.4 | 1 |  | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113445 | Balud Central School | BALUD | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1468896.56 | 1 | 1466691.99 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302116 | Balud National High School | BALUD | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1459595.45 | 1 | 1457079.06 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113454 | Ilaya ES | BALUD | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2847655.12 | 1 | 2845114.84 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113464 | Pulanduta ES | BALUD | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 4286453.44 | 1 | 4284248.03 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113649 | Jose Z. Meza Sr MES | MANDAON | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3566788.77 | 1 | 3564016.95 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113649 | Jose Z. Meza Sr MES | MANDAON | 2nd |  | 2 | 1STY2CL | 7138225.65 | 1 | 7136111.36 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113664 | Yaneza Landed Estate Elementary School | MANDAON | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 786872.11 | 1 | 784887.04 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113694 | Jamorawon ES | MILAGROS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 2165358.33 | 1 | 2163946.88 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113694 | Jamorawon ES | MILAGROS | 2nd |  | 2 | 1STY2CL | 7346487.45 | 1 | 7344657.05 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113700 | Milagros East CS | MILAGROS | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 8578595.23 | 1 | 8577416.37 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113703 | Punta Tigbao ES | MILAGROS | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 812356.15 | 1 | 810340.71 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113710 | Sawmill ES | MILAGROS | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 854634.32 | 1 | 852482.65 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113714 | Tinaclipan ES | MILAGROS | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1478998.55 | 1 | 1475471.78 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113714 | Tinaclipan ES | MILAGROS | 2nd |  | 2 | 1STY2CL | 7136143.12 | 1 | 7133842.74 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113736 | Bagacay ES | MOBO | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1435968.54 | 1 | 1430915.29 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113736 | Bagacay ES | MOBO | 2nd |  | 6 | 2-UNITS 1STY3CL | 21233516.44 | 1 | 21222162.48 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113749 | Fabian R. De Mesa Elementary School | MOBO | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 2153668.54 | 1 | 2148112.16 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113749 | Fabian R. De Mesa Elementary School | MOBO | 2nd |  | 6 | 2-UNITS 1STY3CL | 21235356.44 | 1 | 21225753.08 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 309922 | Floro L. Medina Memorial High School | MOBO | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1499646.15 | 1 | 1497506.25 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 309922 | Floro L. Medina Memorial High School | MOBO | 2nd |  | 0 | SLOPE PROTECTION | 6945352.45 | 1 | 6942449.08 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 174502 | Jose B. Gamora ES | MOBO | 2nd | 1 | 0 | SLOPE PROTECTION | 2174766.56 | 1 | 2172269.41 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 113745 | Luyong Catungan ES | MOBO | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 2168684.56 | 1 | 2166490.98 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113752 | PINAMARBUHAN ES | MOBO | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1436844.14 | 1 | 1434626.73 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113752 | PINAMARBUHAN ES | MOBO | 2nd |  | 0 | SLOPE PROTECTION | 2384654.15 | 1 | 2380660.73 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 113752 | PINAMARBUHAN ES | MOBO | 2nd |  | 6 | 2-UNITS 1STY3CL | 21138396.9 | 1 | 21130527.89 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302129 | Cataingan National High School | CATAINGAN | 3rd | 1 | 40 | REPAIR OF CLASSROOMS | 26809782.4 | 1 | 26794782 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113510 | Curvada ES | CATAINGAN | 3rd | 1 | 5 | 1STY3CL & 1STY2CL | 18303107.51 | 1 | 18294569.66 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | NJNY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113513 | Emilio S. Boro Sr. Central School | CATAINGAN | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 2701390.6 | 1 | 2699492.06 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | NJNY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113514 | Estampar ES | CATAINGAN | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1380490.6 | 1 | 1377395.38 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 309921 | Feliciano S. Samonte Memorial High School | CATAINGAN | 3rd | 1 | 12 | 2STY6CL & 2-UNITS 1STY3CL | 40527006.23 | 1 | 40476902.44 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | GINA'S CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302142 | Liong National High School | CATAINGAN | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 2076928.63 | 1 | 2072316.7 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | GINA'S CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113495 | Malobago Elementary School | CATAINGAN | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 2055798.45 | 1 | 2053497.6 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113495 | Malobago Elementary School | CATAINGAN | 3rd |  | 2 | 1STY2CL | 7695433.27 | 1 | 7688589.12 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113496 | Matayum Elementary School | CATAINGAN | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 2055798.45 | 1 | 2053708.99 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113496 | Matayum Elementary School | CATAINGAN | 3rd |  | 2 | 1STY2CL | 7695433.27 | 1 | 7693566.23 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113520 | Matubinao Elementary School | CATAINGAN | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 2055798.45 | 1 | 2052910.78 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113522 | Osmeña Elementary School | CATAINGAN | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 675347.65 | 1 | 674427.94 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113524 | Quezon ES | CATAINGAN | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1310556.7 | 1 | 1308753.98 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113531 | Calapayan Elementary School | CAWAYAN | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1384619.0867 | 1 | 1382445.47 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | GINA'S CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113548 | Mahayahay Elementary School | CAWAYAN | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1361487.04 | 1 | 1360606.57 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113550 | Malbug Elementary School | CAWAYAN | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1384619.0867 | 1 | 1384380.03 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113562 | Taberna Elementary School | CAWAYAN | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 675347.65 | 1 | 675007.87 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 309914 | Tomas V. Rivera National High School | CAWAYAN | 3rd | 1 | 9 | REPAIR OF CLASSROOMS | 5897505.15 | 1 | 5894875.58 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 309914 | Tomas V. Rivera National High School | CAWAYAN | 3rd |  | 0 | SLOPE PROTECTION | 9570000 | 1 | 9555635.43 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | GINA'S CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 302177 | Villahermosa National High School | CAWAYAN | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 685266.15 | 1 | 684436.3 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113599 | Buracan ES | DIMASALANG | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 692309.5433 | 1 | 691376.41 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113600 | Cabanuyoan Elementary School | DIMASALANG | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 2720935 | 1 | 2713867.85 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113600 | Cabanuyoan Elementary School | DIMASALANG | 3rd |  | 5 | 1STY3CL & 1STY2CL | 18303107.51 | 1 | 18295174.66 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113606 | Dimasalang CS | DIMASALANG | 3rd | 1 | 5 | REPAIR OF CLASSROOMS | 3376738.25 | 1 | 3374660.19 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113606 | Dimasalang CS | DIMASALANG | 3rd |  | 2 | 1STY2CL | 7530785.98 | 1 | 7525833.58 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113609 | Gregorio Alino Elementary School | DIMASALANG | 3rd | 1 | 2 | 1STY2CL | 7730974.41 | 1 | 7724358.85 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113611 | Mambog Elementary School | DIMASALANG | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 685266.15 | 1 | 684344.98 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113620 | Baras ES | ESPERANZA | 3rd | 1 | 4 | 2-UNITS 1STY2CL | 15461948.82 | 1 | 15449947.7 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113778 | Buenasuerte Elementary School | PALANAS | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1375350.76 | 1 | 1372050.87 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113781 | Palanas North CS | PALANAS | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 2026042.95 | 1 | 2023200.04 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113783 | San Antonio ES | PALANAS | 3rd | 1 | 4 | 2-UNITS 1STY2CL | 15461948.82 | 1 | 15456890.38 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113808 | Gregorio M. Bolitres Elementary School | PIO V. CORPUZ (LIMBUHAN) | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 680743.52 | 1 | 680536.53 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113841 | Camayabsan Elementary School | PLACER | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 685254.25 | 1 | 684264.79 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113845 | Daraga ES | PLACER | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 2741064.6 | 1 | 2737171.5 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113845 | Daraga ES | PLACER | 3rd |  | 6 | 3-UNITS 1STY2CL | 21144266.2 | 1 | 21133158.49 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113851 | Felifranco R. Avenido Sr. Mem. ES | PLACER | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1384619.0867 | 1 | 1383369.11 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113850 | M & R Lecciones ES | PLACER | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 680233.75 | 1 | 679314.9 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113854 | San Pero ES | PLACER | 3rd | 1 | 2 | 1STY2CL | 7730974.41 | 1 | 7724147.32 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113940 | Arado Elementary School | USON | 3rd | 1 | 2 | 1STY2CL | 7682455.25 | 1 | 7677740.1 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302121 | Buenavista National High School | USON | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 675347.65 | 1 | 674383 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION | Waiting for the Approval of Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113946 | Crossing ES | USON | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 655278.35 | 1 | 654395.38 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113948 | Del Rosario ES | USON | 3rd | 1 | 2 | 1STY2CL | 7570420.7 | 1 | 7563561.43 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113965 | Felix S. Merioles Elementary School | USON | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1340489.12 | 1 | 1337942.47 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | COLINA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113965 | Felix S. Merioles Elementary School | USON | 3rd |  | 2 | 1STY2CL | 7570420.7 | 1 | 7566448.93 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113949 | Mabini ES | USON | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1370532.3 | 1 | 1369941.47 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | COLINA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113971 | Panisijan Elementary School | USON | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 655278.35 | 1 | 654746.15 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302170 | San Ramon National High School | USON | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 670244.56 | 1 | 668979.51 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | USON | 3rd | 1 | 0 | SLOPE PROTECTION | 4730000 | 1 | 4724144.75 | Completed | 1 | 2023-12-01 |  |  |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%