## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2 | Unnamed: 43 | Status as of July 4, 2025
ELECTRIFICATION 2017 | Region VI | Aklan | 114728 | Yawan PS | IBAJAY | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 218247.73 | 217775.5 | COMPLETED | 1 |  |  |  |  | 2017-11-06 | 2017-11-13 | 2017-11-27 | 2017-12-01 | 2017-12-18 | Solid Merchandising |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Aklan | 114799 | Sibalew PS | LIBACAO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 217807.91 | 217497.55 | COMPLETED | 1 |  |  |  |  | 2017-11-06 | 2017-11-13 | 2017-11-27 | 2017-12-01 | 2017-12-18 | Solid Merchandising |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Aklan | 114808 | Catabana PS | MADALAG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 139502.69 | 138000 | COMPLETED | 1 |  |  |  |  | 2017-11-06 | 2017-11-13 | 2017-11-27 | 2017-12-01 | 2017-12-18 | Solid Merchandising |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Aklan | 114824 | Panipiason PS | MADALAG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 155252.69 | 155000 | COMPLETED | 1 |  |  |  |  | 2017-11-06 | 2017-11-13 | 2017-11-27 | 2017-12-01 | 2017-12-18 | Solid Merchandising |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Aklan | 114931 | Lanipga-Napatag PS | TANGALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220151.62 | 219144 | COMPLETED | 1 |  |  |  |  | 2017-11-06 | 2017-11-13 | 2017-11-27 | 2017-12-01 | 2017-12-18 | Solid Merchandising |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Antique | 115029 | Batbatan ES | CULASI | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 232720.9 | 231627.1 | COMPLETED | 1 | 2018-04-15 |  | R6-D2-2017BEFF-01A-E | R6-D2-ELECTRIFICATION OF SCHOOLS ON-GRID-2017BEFF-112 |  |  | December 14, 2017 | December 15, 2017 | January 3, 2018 | Hadden Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Antique | 115067 | Cantulan ES | HAMTIC | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 232720.9 | 231627.1 | COMPLETED | 1 | 2018-04-15 |  | R6-D2-2017BEFF-01A-E | R6-D2-ELECTRIFICATION OF SCHOOLS ON-GRID-2017BEFF-112 |  |  | December 14, 2017 | December 15, 2017 | January 3, 2018 | Hadden Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | for termination (far flung/contractor issue) | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Antique | 178503 | Cacao PS | SAN REMIGIO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 232720.9 | 231627.1 | COMPLETED | 1 | 2018-04-15 |  | R6-D2-2017BEFF-01A-E | R6-D2-ELECTRIFICATION OF SCHOOLS ON-GRID-2017BEFF-112 |  |  | December 14, 2017 | December 15, 2017 | January 3, 2018 | Hadden Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | for termination (far flung/contractor issue) | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Antique | 115241 | Carmelo I PS | SAN REMIGIO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 174755.62 | 174652.76 | COMPLETED | 1 | 2018-04-15 |  | R6-D2-2017BEFF-01A-E | R6-D2-ELECTRIFICATION OF SCHOOLS ON-GRID-2017BEFF-112 |  |  | December 14, 2017 | December 15, 2017 | January 3, 2018 | Hadden Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | for termination (far flung/contractor issue) | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Antique | 115284 | P. Javier PS | SEBASTE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 178560.06 | 177709.16 | COMPLETED | 1 | 2018-04-15 |  | R6-D2-2017BEFF-01A-E | R6-D2-ELECTRIFICATION OF SCHOOLS ON-GRID-2017BEFF-112 |  |  | December 14, 2017 | December 15, 2017 | January 3, 2018 | Hadden Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Cadiz City | 117569 | Aluyan ES | CADIZ CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1101216.52 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Capiz | 115626 | Eugenio Regalado PS | PANAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 185817.69 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Capiz | 302389 | Camburanan NHS | TAPAZ | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 123326.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Iloilo | 116731 | IGDAGMAY ELEMENTARY SCHOOL | SAN JOAQUIN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 278988.16 | 360162.5 | COMPLETED | 1 | [6 empty] | December 1, 2017 | December 13, 2017 | January 12, 2018 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Iloilo | 180044 | Jawod ES | SAN JOAQUIN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 208479 | 196344.52 | COMPLETED | 1 | [6 empty] | December 1, 2017 | December 13, 2017 | January 12, 2018 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Iloilo | 116408 | Cunsad PS | JANIUAY | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 366003.6 | 302542.73 | COMPLETED | 1 | [6 empty] | December 1, 2017 | December 13, 2017 | January 12, 2018 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Iloilo | 180017 | Bayuco PS | LAMBUNAO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 161809.47 | 156251.44 | COMPLETED | 1 | [6 empty] | December 1, 2017 | December 13, 2017 | January 12, 2018 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Iloilo | 116675 | Amayong PS | SAN DIONISIO | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 108102.06 | 103081.11 | COMPLETED | 1 | [6 empty] | December 1, 2017 | December 13, 2017 | January 12, 2018 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117831 | Ballo ES | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 327426.32 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117878 | Camandaan PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 103109.53 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 185501 | Cara-an ES | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 575339.29 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117883 | Ilan PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 375014.12 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 185502 | Mambaog PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 258222.93 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117888 | Mamig Elementary School | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233902.03 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117866 | Piliopiliohan PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 377135.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117891 | Sagumayon PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 77360.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117868 | Sampac PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 201772.03 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 180505 | Tugas ES | CITY OF HIMAMAYLAN | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1116889.07 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117202 | Canlupa PS | ISABELA | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 263400 | 265174.3 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C3 | 17-12-111 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117258 | Binata-an ES | MOISES PADILLA (MAGALLON) | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 536631.35 | 698921.58 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C3 | 17-12-111 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117262 | E. Basa PS | MOISES PADILLA (MAGALLON) | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 699806.92 | 535718.22 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C3 | 17-12-111 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 116971 | Macapula ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 629037.28 | 628377.12 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 116973 | Maloy-a Elementary School | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 669838 | 667903.43 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C1 | 17-12-109 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 116977 | Payong PS | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 758672.56 | 757285.55 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 116979 | Sibucao ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 896856.69 | 896003.99 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 116983 | Talimagao ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 349163.74 | 348928.02 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117014 | Taya-o ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 549601.5 | 548807.25 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C1 | 17-12-109 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 180518 | Aguinaldo Primary School | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 723035.78 | 922663.56 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C7 | 17-12-117 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117143 | Bonifacio ES | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 923210.17 | 722527.62 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C7 | 17-12-117 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117145 | Cabanbanan PS | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 835486.41 | 834624.64 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C6 | 17-12-114 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117146 | Cemeco ES | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 970538.94 | 969541.76 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C5 | 17-12-113 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 180508 | MAATOP ELEMENTARY SCHOOL | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 958158.87 | 956847.73 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C6 | 17-12-114 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117155 | Manlawa-an Elementary School | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 786342.28 | 784935.17 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C5 | 17-12-113 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Sagay City | 117731 | Hamticon ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 572834.21 |  | COMPLETED | 1 | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Sagay City | 117732 | Laon ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 504099.64 |  | COMPLETED | 1 | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Sagay City | 117701 | Onofre Dela Paz ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 841603.67 |  | COMPLETED | 1 | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Sagay City | 117702 | Pedro R.Katalbas, Sr. II ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 433936.72 |  | COMPLETED | 1 | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VI | Sagay City | 184001 | Uychiat ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 570050.58 |  | COMPLETED | 1 | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114625 | Altavas ES | ALTAVAS | 0 | 1 | UPGRADING | 2 | 1493310.87 | 1479478.88 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-20 | HOVERT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302286 | ALTAVAS NATIONAL SCHOOL | ALTAVAS | 0 | 1 | UPGRADING | 1 | 1828613.6343 | 1817691.55 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302288 | LINAYASAN NHS | ALTAVAS | 0 | 1 | UPGRADING | 1 | 1054537.9176 | 1048040.97 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500170 | AGUINALDO T. REPIEDAD, Sr. INTEGRATED SCHOOL | BANGA | 0 | 1 | UPGRADING | 1 | 1334452.73 | 1325969.03 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302289 | BACAN NATIONAL HIGH SCHOOL | BANGA | 0 | 1 | UPGRADING | 1 | 1252893.42 | 1244975.31 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302338 | TORRALBA NATIONAL HIGH SCHOOL | BANGA | 0 | 1 | UPGRADING | 1 | 1087308.492 | 1080649.5 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302291 | BATAN ACADEMY (A NAT'L SCH.) | BATAN | 0 | 1 | UPGRADING | 1 | 1081899 | 1080649.5 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302294 | BAY-ANG MAGPAG-ONG NHS | BATAN | 0 | 1 | UPGRADING | 1 | 1170314.3204 | 1163311.24 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302301 | CAMANCI NATIONAL HIGH SCHOOL | BATAN | 0 | 1 | UPGRADING | 1 | 1054537.9176 | 1048224.4 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302333 | RIZAL J. RODRIGUEZ Sr. NATIONAL HIGH SCHOOL | BATAN | 0 | 1 | UPGRADING | 1 | 1071776.59 | 1065266.16 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302297 | BURUANGA VOCATIONAL SCHOOL | BURUANGA | 0 | 1 | UPGRADING | 1 | 1433471.0093 | 1424067.78 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302330 | IBAJAY NATIONAL HIGH SCHOOL | IBAJAY | 0 | 1 | UPGRADING | 1 | 1087308.492 | 1080649.5 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302321 | NAILE NHS | IBAJAY | 0 | 1 | UPGRADING | 1 | 1170314.3204 | 1163244.61 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302322 | NAISUD NATIONAL HIGH SCHOOL | IBAJAY | 0 | 1 | UPGRADING | 1 | 1087308.49 | 1080648.45 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114750 | Kalibo Pilot Elementary School | KALIBO (Capital) | 0 | 1 | UPGRADING | 2 | 1559325.69 | 1549237.27 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-20 | HOVERT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302332 | REGIONAL SCIENCE HIGH SCHOOL FOR REGION VI | KALIBO (Capital) | 0 | 1 | UPGRADING | 1 | 1076755.992 | 1070325.88 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500171 | LEZO INTEGRATED SCHOOL | LEZO | 0 | 1 | UPGRADING | 1 | 1334452.7327 | 1326561.92 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500181 | DALAGSAAN INTRGRATED SCHOOL | LIBACAO | 0 | 1 | SOLAR PANEL | 1 | 689097.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302311 | GUADALUPE NHS | LIBACAO | 0 | 1 | UPGRADING | 1 | 1180866.8204 | 1173499.96 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302310 | LIBACAO NFVHS | LIBACAO | 0 | 1 | UPGRADING | 1 | 1252893.4202 | 1245178.92 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114791 | MAYTARAW PRIMARY SCHOOL | LIBACAO | 0 | 1 | SOLAR PANEL | 1 | 558245.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114800 | TAROYTOY PRIMARY SCHOOL | LIBACAO | 0 | 1 | SOLAR PANEL | 1 | 778090.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302315 | MADALAG NHS | MADALAG | 0 | 1 | UPGRADING | 1 | 1087308.492 | 1080811.72 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302305 | ANSELMO B. LEGASPI NHS | MAKATO | 0 | 1 | UPGRADING | 1 | 1054537.92 | 1047441.42 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500172 | MAKATO IS | MAKATO | 0 | 1 | UPGRADING | 1 | 1499637.911 | 1490537.95 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302295 | Boracay NHS-Main | MALAY | 0 | 1 | UPGRADING | 2 | 1424551.34 | 1416036.31 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 0 | 1 | UPGRADING | 2 | 1340741.03 | 1332392.44 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114850 | Malay Elementary School | MALAY | 0 | 1 | UPGRADING | 2 | 1375101.76 | 1366795.3 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 310611 | Manocmanoc National High School | MALAY | 0 | 1 | UPGRADING | 2 | 1424551.34 | 1416037.9 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302317 | MALAY NHS | MALAY | 0 | 1 | UPGRADING | 1 | 1252893.4202 | 1245413.07 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302319 | MALINAO SFPC | MALINAO | 0 | 1 | UPGRADING | 1 | 1252893.4202 | 1245399.42 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114887 | Nabas ES | NABAS | 0 | 1 | UPGRADING | 2 | 1359273.01 | 1346335.63 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302302 | CANDELARIA NHS | NEW WASHINGTON | 0 | 1 | UPGRADING | 1 | 1252893.4202 | 1245100.04 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114907 | New Washington ES | NEW WASHINGTON | 0 | 1 | UPGRADING | 2 | 1359273.01 | 1346585.61 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302303 | NEW WASHINGTON NCHS | NEW WASHINGTON | 0 | 1 | UPGRADING | 1 | 1252893.4202 | 1244985.81 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302328 | OCHANDO NHS | NEW WASHINGTON | 0 | 1 | UPGRADING | 1 | 1087308.492 | 1080248.4 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500035 | NUMANCIA IS | NUMANCIA | 0 | 1 | UPGRADING | 1 | 1433471.0093 | 1424990.47 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302327 | NUMANCIA NSOF | NUMANCIA | 0 | 1 | UPGRADING | 1 | 1334452.7327 | 1326239.93 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500183 | JAWILI INTEGRATED SCHOOL | TANGALAN | 0 | 1 | UPGRADING | 1 | 988371.02 | 982463.37 | COMPLETED | 1 |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500173 | TAMALAGON INTEGRATED SCHOOL | TANGALAN | 0 | 1 | UPGRADING | 1 | 1071776.59 | 1065192.94 | COMPLETED | 1 |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302361 | Igpalge NHS | ANINI-Y | 0 | 1 | UPGRADING | 1 | 1473366.6544 | 1098409.6 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302376 | San Roque-Ezpeleta NHS | ANINI-Y | 0 | 1 | UPGRADING | 1 | 763541.358 | 737317.19 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302346 | Barbaza NHS | BARBAZA | 0 | 1 | UPGRADING | 1 | 1574739.8 | 1142078.54 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302347 | Belison NS | BELISON | 0 | 1 | UPGRADING | 1 | 1893925.7549 | 1511206.51 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302368 | Northern Bugasong NHS | BUGASONG | 0 | 1 | UPGRADING | 1 | 1167437.5 | 872394.36 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310709 | Northern Bugasong NHS Annex - Pangalcagan Campus | BUGASONG | 0 | 1 | UPGRADING | 1 | 1180187.63 | 867967.43 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302379 | Southern Bugasong NHS | BUGASONG | 0 | 1 | UPGRADING | 1 | 1232482 | 1150672.42 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302348 | Bitadton NHS | CULASI | 0 | 1 | UPGRADING | 1 | 1560551.4094 | 1063790.67 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302349 | Buhang NHS | HAMTIC | 0 | 1 | UPGRADING | 1 | 1468090.4044 | 1099736.23 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310704 | Gen. Leandro Fullon NS | HAMTIC | 0 | 1 | UPGRADING | 1 | 1552046.0944 | 1099736.23 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302358 | Gov. Julio V. Macuja MCHS | HAMTIC | 0 | 1 | UPGRADING | 1 | 1528613.09 | 1213982.18 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302356 | Governor Julian Fullon Pacificador National School | HAMTIC | 0 | 1 | UPGRADING | 2 | 1540311.71 | 1079396.57 | COMPLETED | 1 | August 24, 2018 |  | R6-D2-2018BEFF-06A-E | R6-D2-2018BEFF-06A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Elaectrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310701 | Guintas NHS | HAMTIC | 0 | 1 | UPGRADING | 1 | 1576380.1594 | 1102389.47 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302366 | Moscoso-Rios NHS | HAMTIC | 0 | 1 | UPGRADING | 1 | 1644507.0994 | 1099736.23 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302351 | Col. Ruperto Abellon NHS | LAUA-AN | 0 | 1 | UPGRADING | 1 | 1654631.47 | 1185529.48 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310708 | Eastern Laua-an NHS (Maria NHS) | LAUA-AN | 0 | 1 | UPGRADING | 2 | 1555222.1 | 1172199.65 | COMPLETED | 1 | August 24, 2018 |  | R6-D2-2018BEFF-06A-E | R6-D2-2018BEFF-06A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Elaectrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302362 | Laua-an NHS | LAUA-AN | 0 | 1 | UPGRADING | 1 | 1546769.8444 | 1063973.99 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302363 | Libertad NVS | LIBERTAD | 0 | 1 | UPGRADING | 1 | 1975998.14 | 1439565.2 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302383 | Union NHS | LIBERTAD | 0 | 1 | UPGRADING | 1 | 1557322.3444 | 1073165.07 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302365 | Mag-aba NHS | PANDAN | 0 | 1 | UPGRADING | 1 | 1543540.7794 | 1063790.67 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302369 | Pandan NVHS | PANDAN | 0 | 1 | UPGRADING | 1 | 1844124.87 | 1331376.2 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302372 | Patria NS | PANDAN | 0 | 1 | UPGRADING | 1 | 1229855.65 | 918108.34 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302380 | Sta. Ana NHS | PANDAN | 0 | 1 | UPGRADING | 1 | 1494471.6544 | 1205431.84 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302343 | Aureliana NHS | PATNONGON | 0 | 1 | UPGRADING | 1 | 1459585.0894 | 999701.27 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302359 | Igburi NHS | PATNONGON | 0 | 1 | UPGRADING | 1 | 832310.3157 | 668041.78 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302364 | Lirio M. Escaño, Sr. NHS | PATNONGON | 0 | 1 | UPGRADING | 1 | 1329218.7011 | 1299724.65 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302375 | San Pedro NHS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | 1 | 1457911.07 | 1133633.31 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302344 | Barangbang NHS | SAN REMIGIO | 0 | 1 | UPGRADING | 1 | 1528253.2 | 1094086.08 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302357 | Gideon M. Cabigunda MS | SAN REMIGIO | 0 | 1 | UPGRADING | 1 | 700909.9822 | 597725.96 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310707 | Gov. Evelio B. Javier MNHS | SAN REMIGIO | 0 | 1 | UPGRADING | 1 | 949316.1463 | 797834.36 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302377 | Sebaste HS | SEBASTE | 0 | 1 | UPGRADING | 1 | 1457911.07 | 1095657.93 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310710 | Dr. Luis E. Baraquia NHS | SIBALOM | 0 | 1 | UPGRADING | 1 | 634046.1785 | 549869.52 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302354 | Egaña NHS | SIBALOM | 0 | 1 | UPGRADING | 1 | 693745.6283 | 617849.38 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302370 | Pangpang NHS | SIBALOM | 0 | 1 | UPGRADING | 1 | 673996.0322 | 614584.85 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302373 | Pis-anan NHS | SIBALOM | 0 | 1 | UPGRADING | 1 | 1303808.4367 | 1071547.63 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310703 | Sibalom NHS | SIBALOM | 0 | 1 | UPGRADING | 1 | 1653380.373 | 1374861.34 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302378 | Sido-San Juan NHS | SIBALOM | 0 | 1 | UPGRADING | 1 | 610902.0933 | 489178.33 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302381 | Sta. Justa NHS | TIBIAO | 0 | 1 | UPGRADING | 1 | 1488330.0994 | 1057724.39 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310702 | Tario Lim MHS | TIBIAO | 0 | 1 | UPGRADING | 1 | 1695162.5 | 1270558.12 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302345 | Barasanan NHS | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING | 1 | 1506206.0344 | 1098596.17 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302352 | Concepcion L. Cazeñas MS | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING | 1 | 1581682.35 | 1206038.48 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302353 | Diclum NHS | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING | 1 | 1166834.99 | 946551.84 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302360 | Igcado NHS | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING | 1 | 1379634.7568 | 1028762.01 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302371 | Pascual M. Osuyos MS | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING | 1 | 1327737.5618 | 1029816.89 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302384 | Valderrama NHS | VALDERRAMA | 0 | 1 | UPGRADING | 1 | 1046325.6906 | 985225.09 | COMPLETED | 1 | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bacolod City | 302713 | Jovito H. Sayson NHS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 1243711.98 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2018 | Region VI | Bacolod City | 302710 | Mandalagan NHS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 1198382.95 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2018 | Region VI | Bacolod City | 302718 | Teofilo M. Gensoli Sr. NHS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 1183857.74 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2018 | Region VI | Bago City | 302720 | Ramon Torres Dulao NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 1102366.73 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 1200557.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 1043874.29 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bago City | 302722 | RAMON TORRES MALINGIN NATIONAL HIGH SCHOOL | BAGO CITY | 4 | 1 | UPGRADING | 1 | 699622.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 1099930.86 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bago City | 302723 | Ramon Torres Sagasa National High School | BAGO CITY | 4 | 1 | UPGRADING | 1 | 684142.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 817515.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302726 | Cadiz Viejo NHS | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1457684.85 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302728 | Caduha-an NHS | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1457684.85 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | UPGRADING | 2 | 1457684.85 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302736 | Jerusalem National High School (Villacin NHS - Jerusalem Ext. HS) | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1433253.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1529330.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302727 | Sicaba National High School | CADIZ CITY | 2 | 1 | UPGRADING | 2 | 1457684.85 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302732 | SPED High School | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1433253.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302733 | Tiglawigan NHS | CADIZ CITY | 2 | 1 | SOLAR PANEL | 1 | 1476567.94 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310802 | Dao National High School | DAO | 1 | 1 | UPGRADING | 1 | 577012.2934 | 570121.48 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115553 | Cabungahan Elementary School | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115554 | Canapian ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115555 | Carataya ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115552 | Dominador T. Esmeralda ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115557 | East Villaflores ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302412 | East Villaflores NHS | MA-AYON | 1 | 1 | UPGRADING | 1 | 491147.8672 | 487116.68 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115558 | Fernandez ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302404 | Florentina B. Degala NHS | MA-AYON | 1 | 1 | UPGRADING | 1 | 577012.2934 | 570093.12 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115560 | Ilawod Elementary School | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115561 | Indayagan PS | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 511754.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115562 | Jebaca ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115563 | Maalan Primary School | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 511754.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115564 | Maayon ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 849437.03 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302413 | Maayon NHS | MA-AYON | 1 | 1 | UPGRADING | 1 | 1169728.0681 | 1162433.4 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115565 | Manayupit ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 570194.02 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115566 | New Guia ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 794739.95 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115567 | Old Guia PS | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 540542.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115568 | Palaguian ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115569 | Parallan Elementary School | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 653679.04 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115570 | Piña ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 570194.02 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115571 | Quevedo ES (ngalan es) | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 765952.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115572 | Quinabonglan ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 932922.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115573 | Quinat-uyan ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 765952.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115574 | Salgan ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115575 | Tapulang Elementary School | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 653679.04 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115576 | Tepacla ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115577 | Tuburan ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302403 | Tuburan NHS | MA-AYON | 1 | 1 | UPGRADING | 1 | 487575.6349 | 483682.9 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115578 | West Villaflores ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302395 | Comsr. Luis R. Asis NHS | PANAY | 1 | 1 | UPGRADING | 1 | 487575.6349 | 483682.9 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302398 | Felix Balgos MNHS | PANAY | 1 | 1 | UPGRADING | 1 | 660495.2314 | 654695.2 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310812 | Pawa National High School | PANAY | 1 | 1 | UPGRADING | 1 | 578203.0375 | 571256.62 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302410 | Leodegario D. Deocampo Sr. NHS | PANITAN | 1 | 1 | UPGRADING | 1 | 641705.0278 | 611148.81 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302418 | Panitan NHS | PANITAN | 1 | 1 | UPGRADING | 1 | 645277.2601 | 611969.72 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302392 | Casanayan NHS | PILAR | 1 | 1 | UPGRADING | 1 | 745160.4082 | 740395.36 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302400 | Dulangan NHS | PILAR | 1 | 1 | UPGRADING | 1 | 660495.2314 | 654695.2 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302419 | Marciano M. Patricio (Pilar) | PILAR | 1 | 1 | UPGRADING | 1 | 800353.36 | 791538.42 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | CAPIZ | 302422 | San Nicolas NHS (Pilar) | PILAR | 1 | 1 | UPGRADING | 1 | 745160.4082 | 738002.63 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310811 | YATING NATIONAL HIGH SCHOOL | PILAR | 1 | 1 | UPGRADING | 1 | 491147.8672 | 487116.68 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302405 | Hipona NHS | PONTEVEDRA | 1 | 1 | UPGRADING | 1 | 748732.6405 | 743800.76 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302420 | Pontevedra NHS | PONTEVEDRA | 1 | 1 | UPGRADING | 1 | 658113.7432 | 652424.93 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302388 | Cabugcabug NHS | PRESIDENT ROXAS | 1 | 1 | UPGRADING | 1 | 665249.7025 | 659227.04 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115713 | Cubay-Ibaca ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115711 | DOMINGO M. LOCSIN ES (CABUGCABUG) | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115714 | Goce ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115715 | Madulano ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115716 | Manoling ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115717 | Marita ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115718 | Pandan ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115719 | Pondol ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115720 | Pres. Roxas East ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 904134.12 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115721 | Pres. Roxas West Elementary School | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 653679.04 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115722 | Quiajo ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 656557.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115723 | Sangkal ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115724 | Vedasto T. Javellosa ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302391 | Capiz National High School | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 359385.49 | 297233.15 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115416 | Bun-od Primary School | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 511754.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115417 | Carataya ES (cuartero) | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115418 | Cuartero CES | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 765952.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302396 | Cuartero NHS | CUARTERO | 2 | 1 | UPGRADING | 1 | 896942.9884 | 890528.4 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115419 | Lunayan E/S | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115420 | Mahabang Sapa PS | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 540542.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115421 | Mahunodhunod ES | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115422 | Maindang Elementary School | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310804 | Maindang NHS | CUARTERO | 2 | 1 | UPGRADING | 1 | 460476.3928 | 454038.44 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115423 | Mainit Elementary School | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115424 | Malagab-i ES | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115425 | Nagba ES | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115426 | Putian ES | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302421 | Putian NHS | CUARTERO | 2 | 1 | UPGRADING | 1 | 920469.9982 | 911404.75 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115427 | San Antonio ES (Cuartero) | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 708376.13 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310808 | SAN ANTONIO NATIONAL HIGH SCHOOL | CUARTERO | 2 | 1 | UPGRADING | 1 | 720451.1596 | 711055.12 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115428 | SINABSABAN ELEMENTARY SCHOOL | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115415 | Vicente F. Fabuna ES (Bito-on Ilaya) | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 653679.04 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302385 | Arturo Jugo NHS | DAO | 2 | 1 | UPGRADING | 1 | 593486.4343 | 568081.08 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302415 | Luis Escutin NHS | DAO | 2 | 1 | UPGRADING | 1 | 575821.5493 | 568986.35 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302414 | MALONOY NATIONAL HIGH SCHOOL (DAO) | DAO | 2 | 1 | UPGRADING | 1 | 722824.1425 | 713297.85 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115441 | Manhoy ES | DAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115442 | Mapulang Bato Primary School | DAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 540542.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115443 | Matagnop Elementary School | DAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 765952.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115436 | Nicanor Escutin ES | DAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 765952.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115446 | Quinayuya Elementary School | DAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115447 | Tabuc ES | DAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 737164.07 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302401 | Concepcion Castro Garcia NHS (Dumalag NHS) Sta. Cruz | DUMALAG | 2 | 1 | UPGRADING | 1 | 661685.9755 | 655830.34 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310806 | Dumalag Central NHS | DUMALAG | 2 | 1 | UPGRADING | 1 | 886226.2915 | 877667.33 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302386 | Bungsuan NHS | DUMARAO | 2 | 1 | UPGRADING | 1 | 743969.6641 | 733287.85 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302402 | Estefania Montemayor NHS | DUMARAO | 2 | 1 | UPGRADING | 1 | 833406.3226 | 822785.16 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302416 | Manuel F. Onato NHS | DUMARAO | 2 | 1 | UPGRADING | 1 | 751114.1287 | 740041.9 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310814 | Presentacion Diez Gregorio NHS | DUMARAO | 2 | 1 | UPGRADING | 1 | 745160.4082 | 734413.53 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302417 | Ramon A. Benjamin Sr. NHS | DUMARAO | 2 | 1 | UPGRADING | 1 | 632196.7399 | 627717.72 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310807 | Basiao NHS (formerly Ext. of Ivisan NHS) | IVISAN | 2 | 1 | UPGRADING | 1 | 829834.0903 | 819408.14 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302406 | Ivisan NHS | IVISAN | 2 | 1 | UPGRADING | 1 | 835787.8108 | 825036.51 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302408 | Jagnaya NHS | JAMINDAN | 2 | 1 | UPGRADING | 1 | 665258.2078 | 659235.74 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302409 | Jamindan NHS | JAMINDAN | 2 | 1 | UPGRADING | 1 | 671211.9283 | 659558.6 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302411 | Lucero NHS | JAMINDAN | 2 | 1 | UPGRADING | 1 | 666448.9519 | 660370.87 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302407 | Macario Delfin Bermejo NHS | JAMINDAN | 2 | 1 | UPGRADING | 1 | 834605.572 | 823919.46 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302397 | David Moises MHS | MAMBUSAO | 2 | 1 | UPGRADING | 1 | 889798.5238 | 881044.35 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310813 | Mambusao East NHS (ext. of David Moises) | MAMBUSAO | 2 | 1 | UPGRADING | 1 | 883844.8033 | 875415.98 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310805 | MAMBUSAO NATIONAL HIGH SCHOOL | MAMBUSAO | 2 | 1 | UPGRADING | 1 | 890989.2679 | 882170.02 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310810 | Lonoy National High School | SAPI-AN | 2 | 1 | UPGRADING | 1 | 749774.8687 | 727257.71 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302424 | Sapian National High School | SAPI-AN | 2 | 1 | UPGRADING | 1 | 1228794.2095 | 1198341.71 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310815 | Mianay NHS | SIGMA | 2 | 1 | UPGRADING | 1 | 718069.6714 | 708803.77 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302399 | Vicente Andaya Sr. NHS | SIGMA | 2 | 1 | UPGRADING | 1 | 575821.5493 | 564432.92 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310801 | Bagong Barrio NHS | TAPAZ | 2 | 1 | UPGRADING | 1 | 574630.8052 | 563307.25 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302389 | Camburanan NHS | TAPAZ | 2 | 1 | UPGRADING | 1 | 574630.8052 | 563307.25 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302390 | Candelaria NHS | TAPAZ | 2 | 1 | UPGRADING | 1 | 574630.8052 | 563307.25 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 311705 | Candelaria NHS- Roxas Ext. | TAPAZ | 2 | 1 | UPGRADING | 1 | 631014.5011 | 621557.81 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302393 | Col. Patrocinio Artuz NHS | TAPAZ | 2 | 1 | UPGRADING | 1 | 578203.0375 | 571256.62 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | CAPIZ | 310809 | REV. TOMAS CONEJAR NHS | TAPAZ | 2 | 1 | UPGRADING | 1 | 578203.0375 | 571256.62 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302423 | San Nicolas NHS (Tapaz) | TAPAZ | 2 | 1 | UPGRADING | 1 | 575821.5493 | 568986.35 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310803 | Tapaz NHS | TAPAZ | 2 | 1 | UPGRADING | 1 | 578203.0375 | 571256.62 | COMPLETED | 1 | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Escalante City | 302625 | Escalante NHS | CITY OF ESCALANTE | 1 | 1 | UPGRADING | 1 | 1141365.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Guimaras | 310901 | Ayangan National High School | SIBUNAG | 0 | 1 | UPGRADING | 1 | 3911646.12 | 3,660,995.52 | COMPLETED | 1 | Sept. 30, 2018 |  | 02-2018 -lot 1 |  | March 12, 2018 | April 3, 2018 | April 3, 2018 | April 18, 2018 | May 18, 2018 | Noe's Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302445 | Alejandro Firmeza MNHS | MIAGAO | 1 | 1 | UPGRADING | 1 | 3134244.08 | 3084214.84 | COMPLETED | 1 | 2018-12-18 | 2018-12-20 | R06-022-BEFF2918Electrification-B1-L1 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-07-18 | 2018-08-13 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302531 | Miagao NHS | MIAGAO | 1 | 1 | UPGRADING | 1 | 4841253.95 | 4742100 | COMPLETED | 1 | 2018-11-06 | 2019-01-19 | R06-022-BEFF2918Electrification-B1-L2 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-05-18 | 2018-07-02 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302585 | Zarraga National High School | ZARRAGA | 2 | 1 | UPGRADING | 2 | 4863807.6433 | 4618492.77 | COMPLETED | 1 | 2018-01-02 | 2018-12-06 | R06-022-BEFF2918Electrification-B2-L1 |  | 2018-06-05 | 2018-06-13 | 2018-06-26 | 2018-09-03 | 2018-09-20 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302514 | Jose Facultad MNHS | POTOTAN | 3 | 1 | UPGRADING | 1 | 2447822.13 | 4649551.37 | COMPLETED | 1 | 2019-01-02 | 2018-12-06 | R06-022-BEFF2918Electrification-B1-L3 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-07-18 | 2018-08-13 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302556 | Pototan National Comprehensive High School | POTOTAN | 3 | 1 | UPGRADING | 1 | 4063058.75 | 4012805.88 | COMPLETED | 1 | 2018-10-23 | 2018-10-31 | R06-022-BEFF2918Electrification-B1-L4 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-05-24 | 2018-06-18 | Culasi General merchandising and Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302455 | Banate NHS | BANATE | 4 | 1 | UPGRADING | 1 | 4136526.85 | 4100834.58 | COMPLETED | 1 | 2018-11-10 | 2019-03-29 | R06-022-BEFF2918Electrification-B1-L5 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-05-25 | 2018-07-06 | Direct Electriix Equiptment Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302489 | De La Paz National High School | BANATE | 4 | 1 | UPGRADING | 1 | 3496108.79 | 3431471.35 | COMPLETED | 1 | 2018-12-18 | 2018-12-20 | R06-022-BEFF2918Electrification-B1-L6 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-07-18 | 2018-08-13 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302490 | Dingle NHS | DINGLE | 4 | 1 | UPGRADING | 1 | 4041949.4 | 3991552.18 | COMPLETED | 1 | 2018-10-23 | 2018-10-31 | R06-022-BEFF2918Electrification-B1-L7 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-05-24 | 2018-06-18 | Culasi General merchandising and Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 311008 | Rufino G. Palabrica, Sr. NHS | DINGLE | 4 | 1 | UPGRADING | 1 | 3116337.49 | 3066013.4 | COMPLETED | 1 | 2018-10-23 | 2018-10-31 | R06-022-BEFF2918Electrification-B1-L8 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-05-24 | 2018-06-18 | Culasi General merchandising and Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302443 | Ajuy NHS | AJUY | 5 | 1 | UPGRADING | 2 | 4791597.203 | 4726996.64 | COMPLETED | 1 | 2018-01-02 | 2018-12-06 | R06-022-BEFF2918Electrification-B2-L2 |  | 2018-06-05 | 2018-06-13 | 2018-06-26 | 2018-09-03 | 2018-09-20 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302458 | Barotac Viejo National High School | BAROTAC VIEJO | 5 | 1 | UPGRADING | 2 | 4712460.5419 | 4649551.64 | COMPLETED | 1 | 2018-01-02 | 2018-12-06 | R06-022-BEFF2918Electrification-B2-L3 |  | 2018-06-05 | 2018-06-13 | 2018-06-26 | 2018-09-03 | 2018-09-20 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302532 | Milan NHS | LEMERY | 5 | 1 | UPGRADING | 1 | 2546414.24 | 2514225.65 | COMPLETED | 1 | 2018-12-18 | 2018-12-20 | R06-022-BEFF2918Electrification-B1-L9 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-07-18 | 2018-08-13 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302570 | Sara NHS | SARA | 5 | 1 | UPGRADING | 2 | 5410620.46 | 5357379.26 | COMPLETED | 1 | 2018-01-02 | 2018-12-06 | R06-022-BEFF2918Electrification-B2-L4 |  | 2018-06-05 | 2018-06-13 | 2018-06-26 | 2018-09-03 | 2018-09-20 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo City | 302738 | Iloilo City NHS | ILOILO CITY (Capital) | 0 | 1 | UPGRADING | 1 | 4475369.9 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302785 | Bantayan NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1242920.54 | 1233763.67 | COMPLETED | 1 | September 8,2018 |  |  | 2018-011 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117876 | Binicuil ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 1289994.35 | 1279684.23 | COMPLETED | 1 | October 23,2018 |  | 2018-016 | 2018-016 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1079432.83 | 1070675.04 | COMPLETED | 1 | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117877 | Calabasahan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 524506.15 | 518045.22 | COMPLETED | 1 | October 30,2018 |  | 2018-017 | 2018-017 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 25,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302792 | Camansi NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 735237.11 | 729079.2 | COMPLETED | 1 | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1062593.61 | 1053919.59 | COMPLETED | 1 | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117839 | D.C.Gurrucharri MS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1189719.39 | 1179653.73 | COMPLETED | 1 | September 13,2018 |  |  | 2018-012 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117880 | Daan Banua ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 1121839.62 | 1111632.05 | COMPLETED | 1 | October 23,2018 |  | 2018-018 | 2018-018 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1470360.01 | 1459657.31 | COMPLETED | 1 | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117859 | Hilamonan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1235574.22 | 1222832.52 | COMPLETED | 1 | September 13,2018 |  |  | 2018-012 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117860 | Inapoy ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 1118972.87 | 1107188.35 | COMPLETED | 1 | October 30,2018 |  | 2018-017 | 2018-017 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 25,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117862 | Linao ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 610781.59 | 602926.46 | COMPLETED | 1 | October 23,2018 |  | 2018-018 | 2018-018 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117885 | Locotan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1524238.54 | 1510168.12 | COMPLETED | 1 | September 13,2018 |  |  | 2018-014 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117887 | Magballo ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1674056.79 | 1661209.91 | COMPLETED | 1 | September 8,2018 |  |  | 2018-013 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117864 | Matama ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 886082.7 | 874897.42 | COMPLETED | 1 | October 23,2018 |  | 2018-018 | 2018-018 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117848 | Orong ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 739363.37 | 730730.71 | COMPLETED | 1 | October 23,2018 |  | 2018-016 | 2018-016 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117890 | Pacao ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 823203.85 | 812381.19 | COMPLETED | 1 | October 23,2018 |  | 2018-016 | 2018-016 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117867 | Pinaguinpinan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1405408.16 | 1393914.58 | COMPLETED | 1 | September 8,2018 |  |  | 2018-013 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302798 | PINAGUINPINAN NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1178458.45 | 1169522.29 | COMPLETED | 1 | September 8,2018 |  |  | 2018-011 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1211309.76 | 1203264.7 | COMPLETED | 1 | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 777804.47 | 771434.8 | COMPLETED | 1 | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117870 | Tagoc ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 1125610.39 | 1113766.43 | COMPLETED | 1 | October 30,2018 |  | 2018-017 | 2018-017 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 25,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117894 | Talubangi ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1294087.86 | 1283512.02 | COMPLETED | 1 | September 13,2018 |  |  | 2018-012 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1066144.14 | 1058821.3 | COMPLETED | 1 | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 312101 | TAN-AWAN NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1015085.74 | 1006648.06 | COMPLETED | 1 | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117895 | Tapi ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 2109898.02 | 2090797.87 | COMPLETED | 1 | September 13, 2018 |  |  | 2018-014 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 8,2018 | Micro-asia Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302801 | Tapi NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1141365.67 | 1132714.04 | COMPLETED | 1 | September 8,2018 |  |  | 2018-011 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117872 | Yanog ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 477986.55 | 471075.51 | COMPLETED | 1 | September 8,2018 |  |  | 2018-013 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 5285721.3 | 4974653.02 | COMPLETED | 1 |  |  | 5460136 | 18-09-013 | July 3, 2018 | July 11, 2018 | August 20, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302652 | Inocencio V. Ferrer SOF (TASOF) (under the Reg'l Office) | CITY OF TALISAY | 3 | 1 | UPGRADING | 1 | 3764775.05 | 3721032.46 | COMPLETED | 1 |  |  | 5460154 | 18-09-014 | July 3, 2018 | July 11, 2018 | July 23, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302678 | Rafael B. Lacson NHS | CITY OF TALISAY | 3 | 1 | UPGRADING | 1 | 3817604.51 | 3788330.6 | COMPLETED | 1 |  |  | 5605695 | 18-10-015 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302695 | Victorias National High School | CITY OF VICTORIAS | 3 | 1 | UPGRADING | 1 | 5241938.17 | 5205258.47 | COMPLETED | 1 |  |  | 5605347 | 18-10-014 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302609 | Cansilayan NHS | MURCIA | 3 | 1 | UPGRADING | 1 | 1274910.45 | 1249959.61 | COMPLETED | 1 |  |  | 5463534 | 18-09-017 | July 4, 2018 | July 12, 2018 | July 24, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302670 | Murcia National High School | MURCIA | 3 | 1 | UPGRADING | 1 | 3382586.69 | 3346741.14 | COMPLETED | 1 |  |  | 5460097 | 18-09-012 | July 3, 2018 | July 11, 2018 | July 23, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4 | 1 | UPGRADING | 1 | 3817604.51 | 3780045.51 | COMPLETED | 1 |  |  | 5463520 | 18-09-016 | July 4, 2018 | July 12, 2018 | July 24, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 116882 | Binadlan ES | BINALBAGAN | 5 | 1 | SOLAR PANEL | 1 | 881548.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 116875 | Nabu-ac ES | BINALBAGAN | 5 | 1 | SOLAR PANEL | 1 | 473564.08 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117087 | Tiqui ES | CITY OF HIMAMAYLAN | 5 | 1 | SOLAR PANEL | 1 | 614377.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302651 | Hinigaran NHS | HINIGARAN | 5 | 1 | UPGRADING | 1 | 5608104.57 | 5180471.84 | COMPLETED | 1 |  |  | 5460162 | 18-09-015 | July 3, 2018 | July 11, 2018 | August 2, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302668 | Negros Occ. NAISHI ( under the Reg'l Office) | HINIGARAN | 5 | 1 | UPGRADING | 1 | 3745342.73 | 3461829.73 | COMPLETED | 1 |  |  | 5460063 | 18-09-011 | July 3, 2018 | July 11, 2018 | August 2, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 | 1 | UPGRADING | 1 | 2814054.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117256 | Agogolo ES | MOISES PADILLA (MAGALLON) | 5 | 1 | SOLAR PANEL | 1 | 1287247.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117259 | Cuyaoyao ES | MOISES PADILLA (MAGALLON) | 5 | 1 | SOLAR PANEL | 1 | 881548.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117270 | Nacurohan ES | MOISES PADILLA (MAGALLON) | 5 | 1 | SOLAR PANEL | 1 | 1287247.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 116967 | Jerusalem ES | CAUAYAN | 6 | 1 | SOLAR PANEL | 1 | 612976.08 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117009 | Pinamay-an ES | CAUAYAN | 6 | 1 | SOLAR PANEL | 1 | 1079342.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 180521 | Dung-I ES | CITY OF SIPALAY | 6 | 1 | SOLAR PANEL | 1 | 1079342.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 | 1 | UPGRADING | 1 | 4406315.1 | 4372766.4 | COMPLETED | 1 |  |  | 5605736 | 18-10-016 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117359 | Hda. Maricalum ES | CITY OF SIPALAY | 6 | 1 | SOLAR PANEL | 1 | 875895.2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117378 | Patag Magbanua ES | CITY OF SIPALAY | 6 | 1 | SOLAR PANEL | 1 | 1491653.57 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Passi City | 302806 | Efraim M. Santibanez National High School | CITY OF PASSI | 4 | 1 | UPGRADING | 1 | 3134244.08 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 302755 | Bago NHS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 547749.92 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 302756 | Balijuagan NHS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 578369.05 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117666 | Banica Elementary School | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 869082.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117652 | Barra ES | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 950120.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 302757 | Cong. Ramon A. Arnaldo HS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 978658.94 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117654 | Culasi ES | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 955368.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117667 | Don Amando Bayot, Sr. MS | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 869435.16 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 311704 | Don Ynocencio A. Del Rosario National High School formerly Tanque NHS-Dayao Extension | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 988944.69 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117656 | Don Ynocencio del Rosario MS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 579912.76 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 302759 | Dumolog NHS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 580044.6 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117685 | Lawa-an ES | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1104086.97 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117686 | Loctugan ES | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 986563.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 311703 | Marcos Fuentes IS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 607797.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 302760 | Milibili NHS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 578369.05 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117661 | Pres. Manuel Roxas MS - North | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 889037.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117662 | Pres. Manuel Roxas MS - South | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 890228.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 311702 | Roxas City School for Philippine Craftsmen | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 679412.19 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 500195 | Sofronio A. Cordovero Integrated School | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 913755.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 302761 | Tanque NHS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 579559.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117689 | Venancio Alba ES | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 884274.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1191398.82 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 302764 | Colonia Divina Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1170095.84 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1496882.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 302766 | Himogaan Baybay Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1495260.19 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 343922 | Sagay City SHS | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1496882.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 302767 | Sagay NHS | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1496882.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 311803 | Sagay NHS-Lopez Jaena Ext. | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1170095.84 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 311802 | Sagay NHS-Rizal Ext. | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1271236.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 302771 | Vito NHS | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1225112.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | San Carlos City | 117759 | Gigalaman ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 1793278.34 |  | COMPLETED | 1 |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2019 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | San Carlos City | 117761 | Handalago ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 1144542.09 |  | COMPLETED | 1 |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2020 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | San Carlos City | 117778 | Lagha Elementary School - Extension | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 917691.67 |  | COMPLETED | 1 |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2021 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | San Carlos City | 117797 | Pagbatangan ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 3955732.52 |  | COMPLETED | 1 |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2022 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | San Carlos City | 117798 | Paniagan ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 928296.67 |  | COMPLETED | 1 |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2023 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | San Carlos City | 117755 | Rizal ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 1577032.92 |  | COMPLETED | 1 |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2018 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2018 | Region VI | Silay City | 302781 | Brgy. E. Lopez National High School | SILAY CITY | 3 | 1 | UPGRADING | 1 | 1678512.43 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Silay City | 302778 | Brgy. Guimbala-on NHS | SILAY CITY | 3 | 1 | UPGRADING | 1 | 1226572.17 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Silay City | 302779 | Don Felix T. Lacson NHS (Brgy. Capitan Ramon) | SILAY CITY | 3 | 1 | UPGRADING | 1 | 1223049.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VI | Silay City | 302780 | Doña Montserrat Lopez MHS | SILAY CITY | 3 | 1 | UPGRADING | 2 | 4612008.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 500543 | Balete Integrated School | BALETE | 0 | 1 | UPGRADING |  | 1266873.53 | 1068886.54 | COMPLETED | 1 | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114660 | Banga ES | BANGA | 0 | 1 | UPGRADING |  | 2162134.07 | 1938079.79 | COMPLETED | 1 |  | August 6, 2021 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C2-143-2018 |  | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114678 | Torralba ES | BANGA | 0 | 1 | UPGRADING | Batch 3 | 1128105.53 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114681 | Batan Elementary School | BATAN | 0 | 1 | UPGRADING |  | 1642173.37 | 1385534.51 | COMPLETED | 1 | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114686 | Camaligan ES | BATAN | 0 | 1 | UPGRADING | Batch 3 | 1295560.24 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 500184 | Mandong Integrated School | BATAN | 0 | 1 | UPGRADING | Batch 3 | 1287978.53 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 500642 | Palay Integrated School | BATAN | 0 | 1 | UPGRADING |  | 1183233.32 | 998317.62 | COMPLETED | 1 | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 500187 | Tabon Integrated School | BATAN | 0 | 1 | UPGRADING |  | 1230719.57 | 1038382.72 | COMPLETED | 1 | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114702 | Bel-is ES | BURUANGA | 0 | 1 | UPGRADING | Batch 3 | 1211747.83 | 1195000 | COMPLETED | 1 |  |  | DepED-RO6-D1-BEFF2019ELEC.B2-C3-053-2019 |  | 2019-08-08 | 2019-08-15 | 2019-08-27 | 2019-08-29 | 2019-10-07 | First Makeen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114719 | Ibajay Central School | IBAJAY | 0 | 1 | UPGRADING |  | 2162188.12 | 1824281.36 | COMPLETED | 1 | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114736 | Monlaque Elementary School | IBAJAY | 0 | 1 | UPGRADING | Batch 3 | 1060061.31 | 1045000 | COMPLETED | 1 |  |  | DepED-RO6-D1-BEFF2019ELEC.B2-C3-053-2019 |  | 2019-08-08 | 2019-08-15 | 2019-08-27 | 2019-08-29 | 2019-10-07 | First Makeen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114737 | Naile ES | IBAJAY | 0 | 1 | UPGRADING | Batch 3 | 1248621.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114738 | Naisud CS | IBAJAY | 0 | 1 | UPGRADING |  | 1559364.68 | 1315667.17 | COMPLETED | 1 | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114746 | Andagaw Elementary School | KALIBO (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1139450.85 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114756 | Kalibo I ES | KALIBO (Capital) | 0 | 1 | UPGRADING |  | 1223263.26 | 1096446.46 | COMPLETED | 1 |  | August 6, 2021 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C2-143-2018 |  | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 500179 | Kalibo Integrated Special Education Center | KALIBO (Capital) | 0 | 1 | UPGRADING |  | 1183233.32 | 1096236.47 | COMPLETED | 1 |  | August 6, 2021 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C2-143-2018 |  | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114758 | Linabuan Norte ES | KALIBO (Capital) | 0 | 1 | UPGRADING |  | 1223263.26 | 1058883.25 | COMPLETED | 1 |  | August 6, 2021 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C2-143-2018 |  | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114752 | New Buswang Elementary School | KALIBO (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1223263.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114762 | Tinigaw ES | KALIBO (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1223263.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114856 | Yapak Elementary School | MALAY | 0 | 1 | UPGRADING | Batch 3 | 1186938.28 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114866 | Malinao ES | MALINAO | 0 | 1 | UPGRADING |  | 1301436.87 | 1166644.91 | COMPLETED | 1 |  | August 6, 2021 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C2-143-2018 |  | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114883 | LASERNA ELEMENTARY SCHOOL | NABAS | 0 | 1 | UPGRADING |  | 1275494.58 | 1076160.29 | COMPLETED | 1 | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 302337 | Toledo NHS | NABAS | 0 | 1 | UPGRADING |  | 1486724.18 | 1254378.93 | COMPLETED | 1 | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114895 | Unidos Elementary School | NABAS | 0 | 1 | UPGRADING | Batch 3 | 1359307 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114896 | Union Elementary School | NABAS | 0 | 1 | UPGRADING | Batch 3 | 1275494.58 | 1129034.12? | COMPLETED | 1 |  |  | DepED-RO6-D1-BEFF2019ELEC.B2-C6-056-2019 |  | 2019-08-08 | 2019-08-08 | 2019-08-27 | 2019-08-29 | 2019-10-07 | KRIS DB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 302340 | Union National High School | NABAS | 0 | 1 | UPGRADING |  | 1193785.82 | 1007220.97 | COMPLETED | 1 | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | 2.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 114939 | Anini-y CS | ANINI-Y | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366539.9132 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 114958 | Barbaza Central School | BARBAZA | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366539.9132 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 114961 | Capoyu-an ES | BARBAZA | 0 | 1 | UPGRADING | Batch 3 | 1305579.42 | 1295902.67 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 114973 | Belison CS | BELISON | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366539.9132 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 302342 | Antique Vocational School | BUGASONG | 0 | 1 | UPGRADING | Batch 1 | 3010746.02 | 2680652.5155 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 114984 | Bugasong CS | BUGASONG | 0 | 1 | UPGRADING | Batch 1 | 1841129.22 | 1639233.1205 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 114991 | Jinalinan-Paliwan ES | BUGASONG | 0 | 1 | UPGRADING | Batch 3 | 2164419.44 | 2145894.44 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115033 | Bitadton ES | CULASI | 0 | 1 | UPGRADING | Batch 3 | 1467887.06 | 1458367.7 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115038 | Culasi CS | CULASI | 0 | 1 | UPGRADING | Batch 1 | 1805242.29 | 1607264.3707 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115039 | Culasi North ES | CULASI | 0 | 1 | UPGRADING | Batch 1 | 1235709.96 | 1099907.0222 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 500515 | Kawit Integrated School | CULASI | 0 | 1 | UPGRADING | Batch 3 | 1284212.15 | 1274291.2 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 500548 | Lipata-Lamputong Integrated School | CULASI | 0 | 1 | UPGRADING | Batch 3 | 1358635.52 | 1347905.79 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 302367 | Northern Antique Vocational School | CULASI | 0 | 1 | UPGRADING | Batch 1 | 3080424.07 | 2743061.1626 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115064 | Buhang ES | HAMTIC | 0 | 1 | UPGRADING | Batch 3 | 1161286.59 | 1152020.72 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115069 | Hamtic Central School | HAMTIC | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366539.9132 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115094 | Moscoso-Rios CS | HAMTIC | 0 | 1 | UPGRADING | Batch 3 | 1427278.86 | 1416377.96 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115106 | Guisijan ES | LAUA-AN | 0 | 1 | UPGRADING | Batch 3 | 1393463.69 | 1382565.37 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115110 | Laua-an CS | LAUA-AN | 0 | 1 | UPGRADING | Batch 1 | 1305579.42 | 1162557.5503 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115130 | Libertad Central School | LIBERTAD | 0 | 1 | UPGRADING | Batch 1 | 1501702.22 | 1337128.0484 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115161 | Pandan CS | PANDAN | 0 | 1 | UPGRADING | Batch 1 | 1805242.29 | 1607527.2385 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115162 | Patria ES | PANDAN | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187577.09 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115193 | Carit-an Central School | PATNONGON | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187750.03 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115179 | Col. Ruperto Abellon Sr. MS | PATNONGON | 0 | 1 | UPGRADING | Batch 1 | 1305579.42 | 1162586.7528 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115196 | Igbarawan-Mabasa Elementary School | PATNONGON | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187750.03 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 178509 | Antique Integrated School | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1473187.68 | 1462402.62 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 302341 | Antique NS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 3849768.93 | 3426899.1597 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115212 | Assemblyman Segundo Moscoso MS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 1501702.22 | 1337201.0682 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115213 | Atabay ES | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 1271764.26 | 1132163.4481 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115224 | Canuto B. Pefianco Sr. ES (Madrangca ES) | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1188312.05 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115218 | Delegate Angel Salazar Jr. MS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 1678988.95 | 1494833.2796 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115220 | Gov. Santos Capadocia MS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 1271764.26 | 1132163.4481 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115225 | Maybato ES | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187749.5 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115229 | Salazar ES (Funda Dalipe ES) | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187577.09 | COMPLETED | 1 | March 5, 2020 |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115231 | San Fernando ES | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1186903.7 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115258 | BUGO CENTRAL SCHOOL | SAN REMIGIO | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 11888268.83 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115238 | Calag-itan CS | SAN REMIGIO | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366481.4991 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115285 | Sebaste CS | SEBASTE | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366539.9132 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115315 | Egaña ES | SIBALOM | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187750.03 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 500549 | Lacaron lntegrated School | SIBALOM | 0 | 1 | UPGRADING | Batch 3 | 1358635.52 | 1347905.79 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115331 | Pis-anan Central School | SIBALOM | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187750.03 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115306 | Sibalom Central ELementary School | SIBALOM | 0 | 1 | UPGRADING | Batch 1 | 1645006.42 | 1464325.0969 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115352 | Tibiao Central School | TIBIAO | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366539.9132 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 302355 | Gamad-Sto. Tomas NHS | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING | Batch 3 | 2138907.08 | 2122370.86 | COMPLETED | 1 |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115408 | Valderama CES | VALDERRAMA | 0 | 1 | UPGRADING | Batch 1 | 1338573.32 | 1191829.2195 | COMPLETED | 1 | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117504 | Bago City Elementary School | BAGO CITY | 4 | 1 | UPGRADING | Batch 3 | 662718.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117506 | Gen. Juan A. Araneta ES | BAGO CITY | 4 | 1 | UPGRADING | Batch 3 | 534638.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117498 | J.L. Araneta Elementary School | BAGO CITY | 4 | 1 | UPGRADING | Batch 3 | 500013.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117508 | L. De La Rama ES | BAGO CITY | 4 | 1 | UPGRADING |  | 216001.52 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117509 | Lag-asan ES | BAGO CITY | 4 | 1 | UPGRADING |  | 672967.88 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117510 | M.L. Araneta ES | BAGO CITY | 4 | 1 | UPGRADING |  | 755636.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117499 | Ma. Rosario Araneta ES | BAGO CITY | 4 | 1 | UPGRADING |  | 279050.04 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117501 | T.M. Morada Sr. ES | BAGO CITY | 4 | 1 | UPGRADING |  | 332856.69 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311405 | Banquerohan NHS (Dr. Vicente F Gustilo NHS-Banquerohan Ext) | CADIZ CITY | 2 | 1 | UPGRADING | Batch 1 | 3176131.35 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311406 | Burgos National High School | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1402643.61 |  | COMPLETED | 1 | [10 empty] | Energized already | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 302729 | Caduha-an NHS - Andres Bonifacio Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1524721.65 |  | COMPLETED | 1 | [10 empty] | Energized already | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311401 | Caduha-an NHS - Luna Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1409045.19 |  | COMPLETED | 1 | [10 empty] | Energized already | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311402 | Caduha-an NHS - Tagbanon Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1602136.72 |  | COMPLETED | 1 | [10 empty] | Energized already | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311404 | Dr. Vicente F. Gustilo Memorial NHS - Daga Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1805687.43 |  | COMPLETED | 1 | [10 empty] | Energized already | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 1 | 4631699.05 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311407 | V NHS-Sewahon Extension High School | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1610170.12 |  | COMPLETED | 1 | [10 empty] | Energized already | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 302735 | Villacin National High School | CADIZ CITY | 2 | 1 | UPGRADING | Batch 1 | 3560415.93 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115547 | Aglimocon ES | MA-AYON | 1 | 1 | UPGRADING |  | 653679.04 |  | COMPLETED | 1 | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115548 | Alasaging ES | MA-AYON | 1 | 1 | UPGRADING |  | 624891.1 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115549 | Alayunan ES | MA-AYON | 1 | 1 | UPGRADING |  | 570194.02 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115550 | Balighot Elementary School | MA-AYON | 1 | 1 | UPGRADING |  | 598981.96 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115551 | Batabat ES | MA-AYON | 1 | 1 | UPGRADING |  | 570194.02 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115707 | Aranguel ES | PRESIDENT ROXAS | 1 | 1 | UPGRADING | Batch 3 | 682466.98 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115708 | Badiangon ES | PRESIDENT ROXAS | 1 | 1 | UPGRADING |  | 682466.98 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115709 | Bayuyan ES | PRESIDENT ROXAS | 1 | 1 | UPGRADING | Batch 3 | 682466.98 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115710 | Bliss Pantalan ES | PRESIDENT ROXAS | 1 | 1 | UPGRADING |  | 570194.02 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 179002 | Cabugcabug ES (president roxas) | PRESIDENT ROXAS | 1 | 1 | UPGRADING | Batch 3 | 598981.96 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115712 | Carmencita-Sto.Niño ES | PRESIDENT ROXAS | 1 | 1 | UPGRADING |  | 682466.98 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115409 | Agcabugao Elementary School | CUARTERO | 2 | 1 | UPGRADING | Batch 3 | 598981.96 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115410 | Agdahon ES | CUARTERO | 2 | 1 | UPGRADING |  | 682466.98 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115411 | Agnaga ES | CUARTERO | 2 | 1 | UPGRADING |  | 598981.96 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115412 | Angub Elementary School | CUARTERO | 2 | 1 | UPGRADING | Batch 3 | 872467.38 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115413 | Balingasag PS | CUARTERO | 2 | 1 | UPGRADING | Batch 3 | 482966.56 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115414 | Bito-on Elementary School | CUARTERO | 2 | 1 | UPGRADING | Batch 3 | 598981.96 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115429 | Agtambi PS | DAO | 2 | 1 | UPGRADING |  | 482966.56 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115430 | Agtanguay ES | DAO | 2 | 1 | UPGRADING |  | 708376.13 |  | COMPLETED | 1 | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115435 | Alfonso E. Espiritu ES (aganan) | DAO | 2 | 1 | UPGRADING |  | 598981.96 |  | COMPLETED | 1 | 2020-03-27 | 2020-02-12 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115444 | Andres E. Quintia Sr. ES (Nasunogan) | DAO | 2 | 1 | UPGRADING |  | 737164.07 |  | COMPLETED | 1 | 2020-03-27 | 2020-02-12 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115445 | Antonio Abad ES (Quinabcaban) | DAO | 2 | 1 | UPGRADING |  | 624891.1 |  | COMPLETED | 1 | 2020-03-27 | 2020-02-12 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115431 | Bita PS | DAO | 2 | 1 | UPGRADING | Batch 3 | 482966.56 |  | COMPLETED | 1 | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115432 | Centro Primary School | DAO | 2 | 1 | UPGRADING | Batch 3 | 540542.44 |  | COMPLETED | 1 | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115433 | Dao Central School | DAO | 2 | 1 | UPGRADING |  | 872467.38 |  | COMPLETED | 1 | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115434 | Daplas Primary School | DAO | 2 | 1 | UPGRADING | Batch 3 | 482966.56 |  | COMPLETED | 1 | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115437 | Ilas Norte ES | DAO | 2 | 1 | UPGRADING |  | 794739.95 |  | COMPLETED | 1 | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115438 | Ilas Sur ES | DAO | 2 | 1 | UPGRADING | Batch 3 | 737164.07 |  | COMPLETED | 1 | 2020-03-27 | 2020-02-12 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115439 | Lacaron ES | DAO | 2 | 1 | UPGRADING |  | 737164.07 |  | COMPLETED | 1 | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115440 | Malonoy ES (dao) | DAO | 2 | 1 | UPGRADING | Batch 3 | 682466.98 |  | COMPLETED | 1 | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Escalante City | 302595 | Buenavista National High School | CITY OF ESCALANTE | 1 | 1 | UPGRADING |  | 1484496.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Escalante City | 302615 | Dian-ay National High School | CITY OF ESCALANTE | 1 | 1 | UPGRADING |  | 1708168.21 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Escalante City | 302626 | Old Poblacion National High School | CITY OF ESCALANTE | 1 | 1 | UPGRADING |  | 1484496.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Escalante City | 302627 | Tamlang National High School | CITY OF ESCALANTE | 1 | 1 | UPGRADING |  | 1335649.91 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302427 | Agsanayan National High School | BUENAVISTA | 0 | 1 | UPGRADING |  | 3034636.02 | 2483302.49 | COMPLETED | 1 | 9-Sept 2019 | 2020-06-02 | 08-2018-01 | 08-2018-01 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Goldentec contractor corporatrion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115821 | Buenavista Central School | BUENAVISTA | 0 | 1 | UPGRADING | Batch 3 | 2830060.1 | 2171152.9061 | COMPLETED | 1 | 2020-06-20 | 2020-11-25 | 04-2019-01 | 04-2019-01 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302426 | Buenavista National High School | BUENAVISTA | 0 | 1 | UPGRADING |  | 2985014.84 | 2441354.27 | COMPLETED | 1 | 9-Sept. 2019 | 2020-06-02 | 08-2018-01 | 08-2018-01 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Goldentec contractor corporatrion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302430 | East Valencia National High School | BUENAVISTA | 0 | 1 | UPGRADING |  | 3034636.02 | 2483302.49 | COMPLETED | 1 | 9-Sept. 2019 | 2020-06-02 | 08-2018-01 | 08-2018-01 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Goldentec contractor corporatrion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302431 | Getulio NHS | BUENAVISTA | 0 | 1 | UPGRADING |  | 3006120.37 | 2459196.23 | COMPLETED | 1 | 9-Sept. 2019 | 2020-06-02 | 08-2018-01 | 08-2018-01 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Goldentec contractor corporatrion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115844 | Supang Central School | BUENAVISTA | 0 | 1 | UPGRADING | Batch 3 | 2804695.36 | 2145914.9839 | COMPLETED | 1 | 2020-06-20 | 2020-11-25 | 04-2019-01 | 04-2019-01 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 310902 | Supang National High School | BUENAVISTA | 0 | 1 | UPGRADING |  | 3359179.9 | 2757662.01 | COMPLETED | 1 | 9-Sept. 2019 | 2020-06-02 | 08-2018-01 | 08-2018-01 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Goldentec contractor corporatrion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115864 | Jordan Central School | JORDAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 2851165.63 | 2227237.9017 | COMPLETED | 1 | 2020-06-20 | 2020-11-25 | 04-2019-02 | 04-2019-02 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115873 | San Miguel Central School | JORDAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 2696555.69 | 2073401.0093 | COMPLETED | 1 | 2020-06-20 | 2020-11-25 | 04-2019-02 | 04-2019-02 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115875 | Sta. Teresa ES | JORDAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 2444481.89 | 1822587.579 | COMPLETED | 1 | 2020-06-20 | 2020-11-25 | 04-2019-02 | 04-2019-02 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115897 | Nueva Valencia Central School | NUEVA VALENCIA | 0 | 1 | UPGRADING | Batch 3 | 2861718.39 | 2105963.1007 | COMPLETED | 1 | 2020-06-20 | 2020-11-25 | 04-2019-03 | 04-2019-03 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302434 | Nueva Valencia National High School | NUEVA VALENCIA | 0 | 1 | UPGRADING |  | 3675064.98 | 3003559.14 | COMPLETED | 1 | 9-Sept. 2019 | 2020-06-02 | 08-2018-02 | 08-2018-02 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Goldentec contractor corporatrion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115915 | Salvacion Central School | NUEVA VALENCIA | 0 | 1 | UPGRADING | Batch 3 | 3618043.01 | 2858506.0891 | COMPLETED | 1 | 2020-06-20 | 2020-11-25 | 04-2019-03 | 04-2019-03 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | SAN LORENZO | 0 | 1 | UPGRADING |  | 3232550.05 | 3208500 | COMPLETED | 1 | 2020-01-22 | 2019-12-26 | 08-2018-03 | 08-2018-03 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302439 | Remedios E. Vilches-San Lorenzo National High School | SAN LORENZO | 0 | 1 | UPGRADING |  | 3232550.05 | 3208500 | COMPLETED | 1 | 2020-01-22 | 2019-12-26 | 08-2018-03 | 08-2018-03 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115858 | Suclaran Central School | SAN LORENZO | 0 | 1 | UPGRADING | Batch 3 | 2521747.1 | 2007310.69 | COMPLETED | 1 | 2020-06-20 | 2020-11-25 | 04-2019-04 | 04-2019-04 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302425 | Alegria NHS | SIBUNAG | 0 | 1 | UPGRADING |  | 2995567.61 | 2973160.5 | COMPLETED | 1 | 2020-01-22 | 2019-12-26 | 08-2018-03 | 08-2018-03 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302429 | Desiderio C. Gange NHS | SIBUNAG | 0 | 1 | UPGRADING |  | 3221997.29 | 3198219.5 | COMPLETED | 1 | 2020-01-22 | 2019-12-26 | 08-2018-03 | 08-2018-03 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115879 | Liningwan Central School | SIBUNAG | 0 | 1 | UPGRADING | Batch 3 | 2448519.96 | 1949021.89 | COMPLETED | 1 | 2020-06-20 | 2020-11-25 | 04-2019-05 | 04-2019-05 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302479 | CAMANGAHAN NATIONAL HIGH SCHOOL | GUIMBAL | 1 | 1 | UPGRADING | Batch 3 | 2448519.96 | 3232266.98 | COMPLETED | 1 | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L8 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302506 | Guimbal NHS | GUIMBAL | 1 | 1 | UPGRADING |  | 4499246.18 | 2916481.83 | COMPLETED | 1 | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L8 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302467 | Botong-Cabanbanan NHS | OTON | 1 | 1 | UPGRADING | Batch 3 | 2406308.91 | 4135434.57 | COMPLETED | 1 | 2020-10-12 | 2020-10-10 | R06-022-ELECBEFF2019-B2-L2 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302542 | Oton National High School | OTON | 1 | 1 | UPGRADING |  | 5412015.58 | 2128834.42 | COMPLETED | 1 | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L3 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302566 | SAN JOAQUIN SCHOOL OF FISHERIES | SAN JOAQUIN | 1 | 1 | UPGRADING | Batch 3 | 3248155.19 | 2790710.35 | COMPLETED | 1 | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L5 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 311024 | Bagacay National High School | TIGBAUAN | 1 | 1 | UPGRADING | Batch 3 | 2480178.25 | 4369081.69 | COMPLETED | 1 | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L13 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302578 | Tigbauan NHS | TIGBAUAN | 1 | 1 | UPGRADING |  | 5323135.66 | 5366544.79 | COMPLETED | 1 | 2019-12-25 | 2019-12-17 | R06-022-ELECBEFF2019-B1-L14 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302583 | Tubungan NHS | TUBUNGAN | 1 | 1 | UPGRADING |  | 2935850.21 | 4867582.78 | COMPLETED | 1 | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L9 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302446 | Alimodian NCHS | ALIMODIAN | 2 | 1 | UPGRADING | Batch 3 | 5467471.36 | 3299648.81 | COMPLETED | 1 | 2019-12-25 | 2019-12-17 | R06-022-ELECBEFF2019-B1-L11 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 311017 | Bancal NHS | ALIMODIAN | 2 | 1 | UPGRADING | Batch 3 | 2893639.15 | 2198099.21 | COMPLETED | 1 | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L5 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302520 | Leganes National High School | LEGANES | 2 | 1 | UPGRADING |  | 4993078 | 4952016.94 | COMPLETED | 1 | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L7 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302522 | Leon National High School | LEON | 2 | 1 | UPGRADING |  | 3300919.01 | 5284471.01 | COMPLETED | 1 | 2019-12-25 | 2019-12-17 | R06-022-ELECBEFF2019-B1-L11 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302539 | New Lucena National Comprehensive High School | NEW LUCENA | 2 | 1 | UPGRADING |  | 3438750.58 | 3174000 | COMPLETED | 1 | 2020-12-13 | 2020-12-03 | R06-022-ELECBEFF2019-B1-L10 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-11-12 | 2019-12-17 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302540 | New Lucena National High School | NEW LUCENA | 2 | 1 | UPGRADING | Batch 3 | 3470408.87 | 3278671.11 | COMPLETED | 1 | 2019-12-25 | 2019-12-16 | R06-022-ELECBEFF2019-B1-L15 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-08 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302550 | Pavia National High School | PAVIA | 2 | 1 | UPGRADING |  | 5478024.13 | 3751760.78 | COMPLETED | 1 | 2019-12-25 | 2019-12-17 | R06-022-ELECBEFF2019-B1-L14 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302516 | Leonora S. Salapantan NHS | SAN MIGUEL | 2 | 1 | UPGRADING |  | 4704901.05 | 5683741.07 | COMPLETED | 1 | Deceber 19, 2019 | 2019-12-19 | R06-022-ELECBEFF2019-B1-L12 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-08 | 2019-08-23 | Culasi General Merchandising and Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302452 | Badiangan NHS | BADIANGAN | 3 | 1 | UPGRADING | Batch 3 | 3788609.81 | 3536380.54 | COMPLETED | 1 | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L13 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302465 | Bingawan NHS | BINGAWAN | 3 | 1 | UPGRADING |  | 3322024.54 | 2879319.26 | COMPLETED | 1 | 2020-11-05 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L6 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302447 | Ambrosio Maido MNHS | CABATUAN | 3 | 1 | UPGRADING | Batch 3 | 2985014.84 | 2218314.71 | COMPLETED | 1 | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L13 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302473 | Cabatuan NCHS | CABATUAN | 3 | 1 | UPGRADING |  | 5456918.6 | 5704794.05 | COMPLETED | 1 | 2019-12-25 | 2019-12-16 | R06-022-ELECBEFF2019-B1-L15 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-08 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302477 | Calinog NCHS | CALINOG | 3 | 1 | UPGRADING |  | 5320306.79 | 1847005.4 | COMPLETED | 1 | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L1 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302512 | Janiuay NCHS | JANIUAY | 3 | 1 | UPGRADING |  | 5541340.71 | 4468748.95 | COMPLETED | 1 | 2019-12-25 | 2019-12-19 | R06-022-ELECBEFF2019-B1-L1 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302517 | Lambunao National High School | LAMBUNAO | 3 | 1 | UPGRADING | Batch 3 | 3375434 | 5480179.03 | COMPLETED | 1 | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L9 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302524 | Maasin National Comprehensive High School | MAASIN | 3 | 1 | UPGRADING |  | 5509682.42 | 2484986 | COMPLETED | 1 | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L5 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302533 | Mina NHS | MINA | 3 | 1 | UPGRADING |  | 5530787.95 | 4503439.73 | COMPLETED | 1 | 2019-12-25 | 2019-12-16 | R06-022-ELECBEFF2019-B1-L6 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-08 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302457 | Barotac Nuevo National Comprehensive High School | BAROTAC NUEVO | 4 | 1 | UPGRADING |  | 4760009.49 | 2722913.85 | COMPLETED | 1 | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L511 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302497 | Duenas General Comprehensive High School | DUEÑAS | 4 | 1 | UPGRADING |  | 5736096.31 | 7940700 | COMPLETED | 1 | Deceber 24, 2019 | 2020-03-20 | R06-022-ELECBEFF2019-B1-L5 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-05 | 2019-08-19 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302498 | Dumangas NHS | DUMANGAS | 4 | 1 | UPGRADING |  | 3858601.45 | 5454516.02 | COMPLETED | 1 | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L8 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 311006 | P.D. Monfort National Science HS | DUMANGAS | 4 | 1 | UPGRADING | Batch 3 | 3858120.05 | 5488131.64 | COMPLETED | 1 | 2019-12-25 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L10 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302543 | Pagdugue National High School | DUMANGAS | 4 | 1 | UPGRADING |  | 2416861.67 | 2552677.34 | COMPLETED | 1 | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L4 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302564 | San Enrique NCHS | SAN ENRIQUE | 4 | 1 | UPGRADING | Batch 3 | 3279813.48 | 3092961.51 | COMPLETED | 1 | 2019-12-25 | 2019-12-16 | R06-022-ELECBEFF2019-B1-L6 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-08 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302486 | Culasi NHS | AJUY | 5 | 1 | UPGRADING | Batch 3 | 3257469.23 | 1814718.49 | COMPLETED | 1 | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L1 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302552 | Pili NHS | AJUY | 5 | 1 | UPGRADING | Batch 3 | 2942803.79 | 5018420.62 | COMPLETED | 1 | 2020-01-01 | 2020-03-01 | R06-022-ELECBEFF2019-B1-L2 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-23 | 2019-09-11 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302460 | Batad National High School | BATAD | 5 | 1 | UPGRADING |  | 5404154.78 | 4971473.03 | COMPLETED | 1 | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L4 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 311001 | Valerio P. Palmares NHS | BATAD | 5 | 1 | UPGRADING | Batch 3 | 4919628.81 | 3545169.62 | COMPLETED | 1 | 2020-03-25 | 2020-09-12 | R06-022-ELECBEFF2019-B2-L512 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-12 | 2019-11-19 | Anjush Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302482 | Cawayan NHS | CARLES | 5 | 1 | UPGRADING | Batch 3 | 3195391.37 | 5481530.74 | COMPLETED | 1 | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L513 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302494 | Don Casimero Andrada NHS | CARLES | 5 | 1 | UPGRADING |  | 3321680.24 | 2448015.06 | COMPLETED | 1 | 2020-11-05 | 2020-09-28 | R06-022-ELECBEFF2019-B2-L7 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302484 | Roberto H. Tirol High School | CONCEPCION | 5 | 1 | UPGRADING |  | 3778057.05 | 2452880.48 | COMPLETED | 1 | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L1 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5 | 1 | UPGRADING |  | 5757201.84 | 3284414.42 | COMPLETED | 1 | Deceber 24, 2019 | 2020-03-20 | R06-022-ELECBEFF2019-B1-L5 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-05 | 2019-08-19 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302521 | Lemery National High School | LEMERY | 5 | 1 | UPGRADING | Batch 3 | 3701324.06 | 1863148.86 | COMPLETED | 1 | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L1 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302493 | Carlos Lopez NHS | SAN DIONISIO | 5 | 1 | UPGRADING | Batch 3 | 3597861.45 | 5273446.66 | COMPLETED | 1 | 2019-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L3 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-08 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302541 | Nicomedes R. Tubar Sr. NHS | SAN DIONISIO | 5 | 1 | UPGRADING | Batch 3 | 5520235.18 | 2921170.95 | COMPLETED | 1 | 2019-12-25 | 2019-12-19 | R06-022-ELECBEFF2019-B1-L1 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo City | 117580 | Arevalo ES | ILOILO CITY (Capital) | 0 | 1 | UPGRADING |  | 1838904.81 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo City | 117605 | Graciano Lopez Jaena ES | ILOILO CITY (Capital) | 0 | 1 | UPGRADING | Batch 3 | 2039709.09 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo City | 117621 | I. Arroyo ES | ILOILO CITY (Capital) | 0 | 1 | UPGRADING |  | 1372197.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo City | 117617 | Mandurriao Elementary School | ILOILO CITY (Capital) | 0 | 1 | UPGRADING |  | 1890587.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117832 | Basak ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 628605.53 | 550460.45 | COMPLETED | 1 | [9 empty] | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117835 | Camingawan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 262470.43 | 260100 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117879 | Candiacap ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 407822.33 | 331508.3 | COMPLETED | 1 | [9 empty] | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117882 | Dr. Pablo Torre PS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 446008.26 | 370031.25 | COMPLETED | 1 | [9 empty] | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 302794 | Inapoy NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 289754.27 | 287300 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117861 | Kabanyohan Elementary School | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 256850.37 | 253800 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 302795 | Locotan NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 365146.42 | 362300 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117843 | Lorenzo Zayco ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 760560.62 | 665681.84 | COMPLETED | 1 | [9 empty] | PAR Builders,Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117846 | NOAC ELEMENTARY SCHOOL | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 329604.62 | 237776.08 | COMPLETED | 1 | [9 empty] | PAR Builders,Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117889 | Nursery PS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 405171.76 | 311542.08 | COMPLETED | 1 | [9 empty] | PAR Builders,Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117847 | Oringao ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 346562.59 | 343800 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117869 | Tabugon ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 878730.89 | 872600 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117852 | Tagukon ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 412868.5 | 409800 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117871 | Tampalon ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 728041.35 | 722700 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117853 | Tan-awan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 427403.76 | 424200 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Negros Occidental | 343897 | SHS in Calatrava | CALATRAVA | 1 | 1 | UPGRADING | Batch 1 | 2150211.82 | 1731414 | COMPLETED | 1 | 2020-01-31 | [6 empty] | 2019-08-02 | 2019-09-23 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Negros Occidental | 302693 | Toboso NHS | TOBOSO | 2 | 1 | UPGRADING | Batch 1 | 1780753.92 | 2370390.96 | COMPLETED | 1 | 2020-01-31 | [6 empty] | 2019-08-02 | 2019-09-23 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Negros Occidental | 302656 | La Castellana NHS | LA CASTELLANA | 5 | 1 | UPGRADING | Batch 1 | 1708168.21 | 1697812.15 | COMPLETED | 1 | 2019-12-27 | [6 empty] | 2019-08-19 | 2019-08-19 | TMTC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Negros Occidental | 302606 | Caningay NHS | CANDONI | 6 | 1 | UPGRADING | Batch 1 | 2535306.24 | 1432540 | COMPLETED | 1 | 2020-01-31 | [6 empty] | 2019-08-02 | 2019-09-23 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Passi City | 302803 | Gemumua-Agahon National High School | CITY OF PASSI | 4 | 1 | UPGRADING | Batch 3 | 2942803.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Passi City | 500205 | Man-it Integrated School | CITY OF PASSI | 4 | 1 | UPGRADING | Batch 3 | 2942803.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Passi City | 302804 | Mulapula National High School | CITY OF PASSI | 4 | 1 | UPGRADING | Batch 1 | 2942803.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Passi City | 117908 | Passi I Central School | CITY OF PASSI | 4 | 1 | UPGRADING | Batch 3 | 3195391.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Passi City | 302805 | Passi National High School | CITY OF PASSI | 4 | 1 | UPGRADING | Batch 1 | 5456918.6 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Passi City | 302807 | Salngan National High School | CITY OF PASSI | 4 | 1 | UPGRADING | Batch 1 | 3195391.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117690 | Alfredo E. Marañon Sr. ES | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 785518.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117724 | Bato Central Elementary School | SAGAY CITY | 2 | 1 | UPGRADING |  | 1436339.2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117693 | Bulanon Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 596388.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 500037 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117716 | Gil Lopez Elementary School | SAGAY CITY | 2 | 1 | UPGRADING |  | 1436339.2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117696 | Jose B. Puey Sr. Elementary School | SAGAY CITY | 2 | 1 | UPGRADING |  | 2632677.65 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117733 | Lopez Jaena Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 826799.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117721 | Maria Lopez Elementary School | SAGAY CITY | 2 | 1 | UPGRADING |  | 2121705.88 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117700 | Old Sagay Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 2436633.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117704 | Raymundo Tupas Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 823050.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 343922 | Sagay City Senior High School (Stand Alone) | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 302767 | Sagay National High School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 311801 | Sagay National High School - Old Sagay Ext. | SAGAY CITY | 2 | 1 | UPGRADING |  | 864251.93 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117709 | Vito Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 767526.91 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Silay City | 117811 | Bongol ES | SILAY CITY | 3 | 1 | UPGRADING |  | 229262.85 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Silay City | 117801 | Don Eustaquio Hofilena Mem.Elem. School | SILAY CITY | 3 | 1 | UPGRADING | Batch 3 | 1105925.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Silay City | 117813 | Don Homero H. Tanpinco ES | SILAY CITY | 3 | 1 | UPGRADING | Batch 3 | 1295636.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Silay City | 117807 | Gov. Emilio Gaston Memorial ES | SILAY CITY | 3 | 1 | UPGRADING |  | 1653365.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Silay City | 117817 | Mambag-id ES | SILAY CITY | 3 | 1 | UPGRADING |  | 404044.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VI | Silay City | 500198 | Silay SPED Center | SILAY CITY | 3 | 1 | UPGRADING |  | 663530.47 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302287 | Justicia Morales-Young National High School | ALTAVAS | 0 | 1 | UPGRADING |  | 2225930.09 | 2222722.79 | COMPLETED | 1 | 2021-01-20 | 2020-11-23 | ELEC2020-RVI-AKLAN-015 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 310601 | LUPO NATIONAL HIGH SCHOOL | ALTAVAS | 0 | 1 | UPGRADING |  | 1799319.29 | 1799035.72 | COMPLETED | 1 | 2021-01-20 | 2020-11-23 | ELEC2020-RVI-AKLAN-020 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302307 | Father Julian C. Rago Memorial NHS | BALETE | 0 | 1 | UPGRADING |  | 2153200.79 | 2150859.95 | COMPLETED | 1 | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-042 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114670 | Mangga Primary School | BANGA | 0 | 1 | SOLAR PANEL |  | 899472.82 | 898607.75 | COMPLETED | 1 | 2021-01-20 | 2021-11-10 | ELEC2020-RVI-AKLAN-047 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114711 | Tag-osip Elementary School | BURUANGA | 0 | 1 | SOLAR PANEL |  | 920472.82 | 917972.82 | COMPLETED | 1 | 2021-01-20 | 2021-04-26 | ELEC2020-RVI-AKLAN-046 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114722 | Malindog PS | IBAJAY | 0 | 1 | SOLAR PANEL |  | 600993.23 | 599356.54 | COMPLETED | 1 | 2021-01-20 | 2021-12-01 | ELEC2020-RVI-AKLAN-060 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-20 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302320 | Maloco NHS | IBAJAY | 0 | 1 | UPGRADING |  | 2082046.49 | 2080046.49 | COMPLETED | 1 | 2021-01-20 | 2021-05-03 | ELEC2020-RVI-AKLAN-033 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114735 | Mina-a ES | IBAJAY | 0 | 1 | SOLAR PANEL |  | 930972.82 | 929500.43 | COMPLETED | 1 | 2021-01-20 | 2021-12-01 | ELEC2020-RVI-AKLAN-049 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-20 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302324 | Aklan NHS for Arts & Trades | KALIBO (Capital) | 0 | 1 | UPGRADING |  | 1454991.76 | 1452460.32 | COMPLETED | 1 | 2021-01-20 | 2021-05-25 | ELEC2020-RVI-AKLAN-010 |  | 2019-11-20 | 2019-12-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302323 | Gaudencio L. Vega NHS (Nalook NHS) | KALIBO (Capital) | 0 | 1 | UPGRADING |  | 1944227.69 | 1942149.56 | COMPLETED | 1 | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-011 |  | 2019-11-20 | 2019-12-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114770 | Agbatuan PS | LIBACAO | 0 | 1 | SOLAR PANEL |  | 1019823.4 | 1018131.51 | COMPLETED | 1 | 2021-01-20 | 2021-11-25 | ELEC2020-RVI-AKLAN-051 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 310617 | Alfonso XII NHS | LIBACAO | 0 | 1 |  |  | 1927485.357 | 1828000 | COMPLETED | 1 | 2021-11-17 |  | ELEC2020-RVI-AKLAN-008 |  | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-08-12 | Rism Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114789 | Manika ES | LIBACAO | 0 | 1 | SOLAR PANEL |  | 1275359.67 | 1274184.19 | COMPLETED | 1 | 2021-01-20 | 2021-11-25 | ELEC2020-RVI-AKLAN-048 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 500174 | Ortega Integrated School | LIBACAO | 0 | 1 | UPGRADING |  | 1898395.19 | 1897093.12 | COMPLETED | 1 | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-030 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 500641 | Ma. Cristina IS | MADALAG | 0 | 1 | SOLAR PANEL |  | 1243859.67 | 1243734.19 | COMPLETED | 1 | 2021-01-20 | 2021-11-11 | ELEC2020-RVI-AKLAN-059 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302298 | Dr. Ramon B. Legaspi, Sr. National High School | MAKATO | 0 | 1 | UPGRADING |  | 1959131.39 | 1956094.61 | COMPLETED | 1 | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-014 |  | 2019-11-20 | 2019-12-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114846 | Balabag ES | MALAY | 0 | 1 | UPGRADING |  | 1856395.19 | 1855104.93 | COMPLETED | 1 | 2021-01-20 | 2021-01-21 | ELEC2020-RVI-AKLAN-006 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114851 | Manocmanoc ES | MALAY | 0 | 1 | UPGRADING |  | 1785240.89 | 1781167.55 | COMPLETED | 1 | 2021-01-20 | 2021-01-21 | ELEC2020-RVI-AKLAN-007 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 500175 | Kinalangay Viejo IS | MALINAO | 0 | 1 | UPGRADING |  | 2149935.29 | 2148277.79 | COMPLETED | 1 | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-018 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302312 | Lilo-an National High School | MALINAO | 0 | 1 | UPGRADING |  | 1736535.59 | 1734618.22 | COMPLETED | 1 | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-019 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114869 | Osman Elementary School | MALINAO | 0 | 1 | SOLAR PANEL |  | 920472.82 | 919945.43 | COMPLETED | 1 | 2021-01-20 | 2021-11-11 | ELEC2020-RVI-AKLAN-044 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | SOLAR | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302334 | Rosario National High School | MALINAO | 0 | 1 | UPGRADING |  | 1784272.79 | 1783548.22 | COMPLETED | 1 | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-023 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302335 | Solido National High School | NABAS | 0 | 1 | UPGRADING |  | 2082046.49 | 2076911.03 | COMPLETED | 1 | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-031 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302339 | Unidos NHS | NABAS | 0 | 1 | UPGRADING |  | 1489848.59 | 1488973.71 | COMPLETED | 1 | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-032 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 114957 | Bahoyan-Yapo ES | BARBAZA | 0 | 1 | UPGRADING |  | 1311509.98 | 1217440.1 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-007 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 114965 | Ipil-Jinalinan ES | BARBAZA | 0 | 1 | UPGRADING |  | 1457460.09 | 1619558.3 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-009 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 114983 | Bagtason ES | BUGASONG | 0 | 1 | UPGRADING |  | 1311509.98 | 1216823.95 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-014 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 114986 | Camangahan ES | BUGASONG | 0 | 1 | UPGRADING |  | 1311509.98 | 1230145.88 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-015 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 114995 | Pangalcagan ES | BUGASONG | 0 | 1 | UPGRADING |  | 1337759.98 | 1251601.86 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-019 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115002 | Zaragoza Elementary School | BUGASONG | 0 | 1 | UPGRADING |  | 1457460.09 | 1372624.8 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-021 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115007 | Caluya Central School | CALUYA | 0 | 1 | UPGRADING |  | 1646460.09 | 1598426.76 | COMPLETED | 1 | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-022 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 302350 | Caluya NHS | CALUYA | 0 | 1 | UPGRADING |  | 1884833.19 | 1822166.08 | COMPLETED | 1 | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-110 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115019 | Semirara Elementary School | CALUYA | 0 | 1 | UPGRADING |  | 1646460.09 | 1598776.75 | COMPLETED | 1 | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-027 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 310705 | Semirara NHS | CALUYA | 0 | 1 | UPGRADING |  | 1884833.19 | 1825505.96 | COMPLETED | 1 | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-112 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115025 | Tinogboc ES | CALUYA | 0 | 1 | UPGRADING |  | 1646460.09 | 1598776.75 | COMPLETED | 1 | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-028 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 302382 | Tinogboc NHS | CALUYA | 0 | 1 | UPGRADING |  | 1865933.19 | 1808248.27 | COMPLETED | 1 | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-111 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115026 | Villarises ES | CALUYA | 0 | 1 | UPGRADING |  | 1646460.09 | 1591929.5 | COMPLETED | 1 | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-029 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115036 | Camancijan ES | CULASI | 0 | 1 | UPGRADING |  | 1311509.98 | 1316920.74 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-031 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115053 | San Juan ES | CULASI | 0 | 1 | UPGRADING |  | 1235384.9193 | 1160151.52 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | ELEC 2020-RVI-Antique-034 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115086 | Fabrica ES | HAMTIC | 0 | 1 | UPGRADING |  | 1310428.48 | 1308726.01 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-042 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115087 | Guintas ES | HAMTIC | 0 | 1 | UPGRADING |  | 1389211.51 | 1388009.23 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-043 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115075 | Malandog ES | HAMTIC | 0 | 1 | UPGRADING |  | 1304974.78 | 1302758.68 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-040 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115093 | Mapatag ES | HAMTIC | 0 | 1 | UPGRADING |  | 1236469.36 | 1235954.53 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-047 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115105 | Guinbanga-an ES | LAUA-AN | 0 | 1 | UPGRADING |  | 1331663.68 | 1253331.14 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | ELEC2020-RVI-Antique-050 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115136 | San Roque ES | LIBERTAD | 0 | 1 | UPGRADING |  | 1312628.86 | 1259349.44 | COMPLETED | 1 | 2021-01-30 | 2021-12-31 | ELEC2020-RVI-Antique-057 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115152 | Guia Elementary School | PANDAN | 0 | 1 | UPGRADING |  | 1350547.93 | 1331069.9 | COMPLETED | 1 | 2021-01-30 | 2021-12-31 | ELEC2020-RVI-Antique-061 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115176 | Aureliana ES | PATNONGON | 0 | 1 | UPGRADING |  | 1309873.03 | 1617392.77 | COMPLETED | 1 | 2021-01-30 | 2021-12-31 | ELEC2020-RVI-Antique-062 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115244 | La Union ES | SAN REMIGIO | 0 | 1 | UPGRADING |  | 1337759.98 | 1338505.6 | COMPLETED | 1 | 2021-01-30 | 2021-12-31 | ELEC2020-RVI-Antique-063 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115272 | Sinondolan ES | SAN REMIGIO | 0 | 1 | UPGRADING |  | 1343009.98 | 1404637.91 | COMPLETED | 1 | 2021-01-30 | 2021-12-31 | ELEC2020-RVI-Antique-064 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115280 | Bacalan ES | SEBASTE | 0 | 1 | UPGRADING |  | 1319809.6 | 1231875.16 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | ELEC2020-RVI-Antique-067 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115282 | Idio ES | SEBASTE | 0 | 1 | UPGRADING |  | 1310494.42 | 1231342.93 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-071 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115307 | Sido-San Juan ES | SIBALOM | 0 | 1 | UPGRADING |  | 1311509.98 | 1316593.48 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-075 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115348 | San Francisco Norte ES | TIBIAO | 0 | 1 | UPGRADING |  | 1311509.98 | 1231342.93 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-076 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115350 | Sta. Justa ES | TIBIAO | 0 | 1 | UPGRADING |  | 1457460.09 | 1336577.08 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | Elec2020-RVI-ANTIQUE-078 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115354 | Tuno Elementary School | TIBIAO | 0 | 1 | UPGRADING |  | 1311509.98 | 1314659.17 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-079 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115355 | Abaca ES | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING |  | 1311509.98 | 1245177.73 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-080 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115359 | Barasanan ES | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING |  | 1457460.09 | 1234417.33 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-081 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115364 | Dao Central School | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING |  | 1457460.09 | 1341188.68 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | Elec2020-RVI-ANTIQUE-082 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115393 | Buluangan I ES | VALDERRAMA | 0 | 1 | UPGRADING |  | 1311509.98 | 1316920.74 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | ELEC2020-RVI-Antique-084 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115151 | Fragante ES | PANDAN | 1 | 1 | UPGRADING |  | 1307767.57 | 1511958.48 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | ELEC2020-RVI-Antique-085 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115153 | Idiacacan ES | PANDAN | 1 | 1 | UPGRADING |  | 1325739.58 | 1239176.59 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | ELEC2020-RVI-Antique-086 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115157 | Mag-aba ES | PANDAN | 1 | 1 | UPGRADING |  | 1307566.22 | 1235333.74 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | ELEC2020-RVI-Antique-087 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115214 | Loreto-Joaquin Delgado ES (Badiang ES) | SAN JOSE (Capital) | 1 | 1 | UPGRADING |  | 1233084.75 | 1310444.68 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | Elec2020-RVI-ANTIQUE-090 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115235 | Barangbang ES | SAN REMIGIO | 1 | 1 | UPGRADING |  | 1318150.85 | 1730043.63 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-094 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115237 | Cadolonan ES | SAN REMIGIO | 1 | 1 | UPGRADING |  | 1232610.82 | 1461668.23 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-095 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115245 | Magdalena ES | SAN REMIGIO | 1 | 1 | UPGRADING |  | 1316729.3 | 1231875.16 | COMPLETED | 1 | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-097 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 11.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115246 | Maragubdub ES | SAN REMIGIO | 1 | 1 | UPGRADING |  | 1245845.54 | 1310444.68 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | Elec2020-RVI-ANTIQUE-098 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115271 | San Rafael ES | SAN REMIGIO | 1 | 1 | UPGRADING |  | 1235911.39 | 1456350.58 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | Elec2020-RVI-ANTIQUE-099 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115279 | Aras-asan ES | SEBASTE | 1 | 1 | UPGRADING |  | 1309235.12 | 1456350.58 | COMPLETED | 1 | 2021-02-27 | 2021-12-24 | Elec2020-RVI-ANTIQUE-100 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115281 | Callan ES | SEBASTE | 1 | 1 | UPGRADING |  | 1231205.96 | 1311510 | COMPLETED | 1 | 2021-07-22 | 2021-08-06 | Elec2020-RVI-ANTIQUE-105 | [6 empty] | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115611 | Agbalo ES | PANAY | 1 | 1 |  |  | 1118912.76 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 501089 | Bago Chiquito Integrated School | PANAY | 1 | 1 |  |  | 1210573.56 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115623 | Calapawan ES | PANAY | 1 | 1 |  |  | 1210573.56 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115636 | Panay CS | PANAY | 1 | 1 |  |  | 1485555.96 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115637 | Pawa ES | PANAY | 1 | 1 |  |  | 1000040.16 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115624 | Ricardo Bernas ES (calitan) | PANAY | 1 | 1 |  |  | 1027251.96 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115638 | Tanza Norte ES | PANAY | 1 | 1 |  |  | 1302234.36 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115644 | Ambilay Elem. Sch. | PANITAN | 1 | 1 |  |  | 1091700.96 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115645 | Bahit Elem. Sch. | PANITAN | 1 | 1 |  |  | 1210573.56 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115652 | Cogon Elem. Sch. | PANITAN | 1 | 1 |  |  | 1210573.56 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115653 | Conciencia Elem. Sch. | PANITAN | 1 | 1 |  |  | 1118912.76 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115656 | Jesus Gonzalo Albana ES | PANITAN | 1 | 1 |  |  | 1043709.24 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-016 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115657 | Maluboglubog Elem. Sch. | PANITAN | 1 | 1 |  |  | 1210573.56 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-018 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115658 | Panit-an Elem. Sch. | PANITAN | 1 | 1 |  |  | 1550004.96 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-025 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115499 | Agustin P. Navarra Elemenatary School | IVISAN | 2 | 1 |  |  | 1302234.36 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-037 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115502 | BASIAO ELEMENTARY SCHOOL | IVISAN | 2 | 1 |  |  | 1275022.56 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-038 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115503 | Cabugao ES (ivisan) | IVISAN | 2 | 1 |  |  | 1393895.16 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-039 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115505 | Catalino Andrada MS | IVISAN | 2 | 1 |  |  | 1421106.96 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-040 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115504 | Cudian ES | IVISAN | 2 | 1 |  |  | 1413945.96 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-045 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115507 | Ivisan ES | IVISAN | 2 | 1 |  |  | 1760538.36 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-046 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115506 | Juan S. Jarencio MS | IVISAN | 2 | 1 |  |  | 1091700.96 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-047 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115509 | Mahayag Elementary School | IVISAN | 2 | 1 |  |  | 1366683.36 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-051 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115510 | Malocloc ES | IVISAN | 2 | 1 |  |  | 1275022.56 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-053 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115511 | Panfilo Mendoza ES | IVISAN | 2 | 1 |  |  | 1550004.96 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-054 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115508 | Victor A. Umiten Elementary School | IVISAN | 2 | 1 |  |  | 1570055.76 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-042 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 501088 | Antonio Belo ES | PANITAN | 2 | 1 |  |  | 1485555.96 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-057 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115650 | Capagao ES | PANITAN | 2 | 1 |  |  | 1118912.76 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-CAPIZ-058 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Guimaras | 302432 | Jordan NHS | JORDAN (Capital) | 0 | 1 |  |  | 8683062.82 |  | COMPLETED | 1 | 2021-02-19 | 2021-02-19 | Elec2020-RVI-Guimaras-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | 0 | 1 |  |  | 8452649.92 |  | COMPLETED | 1 | 2021-02-19 | 2021-02-19 | Elec2020-RVI-Guimaras-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Guimaras | 302428 | Cabalagnan National High School | NUEVA VALENCIA | 0 | 1 |  |  | 6601348.58 |  | COMPLETED | 1 | 2021-02-19 | 2021-02-19 | Elec2020-RVI-Guimaras-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Guimaras | 302435 | Calaya National High School | NUEVA VALENCIA | 0 | 1 |  |  | 8222237.02 |  | COMPLETED | 1 | 2021-12-12 | 2021-12-12 | Elec2020-RVI-Guimaras-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Guimaras | 302436 | Salvacion National High School | NUEVA VALENCIA | 0 | 1 |  |  | 5193167.94 |  | COMPLETED | 1 | 2021-02-19 | 2021-02-19 | Elec2020-RVI-Guimaras-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Guimaras | 302433 | Simeon J. Jabasa National High School | NUEVA VALENCIA | 0 | 1 |  |  | 7070172.53 |  | COMPLETED | 1 | 2021-02-19 | 2021-02-19 | Elec2020-RVI-Guimaras-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302509 | Iloilo NHS | ILOILO CITY (Capital) | 0 | 1 |  |  | 21603497.96 | 5081769.4 | COMPLETED | 1 | 2021-12-02 | 2021-01-13 | ELEC2020-RVI-ILOILO-032 | ELEC2020-RVI-ILOILO-032 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-15 | NOE'S BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302495 | Don Felix Serra NHS | SAN JOAQUIN | 1 | 1 |  |  | 9086311.69 | 4660059.52 | COMPLETED | 1 | 2021-02-02 | 2021-01-12 | ELEC2020-RVI-ILOILO-005 | ELEC2020-RVI-ILOILO-005 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-05 | MJ Barcelona Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302459 | Barroc NHS | TIGBAUAN | 1 | 1 |  |  | 6124419.12 | 21538687.47 | COMPLETED | 1 | 2021-10-02 | 2021-02-16 | ELEC2020-RVI-ILOILO-019 | ELEC2020-RVI-ILOILO-019 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-13 | MICRO ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302487 | Daga-Barasan NHS | SANTA BARBARA | 2 | 1 |  |  | 4217214.52 | 8683035.31 | COMPLETED | 1 | 13/02/2021 | 2021-01-15 | ELEC2020-RVI-ILOILO-026 | ELEC2020-RVI-ILOILO-026 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-16 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302580 | Tina National High School | BADIANGAN | 3 | 1 |  |  | 4843463.92 | 13734009.49 | COMPLETED | 1 | 13/02/2021 | 2021-01-07 | ELEC2020-RVI-ILOILO-028 | ELEC2020-RVI-ILOILO-028 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-16 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302546 | PALANGUIA NATIONAL HIGH SCHOOL | POTOTAN | 3 | 1 |  |  | 6903244.43 | 4972203.86 | COMPLETED | 1 | 2021-09-02 | 2021-02-04 | ELEC2020-RVI-ILOILO-016 | ELEC2020-RVI-ILOILO-016 | 2019-12-21 | 2019-12-27 | 2020-01-10 | Septmber 25, 2020 | 2020-10-12 | NOE'S BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302563 | San Enrique Manuel Paluay, Sr. MHS | SAN ENRIQUE | 4 | 1 |  |  | 5111080.79 | 8996000 | COMPLETED | 1 | 2021-02-02 | 2021-01-12 | ELEC2020-RVI-ILOILO-033 | ELEC2020-RVI-ILOILO-033 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-05 | RISM BULDERS & CONSTRUCTION SERVICES INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302454 | Balasan NHS | BALASAN | 5 | 1 |  |  | 13773244.05 | 4757857.58 | COMPLETED | 1 | 16/02/2021 | 2020-02-16 | ELEC2020-RVI-ILOILO-014 | ELEC2020-RVI-ILOILO-014 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-19 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302569 | San Rafael NHS (San Rafael) | SAN RAFAEL | 5 | 1 |  |  | 8745250.93 | 3693373.72 | COMPLETED | 1 | 28/10/2021 | 2021-10-26 | ELEC2020-RVI-ILOILO-024 | ELEC2020-RVI-ILOILO-024 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2021-06-07 | 2021-06-30 | HF Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302525 | Malapaya NHS | SARA | 5 | 1 |  |  | 5776411.41 | 3574085.65 | COMPLETED | 1 | 13/02/2021 | 2021-06-07 | ELEC2020-RVI-ILOILO-006 | ELEC2020-RVI-ILOILO-006 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-16 | CULASI GENERAL MERCHANDISING AND CONSTRUCTION SERICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo City | 117619 | Baluarte ES | ILOILO CITY (Capital) | 0 | 1 |  |  | 10933410.95 |  | COMPLETED | 1 |  |  | Elec2020-RVI-ILOILOCITY-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo City | 117606 | La Paz ES I | ILOILO CITY (Capital) | 0 | 1 |  |  | 8740315.64 |  | COMPLETED | 1 |  |  | Elec2020-RVI-ILOILOCITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo City | 117607 | La Paz ES II | ILOILO CITY (Capital) | 0 | 1 |  |  | 6327540.57 |  | COMPLETED | 1 |  |  | Elec2020-RVI-ILOILOCITY-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo City | 302749 | Mandurriao NHS | ILOILO CITY (Capital) | 0 | 1 |  |  | 7826181.84 |  | COMPLETED | 1 |  |  | Elec2020-RVI-ILOILOCITY-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Kabankalan City | 117829 | Badiangay ES | CITY OF KABANKALAN | 6 | 1 |  |  | 996308.04 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-KABANKALANCITY-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Kabankalan City | 117874 | Bantayan ES | CITY OF KABANKALAN | 6 | 1 |  |  | 2918681.94 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-KABANKALANCITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Kabankalan City | 117856 | Camansi ES | CITY OF KABANKALAN | 6 | 1 |  |  | 1640793.7 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-KABANKALANCITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Kabankalan City | 117849 | Pitgong ES | CITY OF KABANKALAN | 6 | 1 |  |  | 479345.9 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-KABANKALANCITY-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Negros Occidental | 302603 | Calatrava NHS | CALATRAVA | 1 | 1 |  |  | 5349237.01 |  | COMPLETED | 1 |  |  | Elec2020-R6-Negros Occidental-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Negros Occidental | 302624 | ENRIQUETA MONTILLA DE ESTEBAN MEMORIAL HIGH SCHOOL | PULUPANDAN | 4 | 1 |  |  | 6176278.18 | 6140194.07 | COMPLETED | 1 | 2020-12-30 |  | Elec2020-R6-Negros Occidental-006 | 20-09-007 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-17 | 2020-09-21 | JPEG Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Negros Occidental | 302683 | San Enrique NHS | SAN ENRIQUE | 4 | 1 |  |  | 4601842.13 |  | COMPLETED | 1 |  |  | Elec2020-R6-Negros Occidental-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Negros Occidental | 302600 | Bilbao-Uybico NHS | HINOBA-AN (ASIA) | 6 | 1 |  |  | 8670357.39 | 3296807.84 | COMPLETED | 1 | 2020-12-30 |  | Elec2020-R6-Negros Occidental-004 | 20-09-006 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-17 | 2020-09-21 | JPEG Construction and Supply | Energized already on OCT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | ROXAS CITY | 117653 | COGON IS | ROXAS CITY | 1 | 1 |  |  | 1138963.56 | 1081502.38 | COMPLETED | 1 | 2021-04-09 | 2021-04-07 | ELEC2020-RVI-ROXAS CITY-010 | CON-2020-092/1 |  |  | 2020-10-20 | 2020-10-23 | 2020-12-17 | RJZW ELECTRICAL ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | ROXAS CITY | 117668 | DON FRANCISCO DINGLASAN MS | ROXAS CITY | 1 | 1 |  |  | 1193387.16 | 1133810.02 | COMPLETED | 1 | 2021-04-09 | 2021-04-07 | ELEC2020-RVI-ROXAS CITY-008 | CON-2020-092/3 |  |  | 2020-10-22 | 2020-10-25 | 2020-12-17 | RJZW ELECTRICAL ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | ROXAS CITY | 117682 | DONA EMILIANA ALBA MS | ROXAS CITY | 1 | 1 |  |  | 1275022.56 | 1211968.04 | COMPLETED | 1 | 2021-09-19 | 2021-07-15 | ELEC2020-RVI-ROXAS CITY-003 |  | 2021-04-13 | 2021-04-21 | 2021-05-05 |  |  | RJZW ELECTRICAL ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | ROXAS CITY | 117683 | DONA VICENTA P.HONTIVEROS MS | ROXAS CITY | 1 | 1 |  |  | 1302234.36 | 1238425.3 | COMPLETED | 1 | 2021-04-09 | 2021-04-07 | ELEC2020-RVI-ROXAS CITY-001 | CON-2020-092/4 |  |  | 2020-10-23 | 2020-10-26 | 2020-12-17 | RJZW ELECTRICAL ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | ROXAS CITY | 117657 | DUMOLOG ES | ROXAS CITY | 1 | 1 |  |  | 1166175.36 | 1107656.2 | COMPLETED | 1 | 2021-04-09 | 2021-04-07 | ELEC2020-RVI-ROXAS CITY-009 | CON-2020-092/2 |  |  | 2020-10-21 | 2020-10-24 | 2020-12-17 | RJZW ELECTRICAL ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Sagay City | 117691 | Alfredo E. Maranon Sr. ES- School of the Future | Sagay City | 2 | 1 |  |  | 1193711.9 | 893000 | COMPLETED | 1 | September 16, 2021 | August 21, 2021 | ELEC2020-RVI-SAGAYCITY-001 | 43831 | February 25- March 16, 2020 | 2020-03-03 | 2020-03-16 | 2021-05-31 | 2021-07-16 | RISM BUILDERS & CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Sagay City | 117695 | Buenaventura Rodriguez Elem School | Sagay City | 2 | 1 |  |  | 946032.78 | 793222.9845 | COMPLETED | 1 | Decemeber 2, 2020 | Decemeber 2, 2020 | ELEC2020-RVI-SAGAYCITY-002 | 43709 | Novmber 21-December 11, 2019 | 2019-11-29 | 2019-12-12 | 2020-09-11 | 2020-10-06 | RISM BUILDERS & CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Sagay City | 117739 | Rufino T. Halipa Sr. Elem School | Sagay City | 2 | 1 |  |  | 662421.31 | 555335.4289 | COMPLETED | 1 | Decemeber 2, 2020 | Decemeber 2, 2020 | ELEC2020-RVI-SAGAYCITY-003 | 43709 | Novmber 21-December 11, 2019 | 2019-11-29 | 2019-12-12 | 2020-09-11 | 2020-10-06 | RISM BUILDERS & CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Silay City | 302780 | Doña Montserrat Lopez Memorial National High School (JHS) | SILAY CITY | 3 | 1 |  |  | 2028763.71 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-SILAYCITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VI | Silay City | 117804 | Silay South ES | SILAY CITY | 3 | 1 |  |  | 2266185.32 |  | ONGOING | 0.95 |  |  | ELEC2020-RVI-SILAYCITY-001 | [7 empty] | transformer requirements. As per PO, 100kva single phase Max allowed by COOP for a single phase is only 50kva...for VO as end of January | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.95 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2023 | Region VI | Aklan | 500182 | Habana Integrated School | Buruanga | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2863138.92 | 2313786.71 | COMPLETED | 1 | 18-Sept-2023 |  | DEPED-RO6-D1-2023BEFF(ELEC0-20-2023 |  |  | 2023-05-03 | 2023-05-15 |  | 2023-06-28 | AGM SILVER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VI | Aklan | 114706 | Katipunan Elementary School | Buruanga | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2098033.87 | 1544660.91 | COMPLETED | 1 | 18-Sept-2023 |  | DEPED-RO6-D1-2023BEFF(ELEC0-20-2023 |  |  | 2023-05-03 | 2023-05-15 |  | 2023-06-28 | AGM SILVER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VI | Aklan | 114764 | Bugasongan Elementary School | Lezo | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1937047.27 | 1441852.73 | COMPLETED | 1 | 18-Sept-2023 |  | DEPED-RO6-D1-2023BEFF(ELEC0-20-2023 |  |  | 2023-05-03 | 2023-05-15 |  | 2023-06-28 | AGM SILVER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VI | Aklan | 114934 | Tagas Elementary School | Tangalan | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1940940.88 | 1439641.39 | COMPLETED | 1 | 18-Sept-2023 |  | DEPED-RO6-D1-2023BEFF(ELEC0-20-2023 |  |  | 2023-05-03 | 2023-05-15 |  | 2023-06-28 | AGM SILVER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VI | Aklan | 114936 | Tangalan Elementary School | Tangalan | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2299400.96 | 1707060.99 | COMPLETED | 1 | 18-Sept-2023 |  | DEPED-RO6-D1-2023BEFF(ELEC0-20-2023 |  |  | 2023-05-03 | 2023-05-15 |  | 2023-06-28 | AGM SILVER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114974 | Borocboroc-Delima-Ipil ES | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1172908.53 | 950500.95 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114975 | Buenavista ES | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1169478.37 | 945248.85 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114976 | Concepcion ES | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1205748.51 | 982013.55 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114977 | Maradiona Elementary School | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1265643.85 | 1024030.35 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114978 | Mojon ES | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1135093.88 | 929492.55 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114979 | Rombang ES | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1175619.87 | 955753.05 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114980 | Sinaja-Salvacion Elementary School | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1176139.57 | 955753.05 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115127 | Bulanao ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1178608.98 | 897475.43 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115128 | Codiong ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1139519.44 | 867884.33 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115131 | Lindero ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1263237.47 | 961589.48 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115133 | Paz ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1169577.93 | 887611.73 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115134 | Pucio ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1180978.83 | 902407.28 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115137 | Taboc ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1169353.93 | 887611.73 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115138 | Tinigbas ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1106828.79 | 849612.23 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115140 | Union ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1302154.64 | 996597.53 | COMPLETED | 1 | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2024 | Region VI | Aklan | 114786 | Libacao Central ES | LIBACAO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2736068.52 | 1767672.15 | COMPLETED | 1 | 2024-09-26 |  | DEPED-RO6-DI-EPA-2024 BEFF (ELEC)-058-2023 LOT-1 | DEPED-RO6-DI-EPA-2024 BEFF (ELEC)-058-2023 LOT-2 | 2023-11-14 | 2023-11-21 | 2023-12-04 | 2023-12-29 | 2024-05-27 | NEM CONSTRUCTION SUPPLIES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2024 | Region VI | Aklan | 500643 | San Roque Integrated School | MALINAO | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2372783.92 | 1517286.95 | COMPLETED | 1 | 2024-09-27 |  | DEPED-RO6-DI-EPA-2024 BEFF (ELEC)-058-2023 LOT-2 | DEPED-RO6-DI-EPA-2024 BEFF (ELEC)-058-2023 LOT-3 | 2023-11-15 | 2023-11-22 | 2024-12-04 | 2023-12-29 | 2024-05-27 | NEM CONSTRUCTION SUPPLIES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2024 | Region VI | Antique | 115344 | Malabor ES | TIBIAO | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1794268.13 | 1235734.5 | COMPLETED | 1 | 2024-09-29 | 2024-09-02 | R6-D2-GAA2024-09-E | R6-D2-GAA2024-09-E | 2024-01-26 | 2024-02-02 | 2024-02-16 | 2024-04-05 | 2024-07-19 | RANP Construction Supply and Services | Completed as per POW and VO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2024 | Region VI | Bacolod City | 181005 | Handumanan Elementary School II | BACOLOD CITY (Capital) | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2179424.96 |  | Under Procurement | 0 | [10 empty] | no subaro yet; issue with the compliance of local cooperative; fund insufficient | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | Under Procurement
ELECTRIFICATION 2024 | Region VI | Bago City | 117504 | Bago City Elementary School | BAGO CITY | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3809119.24 |  | Under Procurement | 0 | [10 empty] | no subaro yet; CO awaiting submission of RTA from division office to download subaro | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | Under Procurement
ELECTRIFICATION 2024 | Region VI | Cadiz City | 302728 | Caduha-an NHS | CADIZ CITY | 2nd | 1 | Installation of primary Poles and Service Lines with Transformers and Complete Accessories | 1 | 4175702.24 | 4127265.51 | COMPLETED | 1 | 2025-02-20 |  |  |  | 2024-06-27 | 2024-07-05 | 2024-07-24 | 2024-07-31 | 2024-09-16 | PAR BUILDERS ELECTRICAL AND CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VI | Capiz | 115667 | Casanayan ES | PILAR | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2156909.78 | 2150000 | NOT YET started | 0 |  |  | R6-DEPED-CAPIZ-CY2024-BEFF-CASANAYANES-LOT1-(Re-Bid) |  | 2024-10-17 | 2024-10-25 | 2024-11-06 |  |  | RJZW ELECTRICAL ENGINEERING SUPPLY | FOR ISSUANCE OF AWARD AND NTP, SARO Received last February 28, 2025 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region VI | Capiz | 115590 | Ilawod ES (mambusao east) | MAMBUSAO | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2601712.15 | 2595200 | COMPLETED | 1 | 2025-05-03 |  | R6-DEPED-CAPIZ-CY2024-BEFF-ILAWODES-LOT2 | CB No. 2024 - 030 | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-08-19 | 2024-12-27 | RJZW ELECTRICAL ENGINEERING SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.25 | 0.75 |  | 5.25 | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region VI | Escalante City | 117043 | Escalante Central Elementary School | CITY OF ESCALANTE | 1st | 1 | Upgrading of Electrical System | 1 | 3692973.81 | 3508000 | ONGOING | 0.95 | 2025-03-09 |  | Project 02-2024 | Project 02-2024 | 2024-06-29 | 2024-07-08 | 2024-07-19 |  | 2024-10-09 | PAR BUILDERS | Waiting for the Cooperative schedule to energize | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.7 | 0.25 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region VI | Guimaras | 115892 | Calaya Elementary School | NUEVA VALENCIA | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3369617.68 | 3358846.89 | COMPLETED | 1 | 2024-10-22 | 2024-07-17 | No. 07-2023 | No. 07-2023 | 2023-10-16 | 2023-10-24 | 2023-11-06 | 2024-05-13 | 2024-05-20 | AGM Silver Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 7.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2024 | Region VI | Iloilo | 302507 | Igbaras NHS | IGBARAS | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5552051.97 | 3495252.08 | ONGOING | 0.8 | 2025-07-01 |  | BEFF2024-RVI-022-ILOILO-ELEC-L3 | BEFF2024-RVI-022-ILOILO-ELEC-L3 | 2024-07-23 | July 10, 10, 2024 | 2024-07-22 | 2024-08-06 | 2025-03-03 | EARLY RISER CONSTRUCTION | RTA submitted to CO, waiting for sub-aro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.47 | 0.33 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region VI | Iloilo | 302470 | Buga National High School | LEON | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2868850.32 | 2847447.4 | ONGOING | 0.8 | 2025-07-01 |  | BEFF2024-RVI-022-ILOILO-ELEC-L4 | BEFF2024-RVI-022-ILOILO-ELEC-L4 | 2024-07-23 | July 10, 10, 2024 | 2024-07-22 | 2024-08-06 | 2025-03-03 | EARLY RISER CONSTRUCTION | RTA submitted to CO, waiting for sub-aro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.78 | 0.02 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region VI | Iloilo | 302471 | Burak NHS | MAASIN | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3310765.64 | 2083965.51 | ONGOING | 0.75 | 2025-07-01 |  | BEFF2024-RVI-022-ILOILO-ELEC-L1 | BEFF2024-RVI-022-ILOILO-ELEC-L1 | 2024-07-23 | July 10, 10, 2024 | 2024-07-22 | 2024-08-06 | 2025-03-03 | EARLY RISER CONSTRUCTION | RTA submitted to CO, waiting for sub-aro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.64 | 0.11 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region VI | Iloilo | 302449 | Anilao NHS | ANILAO | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4425596.02 | 2778779.59 | ONGOING | 0.95 | 2025-07-01 |  | BEFF2024-RVI-022-ILOILO-ELEC-L5 | BEFF2024-RVI-022-ILOILO-ELEC-L5 | 2024-07-23 | July 10, 10, 2024 | 2024-07-22 | 2024-08-06 | 2025-03-03 | EARLY RISER CONSTRUCTION | RTA submitted to CO, waiting for sub-aro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.84 | 0.11 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region VI | Iloilo | 116349 | Estancia Central Elementary School | ESTANCIA | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4962542.47 | 3124171.36 | ONGOING | 0.9 | 2025-07-01 |  | BEFF2024-RVI-022-ILOILO-ELEC-L2 | BEFF2024-RVI-022-ILOILO-ELEC-L2 | 2024-07-23 | July 10, 10, 2024 | 2024-07-22 | 2024-08-06 | 2025-03-03 | EARLY RISER CONSTRUCTION | RTA submitted to CO, waiting for sub-aro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.63 | 0.27 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region VI | Iloilo City | 117580 | Arevalo ES | ILOILO CITY (Capital) | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 594034.64 |  | not yet started | 0 |  |  |  |  | 2024-08-05 | 2024-08-12 | 2024-08-24 | Sept. 26, 2024 |  |  | RTA submitted to CO, waiting for sub-aro | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 20047981.78 |  | not yet started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region VI | Negros Occidental | 302694 | Valladolid NHS | VALLADOLID | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3233807.07 | 3223059.63 | COMPLETED | 1 | 2025-02-02 | 2025-04-17 | 23-11-33 | 24-09-002 | 2023-11-20 | 2023-11-27 | 2023-12-12 | 2024-08-29 | 2024-09-20 | PAR BUILDERS, ELECTRICAL AND CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.8 | 0.2 |  | 5.25 | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region VI | Negros Occidental | 302608 | Quirico G. Manzano NHS | CANDONI | 6th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3416277.7 | 3394508.88 | COMPLETED | 1 | 2025-02-02 | 2025-04-02 | 23-11-30 | 24-08-001 | 2023-11-20 | 2023-11-27 | 2023-12-12 | 2024-08-29 | 2024-09-20 | PAR BUILDERS, ELECTRICAL AND CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.9 | 0.1 |  | 5.25 | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region VI | Passi City | 302806 | EFRAIM M. SANTIBAÑEZ NATIONAL HIGH SCHOOL | CITY OF PASSI | 4th | 1 | Upgrading of Electrical System | 1 | 1212555.45 | 972508.03 | COMPLETED | 1 | 2024-09-24 | 2024-08-30 | BEFF-ELECTRIFICATION | RO6-D14-FY2024-BEFF-UES-EMSNHS | 2024-02-12 | 2024-02-21 | 2024-03-03 | 2024-04-05 | 2024-07-04 | Early Riser Construction | 100% Disbursement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VI | Roxas City | 117670 | Mongpong ES | ROXAS CITY (Capital) | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1674765.43 | 1608191.95 | NOT YET started | 0 |  |  | 2024-050 | Con-2024-050 | 2024-06-28 | 2024-07-08 | 2024-07-22 | 2024-11-27 |  | RJZW Elect. Eng'g. Svs. | for issuance of NOA after lifting of banning | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | not yet started
ELECTRIFICATION 2024 | Region VI | Sagay City | 302767 | Sagay National High School | SAGAY CITY | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3575492.35 | 2789804.67 | COMPLETED | 1 |  |  | 45352 | 45352 | 2024-07-23 | 2024-07-30 | 2024-08-12 | 2024-09-28 | 2025-01-06 | CAPRICORN GENERAL MERCHANDISING & SERVICES | already downloaded subaro | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2024 | Region VI | San Carlos City | 302775 | Julio Ledesma National High School | SAN CARLOS CITY | 1st | 1 | Upgrading of Electrical System | 1 | 2426232.73 | 2370639.42 | ONGOING | 0.98 | 2024-09-12 |  | 2023-10-0094 | 10389058-2023-10-0094 | 2023-12-03 | 2023-12-18 | Decemebr 27, 2023 | 2024-01-18 | 2024-06-07 | 2023 BEFF Upgrading of Electrical System ( Overhead System) | waiting of electric cooperative to energized | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.98 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region VI | Silay City | 302781 | Brgy. E. Lopez NHS (SHS) | SILAY CITY | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3024557.77 | 2975811 | Completed | 1 | 2025-05-06 |  | 2024-07-ELNHS-002 | 2024-C-005 | 2024-06-29 | 2024-07-07 | 2024-07-30 | 2024-08-05 | 2025-01-06 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.05 | 0.95 |  | 5.25 | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region VI | Sipalay City | 302633 | Sipalay City NHS | CITY OF SIPALAY | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3546699.83 |  | Under Procurement | 0 | [10 empty] | CO awaiting submission of RTA from division office to download subaro | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | not yet started
ELECTRIFICATION 2024 | Region VI | Victorias City | 117447 | Victorias North ES | CITY OF VICTORIAS | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3479568.81 | 2999675.4 | ONGOING | 0.98 | 2025-03-31 |  | SDOVC-INFRA2024-001 | SDOVC-INFRA2024-001 | 2024-07-11 | 2024-07-19 | 2024-07-31 | 2024-08-22 | 2024-08-27 | Nem Construction Supplies and Services | On-going project | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.7 | 0.28 |  |  | ENERGIZATION | ONGOING

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%