## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | No. of Classrooms | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated | Previous % | Difference | STOREY | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | Status as of July 4, 2025
NEWCON 2016 | REGION VI | Bacolod City | 302700 | Alangilan Nhs | Bacolod City (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8471400 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302701 | Bacolod City Nhs | Bacolod City (Capital) | 0 | 1 | 40 | 4STY20CL | BATCH 9 CL | 67836000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302701 | Bacolod City Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2448130 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302702 | Barangay Singcang-Airport Nhs | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 3 CL | 33490440 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302703 | Bata National High School | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 3 CL | 33575440 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302705 | Domingo Lacson Nhs | Bacolod City (Capital) | 0 | 1 | 30 | 3STY15CL | BATCH 9 CL | 47296129.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302705 | Domingo Lacson Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2448130 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302706 | Emiliano Lizares Nhs | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34318179.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302706 | Emiliano Lizares Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Bacolod City | 117484 | Estefania Es | Bacolod City (Capital) | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22253143.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Bacolod City | 500190 | Fr. Gratian Murray, Afsc Is | Bacolod City (Capital) | 0 | 1 | 12 | 2STY6CL | BATCH 9 CL | 16942800 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302712 | Handumanan Nhs | Bacolod City (Capital) | 0 | 1 | 40 | 4STY20CL | BATCH 3 CL | 66980000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302713 | Jovito H. Sayson Nhs | Bacolod City (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16703510.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302713 | Jovito H. Sayson Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2448130 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302709 | Luis Hervias Nhs | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31252890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302709 | Luis Hervias Nhs | Bacolod City (Capital) | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302709 | Luis Hervias Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302711 | Luisa Medel Nhs | Bacolod City (Capital) | 0 | 1 | 40 | 4STY20CL | BATCH 9 CL | 66980000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION VI | Bacolod City | 311201 | M. G. Medalla Integrated School | Bacolod City (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16703510.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302710 | Mandalagan National High School | Bacolod City (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16703510.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302714 | Mansilingan Agro-Ind. Hs | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34318179.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302714 | Mansilingan Agro-Ind. Hs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302704 | Romanito Maravilla Nhs | Bacolod City (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16703510.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302716 | Sum-Ag National High School | Bacolod City (Capital) | 0 | 1 | 40 | 4STY20CL | BATCH 9 CL | 66980000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302716 | Sum-Ag National High School | Bacolod City (Capital) | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5379660 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Bacolod City | 302718 | Teofilo M. Gensoli Sr. Nhs | Bacolod City (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8471400 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Bago City | 117524 | Mailum Es | Bago City | 4 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2802592.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Bago City | 117516 | R. M. Salas Es | Bago City | 4 | 1 | 4 | 1STY2CL | BATCH 5 CL | 3877212.08 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Bago City | 302720 | Ramon Torres Dulao Nhs | Bago City | 4 | 1 | 15 | 3STY15CL | BATCH 3 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VI | Bago City | 302720 | Ramon Torres Dulao Nhs | Bago City | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2417461.96 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Bago City | 302720 | Ramon Torres Dulao Nhs | Bago City | 4 |  | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2417461.96 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Bago City | 302724 | Ramon Torres Louisiana Nhs | Bago City | 4 | 1 | 30 | 3STY15CL | BATCH 1 CL | 43187226.9 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION VI | Bago City | 302721 | Ramon Torres Maao Sugar Central Nhs | Bago City | 4 | 1 | 12 | 2STY6CL | BATCH 5 CL | 16429930.12 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Bago City | 302721 | Ramon Torres Maao Sugar Central Nhs | Bago City | 4 |  | 16 | 1STY4CL | BATCH 5 CL | 14671875.152 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Bago City | 302722 | Ramon Torres Malingin Nhs | Bago City | 4 | 1 | 16 | 2STY8CL | BATCH 5 CL | 21754685.18 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Bago City | 302719 | Ramon Torres Nhs | Bago City | 4 | 1 | 40 | 4STY20CL | BATCH 1 CL | 63890580.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION VI | Bago City | 302723 | Ramon Torres Sagasa Nhs | Bago City | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8214965.06 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Bago City | 302723 | Ramon Torres Sagasa Nhs | Bago City | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2417461.96 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Bago City | 302725 | Ramon Torres Taloc Nhs | Bago City | 4 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Cadiz City | 117571 | Cadiz Viejo Es | Cadiz City | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Cadiz City | 117573 | Caduha-An Es | Cadiz City | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302728 | Caduha-An Nhs | Cadiz City | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302729 | Caduha-An Nhs - Andres Bonifacio Ext. Hs | Cadiz City | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Cadiz City | 311401 | Caduha-An Nhs - Luna Ext. Hs | Cadiz City | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814741 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial Nhs - Daga Ext. Hs | Cadiz City | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 53085903.72 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial Nhs - Daga Ext. Hs | Cadiz City | 2 |  | 15 | 3STY15CL | BATCH 9 CL |  |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION VI | Cadiz City | 311405 | Dr. Vicente F. Gustilo Memorial Nhs - Daga Ext. Hs To Banquerohan Nhs | Cadiz City | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6563273 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302736 | Jerusalem National High School | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 9834608.3325 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302731 | Mabini National High School | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11980076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302731 | Mabini National High School | Cadiz City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2427000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Cadiz City | 311403 | Mabini Nhs - Alimatoc Ext. Hs | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12100076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302727 | Sicaba National High School | Cadiz City | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302732 | Sped High School | Cadiz City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2505684.72 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302732 | Sped Hs | Cadiz City | 2 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302733 | Tiglawigan Nhs | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302734 | Tiglawigan Nhs - Magsaysay Extension High School | Cadiz City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2552371.2576 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Cadiz City | 117556 | Tres Andanas Es | Cadiz City | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1934741 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Cadiz City | 302735 | Villacin Nhs | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Escalante City | 325602 | Buenavista Nhs - Langub Ext. | City Of Escalante | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Escalante City | 302625 | Escalante Nhs | City Of Escalante | 1 | 1 | 16 | 2STY8CL | BATCH 13 CL | 24300153.698 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Escalante City | 325603 | Escalante Nhs - Pinapugasan Ext. | City Of Escalante | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Escalante City | 302660 | Mabini Nhs | City Of Escalante | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12950000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Escalante City | 302626 | Old Poblacion Nhs | City Of Escalante | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1900000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 117854 | Amian Es | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2108000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302785 | Bantayan National High School | City Of Kabankalan | 6 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13398000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302785 | Bantayan National High School | City Of Kabankalan | 6 |  | 12 | 2STY12CL | BATCH 3 CL | 15324000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302785 | Bantayan National High School | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2479549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302786 | Binicuil National High School | City Of Kabankalan | 6 | 1 | 24 | 3STY12CL | BATCH 1 CL | 38844537.58 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302786 | Binicuil National High School | City Of Kabankalan | 6 |  | 6 | 3STY6CL | BATCH 1 CL | 11017131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302792 | Camansi Nhs | City Of Kabankalan | 6 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11225000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302792 | Camansi Nhs | City Of Kabankalan | 6 |  | 6 | 2STY6CL | BATCH 5 CL | 8476000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 117879 | Candiacap Es | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 117836 | Carol-An Es | City Of Kabankalan | 6 | 1 | 3 | 1STY3CL | BATCH 5 CL | 3056000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302787 | Carol-An Nhs | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2617000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302787 | Carol-An Nhs | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2153800 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302787 | Carol-An Nhs | City Of Kabankalan | 6 |  | 4 | 1STY4CL | BATCH 9 CL | 4075500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 117837 | Casipsipan Es | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1958000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 117837 | Casipsipan Es | City Of Kabankalan | 6 |  | 3 | 1STY3CL | BATCH 5 CL | 2831000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 117881 | Dacongcogon Elementary School | City Of Kabankalan | 6 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2931000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302793 | Florentino Galang Sr. National High School | City Of Kabankalan | 6 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8416000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302793 | Florentino Galang Sr. National High School | City Of Kabankalan | 6 |  | 18 | 3STY9CL | BATCH 5 CL | 30602000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302793 | Florentino Galang Sr. National High School | City Of Kabankalan | 6 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4899098.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302793 | Florentino Galang Sr. National High School | City Of Kabankalan | 6 |  | 12 | 3STY12CL | BATCH 5 CL | 18462000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 312103 | Hinapunan Integrated School | City Of Kabankalan | 6 | 1 | 5 | 1STY5CL | BATCH 5 CL | 4869000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302794 | Inapoy Nhs | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 117844 | Mansumbil Elementary School | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 117846 | Noac Elementary School | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2108000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302798 | Pinaguinpinan Nhs | City Of Kabankalan | 6 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8396000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302798 | Pinaguinpinan Nhs | City Of Kabankalan | 6 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4899098.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 117850 | Pres. Osmena Es | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2158000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 117891 | Sagumayon Ps | City Of Kabankalan | 6 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302797 | Tabugon National High School | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2689549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302797 | Tabugon National High School | City Of Kabankalan | 6 | 1 | 24 | 3STY12CL | BATCH 1 CL | 39564537.58 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302799 | Tabugon Nhs - Tagoc Ext. | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302790 | Tagukon Nhs | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302800 | Tampalon National High School | City Of Kabankalan | 6 | 1 | 12 | 3STY12CL | BATCH 1 CL | 19782268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302800 | Tampalon National High School | City Of Kabankalan | 6 |  | 4 | 2STY4CL | BATCH 1 CL | 6902000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 117853 | Tan-Awan Es | City Of Kabankalan | 6 | 1 | 4 | 1STY4CL | BATCH 5 CL | 3855000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 312101 | Tan-Awan National High School | City Of Kabankalan | 6 | 1 | 10 | 2STY10CL | BATCH 1 CL | 14198000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 312101 | Tan-Awan National High School | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2559549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302801 | Tapi National High School | City Of Kabankalan | 6 | 1 | 12 | 3STY12CL | BATCH 1 CL | 19782000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302801 | Tapi National High School | City Of Kabankalan | 6 |  | 8 | 2STY8CL | BATCH 1 CL | 12025000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Kabankalan City | 302801 | Tapi National High School | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2559549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | La Carlota City | 302751 | Dona H.S.Benedicto Nhs | La Carlota City | 4 | 1 | 32 | 2STY8CL | BATCH 9 CL | 45627903.56 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION VI | La Carlota City | 302751 | Dona H.S.Benedicto Nhs | La Carlota City | 4 |  | 12 | 2STY6CL | BATCH 9 CL | 16799979.18 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Negros Occidental | PSA328544 | Shs In Calatrava, Negros Occidental | Calatrava | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | PSA328544 | Shs In Calatrava, Negros Occidental | Calatrava | 0 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16022138.8978 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302684 | Andres Gumban Mnhs | Toboso | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302597 | Bug-Ang National High School | Toboso | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16690460.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302613 | Col. Griffin National High School | Calatrava | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6499337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 117406 | Hayangon Elementary School | Toboso | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2089214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302604 | Laga-An National High School | Calatrava | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23626314.795 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302604 | Laga-An National High School | Calatrava | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2425000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302683 | San Enrique Hs | San Enrique | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2564500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302683 | San Enrique Hs | San Enrique | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8215000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302682 | Sofronio Carmona Mem. Nhs | Salvador Benedicto | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6350000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302693 | Toboso Nhs | Toboso | 1 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16022138.8978 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302693 | Toboso Nhs | Toboso | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302662 | Manapla Nhs | Manapla | 2 | 1 | 16 | 2STY8CL | BATCH 9 CL | 23900153.7017 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 117275 | Balasyang Elementary School To Alegria Es | Murcia | 3 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2997910.9364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302609 | Cansilayan Nhs | Murcia | 3 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16022138.8978 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302621 | Enrique B. Magalona Nhs | Enrique B. Magalona (Saravia) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 180526 | Hda. Puyas Elementary School | Murcia | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302652 | Inocencio V. Ferrer Sof (Tasof) (Under The Reg'L Office) | City Of Talisay | 3 | 1 | 20 | 2STY10CL | BATCH 9 CL | 28066882.2047 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302659 | Lopez Jaena Nhs | Murcia | 3 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6350000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302670 | Murcia National High School | Murcia | 3 | 1 | 12 | 2STY6CL | BATCH 13 CL | 18042923.11 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302667 | Negros Occ National Science Hs | City Of Victorias | 3 | 1 | 24 | 3STY12CL | BATCH 9 CL | 40058991.338 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302667 | Negros Occ National Science Hs | City Of Victorias | 3 |  | 4 | 2STY4CL | BATCH 9 CL | 6350000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302678 | Rafael B. Lacson Nhs | City Of Talisay | 3 | 1 | 48 | 4STY24CL | BATCH 9 CL | 78281765.708 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302685 | San Isidro Nhs (Pontevedra) | Pontevedra | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302695 | Victorias National High School | City Of Victorias | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302695 | Victorias National High School | City Of Victorias | 3 |  | 45 | 3STY15CL | BATCH 9 CL | 70518944.385 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 45 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302695 | Victorias National High School | City Of Victorias | 3 |  | 36 | 2STY12CL | BATCH 9 CL | 48066416.6933 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302695 | Victorias National High School | City Of Victorias | 3 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7251000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302592 | Biao Nhs | Binalbagan | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2460000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302602 | Cabacungan Nhs | La Castellana | 5 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 117263 | Guinpana-An Es | Moises Padilla (Magallon) | 5 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 117232 | Jose Soriano Es To Don Felix Robles Es | La Castellana | 5 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12771000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302654 | Libas Nhs | Isabela | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2520000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302590 | Andulauan Nhs - Ilog Poblacion Ext. | Ilog | 6 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.06 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 116958 | Basak Es | Cauayan | 6 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8376300 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302600 | Bilbao Uybico Nhs | Hinoba-An (Asia) | 6 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302600 | Bilbao Uybico Nhs | Hinoba-An (Asia) | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302593 | Bocana Nhs | Ilog | 6 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302594 | Bocana Nhs - Galicia Ext. | Ilog | 6 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302594 | Bocana Nhs - Galicia Ext. | Ilog | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302601 | Bulwangan National High School - Talacagay Ext. | Hinoba-An (Asia) | 6 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8264965.06 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 117148 | Damutan Es | Hinoba-An (Asia) | 6 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11198810 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302629 | Eva J. Montilla Nhs | Cauayan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 117357 | Genaro P. Alvarez Elementary School | City Of Sipalay | 6 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12771000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 117357 | Genaro P. Alvarez Elementary School | City Of Sipalay | 6 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302636 | Gil Montilla Nhs - Camindangan Ext. | City Of Sipalay | 6 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8314965.06 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302636 | Gil Montilla Nhs - Camindangan Ext. | City Of Sipalay | 6 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4854000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302639 | Gil Montilla Nhs - Crossing Tanduay Ext. | City Of Sipalay | 6 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2046214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302639 | Gil Montilla Nhs - Crossing Tanduay Ext. | City Of Sipalay | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302642 | Guiljungan Nhs - Abaca Ext. | Cauayan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302651 | Hinigaran Nhs | Hinigaran | 6 | 1 | 40 | 4STY20CL | BATCH 11 CL | 62206000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302661 | Juan Gequillana Nhs (Manalad Nhs) | Ilog | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302664 | Nabulao Nhs | City Of Sipalay | 6 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302664 | Nabulao Nhs | City Of Sipalay | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302666 | Nabulao Nhs - Maricalum Ext. | City Of Sipalay | 6 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302666 | Nabulao Nhs - Maricalum Ext. | City Of Sipalay | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302608 | Quirico G. Manzano Nhs | Candoni | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2470000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302633 | Sipalay City National High School | City Of Sipalay | 6 | 1 | 12 | 2STY12CL | BATCH 9 CL | 14579217.18 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Negros Occidental | 302688 | Tabu Nhs | Ilog | 6 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Sagay City | 302762 | Bato National High School | Sagay City | 2 | 1 | 32 | 4STY32CL | BATCH 9 CL | 48970442.044 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION VI | Sagay City | 302762 | Bato National High School | Sagay City | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 8916630.47 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Sagay City | 302762 | Bato National High School | Sagay City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429550 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Sagay City | 117725 | Baviera Es | Sagay City | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2088607 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Sagay City | 302768 | Bulanon National High School | Sagay City | 2 | 1 | 18 | 3STY9CL | BATCH 5 CL | 28292601 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VI | Sagay City | 302763 | Campo Bago Nhs | Sagay City | 2 |  | 2 | 1STY2CL | BATCH 3 CL | 2088607 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Sagay City | 302764 | Colonia Divina Integrated School | Sagay City | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Sagay City | 302764 | Colonia Divina Integrated School | Sagay City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2464550 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | Sagay City | 2 | 1 | 32 | 4STY32CL | BATCH 9 CL | 44532220.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION VI | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | Sagay City | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 10877342.5917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | Sagay City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429550 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Sagay City | 302766 | Himogaan Baybay Integrated School | Sagay City | 2 | 1 | 15 | 3STY15CL | BATCH 5 CL | 23477167 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VI | Sagay City | 302767 | Sagay Nhs | Sagay City | 2 | 1 | 24 | 4STY24CL | BATCH 13 CL | 37473468 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Sagay City | PSA328548 | Shs, Sagay City | Sagay City | 2 | 1 | 64 | 4STY32CL | BATCH 9 CL | 97940884.088 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 64 | 0
NEWCON 2016 | REGION VI | Sagay City | PSA328548 | Shs, Sagay City | Sagay City | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7288650 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Sagay City | EXT330016 | Snhs-Lopez Jaena Ext. | Sagay City | 2 | 1 | 24 | 4STY24CL | BATCH 1 CL | 37473468 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Sagay City | EXT330015 | Snhs-Rizal Ext. | Sagay City | 2 | 1 | 18 | 3STY9CL | BATCH 1 CL | 30242655.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VI | Sagay City | 117705 | Suyac Es | Sagay City | 2 | 1 | 2 | 2STY2CL | BATCH 9 CL | 4785541.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Sagay City | 302771 | Vito Nhs | Sagay City | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 25032312 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Sagay City | 302771 | Vito Nhs | Sagay City | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7251000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | San Carlos City | 302774 | Don Carlos Ledesma Nhs | San Carlos City | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | San Carlos City | 302775 | Julio Ledesma Nhs | San Carlos City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | San Carlos City | 302775 | Julio Ledesma Nhs | San Carlos City | 1 | 1 | 12 | 3STY6CL | BATCH 13 CL | 22100000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | San Carlos City | 302776 | Quezon Nhs | San Carlos City | 1 | 1 | 12 | 2STY12CL | BATCH 3 CL | 15006508.15 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | San Carlos City | 302777 | Sipaway Nhs | San Carlos City | 1 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3850000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | San Carlos City | 302777 | Sipaway Nhs | San Carlos City | 1 |  | 5 | 1STY5CL | BATCH 3 CL | 4650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2016 | REGION VI | Silay City | 302780 | Doña Montserrat Lopez Memorial High School | Silay City | 3 | 1 | 48 | 4STY24CL | BATCH 9 CL | 77100000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION VI | Silay City | 302780 | Doña Montserrat Lopez Memorial High School | Silay City | 3 |  | 48 | 4STY16CL | BATCH 9 CL | 80107408.26 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 48 | 0
NEWCON 2016 | REGION VI | Silay City | 117826 | Sibato Integrated School | Silay City | 3 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1188254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Aklan | 310620 | 4. Habana Integrated School | Buruanga | 2 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8950000 |  |  | Completed | 1 |  |  | P00070106VS - CW1 | 16GA0029 | March 2 - 8, 2016 | 2016-03-09 | March 22, 20106 | 2016-05-26 | 42521 | LUMEL GLENN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Aklan | 302337 | 8. Toledo National High School | Nabas | 2 | 1 | 12 | 3STY12CL | BATCH 3 CL | 18250000 |  |  | Completed | 1 |  |  | P00070532VS - CW1 | 16GA0030 | March 2 - 8, 2016 | 2016-03-09 | March 22, 20106 | 2016-05-26 | 42521 | AUDRIC CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Aklan | 310616 | Agtughangin Integrated School | Madalag | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2860000 |  |  | Completed | 1 |  |  | P00073579VS - CW1 | 16GA0046 | June 6 - 10, 2016 | 2016-06-17 | 2016-06-17 | Failure of Bidding |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Aklan | 310616 | Agtughangin Integrated School | Madalag | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 |  |  | P00072356VS - CW1 | 16GA0038 | April 13 - 19, 2016 | 2016-04-20 | 2016-04-20 | 2016-06-14 | 42536 | STEVEN CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Aklan | 302286 | Altavas National School | Altavas | 1 | 1 | 24 | 3STY12CL | BATCH 7 CL | 36494537.58 |  |  | Completed | 1 |  |  | P00072357VS - CW1 | 16GA0031 | March 2 - 8, 2016 | 2016-03-09 | 2016-03-09 | 2016-05-26 | 42521 | AFG CONST. & CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Aklan | 302286 | Altavas National School | Altavas | 1 |  | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072358VS - CW1 | 16GA0056 | July 8 -14, 2016 | 2016-07-15 | 2016-07-15 |  |  | G.F. ROVERO MERCHADISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Aklan | 302334 | Rosario National High School | Malinao | 2 | 1 | 12 | 2STY6CL | BATCH 7 CL | 16549930.102 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Aklan | 302336 | Tangalan National High School | Tangalan | 2 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15221327.92 |  |  | Completed | 1 |  |  | P00074511VS - CW1 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Antique | 115141 | Agripino Tambagahan Ms | Pandan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 115027 | Alojipan Es | Culasi | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2016300 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302341 | Antique Ns | San Jose (Capital) | 0 | 1 | 24 | 4STY24CL | BATCH 9 CL | 35596257 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Antique | 302341 | Antique Ns | San Jose (Capital) | 0 |  | 20 | 4STY20CL | BATCH 9 CL | 31102890 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Antique | 302341 | Antique Ns | San Jose (Capital) | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4860000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302342 | Antique Vocational School | Bugasong | 0 | 1 | 30 | 3STY15CL | BATCH 9 CL | 42766026 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION VI | Antique | 302342 | Antique Vocational School | Bugasong | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 115287 | Apong Elementary School | Sibalom | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1924650 |  |  | Terminated | 0 | [10 empty] | Terminated;abandoned | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2
NEWCON 2016 | REGION VI | Antique | 114981 | Arangote Es | Bugasong | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1906320 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302343 | Aureliana Nhs | Patnongon | 0 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222269 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Antique | 114957 | Bahoyan-Yapo Es | Barbaza | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1113254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 302344 | Barangbang Nhs | San Remigio | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Antique | 302344 | Barangbang Nhs | San Remigio | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489900 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 302345 | Barasanan National High School | Tobias Fornier (Dao) | 0 | 1 | 8 | 2STY4CL | BATCH 9 CL | 12864000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Antique | 302345 | Barasanan National High School | Tobias Fornier (Dao) | 0 |  | 2 | 1STY2CL | BATCH 9 CL | 1848000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302346 | Barbaza Nhs | Barbaza | 0 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1 | [10 empty] | Abandoned;Contractor made an appeal to continue | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Antique | 302346 | Barbaza Nhs | Barbaza | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 302347 | Belison Ns | Belison | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VI | Antique | 115178 | Bitas Es | Patnongon | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1942980 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 115082 | Bongbongan Es | Hamtic | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1878825 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302350 | Caluya Nhs | Caluya | 0 | 1 | 18 | 3STY9CL | BATCH 9 CL | 32840921.6 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VI | Antique | 115397 | Cananghan Ps | Valderrama | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1997970 |  |  | Terminated | 0 | [10 empty] | Terminated; Abandoned | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2
NEWCON 2016 | REGION VI | Antique | 115101 | Canituan Ps | Laua-An | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1924650 |  |  | Reverted | 0 | [10 empty] | For reversion; Site Problem | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION VI | Antique | 302351 | Col. Ruperto Abellon Nhs | Laua-An | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 302352 | Concepcion L. Cazeñas Ms | Tobias Fornier (Dao) | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8377460 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Antique | 302352 | Concepcion L. Cazeñas Ms | Tobias Fornier (Dao) | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6444320 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 302352 | Concepcion L. Cazeñas Ms | Tobias Fornier (Dao) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2441300 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 115039 | Culasi North Es | Culasi | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 14941328 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Antique | 115008 | Dawis Es | Caluya | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2934800 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Antique | 302353 | Diclum National High School | Tobias Fornier (Dao) | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Antique | 310710 | Dr. Luis E. Baraquia Nhs | Sibalom | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 310708 | Eastern Laua-An Nhs (Maria Nhs) | Laua-An | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Antique | 310708 | Eastern Laua-An Nhs (Maria Nhs) | Laua-An | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 302354 | Egaña National High School | Sibalom | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 302355 | Gamad-Sto. Tomas Nhs | Tobias Fornier (Dao) | 0 | 1 | 8 | 2STY4CL | BATCH 9 CL | 12926032 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Antique | 115195 | Gella Es | Patnongon | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1924650 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 115195 | Gella Es | Patnongon | 0 |  | 1 | 1STY1CL | BATCH 9 CL | 1074150 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 310704 | Gen. Leandro Fullon Ns | Hamtic | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15163198 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Antique | 310704 | Gen. Leandro Fullon Ns | Hamtic | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 8418190 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Antique | 310704 | Gen. Leandro Fullon Ns | Hamtic | 0 |  | 4 | 1STY4CL | BATCH 9 CL | 3552500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 310704 | Gen. Leandro Fullon Ns | Hamtic | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2453450 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 115242 | General Luna Es | San Remigio | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1979640 |  |  | Terminated | 0 | [10 empty] | Terminated; Abandoned | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2
NEWCON 2016 | REGION VI | Antique | 302357 | Gideon M. Cabigunda Ms | San Remigio | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Antique | 302357 | Gideon M. Cabigunda Ms | San Remigio | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 310707 | Gov. Evelio B. Javier Mnhs | San Remigio | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1860495 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 310707 | Gov. Evelio B. Javier Mnhs | San Remigio | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2453450 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 302358 | Gov. Julio V. Macuja Mchs | Hamtic | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 302356 | Governor Julian Fullon Pacificador Ns | Hamtic | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12898000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Antique | 310701 | Guintas Nhs | Hamtic | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 115221 | Igbonglo Es | San Jose (Capital) | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1053690 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 302359 | Igburi Nhs | Patnongon | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 302360 | Igcado Nhs | Tobias Fornier (Dao) | 0 | 1 | 4 | 1STY2CL | BATCH 9 CL | 3757650 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 115372 | Igcaputol Ps | Tobias Fornier (Dao) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1860495 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 115373 | Igdanlog Es | Tobias Fornier (Dao) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1874243 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302361 | Igpalge Nhs | Anini-Y | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6506640 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 115320 | Indag-An Es | Sibalom | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1906320 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 115322 | Insarayan Es | Sibalom | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1869660 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 115108 | Lactudan Ps | Laua-An | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1942980 |  |  | Terminated | 0 | [10 empty] | Terminated; Abandoned | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2
NEWCON 2016 | REGION VI | Antique | 115109 | Latazon Ps | Laua-An | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2016300 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302362 | Laua-An National High School | Laua-An | 0 | 1 | 8 | 2STY8CL | BATCH 1 CL | 10877342.5917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Antique | 302363 | Libertad Nvs | Libertad | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12898000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Antique | 302363 | Libertad Nvs | Libertad | 0 |  | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Antique | 302364 | Lirio M. Escaño, Sr. Nhs | Patnongon | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Antique | 302364 | Lirio M. Escaño, Sr. Nhs | Patnongon | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 115324 | Lotilla Es | Sibalom | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 115092 | M.V. Velasco Mes | Hamtic | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1869660 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302365 | Mag-Aba Nhs | Pandan | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Antique | 302365 | Mag-Aba Nhs | Pandan | 0 |  | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302366 | Moscoso-Rios Nhs | Hamtic | 0 | 1 | 20 | 2STY10CL | BATCH 9 CL | 25692620 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Antique | 302366 | Moscoso-Rios Nhs | Hamtic | 0 |  | 2 | 1STY2CL | BATCH 9 CL | 1814740 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302366 | Moscoso-Rios Nhs | Hamtic | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 115048 | Naba Ps | Culasi | 0 | 1 | 4 | 1STY2CL | BATCH 9 CL | 3666000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 115328 | Nazareth Es | Sibalom | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302367 | Northern Antique Vocational School | Culasi | 0 | 1 | 12 | 2STY6CL | BATCH 9 CL | 16429930 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Antique | 302367 | Northern Antique Vocational School | Culasi | 0 |  | 24 | 2STY12CL | BATCH 9 CL | 29158434 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Antique | 310709 | Northern Bugasong Nhs Annex | Bugasong | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6600120 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 302369 | Pandan Nvhs | Pandan | 0 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12898000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Antique | 302370 | Pangpang Nhs | Sibalom | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12898000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Antique | 302370 | Pangpang Nhs | Sibalom | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 302371 | Pascual M. Osuyos Ms | Tobias Fornier (Dao) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 115185 | Patlabawon Es | Patnongon | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1897155 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302372 | Patria National School | Pandan | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 115133 | Paz Es | Libertad | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302373 | Pis-Anan National High Sshool | Sibalom | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12898000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Antique | 302373 | Pis-Anan National High Sshool | Sibalom | 0 |  | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 115229 | Salazar Es (Funda Dalipe Es) | San Jose (Capital) | 0 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10417232 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Antique | 115229 | Salazar Es (Funda Dalipe Es) | San Jose (Capital) | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6473000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 302376 | San Roque-Ezpeleta Nhs | Anini-Y | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8418190 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Antique | 302376 | San Roque-Ezpeleta Nhs | Anini-Y | 0 |  | 4 | 1STY4CL | BATCH 9 CL | 3552500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 115231 | San Fernando Es | San Jose (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 115055 | San Pascual Es | Culasi | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1924650 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302375 | San Pedro Nhs | San Jose (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 302377 | Sebaste Hs | Sebaste | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Antique | 302377 | Sebaste Hs | Sebaste | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 310703 | Sibalom Nhs | Sibalom | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VI | Antique | 310703 | Sibalom Nhs | Sibalom | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 14941328 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Antique | 310703 | Sibalom Nhs | Sibalom | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4860000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 310706 | Sibay Nhs | Caluya | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3850000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 302378 | Sido-San Juan Nhs | Sibalom | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Antique | 114980 | Sinaja-Salvacion Elementary School | Belison | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302379 | Southern Bugasong Nhs | Bugasong | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 302380 | Sta. Ana Nhs | Pandan | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7116271.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 302380 | Sta. Ana Nhs | Pandan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2507000 |  |  | Terminated | 0 | [10 empty] | For request of funding to complete | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
NEWCON 2016 | REGION VI | Antique | 115169 | Tabay Es | Pandan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1897155 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 114955 | Tagaytay Es | Anini-Y | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1906320 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 310702 | Tario Lim National Memorial High School | Tibiao | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VI | Antique | 310702 | Tario Lim National Memorial High School | Tibiao | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 310702 | Tario Lim National Memorial High School | Tibiao | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 115171 | Tingib Es | Pandan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 302382 | Tinogboc Nhs | Caluya | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3850000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 302383 | Union Nhs | Libertad | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Antique | 302383 | Union Nhs | Libertad | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Antique | 302384 | Valderrama Nhs | Valderrama | 0 | 1 | 18 | 3STY9CL | BATCH 9 CL | 29882656 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VI | Antique | 302384 | Valderrama Nhs | Valderrama | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Antique | 115173 | Zaldivar Elementary School | Pandan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 302388 | Cabugcabug Nhs | President Roxas | 1 | 1 | 24 | 4STY24CL | BATCH 9 CL | 39440882.854 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Capiz | 302392 | Casanayan Nhs | Pilar | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22352343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Capiz | 302395 | Comsr. Luis R. Asis Nhs | Panay | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Capiz | 302395 | Comsr. Luis R. Asis Nhs | Panay | 1 |  | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Capiz | 310802 | Dao National High School | Dao | 1 | 1 | 24 | 4STY24CL | BATCH 3 CL | 35627000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Capiz | 302400 | Dulangan Nhs | Pilar | 1 | 1 | 10 | 2STY10CL | BATCH 1 CL | 13321310.093 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Capiz | 302400 | Dulangan Nhs | Pilar | 1 |  | 6 | 2STY6CL | BATCH 1 CL | 9200000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Capiz | 302398 | Felix Balgos Nhs | Panay | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8829965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Capiz | 302405 | Hipona Nhs | Pontevedra | 1 | 1 | 18 | 3STY18CL | BATCH 1 CL | 32550000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VI | Capiz | 302405 | Hipona Nhs | Pontevedra | 1 |  | 9 | 3STY9CL | BATCH 1 CL | 16350000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Capiz | 302405 | Hipona Nhs | Pontevedra | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 302410 | Leodegario D. Deocampo Sr. Nhs | Panitan | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10717131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Capiz | 302413 | Maayon Nhs | Ma-Ayon | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 27600000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Capiz | 302413 | Maayon Nhs | Ma-Ayon | 1 |  | 20 | 4STY20CL | BATCH 9 CL | 31470000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Capiz | 302413 | Maayon Nhs | Ma-Ayon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 302419 | Marciano M. Patricio (Pilar) | Pilar | 1 | 1 | 24 | 4STY24CL | BATCH 9 CL | 39140882.854 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Capiz | 302419 | Marciano M. Patricio (Pilar) | Pilar | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 302418 | Panitan Nhs | Panitan | 1 | 1 | 32 | 4STY32CL | BATCH 1 CL | 44832220.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION VI | Capiz | 302418 | Panitan Nhs | Panitan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2750000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 310812 | Pawa National High School | Panay | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 11504807.7485 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Capiz | 302420 | Pontevedra Nhs | Pontevedra | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2479549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 302420 | Pontevedra Nhs | Pontevedra | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 23606314.795 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VI | Capiz | 302422 | San Nicolas Nhs (Pilar) | Pilar | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14183441.1023 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Capiz | 115662 | Tabuc Norte Ps | Panitan | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 302403 | Tuburan Nhs | Ma-Ayon | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14183441.1023 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Capiz | 115470 | Aglanot Es | Dumarao | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 115412 | Angub Elementary School | Cuartero | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 302385 | Arturo Jugo Nhs | Dao | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 115475 | Badbaranan Es | Dumarao | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 310801 | Bagong Barrio Nhs | Tapaz | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 310807 | Basiao Nhs (Formerly Ext. Of Ivisan Nhs) | Ivisan | 2 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15122000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Capiz | 115585 | Bergante Es | Mambusao | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 302386 | Bungsuan Nhs | Dumarao | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 302389 | Camburanan Nhs | Tapaz | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 302390 | Candelaria Nhs | Tapaz | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 311705 | Candelaria Nhs- Roxas Extension | Tapaz | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 302393 | Col. Patrocinio Artuz Nhs | Tapaz | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8215000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Capiz | 302401 | Concepcion Castro Garcia Nhs (Dumalag Nhs) Sta. Cruz | Dumalag | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 302396 | Cuartero Nhs | Cuartero | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22153000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Capiz | 302396 | Cuartero Nhs | Cuartero | 2 |  | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 302397 | David Moises Mhs | Mambusao | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 310806 | Dumalag Central Nhs | Dumalag | 2 | 1 | 24 | 4STY24CL | BATCH 3 CL | 35597000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Capiz | 310806 | Dumalag Central Nhs | Dumalag | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 302402 | Estefania Montemayor Nhs | Dumarao | 2 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31103000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Capiz | 302402 | Estefania Montemayor Nhs | Dumarao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 115485 | Guinotos Ps | Dumarao | 2 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1013000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 115507 | Ivisan Es | Ivisan | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 302406 | Ivisan Nhs | Ivisan | 2 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22153000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Capiz | 302406 | Ivisan Nhs | Ivisan | 2 |  | 20 | 4STY20CL | BATCH 3 CL | 31103000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Capiz | 302406 | Ivisan Nhs | Ivisan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 302408 | Jagnaya Nhs | Jamindan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 179001 | Jambad Ps | Dumarao | 2 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1013000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 302409 | Jamindan Nhs | Jamindan | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15122000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Capiz | 302409 | Jamindan Nhs | Jamindan | 2 |  | 12 | 4STY12CL | BATCH 3 CL | 22153000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Capiz | 302409 | Jamindan Nhs | Jamindan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 310810 | Lonoy National High School | Sapi-An | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 302411 | Lucero Nhs | Jamindan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 302415 | Luis Escutin Nhs | Dao | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 115419 | Lunayan E/S | Cuartero | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 115422 | Maindang Elementary School | Cuartero | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 310804 | Maindang National High School | Cuartero | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8215000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Capiz | 302414 | Malonoy National High School | Dao | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 302414 | Malonoy National High School | Dao | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 310813 | Mambusao East Nhs (Ext. Of David Moises) | Mambusao | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8215000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Capiz | 310805 | Mambusao National High School | Mambusao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 302416 | Manuel F. Onato Memorial Nhs | Dumarao | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8215000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Capiz | 302416 | Manuel F. Onato Memorial Nhs | Dumarao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 115762 | Matinabus Es | Sigma | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 310815 | Mianay Nhs | Sigma | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 115489 | Nagsulang Elementary School | Dumarao | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 310814 | Presentacion Diez Gregorio Nhs | Dumarao | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 302421 | Putian National High School | Cuartero | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1744744.436 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 115491 | R. Advincula Sr. Ms | Dumarao | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 302417 | Ramon A. Benjamin Sr. Nhs | Dumarao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Capiz | 310809 | Rev. Tomas Conejar Nhs | Tapaz | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 310808 | San Antonio National High School | Cuartero | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 302423 | San Nicolas Nhs (Tapaz) | Tapaz | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 302424 | Sapian National High School | Sapi-An | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Capiz | 302424 | Sapian National High School | Sapi-An | 2 |  | 12 | 3STY12CL | BATCH 3 CL | 18223000 |  |  | Completed | 1 | [10 empty] | With approved additional funds | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Capiz | 115495 | Tamulalod Es | Dumarao | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 310803 | Tapaz Nhs | Tapaz | 2 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26703000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Capiz | 115546 | Ubog Es | Jamindan | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Capiz | 302399 | Vicente Andaya Sr. Nhs | Sigma | 2 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [10 empty] | With approved additional funds | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Capiz | 302399 | Vicente Andaya Sr. Nhs | Sigma | 2 |  | 8 | 2STY8CL | BATCH 7 CL | 10877343 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Capiz | 302399 | Vicente Andaya Sr. Nhs | Sigma | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 1250000 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION VI | Guimaras | 302427 | Agsanayan National High School | Buenavista | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Guimaras | 302425 | Alegria National High School | Sibunag | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8546000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Guimaras | 302425 | Alegria National High School | Sibunag | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Guimaras | 310901 | Ayangan National High School | Sibunag | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6532000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Guimaras | 302426 | Buenavista Nhs | Buenavista | 0 | 1 | 32 | 4STY32CL | BATCH 1 CL | 44532220.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION VI | Guimaras | 302428 | Cabalagnan National High School | Nueva Valencia | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8546000 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION VI | Guimaras | 302435 | Calaya National High School | Nueva Valencia | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Guimaras | 302429 | Desiderio C. Gange National High School | Sibunag | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | San Lorenzo | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8496000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | San Lorenzo | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Guimaras | 302430 | East Valencia National High School | Buenavista | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Guimaras | 302430 | East Valencia National High School | Buenavista | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Guimaras | 302431 | Getulio National High School | Buenavista | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Guimaras | 302432 | Jordan Nhs | Jordan Nhs | 0 | 1 | 18 | 3STY18CL | BATCH 1 CL | 28350000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VI | Guimaras | 179503 | Mabini Primary School | Buenavista | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2668000 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION VI | Guimaras | 302434 | Nueva Valencia National High School | Nueva Valencia | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31353000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Guimaras | 115881 | Paaralan Ng Buhay Ng Ravina Sur | Sibunag | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Guimaras | 302436 | Salvacion National High School | Nueva Valencia | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Guimaras | 302439 | San Lorenzo Nhs-Suclaran Annex | San Lorenzo | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Guimaras | 179502 | San Nicolas Primary School | Buenavista | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3650000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Guimaras | 115890 | Sebaste-Bubog Es | Sibunag | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1933000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Guimaras | 302433 | Semion J. Jabasa National High School | Nueva Valencia | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Guimaras | 310902 | Supang National High School | Buenavista | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13048000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa National High School | Jordan | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31353000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa National High School | Jordan | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Guimaras | 115846 | Umilig Primary School | Buenavista | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1933000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Iloilo | 116717 | Andres Bonifacio Es | San Joaquin | 1 | 1 | 6 | 1STY3CL | BATCH 9 CL | 5884821.8728 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 116717 | Andres Bonifacio Es | San Joaquin | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1138254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302545 | Bacolod Nhs | Miagao | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2326509.2394 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Iloilo | 311024 | Bagacay Nhs | Tigbauan | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Iloilo | 302479 | Camangahan Nhs | Guimbal | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302488 | Dapdap Nhs | Tigbauan | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302495 | Don Felix Serra Nhs | San Joaquin | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302495 | Don Felix Serra Nhs | San Joaquin | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8850000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302495 | Don Felix Serra Nhs | San Joaquin | 1 |  | 9 | 3STY9CL | BATCH 13 CL | 15418925.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Iloilo | 302499 | Escalantera Nhs | San Joaquin | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11443844.661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302506 | Guimbal Nhs | Guimbal | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Iloilo | 302507 | Igbaras Nhs | Igbaras | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15418925.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Iloilo | 302531 | Miag-Ao Nhs | Miag-Ao | 1 | 1 | 24 | 2STY12CL | BATCH 13 CL | 29158434.36 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Iloilo | 302542 | Oton Nhs | Oton | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302542 | Oton Nhs | Oton | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Iloilo | 302542 | Oton Nhs | Oton | 1 |  | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 302549 | Particion Nhs | Guimbal | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302566 | San Joaquin School Of Fisheries | San Joaquin | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2564500 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302566 | San Joaquin School Of Fisheries | San Joaquin | 1 | 1 | 12 | 2STY12CL | BATCH 13 CL | 14579217.18 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 311013 | Supt. Arsenio M. Napud Mnhs | Miagao | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 311013 | Supt. Arsenio M. Napud Mnhs | Miagao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302578 | Tigbauan Nhs | Tigbauan | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Iloilo | 302578 | Tigbauan Nhs | Tigbauan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302583 | Tubungan Nhs | Tubungan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302446 | Alimodian Nhs | Alimodian | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 12638675.2761 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 302446 | Alimodian Nhs | Alimodian | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302446 | Alimodian Nhs | Alimodian | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 311017 | Bancal Nhs | Alimodian | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 311017 | Bancal Nhs | Alimodian | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302466 | Bololacao Nhs | New Lucena | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11660000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 302470 | Buga Nhs | Leon | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 311028 | Dalid Nhs | Alimodian | 2 | 1 | 12 | 2STY6CL | BATCH 9 CL | 18162923.1122 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 182504 | Desamparados Amita Elementary School | Alimodian | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Iloilo | 302513 | Jelicuon-Cabugao Nhs | New Lucena | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302520 | Leganes Nhs | Leganes | 2 | 1 | 16 | 2STY8CL | BATCH 9 CL | 23170000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Iloilo | 302520 | Leganes Nhs | Leganes | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 7380000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302520 | Leganes Nhs | Leganes | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302522 | Leon Nhs | Leon | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11660000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 302522 | Leon Nhs | Leon | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302522 | Leon Nhs | Leon | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 7380000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302539 | New Lucena Nchs | New Lucena | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Iloilo | 302540 | New Lucena Nhs | New Lucena | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11660000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 302550 | Pavia Nhs | Pavia | 2 | 1 | 20 | 2STY8CL | BATCH 9 CL | 23320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Iloilo | 302550 | Pavia Nhs | Pavia | 2 |  | 4 | 2STY4CL |  | 6936271.4 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 311027 | Sinamay Nhs | Alimodian | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 13872542.808 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 302573 | Sta. Barbara Nhs | Sta. Barbara | 2 | 1 | 16 | 2STY8CL | BATCH 9 CL | 23320000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Iloilo | 302573 | Sta. Barbara Nhs | Sta. Barbara | 2 |  | 12 | 2STY6CL | BATCH 9 CL | 18042923.1122 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 302573 | Sta. Barbara Nhs | Sta. Barbara | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 311021 | Tacuyong Sur Nhs | Leon | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7016271.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302585 | Zarraga Nhs | Zarraga | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302585 | Zarraga Nhs | Zarraga | 2 |  | 12 | 2STY6CL | BATCH 9 CL | 18042923.1122 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 302585 | Zarraga Nhs | Zarraga | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 11660000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 302441 | Abangay Nhs | Janiuay | 3 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Iloilo | 302447 | Ambrosio Maido Mnhs | Cabatuan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302452 | Badiangan Nhs | Badiangan | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8707539.88 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 311020 | Caninguan Nhs | Lambunao | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8664965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 311020 | Caninguan Nhs | Lambunao | 3 |  | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 311020 | Caninguan Nhs | Lambunao | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 311003 | Jayobo Nhs | Lambunao | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 311003 | Jayobo Nhs | Lambunao | 3 |  | 10 | 2STY10CL | BATCH 9 CL | 12971310.09 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VI | Iloilo | 311003 | Jayobo Nhs | Lambunao | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 311025 | Jovito Alfaras Rivera Nhs | Bingawan | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 311025 | Jovito Alfaras Rivera Nhs | Bingawan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 311025 | Jovito Alfaras Rivera Nhs | Bingawan | 3 |  | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302559 | Leon Mediana Nhs | Maasin | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302559 | Leon Mediana Nhs | Maasin | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302526 | Malitbog Nhs | Calinog | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8664965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302526 | Malitbog Nhs | Calinog | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302546 | Palanguia Nhs | Pototan | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Iloilo | 302546 | Palanguia Nhs | Pototan | 3 | 1 | 9 | 3STY9CL | BATCH 9 CL | 13816701.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Iloilo | 302580 | Tina Nhs | Badiangan | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8664965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302580 | Tina Nhs | Badiangan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302489 | De La Paz Nhs | Banate | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302489 | De La Paz Nhs | Banate | 4 |  | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302543 | Pagdugue Nhs | Dumangas | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302543 | Pagdugue Nhs | Dumangas | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 311006 | Pd Monfort National Science Hs | Dumangas | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 311006 | Pd Monfort National Science Hs | Dumangas | 4 |  | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302443 | Ajuy National High School | Ajuy | 5 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8814965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302443 | Ajuy National High School | Ajuy | 5 |  | 8 | 2STY4CL | BATCH 13 CL | 13438675.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 116769 | Alfredo Sanson Mes | Sara | 5 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11077342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 116769 | Alfredo Sanson Mes | Sara | 5 |  | 4 | 2STY4CL | BATCH 9 CL | 6719337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 116771 | Apelo Es | Sara | 5 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6719337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 116771 | Apelo Es | Sara | 5 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Iloilo | 116772 | Ardemil Es | Sara | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Iloilo | 116012 | Balasan Ces | Balasan | 5 | 1 | 18 | 3STY9CL | BATCH 13 CL | 30242655.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VI | Iloilo | 116012 | Balasan Ces | Balasan | 5 |  | 6 | 2STY6CL | BATCH 13 CL | 8864965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 116012 | Balasan Ces | Balasan | 5 |  | 6 | 2STY6CL | BATCH 13 CL | 8864965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302454 | Balasan National High School | Balasan | 5 | 1 | 20 | 2STY10CL | BATCH 9 CL | 28066882.2047 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Iloilo | 302454 | Balasan National High School | Balasan | 5 |  | 6 | 2STY6CL | BATCH 9 CL | 8864965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302454 | Balasan National High School | Balasan | 5 |  | 16 | 2STY8CL | BATCH 9 CL | 23900153.7017 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Iloilo | 116201 | Bancal Es | Carles | 5 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Iloilo | 116201 | Bancal Es | Carles | 5 |  | 4 | 2STY4CL | BATCH 13 CL | 6719337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 116202 | Barangcalan Es | Carles | 5 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3195402.03 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Iloilo | 302458 | Barotac Viejo National High School | Barotac Viejo | 5 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8814965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302458 | Barotac Viejo National High School | Barotac Viejo | 5 |  | 24 | 2STY8CL | BATCH 9 CL | 35850230.5526 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Iloilo | 302460 | Batad National High School | Batad | 5 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11027342.5917 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 302460 | Batad National High School | Batad | 5 |  | 24 | 2STY8CL | BATCH 1 CL | 33232027.7751 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Iloilo | 302462 | Bayas National High School | Estancia | 5 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302493 | Carlos Lopez National High School | San Dionisio | 5 | 1 | 16 | 2STY8CL | BATCH 9 CL | 23900153.7017 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Iloilo | 302493 | Carlos Lopez National High School | San Dionisio | 5 |  | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302482 | Cawayan National High School | Carles | 5 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6719337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302482 | Cawayan National High School | Carles | 5 |  | 6 | 2STY6CL | BATCH 3 CL | 8814965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302482 | Cawayan National High School | Carles | 5 |  | 6 | 2STY6CL | BATCH 3 CL | 8814965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 116241 | Claudia Morata Villarias Ms | Concepcion | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Iloilo | 116488 | Concepcion Juanillo Mes | Lemery | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Iloilo | 302486 | Culasi National High School | Ajuy | 5 | 1 | 8 | 2STY4CL | BATCH 3 CL | 13438675.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 302486 | Culasi National High School | Ajuy | 5 |  | 6 | 2STY6CL | BATCH 3 CL | 8814965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 116775 | Del Castillo Es | Sara | 5 | 1 | 4 | 1STY2CL | BATCH 9 CL | 3489488.872 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 116775 | Del Castillo Es | Sara | 5 |  | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Iloilo | 302500 | Estancia National High School | Estancia | 5 | 1 | 12 | 2STY6CL | BATCH 9 CL | 17779930.1 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 302500 | Estancia National High School | Estancia | 5 |  | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 302500 | Estancia National High School | Estancia | 5 |  | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 302500 | Estancia National High School | Estancia | 5 |  | 16 | 2STY8CL | BATCH 9 CL | 23900153.7017 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Iloilo | 302500 | Estancia National High School | Estancia | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2450333.3333 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302502 | Gen. Luna Nhs | Barotac Viejo | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 116350 | Gogo Es | Estancia | 5 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Iloilo | 302505 | Granada Nhs | Carles | 5 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9736461.555 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 311009 | Granada Nhs-Ballesteros Campus | Carles | 5 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12170076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 311009 | Granada Nhs-Ballesteros Campus | Carles | 5 |  | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Iloilo | 302521 | Lemery National High School | Lemery | 5 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8814965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302521 | Lemery National High School | Lemery | 5 |  | 4 | 2STY4CL | BATCH 13 CL | 6569337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 311007 | Loong Nhs | Concepcion | 5 | 1 | 12 | 2STY6CL | BATCH 9 CL | 14816937.0918 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 116783 | Malapaya Es | Sara | 5 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Iloilo | 116783 | Malapaya Es | Sara | 5 |  | 6 | 2STY6CL | BATCH 9 CL | 8864965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 116783 | Malapaya Es | Sara | 5 |  | 1 | 1STY1CL | BATCH 9 CL | 1113254.6197 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302541 | Nicomedes R. Tubar Sr. National High School | San Dionisio | 5 | 1 | 16 | 2STY8CL | BATCH 9 CL | 23900153.7017 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Iloilo | 302541 | Nicomedes R. Tubar Sr. National High School | San Dionisio | 5 |  | 6 | 2STY6CL | BATCH 9 CL | 8814965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302555 | Polopiña Nhs | Concepcion | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Iloilo | 302555 | Polopiña Nhs | Concepcion | 5 |  | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302484 | Roberto H. Tirol National High School | Concepcion | 5 | 1 | 16 | 2STY8CL | BATCH 1 CL | 21804685.1834 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Iloilo | 302484 | Roberto H. Tirol National High School | Concepcion | 5 |  | 12 | 2STY6CL | BATCH 1 CL | 17769930.1 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 302569 | San Rafael Nhs | San Rafael | 5 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6799337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302569 | San Rafael Nhs | San Rafael | 5 |  | 8 | 2STY8CL | BATCH 9 CL | 11237342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 302569 | San Rafael Nhs | San Rafael | 5 |  | 9 | 3STY9CL | BATCH 9 CL | 13830000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Iloilo | 311004 | Santiago Nhs | Barotac Viejo | 5 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6719337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 311004 | Santiago Nhs | Barotac Viejo | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Iloilo | 302570 | Sara National High School | Sara | 5 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8864965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302570 | Sara National High School | Sara | 5 |  | 16 | 2STY8CL | BATCH 13 CL | 23975153.698 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Iloilo | 302570 | Sara National High School | Sara | 5 |  | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 116695 | Talo-Ato Ps | San Dionisio | 5 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VI | Iloilo | 311012 | Tambaliza Nhs | Concepcion | 5 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12170076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 311012 | Tambaliza Nhs | Concepcion | 5 |  | 6 | 2STY6CL | BATCH 9 CL | 9736461.555 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 311001 | Valerio Palmares National High School | Batad | 5 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6624337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 311001 | Valerio Palmares National High School | Batad | 5 |  | 8 | 2STY8CL | BATCH 9 CL | 12040076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo City | 302738 | Iloilo City Nhs | Iloilo City (Capital) | 0 | 1 | 24 | 4STY12CL | BATCH 9 CL | 40334214.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Iloilo City | 302738 | Iloilo City Nhs | Iloilo City (Capital) | 0 |  | 40 | 4STY20CL | BATCH 9 CL | 57041951.34 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION VI | Iloilo City | 302742 | Jalandoni Mnhs | Iloilo City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28520975.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Iloilo City | 302744 | Jaro Nhs | Iloilo City (Capital) | 0 | 1 | 12 | 4STY12CL | BATCH 9 CL | 20167107.46 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo City | 302744 | Jaro Nhs | Iloilo City (Capital) | 0 |  | 20 | 4STY20CL | BATCH 9 CL | 28520975.67 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Iloilo City | 302744 | Jaro Nhs | Iloilo City (Capital) | 0 |  | 12 | 4STY12CL | BATCH 9 CL | 20167107.46 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo City | 302747 | La Paz Nhs | Iloilo City (Capital) | 0 | 1 | 12 | 3STY12CL | BATCH 3 CL | 17127665.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo City | 302747 | La Paz Nhs | Iloilo City (Capital) | 0 |  | 6 | 3STY6CL | BATCH 3 CL | 10316033.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo City | 117606 | La Paz Nhs To La Paz Es I | Iloilo City (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6252451.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo City | 302750 | Ramon Avancena Nhs | Iloilo City (Capital) | 0 | 1 | 16 | 4STY16CL | BATCH 1 CL | 27914453.1855 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Iloilo | 302473 | Cabatuan Nchs | Cabatuan | 3 | 1 | 24 | 4STY24CL | BATCH 13 CL | 39140882.854 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Iloilo | 302473 | Cabatuan Nchs | Cabatuan | 3 |  | 15 | 3STY15CL | BATCH 13 CL | 23506314.795 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VI | Iloilo | 302477 | Calinog Nchs | Calinog | 3 | 1 | 15 | 3STY15CL | BATCH 13 CL | 23506314.795 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VI | Iloilo | 302477 | Calinog Nchs | Calinog | 3 |  | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Iloilo | 302512 | Janiuay Nchs | Janiuay | 3 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Iloilo | 302512 | Janiuay Nchs | Janiuay | 3 |  | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 302517 | Lambunao Nhs | Lambunao | 3 | 1 | 15 | 3STY15CL | BATCH 13 CL | 23506314.795 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VI | Iloilo | 302517 | Lambunao Nhs | Lambunao | 3 |  | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 302524 | Maasin Nhs | Maasin | 3 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 302533 | Mina Nhs | Mina | 3 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12638675.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Iloilo | 302533 | Mina Nhs | Mina | 3 |  | 6 | 2STY6CL | BATCH 13 CL | 8404965.045 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302556 | Pototan Nhs | Pototan | 3 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VI | Iloilo | 302556 | Pototan Nhs | Pototan | 3 |  | 6 | 2STY6CL | BATCH 13 CL | 8404965.045 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302556 | Pototan Nhs | Pototan | 3 |  | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 302556 | Pototan Nhs | Pototan | 3 |  | 6 | 3STY6CL | BATCH 13 CL | 11443844.661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302556 | Pototan Nhs | Pototan | 3 |  | 6 | 3STY6CL | BATCH 13 CL | 11443844.661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VI | Iloilo | 302449 | Anilao Nhs | Anilao | 4 | 1 | 12 | 2STY12CL | BATCH 13 CL | 14579217.18 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 302455 | Banate Nhs | Banate | 4 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VI | Iloilo | 302457 | Barotac Nuevo Cnhs | Barotac Nuevo | 4 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VI | Iloilo | 302457 | Barotac Nuevo Cnhs | Barotac Nuevo | 4 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Iloilo | 302490 | Dingle Nhs | Dingle | 4 | 1 | 12 | 3STY6CL | BATCH 13 CL | 22887689.322 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 302497 | Dueñas Nhs | Dueñas | 4 | 1 | 28 | 4STY28CL | BATCH 13 CL | 44059740.754 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0
NEWCON 2016 | REGION VI | Iloilo | 302497 | Dueñas Nhs | Dueñas | 4 |  | 32 | 4STY32CL | BATCH 13 CL | 48970442.044 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION VI | Iloilo | 302498 | Dumangas Nhs | Dumangas | 4 | 1 | 24 | 4STY24CL | BATCH 13 CL | 39140882.854 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Iloilo | 302564 | San Enrique Nhs | San Enrique | 4 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Iloilo | 302564 | San Enrique Nhs | San Enrique | 4 |  | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Passi City | 302806 | Efraim M. Santibañez National High School | City Of Passi | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VI | Passi City | 302804 | Mulapula National High School | City Of Passi | 4 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13138675.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Passi City | 302805 | Passi National High School | City Of Passi | 4 |  | 45 | 3STY15CL | BATCH 9 CL | 68783507.97 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 45 | 0
NEWCON 2016 | REGION VI | Passi City | 302805 | Passi National High School | City Of Passi | 4 | 1 | 15 | 3STY15CL | BATCH 9 CL | 22927835.99 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VI | Passi City | 302805 | Passi National High School | City Of Passi | 4 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4350600 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VI | Passi City | 302807 | Salngan National High School | City Of Passi | 4 | 1 | 12 | 2STY6CL | BATCH 9 CL | 17329930.1 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VI | Roxas City | 117666 | Banica Elementary School | Roxas City (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VI | Roxas City | 302757 | Cong. Ramon A. Arnaldo Hs | Roxas City (Capital) | 1 | 1 | 24 | 2STY6CL | BATCH 5 CL | 33456660 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VI | Roxas City | 302757 | Cong. Ramon A. Arnaldo Hs | Roxas City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VI | Roxas City | 311702 | Roxas City School For Philippine Craftsmen | Roxas City (Capital) | 1 | 1 | 24 | 2STY6CL | BATCH 1 CL | 33808660 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.