## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | Total Physical Target | SCOPE OF WORK | PROJECT ALLOCATION | Batch | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 4, 2025
SCHOOL HEALTH FACILITIES 2024 | Region VII | Carcar City | 119161 | PERRELOS ELEMENTARY SCHOOL | Carcar City | 2nd | 1 | - | Convertion Of Classrooms to School Dental Clinic | 2257172.73 | - | 1687612.07 | COMPLETED | 1 | September 28, 2024 | August 16, 2024 | School Clinic-01Carcar | BEFF 2024-REpair of Classroom to be used / convered to School Clinic (7.00mx9.00m) at Perrelos Elementary School | March 13, 2024 | March 19, 2024 | April 3, 2024 | April 17, 2024 | June 21, 2024 | A.O.S. Construction Services
SCHOOL HEALTH FACILITIES 2024 | Region VII | Cebu | 119628 | Pitalo ES | SAN FERNANDO | 1st | 1 | - | Construction of School Clinic | 2726233.05 | - | 2701147.62 | completed | 1 | February 5, 2025 | February 5, 2025 | CY 2024 BEFF Health-DepED-R7-Cebu-01 | CY 2024 BEFF Health-DepED-R7-Cebu-01 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 22, 2024 | September 30, 2024 | GELA CONSTRUCTION OPC
SCHOOL HEALTH FACILITIES 2024 | Region VII | Cebu | 118917 | Argao I Central ES | ARGAO | 2nd | 1 | - | Construction of School Clinic | 2726233.05 | - | 2700751.08 | completed | 1 | February 5, 2025 | January 9, 2025 | CY 2024 BEFF Health-DepED-R7-Cebu-02 | CY 2024 BEFF Health-DepED-R7-Cebu-02 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 22, 2024 | September 30, 2024 | BARR STEEL CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | Region VII | Cebu | 119092 | Guibuangan Central ES | BARILI | 3rd | 1 | - | Construction of School Clinic | 2726233.05 | - | 2715451.46 | completed | 1 | February 5, 2025 | February 5, 2025 | CY 2024 BEFF Health-DepED-R7-Cebu-03 | CY 2024 BEFF Health-DepED-R7-Cebu-03 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 22, 2024 | September 30, 2024 | RT CONSTRUCTION & ENTERPRISES
SCHOOL HEALTH FACILITIES 2024 | Region VII | Cebu | 500694 | Caputatan Norte Integrated School | MEDELLIN | 4th | 1 | - | Construction of School Clinic | 2810788.92 | - | 2790352.41 | completed | 1 | February 5, 2025 | February 5, 2025 | CY 2024 BEFF Health-DepED-R7-Cebu-04 | CY 2024 BEFF Health-DepED-R7-Cebu-04 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 22, 2024 | September 30, 2024 | ANIELTHON CONSTRUCTION & SUPPLY
SCHOOL HEALTH FACILITIES 2024 | Region VII | Cebu | 119192 | Francisco S. Villamor Sr.Elementary School | CARMEN | 5th | 1 | - | Construction of School Clinic | 2810788.92 | - | 2780858.27 | completed | 1 | February 5, 2025 | February 5, 2025 | CY 2024 BEFF Health-DepED-R7-Cebu-05 | CY 2024 BEFF Health-DepED-R7-Cebu-05 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 22, 2024 | September 30, 2024 | GOLDEN HAMMER CONSTRUCTION & SUPPLY
SCHOOL HEALTH FACILITIES 2024 | Region VII | CEBU | 119445 | MALABUYOC CES | MALABUYOC | 7th | 1 | - | Construction of School Clinic | 2726233.05 | - | 2696590.22 | completed | 1 | February 5, 2025 | February 5, 2025 | CY 2024 BEFF Health-DepED-R7-Cebu-06 | CY 2024 BEFF Health-DepED-R7-Cebu-06 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 22, 2024 | September 30, 2024 | HERO CONSTRUCTION & DEV'T CORP
SCHOOL HEALTH FACILITIES 2024 | Region VII | Guihulngan City | 120245 | Hilaitan ES | CITY OF GUIHULNGAN | 1st | 1 | - | Clinic & Watsan | 3525668.96 | - |  | not yet started | 0
SCHOOL HEALTH FACILITIES 2024 | Region VII | Siquijor | 190004 | Cangmunag Elementary School | SAN JUAN | Lone | 1 | - | Construction of Hanwashing Facilities | 200898.19 | - | 188138.49 | completed | 1 | August 21, 2024 | January 6, 2025 | 10336657 | 2023-88 | November 20, 2023 | November 28, 2023 | December 11, 2023 | December 12, 2023 | May 21, 2024 | Quicksilver Construction
SCHOOL HEALTH FACILITIES 2024 | Region VII | Siquijor | 190004 | Cangmunag Elementary School | SAN JUAN | Lone |  | - | Construction of School Clinic | 3010654.85 | - | 2153178.16 | completed | 1 | August 21, 2024 | January 6, 2025 | 10336657 | 2023-88 | November 20, 2023 | November 28, 2023 | December 11, 2023 | December 12, 2023 | May 21, 2024 | Quicksilver Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117929 | Alburquerque Central ES | Alburquerque | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117930 | Bahi Primary School | Alburquerque | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117933 | Dangay ES | Alburquerque | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117934 | Tagbuane ES | Alburquerque | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117935 | Toril ES | Alburquerque | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117953 | Anda Central ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117954 | Bacong ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117955 | Badiang ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117957 | Candabong ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117958 | Casica PS | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117961 | Londag ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117963 | Porcenas ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117964 | Talisay ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117966 | Virgen ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 186509 | Suba PS | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 302812 | Badiang NHS | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 302829 | Candabong National High School | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118012 | Batuan Central ES | Batuan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118018 | Cantigdas Elementary School | Batuan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118020 | Janlud ES | Batuan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118025 | Rosariohan ES | Batuan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118026 | Sta. Cruz ES | Batuan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118184 | Bacani ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118185 | Bogtongbod ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118186 | Bonbon Elementary School | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118188 | Buacao ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118189 | Buangan ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118190 | Cabog ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118191 | Caboy ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118192 | Cantoyoc PS | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118193 | Clarin Central ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118195 | Lajog ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118197 | Nahawan ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118201 | Canapnapan PS | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118202 | Cancatac ES | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118203 | Corella Central ES | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118204 | Sambog ES | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118205 | Tanday ES | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 186510 | Pandol Primary School | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 500212 | Canangcaan Integrated School | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118206 | Cortes Central ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118207 | Dela Paz ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118208 | Fatima ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118209 | Loreto ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118210 | Lourdes ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118211 | Malayo ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118216 | San Roque ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118218 | Babag ES | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118219 | Cagawasan ES | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118220 | Caluasan ES | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118221 | Candelaria ES | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118222 | Can-oling ES | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118223 | Dagohoy Central Elementary | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118227 | Mahayag Elementary School | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118228 | Malitbog Elementary School | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118630 | Abehilan ES | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118634 | Caimbang ES | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118635 | Cambansag Elementary | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118636 | Candungao ES | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118638 | Cansague Sur ES | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118641 | San Isidro Central ES | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 312327 | Candungao High School | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118660 | Bayawahan ES | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118663 | Calinginan Norte Elementary School | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118665 | Cambagui ES | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118668 | Lagtangan ES | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118671 | Magsaysay ES | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118672 | Sevilla Central ES | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 302903 | Sevilla National High School | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 302904 | Cambagui-Calinginan Norte National HS | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 312310 | Bayawahan National High School | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118699 | Cambuac Sur ES | Sikatuna | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118700 | Sikatuna Central ES | Sikatuna | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 |  | Completed | 1 | [5 empty] | 2022-06-03 | 2022-06-15
SCHOOL HEALTH FACILITIES 2022 | Region VII | Negros Oriental | 120431 | Jose R. Remollo ES (Cambaloctot ES) | San Jose | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 193423.04 | BATCH 1 | 192459.09 | Completed | 1 | 2022-11-30 |  |  |  | 03/28/22; 07/04/22 | 04/6/22; 07/12/22 | 4/18/22; 07/25/22 | 2022-08-09 | 2022-10-21 | Sagittarius Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Negros Oriental | 120438 | Siapo Elementary School | San Jose | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 79744.75 | BATCH 1 | 78628.58 | Completed | 1 | 2022-11-30 |  |  |  | 03/28/22; 07/04/22 | 04/6/22; 07/12/22 | 4/18/22; 07/25/22 | 2022-08-09 | 2022-10-21 | Sagittarius Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Negros Oriental | 303278 | Crisostomo O. Retes National High School | San Jose | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF THREE (3) UNITS GROUP HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 218188.87 | BATCH 1 | 217530.71 | Completed | 1 | 2022-12-15 |  |  |  | 03/28/22; 07/04/22 | 04/6/22; 07/12/22 | 4/18/22; 07/25/22 | 2022-08-09 | 2022-10-21 | Sagittarius Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 120658 | Enrique Villanueva Central Elementary School | Larena | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 303303 | BASAC NATIONAL HIGH SCHOOL | Larena | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 501427 | Larena Integrated School | Larena | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 184826.54 | BATCH 1 | 176198.13 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 120669 | Candaping Elementary School | Maria | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 303304 | Candaping National High School | MARIA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 501429 | Maria Integrated School | Maria | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 120699 | Catulayan Elementary School | San Juan | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 303300 | Tambisan National High School | San Juan | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 184826.54 | BATCH 1 | 176198.13 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 303305 | Catulayan National High School | San Juan | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 501430 | San Juan Integrated School | San Juan | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 184826.54 | BATCH 1 | 176198.13 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 118866 | Alcantara Central ES | ALCANTARA | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 439726 | BATCH 2 |  | COMPLETED | 1 | 2023-04-12 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Ten twenty allied developers
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 118868 | Candabong ES | ALCANTARA | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 439726 | BATCH 2 |  | COMPLETED | 1 | 2023-04-12 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Ten twenty allied developers
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 187004 | Palanas ES | ALCANTARA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 219863 | BATCH 2 |  | COMPLETED | 1 | 2023-04-12 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Ten twenty allied developers
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 302922 | Alcantara NHS | ALCANTARA | 2 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION B - WITH ROOFING) | 657930 | BATCH 2 |  | COMPLETED | 1 | 2023-04-12 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Ten twenty allied developers
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 302922 | Alcantara NHS | ALCANTARA | 2 |  | 1 | PROPOSED CONSTRUCTION OF SCHOOL CLINIC | 2558274.37 | BATCH 2 |  | Completed | 1 | 2023-04-12 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Ten twenty allied developers
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 500649 | Cabadiangan Integrated School | ALCANTARA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 2A - WITH WATER CONTAINER, WITHOUT ROOFING) | 89547.33 | BATCH 2 |  | COMPLETED | 1 | 2023-04-12 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Ten twenty allied developers
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 302918 | Nug-as NHS | ALCOY | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION B - WITH ROOFING) | 219310 | BATCH 2 |  | COMPLETED | 1 | 2023-03-13 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | GCATZ Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 500650 | Pasol-Pugalo IS | ALCOY | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 219863 | BATCH 2 |  | COMPLETED | 1 | 2023-03-13 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | GCATZ Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119132 | Lunop ES | BOLJOON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 219863 | BATCH 2 |  | COMPLETED | 1 | 2023-03-13 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | GCATZ Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 302944 | Lunop NHS | BOLJOON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION B - WITH ROOFING) | 219310 | BATCH 2 |  | COMPLETED | 1 | 2023-03-13 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | GCATZ Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119404 | Kabatuan ES | GINATILAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 219863 | BATCH 2 |  | COMPLETED | 1 | 2023-04-12 |  | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Ten twenty allied Developers
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 500894 | Ginatilan Integrated School | GINATILAN | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 289269.18 | BATCH 2 |  | COMPLETED | 1 | 2023-04-12 |  | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Ten twenty allied Developers
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 500894 | Ginatilan Integrated School | GINATILAN | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Installation of Overhead water tank and Cistern tank with Solar - Powered Submersible Water Pump) | 1325497.29 | BATCH 2 |  | COMPLETED | 1 | 2023-04-12 |  | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Ten twenty allied Developers
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119445 | Malabuyoc Central ES | MALABUYOC | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF THREE (3) UNITS GROUP HANDWASHING FACILITY OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH & ONE UNIT OPTION 1A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH | 576528.38 | BATCH 2 |  | COMPLETED | 1 | 2023-04-12 |  | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Ten twenty allied Developers
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119446 | Mindanao ES | MALABUYOC | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 2A - WITH WATER CONTAINER, WITHOUT ROOFING) | 89547.33 | BATCH 2 |  | COMPLETED | 1 | 2023-04-12 |  | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Ten twenty allied Developers
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119601 | Ronda Central ES | RONDA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 162952.68 | BATCH 2 |  | Completed | 1 | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | M.P. Sorela Const. & Supply & Marine Services
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119601 | Ronda Central ES | RONDA | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Installation of Overhead water tank and Cistern tank with Solar - Powered Submersible Water Pump) | 1325497.29 | BATCH 2 |  | Completed | 1 | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | M.P. Sorela Const. & Supply & Marine Services
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119602 | Sta. Cruz ES | RONDA | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 289269.18 | BATCH 2 |  | Completed | 1 | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | M.P. Sorela Const. & Supply & Marine Services
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119602 | Sta. Cruz ES | RONDA | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Installation of Overhead water tank and Cistern tank with Solar - Powered Submersible Water Pump) | 1325497.29 | BATCH 2 |  | Completed | 1 | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | M.P. Sorela Const. & Supply & Marine Services
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 303034 | Ronda NHS- Langin NHS Ext. | RONDA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 3B - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 162432.34 | BATCH 2 |  | Completed | 1 | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Tri-bairn Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 303034 | Ronda NHS- Langin NHS Ext. | RONDA | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Installation of Overhead water tank and Cistern tank with Solar - Powered Submersible Water Pump) | 1325497.29 | BATCH 2 |  | Completed | 1 | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Tri-bairn Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 303034 | Ronda NHS- Langin NHS Ext. | RONDA | 2 |  | 1 | PROPOSED CONSTRUCTION OF SCHOOL CLINIC | 2558274.37 | BATCH 2 |  | Completed | 1 | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Tri-bairn Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119613 | Samboan Central ES | SAMBOAN | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 289269.18 | BATCH 2 |  | COMPLETED | 1 | 2023-03-13 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | GCATZ Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 303090 | Samboan NHS | SAMBOAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION B - WITH ROOFING) | 219310 | BATCH 2 |  | COMPLETED | 1 | 2023-03-13 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | GCATZ Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119860 | Puertobello ES | TUDELA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 239863 | BATCH 2 |  | Completed | 1 | 2023-04-12 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Barr steel Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 303080 | Puertobello NHS | TUDELA | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION B - WITH ROOFING) | 478620 | BATCH 2 |  | Completed | 1 | 2023-04-12 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Barr steel Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 303080 | Puertobello NHS | TUDELA | 2 |  | 2 | PROPOSED CONSTRUCTION OF SCHOOL CLINIC | 2808274.37 | BATCH 2 |  | Completed | 1 | 2023-04-12 |  | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | October 14, 2022 | October 24, 2022 | Novembe 7, 2022 | November 21, 2022 | 2023-01-05 | Barr steel Construction

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%