## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2 | Unnamed: 43 | Status as of July 4, 2025
ELECTRIFICATION 2017 | Region VIII | Borongan City | 122400 | Canyupay ES | CITY OF BORONGAN (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 245013.26 | 216888.33 | COMPLETED | 1 | February 19, 2018 | February 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID BORONGAN-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | Ootober 10, 2018 | October 20, 2018 | November 3, 2018 | November 6, 2018 | November 13, 2018 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122324 | Aguinaldo ES | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 190242.77 | 190117.84 | COMPLETED | 1 | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122330 | Cagsalay ES | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 228038.08 | 227972.11 | COMPLETED | 1 | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122331 | Campacion ES | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 171252.93 | 171187.07 | COMPLETED | 1 | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122333 | Casidman Elementary School | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 189411.34 | 189359.73 | COMPLETED | 1 | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192501 | Inayawan Elementary School | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 168654.72 | 168550.02 | COMPLETED | 1 | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122336 | Macarthur Elementary School | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 245013.26 | 245004.03 | COMPLETED | 1 | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122339 | Tibalawon Elementary School | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 186392.77 | 186272.45 | COMPLETED | 1 | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122409 | Baruk ES | CAN-AVID | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 544518.25 | 541551.01 | COMPLETED | 1 | February 23, 2018 | February 28, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 8 | CY 2017 BEFF ELECTRIFICATION-08 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122411 | Caghalong PS | CAN-AVID | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 232283.83 | 231539.61 | COMPLETED | 1 | February 23, 2018 | February 28, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 8 | CY 2017 BEFF ELECTRIFICATION-08 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122422 | Obong PS | CAN-AVID | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 190108.9 | 189894.16 | COMPLETED | 1 | February 23, 2018 | February 28, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 8 | CY 2017 BEFF ELECTRIFICATION-08 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122447 | Cabago-an ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 470006.38 | 468983.99 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192511 | Cagdanao ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 324124.37 | 322963.97 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122448 | Cagtabon ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 168114.82 | 167079.73 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122431 | Del Pilar ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220455.4 | 219357.17 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122452 | Gap-ang ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 451823.73 | 450882.22 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122464 | Osmena ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 380236.45 | 379219.99 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122465 | Pasak ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 303437.3 | 302457.68 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192505 | Quiatan ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 312518.47 | 311425.1 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122437 | San Isidro ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 392961.69 | 392337.8 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122440 | San Vicente ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 306873.58 | 305536.52 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122468 | Sta. Catalina PS | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 195849.99 | 195417.5 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122443 | Tamsion PS | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 170447.81 | 169561.23 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122469 | Tan-awan ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 401627.55 | 401330.72 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122472 | Villahermosa ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 477742.36 | 463065.91 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122474 | Alang-alang PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 178353.68 | 175579.75 | COMPLETED | 1 | February 23, 2018 | May 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122478 | Calutan PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 187667.44 | 185690.89 | COMPLETED | 1 | February 23, 2018 | May 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192502 | Inu-olanguhan PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 168161.09 | 166401.15 | COMPLETED | 1 | February 23, 2018 | May 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122487 | Limbujan PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 180596.25 | 177094.53 | COMPLETED | 1 | February 23, 2018 |  | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122495 | Quirino PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 189824.69 | 187618.8 | COMPLETED | 1 | February 23, 2018 |  | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122496 | Roxas PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 178540.55 | 174356.4 | COMPLETED | 1 | February 23, 2018 |  | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122500 | San Roque PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 195849.99 | 193314.86 | COMPLETED | 1 | February 23, 2018 | May 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122515 | Pres. Roxas ES | GIPORLOS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 323898.08 | 321889.96 | COMPLETED | 1 | February 23, 2018 | January 10, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 10 | CY 2017 BEFF ELECTRIFICATION-10 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122517 | San Miguel ES | GIPORLOS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 224354.54 | 222851.21 | COMPLETED | 1 | February 23, 2018 | January 10, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 10 | CY 2017 BEFF ELECTRIFICATION-10 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122534 | Banahao ES | GUIUAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 502965.21 | 487057.72 | COMPLETED | 1 | February 23, 2018 | March 12. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122547 | San Antonio PS | GUIUAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 169079.12 | 167041.65 | COMPLETED | 1 | February 23, 2018 | March 12. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192519 | San Juan ES | GUIUAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 224354.54 | 220289.21 | COMPLETED | 1 | February 23, 2018 | March 12. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192518 | Tagporo ES | GUIUAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 176549.25 | 173008.14 | COMPLETED | 1 | February 23, 2018 | March 12. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122553 | Trinidad ES | GUIUAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 558391.64 | 542422.31 | COMPLETED | 1 | February 23, 2018 | March 12. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122477 | Cacatmonan PS | HERNANI | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 169583.63 | 169573.57 | COMPLETED | 1 | February 23, 2018 | January 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122573 | Casapa PS | JIPAPAD | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 224661.33 | 222563.84 | COMPLETED | 1 | February 23, 2018 | March 10, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 2 | CY 2017-BEFF ELECTRIFICATION-02 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122576 | Jiwaran PS | JIPAPAD | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 224988.77 | 218797.18 | COMPLETED | 1 | February 23, 2018 | February 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 2 | CY 2017-BEFF ELECTRIFICATION-02 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122577 | Mabuhay ES | JIPAPAD | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 312132.55 | 307690.63 | COMPLETED | 1 | February 23, 2018 | January 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 2 | CY 2017-BEFF ELECTRIFICATION-02 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122580 | Recare ES | JIPAPAD | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233222.41 | 230211.41 | COMPLETED | 1 | February 23, 2018 | February 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 2 | CY 2017-BEFF ELECTRIFICATION-02 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122581 | Roxas ES | JIPAPAD | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 329283.85 | 325845.74 | COMPLETED | 1 | February 23, 2018 | January 5, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 2 | CY 2017-BEFF ELECTRIFICATION-02 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122582 | San Roque ES | JIPAPAD | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 459544.25 | 456790.07 | COMPLETED | 1 | February 23, 2018 | January 5, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 2 | CY 2017-BEFF ELECTRIFICATION-02 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122352 | San Isidro PS | LAWAAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 195849.99 | 184256.29 | COMPLETED | 1 | February 23, 2018 | February 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 10 | CY 2017 BEFF ELECTRIFICATION-10 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122466 | San Miguel Elementary School | MASLOG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 408495.62 | 218703.93 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192515 | Taytay PS | MASLOG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 222349.09 | 407901.96 | COMPLETED | 1 | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122615 | Del Pilar ES | MAYDOLONG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223783.25 | 220221.96 | COMPLETED | 1 | February 23, 2018 | January 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122629 | San Gabriel ES | MAYDOLONG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 303314.44 | 303180.18 | COMPLETED | 1 | February 23, 2018 | February 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122630 | Tagasli-an Elementary School | MAYDOLONG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 298329.53 | 297876.2 | COMPLETED | 1 | February 23, 2018 | March 10, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122535 | Banuyo ES | MERCEDES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 372480.66 | 368930.21 | COMPLETED | 1 | February 23, 2018 | March 2, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122539 | Cabunga-an PS | MERCEDES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 170555.27 | 166401.15 | COMPLETED | 1 | February 23, 2018 | March 2, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122550 | San Roque PS | MERCEDES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 299085.39 | 295990.11 | COMPLETED | 1 | February 23, 2018 | March 2, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122652 | Agsam ES | ORAS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 553874.61 | 551425.2 | COMPLETED | 1 | February 23, 2018 | January 28, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 9 | CY 2017 BEFF ELECTRIFICATION-09 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122653 | Alang-alang PS | ORAS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 234478.86 | 233406.1 | COMPLETED | 1 | February 23, 2018 | January 28, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 9 | CY 2017 BEFF ELECTRIFICATION-09 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122655 | Balingasag ES | ORAS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 392928.66 | 391826.62 | COMPLETED | 1 | February 23, 2018 | February. 12, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 9 | CY 2017 BEFF ELECTRIFICATION-09 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122664 | Gamot PS | ORAS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 219556.54 | 219231.1 | COMPLETED | 1 | February 23, 2018 | January 28, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 9 | CY 2017 BEFF ELECTRIFICATION-09 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122667 | Naga ES | ORAS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 323913.65 | 323005.83 | COMPLETED | 1 | February 23, 2018 | March 3, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 9 | CY 2017 BEFF ELECTRIFICATION-09 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122669 | Rizal ES | ORAS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 469541.73 | 468171.17 | COMPLETED | 1 | February 23, 2018 | March 3, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 9 | CY 2017 BEFF ELECTRIFICATION-09 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122677 | Cambilla ES | QUINAPONDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 230252.7 | 227259.16 | COMPLETED | 1 | February 23, 2018 | April 2. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 10 | CY 2017 BEFF ELECTRIFICATION-10 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122678 | Cantinio PS | QUINAPONDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 168901.65 | 165760.65 | COMPLETED | 1 | February 23, 2018 | April 12, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 10 | CY 2017 BEFF ELECTRIFICATION-10 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122717 | Maliwaliw ES | SALCEDO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 336540.42 | 334891.69 | COMPLETED | 1 | February 23, 2018 | February 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 10 | CY 2017 BEFF ELECTRIFICATION-10 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122735 | Bangon PS | SAN POLICARPO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 170555.27 | 170545.05 | COMPLETED | 1 | February 23, 2018 | March 12, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122743 | Sta. Cruz ES | SAN POLICARPO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 218776.35 | 218760.39 | COMPLETED | 1 | February 23, 2018 | March 12, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122748 | Kandalakit ES | SULAT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 186023.48 | 185937.19 | COMPLETED | 1 | February 23, 2018 | March 18, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122749 | Mabini ES | SULAT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 387754.43 | 386510.7 | COMPLETED | 1 | February 23, 2018 | March 18, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122760 | Beto PS | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 213897.81 | 213573.35 | COMPLETED | 1 | February 23, 2018 | march 17. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122762 | Bongdo PS | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 241138.48 | 240935.86 | COMPLETED | 1 | February 23, 2018 | April 2, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122764 | Danao ES | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 225506.12 | 225292.14 | COMPLETED | 1 | February 23, 2018 | march 17. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122765 | Del Remedios ES | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 308879.48 | 308702.32 | COMPLETED | 1 | February 23, 2018 | march 17. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122766 | Gayam PS | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 169344.07 | 169217.01 | COMPLETED | 1 | February 23, 2018 | April 2, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192509 | Pangabutan PS | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 227008.72 | 226483.9 | COMPLETED | 1 | February 23, 2018 | February 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 8 | CY 2017 BEFF ELECTRIFICATION-08 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122774 | San Rafael PS | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243122.67 | 242352.21 | COMPLETED | 1 | February 23, 2018 | march 17. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 8 | CY 2017 BEFF ELECTRIFICATION-08 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Baybay City | 344593 | Baybay City Senior High School | CITY OF BAYBAY | 5 | 1 | UPGRADING | 2 | 1700496.67 |  | COMPLETED | 1 |  |  |  |  | 2018-05-28 | 2018-06-20 | 2018-06-25 | 2018-07-11 | 2018-07-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Baybay City | 313323 | Ciabu National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING | 2 | 2390942.48 |  | COMPLETED | 1 |  |  |  |  | 2018-05-28 | 2018-06-20 | 2018-06-25 | 2018-07-11 | 2018-07-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Baybay City | 313312 | Mailhi National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING | 2 | 2680839.11 |  | COMPLETED | 1 |  |  |  |  | 2018-05-28 | 2018-06-20 | 2018-06-25 | 2018-07-11 | 2018-07-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 313202 | Biliran Science High School | BILIRAN | 0 | 1 | UPGRADING | 2 | 1482557.79 | 1471181.88 | COMPLETED | 1 | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | W.B ALAGAO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 303322 | Cabucgayan National School of Arts and Trade | CABUCGAYAN | 0 | 1 | UPGRADING | 2 | 4379481.59 | 4345813.3 | COMPLETED | 1 | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | QYT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 303328 | Manlabang National High School | CAIBIRAN | 0 | 1 | UPGRADING | 2 | 4368287.45 | 4,304,00.00 | COMPLETED | 1 | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | J.CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 303324 | Culaba NVS | CULABA | 0 | 1 | UPGRADING | 2 | 4315524.95 | 4273054.68 | COMPLETED | 1 | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | MKB BUILDERS & SUPPY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 303327 | Lucsoon NHS | NAVAL (Capital) | 0 | 1 | UPGRADING | 2 | 1573233.98 | 1554689.64 | COMPLETED | 1 | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | A & B ENTERPRISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 303330 | Naval National High School | NAVAL (Capital) | 0 | 1 | UPGRADING | 2 | 3051257.34 | 3017616 | COMPLETED | 1 | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | MB ANG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 303331 | Naval School of Fisheries | NAVAL (Capital) | 0 | 1 | UPGRADING | 2 | 4724556.18 | 4685748.31 | COMPLETED | 1 | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | BNL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Borongan City | 313504 | Benowangan NHS (Lalawigan NHS - Benowangan Annex) | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | 1 | 1481515.29 | 1468931.48 | COMPLETED | 1 | July 4, 2019 |  | CY 2018 BEFF - ELECTRIFICATION OF UNENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 BORONGAN CITY - LOT 2 | CY 2018 - BEFF ELECTRIFICATION - 02 | February 26, 2018 | March 7, 2018 | March 20, 2018 | March 26, 2018 | March 29, 2018 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Borongan City | 313515 | E. Samar NCHS - Supt. Fidel E. Anacta, Sr. MHS Annex | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | 1 | 2534404.17 | 2501753.8 | COMPLETED | 1 | July 4, 2020 |  | CY 2018 BEFF - ELECTRIFICATION OF UNENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 BORONGAN CITY - LOT 3 | CY 2018 - BEFF ELECTRIFICATION - 03 | February 26, 2018 | March 7, 2018 | March 20, 2018 | March 26, 2018 | March 29, 2018 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Borongan City | 303526 | Maypangdan NHS | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | 1 | 2514611.87 | 2482032.29 | COMPLETED | 1 | July 4, 2018 |  | CY 2018 BEFF - ELECTRIFICATION OF UNENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 BORONGAN CITY - LOT 1 | CY 2018 - BEFF ELECTRIFICATION - 01 | February 26, 2018 | March 7, 2018 | March 20, 2018 | March 26, 2018 | March 29, 2018 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Calbayog City | 500807 | Bagacay Integrated School | CALBAYOG CITY | 1 | 1 | UPGRADING | 2 | 2360813.61 |  | COMPLETED | 1 |  |  | CAL ESUP CY2018 B2 | CAL ESUP CY2018 B2 | 2018-04-20 | 2018-04-21 | 2018-05-11 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Calbayog City | 303644 | Mag-Ubay National High School | CALBAYOG CITY | 1 | 1 | UPGRADING | 1 | 978107.61 |  | COMPLETED | 1 |  |  | CAL ESUP CY2018 B1 | CAL ESUP CY2018 B1 | 2018-04-21 | 2018-04-20 | 2018-05-11 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Calbayog City | 303645 | Malaga National High School | CALBAYOG CITY | 1 | 1 | UPGRADING | 1 | 1485553.14 |  | COMPLETED | 1 |  |  | CAL ESUP CY2018 B2 | CAL ESUP CY2018 B1 | 2018-04-21 | 2018-04-20 | 2018-05-11 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Calbayog City | 303646 | Oquendo National High School | CALBAYOG CITY | 1 | 1 | UPGRADING | 1 | 1195826.77 |  | COMPLETED | 1 |  |  | CAL ESUP CY2018 B3 | CAL ESUP CY2018 B1 | 2018-04-21 | 2018-04-20 | 2018-05-11 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Catbalogan City | 313701 | Catbalogan NCHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | 1 | 907149.62 | 892311.17 | COMPLETED | 1 |  |  | CY 2018- BEFF- ESUP- R8 - CC- L3 |  | 2018-07-05 | 2018-07-13 | 2018-08-01 | 2018-09-03 | 2018-09-28 | RNA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Catbalogan City | 313706 | Pangdan National High School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | 1 | 978526.9 | 933000 | COMPLETED | 1 |  |  | CY 2018- BEFF- ESUP- R8 - CC- L2 |  | 2018-07-05 | 2018-07-13 | 2018-08-01 | 2018-09-16 | 2018-10-05 | J .Custorio Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Catbalogan City | 303623 | Silanga NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | 1 | 967974.4 | 953285.25 | COMPLETED | 1 |  |  | CY 2018- BEFF- ESUP- R8 - CC- L1 |  | 2018-07-05 | 2018-07-13 | 2018-08-01 | 2018-08-20 | 2018-08-31 | WC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 313501 | Can-avid National High School | CAN-AVID | 0 | 1 | UPGRADING | 2 | 3376983.67 |  | COMPLETED | 1 |  |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2 ESAMAR-LOT 2 - REBID | CY 2018-BEFF ELECTRIFICATION-02 | 2018-06-04 | 2018-06-14 | 2018-06-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | GIPORLOS | 0 | 1 | UPGRADING | 2 | 2850070.88 |  | COMPLETED | 1 |  |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2 ESAMAR-LOT 1 | CY 2018-BEFF ELECTRIFICATION-01 | 2018-04-16 | 2018-03-11 | 2018-05-31 |  |  | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303510 | Jipapad NHS | JIPAPAD | 0 | 1 | UPGRADING | 1 | 1899932.73 | 1883623.09 | COMPLETED | 1 | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 4 | CY 2018-BEFF ELECTRIFICATION-04 | March 16, 2018 | March 26, 2018 | April 10, 2018 | Arpil 17, 2018 | April 20, 2018 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303518 | Mercedes HS | MERCEDES | 0 | 1 | UPGRADING | 1 | 2174089.73 | 2133791.35 | COMPLETED | 1 | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 5 | CY 2018-BEFF ELECTRIFICATION-05 | March 16, 2018 | March 26, 2018 | April 10, 2018 | Arpil 17, 2018 | April 20, 2018 | DAY-BREAK ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303520 | Oras National High School | ORAS | 0 | 1 | UPGRADING | 2 | 2549376.4 |  | COMPLETED | 1 |  |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2 ESAMAR-LOT 3- REBID | CY 2018-BEFF ELECTRIFICATION-03 | 2018-06-04 | 2018-06-14 | 2018-06-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303516 | Matarinao SOF | SALCEDO | 0 | 1 | UPGRADING | 1 | 2480957.29 | 2443569.47 | COMPLETED | 1 | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 3 | CY 2018-BEFF ELECTRIFICATION-03 | March 16, 2018 | March 26, 2018 | April 10, 2018 | Arpil 17, 2018 | April 20, 2018 | DAY-BREAK ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303524 | San Julian NHS | SAN JULIAN | 0 | 1 | UPGRADING | 1 | 2683247.19 | 2659952.85 | COMPLETED | 1 | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 1 | CY 2018-BEFF ELECTRIFICATION-01 | March 16, 2018 | March 26, 2018 | April 10, 2018 | Arpil 17, 2018 | April 20, 2018 | LOBRIÑO'S CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303527 | Sulat NHS | SULAT | 0 | 1 | UPGRADING | 1 | 3227556.88 | 3199782.49 | COMPLETED | 1 | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 2 | CY 2018-BEFF ELECTRIFICATION-02 | March 16, 2018 | March 26, 2018 | April 10, 2019 | Arpil 17, 2018 | April 20, 2018 | LOBRIÑO'S CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303336 | Alangalang National High School | ALANGALANG | 1 | 1 | UPGRADING | 2 | 6177826.74 | 6036005.25 | COMPLETED | 1 |  |  | lot 5-cy-2018-E-B2-leyte | lot 5-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313398 | Borseth National High School | ALANGALANG | 1 | 1 | UPGRADING | 3 | 1190462.69 |  | COMPLETED | 1 | [9 empty] | FM4 BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303343 | Juan S. Tismo National High School (Babatngon National High School) | BABATNGON | 1 | 1 | UPGRADING | 2 | 1982220.18 | 1935484.34 | COMPLETED | 1 |  |  | lot 6-cy-2018-E-B2-leyte | lot 6-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | MJM BUILDERS AND INTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121736 | Anahaway Elementary School | PALO | 1 | 1 | UPGRADING | 3 | 591708.82 |  | COMPLETED | 1 | [9 empty] | FOUR K BUILDERS & CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303339 | Anahaway National High School | PALO | 1 | 1 | UPGRADING | 3 | 1277292.87 |  | COMPLETED | 1 | [9 empty] | CAFRENCILLO ARCH DESIGN & BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121738 | Canhidoc Elementary School | PALO | 1 | 1 | UPGRADING | 3 | 666114.39 |  | COMPLETED | 1 | [9 empty] | LJPM BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121739 | Capirawan Elementary School | PALO | 1 | 1 | UPGRADING | 3 | 610371.35 |  | COMPLETED | 1 | [9 empty] | FOUR K BUILDERS & CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121740 | Castilla ElementarySchool | PALO | 1 | 1 | UPGRADING | 3 | 586218.65 |  | COMPLETED | 1 | [9 empty] | CAFRENCILLO ARCH DESIGN & BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121741 | Gacao Elementary School | PALO | 1 | 1 | UPGRADING | 3 | 622190.03 |  | COMPLETED | 1 | [9 empty] | FOUR K BUILDERS & CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121742 | Luntad Elementary School | PALO | 1 | 1 | UPGRADING | 3 | 772659.86 |  | COMPLETED | 1 | [9 empty] | LJPM BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121743 | Palo I Central School | PALO | 1 | 1 | UPGRADING | 3 | 2496173.72 |  | COMPLETED | 1 | [9 empty] | HD GOLDEN BUILDERS & SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303415 | Palo National High School | PALO | 1 | 1 | UPGRADING | 2 | 1967538.7 | 1922728.25 | COMPLETED | 1 |  |  | lot 7-cy-2018-E-B2-leyte | lot 7-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | HD GOLDEN BULDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121744 | Salvacion Elementary School | PALO | 1 | 1 | UPGRADING | 3 | 399138.7 |  | COMPLETED | 1 | [9 empty] | LJPM BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303388 | Tanauan Sch. Of Craftsmanship & Home Industries (LIT-Tanauan Campus)Campus | TANAUAN | 1 | 1 | UPGRADING | 2 | 1690466.94 | 1658407.13 | COMPLETED | 1 |  |  | lot 9-cy-2018-E-B2-leyte | lot 9-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | J.A. CONST. AND TRADING CORP. (Formerly: J.A. Construction ) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313305 | Tanauan School of Arts and Trade | TANAUAN | 1 | 1 | UPGRADING | 2 | 1174573.79 | 1147827.61 | COMPLETED | 1 |  |  | lot 8-cy-2018-E-B2-leyte | lot 8-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | JELM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121946 | Burak Elementary School | TOLOSA | 1 | 1 | UPGRADING | 3 | 897652.53 |  | COMPLETED | 1 | [9 empty] | BENCH CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121950 | Daniel Z. Romualdez Memorial Elementary School | TOLOSA | 1 | 1 | UPGRADING | 3 | 945617.42 |  | COMPLETED | 1 | [9 empty] | BENCH CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121957 | Telegrafo Elementary School | TOLOSA | 1 | 1 | UPGRADING | 3 | 750365.63 |  | COMPLETED | 1 | [9 empty] | BENCH CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121181 | Arado Elementary School | BARAUEN | 2 | 1 | UPGRADING | 3 | 575754.28 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121154 | Burauen North Central School | BARAUEN | 2 | 1 | UPGRADING | 3 | 914305.38 |  | COMPLETED | 1 | [9 empty] | H.A.H REVERIE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121185 | Burauen South Central School | BARAUEN | 2 | 1 | UPGRADING | 3 | 766640.52 |  | COMPLETED | 1 | [9 empty] | AGB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121199 | Paghudlan Elementary School | BARAUEN | 2 | 1 | UPGRADING | 3 | 795067.68 |  | COMPLETED | 1 | [9 empty] | AGB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121205 | San Isidro Elementary School | BARAUEN | 2 | 1 | UPGRADING | 3 | 567475.63 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121177 | Toloyao Elementary School | BARAUEN | 2 | 1 | UPGRADING | 3 | 513506.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121179 | Villa Rosas Elementary School | BARAUEN | 2 | 1 | UPGRADING | 3 | 855843.81 |  | COMPLETED | 1 | [9 empty] | H.A.H REVERIE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313324 | Barugo National High School | BARUGO | 2 | 1 | UPGRADING | 3 | 2013502.03 |  | COMPLETED | 1 | [9 empty] | FM4 BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303357 | Calingcaguing National High School | BARUGO | 2 | 1 | UPGRADING | 3 | 1213545.38 |  | COMPLETED | 1 | [9 empty] | FM4 BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303363 | Celestino De Guzman Memorial National High School | BARUGO | 2 | 1 | UPGRADING | 2 | 1788212.64 | 1762836.24 | COMPLETED | 1 |  |  | lot 10-cy-2018-E-B2-leyte | lot 10-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | FJ. TIU & ASSOCIATES CONSTRUCTION & DEVELOPMENT CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303433 | Sta. Rosa National High School | BARUGO | 2 | 1 | UPGRADING | 3 | 1876187.49 |  | COMPLETED | 1 | [9 empty] | FM4 BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303341 | Asuncion S. Melgar National High School | CAPOOCAN | 2 | 1 | UPGRADING | 2 | 1715056.46 | 1677900.42 | COMPLETED | 1 |  |  | lot 11-cy-2018-E-B2-leyte | lot 11-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303418 | Pinamopoan National High School | CAPOOCAN | 2 | 1 | UPGRADING | 3 | 1328911.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303362 | Carigara National Vocational School | CARIGARA | 2 | 1 | UPGRADING | 2 | 2036324.97 | 2000351.02 | COMPLETED | 1 |  |  | lot 13-cy-2018-E-B2-leyte | lot 13-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | LRD CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313307 | Jugaban National High School | CARIGARA | 2 | 1 | UPGRADING | 2 | 1677277.16 | 1642209.33 | COMPLETED | 1 |  |  | lot 12-cy-2018-E-B2-leyte | lot 12-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | HARDLINES BUILDERS AND SALES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121319 | Bulod Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 589524.03 |  | COMPLETED | 1 | [9 empty] | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303355 | Cabacungan National High School | DULAG | 2 | 1 | UPGRADING | 3 | 1333806.21 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121320 | Cabatoan Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 994077.4 |  | COMPLETED | 1 | [9 empty] | CAFRENCILLO ARCH DESIGN & BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121321 | Calipayan Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 576756.16 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121350 | RIZAL ELEMENTARY SCHOOL | DULAG | 2 | 1 | UPGRADING | 3 | 758435.92 |  | COMPLETED | 1 | [9 empty] | PALMERA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121331 | San Agustin Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 807290.52 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121353 | San Miguel Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 748968.36 |  | COMPLETED | 1 | [9 empty] | PALMERA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121336 | Tabu Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 577762.85 |  | COMPLETED | 1 | [9 empty] | CAFRENCILLO ARCH DESIGN & BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121337 | Tigbao Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 984888.74 |  | COMPLETED | 1 | [9 empty] | PALMERA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303387 | Leyte Agro Industrial School | LEYTE | 3 | 1 | UPGRADING | 2 | 3214202.53 | 3139000 | COMPLETED | 1 |  |  | lot 14-cy-2018-E-B2-leyte | lot 14-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303434 | Tabango National High School | TABANGO | 3 | 1 | UPGRADING | 3 | 1241888.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313322 | Cahigan NHS | VILLABA | 3 | 1 | UPGRADING | 1 | 1104935.83 | 1086973.98 | COMPLETED | 1 |  |  | lot 3-cy-2018-E-B1-leyte | lot 3-cy-2018-E-B1-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | NV& C CONSTRUCTION AND GENERAL SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313345 | Sulpa NHS | VILLABA | 3 | 1 | UPGRADING | 1 | 1232603.71 | 1198725.5 | COMPLETED | 1 |  |  | lot 4-cy-2018-E-B1-leyte | lot 4-cy-2018-E-B1-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | AGB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303442 | Villaba National Comprehensive High School | VILLABA | 3 | 1 | UPGRADING | 1 | 3162822.17 | 3098929.27 | COMPLETED | 1 |  |  | lot 2-cy-2018-E-B1-leyte | lot 2-cy-2018-E-B1-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | D.L. AUREO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303389 | Villaba NHS (LNCAST) | VILLABA | 3 | 1 | UPGRADING | 1 | 1184101.21 | 1151115.37 | COMPLETED | 1 |  |  | lot 1-cy-2018-E-B1-leyte | lot 1-cy-2018-E-B1-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | R.M. PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303368 | Dr. Geronimo B. Zaldivar Memorial School of Fisheries | ALBUERA | 4 | 1 | UPGRADING | 2 | 1655671.04 | 1616917.39 | COMPLETED | 1 |  |  | lot 15-cy-2018-E-B2-leyte | lot 15-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | BENCH CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303406 | Matlang National High School | ISABEL | 4 | 1 | UPGRADING | 2 | 2134188.44 | 2091336.37 | COMPLETED | 1 |  |  | lot 16-cy-2018-E-B2-leyte | lot 16-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | MAGA CONSTRUTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313306 | Palompon National High School | PALOMPON | 4 | 1 | UPGRADING | 3 | 1962688.7 |  | COMPLETED | 1 | [9 empty] | BCG DESIGN & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313315 | San Guillermo National High School | PALOMPON | 4 | 1 | UPGRADING | 3 | 1547694.85 |  | COMPLETED | 1 | [9 empty] | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303373 | Hampipila National High School | ABUYOG | 5 | 1 | UPGRADING | 3 | 1345005.47 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303365 | Concepcion National High School | HILONGOS | 5 | 1 | UPGRADING | 3 | 1493207.13 |  | COMPLETED | 1 | [9 empty] | JAMT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5 | 1 | UPGRADING | 2 | 1666610.71 | 1619847.86 | COMPLETED | 1 |  |  | lot 17-cy-2018-E-B2-leyte | lot 17-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303431 | Sta. Margarita National High School | HILONGOS | 5 | 1 | UPGRADING | 3 | 1978115.07 |  | COMPLETED | 1 | [9 empty] | JAMT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303379 | Javier National High School | JAVIER (BUGHO) | 5 | 1 | UPGRADING | 3 | 1504649.55 |  | COMPLETED | 1 | [9 empty] | VITHS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303356 | Cahagnaan National High School | MATALOM | 5 | 1 | UPGRADING | 2 | 1673096.47 | 1636201.66 | COMPLETED | 1 |  |  | lot 18-cy-2018-E-B2-leyte | lot 18-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313337 | Sta. Paz Integrated School | MATALOM | 5 | 1 | UPGRADING | 3 | 1898479.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Maasin City | 303454 | Dongon NHS | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING | 2 | 1628954.86 | 1620850.61 | COMPLETED | 1 |  |  | ELECTRIFICATION-18-6-001 | ELECTRIFICATION-18-6-001 | 2018-06-11 | 2018-06-20 | 2018-07-02 | 2018-07-18 | 2018-12-10 | DAYBREAK ENTERPRISES ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Maasin City | 323101 | Ibarra National High School | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING | 2 | 1639879.93 | 1631721.33 | COMPLETED | 1 |  |  | ELECTRIFICATION-18-6-002 | ELECTRIFICATION-18-6-002 | 2018-06-11 | 2018-06-20 | 2018-07-02 | 2018-07-18 | 2018-12-10 | DAYBREAK ENTERPRISES ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303535 | Bobon School for Philippine Craftsmen | BOBON | 1 | 1 | UPGRADING | 1 | 3153787.21 | 2636473.12 | COMPLETED | 1 |  |  | BEFF2018-B1-E-NS-L1 | BEFF2018-B1-E-NS-L1 | June 6, 2018 | June 14, 2018 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303548 | Eladio T. Balite Memorial School of Fisheries | BOBON | 1 | 1 | UPGRADING | 1 | 2555079.02 | 2237178.28 | COMPLETED | 1 |  |  | BEFF2018-B1-E-NS-L2 | BEFF2018-B1-E-NS-L2 | June 6, 2019 | June 14, 2019 | June 28, 2018 | 2018-07-25 |  | ROSS Engineering & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303541 | Catarman National High School | CATARMAN (Capital) | 1 | 1 | UPGRADING | 1 | 3833968.6 | 3205230.91 | COMPLETED | 1 |  |  | BEFF2018-B1-E-NS-L3 | BEFF2018-B1-E-NS-L3 | June 6, 2020 | June 14, 2020 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 313605 | Leonardo M. Amigo High School | MONDRAGON | 1 | 1 | UPGRADING | 1 | 1149519.71 | 996008.08 | COMPLETED | 1 |  |  | BEFF2018-B1-E-NS-L5 | BEFF2018-B1-E-NS-L5 | June 6, 2022 | June 14, 2022 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L HS | MONDRAGON | 1 | 1 | UPGRADING | 1 | 3334063.59 | 2918463.7 | COMPLETED | 1 |  |  | BEFF2018-B1-E-NS-L4 | BEFF2018-B1-E-NS-L4 | June 6, 2021 | June 14, 2021 | June 28, 2018 | 2018-07-25 |  | ROSS Engineering & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303577 | San Isidro Agro-Industrial High School | SAN ISIDRO | 1 | 1 | UPGRADING | 2 | 2694755.8 | 2252210.12 | COMPLETED | 1 |  |  | BEFF2018-B2-E-NS-L1 | BEFF2018-B2-E-NS-L1 | June 6, 2018 | June 14, 2018 | 2018-07-02 | 2018-07-25 |  | MAGA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303580 | San Jose Technical HS | SAN JOSE | 1 | 1 | UPGRADING | 2 | 2123000.01 | 1774492.2 | COMPLETED | 1 |  |  | BEFF2018-B2-E-NS-L2 | BEFF2018-B2-E-NS-L2 | June 6, 2019 | June 14, 2019 | 2018-07-02 | 2018-07-25 |  | MAGA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303556 | Laoang National Technical High School | LAOANG | 2 | 1 | UPGRADING | 2 | 2131770.4 | 2089873.18 | COMPLETED | 1 |  |  | BEFF2018-B2-E-NS-L3 | BEFF2018-B2-E-NS-L3 | June 6, 2020 | June 14, 2020 | 2018-07-02 | 2018-07-25 |  | ROSS ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303564 | Mapanas Agro-Industrial High School | MAPANAS | 2 | 1 | UPGRADING | 2 | 2634837.55 | 2202290.21 | COMPLETED | 1 |  |  | BEFF2018-B2-E-NS-L4 | BEFF2018-B2-E-NS-L4 | June 6, 2021 | June 14, 2021 | 2018-07-02 | 2018-07-25 |  | MAGA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 313609 | Cabatuan NHS | PALAPAG | 2 | 1 | UPGRADING | 1 | 954013.8 | 801753.1975 | COMPLETED | 1 |  |  | BEFF2018-B1-E-NS-L6 | BEFF2018-B1-E-NS-L6 | June 6, 2024 | June 14, 2024 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303539 | Capacujan NHS | PALAPAG | 2 | 1 | UPGRADING | 1 | 1675760.29 | 1408308.9477 | COMPLETED | 1 |  |  | BEFF2018-B1-E-NS-L6 | BEFF2018-B1-E-NS-L6 | June 6, 2023 | June 14, 2023 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 313621 | Zoilo T. Lobos Memorial High School | PAMBUJAN | 2 | 1 | UPGRADING | 1 | 1393081.21 | 1220283.63 | COMPLETED | 1 |  |  | BEFF2018-B1-E-NS-L7 | BEFF2018-B1-E-NS-L7 | June 6, 2025 | June 14, 2025 | June 28, 2018 | 2018-07-25 | 2018-08-10 | SMU Construction & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 313618 | Balnasan National High School | SAN ROQUE | 2 | 1 | UPGRADING | 1 | 1577033.76 | 1381476.98 | COMPLETED | 1 |  |  | BEFF2018-B1-E-NS-L8 | BEFF2018-B1-E-NS-L8 | June 6, 2026 | June 14, 2026 | June 28, 2018 | 2018-07-25 | 2018-08-10 | SMU Construction & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124194 | Alegria Batuan ES | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 1576999.15 |  | COMPLETED | 1 |  |  | 2018-beff-e-b2-c6 | 2018-beff-e-b2-c6 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124201 | Bagong Buhay Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 1381598.37 |  | COMPLETED | 1 |  |  | 2018-beff-e-b2-c7 | 2018-beff-e-b2-c7 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124202 | Cabintan Elementary School | Ormoc City | 4 | 1 | UPGRADING | 3 | 1293491.95 | 4495169.04 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C1 | 2018-BEFF-E-B3-C1 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | NV and C Construction and General Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 313903 | Cabintan National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 1654412.29 | 1620629.31 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c12 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | V.JYN Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124148 | Can-adieng Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 2245826.86 |  | COMPLETED | 1 |  |  | 2018-beff-e-b2-c3 | 2018-beff-e-b2-c3 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124203 | Cogon Central School | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 2757663.47 |  | COMPLETED | 1 |  |  | 2018-beff-e-b2-c2 | 2018-beff-e-b2-c2 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124177 | Concepcion Elementary School | Ormoc City | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1478463.34 | 3602646.96 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C6 | 2018-BEFF-E-B3-C6 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124150 | Dolores Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | 3 | 2493754.39 | 4495169.05 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C1 | 2018-BEFF-E-B3-C1 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | NV and C Construction and General Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303654 | Dolores National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 3007642.38 | 2957771.42 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c5 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | JB BautistaEnterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124151 | Don Carlos Rivilla Elemetary School | ORMOC CITY | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1282939.18 | 3962356.38 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C2 | 2018-BEFF-E-B3-C2 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124207 | Doña Feliza Z. Mejia Elementary School | Ormoc City | 4 | 1 | UPGRADING | 3 | 1480326.64 | 3602646.96 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C6 | 2018-BEFF-E-B3-C6 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124152 | Donghol Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | 3 | 1883203.55 | 3552520.68 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C5 | 2018-BEFF-E-B3-C5 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124153 | Gaas Elementary School | ORMOC CITY | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1277662.8 | 4495169.05 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C1 | 2018-BEFF-E-B3-C1 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | NV and C Construction and General Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303661 | Genero B. Lureñana National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 3292258.37 | 3200462.84 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c3 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | silverscket Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124178 | Guintiguian Elementary School | Ormoc City | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1582314.96 | 4614565.47 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C3 | 2018-BEFF-E-B3-C3 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124155 | Ipil Central School | ORMOC CITY | 4 | 1 | UPGRADING | 3 | 2878625.57 | 3962356.38 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C2 | 2018-BEFF-E-B3-C2 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303655 | Ipil National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 2515883.21 | 2462794.19 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c6 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | JRM Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 313906 | Julian C. Gantuangco NHS | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 1440097.15 | 1410802.45 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c14 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | JFR COnstrUction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 313901 | Lilo-an National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 2032322.68 | 1947137.8 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c10 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Tom bUilders & supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124195 | Linao Central School | Ormoc City | 4 | 1 | UPGRADING | 3 | 3128610.73 | 5180301.57 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C4 | 2018-BEFF-E-B3-C4 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Tubigan Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303656 | Linao National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 3128532.52 | 3081891.71 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c4 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Melgazo construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124160 | Mabini Elementary School | ORMOC CITY | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1293491.95 | 3962356.38 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C2 | 2018-BEFF-E-B3-C2 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124184 | Manlilinao Elementary School | Ormoc City | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1592867.72 | 3602646.96 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C6 | 2018-BEFF-E-B3-C6 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303657 | Margen National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 2153212.81 | 2121357.24 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c9 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Vhits. D.G. Builders Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 313904 | Matica-a National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 2381911.9 | 1799816.48 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c7 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Melgazo construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124196 | Naungan Elementary School | Ormoc City | 4 | 1 | UPGRADING | 3 | 2124989.86 | 5180301.57 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C4 | 2018-BEFF-E-B3-C4 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Tubigan Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303658 | New Ormoc City National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 3781284.86 | 3728200.82 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c1 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | QCC Consuction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 194501 | Ormoc City Central School | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 3776008.61 |  | COMPLETED | 1 |  |  | 2018-beff-e-b2-c1 | 2018-beff-e-b2-c1 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 313905 | Ormoc City Night High School | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 1282907.11 |  | COMPLETED | 1 |  |  | 2018-beff-e-b2-c8 | 2018-beff-e-b2-c8 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 330523 | Ormoc City Senior High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 2158792.3 | 2126853.5 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c8 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Vhits. D.G. Builders Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124197 | Ormoc City SPED Center | Ormoc City | 4 | 1 | UPGRADING | 3 | 1628071.74 | 3552520.68 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C5 | 2018-BEFF-E-B3-C5 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124167 | Patag Elementary School | ORMOC CITY | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1379888.1 | 3552520.68 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C5 | 2018-BEFF-E-B3-C5 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 313902 | Pedro G. Bañez National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 1551618.51 | 1476661.27 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c13 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Bench Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124198 | Punta Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 1674516.68 |  | COMPLETED | 1 |  |  | 2018-beff-e-b2-c5 | 2018-beff-e-b2-c5 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303660 | Rustico Capahi Sr. Memorial National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 2017943.15 | 1958299.41 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c11 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | HD Golden Buliders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124190 | San Jose Elementary School | Ormoc City | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1774189.06 | 4614565.47 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C3 | 2018-BEFF-E-B3-C3 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124221 | San Pablo Elementary School (Simangan) | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 1772034.2 |  | COMPLETED | 1 |  |  | 2018-beff-e-b2-c4 | 2018-beff-e-b2-c4 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124193 | Valencia Central School | Ormoc City | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 2459994.63 | 4614565.47 | COMPLETED | 1 | April 7, 2019 |  | 2018-BEFF-E-B3-C3 | 2018-BEFF-E-B3-C3 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303662 | Valencia National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 3293173.99 | 3254055.18 | COMPLETED | 1 | Aug. 19 |  | 2018-beff-e-b1-c2 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Vhits D.G. Builders Enterprise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 123498 | Beslig ES | GANDARA | 1 | 1 | UPGRADING | 2 | 655750.5 | 647586.2 | COMPLETED | 1 | 2018-10-11 |  | CY2018BEFF-ELB2-L1 | CY2018BEFF-ELB2-L1 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | MAGA Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 123509 | Gandara I CS | GANDARA | 1 | 1 | UPGRADING | 1 | 3200049.06 |  | COMPLETED | 1 | 2018-10-11 |  | CY2018BEFF-ELB1-L1 | CY2018BEFF-ELB1-L1 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | ROS Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303599 | Clarencio Calagos Mem SOF | SANTA MARGARITA | 1 | 1 | UPGRADING | 2 | 2280064.55 | 2253634.61 | COMPLETED | 1 | 2018-10-11 |  | CY2018BEFF-ELB2-L2 | CY2018BEFF-ELB2-L2 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | NV & C Const. Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 313727 | Mabini NHS | BASEY | 2 | 1 | UPGRADING | 1 | 1271594.45 |  | COMPLETED | 1 | 2018-10-11 |  | CY2018BEFF-ELB1-L2 | CY2018BEFF-ELB1-L2 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303597 | CALBIGA NATIONAL HIGH SCHOOL | CALBIGA | 2 | 1 | UPGRADING | 1 | 2166391.77 | 2140444.93 | COMPLETED | 1 | 2018-10-11 |  | CY2018BEFF-ELB1-L3 | CY2018BEFF-ELB1-L3 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 313719 | Bagacay NHS-Daram NHS Annex | DARAM | 2 | 1 | UPGRADING | 1 | 1725508.53 | 1710108.44 | COMPLETED | 1 | 2018-10-04 |  | CY2018BEFF-ELB1-L5 | CY2018BEFF-ELB1-L5 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303601 | Daram NHS | DARAM | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1531224.89 | 1513553.01 | COMPLETED | 1 | 2018-10-11 |  | CY2018BEFF-ELB1-L4 | CY2018BEFF-ELB1-L4 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303609 | Jiabong National High School | JIABONG | 2 | 1 | UPGRADING | 2 | 2133635.11 | 2121485.36 | COMPLETED | 1 | 2018-10-11 |  | CY2018BEFF-ELB2-L3 | CY2018BEFF-ELB2-L3 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | NV & C Const. Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 313710 | Malino National High School | JIABONG | 2 | 1 | UPGRADING | 1 | 965109.08 |  | COMPLETED | 1 | 2018-10-04 |  | CY2018BEFF-ELB1-L6 | CY2018BEFF-ELB1-L6 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Tubigan Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303611 | Marabut NHS | MARABUT | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 526801.85 |  | COMPLETED | 1 | 2018-10-11 |  | CY2018BEFF-ELB1-L2 | CY2018BEFF-ELB1-L2 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303596 | Calapi NHS | MOTIONG | 2 | 1 | UPGRADING | 1 | 1723736.2 | 1713315.58 | COMPLETED | 1 | 2018-10-04 |  | CY2018BEFF-ELB1-L8 | CY2018BEFF-ELB1-L8 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303641 | Wright NHS | PARANAS (WRIGHT) | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 793826.39 |  | COMPLETED | 1 | 2018-10-04 |  | CY2018BEFF-ELB1-L7 | CY2018BEFF-ELB1-L7 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303631 | Sta. Rita NHS | SANTA RITA | 2 | 1 | UPGRADING | 2 | 2002105.61 | 1970291.48 | COMPLETED | 1 | 2018-10-11 |  | CY2018BEFF-ELB2-L4 | CY2018BEFF-ELB2-L4 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | MAGA Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303605 | Guintarcan NHS | VILLAREAL | 2 | 1 | UPGRADING | 2 | 1535226.82 | 1511737.82 | COMPLETED | 1 | 2018-10-11 |  | CY2018BEFF-ELB2-L5 | CY2018BEFF-ELB2-L5 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | NV & C Const. Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 313718 | Primitivo T. Torrechiva National High School | VILLAREAL | 2 | 1 | UPGRADING | 1 | 467199.47 |  | COMPLETED | 1 | 2018-10-04 |  | CY2018BEFF-ELB1-L7 | CY2018BEFF-ELB1-L7 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 313721 | San Isidro NHS | ZUMARRAGA | 2 | 1 | UPGRADING | 1 | 504571.49 |  | COMPLETED | 1 | 2018-10-04 |  | CY2018BEFF-ELB1-L6 | CY2018BEFF-ELB1-L6 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Tubigan Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Southern Leyte | 303475 | Paku NHS | BONTOC | 0 | 1 | UPGRADING | 2 | 2380206.32 | 2356522.67 | COMPLETED | 1 |  |  | 18-5-001 | 18-5-001 | 2018-05-25 | 2018-06-01 | 2018-06-18 | 2018-07-04 | 2018-07-10 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Southern Leyte | 303460 | Himbangan National High School | SAINT BERNARD | 0 | 1 | UPGRADING | 2 | 3051800.83 | 3021434.65 | COMPLETED | 1 |  |  | 18-5-002 | 18-5-002 | 2018-05-25 | 2018-06-01 | 2018-06-18 | 2018-07-04 | 2018-07-10 | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Tacloban City | 303663 | Leyte NHS | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | 1 | 3268867.99 | 3232604.53 | COMPLETED | 1 | 2018-07-23 |  | CY 2018_BEFF ELECTRIFICATION-Batch 1 | CY 2018_BEFF ELECTRIFICATION-Batch 1 | 2018-04-19 | 2018-04-26 | 2018-05-08 | 2018-05-15 | 2018-05-17 | JELM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Tacloban City | 314005 | Scandinavian National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1530499.13 | 1507884.51 | COMPLETED | 1 | 2018-07-30 |  | CY 2018_BEFF ELECTRIFICATION-Batch 2_C1 | CY 2018_BEFF ELECTRIFICATION-Batch 2_C1 | 2018-04-26 | 2018-05-03 | 2018-05-15 | 2018-05-18 | 2018-05-22 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Tacloban City | 330503 | V&G National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1728949.63 | 1701750.55 | COMPLETED | 1 | 2018-07-30 |  | CY 2018_BEFF ELECTRIFICATION-Batch 2_C2 | CY 2018_BEFF ELECTRIFICATION-Batch 2_C2 | 2018-04-26 | 2018-05-03 | 2018-05-15 | 2018-05-18 | 2018-05-22 | TITANYA CONSTRUCTION & DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 327501 | Banahao National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 833968.42 | 818355.58 | COMPLETED | 1 | NOV. 28, 2019 | [7 empty] | August 23, 2019 | NV&C Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 313316 | Baybay City National Night High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 1293654.95 | 1260802.44 | COMPLETED | 1 | NOV. 28, 2019 | October 30, 2019 | [6 empty] | August 23, 2019 | QCC Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 121079 | Baybay I CS (Baybay North CS) | CITY OF BAYBAY | 5 | 1 | UPGRADING | Batch 3 | 2027630.48 | 2007540.28 | COMPLETED | 1 | February 10.2020 |  | 2019-07-002 | 2019-07-002 | July 24, 2019 | August 5, 2019 | August 28, 2019 | August 30, 2019 | November 5, 2019 | JFR Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 303360 | Caridad National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 2506936.93 | 2486132.63 | COMPLETED | 1 | NOV. 28, 2019 | [7 empty] | August 23, 2019 | HD Golden Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 500672 | Gabas Integrated School | CITY OF BAYBAY | 5 | 1 | UPGRADING | Batch 3 | 2368113.65 | 2329314.43 | COMPLETED | 1 | February 10.2020 |  | 2019-07-004 | 2019-07-004 | July 24, 2019 | August 5, 2019 | August 28, 2019 | August 30, 2019 | November 5, 2019 | QCC Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 121121 | Maitum Elementary School | CITY OF BAYBAY | 5 | 1 | UPGRADING | Batch 3 | 794359.38 | 780000 | COMPLETED | 1 | February 10.2020 | January 8, 2020 | 2019-07-003 | 2019-07-003 | July 24, 2019 | August 5, 2019 | August 28, 2019 | August 30, 2019 | November 5, 2019 | J.Costurio Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 303419 | Plaridel National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 2320890.78 | 2268965.73 | COMPLETED | 1 | NOV. 28, 2019 | [7 empty] | August 23, 2019 | AGB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 303420 | Pomponan National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 2698921.42 | 2602929.56 | COMPLETED | 1 | NOV. 28, 2019 | [7 empty] | August 23, 2019 | Melgazo Construcion and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 121099 | Pres. Carlos P. Garcia Elementary School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 552077.41 | 548181.4 | COMPLETED | 1 | NOV. 28, 2019 | November 25, 2019 | [6 empty] | August 23, 2019 | Kublai Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 303319 | Almeria NHS | ALMERIA | 0 | 1 | UPGRADING |  | 2474179.07 | 2451434.04 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-09-16 | VFD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 120762 | Jamorawon ES | ALMERIA | 0 | 1 | UPGRADING | Batch 3 | 763488.68 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 120763 | Lo-ok ES | ALMERIA | 0 | 1 | UPGRADING | Batch 3 | 596700.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 120770 | TABUNAN ES | ALMERIA | 0 | 1 | UPGRADING | Batch 3 | 736334.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 303332 | Tabunan National High School | ALMERIA | 0 | 1 | UPGRADING |  | 1674198.95 | 1643867.02 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-30 | G. BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 120772 | Tamarindo ES | ALMERIA | 0 | 1 | UPGRADING | Batch 3 | 740876.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 313201 | Western Biliran High School for the Arts and Culture | ALMERIA | 0 | 1 | UPGRADING |  | 1476540.44 | 1464153.21 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-16 | 5 STARS J CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 303320 | Biliran National Agricultural High School | BILIRAN | 0 | 1 | UPGRADING |  | 4315524.95 | 4262590.55 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-16 | QYT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 120778 | Core Shelter ES | BILIRAN | 0 | 1 | UPGRADING | Batch 3 | 518226.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 313203 | ICT High School of Eastern Biliran | CAIBIRAN | 0 | 1 | UPGRADING |  | 1716408.95 | 1702869.6 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-14 | WB ALAGAO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 303321 | Bool NHS | CULABA | 0 | 1 | UPGRADING |  | 2683076.97 | 2664076 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-22 | A&B ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 120827 | Baganito ES | KAWAYAN | 0 | 1 | UPGRADING | Batch 3 | 769843.88 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 303326 | Kawayan National High School | KAWAYAN | 0 | 1 | UPGRADING | Batch 3 | 2683076.97 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 303333 | Tucdao National High School | KAWAYAN | 0 | 1 | UPGRADING |  | 1658247.21 | 1634100 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-23 | J. COSTURIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 313204 | Naval Night High School | NAVAL (Capital) | 0 | 1 | UPGRADING |  | 1283291.55 | 1271575.43 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-28 | NB ANG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122368 | Amantacop ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 371928.57 | 365497.76 | COMPLETED | 1 | 2020-01-02 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 2 | Electrification-Lot 1 | 2019-06-21 | 2019-07-01 | 2019-07-16 | 2019-08-09 | 2019-09-07 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122392 | Bagong Barrio ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 344753.14 | 341857.58 | COMPLETED | 1 | 2020-01-02 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 2 | Electrification-Lot 2 | 2019-06-21 | 2019-07-01 | 2019-07-16 | 2019-08-09 | 2019-09-07 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122394 | Baras ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1079665.66 | 1072602.03 | COMPLETED | 1 | 2020-01-02 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 2 | Electrification-Lot 2 | 2019-06-21 | 2019-07-01 | 2019-07-16 | 2019-08-09 | 2019-09-07 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122357 | Calico-an ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING |  | 601189.1 | 594787.29 | COMPLETED | 1 | 2019-12-03 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 1 | Electrification-Lot 1 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122379 | Maypangdan ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING |  | 1918464.33 | 1898117.84 | COMPLETED | 1 | 2019-12-03 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 1 | Electrification-Lot 3 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122405 | Pinanag-an ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 443748.2 | 439836.86 | COMPLETED | 1 | 2020-01-02 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 2 | Electrification-Lot 2 | 2019-06-21 | 2019-07-01 | 2019-07-16 | 2019-08-09 | 2019-09-07 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122381 | Punta Maria ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING |  | 585891.5 | 579210.98 | COMPLETED | 1 | 2019-12-03 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 1 | Electrification-Lot 1 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122383 | San Andres Lower PS | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING |  | 374798 | 371346.72 | COMPLETED | 1 | 2019-12-03 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 1 | Electrification-Lot 2 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122362 | San Gabriel ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1295134.72 | 1279785.59 | COMPLETED | 1 | 2020-01-02 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 2 | Electrification-Lot 1 | 2019-06-21 | 2019-07-01 | 2019-07-16 | 2019-08-09 | 2019-09-07 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122363 | San Jose ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING |  | 1120481.91 | 1106232.37 | COMPLETED | 1 | 2019-12-03 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 1 | Electrification-Lot 2 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122388 | Sta. Fe ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING |  | 593062.41 | 586638.66 | COMPLETED | 1 | 2019-12-03 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 1 | Electrification-Lot 1 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 344634 | Calbayog Arts and Design School of Eastern Visayas | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 1521797.1 | 1503534.84 | COMPLETED | 1 | NOV. 30, 2020 |  | BEFF 2019-MES-CAL-L6 | FOR ISSUANCE | NOVEMBER 21, 2018 | NOVEMBER 14, 2018 | DECEMBER 11, 2018 | FOR ISSUANCE | FOR ISSUANCE | PEDAB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 313801 | Calbayog City National High School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 3167353.68 | 3120777.4 | COMPLETED | 1 | NOV. 30, 2020 |  | BEFF 2019-MES-CAL-L3 | FOR ISSUANCE | NOVEMBER 21, 2018 | NOVEMBER 14, 2018 | DECEMBER 11, 2018 | FOR ISSUANCE | FOR ISSUANCE | RNA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 313806 | Calbayog City National High School - Carayman Campus | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 2260062.51 | 2233700.43 | COMPLETED | 1 | NOV. 30, 2020 |  | BEFF 2019-MES-CAL-L5 | FOR ISSUANCE | NOVEMBER 21, 2018 | NOVEMBER 14, 2018 | DECEMBER 11, 2018 | FOR ISSUANCE | FOR ISSUANCE | NV & C CONSTRUCTION AND GENERAL SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 313811 | Malaga NHS - Pena I Annex School | CALBAYOG CITY | 1 | 1 | UPGRADING | Batch 3 | 1756058.96 | 1467398.23 | COMPLETED | 1 |  |  | CY2019 BEFF-ESSM-CAL-L4 | FOR ISSUANCE | JULY 25, 2019 | AUGUST 2, 2019 | AUGUST 14, 2019 | UNDER POSTQUAL | FOR ISSUANCE | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 313802 | Migara National High School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 2058442.24 | 2038083.44 | COMPLETED | 1 | NOV. 30, 2020 |  | BEFF 2019-MES-CAL-L4 | FOR ISSUANCE | NOVEMBER 21, 2018 | NOVEMBER 14, 2018 | DECEMBER 11, 2018 | FOR ISSUANCE | FOR ISSUANCE | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 303648 | Pilar National Agricultural High School | CALBAYOG CITY | 1 | 1 | UPGRADING | Batch 3 | 2764113.16 | 2061162.77 | COMPLETED | 1 |  |  | CY2019 BEFF-ESSM-CAL-L3 | FOR ISSUANCE | JULY 25, 2019 | AUGUST 2, 2019 | AUGUST 14, 2019 | UNDER POSTQUAL | FOR ISSUANCE | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 303649 | R. Lentejas Mem. School Of Fisheries | CALBAYOG CITY | 1 | 1 | UPGRADING | Batch 3 | 3066543.55 | 2010360 | COMPLETED | 1 |  |  | CY2019 BEFF-ESSM-CAL-L2 | FOR ISSUANCE | JULY 25, 2019 | AUGUST 2, 2019 | AUGUST 14, 2019 | UNDER POSTQUAL | FOR ISSUANCE | J.CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 303650 | San Joaquin National HIgh School | CALBAYOG CITY | 1 | 1 | UPGRADING | Batch 3 | 3066543.55 | 2010360 | COMPLETED | 1 |  |  | CY2019 BEFF-ESSM-CAL-L1 | FOR ISSUANCE | JULY 25, 2019 | AUGUST 2, 2019 | AUGUST 14, 2019 | UNDER POSTQUAL | FOR ISSUANCE | J.CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 303651 | San Policarpo National High School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 2864923.29 | 2835596.49 | COMPLETED | 1 | NOV. 30, 2020 |  | BEFF 2019-MES-CAL-L | FOR ISSUANCE | NOVEMBER 21, 2018 | NOVEMBER 14, 2018 | DECEMBER 11, 2018 | FOR ISSUANCE | FOR ISSUANCE | NV & C CONSTRUCTION AND GENERAL SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 303652 | Tarabucan National High School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 2461682.77 | 2418917.79 | COMPLETED | 1 | NOV. 30, 2020 |  | BEFF 2019-MES-CAL-L2 | FOR ISSUANCE | NOVEMBER 21, 2018 | NOVEMBER 14, 2018 | DECEMBER 11, 2018 | FOR ISSUANCE | FOR ISSUANCE | TOM BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123419 | Bliss Community School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 2347694.34 | 2310452.23 | COMPLETED | 1 |  |  | CY 2019_ESUP_R8_CC-L7 | CY 2019_ESUP_R8_CC-L7 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-10 | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123408 | Bunu-Anan Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1901559.27 | 1872996.44 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L3 | CY2019-BEFF-B2-ESUP-R8-CC-L3 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | SANGREE INDUSTRIAL SALES INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123429 | Buri Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2043838.16 | 2021935.66 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L7 | CY2019-BEFF-B2-ESUP-R8-CC-L7 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123397 | Catbalogan I Central Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 3073527.29 | 3032885.2 | COMPLETED | 1 |  |  | CY 2019_ESUP_R8_CC-L1 | CY 2019_ESUP_R8_CC-L1 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-10 | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123423 | Catbalogan III Central Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 3043381.6 | 2540401.82 | COMPLETED | 1 |  |  | CY 2019_ESUP_R8_CC-L8 | CY 2019_ESUP_R8_CC-L8 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-12 | LOBRIÑOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123431 | Catbalogan IV Central Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 2853315.25 | 2818239.45 | COMPLETED | 1 |  |  | CY 2019_ESUP_R8_CC-L9 | CY 2019_ESUP_R8_CC-L9 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-11 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123416 | Catbalogan V CES (Mercedes ES) | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 3024692.47 | 2462009.45 | COMPLETED | 1 |  |  | CY 2019_ESUP_R8_CC-L5 | CY 2019_ESUP_R8_CC-L5 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-12 | LOBRIÑOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123410 | Darahuway Dako Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1946024.07 | 1919374.51 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L4 | CY2019-BEFF-B2-ESUP-R8-CC-L4 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-11 | ALPHAHAWK CONSTRUCTION CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123411 | Darahuway Guti ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2046394.53 | 2020776.32 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L5 | CY2019-BEFF-B2-ESUP-R8-CC-L5 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-11 | ALPHAHAWK CONSTRUCTION CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123412 | Guinsorongan Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 1944453.82 | 1914317.18 | COMPLETED | 1 |  |  | CY 2019_ESUP_R8_CC-L2 | CY 2019_ESUP_R8_CC-L2 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-11 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 303621 | Guinsorongan NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 2013419.26 | 2002145.87 | COMPLETED | 1 |  |  | CY 2019_ESUP_R8_CC-L12 | CY 2019_ESUP_R8_CC-L12 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-04 | HEROES CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123413 | Ibol Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 2055580.5 | 2039541.59 | COMPLETED | 1 |  |  | CY 2019_ESUP_R8_CC-L3 | CY 2019_ESUP_R8_CC-L3 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-11 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123432 | Iguid Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2047016.35 | 2012943.09 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L8 | CY2019-BEFF-B2-ESUP-R8-CC-L8 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | MJM BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123435 | Jose P. Casiño Sr. Memorial ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 2046771.39 | 2011633.41 | COMPLETED | 1 |  |  | CY 2019_ESUP_R8_CC-L10 | CY 2019_ESUP_R8_CC-L10 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-10 | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123425 | Lagundi ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2046049.08 | 2005733.46 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L6 | CY2019-BEFF-B2-ESUP-R8-CC-L6 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123414 | Madalunot Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 1980883.65 | 1955629.43 | COMPLETED | 1 |  |  | CY 2019_ESUP_R8_CC-L4 | CY 2019_ESUP_R8_CC-L4 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-11 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123433 | New Mahayag Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2046539.78 | 2011306.61 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L9 | CY2019-BEFF-B2-ESUP-R8-CC-L9 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123434 | Old Mahayag Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1899411.17 | 1859875.31 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L10 | CY2019-BEFF-B2-ESUP-R8-CC-L10 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123417 | Pangdan Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 2651694.99 | 2627508.24 | COMPLETED | 1 |  |  | CY 2019_ESUP_R8_CC-L6 | CY 2019_ESUP_R8_CC-L6 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-10 | BEECARTINE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123436 | Pupua Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1844919.52 | 1823554.86 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L11 | CY2019-BEFF-B2-ESUP-R8-CC-L11 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-15 | RICHMARK CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123404 | Salug Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2046834.2 | 2021528.48 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L1 | CY2019-BEFF-B2-ESUP-R8-CC-L1 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | HEROES CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 303620 | Samar National School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 3287646.75 | 3255662.01 | COMPLETED | 1 |  |  | CY 2019_ESUP_R8_CC-L11 | CY 2019_ESUP_R8_CC-L11 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-11 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123405 | San Andres Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2692019.04 | 2667429.97 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L2 | CY2019-BEFF-B2-ESUP-R8-CC-L2 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | HAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123437 | San Roque ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1885537.99 | 1870029.88 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L12 | CY2019-BEFF-B2-ESUP-R8-CC-L12 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | BENCH CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123438 | San Vicente Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1885066.91 | 1853736.47 | COMPLETED | 1 |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L13 | CY2019-BEFF-B2-ESUP-R8-CC-L13 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | NV & C CONSTRUCTION AND GENERAL SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122326 | Bato Elementary School | ARTECHE | 0 | 1 | UPGRADING | Batch 3 | 591167.88 | 584236.31 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 1 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122327 | Beri Elementary School | ARTECHE | 0 | 1 | UPGRADING |  | 671405.64 |  | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-3 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122328 | Bigo Elementary School | ARTECHE | 0 | 1 | UPGRADING | Batch 3 | 370052.61 | 365763.68 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 1 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122335 | Concepcion Elementary School | ARTECHE | 0 | 1 | UPGRADING | Batch 3 | 1082533.51 | 1070510.31 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 2 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 313522 | Concepcion National High School | ARTECHE | 0 | 1 | UPGRADING | Batch 3 | 717392.92 | 709489.69 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 2 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122452 | Gap-ang Elementary School | DOLORES | 0 | 1 | UPGRADING | Batch 3 | 889010.44 | 878349.39 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 7 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 303501 | Gen. MacArthur National Agricultural School | GENERAL MACARTHUR | 0 | 1 | UPGRADING | Batch 3 | 2154756.42 |  | COMPLETED | 1 | JAN. 12, 2020 |  | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | [6 empty] | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 3 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 303532 | Tubabao National High School | GUIUAN | 0 | 1 | UPGRADING | Batch 3 | 522514.14 | 519901.56 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 4 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122585 | Bacayawan Elementary School | LLORENTE | 0 | 1 | UPGRADING |  | 449935.04 |  | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-7 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | ROSS ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122586 | Banika Elementary School | LLORENTE | 0 | 1 | UPGRADING |  | 854696.08 |  | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-7 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | ROSS ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122591 | Canliwag Elementary School | LLORENTE | 0 | 1 | UPGRADING |  | 362954.05 |  | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-8 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | ROSS ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122594 | Llorente Central Elementary School | LLORENTE | 0 | 1 | UPGRADING |  | 1874589.86 | 2487265.11 | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-1 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 303513 | Llorente National High School | LLORENTE | 0 | 1 | UPGRADING |  | 2516975.27 | 2487265.11 | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-1 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122597 | Minaanod Elementary School | LLORENTE | 0 | 1 | UPGRADING | Batch 3 | 597804.62 | 591430.39 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 8 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122599 | Piliw Elementary School | LLORENTE | 0 | 1 | UPGRADING | Batch 3 | 444381.23 | 441117.73 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 8 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122601 | San Miguel Elementary School | LLORENTE | 0 | 1 | UPGRADING | Batch 3 | 583019.28 | 577451.88 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 8 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122604 | Tabok Elementary School | LLORENTE | 0 | 1 | UPGRADING |  | 838595.58 |  | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-8 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | ROSS ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122634 | Bantayan Elementary School | ORAS | 0 | 1 | UPGRADING |  | 893712.1 |  | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-2 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122659 | Buntay Elementary School | ORAS | 0 | 1 | UPGRADING | Batch 3 | 1126339.85 | 1114000 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 6 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122665 | Iwayan Elementary School | ORAS | 0 | 1 | UPGRADING | Batch 3 | 726245.06 | 718961.17 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 9 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122639 | Japay Elementary School | ORAS | 0 | 1 | UPGRADING | Batch 3 | 678676.63 | 671038.83 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 9 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122642 | Malingon Elementary School | ORAS | 0 | 1 | UPGRADING |  | 384979.03 |  | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-3 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122645 | Pangudtan Elementary School | ORAS | 0 | 1 | UPGRADING |  | 610470.56 |  | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-3 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122649 | Saurong Elementary School | ORAS | 0 | 1 | UPGRADING |  | 569055.39 |  | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-2 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122704 | Alog Elementary School | SALCEDO | 0 | 1 | UPGRADING | Batch 3 | 377979.21 | 375098.44 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 4 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122709 | Bugay Elementary School | SALCEDO | 0 | 1 | UPGRADING |  | 408504.58 |  | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-4 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122710 | Burak Elementary School | SALCEDO | 0 | 1 | UPGRADING | Batch 3 | 1174080.38 | 1162000 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 5 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122718 | Matarinao Elementary School | SALCEDO | 0 | 1 | UPGRADING |  | 716067.2 |  | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-4 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 313509 | Salcedo Vocational High School | SALCEDO | 0 | 1 | UPGRADING |  | 2937017.52 | 2907983.05 | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-5 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122773 | San Pablo Elementary School | TAFT | 0 | 1 | UPGRADING | Batch 3 | 876030.76 | 871650.61 | COMPLETED | 1 | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 7 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 303529 | Taft National High School | TAFT | 0 | 1 | UPGRADING |  | 1867566.93 | 1843338.78 | COMPLETED | 1 | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-6 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121005 | Babatngon Central School | BABATNGON | 1 | 1 | UPGRADING |  | 2559647.31 | 2185607.3626 | COMPLETED | 1 |  |  | lot 1-cy-2019-E-B1-leyte | lot 1-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121009 | Gov. E. Jaro ES | BABATNGON | 1 | 1 | UPGRADING | Batch 3 | 898563.28 |  | COMPLETED | 1 |  |  | lot 3-cy-2019-E-B2-leyte | lot 3-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121013 | Malibago Elementary School | BABATNGON | 1 | 1 | UPGRADING | Batch 3 | 1259097.68 |  | COMPLETED | 1 |  |  | lot 1-cy-2019-E-B2-leyte | lot 1-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121015 | Pagsulhugon Elementary School | BABATNGON | 1 | 1 | UPGRADING | Batch 3 | 991832.39 | 1265105.9498 | COMPLETED | 1 |  |  | lot 2-cy-2019-E-B2-leyte | lot 2-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 303413 | Pagsulhugon National High School | BABATNGON | 1 | 1 | UPGRADING |  | 1483471.57 | 1265105.9498 | COMPLETED | 1 |  |  | lot 2-cy-2019-E-B1-leyte | lot 2-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121018 | San Agustin Elementary School | BABATNGON | 1 | 1 | UPGRADING | Batch 3 | 630906.23 |  | COMPLETED | 1 |  |  | lot 1-cy-2019-E-B2-leyte | lot 1-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121021 | Taguite Elementary School | BABATNGON | 1 | 1 | UPGRADING | Batch 3 | 693222.65 |  | COMPLETED | 1 |  |  | lot 2-cy-2019-E-B2-leyte | lot 2-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121022 | Uban Elementary School | BABATNGON | 1 | 1 | UPGRADING | Batch 3 | 753618.11 |  | COMPLETED | 1 |  |  | lot 3-cy-2019-E-B2-leyte | lot 3-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 303432 | STA. MESA NATIONAL HIGH SCHOOL | DAGAMI | 2 | 1 | UPGRADING |  | 3769162.06 | 3711756.32 | COMPLETED | 1 |  |  | lot 3-cy-2019-E-B1-leyte | lot 3-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | BLACK NAZARENE BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121527 | Julita Central School | JULITA | 2 | 1 | UPGRADING |  | 1227786.41 | 959815.3754 | COMPLETED | 1 |  |  | lot 4-cy-2019-E-B1-leyte | lot 4-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121572 | La Paz Central School | LA PAZ | 2 | 1 | UPGRADING |  | 1280880.53 | 1091706.8674 | COMPLETED | 1 |  |  | lot 5-cy-2019-E-B1-leyte | lot 5-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121576 | Mag-aso Elementary School | LA PAZ | 2 | 1 | UPGRADING | Batch 3 | 886142.26 |  | COMPLETED | 1 |  |  | RFQ1-cy-2019-E-B2-leyte | RFQ1-cy-2019-E-B2-leyte | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121582 | Rizal Elementary School | LA PAZ | 2 | 1 | UPGRADING | Batch 3 | 632089.73 |  | COMPLETED | 1 |  |  | lot 4-cy-2019-E-B2-leyte | lot 4-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121584 | Sta. Ana Elementary School | LA PAZ | 2 | 1 | UPGRADING | Batch 3 | 1158603.62 |  | COMPLETED | 1 |  |  | lot 4-cy-2019-E-B2-leyte | lot 4-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121701 | Burgos Elementary School | MAYORGA | 2 | 1 | UPGRADING | Batch 3 | 692390.85 |  | COMPLETED | 1 |  |  | RFQ3-cy-2019-E-B2-leyte | RFQ3-cy-2019-E-B2-leyte | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121705 | Liberty Elementary School | MAYORGA | 2 | 1 | UPGRADING | Batch 3 | 654053.51 |  | COMPLETED | 1 |  |  | RFQ4-cy-2019-E-B2-leyte | RFQ4-cy-2019-E-B2-leyte | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121707 | Mayorga Central School | MAYORGA | 2 | 1 | UPGRADING |  | 1340308.85 | 1091706.8674 | COMPLETED | 1 |  |  | lot 6-cy-2019-E-B1-leyte | lot 6-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121712 | Union Elementary School | MAYORGA | 2 | 1 | UPGRADING | Batch 3 | 916655.04 |  | COMPLETED | 1 |  |  | RFQ2-cy-2019-E-B2-leyte | RFQ2-cy-2019-E-B2-leyte | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 303427 | Seguinon National High School | ALBUERA | 4 | 1 | UPGRADING |  | 2729312.17 | 2342487.9176 | COMPLETED | 1 |  |  | lot 7-cy-2019-E-B1-leyte | lot 7-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Maasin City | 303464 | Libhu National High School | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING | Batch 2 | 3030279.24 | 2946977.22 | COMPLETED | 1 |  |  | ELECTRIFICTION-19-7-002 | ELECTRIFICTION-19-7-002 | 2019-07-30 | 2019-08-08 | 2019-08-22 | 2019-08-29 | 2019-11-21 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Maasin City | 122135 | Maasin Central School | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING | Batch 2 | 3450000 | 3366284.2 | COMPLETED | 1 |  |  | ELECTRIFICTION-19-7-001 | ELECTRIFICTION-19-7-001 | 2019-07-30 | 2019-08-08 | 2019-08-22 | 2019-08-29 | 2019-11-21 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Maasin City | 303469 | Manhilo National High School | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING | Batch 2 | 2941716.74 | 2857629.21 | COMPLETED | 1 |  |  | ELECTRIFICTION-19-7-003 | ELECTRIFICTION-19-7-003 | 2019-07-30 | 2019-08-08 | 2019-08-22 | 2019-08-29 | 2019-11-21 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Northern Samar | 303570 | Polangi National HIgh School | CATARMAN (Capital) | 1 | 1 | UPGRADING | Batch 3 | 2042069.78 | 2029870.49 | COMPLETED | 1 |  |  | BEFF2019-B2-ELEC-NS-L1 | BEFF2019-B2-ELEC-NS-L1 |  | Aug. 8, 2019 | Aug. 20, 2019 | Sept. 2, 2019 |  | HD GOLDEN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Northern Samar | 303573 | Rosario National High School | ROSARIO | 1 | 1 | UPGRADING |  | 1654345.69 | 1065752.65 | COMPLETED | 1 |  |  | BEFF2019-ELEC-NS-L1 | BEFF2019-ELEC-NS-L1 |  | Dec. 7, 2018 | Dec. 19, 2018 | Jan. 9, 2019 |  | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Northern Samar | 303530 | Alegria NHS | SAN ISIDRO | 1 | 1 | UPGRADING |  | 1449724.7 | 936709.96 | COMPLETED | 1 |  |  | BEFF2019-ELEC-NS-L2 | BEFF2019-ELEC-NS-L2 |  | Dec. 7, 2018 | Dec. 19, 2018 | Jan. 9, 2019 |  | JCAD ENGINEERING & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Northern Samar | 303544 | Catubig Valley NHS | CATUBIG | 2 | 1 | UPGRADING |  | 1941673.21 | 1254931.67 | COMPLETED | 1 |  |  | BEFF2019-ELEC-NS-L3 | BEFF2019-ELEC-NS-L3 |  | Dec. 7, 2018 | Dec. 19, 2018 | Jan. 9, 2019 |  | JCAD ENGINEERING & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Northern Samar | 313603 | Rawis National High School | LAOANG | 2 | 1 | UPGRADING |  | 2016055.02 | 1206281.85 | COMPLETED | 1 |  |  | BEFF2019-ELEC-NS-L4 | BEFF2019-ELEC-NS-L4 |  | Dec. 7, 2018 | Dec. 19, 2018 | Jan. 9, 2019 |  | ROSS ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Northern Samar | 303546 | Don Juan F. Avalon National High School | SAN ROQUE | 2 | 1 | UPGRADING | Batch 3 | 1949178.92 | 1938010.69 | COMPLETED | 1 |  |  | BEFF2019-B2-ELEC-NS-L2 | BEFF2019-B2-ELEC-NS-L2 |  | Aug. 8, 2019 | Aug. 20, 2019 | Sept. 2, 2019 |  | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124204 | Curva Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | Batch 3 | 1694778.98 |  | COMPLETED | 1 |  |  | BEFF-2019-E-B2-C3 | BEFF-2019-E-B2-C3 | July 2, 2019 | July 11 2019 | July 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124212 | Libertad Elementary School | Ormoc City | 4 | 1 | UPGRADING |  | 2366776.16 | 2307111.11 | COMPLETED | 1 | November 16, 2019 |  | BEFF-2019-E-B1-C1 | BEFF-2019-E-B1-C1 | October 30, 2018 | November 7, 2018 | November 19, 2018 | November 22, 2018 | August 9, 2019 | Melgazo Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124213 | Licuma Elementary School | Ormoc City | 4 | 1 | UPGRADING | Batch 3 | 1257239.84 |  | COMPLETED | 1 |  |  | BEFF-2019-E-B2-C1 | BEFF-2019-E-B2-C1 | July 2, 2019 | July 11 2019 | July 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124214 | Liloan Central School | Ormoc City | 4 | 1 | UPGRADING |  | 2263899.43 | 2230387.17 | COMPLETED | 1 | November 16, 2019 |  | BEFF-2019-E-B1-C2 | BEFF-2019-E-B1-C2 | October 30, 2018 | November 7, 2018 | November 19, 2018 | November 22, 2018 | August 9, 2019 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124215 | Margen Elementary School | Ormoc City | 4 | 1 | UPGRADING | Batch 3 | 2133592.31 |  | COMPLETED | 1 |  |  | BEFF-2019-E-B2-C4 | BEFF-2019-E-B2-C4 | July 2, 2019 | July 11 2019 | July 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124216 | Mas-in Elementary School | Ormoc City | 4 | 1 | UPGRADING |  | 1967118.43 | 1944292.34 | COMPLETED | 1 | November 16, 2019 |  | BEFF-2019-E-B1-C3 | BEFF-2019-E-B1-C3 | October 30, 2018 | November 7, 2018 | November 19, 2018 | November 22, 2018 | August 9, 2019 | melgazo Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 344795 | Ormoc City Sports Senior High School | Ormoc City | 4 | 1 | UPGRADING |  | 1184245.46 | 1148493.36 | COMPLETED | 1 | November 16, 2019 |  | BEFF-2019-E-B1-C5 | BEFF-2019-E-B1-C5 | October 30, 2018 | November 7, 2018 | November 19, 2018 | November 22, 2018 | August 9, 2019 | melgazo Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124218 | Salvacion Elementary School | Ormoc City | 4 | 1 | UPGRADING | Batch 3 | 1984626.42 |  | COMPLETED | 1 |  |  | BEFF-2019-E-B2-C5 | BEFF-2019-E-B2-C5 | July 2, 2019 | July 11 2019 | July 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124169 | San Antonio Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | Batch 3 | 1700055.36 |  | COMPLETED | 1 |  |  | BEFF-2019-E-B2-C2 | BEFF-2019-E-B2-C2 | July 2, 2019 | July 11 2019 | July 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124219 | San Isidro Elementary School | Ormoc City | 4 | 1 | UPGRADING |  | 2004096.7 | 1938938.91 | COMPLETED | 1 | November 16, 2019 |  | BEFF-2019-E-B1-C4 | BEFF-2019-E-B1-C4 | October 30, 2018 | November 7, 2018 | November 19, 2018 | November 22, 2018 | August 9, 2019 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124223 | Sto. Nino Elementary School | Ormoc City | 4 | 1 | UPGRADING | Batch 3 | 2130360.89 |  | COMPLETED | 1 |  |  | BEFF-2019-E-B1-C6 | BEFF-2019-E-B2-C6 | July 2, 2019 | July 11 2019 | July 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 123507 | Concepcion ES | GANDARA | 1 | 1 | UPGRADING |  | 478258.94 | 469858.84 | COMPLETED | 1 | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | MAGA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 123516 | Nacube Elementary School | GANDARA | 1 | 1 | UPGRADING | Batch 3 | 482107.83 | 477979.53 | COMPLETED | 1 |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | H.A.H REVERIE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 313734 | Sto. Niño IS | GANDARA | 1 | 1 | UPGRADING |  | 1527702.63 | 1514910.82 | COMPLETED | 1 | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | MAGA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 313708 | San Jorge NHS | SAN JORGE | 1 | 1 | UPGRADING |  | 2158365.56 | 2135282.9 | COMPLETED | 1 | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | BENCH CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303629 | Sta. Margarita NHS | SANTA MARGARITA | 1 | 1 | UPGRADING | Batch 3 | 1382210.1 | 1354969.37 | COMPLETED | 1 |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | PABLO S. LABASBAS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303635 | OESTE NHS | TARANGNAN | 1 | 1 | UPGRADING | Batch 3 | 1026448.14 | 1010982.7 | COMPLETED | 1 |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | VFD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303634 | Tarangnan NHS | TARANGNAN | 1 | 1 | UPGRADING | Batch 3 | 2498105.12 | 2459837.45 | COMPLETED | 1 |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | TOM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303637 | Valeriano C. Yancha MAS | BASEY | 2 | 1 | UPGRADING |  | 6330348.24 | 6247643.19 | COMPLETED | 1 | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | MAGA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303606 | Hinabangan NHS | HINABANGAN | 2 | 1 | UPGRADING | Batch 3 | 2242201.28 | 2215897.49 | COMPLETED | 1 |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | GPUY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303614 | Osmeña NHS | MARABUT | 2 | 1 | UPGRADING |  | 3466907.47 | 3053776.52 | COMPLETED | 1 | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | BLACK NAZARENE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303640 | Quintin Quijano SAS | PINABACDAO | 2 | 1 | UPGRADING |  | 2055565.25 | 2040000.83 | COMPLETED | 1 | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | NV&C CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303627 | San Sebastian NHS | SAN SEBASTIAN | 2 | 1 | UPGRADING | Batch 3 | 1417708.1 | 1400570.14 | COMPLETED | 1 |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | NV&C CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303636 | Tominamos IS | SANTA RITA | 2 | 1 | UPGRADING |  | 1983478.83 | 1943204.7 | COMPLETED | 1 | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | PYUKEI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303639 | Villareal NHS | VILLAREAL | 2 | 1 | UPGRADING | Batch 3 | 2139035.77 | 2106294.45 | COMPLETED | 1 |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303643 | Zumarraga NHS | ZUMARRAGA | 2 | 1 | UPGRADING | Batch 3 | 2142887.6 | 2120725.92 | COMPLETED | 1 |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | NV&C CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 313403 | Bontoc National High School | BONTOC | 0 | 1 | UPGRADING | Batch 3 | 4978956.62 | 4890275.91 | COMPLETED | 1 |  |  | BEFF-CY2019-B2-ELECTRIFICATION-L1 | BEFF-CY2019-B2-ELECTRIFICATION-L1 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Vhits D.G. Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 303466 | Lungsodaan National High School | HINUNDAYAN | 0 | 1 | UPGRADING | Batch 3 | 4266684.2 | 2759718.17 | COMPLETED | 1 |  |  | BEFF-CY2019-B2-ELECTRIFICATION-L2 | BEFF-CY2019-B2-ELECTRIFICATION-L2 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Maxter Resources Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 303472 | Rito Monte de Ramos Sr. MHS (Nahaong NHS) | LIBAGON | 0 | 1 | UPGRADING | Batch 3 | 4069143.06 | 2429565.22 | COMPLETED | 1 |  |  | BEFF-CY2019-B2-ELECTRIFICATION-L3 | BEFF-CY2019-B2-ELECTRIFICATION-L3 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Maxter Resources Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational High School | LILOAN | 0 | 1 | UPGRADING |  | 8150875.02 | 8084882.48 | COMPLETED | 1 |  |  | BEFF-CY2019- ELECTRIFICATION-L1 | BEFF-CY2019- ELECTRIFICATION-L1 | Nov. 6, 2018 | Nov. 14, 2018 | Nov. 27, 2018 | Dec. 7, 2018 | 2019-08-22 | Vhits D.G. Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 303477 | Pintuyan National Vocational High School | PINTUYAN | 0 | 1 | UPGRADING | Batch 3 | 5162592.23 | 3184129.7 | COMPLETED | 1 |  |  | BEFF-CY2019-B2-ELECTRIFICATION-L4 | BEFF-CY2019-B2-ELECTRIFICATION-L4 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Maxter Resources Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 303481 | San Juan NHS | SAN JUAN (CABALIAN) | 0 | 1 | UPGRADING | Batch 3 | 5898252.2 | 5796677.51 | COMPLETED | 1 |  |  | BEFF-CY2019-B2-ELECTRIFICATION-L5 | BEFF-CY2019-B2-ELECTRIFICATION-L5 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Vhits D.G. Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 303461 | Hingatungan NHS | SILAGO | 0 | 1 | UPGRADING | Batch 3 | 4298980.85 | 4244575 | COMPLETED | 1 |  |  | BEFF-CY2019-B2-ELECTRIFICATION-L6 | BEFF-CY2019-B2-ELECTRIFICATION-L6 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Vhits D.G. Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 303486 | Silago NVHS | SILAGO | 0 | 1 | UPGRADING | Batch 3 | 5689118.46 | 5630573.22 | COMPLETED | 1 | 2020-04-10 |  | BEFF-CY2019-B2-ELECTRIFICATION-L7 | BEFF-CY2019-B2-ELECTRIFICATION-L7 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Vhits D.G. Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124256 | City CS | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1690724.22 |  | COMPLETED | 1 |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124257 | Kapangian Central School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1632794.18 |  | COMPLETED | 1 |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 303664 | Marasbaras NHS | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 3214060.75 | 3166003.26 | COMPLETED | 1 |  |  |  |  | 2018-11-07 | 2018-11-14 | 2018-11-26 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 314004 | Northern Tacloban City National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 5138521.43 |  | COMPLETED | 1 |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124228 | Remedios T. Romualdez ES (Rizal Central Annex ES) | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1943458.18 |  | COMPLETED | 1 |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124229 | Sagkahan ES | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 3801154.14 |  | COMPLETED | 1 |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 303666 | Sagkahan National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 3655037.55 | 2269553.71 | COMPLETED | 1 |  |  |  |  | 2018-11-07 | 2018-11-14 | 2018-11-26 |  |  | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124249 | San Fernando Central School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 2739384.28 |  | COMPLETED | 1 |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124250 | San Jose ES | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 5081529.16 |  | COMPLETED | 1 |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 303667 | San Jose National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 5028520.62 | 4920358.77 | COMPLETED | 1 |  |  |  |  | 2018-11-07 | 2018-11-14 | 2018-11-26 |  |  | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124260 | Sto. Nino SPED Center | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 3183652.83 |  | COMPLETED | 1 |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 303670 | Tacloban City National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 2748292.82 |  | COMPLETED | 1 |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 344881 | Tacloban City Stand Alone 1 Senior High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1599219.19 |  | COMPLETED | 1 |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 303669 | Tacloban National Agricultural School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 6049755.3 |  | COMPLETED | 1 |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124230 | V & G Mem. ES | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 2285155.06 |  | COMPLETED | 1 |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Baybay City | 121102 | BAYBAY II CS | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 1702836.12 | 1654979.75 | COMPLETED | 1 |  |  | ELEC2020-R8-BAYBAY CITY-001 | 2019-11-009 | November 21, 2019 | November 29, 2019 | December 11, 2019 | December 18, 2019 |  | BENCH CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Baybay City | 303349 | Bitanhuan National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 1359964.45 | 1204857.41 | COMPLETED | 1 |  |  | ELEC2020-R8-BAYBAY CITY-003 | 2019-11-010 | November 21, 2019 | November 29, 2019 | December 11, 2019 | December 18, 2019 |  | JUNVILL ENTERPRISES & CONSTRUCTION SERVICE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Baybay City | 303351 | Bunga National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 2176912.05 | 2155874.84 | COMPLETED | 1 |  |  | ELEC2020-R8-BAYBAY CITY-004 | 2019-11-011 | November 21, 2019 | November 29, 2019 | December 11, 2019 | December 18, 2019 |  | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Baybay City | 500673 | Kabunga-an Integrated School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 1649632.87 | 1853375.18 | COMPLETED | 1 |  |  | ELEC2020-R8-BAYBAY CITY-006 | 2019-11-012 | November 21, 2019 | November 29, 2019 | December 11, 2019 | December 18, 2019 |  | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Baybay City | 303400 | Makinhas National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 1876325.75 | 1508346.81 | COMPLETED | 1 |  |  | ELEC2020-R8-BAYBAY CITY-007 | 2019-11-013 | November 21, 2019 | November 29, 2019 | December 11, 2019 | December 18, 2019 |  | JUNVILL ENTERPRISES & CONSTRUCTION SERVICE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Baybay City | 500746 | Mapgap Integrated School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 488908.05 |  | COMPLETED | 1 |  |  | ELEC2020-R8-BAYBAY CITY-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Biliran | 120774 | BILIRAN CS | BILIRAN | 0 | 1 | UPGRADING |  | 1612387.81 | 1597243.65 | COMPLETED | 1 | 12/28/20 | 12/28/20 | ELEC2020-R8-BILIRAN-002 | [6 empty] | MB Ang Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Biliran | 120788 | CABUCGAYAN CS | CABUCGAYAN | 0 | 1 | UPGRADING |  | 1845539.23 | 1840527.68 | COMPLETED | 1 | 12/28/20 | 12/28/20 | ELEC2020-R8-BILIRAN-003 | [6 empty] | MB Ang Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Biliran | 303323 | CABUCGAYAN NHS | CABUCGAYAN | 0 | 1 | UPGRADING |  | 2094055.88 | 2086877.03 | COMPLETED | 1 | 12/28/20 | 12/28/20 | ELEC2020-R8-BILIRAN-004 | [6 empty] | MB Ang Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Biliran | 500411 | INASUYAN IS | KAWAYAN | 0 | 1 | UPGRADING |  | 1719745.19 | 1714750.25 | COMPLETED | 1 | 12/28/20 | 12/28/20 | ELEC2020-R8-BILIRAN-009 | [6 empty] | MB Ang Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Biliran | 120834 | KAWAYAN CS | KAWAYAN | 0 | 1 | UPGRADING |  | 1592369.85 | 1586595.66 | COMPLETED | 1 | 12/28/20 | 12/28/20 | ELEC2020-R8-BILIRAN-010 | [6 empty] | MB Ang Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Biliran | 120860 | NAVAL CS | NAVAL | 0 | 1 | UPGRADING |  | 2655167.6 |  | COMPLETED | 1 |  |  | ELEC2020-R8-BILIRAN-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Borongan City | 122372 | BUGAS ELEMENTARY SCHOOL | Borongan City | 0 | 1 | UPGRADING |  | 1551977.85 | 1550000 | COMPLETED | 1 | JAN. 17, 2021 | DEC. 15, 2020 | ELEC2020 - R8 - BORONGAN CITY - 001 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schoolsn | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 | NOV. 9, 2020 | NOV. 11, 2020 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Borongan City | 122404 | SAN SATURNINO ELEMENTARY SCHOOL | Borongan City | 0 | 1 | UPGRADING |  | 1424913.98 | 860000 | COMPLETED | 1 | DEC. 4, 2020 | NOV. 30, 2020 | ELEC2020 - R8 - BORONGAN CITY - 004 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schoolsn - Lot 2 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 | AUG. 28, 2020 | SEPT. 1, 2020 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Borongan City | 122407 | SURIBAO ELEMENTARY SCHOOL | Borongan City | 0 | 1 | UPGRADING |  | 869954.57 | 1415000 | COMPLETED | 1 | DEC. 4, 2020 | NOV. 30, 2020 | ELEC2020 - R8 - BORONGAN CITY - 003 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schoolsn - Lot 3 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 | AUG. 28, 2020 | SEPT. 1, 2020 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Calbayog City | 194001 | Calbayog City SPED Center | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 956248.5 | 946443.2 | COMPLETED | 1 |  |  | ELEC-2020 - R8-CALBAYOG CITY-001 |  | Oct. 27, 2020 | Oct. 30, 2021 | Nov. 3, 2020 | Dec. 11, 2020 |  | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Calbayog City | 124006 | Calbayog East Central Elementary School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 2062355.88 | 2042815.11 | COMPLETED | 1 |  |  | ELEC-2020 - R8-CALBAYOG CITY-002 |  | Oct. 27, 2020 | Oct. 30, 2021 | Nov. 3, 2020 | Dec. 11, 2020 |  | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Calbayog City | 124137 | Malaga Central Elementary School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 999370.74 | 986852.45 | COMPLETED | 1 |  |  | ELEC-2020 - R8-CALBAYOG CITY-003 |  | Oct. 27, 2020 | Oct. 30, 2021 | Nov. 3, 2020 | Dec. 11, 2020 |  | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Calbayog City | 124070 | Oquendo Central School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 1882118.05 |  | COMPLETED | 1 |  |  | ELEC-2020 - R8-CALBAYOG CITY-004 |  | Oct. 27, 2020 | Oct. 30, 2021 | Nov. 3, 2020 | Dec. 11, 2020 |  | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Calbayog City | 124048 | San Policarpo Central Elem. School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 1931678.07 | 1920026.8 | COMPLETED | 1 |  |  | ELEC-2020 - R8-CALBAYOG CITY-006 |  | Oct. 27, 2020 | Oct. 30, 2021 | Nov. 3, 2020 | Dec. 11, 2020 |  | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Catbalogan City | 123439 | Silanga Elementary School | Catbalogan City | 2 | 1 | UPGRADING |  | 985061.87 |  | COMPLETED | 1 |  |  | ELEC2020 - R8 - CATBALOGAN CITY - 001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Catbalogan City | 123428 | Socorro Elementary School | Catbalogan City | 2 | 1 | UPGRADING |  | 870579.39 |  | COMPLETED | 1 |  |  | ELEC2020 - R8 - CATBALOGAN CITY - 002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 313520 | Carapdapan National High School | ARTECHE | 0 | 1 | UPGRADING |  | 1491278.49 |  | COMPLETED | 1 |  |  | ELEC2020 - R8 - EASTERN SAMAR - 025 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 313521 | Dapdap National Technical Vocational High School | DOLORES | 0 | 1 | UPGRADING |  | 1082114.71 | 1070000 | COMPLETED | 1 |  |  | ELEC2020 - R8 - EASTERN SAMAR - 011 | ELEC2020 - R8 - EASTERN SAMAR - 012 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 122534 | Banahao Elementary School | GUIUAN | 0 | 1 | UPGRADING |  | 591827.37 | 590146.95 | COMPLETED | 1 |  |  | ELEC2020 - R8 - EASTERN SAMAR - 002 | ELEC2020 - R8 - EASTERN SAMAR - 003 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 122521 | Campoyong Elementary School | GUIUAN | 0 | 1 | UPGRADING |  | 1277433.98 | 1269853.05 | COMPLETED | 1 |  |  | ELEC2020 - R8 - EASTERN SAMAR - 004 | ELEC2020 - R8 - EASTERN SAMAR - 005 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 122349 | Lawaan Central Elementary School | LAWAAN | 0 | 1 | UPGRADING |  | 1774394.72 | 1768000 | COMPLETED | 1 |  |  | ELEC2020 - R8 - EASTERN SAMAR - 027 | ELEC2020 - R8 - EASTERN SAMAR - 028 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 500235 | Dao Integrated School | ORAS | 0 | 1 | UPGRADING |  | 1228899.12 | 1218000 | COMPLETED | 1 |  |  | ELEC2020 - R8 - EASTERN SAMAR - 026 | ELEC2020 - R8 - EASTERN SAMAR - 027 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 122708 | Buabua Elementary School | SALCEDO | 0 | 1 | UPGRADING |  | 1939734.44 | 1930000 | COMPLETED | 1 |  |  | ELEC2020 - R8 - EASTERN SAMAR - 003 | ELEC2020 - R8 - EASTERN SAMAR - 004 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 122731 | San Julian Central Elementary School | SAN JULIAN | 0 | 1 | UPGRADING |  | 1595953.93 | 1594579.11 | COMPLETED | 1 |  |  | ELEC2020 - R8 - EASTERN SAMAR - 028 | ELEC2020 - R8 - EASTERN SAMAR - 029 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 122774 | San Rafael Elementary School | TAFT | 0 | 1 | UPGRADING |  | 302045.74 | 295420.89 | COMPLETED | 1 |  |  | ELEC2020 - R8 - EASTERN SAMAR - 021 | ELEC2020 - R8 - EASTERN SAMAR - 016 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303386 | Kiling National High School | TANAUAN | 1 | 1 | UPGRADING |  | 1329322.98 | 1297441.71 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-010 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303391 | Daniel Z. Romualdez State Comprehensive School of Fisheries | TOLOSA | 1 | 1 | UPGRADING |  | 805004.86 | 792280.74 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-043 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303354 | Burauen National High School | BARAUEN | 2 | 1 | UPGRADING |  | 1677259.6 | 1198763.13 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-003 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | NETS ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 313325 | Hibunauan National High School | BARAUEN | 2 | 1 | UPGRADING |  | 1001808.54 | 716151.59 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-022 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | NETS ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303367 | Don Mariano Salvacion Memorial National High School | CAPOOCAN | 2 | 1 | UPGRADING |  | 873899.3 | 503770.13 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-005 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303369 | Dulag National High School | DULAG | 2 | 1 | UPGRADING |  | 743766.1 | 541761.61 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-006 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303428 | Sta. Ana National High School | LA PAZ | 2 | 1 | UPGRADING |  | 1397248.46 | 1025969.38 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-017 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303397 | Macarthur National High School | MACARTHUR | 2 | 1 | UPGRADING |  | 1797196.33 | 1041227.93 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-015 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303380 | Juan Villablanca Memorial High School | PASTRANA | 2 | 1 | UPGRADING |  | 2970335.67 | 1724004.22 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-009 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303358 | Calubian National High School (Calubian Nat'l. Voc'l. School) | CALUBIAN | 3 | 1 | UPGRADING |  | 2367360.56 | 1373016.19 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-026 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303378 | Isabel National High School | ISABEL | 4 | 1 | UPGRADING |  | 2563699.74 | 1487565.01 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-008 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303422 | San Francisco National High School | ISABEL | 4 | 1 | UPGRADING |  | 995962.3 | 574966.58 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-020 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303335 | Abuyog National High School | ABUYOG | 5 | 1 | UPGRADING |  | 2546085.48 | 1489874.66 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-001 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 120904 | Bernardo V. Closa Central School | ABUYOG | 5 | 1 | UPGRADING |  | 995109.23 | 711515.82 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-023 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | NETS ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 313313 | Libertad National High School | ABUYOG | 5 | 1 | UPGRADING |  | 798007.3 | 570597.94 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-012 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | NETS ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303338 | Anahawan National High School | BATO | 5 | 1 | UPGRADING |  | 1687480.85 |  | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-025 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303347 | Bato School of Fisheries | BATO | 5 | 1 | UPGRADING |  | 2163896.08 | 1692178.29 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-032 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | BCG DESIGN AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303350 | Bontoc Senior High School | HINDANG | 5 | 1 | UPGRADING |  | 1537927.06 | 913047.8 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-002 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 313329 | Capudlosan National High School | HINDANG | 5 | 1 | UPGRADING |  | 889891.86 | 696900.42 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-004 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | BCG DESIGN AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303405 | Matalom National High School | MATALOM | 5 | 1 | UPGRADING |  | 1703686.08 | 1012030.8 | COMPLETED | 1 |  |  | ELEC2020-R8-LEYTE-014 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Maasin City | 122129 | Guadalupe Elementary School | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING |  | 477093.71 | 470814.34 | COMPLETED | 1 |  |  | ELEC2020-R8-MAASIN CITY-001 | ELECTRIFICTION-20-001 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2020-02-13 | 2020-10-09 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Maasin City | 313401 | Maasin City NHS | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING |  | 2862262.71 | 2147479.63 | COMPLETED | 1 |  |  | ELEC2020-R8-MAASIN CITY-004 | ELECTRIFICATION-20-Batch 2-001 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-07-30 | 2021-08-12 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Maasin City | 122139 | Manhilo ES | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING |  | 495031.46 | 488407.87 | COMPLETED | 1 |  |  | ELEC2020-R8-MAASIN CITY-005 | ELECTRIFICTION-20-001 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2020-02-13 | 2020-10-09 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Maasin City | 501050 | Maria Clara Integrated School | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING |  | 685660.96 | 676528.93 | COMPLETED | 1 |  |  | ELEC2020-R8-MAASIN CITY-006 | ELECTRIFICTION-20-002 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2020-02-13 | 2020-10-09 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Maasin City | 122174 | San Rafael ES | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING |  | 751393.08 | 740070.54 | COMPLETED | 1 |  |  | ELEC2020-R8-MAASIN CITY-007 | ELECTRIFICTION-20-002 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2020-02-13 | 2020-10-09 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Maasin City | 122146 | Tam-Is ES | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING |  | 441197.89 | 433917.53 | COMPLETED | 1 |  |  | ELEC2020-R8-MAASIN CITY-008 | ELECTRIFICTION-20-001 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2020-02-13 | 2020-10-09 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Northern Samar | 303531 | Allen National High School | ALLEN | 1 | 1 | UPGRADING |  | 4179247.27 |  | COMPLETED | 1 |  |  | ELEC-2020 - R8-NORTHERN SAMAR-013 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Northern Samar | 303561 | Basilio B. Chan Mem. Agricultural and Industrial Sch. | LAVEZARES | 1 | 1 | UPGRADING |  | 3153143.95 |  | COMPLETED | 1 |  |  | ELEC-2020 - R8-NORTHERN SAMAR-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Northern Samar | 303551 | Gala Vocational School | GAMAY | 2 | 1 | UPGRADING |  | 4181233.91 |  | COMPLETED | 1 |  |  | ELEC-2020 - R8-NORTHERN SAMAR-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Northern Samar | 303538 | Cahayagan NHS | LAOANG | 2 | 1 | UPGRADING |  | 1263351.56 |  | REVERTED | 0 |  |  | ELEC-2020 - R8-NORTHERN SAMAR-015 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2020 | Region VIII | Northern Samar | 303559 | Lorenzo S. Menzon AIS | LAPINIG | 2 | 1 | UPGRADING |  | 2782521.44 |  | COMPLETED | 1 |  |  | ELEC-2020 - R8-NORTHERN SAMAR-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Northern Samar | 303584 | SUMOROY AGRO-INDUSTRIAL SCHOOL | PALAPAG | 2 | 1 | UPGRADING |  | 4842800.53 |  | COMPLETED | 1 |  |  | ELEC-2020 - R8-NORTHERN SAMAR-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Ormoc City | 124200 | Airport Elementary School | ORMOC CITY | 4 | 1 | UPGRADING |  | 1108047.84 | 1092971.7328 | COMPLETED | 1 |  |  | ELEC2020-R8-ORMOC CITY-002 | [6 empty] | SILVERSOCKET ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Ormoc City | 124210 | Lao Elementary School | ORMOC CITY | 4 | 1 | UPGRADING |  | 1103219.18 | 1088087.5383 | COMPLETED | 1 |  |  | ELEC2020-R8-ORMOC CITY-003 | [6 empty] | VHITS D.G. Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Ormoc City | 124161 | Macabug Elementary School | ORMOC CITY | 4 | 1 | UPGRADING |  | 1106855.79 | 1085999.9864 | COMPLETED | 1 |  |  | ELEC2020-R8-ORMOC CITY-001 | [6 empty] | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303618 | Ramon T. Diaz NHS | GANDARA | 1 | 1 | UPGRADING |  | 4258691.09 | 4156897.2 | COMPLETED | 1 |  |  | ELEC-2020 - R8-WESTERN SAMAR-014 | Electrical System Upgrade and Rewiring -L1 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303612 | Matuguinao National High School | MATUGUINAO | 1 | 1 | UPGRADING |  | 1157628.07 | 1254211.56 | COMPLETED | 1 |  |  | ELEC-2020 - R8-WESTERN SAMAR-025 | Electrical System Upgrade and Rewiring - L2 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | VHITS DG BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303615 | Pagsanghan NHS | PAGSANGHAN | 1 | 1 | UPGRADING |  | 2062902.13 | 2042871 | COMPLETED | 1 |  |  | ELEC-2020 - R8-WESTERN SAMAR-013 | Electrical System Upgrade and Rewiring - L3 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | NV&C Construction & General Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303630 | Napuro NHS | SANTA MARGARITA | 1 | 1 | UPGRADING |  | 963427.41 | 960465 | COMPLETED | 1 |  |  | ELEC-2020 - R8-WESTERN SAMAR-016 | Electrical System Upgrade and Rewiring - L4 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | NV&C Construction & General Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303592 | BASEY NHS | BASEY | 2 | 1 | UPGRADING |  | 5045609.5 | 5024994.19 | COMPLETED | 1 |  |  | ELEC-2020 - R8-WESTERN SAMAR-004 | Electrical System Upgrade and Rewiring - L5 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | MAGA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303628 | Simeon Ocdol NHS | BASEY | 2 | 1 | UPGRADING |  | 2670135.96 | 2655120.6 | COMPLETED | 1 |  |  | ELEC-2020 - R8-WESTERN SAMAR-027 | Electrical System Upgrade and Rewiring - L6 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | GPUY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 313730 | Baclayan NHS | DARAM | 2 | 1 | UPGRADING |  | 911420.18 | 939520.89 | COMPLETED | 1 |  |  | ELEC-2020 - R8-WESTERN SAMAR-001 | Electrical System Upgrade and Rewiring - L7 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | GPUY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303595 | Birawan NHS | DARAM | 2 | 1 | UPGRADING |  | 2105612.71 |  | COMPLETED | 1 |  |  | ELEC-2020 - R8-WESTERN SAMAR-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 313716 | Anibongon IS | SANTA RITA | 2 | 1 | UPGRADING |  | 2635204.16 | 2616137.74 | COMPLETED | 1 |  |  | ELEC-2020 - R8-WESTERN SAMAR-005 | Electrical System Upgrade and Rewiring - L8 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | PYUKEI CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303607 | Igot National High School | VILLAREAL | 2 | 1 | UPGRADING |  | 1848306.15 | 1832939.66 | COMPLETED | 1 |  |  | ELEC-2020 - R8-WESTERN SAMAR-010 | Electrical System Upgrade and Rewiring - L9 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | RICHMARK CONST. INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Southern Leyte | 303462 | ICHON NATIONAL HIGH SCHOOL | Macrohon | 0 | 1 | UPGRADING |  | 4139395.23 |  | COMPLETED | 1 |  |  | ELECTRIFICATION 2020 - R8- SOUTHERN LEYTE - 01 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Southern Leyte | 303492 | VILLA JACINTA NATIONAL VOCATIONAL HIGH SCHOOL | MACROHON | 0 | 1 | UPGRADING |  | 3185646.9 |  | COMPLETED | 1 |  |  | ELECTRIFICATION 2020 - R8- SOUTHERN LEYTE - 03 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Southern Leyte | 303453 | DON AGUSTIN F. ESCANO NATIONAL HIGH SCHOOL | TOMAS UPPOS | 0 | 1 | UPGRADING |  | 3008879.86 |  | COMPLETED | 1 |  |  | ELECTRIFICATION 2020 - R8- SOUTHERN LEYTE - 02 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 314003 | Antonio Balmes National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1264277.79 | 1254382.6 | COMPLETED | 1 |  |  | ELEC2020-R8-TACLOBAN CITY-006 | [6 empty] | NV&C CONST. AND GENERAL SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 124233 | BAYANIHAN ELEMENTARY SCHOOL | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 736784.62 | 718870.99 | COMPLETED | 1 |  |  | ELEC2020-R8-TACLOBAN CITY-014 | [6 empty] | VHITS D. G BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 303665 | Cirilo Roy Montejo National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1616282.66 | 1598300.63 | COMPLETED | 1 |  |  | ELEC2020-R8-TACLOBAN CITY-005 | [6 empty] | RM PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 500892 | Guadalupe Heights Integrated School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1298916.72 | 1290428.29 | COMPLETED | 1 |  |  | ELEC2020-R8-TACLOBAN CITY-004 | [6 empty] | RM PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 500490 | Kapuso Village Integrated School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1261385.86 | 1237160 | COMPLETED | 1 |  |  | ELEC2020-R8-TACLOBAN CITY-002 | [6 empty] | J. COSTURIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 500891 | North Hill Arbours Integrated School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1256136.19 | 1240000 | COMPLETED | 1 |  |  | ELEC2020-R8-TACLOBAN CITY-003 | [6 empty] | J. COSTURIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 500489 | Ridge View Park Integrated School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 2416007.52 | 2386007.45 | COMPLETED | 1 |  |  | ELEC2020-R8-TACLOBAN CITY-001 | [6 empty] | MASS CONST. AND CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 124227 | Rizal Central School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1280537.69 | 1265362.68 | COMPLETED | 1 |  |  | ELEC2020-R8-TACLOBAN CITY-007 | [6 empty] | BELGES CONST. AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Biliran | 120768 | Salangi Elementary School | ALMERIA | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1442658.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Biliran | 120771 | Talahid Elementary school | ALMERIA | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1379400.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Biliran | 303322 | Cabucgayan National School of Arts and Trade | CABUCGAYAN | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1895091.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122610 | Caisawan Elementary School | BALANGKAYAN | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1601371.47 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-06-28 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122476 | Binalay Elementary School | GENERAL MACARTHUR | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1669964.83 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-06-28 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122504 | Tugop Elementary School | GENERAL MACARTHUR | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2085746.9 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122509 | Gigoso Elementary School | GIPORLOS | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2776436.97 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-06-28 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122512 | Malabag Elementary School | GIPORLOS | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2086104.03 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-06-28 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122513 | Parena Elementary School | GIPORLOS | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3052462.8 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-06-28 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122516 | Salvacion Elementary School | GIPORLOS | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1877521.63 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122572 | Cagmanaba Elementary School | JIPAPAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1877521.63 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-08-26 | NV&C CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122446 | Bulawan Elementary School | MASLOG | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2120060.66 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122467 | San Roque Elementary School | MASLOG | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1878403.25 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122673 | Bagte Elementary School | QUINAPONDAN | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2262757.36 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122682 | Paco Elementary School | QUINAPONDAN | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1580167.51 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122705 | Asgad Elementary School | SALCEDO | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2149692.2 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-06-28 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122698 | Naparaan Elementary School | SALCEDO | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1741352.23 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-08-26 | NV&C CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122703 | Talangdawan Elementary School | SALCEDO | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1669316.14 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121877 | San Juan Elementary Shool | SANTA FE | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 772727.25 |  | COMPLETED | 1 | 2023-11-04 | 2023-09-25 | CY2023-BEFF-ELEC-LOT0 | CY2023-BEFF-ELEC-LOT1 | 2023-04-25 | 2023-05-03 | 2023-05-15 | 2023-06-20 | 2023-06-30 | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2023 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121879 | San Roque Elementary School | SANTA FE | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 918692.87 |  | COMPLETED | 1 | 2023-11-04 | 2023-10-16 | CY2023-BEFF-ELEC-LOT0 | CY2023-BEFF-ELEC-LOT1 | 2023-04-25 | 2023-05-03 | 2023-05-15 | 2023-06-20 | 2023-06-30 | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2023 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121880 | Sta. Fe Central School | SANTA FE | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1987746.66 |  | COMPLETED | 1 | 2024-01-03 | 2023-12-01 | CY2023-BEFF-ELEC-LOT1 | CY2023-BEFF-ELEC-LOT2 | 2023-07-18 | 2023-05-03 | 2023-07-26 | 2023-08-17 | 2023-08-29 | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2023 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 305523 | Sta. Fe Stand Alone Senior High School | SANTA FE | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2492793.04 |  | COMPLETED | 1 | 2023-11-22 | 2023-11-20 | CY2023-BEFF-ELEC-LOT2 | CY2023-BEFF-ELEC-LOT3 | 2023-04-25 | 2023-05-03 | 2023-05-15 | 2023-06-19 | 2023-06-23 | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2023 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121881 | Tibak Elementary School | SANTA FE | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 776428.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303440 | Tolosa National High School | TOLOSA | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4080740.11 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121520 | Calbasag Elementary School | JULITA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 818344.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303381 | Julita National High School | JULITA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1471270.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte |  | JULITA SENIOR HIGH SCHOOL | JULITA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1526774.3 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121530 | Sto. Nino Elementary School | JULITA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 721700.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz NHS) | LA PAZ | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2249725.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 313332 | Buracan National High School | LA PAZ | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1371927.76 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121625 | Palale Elementary School | MACARTHUR | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1269846.62 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303414 | Palale National High School | MACARTHUR | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1220104.17 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 313343 | Macalpi-ay National High School | PASTRANA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1426504.68 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 313330 | Manaybanay National High School | PASTRANA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1727293.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121825 | Pastrana Central School | PASTRANA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2010412.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121961 | Capahuan ES | TABONTABON | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 777292.87 |  | COMPLETED | 1 | 2023-10-28 |  | 2023-04-25 | 2023-05-03 | 2023-05-15 | 2023-06-19 | 2023-06-23 |  |  |  | Realigned from Himokilan ES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121912 | Guingauan Elementary School | TABONTABON | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 699542.52 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121916 | San Pablo Elementary School | TABONTABON | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 725225.28 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121917 | Tabontabon Central School | TABONTABON | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2156995.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303441 | Gregorio C. Catenza NHS (Tunga NHS) | TUNGA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2831680.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121961 | Tunga Central School | TUNGA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2291156.97 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121716 | Calunangan Elementary School | MERIDA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 833971.87 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121721 | Casilda Elementary School | MERIDA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1253532.73 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303393 | Libas National High School | MERIDA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1267471.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121725 | Lundag Elementary School | MERIDA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 890533.2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121727 | Mahalit Elementary School | MERIDA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 768212.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121732 | Puerto Bello Elementary School | MERIDA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1030561.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121403 | Capudlosan Elementary School | HINDANG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 869012.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121408 | Hindang Central School | HINDANG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1786409.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303375 | Hindang National High School | HINDANG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2134736.69 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121411 | Mabagon Elementary School | HINDANG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 884879.6 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121413 | Tabok Elementary School | HINDANG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 917163.92 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121414 | Tagbibi Elementary School | HINDANG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 885977.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303399 | MAHAPLAG NHS-UPPERS | MAHAPLAG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2824737.5 | 2774367.1 | COMPLETED | 1 | 2023-12-27 |  | 2023-07-18 |  | 2023-07-26 | 2023-08-16 | 2023-08-22 | HD GOLDEN BUILDERS & SUPPLY | Re-bid |  | Realigned from Himokilan ES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Northern Samar | 303540 | Capul Agro-Industrial School | CAPUL | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 4489207.93 |  | COMPLETED | 1 |  | 2023-11-29 | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-05-18 | 2023-05-30 |  | 2023-08-01 | HD GOLDEN BUILDERS & SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2023 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Northern Samar | 313622 | Magtaon NHS | MAPANAS | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2135962.33 |  | COMPLETED | 1 |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-10-06 | 2023-10-18 | 2023-10-25 | 2023-11-03 | J. CUSTORIO CONSTRUCTION & SUPPLY | rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Samar (Western Samar) | 123289 | Guin-ansan Elementary School | ALMAGRO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3312421.71 |  | COMPLETED | 1 | ############# | 2023-09-08 | CY2023BEFFELECLOT1 | 2023-014 | 2023-04-06 | 2023-04-14 | 2023-04-28 | 2023-05-23 | 2023-06-19 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2023 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Samar (Western Samar) | 123292 | Lunang I Elementary School | ALMAGRO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3498488.78 |  | COMPLETED | 1 | ############# | 2023-09-08 | CY2023BEFFELECLOT2 | 2023-015 | 2023-04-06 | 2023-04-14 | 2023-04-28 | 2023-05-23 | 2023-06-19 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2023 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Samar (Western Samar) | 313713 | Villahermosa Integrated School | PAGSANGHAN | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2053376.78 |  | COMPLETED | 1 | ############# | 2023-09-21 | CY2023BEFFELECLOT3 | 2023-016 | 2023-04-06 | 2023-04-14 | 2023-04-28 | 2023-05-23 | 2023-06-19 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2023 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Samar (Western Samar) | 123593 | Jiabong Central Elementary School | JIABONG | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2745446.97 |  | COMPLETED | 1 | ############# | 2023-09-21 | CY2023BEFFELECLOT4 | 2023-017 | 2023-04-06 | 2023-04-14 | 2023-04-28 | 2023-05-23 | 2023-06-19 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2023 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Southern Leyte | 303465 | LIMASAWA NATIONAL HIGH SCHOOL | LIMASAWA | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 3615152.31 | 3437262.47 | COMPLETED | 1 | 2024-02-16 | Not yet completed | CY2023-ELECTRIFICATION-L1 | CY2023-ELECTRIFICATION-L1 | 2023-06-20 | 2023-06-29 | 2023-07-11 |  | 2023-10-19 | Victoria Development and Ventures Corp. | Contract Expired | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | SOLAR | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Southern Leyte | 303483 | San Ricardo National High School | SAN RICARDO | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2575774.71 | 2449982.31 | COMPLETED | 1 | 2024-01-17 | Not yet completed | CY2023-ELECTRIFICATION-L2 | CY2023-ELECTRIFICATION-L2 | 2023-06-20 | 2023-06-29 | 2023-07-11 |  | 2023-10-19 | Victoria Development and Ventures Corp. | Contract Expired | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Baybay City | 121089 | Kilim Elementary School | CITY OF BAYBAY | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1011775.91 | 940447.2 | COMPLETED | 1 | 2024-08-25 | 2024-07-05 | 2023-12-I002 | 2023-12-I002 |  | 2023-12-11 | 2023-12-27 | 2024-05-23 | 2024-05-27 | J.A. CONSTRUCTION AND TRADING CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 7.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Biliran | 120758 | Almeria CS | ALMERIA | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1956456.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Borongan City | 122386 | SAN PABLO ES | BORONGAN CITY | Lone | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 1910064.17 | 1889381.54 | COMPLETED | 1 | [6 empty] | 2024-11-07 |  | 2024-05-07 | Lobrinos Consolidated Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 7.24 | SOLAR | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Calbayog City | 124128 | Tinambacan Central School | CALBAYOG CITY | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2733516.07 | 2711092.15 | COMPLETED | 1 | 2024-11-01 | 2024-08-27 | 2024-RVIII-CALBAYOG-EP |  | 2024-03-26 | 2024-04-03 | 2024-05-15 | 2024-05-27 | 2024-07-19 | JFR CONSTRUCTION, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Catbalogan City | 123399 | Libas Elementary School | CITY OF CATBALOGAN (Capital) | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 895038.5 |  | Under Procurement | 0 | [10 empty] | RTA submitted to CO- waiting for approval of downloading of funds | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING | not yet started
ELECTRIFICATION 2024 | Region VIII | Eastern Samar | 122325 | Arteche Central Elementary School | ARTECHE | Lone | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3336938.1 | 3316854.65 | COMPLETED | 1 | 2024-08-21 |  | CY2024-BEFF-ELEC-ES-C1 | CY2024-BEFF-ELEC-ES-C1 | 2023-10-13 | 2023-10-24 | 2023-11-08 | 2024-05-09 | 2024-05-16 | YFL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | SOLAR | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Eastern Samar | 313522 | Concepcion National High School | ARTECHE | Lone | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 1886379.12 | 1866325.43 | COMPLETED | 1 | 2024-08-21 | 2024-08-20 | CY2024-BEFF-ELEC-ES-C2 | CY2024-BEFF-ELEC-ES-C2 | 2023-10-13 | 2023-10-24 | 2023-11-08 | 2024-05-09 | 2024-05-16 | YFL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | SOLAR | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Leyte | 303429 | Sta. Cruz National High School | SAN MIGUEL | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2459541.74 | 1498109.28 | COMPLETED | 1 | 2024-12-25 |  |  |  | 2024-11-09 | 2024-11-17 | 2023-12-04 | 2024-07-02 | 2024-08-20 | J.CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Leyte | 303361 | Carigara National High School | CARIGARA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2982440.59 | 2962361.35 | COMPLETED | 1 |  |  |  |  | 2024-11-09 | 2024-11-17 | 2023-12-04 | 2024-01-18 | 2024-06-05 | HD GOLDEN BUILDERS AND SUPPLY, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Leyte | 121600 | Macupa Central School | LEYTE | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1796111.56 | 1109313.84 | COMPLETED | 1 | 2024-12-25 |  |  |  | 2024-11-09 | 2024-11-17 | 2023-12-04 | 2024-07-02 | 2024-08-20 | J.CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Leyte | 313328 | Kananga National High School - Montebello Annex | KANANGA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1397251.53 | 862667.04 | COMPLETED | 1 | 2024-12-25 |  |  |  | 2024-11-09 | 2024-11-17 | 2023-12-04 | 2024-07-02 | 2024-08-20 | J.CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Leyte | 121378 | Baas Elementary School | HILONGOS | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 998861.08 | 848777.46 | COMPLETED | 1 |  |  |  |  | 2024-11-09 | 2024-11-17 | 2023-12-04 | 2024-01-18 | 2024-06-05 | HD GOLDEN BUILDERS AND SUPPLY, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 8.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Maasin City | 323103 | Lunas National High School | CITY OF MAASIN (Capital) | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2950439.41 | 2766444.12 | ONGOING | 0.95 |  |  | INFRA-2024-02 | INFRA-2024-02 | 2024-02-27 | 2024-03-12 | 2024-03-27 | 2024-05-27 |  | M.G. VILLAMIN CONSTRUCTION | For Variation Order | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.95 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region VIII | Northern Samar | 303534 | BIRI NATIONAL HIGH SCHOOL | BIRI | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3162928.14 | 3162928.14 | COMPLETED | 1 | [6 empty] | 2023-11-20 |  |  | Open Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Northern Samar | 313613 | La Perla NHS | LAOANG | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2394649.4 | 2394649.4 | COMPLETED | 1 | [6 empty] | 2023-11-20 |  |  | HD Golden Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Ormoc City | 305904 | Salvacion National High School | ORMOC CITY | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1565073.02 | 1317783.58 | COMPLETED | 1 | 2024-09-06 | 2024-08-30 | ELEC-2024-RVIII-ORMOC-001 | BEFF-CY-2024-ELECTRIFICATION-L1 | 2024-01-25 | 2024-02-01 | 2024-02-13 | 2024-02-24 | 2024-06-06 | JA Construction and Trading Corporation | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 8.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Samar (Western Samar) | 123542 | Gandara II Central Elementary School | GANDARA | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2120724.46 | 2109908.47 | COMPLETED | 1 | 2024-08-27 | 2024-09-11 | elec-2024-samar-lot1 | 2024-001 |  | 2024-11-08 | 2024-12-01 |  | 2024-05-22 | GPUY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Samar (Western Samar) | 303608 | Talalora National High School | TALALORA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2175763.84 | 2155204.63 | COMPLETED | 1 | 2024-08-27 | 2024-09-23 | elec-2024-samar-lot2 | 2024-002 |  | 2024-11-08 | 2024-12-01 |  | 2024-05-22 | GPUY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Southern Leyte | 303458 | Hilaan NHS | BONTOC | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3108855.25 | 2086463 | COMPLETED | 1 | 2024-10-11 |  | CY2024-BEFF-ELECTRIFICATION-L1 | CY2024-BEFF-ELECTRIFICATION-L1 | 2023-10-20 | 2023-10-27 | 2023-11-09 |  | 2024-06-13 | VHITS D. G. BUILDERS AND ENTERPRISES | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Southern Leyte | 122323 | Tomas Oppus Central School | TOMAS OPPUS | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2621273.29 | 1760901.44 | COMPLETED | 1 | 2024-10-11 |  | CY2024-BEFF-ELECTRIFICATION-L2 | CY2024-BEFF-ELECTRIFICATION-L2 | 2023-10-20 | 2023-10-27 | 2023-11-09 |  | 2024-06-13 | VHITS D. G. BUILDERS AND ENTERPRISES | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Southern Leyte | 122252 | San Juan Central Elementary School with SPED CENTER | SAN JUAN (CABALIAN) | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4461051.31 | 2737144.42 | COMPLETED | 1 | 2024-11-10 |  | CY2024-BEFF-ELECTRIFICATION-L3 | CY2024-BEFF-ELECTRIFICATION-L3 | 2023-10-20 | 2023-10-27 | 2023-11-09 |  | 2024-06-13 | HD GOLDEN BUILDERS AND SUPPLY INC. | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Tacloban City | 124245 | Dr. AP Banez Memorial School | TACLOBAN CITY (Capital) | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1750534.4 | 1730780.61 | COMPLETED | 1 | 2024-09-15 | 2024-08-20 | CY 2024 BEFF_SCHOOL ELECTRIFICATION-02 | 02-2024 BEFF SE-02 | 2024-11-07 | 2023-11-14 | 2023-11-27 | 2023-11-30 | 2024-06-11 | KAMARI CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | COMPLETED

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%