## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | Total Physical Target | SCOPE OF WORK | PROJECT ALLOCATION | Batch | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 4, 2025
SCHOOL HEALTH FACILITIES 2024 | Region XI | Davao City | 304359 | Daniel R. Aguinaldo NHS | DAVAO CITY | 1st | 1 | - | Construction of Health Facility with 2 units Comfort Rooms and 2 units Handwashing | 5163932.14 | - | 4464112.6 | Completed | 1 | Sept. 29, 2024 |  | BEFF-L002-2024 | #3s.2024 INF DL-XI | Oct 27-Nov 16, 2023 | Nov.3, 2023 | Nov.16, 2023 | Jan.12, 2024 | May 29, 2024 | Panabo General Contractors Development | work suspended due to change location and Approval of Demolition Permit
SCHOOL HEALTH FACILITIES 2024 | Region XI | Davao De Oro | 128302 | Kapatagan ES | LAAK (SAN VICENTE) | 2nd | 1 | - | Construction/Repair of Health Facilities | 5000000 | - | 3545990.37 | COMPLETED | 1 | June 5, 2025 | June 4, 2025 | SDDO-016-2024 | SDDO-016-2024 | Aug. 6, 2024 | Aug. 18, 2024 | September 9, 2024 | September 30, 2024 | January 6, 2025 | JJR ACE CONSTRUCTION AND SUPPLY CORP
SCHOOL HEALTH FACILITIES 2024 | Region XI | Davao del Norte | 128652 | Gov. Dujali ES | SAN ISIDRO | 1st | 1 | - | Construction/Repair of Health Facilities | 3600000 | - | 3324097.66 | ongoing | 0.98 |  |  |  |  | January 10, 2024 | January 17, 2024 | January 30, 2924 | March 19, 2024 | June 28, 2024 | MJTP Construction | On-going
SCHOOL HEALTH FACILITIES 2024 | Region XI | Davao del Sur | 304298 | Tacul Agricultural High School | MAGSAYSAY | 1st | 1 | - | Construction/Repair of Health Facilities | 4335202 | - | 3444215.43 | Completed | 1 | February 11, 2025 | February 11, 2025 | DS- SCHBLDG - 2024 - E - LOT 2 | DS- SCHBLDG - 2024 - E - LOT 2 | May 21, 2024 | May 28, 2024 | June 07, 2024 | August 09, 2024 | September 5, 2024 | IRE INDUSTRIAL FACILITIES CONSTRUCTION | completed
SCHOOL HEALTH FACILITIES 2024 | Region XI | Davao Occidental | 304292 | John Martin Johnson High School (Lamidan) | DON MARCELINO | Lone | 1 | - | Construction of School Clinic | 3265907.06 | - | 3263892.8 | Completed | 1 | November 14,2024 | November 14,2024 | ITB W-02-2024 | contract no. 2024-007 | April 15, 2024- April 29, 2024 | April 23, 2024 | April 29, 2024 | resolution no. 08,s. 2024 | July 17, 2024 | Digos Constrak Corporation | On-going
SCHOOL HEALTH FACILITIES 2024 | Region XI | Davao Oriental | 129356 | Gregorio Moralizon ES 1 | MANAY | 1st | 1 | - | Construction of School Clinic | 5110702.18 | - | 4002640.57 | Completed | 1 | August 20, 2024 | October 16, 2024 | GS 2023 154 | 2024-002 | December 8, 2023 | December 15, 2023 | December 27,2023 | May 2, 2024 | May 22, 2024 | ELLE | Completed w/ Time Extension
SCHOOL HEALTH FACILITIES 2024 | Region XI | Digos City | 304400 | Digos City NHS (Davao Del Sur NHS) | CITY OF DIGOS (Capital) | 1st | 1 | - | Construction of Clinic & Const of 4UNITS 3 Seater CR with Handwashing | 5487480.98 | - | 4236026.94 | Completed | 1 | Nov. 22, 2024 | Nov. 12, 2024 | 42059 | 42059 | March 6-26, 2024 | March 12, 2024 | March 26, 2024 | June 06,2024 | July 18, 2024 | RRJJ Quinto Builders Corp. | Completed
SCHOOL HEALTH FACILITIES 2024 | Region XI | Island Garden City of Samal | 128598 | Angel Villarica Central Elementary School | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 | - | Construction/Repair of Health Facilities | 5500000 | - | 4553697.99 | Completed | 1 | September 20, 2024 | September 2, 2024 | infra 001-11-2023 | infra 001-11-2023 | October 31, 2023 | November 8, 2025 | November 20, 2023 | December 12, 2025 | May 23, 2024 | R. Fabale Const. Corp. | Completed
SCHOOL HEALTH FACILITIES 2024 | Region XI | Panabo City | 129783 | Gredu ES | CITY OF PANABO | 2nd | 1 | - | Construction/Repair of Health Facilities | 3000000 | - |  | Under Procurement | 0 | [10 empty] | DO would like to revert- with request for additional fund
SCHOOL HEALTH FACILITIES 2024 | Region XI | Tagum City | 128768 | APOKON ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1st | 1 | - | Construction/Repair of Health Facilities | 3000000 | - | 2390532.83 | ongoing | 0.95 | March 3, 2025 | June 30, 2025 | NEWCON 2024 - HEALTH FACILITY - RXI - TAGUM CITY – 001 | NEWCON 2024 - HEALTH FACILITY - RXI - TAGUM CITY – 001 | June 28, 2024 | July 8, 2024 | July 22, 2024 | Aug. 12, 2024 | Oct.. 8, 2024 | Al Handasa Const. | Physically Completed
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 500859 | Igangon Integrated School | SAN ISIDRO | 2 | 1 | 12 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - 2 SETS OF 12 FAUCETS | 497885.97 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 315906 | Pinamuno National High School | SAN ISIDRO | 2 | 1 | 7 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - 1 SET OF 7 FAUCETS | 254314.72 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 128581 | Mamangan ES | SAN ISIDRO | 2 | 1 | 7 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - 1 SET OF 7 FAUCETS | 262714.72 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 128656 | Libuton ES | SAN ISIDRO | 2 | 1 | 7 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - 1 SET OF 7 FAUCETS | 262714.72 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 128581 | Mamangan ES | SAN ISIDRO | 1 | 1 | 1 | CONSTRUCTION OF SCHOOL CLINIC | 3259817.87 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 128590 | Sabangan ES | SAN ISIDRO | 1 | 1 | 1 | CONSTRUCTION OF SCHOOL CLINIC | 3213617.87 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 128657 | Linao ES | SAN ISIDRO | 1 | 1 | 1 | REPAIR/CONVERSION OF 1 CL TO SCHOOL CLINIC | 1010630.12 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 500859 | Igangon Integrated School | SAN ISIDRO | 1 | 1 | 1 | CONSTRUCTION OF SCHOOL CLINIC | 3226217.87 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129374 | Badas ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 220962.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129380 | Rabat-Rocamora Mati CES I | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | MATT GLASS ALUMINUM SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129381 | Rabat-Rocamora Mati CES II | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | MATT GLASS ALUMINUM SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129382 | Mayor Luisito G. Rabat MS | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 1 | 2022-11-05 | [8 empty] | MATT GLASS ALUMINUM SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129383 | Mayor Santiago Garcia MS | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 1 | 2022-11-05 | [8 empty] | MATT GLASS ALUMINUM SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 205504 | Rabat Rocamora Mati Central School SPED Center | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | MATT GLASS ALUMINUM SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 500454 | Licop Integrated School | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 220962.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129388 | Antonino Vicentino ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 220962.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129390 | Bobon ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 218862.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129392 | Cabubuanan Elementary School | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129395 | Don Luis Rabat Sr. MS | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129396 | Don Salvador Lopez ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 219912.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129418 | Magum ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 220437.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129398 | Gov. Leopoldo Lopez Sr. MS | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 1 | 2022-11-05 | [8 empty] | MATT GLASS ALUMINUM SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129405 | Taguibo ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 220962.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129409 | Vicente Almario Sr. MS | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129414 | Francisco Hinayon ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 220962.01 | BATCH 1 |  | Completed | 1 | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%