## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | Total Physical Target | SCOPE OF WORK | PROJECT ALLOCATION | Batch | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 4, 2025
SCHOOL HEALTH FACILITIES 2024 | Region XII | General Santos City | 304641 | Fatima National High School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | - | 1STY1CL Dental/Medical Clinic | 3538288.18 | - | 2761101.88 | ongoing | 0.7 | 90 CD | On-Going | 011-2024 | 011-2024 | 2024-11-09 | 9/23/2024 | 2024-07-10 | 2024-11-10 | 01/13/2025 | BEBCON BUILDERS AND SUPPLY | On-Going
SCHOOL HEALTH FACILITIES 2024 | Region XII | South Cotabato | 304560 | Polomolok National High School | POLOMOLOK | 1st | 1 | - | Construction of School Clinic | 2900000 | - | 2170506.18 | ongoing | 0.6587 | June 8, 2025 |  | DSC-24-06-111 | 2025-002 | June 25, 2024 | July 3, 2024 | July 23, 2024 | September 6, 2024 | January 16, 2025 | RYCH CONSTRUCTION | On-going
SCHOOL HEALTH FACILITIES 2024 | Region XII | South Cotabato | 304575 | Tupi National High School | TUPI | 1st | 1 | - | Repair of School Clinic | 750000 | - | 1484161.96 | ongoing | 0.9878 | June 8, 2025 |  | DSC-24-06-111 | 2025-004 | June 25, 2024 | July 3, 2024 | July 23, 2024 | September 6, 2024 | January 16, 2025 | RYCH CONSTRUCTION | TUPI NHS AND TBOLI NHS ONE CONTRACT (CLUSTER)
SCHOOL HEALTH FACILITIES 2024 | Region XII | South Cotabato | 304555 | Libertad National High School | SURALLAH | 2nd | 1 | - | Construction of School Clinic | 2900000 | - | 2189306.87 | ongoing | 0.8794 | June 8, 2025 |  | DSC-24-06-111 | 2025-003 | June 25, 2024 | July 3, 2024 | July 23, 2024 | September 6, 2024 | January 16, 2025 | RYCH CONSTRUCTION | On-going
SCHOOL HEALTH FACILITIES 2024 | Region XII | South Cotabato | 304574 | Tboli National High School | T'BOLI | 2nd | 1 | - | Repair of School Clinic | 750000 | - | clustered to tupi nhs | ongoing | 0.9515 | June 8, 2025 |  | DSC-24-06-111 | 2025-004 | June 25, 2024 | July 3, 2024 | July 23, 2024 | September 6, 2024 | January 16, 2025 | RYCH CONSTRUCTION | TUPI NHS AND TBOLI NHS ONE CONTRACT (CLUSTER)
SCHOOL HEALTH FACILITIES 2024 | Region XII | Sultan Kudarat | 304594 | Kalanawe II National High School | PRESIDENT QUIRINO | 1st | 1 | - | Construction/Repair of Health Facilities | 3374434.48 | - | 2555554.86 | Completed | 1 | 2024-12-07 | 2024-12-03 | 24-01-006 | 24-01-006-01 | 2024-04-05 | 2024-04-17 | 2024-04-29 | 2024-05-08 | Sept. 02, 2024 | Rivier-Stone Construction Services | Completed
SCHOOL HEALTH FACILITIES 2024 | Region XII | Sultan Kudarat | 130914 | Kapaya Elementary School | BAGUMBAYAN | 2nd | 1 | - | Construction/Repair of Health Facilities | 3374434.47 | - | 2332180.48 | Completed | 1 | 2024-12-08 | 2024-11-12 | 24-01-006 | 24-01-006-02 | 2024-04-05 | 2024-04-17 | 2024-04-29 | 2024-05-08 | Sept. 03, 2024 | RYCH Construction | Completed

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%