## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated/ Abandoned | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated/ Abandoned | No. of Sites Reverted.1 | No. of Sites Not yet started.1 | No. of Sites Under Procurement.1 | No. of Sites On Going.1 | No. of Sites Completed.1 | No. of Sites Terminated/ Abandoned.1 | Previous % | Difference | Month Completed | OGP SCHOOLS with DCP Packages | TO BE COMPLETED BY 2023 | TO BE COMPLETED BY 2023.1 | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM ADMINISTRATION | Batch | Municipality Class | Provision of Solar Panel | Status as of July 4, 2025
LMS 2020 | Region XII | North Cotabato | 130239 | Dungoan ES | M'LANG | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20128417.6491 | 0 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2020 | Region XII | North Cotabato | 100863 | Colonsalnafil Elementary School | TULUNAN | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19394758.1121 | 0 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 | 1 | [5 empty] | CY 2023 |  |  | 1
LMS 2020 | Region XII | South Cotabato | 136932 | Lemkati ES | Tboli | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH TOILET AND ONE (1) UNIT ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF SCHOOL FURNITURE AND SOLAR ENERGY SYSTEM | 16334333.676 | 0 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs |  | 1 | [7 empty] | 1
LMS 2020 | Region XII | South Cotabato | 136932 | Lemkati ES | Tboli | 2 |  | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH TOILET AND ONE (1) UNIT ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF SCHOOL FURNITURE AND SOLAR ENERGY SYSTEM | 16334333.676 | 0 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs |  | 0 | [7 empty] | 1
LMS 2021 | Region XII | North Cotabato | 130084 | Balawan ES | MAKILALA | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19188630.3041 | 0 | Ongoing | 0.3 | CO Procured and subject for termination due to Prismoidal Contruction abandoned the project | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.3 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region XII | Sarangani | 208019 | Nicomedes I. Sunio ES | MALUNGON | 0 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM and SCHOOL FENCE | 20549897.8317 | 0 | Ongoing | 0.25 | CO Procured and subject for termination due to Prismoidal Contruction abandoned the project | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.25 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2024 | Region XII | General Santos City | 281537 | Tanda Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 4 | CONSTRUCTION OF TWO(2) STOREY - FOUR(4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22222222.22 | 0 | Under Procurement | 0 |  |  | 0 | 0 | [5 empty] | 0 | change of program; for reversion/ waive due to armed conflict | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region XII | South Cotabato | 137086 | Tubak Elementary School | LAKE SEBU | 2nd | 1 | 5 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS AND ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 22222222.22 | 21979700.2 | Ongoing | 0 | 2026-04-02 |  | DSC-24-08-131 | 2025-009 | 2024-08-06 | 2024-08-14 | 2024-08-27 | 2024-09-30 | 2025-03-07 | COFFEJOK CONSTRUCTION & SUPPLY CORPORATION | suspended; WITH TIME SUSPENSION | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 3rd | 1
LMS 2024 | Region XII | South Cotabato | 136941 | Kule Elementary School | T'BOLI | 2nd | 1 | 5 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS AND ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 22222222.22 | 21978971.76 | Ongoing | 0.0311 | 2026-02-01 |  | DSC-24-08-131 | 2025-008 | 2024-08-06 | 2024-08-14 | 2024-08-27 | 2024-09-30 | 2025-03-07 | COFFEJOK CONSTRUCTION & SUPPLY CORPORATION | ON-GOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.0311 | [9 empty] | 3rd | 1
LMS 2024 | Region XII | Sultan Kudarat | 137132 | DATU SALAYAN ELEMENTARY SCHOOL | BAGUMBAYAN | 2nd | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18079433.89 | 17635084.59 | Ongoing | 0.87 | 2025-06-24 | 00:00:00 | 24-01-005 | 24-01-005 | 2024-04-05 | 2024-04-17 | 2024-04-29 | 2024-05-07 | 2024-10-07 | Cofejok Construction and Supply Corporation | Time Extended due to road inaccessibility | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.84 | 0.03 | [9 empty] | 1st | 1

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.