## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | No. of Classrooms | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated | Previous % | Difference | STOREY | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | Status as of July 4, 2025
NEWCON 2016 | REGION XII | General Santos City | 304636 | A.G. Busano, Sr. Hs | General Santos City (Dadiangas) | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12931310.09 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION XII | General Santos City | 317003 | Baluan Nhs | General Santos City (Dadiangas) | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15271327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | General Santos City | 317003 | Baluan Nhs | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | General Santos City | 304643 | Banisil Nhs | General Santos City (Dadiangas) | 1 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26852890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | General Santos City | 304643 | Banisil Nhs | General Santos City (Dadiangas) | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4859098.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | General Santos City | 131294 | Bawing Es | General Santos City (Dadiangas) | 1 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15271327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | General Santos City | 304644 | Bawing Nhs | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | General Santos City | 304639 | Bula National School Of Fisheries | General Santos City (Dadiangas) | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | General Santos City | 131269 | Conel Ces | General Santos City (Dadiangas) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | General Santos City | 317005 | Dadiangas North Hs | General Santos City (Dadiangas) | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | General Santos City | 304649 | Datu B. Balunto Nhs | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6489337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | General Santos City | 304649 | Datu B. Balunto Nhs | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2449549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | General Santos City | 317004 | E.J. Buscano Sr, Hs | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6489337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | General Santos City | 317004 | E.J. Buscano Sr, Hs | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2449549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | General Santos City | 304640 | Engracia I. Valdomar Nhs | General Santos City (Dadiangas) | 1 | 1 | 18 | 3STY9CL | BATCH 5 CL | 30542655.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION XII | General Santos City | 304641 | Fatima Nhs | General Santos City (Dadiangas) | 1 | 1 | 40 | 4STY20CL | BATCH 1 CL | 65222918.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION XII | General Santos City | 304641 | Fatima Nhs | General Santos City (Dadiangas) | 1 |  | 16 | 4STY16CL | BATCH 1 CL | 27820322.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | General Santos City | 304642 | General Santos City National High School (Main) | General Santos City (Dadiangas) | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | General Santos City | 304642 | General Santos City National High School (Main) | General Santos City (Dadiangas) | 1 |  | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | General Santos City | 304642 | General Santos City National High School (Main) | General Santos City (Dadiangas) | 1 |  | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | General Santos City | 304642 | General Santos City National High School (Main) | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | General Santos City | 304646 | Gsc Hs - Lanton Hs Annex | General Santos City (Dadiangas) | 1 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 7318647.81 |  |  | Completed | 1 | [9 empty] | C.A.V. Builders and Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | General Santos City | 304655 | Gsc Nat'L. Sec. Sch. Of Arts & Trades | General Santos City (Dadiangas) | 1 | 1 | 40 | 4STY20CL | BATCH 1 CL | 66129161.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION XII | General Santos City | 304655 | Gsc Nat'L. Sec. Sch. Of Arts & Trades | General Santos City (Dadiangas) | 1 |  | 8 | 2STY8CL | BATCH 1 CL | 11227925.59 |  |  | Completed | 1 | [9 empty] | Vertical Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | General Santos City | 304655 | Gsc Nat'L. Sec. Sch. Of Arts & Trades | General Santos City (Dadiangas) | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 4887746.99 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | General Santos City | 317001 | Gsc Sped Integrated School | General Santos City (Dadiangas) | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | General Santos City | 317001 | Gsc Sped Integrated School | General Santos City (Dadiangas) | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8464965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | General Santos City | 304648 | Irineo Santiago Nhs Of Metro Dadiangas (Main) | General Santos City (Dadiangas) | 1 | 1 | 40 | 4STY20CL | BATCH 3 CL | 62505780.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION XII | General Santos City | 304648 | Irineo Santiago Nhs Of Metro Dadiangas (Main) | General Santos City (Dadiangas) | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8364965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | General Santos City | 304645 | Johnny Ang Nhs | General Santos City (Dadiangas) | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12921310.09 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION XII | General Santos City | 304645 | Johnny Ang Nhs | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | General Santos City | 131272 | Jose Catolico Sr. Es | General Santos City (Dadiangas) | 1 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | General Santos City | 304650 | Labangal Nhs (Main) | General Santos City (Dadiangas) | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | General Santos City | 304650 | Labangal Nhs (Main) | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | General Santos City | 131285 | Lagao 2Nd Bo. Es | General Santos City (Dadiangas) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | General Santos City | 304653 | Lagao Nhs (Main) | General Santos City (Dadiangas) | 1 |  | 16 | 4STY16CL | BATCH 1 CL | 28244890.27 |  |  | Completed | 1 | [9 empty] | AB Vision Engineering |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | General Santos City | 304653 | Lagao Nhs (Main) | General Santos City (Dadiangas) | 1 | 1 | 40 | 4STY20CL | BATCH 1 CL | 65989780.54 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION XII | General Santos City | 304654 | Lagao Nhs Annex | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | General Santos City | 304654 | Lagao Nhs Annex | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | General Santos City | 131279 | Lanton Es | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | General Santos City | 304651 | Ligaya Hs | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | General Santos City | 131286 | Mabuhay Es | General Santos City (Dadiangas) | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8374465.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | General Santos City | 210009 | Maligaya Es | General Santos City (Dadiangas) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1829740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | General Santos City | 131321 | Nasa Es | General Santos City (Dadiangas) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | General Santos City | 304647 | New Society National High School | General Santos City (Dadiangas) | 1 | 1 | 40 | 4STY20CL | BATCH 1 CL | 65690501.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION XII | General Santos City | 304647 | New Society National High School | General Santos City (Dadiangas) | 1 |  | 8 | 2STY8CL | BATCH 1 CL | 11236925.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | General Santos City | 317002 | Pao - Pao Hs | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6489337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | General Santos City | 317002 | Pao - Pao Hs | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2449549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | General Santos City | 131316 | Pao-Pao Es | General Santos City (Dadiangas) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1834740.17 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | General Santos City | 131280 | Saavedra Saway Ces | General Santos City (Dadiangas) | 1 | 1 | 6 | 3STY6CL | BATCH 3 CL | 10567131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | General Santos City | 317006 | Samboang-Ngilay Hs | General Santos City (Dadiangas) | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11037342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | General Santos City | 304652 | Upper Labay Hs | General Santos City (Dadiangas) | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8504965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | General Santos City | 131324 | Upper Tambler Es I | General Santos City (Dadiangas) | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11027342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | General Santos City | 131323 | Upper Tambler Es I Ces | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.64 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304656 | Amas Nhs | City Of Kidapawan (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11055006.99 |  |  | Completed | 1 | [9 empty] | GP & H Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304656 | Amas Nhs | City Of Kidapawan (Capital) | 2 |  | 6 | 2STY6CL | BATCH 1 CL | 8387706.21 |  |  | Completed | 1 | [9 empty] | LTB Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304656 | Amas Nhs | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2507239.6 |  |  | Completed | 1 | [9 empty] | Llaban Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304658 | Ginatilan Nhs | City Of Kidapawan (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 3 CL | 18224268.79 |  |  | Completed | 1 | [9 empty] | Aguero Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304658 | Ginatilan Nhs | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [9 empty] | RNH Bentulan Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 210504 | Habitat Elementary School | City Of Kidapawan (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1814740.17 |  |  | Completed | 1 | [9 empty] | Isulan ECT Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 317102 | Juan L. Gantuangco School Of Arts And Trades | City Of Kidapawan (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11196007.09 |  |  | Completed | 1 | [9 empty] | Verguz Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 317102 | Juan L. Gantuangco School Of Arts And Trades | City Of Kidapawan (Capital) | 2 |  | 6 | 2STY6CL | BATCH 1 CL | 8498904.05 |  |  | Completed | 1 | [9 empty] | Verguz Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 317102 | Juan L. Gantuangco School Of Arts And Trades | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2546473.75 |  |  | Completed | 1 | [9 empty] | Verguz Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304662 | Juan P. Jalipa Mem. Nhs | City Of Kidapawan (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1814740.17 |  |  | Completed | 1 | [9 empty] | Isulan ECT Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304663 | Kalaisan National High School | City Of Kidapawan (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11178693.34 |  |  | Completed | 1 | [9 empty] | GP & H Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304663 | Kalaisan National High School | City Of Kidapawan (Capital) | 2 |  | 6 | 2STY6CL | BATCH 1 CL | 8487053.05 |  |  | Completed | 1 | [9 empty] | Aguero Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304661 | Kidapawan City National High School | City Of Kidapawan (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [9 empty] | Jargon Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304661 | Kidapawan City National High School | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1 | [9 empty] | Jargon Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 317101 | Linangkob National High School | City Of Kidapawan (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6469337.64 |  |  | Completed | 1 | [9 empty] | Llaban Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304659 | Manongol Nhs | City Of Kidapawan (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8364965.05 |  |  | Completed | 1 | [9 empty] | Cofejok Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304659 | Manongol Nhs | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [9 empty] | RNH Bentulan Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304668 | Paco Nhs | City Of Kidapawan (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15121327.92 |  |  | Completed | 1 | [9 empty] | AYU Eng'g & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304668 | Paco Nhs | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [9 empty] | RNH Bentulan Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 131369 | Patadon Es | City Of Kidapawan (Capital) | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2640828.12 |  |  | Completed | 1 | [9 empty] | John Rey Devt & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304665 | Saniel Cruz National High School | City Of Kidapawan (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 1 CL | 18395418.84 |  |  | Completed | 1 | [9 empty] | Jargon Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304665 | Saniel Cruz National High School | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2554041.64 |  |  | Completed | 1 | [9 empty] | LTB Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Kidapawan City | 304665 | Saniel Cruz National High School | City Of Kidapawan (Capital) | 2 |  | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2500000 |  |  | Completed | 1 | [9 empty] | LTB Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Koronadal City | 317201 | Bacongco National High School | City Of Koronadal (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 |  |  | P00071694MN | 16MG0044 | 2016-06-22 | 2016-07-04 | 2016-07-18 | 2016-08-10 | 42606 | Cofejok Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Koronadal City | 304671 | Koronadal Nchs | City Of Koronadal (Capital) | 2 | 1 | 24 | 4STY12CL | BATCH 13 CL | 48705155.964 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION XII | Koronadal City | 304671 | Koronadal Nchs | City Of Koronadal (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Koronadal City | 304672 | Marbel 7 National High School | City Of Koronadal (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00072497MN | 16MG0102 | 2016-06-16 | 2016-06-28 | 2016-07-11 | 2016-07-25 | 42591 | FH Gopiteo Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | Koronadal City | 304672 | Marbel 7 National High School | City Of Koronadal (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2429549.27 |  |  | Completed | 1 |  |  | P00072652MN | 16MG0083 | 2016-02-29 | 2016-03-09 | 2016-03-21 | 2016-06-10 | 42545 | Rockstone Construction Services and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Koronadal City | 317205 | Saravia Nhs (Koronadal Nchs - Annex, Saravia Campus) (Realigned To Esperanza Nhs Annex- San Jose Campus) | City Of Koronadal (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | Koronadal City | 317202 | Saravia Nhs (Koronadal Nchs - Annex, Saravia Campus) | City Of Koronadal (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072499MN | 16MG0046 | 2016-02-29 | 2016-03-09 | 2016-03-21 | 2016-06-10 | 42545 | Reydan Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Koronadal City | 317202 | Saravia Nhs (Koronadal Nchs - Annex, Saravia Campus) | City Of Koronadal (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2429549.27 |  |  | Completed | 1 |  |  | P00072653MN | 16MG0084 | 2016-06-20 | 2016-06-30 | 2016-07-12 | 2016-07-25 | 42591 | Reydan Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Koronadal City | 131400 | Sto. Nino Es | City Of Koronadal (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606 |  |  | Completed | 1 |  |  | P00070639MN | 16MG0121 | 2016-06-20 | 2016-06-30 | 2016-07-12 | 2016-07-25 | 42591 | FH Gopiteo Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304412 | Alamada Nhs | Alamada | 1 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26712469.42 |  |  | Completed | 1 |  |  | P00070640MN | 16MD0063 | 2016-06-24 | 2016-07-01 | 2016-07-14 | 2016-07-29 | 42593 | ACJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304413 | Aleosan Nhs | Aleosan | 1 | 1 | 24 | 4STY24CL | BATCH 5 CL | 35606257.14 |  |  | Completed | 1 |  |  | P00071231MN | 16MD0083 | 2016-08-18 | 2016-08-25 | 2016-09-07 | 2016-09-13 | 42639 | FFJJ Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION XII | North Cotabato | 316521 | Aringay National High School | Kabacan | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10887342.59 |  |  | Completed | 1 |  |  | P00070641MN | 16MD0051 | 2016-07-11 | 2016-07-19 | 2016-08-02 | 2016-08-09 | 42604 | MARCUS Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | North Cotabato | 316556 | Bentangan Hs | Carmen | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8314965.051 |  |  | Completed | 1 |  |  | P00072508MN | 16MD0067 | 2016-06-24 | 2016-07-01 | 2016-07-15 | 2016-07-29 | 42593 | PADER Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | North Cotabato | 316556 | Bentangan Hs | Carmen | 1 |  | 1 | 1STY1CL | BATCH 7 CL | 1112049.6543 |  |  | Completed | 1 |  |  | P00072509MN | 16MD0055 | 2016-04-28 | 2016-05-06 | 2016-05-24 | 2016-05-27 | 42535 | BORDERLINE Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 316556 | Bentangan Hs | Carmen | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2563728.13 |  |  | Completed | 1 |  |  | P00072657MN | 16MD0059 | 2016-05-17 | 2016-05-24 | 2016-06-06 | 2016-06-09 | 42544 | BORDERLINE Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304427 | Carmen National High School | Carmen | 1 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21408013.45 |  |  | Completed | 1 |  |  | P00072510MN | 16MD0073 | 2016-07-11 | 2016-07-18 | 2016-08-02 | 2016-10-06 | 42660 | MARCUS Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304427 | Carmen National High School | Carmen | 1 |  | 4 | 2STY4CL | BATCH 7 CL | 6344337.6381 |  |  | Completed | 1 |  |  | P00072511MN | 16MD0054 | 2016-07-11 | 2016-07-19 | 2016-08-02 | 2016-08-09 | 42604 | MARCUS Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304427 | Carmen National High School | Carmen | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5102456.26 |  |  | Completed | 1 |  |  | P00072658MN | 16MD0061 | 2016-05-17 | 2016-05-24 | 2016-06-06 | 2016-06-09 | 42544 | BORDERLINE Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304432 | Dilangalen National High School | Midsayap | 1 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6319337.64 |  |  | Completed | 1 |  |  | P00070172MN | 16MD0046 | 2016-02-13 | 2016-02-22 | 2016-03-08 | 2016-03-11 | 42524 | BANDAR KUTAWATO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304432 | Dilangalen National High School | Midsayap | 1 |  | 20 | 4STY20CL | BATCH 1 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00070173MN | 16MD0070 | 2016-07-05 | 2016-07-13 | 2016-07-26 | 2016-07-29 | 42593 | ACJ/RDEN Const. (Joint Venture) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304432 | Dilangalen National High School | Midsayap | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26712469.42 |  |  | Completed | 1 |  |  | P00074327MN | 16MD0064 | 2016-06-24 | 2016-07-01 | 2016-08-02 | 2016-08-09 | 42604 | ACJ/RDEN Const. (Joint Venture) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304444 | Kabacan National Hs | Kabacan | 1 | 1 | 32 | 4STY32CL | BATCH 5 CL | 44572220.04 |  |  | Completed | 1 |  |  | P00071232MN | 16MD0081 | 16MD0081 | 2016-08-18 | 2016-08-25 | 2016-09-07 | 42643 | 42660 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304444 | Kabacan National Hs | Kabacan | 1 |  | 8 | 4STY8CL | BATCH 5 CL | 14937518.84 |  |  | Completed | 1 |  |  | P00071233MN | 16MD0066 | 2016-06-24 | 2016-07-01 | 2016-07-14 | 2016-07-29 | 42593 | MARCUS Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304458 | Kitub-Bao Nhs | Alamada | 1 | 1 | 15 | 3STY15CL | BATCH 5 CL | 21453013.45 |  |  | Completed | 1 |  |  | P00071234MN | 16MD0071 | 2016-08-11 | 2016-08-18 | 2016-08-31 | 2016-12-13 | 42727 | ACJ/RDEN Const. (Joint Venture) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304468 | Malapag Nhs | Carmen | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26802469.42 |  |  | Completed | 1 |  |  | P00072512MN | 16MD0065 | 2016-06-24 | 2016-07-01 | 2016-07-14 | 2016-07-29 | 42593 | MARCUS Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304468 | Malapag Nhs | Carmen | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2563728.13 |  |  | Completed | 1 |  |  | P00072659MN | 16MD0060 | 2016-05-17 | 2016-05-24 | 2016-06-06 | 2016-06-09 | 42544 | BORDERLINE Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304472 | Malinao High School | Banisilan | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21513013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304474 | Manuangan Hs | Pigkawayan | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6329337.64 |  |  | Completed | 1 |  |  | P00070643MN | 16MD0049 | 2016-02-25 | 2016-03-04 | 2016-03-22 | 2016-03-29 | 42524 | LLABAN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304493 | Pigcawayan National High School | Pigkawayan | 1 | 1 | 28 | 4STY28CL | BATCH 9 CL | 40107946.14 |  |  | Completed | 1 |  |  | P00074328MN | 16MD0080 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304493 | Pigcawayan National High School | Pigkawayan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1 |  |  | P00074619MN | 16MD0057 | 2016-04-28 | 2016-05-06 | 2016-05-24 | 2016-05-27 | 42535 | SHERATANNOR CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 316520 | Pigcawayan Nhs - Libungan Torreta Annex | Pigkawayan | 1 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15191327.92 |  |  | Completed | 1 |  |  | P00070644MN | 16MD0072 | 2016-07-05 | 2016-07-13 | 2016-07-27 |  |  | STONELINE/CURVELINE (Joint Venture) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304494 | Pikit Nhs | Pikit | 1 | 1 | 32 | 4STY32CL | BATCH 9 CL | 44572220.84 |  |  | Completed | 1 |  |  | P00074330MN | 16MD0079 | 2016-08-18 | 2016-08-25 | 2016-09-01 | 2016-09-30 | 42664 | HEXAMINDZ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304494 | Pikit Nhs | Pikit | 1 |  | 24 | 4STY24CL | BATCH 9 CL | 35636257.14 |  |  | Completed | 1 |  |  | P00074331MN | 16MD0084 | 2016-08-18 | 2016-08-25 | 2016-09-01 | 2016-09-30 | 42664 | HEXAMINDZ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304494 | Pikit Nhs | Pikit | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5000000 |  |  | Completed | 1 |  |  | P00074620MN | 16MD0056 | 2016-04-28 | 2016-05-06 | 2016-05-24 | 2016-05-27 | 42535 | J-ONE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304499 | Presbitero Hs | Pigkawayan | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12781310.09 |  |  | Completed | 1 |  |  | P00070645MN | 16MD0052 | 2016-08-11 | 2016-08-18 | 2016-08-31 | 2016-09-05 | 42633 | STONELINE CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304429 | Ranzo National High School | Carmen | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2551228.13 |  |  | Completed | 1 |  |  | P00075351MN | 16MD0085 | 2016-08-18 | 2016-08-25 | 2016-09-07 | 2016-09-13 | 42647 | HAQ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304500 | Salama Nhs | Banisilan | 1 | 1 | 8 | 2STY8CL | BATCH 5 CL | 10977342.59 |  |  | Completed | 1 |  |  | P00071235MN | 16MD0048 | 2016-07-11 | 2016-07-19 | 2016-08-09 | 2016-08-12 | 42608 | K.A.BUILDERS/CAMIA Const. (Joint Vwnture) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304501 | Salunayan Hs | Midsayap | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31112890.27 |  |  | Completed | 1 |  |  | P00072500MN | 16MD0069 | 2016-07-05 | 2016-07-13 | 2016-08-31 | 2016-09-05 | 42633 | K.A.BUILDERS/CAMIA Const. (Joint Vwnture) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304501 | Salunayan Hs | Midsayap | 1 |  | 4 | 2STY4CL | BATCH 7 CL | 6329337.64 |  |  | Completed | 1 |  |  | P00072501MN | 16MD0053 | 2016-03-17 | 2016-03-28 | 2016-04-11 | 2016-04-14 | 42551 | DINGO BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304505 | Silik High School | Pikit | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31177890.27 |  |  | Terminated | 0.75 |  |  | P00070646MN | 16MD0078 | 2016-08-18 | 2016-08-25 | 2016-09-07 | 2016-09-30 | 42664 | HEXAMINDZ | Terminated due to contractor's fault: Hexamindz Corporation; added demolition of structure which was the incomplete structure been abandoned by the said contractor;PROCESS OF BLACKLISTING THE CONTRACTOR! | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20
NEWCON 2016 | REGION XII | North Cotabato | 304505 | Silik High School | Pikit | 1 |  | 16 | 4STY16CL | BATCH 3 CL | 26777469.42 |  |  | Terminated | 0.7 |  |  | P00070647MN | 16MD0082 | 2016-08-18 | 2016-08-25 | 2016-09-01 | 2016-09-30 | 42664 | HEXAMINDZ | Terminated due to contractor's fault: Hexamindz Corporation; added demolition of structure which was the incomplete structure been abandoned by the said contractor;PROCESS OF BLACKLISTING THE CONTRACTOR! | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16
NEWCON 2016 | REGION XII | North Cotabato | 304507 | Sinawingan Hs | Libungan | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8224965.05 |  |  | Completed | 1 |  |  | P00070642MN | 16MD0050 | 2016-07-11 | 2016-07-19 | 2016-08-02 | 2016-08-09 | 42604 | RDEN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | North Cotabato | 316507 | Agustin M. Valdevieso, Sr. High School | Matalam | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072517MN | 16MC0150 | 2016-06-09 | 2016-06-17 | 2016-06-29 | 2016-07-15 | 42594 | BORDERLINE CONST & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304415 | Antipas Nhs | Antipas | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22229351.8227 |  |  | Completed | 1 |  |  | P00072502MN | 16MC158 | 2016-06-07 | 2016-06-16 | 2016-06-27 | 2016-07-15 | Aug. 12, 2016 | BRE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304415 | Antipas Nhs | Antipas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2517500 |  |  | Completed | 1 |  |  | P00072654MN | 16MC0138 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-07-04 | 42573 | SHEPPERD CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 130400 | Bacong Es | Tulunan | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8327874.5607 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304419 | Banayal Hs | Tulunan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  | P00075353MN | 16MC0208 | 2016-08-10 | 2016-08-18 | 2016-08-30 | 2016-09-06 | 42632 | MEGALINE BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304423 | Bulakanon High School | Makilala | 2 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1 |  |  | P00072515MN | 16MC0145 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-06 | 42542 | THREE W BUILDERS, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304431 | Dalapitan Hs | Matalam | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072518MN | 16MC0152 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-15 | 42542 | BORDERLINE CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304438 | Dallag Hs | Arakan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6364337.64 |  |  | Completed | 1 |  |  | P00072504MN | 16MC0154 | 2016-03-28 | 2016-04-06 | 2016-04-18 | 2016-06-03 | 42549 | JARGON CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304434 | Don Antonio Jayme Mem. Hs | President Roxas | 2 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12771310.09 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304436 | Greenfield Nhs | Arakan | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10977342.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304440 | Kabalantian Hs | Arakan | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8259965.05 |  |  | Completed | 1 |  |  | P00072505MN | 16MC0161 | 2016-03-28 | 2016-04-06 | 2016-04-18 | 2016-05-06 | 42549 | JARGON CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304441 | Katipunan Hs | Arakan | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072506MN | 16MC0151 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-10 | 42548 | CHJ CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304441 | Katipunan Hs | Arakan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1 |  |  | P00072656MN | 16MC0140 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-06 | 42562 | CHJ CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304452 | Kibia Hs | Matalam | 2 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00072519MN | 16MC0147 | 2016-03-12 | 2016-03-10 | 2016-03-21 | 2016-05-06 | 42555 | JARGON CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | North Cotabato | 316519 | Kisante Nhs - Batasan Hs Annex | Makilala | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  | P00075352MN | 16MC0207 | 2015-08-10 | 2016-08-18 | 2016-08-30 | 2016-09-06 | 42638 | CARLSON CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304463 | Magpet Nhs | Magpet | 2 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1 |  |  | P00072513MN | 16MC0144 | 2016-03-02 | 2016-03-10 | 2016-03-22 | 2016-05-06 | 42548 | BRE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304463 | Magpet Nhs | Magpet | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1 |  |  | P00072660MN | 16MC0139 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-06 | 42548 | MEGALINE BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304466 | Makilala National High School | Makilala | 2 | 1 | 12 | 3STY12CL | BATCH 1 CL | 18282268.79 |  |  | Completed | 1 |  |  | P00070174MN | 16MC0116 | 2016-02-10 | 2016-02-16 | 2016-02-29 | 2016-05-10 | 42541 | GP & H Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304470 | Malatab Hs | Antipas | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10914888.2891 |  |  | Completed | 1 |  |  | P00072503MN | 16MC0160 | 2016-03-02 | 2016-03-10 | 2016-03-22 | 2016-05-06 | 42548 | ACJ CONST. RESOURSES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304470 | Malatab Hs | Antipas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2517500 |  |  | Completed | 1 |  |  | P00072655MN | 16MC0137 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-06 | 42548 | Y.R. BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304471 | Malibatuan High School | Arakan | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072507MN | 16MC0153 | 2016-06-09 | 2016-06-17 | 2016-06-29 | 2016-07-15 | 42594 | JARGON CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304473 | Manobo Nhs | Magpet | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 |  |  | P00072514MN | 16MC0159 | 2016-06-07 | 2016-06-16 | 2016-06-27 | 2016-07-15 | 42594 | AGUERO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304473 | Manobo Nhs | Magpet | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1 |  |  | P00072661MN | 16MC0143 | 2016-06-09 | 2016-06-17 | 2016-06-29 | 2016-07-15 | 42594 | BRE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304418 | Mariano Untal Hs | M'Lang | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8244965.05 |  |  | Completed | 1 |  |  | P00074328MN | 16MC0171 | 2016-04-15 | 2016-04-22 | 2016-03-29 | 2016-05-18 | 42542 | J & S ESCUADRA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304418 | Mariano Untal Hs | M'Lang | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7500000 |  |  | Completed | 1 |  |  | P00074618MN | 16MC0170 | 2016-04-15 | 2016-04-22 | 2016-05-05 | 2016-06-02 | 42542 | WHITE YOUNG CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304476 | Matalam Nhs, Brgy Linao | Matalam | 2 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26757469.42 |  |  | Completed | 1 |  |  | P00072520MN | 16MC0187 | 2016-07-29 | 2016-08-05 | 2016-08-18 | 2016-08-26 | 42635 | JARGON CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304478 | Matalam Nhs, Brgy Poblacion | Matalam | 2 | 1 | 24 | 4STY24CL | BATCH 13 CL | 39140882.854 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION XII | North Cotabato | 316534 | Meocan High School | Arakan | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22460376.4307 |  |  | Completed | 1 |  |  | P00074939MN | 16MC0216 | 2016-09-06 | 2016-09-15 | 2016-09-27 | 2015-10-07 | Nov. 16, 2016 | JARGON CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | North Cotabato | 316514 | Minapan High School | Tulunan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | P00072521MN | 16MC0184 | 2016-06-28 | 2016-07-06 | 2016-07-18 | 2016-08-05 | 42618 | ISULAN ECT CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | North Cotabato | 316514 | Minapan High School | Tulunan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1 |  |  | P00072662MN | 16MC0141 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-10 | 42542 | ISULAN ECT CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304480 | M'Lang Nhs | M'Lang | 2 | 1 | 32 | 4STY32CL | BATCH 5 CL | 44582220.04 |  |  | Completed | 1 |  |  | P00071236MN | 16MC0186 | 2016-06-30 | 2016-07-08 | 2016-07-20 | 2016-08-08 | Nov. 14, 2016 | LEGACY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304496 | Pres. Roxas National High School | President Roxas | 2 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304457 | Ricardo L. Ipong Nhs | Makilala | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | P00072516MN | 16MC0155 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-18 | 42542 | ISULAN ECT CONST,. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | North Cotabato | 130123 | San Vicente Elementary School | Makilala | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8327874.5607 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304515 | Tulunan Nhs | Tulunan | 2 | 1 | 45 | 3STY15CL | BATCH 9 CL | 64269040.35 |  |  | Completed | 1 |  |  | P00074332MN | 16MC0185 | 2016-07-29 | 2016-08-05 | 2016-08-18 | 2016-08-26 | Nov. 16, 2016 | JARGON CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 45 | 0
NEWCON 2016 | REGION XII | North Cotabato | 304515 | Tulunan Nhs | Tulunan | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5000000 |  |  | Completed | 1 |  |  | P00074621MN | 16MC0172 | 2016-04-15 | 2016-04-22 | 2016-05-05 | 2016-05-31 | 42542 | WHITE YOUNG CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | Sarangani | 316634 | Alabel Central Integrated Sped Center | Alabel (Capital) | 0 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24715057.382 |  |  | Completed | 1 |  |  | P00074333MN-CW1 | 16ME0135 |  |  | 2016-07-08 |  | 42584 | R.R. Seismundo Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | Sarangani | 304517 | Alabel Nat'L Science Hs | Alabel (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6440885.48 |  |  | Completed | 1 |  |  | P00070648MN-CW1 | 16ME0114 |  |  | 2016-06-27 |  | 42572 | MIGO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | Sarangani | 304518 | Alabel Nhs | Alabel (Capital) | 0 | 1 | 24 | 4STY12CL | BATCH 13 CL | 49067635.3627 |  |  | Completed | 1 |  |  | P00076040MN-CW1 | 16ME0173 |  |  | December 5, 2016 |  | December 23, 2016 | LHE Construction & Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION XII | Sarangani | 304519 | Alegria Nhs | Alabel (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6450485.7993 |  |  | Completed | 1 |  |  | P00072522MN-CW1 | 16ME0117 |  |  | 2016-06-27 |  | 42572 | Shepperd Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | Sarangani | 500262 | Cabales Enarbia Sr. Is | Kiamba | 0 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8608332.7 |  |  | Completed | 1 |  |  | P00070652MN-CW1 | 16ME0115 |  |  | 2016-08-10 |  | 42612 | Verguz Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Sarangani | 500280 | Cablalan Is | Glan | 0 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8577020.39 |  |  | Completed | 1 |  |  | P00070649MN-CW1 | 16ME0116 |  |  | 2016-06-27 |  | 42572 | LTB Builders & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Sarangani | 304523 | Colon Nhs | Maasim | 0 | 1 | 24 | 4STY12CL | BATCH 9 CL | 50215800.7102 |  |  | Completed | 1 |  |  | P00074340MN-CW1 | 16ME0124 |  |  | 2016-07-08 |  | 42583 | Three W Builders/Sophia Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION XII | Sarangani | 304523 | Colon Nhs | Maasim | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 17229338.8409 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | Sarangani | 316623 | Datu Pangolima Integrated School | Malapatan | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6486813.8622 |  |  | Completed | 1 |  |  | P00072523MN-CW1 | 16ME0121 |  |  | 2016-06-27 |  | 42572 | Lawrence Eric Construction & Eng'g Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | Sarangani | 130457 | E. Alegado Integrated School | Glan | 0 | 1 | 8 | 1STY4CL | BATCH 13 CL | 8696912.556 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | Sarangani | 304524 | Glan School Of Arts And Trades | Glan | 0 | 1 | 32 | 4STY16CL | BATCH 9 CL | 60941225.2172 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION XII | Sarangani | 304524 | Glan School Of Arts And Trades | Glan | 0 |  | 2 | 1STY2CL | BATCH 9 CL | 2077794.145 |  |  | Completed | 1 |  |  | P00074335MN-CW1 | 16ME0128 |  |  | 2106-06-29 |  | 42579 | LTB Builders & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | Sarangani | 304525 | Glan-Padidu Nhs | Glan | 0 | 1 | 9 | 3STY9CL | BATCH 13 CL | 17631965.0809 |  |  | Completed | 1 | [6 empty] | December 27. 2016 |  | February 13, 2017 | LTB Builders & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | Sarangani | 130516 | Ireneo E. Lopez (Lumasal) Es | Maasim | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8577204.6765 |  |  | Completed | 1 |  |  | P0006053MN-CW1 | 16ME0178 |  |  | December 5. 2016 |  | December 29, 2016 | Legacy Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Sarangani | 130516 | Ireneo E. Lopez (Lumasal) Es | Maasim | 0 |  | 3 | 1STY3CL | BATCH 13 CL | 3218505.9715 |  |  | Completed | 1 |  |  |  | 16ME0179 |  |  | December 29. 2016 |  | February 13, 2017 | LTB Builders & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | Sarangani | 304529 | James L. Chiongbian National Trade School | Kiamba | 0 | 1 | 30 | 3STY15CL | BATCH 9 CL | 50625885.0217 |  |  | Completed | 1 |  |  | P00074336MN-CW1 | 16ME0137 |  |  | 2016-07-08 |  | 42592 | Sarangani Rockmixer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION XII | Sarangani | 304529 | James L. Chiongbian National Trade School | Kiamba | 0 |  | 2 | 1STY2CL | BATCH 9 CL | 2129946.3493 |  |  | Completed | 1 |  |  | P00074337MN-CW1 | 16ME0129 |  |  | 2016-08-02 |  | 42604 | LTB Builders & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | Sarangani | 130463 | Kaltuad Es | Glan | 0 | 1 | 6 | 1STY3CL | BATCH 13 CL | 6520116.768 |  |  | Completed | 1 |  |  | P00076045MN-CW1 | 16ME0174 |  |  | December 5, 2016 |  | December 23, 2016 | Legacy Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Sarangani | 304527 | Kiamba National High School | Kiamba | 0 | 1 | 16 | 4STY16CL | BATCH 9 CL | 31143449.222 |  |  | Completed | 1 |  |  | P000743398MN-CW1 | 16ME0122 |  |  | 2016-08-09 |  | 42626 | R.Semilla Construction & Marketing |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | Sarangani | 304527 | Kiamba National High School | Kiamba | 0 |  | 1 | 1STY1CL | BATCH 9 CL | 1183053.5453 |  |  | Completed | 1 |  |  | P00074339MN-CW1 | 16ME0127 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sarangani | 130428 | Ladol Elementary School | Alabel (Capital) | 0 | 1 | 8 | 2STY4CL | BATCH 7 CL | 12820255.1921 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | Sarangani | 208014 | Lanao Kapanglao Es | Glan | 0 | 1 | 9 | 1STY3CL | BATCH 13 CL | 10173410.5572 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | Sarangani | 304530 | Leonard Young Sr. National High School | Glan | 0 | 1 | 32 | 4STY16CL | BATCH 13 CL | 62288952.7915 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION XII | Sarangani | 304530 | Leonard Young Sr. National High School | Glan | 0 |  | 12 | 4STY12CL | BATCH 13 CL | 25696006.5788 |  |  | Completed | 1 |  |  | P00076042MN-CW1 | 16ME0172 |  |  | December 5, 2016 |  | December 29, 2016 | Jargon Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | Sarangani | 304530 | Leonard Young Sr. National High School | Glan | 0 |  | 2 | 1STY2CL | BATCH 13 CL | 2264970.5238 |  |  | Completed | 1 |  |  | P00076043MN-CW1 | 16ME0180 |  |  | December 5, 2016 |  | December 22, 2016 | DJE Design Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | Sarangani | 130466 | Lumigo Is | Glan | 0 | 1 | 6 | 1STY3CL | BATCH 13 CL | 6659035.9093 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Sarangani | 130466 | Lumigo Is | Glan | 0 |  | 2 | 1STY2CL | BATCH 13 CL | 2307549.6433 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | Sarangani | 304531 | Lun Padidu National High School | Malapatan | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 35028414.292 |  |  | Completed | 1 |  |  | P00074344MN-CW1 | 16ME0138 |  |  | 2016-06-29 |  | 42583 | Curveline Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | Sarangani | 304531 | Lun Padidu National High School | Malapatan | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6414681.6735 |  |  | Completed | 1 |  |  | P00074345MN-CW1 | 16ME0130 |  |  | 2016-06-29 |  | 42583 | Curveline Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | Sarangani | 304534 | Malalag National High School | Maitum | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 36822205.5095 |  |  | Completed | 1 |  |  | P00074342MN-CW1 | 16ME0136 |  |  | 2016-07-08 |  | 42583 | AB Vision Eng'g & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | Sarangani | 304534 | Malalag National High School | Maitum | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 17898232.0111 |  |  | Completed | 1 |  |  | P00074343MN-CW1 | 16ME0132 |  |  | August 9, 2016 |  | August 31, 2016 | R. Semilla Construction & Marketing |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | Sarangani | 304535 | Malandag National High School | Malungon | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 35087749.8435 |  |  | Completed | 1 |  |  | P00074348MN-CW1 | 16ME0137 |  |  | 2016-07-08 |  | 42593 | J.G. Oranza Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | Sarangani | 304535 | Malandag National High School | Malungon | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 17051169.4911 |  |  | Completed | 1 |  |  | P00074349MN-CW1 | 16ME0133 |  |  | 2016-07-08 |  | 42592 | J.G. Oranza Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | Sarangani | 304537 | Malapatan Nhs | Malapatan | 0 | 1 | 36 | 4STY12CL | BATCH 9 CL | 74555902.3581 |  |  | Completed | 1 |  |  | P00074346MN-CW1 | 16ME0126 |  |  | Septamber 1, 2016 |  | September 26, 2016 | LHE Construction & Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0
NEWCON 2016 | REGION XII | Sarangani | 304537 | Malapatan Nhs | Malapatan | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 8431606.7031 |  |  | Completed | 1 |  |  | P00074347MN-CW1 | 16ME0131 |  |  | August 10, 2016 |  | August 30, 2016 | Palmares General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Sarangani | 304538 | Malungon Nhs | Malungon | 0 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13722509.59 |  |  | Completed | 1 |  |  | P00070653MN-CW1 | 16ME0113 |  |  | 2016-08-10 |  | 42612 | Freden Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION XII | Sarangani | 130564 | Millona Upper Suyan Es | Malapatan | 0 | 1 | 8 | 1STY4CL | BATCH 13 CL | 8311652.1846 |  |  | Completed | 1 |  |  |  | 16ME0176 |  |  | December 27, 2016 |  | February 13, 2017 | Curveline Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | Sarangani | 130564 | Millona Upper Suyan Es | Malapatan | 0 |  | 2 | 1STY2CL | BATCH 13 CL | 2195933.542 |  |  | Completed | 1 |  |  |  | 16ME0181 |  |  | December 27, 2016 |  | February 13, 2017 | Curveline Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | Sarangani | 500261 | Roque Adarna Is | Glan | 0 | 1 | 8 | 2STY4CL | BATCH 3 CL | 13109259.47 |  |  | Completed | 1 |  |  | P00070650MN-CW1 | 16ME0119 |  |  | 2016-06-27 |  | 42585 | Freden Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | Sarangani | 130477 | San Jose Es | Glan | 0 | 1 | 8 | 1STY4CL | BATCH 13 CL | 8876484.4476 |  |  | Completed | 1 |  |  |  | 16ME0175 |  |  | December 29, 2016 |  | February 13, 2017 | Yap Mabuhay Enterprises, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | Sarangani | 316601 | San Vicente Nhs | Glan | 0 | 1 | 8 | 2STY4CL | BATCH 3 CL | 13099717.72 |  |  | Completed | 1 |  |  | P00070651MN-CW1 | 16ME0118 |  |  | 2016-06-27 |  | 42576 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | Sarangani | 208040 | Segafu Esgapo Ps | Glan | 0 | 1 | 6 | 1STY3CL | BATCH 13 CL | 6782273.7048 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Sarangani | 130485 | Young Es | Glan | 0 | 1 | 9 | 1STY3CL | BATCH 13 CL | 9823766.482 |  |  | Completed | 1 |  |  |  | 16ME0177 |  |  | December 29, 2017 |  | February 13, 2017 | LTB Builders & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304544 | Bentung Sulit National High School | Polomolok | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8404965.25 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 42636 | FH GOPITEO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130852 | Bukang Liwayway Es | Tampakan | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1968000 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 42643 | NIRVANA CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130718 | Bukay-Eel Elementary School | Polomolok | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1988000 |  |  | Completed | 1 | [6 empty] | 2016-07-27 |  | 42636 | FFJJ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304576 | Cebuano National High School | Tupi | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6489337.64 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 42636 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304576 | Cebuano National High School | Tupi | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8404965.05 |  |  | Completed | 1 | [6 empty] | 2016-08-02 |  | 42643 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316707 | Danlag High School | Tampakan | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6549337.64 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 42669 | MARCUS CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316717 | Emiliano P. Baquial National High School | Tupi | 1 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15281327.92 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 42636 | FFJJ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304545 | Glamang High School | Polomolok | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2434549.27 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 42636 | CAV BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304545 | Glamang High School | Polomolok | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1963000 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42608 | CAV BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130723 | Guaza Elementary School | Polomolok | 1 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1130000 |  |  | Completed | 1 | [6 empty] | 2016-07-27 |  | 42669 | FFJJ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304562 | Jose D. Escabilio National High School | Tupi | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2479549.27 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 42669 | FFJJ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304562 | Jose D. Escabilio National High School | Tupi | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2008000 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 42636 | FFJJ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130739 | Jose Natividad Elementary School | Polomolok | 1 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2841000 |  |  | Completed | 1 | [6 empty] | 2016-07-27 |  | 42669 | NIRVANA CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130740 | Juan Bayan Elementary School | Polomolok | 1 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2841000 |  |  | Completed | 1 | [6 empty] | 2016-09-13 |  |  | TRIPLE Z MERCHANDISING & ELEC. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304564 | Kablon National High School | Tupi | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2449549.27 |  |  | Completed | 1 | [6 empty] | 2016-06-30 |  | 42615 | VERGUZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316711 | Lampitak High School | Tampakan | 1 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2846000 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 42643 | NIRVANA CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316712 | Landan National High School | Polomolok | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12971310.09 |  |  | Completed | 1 | [6 empty] | 2016-08-02 |  | 42669 | R.R. SEISMUNDO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION XII | South Cotabato | 208526 | Ludovico I. Senador Es | Tupi | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1968000 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 42669 | JARGON CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304556 | Maltana Nhs | Tampakan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2434549.27 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 42667 | MARBEL DYNAMIC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304556 | Maltana Nhs | Tampakan | 1 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11037342.59 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 42636 | MARBEL DYNAMIC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316702 | Pablo Valencia High School | Polomolok | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2439549.27 |  |  | Completed | 1 | [6 empty] | 2016-06-30 |  | 42608 | VERGUZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316702 | Pablo Valencia High School | Polomolok | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8404965.05 |  |  | Completed | 1 | [6 empty] | 2016-07-27 |  | 42636 | SOPHIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304578 | Palkan High School | Polomolok | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2439549.27 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42608 | SOPHIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304578 | Palkan High School | Polomolok | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8404965.05 |  |  | Completed | 1 | [6 empty] | 2016-07-27 |  | 42621 | SOPHIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304559 | Poblacion Polomolok Nhs | Polomolok | 1 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 7288647.81 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42615 | LEIGHCHEEN CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304559 | Poblacion Polomolok Nhs | Polomolok | 1 | 1 | 40 | 4STY20CL | BATCH 3 CL | 62505780.54 |  |  | Completed | 1 | [6 empty] | 2016-07-27 |  | 42664 | LEGACY CONST. (JOINT VENTURE) & VERGUZ CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130745 | Polomolok Central Elementary School | Polomolok | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11027342.59 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 42663 | AB VISION CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304560 | Polomolok Nhs | Polomolok | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 42664 | VERGUZ CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304560 | Polomolok Nhs | Polomolok | 1 |  | 9 | 3STY9CL | BATCH 9 CL | 15271327.92 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 42667 | R. SEMILLA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304560 | Polomolok Nhs | Polomolok | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31252890.27 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 42636 | LEGACY CONST. (JOINT VENTURE) & VERGUZ CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130907 | Polonuling Central Elementary School | Tupi | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 | [6 empty] | 2016-12-06 |  | 42762 | LLM Concrete Products |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304567 | Silway-8 National High School | Polomolok | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4859098.54 |  |  | Completed | 1 | [6 empty] | 2016-06-30 | 2016-07-26 | 42608 | SHEPPERD CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304567 | Silway-8 National High School | Polomolok | 1 |  | 9 | 3STY9CL | BATCH 5 CL | 15271327.92 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 42669 | R.R SEISMUNDO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304567 | Silway-8 National High School | Polomolok | 1 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31252890.27 |  |  | Completed | 1 | [6 empty] | 2016-10-24 |  | 42703 | VERTICAL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316716 | Tablu High School | Tampakan | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6509337.64 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 42667 | MARCUS CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304570 | Tampakan National High School | Tampakan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2434549.27 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 42667 | MARBEL DYNAMIC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304570 | Tampakan National High School | Tampakan | 1 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31272890.27 |  |  | Completed | 1 | [6 empty] | 2016-08-02 |  | 42643 | F.H. GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304563 | Teodoro P. Prudente National High School | Tupi | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6509337.64 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 42669 | CEK CONST. & WATER SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304575 | Tupi Nhs | Tupi | 1 |  | 16 | 4STY16CL | BATCH 5 CL | 26852890.27 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 42667 | R. SEMILLA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304575 | Tupi Nhs | Tupi | 1 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62505780.54 |  |  | Completed | 1 | [6 empty] | 2016-08-03 |  | 42667 | FFJJ CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304577 | Upper Klinan High School | Polomolok | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1968000 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 42642 | VERGUZ CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 208505 | Abboy Es | Lake Sebu | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 3002592.44 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 42732 | DALANON CONST., REF. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316727 | Aflek Nhs - Edwards Nhs Annex | T'Boli | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8264965.05 |  |  | Completed | 1 | [6 empty] | 2016-10-11 |  | 42765 | MFN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304543 | Banga Nhs | Banga | 2 | 1 | 18 | 3STY9CL | BATCH 13 CL | 33236921.424 |  |  | Completed | 1 | [6 empty] | 2017-05-08 |  | 42900 | REYDAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130799 | Basag Elementary School | T'Boli | 2 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3687968.78 |  |  | Completed | 1 | [6 empty] | 2016-08-12 |  | 42681 | HAQ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316720 | Basag Nhs - Tboli Annex | T'Boli | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-07-18 |  | 42607 | MIGO CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316720 | Basag Nhs - Tboli Annex | T'Boli | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.64 |  |  | Completed | 1 | [6 empty] | 2016-07-13 |  | 42607 | MIGO CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130801 | Bianan Es | T'Boli | 2 |  | 1 | 1STY1CL | BATCH 3 CL | 1109434.19 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42606 | COFEJOK CONST. & SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130801 | Bianan Es | T'Boli | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6319337.64 |  |  | Completed | 1 | [6 empty] | 2016-08-24 |  | 42678 | HVC SAGITTARIUS COMMERCIAL & COMMERCIAL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130660 | Blit Es | Lake Sebu | 2 | 1 | 6 | 1STY3CL | BATCH 3 CL | 6145184.88 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 42732 | DALANON CONST., REF. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304565 | Bukay Pait Nhs | Tantangan | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 10877342.59 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 42544 | REYDAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304546 | Centrala Nhs | Surallah | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606 |  |  | Completed | 1 | [6 empty] | 2016-07-08 |  | 42591 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316713 | Colongulo Nhs - Libertad Nhs Annex | Surallah | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-10-03 |  | 42681 | MIGO CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 208503 | Coong Es | T'Boli | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1958606.04 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 42731 | STONELINE CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130807 | Datal Dlanag Es | T'Boli | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1958606.04 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 42613 | CEK CONST. & WATER SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130809 | Datal Tablo Es | T'Boli | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1973606.04 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 42613 | CEK CONST. & WATER SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130768 | Defensor Es | Surallah | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1864740.17 |  |  | Completed | 1 | [6 empty] | 2016-08-23 |  | 42640 | MRS BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130810 | Demamis Es | T'Boli | 2 |  | 2 | 1STY2CL | BATCH 3 CL | 1988606.04 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 42731 | STONELINE CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130810 | Demamis Es | T'Boli | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2882592.44 |  |  | Completed | 1 | [6 empty] | 2016-12-01 | 2016-12-27 | 42731 | STONELINE CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130811 | Desawo Es | T'Boli | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606.04 |  |  | Completed | 1 | [6 empty] | 2016-08-23 | 2016-09-27 | 42640 | NASCON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130664 | Diente Es | Lake Sebu | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1968606 |  |  | Completed | 1 | [6 empty] | 2016-08-12 |  | 42681 | HAQ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304547 | Edwards Nhs | T'Boli | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429549.27 |  |  | Completed | 1 | [8 empty] | 42640 | MRS BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316914 | El Nonok Integrated School | Banga | 2 | 1 | 12 | 2STY6CL | BATCH 3 CL | 16429930.1 |  |  | Completed | 1 | [6 empty] | 2016-07-11 |  | 42591 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304548 | Guinsang-An Nhs | Santo Niño | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-21 |  | 42545 | ISULAN ECT CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304548 | Guinsang-An Nhs | Santo Niño | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [6 empty] | 2016-07-13 |  | 42591 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130666 | Haliland Es | Lake Sebu | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1968606 |  |  | Completed | 1 | [6 empty] | 2016-08-11 |  | 42681 | HAQ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130702 | Julio Zuyco Memorial Es | Norala | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1814740.17 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42592 | LEIGHCHEEN CONST. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130629 | Kataan Es | Banga | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42606 | COFEJOK CONST. & SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304549 | Katipunan Nhs | Santo Niño | 2 | 1 | 8 | 2STY4CL | BATCH 7 CL | 12638675.28 |  |  | Completed | 1 | [6 empty] | 2016-03-21 |  | 42545 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130816 | Kebuling Es | T'Boli | 2 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3717968.78 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 42613 | SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 208519 | Kiantay Es | Surallah | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2852592.44 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 42732 | DALANON CONS., REF. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316708 | Kibang Nhs - Lake Sebu Nhs Annex | Lake Sebu | 2 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11057342.59 |  |  | Completed | 1 | [6 empty] | 2016-10-11 |  | 42755 | AGUERO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316926 | Laconon Integrated Hs | T'Boli | 2 | 1 | 4 | 1STY4CL | BATCH 5 CL | 3667968.78 |  |  | Completed | 1 | [6 empty] | 2016-07-18 |  | 42612 | COFEJOK CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316919 | Lake Soluton Integrated School | Lake Sebu | 2 | 1 | 12 | 2STY6CL | BATCH 7 CL | 16429930.1 |  |  | Completed | 1 | [6 empty] | 2016-07-13 |  | 42591 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316704 | Lamba Nhs - Banga Nhs Annex | Banga | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 10877342.59 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 42544 | REYDAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130819 | Lambangan Es | T'Boli | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12678675.28 |  |  | Completed | 1 | [6 empty] | 2017-04-03 |  | 42861 | NASCON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304553 | Lambontong Nhs | Surallah | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.42 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 42544 | HVC SAGITTARIUS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304553 | Lambontong Nhs | Surallah | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 42544 | HVC SAGITTARIUS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130820 | Lambuling Es | T'Boli | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1958606.04 |  |  | Completed | 1 | [6 empty] | 2016-12-01 | 2016-12-28 | 42731 | KGD BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130673 | Lamcade Es | Lake Sebu | 2 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8294695.05 |  |  | Completed | 1 | [6 empty] | 2016-07-13 |  | 42612 | BETTER WORKS CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304552 | Lamian Nhs | Surallah | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 7288647.81 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 42545 | MIGO CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304552 | Lamian Nhs | Surallah | 2 | 1 | 12 | 3STY12CL | BATCH 5 CL | 18222268.79 |  |  | Completed | 1 | [6 empty] | 2016-03-22 |  | 42548 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130823 | Lamla Es | T'Boli | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2802592.44 |  |  | Completed | 1 | [8 empty] | 42678 | MRS BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316710 | Lamsugod National High School | Surallah | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 42545 | REYDAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316710 | Lamsugod National High School | Surallah | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 42545 | MIGO CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304554 | Lapuz Nhs | Norala | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 42545 | FH GOPITEO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304554 | Lapuz Nhs | Norala | 2 | 1 | 6 | 1STY6CL | BATCH 5 CL | 5373000 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 42545 | FH GOPITEO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304555 | Libertad Nhs | Surallah | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [6 empty] | 2017-05-08 |  | 42900 | FH GOPITEO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304555 | Libertad Nhs | Surallah | 2 |  | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316917 | Lubol Is | Surallah | 2 | 1 | 8 | 2STY4CL | BATCH 3 CL | 12838675.28 |  |  | Completed | 1 | [8 empty] | 42786 | REYDAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316921 | Lusok Is | T'Boli | 2 | 1 | 8 | 2STY4CL | BATCH 5 CL | 12788675.28 |  |  | Completed | 1 | [6 empty] | 2016-07-13 |  | 42591 | FH GOPITEO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316719 | Maan Nhs - Tboli Annex | T'Boli | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2459549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-23 |  | 42545 | ROCKSTONE CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316719 | Maan Nhs - Tboli Annex | T'Boli | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8269965.05 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 42544 | REYDAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130875 | Maibo Es | Tantangan | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8214965.05 |  |  | Completed | 1 | [6 empty] | 2016-07-11 |  | 42592 | PALMARES GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316714 | Malaya Nhs - Banga Nhs Annex | Banga | 2 |  | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 42545 | YAP MABUHAY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316714 | Malaya Nhs - Banga Nhs Annex | Banga | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 | [6 empty] | 2016-03-21 |  | 42545 | YAP MABUHAY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316912 | Mangilala Integrated School | Tantangan | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2802592.44 |  |  | Completed | 1 | [6 empty] | 2016-03-21 |  | 42545 | MIGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304551 | Ned National High School | Lake Sebu | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2579549.27 |  |  | Completed | 1 | [6 empty] | 2016-10-12 |  | 42683 | DALANON CONST. REF SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304551 | Ned National High School | Lake Sebu | 2 | 1 | 8 | 2STY4CL | BATCH 3 CL | 13038675.28 |  |  | Completed | 1 | [6 empty] | 2016-08-11 |  | 42681 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316706 | New Dumangas Nhs | T'Boli | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [8 empty] | 42678 | HVC SAGITTARIUS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316706 | New Dumangas Nhs | T'Boli | 2 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8214965.05 |  |  | Completed | 1 | [8 empty] | 42678 | HVC SAGITTARIUS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316911 | New Lambunao Integrated Hs | Tantangan | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2802592.44 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42591 | ISULAN ECT CONST. & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304557 | Norala Nhs | Norala | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [8 empty] | 42545 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304557 | Norala Nhs | Norala | 2 |  | 12 | 3STY12CL | BATCH 5 CL | 18222268.79 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 42545 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304557 | Norala Nhs | Norala | 2 | 1 | 15 | 3STY15CL | BATCH 5 CL | 21383013.45 |  |  | Completed | 1 | [6 empty] | 2016-07-13 |  | 42591 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130681 | Odos Angkoy Es | Lake Sebu | 2 |  | 4 | 2STY4CL | BATCH 3 CL | 6359337.64 |  |  | Completed | 1 | [6 empty] | 2016-10-11 |  | 42683 | EC SOLICON BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130681 | Odos Angkoy Es | Lake Sebu | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8274695.05 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 42731 | AGUERO CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304558 | Panay Nhs | Santo Niño | 2 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [6 empty] | 2016-07-11 |  | 42591 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130682 | Proper Ned Es | Lake Sebu | 2 | 1 | 6 | 1STY3CL | BATCH 3 CL | 5905184.88 |  |  | Completed | 1 | [6 empty] | 2016-10-11 |  | 42683 | CEK CONST. & WATER SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316709 | Proper Ned Nhs - Lake Sebu Nhs Annex | Lake Sebu | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6519337.64 |  |  | Completed | 1 | [6 empty] | 2016-10-11 |  | 42683 | CEK CONST. & WATER SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316920 | Pulo Subong Integrated Hs | Lake Sebu | 2 | 1 | 4 | 1STY2CL | BATCH 3 CL | 4177212 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 42732 | DALANON CONST. REF. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316705 | Punong Grande Nhs - Banga Nhs Annex | Banga | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2802592.44 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42576 | MIGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316723 | Rizal 3 National High School- Banga Nhs Annex | Banga | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2802592.44 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42591 | FH GOPITEO CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 208530 | Salabanog Es | T'Boli | 2 | 1 | 9 | 1STY3CL | BATCH 3 CL | 8647777.32 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 42731 | STONELINE CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130840 | Salacafe Es | T'Boli | 2 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3687968.78 |  |  | Completed | 1 | [6 empty] | 2016-10-12 |  | 42683 | HAQ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316703 | San Jose Nhs | Banga | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-07-18 |  | 42607 | MIGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316703 | San Jose Nhs | Banga | 2 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3667968.78 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42591 | FH GOPITEO CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316715 | San Jose Nhs - Lapuz Nhs Annex | Norala | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1938606 |  |  | Completed | 1 | [6 empty] | 2016-03-21 |  | 42544 | C.A. BETALAC CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304566 | San Miguel National High School | Norala | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 42544 | ROCKSTONE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304566 | San Miguel National High School | Norala | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8214965.05 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 42545 | MIGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316718 | San Vicente Nhs - Banga Nhs Annex | Banga | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42591 | SOPHIA CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316724 | Sergio L. Legayada Nhs - Norala Nhs Annex | Norala | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8214965.05 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 42545 | MIGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130713 | Simsiman Es | Norala | 2 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1012049.65 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42592 | LEIGHCHEEN CONST. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304568 | Sto. Niño Nhs | Santo Niño | 2 | 1 | 24 | 3STY12CL | BATCH 1 CL | 36486537.58 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 42548 | BETTERWORK CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304569 | Sto. Niño Nsat | Santo Niño | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 42545 | MIGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304569 | Sto. Niño Nsat | Santo Niño | 2 | 1 | 12 | 2STY6CL | BATCH 5 CL | 16429930.1 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 42544 | REYDAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316701 | Surallah Nhs | Surallah | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 42545 | MIGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316701 | Surallah Nhs | Surallah | 2 | 1 | 15 | 3STY15CL | BATCH 5 CL | 21383013.45 |  |  | Completed | 1 | [6 empty] | 2016-03-22 |  | 42544 | KGD BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130785 | Talahik Es | Surallah | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606.04 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 42592 | LEIGHCHEEN CONST. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130845 | Talcon Es | T'Boli | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606.04 |  |  | Completed | 1 | [6 empty] | 2016-08-23 |  | 42640 | NASCON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316918 | Talisay Integrated Hs | Lake Sebu | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4859098.54 |  |  | Completed | 1 | [6 empty] | 2016-07-18 |  | 42606 | COFEJOK CONST. & SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316918 | Talisay Integrated Hs | Lake Sebu | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [6 empty] | 2016-03-21 |  | 42545 | KGD BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304572 | Tantangan Nhs | Tantangan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 42545 | REYDAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304572 | Tantangan Nhs | Tantangan | 2 | 1 | 15 | 3STY15CL | BATCH 5 CL | 21383013.45 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 42545 | FH GOPITEO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304573 | Tantangan Nths | Tantangan | 2 | 1 | 16 | 2STY8CL | BATCH 3 CL | 21754685.18 |  |  | Completed | 1 | [6 empty] | 2016-07-11 |  | 42591 | FH GOPITEO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | South Cotabato | 304574 | Tboli Nhs | T'Boli | 2 | 1 | 36 | 4STY12CL | BATCH 1 CL | 66517030.86 |  |  | Completed | 1 | [6 empty] | 2016-02-22 |  | 42612 | FFJJ CONST. (JV) & BETTER WORKS CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130690 | T'Boyung Es | Lake Sebu | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2952592.44 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 42732 | DALANON CONST., REF. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130848 | Tuburan Es Realigned To T'Bolok Es | T'Boli | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2952592.44 |  |  | Completed | 1 | [6 empty] | 2016-10-27 |  | 42702 | COFEJOK CONST. & SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130658 | Tuburan Es Realigned To Bakdulong Es | Lake Sebu | 2 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3867968.78 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 42706 | STONELINE CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130850 | Tudok Es | T'Boli | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2952592.44 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 42731 | STONELINE CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | South Cotabato | 316725 | Upper Maculan Nhs - Lake Sebu Nhs Annex | Lake Sebu | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606 |  |  | Completed | 1 | [6 empty] | 2016-07-18 |  | 42607 | C.A BETALAC CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | South Cotabato | 130793 | V. L. Barber Es | Surallah | 2 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1109434.19 |  |  | Completed | 1 | [8 empty] | 42678 | HVC SAGITTARIUS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 130956 | Balisan Ps | Columbio | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1059556.05 |  |  | Completed | 1 |  |  | P00072543MN_CW1 | 16MF0059 | 05-05-2016 | 05-13-2016 | 05-26-2016 | 06-21-2016 | 07-08-2016 | Robeth Gen. Mdse. Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304585 | Bambad Nhs | Isulan | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 32317976 |  |  | Completed | 1 |  |  | P00072536MN_CW1 | 16MF0076 | 06-23-2016 | 07-01-2016 | 07-15-2016 | 08-15-2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 131207 | Bayawa Es | President Quirino | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2737525.25 |  |  | Completed | 1 |  |  | P00072548MN_CW1 | 16MF0058 | 05-05-2016 | 05-13-2016 | 05-26-2016 | 06-21-2016 | 07-08-2016 | Robeth Gen. Mdse. Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304588 | Columbio National High School | Columbio | 1 | 1 | 18 | 3STY9CL | BATCH 7 CL | 30866854.06 |  |  | Completed | 1 |  |  | P00072537MN_CW1 | 16MF0071 | 06-23-2016 | 07-01-2016 | 07-15-2016 | 08-15-2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304590 | Isulan National High School | Isulan (Capital) | 1 | 1 | 30 | 3STY15CL | BATCH 13 CL | 47012629.59 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304590 | Isulan National High School | Isulan (Capital) | 1 |  | 12 | 3STY12CL | BATCH 13 CL | 20000467.74 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304590 | Isulan National High School | Isulan (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  |  | 16MF0030 | 02-22-2016 | 03-02-2016 | 03-10-2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304594 | Kalanawe Ii Nhs | President Quirino | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 9002105.5 |  |  | Completed | 1 |  |  | P00072542MN_CW1 | 16MF0067 | 05-18-2016 | 06-01-2016 | 06-13-2016 | 07-18-2016 | 08-03-2016 | Robeth Gen. Mdse. Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304594 | Kalanawe Ii Nhs | President Quirino | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2770298.44 |  |  | Completed | 1 |  |  | P00072670MN_CW1 | 16MF0056 | 05-05-2016 | 05-13-2016 | 05-26-2016 | 06-21-2016 | 07-08-2016 | FPJ Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304595 | Kapingkong Nhs | Lambayong | 1 | 1 | 18 | 3STY9CL | BATCH 7 CL | 30866850.06 |  |  | Completed | 1 |  |  | P00072539MN_CW1 | 16MF0070 | 05-18-2016 | 06-01-2016 | 06-13-2016 | 07-18-2016 | 08-03-2016 | Blimex Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304595 | Kapingkong Nhs | Lambayong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2770298.44 |  |  | Completed | 1 |  |  | P00072667MN_CW1 | 16MF0053 | 05-05-2016 | 05-13-2016 | 05-26-2016 | 06-21-2016 | 07-08-2016 | Robeth Gen. Mdse. Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304597 | Lambayong National High School | Lambayong (Mariano Marcos) | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 32577116 |  |  | Completed | 1 |  |  | P00072534MN_CW1 | 16MF0074 | 06-09-2016 | 06-17-2016 | 06-30-2016 | 07-26-2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304597 | Lambayong National High School | Lambayong (Mariano Marcos) | 1 |  | 16 | 4STY16CL | BATCH 7 CL | 26044086 |  |  | Completed | 1 |  |  | P00072535MN_CW1 | 16MF0072 | 06-23-2016 | 07-01-2016 | 07-15-2016 | 08-15-2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304597 | Lambayong National High School | Lambayong (Mariano Marcos) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2735034.44 |  |  | Completed | 1 |  |  | P00072665MN_CW1 | 16MF0051 | 07-28-2016 | 08-05-2016 | 08-18-2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304606 | Lutayan National High Schoool | Lutayan | 1 | 1 | 12 | 3STY12CL | BATCH 1 CL | 20522649.79 |  |  | Completed | 1 |  |  | P00070177MN_CW1 | 16MF0064 | 05-18-2016 | 06-01-2016 | 06-13-2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304606 | Lutayan National High Schoool | Lutayan | 1 |  | 10 | 2STY10CL | BATCH 1 CL | 14684021.713 |  |  | Completed | 1 |  |  | P00070178MN_CW1 | 16MF0038 | 02-22-2016 | 03-02-2016 | 03-14-2016 | 05-11-2016 | 05-26-2016 | Gemma Const. Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304606 | Lutayan National High Schoool | Lutayan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2831034.44 |  |  | Completed | 1 |  |  | P00070223MN_CW1 | 16MF0029 | 02-22-2016 | 03-02-2016 | 03-10-2016 | 05-11-2016 | 05-26-2016 | Gemma Const Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304607 | Madanding Nhs | Lambayong | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15433427 |  |  | Completed | 1 |  |  | P00072540MN_CW1 | 16MF0069 | 05-18-2016 | 06-01-2016 | 06-13-2016 | 07-18-2016 | 08-03-2016 | Stoneline Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304607 | Madanding Nhs | Lambayong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2770298.44 |  |  | Completed | 1 |  |  | P00072668MN_CW1 | 16MF0054 | 05-05-2016 | 05-13-2016 | 05-26-2016 | 06-21-2016 | 07-08-2016 | CEK Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304608 | Maligaya Nhs | Lambayong | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6812821 |  |  | Completed | 1 |  |  | P00072544MN_CW1 | 16MF0048 | 05-05-2016 | 05-13-2016 | 05-26-2016 | 06-21-2016 | 07-08-2016 | Cofejok Const. & Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 131152 | Mangudadatu Es | Lutayan | 1 | 1 | 4 | 1STY4CL | BATCH 7 CL | 3764244 |  |  | Completed | 1 |  |  | P00072546MN_CW1 | 16MF0060 | 05-05-2016 | 05-13-2016 | 05-26-2016 | 06-21-2016 | 07-11-2016 | Minrock Multi-Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304614 | New Pangasinan Nhs | Isulan | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11418798 |  |  | Completed | 1 |  |  | P00072538MN_CW1 | 16MF0066 | 05-18-2016 | 06-01-2016 | 06-13-2016 | 07-18-2016 | 08-03-2016 | C.S. Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304614 | New Pangasinan Nhs | Isulan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2770298.44 |  |  | Completed | 1 |  |  | P00072668MN_CW1 | 16MF0054 | 05-05-2016 | 05-13-2016 | 05-26-2016 | 06-21-2016 | 07-08-2016 | CEK Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304598 | Pimbalayan Nhs - Lambayong Annex | Lambayong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2770298.44 |  |  | Completed | 1 |  |  | P00072669MN_CW1 | 16MF0055 | 05-05-2016 | 05-13-2016 | 05-26-2016 | 06-21-2016 | 07-08-2016 | Minrock Multi-Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304598 | Pimbalayan Nhs - Lambayong Annex | Lambayong | 1 | 1 | 5 | 1STY5CL | BATCH 7 CL | 4425866.5 |  |  | Completed | 1 |  |  | P00072541MN_CW1 | 16MF0049 | 05-05-2016 | 05-13-2016 | 05-26-2016 | 06-21-2016 | 07-08-2016 | Robeth Gen. Mdse. Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304617 | President Quirino National High School | President Quirino | 1 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26149190 |  |  | Completed | 1 |  |  | P00070726MN_CW1 | 16MF0062 | 06-23-2016 | 07-01-2016 | 07-15-2016 | 08-15-2016 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304617 | President Quirino National High School | President Quirino | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8601369.5 |  |  | Completed | 1 |  |  | P00070727MN_CW1 | 16MF0037 | 02-22-2016 | 03-02-2016 | 03-10-2016 | 05-11-2016 | 05-26-2016 | Robeth Gen. Mdse. Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 131160 | Sisiman Es | Lutayan | 1 | 1 | 5 | 1STY5CL | BATCH 7 CL | 4425866.5 |  |  | Completed | 1 |  |  | P00072547MN_CW1 | 16MF0050 | 05-05-2016 | 05-13-2016 | 05-26-2016 | 06-21-2016 | 07-08-2016 | Minrock Multi-Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304625 | Telafas National High School | Columbio | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2692979.7865 |  |  | Completed | 1 |  |  |  | 16MF0079 | 07-28-2016 | 08-05-2016 | 08-18-2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 131107 | Zeneben Es | Lambayong | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1978047.5 |  |  | Completed | 1 |  |  | P00072545MN_CW1 | 16MF0057 | 07-28-2016 | 08-05-2016 | 08-18-2016 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304591 | Kalamansig National High School | Kalamansig | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 16740000 |  |  | Completed | 1 |  |  | P00074353MN | 16MH0027 | May 27, 2016 | July 7, 2016 | July 19, 2016 | July 29, 2016 | On process | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304591 | Kalamansig National High School | Kalamansig | 2 |  | 6 | 3STY6CL | BATCH 9 CL | 10537131.51 |  |  | Completed | 1 |  |  | P00074354MN | 16MH0030 | May 27, 2016 | July 7, 2016 | July 19, 2016 | July 29, 2016 | On process | JV Constech |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304591 | Kalamansig National High School | Kalamansig | 2 |  | 10 | 2STY10CL | BATCH 9 CL | 13975000 |  |  | Completed | 1 |  |  | P00074355MN | 16MH0028 | May 27, 2016 | July 7, 2016 | Failure of bidding (Re-bidding schedule on September 23, 2016) |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304591 | Kalamansig National High School | Kalamansig | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2688700 |  |  | Completed | 1 |  |  | P00074623MN | 16MH0029 | May 27, 2016 | June 6, 2016 | June 21, 2016 | July 4, 2016 | July 17, 2016 | Jargon Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304605 | Lebak Legislated National High School | Lebak | 2 | 1 | 24 | 3STY12CL | BATCH 9 CL | 33480000 |  |  | Completed | 1 |  |  | P00074356MN | 16MH0026 | May 27, 2016 | July 7, 2016 | July 19, 2016 | July 29, 2016 | On process | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304613 | New Panay National High School | Esperanza | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 20887500 |  |  | Completed | 1 |  |  | P00074352MN | 16MH0031 | May 27, 2016 | July 7, 2016 | July 19, 2016 | July 29, 2016 | On process | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION XII | Sultan Kudarat | 304613 | New Panay National High School | Esperanza | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2688700 |  |  | Completed | 1 |  |  | P00074624MN | 16MH0032 | May 27, 2016 | June 6, 2016 | June 21, 2016 | July 4, 2016 | July 17, 2016 | CEK Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Tacurong City | 304579 | A.S. Bernardo Mem. Nhs | City Of Tacurong | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6812821 |  |  | Completed | 1 |  |  | P00070728MNCWI | 16MF0033 | Feb. 19, 2016 | Feb. 26, 2016 | 2016-03-10 | 2016-05-22 | 42516 | K.A. Builders And Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | Tacurong City | 304579 | A.S. Bernardo Mem. Nhs | City Of Tacurong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2735034.44 |  |  | Completed | 1 |  |  | P00070805MNCWI | 16MF0027 | Feb. 19, 2016 | Feb. 26, 2016 | 2016-03-10 | 2016-05-22 | 42516 | Bandar Kutawato Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Tacurong City | 304620 | Rajah Muda Nhs | City Of Tacurong | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11418798 |  |  | Completed | 1 |  |  | P00070729MNCWI | 16MF0035 | Feb. 19, 2016 | Feb. 26, 2016 | 2016-03-10 | 2016-05-22 | 42516 | Palmares Gen. MDSE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | Tacurong City | 326102 | San Emmanuel National High School-Annex | City Of Tacurong | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6765435 |  |  | Completed | 1 |  |  | P00070731MNCWI | 16MF0034 | Feb. 19, 2016 | Feb. 26, 2016 | 2016-03-10 | 2016-05-22 | 42516 | Robeth Gen Mdse.Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION XII | Tacurong City | 304622 | San Emmanuel Nhs | City Of Tacurong | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11418798 |  |  | Completed | 1 |  |  | P00070730MNCWI | 16MF0034 | Feb. 19, 2016 | Feb. 26, 2016 | 2016-03-10 | 2016-05-22 | 42516 | Palmares Gen. MDSE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION XII | Tacurong City | 304622 | San Emmanuel Nhs | City Of Tacurong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2735034.44 |  |  | Completed | 1 |  |  | P00070806MNCWI | 16MF0026 | Feb. 19, 2016 | Feb. 26, 2016 | 2016-03-10 | 2016-05-22 | 42516 | Robeth Gen Mdse.Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION XII | Tacurong City | 304627 | V.F. Grino Mem. Nhs | City Of Tacurong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2692979.7865 |  |  | Completed | 1 |  |  | P00075358MNCW1 | 16-MF-0078 | July 28-Aug. 3, 2016 |  | Aug. 5, 2016 | Sept.16, 2016 | Oct. 7, 2016 | Robeth Gen Mdse.Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2015 | REGION XII | North Cotabato | 304440 | Kabalantian HS | ARAKAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2015 | REGION XII | North Cotabato | 304473 | Manobo NHS | MAGPET | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.