## ALS-CLC 2024
Region | Division | School ID | School Name | Municipality | Leg District | No. of Sites | Scope of Work | Total Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Municipality Classification
CARAGA | Agusan del Norte | 131508 | Buenavista CES | BUENAVISTA | 2nd | 1 | CONSTRUCTION OF TWO (2) STOREY ALTERNATIVE LEARNING SYSTEM - COMMUNITY LEARNING CENTER WITH ROOF DECK- (18.00m x 9.50m), WITH RAINWATER COLLECTOR, PERIMETER FENCE AND FURNITURE | 14141414.14 | 14070707.07 | completed | 100% | April 26, 2025 | May 15, 2025 | ALS-CLC 2024 - CARAGA - AGUSAN DEL NORTE - 001 | ALS-CLC 2024 - CARAGA - AGUSAN DEL NORTE - 001 | June 5, 2024 | June 28, 2024 | July 11, 2024 | August 5, 2024 | August 15, 2024 | JD-RG Const. & Supplies | WITH VARIATION ORDER AND TIME EXTENSION | [5 empty] | 100% |  |  | 4.25 | 1st
Region I | Ilocos Sur | 100684 | Sta. Cruz CS | SANTA CRUZ | 2nd | 1 | PROPOSED TWO (2) - STOREY ALTERNATIVE LEARNING SYSTEM (ALS) BUILDING (22.50m x 9.50m) - with Roof Deck | 12871493.45 | Original: 9,322,239.10 Revised: Php 10,250,272.33 | ongoing | 80% | Original: 4/18/2025 Revised: 5/18/2025 |  | PB-015-2024 | n/a | October 2, 2024 | October 9, 2024 | October 22, 2024 | October 30, 2024 | November 20, 2024 | MA Tejada COnstruction | With additional works amounting to Php 928,033.23 due to revision of plans | [5 empty] | 60% |  |  |  | 1st
Region III | Aurora | 300690 | Lual NHS | CASIGURAN | Lone | 1 | PROPOSED TWO (2) - STOREY ALTERNATIVE LEARNING SYSTEM (ALS) BUILDING (22.50m x 9.50m) - with Roof Deck( TO be elevated by 1.0m) | 12446387.1 | 10458975.45 | ongoing | 70% | June 21, 2025 |  | 2024-04-181 | SGOD-INFRA-32 | July 1, 2024 | July 8, 2024 | July 22, 2024 | August 1, 2024 | August 17, 2024 | MACCO CONSTRUCTION | Request to utilized savings is up to now no response from CO | [5 empty] | 50% |  |  |  | 2nd
Region IV-B | Occidental Mindoro | 301596 | Sablayan National Comprehensive High School | SABLAYAN | Lone | 1 | PROPOSED TWO (2) - STOREY ALTERNATIVE LEARNING SYSTEM (ALS) BUILDING (22.50m x 9.50m) - with Roof Deck | 16540705.31 | 16458637.91 | completed | 100% | April 10, 2025 | April 15,2025 | DepEd-OccMdo-2024-05 |  | May 31, 2024 | June 10 2024 | June 24, 2024 | June 28, 2024 | June 19, 2024 | hawkstow construction and development | actual target completion was adjusted due to contractor request for extension regarding weather condition | [5 empty] | 83% |  |  |  | 1st